## FCP
InfraYear | Region | Province | Municipality | ProjectID | TypeofWork | Longitude | Latitude | ApprovedBudget | ContractCost | CompletionYear | Contractor | ObjectId | FundingYear | CompletionDateActual | StartDate | SurplusBudget | DeficiencyBudget | CompletionDateOrig | Delayed Completion | Early Completion
2024 | Region IV-B | PALAWAN | PUERTO PRINCESA CITY (CAPITAL) (PALAWAN) | P00824759LZ | Construction of Flood Mitigation Structure | 118.8924 | 9.9965 | 17963475 | 17961569.07 | 2024 | AZARRAGA CONSTRUCTION | 1 | 2024 | 2024-05-23 | 02/15/2024 | 1905.93 | 0 | 2024-07-13 | 51
2024 | Region IV-B | PALAWAN | PUERTO PRINCESA CITY (CAPITAL) (PALAWAN) | P00824758LZ | Construction of Flood Mitigation Structure | 118.8925 | 9.9976 | 17370000 | 17369992.99 | 2024 | AZARRAGA CONSTRUCTION | 2 | 2024 | 2024-07-19 | 02/23/2024 | 7.01 | 0 | 2024-07-23 | 4
2024 | Region IV-B | PALAWAN | PUERTO PRINCESA CITY (CAPITAL) (PALAWAN) | P00824750LZ | Construction of Flood Mitigation Structure | 118.8932 | 9.9967 | 18335000 | 16802607.63 | 2024 | F.F. GALANG CONSTRUCTION | 3 | 2024 | 2024-07-24 | 02/23/2024 | 1532392.37 | 0 | 2024-07-24 | 0
2023 | Region IV-B | PALAWAN | PUERTO PRINCESA CITY (CAPITAL) (PALAWAN) | P00737551LZ | Construction of Drainage Structure | 118.8997 | 10.0027 | 4900000 | 4899590 | 2023 | PALBIC CONSTRUCTION AND SUPPLY | 4 | 2023 | 2023-05-05 | 02/15/2023 | 410 | 0 | 2023-04-21 |  | 14
2024 | Region IV-B | PALAWAN | PUERTO PRINCESA CITY (CAPITAL) (PALAWAN) | P00823565LZ | Construction of Flood Mitigation Structure | 118.9902 | 9.999 | 154400000 | 154395357.9 | 2024 | OCTAGON CONCRETE SOLUTIONS INC. / MAC BUILDERS CORP. (FORMERLY: MAC BUILDERS DEVELOPMENT CORPORATION) | 5 | 2024 | 2024-09-05 | 03/09/2024 | 4642.1 | 0 | 2025-01-17 | 134
2024 | Region IV-B | PALAWAN | PUERTO PRINCESA CITY (CAPITAL) (PALAWAN) | P00824756LZ | Construction of Flood Mitigation Structure | 119.122 | 10.0297 | 17370000 | 17369997.4 | 2024 | MAINTIN CONSTRUCTION & SUPPLY | 6 | 2024 | 2024-09-17 | 02/15/2024 | 2.6 | 0 | 2024-10-01 | 14
2024 | Region IV-B | PALAWAN | PUERTO PRINCESA CITY (CAPITAL) (PALAWAN) | P00824757LZ | Construction of Flood Mitigation Structure | 119.1238 | 10.0288 | 17370000 | 16120415.26 | 2024 | LOUIESE TRADING AND CONSTRUCTION | 7 | 2024 | 2024-06-25 | 02/23/2024 | 1249584.74 | 0 | 2024-07-21 | 26
2024 | Region IV-B | PALAWAN | PUERTO PRINCESA CITY (CAPITAL) (PALAWAN) | P00824760LZ | Construction of Flood Mitigation Structure | 119.1242 | 10.0275 | 17370000 | 17370000 | 2024 | TAGUSAO CONSTRUCTION & TRADING INC. (FORMERLY: TAGUSAO CONSTRUCTION & TRADING) | 8 | 2024 | 2024-09-13 | 02/15/2024 | 0 | 0 | 2024-09-14 | 1
2023 | Region IV-B | PALAWAN | ROXAS (PALAWAN) | P00726266LZ | Construction of Flood Mitigation Structure | 119.2062 | 10.2529 | 9064943.69 | 9014282.42 | 2023 | PANAAD CONSTRUCTION | 9 | 2023 | 2023-09-12 | 04/18/2023 | 50661.27 | 0 | 2023-09-11 |  | 1
2024 | Region I | PANGASINAN | SANTA BARBARA (PANGASINAN) | P00821520LZ | Construction of Flood Mitigation Structure | 120.4008 | 16.0068 | 48250000 | 48248598.38 | 2024 | ALCEL CONSTRUCTION | 10 | 2024 | 2024-09-23 | 03/07/2024 | 1401.62 | 0 | 2024-10-01 | 8
2024 | Region IV-B | ISABELA | ROXAS (ISABELA) | P00820974LZ | Construction of Flood Mitigation Structure | 119.2156 | 10.147 | 48249976.12 | 48249914.4 | 2024 | YURICH BUILDERS AND CONSTRUCTION SUPPLY INC. / F.F. GALANG CONSTRUCTION | 11 | 2024 | 2024-12-11 | 05/20/2024 | 61.72 | 0 | 2024-12-20 | 9
2024 | Region IV-B | ISABELA | ROXAS (ISABELA) | P00820979LZ | Construction of Flood Mitigation Structure | 119.2256 | 10.276 | 44099975.3 | 44095477.55 | 2024 | YURICH BUILDERS AND CONSTRUCTION SUPPLY INC. / SEVEN DIGIT CONSTRUCTION AND TRUCKING SERVICES CORP. (FORMERLY: SEVEN DIGIT CONSTRUCTION & SUPPLIES) | 12 | 2024 | 2024-10-15 | 02/14/2024 | 4497.75 | 0 | 2024-10-03 |  | 12
2022 | Region IV-B | PALAWAN | ROXAS (PALAWAN) | P00632934LZ | Construction of Flood Mitigation Structure | 119.2315 | 10.1838 | 4949962.82 | 4949962.82 | 2022 | A.P. CONSEBIDO CONSTRUCTION AND TRADING | 13 | 2022 | 2022-07-29 | 02/17/2022 | 0 | 0 | 2022-07-28 |  | 1
2024 | Region IV-B | ISABELA | ROXAS (ISABELA) | P00844779LZ | Construction of Drainage Structure | 119.3465 | 10.324 | 9899934.12 | 9784647.85 | 2024 | M.G.M. CONSTRUCTION | 14 | 2024 | 2024-12-20 | 03/18/2024 | 115286.27 | 0 | 2024-09-07 |  | 104
2024 | Region IV-B | ISABELA | ROXAS (ISABELA) | P00820975LZ | Construction of Flood Mitigation Structure | 119.3744 | 10.4293 | 44099956.7 | 44097536.12 | 2024 | YURICH BUILDERS AND CONSTRUCTION SUPPLY INC. / SEVEN DIGIT CONSTRUCTION AND TRUCKING SERVICES CORP. (FORMERLY: SEVEN DIGIT CONSTRUCTION & SUPPLIES) | 15 | 2024 | 2024-10-15 | 02/14/2024 | 2420.58 | 0 | 2024-10-03 |  | 12
2021 | Region IV-B | PALAWAN |  | P00561401LZ | Construction of Flood Mitigation Structure | 119.3864 | 11.1803 | 9899984.53 | 7778048.48 | 2023 | LOUIESE TRADING AND CONSTRUCTION | 16 | 2021 | 2023-06-25 | 01/24/2022 | 2121936.05 | 0 | 2022-05-26 |  | 395
2024 | Region IV-B | PALAWAN | EL NIDO (BACUIT) (PALAWAN) | P00820977LZ | Construction of Flood Mitigation Structure | 119.4169 | 11.1934 | 44099949.37 | 44097774.54 | 2024 | AR LUSTRE CONSTRUCTION CORPORATION (FORMERLY:A.R. LUSTRE JR. CONSTRUCTION) / A.R.L. CONSTRUCTION | 17 | 2024 | 2024-11-19 | 02/14/2024 | 2174.83 | 0 | 2024-11-18 |  | 1
2023 | Region IV-B | PALAWAN | EL NIDO (BACUIT) (PALAWAN) | P00726267LZ | Construction of Flood Mitigation Structure | 119.4304 | 11.2435 | 9064950.34 | 8929075.23 | 2023 | 12-30 CONSTRUCTION AND SUPPLY | 18 | 2023 | 2023-12-08 | 04/18/2023 | 135875.11 | 0 | 2023-09-03 |  | 96
2023 | Region IV-B | PALAWAN | ROXAS (PALAWAN) | P00742461LZ | Construction of Drainage Structure | 119.4618 | 10.3794 | 4949974.91 | 4514354.14 | 2023 | AFG CONSTRUCTION CORPORATION | 19 | 2023 | 2023-06-29 | 03/30/2023 | 435620.77 | 0 | 2023-07-21 | 22
2024 | Region IV-B | RIZAL | TAYTAY (RIZAL) | P00820972LZ | Construction of Drainage Structure | 119.4626 | 10.6863 | 19599983.05 | 19598517.1 | 2024 | REINASTAR TRADING AND CONSTRUCTION SUPPLY | 20 | 2024 | 2024-10-28 | 02/14/2024 | 1465.95 | 0 | 2024-10-27 |  | 1
2023 | Region IV-B | PALAWAN | TAYTAY (PALAWAN) | P00726264LZ | Construction of Flood Mitigation Structure | 119.4937 | 10.7173 | 9064927.16 | 9064029.8 | 2023 | MAC BUILDERS CIVIL ENGINEERING CONSTRUCTION | 21 | 2023 | 2023-10-23 | 03/15/2023 | 897.36 | 0 | 2023-08-27 |  | 57
2024 | Region IV-B | RIZAL | TAYTAY (RIZAL) | P00820412LZ | Construction of Flood Mitigation Structure | 119.4963 | 10.6428 | 96499945.21 | 96499967.12 | 2024 | JASMIG CONSTRUCTION CORPORATION (FORMERLY: JASMIG CONSTRUCTION SUPPLY) | 22 | 2024 | 2024-08-27 | 02/14/2024 | 0 | 21.91 | 2024-12-12 | 107
2024 | Region IV-B | RIZAL | TAYTAY (RIZAL) | P00820414LZ | Construction of Flood Mitigation Structure | 119.5003 | 10.6478 | 96499980.15 | 96499998.63 | 2024 | JASMIG CONSTRUCTION CORPORATION (FORMERLY: JASMIG CONSTRUCTION SUPPLY) | 23 | 2024 | 2024-09-20 | 02/14/2024 | 0 | 18.48 | 2025-01-05 | 107
2024 | Region I | PANGASINAN | AGNO (PANGASINAN) | P00843194LZ | Construction of Flood Mitigation Structure | 119.7782 | 16.1327 | 96500000 | 96500000 | 2024 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES / RANIA CONSTRUCTION AND SUPPLIES | 24 | 2024 | 2024-09-25 | 04/08/2024 | 0 | 0 | 2024-11-02 | 38
2024 | Region I | PANGASINAN | AGNO (PANGASINAN) | P00843195LZ | Construction of Flood Mitigation Structure | 119.7815 | 16.1348 | 96500000 | 96500000 | 2024 | RANIA CONSTRUCTION AND SUPPLIES / JHI CONSTRUCTION & SUPPLY | 25 | 2024 | 2024-09-25 | 04/08/2024 | 0 | 0 | 2024-11-02 | 38
2023 | Region I | PANGASINAN | AGNO (PANGASINAN) | P00726326LZ | Construction of Flood Mitigation Structure | 119.7878 | 16.1282 | 77200000 | 77200000 | 2023 | SAMANTHA ENTERPRISES / ALCEL CONSTRUCTION | 26 | 2023 | 2023-12-07 | 03/30/2023 | 0 | 0 | 2023-12-08 | 1
2024 | Region I | PANGASINAN | AGNO (PANGASINAN) | P00820714LZ | Construction of Flood Mitigation Structure | 119.7879 | 16.1317 | 49000000 | 49000000 | 2024 | JONIK TRADING & CONSTRUCTION | 27 | 2024 | 2024-05-03 | 02/05/2024 | 0 | 0 | 2024-08-31 | 120
2024 | Region I | PANGASINAN | AGNO (PANGASINAN) | P00820122LZ | Construction of Flood Mitigation Structure | 119.7881 | 16.1283 | 96500000 | 96500000 | 2024 | SAMANTHA ENTERPRISES / ALCEL CONSTRUCTION | 28 | 2024 | 2024-12-17 | 04/19/2024 | 0 | 0 | 2025-01-12 | 26
2024 | Region I | PANGASINAN | AGNO (PANGASINAN) | P00820127LZ | Construction of Flood Mitigation Structure | 119.7895 | 16.1286 | 96500000 | 96500000 | 2024 | ALCEL CONSTRUCTION | 29 | 2024 | 2024-08-27 | 02/12/2024 | 0 | 0 | 2024-12-03 | 98
2024 | Region I | PANGASINAN | AGNO (PANGASINAN) | P00820126LZ | Construction of Flood Mitigation Structure | 119.7907 | 16.1248 | 96500000 | 96500000 | 2025 | RAMDC CONSTRUCTION AND TRADING / ALCEL CONSTRUCTION | 30 | 2024 | 2025-01-09 | 02/14/2024 | 0 | 0 | 2025-02-03 | 25
2023 | Region I | PANGASINAN | AGNO (PANGASINAN) | P00726365LZ | Construction of Flood Mitigation Structure | 119.7927 | 16.1215 | 51145000 | 51145000 | 2024 | ALCEL CONSTRUCTION | 31 | 2023 | 2024-01-05 | 04/13/2023 | 0 | 0 | 2024-01-06 | 1
2024 | Region I | PANGASINAN | AGNO (PANGASINAN) | P00820715LZ | Construction of Flood Mitigation Structure | 119.7998 | 16.1136 | 49000000 | 49000000 | 2024 | JONIK TRADING & CONSTRUCTION | 32 | 2024 | 2024-10-16 | 02/05/2024 | 0 | 0 | 2024-10-15 |  | 1
2023 | Region I | PANGASINAN | AGNO (PANGASINAN) | P00726328LZ | Construction of Flood Mitigation Structure | 119.8016 | 16.1118 | 77200000 | 77200000 | 2023 | JONIK TRADING & CONSTRUCTION / ALCEL CONSTRUCTION | 33 | 2023 | 2023-12-22 | 04/13/2023 | 0 | 0 | 2023-12-22 | 0
2024 | Region I | PANGASINAN | AGNO (PANGASINAN) | P00820123LZ | Construction of Flood Mitigation Structure | 119.8293 | 16.1087 | 96500000 | 96500000 | 2025 | JONIK TRADING & CONSTRUCTION / ALCEL CONSTRUCTION | 34 | 2024 | 2025-03-03 | 02/23/2024 | 0 | 0 | 2025-03-02 |  | 1
2022 | Region I | PANGASINAN | DASOL (PANGASINAN) | P00631082LZ | Construction of Flood Mitigation Structure | 119.8655 | 15.9417 | 19600000 | 19600000 | 2022 | BERSON'S CONSTRUCTION & TRADING | 35 | 2022 | 2022-12-26 | 02/10/2022 | 0 | 0 | 2022-12-25 |  | 1
2024 | Region I | PANGASINAN | MABINI (PANGASINAN) | P00820124LZ | Construction of Flood Mitigation Structure | 119.8757 | 16.0883 | 96500000 | 96500000 | 2024 | ALCEL CONSTRUCTION | 36 | 2024 | 2024-04-23 | 02/12/2024 | 0 | 0 | 2024-12-02 | 223
2023 | Region IV-B | PALAWAN | BUSUANGA (PALAWAN) | P00726265LZ | Construction of Flood Mitigation Structure | 119.8775 | 12.2216 | 9064955.46 | 8884656 | 2023 | MAC BUILDERS CIVIL ENGINEERING CONSTRUCTION | 37 | 2023 | 2023-08-11 | 04/18/2023 | 180299.46 | 0 | 2023-07-17 |  | 25
2024 | Region I | PANGASINAN | MABINI (PANGASINAN) | P00823306LZ | Construction of Slope Protection Structure | 119.8864 | 16.0825 | 96500000 | 96500000 | 2025 | IGWT-JAV CONSTRUCTION & DEVELOPMENT CORPORATION | 38 | 2024 | 2025-02-12 | 04/19/2024 | 0 | 0 | 2025-02-11 |  | 1
2024 | Region I | PANGASINAN | MABINI (PANGASINAN) | P00823307LZ | Construction of Slope Protection Structure | 119.8895 | 16.0815 | 96500000 | 96500000 | 2024 | IGWT-JAV CONSTRUCTION & DEVELOPMENT CORPORATION | 39 | 2024 | 2024-12-28 | 03/04/2024 | 0 | 0 | 2024-12-27 |  | 1
2024 | Region I | PANGASINAN | BURGOS (PANGASINAN) | P00821091LZ | Construction of Flood Mitigation Structure | 119.8909 | 16.0799 | 72686695 | 72686685 | 2024 | CDC CONSTRUCTION & SUPPLIES | 40 | 2024 | 2024-04-29 | 02/12/2024 | 10 | 0 | 2024-09-07 | 131
2023 | Region I | PANGASINAN | MABINI (PANGASINAN) | P00726363LZ | Construction of Flood Mitigation Structure | 119.8928 | 16.0765 | 53075000 | 52809625 | 2023 | ALCEL CONSTRUCTION | 41 | 2023 | 2023-05-29 | 03/30/2023 | 265375 | 0 | 2023-10-24 | 148
2022 | Region I | PANGASINAN | BURGOS (PANGASINAN) | P00620955LZ | Construction of Flood Mitigation Structure | 119.8942 | 16.0754 | 49000000 | 49000000 | 2022 | ALCEL CONSTRUCTION | 42 | 2022 | 2022-07-12 | 02/17/2022 | 0 | 0 | 2022-09-13 | 63
2023 | Region I | PANGASINAN | INFANTA (PANGASINAN) | P00726330LZ | Construction of Flood Mitigation Structure | 119.8976 | 15.8817 | 77200000 | 77200000 | 2023 | CHIARA2300 INCORPORATED / EJR BUILDERS & CONSTRUCTION SUPPLY | 43 | 2023 | 2023-09-26 | 03/30/2023 | 0 | 0 | 2023-12-08 | 73
2023 | Region III | ZAMBALES | SANTA CRUZ (ZAMBALES) | P00727153LZ | Construction of Flood Mitigation Structure | 119.9108 | 15.7847 | 48999232.94 | 48117246.7 | 2024 | E.R. DELA CRUZ CONSTRUCTION & SUPPLY | 44 | 2023 | 2024-01-22 | 04/19/2023 | 881986.24 | 0 | 2024-01-27 | 5
2024 | Region III | ZAMBALES | SANTA CRUZ (ZAMBALES) | P00824717LZ | Construction of Slope Protection Structure | 119.911 | 15.788 | 48249239.42 | 47694698 | 2024 | E.R. DELA CRUZ CONSTRUCTION & SUPPLY | 45 | 2024 | 2024-04-15 | 02/15/2024 | 554541.42 | 0 | 2024-09-10 | 148
2024 | Region III | ZAMBALES | SANTA CRUZ (ZAMBALES) | P00824716LZ | Construction of Slope Protection Structure | 119.9111 | 15.7882 | 48249959.91 | 47695117 | 2024 | E.R. DELA CRUZ CONSTRUCTION & SUPPLY | 46 | 2024 | 2024-04-15 | 02/15/2024 | 554842.91 | 0 | 2024-09-10 | 148
2022 | Region III | ZAMBALES | SANTA CRUZ (ZAMBALES) | P00640535LZ | Construction of Flood Mitigation Structure | 119.9117 | 15.7221 | 29392945.08 | 29698817.29 | 2022 | BIG BERTHA CONSTRUCTION & DEVELOPMENT | 47 | 2022 | 2022-09-14 | 04/04/2022 | 0 | 305872.21 | 2022-09-14 | 0
2023 | Region III | ZAMBALES | SANTA CRUZ (ZAMBALES) | P00740644LZ | Construction of Drainage Structure | 119.9147 | 15.7614 | 19599664.01 | 19266907.03 | 2023 | GASAT BUILDERS AND SUPPLIES INC. | 48 | 2023 | 2023-11-20 | 05/29/2023 | 332756.98 | 0 | 2023-11-23 | 3
2022 | Region III | ZAMBALES | CANDELARIA (ZAMBALES) | P00631277LZ | Construction of Drainage Structure | 119.9159 | 15.6223 | 9800000 | 9506441.08 | 2022 | JAM-C BUILDERS | 49 | 2022 | 2022-07-25 | 03/10/2022 | 293558.92 | 0 | 2022-07-06 |  | 19
2023 | Region I | PANGASINAN | INFANTA (PANGASINAN) | P00726327LZ | Construction of Flood Mitigation Structure | 119.9231 | 15.8163 | 77200000 | 77200000 | 2023 | ALCEL CONSTRUCTION | 50 | 2023 | 2023-12-19 | 03/30/2023 | 0 | 0 | 2024-01-07 | 19
2024 | Region I | PANGASINAN | MABINI (PANGASINAN) | P00843196LZ | Construction of Flood Mitigation Structure | 119.9267 | 16.0782 | 96500000 | 96500000 | 2025 | ANORE CONSTRUCTION | 51 | 2024 | 2025-01-31 | 04/08/2024 | 0 | 0 | 2025-01-31 | 0
2024 | Region I | PANGASINAN | INFANTA (PANGASINAN) | P00824834LZ | Construction of Flood Mitigation Structure | 119.9283 | 15.8073 | 96500000 | 96500000 | 2024 | IGWT-JAV CONSTRUCTION & DEVELOPMENT CORPORATION | 52 | 2024 | 2024-12-06 | 02/12/2024 | 0 | 0 | 2024-12-06 | 0
2024 | Region I | PANGASINAN | MABINI (PANGASINAN) | P00843197LZ | Construction of Flood Mitigation Structure | 119.9296 | 16.0756 | 96500000 | 96500000 | 2025 | ANORE CONSTRUCTION | 53 | 2024 | 2025-02-12 | 04/19/2024 | 0 | 0 | 2025-02-11 |  | 1
2024 | Region I | PANGASINAN | INFANTA (PANGASINAN) | P00824835LZ | Construction of Flood Mitigation Structure | 119.9333 | 15.8101 | 96500000 | 96500000 | 2024 | IGWT-JAV CONSTRUCTION & DEVELOPMENT CORPORATION | 54 | 2024 | 2024-12-18 | 02/23/2024 | 0 | 0 | 2024-12-17 |  | 1
2024 | Region I | PANGASINAN | INFANTA (PANGASINAN) | P00843180LZ | Construction of Flood Mitigation Structure | 119.9381 | 15.8128 | 96500000 | 96500000 | 2025 | ANORE CONSTRUCTION | 55 | 2024 | 2025-02-05 | 04/12/2024 | 0 | 0 | 2025-02-04 |  | 1
2023 | Region I | PANGASINAN | MABINI (PANGASINAN) | P00726364LZ | Construction of Flood Mitigation Structure | 119.9401 | 16.0681 | 53075000 | 53075000 | 2023 | CHIARA2300 INCORPORATED / EJR BUILDERS & CONSTRUCTION SUPPLY | 56 | 2023 | 2023-11-24 | 03/30/2023 | 0 | 0 | 2023-11-23 |  | 1
2024 | Region I | PANGASINAN | MABINI (PANGASINAN) | P00821105LZ | Construction of Flood Mitigation Structure | 119.9428 | 16.059 | 72687660 | 72687660 | 2025 | BERSON'S CONSTRUCTION & TRADING | 57 | 2024 | 2025-01-20 | 02/12/2024 | 0 | 0 | 2025-01-19 |  | 1
2024 | Region I | PANGASINAN | CITY OF ALAMINOS (PANGASINAN) | P00820716LZ | Construction of Flood Mitigation Structure | 119.9471 | 16.1407 | 49000000 | 49000000 | 2024 | CDC CONSTRUCTION & SUPPLIES | 58 | 2024 | 2024-04-11 | 02/05/2024 | 0 | 0 | 2024-08-31 | 142
2023 | Region III | ZAMBALES | IBA (CAPITAL) (ZAMBALES) | P00727154LZ | Construction of Flood Mitigation Structure | 119.9616 | 15.3857 | 48999487.57 | 48995000.77 | 2023 | E.R. DELA CRUZ CONSTRUCTION & SUPPLY | 59 | 2023 | 2023-11-22 | 04/14/2023 | 4486.8 | 0 | 2024-01-07 | 46
2022 | Region III | ZAMBALES | PALAUIG (ZAMBALES) | P00630935LZ | Construction of Slope Protection Structure | 119.9617 | 15.475 | 96494951.88 | 96498232.03 | 2023 | STO. CRISTO CONSTRUCTION & TRADING INC. (FOR: STO. CRISTO CONSTRUCTION & TRADING) | 60 | 2022 | 2023-03-23 | 04/04/2022 | 0 | 3280.15 | 2023-03-28 | 5
2022 | Region III | ZAMBALES | PALAUIG (ZAMBALES) | P00630936LZ | Construction of Slope Protection Structure | 119.9635 | 15.4706 | 96499280.08 | 96482482.65 | 2023 | STO. CRISTO CONSTRUCTION & TRADING INC. (FOR: STO. CRISTO CONSTRUCTION & TRADING) | 61 | 2022 | 2023-02-17 | 03/23/2022 | 16797.43 | 0 | 2023-03-16 | 27
2022 | Region III | ZAMBALES | PALAUIG (ZAMBALES) | P00630937LZ | Construction of Slope Protection Structure | 119.9635 | 15.4706 | 96494369.21 | 91669651.44 | 2023 | STO. CRISTO CONSTRUCTION & TRADING INC. (FOR: STO. CRISTO CONSTRUCTION & TRADING) | 62 | 2022 | 2023-03-20 | 03/23/2022 | 4824717.77 | 0 | 2023-03-16 |  | 4
2021 | Region III | ZAMBALES |  | P00526066LZ | Construction of Slope Protection Structure | 119.9638 | 15.4699 | 48999266.55 | 46794299.56 | 2022 | STO. CRISTO CONSTRUCTION & TRADING INC. (FOR: STO. CRISTO CONSTRUCTION & TRADING) | 63 | 2021 | 2022-12-05 | 04/27/2022 | 2204966.99 | 0 | 2022-11-21 |  | 14
2024 | Region III | ZAMBALES | SANTA CRUZ (ZAMBALES) | P00824714LZ | Construction of Flood Mitigation Structure | 119.9671 | 15.807 | 48249028.28 | 47670294 | 2024 | E.R. DELA CRUZ CONSTRUCTION & SUPPLY | 64 | 2024 | 2024-04-15 | 02/15/2024 | 578734.28 | 0 | 2024-09-10 | 148
2024 | Region I | PANGASINAN | CITY OF ALAMINOS (PANGASINAN) | P00824799LZ | Construction of Flood Mitigation Structure | 119.9683 | 16.1709 | 96500000 | 96500000 | 2025 | ANORE CONSTRUCTION | 65 | 2024 | 2025-02-01 | 04/08/2024 | 0 | 0 | 2025-01-31 |  | 1
2024 | Region I | PANGASINAN | CITY OF ALAMINOS (PANGASINAN) | P00820121LZ | Construction of Flood Mitigation Structure | 119.9683 | 16.1724 | 96500000 | 96500000 | 2024 | JONIK TRADING & CONSTRUCTION / ALCEL CONSTRUCTION | 66 | 2024 | 2024-12-03 | 02/23/2024 | 0 | 0 | 2024-12-02 |  | 1
2025 | Region I | PANGASINAN | CITY OF ALAMINOS (PANGASINAN) | P00941153LZ | Rehabilitation / Major Repair of Flood Control Structure | 119.9692 | 16.0968 | 4950000 | 4850385.71 | 2025 | GED CONSTRUCTION | 67 | 2025 | 2025-05-14 | 02/21/2025 | 99614.29 | 0 | 2025-05-13 |  | 1
2024 | Region I | PANGASINAN | CITY OF ALAMINOS (PANGASINAN) | P00824798LZ | Construction of Flood Mitigation Structure | 119.9703 | 16.1739 | 96500000 | 96500000 | 2025 | ANORE CONSTRUCTION | 68 | 2024 | 2025-02-01 | 04/08/2024 | 0 | 0 | 2025-01-31 |  | 1
2022 | Region I | PANGASINAN | CITY OF ALAMINOS (PANGASINAN) | P00620792LZ | Construction of Flood Mitigation Structure | 119.9711 | 16.1428 | 66585000 | 66585000 | 2022 | JASA GD 2000 CONSTRUCTION CORPORATION (FORMERLY:JASA BUILDER'S) / JONIK TRADING & CONSTRUCTION | 69 | 2022 | 2022-10-14 | 02/17/2022 | 0 | 0 | 2022-10-13 |  | 1
2024 | Region I | PANGASINAN | CITY OF ALAMINOS (PANGASINAN) | P00823305LZ | Construction of Slope Protection Structure | 119.9713 | 16.1735 | 96500000 | 96500000 | 2024 | IGWT-JAV CONSTRUCTION & DEVELOPMENT CORPORATION | 70 | 2024 | 2024-12-18 | 02/23/2024 | 0 | 0 | 2024-12-17 |  | 1
2023 | Region I | PANGASINAN | CITY OF ALAMINOS (PANGASINAN) | P00726332LZ | Construction of Flood Mitigation Structure | 119.9715 | 16.1705 | 77200000 | 77200000 | 2024 | JONIK TRADING & CONSTRUCTION / ALCEL CONSTRUCTION | 71 | 2023 | 2024-02-08 | 04/13/2023 | 0 | 0 | 2024-02-20 | 12
2022 | Region I | PANGASINAN | CITY OF ALAMINOS (PANGASINAN) | P00620794LZ | Construction of Flood Mitigation Structure | 119.972 | 16.1673 | 66585000 | 66585000 | 2022 | CHIARA2300 INCORPORATED / BERSON'S CONSTRUCTION & TRADING | 72 | 2022 | 2022-08-30 | 02/17/2022 | 0 | 0 | 2022-10-13 | 44
2022 | Region I | PANGASINAN | CITY OF ALAMINOS (PANGASINAN) | P00620793LZ | Construction of Flood Mitigation Structure | 119.9724 | 16.1673 | 66971000 | 66971000 | 2022 | CHIARA2300 INCORPORATED / EJR BUILDERS & CONSTRUCTION SUPPLY | 73 | 2022 | 2022-07-25 | 02/17/2022 | 0 | 0 | 2022-10-13 | 80
2024 | Region I | PANGASINAN | CITY OF ALAMINOS (PANGASINAN) | P00820120LZ | Construction of Flood Mitigation Structure | 119.9734 | 16.1699 | 96500000 | 96500000 | 2024 | CHIARA2300 INCORPORATED / EJR BUILDERS & CONSTRUCTION SUPPLY | 74 | 2024 | 2024-07-17 | 02/12/2024 | 0 | 0 | 2024-12-02 | 138
2023 | Region I | PANGASINAN | CITY OF ALAMINOS (PANGASINAN) | P00726361LZ | Construction of Flood Mitigation Structure | 119.9753 | 16.1678 | 72375000 | 72375000 | 2023 | CDC CONSTRUCTION & SUPPLIES | 75 | 2023 | 2023-05-22 | 04/13/2023 | 0 | 0 | 2023-12-07 | 199
2023 | Region I | PANGASINAN | CITY OF ALAMINOS (PANGASINAN) | P00726362LZ | Construction of Flood Mitigation Structure | 119.9754 | 16.1668 | 72375000 | 72375000 | 2024 | CHIARA2300 INCORPORATED / BERSON'S CONSTRUCTION & TRADING | 76 | 2023 | 2024-02-05 | 04/13/2023 | 0 | 0 | 2024-02-05 | 0
2022 | Region I | PANGASINAN | CITY OF ALAMINOS (PANGASINAN) | P00620954LZ | Construction of Flood Mitigation Structure | 119.9757 | 16.1386 | 49000000 | 49000000 | 2022 | JONIK TRADING & CONSTRUCTION / ALCEL CONSTRUCTION | 77 | 2022 | 2022-11-04 | 02/10/2022 | 0 | 0 | 2022-11-05 | 1
2024 | Region I | PANGASINAN | CITY OF ALAMINOS (PANGASINAN) | P00824797LZ | Construction of Flood Mitigation Structure | 119.9762 | 16.1772 | 96500000 | 96500000 | 2025 | ANORE CONSTRUCTION | 78 | 2024 | 2025-01-26 | 04/12/2024 | 0 | 0 | 2025-01-25 |  | 1
2023 | Region III | ZAMBALES | CANDELARIA (ZAMBALES) | P00742162LZ | Construction of Slope Protection Structure | 119.9799 | 15.5864 | 98999412.33 | 98009377.11 | 2023 | DMLC BUILDERS | 79 | 2023 | 2023-11-22 | 04/14/2023 | 990035.22 | 0 | 2024-03-07 | 106
2023 | Region III | ZAMBALES | CANDELARIA (ZAMBALES) | P00742147LZ | Construction of Slope Protection Structure | 119.9799 | 15.5864 | 98999606.49 | 98999501.03 | 2023 | DMLC BUILDERS | 80 | 2023 | 2023-11-22 | 04/14/2023 | 105.46 | 0 | 2024-03-07 | 106
2024 | Region III | ZAMBALES | SANTA CRUZ (ZAMBALES) | P00824715LZ | Construction of Flood Mitigation Structure | 119.9841 | 15.8093 | 48248273.33 | 47669194 | 2024 | E.R. DELA CRUZ CONSTRUCTION & SUPPLY | 81 | 2024 | 2024-04-15 | 02/15/2024 | 579079.33 | 0 | 2024-09-10 | 148
2023 | Region III | ZAMBALES | CANDELARIA (ZAMBALES) | P00742148LZ | Construction of Slope Protection Structure | 119.9886 | 15.5946 | 98999633.54 | 98999273.23 | 2023 | JTC CRUZ CONSTRUCTION CO., INC. | 82 | 2023 | 2023-11-22 | 04/14/2023 | 360.31 | 0 | 2024-03-07 | 106
2023 | Region III | ZAMBALES | CANDELARIA (ZAMBALES) | P00742149LZ | Construction of Slope Protection Structure | 119.9904 | 15.5945 | 98999994.92 | 98999798.68 | 2023 | JTC CRUZ CONSTRUCTION CO., INC. | 83 | 2023 | 2023-11-22 | 04/14/2023 | 196.24 | 0 | 2024-03-07 | 106
2023 | Region III | ZAMBALES | CANDELARIA (ZAMBALES) | P00742381LZ | Construction of Slope Protection Structure | 119.9938 | 15.5932 | 98999766.65 | 98999580.83 | 2023 | JTC CRUZ CONSTRUCTION CO., INC. | 84 | 2023 | 2023-11-22 | 04/17/2023 | 185.82 | 0 | 2024-03-10 | 109
2022 | Region III | ZAMBALES | BOTOLAN (ZAMBALES) | P00620187LZ | Construction of Slope Protection Structure | 120.0076 | 15.2754 | 72261600.37 | 69009815.77 | 2022 | HIGH STRENGTH DEV. CORPORATION | 85 | 2022 | 2022-07-18 | 02/23/2022 | 3251784.6 | 0 | 2022-09-19 | 63
2022 | Region III | ZAMBALES | IBA (CAPITAL) (ZAMBALES) | P00640537LZ | Construction of Flood Mitigation Structure | 120.0082 | 15.3325 | 37230435.15 | 37620000 | 2022 | CDC CONSTRUCTION & SUPPLIES | 86 | 2022 | 2022-09-27 | 04/04/2022 | 0 | 389564.85 | 2022-09-29 | 2
2022 | Region III | ZAMBALES | IBA (CAPITAL) (ZAMBALES) | P00640538LZ | Construction of Flood Mitigation Structure | 120.0086 | 15.3344 | 37235289.06 | 37620000 | 2022 | ORANI CONSTRUCTION AND SUPPLY CORPORATION (FORMERLY:ORANI BUILDERS & SUPPLY) | 87 | 2022 | 2022-09-26 | 04/04/2022 | 0 | 384710.94 | 2022-09-29 | 3
2024 | Region I | PANGASINAN | CITY OF ALAMINOS (PANGASINAN) | P00820713LZ | Construction of Flood Mitigation Structure | 120.0087 | 16.1151 | 49000000 | 49000000 | 2024 | ALCEL CONSTRUCTION | 88 | 2024 | 2024-07-18 | 02/05/2024 | 0 | 0 | 2024-08-31 | 44
2024 | Region III | ZAMBALES | IBA (CAPITAL) (ZAMBALES) | P00844770LZ | Construction of Flood Mitigation Structure | 120.0087 | 15.3198 | 48249885.77 | 47579211.86 | 2024 | RAIK CONSTRUCTION AND DEVELOPMENT CORPORATION (FORMERLY: RAIK CONSTRUCTION AND SUPPLY) | 89 | 2024 | 2024-11-13 | 02/22/2024 | 670673.91 | 0 | 2024-11-16 | 3
2024 | Region I | PANGASINAN | CITY OF ALAMINOS (PANGASINAN) | P00843215LZ | Construction of Flood Mitigation Structure | 120.0088 | 16.1827 | 96500000 | 96491365.52 | 2025 | ORIENTAL SALES CENTER AND CONTRACTOR / ALCEL CONSTRUCTION | 90 | 2024 | 2025-03-03 | 02/12/2024 | 8634.48 | 0 | 2025-03-02 |  | 1
2022 | Region III | ZAMBALES | IBA (CAPITAL) (ZAMBALES) | P00640536LZ | Construction of Flood Mitigation Structure | 120.0095 | 15.3304 | 38903735.02 | 39303000 | 2022 | CDC CONSTRUCTION & SUPPLIES | 91 | 2022 | 2022-09-28 | 04/04/2022 | 0 | 399264.98 | 2022-09-29 | 1
2022 | Region III | ZAMBALES | IBA (CAPITAL) (ZAMBALES) | P00640540LZ | Construction of Slope Protection Structure | 120.0106 | 15.3339 | 48996495.64 | 49500000 | 2022 | CDC CONSTRUCTION & SUPPLIES | 92 | 2022 | 2022-12-12 | 04/04/2022 | 0 | 503504.36 | 2022-10-14 |  | 59
2022 | Region III | ZAMBALES | IBA (CAPITAL) (ZAMBALES) | P00640539LZ | Construction of Flood Mitigation Structure | 120.0113 | 15.3279 | 38903704.46 | 39303000 | 2022 | HIGH STRENGTH DEV. CORPORATION | 93 | 2022 | 2022-09-28 | 04/04/2022 | 0 | 399295.54 | 2022-09-29 | 1
2023 | Region III | ZAMBALES | BOTOLAN (ZAMBALES) | P00725703LZ | Construction of Flood Mitigation Structure | 120.0159 | 15.2692 | 96499311.36 | 96499292.34 | 2023 | NICLEDON CONSTRUCTION / GRACE CONSTRUCTION CORPORATION | 94 | 2023 | 2023-12-16 | 06/20/2023 | 19.02 | 0 | 2024-04-13 | 119
2023 | Region III | ZAMBALES | BOTOLAN (ZAMBALES) | P00740643LZ | Construction of Flood Mitigation Structure | 120.0286 | 15.2901 | 29399608.39 | 28870422.99 | 2023 | MARKBILT CONSTRUCTION TRADING & DEVELOPMENT CORP. (FORMERLY:MARKBILT CONSTRUCTION) | 95 | 2023 | 2023-12-07 | 04/17/2023 | 529185.4 | 0 | 2023-12-11 | 4
2023 | Region III | ZAMBALES | BOTOLAN (ZAMBALES) | P00726748LZ | Construction of Flood Mitigation Structure | 120.03 | 15.2656 | 48999304.04 | 48998700.23 | 2023 | R.A. PAHATI CONST. & SUPPLY, INC. | 96 | 2023 | 2023-11-22 | 02/22/2023 | 603.81 | 0 | 2023-12-17 | 25
2023 | Region I | PANGASINAN | DAGUPAN CITY (PANGASINAN) | P00726837LZ | Construction of Flood Mitigation Structure | 120.0345 | 16.0345 | 106150000 | 106150000 | 2024 | BET CONSTRUCTION & SUPPLY | 97 | 2023 | 2024-02-02 | 05/09/2023 | 0 | 0 | 2024-02-01 |  | 1
2022 | Region III | ZAMBALES | BOTOLAN (ZAMBALES) | P00620555LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.0401 | 15.2692 | 48999306.81 | 47039334.54 | 2022 | ORANI CONSTRUCTION AND SUPPLY CORPORATION (FORMERLY:ORANI BUILDERS & SUPPLY) | 98 | 2022 | 2022-09-28 | 03/16/2022 | 1959972.27 | 0 | 2022-09-25 |  | 3
2022 | Region III | BULACAN | SAN MIGUEL (BULACAN) | P00620523LZ | Construction of Flood Mitigation Structure | 120.0471 | 15.241 | 46059437.96 | 46031419.24 | 2022 | MRRM TRADING & CONSTRUCTION | 99 | 2022 | 2022-09-11 | 02/28/2022 | 28018.72 | 0 | 2022-09-10 |  | 1
2023 | Region III | ZAMBALES | CABANGAN (ZAMBALES) | P00742377LZ | Construction of Slope Protection Structure | 120.0551 | 15.1565 | 5939285.37 | 5850198.15 | 2023 | KAEE CONSTRUCTION SERVICES | 100 | 2023 | 2023-10-23 | 05/31/2023 | 89087.22 | 0 | 2023-10-26 | 3
2021 | Region III | ZAMBALES |  | P00561720LZ | Construction of Slope Protection Structure | 120.0561 | 15.3131 | 24499951.53 | 24750000 | 2022 | CDC CONSTRUCTION & SUPPLIES | 101 | 2021 | 2022-07-11 | 01/10/2022 | 0 | 250048.47 | 2022-07-07 |  | 4
2021 | Region IV-B | OCCIDENTAL MINDORO |  | P00561574LZ | Construction of Flood Mitigation Structure | 120.4011 | 13.4164 | 19600000 | 19042647.14 | 2023 | NEW MINDORENOS LUMBER, HARDWARE AND GEN MERCHANDISE | 102 | 2021 | 2023-05-29 | 09/23/2021 | 557352.86 | 0 | 2022-05-28 |  | 366
2023 | Region III | TARLAC | CAMILING (TARLAC) | P00742373LZ | Construction of Slope Protection Structure | 120.4012 | 15.6552 | 49500000 | 48050158.9 | 2023 | A.C. SOLIVEN CONSTRUCTION & GENERAL MERCHANDISE | 103 | 2023 | 2023-09-13 | 03/17/2023 | 1449841.1 | 0 | 2023-09-12 |  | 1
2022 | Region I | PANGASINAN | MANGALDAN (PANGASINAN) | P00630929LZ | Construction of Slope Protection Structure | 120.4012 | 16.065 | 57900000 | 57900000 | 2022 | J.G. GARCIA CONSTRUCTION & SUPPLY (FOR: J.G. GARCIA CONST.) | 104 | 2022 | 2022-10-03 | 04/07/2022 | 0 | 0 | 2022-10-02 |  | 1
2023 | Region I | LA UNION | BALAOAN (LA UNION) | P00742271LZ | Construction of Flood Mitigation Structure | 120.4015 | 16.8187 | 9799975.97 | 9799384.97 | 2023 | PAGTAENGAN BUILDERS AND CONCRETE PRODUCTS | 105 | 2023 | 2023-06-26 | 05/24/2023 | 591 | 0 | 2023-08-24 | 59
2024 | Region I | LA UNION | TUBAO (LA UNION) | P00821475LZ | Construction of Flood Mitigation Structure | 120.4017 | 16.368 | 48999995.52 | 48926107.83 | 2025 | RODEKOM GENERAL CONSTRUCTION AND ENTERPRISE | 106 | 2024 | 2025-03-17 | 02/02/2024 | 73887.69 | 0 | 2024-08-15 |  | 214
2024 | Region I | LA UNION | SAN GABRIEL (LA UNION) | P00824807LZ | Construction of Flood Mitigation Structure | 120.402 | 16.6652 | 154400000 | 154399996.8 | 2024 | ST. GERRARD CONSTRUCTION GEN. CONTRACTOR & DEVELOPMENT CORP. (FORMERLY:ST. GERRARD CONSTRUCTION) | 107 | 2024 | 2024-04-15 | 03/01/2024 | 3.2 | 0 | 2024-11-24 | 223
2023 | Region I | LA UNION | TUBAO (LA UNION) | P00727245LZ | Construction of Flood Mitigation Structure | 120.4022 | 16.3665 | 72374997.36 | 72334997.36 | 2024 | UNIVERSAL DE LEON CONSTRUCTION AND AGGREGATES | 108 | 2023 | 2024-02-11 | 04/19/2023 | 40000 | 0 | 2023-12-09 |  | 64
2023 | Region I | LA UNION | TUBAO (LA UNION) | P00727243LZ | Construction of Flood Mitigation Structure | 120.4023 | 16.3702 | 72374995.83 | 72334995.83 | 2024 | UNIVERSAL DE LEON CONSTRUCTION AND AGGREGATES | 109 | 2023 | 2024-02-11 | 04/19/2023 | 40000 | 0 | 2023-12-09 |  | 64
2023 | Region I | LA UNION | TUBAO (LA UNION) | P00727244LZ | Construction of Flood Mitigation Structure | 120.4023 | 16.3703 | 72374992.2 | 72334992.2 | 2024 | UNIVERSAL DE LEON CONSTRUCTION AND AGGREGATES | 110 | 2023 | 2024-02-11 | 04/19/2023 | 40000 | 0 | 2023-12-09 |  | 64
2024 | Region I | PANGASINAN | MANGALDAN (PANGASINAN) | P00839554LZ | Construction of Drainage Structure | 120.4032 | 16.0598 | 4950000 | 4950000 | 2024 | MIGHTYWAY CONSTRUCTION AND SUPPLY | 111 | 2024 | 2024-05-18 | 02/15/2024 | 0 | 0 | 2024-05-17 |  | 1
2022 | Region III | TARLAC | CAMILING (TARLAC) | P00621287LZ | Construction of Flood Mitigation Structure | 120.4033 | 15.7409 | 289499110.9 | 289499994.8 | 2024 | BMK CONSTRUCTION CORPORATION (FORMERLY B.M.K. CONSTRUCTION) / ROYAL CROWN MONARCH CONSTRUCTION & SUPPLIES CORP. | 112 | 2022 | 2024-09-01 | 07/25/2022 | 0 | 883.9 | 2024-08-31 |  | 1
2024 | Region I | LA UNION | SAN GABRIEL (LA UNION) | P00820103LZ | Construction of Flood Mitigation Structure | 120.4033 | 16.6717 | 84262347.69 | 82971487.54 | 2024 | MY BUILDERS AND CONSTRUCTION | 113 | 2024 | 2024-10-25 | 02/14/2024 | 1290860.15 | 0 | 2024-12-19 | 55
2022 | Region I | LA UNION | NAGUILIAN (LA UNION) | P00631073LZ | Construction of Flood Mitigation Structure | 120.4036 | 16.577 | 7839996.91 | 7693165.65 | 2022 | E.E. MADAYAG CONSTRUCTION | 114 | 2022 | 2022-07-25 | 02/22/2022 | 146831.26 | 0 | 2022-05-14 |  | 72
2024 | Region I | LA UNION | TUBAO (LA UNION) | P00821474LZ | Construction of Flood Mitigation Structure | 120.4037 | 16.3652 | 48999991.25 | 48987820.45 | 2025 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | 115 | 2024 | 2025-03-16 | 02/29/2024 | 12170.8 | 0 | 2024-09-11 |  | 186
2023 | Region I | LA UNION | TUBAO (LA UNION) | P00742276LZ | Construction of Flood Mitigation Structure | 120.4047 | 16.3813 | 29399982.27 | 29000189.13 | 2023 | E.E. MADAYAG CONSTRUCTION | 116 | 2023 | 2023-07-03 | 03/15/2023 | 399793.14 | 0 | 2023-09-02 | 61
2023 | Region I | LA UNION | TUBAO (LA UNION) | P00727333LZ | Construction of Flood Mitigation Structure | 120.4047 | 16.3806 | 24499999.44 | 24459999.44 | 2024 | ROCK-WBL CONSTRUCTION CORP. (FOR: ROCK-WBL CONSTRUCTION TRADING & SERVICES) | 117 | 2023 | 2024-02-11 | 04/19/2023 | 40000 | 0 | 2023-10-02 |  | 132
2023 | Region I | LA UNION | TUBAO (LA UNION) | P00727242LZ | Construction of Flood Mitigation Structure | 120.4049 | 16.3727 | 72374993.61 | 72334993.61 | 2024 | UNIVERSAL DE LEON CONSTRUCTION AND AGGREGATES | 118 | 2023 | 2024-02-11 | 04/19/2023 | 40000 | 0 | 2023-12-09 |  | 64
2023 | Region I | LA UNION | TUBAO (LA UNION) | P00727240LZ | Construction of Flood Mitigation Structure | 120.405 | 16.2789 | 72374996.18 | 72334422.8 | 2024 | ROCK-WBL CONSTRUCTION CORP. (FOR: ROCK-WBL CONSTRUCTION TRADING & SERVICES) | 119 | 2023 | 2024-02-11 | 04/19/2023 | 40573.38 | 0 | 2023-12-09 |  | 64
2024 | Region I | LA UNION | TUBAO (LA UNION) | P00845902LZ | Construction of Flood Mitigation Structure | 120.405 | 16.3634 | 29699998.74 | 29693457.1 | 2025 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | 120 | 2024 | 2025-02-16 | 02/27/2024 | 6541.64 | 0 | 2024-08-18 |  | 182
2024 | Region I | LA UNION | TUBAO (LA UNION) | P00839551LZ | Construction of Flood Mitigation Structure | 120.405 | 16.3624 | 14850000 | 14849401.14 | 2024 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | 121 | 2024 | 2024-10-01 | 09/09/2024 | 598.86 | 0 | 2025-01-11 | 102
2023 | Region I | ILOCOS SUR | CITY OF CANDON (ILOCOS SUR) | P00727079LZ | Construction of Flood Mitigation Structure | 120.4052 | 17.2141 | 39200000 | 38023727.14 | 2024 | FIRST NORTHWAY DEVELOPMENT & CONSTRUCTION CORP. | 122 | 2023 | 2024-10-29 | 04/04/2023 | 1176272.86 | 0 | 2024-01-06 |  | 297
2023 | Region III | TARLAC | CAMILING (TARLAC) | P00726498LZ | Construction of Slope Protection Structure | 120.4053 | 15.6607 | 144749610 | 144749856.7 | 2024 | ROYAL CROWN MONARCH CONSTRUCTION & SUPPLIES CORP. | 123 | 2023 | 2024-04-22 | 03/20/2023 | 0 | 246.7 | 2024-04-21 |  | 1
2023 | Region I | LA UNION | TUBAO (LA UNION) | P00727241LZ | Construction of Flood Mitigation Structure | 120.4059 | 16.3762 | 72374998.14 | 72334998.14 | 2024 | MG SAMIDAN CONSTRUCTION | 124 | 2023 | 2024-02-11 | 04/19/2023 | 40000 | 0 | 2023-12-09 |  | 64
2022 | Region I | LA UNION | BAGULIN (LA UNION) | P00639316LZ | Construction of Slope Protection Structure | 120.4063 | 16.5557 | 207475000 | 201253790 | 2023 | J.H. PAJARA CONSTRUCTION CORPORATION / S-ANG CONSTRUCTION & GENERAL TRADING, INC. | 125 | 2022 | 2023-04-12 | 04/12/2022 | 6221210 | 0 | 2023-04-11 |  | 1
2023 | Region I | PANGASINAN | MALASIQUI (PANGASINAN) | P00737427LZ | Construction of Flood Mitigation Structure | 120.4075 | 15.9439 | 4950000 | 4847330.62 | 2023 | HIGH ROCK CONSTRUCTION AND SUPPLIES INCORPORATED | 126 | 2023 | 2023-09-01 | 06/21/2023 | 102669.38 | 0 | 2023-09-01 | 0
2022 | Region III | TARLAC | CAMILING (TARLAC) | P00621085LZ | Construction of Flood Mitigation Structure | 120.4083 | 15.6809 | 49000000 | 48167000.08 | 2022 | ROYAL CROWN MONARCH CONSTRUCTION & SUPPLIES CORP. | 127 | 2022 | 2022-11-07 | 03/12/2022 | 832999.92 | 0 | 2022-11-06 |  | 1
2023 | Region I | PANGASINAN | MALASIQUI (PANGASINAN) | P00726068LZ | Construction of Flood Mitigation Structure | 120.4085 | 15.9491 | 19600000 | 19192162.85 | 2023 | JEUSMACK BUILDERS & CONSTRUCTION SUPPLY | 128 | 2023 | 2023-03-20 | 02/13/2023 | 407837.15 | 0 | 2023-07-24 | 126
2023 | Region I | PANGASINAN | MALASIQUI (PANGASINAN) | P00726090LZ | Construction of Flood Mitigation Structure | 120.4087 | 15.9219 | 19600000 | 19599584.16 | 2023 | JEUSMACK BUILDERS & CONSTRUCTION SUPPLY | 129 | 2023 | 2023-03-20 | 02/13/2023 | 415.84 | 0 | 2023-07-24 | 126
2024 | Region I | LA UNION | NAGUILIAN (LA UNION) | P00823292LZ | Construction of Flood Mitigation Structure | 120.4098 | 16.5025 | 115800000 | 115799720.8 | 2024 | MG SAMIDAN CONSTRUCTION | 130 | 2024 | 2024-08-19 | 05/13/2024 | 279.2 | 0 | 2024-12-31 | 134
2024 | Region I | LA UNION | SAN GABRIEL (LA UNION) | P00824809LZ | Construction of Flood Mitigation Structure | 120.4098 | 16.6822 | 154400000 | 154399995.6 | 2024 | ST. GERRARD CONSTRUCTION GEN. CONTRACTOR & DEVELOPMENT CORP. (FORMERLY:ST. GERRARD CONSTRUCTION) | 131 | 2024 | 2024-04-15 | 03/01/2024 | 4.4 | 0 | 2024-11-24 | 223
2022 | Region III | TARLAC | CAMILING (TARLAC) | P00631271LZ | Construction of Slope Protection Structure | 120.4101 | 15.6826 | 44100000 | 43210090.76 | 2022 | R.R. RICAFORT CONSTRUCTION AND SUPPLIES | 132 | 2022 | 2022-07-22 | 01/28/2022 | 889909.24 | 0 | 2022-07-21 |  | 1
2023 | Region III | BATAAN | DINALUPIHAN (BATAAN) | P00725712LZ | Construction of Flood Mitigation Structure | 120.4105 | 14.8471 | 48249997.25 | 48250000 | 2024 | ORANI CONSTRUCTION AND SUPPLY CORPORATION (FORMERLY:ORANI BUILDERS & SUPPLY) | 133 | 2023 | 2024-01-26 | 07/31/2023 | 0 | 2.75 | 2024-01-25 |  | 1
2022 | Region III | TARLAC | CAMILING (TARLAC) | P00631267LZ | Construction of Flood Mitigation Structure | 120.4106 | 15.6833 | 29400000 | 28870799.6 | 2022 | GJE BUILDERS CORPORATION (FORMERLY: GJE BUILDERS) | 134 | 2022 | 2022-10-15 | 03/10/2022 | 529200.4 | 0 | 2022-10-14 |  | 1
2022 | Region III | TARLAC | CAMILING (TARLAC) | P00620549LZ | Construction of Flood Mitigation Structure | 120.4111 | 15.6883 | 19600000 | 19219599.55 | 2022 | CS GONZALES CONSTRUCTION AND SUPPLY | 135 | 2022 | 2022-07-14 | 02/14/2022 | 380400.45 | 0 | 2022-08-04 | 21
2022 | Region III | BATAAN | DINALUPIHAN (BATAAN) | P00639363LZ | Rehabilitation / Major Repair of Drainage Structure | 120.4117 | 14.845 | 72374999.81 | 72374999.81 | 2023 | TDC II PRO BUILDERS | 136 | 2022 | 2023-04-19 | 06/13/2022 | 0 | 0 | 2023-04-20 | 1
2022 | Region III | TARLAC | CAMILING (TARLAC) | P00621570LZ | Construction of Slope Protection Structure | 120.4117 | 15.6827 | 96500000 | 93605000 | 2022 | ROYAL CROWN MONARCH CONSTRUCTION & SUPPLIES CORP. | 137 | 2022 | 2022-11-28 | 03/30/2022 | 2895000 | 0 | 2022-11-27 |  | 1
2022 | Region III | TARLAC | CAMILING (TARLAC) | P00621572LZ | Construction of Slope Protection Structure | 120.4124 | 15.6833 | 96500000 | 96500000 | 2022 | ROYAL CROWN MONARCH CONSTRUCTION & SUPPLIES CORP. | 138 | 2022 | 2022-11-22 | 03/24/2022 | 0 | 0 | 2022-11-21 |  | 1
2024 | Region I | ILOCOS SUR | CITY OF CANDON (ILOCOS SUR) | P00823295LZ | Construction of Revetment | 120.4128 | 17.2069 | 34300000 | 33774671.1 | 2024 | FIRST NORTHWAY DEVELOPMENT & CONSTRUCTION CORP. | 139 | 2024 | 2024-11-22 | 05/03/2024 | 525328.9 | 0 | 2024-12-08 | 16
2021 | Region I | ILOCOS SUR |  | P00525866LZ | Construction of Revetment | 120.4135 | 17.7813 | 49000000 | 49000000 | 2022 | VIKING CONSTRUCTION & SUPPLIES | 140 | 2021 | 2022-12-31 | 02/24/2022 | 0 | 0 | 2023-03-11 | 70
2022 | Region III | TARLAC | CAMILING (TARLAC) | P00640457LZ | Construction of Slope Protection Structure | 120.4142 | 15.6828 | 99000000 | 97015000 | 2022 | A.C. SOLIVEN CONSTRUCTION & GENERAL MERCHANDISE | 141 | 2022 | 2022-11-29 | 03/31/2022 | 1985000 | 0 | 2022-11-28 |  | 1
2022 | Region III | TARLAC | CAMILING (TARLAC) | P00621571LZ | Construction of Slope Protection Structure | 120.4146 | 15.682 | 96500000 | 96500000 | 2023 | ROYAL CROWN MONARCH CONSTRUCTION & SUPPLIES CORP. | 142 | 2022 | 2023-04-06 | 03/30/2022 | 0 | 0 | 2023-04-05 |  | 1
2024 | Region I | LA UNION | TUBAO (LA UNION) | P00823314LZ | Construction of Flood Mitigation Structure | 120.4147 | 16.3565 | 19299998.86 | 19284998.86 | 2025 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | 143 | 2024 | 2025-03-16 | 05/07/2024 | 15000 | 0 | 2024-10-13 |  | 154
2022 | Region III | TARLAC | CAMILING (TARLAC) | P00621474LZ | Construction of Slope Protection Structure | 120.415 | 15.7466 | 96500000 | 94564193 | 2023 | FLORDES CONSTRUCTION & TRADING CORP. (FORMERLY FLO | 144 | 2022 | 2023-04-28 | 03/30/2022 | 1935807 | 0 | 2023-05-11 | 13
2022 | Region I | PANGASINAN | MANGALDAN (PANGASINAN) | P00620956LZ | Construction of Flood Mitigation Structure | 120.4154 | 16.0813 | 24124999.81 | 24124966.41 | 2022 | FORTHRIGHT CONSTRUCTION | 145 | 2022 | 2022-12-14 | 04/07/2022 | 33.4 | 0 | 2022-12-13 |  | 1
2022 | Region III | TARLAC | CAMILING (TARLAC) | P00621090LZ | Construction of Flood Mitigation Structure | 120.4157 | 15.7015 | 39200000 | 38708110.64 | 2022 | A.C. SOLIVEN CONSTRUCTION & GENERAL MERCHANDISE | 146 | 2022 | 2022-07-16 | 01/28/2022 | 491889.36 | 0 | 2022-07-15 |  | 1
2024 | Region I | LA UNION | TUBAO (LA UNION) | P00845904LZ | Construction of Flood Mitigation Structure | 120.4158 | 16.3485 | 29699997.95 | 29693452.57 | 2025 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | 147 | 2024 | 2025-03-16 | 02/27/2024 | 6545.38 | 0 | 2024-08-18 |  | 210
2024 | Region I | LA UNION | NAGUILIAN (LA UNION) | P00823291LZ | Construction of Flood Mitigation Structure | 120.416 | 16.5037 | 115800000 | 115799749.5 | 2024 | ROCK-WBL CONSTRUCTION CORP. (FOR: ROCK-WBL CONSTRUCTION TRADING & SERVICES) | 148 | 2024 | 2024-11-11 | 05/03/2024 | 250.5 | 0 | 2025-02-01 | 82
2022 | Region III | TARLAC | CAMILING (TARLAC) | P00621088LZ | Construction of Flood Mitigation Structure | 120.416 | 15.6938 | 29400000 | 28782600.04 | 2022 | GJE BUILDERS CORPORATION (FORMERLY: GJE BUILDERS) | 149 | 2022 | 2022-07-24 | 02/14/2022 | 617399.96 | 0 | 2022-07-22 |  | 2
2023 | Region I | LA UNION | TUBAO (LA UNION) | P00726336LZ | Construction of Flood Mitigation Structure | 120.4169 | 16.3524 | 144750000 | 144732166.4 | 2023 | RODEKOM GENERAL CONSTRUCTION AND ENTERPRISE | 150 | 2023 | 2023-11-13 | 02/14/2023 | 17833.6 | 0 | 2024-01-12 | 60
2023 | Region I | PANGASINAN | MANGALDAN (PANGASINAN) | P00727095LZ | Construction of Flood Mitigation Structure | 120.4173 | 16.0766 | 26937260 | 26934215.03 | 2023 | BET CONSTRUCTION & SUPPLY | 151 | 2023 | 2023-10-26 | 05/12/2023 | 3044.97 | 0 | 2023-11-03 | 8
2022 | Region III | TARLAC | CAMILING (TARLAC) | P00631272LZ | Construction of Slope Protection Structure | 120.4173 | 15.7041 | 44100000 | 43206331.56 | 2022 | R.R. RICAFORT CONSTRUCTION AND SUPPLIES | 152 | 2022 | 2022-09-20 | 01/28/2022 | 893668.44 | 0 | 2022-09-19 |  | 1
2023 | Region III | TARLAC | CAMILING (TARLAC) | P00726742LZ | Construction of Flood Mitigation Structure | 120.4174 | 15.6819 | 49000000 | 48018969.45 | 2023 | A.C. SOLIVEN CONSTRUCTION & GENERAL MERCHANDISE | 153 | 2023 | 2023-06-21 | 02/02/2023 | 981030.55 | 0 | 2023-07-31 | 40
2022 | Region III | BATAAN | HERMOSA (BATAAN) | P00632808LZ | Construction of Flood Mitigation Structure | 120.4177 | 14.845 | 14849999.96 | 14849999.56 | 2022 | VM BUILDERS CONSTRUCTION CORPORATION | 154 | 2022 | 2022-08-27 | 02/21/2022 | 0.4 | 0 | 2022-08-28 | 1
2023 | Region III | TARLAC | CAMILING (TARLAC) | P00726743LZ | Construction of Flood Mitigation Structure | 120.4177 | 15.6875 | 49000000 | 49000000 | 2023 | A.C. SOLIVEN CONSTRUCTION & GENERAL MERCHANDISE | 155 | 2023 | 2023-06-22 | 01/30/2023 | 0 | 0 | 2023-07-28 | 36
2024 | Region I | LA UNION | TUBAO (LA UNION) | P00821479LZ | Construction of Flood Mitigation Structure | 120.4179 | 16.3559 | 48250000 | 48249980.3 | 2024 | JABEN GENERAL CONTRACTING & ENG'G SERVICES | 156 | 2024 | 2024-11-27 | 03/15/2024 | 19.7 | 0 | 2024-12-12 | 15
2023 | Region III | BATAAN | HERMOSA (BATAAN) | P00742314LZ | Construction of Flood Mitigation Structure | 120.4189 | 14.8453 | 19799999.45 | 19799993.13 | 2023 | M.C.J. VALENZUELA CONSTRUCTION ENTERPRISES | 157 | 2023 | 2023-12-21 | 05/25/2023 | 6.32 | 0 | 2023-12-25 | 4
2022 | Region III | TARLAC | CAMILING (TARLAC) | P00621087LZ | Construction of Flood Mitigation Structure | 120.419 | 15.7059 | 44756600 | 44217525.58 | 2022 | A.C. SOLIVEN CONSTRUCTION & GENERAL MERCHANDISE | 158 | 2022 | 2022-09-21 | 03/29/2022 | 539074.42 | 0 | 2022-09-20 |  | 1
2022 | Region III | TARLAC | CAMILING (TARLAC) | P00640527LZ | Construction of Slope Protection Structure | 120.4193 | 15.7488 | 49500000 | 48511637.23 | 2022 | HIGH STRENGTH DEV. CORPORATION / RCUBE ENGINEERING SERVICES | 159 | 2022 | 2022-09-26 | 03/30/2022 | 988362.77 | 0 | 2022-09-25 |  | 1
2024 | Region I | LA UNION | BANGAR (LA UNION) | P00844719LZ | Construction of Flood Mitigation Structure | 120.4195 | 16.9205 | 48999990.12 | 48999163.46 | 2024 | ARM-ASIA CONSTRUCTION & ENGINEERING | 160 | 2024 | 2024-09-10 | 03/27/2024 | 826.66 | 0 | 2024-11-12 | 63
2022 | Region III | TARLAC | CAMILING (TARLAC) | P00621161LZ | Construction of Flood Mitigation Structure | 120.4195 | 15.7475 | 289496487 | 289500000 | 2024 | BMK CONSTRUCTION CORPORATION (FORMERLY B.M.K. CONSTRUCTION) / ROYAL CROWN MONARCH CONSTRUCTION & SUPPLIES CORP. | 161 | 2022 | 2024-02-19 | 07/25/2022 | 0 | 3513 | 2024-02-18 |  | 1
2024 | Region III | BATAAN | HERMOSA (BATAAN) | P00823396LZ | Construction of Revetment | 120.4202 | 14.8453 | 96499998.25 | 96499998.25 | 2024 | M.C.J. VALENZUELA CONSTRUCTION ENTERPRISES | 162 | 2024 | 2024-12-09 | 04/23/2024 | 0 | 0 | 2025-01-01 | 23
2024 | Region I | ILOCOS SUR | CITY OF CANDON (ILOCOS SUR) | P00823296LZ | Construction of Revetment | 120.4202 | 17.2044 | 43120000 | 41782461.14 | 2025 | FIRST NORTHWAY DEVELOPMENT & CONSTRUCTION CORP. | 163 | 2024 | 2025-02-03 | 04/24/2024 | 1337538.86 | 0 | 2024-11-07 |  | 88
2024 | Region I | PANGASINAN | MALASIQUI (PANGASINAN) | P00820729LZ | Construction of Flood Mitigation Structure | 120.421 | 15.925 | 49000000 | 47699899.6 | 2024 | BET CONSTRUCTION & SUPPLY / RIEMAR CONSTRUCTION | 164 | 2024 | 2024-04-17 | 02/06/2024 | 1300100.4 | 0 | 2024-08-22 | 127
2022 | Region III | TARLAC | CAMILING (TARLAC) | P00621567LZ | Construction of Slope Protection Structure | 120.4217 | 15.7058 | 96500000 | 93624301.65 | 2022 | IM CONSTRUCTION CORPORATION | 165 | 2022 | 2022-11-22 | 03/24/2022 | 2875698.35 | 0 | 2022-11-21 |  | 1
2022 | Region III | TARLAC | CAMILING (TARLAC) | P00621092LZ | Construction of Flood Mitigation Structure | 120.4219 | 15.712 | 49000000 | 48019463.48 | 2022 | R.R. RICAFORT CONSTRUCTION AND SUPPLIES | 166 | 2022 | 2022-09-25 | 01/28/2022 | 980536.52 | 0 | 2022-09-24 |  | 1
2022 | Region III | TARLAC | CAMILING (TARLAC) | P00637029LZ | Construction of Flood Mitigation Structure | 120.4222 | 15.7524 | 96500000 | 94473500 | 2023 | ROYAL CROWN MONARCH CONSTRUCTION & SUPPLIES CORP. | 167 | 2022 | 2023-03-28 | 03/30/2022 | 2026500 | 0 | 2023-03-27 |  | 1
2023 | Region I | PANGASINAN | MALASIQUI (PANGASINAN) | P00726067LZ | Construction of Flood Mitigation Structure | 120.4226 | 15.9262 | 19600000 | 19591606.43 | 2023 | JEUSMACK BUILDERS & CONSTRUCTION SUPPLY | 168 | 2023 | 2023-04-17 | 02/13/2023 | 8393.57 | 0 | 2023-07-24 | 98
2022 | Region III | TARLAC | CAPAS (TARLAC) | P00621574LZ | Construction of Dike | 120.4226 | 15.3198 | 96499871.83 | 94757810.2 | 2022 | FLORDES CONSTRUCTION & TRADING CORP. (FORMERLY FLO | 169 | 2022 | 2022-11-24 | 03/26/2022 | 1742061.63 | 0 | 2022-11-23 |  | 1
2023 | Region I | PANGASINAN | MALASIQUI (PANGASINAN) | P00737425LZ | Construction of Flood Mitigation Structure | 120.4232 | 15.9262 | 9900000 | 9610913.73 | 2023 | JEUSMACK BUILDERS & CONSTRUCTION SUPPLY | 170 | 2023 | 2023-06-19 | 05/12/2023 | 289086.27 | 0 | 2023-08-15 | 57
2022 | Region III | TARLAC | CAMILING (TARLAC) | P00637018LZ | Construction of Slope Protection Structure | 120.4233 | 15.7277 | 96500000 | 94859500.09 | 2022 | ROYAL CROWN MONARCH CONSTRUCTION & SUPPLIES CORP. | 171 | 2022 | 2022-11-28 | 03/30/2022 | 1640499.91 | 0 | 2022-11-27 |  | 1
2024 | Region I | LA UNION | TUBAO (LA UNION) | P00845905LZ | Construction of Flood Mitigation Structure | 120.4233 | 16.3448 | 29699998.12 | 29694079.43 | 2025 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | 172 | 2024 | 2025-03-16 | 02/27/2024 | 5918.69 | 0 | 2024-08-18 |  | 210
2022 | Region I | ILOCOS SUR | SANTA (ILOCOS SUR) | P00642731LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.4237 | 17.4989 | 28950000 | 28341642.04 | 2023 | M.G. LUALHATI CONSTRUCTION CORP. | 173 | 2022 | 2023-04-23 | 09/28/2022 | 608357.96 | 0 | 2023-04-22 |  | 1
2024 | Region I | LA UNION | BANGAR (LA UNION) | P00821467LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.4237 | 16.9098 | 48250000 | 48249960.93 | 2024 | AMETHYST HORIZON BUILDERS AND GEN. CONTRACTOR AND DEVELOPMENT CORP. | 174 | 2024 | 2024-09-05 | 04/19/2024 | 39.07 | 0 | 2024-10-18 | 43
2023 | Region I | ILOCOS SUR | CITY OF CANDON (ILOCOS SUR) | P00727083LZ | Construction of Flood Mitigation Structure | 120.4237 | 17.2066 | 49000000 | 47492773.91 | 2024 | NORTH TECH BUILDERS AND CONSTRUCTION SUPPLY | 175 | 2023 | 2024-05-30 | 04/17/2023 | 1507226.09 | 0 | 2023-09-09 |  | 264
2024 | Region I | LA UNION | LUNA (LA UNION) | P00820128LZ | Construction of Flood Mitigation Structure | 120.4237 | 16.8497 | 84262316.12 | 82971637.15 | 2024 | ALPHA & OMEGA GEN. CONTRACTOR & DEVELOPMENT CORP. | 176 | 2024 | 2024-04-29 | 02/14/2024 | 1290678.97 | 0 | 2024-12-19 | 234
2023 | Region I | ILOCOS SUR | SANTA (ILOCOS SUR) | P00726341LZ | Construction of Flood Mitigation Structure | 120.4239 | 17.5001 | 104220000 | 104218299.8 | 2024 | BET CONSTRUCTION & SUPPLY / M.G. LUALHATI CONSTRUCTION CORP. | 177 | 2023 | 2024-08-08 | 03/03/2023 | 1700.2 | 0 | 2024-08-14 | 6
2023 | Region I | PANGASINAN | SAN JACINTO (PANGASINAN) | P00726836LZ | Construction of Flood Mitigation Structure | 120.4242 | 16.0713 | 28950000 | 28946887.58 | 2023 | BET CONSTRUCTION & SUPPLY | 178 | 2023 | 2023-11-30 | 03/22/2023 | 3112.42 | 0 | 2023-12-27 | 27
2023 | Region III | TARLAC | CAMILING (TARLAC) | P00735972LZ | Construction of Flood Mitigation Structure | 120.4246 | 15.7278 | 64655000 | 62715307.43 | 2023 | ROYAL CROWN MONARCH CONSTRUCTION & SUPPLIES CORP. | 179 | 2023 | 2023-07-16 | 02/06/2023 | 1939692.57 | 0 | 2023-08-25 | 40
2022 | Region III | BATAAN | DINALUPIHAN (BATAAN) | P00621238LZ | Construction of Flood Mitigation Structure | 120.4246 | 14.8678 | 96499999.48 | 96499999.24 | 2023 | ROCKSTEEL CONSTRUCTION AND DEV'T CORPORATION / EGB CONSTRUCTION CORPORATION (FORMERLY: EGB CONSTRUCTION) | 180 | 2022 | 2023-04-15 | 07/05/2022 | 0.24 | 0 | 2023-04-17 | 2
2022 | Region III | TARLAC | CAMILING (TARLAC) | P00621084LZ | Construction of Flood Mitigation Structure | 120.4249 | 15.7168 | 49000000 | 48388239.68 | 2022 | A.C. SOLIVEN CONSTRUCTION & GENERAL MERCHANDISE | 181 | 2022 | 2022-08-10 | 03/23/2022 | 611760.32 | 0 | 2022-09-18 | 39
2023 | Region I | ILOCOS SUR | CITY OF CANDON (ILOCOS SUR) | P00742270LZ | Construction of Flood Mitigation Structure | 120.4251 | 17.1755 | 19800000 | 19205970.89 | 2024 | FIRST NORTHWAY DEVELOPMENT & CONSTRUCTION CORP. | 182 | 2023 | 2024-10-29 | 03/31/2023 | 594029.11 | 0 | 2023-08-07 |  | 449
2022 | Region I | ILOCOS SUR | TAGUDIN (ILOCOS SUR) | P00620939LZ | Construction of Flood Mitigation Structure | 120.4253 | 16.9113 | 19300000 | 19299963.13 | 2022 | POWER K CONSTRUCTION SUPPLY & SERVICES | 183 | 2022 | 2022-08-09 | 04/12/2022 | 36.87 | 0 | 2022-09-04 | 26
2023 | Region III | BATAAN | HERMOSA (BATAAN) | P00742310LZ | Construction of Flood Mitigation Structure | 120.4254 | 14.8465 | 4949998.84 | 4949998.84 | 2023 | JBI CONSTRUCTION | 184 | 2023 | 2023-11-16 | 08/22/2023 | 0 | 0 | 2023-11-19 | 3
2024 | Region I | LA UNION | TUBAO (LA UNION) | P00824839LZ | Construction of Flood Mitigation Structure | 120.4257 | 16.3491 | 19299998.89 | 19284998.86 | 2025 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | 185 | 2024 | 2025-03-16 | 05/07/2024 | 15000.03 | 0 | 2024-10-13 |  | 154
2024 | Region I | ILOCOS SUR | SANTA (ILOCOS SUR) | P00844712LZ | Construction of Flood Mitigation Structure | 120.4261 | 17.4917 | 34300000 | 34299950.55 | 2024 | M.V. SABALBURO CONSTRUCTION AND SUPPLY | 186 | 2024 | 2024-10-01 | 02/28/2024 | 49.45 | 0 | 2024-07-16 |  | 77
2022 | Region I | ILOCOS SUR | CITY OF CANDON (ILOCOS SUR) | P00641929LZ | Construction of Flood Mitigation Structure | 120.4272 | 17.1671 | 24500000 | 24498030.54 | 2023 | FIRST NORTHWAY DEVELOPMENT & CONSTRUCTION CORP. | 187 | 2022 | 2023-08-30 | 04/04/2022 | 1969.46 | 0 | 2022-11-12 |  | 291
2022 | Region IV-B | OCCIDENTAL MINDORO | PALUAN (OCCIDENTAL MINDORO) | P00640563LZ | Construction of Slope Protection Structure | 120.428 | 13.4261 | 49500000 | 46063691.36 | 2023 | HI-TONE CONSTRUCTION & DEVELOPMENT CORP. (FORMERLY | 188 | 2022 | 2023-02-28 | 04/11/2022 | 3436308.64 | 0 | 2022-12-05 |  | 85
2023 | Region I | PANGASINAN | SAN JACINTO (PANGASINAN) | P00726835LZ | Construction of Flood Mitigation Structure | 120.4281 | 16.0709 | 48250000 | 48247153.84 | 2024 | BET CONSTRUCTION & SUPPLY | 189 | 2023 | 2024-01-18 | 03/22/2023 | 2846.16 | 0 | 2024-01-17 |  | 1
2023 | Region I | PANGASINAN | SAN JACINTO (PANGASINAN) | P00742278LZ | Construction of Slope Protection Structure | 120.4285 | 16.0738 | 21780000 | 21774296.02 | 2023 | ZOTA TRADING & CONSTRUCTION | 190 | 2023 | 2023-08-14 | 04/03/2023 | 5703.98 | 0 | 2023-09-16 | 33
2022 | Region III | BATAAN | DINALUPIHAN (BATAAN) | P00620503LZ | Construction of Flood Mitigation Structure | 120.4286 | 14.8433 | 23956099.8 | 23956086.13 | 2022 | M.C.J. VALENZUELA CONSTRUCTION ENTERPRISES | 191 | 2022 | 2022-07-25 | 02/21/2022 | 13.67 | 0 | 2022-07-26 | 1
2022 | Region III | TARLAC | CAMILING (TARLAC) | P00631268LZ | Construction of Flood Mitigation Structure | 120.4286 | 15.7203 | 29400000 | 28767900.51 | 2022 | GJE BUILDERS CORPORATION (FORMERLY: GJE BUILDERS) | 192 | 2022 | 2022-07-23 | 02/14/2022 | 632099.49 | 0 | 2022-07-22 |  | 1
2023 | Region III | BATAAN | HERMOSA (BATAAN) | P00726712LZ | Construction of Flood Mitigation Structure | 120.4287 | 14.845 | 29007996.56 | 29007996.56 | 2023 | PASCAL CONSTRUCTION | 193 | 2023 | 2023-09-25 | 02/20/2023 | 0 | 0 | 2023-09-25 | 0
2024 | Region I | LA UNION | TUBAO (LA UNION) | P00821096LZ | Construction of Flood Mitigation Structure | 120.4287 | 16.3565 | 144750000 | 144749737 | 2024 | RODEKOM GENERAL CONSTRUCTION AND ENTERPRISE | 194 | 2024 | 2024-07-26 | 03/15/2024 | 263 | 0 | 2025-01-10 | 168
2024 | Region I | LA UNION | NAGUILIAN (LA UNION) | P00823290LZ | Construction of Flood Mitigation Structure | 120.429 | 16.5148 | 115800000 | 115799805.6 | 2024 | MG SAMIDAN CONSTRUCTION | 195 | 2024 | 2024-11-11 | 05/13/2024 | 194.4 | 0 | 2025-02-11 | 92
2022 | Region I | ILOCOS SUR | SANTO DOMINGO (ILOCOS SUR) | P00620778LZ | Construction of Flood Mitigation Structure | 120.429 | 17.6258 | 93100000 | 91675000 | 2022 | A.P.B. CONSTRUCTION | 196 | 2022 | 2022-10-21 | 02/24/2022 | 1425000 | 0 | 2022-10-20 |  | 1
2024 | Region I | LA UNION | BALAOAN (LA UNION) | P00843205LZ | Construction of Flood Mitigation Structure | 120.4291 | 16.8333 | 96500000 | 96492408.53 | 2024 | SILVERWOLVES CONSTRUCTION CORPORATION | 197 | 2024 | 2024-12-29 | 05/03/2024 | 7591.47 | 0 | 2024-12-28 |  | 1
2023 | Region I | LA UNION | TUBAO (LA UNION) | P00726335LZ | Construction of Flood Mitigation Structure | 120.4294 | 16.3565 | 144750000 | 144720639.7 | 2023 | RODEKOM GENERAL CONSTRUCTION AND ENTERPRISE | 198 | 2023 | 2023-11-13 | 02/14/2023 | 29360.3 | 0 | 2024-01-12 | 60
2022 | Region I | ILOCOS SUR | SANTA (ILOCOS SUR) | P00621513LZ | Construction of Flood Mitigation Structure | 120.4295 | 17.5483 | 19600000 | 19004737.39 | 2022 | M.V. SABALBURO CONSTRUCTION AND SUPPLY | 199 | 2022 | 2022-08-02 | 04/04/2022 | 595262.61 | 0 | 2022-08-01 |  | 1
2022 | Region III | TARLAC | CAMILING (TARLAC) | P00621569LZ | Construction of Slope Protection Structure | 120.4296 | 15.7251 | 96500000 | 93605000 | 2022 | ROYAL CROWN MONARCH CONSTRUCTION & SUPPLIES CORP. | 200 | 2022 | 2022-11-22 | 03/24/2022 | 2895000 | 0 | 2022-11-21 |  | 1
2022 | Region I | ILOCOS SUR | CABUGAO (ILOCOS SUR) | P00640494LZ | Construction of Flood Mitigation Structure | 120.4578 | 17.7966 | 4950000 | 4950000 | 2022 | R.B. PANO CONSTRUCTION CORP. (FORMERLY: R.B. PANO CONSTRUCTION AND SUPPLY) | 201 | 2022 | 2022-08-19 | 04/08/2022 | 0 | 0 | 2022-08-07 |  | 12
2022 | Region I | ILOCOS SUR | SANTA MARIA (ILOCOS SUR) | P00620787LZ | Construction of Flood Mitigation Structure | 120.4579 | 17.3881 | 29400000 | 28949952.43 | 2023 | 739 BUILDERS | 202 | 2022 | 2023-05-15 | 10/25/2022 | 450047.57 | 0 | 2023-07-03 | 49
2023 | Region I | PANGASINAN | MAPANDAN (PANGASINAN) | P00726070LZ | Construction of Flood Mitigation Structure | 120.4581 | 16.0306 | 19600000 | 19221664.9 | 2023 | JEUSMACK BUILDERS & CONSTRUCTION SUPPLY | 203 | 2023 | 2023-04-18 | 02/13/2023 | 378335.1 | 0 | 2023-07-24 | 97
2024 | Region I | ILOCOS SUR | SAN JUAN (LAPOG) (ILOCOS SUR) | P00823312LZ | Construction of Flood Mitigation Structure | 120.4582 | 17.7367 | 83300000 | 82004907.35 | 2024 | FIT CONSTRUCTION | 204 | 2024 | 2024-08-27 | 03/05/2024 | 1295092.65 | 0 | 2024-09-16 | 20
2022 | Region III | BATAAN | MARIVELES (BATAAN) | P00631172LZ | Construction of Flood Mitigation Structure | 120.4582 | 14.449 | 9799999.45 | 9800000 | 2022 | AJA BUILDERS | 205 | 2022 | 2022-08-04 | 03/18/2022 | 0 | 0.55 | 2022-08-03 |  | 1
2022 | Region I | ILOCOS SUR | CITY OF CANDON (ILOCOS SUR) | P00632739LZ | Construction of Slope Protection Structure | 120.4585 | 17.204 | 29700000 | 29695852.29 | 2023 | FIRST NORTHWAY DEVELOPMENT & CONSTRUCTION CORP. | 206 | 2022 | 2023-03-29 | 04/04/2022 | 4147.71 | 0 | 2022-11-02 |  | 147
2022 | Region I | ILOCOS SUR | CITY OF CANDON (ILOCOS SUR) | P00639421LZ | Construction of Flood Mitigation Structure | 120.4586 | 17.2036 | 29400000 | 28517340.06 | 2023 | FIRST NORTHWAY DEVELOPMENT & CONSTRUCTION CORP. | 207 | 2022 | 2023-09-20 | 05/19/2022 | 882659.94 | 0 | 2022-11-28 |  | 296
2023 | Region I | ILOCOS SUR | CITY OF CANDON (ILOCOS SUR) | P00727074LZ | Construction of Flood Mitigation Structure | 120.4589 | 17.2338 | 24500000 | 23764976.32 | 2024 | FIRST NORTHWAY DEVELOPMENT & CONSTRUCTION CORP. | 208 | 2023 | 2024-03-12 | 05/11/2023 | 735023.68 | 0 | 2023-09-20 |  | 174
2023 | Region III | TARLAC | CAPAS (TARLAC) | P00726906LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.46 | 15.3714 | 72374261.77 | 72367030.12 | 2023 | 11-16 CONSTRUCTION | 209 | 2023 | 2023-12-15 | 04/18/2023 | 7231.65 | 0 | 2023-12-14 |  | 1
2023 | Region I | ILOCOS SUR | BANTAY (ILOCOS SUR) | P00727065LZ | Construction of Flood Mitigation Structure | 120.46 | 17.6063 | 39200000 | 39200000 | 2024 | SJ MILLENNIUM CONSTRUCTION AND CONSTRUCTION SUPPLY CORPORATION / EGB CONSTRUCTION CORPORATION (FORMERLY: EGB CONSTRUCTION) | 210 | 2023 | 2024-05-05 | 04/27/2023 | 0 | 0 | 2024-05-04 |  | 1
2024 | Region I | PANGASINAN | MALASIQUI (PANGASINAN) | P00845916LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.46 | 15.895 | 54450000 | 9807797.77 | 2024 | MIGHTYWAY CONSTRUCTION AND SUPPLY | 211 | 2024 | 2024-09-11 | 06/03/2024 | 44642202.23 | 0 | 2024-11-18 | 68
2024 | Region I | PANGASINAN | MALASIQUI (PANGASINAN) | P00845923LZ | Construction of Flood Mitigation Structure | 120.46 | 15.895 | 54450000 | 24120025.11 | 2024 | MIGHTYWAY CONSTRUCTION AND SUPPLY | 212 | 2024 | 2024-09-11 | 06/03/2024 | 30329974.89 | 0 | 2024-11-18 | 68
2023 | Region I | ILOCOS SUR | BANTAY (ILOCOS SUR) | P00727062LZ | Construction of Flood Mitigation Structure | 120.46 | 17.6224 | 24500000 | 24500000 | 2023 | SJ MILLENNIUM CONSTRUCTION AND CONSTRUCTION SUPPLY CORPORATION | 213 | 2023 | 2023-12-10 | 04/27/2023 | 0 | 0 | 2023-12-09 |  | 1
2022 | Region I | ILOCOS SUR | SANTA MARIA (ILOCOS SUR) | P00620788LZ | Construction of Flood Mitigation Structure | 120.4601 | 17.3865 | 29400000 | 28949536.8 | 2023 | M.A. TEJADA CONSTRUCTION | 214 | 2022 | 2023-03-15 | 11/03/2022 | 450463.2 | 0 | 2023-04-03 | 19
2024 | Region I | LA UNION | PUGO (LA UNION) | P00821480LZ | Construction of Flood Mitigation Structure | 120.4608 | 16.3192 | 48250000 | 48249567.54 | 2025 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | 215 | 2024 | 2025-02-26 | 06/10/2024 | 432.46 | 0 | 2025-03-27 | 29
2021 | Region III | TARLAC |  | P00526418LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.461 | 15.3709 | 29399567.7 | 29388967.02 | 2022 | 11-16 CONSTRUCTION | 216 | 2021 | 2022-08-16 | 03/24/2022 | 10600.68 | 0 | 2022-08-15 |  | 1
2024 | Region I | PANGASINAN | BAYAMBANG (PANGASINAN) | P00821514LZ | Construction of Flood Mitigation Structure | 120.461 | 15.744 | 49000000 | 48125303.6 | 2024 | RS RODRIGUEZ CONSTRUCTION & SUPPLIES / HIGH ROCK CONSTRUCTION AND SUPPLIES INCORPORATED | 217 | 2024 | 2024-04-08 | 02/06/2024 | 874696.4 | 0 | 2024-08-22 | 136
2022 | Region I | PANGASINAN | SAN JACINTO (PANGASINAN) | P00621272LZ | Construction of Flood Mitigation Structure | 120.4613 | 16.1171 | 96500000 | 96498788.06 | 2023 | TG SURCON BUILDERS INC. / FRAMECON BUILDERS | 218 | 2022 | 2023-06-03 | 04/07/2022 | 1211.94 | 0 | 2023-06-02 |  | 1
2023 | Region I | PANGASINAN | MALASIQUI (PANGASINAN) | P00726069LZ | Construction of Flood Mitigation Structure | 120.4614 | 15.8941 | 19600000 | 19207862.6 | 2023 | EXTENSIVE STEEL WORKS AND CONSTRUCTION | 219 | 2023 | 2023-05-12 | 02/13/2023 | 392137.4 | 0 | 2023-07-24 | 73
2023 | Region I | PANGASINAN | BAYAMBANG (PANGASINAN) | P00727337LZ | Construction of Flood Mitigation Structure | 120.4616 | 15.7454 | 19600000 | 19011840.59 | 2023 | HIGH ROCK CONSTRUCTION AND SUPPLIES INCORPORATED | 220 | 2023 | 2023-07-17 | 06/02/2023 | 588159.41 | 0 | 2023-11-10 | 116
2022 | Region I | ILOCOS SUR | SANTA MARIA (ILOCOS SUR) | P00620789LZ | Construction of Flood Mitigation Structure | 120.4617 | 17.3844 | 29400000 | 28949795.51 | 2023 | MRK-SQUARE CONSTRUCTION AND SUPPLY | 221 | 2022 | 2023-03-26 | 10/25/2022 | 450204.49 | 0 | 2023-03-25 |  | 1
2022 | Region I | PANGASINAN | MALASIQUI (PANGASINAN) | P00637768LZ | Construction of Revetment | 120.4618 | 15.8937 | 9900000 | 9899961.42 | 2022 | JEUSMACK BUILDERS & CONSTRUCTION SUPPLY | 222 | 2022 | 2022-08-12 | 03/24/2022 | 38.58 | 0 | 2022-08-11 |  | 1
2023 | Region I | PANGASINAN | BAYAMBANG (PANGASINAN) | P00727336LZ | Construction of Flood Mitigation Structure | 120.4618 | 15.7462 | 49000000 | 18983001.6 | 2023 | BET CONSTRUCTION & SUPPLY / JEUSMACK BUILDERS & CONSTRUCTION SUPPLY | 223 | 2023 | 2023-12-18 | 06/21/2023 | 30016998.4 | 0 | 2024-02-17 | 61
2024 | Region I | PANGASINAN | SAN JACINTO (PANGASINAN) | P00820129LZ | Construction of Flood Mitigation Structure | 120.4619 | 16.1156 | 77200000 | 77197170.06 | 2024 | BET CONSTRUCTION & SUPPLY | 224 | 2024 | 2024-07-12 | 02/26/2024 | 2829.94 | 0 | 2024-11-10 | 121
2023 | Region III | TARLAC | CAPAS (TARLAC) | P00726907LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.462 | 15.3739 | 72374946.37 | 72369873.3 | 2023 | 11-16 CONSTRUCTION | 225 | 2023 | 2023-12-15 | 04/18/2023 | 5073.07 | 0 | 2023-12-14 |  | 1
2022 | Region I | ILOCOS SUR | SANTIAGO (ILOCOS SUR) | P00632735LZ | Construction of Flood Mitigation Structure | 120.4622 | 17.2457 | 4900000 | 4897213.84 | 2023 | FIRST NORTHWAY DEVELOPMENT & CONSTRUCTION CORP. | 226 | 2022 | 2023-01-30 | 02/24/2022 | 2786.16 | 0 | 2022-06-09 |  | 235
2022 | Region I | ILOCOS SUR | BANTAY (ILOCOS SUR) | P00620938LZ | Construction of Flood Mitigation Structure | 120.4627 | 17.6171 | 24500000 | 24500000 | 2022 | SJ MILLENNIUM CONSTRUCTION AND CONSTRUCTION SUPPLY CORPORATION | 227 | 2022 | 2022-07-22 | 02/14/2022 | 0 | 0 | 2022-07-23 | 1
2023 | Region I | LA UNION | PUGO (LA UNION) | P00726641LZ | Construction of Flood Mitigation Structure | 120.4635 | 16.3169 | 48999998.49 | 48607982.24 | 2024 | A.I.P. CONSTRUCTION | 228 | 2023 | 2024-02-11 | 01/31/2023 | 392016.25 | 0 | 2023-07-18 |  | 208
2024 | Region I | LA UNION | BALAOAN (LA UNION) | P00838507LZ | Construction of Flood Mitigation Structure | 120.4649 | 16.8175 | 28950000 | 28947643.81 | 2024 | JMBM CONSTRUCTION | 229 | 2024 | 2024-06-04 | 04/08/2024 | 2356.19 | 0 | 2024-10-11 | 129
2022 | Region III | TARLAC | CAPAS (TARLAC) | P00639486LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.465 | 15.3728 | 48999809.37 | 48953097.08 | 2022 | 11-16 CONSTRUCTION | 230 | 2022 | 2022-10-16 | 03/24/2022 | 46712.29 | 0 | 2022-10-15 |  | 1
2024 | Region I | PANGASINAN | BAYAMBANG (PANGASINAN) | P00825215LZ | Construction of Flood Mitigation Structure | 120.466 | 15.82 | 39200000 | 9533441.56 | 2024 | HIGH ROCK CONSTRUCTION AND SUPPLIES INCORPORATED / JHI CONSTRUCTION & SUPPLY | 231 | 2024 | 2024-08-05 | 05/06/2024 | 29666558.44 | 0 | 2024-10-14 | 70
2023 | Region III | TARLAC | CITY OF TARLAC (CAPITAL) (TARLAC) | P00725734LZ | Construction of Flood Mitigation Structure | 120.4661 | 15.6179 | 72375000 | 70203779.61 | 2023 | ROYAL CROWN MONARCH CONSTRUCTION & SUPPLIES CORP. | 232 | 2023 | 2023-06-15 | 02/06/2023 | 2171220.39 | 0 | 2023-09-04 | 81
2024 | Region I | PANGASINAN | MALASIQUI (PANGASINAN) | P00821512LZ | Construction of Flood Mitigation Structure | 120.467 | 15.853 | 49000000 | 48999982.32 | 2024 | J.G. GARCIA CONSTRUCTION & SUPPLY (FOR: J.G. GARCIA CONST.) | 233 | 2024 | 2024-05-08 | 02/06/2024 | 17.68 | 0 | 2024-08-22 | 106
2023 | Region I | ILOCOS SUR | CABUGAO (ILOCOS SUR) | P00726049LZ | Construction of Flood Mitigation Structure | 120.4679 | 17.798 | 29400000 | 29400000 | 2023 | N.A. IBARRA CONSTRUCTION(FOR. DIOCLETIANS CONST.) | 234 | 2023 | 2023-12-15 | 04/27/2023 | 0 | 0 | 2023-12-15 | 0
2023 | Region I | LA UNION | PUGO (LA UNION) | P00737417LZ | Construction of Flood Mitigation Structure | 120.468 | 16.3088 | 4949987.72 | 4946717.84 | 2023 | E.E. MADAYAG CONSTRUCTION | 235 | 2023 | 2023-06-05 | 02/06/2023 | 3269.88 | 0 | 2023-04-27 |  | 39
2022 | Region III | BATAAN | HERMOSA (BATAAN) | P00620507LZ | Construction of Flood Mitigation Structure | 120.4681 | 14.8594 | 48999999.6 | 48999999.6 | 2023 | PASCAL CONSTRUCTION | 236 | 2022 | 2023-02-01 | 04/11/2022 | 0 | 0 | 2023-02-07 | 6
2023 | Region I | PANGASINAN | MALASIQUI (PANGASINAN) | P00737431LZ | Construction of Flood Mitigation Structure | 120.4681 | 15.8524 | 13860000 | 13546760.75 | 2023 | 2-R CONSTRUCTION SUPPLY | 237 | 2023 | 2023-09-27 | 05/12/2023 | 313239.25 | 0 | 2023-09-26 |  | 1
2024 | Region III | PAMPANGA | FLORIDABLANCA (PAMPANGA) | P00846004LZ | Construction of Slope Protection Structure | 120.4684 | 14.9453 | 14849528.4 | 14844483.15 | 2024 | 120 OVER CONSTRUCTION CO. | 238 | 2024 | 2024-05-20 | 03/18/2024 | 5045.25 | 0 | 2024-07-29 | 70
2024 | Region I | PANGASINAN | BAYAMBANG (PANGASINAN) | P00821515LZ | Construction of Flood Mitigation Structure | 120.469 | 15.76 | 49000000 | 48999990.55 | 2024 | ALCEL CONSTRUCTION | 239 | 2024 | 2024-08-27 | 02/23/2024 | 9.45 | 0 | 2024-09-08 | 12
2022 | Region IV-B | OCCIDENTAL MINDORO | PALUAN (OCCIDENTAL MINDORO) | P00621623LZ | Construction of Flood Mitigation Structure | 120.4692 | 13.4274 | 49000000 | 46100036.07 | 2023 | HI-TONE CONSTRUCTION & DEVELOPMENT CORP. (FORMERLY | 240 | 2022 | 2023-03-15 | 05/30/2022 | 2899963.93 | 0 | 2023-01-29 |  | 45
2024 | Region I | ILOCOS SUR | CITY OF CANDON (ILOCOS SUR) | P00824651LZ | Construction of Revetment | 120.4696 | 17.2344 | 49000000 | 48989188.24 | 2024 | NORTH TECH BUILDERS AND CONSTRUCTION SUPPLY | 241 | 2024 | 2024-06-25 | 03/14/2024 | 10811.76 | 0 | 2024-08-06 | 42
2024 | Region III | BATAAN | HERMOSA (BATAAN) | P00820801LZ | Construction of Revetment | 120.4699 | 14.8568 | 48999999.85 | 48999999.85 | 2024 | PASCAL CONSTRUCTION | 242 | 2024 | 2024-12-26 | 02/21/2024 | 0 | 0 | 2024-12-31 | 5
2024 | Region I | ILOCOS SUR | SAN ESTEBAN (ILOCOS SUR) | P00824650LZ | Construction of Flood Mitigation Structure | 120.4703 | 17.3119 | 29400000 | 29399480.08 | 2024 | MRK-SQUARE CONSTRUCTION AND SUPPLY | 243 | 2024 | 2024-09-13 | 03/06/2024 | 519.92 | 0 | 2024-07-02 |  | 73
2023 | Region IV-B | OCCIDENTAL MINDORO | PALUAN (OCCIDENTAL MINDORO) | P00725871LZ | Construction of Flood Mitigation Structure | 120.4705 | 13.3895 | 96500000 | 96492142.55 | 2024 | F.A. TORRES CONSTRUCTION / C.T. LEONCIO CONSTRUCTION & TRADING | 244 | 2023 | 2024-04-23 | 05/02/2023 | 7857.45 | 0 | 2024-04-22 |  | 1
2024 | Region III | TARLAC | CAPAS (TARLAC) | P00823375LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.4714 | 15.3493 | 96499769.92 | 95527152.18 | 2024 | RD8 BUILDERS CORPORATION UNDER THE NAME OF RD8 BUILDERS | 245 | 2024 | 2024-11-12 | 07/02/2024 | 972617.74 | 0 | 2024-12-31 | 49
2023 | Region I | ILOCOS SUR | SANTA MARIA (ILOCOS SUR) | P00726359LZ | Construction of Flood Mitigation Structure | 120.4715 | 17.3819 | 48250000 | 46808283.34 | 2024 | MBB CONSTRUCTION AND SUPPLY (FORMERLY: MBB CONSTRUCTION) | 246 | 2023 | 2024-12-02 | 04/05/2023 | 1441716.66 | 0 | 2023-10-26 |  | 403
2022 | Region III | PAMPANGA | FLORIDABLANCA (PAMPANGA) | P00637779LZ | Construction of Slope Protection Structure | 120.4716 | 14.9423 | 19799675.86 | 19794566.45 | 2022 | R.M. VITUG CONSTRUCTION | 247 | 2022 | 2022-07-06 | 04/13/2022 | 5109.41 | 0 | 2022-09-08 | 64
2022 | Region I | ILOCOS SUR | NARVACAN (ILOCOS SUR) | P00621525LZ | Construction of Flood Mitigation Structure | 120.4724 | 17.42 | 9800000 | 9505483.78 | 2023 | M.A. TEJADA CONSTRUCTION | 248 | 2022 | 2023-04-06 | 04/04/2022 | 294516.22 | 0 | 2022-06-24 |  | 286
2022 | Region III | BATAAN | DINALUPIHAN (BATAAN) | P00620504LZ | Construction of Flood Mitigation Structure | 120.4731 | 14.8533 | 48999997.98 | 48999998.32 | 2022 | PASCAL CONSTRUCTION | 249 | 2022 | 2022-11-10 | 04/08/2022 | 0 | 0.34 | 2022-11-12 | 2
2024 | Region I | LA UNION | ROSARIO (LA UNION) | P00843190LZ | Construction of Flood Mitigation Structure | 120.4732 | 16.214 | 115800000 | 115799701.5 | 2024 | UNIVERSAL DE LEON CONSTRUCTION AND AGGREGATES | 250 | 2024 | 2024-08-19 | 05/03/2024 | 298.5 | 0 | 2024-12-21 | 124
2023 | Region I | PANGASINAN | MALASIQUI (PANGASINAN) | P00737433LZ | Construction of Flood Mitigation Structure | 120.4732 | 15.928 | 4950000 | 4840512.64 | 2023 | ROCKWELL CONSTRUCTION AND SUPPLY | 251 | 2023 | 2023-07-17 | 03/28/2023 | 109487.36 | 0 | 2023-09-14 | 59
2023 | Region I | ILOCOS SUR | SANTA MARIA (ILOCOS SUR) | P00726360LZ | Construction of Flood Mitigation Structure | 120.4735 | 17.3861 | 48250000 | 46807469.14 | 2024 | MBB CONSTRUCTION AND SUPPLY (FORMERLY: MBB CONSTRUCTION) | 252 | 2023 | 2024-12-02 | 04/05/2023 | 1442530.86 | 0 | 2023-10-26 |  | 403
2022 | Region I | ILOCOS NORTE | BADOC (ILOCOS NORTE) | P00632727LZ | Construction of Drainage Structure | 120.4738 | 17.9266 | 4900000 | 4900000 | 2022 | BADOC BUILDERS & SUPPLY, INC. (FORMERLY: BADOC BUILDER & SUPPLY | 253 | 2022 | 2022-07-09 | 02/11/2022 | 0 | 0 | 2022-07-08 |  | 1
2023 | Region III | BATAAN | CITY OF BALANGA (CAPITAL) (BATAAN) | P00737451LZ | Construction of Flood Mitigation Structure | 120.4743 | 14.6357 | 9900000 | 9900000 | 2023 | E.R. VENZON CONSTRUCTION | 254 | 2023 | 2023-05-24 | 02/08/2023 | 0 | 0 | 2023-05-27 | 3
2024 | Region IV-B | OCCIDENTAL MINDORO | PALUAN (OCCIDENTAL MINDORO) | P00820400LZ | Construction of Flood Mitigation Structure | 120.4744 | 13.3941 | 96500000 | 96496449.5 | 2024 | JIIK CONSTRUCTION SERVICES | 255 | 2024 | 2024-09-15 | 04/05/2024 | 3550.5 | 0 | 2025-02-26 | 164
2022 | Region III | BATAAN | PILAR (BATAAN) | P00621486LZ | Construction of Flood Mitigation Structure | 120.4745 | 14.6285 | 49000000 | 49000000 | 2023 | ORACLE CONCRETE AND CONSTRUCTION CORP. / ALCEL CONSTRUCTION | 256 | 2022 | 2023-04-26 | 05/26/2022 | 0 | 0 | 2023-04-25 |  | 1
2022 | Region I | ILOCOS SUR | BANAYOYO (ILOCOS SUR) | P00640495LZ | Construction of Flood Mitigation Structure | 120.4746 | 17.2336 | 19800000 | 19799995.98 | 2023 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | 257 | 2022 | 2023-04-05 | 04/04/2022 | 4.02 | 0 | 2022-09-09 |  | 208
2022 | Region III | BATAAN | DINALUPIHAN (BATAAN) | P00620505LZ | Construction of Flood Mitigation Structure | 120.476 | 14.852 | 48999999.85 | 48999999.85 | 2022 | PASCAL CONSTRUCTION | 258 | 2022 | 2022-12-12 | 04/08/2022 | 0 | 0 | 2022-12-13 | 1
2022 | Region III | BATAAN | HERMOSA (BATAAN) | P00620506LZ | Construction of Flood Mitigation Structure | 120.4761 | 14.8517 | 48999999.42 | 48999999.42 | 2022 | PASCAL CONSTRUCTION | 259 | 2022 | 2022-11-08 | 04/08/2022 | 0 | 0 | 2022-11-09 | 1
2022 | Region III | BATAAN | PILAR (BATAAN) | P00620169LZ | Construction of Flood Mitigation Structure | 120.4763 | 14.6318 | 93660970 | 93660970 | 2023 | BET CONSTRUCTION & SUPPLY | 260 | 2022 | 2023-02-07 | 03/14/2022 | 0 | 0 | 2023-02-06 |  | 1
2023 | Region I | ILOCOS NORTE | BADOC (ILOCOS NORTE) | P00725586LZ | Construction of Flood Mitigation Structure | 120.4764 | 17.9437 | 19300000 | 19299995.86 | 2023 | BADOC BUILDERS & SUPPLY, INC. (FORMERLY: BADOC BUILDER & SUPPLY | 261 | 2023 | 2023-06-30 | 02/14/2023 | 4.14 | 0 | 2023-07-03 | 3
2024 | Region I | LA UNION | PUGO (LA UNION) | P00821469LZ | Construction of Flood Mitigation Structure | 120.4766 | 16.3299 | 48999991.11 | 48655692.77 | 2025 | A.I.P. CONSTRUCTION | 262 | 2024 | 2025-02-16 | 02/12/2024 | 344298.34 | 0 | 2024-08-16 |  | 184
2022 | Cordillera Administrative Region | BENGUET | TUBA (BENGUET) | P00621001LZ | Construction of Flood Mitigation Structure | 120.478 | 16.4356 | 24500000 | 24113608.31 | 2022 | SEJ CONSTRUCTION & AGGREGATES | 263 | 2022 | 2022-08-05 | 01/31/2022 | 386391.69 | 0 | 2022-08-04 |  | 1
2022 | Region IV-B | OCCIDENTAL MINDORO | PALUAN (OCCIDENTAL MINDORO) | P00621624LZ | Construction of Flood Mitigation Structure | 120.478 | 13.4131 | 46060000 | 45141156.75 | 2023 | HI-TONE CONSTRUCTION & DEVELOPMENT CORP. (FORMERLY | 264 | 2022 | 2023-03-15 | 07/11/2022 | 918843.25 | 0 | 2023-02-03 |  | 40
2021 | Region III | PAMPANGA |  | P00525587LZ | Construction of Slope Protection Structure | 120.4783 | 14.981 | 55969179.22 | 55958985.69 | 2022 | R.M. VITUG CONSTRUCTION | 265 | 2021 | 2022-10-24 | 04/13/2022 | 10193.53 | 0 | 2022-10-23 |  | 1
2023 | Region III | PAMPANGA | FLORIDABLANCA (PAMPANGA) | P00740615LZ | Construction of Slope Protection Structure | 120.4789 | 14.8941 | 29399936.74 | 29394256.81 | 2023 | MJBZ BUILDERS AND TRADING | 266 | 2023 | 2023-10-23 | 04/17/2023 | 5679.93 | 0 | 2023-11-26 | 34
2023 | Region III | PAMPANGA | FLORIDABLANCA (PAMPANGA) | P00742351LZ | Construction of Slope Protection Structure | 120.4789 | 14.8938 | 28709344.15 | 28704277.87 | 2023 | RADIANS BUILDERS AND SUPPLY CORPORATION | 267 | 2023 | 2023-11-27 | 04/17/2023 | 5066.28 | 0 | 2023-11-26 |  | 1
2023 | Region III | PAMPANGA | FLORIDABLANCA (PAMPANGA) | P00742355LZ | Construction of Slope Protection Structure | 120.4792 | 14.8919 | 36629950.35 | 36624784.11 | 2023 | RADIANS BUILDERS AND SUPPLY CORPORATION | 268 | 2023 | 2023-11-27 | 04/17/2023 | 5166.24 | 0 | 2023-11-26 |  | 1
2023 | Region I | LA UNION | PUGO (LA UNION) | P00737416LZ | Construction of Flood Mitigation Structure | 120.4799 | 16.2944 | 4949997.64 | 4946964.09 | 2023 | E.E. MADAYAG CONSTRUCTION | 269 | 2023 | 2023-06-19 | 02/06/2023 | 3033.55 | 0 | 2023-04-27 |  | 53
2021 | Region I | ILOCOS SUR |  | P00525862LZ | Construction of Revetment | 120.4799 | 17.7881 | 19600000 | 19600000 | 2022 | R.B. PANO CONSTRUCTION CORP. (FORMERLY: R.B. PANO CONSTRUCTION AND SUPPLY) | 270 | 2021 | 2022-12-02 | 02/24/2022 | 0 | 0 | 2022-12-01 |  | 1
2024 | Region III | BATAAN | PILAR (BATAAN) | P00839574LZ | Construction of Flood Mitigation Structure | 120.4802 | 14.6363 | 5940000 | 5798658.09 | 2024 | LEBERN BUILDERS TRADING AND GENERAL SERVICES | 271 | 2024 | 2024-05-24 | 02/21/2024 | 141341.91 | 0 | 2024-05-23 |  | 1
2023 | Region I | PANGASINAN | MANAOAG (PANGASINAN) | P00727091LZ | Construction of Flood Mitigation Structure | 120.4809 | 16.0463 | 19600000 | 19595588.4 | 2023 | J.G. GARCIA CONSTRUCTION & SUPPLY (FOR: J.G. GARCIA CONST.) | 272 | 2023 | 2023-09-14 | 05/12/2023 | 4411.6 | 0 | 2023-10-15 | 31
2024 | Region I | PANGASINAN | BAYAMBANG (PANGASINAN) | P00821517LZ | Construction of Flood Mitigation Structure | 120.481 | 15.755 | 49000000 | 48999982.86 | 2024 | J.G. GARCIA CONSTRUCTION & SUPPLY (FOR: J.G. GARCIA CONST.) | 273 | 2024 | 2024-08-27 | 02/23/2024 | 17.14 | 0 | 2024-09-08 | 12
2023 | Region I | PANGASINAN | BAYAMBANG (PANGASINAN) | P00727339LZ | Construction of Flood Mitigation Structure | 120.4827 | 15.7552 | 49000000 | 9491153.3 | 2023 | BET CONSTRUCTION & SUPPLY / JEUSMACK BUILDERS & CONSTRUCTION SUPPLY | 274 | 2023 | 2023-12-18 | 06/21/2023 | 39508846.7 | 0 | 2024-02-17 | 61
2023 | Region III | PAMPANGA | FLORIDABLANCA (PAMPANGA) | P00742350LZ | Construction of Slope Protection Structure | 120.4828 | 14.8998 | 28709903.47 | 28704722.99 | 2023 | RADIANS BUILDERS AND SUPPLY CORPORATION | 275 | 2023 | 2023-11-27 | 04/17/2023 | 5180.48 | 0 | 2023-11-26 |  | 1
2022 | Region I | PANGASINAN | SISON (PANGASINAN) | P00631098LZ | Construction of Revetment | 120.4834 | 16.1642 | 49000000 | 48261362.1 | 2022 | W.J.P. CONSTRUCTION AND SUPPLY | 276 | 2022 | 2022-12-27 | 02/24/2022 | 738637.9 | 0 | 2022-09-02 |  | 116
2023 | Region I | PANGASINAN | MANAOAG (PANGASINAN) | P00727087LZ | Construction of Flood Mitigation Structure | 120.4837 | 16.0499 | 29400000 | 29392643.7 | 2024 | J.G. GARCIA CONSTRUCTION & SUPPLY (FOR: J.G. GARCIA CONST.) | 277 | 2023 | 2024-02-15 | 03/17/2023 | 7356.3 | 0 | 2024-03-23 | 37
2022 | Region III | BATAAN | DINALUPIHAN (BATAAN) | P00620500LZ | Construction of Flood Mitigation Structure | 120.4838 | 14.9138 | 24499999.72 | 24499999.72 | 2022 | VM BUILDERS CONSTRUCTION CORPORATION | 278 | 2022 | 2022-09-23 | 02/21/2022 | 0 | 0 | 2022-09-24 | 1
2024 | Region I | ILOCOS SUR | SINAIT (ILOCOS SUR) | P00820101LZ | Construction of Flood Mitigation Structure | 120.4846 | 17.8703 | 35370145 | 35065183.86 | 2024 | 739 BUILDERS | 279 | 2024 | 2024-09-06 | 02/14/2024 | 304961.14 | 0 | 2024-09-05 |  | 1
2022 | Region III | PAMPANGA | FLORIDABLANCA (PAMPANGA) | P00621458LZ | Construction of Slope Protection Structure | 120.4852 | 14.9023 | 48852777.44 | 48847004.76 | 2022 | R.M. VITUG CONSTRUCTION | 280 | 2022 | 2022-10-09 | 04/13/2022 | 5772.68 | 0 | 2022-10-08 |  | 1
2022 | Region I | ILOCOS SUR | BANTAY (ILOCOS SUR) | P00631069LZ | Construction of Flood Mitigation Structure | 120.4855 | 17.5562 | 49000000 | 49000000 | 2022 | SJ MILLENNIUM CONSTRUCTION AND CONSTRUCTION SUPPLY CORPORATION / EGB CONSTRUCTION CORPORATION (FORMERLY: EGB CONSTRUCTION) | 281 | 2022 | 2022-08-07 | 02/18/2022 | 0 | 0 | 2022-08-06 |  | 1
2024 | Region I | PANGASINAN | SANTA BARBARA (PANGASINAN) | P00821524LZ | Construction of Flood Mitigation Structure | 120.486 | 15.9825 | 48250000 | 48137413.02 | 2024 | J.G. GARCIA CONSTRUCTION & SUPPLY (FOR: J.G. GARCIA CONST.) | 282 | 2024 | 2024-09-20 | 04/19/2024 | 112586.98 | 0 | 2024-11-13 | 54
2022 | Region I | ILOCOS SUR | BANTAY (ILOCOS SUR) | P00631068LZ | Construction of Flood Mitigation Structure | 120.4865 | 17.5539 | 29400000 | 29400000 | 2022 | SJ MILLENNIUM CONSTRUCTION AND CONSTRUCTION SUPPLY CORPORATION | 283 | 2022 | 2022-12-16 | 02/10/2022 | 0 | 0 | 2022-11-20 |  | 26
2022 | Region I | ILOCOS SUR | NARVACAN (ILOCOS SUR) | P00620129LZ | Construction of Flood Mitigation Structure | 120.4874 | 17.4088 | 88200000 | 86849854.45 | 2023 | 739 BUILDERS | 284 | 2022 | 2023-04-17 | 02/24/2022 | 1350145.55 | 0 | 2022-08-29 |  | 231
2023 | Region III | PAMPANGA | FLORIDABLANCA (PAMPANGA) | P00726176LZ | Construction of Dike | 120.4888 | 14.9457 | 29398757.7 | 29393715.3 | 2023 | PASCAL CONSTRUCTION | 285 | 2023 | 2023-08-25 | 02/27/2023 | 5042.4 | 0 | 2023-08-24 |  | 1
2022 | Region III | BATAAN | HERMOSA (BATAAN) | P00640513LZ | Construction of Flood Mitigation Structure | 120.489 | 14.8531 | 39599997.96 | 39599984.38 | 2022 | TRICHES CONSTRUCTION & TRADING | 286 | 2022 | 2022-12-09 | 06/07/2022 | 13.58 | 0 | 2022-12-11 | 2
2022 | Region I | ILOCOS NORTE | PAOAY (ILOCOS NORTE) | P00644722LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.489 | 18.0711 | 48250000 | 47528651.6 | 2023 | RCD GEN. CONTRACTOR & CONSTRUCTION SUPPLY / NOSIDE CONSTRUCTION | 287 | 2022 | 2023-04-11 | 01/19/2023 | 721348.4 | 0 | 2023-07-19 | 99
2024 | Region III | BATAAN | HERMOSA (BATAAN) | P00823392LZ | Construction of Revetment | 120.4897 | 14.8529 | 96499999.64 | 96499998.25 | 2024 | M.C.J. VALENZUELA CONSTRUCTION ENTERPRISES | 288 | 2024 | 2024-12-02 | 04/23/2024 | 1.39 | 0 | 2024-12-31 | 29
2022 | Region I | ILOCOS SUR | SANTA LUCIA (ILOCOS SUR) | P00640498LZ | Construction of Flood Mitigation Structure | 120.4899 | 17.1179 | 19800000 | 19799998.31 | 2023 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES / EJIEV CONSTRUCTION SERVICES | 289 | 2022 | 2023-05-01 | 04/04/2022 | 1.69 | 0 | 2022-09-23 |  | 220
2023 | Region I | ILOCOS NORTE | PAOAY (ILOCOS NORTE) | P00726853LZ | Construction of Flood Mitigation Structure | 120.4902 | 18.0725 | 9650000 | 9650000 | 2023 | RCD GEN. CONTRACTOR & CONSTRUCTION SUPPLY | 290 | 2023 | 2023-08-15 | 05/08/2023 | 0 | 0 | 2023-08-20 | 5
2023 | Region I | ILOCOS NORTE | SAN NICOLAS (ILOCOS NORTE) | P00726850LZ | Construction of Flood Mitigation Structure | 120.4902 | 17.9491 | 9650000 | 9215046.51 | 2023 | JLP CONSTRUCTION & SUPPLY (FORMERLY: JLP CONSTRUCT | 291 | 2023 | 2023-10-05 | 05/08/2023 | 434953.49 | 0 | 2023-10-04 |  | 1
2022 | Region I | PANGASINAN | SISON (PANGASINAN) | P00631097LZ | Construction of Revetment | 120.4903 | 16.1722 | 49000000 | 48255997.27 | 2022 | W.J.P. CONSTRUCTION AND SUPPLY | 292 | 2022 | 2022-12-26 | 02/24/2022 | 744002.73 | 0 | 2022-09-02 |  | 115
2024 | Region IV-B | OCCIDENTAL MINDORO | PALUAN (OCCIDENTAL MINDORO) | P00823576LZ | Construction of Flood Mitigation Structure | 120.4903 | 13.4177 | 241250000 | 241246348.7 | 2024 | ALPHA & OMEGA GEN. CONTRACTOR & DEVELOPMENT CORP. | 293 | 2024 | 2024-12-07 | 03/02/2024 | 3651.3 | 0 | 2025-02-23 | 78
2022 | Region III | TARLAC | CAPAS (TARLAC) | P00639367LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.4905 | 15.378 | 96499939.51 | 94481613.13 | 2022 | ROYAL CROWN MONARCH CONSTRUCTION & SUPPLIES CORP. | 294 | 2022 | 2022-08-08 | 03/26/2022 | 2018326.38 | 0 | 2022-09-24 | 47
2024 | Region I | ILOCOS NORTE | BADOC (ILOCOS NORTE) | P00848604LZ | Construction of Flood Mitigation Structure | 120.4908 | 17.9273 | 53460000 | 53459995.32 | 2024 | BADOC BUILDERS & SUPPLY, INC. (FORMERLY: BADOC BUILDER & SUPPLY | 295 | 2024 | 2024-11-30 | 05/03/2024 | 4.68 | 0 | 2024-12-15 | 15
2022 | Region I | PANGASINAN | ALCALA (PANGASINAN) | P00620461LZ | Construction of Dike | 120.4911 | 15.8331 | 34300000 | 33779643.34 | 2022 | W.J.P. CONSTRUCTION AND SUPPLY | 296 | 2022 | 2022-07-02 | 03/08/2022 | 520356.66 | 0 | 2022-09-06 | 66
2022 | Region I | PANGASINAN | MANAOAG (PANGASINAN) | P00631085LZ | Construction of Slope Protection Structure | 120.4913 | 16.0622 | 14700000 | 14260946.7 | 2022 | BET CONSTRUCTION & SUPPLY | 297 | 2022 | 2022-07-11 | 02/17/2022 | 439053.3 | 0 | 2022-07-10 |  | 1
2021 | Region III | BATAAN |  | P00525984LZ | Construction of Flood Mitigation Structure | 120.4914 | 14.8644 | 48999998.19 | 48999998.19 | 2022 | ORANI CONSTRUCTION AND SUPPLY CORPORATION (FORMERLY:ORANI BUILDERS & SUPPLY) | 298 | 2021 | 2022-12-01 | 03/14/2022 | 0 | 0 | 2023-02-27 | 88
2023 | Region I | ILOCOS NORTE | BADOC (ILOCOS NORTE) | P00725600LZ | Construction of Flood Mitigation Structure | 120.4933 | 17.9205 | 48250000 | 48249992.07 | 2023 | BADOC BUILDERS & SUPPLY, INC. (FORMERLY: BADOC BUILDER & SUPPLY | 299 | 2023 | 2023-08-06 | 02/14/2023 | 7.93 | 0 | 2023-08-05 |  | 1
2022 | Region III | TARLAC | CAPAS (TARLAC) | P00639366LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.494 | 15.3801 | 96499799.7 | 96496291.64 | 2023 | FLORDES CONSTRUCTION & TRADING CORP. (FORMERLY FLO | 300 | 2022 | 2023-01-18 | 03/26/2022 | 3508.06 | 0 | 2023-01-17 |  | 1
2022 | Region X | MISAMIS OCCIDENTAL | BONIFACIO (MISAMIS OCCIDENTAL) | P00630587MN | Construction of Flood Mitigation Structure | 123.5905 | 8.0192 | 19600000 | 19300519.14 | 2023 | VICENTE T. LAO CONSTRUCTION | 301 | 2022 | 2023-04-23 | 04/04/2022 | 299480.86 | 0 | 2022-09-27 |  | 208
2022 | Region XIII | AGUSAN DEL SUR | ROSARIO (AGUSAN DEL SUR) | P00620299MN | Construction of Flood Mitigation Structure | 126.0064 | 8.3734 | 29400000 | 29399995.42 | 2023 | INNOVATI CONSTRUCTION & DEVELOPMENT CORPORATION | 302 | 2022 | 2023-03-13 | 07/11/2022 | 4.58 | 0 | 2023-03-12 |  | 1
2022 | Region X | BUKIDNON | SAN FERNANDO (BUKIDNON) | P00620114MN | Construction of Flood Mitigation Structure | 125.3936 | 7.8004 | 49000000 | 48999994.29 | 2022 | RITCHE-NATHALIE BUILDERS & GENERAL MERCHANDISE | 303 | 2022 | 2022-10-26 | 01/28/2022 | 5.71 | 0 | 2022-11-07 | 12
2022 | Region XIII | SURIGAO DEL SUR | CITY OF BISLIG (SURIGAO DEL SUR) | P00632322MN | Rehabilitation / Major Repair of Slope Protection Structure | 126.3582 | 7.9088 | 96500000 | 96399243.69 | 2023 | HGG BUILDERS & SUPPLY | 304 | 2022 | 2023-09-15 | 06/22/2022 | 100756.31 | 0 | 2023-10-03 | 18
2022 | Region I | PANGASINAN | BOLINAO (PANGASINAN) | P00631081LZ | Construction of Flood Mitigation Structure | 119.8914 | 16.3937 | 34300000 | 34299548.02 | 2022 | JASA GD 2000 CONSTRUCTION CORPORATION (FORMERLY:JASA BUILDER'S) | 305 | 2022 | 2022-09-06 | 02/10/2022 | 451.98 | 0 | 2022-09-06 | 0
2023 | Region I | ILOCOS SUR | SANTA CATALINA (ILOCOS SUR) | P00725616LZ | Construction of Flood Mitigation Structure | 120.346 | 17.5659 | 67550000 | 67549992.23 | 2023 | SATRAP CONSTRUCTION CO., INC. | 306 | 2023 | 2023-10-08 | 02/14/2023 | 7.77 | 0 | 2023-10-07 |  | 1
2024 | Region I | LA UNION | NAGUILIAN (LA UNION) | P00824812LZ | Construction of Flood Mitigation Structure | 120.4014 | 16.5056 | 82410999.95 | 82403230.11 | 2025 | UNIMAX STEEL STRUCTURE AND CONSTRUCTION CORP. | 307 | 2024 | 2025-03-16 | 04/18/2024 | 7769.84 | 0 | 2024-12-24 |  | 82
2022 | Region I | ILOCOS SUR | SANTA MARIA (ILOCOS SUR) | P00639420LZ | Construction of Flood Mitigation Structure | 120.5494 | 17.3758 | 4900000 | 4899720.46 | 2023 | MBB CONSTRUCTION AND SUPPLY (FORMERLY: MBB CONSTRUCTION) | 308 | 2022 | 2023-08-29 | 04/04/2022 | 279.54 | 0 | 2022-06-04 |  | 451
2024 | Region I | ILOCOS NORTE | BACARRA (ILOCOS NORTE) | P00838484LZ | Construction of Flood Mitigation Structure | 120.5611 | 18.2632 | 4899984.16 | 4899978.15 | 2024 | BJMJB CONSTRUCTION & SUPPLY | 309 | 2024 | 2024-04-13 | 02/27/2024 | 6.01 | 0 | 2024-04-12 |  | 1
2023 | Region III | BULACAN | CITY OF MALOLOS (CAPITAL) (BULACAN) | P00742158LZ | Construction of Flood Mitigation Structure | 120.8097 | 14.7574 | 59399680.02 | 59358779.56 | 2023 | JTC CRUZ CONSTRUCTION CO., INC. | 310 | 2023 | 2023-12-22 | 03/28/2023 | 40900.46 | 0 | 2023-12-21 |  | 1
2024 | Region III | BULACAN | CITY OF MALOLOS (CAPITAL) (BULACAN) | P00820227LZ | Construction of Flood Mitigation Structure | 120.8205 | 14.8274 | 72374911.43 | 72374895.37 | 2024 | SYMS CONSTRUCTION TRADING | 311 | 2024 | 2024-06-11 | 04/02/2024 | 16.06 | 0 | 2024-11-26 | 168
2023 | Region III | BULACAN | MARILAO (BULACAN) | P00727363LZ | Rehabilitation / Major Repair of Flood Mitigation Facility | 120.9518 | 14.7536 | 4898928.32 | 4825444.4 | 2023 | JB CONSTRUCTION AND SUPPLY INC. (FORMERLY:JB CONSTRUCTION AND SUPPLY) | 312 | 2023 | 2023-05-16 | 03/13/2023 | 73483.92 | 0 | 2023-07-22 | 67
2023 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00740278LZ | Construction of Flood Mitigation Facility | 120.971 | 14.6311 | 96499104.19 | 96419364.54 | 2024 | EIGHT J'S CONSTRUCTION SERVICES / JIIK CONSTRUCTION SERVICES | 313 | 2023 | 2024-05-05 | 03/28/2023 | 79739.65 | 0 | 2024-05-04 |  | 1
2023 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00737403LZ | Rehabilitation / Major Repair of Drainage Structure | 120.9727 | 14.6296 | 4948968.77 | 4948482.78 | 2023 | DENNREY CONSTRUCTION AND TRADING COMPANY | 314 | 2023 | 2023-07-23 | 03/08/2023 | 485.99 | 0 | 2023-08-04 | 12
2023 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00737404LZ | Rehabilitation / Major Repair of Drainage Structure | 120.9733 | 14.6313 | 9898703.16 | 9892991.03 | 2023 | DENNREY CONSTRUCTION AND TRADING COMPANY | 315 | 2023 | 2023-09-01 | 03/08/2023 | 5712.13 | 0 | 2023-08-31 |  | 1
2023 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00740287LZ | Construction of Flood Mitigation Facility | 120.9737 | 14.6348 | 96499285.72 | 93973783.55 | 2023 | EIGHT J'S CONSTRUCTION SERVICES | 316 | 2023 | 2023-07-12 | 03/28/2023 | 2525502.17 | 0 | 2023-07-04 |  | 8
2023 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00740288LZ | Construction of Flood Mitigation Facility | 120.9737 | 14.6348 | 96499390.45 | 93855667.56 | 2023 | EIGHT J'S CONSTRUCTION SERVICES | 317 | 2023 | 2023-07-25 | 03/28/2023 | 2643722.89 | 0 | 2023-09-02 | 39
2023 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00740289LZ | Construction of Flood Mitigation Facility | 120.9737 | 14.6348 | 96499089.29 | 93950837.84 | 2023 | EIGHT J'S CONSTRUCTION SERVICES | 318 | 2023 | 2023-07-26 | 03/28/2023 | 2548251.45 | 0 | 2023-09-02 | 38
2023 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00737405LZ | Rehabilitation / Major Repair of Drainage Structure | 120.9743 | 14.6308 | 9898819.64 | 9879998.59 | 2023 | DENNREY CONSTRUCTION AND TRADING COMPANY | 319 | 2023 | 2023-11-24 | 03/08/2023 | 18821.05 | 0 | 2023-11-29 | 5
2023 | Region IV-A | CAVITE | BACOOR CITY (CAVITE) | P00742425LZ | Construction of Flood Mitigation Structure | 120.9777 | 14.4363 | 19800000 | 19797210.25 | 2024 | E. F. CHUA CONSTRUCTION, INC. | 320 | 2023 | 2024-04-05 | 07/17/2023 | 2789.75 | 0 | 2024-04-04 |  | 1
2023 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00725996LZ | Construction of Flood Mitigation Structure | 120.9784 | 14.6343 | 34299867.73 | 34298030.64 | 2024 | G.F. FABIAN CONSTRUCTION | 321 | 2023 | 2024-01-30 | 02/13/2023 | 1837.09 | 0 | 2024-01-29 |  | 1
2022 | National Capital Region | PARAÃ‘AQUE CITY | CITY OF PARAÃ‘AQUE (METROPOLITAN MANILA) | P00620370LZ | Rehabilitation / Major Repair of Drainage Structure | 120.9897 | 14.4887 | 24500000 | 24495923.62 | 2022 | GREAT PACIFIC BUILDERS AND GEN. CONTRACTOR INC. | 322 | 2022 | 2022-12-08 | 02/09/2022 | 4076.38 | 0 | 2022-12-07 |  | 1
2022 | National Capital Region | LAS PIÃ‘AS CITY | CITY OF LAS PIÃ‘AS (METROPOLITAN MANILA) | P00620906LZ | Construction of Flood Mitigation Structure | 121.0021 | 14.3941 | 29397955.97 | 28158400.47 | 2022 | E. F. CHUA CONSTRUCTION, INC. | 323 | 2022 | 2022-08-07 | 02/09/2022 | 1239555.5 | 0 | 2022-08-06 |  | 1
2024 | National Capital Region | QUEZON CITY | QUEZON CITY (METROPOLITAN MANILA) | P00821458LZ | Construction of Revetment | 121.0121 | 14.63 | 48999608.72 | 48508612.63 | 2024 | AMETHYST HORIZON BUILDERS AND GEN. CONTRACTOR AND DEVELOPMENT CORP. | 324 | 2024 | 2024-12-01 | 02/06/2024 | 490996.09 | 0 | 2024-11-30 |  | 1
2021 | Region IV-A | LAGUNA |  | P00561774LZ | Construction of Revetment | 121.0231 | 14.3457 | 29700000 | 28809112.3 | 2022 | NEWBIG FOUR J CONSTRUCTION INC., (FORMERLY FOUR J | 325 | 2021 | 2022-08-24 | 12/07/2021 | 890887.7 | 0 | 2022-08-23 |  | 1
2023 | Region IX | SULU | MAIMBUNG (SULU) | P00735025MN | Construction of Flood Mitigation Structure | 121.0278 | 5.9288 | 48250000 | 48192075.61 | 2024 | ESR CONSTRUCTION AND DEVELOPMENT CORPORATION (FORMERLY: ESR CONSTRUCTION & SUPPLIES) | 326 | 2023 | 2024-01-20 | 08/03/2023 | 57924.39 | 0 | 2024-01-19 |  | 1
2022 | National Capital Region | MUNTINLUPA CITY | CITY OF MUNTINLUPA (METROPOLITAN MANILA) | P00620763LZ | Construction of Flood Mitigation Structure | 121.0522 | 14.4006 | 91673632.46 | 91568484.81 | 2022 | E. F. CHUA CONSTRUCTION, INC. | 327 | 2022 | 2022-08-25 | 02/17/2022 | 105147.65 | 0 | 2022-08-24 |  | 1
2022 | National Capital Region | MUNTINLUPA CITY | CITY OF MUNTINLUPA (METROPOLITAN MANILA) | P00620764LZ | Construction of Flood Mitigation Structure | 121.0541 | 14.3896 | 92636132.18 | 92570039.77 | 2022 | E. F. CHUA CONSTRUCTION, INC. | 328 | 2022 | 2022-12-12 | 04/07/2022 | 66092.41 | 0 | 2022-12-11 |  | 1
2024 | National Capital Region | TAGUIG CITY | TAGUIG CITY (METROPOLITAN MANILA) | P00821069LZ | Construction of Slope Protection Structure | 121.069 | 14.5051 | 144749873.5 | 141782501.1 | 2025 | TOPNOTCH CATALYST BUILDERS INC. / BEAM TEAM DEVELOPER SPECIALIST INC. | 329 | 2024 | 2025-01-07 | 05/29/2024 | 2967372.4 | 0 | 2025-05-20 | 133
2022 | Region IV-A | LAGUNA | CITY OF BIÃ‘AN (LAGUNA) | P00620218LZ | Construction of Flood Mitigation Structure | 121.0941 | 14.3561 | 92640000 | 92594196.37 | 2023 | ST. MATTHEW GEN. CONTRACTOR & DEVELOPMENT CORP. | 330 | 2022 | 2023-09-18 | 04/04/2022 | 45803.63 | 0 | 2023-09-17 |  | 1
2023 | National Capital Region | PASIG CITY | CITY OF PASIG (METROPOLITAN MANILA) | P00725939LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.099 | 14.5696 | 32045188.35 | 26918501.97 | 2023 | ST. TIMOTHY CONSTRUCTION CORPORATION | 331 | 2023 | 2023-09-03 | 02/06/2023 | 5126686.38 | 0 | 2023-09-02 |  | 1
2022 | National Capital Region | PASIG CITY | CITY OF PASIG (METROPOLITAN MANILA) | P00620365LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.1041 | 14.5514 | 48249709.4 | 45822749.02 | 2022 | ST. GERRARD CONSTRUCTION GEN. CONTRACTOR & DEVELOPMENT CORP. (FORMERLY:ST. GERRARD CONSTRUCTION) | 332 | 2022 | 2022-10-03 | 03/14/2022 | 2426960.38 | 0 | 2022-10-08 | 5
2023 | National Capital Region | PASIG CITY | CITY OF PASIG (METROPOLITAN MANILA) | P00727008LZ | Rehabilitation / Major Repair of Drainage Structure | 121.1061 | 14.5919 | 3918778.99 | 3717255 | 2023 | 1HB CONSTRUCTION CORP. (FORMERLY: HB CONSTRUCTION) | 333 | 2023 | 2023-05-04 | 03/06/2023 | 201523.99 | 0 | 2023-05-03 |  | 1
2023 | National Capital Region | PASIG CITY | CITY OF PASIG (METROPOLITAN MANILA) | P00725958LZ | Rehabilitation / Major Repair of Drainage Structure | 121.1064 | 14.591 | 14699439.76 | 13917186 | 2023 | 1HB CONSTRUCTION CORP. (FORMERLY: HB CONSTRUCTION) | 334 | 2023 | 2023-07-05 | 02/06/2023 | 782253.76 | 0 | 2023-07-04 |  | 1
2022 | Region IV-A | RIZAL | TAYTAY (RIZAL) | P00620644LZ | Construction of Flood Mitigation Structure | 121.1379 | 14.5321 | 39200000 | 38092846.4 | 2022 | C.F. TRINIDAD CONSTRUCTION AND SUPPLIES CORP. (FOR | 335 | 2022 | 2022-09-26 | 04/06/2022 | 1107153.6 | 0 | 2022-10-31 | 35
2021 | Region IV-A | RIZAL |  | P00561394LZ | Construction of Drainage Structure | 121.1488 | 14.5378 | 44550000 | 44510754.03 | 2023 | AARCON BUILDERS | 336 | 2021 | 2023-02-15 | 03/24/2022 | 39245.97 | 0 | 2023-03-17 | 30
2023 | Region IX | SULU | OLD PANAMAO (SULU) | P00721663MN | Construction of Flood Mitigation Structure | 121.2151 | 5.9794 | 67550000 | 67212246.7 | 2024 | ST. TIMOTHY CONSTRUCTION CORPORATION / ZHEREB CONSTRUCTION | 337 | 2023 | 2024-04-28 | 08/03/2023 | 337753.3 | 0 | 2024-04-27 |  | 1
2023 | Region IX | SULU | LUUK (SULU) | P00721236MN | Construction of Flood Mitigation Structure | 121.3134 | 5.9673 | 48250000 | 48008750.33 | 2023 | ST. MATTHEW GEN. CONTRACTOR & DEVELOPMENT CORP. | 338 | 2023 | 2023-12-07 | 04/17/2023 | 241249.67 | 0 | 2023-12-06 |  | 1
2023 | Region IV-A | BATANGAS | SAN JUAN (BATANGAS) | P00737497LZ | Construction of Drainage Structure | 121.3992 | 13.8267 | 4950000 | 4801496 | 2023 | TONIJON CONSTRUCTION AND DEVELOPMENT INC. (FORMERLY: TONIJON CONSTRUCTION) | 339 | 2023 | 2023-05-18 | 02/13/2023 | 148504 | 0 | 2023-05-17 |  | 1
2022 | Region II | ISABELA | ROXAS (ISABELA) | P00631118LZ | Construction of Flood Mitigation Structure | 121.565 | 17.1346 | 42140000 | 41663887.47 | 2022 | DANYSONS CONSTRUCTION AND DEVELOPMENT CORPORATION (FORMERLY: DANYSONS CONSTRUCTION) | 340 | 2022 | 2022-12-02 | 02/28/2022 | 476112.53 | 0 | 2022-12-01 |  | 1
2023 | Region II | ISABELA | ROXAS (ISABELA) | P00726426LZ | Construction of Flood Mitigation Structure | 121.5665 | 17.1354 | 48250000 | 48229649.53 | 2023 | DANYSONS CONSTRUCTION AND DEVELOPMENT CORPORATION (FORMERLY: DANYSONS CONSTRUCTION) / JWU CONSTRUCTION AND SUPPLY | 341 | 2023 | 2023-07-02 | 02/27/2023 | 20350.47 | 0 | 2023-11-09 | 130
2023 | Region II | CAGAYAN | LASAM (CAGAYAN) | P00726115LZ | Construction of Flood Mitigation Structure | 121.6066 | 18.0774 | 4900000 | 4847996.84 | 2023 | HHK CONSTRUCTION | 342 | 2023 | 2023-05-25 | 02/22/2023 | 52003.16 | 0 | 2023-05-24 |  | 1
2023 | Region II | ISABELA | REINA MERCEDES (ISABELA) | P00727355LZ | Construction of Flood Mitigation Structure | 121.7521 | 17.0055 | 48679453.7 | 48659086.18 | 2023 | ROAD EDGE TRADING & DEVELOPMENT SERVICES | 343 | 2023 | 2023-10-25 | 03/15/2023 | 20367.52 | 0 | 2023-10-24 |  | 1
2021 | Region II | ISABELA |  | P00525960LZ | Construction of Flood Mitigation Structure | 121.8073 | 16.9792 | 47225210.54 | 46493250.44 | 2022 | RRC CO. INC. (FORMERLY: R R C CONSTRUCTION) | 344 | 2021 | 2022-12-15 | 01/19/2022 | 731960.1 | 0 | 2022-12-14 |  | 1
2022 | Region IX | BASILAN | MALUSO (BASILAN) | P00630472MN | Construction of Flood Mitigation Structure | 121.8948 | 6.5479 | 53075000 | 53034576.67 | 2023 | RCDG CONSTRUCTION CORPORATION / BOSH MEGATRADE AND SERVICES CO. | 345 | 2022 | 2023-05-15 | 02/26/2022 | 40423.33 | 0 | 2022-12-17 |  | 149
2022 | Region IV-A | QUEZON | ATIMONAN (QUEZON) | P00620616LZ | Construction of Flood Mitigation Structure | 121.9256 | 14.0029 | 24500000 | 24500000 | 2022 | R.T.Y. CONSTRUCTION | 346 | 2022 | 2022-08-03 | 03/24/2022 | 0 | 0 | 2022-11-21 | 110
2024 | Region IV-A | QUEZON | ATIMONAN (QUEZON) | P00820910LZ | Construction of Flood Mitigation Structure | 121.9259 | 14.0037 | 19600000 | 19579679.37 | 2024 | R.T.Y. CONSTRUCTION | 347 | 2024 | 2024-06-10 | 03/12/2024 | 20320.63 | 0 | 2024-11-05 | 148
2024 | Region IV-A | QUEZON | ATIMONAN (QUEZON) | P00820925LZ | Construction of Flood Mitigation Structure | 121.9261 | 14.004 | 9800000 | 9796174.35 | 2024 | R.T.Y. CONSTRUCTION | 348 | 2024 | 2024-06-10 | 03/13/2024 | 3825.65 | 0 | 2024-10-07 | 119
2020 | Region IX | BASILAN |  | P00420382MN | Construction of Revetment | 121.9319 | 6.6181 | 107725803.8 | 105571270.5 | 2022 | RCDG CONSTRUCTION CORPORATION / HHH DEVELOPER AND CONSTRUCTION | 349 | 2020 | 2022-07-17 | 11/23/2020 | 2154533.3 | 0 | 2022-01-16 |  | 182
2023 | Region II | BATANES | MAHATAO (BATANES) | P00727341LZ | Construction of Flood Mitigation Structure | 121.945 | 20.4169 | 20580000 | 16445177.1 | 2024 | STRONGLANE BUILDERS AND TRADING CORPORATION (FORMERLY: STRONGLANE CONSTRUCTION & TRADING) | 350 | 2023 | 2024-08-15 | 05/16/2023 | 4134822.9 | 0 | 2024-05-27 |  | 80
2023 | Region IX | BASILAN | SUMISIP (BASILAN) | P00733983MN | Construction of Flood Mitigation Structure | 122.0213 | 6.4737 | 49143590 | 49113586.1 | 2024 | RCDG CONSTRUCTION CORPORATION / BOSH MEGATRADE AND SERVICES CO. | 351 | 2023 | 2024-04-01 | 05/11/2023 | 30003.9 | 0 | 2023-11-02 |  | 151
2024 | Region IX | BASILAN | SUMISIP (BASILAN) | P00835755MN | Construction of Flood Mitigation Structure | 122.0433 | 6.4205 | 24125000 | 24107610.26 | 2024 | BOSH MEGATRADE AND SERVICES CO. | 352 | 2024 | 2024-11-14 | 06/06/2024 | 17389.74 | 0 | 2024-11-13 |  | 1
2023 | Region IX | BASILAN | SUMISIP (BASILAN) | P00732467MN | Construction of Flood Mitigation Structure | 122.0433 | 6.4205 | 39600000 | 39595356.53 | 2024 | BOSH MEGATRADE AND SERVICES CO. | 353 | 2023 | 2024-03-31 | 03/02/2023 | 4643.47 | 0 | 2024-01-30 |  | 61
2023 | Region IX | BASILAN | TIPO-TIPO (BASILAN) | P00733984MN | Construction of Flood Mitigation Structure | 122.0877 | 6.484 | 27091410 | 27040410 | 2023 | BOSH MEGATRADE AND SERVICES CO. | 354 | 2023 | 2023-11-29 | 05/11/2023 | 51000 | 0 | 2023-08-26 |  | 95
2023 | Region IX | BASILAN | CITY OF LAMITAN (BASILAN) | P00734382MN | Construction of Flood Mitigation Structure | 122.1298 | 6.6934 | 9800000 | 9779883.56 | 2023 | MMP CONSTRUCTION AND SUPPLIES | 355 | 2023 | 2023-07-05 | 03/23/2023 | 20116.44 | 0 | 2023-07-04 |  | 1
2021 | Region VI | NEGROS OCCIDENTAL |  | P00538301VS | Rehabilitation / Major Repair of Slope Protection Structure | 122.3972 | 9.775 | 5751010.1 | 5751010.14 | 2022 | RHT CONSTRUCTION AND SUPPLIES | 356 | 2021 | 2022-08-31 | 04/13/2022 | 0 | 0.04 | 2022-08-09 |  | 22
2022 | Region VII | NEGROS ORIENTAL | CITY OF TANJAY (NEGROS ORIENTAL) | P00620279VS | Construction of Flood Mitigation Structure | 123.1629 | 9.5269 | 59904305 | 59904305 | 2022 | LEGACY CONSTRUCTION CORPORATION (FORMERLY: LEGACY CONSTRUCTION) / MIGHTY HOK SUMMIT CONSTRUCTION & DEVELOPMENT CORP. | 357 | 2022 | 2022-12-19 | 02/18/2022 | 0 | 0 | 2022-12-18 |  | 1
2023 | Region VII | CEBU | BARILI (CEBU) | P00746103VS | Construction of Flood Mitigation Structure | 123.476 | 10.1072 | 92108285 | 92108285 | 2024 | QM BUILDERS | 358 | 2023 | 2024-11-08 | 01/09/2024 | 0 | 0 | 2024-11-09 | 1
2024 | Region XII | SULTAN KUDARAT | LEBAK (SULTAN KUDARAT) | P00833602MN | Construction of Flood Mitigation Structure | 124.041 | 6.7499 | 4950000 | 4924487.07 | 2024 | JV CONSTECH | 359 | 2024 | 2024-09-02 | 03/25/2024 | 25512.93 | 0 | 2024-07-01 |  | 63
2023 | Region XII | SULTAN KUDARAT | LEBAK (SULTAN KUDARAT) | P00734416MN | Construction of Flood Mitigation Structure | 124.041 | 6.7499 | 4950000 | 4950000 | 2023 | JV CONSTECH | 360 | 2023 | 2023-09-15 | 03/24/2023 | 0 | 0 | 2023-08-16 |  | 30
2023 | Region XII | MAGUINDANAO DEL NORTE | DATU ODIN SINSUAT (DINAIG) (CAPITAL) (MAGUINDANAO) | P00721320MN | Construction of Flood Mitigation Structure | 124.2151 | 7.191 | 109696375 | 109380392.3 | 2024 | FFJJ CONSTRUCTION | 361 | 2023 | 2024-05-04 | 07/20/2023 | 315982.7 | 0 | 2024-05-03 |  | 1
2022 | Region XII | MAGUINDANAO DEL NORTE | DATU PIANG (MAGUINDANAO) | P00620244MN | Construction of Revetment | 124.2218 | 7.1801 | 82024859 | 81574238.89 | 2023 | FFJJ CONSTRUCTION | 362 | 2022 | 2023-07-25 | 10/12/2022 | 450620.11 | 0 | 2023-08-26 | 32
2022 | Region XII | MAGUINDANAO DEL NORTE | DATU PIANG (MAGUINDANAO) | P00620245MN | Construction of Revetment | 124.2238 | 7.1774 | 82024542.28 | 81999595.28 | 2023 | AMPLEX CONSTRUCTION AND SUPPLIES / KEY GENERAL MERCHANDISE AND CONSTRUCTION SERVICES | 363 | 2022 | 2023-08-10 | 10/26/2022 | 24947 | 0 | 2023-07-10 |  | 31
2022 | Region XII | MAGUINDANAO DEL NORTE | DATU PIANG (MAGUINDANAO) | P00620246MN | Construction of Revetment | 124.227 | 7.1751 | 82024630.37 | 81223898.37 | 2023 | DCD BUILDERS & ENTERPISES / CORICS CONSTRUCTION | 364 | 2022 | 2023-12-22 | 10/12/2022 | 800732 | 0 | 2023-10-31 |  | 52
2023 | Region XII | MAGUINDANAO DEL NORTE | SULTAN KUDARAT (NULING) (MAGUINDANAO) | P00734032MN | Rehabilitation / Major Repair of Flood Control Structure | 124.2552 | 7.2655 | 9800000 | 9505468.74 | 2024 | ISFB CONSTRUCTION | 365 | 2023 | 2024-01-22 | 08/25/2023 | 294531.26 | 0 | 2024-01-06 |  | 16
2024 | Region XII | MAGUINDANAO DEL SUR | DATU PIANG (MAGUINDANAO) | P00820356MN | Construction of Flood Mitigation Structure | 124.469 | 7.0491 | 48250000 | 47283436.87 | 2025 | ED1SON DEVELOPMENT & CONSTRUCTION INC. / H-ROYAL CONSTRUCTION | 366 | 2024 | 2025-03-03 | 03/18/2024 | 966563.13 | 0 | 2025-02-03 |  | 28
2022 | Region XII | MAGUINDANAO DEL SUR | DATU SALIBO (MAGUINDANAO) | P00633902MN | Construction of Flood Mitigation Structure | 124.4799 | 6.9895 | 96499647.65 | 91674665.27 | 2023 | JDRC CONSTRUCTION & SUPPLIES, CORP. | 367 | 2022 | 2023-08-13 | 09/23/2022 | 4824982.38 | 0 | 2023-09-03 | 21
2021 | Region XII | MAGUINDANAO DEL SUR |  | P00522108MN | Construction of Revetment | 124.4829 | 6.9885 | 24119799.72 | 23995000.03 | 2022 | LLABAN CONSTRUCTION & SUPPLY (FORMERLY: LLABAN CON | 368 | 2021 | 2022-12-13 | 06/21/2022 | 124799.69 | 0 | 2022-12-12 |  | 1
2022 | Region XII | MAGUINDANAO DEL SUR | DATU PIANG (MAGUINDANAO) | P00632318MN | Construction of Revetment | 124.4975 | 7.0178 | 96499372.19 | 91674403.59 | 2023 | JDRC CONSTRUCTION & SUPPLIES, CORP. | 369 | 2022 | 2023-07-24 | 09/23/2022 | 4824968.6 | 0 | 2023-09-03 | 41
2021 | Region XII | MAGUINDANAO DEL SUR |  | P00522107MN | Construction of Revetment | 124.4993 | 7.0302 | 24095997.89 | 23995000 | 2022 | LLABAN CONSTRUCTION & SUPPLY (FORMERLY: LLABAN CON | 370 | 2021 | 2022-12-26 | 06/21/2022 | 100997.89 | 0 | 2022-12-12 |  | 14
2023 | Region XII | COTABATO (NORTH COTABATO) | MIDSAYAP (COTABATO (NORTH COTABATO)) | P00721448MN | Construction of Flood Mitigation Structure | 124.4997 | 7.0323 | 93219000 | 92286809.99 | 2024 | LLABAN CONSTRUCTION & SUPPLY (FORMERLY: LLABAN CON / RNS CONSTRUCTION ENGINEERING | 371 | 2023 | 2024-01-29 | 02/22/2023 | 932190.01 | 0 | 2024-01-28 |  | 1
2022 | Region XII | MAGUINDANAO DEL SUR | DATU PIANG (MAGUINDANAO) | P00620243MN | Construction of Revetment | 124.5068 | 7.0266 | 81059111.69 | 78620793.02 | 2023 | JDRC CONSTRUCTION & SUPPLIES, CORP. | 372 | 2022 | 2023-07-24 | 04/13/2022 | 2438318.67 | 0 | 2023-02-22 |  | 152
2022 | Region XII | MAGUINDANAO DEL SUR | DATU PIANG (MAGUINDANAO) | P00620242MN | Construction of Revetment | 124.5081 | 7.0242 | 81059585.8 | 78992559.63 | 2023 | FFJJ CONSTRUCTION | 373 | 2022 | 2023-08-14 | 04/13/2022 | 2067026.17 | 0 | 2023-02-22 |  | 173
2022 | Region XII | MAGUINDANAO DEL SUR | DATU PIANG (MAGUINDANAO) | P00620241MN | Construction of Revetment | 124.5118 | 7.0226 | 82024233.29 | 79932563.97 | 2023 | FFJJ CONSTRUCTION | 374 | 2022 | 2023-02-27 | 04/13/2022 | 2091669.32 | 0 | 2023-02-24 |  | 3
2023 | Region XII | COTABATO (NORTH COTABATO) | MIDSAYAP (COTABATO (NORTH COTABATO)) | P00721449MN | Construction of Flood Mitigation Structure | 124.5203 | 7.0314 | 57900000 | 57324045.23 | 2023 | GEMMA CONSTRUCTION SUPPLY, INC.(FORMERLY:GEMMA CON | 375 | 2023 | 2023-09-27 | 03/24/2023 | 575954.77 | 0 | 2023-09-26 |  | 1
2023 | Region VIII | LEYTE | CARIGARA (LEYTE) | P00721575VS | Construction of Flood Mitigation Structure | 124.6856 | 11.3049 | 123519481 | 123519982.6 | 2024 | LANOY CONSTRUCTION | 376 | 2023 | 2024-07-19 | 03/15/2023 | 0 | 501.6 | 2024-07-18 |  | 1
2021 | Region VIII | LEYTE |  | P00521566VS | Construction of Flood Mitigation Structure | 124.6868 | 11.3048 | 96399769.32 | 92505676.69 | 2024 | LANOY CONSTRUCTION | 377 | 2021 | 2024-03-22 | 05/08/2021 | 3894092.63 | 0 | 2024-04-04 | 13
2023 | Region XII | MAGUINDANAO DEL SUR | PAGAGAWAN (MAGUINDANAO) | P00721321MN | Construction of Flood Mitigation Structure | 124.739 | 7.0838 | 75270000 | 74329125 | 2023 | LLABAN CONSTRUCTION & SUPPLY (FORMERLY: LLABAN CON | 378 | 2023 | 2023-09-25 | 04/03/2023 | 940875 | 0 | 2023-12-05 | 71
2023 | Region XII | MAGUINDANAO DEL SUR | PAGAGAWAN (MAGUINDANAO) | P00721323MN | Construction of Flood Mitigation Structure | 124.7399 | 7.0839 | 48250000 | 47646875 | 2023 | LLABAN CONSTRUCTION & SUPPLY (FORMERLY: LLABAN CON | 379 | 2023 | 2023-10-19 | 04/03/2023 | 603125 | 0 | 2023-10-18 |  | 1
2023 | Region XII | MAGUINDANAO DEL SUR | PAGALUNGAN (MAGUINDANAO) | P00721322MN | Construction of Flood Mitigation Structure | 124.7405 | 7.0782 | 48250000 | 47646875 | 2023 | LLABAN CONSTRUCTION & SUPPLY (FORMERLY: LLABAN CON | 380 | 2023 | 2023-09-15 | 04/03/2023 | 603125 | 0 | 2023-10-18 | 33
2021 | Region XII | MAGUINDANAO DEL SUR |  | P00522109MN | Construction of Revetment | 124.7916 | 6.6384 | 24124331.49 | 21591512.98 | 2022 | STONELINE CONSTRUCTION (FORMERLY: ABUBAKAR ENGINEERING EXPONENT) | 381 | 2021 | 2022-12-27 | 05/31/2022 | 2532818.51 | 0 | 2023-01-11 | 15
2022 | Region XII | MAGUINDANAO DEL SUR | BULUAN (MAGUINDANAO) | P00633905MN | Construction of Flood Mitigation Structure | 124.8073 | 6.682 | 96499984.13 | 96499063.51 | 2023 | JDRC CONSTRUCTION & SUPPLIES, CORP. | 382 | 2022 | 2023-04-24 | 10/05/2022 | 920.62 | 0 | 2023-07-17 | 84
2022 | Region XII | MAGUINDANAO DEL SUR | BULUAN (MAGUINDANAO) | P00620088MN | Construction of Flood Mitigation Structure | 124.8105 | 6.6655 | 81059935.47 | 81000521.2 | 2023 | FFJJ CONSTRUCTION | 383 | 2022 | 2023-02-27 | 04/12/2022 | 59414.27 | 0 | 2023-02-21 |  | 6
2022 | Region XII | MAGUINDANAO DEL SUR | BULUAN (MAGUINDANAO) | P00631075MN | Construction of Slope Protection Structure | 124.8106 | 6.6679 | 49499405.92 | 49399692.3 | 2022 | FFJJ CONSTRUCTION | 384 | 2022 | 2022-12-18 | 04/13/2022 | 99713.62 | 0 | 2022-12-17 |  | 1
2024 | Region VIII | SAMAR (WESTERN SAMAR) | GANDARA (SAMAR (WESTERN SAMAR)) | P00820418VS | Construction of Flood Mitigation Structure | 124.8117 | 12.0199 | 40894420 | 40694013.14 | 2024 | JUPA CONSTRUCTION | 385 | 2024 | 2024-11-21 | 04/22/2024 | 200406.86 | 0 | 2024-11-11 |  | 10
2022 | Region XII | MAGUINDANAO DEL SUR | BULUAN (MAGUINDANAO) | P00620087MN | Construction of Flood Mitigation Structure | 124.8128 | 6.6637 | 81059129.86 | 80831781.63 | 2023 | LEGACY CONSTRUCTION CORPORATION (FORMERLY: LEGACY CONSTRUCTION) | 386 | 2022 | 2023-04-04 | 05/23/2022 | 227348.23 | 0 | 2023-04-03 |  | 1
2020 | Region XII | MAGUINDANAO DEL SUR |  | P00444687MN | Construction of Flood Mitigation Structure | 124.813 | 6.6639 | 48995449.04 | 48512932.29 | 2023 | FFJJ CONSTRUCTION | 387 | 2020 | 2023-02-27 | 09/24/2020 | 482516.75 | 0 | 2022-03-15 |  | 349
2021 | Region XII | MAGUINDANAO DEL SUR |  | P00444687MN | Construction of Flood Mitigation Structure | 124.813 | 6.6639 | 48995449.04 | 48512932.29 | 2023 | FFJJ CONSTRUCTION | 388 | 2021 | 2023-02-27 | 09/24/2020 | 482516.75 | 0 | 2022-03-15 |  | 349
2022 | Region XII | MAGUINDANAO DEL SUR | MANGUDADATU (MAGUINDANAO) | P00620086MN | Construction of Flood Mitigation Structure | 124.8409 | 6.6925 | 81059486.75 | 80300725.51 | 2023 | LLABAN CONSTRUCTION & SUPPLY (FORMERLY: LLABAN CON / RNS CONSTRUCTION ENGINEERING | 389 | 2022 | 2023-01-30 | 03/14/2022 | 758761.24 | 0 | 2023-01-23 |  | 7
2020 | Region XII | MAGUINDANAO DEL SUR |  | P00444655MN | Construction of Flood Mitigation Structure | 124.8412 | 6.6923 | 48998194.27 | 48600631.28 | 2023 | FFJJ CONSTRUCTION | 390 | 2020 | 2023-02-27 | 10/22/2020 | 397562.99 | 0 | 2022-03-15 |  | 349
2021 | Region XII | MAGUINDANAO DEL SUR |  | P00444655MN | Construction of Flood Mitigation Structure | 124.8412 | 6.6923 | 48998194.27 | 48600631.28 | 2023 | FFJJ CONSTRUCTION | 391 | 2021 | 2023-02-27 | 10/22/2020 | 397562.99 | 0 | 2022-03-15 |  | 349
2022 | Region XII | MAGUINDANAO DEL SUR | BULUAN (MAGUINDANAO) | P00633904MN | Construction of Flood Mitigation Structure | 124.8412 | 6.6999 | 96499999.83 | 96499939.49 | 2023 | JDRC CONSTRUCTION & SUPPLIES, CORP. | 392 | 2022 | 2023-04-24 | 10/05/2022 | 60.34 | 0 | 2023-07-17 | 84
2024 | Region XII | MAGUINDANAO DEL SUR | DATU PAGLAS (MAGUINDANAO) | P00820105MN | Construction of Flood Mitigation Structure | 124.8671 | 6.7399 | 96500000 | 96008853.82 | 2025 | PATE-KHAY CONSTRUCTION | 393 | 2024 | 2025-02-11 | 05/20/2024 | 491146.18 | 0 | 2025-02-03 |  | 8
2022 | Region VIII | SAMAR (WESTERN SAMAR) | VILLAREAL (SAMAR (WESTERN SAMAR)) | P00630686VS | Construction of Slope Protection Structure | 124.9292 | 11.5697 | 14699999.97 | 14847437.16 | 2022 | CDU CONSTRUCTION | 394 | 2022 | 2022-12-16 | 02/28/2022 | 0 | 147437.19 | 2022-12-15 |  | 1
2021 | Region VIII | SOUTHERN LEYTE |  | P00549877VS | Construction of Slope Protection Structure | 124.9309 | 10.1237 | 96500000 | 96500000 | 2022 | S-ANG CONSTRUCTION & GENERAL TRADING, INC. / MORTAR MASTERS & CONCRETE BUILDERS | 395 | 2021 | 2022-10-07 | 11/22/2021 | 0 | 0 | 2022-10-06 |  | 1
2022 | Region VIII | LEYTE | TACLOBAN CITY (CAPITAL) (LEYTE) | P00620235VS | Construction of Flood Mitigation Structure | 125.0043 | 11.2525 | 48996130.43 | 48998750 | 2023 | LEDA CONSTRUCTION INCORPORATED | 396 | 2022 | 2023-05-13 | 02/23/2022 | 0 | 2619.57 | 2023-05-12 |  | 1
2021 | Region VIII | SOUTHERN LEYTE |  | P00549876VS | Construction of Slope Protection Structure | 125.0234 | 10.0555 | 96500000 | 96500000 | 2022 | S-ANG CONSTRUCTION & GENERAL TRADING, INC. / MORTAR MASTERS & CONCRETE BUILDERS | 397 | 2021 | 2022-11-20 | 11/22/2021 | 0 | 0 | 2022-12-05 | 15
2023 | Region VIII | LEYTE | TACLOBAN CITY (CAPITAL) (LEYTE) | P00721593VS | Construction of Flood Mitigation Structure | 125.0279 | 11.2123 | 151772091 | 151771943.3 | 2025 | SUNWEST, INC. (FORMERLY: SUNWEST CONSTRUCTION & DEVELOPMENT CORPORATION) | 398 | 2023 | 2025-02-15 | 08/09/2023 | 147.7 | 0 | 2025-02-14 |  | 1
2022 | Region XI | DAVAO DEL SUR | DAVAO CITY (DAVAO DEL SUR) | P00634138MN | Construction of Flood Mitigation Structure | 125.6355 | 7.0874 | 9900000 | 9900000 | 2023 | AGONG BUILDERS AND CONSTRUCTION SUPPLY, INC. | 399 | 2022 | 2023-03-15 | 06/02/2022 | 0 | 0 | 2023-03-14 |  | 1
2021 | Region XIII | AGUSAN DEL NORTE |  | P00538309MN | Rehabilitation / Major Repair of Slope Protection Structure | 125.6458 | 8.9131 | 7085332.41 | 7085328.3 | 2022 | TRIPARCO DEVELOPMENT CORPORATION | 400 | 2021 | 2022-10-24 | 03/22/2022 | 4.11 | 0 | 2022-10-29 | 5
2022 | Region III | ZAMBALES | BOTOLAN (ZAMBALES) | P00637032LZ | Construction of Slope Protection Structure | 120.0587 | 15.7715 | 96499359.64 | 92634459.47 | 2023 | ALEXI LOUISSE CONSTRUCTION & GENERAL MERCHANDISE / EGB CONSTRUCTION CORPORATION (FORMERLY: EGB CONSTRUCTION) | 401 | 2022 | 2023-05-29 | 06/24/2022 | 3864900.17 | 0 | 2023-06-17 | 19
2022 | Region III | ZAMBALES | SAN ANTONIO (ZAMBALES) | P00620844LZ | Construction of Flood Mitigation Structure | 120.0604 | 14.9483 | 72278365.91 | 72260538.6 | 2022 | CDC CONSTRUCTION & SUPPLIES | 402 | 2022 | 2022-09-26 | 02/23/2022 | 17827.31 | 0 | 2022-09-19 |  | 7
2023 | Region III | ZAMBALES | SAN ANTONIO (ZAMBALES) | P00740641LZ | Construction of Flood Mitigation Structure | 120.0641 | 14.9182 | 19599661.31 | 19286075.3 | 2024 | KAEE CONSTRUCTION SERVICES | 403 | 2023 | 2024-01-12 | 05/23/2023 | 313586.01 | 0 | 2024-01-16 | 4
2024 | Region IV-B | PALAWAN | CORON (PALAWAN) | P00820978LZ | Construction of Flood Mitigation Structure | 120.0671 | 12.0248 | 44099999.16 | 44079742.82 | 2024 | L. B. LEONCIO TRADING AND CONSTRUCTION CORPORATION (FORMERLY: L.B. LEONCIO TRADING & CONSTRUCTION) / ONE HUNDRED PERCENT CONSTRUCTION AND DEVELOPMENT CORPORATION (FORMERLY:BCT TRADING & CONSTRUCTION) | 404 | 2024 | 2024-07-26 | 02/14/2024 | 20256.34 | 0 | 2024-07-25 |  | 1
2023 | Region III | ZAMBALES | SAN FELIPE (ZAMBALES) | P00742378LZ | Construction of Slope Protection Structure | 120.0769 | 15.0654 | 9899246.88 | 9721105.3 | 2023 | VM BUILDERS CONSTRUCTION CORPORATION | 405 | 2023 | 2023-10-16 | 04/24/2023 | 178141.58 | 0 | 2023-10-19 | 3
2024 | Region III | ZAMBALES | SAN FELIPE (ZAMBALES) | P00824713LZ | Construction of Slope Protection Structure | 120.077 | 15.0654 | 28949971.76 | 28515722.18 | 2024 | VM BUILDERS CONSTRUCTION CORPORATION | 406 | 2024 | 2024-05-17 | 02/22/2024 | 434249.58 | 0 | 2024-10-17 | 153
2023 | Region III | ZAMBALES | SAN ANTONIO (ZAMBALES) | P00740323LZ | Construction of Flood Mitigation Structure | 120.0873 | 14.9621 | 72374705.67 | 72374965.08 | 2023 | CDC CONSTRUCTION & SUPPLIES | 407 | 2023 | 2023-12-11 | 05/31/2023 | 0 | 259.41 | 2024-02-08 | 59
2023 | Region III | ZAMBALES | SAN FELIPE (ZAMBALES) | P00725702LZ | Construction of Flood Mitigation Structure | 120.0992 | 15.1065 | 96499963.12 | 96500000 | 2024 | R.A. PAHATI CONST. & SUPPLY, INC. | 408 | 2023 | 2024-03-30 | 06/05/2023 | 0 | 36.88 | 2024-03-29 |  | 1
2024 | Region IV-B | PALAWAN | CORON (PALAWAN) | P00820976LZ | Construction of Flood Mitigation Structure | 120.1548 | 12.0444 | 44099998.89 | 44098571.94 | 2024 | ALPHA VECTOR CONSTRUCTION AND SUPPLY / JASMIG CONSTRUCTION CORPORATION (FORMERLY: JASMIG CONSTRUCTION SUPPLY) | 409 | 2024 | 2024-08-21 | 02/14/2024 | 1426.95 | 0 | 2024-08-30 | 9
2023 | Region IV-B | PALAWAN | CORON (PALAWAN) | P00726768LZ | Construction of Flood Mitigation Structure | 120.1552 | 12.0476 | 20089948.32 | 20088519.55 | 2024 | JRMX CONSTRUCTION & GENERAL MERCHANDISE | 410 | 2023 | 2024-10-01 | 05/31/2023 | 1428.77 | 0 | 2024-02-18 |  | 226
2022 | Region III | ZAMBALES | SAN NARCISO (ZAMBALES) | P00620554LZ | Construction of Dike | 120.1588 | 15.0005 | 48998584.87 | 48999754.56 | 2022 | MCB ZAMORA CONSTRUCTION & SUPPLY | 411 | 2022 | 2022-09-10 | 03/02/2022 | 0 | 1169.69 | 2022-09-11 | 1
2022 | Region III | ZAMBALES | CASTILLEJOS (ZAMBALES) | P00620852LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.1686 | 14.9101 | 77199184.38 | 77199999.49 | 2022 | STO. CRISTO CONSTRUCTION & TRADING INC. (FOR: STO. CRISTO CONSTRUCTION & TRADING) | 412 | 2022 | 2022-08-22 | 03/24/2022 | 0 | 815.11 | 2022-12-17 | 117
2022 | Region III | ZAMBALES | CASTILLEJOS (ZAMBALES) | P00620853LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.1802 | 14.9068 | 77199667 | 77199999.88 | 2022 | STO. CRISTO CONSTRUCTION & TRADING INC. (FOR: STO. CRISTO CONSTRUCTION & TRADING) | 413 | 2022 | 2022-08-22 | 03/24/2022 | 0 | 332.88 | 2022-12-17 | 117
2023 | Region III | ZAMBALES | CASTILLEJOS (ZAMBALES) | P00725740LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.1802 | 14.9504 | 67549142.65 | 67549998.17 | 2023 | HIGH STRENGTH DEV. CORPORATION | 414 | 2023 | 2023-05-09 | 02/14/2023 | 0 | 855.52 | 2023-10-10 | 154
2022 | Region III | ZAMBALES | CASTILLEJOS (ZAMBALES) | P00620854LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.1807 | 14.9068 | 82449318.3 | 82024999.11 | 2022 | ORANI CONSTRUCTION AND SUPPLY CORPORATION (FORMERLY:ORANI BUILDERS & SUPPLY) | 415 | 2022 | 2022-08-13 | 02/21/2022 | 424319.19 | 0 | 2022-10-17 | 65
2023 | Region III | ZAMBALES | CASTILLEJOS (ZAMBALES) | P00726517LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.1835 | 14.9093 | 96499334.12 | 96499859.1 | 2023 | ORANI CONSTRUCTION AND SUPPLY CORPORATION (FORMERLY:ORANI BUILDERS & SUPPLY) | 416 | 2023 | 2023-05-14 | 02/14/2023 | 0 | 524.98 | 2023-11-29 | 199
2022 | Region III | ZAMBALES | CASTILLEJOS (ZAMBALES) | P00620198LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.1924 | 14.9561 | 77199039.61 | 77199999.95 | 2022 | ORANI CONSTRUCTION AND SUPPLY CORPORATION (FORMERLY:ORANI BUILDERS & SUPPLY) | 417 | 2022 | 2022-08-22 | 03/24/2022 | 0 | 960.34 | 2022-12-17 | 117
2022 | Region III | ZAMBALES | CASTILLEJOS (ZAMBALES) | P00620199LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.194 | 14.9551 | 77199636.62 | 77199999.54 | 2022 | ORANI CONSTRUCTION AND SUPPLY CORPORATION (FORMERLY:ORANI BUILDERS & SUPPLY) | 418 | 2022 | 2022-11-27 | 03/24/2022 | 0 | 362.92 | 2022-12-17 | 20
2024 | Region III | ZAMBALES | CASTILLEJOS (ZAMBALES) | P00825099LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.1975 | 14.9322 | 77199351.32 | 77199613.07 | 2024 | REPOLMAN CONSTRUCTION CORP. (FORMERLY: REPOLMAN CONSTRUCTION) | 419 | 2024 | 2024-11-09 | 02/14/2024 | 0 | 261.75 | 2024-11-08 |  | 1
2024 | Region III | ZAMBALES | CASTILLEJOS (ZAMBALES) | P00825245LZ | Rehabilitation / Major Repair of Drainage Structure | 120.1988 | 14.9339 | 19599791.58 | 19599347.92 | 2024 | M.V.GUBALLA CONSTRUCTION CORPORATION (FORMERLY: M.V. GUBALLA CONSTRUCTION) | 420 | 2024 | 2024-11-25 | 02/16/2024 | 443.66 | 0 | 2025-02-23 | 90
2023 | Region III | ZAMBALES | SAN MARCELINO (ZAMBALES) | P00726919LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.1995 | 14.9672 | 67549783.44 | 67549976.8 | 2023 | STO. CRISTO CONSTRUCTION & TRADING INC. (FOR: STO. CRISTO CONSTRUCTION & TRADING) | 421 | 2023 | 2023-06-09 | 03/15/2023 | 0 | 193.36 | 2023-11-06 | 150
2024 | Region III | ZAMBALES | SUBIC (ZAMBALES) | P00825101LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.2052 | 14.8676 | 96499795.17 | 96499979.14 | 2024 | REPOLMAN CONSTRUCTION CORP. (FORMERLY: REPOLMAN CONSTRUCTION) | 422 | 2024 | 2024-12-24 | 02/14/2024 | 0 | 183.97 | 2024-12-23 |  | 1
2024 | Region III | ZAMBALES | SAN MARCELINO (ZAMBALES) | P00823350LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.2111 | 15.0118 | 192999874.1 | 192999998.6 | 2024 | REPOLMAN CONSTRUCTION CORP. (FORMERLY: REPOLMAN CONSTRUCTION) / THREE W BUILDERS, INC. | 423 | 2024 | 2024-11-24 | 05/30/2024 | 0 | 124.5 | 2025-05-23 | 180
2022 | Region III | ZAMBALES | CASTILLEJOS (ZAMBALES) | P00620856LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.2132 | 14.9313 | 67899591.99 | 67549948.39 | 2022 | REPOLMAN CONSTRUCTION CORP. (FORMERLY: REPOLMAN CONSTRUCTION) | 424 | 2022 | 2022-09-21 | 02/24/2022 | 349643.6 | 0 | 2022-09-20 |  | 1
2022 | Region III | ZAMBALES | CASTILLEJOS (ZAMBALES) | P00620855LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.2134 | 14.9336 | 82449456.39 | 82024973.17 | 2022 | ORANI CONSTRUCTION AND SUPPLY CORPORATION (FORMERLY:ORANI BUILDERS & SUPPLY) | 425 | 2022 | 2022-08-24 | 02/18/2022 | 424483.22 | 0 | 2022-10-14 | 51
2023 | Region III | ZAMBALES | CASTILLEJOS (ZAMBALES) | P00726518LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.2143 | 14.9302 | 49214932.34 | 49214867.35 | 2023 | ORANI CONSTRUCTION AND SUPPLY CORPORATION (FORMERLY:ORANI BUILDERS & SUPPLY) | 426 | 2023 | 2023-08-28 | 02/14/2023 | 64.99 | 0 | 2023-09-10 | 13
2023 | Region I | PANGASINAN | BUGALLON (PANGASINAN) | P00737423LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.2177 | 15.9743 | 34650000 | 34649388.88 | 2023 | GEORAVIN CONSTRUCTION & SUPPLIES / ALCEL CONSTRUCTION | 427 | 2023 | 2023-09-25 | 03/16/2023 | 611.12 | 0 | 2023-09-24 |  | 1
2023 | Region III | ZAMBALES | SUBIC (ZAMBALES) | P00727155LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.222 | 14.9243 | 48588038.51 | 48588399.53 | 2023 | REPOLMAN CONSTRUCTION CORP. (FORMERLY: REPOLMAN CONSTRUCTION) | 428 | 2023 | 2023-07-27 | 03/03/2023 | 0 | 361.02 | 2023-08-28 | 32
2023 | Region I | PANGASINAN | BUGALLON (PANGASINAN) | P00737424LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.223 | 15.9883 | 34650000 | 34649416.67 | 2023 | ALCEL CONSTRUCTION | 429 | 2023 | 2023-12-23 | 03/14/2023 | 583.33 | 0 | 2023-12-22 |  | 1
2023 | Region III | ZAMBALES | SUBIC (ZAMBALES) | P00725741LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.2248 | 14.8907 | 77199352.81 | 77199858.11 | 2023 | MCB ZAMORA CONSTRUCTION & SUPPLY | 430 | 2023 | 2023-07-07 | 02/14/2023 | 0 | 505.3 | 2023-10-27 | 112
2022 | Region III | ZAMBALES | SUBIC (ZAMBALES) | P00637078LZ | Rehabilitation / Major Repair of Drainage Structure | 120.2269 | 14.927 | 48999837.71 | 48999925.14 | 2022 | REPOLMAN CONSTRUCTION CORP. (FORMERLY: REPOLMAN CONSTRUCTION) | 431 | 2022 | 2022-09-19 | 03/24/2022 | 0 | 87.43 | 2022-09-18 |  | 1
2022 | Region I | PANGASINAN | BUGALLON (PANGASINAN) | P00620960LZ | Construction of Flood Mitigation Structure | 120.2364 | 15.9756 | 29400000 | 29395977.64 | 2022 | PANGASINAN NEW WILSON LUMBER & CONSTRUCTION SUPPLY | 432 | 2022 | 2022-09-29 | 03/25/2022 | 4022.36 | 0 | 2022-09-17 |  | 12
2023 | Region III | ZAMBALES | SUBIC (ZAMBALES) | P00725742LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.2391 | 14.8619 | 67549574.77 | 67549986.63 | 2023 | STO. CRISTO CONSTRUCTION & TRADING INC. (FOR: STO. CRISTO CONSTRUCTION & TRADING) | 433 | 2023 | 2023-05-10 | 02/14/2023 | 0 | 411.86 | 2023-10-10 | 153
2022 | Region I | PANGASINAN | BUGALLON (PANGASINAN) | P00620959LZ | Construction of Flood Mitigation Structure | 120.2394 | 15.9424 | 29400000 | 29397122.87 | 2022 | PANGASINAN NEW WILSON LUMBER & CONSTRUCTION SUPPLY | 434 | 2022 | 2022-11-25 | 03/25/2022 | 2877.13 | 0 | 2022-09-17 |  | 69
2022 | Region I | PANGASINAN | BUGALLON (PANGASINAN) | P00620961LZ | Construction of Flood Mitigation Structure | 120.2401 | 15.9457 | 39200000 | 39196253.39 | 2022 | ALCEL CONSTRUCTION | 435 | 2022 | 2022-11-25 | 03/25/2022 | 3746.61 | 0 | 2022-09-29 |  | 57
2024 | Region III | ZAMBALES | SUBIC (ZAMBALES) | P00825100LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.2401 | 14.8628 | 96499504.04 | 96499707.06 | 2024 | STO. CRISTO CONSTRUCTION & TRADING INC. (FOR: STO. CRISTO CONSTRUCTION & TRADING) | 436 | 2024 | 2024-05-24 | 02/14/2024 | 0 | 203.02 | 2024-12-23 | 213
2022 | Region I | PANGASINAN | BUGALLON (PANGASINAN) | P00620957LZ | Construction of Flood Mitigation Structure | 120.2421 | 15.9588 | 44100000 | 44095038.26 | 2022 | ALCEL CONSTRUCTION | 437 | 2022 | 2022-10-28 | 03/25/2022 | 4961.74 | 0 | 2022-10-05 |  | 23
2024 | Region III | ZAMBALES | SUBIC (ZAMBALES) | P00825244LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.2442 | 14.8512 | 48999685.29 | 48999585.54 | 2024 | MICKAJETTE CONSTRUCTION AND TRADING | 438 | 2024 | 2024-07-25 | 02/14/2024 | 99.75 | 0 | 2024-09-09 | 46
2024 | Region IV-B | ROMBLON | LOOC (ROMBLON) | P00820966LZ | Construction of Flood Mitigation Structure | 120.2454 | 13.7609 | 19600000 | 19599535.39 | 2024 | KEJAMARENIK CONSTRUCTION & CONSTRUCTION SUPPLIES | 439 | 2024 | 2024-09-08 | 02/06/2024 | 464.61 | 0 | 2024-09-07 |  | 1
2022 | Region I | PANGASINAN | AGUILAR (PANGASINAN) | P00620963LZ | Construction of Flood Mitigation Structure | 120.2461 | 15.9105 | 44100000 | 43320017.5 | 2022 | ALCEL CONSTRUCTION | 440 | 2022 | 2022-10-01 | 03/25/2022 | 779982.5 | 0 | 2022-11-09 | 39
2023 | Region IV-B | OCCIDENTAL MINDORO | LOOC (OCCIDENTAL MINDORO) | P00737549LZ | Construction of Flood Mitigation Structure | 120.2462 | 13.7613 | 4900000 | 4899368.2 | 2023 | KEJAMARENIK CONSTRUCTION & CONSTRUCTION SUPPLIES | 441 | 2023 | 2023-04-25 | 02/10/2023 | 631.8 | 0 | 2023-04-24 |  | 1
2023 | Region IV-B | OCCIDENTAL MINDORO | LOOC (OCCIDENTAL MINDORO) | P00742454LZ | Construction of Flood Mitigation Structure | 120.2568 | 13.7133 | 4900000 | 4899326.3 | 2023 | KEJAMARENIK CONSTRUCTION & CONSTRUCTION SUPPLIES | 442 | 2023 | 2023-08-05 | 03/24/2023 | 673.7 | 0 | 2023-08-04 |  | 1
2023 | Region IV-B | PALAWAN | EL NIDO (BACUIT) (PALAWAN) | P00727181LZ | Construction of Flood Mitigation Structure | 120.2569 | 13.7134 | 49000000 | 48999373.17 | 2024 | FAAA CONSTRUCTION AND TRADING / D.K. JOCSON CONSTRUCTION | 443 | 2023 | 2024-05-10 | 03/10/2023 | 626.83 | 0 | 2023-11-26 |  | 166
2022 | Region III | ZAMBALES | SUBIC (ZAMBALES) | P00620205LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.2589 | 14.8663 | 82024735.32 | 82024855.75 | 2022 | MARKBILT CONSTRUCTION TRADING & DEVELOPMENT CORP. (FORMERLY:MARKBILT CONSTRUCTION) | 444 | 2022 | 2022-08-19 | 02/17/2022 | 0 | 120.43 | 2022-09-13 | 25
2022 | Region I | PANGASINAN | BINMALEY (PANGASINAN) | P00632743LZ | Construction of Drainage Structure | 120.2619 | 16.0349 | 2970000 | 2874135.77 | 2022 | ST. ALMERS CONSTRUCTION AND ENTERPRISE | 445 | 2022 | 2022-07-16 | 02/23/2022 | 95864.23 | 0 | 2022-05-11 |  | 66
2022 | Region III | ZAMBALES | SUBIC (ZAMBALES) | P00620206LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.2645 | 14.8764 | 77199737.36 | 77199747.86 | 2022 | MARKBILT CONSTRUCTION TRADING & DEVELOPMENT CORP. (FORMERLY:MARKBILT CONSTRUCTION) | 446 | 2022 | 2022-07-21 | 02/17/2022 | 0 | 10.5 | 2022-09-13 | 54
2023 | Region III | ZAMBALES | OLONGAPO CITY (ZAMBALES) | P00726516LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.2681 | 14.8233 | 77198954.4 | 77199995.6 | 2023 | JAMJLE PROPERTIES (SUBIC) AND DEVELOPMENT CORPORAT | 447 | 2023 | 2023-10-28 | 02/14/2023 | 0 | 1041.2 | 2023-10-27 |  | 1
2024 | Region I | PANGASINAN | AGUILAR (PANGASINAN) | P00845907LZ | Construction of Flood Mitigation Structure | 120.2698 | 15.8856 | 9900000 | 9900000 | 2024 | MIGHTYWAY CONSTRUCTION AND SUPPLY | 448 | 2024 | 2024-05-17 | 04/03/2024 | 0 | 0 | 2024-07-18 | 62
2024 | Region I | PANGASINAN | AGUILAR (PANGASINAN) | P00821484LZ | Construction of Flood Mitigation Structure | 120.2698 | 15.8856 | 48250000 | 48249995.84 | 2024 | RANIA CONSTRUCTION AND SUPPLIES / JHI CONSTRUCTION & SUPPLY | 449 | 2024 | 2024-04-19 | 02/26/2024 | 4.16 | 0 | 2024-09-22 | 156
2022 | Region III | ZAMBALES | OLONGAPO CITY (ZAMBALES) | P00620201LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.2704 | 14.8261 | 77199808.4 | 77199029.61 | 2022 | JAMJLE PROPERTIES (SUBIC) AND DEVELOPMENT CORPORAT | 450 | 2022 | 2022-10-21 | 02/24/2022 | 778.79 | 0 | 2022-10-20 |  | 1
2022 | Region III | ZAMBALES | OLONGAPO CITY (ZAMBALES) | P00621292LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.2726 | 14.8287 | 82024420.48 | 82024373.44 | 2022 | 11-16 CONSTRUCTION | 451 | 2022 | 2022-09-23 | 03/24/2022 | 47.04 | 0 | 2023-01-16 | 115
2022 | Region I | PANGASINAN | AGUILAR (PANGASINAN) | P00620962LZ | Construction of Flood Mitigation Structure | 120.276 | 15.8739 | 44100000 | 44098697.87 | 2022 | GOLDRICH CONSTRUCTION & TRADING | 452 | 2022 | 2022-10-04 | 03/25/2022 | 1302.13 | 0 | 2022-11-07 | 34
2022 | Region I | PANGASINAN | SAN CARLOS CITY (PANGASINAN) | P00620980LZ | Construction of Flood Mitigation Structure | 120.2762 | 15.8788 | 49000000 | 48999983.45 | 2022 | J.G. GARCIA CONSTRUCTION & SUPPLY (FOR: J.G. GARCIA CONST.) | 453 | 2022 | 2022-08-26 | 02/21/2022 | 16.55 | 0 | 2022-10-05 | 40
2024 | Region III | ZAMBALES | OLONGAPO CITY (ZAMBALES) | P00825098LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.2766 | 14.8334 | 96499842.11 | 96499999.98 | 2024 | JAMJLE PROPERTIES (SUBIC) AND DEVELOPMENT CORPORAT | 454 | 2024 | 2024-06-21 | 02/16/2024 | 0 | 157.87 | 2024-12-25 | 187
2022 | Region III | ZAMBALES | OLONGAPO CITY (ZAMBALES) | P00621288LZ | Construction of Flood Mitigation Structure | 120.2828 | 14.8428 | 48999957.94 | 48249970.41 | 2022 | GCLT CONSTRUCTION INCORPORATED (FORMERLY: GCLT CONSTRUCTION) | 455 | 2022 | 2022-08-29 | 03/24/2022 | 749987.53 | 0 | 2022-09-18 | 20
2024 | Region I | PANGASINAN | AGUILAR (PANGASINAN) | P00821108LZ | Construction of Flood Mitigation Structure | 120.2833 | 15.8669 | 96500000 | 96499988.29 | 2024 | ST. GERRARD CONSTRUCTION GEN. CONTRACTOR & DEVELOPMENT CORP. (FORMERLY:ST. GERRARD CONSTRUCTION) | 456 | 2024 | 2024-07-08 | 02/26/2024 | 11.71 | 0 | 2024-12-13 | 158
2022 | Region III | ZAMBALES | OLONGAPO CITY (ZAMBALES) | P00640458LZ | Rehabilitation / Major Repair of Drainage Structure | 120.2837 | 14.8383 | 9799917.08 | 9899964.4 | 2022 | ALFEL CONSTRUCTION CORPORATION | 457 | 2022 | 2022-07-21 | 03/24/2022 | 0 | 100047.32 | 2022-07-20 |  | 1
2022 | Region III | ZAMBALES | OLONGAPO CITY (ZAMBALES) | P00620200LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.2838 | 14.8432 | 77198048.59 | 77199586.11 | 2022 | STO. CRISTO CONSTRUCTION & TRADING INC. (FOR: STO. CRISTO CONSTRUCTION & TRADING) | 458 | 2022 | 2022-08-22 | 03/24/2022 | 0 | 1537.52 | 2022-12-17 | 117
2022 | Region III | ZAMBALES | OLONGAPO CITY (ZAMBALES) | P00620556LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.2867 | 14.8465 | 38599328.1 | 39199639.49 | 2022 | STO. CRISTO CONSTRUCTION & TRADING INC. (FOR: STO. CRISTO CONSTRUCTION & TRADING) | 459 | 2022 | 2022-07-09 | 02/10/2022 | 0 | 600311.39 | 2022-07-08 |  | 1
2023 | Region I | PANGASINAN | AGUILAR (PANGASINAN) | P00727251LZ | Construction of Flood Mitigation Structure | 120.2881 | 15.8659 | 57900000 | 57899999.6 | 2023 | YPR GEN. CONTRACTOR AND CONSTRUCTION SUPPLY INC. | 460 | 2023 | 2023-07-18 | 03/22/2023 | 0.4 | 0 | 2023-09-26 | 70
2023 | Region I | PANGASINAN | SAN CARLOS CITY (PANGASINAN) | P00726650LZ | Construction of Flood Mitigation Structure | 120.2909 | 15.9189 | 19600000 | 19574868.44 | 2023 | HIGH ROCK CONSTRUCTION AND SUPPLIES INCORPORATED | 461 | 2023 | 2023-08-18 | 06/02/2023 | 25131.56 | 0 | 2023-11-10 | 84
2022 | Region III | ZAMBALES | OLONGAPO CITY (ZAMBALES) | P00620202LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.2911 | 14.8575 | 39199700.76 | 38598913.89 | 2022 | GCLT CONSTRUCTION INCORPORATED (FORMERLY: GCLT CONSTRUCTION) | 462 | 2022 | 2022-08-28 | 03/24/2022 | 600786.87 | 0 | 2022-09-18 | 21
2024 | Region I | PANGASINAN | BAYAMBANG (PANGASINAN) | P00821523LZ | Construction of Flood Mitigation Structure | 120.292 | 15.841 | 49000000 | 47618177.06 | 2024 | ALCEL CONSTRUCTION | 463 | 2024 | 2024-04-17 | 02/06/2024 | 1381822.94 | 0 | 2024-08-22 | 127
2022 | Region I | PANGASINAN | SAN CARLOS CITY (PANGASINAN) | P00620981LZ | Construction of Flood Mitigation Structure | 120.2928 | 15.8361 | 49000000 | 48999994.57 | 2022 | BET CONSTRUCTION & SUPPLY / 2-R CONSTRUCTION SUPPLY | 464 | 2022 | 2022-09-07 | 02/21/2022 | 5.43 | 0 | 2022-09-07 | 0
2023 | Region I | PANGASINAN | SAN CARLOS CITY (PANGASINAN) | P00726651LZ | Construction of Flood Mitigation Structure | 120.2928 | 15.8361 | 49000000 | 47569136.59 | 2023 | HIGH ROCK CONSTRUCTION AND SUPPLIES INCORPORATED / JHI CONSTRUCTION & SUPPLY | 465 | 2023 | 2023-12-18 | 06/02/2023 | 1430863.41 | 0 | 2024-01-06 | 19
2023 | Region III | BATAAN | MORONG (BATAAN) | P00742164LZ | Construction of Flood Mitigation Structure | 120.2962 | 14.653 | 49499996.81 | 49500000 | 2024 | E.R. VENZON CONSTRUCTION | 466 | 2023 | 2024-02-23 | 09/11/2023 | 0 | 3.19 | 2024-03-07 | 13
2022 | Region I | PANGASINAN | BINMALEY (PANGASINAN) | P00632744LZ | Construction of Drainage Structure | 120.2978 | 15.9958 | 4950000 | 4947605.86 | 2022 | ST. ALMERS CONSTRUCTION AND ENTERPRISE | 467 | 2022 | 2022-09-02 | 02/21/2022 | 2394.14 | 0 | 2022-08-01 |  | 32
2024 | Region I | PANGASINAN | BAYAMBANG (PANGASINAN) | P00821522LZ | Construction of Flood Mitigation Structure | 120.299 | 15.859 | 49000000 | 47784593.1 | 2024 | ALCEL CONSTRUCTION | 468 | 2024 | 2024-05-14 | 02/06/2024 | 1215406.9 | 0 | 2024-08-22 | 100
2023 | Region I | PANGASINAN | SAN CARLOS CITY (PANGASINAN) | P00726088LZ | Construction of Flood Mitigation Structure | 120.2999 | 15.9268 | 19600000 | 19597787.66 | 2023 | AQUINO-DELA CRUZ ENGINEERING & CONSTRUCTION | 469 | 2023 | 2023-03-24 | 02/22/2023 | 2212.34 | 0 | 2023-08-02 | 131
2022 | Region III | BATAAN | MORONG (BATAAN) | P00640512LZ | Construction of Flood Mitigation Structure | 120.3005 | 14.6553 | 18809999.75 | 18809999.75 | 2023 | ROCKSTEEL CONSTRUCTION AND DEV'T CORPORATION / EGB CONSTRUCTION CORPORATION (FORMERLY: EGB CONSTRUCTION) | 470 | 2022 | 2023-04-12 | 08/11/2022 | 0 | 0 | 2023-04-13 | 1
2022 | Region I | PANGASINAN | SAN CARLOS CITY (PANGASINAN) | P00620979LZ | Construction of Flood Mitigation Structure | 120.3013 | 15.8581 | 49000000 | 48762586.97 | 2022 | BALLESTEROS CONSTRUCTION AND SUPPLY / J.G. GARCIA CONSTRUCTION & SUPPLY (FOR: J.G. GARCIA CONST.) | 471 | 2022 | 2022-09-08 | 02/21/2022 | 237413.03 | 0 | 2022-09-07 |  | 1
2023 | Region I | PANGASINAN | SAN CARLOS CITY (PANGASINAN) | P00726082LZ | Construction of Flood Mitigation Structure | 120.3057 | 15.9464 | 19600000 | 19599973.46 | 2024 | 2-R CONSTRUCTION SUPPLY | 472 | 2023 | 2024-03-01 | 05/12/2023 | 26.54 | 0 | 2023-12-19 |  | 73
2022 | Region III | TARLAC | SAN JOSE (TARLAC) | P00639357LZ | Construction of Slope Protection Structure | 120.3097 | 15.4856 | 96500000 | 94372250 | 2023 | CHIARA2300 INCORPORATED / LOUREL DEVELOPMENT CORPORATION (FORMERLY :LOUREL D | 473 | 2022 | 2023-01-24 | 03/31/2022 | 2127750 | 0 | 2023-01-23 |  | 1
2022 | Region III | TARLAC | SAN JOSE (TARLAC) | P00639356LZ | Construction of Slope Protection Structure | 120.3099 | 15.4858 | 96500000 | 94381900 | 2023 | CHIARA2300 INCORPORATED / LOUREL DEVELOPMENT CORPORATION (FORMERLY :LOUREL D | 474 | 2022 | 2023-01-24 | 03/31/2022 | 2118100 | 0 | 2023-01-23 |  | 1
2023 | Region I | PANGASINAN | SAN CARLOS CITY (PANGASINAN) | P00726091LZ | Construction of Flood Mitigation Structure | 120.3103 | 15.9045 | 19600000 | 19303732.61 | 2023 | 2-R CONSTRUCTION SUPPLY | 475 | 2023 | 2023-11-17 | 05/12/2023 | 296267.39 | 0 | 2023-11-18 | 1
2022 | Region III | TARLAC | SAN JOSE (TARLAC) | P00639355LZ | Construction of Slope Protection Structure | 120.3126 | 15.4857 | 96500000 | 94251550 | 2022 | LOUREL DEVELOPMENT CORPORATION (FORMERLY :LOUREL D / THREE W BUILDERS, INC. | 476 | 2022 | 2022-11-25 | 03/31/2022 | 2248450 | 0 | 2022-11-24 |  | 1
2022 | Region I | LA UNION | BAUANG (LA UNION) | P00631076LZ | Construction of Flood Mitigation Structure | 120.3128 | 16.5239 | 34299994.43 | 33712619 | 2023 | J.G. GARCIA CONSTRUCTION & SUPPLY (FOR: J.G. GARCIA CONST.) | 477 | 2022 | 2023-11-27 | 02/18/2022 | 587375.43 | 0 | 2022-08-11 |  | 473
2022 | Region III | TARLAC | SAN JOSE (TARLAC) | P00639354LZ | Construction of Slope Protection Structure | 120.3129 | 15.4869 | 96500000 | 94261200 | 2022 | LOUREL DEVELOPMENT CORPORATION (FORMERLY :LOUREL D / THREE W BUILDERS, INC. | 478 | 2022 | 2022-11-25 | 03/31/2022 | 2238800 | 0 | 2022-11-24 |  | 1
2021 | Region III | ZAMBALES |  | P00525600LZ | Rehabilitation / Major Repair of Drainage Structure | 120.3143 | 14.8628 | 77199921.43 | 77199992.48 | 2022 | STO. CRISTO CONSTRUCTION & TRADING INC. (FOR: STO. CRISTO CONSTRUCTION & TRADING) | 479 | 2021 | 2022-11-27 | 09/12/2022 | 0 | 71.05 | 2023-04-08 | 132
2022 | Region I | PANGASINAN | MANGATAREM (PANGASINAN) | P00620958LZ | Construction of Flood Mitigation Structure | 120.3148 | 15.8291 | 44100000 | 44095982.31 | 2022 | ALCEL CONSTRUCTION | 480 | 2022 | 2022-10-04 | 03/25/2022 | 4017.69 | 0 | 2022-10-05 | 1
2022 | Region I | LA UNION | CITY OF SAN FERNANDO (CAPITAL) (LA UNION) | P00620940LZ | Construction of Flood Mitigation Structure | 120.3154 | 16.6231 | 7839873.81 | 7463294.58 | 2022 | MOLTE ARIES CONSTRUCTION AND INDUSTRIES | 481 | 2022 | 2022-08-01 | 02/18/2022 | 376579.23 | 0 | 2022-06-17 |  | 45
2024 | Region I | PANGASINAN | SAN CARLOS CITY (PANGASINAN) | P00839560LZ | Construction of Drainage Structure | 120.317 | 15.877 | 9900000 | 9662405.17 | 2024 | JEUSMACK BUILDERS & CONSTRUCTION SUPPLY | 482 | 2024 | 2024-07-18 | 02/23/2024 | 237594.83 | 0 | 2024-10-06 | 80
2023 | Region III | ZAMBALES | OLONGAPO CITY (ZAMBALES) | P00726922LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.318 | 14.862 | 77199782.89 | 77199948.01 | 2023 | JAMJLE PROPERTIES (SUBIC) AND DEVELOPMENT CORPORAT | 483 | 2023 | 2023-11-25 | 03/15/2023 | 0 | 165.12 | 2023-11-24 |  | 1
2023 | Region I | PANGASINAN | SAN CARLOS CITY (PANGASINAN) | P00726085LZ | Construction of Flood Mitigation Structure | 120.318 | 15.8773 | 19600000 | 19295169.83 | 2023 | 5J AND G CONSTRUCTION AND SUPPLY | 484 | 2023 | 2023-07-13 | 02/22/2023 | 304830.17 | 0 | 2023-08-02 | 20
2023 | Region I | LA UNION | CITY OF SAN FERNANDO (CAPITAL) (LA UNION) | P00737415LZ | Construction of Drainage Structure | 120.3183 | 16.605 | 9899975.9 | 9898634.44 | 2023 | KRB CONSTRUCTION | 485 | 2023 | 2023-08-21 | 02/20/2023 | 1341.46 | 0 | 2023-08-20 |  | 1
2023 | Region I | LA UNION | BAUANG (LA UNION) | P00726639LZ | Construction of Flood Mitigation Structure | 120.3183 | 16.5145 | 48999961.06 | 48977484.4 | 2024 | JABEN GENERAL CONTRACTING & ENG'G SERVICES | 486 | 2023 | 2024-02-11 | 01/31/2023 | 22476.66 | 0 | 2023-08-14 |  | 181
2024 | Region I | LA UNION | CITY OF SAN FERNANDO (CAPITAL) (LA UNION) | P00820116LZ | Construction of Flood Mitigation Structure | 120.3203 | 16.6284 | 84262432.59 | 82970000 | 2024 | MY BUILDERS AND CONSTRUCTION | 487 | 2024 | 2024-07-26 | 02/14/2024 | 1292432.59 | 0 | 2024-12-19 | 146
2023 | Region I | LA UNION | BAUANG (LA UNION) | P00735957LZ | Construction of Flood Mitigation Structure | 120.3206 | 16.5629 | 78400000 | 77199988 | 2024 | C.T. LEONCIO CONSTRUCTION & TRADING | 488 | 2023 | 2024-04-18 | 03/16/2023 | 1200012 | 0 | 2024-04-17 |  | 1
2023 | Region I | LA UNION | CITY OF SAN FERNANDO (CAPITAL) (LA UNION) | P00726052LZ | Construction of Flood Mitigation Structure | 120.3211 | 16.6265 | 30371165.22 | 30370180 | 2023 | MY BUILDERS AND CONSTRUCTION | 489 | 2023 | 2023-07-12 | 02/17/2023 | 985.22 | 0 | 2023-09-07 | 57
2023 | Region I | LA UNION | BAUANG (LA UNION) | P00726640LZ | Construction of Flood Mitigation Structure | 120.3214 | 16.5155 | 30869993.99 | 30865253.84 | 2023 | RODEKOM GENERAL CONSTRUCTION AND ENTERPRISE | 490 | 2023 | 2023-07-02 | 02/06/2023 | 4740.15 | 0 | 2023-07-01 |  | 1
2023 | Region III | PAMPANGA | PORAC (PAMPANGA) | P00742354LZ | Construction of Drainage Structure | 120.3233 | 15.035 | 47519665.79 | 47513188.02 | 2024 | R.M. VITUG CONSTRUCTION / OMICRON CONSTRUCTION | 491 | 2023 | 2024-02-17 | 08/22/2023 | 6477.77 | 0 | 2024-02-16 |  | 1
2024 | Region I | LA UNION | CITY OF SAN FERNANDO (CAPITAL) (LA UNION) | P00839550LZ | Rehabilitation / Major Repair of Drainage Structure | 120.324 | 16.6252 | 9899620.42 | 9897604.6 | 2024 | ARM-ASIA CONSTRUCTION & ENGINEERING | 492 | 2024 | 2024-06-27 | 02/14/2024 | 2015.82 | 0 | 2024-06-27 | 0
2024 | Region I | LA UNION | SAN JUAN (LA UNION) | P00845900LZ | Construction of Drainage Structure | 120.324 | 16.6625 | 4949920.57 | 4949472.5 | 2025 | AYANA CONSTRUCTION AND TRADING | 493 | 2024 | 2025-01-24 | 03/22/2024 | 448.07 | 0 | 2024-12-01 |  | 54
2022 | Region I | LA UNION | BAUANG (LA UNION) | P00620949LZ | Construction of Flood Mitigation Structure | 120.3246 | 16.5203 | 45591559.23 | 44792502.5 | 2022 | J.G. GARCIA CONSTRUCTION & SUPPLY (FOR: J.G. GARCIA CONST.) | 494 | 2022 | 2022-07-28 | 02/18/2022 | 799056.73 | 0 | 2022-07-27 |  | 1
2023 | Region I | PANGASINAN | SAN CARLOS CITY (PANGASINAN) | P00726089LZ | Construction of Flood Mitigation Structure | 120.3247 | 15.8648 | 19600000 | 19599908.59 | 2023 | MIGHTYWAY CONSTRUCTION AND SUPPLY | 495 | 2023 | 2023-08-03 | 02/22/2023 | 91.41 | 0 | 2023-08-02 |  | 1
2024 | Region I | PANGASINAN | DAGUPAN CITY (PANGASINAN) | P00825212LZ | Construction of Flood Mitigation Structure | 120.3256 | 16.045 | 49000000 | 48994543.21 | 2024 | J.G. GARCIA CONSTRUCTION & SUPPLY (FOR: J.G. GARCIA CONST.) | 496 | 2024 | 2024-09-06 | 02/28/2024 | 5456.79 | 0 | 2024-09-16 | 10
2023 | Region I | PANGASINAN | SAN CARLOS CITY (PANGASINAN) | P00726086LZ | Construction of Flood Mitigation Structure | 120.3278 | 15.9418 | 19600000 | 19599224.91 | 2023 | 2-R CONSTRUCTION SUPPLY | 497 | 2023 | 2023-11-30 | 02/22/2023 | 775.09 | 0 | 2023-10-01 |  | 60
2023 | Region I | PANGASINAN | SAN CARLOS CITY (PANGASINAN) | P00726083LZ | Construction of Flood Mitigation Structure | 120.3281 | 15.8792 | 19600000 | 19162877.93 | 2023 | 2-R CONSTRUCTION SUPPLY | 498 | 2023 | 2023-11-10 | 06/02/2023 | 437122.07 | 0 | 2023-11-10 | 0
2023 | Region I | PANGASINAN | DAGUPAN CITY (PANGASINAN) | P00727089LZ | Construction of Flood Mitigation Structure | 120.3282 | 16.0486 | 49000000 | 48995295.6 | 2023 | BET CONSTRUCTION & SUPPLY | 499 | 2023 | 2023-07-27 | 05/12/2023 | 4704.4 | 0 | 2023-11-28 | 124
2022 | Region I | PANGASINAN | DAGUPAN CITY (PANGASINAN) | P00620457LZ | Construction of Flood Mitigation Structure | 120.3288 | 16.0459 | 49000000 | 48995746.66 | 2023 | ARCINUE COMM'L CORPORATION | 500 | 2022 | 2023-01-23 | 02/18/2022 | 4253.34 | 0 | 2023-01-22 |  | 1
2022 | Region I | PANGASINAN | DAGUPAN CITY (PANGASINAN) | P00620459LZ | Construction of Flood Mitigation Structure | 120.3731 | 16.1106 | 24500000 | 23274708.85 | 2022 | R.A. MATIAS CONSTRUCTION AND DEVELOPERS INC. (FORMERLY : R.A. MATIAS CONSTRUCTION AND DEVELOPERS) | 501 | 2022 | 2022-12-14 | 02/18/2022 | 1225291.15 | 0 | 2022-07-16 |  | 151
2023 | Region I | LA UNION | ARINGAY (LA UNION) | P00727238LZ | Construction of Flood Mitigation Structure | 120.3731 | 16.3937 | 72374999.59 | 72334999.59 | 2024 | MG SAMIDAN CONSTRUCTION | 502 | 2023 | 2024-02-11 | 04/19/2023 | 40000 | 0 | 2023-12-09 |  | 64
2023 | Region III | TARLAC | MAYANTOC (TARLAC) | P00727152LZ | Construction of Flood Mitigation Structure | 120.3732 | 15.62 | 34300000 | 34300000 | 2023 | LAMASIA BUILDERS AND SUPPLY CORP. | 503 | 2023 | 2023-06-26 | 03/06/2023 | 0 | 0 | 2023-08-16 | 51
2023 | Region I | PANGASINAN | SAN CARLOS CITY (PANGASINAN) | P00726092LZ | Construction of Flood Mitigation Structure | 120.3733 | 15.937 | 19600000 | 19139413.03 | 2024 | 2-R CONSTRUCTION SUPPLY | 504 | 2023 | 2024-01-25 | 06/02/2023 | 460586.97 | 0 | 2024-04-22 | 88
2023 | Region I | LA UNION | ARINGAY (LA UNION) | P00727239LZ | Construction of Flood Mitigation Structure | 120.3739 | 16.395 | 72374989.79 | 72334989.79 | 2024 | MG SAMIDAN CONSTRUCTION | 505 | 2023 | 2024-02-11 | 04/19/2023 | 40000 | 0 | 2023-12-09 |  | 64
2022 | Region I | PANGASINAN | MANGALDAN (PANGASINAN) | P00639432LZ | Construction of Drainage Structure | 120.3741 | 16.0625 | 4900000 | 4897000 | 2022 | J.G. GARCIA CONSTRUCTION & SUPPLY (FOR: J.G. GARCIA CONST.) | 506 | 2022 | 2022-08-14 | 03/28/2022 | 3000 | 0 | 2022-06-13 |  | 62
2024 | Region I | PANGASINAN | CALASIAO (PANGASINAN) | P00820730LZ | Construction of Flood Mitigation Structure | 120.3742 | 16.0101 | 48250000 | 48250000 | 2024 | BET CONSTRUCTION & SUPPLY / JEUSMACK BUILDERS & CONSTRUCTION SUPPLY | 507 | 2024 | 2024-07-31 | 03/07/2024 | 0 | 0 | 2024-10-01 | 62
2022 | Region XIII | SURIGAO DEL NORTE | DAPA (SURIGAO DEL NORTE) | P00630561MN | Construction of Flood Mitigation Structure | 126.0472 | 9.7566 | 96500000 | 95535492.09 | 2023 | BOOMETRIX DEVELOPMENT CORP. / MONOLITHIC CONSTRUCTION & CONCRETE PRODUCTS, INC. | 508 | 2022 | 2023-03-19 | 03/06/2022 | 964507.91 | 0 | 2023-03-18 |  | 1
2023 | Region I | LA UNION | AGOO (LA UNION) | P00726828LZ | Construction of Flood Mitigation Structure | 120.375 | 16.3274 | 72375000 | 72373497.78 | 2024 | SILVERWOLVES CONSTRUCTION CORPORATION | 509 | 2023 | 2024-04-05 | 05/12/2023 | 1502.22 | 0 | 2024-04-04 |  | 1
2024 | Region I | LA UNION | BAUANG (LA UNION) | P00824833LZ | Construction of Flood Mitigation Structure | 120.3759 | 16.5152 | 96499999.03 | 96482209.01 | 2024 | HIGH ROCK CONSTRUCTION AND SUPPLIES INCORPORATED / C.T. LEONCIO CONSTRUCTION & TRADING | 510 | 2024 | 2024-05-20 | 02/27/2024 | 17790.02 | 0 | 2024-11-26 | 190
2024 | Region I | LA UNION | BACNOTAN (LA UNION) | P00821109LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.3762 | 16.7347 | 96500000 | 96499911.45 | 2025 | MY BUILDERS AND CONSTRUCTION | 511 | 2024 | 2025-03-14 | 05/03/2024 | 88.55 | 0 | 2025-03-27 | 13
2024 | Region I | PANGASINAN | SAN CARLOS CITY (PANGASINAN) | P00820731LZ | Construction of Flood Mitigation Structure | 120.3786 | 15.9281 | 48250000 | 48216034.15 | 2024 | MIGHTYWAY CONSTRUCTION AND SUPPLY | 512 | 2024 | 2024-09-05 | 04/19/2024 | 33965.85 | 0 | 2024-11-13 | 69
2024 | Region I | PANGASINAN | CALASIAO (PANGASINAN) | P00845922LZ | Construction of Drainage Structure | 120.379 | 16.017 | 6930000 | 6758718.76 | 2024 | JEUSMACK BUILDERS & CONSTRUCTION SUPPLY | 513 | 2024 | 2024-09-03 | 04/19/2024 | 171281.24 | 0 | 2024-10-28 | 55
2023 | Region III | TARLAC | CAMILING (TARLAC) | P00726493LZ | Construction of Flood Mitigation Structure | 120.3793 | 15.6414 | 96500000 | 96500000 | 2023 | ROYAL CROWN MONARCH CONSTRUCTION & SUPPLIES CORP. | 514 | 2023 | 2023-10-11 | 02/10/2023 | 0 | 0 | 2023-10-10 |  | 1
2023 | Region I | PANGASINAN | CALASIAO (PANGASINAN) | P00737429LZ | Construction of Drainage Structure | 120.3796 | 16.0202 | 4950000 | 4839885.37 | 2023 | ALPHIN TRADING & CONSTRUCTION | 515 | 2023 | 2023-10-24 | 03/28/2023 | 110114.63 | 0 | 2023-10-25 | 1
2024 | Region I | ILOCOS SUR | SAN ILDEFONSO (ILOCOS SUR) | P00844707LZ | Construction of Flood Mitigation Structure | 120.3802 | 17.6093 | 14700000 | 14546995.06 | 2024 | AB DIAMOND23 CONSTRUCTION | 516 | 2024 | 2024-09-13 | 04/11/2024 | 153004.94 | 0 | 2024-09-19 | 6
2021 | Region III | BATAAN |  | P00525982LZ | Construction of Flood Mitigation Structure | 120.3804 | 14.8523 | 48999999.36 | 40961972.01 | 2022 | ORANI CONSTRUCTION AND SUPPLY CORPORATION (FORMERLY:ORANI BUILDERS & SUPPLY) | 517 | 2021 | 2022-12-12 | 07/19/2021 | 8038027.35 | 0 | 2023-03-14 | 92
2021 | Region I | LA UNION |  | P00561633LZ | Construction of Slope Protection Structure | 120.381 | 16.2885 | 9899995.88 | 9502019.1 | 2022 | E.E. MADAYAG CONSTRUCTION | 518 | 2021 | 2022-08-01 | 03/03/2021 | 397976.78 | 0 | 2021-09-04 |  | 331
2024 | Region I | LA UNION | ARINGAY (LA UNION) | P00839553LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.381 | 16.401 | 49500000 | 49499698.64 | 2024 | MG SAMIDAN CONSTRUCTION / KRYPTONITE 6S BUILDERS INC. | 519 | 2024 | 2024-06-15 | 04/08/2024 | 301.36 | 0 | 2024-09-27 | 104
2024 | Region I | LA UNION | ARINGAY (LA UNION) | P00824804LZ | Construction of Flood Mitigation Structure | 120.381 | 16.4075 | 144750000 | 144749933 | 2024 | ROCK-WBL CONSTRUCTION CORP. (FOR: ROCK-WBL CONSTRUCTION TRADING & SERVICES) | 520 | 2024 | 2024-08-10 | 05/03/2024 | 67 | 0 | 2025-01-17 | 160
2021 | Region III | BATAAN |  | P00525983LZ | Construction of Flood Mitigation Structure | 120.3811 | 14.8519 | 49000000 | 48999999.48 | 2022 | ORANI CONSTRUCTION AND SUPPLY CORPORATION (FORMERLY:ORANI BUILDERS & SUPPLY) | 521 | 2021 | 2022-11-08 | 03/26/2021 | 0.52 | 0 | 2022-11-09 | 1
2022 | Region I | ILOCOS SUR | SAN VICENTE (ILOCOS SUR) | P00632731LZ | Construction of Drainage Structure | 120.3811 | 17.5867 | 29700000 | 29700000 | 2023 | R.B. PANO CONSTRUCTION CORP. (FORMERLY: R.B. PANO CONSTRUCTION AND SUPPLY) | 522 | 2022 | 2023-07-17 | 02/10/2022 | 0 | 0 | 2022-12-19 |  | 210
2023 | Region I | PANGASINAN | MANGALDAN (PANGASINAN) | P00737418LZ | Construction of Drainage Structure | 120.3813 | 16.049 | 4950000 | 4944500 | 2023 | MIGHTYWAY CONSTRUCTION AND SUPPLY | 523 | 2023 | 2023-07-19 | 02/16/2023 | 5500 | 0 | 2023-07-18 |  | 1
2021 | Region I | ILOCOS SUR |  | P00525871LZ | Construction of Revetment | 120.3816 | 17.6097 | 14700000 | 14700000 | 2022 | FIT CONSTRUCTION | 524 | 2021 | 2022-07-01 | 02/24/2022 | 0 | 0 | 2022-07-04 | 3
2022 | Region I | LA UNION | NAGUILIAN (LA UNION) | P00620953LZ | Construction of Flood Mitigation Structure | 120.3824 | 16.5099 | 46059995.61 | 45075785.1 | 2022 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | 525 | 2022 | 2022-08-22 | 02/16/2022 | 984210.51 | 0 | 2022-08-15 |  | 7
2022 | Region III | BATAAN | HERMOSA (BATAAN) | P00620499LZ | Construction of Flood Mitigation Structure | 120.3825 | 14.8495 | 24499999.88 | 24499999.7 | 2022 | VM BUILDERS CONSTRUCTION CORPORATION | 526 | 2022 | 2022-09-26 | 02/21/2022 | 0.18 | 0 | 2022-09-27 | 1
2023 | Region I | PANGASINAN | MANGALDAN (PANGASINAN) | P00737420LZ | Construction of Drainage Structure | 120.3826 | 16.0721 | 4950000 | 4944700 | 2023 | J.G. GARCIA CONSTRUCTION & SUPPLY (FOR: J.G. GARCIA CONST.) | 527 | 2023 | 2023-05-20 | 02/16/2023 | 5300 | 0 | 2023-05-19 |  | 1
2023 | Region III | TARLAC | CAMILING (TARLAC) | P00726494LZ | Construction of Flood Mitigation Structure | 120.3828 | 15.6421 | 96500000 | 96500000 | 2023 | ROYAL CROWN MONARCH CONSTRUCTION & SUPPLIES CORP. | 528 | 2023 | 2023-10-11 | 02/10/2023 | 0 | 0 | 2023-10-10 |  | 1
2024 | Region I | PANGASINAN | SANTA BARBARA (PANGASINAN) | P00821518LZ | Construction of Flood Mitigation Structure | 120.3828 | 15.9998 | 48250000 | 48249656.72 | 2024 | J.G. GARCIA CONSTRUCTION & SUPPLY (FOR: J.G. GARCIA CONST.) | 529 | 2024 | 2024-09-17 | 03/07/2024 | 343.28 | 0 | 2024-10-01 | 14
2024 | Region I | ILOCOS SUR | SAN ILDEFONSO (ILOCOS SUR) | P00844708LZ | Construction of Flood Mitigation Structure | 120.3832 | 17.6145 | 14700000 | 14646516.95 | 2024 | FIT CONSTRUCTION | 530 | 2024 | 2024-10-19 | 05/10/2024 | 53483.05 | 0 | 2024-10-18 |  | 1
2023 | Region I | ILOCOS SUR | BANTAY (ILOCOS SUR) | P00727064LZ | Construction of Flood Mitigation Structure | 120.3833 | 17.5256 | 39200000 | 39200000 | 2023 | SJ MILLENNIUM CONSTRUCTION AND CONSTRUCTION SUPPLY CORPORATION / EGB CONSTRUCTION CORPORATION (FORMERLY: EGB CONSTRUCTION) | 531 | 2023 | 2023-11-28 | 04/27/2023 | 0 | 0 | 2023-11-26 |  | 2
2023 | Region I | ILOCOS SUR | CITY OF VIGAN (CAPITAL) (ILOCOS SUR) | P00727068LZ | Construction of Drainage Structure | 120.3834 | 17.5582 | 14700000 | 14682103.54 | 2024 | JMCQ CONSTRUCTION AND SUPPLY | 532 | 2023 | 2024-04-02 | 06/14/2023 | 17896.46 | 0 | 2024-01-11 |  | 82
2023 | Region I | ILOCOS SUR | SAN ILDEFONSO (ILOCOS SUR) | P00727067LZ | Construction of Flood Mitigation Structure | 120.3838 | 17.6147 | 34300000 | 34257663.3 | 2023 | A.P.B. CONSTRUCTION / FIT CONSTRUCTION | 533 | 2023 | 2023-11-02 | 03/10/2023 | 42336.7 | 0 | 2023-11-01 |  | 1
2023 | Region III | BATAAN | HERMOSA (BATAAN) | P00726923LZ | Construction of Flood Mitigation Structure | 120.3842 | 14.8491 | 67549999.36 | 67549999.36 | 2023 | AVE-MIRA CONSTRUCTION AND TRADING / ORANI CONSTRUCTION AND SUPPLY CORPORATION (FORMERLY:ORANI BUILDERS & SUPPLY) | 534 | 2023 | 2023-11-22 | 03/30/2023 | 0 | 0 | 2023-11-24 | 2
2024 | Region I | LA UNION | NAGUILIAN (LA UNION) | P00824826LZ | Construction of Flood Mitigation Structure | 120.3845 | 16.5159 | 94569997.62 | 94560757.31 | 2025 | UNIMAX STEEL STRUCTURE AND CONSTRUCTION CORP. | 535 | 2024 | 2025-03-16 | 04/18/2024 | 9240.31 | 0 | 2025-01-13 |  | 62
2023 | Region I | ILOCOS SUR | CITY OF VIGAN (CAPITAL) (ILOCOS SUR) | P00726855LZ | Construction of Flood Mitigation Structure | 120.3846 | 17.5576 | 96500000 | 96499514.67 | 2024 | A.P.B. CONSTRUCTION / AB DIAMOND23 CONSTRUCTION | 536 | 2023 | 2024-02-07 | 05/02/2023 | 485.33 | 0 | 2024-02-06 |  | 1
2024 | Region I | LA UNION | NAGUILIAN (LA UNION) | P00824811LZ | Construction of Flood Mitigation Structure | 120.3849 | 16.5131 | 94569997.8 | 94560825.52 | 2025 | MG SAMIDAN CONSTRUCTION | 537 | 2024 | 2025-01-14 | 04/18/2024 | 9172.28 | 0 | 2025-01-13 |  | 1
2022 | Region I | ILOCOS SUR | CABUGAO (ILOCOS SUR) | P00637049LZ | Construction of Flood Mitigation Structure | 120.3859 | 17.5793 | 49000000 | 44469254.42 | 2022 | NORTH TECH BUILDERS AND CONSTRUCTION SUPPLY | 538 | 2022 | 2022-12-19 | 04/08/2022 | 4530745.58 | 0 | 2022-12-29 | 10
2023 | Region III | TARLAC | CAMILING (TARLAC) | P00726514LZ | Construction of Flood Mitigation Structure | 120.3859 | 15.7466 | 111012270.4 | 111012635 | 2025 | A.C. SOLIVEN CONSTRUCTION & GENERAL MERCHANDISE | 539 | 2023 | 2025-02-10 | 02/27/2023 | 0 | 364.6 | 2025-02-09 |  | 1
2022 | Region I | LA UNION | AGOO (LA UNION) | P00639427LZ | Construction of Slope Protection Structure | 120.386 | 16.3287 | 4900000 | 4751694.41 | 2022 | S-ANG CONSTRUCTION & GENERAL TRADING, INC. | 540 | 2022 | 2022-11-23 | 11/03/2022 | 148305.59 | 0 | 2022-11-22 |  | 1
2023 | Region III | TARLAC | CAMILING (TARLAC) | P00726495LZ | Construction of Flood Mitigation Structure | 120.3862 | 15.644 | 96500000 | 96500000 | 2023 | ROYAL CROWN MONARCH CONSTRUCTION & SUPPLIES CORP. | 541 | 2023 | 2023-10-11 | 02/10/2023 | 0 | 0 | 2023-10-10 |  | 1
2024 | Region I | LA UNION | NAGUILIAN (LA UNION) | P00824828LZ | Construction of Flood Mitigation Structure | 120.3863 | 16.5198 | 96499998.82 | 96492160.98 | 2024 | ANORE CONSTRUCTION | 542 | 2024 | 2024-09-23 | 03/08/2024 | 7837.84 | 0 | 2024-12-06 | 74
2022 | Region I | LA UNION | NAGUILIAN (LA UNION) | P00620951LZ | Construction of Flood Mitigation Structure | 120.3866 | 16.5274 | 46059971.1 | 45147870.9 | 2023 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | 543 | 2022 | 2023-11-27 | 02/16/2022 | 912100.2 | 0 | 2022-09-30 |  | 423
2023 | Region III | TARLAC | CAMILING (TARLAC) | P00726513LZ | Construction of Flood Mitigation Structure | 120.387 | 15.7456 | 192997181.6 | 193000000 | 2025 | BMK CONSTRUCTION CORPORATION (FORMERLY B.M.K. CONSTRUCTION) / ROYAL CROWN MONARCH CONSTRUCTION & SUPPLIES CORP. | 544 | 2023 | 2025-02-10 | 02/27/2023 | 0 | 2818.4 | 2025-02-09 |  | 1
2024 | Region I | LA UNION | BACNOTAN (LA UNION) | P00820104LZ | Construction of Flood Mitigation Structure | 120.3871 | 16.7532 | 84262345.17 | 82971606.98 | 2024 | ARCINUE COMM'L CORPORATION | 545 | 2024 | 2024-07-23 | 02/14/2024 | 1290738.19 | 0 | 2024-12-19 | 149
2023 | Region I | PANGASINAN | SAN CARLOS CITY (PANGASINAN) | P00726075LZ | Construction of Flood Mitigation Structure | 120.3871 | 15.9604 | 19600000 | 19350566.85 | 2023 | JEUSMACK BUILDERS & CONSTRUCTION SUPPLY | 546 | 2023 | 2023-04-18 | 02/13/2023 | 249433.15 | 0 | 2023-07-24 | 97
2024 | Region I | LA UNION | NAGUILIAN (LA UNION) | P00821478LZ | Construction of Flood Mitigation Structure | 120.3874 | 16.5237 | 48999992.02 | 48740182.59 | 2024 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | 547 | 2024 | 2024-05-20 | 02/06/2024 | 259809.43 | 0 | 2024-08-10 | 82
2022 | Region I | PANGASINAN | MANGALDAN (PANGASINAN) | P00631083LZ | Construction of Drainage Structure | 120.3874 | 16.0539 | 49000000 | 49000000 | 2022 | BET CONSTRUCTION & SUPPLY / MIGHTYWAY CONSTRUCTION AND SUPPLY | 548 | 2022 | 2022-10-21 | 02/18/2022 | 0 | 0 | 2022-10-24 | 3
2024 | Region I | LA UNION | NAGUILIAN (LA UNION) | P00824814LZ | Construction of Flood Mitigation Structure | 120.3876 | 16.5192 | 94569998.83 | 94560126.68 | 2025 | MG SAMIDAN CONSTRUCTION | 549 | 2024 | 2025-01-14 | 04/18/2024 | 9872.15 | 0 | 2025-01-13 |  | 1
2023 | Region I | LA UNION | AGOO (LA UNION) | P00727248LZ | Construction of Flood Mitigation Structure | 120.388 | 16.3303 | 72374999.94 | 72334831.82 | 2024 | ROCK-WBL CONSTRUCTION CORP. (FOR: ROCK-WBL CONSTRUCTION TRADING & SERVICES) | 550 | 2023 | 2024-02-11 | 04/19/2023 | 40168.12 | 0 | 2023-12-09 |  | 64
2022 | Region I | LA UNION | NAGUILIAN (LA UNION) | P00620952LZ | Construction of Flood Mitigation Structure | 120.3885 | 16.5278 | 46059998.62 | 45020399.68 | 2022 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | 551 | 2022 | 2022-08-15 | 02/16/2022 | 1039598.94 | 0 | 2022-08-15 | 0
2022 | Region I | LA UNION | AGOO (LA UNION) | P00639428LZ | Construction of Slope Protection Structure | 120.3888 | 16.3237 | 8134000 | 7885653.01 | 2022 | S-ANG CONSTRUCTION & GENERAL TRADING, INC. | 552 | 2022 | 2022-12-02 | 11/03/2022 | 248346.99 | 0 | 2022-12-01 |  | 1
2023 | Region I | PANGASINAN | CALASIAO (PANGASINAN) | P00726063LZ | Construction of Flood Mitigation Structure | 120.3888 | 15.9546 | 49000000 | 48999652.24 | 2023 | MIGHTYWAY CONSTRUCTION AND SUPPLY | 553 | 2023 | 2023-08-11 | 02/13/2023 | 347.76 | 0 | 2023-08-30 | 19
2024 | Region I | LA UNION | NAGUILIAN (LA UNION) | P00824816LZ | Construction of Flood Mitigation Structure | 120.3889 | 16.5217 | 94569998.71 | 94560926.77 | 2025 | MG SAMIDAN CONSTRUCTION | 554 | 2024 | 2025-01-16 | 04/18/2024 | 9071.94 | 0 | 2025-01-13 |  | 3
2024 | Region I | LA UNION | NAGUILIAN (LA UNION) | P00824827LZ | Construction of Flood Mitigation Structure | 120.3891 | 16.5239 | 96499997.99 | 96492336.54 | 2024 | ANORE CONSTRUCTION | 555 | 2024 | 2024-12-23 | 03/08/2024 | 7661.45 | 0 | 2024-12-06 |  | 17
2022 | Region I | LA UNION | AGOO (LA UNION) | P00639429LZ | Construction of Slope Protection Structure | 120.3892 | 16.3225 | 35280000 | 34228109.95 | 2022 | BHM CONSTRUCTION | 556 | 2022 | 2022-12-17 | 11/03/2022 | 1051890.05 | 0 | 2022-12-16 |  | 1
2023 | Region I | ILOCOS SUR | SAN ILDEFONSO (ILOCOS SUR) | P00727063LZ | Construction of Flood Mitigation Structure | 120.39 | 17.6202 | 24500000 | 24500000 | 2023 | SJ MILLENNIUM CONSTRUCTION AND CONSTRUCTION SUPPLY CORPORATION | 557 | 2023 | 2023-08-25 | 04/27/2023 | 0 | 0 | 2023-09-22 | 28
2023 | Region III | BATAAN | BAGAC (BATAAN) | P00725700LZ | Construction of Flood Mitigation Structure | 120.3901 | 14.5931 | 96499351.93 | 96500000 | 2024 | BUILDERS EXPONENT EMPIRE CORP. (FORMERLY: BUILDERS EXPONENT ENTERPRISE) / ORANI CONSTRUCTION AND SUPPLY CORPORATION (FORMERLY:ORANI BUILDERS & SUPPLY) | 558 | 2023 | 2024-05-21 | 04/03/2023 | 0 | 648.07 | 2024-05-20 |  | 1
2021 | Region I | ILOCOS SUR |  | P00561626LZ | Construction of Flood Mitigation Structure | 120.3907 | 17.5752 | 19800000 | 19800000 | 2022 | R.B. PANO CONSTRUCTION CORP. (FORMERLY: R.B. PANO CONSTRUCTION AND SUPPLY) | 559 | 2021 | 2022-12-28 | 06/02/2022 | 0 | 0 | 2023-01-12 | 15
2023 | Region III | TARLAC | CAMILING (TARLAC) | P00726741LZ | Construction of Flood Mitigation Structure | 120.3908 | 15.6421 | 49000000 | 48141152.82 | 2023 | A.C. SOLIVEN CONSTRUCTION & GENERAL MERCHANDISE | 560 | 2023 | 2023-05-25 | 01/30/2023 | 858847.18 | 0 | 2023-07-28 | 64
2023 | Region I | LA UNION | ARINGAY (LA UNION) | P00742275LZ | Construction of Flood Mitigation Structure | 120.391 | 16.3862 | 19599956.48 | 19305948.62 | 2023 | KRYPTONITE 6S BUILDERS INC. | 561 | 2023 | 2023-11-20 | 03/15/2023 | 294007.86 | 0 | 2023-07-30 |  | 113
2021 | Region I | ILOCOS SUR |  | P00561624LZ | Construction of Flood Mitigation Structure | 120.3912 | 17.5735 | 19800000 | 19800000 | 2022 | VIGAN FORTUNE CONSTRUCTION | 562 | 2021 | 2022-09-20 | 06/02/2022 | 0 | 0 | 2022-09-29 | 9
2022 | Region I | ILOCOS SUR | SAN ILDEFONSO (ILOCOS SUR) | P00640493LZ | Construction of Flood Mitigation Structure | 120.3912 | 17.6197 | 4950000 | 4950000 | 2022 | FIT CONSTRUCTION | 563 | 2022 | 2022-07-17 | 04/08/2022 | 0 | 0 | 2022-07-16 |  | 1
2023 | Region I | LA UNION | AGOO (LA UNION) | P00727247LZ | Construction of Flood Mitigation Structure | 120.3915 | 16.3312 | 72374967.69 | 72334831.82 | 2024 | ROCK-WBL CONSTRUCTION CORP. (FOR: ROCK-WBL CONSTRUCTION TRADING & SERVICES) | 564 | 2023 | 2024-02-11 | 04/19/2023 | 40135.87 | 0 | 2023-12-09 |  | 64
2024 | Region I | LA UNION | CABA (LA UNION) | P00843192LZ | Construction of Flood Mitigation Structure | 120.3917 | 16.425 | 48249999.77 | 48244610.83 | 2025 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | 565 | 2024 | 2025-02-16 | 04/03/2024 | 5388.94 | 0 | 2024-10-14 |  | 125
2024 | Region I | PANGASINAN | SANTA BARBARA (PANGASINAN) | P00821519LZ | Construction of Flood Mitigation Structure | 120.3918 | 16.0081 | 48250000 | 46855124.83 | 2024 | RS RODRIGUEZ CONSTRUCTION & SUPPLIES / HIGH ROCK CONSTRUCTION AND SUPPLIES INCORPORATED | 566 | 2024 | 2024-07-30 | 03/07/2024 | 1394875.17 | 0 | 2024-10-01 | 63
2023 | Region III | TARLAC | MAYANTOC (TARLAC) | P00726496LZ | Construction of Flood Mitigation Structure | 120.3922 | 15.6458 | 96500000 | 96500000 | 2023 | ROYAL CROWN MONARCH CONSTRUCTION & SUPPLIES CORP. | 567 | 2023 | 2023-10-11 | 02/10/2023 | 0 | 0 | 2023-10-10 |  | 1
2023 | Region I | PANGASINAN | MANGALDAN (PANGASINAN) | P00737421LZ | Construction of Slope Protection Structure | 120.3923 | 16.0899 | 4950000 | 4948194.59 | 2023 | ZOTA TRADING & CONSTRUCTION | 568 | 2023 | 2023-04-26 | 03/09/2023 | 1805.41 | 0 | 2023-05-16 | 20
2023 | Region I | LA UNION | ARINGAY (LA UNION) | P00742277LZ | Construction of Flood Mitigation Structure | 120.3931 | 16.4113 | 48999969.61 | 48019871.4 | 2024 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | 569 | 2023 | 2024-02-11 | 03/15/2023 | 980098.21 | 0 | 2023-09-26 |  | 138
2022 | Region I | LA UNION | AGOO (LA UNION) | P00639430LZ | Construction of Slope Protection Structure | 120.3932 | 16.313 | 13132000 | 12737486.24 | 2022 | S-ANG CONSTRUCTION & GENERAL TRADING, INC. | 570 | 2022 | 2022-12-02 | 11/03/2022 | 394513.76 | 0 | 2022-12-01 |  | 1
2024 | Region I | LA UNION | ARINGAY (LA UNION) | P00821473LZ | Construction of Flood Mitigation Structure | 120.3938 | 16.4171 | 28949995.54 | 28943409.41 | 2025 | T2B3 BUILDERS AND SUPPLIES CORP. / RPV RED MOUNTAIN KONSTRUCT, INC. | 571 | 2024 | 2025-01-17 | 08/13/2024 | 6586.13 | 0 | 2025-01-31 | 14
2022 | Region III | TARLAC | CAMILING (TARLAC) | P00640526LZ | Construction of Slope Protection Structure | 120.3944 | 15.648 | 49500000 | 49500000 | 2022 | HIGH STRENGTH DEV. CORPORATION / RCUBE ENGINEERING SERVICES | 572 | 2022 | 2022-09-26 | 03/30/2022 | 0 | 0 | 2022-09-25 |  | 1
2024 | Region I | LA UNION | CABA (LA UNION) | P00844722LZ | Construction of Flood Mitigation Structure | 120.3945 | 16.4524 | 48999998.7 | 48995000 | 2025 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | 573 | 2024 | 2025-03-16 | 02/16/2024 | 4998.7 | 0 | 2024-08-29 |  | 199
2022 | Region I | LA UNION | NAGUILIAN (LA UNION) | P00631075LZ | Construction of Flood Mitigation Structure | 120.3949 | 16.545 | 9799998.73 | 9548636.66 | 2022 | E.E. MADAYAG CONSTRUCTION | 574 | 2022 | 2022-07-25 | 02/22/2022 | 251362.07 | 0 | 2022-06-04 |  | 51
2024 | Region I | LA UNION | SAN JUAN (LA UNION) | P00824808LZ | Construction of Flood Mitigation Structure | 120.395 | 16.6632 | 154400000 | 154399985.9 | 2024 | ST. GERRARD CONSTRUCTION GEN. CONTRACTOR & DEVELOPMENT CORP. (FORMERLY:ST. GERRARD CONSTRUCTION) | 575 | 2024 | 2024-04-15 | 03/01/2024 | 14.1 | 0 | 2024-11-24 | 223
2023 | Region I | LA UNION | SAN JUAN (LA UNION) | P00742272LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.3951 | 16.6812 | 5939999.14 | 5839670.96 | 2023 | J.A. OLIVAR ENGINEERING DESIGN, CONSTRUCTION AND S | 576 | 2023 | 2023-07-17 | 04/28/2023 | 100328.18 | 0 | 2023-07-16 |  | 1
2023 | Region III | BATAAN | DINALUPIHAN (BATAAN) | P00725714LZ | Construction of Flood Mitigation Structure | 120.3951 | 14.8478 | 47574499.86 | 47574500 | 2024 | ORANI CONSTRUCTION AND SUPPLY CORPORATION (FORMERLY:ORANI BUILDERS & SUPPLY) | 577 | 2023 | 2024-02-28 | 07/09/2023 | 0 | 0.14 | 2024-02-27 |  | 1
2023 | Region I | PANGASINAN | SAN FABIAN (PANGASINAN) | P00737419LZ | Construction of Drainage Structure | 120.3952 | 16.1143 | 4950000 | 4941245 | 2023 | MIGHTYWAY CONSTRUCTION AND SUPPLY | 578 | 2023 | 2023-05-20 | 02/16/2023 | 8755 | 0 | 2023-05-19 |  | 1
2024 | Region I | LA UNION | NAGUILIAN (LA UNION) | P00824818LZ | Construction of Flood Mitigation Structure | 120.3953 | 16.5224 | 94569996.92 | 94560128.59 | 2025 | UNIVERSAL DE LEON CONSTRUCTION AND AGGREGATES | 579 | 2024 | 2025-03-16 | 04/18/2024 | 9868.33 | 0 | 2025-01-13 |  | 62
2023 | Region I | ILOCOS SUR | SAN ILDEFONSO (ILOCOS SUR) | P00726050LZ | Construction of Flood Mitigation Structure | 120.3954 | 17.6097 | 19600000 | 19600000 | 2023 | SATRAP CONSTRUCTION CO., INC. | 580 | 2023 | 2023-06-17 | 02/17/2023 | 0 | 0 | 2023-06-16 |  | 1
2023 | Region III | TARLAC | MAYANTOC (TARLAC) | P00726497LZ | Construction of Flood Mitigation Structure | 120.3956 | 15.6471 | 96500000 | 96500000 | 2023 | ROYAL CROWN MONARCH CONSTRUCTION & SUPPLIES CORP. | 581 | 2023 | 2023-10-13 | 02/10/2023 | 0 | 0 | 2023-10-10 |  | 3
2023 | Region I | LA UNION | SAN JUAN (LA UNION) | P00727085LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.3959 | 16.6814 | 3108542.23 | 3030571.58 | 2023 | J.A. OLIVAR ENGINEERING DESIGN, CONSTRUCTION AND S | 582 | 2023 | 2023-05-19 | 03/10/2023 | 77970.65 | 0 | 2023-05-18 |  | 1
2024 | Region I | LA UNION | NAGUILIAN (LA UNION) | P00821477LZ | Construction of Flood Mitigation Structure | 120.397 | 16.5227 | 48999999.48 | 48717833.77 | 2024 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | 583 | 2024 | 2024-05-20 | 02/06/2024 | 282165.71 | 0 | 2024-08-10 | 82
2023 | Region III | TARLAC | CAMILING (TARLAC) | P00726194LZ | Construction of Flood Mitigation Structure | 120.3977 | 15.6493 | 49000000 | 48141770.99 | 2023 | A.C. SOLIVEN CONSTRUCTION & GENERAL MERCHANDISE | 584 | 2023 | 2023-06-15 | 01/30/2023 | 858229.01 | 0 | 2023-07-28 | 43
2022 | Region I | LA UNION | CABA (LA UNION) | P00639317LZ | Construction of Slope Protection Structure | 120.3979 | 16.4283 | 241250000 | 241249956 | 2023 | J.H. PAJARA CONSTRUCTION CORPORATION / S-ANG CONSTRUCTION & GENERAL TRADING, INC. | 585 | 2022 | 2023-01-10 | 04/12/2022 | 44 | 0 | 2023-02-04 | 25
2021 | Region III | BATAAN |  | P00525593LZ | Construction of Flood Mitigation Structure | 120.3983 | 14.8468 | 91661488.37 | 91661488.37 | 2022 | ORANI CONSTRUCTION AND SUPPLY CORPORATION (FORMERLY:ORANI BUILDERS & SUPPLY) | 586 | 2021 | 2022-12-26 | 03/31/2022 | 0 | 0 | 2023-05-20 | 145
2024 | Region I | LA UNION | NAGUILIAN (LA UNION) | P00824825LZ | Construction of Flood Mitigation Structure | 120.3985 | 16.5136 | 94569992.94 | 94561818.5 | 2025 | UNIMAX STEEL STRUCTURE AND CONSTRUCTION CORP. | 587 | 2024 | 2025-03-16 | 04/18/2024 | 8174.44 | 0 | 2025-01-13 |  | 62
2021 | Region I | ILOCOS SUR |  | P00525867LZ | Construction of Revetment | 120.3986 | 17.5813 | 14700000 | 14679126.24 | 2022 | SJ MILLENNIUM CONSTRUCTION AND CONSTRUCTION SUPPLY CORPORATION / EGB CONSTRUCTION CORPORATION (FORMERLY: EGB CONSTRUCTION) | 588 | 2021 | 2022-12-06 | 03/24/2022 | 20873.76 | 0 | 2022-12-05 |  | 1
2022 | Region I | ILOCOS SUR | BANTAY (ILOCOS SUR) | P00620937LZ | Construction of Flood Mitigation Structure | 120.3986 | 17.5811 | 24500000 | 24500000 | 2022 | SJ MILLENNIUM CONSTRUCTION AND CONSTRUCTION SUPPLY CORPORATION | 589 | 2022 | 2022-11-06 | 02/10/2022 | 0 | 0 | 2022-11-05 |  | 1
2024 | Region I | LA UNION | BALAOAN (LA UNION) | P00838506LZ | Construction of Flood Mitigation Structure | 120.399 | 16.8212 | 19300000 | 19298382.61 | 2024 | JMBM CONSTRUCTION | 590 | 2024 | 2024-05-31 | 04/08/2024 | 1617.39 | 0 | 2024-09-29 | 121
2023 | Region III | TARLAC | CAMILING (TARLAC) | P00726740LZ | Construction of Flood Mitigation Structure | 120.3992 | 15.6502 | 49000000 | 48140980.09 | 2023 | A.C. SOLIVEN CONSTRUCTION & GENERAL MERCHANDISE | 591 | 2023 | 2023-06-15 | 01/30/2023 | 859019.91 | 0 | 2023-07-28 | 43
2024 | Region I | LA UNION | CABA (LA UNION) | P00844723LZ | Construction of Flood Mitigation Structure | 120.3992 | 16.4292 | 48999999 | 48995000.01 | 2025 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | 592 | 2024 | 2025-02-16 | 02/16/2024 | 4998.99 | 0 | 2024-08-29 |  | 171
2024 | Region I | LA UNION | NAGUILIAN (LA UNION) | P00824822LZ | Construction of Flood Mitigation Structure | 120.3993 | 16.5134 | 94569999.19 | 94562171.36 | 2025 | UNIVERSAL DE LEON CONSTRUCTION AND AGGREGATES | 593 | 2024 | 2025-03-16 | 04/18/2024 | 7827.83 | 0 | 2025-01-13 |  | 62
2024 | Region I | LA UNION | NAGUILIAN (LA UNION) | P00824824LZ | Construction of Flood Mitigation Structure | 120.3995 | 16.5179 | 94569998.62 | 94560506.31 | 2025 | UNIMAX STEEL STRUCTURE AND CONSTRUCTION CORP. | 594 | 2024 | 2025-03-16 | 04/18/2024 | 9492.31 | 0 | 2025-01-13 |  | 62
2022 | Region I | LA UNION | SANTO TOMAS (LA UNION) | P00631071LZ | Construction of Flood Mitigation Structure | 120.3998 | 16.264 | 44099999.49 | 44100000 | 2023 | E.E. MADAYAG CONSTRUCTION | 595 | 2022 | 2023-09-11 | 02/24/2022 | 0 | 0.51 | 2023-02-17 |  | 206
2023 | Region I | LA UNION | ARINGAY (LA UNION) | P00726338LZ | Construction of Flood Mitigation Structure | 120.3999 | 16.3994 | 115800000 | 115799339.3 | 2024 | GREAT PACIFIC BUILDERS AND GEN. CONTRACTOR INC. | 596 | 2023 | 2024-06-05 | 02/14/2023 | 660.7 | 0 | 2024-06-04 |  | 1
2022 | Region III | BATAAN | BAGAC (BATAAN) | P00620508LZ | Construction of Flood Mitigation Structure | 120.4001 | 14.5321 | 49000000 | 49000000 | 2022 | VF CONSTRUCTION / ORANI CONSTRUCTION AND SUPPLY CORPORATION (FORMERLY:ORANI BUILDERS & SUPPLY) | 597 | 2022 | 2022-12-12 | 03/18/2022 | 0 | 0 | 2023-01-04 | 23
2023 | Region III | TARLAC | CAMILING (TARLAC) | P00742372LZ | Construction of Slope Protection Structure | 120.4002 | 15.6517 | 49500000 | 48040048.18 | 2023 | A.C. SOLIVEN CONSTRUCTION & GENERAL MERCHANDISE | 598 | 2023 | 2023-09-13 | 03/17/2023 | 1459951.82 | 0 | 2023-09-12 |  | 1
2024 | Region I | LA UNION | NAGUILIAN (LA UNION) | P00824820LZ | Construction of Flood Mitigation Structure | 120.4002 | 16.5184 | 94569998.62 | 94561136.19 | 2025 | UNIVERSAL DE LEON CONSTRUCTION AND AGGREGATES | 599 | 2024 | 2025-03-16 | 04/18/2024 | 8862.43 | 0 | 2025-01-13 |  | 62
2024 | Region III | TARLAC | CAMILING (TARLAC) | P00821279LZ | Construction of Slope Protection Structure | 120.4004 | 15.6458 | 41791120 | 41151460 | 2024 | GJE BUILDERS CORPORATION (FORMERLY: GJE BUILDERS) | 600 | 2024 | 2024-05-20 | 03/11/2024 | 639660 | 0 | 2024-08-29 | 101
2024 | Region I | LA UNION | CABA (LA UNION) | P00844721LZ | Construction of Flood Mitigation Structure | 120.4006 | 16.4291 | 48999994.05 | 48995000.01 | 2025 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | 601 | 2024 | 2025-03-16 | 02/16/2024 | 4994.04 | 0 | 2024-08-29 |  | 199
2023 | Region XIII | SURIGAO DEL NORTE | DAPA (SURIGAO DEL NORTE) | P00734381MN | Construction of Flood Mitigation Structure | 126.0409 | 9.7638 | 99000000 | 98949816.86 | 2024 | RCDG CONSTRUCTION CORPORATION / KENT MARKETING GROUP OF COMPANIES INC. | 602 | 2023 | 2024-05-21 | 07/13/2023 | 50183.14 | 0 | 2024-05-31 | 10
2021 | Region X | LANAO DEL NORTE |  | P00522069MN | Construction of Flood Mitigation Structure | 124.3129 | 8.1092 | 96489569.26 | 96333246.89 | 2022 | AL HUSSEIN CONSTRUCTION | 603 | 2021 | 2022-12-15 | 11/26/2021 | 156322.37 | 0 | 2022-12-21 | 6
2021 | Region VII | SIQUIJOR |  | P00521556VS | Construction of Flood Mitigation Structure | 123.5142 | 9.1521 | 96500000 | 96499989.16 | 2022 | WTG CONSTRUCTION & DEVELOPMENT CORPORATION | 604 | 2021 | 2022-09-19 | 03/02/2021 | 10.84 | 0 | 2022-09-18 |  | 1
2021 | Region VII | SIQUIJOR |  | P00521555VS | Construction of Flood Mitigation Structure | 123.5144 | 9.1521 | 86662790 | 86662736.91 | 2022 | JASA GD 2000 CONSTRUCTION CORPORATION (FORMERLY:JASA BUILDER'S) | 605 | 2021 | 2022-08-18 | 03/01/2021 | 53.09 | 0 | 2022-08-17 |  | 1
2021 | Region IV-B | PALAWAN |  | P00525653LZ | Construction of Flood Mitigation Structure | 118.2147 | 9.1687 | 120624012.4 | 120624562.1 | 2022 | PTK GROUP INC. / ST. TIMOTHY CONSTRUCTION CORPORATION | 606 | 2021 | 2022-12-31 | 02/18/2021 | 0 | 549.7 | 2023-02-08 | 39
2021 | Region VII | NEGROS ORIENTAL |  | P00521660VS | Construction of Flood Mitigation Structure | 122.7138 | 9.3904 | 49000000 | 49000000 | 2023 | A.D. PENDON CONSTRUCTION & SUPPLY, INC. (FORMERLY: ADP CONSTRUCTION & SUPPLY) | 607 | 2021 | 2023-01-24 | 02/22/2021 | 0 | 0 | 2023-01-23 |  | 1
2021 | Region VII | CEBU |  | P00521644VS | Construction of Flood Mitigation Structure | 123.5277 | 9.7617 | 19600000 | 19600000 | 2022 | O.Q. CONSTRUCTION AND SUPPLY | 608 | 2021 | 2022-07-03 | 10/13/2021 | 0 | 0 | 2022-08-31 | 59
2021 | Region VII | CEBU |  | P00521651VS | Construction of Flood Mitigation Structure | 123.4451 | 10.069 | 29398308.79 | 29398308.79 | 2022 | QM BUILDERS | 609 | 2021 | 2022-10-08 | 03/23/2022 | 0 | 0 | 2022-10-07 |  | 1
2021 | Region VII | CEBU |  | P00521535VS | Construction of Flood Mitigation Structure | 123.8635 | 10.2652 | 96500000 | 96500000 | 2022 | WTG CONSTRUCTION & DEVELOPMENT CORPORATION / LA PRUEBA CONSTRUCTION | 610 | 2021 | 2022-12-28 | 03/24/2022 | 0 | 0 | 2023-01-19 | 22
2021 | Region VII | CEBU |  | P00521536VS | Construction of Flood Mitigation Structure | 123.8698 | 10.2796 | 96500000 | 91209687.18 | 2022 | WTG CONSTRUCTION & DEVELOPMENT CORPORATION | 611 | 2021 | 2022-12-29 | 03/24/2022 | 5290312.82 | 0 | 2023-01-19 | 21
2021 | Region VII | CEBU |  | P00521549VS | Construction of Flood Mitigation Structure | 123.9552 | 10.2806 | 62725000 | 60833104.17 | 2023 | EDANNA CONSTRUCTION / GOLDFIN CONSTRUCTION & DEVELOPMENT CORPORATION (FORMERLY: GOLDFIN CONSTRUCTION) | 612 | 2021 | 2023-07-31 | 03/31/2022 | 1891895.83 | 0 | 2022-10-13 |  | 291
2021 | Region VII | CEBU |  | P00521558VS | Construction of Flood Mitigation Structure | 123.8872 | 10.2863 | 96500000 | 96500000 | 2022 | WTG CONSTRUCTION & DEVELOPMENT CORPORATION | 613 | 2021 | 2022-12-28 | 03/24/2022 | 0 | 0 | 2023-01-19 | 22
2021 | Region VII | CEBU |  | P00521532VS | Construction of Flood Mitigation Structure | 123.9063 | 10.3042 | 96500000 | 82806662.53 | 2022 | C.T. LEONCIO CONSTRUCTION & TRADING | 614 | 2021 | 2022-08-27 | 10/29/2021 | 13693337.47 | 0 | 2022-08-26 |  | 1
2021 | Region VII | CEBU |  | P00521533VS | Construction of Flood Mitigation Structure | 123.9033 | 10.3112 | 96500000 | 96499521.74 | 2022 | JM COLLERA KONSTRACT / C.T. LEONCIO CONSTRUCTION & TRADING | 615 | 2021 | 2022-08-27 | 10/29/2021 | 478.26 | 0 | 2022-08-26 |  | 1
2021 | Region VII | CEBU |  | P00521554VS | Construction of Flood Mitigation Structure | 124.0245 | 10.5283 | 96267435 | 94895726.98 | 2022 | BNR CONSTRUCTION & DEVELOPMENT CORP. / VSP STRUCTURE VENTURES CORP. (FORMERLY: VIRLO CONSTRUCTION) | 616 | 2021 | 2022-08-02 | 03/08/2021 | 1371708.02 | 0 | 2022-08-01 |  | 1
2018 | Region VI | ILOILO |  | P00221318VS | Construction of Drainage Structure | 122.569 | 10.707 | 183350000 | 183182224.3 | 2023 | MGB CONSTRUCTION & TRADING | 617 | 2018 | 2023-05-10 | 09/06/2018 | 167775.7 | 0 | 2023-02-26 |  | 73
2021 | Region VII | CEBU |  | P00521564VS | Rehabilitation / Major Repair of Flood Control Structure | 123.7817 | 11.1802 | 88550330 | 88550330 | 2022 | WTG CONSTRUCTION & DEVELOPMENT CORPORATION / ROVILLA CONSTRUCTION | 618 | 2021 | 2022-09-05 | 12/31/2021 | 0 | 0 | 2022-09-04 |  | 1
2021 | Region IV-B | ROMBLON |  | P00561578LZ | Construction of Flood Mitigation Structure | 122 | 12.283 | 135098806 | 48235589.63 | 2022 | LEGACY CONSTRUCTION CORPORATION (FORMERLY: LEGACY CONSTRUCTION) | 619 | 2021 | 2022-12-22 | 03/24/2022 | 86863216.37 | 0 | 2022-12-21 |  | 1
2021 | Region IV-B | ROMBLON |  | P00561447LZ | Construction of Flood Mitigation Structure | 122.026 | 12.351 | 173698678.8 | 86765881.53 | 2022 | LEGACY CONSTRUCTION CORPORATION (FORMERLY: LEGACY CONSTRUCTION) / FFJJ CONSTRUCTION | 620 | 2021 | 2022-12-20 | 03/24/2022 | 86932797.27 | 0 | 2023-03-15 | 85
2021 | Region IV-B | ROMBLON |  | P00561448LZ | Construction of Flood Mitigation Structure | 122.026 | 12.452 | 173698678.8 | 86802582.54 | 2022 | LEGACY CONSTRUCTION CORPORATION (FORMERLY: LEGACY CONSTRUCTION) / FFJJ CONSTRUCTION | 621 | 2021 | 2022-12-20 | 03/24/2022 | 86896096.26 | 0 | 2023-03-15 | 85
2021 | Region IV-B | ORIENTAL MINDORO |  | P00525656LZ | Construction of Flood Mitigation Structure | 121.1664 | 13.1349 | 48249214.78 | 48249999.78 | 2022 | TCSC CORP. / EFREN RAMIREZ CONSTRUCTION AND GENERAL SERVICES CORPORATION | 622 | 2021 | 2022-07-29 | 03/30/2021 | 0 | 785 | 2022-08-31 | 33
2021 | Region II | CAGAYAN |  | P00538188LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.4808 | 18.0436 | 21287900 | 21287900 | 2022 | NC RODRIGUEZ CONSTRUCTION | 623 | 2021 | 2022-09-30 | 10/29/2021 | 0 | 0 | 2022-07-03 |  | 89
2021 | Region V | ALBAY |  | P00538311LZ | Rehabilitation / Major Repair of Flood Control Structure | 123.7122 | 13.3408 | 37693122.07 | 3874835.79 | 2022 | ROLCO CONSTRUCTION & DEVELOPMENT CORPORATION ( FOR | 624 | 2021 | 2022-07-27 | 03/21/2022 | 33818286.28 | 0 | 2022-08-04 | 8
2021 | Region V | ALBAY |  | P00538312LZ | Rehabilitation / Major Repair of Flood Control Structure | 123.7356 | 13.3481 | 37693122.07 | 2399955 | 2022 | ROLCO CONSTRUCTION & DEVELOPMENT CORPORATION ( FOR | 625 | 2021 | 2022-07-27 | 03/21/2022 | 35293167.07 | 0 | 2022-08-04 | 8
2021 | Region V | ALBAY |  | P00538313LZ | Rehabilitation / Major Repair of Flood Control Structure | 123.7539 | 13.2982 | 37693122.07 | 5003525 | 2022 | ROLCO CONSTRUCTION & DEVELOPMENT CORPORATION ( FOR | 626 | 2021 | 2022-07-27 | 03/21/2022 | 32689597.07 | 0 | 2022-08-04 | 8
2021 | Region V | ALBAY |  | P00538314LZ | Rehabilitation / Major Repair of Slope Protection Structure | 123.6746 | 13.3794 | 37693122.07 | 6697100 | 2022 | ROLCO CONSTRUCTION & DEVELOPMENT CORPORATION ( FOR | 627 | 2021 | 2022-07-27 | 03/21/2022 | 30996022.07 | 0 | 2022-08-04 | 8
2021 | Region V | ALBAY |  | P00538315LZ | Rehabilitation / Major Repair of Slope Protection Structure | 123.7018 | 13.3837 | 37693122.07 | 6899750 | 2022 | ROLCO CONSTRUCTION & DEVELOPMENT CORPORATION ( FOR | 628 | 2021 | 2022-07-27 | 03/21/2022 | 30793372.07 | 0 | 2022-08-04 | 8
2021 | Region V | ALBAY |  | P00538316LZ | Rehabilitation / Major Repair of Flood Control Structure | 123.6897 | 13.3758 | 37693122.07 | 7956425 | 2022 | ROLCO CONSTRUCTION & DEVELOPMENT CORPORATION ( FOR | 629 | 2021 | 2022-07-27 | 03/21/2022 | 29736697.07 | 0 | 2022-08-04 | 8
2021 | Region V | ALBAY |  | P00538317LZ | Rehabilitation / Major Repair of Flood Control Structure | 123.7122 | 13.3408 | 37693122.07 | 4861781.05 | 2022 | ROLCO CONSTRUCTION & DEVELOPMENT CORPORATION ( FOR | 630 | 2021 | 2022-07-27 | 03/21/2022 | 32831341.02 | 0 | 2022-08-04 | 8
2021 | Region VI | NEGROS OCCIDENTAL |  | P00538308VS | Rehabilitation / Major Repair of Slope Protection Structure | 122.8322 | 9.955 | 5928072.01 | 5904535.77 | 2022 | ST. RAYMUND CONSTRUCTION, INC. | 631 | 2021 | 2022-07-14 | 04/13/2022 | 23536.24 | 0 | 2022-08-07 | 24
2022 | Region IV-B | PALAWAN | BALABAC (PALAWAN) | P00620662LZ | Construction of Flood Mitigation Structure | 117.0617 | 7.9879 | 9321620 | 9328616.52 | 2022 | ONE HUNDRED PERCENT CONSTRUCTION AND DEVELOPMENT CORPORATION (FORMERLY:BCT TRADING & CONSTRUCTION) | 632 | 2022 | 2022-12-02 | 03/25/2022 | 0 | 6996.52 | 2022-12-16 | 14
2023 | Region IV-B | PALAWAN | RIZAL (MARCOS) (PALAWAN) | P00726273LZ | Construction of Drainage Structure | 117.309 | 8.658 | 9800000 | 9652747.12 | 2024 | RDF TRADING AND CONSTRUCTION | 633 | 2023 | 2024-10-07 | 02/15/2023 | 147252.88 | 0 | 2023-06-03 |  | 492
2024 | Region IV-B | ZAMBOANGA DEL NORTE | RIZAL (ZAMBOANGA DEL NORTE) | P00820392LZ | Construction of Flood Mitigation Structure | 117.3734 | 8.7244 | 53075000 | 53072829.34 | 2024 | SYNDTITE CONSTRUCTION CORPORATION (FORMERLY: R.C. TAGALA CONSTRUCTION) | 634 | 2024 | 2024-11-15 | 02/14/2024 | 2170.66 | 0 | 2024-09-19 |  | 57
2023 | Region IV-B | PALAWAN | RIZAL (MARCOS) (PALAWAN) | P00726268LZ | Construction of Flood Mitigation Structure | 117.3753 | 8.7247 | 19600000 | 19599689.79 | 2023 | SAMURAI CONSTRUCTION | 635 | 2023 | 2023-12-15 | 05/03/2023 | 310.21 | 0 | 2023-11-01 |  | 44
2023 | Region IV-B | PALAWAN | BATARAZA (PALAWAN) | P00736053LZ | Construction of Revetment | 117.4511 | 8.6575 | 192999999.9 | 192997113.1 | 2024 | ST. MATTHEW GEN. CONTRACTOR & DEVELOPMENT CORP. / RDF TRADING AND CONSTRUCTION | 636 | 2023 | 2024-08-20 | 03/11/2023 | 2886.8 | 0 | 2024-08-19 |  | 1
2023 | Region IV-B | PALAWAN | RIZAL (MARCOS) (PALAWAN) | P00726770LZ | Construction of Flood Mitigation Structure | 117.4931 | 8.8359 | 9800000 | 9701996.2 | 2023 | F A M E CONSTRUCTION TRADING | 637 | 2023 | 2023-05-28 | 02/15/2023 | 98003.8 | 0 | 2023-05-27 |  | 1
2022 | Region IV-B | PALAWAN | RIZAL (MARCOS) (PALAWAN) | P00621114LZ | Construction of Flood Mitigation Structure | 117.4933 | 8.8361 | 9800000 | 9653000 | 2023 | AFG CONSTRUCTION CORPORATION | 638 | 2022 | 2023-04-22 | 05/25/2022 | 147000 | 0 | 2023-02-07 |  | 74
2023 | Region IV-B | PALAWAN | BATARAZA (PALAWAN) | P00736052LZ | Construction of Revetment | 117.5519 | 8.6781 | 192999998 | 192997857.4 | 2024 | KATHA BUILDERS & SUPPLIES INC. / RDF TRADING AND CONSTRUCTION | 639 | 2023 | 2024-05-31 | 03/11/2023 | 2140.6 | 0 | 2024-05-30 |  | 1
2024 | Region IV-B | ZAMBOANGA DEL NORTE | RIZAL (ZAMBOANGA DEL NORTE) | P00820985LZ | Construction of Flood Mitigation Structure | 117.5558 | 8.9258 | 49000000 | 48997260 | 2024 | ST. TIMOTHY CONSTRUCTION CORPORATION | 640 | 2024 | 2024-10-11 | 02/14/2024 | 2740 | 0 | 2024-09-14 |  | 27
2023 | Region IV-B | PALAWAN | RIZAL (MARCOS) (PALAWAN) | P00740415LZ | Construction of Revetment | 117.5562 | 8.926 | 192999996.8 | 192997879.7 | 2024 | ST. MATTHEW GEN. CONTRACTOR & DEVELOPMENT CORP. / RDF TRADING AND CONSTRUCTION | 641 | 2023 | 2024-04-22 | 04/29/2023 | 2117.1 | 0 | 2024-04-21 |  | 1
2023 | Region IV-B | PALAWAN | RIZAL (MARCOS) (PALAWAN) | P00726272LZ | Construction of Flood Mitigation Structure | 117.557 | 8.9259 | 24500000 | 24499994.74 | 2023 | L&M RODRIGUEZ CONSTRUCTION AND TRADING INC. (FORMERLY: M.M. RODRIGUEZ TRADING AND CONSTRUCTION) | 642 | 2023 | 2023-12-07 | 02/15/2023 | 5.26 | 0 | 2023-09-01 |  | 97
2022 | Region IV-B | PALAWAN | BATARAZA (PALAWAN) | P00620660LZ | Construction of Flood Mitigation Structure | 117.6214 | 8.6843 | 29400000 | 28801312.6 | 2023 | L. B. LEONCIO TRADING AND CONSTRUCTION CORPORATION (FORMERLY: L.B. LEONCIO TRADING & CONSTRUCTION) | 643 | 2022 | 2023-04-15 | 05/25/2022 | 598687.4 | 0 | 2023-02-02 |  | 72
2024 | Region IV-B | PALAWAN | BROOKE'S POINT (PALAWAN) | P00820986LZ | Construction of Flood Mitigation Structure | 117.7217 | 8.7049 | 49000000 | 48995638.54 | 2024 | SYNDTITE CONSTRUCTION CORPORATION (FORMERLY: R.C. TAGALA CONSTRUCTION) | 644 | 2024 | 2024-07-15 | 02/14/2024 | 4361.46 | 0 | 2024-08-02 | 18
2022 | Region IV-B | PALAWAN | BROOKE'S POINT (PALAWAN) | P00620664LZ | Construction of Flood Mitigation Structure | 117.7219 | 8.7031 | 39400000 | 39199997 | 2023 | L. B. LEONCIO TRADING AND CONSTRUCTION CORPORATION (FORMERLY: L.B. LEONCIO TRADING & CONSTRUCTION) | 645 | 2022 | 2023-01-23 | 05/25/2022 | 200003 | 0 | 2023-06-01 | 129
2023 | Region IV-B | PALAWAN | BROOKE'S POINT (PALAWAN) | P00725878LZ | Construction of Flood Mitigation Structure | 117.7246 | 8.6969 | 50662500 | 50657737.68 | 2023 | L. B. LEONCIO TRADING AND CONSTRUCTION CORPORATION (FORMERLY: L.B. LEONCIO TRADING & CONSTRUCTION) | 646 | 2023 | 2023-08-25 | 02/20/2023 | 4762.32 | 0 | 2023-09-29 | 35
2024 | Region IV-B | ZAMBOANGA DEL NORTE | RIZAL (ZAMBOANGA DEL NORTE) | P00820987LZ | Construction of Flood Mitigation Structure | 117.7256 | 9.041 | 29400000 | 29396659.04 | 2024 | L&M RODRIGUEZ CONSTRUCTION AND TRADING INC. (FORMERLY: M.M. RODRIGUEZ TRADING AND CONSTRUCTION) | 647 | 2024 | 2024-10-03 | 03/15/2024 | 3340.96 | 0 | 2024-08-10 |  | 54
2024 | Region IV-B | BUKIDNON | QUEZON (BUKIDNON) | P00820982LZ | Construction of Flood Mitigation Structure | 117.8069 | 9.1326 | 24500000 | 24499188 | 2024 | DIANE CONSTRUCTION & ENTERPRISES | 648 | 2024 | 2024-08-15 | 02/14/2024 | 812 | 0 | 2024-07-22 |  | 24
2024 | Region IV-B | BUKIDNON | QUEZON (BUKIDNON) | P00820983LZ | Construction of Flood Mitigation Structure | 117.8107 | 9.1394 | 29400000 | 29399992.5 | 2024 | CUTTING EDGE BUILDERS AND TRADING, INC. | 649 | 2024 | 2024-06-17 | 02/14/2024 | 7.5 | 0 | 2024-07-11 | 24
2023 | Region IV-B | PALAWAN | BROOKE'S POINT (PALAWAN) | P00736051LZ | Construction of Dike | 117.8169 | 8.8306 | 192999985.9 | 192991970 | 2024 | MARCBILT CONSTRUCTION, INC. | 650 | 2023 | 2024-03-05 | 04/13/2023 | 8015.9 | 0 | 2024-04-05 | 31
2023 | Region IV-B | PALAWAN | BROOKE'S POINT (PALAWAN) | P00725864LZ | Construction of Revetment | 117.84 | 8.7722 | 46078749.88 | 45816740.98 | 2023 | MARCBILT CONSTRUCTION, INC. | 651 | 2023 | 2023-09-30 | 04/13/2023 | 262008.9 | 0 | 2023-09-29 |  | 1
2022 | Region IV-B | PALAWAN | BROOKE'S POINT (PALAWAN) | P00620656LZ | Construction of Flood Mitigation Structure | 117.8443 | 8.8857 | 19600000 | 11674127.13 | 2023 | M.C. ESCALA CONSTRUCTION AND SUPPLY | 652 | 2022 | 2023-07-31 | 05/25/2022 | 7925872.87 | 0 | 2022-12-15 |  | 228
2022 | Region IV-B | PALAWAN | QUEZON (PALAWAN) | P00620666LZ | Construction of Flood Mitigation Structure | 117.8518 | 9.1624 | 29400000 | 17279673.78 | 2023 | L&M RODRIGUEZ CONSTRUCTION AND TRADING INC. (FORMERLY: M.M. RODRIGUEZ TRADING AND CONSTRUCTION) | 653 | 2022 | 2023-05-23 | 05/25/2022 | 12120326.22 | 0 | 2023-03-29 |  | 55
2023 | Region IV-B | PALAWAN | BROOKE'S POINT (PALAWAN) | P00725862LZ | Construction of Revetment | 117.8533 | 8.8135 | 96500006.28 | 96497913.06 | 2024 | HARDROCKPLATINUM DEVELOPMENT CORPORATION / C.T. LEONCIO CONSTRUCTION & TRADING | 654 | 2023 | 2024-01-21 | 03/11/2023 | 2093.22 | 0 | 2024-01-20 |  | 1
2024 | Region IV-B | PALAWAN | BROOKE'S POINT (PALAWAN) | P00820416LZ | Construction of Flood Mitigation Structure | 117.8539 | 8.8136 | 53075000 | 53068367.03 | 2024 | SYNDTITE CONSTRUCTION CORPORATION (FORMERLY: R.C. TAGALA CONSTRUCTION) | 655 | 2024 | 2024-10-15 | 02/14/2024 | 6632.97 | 0 | 2024-10-14 |  | 1
2022 | Region IV-B | PALAWAN | BROOKE'S POINT (PALAWAN) | P00620665LZ | Construction of Flood Mitigation Structure | 117.8663 | 8.825 | 39200000 | 39199918.59 | 2023 | IVY MICHELLE CONSTRUCTION AND TRADING INC. (FORMERLY:IVY MICHELLE TRADING & CONTRUCTION) / C.T. LEONCIO CONSTRUCTION & TRADING | 656 | 2022 | 2023-07-06 | 03/21/2022 | 81.41 | 0 | 2023-03-16 |  | 112
2023 | Region IV-B | PALAWAN | BROOKE'S POINT (PALAWAN) | P00726270LZ | Construction of Flood Mitigation Structure | 117.8816 | 8.8418 | 44100000 | 44097967.76 | 2023 | PTK GROUP INC. | 657 | 2023 | 2023-10-15 | 02/15/2023 | 2032.24 | 0 | 2023-09-04 |  | 41
2022 | Region IV-B | PALAWAN | BROOKE'S POINT (PALAWAN) | P00620657LZ | Construction of Flood Mitigation Structure | 117.8817 | 8.8397 | 29400000 | 20226888.84 | 2023 | M.C. ESCALA CONSTRUCTION AND SUPPLY | 658 | 2022 | 2023-11-07 | 05/25/2022 | 9173111.16 | 0 | 2023-07-05 |  | 125
2024 | Region IV-B | PALAWAN | BROOKE'S POINT (PALAWAN) | P00820984LZ | Construction of Flood Mitigation Structure | 117.9169 | 8.8805 | 17966340 | 17963797.88 | 2024 | ALMRIN BUILDERS CORPORATION | 659 | 2024 | 2024-09-30 | 02/14/2024 | 2542.12 | 0 | 2024-06-18 |  | 104
2023 | Region IV-B | PALAWAN | QUEZON (PALAWAN) | P00726769LZ | Construction of Flood Mitigation Structure | 117.9452 | 9.2077 | 24500000 | 24499242.58 | 2023 | RDF TRADING AND CONSTRUCTION | 660 | 2023 | 2023-12-15 | 03/23/2023 | 757.42 | 0 | 2023-09-05 |  | 101
2022 | Region IV-B | PALAWAN | QUEZON (PALAWAN) | P00620658LZ | Construction of Flood Mitigation Structure | 117.9457 | 9.2061 | 9800000 | 5504750.7 | 2023 | R NARRAZID TRADING AND CONSTRUCTION | 661 | 2022 | 2023-12-31 | 05/25/2022 | 4295249.3 | 0 | 2022-11-30 |  | 396
2022 | Region IV-B | PALAWAN | QUEZON (PALAWAN) | P00621115LZ | Construction of Flood Mitigation Structure | 117.9487 | 9.206 | 19600000 | 11892174.24 | 2023 | M.C. ESCALA CONSTRUCTION AND SUPPLY | 662 | 2022 | 2023-04-10 | 05/25/2022 | 7707825.76 | 0 | 2023-01-18 |  | 82
2022 | Region IV-B | PALAWAN | QUEZON (PALAWAN) | P00620668LZ | Construction of Flood Mitigation Structure | 118.058 | 9.2605 | 9800000 | 5210917.61 | 2025 | R NARRAZID TRADING AND CONSTRUCTION | 663 | 2022 | 2025-02-02 | 02/21/2022 | 4589082.39 | 0 | 2022-07-19 |  | 929
2023 | Region IV-B | PALAWAN | SOFRONIO ESPAÃ‘OLA (PALAWAN) | P00726269LZ | Construction of Flood Mitigation Structure | 118.1157 | 9.1584 | 24500000 | 24499265.29 | 2023 | CUTTING EDGE BUILDERS AND TRADING, INC. | 664 | 2023 | 2023-07-19 | 02/15/2023 | 734.71 | 0 | 2023-07-18 |  | 1
2024 | Region IV-B | BUKIDNON | QUEZON (BUKIDNON) | P00820980LZ | Construction of Flood Mitigation Structure | 118.145 | 9.3757 | 29400000 | 29303558.24 | 2024 | RDF TRADING AND CONSTRUCTION | 665 | 2024 | 2024-07-27 | 02/14/2024 | 96441.76 | 0 | 2024-07-26 |  | 1
2023 | Region IV-B | PALAWAN | NARRA (PALAWAN) | P00740416LZ | Construction of Flood Mitigation Structure | 118.1802 | 9.1686 | 192999999.5 | 192997354.3 | 2024 | ST. MATTHEW GEN. CONTRACTOR & DEVELOPMENT CORP. / RDF TRADING AND CONSTRUCTION | 666 | 2023 | 2024-05-20 | 04/13/2023 | 2645.2 | 0 | 2024-05-19 |  | 1
2023 | Region IV-B | PALAWAN | NARRA (PALAWAN) | P00725876LZ | Construction of Flood Mitigation Structure | 118.3261 | 9.2235 | 50662500 | 50662496.45 | 2023 | ORANI CONSTRUCTION AND SUPPLY CORPORATION (FORMERLY:ORANI BUILDERS & SUPPLY) | 667 | 2023 | 2023-12-22 | 02/20/2023 | 3.55 | 0 | 2023-10-30 |  | 53
2024 | Region IV-B | PALAWAN | NARRA (PALAWAN) | P00820391LZ | Construction of Flood Mitigation Structure | 118.3264 | 9.2216 | 53075000 | 53004257.5 | 2024 | ORANI CONSTRUCTION AND SUPPLY CORPORATION (FORMERLY:ORANI BUILDERS & SUPPLY) | 668 | 2024 | 2024-09-16 | 02/14/2024 | 70742.5 | 0 | 2024-08-28 |  | 19
2024 | Region IV-B | PALAWAN | PUERTO PRINCESA CITY (CAPITAL) (PALAWAN) | P00824752LZ | Construction of Flood Mitigation Structure | 118.3424 | 9.6034 | 18335000 | 17029313.08 | 2024 | G. BANZ BUILDERS CORP. | 669 | 2024 | 2024-06-24 | 02/23/2024 | 1305686.92 | 0 | 2024-07-31 | 37
2024 | Region IV-B | PALAWAN | ABORLAN (PALAWAN) | P00824763LZ | Construction of Flood Mitigation Structure | 118.3424 | 9.6034 | 17370000 | 17369994.74 | 2024 | G. BANZ BUILDERS CORP. | 670 | 2024 | 2024-06-24 | 03/07/2024 | 5.26 | 0 | 2024-07-30 | 36
2024 | Region IV-B | PALAWAN | ABORLAN (PALAWAN) | P00824761LZ | Construction of Flood Mitigation Structure | 118.3426 | 9.6028 | 17370000 | 16240699.93 | 2024 | RITCHE-NATHALIE DEVELOPMENT CORPORATION (FORMERLY: RITCHE-NATHALIE BUILDERS AND GEN. MERCHANDISE) | 671 | 2024 | 2024-08-20 | 03/08/2024 | 1129300.07 | 0 | 2024-09-08 | 19
2024 | Region IV-B | PALAWAN | ABORLAN (PALAWAN) | P00824764LZ | Construction of Flood Mitigation Structure | 118.3426 | 9.6028 | 17370000 | 14882574.2 | 2024 | PANAAD CONSTRUCTION | 672 | 2024 | 2024-07-18 | 02/23/2024 | 2487425.8 | 0 | 2024-07-17 |  | 1
2024 | Region IV-B | PALAWAN | ABORLAN (PALAWAN) | P00824762LZ | Construction of Flood Mitigation Structure | 118.3429 | 9.6029 | 17370000 | 17369987.88 | 2024 | RITCHE-NATHALIE DEVELOPMENT CORPORATION (FORMERLY: RITCHE-NATHALIE BUILDERS AND GEN. MERCHANDISE) | 673 | 2024 | 2024-07-24 | 03/08/2024 | 12.12 | 0 | 2024-07-31 | 7
2022 | Region IV-B | PALAWAN | NARRA (PALAWAN) | P00620659LZ | Construction of Flood Mitigation Structure | 118.3694 | 9.2471 | 29400000 | 28986147.77 | 2023 | R NARRAZID TRADING AND CONSTRUCTION / RDF TRADING AND CONSTRUCTION | 674 | 2022 | 2023-05-31 | 07/03/2022 | 413852.23 | 0 | 2023-04-16 |  | 45
2022 | Region IV-B | PALAWAN | NARRA (PALAWAN) | P00631315LZ | Construction of Flood Mitigation Structure | 118.4011 | 9.2439 | 29400000 | 29399879.54 | 2022 | SYNDTITE CONSTRUCTION CORPORATION (FORMERLY: R.C. TAGALA CONSTRUCTION) | 675 | 2022 | 2022-10-10 | 02/21/2022 | 120.46 | 0 | 2022-09-27 |  | 13
2023 | Region IV-B | PALAWAN | NARRA (PALAWAN) | P00742462LZ | Construction of Flood Mitigation Structure | 118.4011 | 9.2439 | 19600000 | 19550848.57 | 2023 | MEGA TAM SUMMIT INCORPORATED | 676 | 2023 | 2023-08-31 | 03/29/2023 | 49151.43 | 0 | 2023-10-02 | 32
2021 | Region IV-B | PALAWAN |  | P00526167LZ | Construction of Flood Mitigation Structure | 118.4014 | 9.2633 | 30354520 | 30353588.62 | 2022 | SYNDTITE CONSTRUCTION CORPORATION (FORMERLY: R.C. TAGALA CONSTRUCTION) | 677 | 2021 | 2022-08-01 | 04/13/2021 | 931.38 | 0 | 2022-03-28 |  | 126
2022 | Region IV-B | PALAWAN | NARRA (PALAWAN) | P00620661LZ | Construction of Flood Mitigation Structure | 118.4046 | 9.2696 | 47040000 | 39324618.9 | 2023 | C.T. LEONCIO CONSTRUCTION & TRADING | 678 | 2022 | 2023-08-31 | 05/25/2022 | 7715381.1 | 0 | 2023-06-17 |  | 75
2023 | Region IV-B | PALAWAN | NARRA (PALAWAN) | P00725861LZ | Construction of Revetment | 118.4062 | 9.2765 | 96499995.64 | 96497566.17 | 2024 | HARDROCKPLATINUM DEVELOPMENT CORPORATION / C.T. LEONCIO CONSTRUCTION & TRADING | 679 | 2023 | 2024-01-16 | 03/11/2023 | 2429.47 | 0 | 2024-01-15 |  | 1
2024 | Region IV-B | PALAWAN | NARRA (PALAWAN) | P00820404LZ | Construction of Flood Mitigation Structure | 118.4099 | 9.2724 | 53075000 | 53063470.45 | 2024 | C.T. LEONCIO CONSTRUCTION & TRADING | 680 | 2024 | 2024-11-15 | 02/14/2024 | 11529.55 | 0 | 2024-08-15 |  | 92
2023 | Region IV-B | PALAWAN | NARRA (PALAWAN) | P00725877LZ | Construction of Flood Mitigation Structure | 118.4114 | 9.2713 | 50421250 | 50418886.99 | 2024 | C.T. LEONCIO CONSTRUCTION & TRADING | 681 | 2023 | 2024-09-01 | 02/20/2023 | 2363.01 | 0 | 2023-09-14 |  | 353
2022 | Region IV-B | PALAWAN | NARRA (PALAWAN) | P00620667LZ | Construction of Flood Mitigation Structure | 118.4747 | 9.303 | 29400000 | 21749296.29 | 2022 | ALMRIN BUILDERS CORPORATION | 682 | 2022 | 2022-12-20 | 03/25/2022 | 7650703.71 | 0 | 2023-01-27 | 38
2023 | Region IV-B | PALAWAN | NARRA (PALAWAN) | P00726271LZ | Construction of Flood Mitigation Structure | 118.4917 | 9.3036 | 24500000 | 21653583.72 | 2024 | SAMURAI CONSTRUCTION | 683 | 2023 | 2024-02-10 | 06/16/2023 | 2846416.28 | 0 | 2023-11-06 |  | 96
2023 | Region IV-B | PALAWAN | ABORLAN (PALAWAN) | P00726601LZ | Construction of Waterway | 118.5412 | 9.4282 | 120624999.4 | 120268876 | 2023 | HARDROCKPLATINUM DEVELOPMENT CORPORATION / C.T. LEONCIO CONSTRUCTION & TRADING | 684 | 2023 | 2023-12-10 | 03/11/2023 | 356123.4 | 0 | 2024-01-16 | 37
2024 | Region IV-B | PALAWAN | ABORLAN (PALAWAN) | P00823564LZ | Construction of Flood Mitigation Structure | 118.5451 | 9.4289 | 154400000 | 154398410.8 | 2024 | YURICH BUILDERS AND CONSTRUCTION SUPPLY INC. | 685 | 2024 | 2024-12-05 | 03/02/2024 | 1589.2 | 0 | 2025-01-10 | 36
2024 | Region IV-B | PALAWAN | ABORLAN (PALAWAN) | P00845836LZ | Construction of Flood Mitigation Structure | 118.5467 | 9.4567 | 98999999.99 | 98999956.57 | 2024 | YURICH BUILDERS AND CONSTRUCTION SUPPLY INC. | 686 | 2024 | 2024-11-05 | 05/21/2024 | 43.42 | 0 | 2024-12-18 | 43
2023 | Region IV-B | PALAWAN | ABORLAN (PALAWAN) | P00740432LZ | Construction of Flood Mitigation Structure | 118.5483 | 9.4483 | 212299999.5 | 212295699.4 | 2024 | YURICH BUILDERS AND CONSTRUCTION SUPPLY INC. | 687 | 2023 | 2024-03-07 | 04/13/2023 | 4300.1 | 0 | 2024-04-05 | 29
2022 | Region IV-B | PALAWAN | ABORLAN (PALAWAN) | P00620901LZ | Construction of Flood Mitigation Structure | 118.5526 | 9.4367 | 96500000 | 96496704.82 | 2023 | HARDROCKPLATINUM DEVELOPMENT CORPORATION / C.T. LEONCIO CONSTRUCTION & TRADING | 688 | 2022 | 2023-07-15 | 05/23/2022 | 3295.18 | 0 | 2023-06-15 |  | 30
2025 | Region IV-B | PALAWAN | PUERTO PRINCESA CITY (CAPITAL) (PALAWAN) | P00921211LZ | Construction of Flood Mitigation Structure | 118.6183 | 9.5541 | 14700000 | 14669999.48 | 2025 | KRATOS STRUCPRIME CONSTRUCTION AND SUPPLY CORP | 689 | 2025 | 2025-05-19 | 02/05/2025 | 30000.52 | 0 | 2025-06-09 | 21
2024 | Region IV-B | PALAWAN | PUERTO PRINCESA CITY (CAPITAL) (PALAWAN) | P00844553LZ | Construction of Flood Mitigation Structure | 118.6931 | 9.8022 | 194930000 | 194927222.8 | 2024 | YURICH BUILDERS AND CONSTRUCTION SUPPLY INC. | 690 | 2024 | 2024-12-05 | 03/09/2024 | 2777.2 | 0 | 2025-03-02 | 87
2023 | Region IV-B | ORIENTAL MINDORO | NAUJAN (ORIENTAL MINDORO) | P00740433LZ | Construction of Revetment | 118.6936 | 9.8 | 212299999.4 | 212296975.9 | 2024 | YURICH BUILDERS AND CONSTRUCTION SUPPLY INC. | 691 | 2023 | 2024-03-07 | 04/13/2023 | 3023.5 | 0 | 2024-04-05 | 29
2024 | Region IV-B | PALAWAN | PUERTO PRINCESA CITY (CAPITAL) (PALAWAN) | P00824755LZ | Construction of Flood Mitigation Structure | 118.6965 | 9.7965 | 17370000 | 17369942.66 | 2024 | MACASAET BUILDERS AND TRADING | 692 | 2024 | 2024-07-22 | 03/08/2024 | 57.34 | 0 | 2024-07-31 | 9
2024 | Region IV-B | PALAWAN | PUERTO PRINCESA CITY (CAPITAL) (PALAWAN) | P00824753LZ | Construction of Flood Mitigation Structure | 118.6967 | 9.7996 | 17370000 | 17369970.05 | 2024 | HARDROCKPLATINUM DEVELOPMENT CORPORATION | 693 | 2024 | 2024-07-12 | 02/15/2024 | 29.95 | 0 | 2024-07-11 |  | 1
2024 | Region IV-B | PALAWAN | PUERTO PRINCESA CITY (CAPITAL) (PALAWAN) | P00824754LZ | Construction of Flood Mitigation Structure | 118.6971 | 9.7987 | 17370000 | 17369990.32 | 2024 | MGB CONSTRUCTION & TRADING | 694 | 2024 | 2024-07-12 | 02/15/2024 | 9.68 | 0 | 2024-07-11 |  | 1
2022 | Region IV-B | PALAWAN | PUERTO PRINCESA CITY (CAPITAL) (PALAWAN) | P00632935LZ | Construction of Drainage Structure | 118.7311 | 9.7407 | 4950000 | 4851100.32 | 2022 | F.F. GALANG CONSTRUCTION | 695 | 2022 | 2022-07-05 | 02/10/2022 | 98899.68 | 0 | 2022-06-24 |  | 11
2022 | Region IV-B | PALAWAN | PUERTO PRINCESA CITY (CAPITAL) (PALAWAN) | P00637809LZ | Construction of Drainage Structure | 118.7446 | 9.7579 | 4950000 | 4359361.95 | 2022 | F.F. GALANG CONSTRUCTION | 696 | 2022 | 2022-12-09 | 04/07/2022 | 590638.05 | 0 | 2022-09-02 |  | 98
2023 | Region IV-B | PALAWAN | PUERTO PRINCESA CITY (CAPITAL) (PALAWAN) | P00737552LZ | Construction of Drainage Structure | 118.7483 | 9.7502 | 4900000 | 4900000 | 2023 | SMMILEY BUILDERS AND TRADING | 697 | 2023 | 2023-09-27 | 02/15/2023 | 0 | 0 | 2023-09-01 |  | 26
2022 | Region IV-B | PALAWAN | PUERTO PRINCESA CITY (CAPITAL) (PALAWAN) | P00637810LZ | Construction of Drainage Structure | 118.7631 | 9.7389 | 4950000 | 4205703.56 | 2022 | N. SALES CONSTRUCTION | 698 | 2022 | 2022-11-04 | 04/07/2022 | 744296.44 | 0 | 2022-08-13 |  | 83
2022 | Region IV-B | PALAWAN | PUERTO PRINCESA CITY (CAPITAL) (PALAWAN) | P00620265LZ | Construction of Flood Mitigation Structure | 118.7734 | 9.772 | 96499990.14 | 96496299.03 | 2023 | HARDROCKPLATINUM DEVELOPMENT CORPORATION / C.T. LEONCIO CONSTRUCTION & TRADING | 699 | 2022 | 2023-12-20 | 07/06/2022 | 3691.11 | 0 | 2023-11-29 |  | 21
2024 | Region IV-B | PALAWAN | PUERTO PRINCESA CITY (CAPITAL) (PALAWAN) | P00824751LZ | Construction of Flood Mitigation Structure | 118.8924 | 9.9927 | 18335000 | 18334889.53 | 2024 | PANAAD CONSTRUCTION | 700 | 2024 | 2024-07-17 | 02/15/2024 | 110.47 | 0 | 2024-07-16 |  | 1
2024 | Region IV-B | OCCIDENTAL MINDORO | PALUAN (OCCIDENTAL MINDORO) | P00823573LZ | Construction of Flood Mitigation Structure | 120.4944 | 13.4222 | 289500000 | 289495739.8 | 2024 | AMETHYST HORIZON BUILDERS AND GEN. CONTRACTOR AND DEVELOPMENT CORP. | 701 | 2024 | 2024-12-07 | 03/02/2024 | 4260.2 | 0 | 2025-02-23 | 78
2021 | Region I | ILOCOS SUR |  | P00561481LZ | Construction of Flood Mitigation Structure | 120.4945 | 16.9599 | 9800000 | 9799946.61 | 2022 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | 702 | 2021 | 2022-12-01 | 10/11/2021 | 53.39 | 0 | 2022-02-26 |  | 278
2024 | Region IV-B | OCCIDENTAL MINDORO | PALUAN (OCCIDENTAL MINDORO) | P00820408LZ | Construction of Flood Mitigation Structure | 120.4952 | 13.3336 | 96500000 | 96494249.47 | 2024 | ST. GERRARD CONSTRUCTION GEN. CONTRACTOR & DEVELOPMENT CORP. (FORMERLY:ST. GERRARD CONSTRUCTION) | 703 | 2024 | 2024-06-15 | 03/06/2024 | 5750.53 | 0 | 2024-12-16 | 184
2023 | Region I | ILOCOS NORTE | BADOC (ILOCOS NORTE) | P00725624LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.4957 | 17.9215 | 125450000 | 125449993.7 | 2023 | BADOC BUILDERS & SUPPLY, INC. (FORMERLY: BADOC BUILDER & SUPPLY / ST. MATTHEW GEN. CONTRACTOR & DEVELOPMENT CORP. | 704 | 2023 | 2023-07-18 | 02/14/2023 | 6.3 | 0 | 2023-10-13 | 87
2022 | Region I | ILOCOS SUR | SUYO (ILOCOS SUR) | P00621511LZ | Construction of Flood Mitigation Structure | 120.4963 | 16.9618 | 19600000 | 19599716.72 | 2023 | KVC CONSTRUCTION | 705 | 2022 | 2023-08-30 | 04/04/2022 | 283.28 | 0 | 2022-08-01 |  | 394
2023 | Region I | ILOCOS NORTE | CURRIMAO (ILOCOS NORTE) | P00725587LZ | Construction of Flood Mitigation Structure | 120.4971 | 17.993 | 28950000 | 28949979.06 | 2023 | MEGAPOLITAN BUILDERS AND CONSTRUCTION SUPPLY | 706 | 2023 | 2023-12-18 | 03/16/2023 | 20.94 | 0 | 2023-12-17 |  | 1
2024 | Region I | PANGASINAN | CITY OF URDANETA (PANGASINAN) | P00845909LZ | Construction of Revetment | 120.4972 | 15.986 | 29700000 | 29650972.66 | 2024 | BUILDERS EXPONENT EMPIRE CORP. (FORMERLY: BUILDERS EXPONENT ENTERPRISE) | 707 | 2024 | 2024-08-30 | 03/06/2024 | 49027.34 | 0 | 2024-08-29 |  | 1
2023 | Region III | BATAAN | CITY OF BALANGA (CAPITAL) (BATAAN) | P00725710LZ | Construction of Flood Mitigation Structure | 120.4973 | 14.6515 | 53072166.23 | 53075000 | 2023 | BPQ CONSTRUCTION AND TRADING / POLYMER-VIC CONSTRUCTION | 708 | 2023 | 2023-06-26 | 02/20/2023 | 0 | 2833.77 | 2023-09-08 | 74
2023 | Region III | BATAAN | HERMOSA (BATAAN) | P00727124LZ | Construction of Flood Mitigation Structure | 120.4976 | 14.8597 | 48999999.71 | 48999982.96 | 2023 | M.C.J. VALENZUELA CONSTRUCTION ENTERPRISES | 709 | 2023 | 2023-10-11 | 03/13/2023 | 16.75 | 0 | 2023-10-13 | 2
2022 | Region I | ILOCOS SUR | BURGOS (ILOCOS SUR) | P00632740LZ | Construction of Flood Mitigation Structure | 120.4979 | 17.3217 | 4900000 | 4899981.03 | 2023 | MRK-SQUARE CONSTRUCTION AND SUPPLY | 710 | 2022 | 2023-04-17 | 02/24/2022 | 18.97 | 0 | 2022-04-26 |  | 356
2023 | Region I | ILOCOS SUR | BURGOS (ILOCOS SUR) | P00727075LZ | Construction of Flood Mitigation Structure | 120.4986 | 17.3326 | 49000000 | 48999357.69 | 2024 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | 711 | 2023 | 2024-07-31 | 03/29/2023 | 642.31 | 0 | 2023-08-29 |  | 337
2024 | Region I | PANGASINAN | CITY OF URDANETA (PANGASINAN) | P00821510LZ | Construction of Dike | 120.4987 | 15.9891 | 49000000 | 48918015.87 | 2024 | R.G.TABIN CONSTRUCTION AND SUPPLY / AMP 723 CONSTRUCTION CORPORATION (FORMERLY: A.M.P. CONSTRUCTION) | 712 | 2024 | 2024-04-30 | 02/14/2024 | 81984.13 | 0 | 2024-08-31 | 123
2022 | Region I | ILOCOS SUR | BURGOS (ILOCOS SUR) | P00632738LZ | Construction of Flood Mitigation Structure | 120.4989 | 17.3291 | 4900000 | 4899983.4 | 2023 | MRK-SQUARE CONSTRUCTION AND SUPPLY | 713 | 2022 | 2023-04-05 | 02/24/2022 | 16.6 | 0 | 2022-04-26 |  | 344
2023 | Region I | ILOCOS SUR | BURGOS (ILOCOS SUR) | P00742263LZ | Construction of Flood Mitigation Structure | 120.4992 | 17.3292 | 9900000 | 9602987.5 | 2023 | FIRST NORTHWAY DEVELOPMENT & CONSTRUCTION CORP. | 714 | 2023 | 2023-12-20 | 03/28/2023 | 297012.5 | 0 | 2023-06-17 |  | 186
2023 | Region III | BATAAN | HERMOSA (BATAAN) | P00727356LZ | Construction of Flood Mitigation Structure | 120.4994 | 14.8411 | 29105999.82 | 29105999.82 | 2023 | SAN SEBASTIAN CONSTRUCTION | 715 | 2023 | 2023-09-06 | 03/13/2023 | 0 | 0 | 2023-09-07 | 1
2023 | Region I | ILOCOS NORTE | CURRIMAO (ILOCOS NORTE) | P00736178LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.4995 | 17.9938 | 49000000 | 48020000 | 2023 | MEGAPOLITAN BUILDERS AND CONSTRUCTION SUPPLY | 716 | 2023 | 2023-12-05 | 02/10/2023 | 980000 | 0 | 2023-12-04 |  | 1
2023 | Region III | BATAAN | CITY OF BALANGA (CAPITAL) (BATAAN) | P00737450LZ | Construction of Flood Mitigation Structure | 120.4997 | 14.6505 | 14699999.1 | 14850000 | 2023 | BPQ CONSTRUCTION AND TRADING / POLYMER-VIC CONSTRUCTION | 717 | 2023 | 2023-05-24 | 02/08/2023 | 0 | 150000.9 | 2023-06-26 | 33
2022 | Region III | BATAAN | HERMOSA (BATAAN) | P00631170LZ | Construction of Flood Mitigation Structure | 120.4997 | 14.8255 | 48999999.61 | 48999995.93 | 2022 | ORANI CONSTRUCTION AND SUPPLY CORPORATION (FORMERLY:ORANI BUILDERS & SUPPLY) | 718 | 2022 | 2022-10-06 | 04/04/2022 | 3.68 | 0 | 2022-10-07 | 1
2023 | Region I | ILOCOS SUR | BURGOS (ILOCOS SUR) | P00742268LZ | Construction of Flood Mitigation Structure | 120.4997 | 17.3286 | 9900000 | 9887142.35 | 2023 | CZMAC CONSTRUCTION SERVICES | 719 | 2023 | 2023-12-19 | 03/28/2023 | 12857.65 | 0 | 2023-06-17 |  | 185
2022 | Region I | PANGASINAN | MANAOAG (PANGASINAN) | P00641867LZ | Construction of Slope Protection Structure | 120.5002 | 16.0186 | 39200000 | 37644065.34 | 2023 | BET CONSTRUCTION & SUPPLY | 720 | 2022 | 2023-04-16 | 03/25/2022 | 1555934.66 | 0 | 2022-09-21 |  | 207
2022 | Region I | PANGASINAN | ROSALES (PANGASINAN) | P00620967LZ | Construction of Revetment | 120.5003 | 15.9078 | 49000000 | 47531186.52 | 2023 | RIVBROS CONSTRUCTION FACTORS & DEVELOPMENT | 721 | 2022 | 2023-01-24 | 03/08/2022 | 1468813.48 | 0 | 2022-09-14 |  | 132
2023 | Region I | ILOCOS NORTE | BADOC (ILOCOS NORTE) | P00725599LZ | Construction of Flood Mitigation Structure | 120.5016 | 17.9247 | 48250000 | 48249998.15 | 2023 | BADOC BUILDERS & SUPPLY, INC. (FORMERLY: BADOC BUILDER & SUPPLY | 722 | 2023 | 2023-07-31 | 02/14/2023 | 1.85 | 0 | 2023-08-05 | 5
2024 | Region III | BATAAN | HERMOSA (BATAAN) | P00839572LZ | Construction of Flood Mitigation Structure | 120.5016 | 14.8409 | 9899999.43 | 9899999.43 | 2024 | STO. CRISTO CONSTRUCTION & TRADING INC. (FOR: STO. CRISTO CONSTRUCTION & TRADING) | 723 | 2024 | 2024-06-13 | 03/18/2024 | 0 | 0 | 2024-06-15 | 2
2024 | Region III | BATAAN | HERMOSA (BATAAN) | P00845963LZ | Construction of Flood Mitigation Structure | 120.5016 | 14.8409 | 29699999.9 | 29699999.9 | 2024 | SAN SEBASTIAN CONSTRUCTION | 724 | 2024 | 2024-09-19 | 04/23/2024 | 0 | 0 | 2024-09-22 | 3
2024 | Region I | PANGASINAN | CITY OF URDANETA (PANGASINAN) | P00820721LZ | Construction of Revetment | 120.5019 | 15.9906 | 48250000 | 48143361.81 | 2024 | AMP 723 CONSTRUCTION CORPORATION (FORMERLY: A.M.P. CONSTRUCTION) | 725 | 2024 | 2024-10-04 | 04/19/2024 | 106638.19 | 0 | 2024-11-04 | 31
2024 | Region III | BATAAN | HERMOSA (BATAAN) | P00820802LZ | Construction of Revetment | 120.5023 | 14.8281 | 48999999.7 | 48999999.92 | 2024 | PASCAL CONSTRUCTION | 726 | 2024 | 2024-07-02 | 02/16/2024 | 0 | 0.22 | 2024-08-12 | 41
2024 | Region III | BATAAN | CITY OF BALANGA (CAPITAL) (BATAAN) | P00824694LZ | Construction of Flood Mitigation Structure | 120.5029 | 14.6488 | 9800000 | 9572581.7 | 2024 | DAJ BUILDERS | 727 | 2024 | 2024-07-01 | 03/27/2024 | 227418.3 | 0 | 2024-06-30 |  | 1
2022 | Region I | PANGASINAN | MANAOAG (PANGASINAN) | P00631086LZ | Construction of Slope Protection Structure | 120.5032 | 16.0494 | 14700000 | 14697245.89 | 2023 | BET CONSTRUCTION & SUPPLY | 728 | 2022 | 2023-06-30 | 02/18/2022 | 2754.11 | 0 | 2023-06-29 |  | 1
2022 | Region I | PANGASINAN | MANAOAG (PANGASINAN) | P00637050LZ | Construction of Slope Protection Structure | 120.5036 | 16.0523 | 24010000 | 24007055.11 | 2023 | BET CONSTRUCTION & SUPPLY | 729 | 2022 | 2023-01-04 | 03/25/2022 | 2944.89 | 0 | 2022-09-05 |  | 121
2022 | Region I | PANGASINAN | MANAOAG (PANGASINAN) | P00631084LZ | Construction of Slope Protection Structure | 120.504 | 16.0514 | 29400000 | 29397356.15 | 2022 | BET CONSTRUCTION & SUPPLY | 730 | 2022 | 2022-10-31 | 02/22/2022 | 2643.85 | 0 | 2022-08-10 |  | 82
2023 | Region I | ILOCOS NORTE | PAOAY (ILOCOS NORTE) | P00727057LZ | Construction of Flood Mitigation Structure | 120.5046 | 18.0604 | 9800000 | 9800000 | 2023 | DJCM CONSTRUCTION CORPORATION (FORMERLY: DJCM CONSTRUCTION) | 731 | 2023 | 2023-08-06 | 04/24/2023 | 0 | 0 | 2023-08-05 |  | 1
2023 | Region III | BATAAN | HERMOSA (BATAAN) | P00726146LZ | Construction of Flood Mitigation Structure | 120.5046 | 14.8402 | 19599999.58 | 19599999.58 | 2023 | M.C.J. VALENZUELA CONSTRUCTION ENTERPRISES | 732 | 2023 | 2023-09-14 | 02/27/2023 | 0 | 0 | 2023-09-16 | 2
2023 | Region III | BATAAN | CITY OF BALANGA (CAPITAL) (BATAAN) | P00725711LZ | Construction of Flood Mitigation Structure | 120.5056 | 14.6489 | 57895440.56 | 57900000 | 2023 | DAJ BUILDERS / POLYMER-VIC CONSTRUCTION | 733 | 2023 | 2023-12-28 | 02/20/2023 | 0 | 4559.44 | 2023-12-27 |  | 1
2021 | Region I | ILOCOS SUR |  | P00561480LZ | Construction of Flood Mitigation Structure | 120.5064 | 17.3163 | 9800000 | 9799963.07 | 2022 | MRK-SQUARE CONSTRUCTION AND SUPPLY | 734 | 2021 | 2022-09-07 | 10/11/2021 | 36.93 | 0 | 2022-01-29 |  | 221
2022 | Region I | ILOCOS NORTE | BADOC (ILOCOS NORTE) | P00621274LZ | Construction of Flood Mitigation Structure | 120.507 | 17.9211 | 96500000 | 96499997.59 | 2023 | ST. MATTHEW GEN. CONTRACTOR & DEVELOPMENT CORP. | 735 | 2022 | 2023-01-05 | 04/07/2022 | 2.41 | 0 | 2023-01-04 |  | 1
2022 | Region I | PANGASINAN | MANAOAG (PANGASINAN) | P00620460LZ | Rehabilitation / Major Repair of Slope Protection Structure | 120.5072 | 16.0257 | 24500000 | 24497954.52 | 2022 | MIGHTYWAY CONSTRUCTION AND SUPPLY | 736 | 2022 | 2022-08-07 | 02/17/2022 | 2045.48 | 0 | 2022-07-30 |  | 8
2023 | Region I | ILOCOS SUR | NAGBUKEL (ILOCOS SUR) | P00727082LZ | Construction of Flood Mitigation Structure | 120.5076 | 17.4292 | 9800000 | 9503793.64 | 2024 | M.V. SABALBURO CONSTRUCTION AND SUPPLY | 737 | 2023 | 2024-05-30 | 04/26/2023 | 296206.36 | 0 | 2023-07-25 |  | 310
2022 | Region I | ILOCOS SUR | BURGOS (ILOCOS SUR) | P00621514LZ | Construction of Flood Mitigation Structure | 120.5078 | 17.3152 | 29400000 | 28526172.61 | 2023 | MRK-SQUARE CONSTRUCTION AND SUPPLY | 738 | 2022 | 2023-08-29 | 04/04/2022 | 873827.39 | 0 | 2022-08-10 |  | 384
2022 | Region I | PANGASINAN | MANAOAG (PANGASINAN) | P00639433LZ | Construction of Slope Protection Structure | 120.5081 | 16.0553 | 27440000 | 27437043.92 | 2023 | BET CONSTRUCTION & SUPPLY | 739 | 2022 | 2023-03-08 | 03/25/2022 | 2956.08 | 0 | 2023-03-07 |  | 1
2023 | Region I | ILOCOS SUR | BURGOS (ILOCOS SUR) | P00742267LZ | Construction of Flood Mitigation Structure | 120.5102 | 17.3128 | 9900000 | 9602986.95 | 2024 | FIRST NORTHWAY DEVELOPMENT & CONSTRUCTION CORP. | 740 | 2023 | 2024-05-29 | 04/20/2023 | 297013.05 | 0 | 2023-07-10 |  | 324
2024 | Region I | PANGASINAN | MALASIQUI (PANGASINAN) | P00844728LZ | Construction of Drainage Structure | 120.511 | 15.883 | 4900000 | 4899968.34 | 2024 | EXTENSIVE STEEL WORKS AND CONSTRUCTION | 741 | 2024 | 2024-10-15 | 04/29/2024 | 31.66 | 0 | 2024-10-16 | 1
2023 | Region I | ILOCOS NORTE | SAN NICOLAS (ILOCOS NORTE) | P00726848LZ | Construction of Flood Mitigation Structure | 120.5112 | 18.0718 | 9650000 | 9650000 | 2023 | BADOC BUILDERS & SUPPLY, INC. (FORMERLY: BADOC BUILDER & SUPPLY | 742 | 2023 | 2023-08-23 | 05/08/2023 | 0 | 0 | 2023-08-22 |  | 1
2024 | Region I | ILOCOS SUR | BURGOS (ILOCOS SUR) | P00845896LZ | Construction of Revetment | 120.5113 | 17.3092 | 19800000 | 19203924.66 | 2024 | MRK-SQUARE CONSTRUCTION AND SUPPLY | 743 | 2024 | 2024-08-10 | 04/12/2024 | 596075.34 | 0 | 2024-08-09 |  | 1
2023 | Region III | PAMPANGA | FLORIDABLANCA (PAMPANGA) | P00742345LZ | Construction of Slope Protection Structure | 120.5117 | 14.9464 | 29699280.6 | 29693975.45 | 2023 | TONKA CONSTRUCTION | 744 | 2023 | 2023-09-07 | 04/05/2023 | 5305.15 | 0 | 2023-09-15 | 8
2023 | Region III | PAMPANGA | FLORIDABLANCA (PAMPANGA) | P00740606LZ | Construction of Slope Protection Structure | 120.5117 | 14.9464 | 48999000.52 | 48985800.03 | 2023 | TONKA CONSTRUCTION | 745 | 2023 | 2023-12-10 | 06/14/2023 | 13200.49 | 0 | 2023-12-09 |  | 1
2022 | Region III | PAMPANGA | PORAC (PAMPANGA) | P00620181LZ | Construction of Slope Protection Structure | 120.5121 | 15.1351 | 96209725.55 | 96200987.74 | 2023 | ALL EML CONSTRUCTION CORPORATION (FORMERLY: E.M.L. CONSTRUCTION & TRADING) | 746 | 2022 | 2023-05-11 | 03/07/2022 | 8737.81 | 0 | 2023-05-10 |  | 1
2022 | Region I | PANGASINAN | MANAOAG (PANGASINAN) | P00640501LZ | Construction of Slope Protection Structure | 120.5122 | 16.0572 | 29700000 | 29696964.87 | 2023 | J.G. GARCIA CONSTRUCTION & SUPPLY (FOR: J.G. GARCIA CONST.) | 747 | 2022 | 2023-07-28 | 03/25/2022 | 3035.13 | 0 | 2023-07-31 | 3
2021 | Cordillera Administrative Region | ABRA |  | P00561500LZ | Construction of Flood Mitigation Structure | 120.5122 | 17.5378 | 49000000 | 48997244.21 | 2022 | R.A. FANGLAYAN (RAF) GENERAL CONSTRUCTION INC. (FORMERLY:RAF GENERAL CONSTRUCTION) | 748 | 2021 | 2022-09-07 | 01/07/2022 | 2755.79 | 0 | 2022-08-22 |  | 16
2022 | Region III | PAMPANGA | PORAC (PAMPANGA) | P00639364LZ | Rehabilitation / Major Repair of Slope Protection Structure | 120.5124 | 15.1356 | 96499186.48 | 96493110.28 | 2023 | 11-16 CONSTRUCTION | 749 | 2022 | 2023-12-18 | 06/01/2022 | 6076.2 | 0 | 2023-12-17 |  | 1
2022 | Region I | ILOCOS SUR | SANTA LUCIA (ILOCOS SUR) | P00621497LZ | Construction of Flood Mitigation Structure | 120.5125 | 17.1131 | 39200000 | 39199988.57 | 2023 | FIRST NORTHWAY DEVELOPMENT & CONSTRUCTION CORP. | 750 | 2022 | 2023-08-30 | 04/04/2022 | 11.43 | 0 | 2022-10-18 |  | 316
2022 | Region III | PAMPANGA | FLORIDABLANCA (PAMPANGA) | P00631246LZ | Construction of Flood Mitigation Structure | 120.5128 | 14.9463 | 19599039.15 | 19578207.58 | 2022 | R.M. VITUG CONSTRUCTION | 751 | 2022 | 2022-07-20 | 02/21/2022 | 20831.57 | 0 | 2022-07-19 |  | 1
2024 | Region III | BATAAN | ABUCAY (BATAAN) | P00820222LZ | Construction of Revetment | 120.5134 | 14.7002 | 96499999.65 | 96499999.65 | 2024 | M.C.J. VALENZUELA CONSTRUCTION ENTERPRISES | 752 | 2024 | 2024-11-07 | 03/06/2024 | 0 | 0 | 2024-12-11 | 34
2023 | Region I | ILOCOS NORTE | SAN NICOLAS (ILOCOS NORTE) | P00726849LZ | Construction of Flood Mitigation Structure | 120.5134 | 18.0631 | 9650000 | 9625000 | 2023 | RCD GEN. CONTRACTOR & CONSTRUCTION SUPPLY | 753 | 2023 | 2023-08-24 | 05/22/2023 | 25000 | 0 | 2023-08-31 | 7
2024 | Region I | ILOCOS NORTE | PAOAY (ILOCOS NORTE) | P00848607LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.514 | 18.037 | 99000000 | 98999993.62 | 2024 | BADOC BUILDERS & SUPPLY, INC. (FORMERLY: BADOC BUILDER & SUPPLY | 754 | 2024 | 2024-11-16 | 05/03/2024 | 6.38 | 0 | 2024-12-13 | 27
2024 | Region I | LA UNION | SUDIPEN (LA UNION) | P00820711LZ | Construction of Flood Mitigation Structure | 120.5145 | 16.9195 | 29249976.07 | 28948715.87 | 2024 | ANORE CONSTRUCTION | 755 | 2024 | 2024-12-13 | 04/30/2024 | 301260.2 | 0 | 2025-01-09 | 27
2023 | Region III | PAMPANGA | FLORIDABLANCA (PAMPANGA) | P00740605LZ | Construction of Slope Protection Structure | 120.5147 | 14.9464 | 48999353.47 | 48990844.14 | 2023 | TONKA CONSTRUCTION | 756 | 2023 | 2023-10-22 | 04/26/2023 | 8509.33 | 0 | 2023-10-21 |  | 1
2024 | Region III | BATAAN | HERMOSA (BATAAN) | P00823393LZ | Construction of Flood Mitigation Structure | 120.5154 | 14.8385 | 96499999.74 | 96499999.74 | 2024 | M.C.J. VALENZUELA CONSTRUCTION ENTERPRISES | 757 | 2024 | 2024-12-03 | 04/23/2024 | 0 | 0 | 2025-01-04 | 32
2021 | Region I | ILOCOS SUR |  | P00525872LZ | Construction of Flood Mitigation Structure | 120.5164 | 16.9022 | 19600000 | 18815968.03 | 2022 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | 758 | 2021 | 2022-12-02 | 10/11/2021 | 784031.97 | 0 | 2022-05-02 |  | 214
2023 | Region III | BATAAN | ABUCAY (BATAAN) | P00727122LZ | Construction of Flood Mitigation Structure | 120.5164 | 14.698 | 48999999.93 | 48999991.82 | 2023 | M.C.J. VALENZUELA CONSTRUCTION ENTERPRISES | 759 | 2023 | 2023-12-28 | 04/27/2023 | 8.11 | 0 | 2024-01-03 | 6
2023 | Region I | PANGASINAN | MANAOAG (PANGASINAN) | P00727093LZ | Construction of Flood Mitigation Structure | 120.5165 | 16.0668 | 29400000 | 29395997.13 | 2023 | J.G. GARCIA CONSTRUCTION & SUPPLY (FOR: J.G. GARCIA CONST.) | 760 | 2023 | 2023-12-08 | 05/12/2023 | 4002.87 | 0 | 2023-12-07 |  | 1
2023 | Region III | BATAAN | ABUCAY (BATAAN) | P00742311LZ | Construction of Flood Mitigation Structure | 120.5166 | 14.7301 | 9900000 | 9899964.83 | 2023 | AS MACHA CONSTRUCTION AND TRADING | 761 | 2023 | 2023-12-06 | 07/10/2023 | 35.17 | 0 | 2023-12-08 | 2
2023 | Region I | PANGASINAN | MANAOAG (PANGASINAN) | P00727094LZ | Construction of Flood Mitigation Structure | 120.5171 | 16.0694 | 29400000 | 29396193.97 | 2023 | J.G. GARCIA CONSTRUCTION & SUPPLY (FOR: J.G. GARCIA CONST.) | 762 | 2023 | 2023-11-10 | 05/12/2023 | 3806.03 | 0 | 2024-01-10 | 61
2023 | Region III | BATAAN | ABUCAY (BATAAN) | P00742312LZ | Construction of Flood Mitigation Structure | 120.5181 | 14.7035 | 9899999.8 | 9899999.8 | 2023 | JEPA CONSTRUCTION & SUPPLIES | 763 | 2023 | 2023-12-27 | 10/03/2023 | 0 | 0 | 2024-01-30 | 34
2024 | Region I | ILOCOS NORTE | PINILI (ILOCOS NORTE) | P00845885LZ | Construction of Flood Mitigation Structure | 120.5181 | 17.9401 | 4950000 | 4950000 | 2024 | JLP CONSTRUCTION & SUPPLY (FORMERLY: JLP CONSTRUCT | 764 | 2024 | 2024-06-23 | 04/25/2024 | 0 | 0 | 2024-06-22 |  | 1
2022 | Region III | BATAAN | MARIVELES (BATAAN) | P00637068LZ | Rehabilitation / Major Repair of Slope Protection Structure | 120.5182 | 14.4528 | 24499999.72 | 24500000 | 2023 | A.T.P. CONSTRUCTION | 765 | 2022 | 2023-01-23 | 04/08/2022 | 0 | 0.28 | 2023-01-11 |  | 12
2023 | Region I | ILOCOS SUR | SANTA MARIA (ILOCOS SUR) | P00726051LZ | Construction of Flood Mitigation Structure | 120.5182 | 17.3635 | 29400000 | 29399959.6 | 2024 | MBB CONSTRUCTION AND SUPPLY (FORMERLY: MBB CONSTRUCTION) | 766 | 2023 | 2024-02-27 | 02/10/2023 | 40.4 | 0 | 2023-06-18 |  | 254
2023 | Region III | BATAAN | ORANI (BATAAN) | P00727123LZ | Construction of Flood Mitigation Structure | 120.5188 | 14.8122 | 48999999.97 | 48999999.97 | 2023 | M.C.J. VALENZUELA CONSTRUCTION ENTERPRISES | 767 | 2023 | 2023-10-19 | 04/17/2023 | 0 | 0 | 2023-10-20 | 1
2023 | Region I | ILOCOS NORTE | CITY OF BATAC (ILOCOS NORTE) | P00726844LZ | Construction of Drainage Structure | 120.519 | 18.0399 | 53075000 | 53074852.19 | 2024 | MEGAPOLITAN BUILDERS AND CONSTRUCTION SUPPLY | 768 | 2023 | 2024-01-26 | 03/22/2023 | 147.81 | 0 | 2024-01-25 |  | 1
2023 | Region I | ILOCOS SUR | ALILEM (ILOCOS SUR) | P00727080LZ | Construction of Flood Mitigation Structure | 120.5192 | 16.9171 | 14700000 | 14699383.62 | 2024 | FIRST NORTHWAY DEVELOPMENT & CONSTRUCTION CORP. | 769 | 2023 | 2024-05-29 | 03/22/2023 | 616.38 | 0 | 2023-07-11 |  | 323
2022 | Region I | ILOCOS SUR | ALILEM (ILOCOS SUR) | P00621512LZ | Construction of Flood Mitigation Structure | 120.5192 | 16.9156 | 19600000 | 19599852.17 | 2023 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | 770 | 2022 | 2023-04-18 | 04/04/2022 | 147.83 | 0 | 2022-08-14 |  | 247
2023 | Region I | ILOCOS NORTE | PAOAY (ILOCOS NORTE) | P00726852LZ | Construction of Flood Mitigation Structure | 120.5207 | 18.0591 | 9650000 | 9650000 | 2023 | TRI-LINE BUILDERS | 771 | 2023 | 2023-11-15 | 05/08/2023 | 0 | 0 | 2023-11-15 | 0
2023 | Region I | ILOCOS NORTE | PAOAY (ILOCOS NORTE) | P00725597LZ | Construction of Flood Mitigation Structure | 120.521 | 18.0642 | 48250000 | 48249956.06 | 2023 | BADOC BUILDERS & SUPPLY, INC. (FORMERLY: BADOC BUILDER & SUPPLY | 772 | 2023 | 2023-10-14 | 05/12/2023 | 43.94 | 0 | 2024-01-25 | 103
2024 | Cordillera Administrative Region | BENGUET | TUBA (BENGUET) | P00824846LZ | Construction of Flood Mitigation Structure | 120.521 | 16.4229 | 84920000 | 84877709.32 | 2025 | MG SAMIDAN CONSTRUCTION | 773 | 2024 | 2025-03-02 | 06/03/2024 | 42290.68 | 0 | 2025-03-01 |  | 1
2024 | Region I | ILOCOS SUR | BURGOS (ILOCOS SUR) | P00844716LZ | Construction of Flood Mitigation Structure | 120.5212 | 17.2941 | 14700000 | 14699536.4 | 2024 | FIRST NORTHWAY DEVELOPMENT & CONSTRUCTION CORP. | 774 | 2024 | 2024-06-28 | 03/27/2024 | 463.6 | 0 | 2024-06-27 |  | 1
2023 | Region I | PANGASINAN | CITY OF URDANETA (PANGASINAN) | P00742280LZ | Construction of Flood Mitigation Structure | 120.5212 | 15.9605 | 19600000 | 19741064.12 | 2024 | BUILDERS EXPONENT EMPIRE CORP. (FORMERLY: BUILDERS EXPONENT ENTERPRISE) | 775 | 2023 | 2024-02-10 | 07/17/2023 | 0 | 141064.12 | 2024-02-09 |  | 1
2022 | Cordillera Administrative Region | BENGUET | TUBA (BENGUET) | P00621002LZ | Construction of Flood Mitigation Structure | 120.5215 | 16.4177 | 12740000 | 12523558.95 | 2022 | J-NINE-INFINITY BUILDERS AND SUPPLIES | 776 | 2022 | 2022-10-18 | 01/31/2022 | 216441.05 | 0 | 2022-08-18 |  | 61
2022 | Region III | PAMPANGA | PORAC (PAMPANGA) | P00631250LZ | Construction of Slope Protection Structure | 120.5217 | 15.0977 | 48996511.82 | 48991419.29 | 2022 | R.D. SADSAD CONSTRUCTION & TRADING | 777 | 2022 | 2022-10-16 | 03/21/2022 | 5092.53 | 0 | 2022-10-15 |  | 1
2023 | Region I | ILOCOS NORTE | PAOAY (ILOCOS NORTE) | P00726851LZ | Construction of Flood Mitigation Structure | 120.5224 | 18.0645 | 9650000 | 9650000 | 2023 | MEGAPOLITAN BUILDERS AND CONSTRUCTION SUPPLY | 778 | 2023 | 2023-10-12 | 05/08/2023 | 0 | 0 | 2023-10-14 | 2
2023 | Region I | ILOCOS SUR | SUGPON (ILOCOS SUR) | P00736179LZ | Construction of Flood Mitigation Structure | 120.5226 | 16.8461 | 29334000.07 | 28518079.07 | 2024 | FIRST NORTHWAY DEVELOPMENT & CONSTRUCTION CORP. | 779 | 2023 | 2024-05-28 | 02/10/2023 | 815921 | 0 | 2023-06-18 |  | 345
2022 | Region III | PAMPANGA | PORAC (PAMPANGA) | P00631251LZ | Construction of Slope Protection Structure | 120.5228 | 15.1439 | 29399306.27 | 29382358.72 | 2022 | MBDIWA CONSTRUCTION AND SUPPLY | 780 | 2022 | 2022-07-12 | 02/21/2022 | 16947.55 | 0 | 2022-07-19 | 7
2024 | Region III | TARLAC | CAPAS (TARLAC) | P00821300LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.5232 | 15.4048 | 86849798.48 | 86844861.33 | 2024 | T2B3 BUILDERS AND SUPPLIES CORP. | 781 | 2024 | 2024-08-21 | 02/20/2024 | 4937.15 | 0 | 2024-08-20 |  | 1
2023 | Region I | ILOCOS NORTE | PAOAY (ILOCOS NORTE) | P00726371LZ | Construction of Flood Mitigation Structure | 120.5235 | 18.0714 | 106150000 | 106149992.4 | 2024 | ST. MATTHEW GEN. CONTRACTOR & DEVELOPMENT CORP. | 782 | 2023 | 2024-02-26 | 02/14/2023 | 7.6 | 0 | 2024-03-28 | 31
2022 | Region III | BATAAN | CITY OF BALANGA (CAPITAL) (BATAAN) | P00620514LZ | Construction of Flood Mitigation Structure | 120.525 | 14.6808 | 24500000 | 24500000 | 2022 | L.R. DE GUZMAN CONSTRUCTION | 783 | 2022 | 2022-08-11 | 02/16/2022 | 0 | 0 | 2022-08-10 |  | 1
2023 | Region III | BATAAN | ABUCAY (BATAAN) | P00727121LZ | Construction of Flood Mitigation Structure | 120.5257 | 14.7059 | 48999997.78 | 48999989.27 | 2023 | M.C.J. VALENZUELA CONSTRUCTION ENTERPRISES | 784 | 2023 | 2023-10-13 | 03/13/2023 | 8.51 | 0 | 2023-10-16 | 3
2024 | Region III | BATAAN | CITY OF BALANGA (CAPITAL) (BATAAN) | P00823487LZ | Construction of Flood Mitigation Structure | 120.526 | 14.6813 | 6860000 | 6695351.42 | 2024 | POLYMER-VIC CONSTRUCTION | 785 | 2024 | 2024-07-26 | 03/11/2024 | 164648.58 | 0 | 2024-07-25 |  | 1
2022 | Region III | BATAAN | ORANI (BATAAN) | P00621494LZ | Construction of Flood Mitigation Structure | 120.5261 | 14.8107 | 48509999.16 | 48509999.16 | 2023 | ROCKSTEEL CONSTRUCTION AND DEV'T CORPORATION / EGB CONSTRUCTION CORPORATION (FORMERLY: EGB CONSTRUCTION) | 786 | 2022 | 2023-09-14 | 08/11/2022 | 0 | 0 | 2023-09-16 | 2
2024 | Region III | BATAAN | CITY OF BALANGA (CAPITAL) (BATAAN) | P00823485LZ | Construction of Flood Mitigation Structure | 120.5274 | 14.6811 | 32340000 | 31845000 | 2024 | BPQ CONSTRUCTION AND TRADING / POLYMER-VIC CONSTRUCTION | 787 | 2024 | 2024-07-22 | 03/11/2024 | 495000 | 0 | 2024-08-16 | 25
2023 | Region I | ILOCOS SUR | SALCEDO (BAUGEN) (ILOCOS SUR) | P00740304LZ | Construction of Flood Mitigation Structure | 120.5276 | 17.1259 | 57900000 | 57899804.66 | 2023 | NORTH TECH BUILDERS AND CONSTRUCTION SUPPLY | 788 | 2023 | 2023-12-04 | 05/08/2023 | 195.34 | 0 | 2023-12-03 |  | 1
2022 | Region III | PAMPANGA | GUAGUA (PAMPANGA) | P00621454LZ | Construction of Slope Protection Structure | 120.5276 | 15.0125 | 48852943.86 | 48843246.67 | 2022 | ARROW CONSTRUCTION | 789 | 2022 | 2022-10-09 | 04/13/2022 | 9697.19 | 0 | 2022-10-08 |  | 1
2022 | Region III | BATAAN | SAMAL (BATAAN) | P00631171LZ | Construction of Flood Mitigation Structure | 120.5277 | 14.7748 | 48999999.81 | 48999999.81 | 2022 | M.C.J. VALENZUELA CONSTRUCTION ENTERPRISES | 790 | 2022 | 2022-10-30 | 02/21/2022 | 0 | 0 | 2022-11-01 | 2
2024 | Region III | BATAAN | ORANI (BATAAN) | P00820803LZ | Construction of Revetment | 120.5284 | 14.7917 | 47039999.94 | 47039999.94 | 2024 | PASCAL CONSTRUCTION | 791 | 2024 | 2024-08-05 | 02/16/2024 | 0 | 0 | 2024-08-20 | 15
2024 | Region III | BATAAN | ABUCAY (BATAAN) | P00839571LZ | Construction of Dike | 120.5284 | 14.7245 | 4949999.6 | 4949999.6 | 2024 | JEPA CONSTRUCTION & SUPPLIES | 792 | 2024 | 2024-09-30 | 07/09/2024 | 0 | 0 | 2024-10-06 | 6
2023 | Region I | ILOCOS NORTE | BADOC (ILOCOS NORTE) | P00725598LZ | Construction of Flood Mitigation Structure | 120.5286 | 17.9178 | 48250000 | 48249994.28 | 2023 | BADOC BUILDERS & SUPPLY, INC. (FORMERLY: BADOC BUILDER & SUPPLY | 793 | 2023 | 2023-06-30 | 02/14/2023 | 5.72 | 0 | 2023-08-05 | 36
2024 | Region III | TARLAC | PANIQUI (TARLAC) | P00820866LZ | Construction of Slope Protection Structure | 120.5287 | 15.6434 | 49000000 | 49500000 | 2024 | A.C. SOLIVEN CONSTRUCTION & GENERAL MERCHANDISE | 794 | 2024 | 2024-06-19 | 04/08/2024 | 0 | 500000 | 2024-10-04 | 107
2024 | Region III | TARLAC | PANIQUI (TARLAC) | P00820865LZ | Construction of Slope Protection Structure | 120.5287 | 15.6419 | 49000000 | 49500000 | 2024 | BIG BERTHA CONSTRUCTION & DEVELOPMENT | 795 | 2024 | 2024-09-19 | 04/08/2024 | 0 | 500000 | 2024-10-04 | 15
2023 | Region III | PAMPANGA | FLORIDABLANCA (PAMPANGA) | P00740608LZ | Construction of Slope Protection Structure | 120.5292 | 14.9664 | 48999144.61 | 48994727.99 | 2023 | ARROW CONSTRUCTION | 796 | 2023 | 2023-10-04 | 05/08/2023 | 4416.62 | 0 | 2023-10-03 |  | 1
2024 | Region III | TARLAC | PANIQUI (TARLAC) | P00820261LZ | Construction of Slope Protection Structure | 120.5297 | 15.6391 | 72375000 | 74250000 | 2024 | J.H.R. ENTERPRISES | 797 | 2024 | 2024-04-19 | 02/07/2024 | 0 | 1875000 | 2024-09-04 | 138
2023 | Region III | BATAAN | ORANI (BATAAN) | P00742313LZ | Construction of Flood Mitigation Structure | 120.5304 | 14.7917 | 9899999.99 | 9899999.99 | 2023 | SAN SEBASTIAN CONSTRUCTION | 798 | 2023 | 2023-10-23 | 07/24/2023 | 0 | 0 | 2023-10-24 | 1
2021 | Region I | ILOCOS SUR |  | P00561479LZ | Construction of Flood Mitigation Structure | 120.5305 | 17.1344 | 19800000 | 19599899.56 | 2022 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | 799 | 2021 | 2022-08-31 | 10/11/2021 | 200100.44 | 0 | 2022-05-02 |  | 121
2024 | Region III | BATAAN | CITY OF BALANGA (CAPITAL) (BATAAN) | P00820221LZ | Construction of Flood Mitigation Structure | 120.5306 | 14.6427 | 67550000 | 67550000 | 2024 | BPQ CONSTRUCTION AND TRADING / POLYMER-VIC CONSTRUCTION | 800 | 2024 | 2024-09-13 | 02/29/2024 | 0 | 0 | 2024-09-14 | 1
2022 | Region I | PANGASINAN | DAGUPAN CITY (PANGASINAN) | P00631089LZ | Construction of Slope Protection Structure | 120.3288 | 16.0458 | 49000000 | 48996222.71 | 2023 | BET CONSTRUCTION & SUPPLY | 801 | 2022 | 2023-05-29 | 02/18/2022 | 3777.29 | 0 | 2023-06-12 | 14
2023 | Region I | LA UNION | BAUANG (LA UNION) | P00726340LZ | Construction of Flood Mitigation Structure | 120.3291 | 16.519 | 78400000 | 77199690.44 | 2024 | C.T. LEONCIO CONSTRUCTION & TRADING | 802 | 2023 | 2024-04-01 | 03/03/2023 | 1200309.56 | 0 | 2024-03-31 |  | 1
2023 | Region I | PANGASINAN | SAN CARLOS CITY (PANGASINAN) | P00726076LZ | Construction of Flood Mitigation Structure | 120.3305 | 15.9155 | 19600000 | 19599856.12 | 2023 | MIGHTYWAY CONSTRUCTION AND SUPPLY | 803 | 2023 | 2023-08-11 | 02/13/2023 | 143.88 | 0 | 2023-08-15 | 4
2024 | Region I | LA UNION | BAUANG (LA UNION) | P00820712LZ | Construction of Flood Mitigation Structure | 120.3308 | 16.4678 | 28949995.25 | 28938082.84 | 2024 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | 804 | 2024 | 2024-09-23 | 04/16/2024 | 11912.41 | 0 | 2024-10-04 | 11
2024 | Region I | LA UNION | BAUANG (LA UNION) | P00824810LZ | Construction of Flood Mitigation Structure | 120.3314 | 16.5191 | 89744999.16 | 89737118.14 | 2025 | SILVERWOLVES CONSTRUCTION CORPORATION | 805 | 2024 | 2025-01-06 | 04/16/2024 | 7881.02 | 0 | 2025-01-03 |  | 3
2024 | Region I | LA UNION | BAUANG (LA UNION) | P00838336LZ | Construction of Flood Mitigation Structure | 120.3317 | 16.4591 | 96499998.37 | 96493843.08 | 2025 | ANORE CONSTRUCTION | 806 | 2024 | 2025-03-16 | 04/16/2024 | 6155.29 | 0 | 2025-01-04 |  | 71
2023 | Region I | PANGASINAN | SAN CARLOS CITY (PANGASINAN) | P00726087LZ | Construction of Flood Mitigation Structure | 120.3322 | 15.95 | 19600000 | 19136072.38 | 2023 | LEZA CONSTRUCTION & SUPPLY | 807 | 2023 | 2023-06-20 | 02/22/2023 | 463927.62 | 0 | 2023-08-02 | 43
2023 | Region I | PANGASINAN | SAN CARLOS CITY (PANGASINAN) | P00726077LZ | Construction of Flood Mitigation Structure | 120.333 | 15.8991 | 19600000 | 19370189.68 | 2023 | BALLESTEROS CONSTRUCTION AND SUPPLY | 808 | 2023 | 2023-04-17 | 02/13/2023 | 229810.32 | 0 | 2023-07-24 | 98
2022 | Region I | LA UNION | BAUANG (LA UNION) | P00620950LZ | Construction of Flood Mitigation Structure | 120.3336 | 16.5166 | 45569965.75 | 44202866.82 | 2022 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | 809 | 2022 | 2022-08-15 | 02/17/2022 | 1367098.93 | 0 | 2022-07-26 |  | 20
2024 | Region I | LA UNION | ARINGAY (LA UNION) | P00824802LZ | Construction of Flood Mitigation Structure | 120.3337 | 16.3889 | 96499995.82 | 96479841.9 | 2025 | ANORE CONSTRUCTION | 810 | 2024 | 2025-01-20 | 03/08/2024 | 20153.92 | 0 | 2024-12-06 |  | 45
2024 | Region I | LA UNION | BAUANG (LA UNION) | P00824821LZ | Construction of Flood Mitigation Structure | 120.3355 | 16.5164 | 89744994.56 | 89737362.73 | 2025 | SILVERWOLVES CONSTRUCTION CORPORATION | 811 | 2024 | 2025-03-16 | 04/16/2024 | 7631.83 | 0 | 2025-01-03 |  | 72
2024 | Region I | LA UNION | ARINGAY (LA UNION) | P00824801LZ | Construction of Flood Mitigation Structure | 120.3368 | 16.3881 | 96499999.35 | 96492336.54 | 2024 | ANORE CONSTRUCTION | 812 | 2024 | 2024-09-23 | 03/08/2024 | 7662.81 | 0 | 2024-12-06 | 74
2022 | Region I | LA UNION | BAUANG (LA UNION) | P00631074LZ | Construction of Flood Mitigation Structure | 120.3368 | 16.5194 | 34299997.97 | 33522947.4 | 2022 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | 813 | 2022 | 2022-08-15 | 02/16/2022 | 777050.57 | 0 | 2022-07-14 |  | 32
2022 | Region I | PANGASINAN | DAGUPAN CITY (PANGASINAN) | P00637752LZ | Construction of Flood Mitigation Structure | 120.3379 | 16.0346 | 69300000 | 69299993.18 | 2023 | BET CONSTRUCTION & SUPPLY | 814 | 2022 | 2023-02-27 | 04/07/2022 | 6.82 | 0 | 2023-02-26 |  | 1
2023 | Region I | LA UNION | ARINGAY (LA UNION) | P00726339LZ | Construction of Flood Mitigation Structure | 120.3379 | 16.3949 | 78400000 | 77199423.32 | 2024 | GREAT PACIFIC BUILDERS AND GEN. CONTRACTOR INC. | 815 | 2023 | 2024-06-07 | 02/14/2023 | 1200576.68 | 0 | 2024-06-06 |  | 1
2024 | Region I | LA UNION | BAUANG (LA UNION) | P00821476LZ | Construction of Flood Mitigation Structure | 120.338 | 16.5183 | 28949999.89 | 28946444.57 | 2025 | PANGASINAN NEW WILSON LUMBER & CONSTRUCTION SUPPLY | 816 | 2024 | 2025-03-16 | 06/19/2024 | 3555.32 | 0 | 2024-12-07 |  | 99
2023 | Region I | PANGASINAN | SAN CARLOS CITY (PANGASINAN) | P00726073LZ | Construction of Flood Mitigation Structure | 120.3382 | 15.9092 | 19600000 | 19599753.41 | 2023 | 2-R CONSTRUCTION SUPPLY | 817 | 2023 | 2023-05-15 | 02/13/2023 | 246.59 | 0 | 2023-07-24 | 70
2022 | Region I | LA UNION | SAN JUAN (LA UNION) | P00621444LZ | Construction of Flood Mitigation Structure | 120.3382 | 16.6905 | 29399785.9 | 29399459.28 | 2022 | J.A. OLIVAR ENGINEERING DESIGN, CONSTRUCTION AND S | 818 | 2022 | 2022-10-15 | 03/28/2022 | 326.62 | 0 | 2022-10-14 |  | 1
2023 | Region I | PANGASINAN | CALASIAO (PANGASINAN) | P00726097LZ | Construction of Flood Mitigation Structure | 120.3388 | 15.9547 | 19600000 | 19599732.5 | 2023 | HIGH ROCK CONSTRUCTION AND SUPPLIES INCORPORATED | 819 | 2023 | 2023-06-26 | 05/12/2023 | 267.5 | 0 | 2023-10-20 | 116
2024 | Region I | PANGASINAN | DAGUPAN CITY (PANGASINAN) | P00824832LZ | Construction of Flood Mitigation Structure | 120.3388 | 16.024 | 96500000 | 96500000 | 2024 | BMK CONSTRUCTION CORPORATION (FORMERLY B.M.K. CONSTRUCTION) | 820 | 2024 | 2024-07-31 | 03/11/2024 | 0 | 0 | 2024-12-22 | 144
2022 | Region I | LA UNION | AGOO (LA UNION) | P00631078LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.3398 | 16.309 | 44099995.78 | 44100000 | 2022 | BERSON'S CONSTRUCTION & TRADING | 821 | 2022 | 2022-08-01 | 02/22/2022 | 0 | 4.22 | 2022-08-18 | 17
2022 | Region I | LA UNION | SAN JUAN (LA UNION) | P00620941LZ | Construction of Flood Mitigation Structure | 120.3405 | 16.6796 | 19086476.65 | 19085370.2 | 2022 | J.A. OLIVAR ENGINEERING DESIGN, CONSTRUCTION AND S | 822 | 2022 | 2022-07-22 | 02/14/2022 | 1106.45 | 0 | 2022-07-21 |  | 1
2022 | Region I | LA UNION | ARINGAY (LA UNION) | P00640500LZ | Construction of Slope Protection Structure | 120.3409 | 16.3962 | 4949997.63 | 4898251.25 | 2022 | KRYPTONITE 6S BUILDERS INC. | 823 | 2022 | 2022-08-15 | 07/08/2022 | 51746.38 | 0 | 2022-09-11 | 27
2022 | Region I | LA UNION | AGOO (LA UNION) | P00631079LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.3411 | 16.3045 | 44099999.53 | 42721838.4 | 2022 | BONIMAR CONSTRUCTION ENTERPRISES | 824 | 2022 | 2022-08-15 | 02/24/2022 | 1378161.13 | 0 | 2022-08-27 | 12
2024 | Region I | LA UNION | ARINGAY (LA UNION) | P00824803LZ | Construction of Flood Mitigation Structure | 120.3417 | 16.3945 | 144750000 | 144739151.6 | 2024 | SILVERWOLVES CONSTRUCTION CORPORATION | 825 | 2024 | 2024-09-02 | 05/03/2024 | 10848.4 | 0 | 2025-01-17 | 137
2024 | Region I | LA UNION | BAUANG (LA UNION) | P00824813LZ | Construction of Flood Mitigation Structure | 120.3421 | 16.5188 | 89744995.99 | 89737280.52 | 2025 | SILVERWOLVES CONSTRUCTION CORPORATION | 826 | 2024 | 2025-01-06 | 04/16/2024 | 7715.47 | 0 | 2025-01-03 |  | 3
2024 | Region I | LA UNION | ARINGAY (LA UNION) | P00824840LZ | Construction of Flood Mitigation Structure | 120.3422 | 16.3981 | 19299998.47 | 19224221.54 | 2025 | KRYPTONITE 6S BUILDERS INC. | 827 | 2024 | 2025-03-16 | 05/08/2024 | 75776.93 | 0 | 2024-10-11 |  | 156
2024 | Region I | LA UNION | CITY OF SAN FERNANDO (CAPITAL) (LA UNION) | P00820710LZ | Construction of Flood Mitigation Structure | 120.3423 | 16.6147 | 38600000 | 38599971.35 | 2024 | E.E. MADAYAG CONSTRUCTION | 828 | 2024 | 2024-11-15 | 03/11/2024 | 28.65 | 0 | 2024-11-14 |  | 1
2022 | Region I | PANGASINAN | DAGUPAN CITY (PANGASINAN) | P00639431LZ | Construction of Drainage Structure | 120.3426 | 16.0765 | 4900000 | 4898112.71 | 2022 | ZOTA TRADING & CONSTRUCTION | 829 | 2022 | 2022-08-19 | 04/05/2022 | 1887.29 | 0 | 2022-06-21 |  | 59
2022 | Region I | PANGASINAN | SAN CARLOS CITY (PANGASINAN) | P00632747LZ | Construction of Flood Mitigation Structure | 120.3427 | 15.8738 | 4950000 | 4949968.24 | 2022 | MIGHTYWAY CONSTRUCTION AND SUPPLY | 830 | 2022 | 2022-09-30 | 02/21/2022 | 31.76 | 0 | 2022-11-09 | 40
2021 | Region I | LA UNION |  | P00525547LZ | Construction of Flood Mitigation Structure | 120.3441 | 16.343 | 67549999.97 | 66702855.9 | 2022 | LEGACY CONSTRUCTION CORPORATION (FORMERLY: LEGACY CONSTRUCTION) | 831 | 2021 | 2022-10-24 | 11/15/2021 | 847144.07 | 0 | 2022-06-26 |  | 120
2023 | Region I | PANGASINAN | SAN CARLOS CITY (PANGASINAN) | P00726078LZ | Construction of Flood Mitigation Structure | 120.3441 | 15.8776 | 19600000 | 19599122.42 | 2023 | JEUSMACK BUILDERS & CONSTRUCTION SUPPLY | 832 | 2023 | 2023-06-08 | 02/13/2023 | 877.58 | 0 | 2023-07-24 | 46
2023 | Region I | PANGASINAN | SAN CARLOS CITY (PANGASINAN) | P00726074LZ | Construction of Flood Mitigation Structure | 120.3442 | 15.9046 | 19600000 | 19599638.68 | 2023 | 5J AND G CONSTRUCTION AND SUPPLY | 833 | 2023 | 2023-05-29 | 02/13/2023 | 361.32 | 0 | 2023-07-24 | 56
2022 | Region I | LA UNION | AGOO (LA UNION) | P00631080LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.3445 | 16.3636 | 9799986.57 | 9554879.78 | 2022 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | 834 | 2022 | 2022-08-15 | 02/22/2022 | 245106.79 | 0 | 2022-06-19 |  | 57
2023 | Region IV-B | OCCIDENTAL MINDORO | LOOC (OCCIDENTAL MINDORO) | P00737550LZ | Construction of Flood Mitigation Structure | 120.345 | 13.6706 | 9800000 | 9798295.61 | 2023 | ANORE CONSTRUCTION | 835 | 2023 | 2023-06-26 | 02/10/2023 | 1704.39 | 0 | 2023-05-17 |  | 40
2022 | Region I | PANGASINAN | DAGUPAN CITY (PANGASINAN) | P00620458LZ | Construction of Flood Mitigation Structure | 120.345 | 16.0295 | 49000000 | 47539279.87 | 2023 | BET CONSTRUCTION & SUPPLY | 836 | 2022 | 2023-02-16 | 02/18/2022 | 1460720.13 | 0 | 2022-09-06 |  | 163
2023 | Region I | PANGASINAN | MANGATAREM (PANGASINAN) | P00726842LZ | Construction of Flood Mitigation Structure | 120.3454 | 15.7325 | 96500000 | 96446398.75 | 2024 | CHIARA2300 INCORPORATED / BERSON'S CONSTRUCTION & TRADING | 837 | 2023 | 2024-05-03 | 04/24/2023 | 53601.25 | 0 | 2024-05-02 |  | 1
2023 | Region I | ILOCOS SUR | SANTA CATALINA (ILOCOS SUR) | P00725617LZ | Construction of Flood Mitigation Structure | 120.3454 | 17.5693 | 53075000 | 53074634.39 | 2024 | APP CONSTRUCTION AND SUPPLIES / A.C. SOLIVEN CONSTRUCTION & GENERAL MERCHANDISE | 838 | 2023 | 2024-10-02 | 10/02/2023 | 365.61 | 0 | 2024-10-01 |  | 1
2022 | Region I | ILOCOS SUR | SANTA CATALINA (ILOCOS SUR) | P00620797LZ | Construction of Flood Mitigation Structure | 120.3458 | 17.5859 | 241250000 | 241249984.4 | 2023 | A.P.B. CONSTRUCTION / EGB CONSTRUCTION CORPORATION (FORMERLY: EGB CONSTRUCTION) | 839 | 2022 | 2023-01-06 | 03/04/2022 | 15.6 | 0 | 2023-01-05 |  | 1
2023 | Region I | PANGASINAN | DAGUPAN CITY (PANGASINAN) | P00727090LZ | Construction of Flood Mitigation Structure | 120.3465 | 16.0271 | 49000000 | 48995165.49 | 2023 | BET CONSTRUCTION & SUPPLY | 840 | 2023 | 2023-11-24 | 05/24/2023 | 4834.51 | 0 | 2023-12-10 | 16
2024 | Region I | LA UNION | BAUANG (LA UNION) | P00824823LZ | Construction of Flood Mitigation Structure | 120.347 | 16.5185 | 89744998.48 | 89737260.38 | 2025 | SILVERWOLVES CONSTRUCTION CORPORATION | 841 | 2024 | 2025-03-16 | 04/16/2024 | 7738.1 | 0 | 2025-01-03 |  | 72
2023 | Region I | ILOCOS SUR | SANTA CATALINA (ILOCOS SUR) | P00726840LZ | Construction of Flood Mitigation Structure | 120.347 | 17.5859 | 77200000 | 77199817.11 | 2024 | BET CONSTRUCTION & SUPPLY / LEZA CONSTRUCTION & SUPPLY | 842 | 2023 | 2024-11-30 | 10/02/2023 | 182.89 | 0 | 2024-11-29 |  | 1
2021 | Region I | ILOCOS SUR |  | P00525864LZ | Construction of Revetment | 120.3471 | 17.5859 | 24500000 | 24500000 | 2022 | LEZA CONSTRUCTION & SUPPLY | 843 | 2021 | 2022-12-28 | 02/24/2022 | 0 | 0 | 2023-01-27 | 30
2024 | Region I | LA UNION | BAUANG (LA UNION) | P00824815LZ | Construction of Flood Mitigation Structure | 120.3485 | 16.5207 | 89744999.91 | 89736907.75 | 2025 | SILVERWOLVES CONSTRUCTION CORPORATION | 844 | 2024 | 2025-03-16 | 04/16/2024 | 8092.16 | 0 | 2025-01-03 |  | 72
2024 | Region I | LA UNION | CABA (LA UNION) | P00843188LZ | Construction of Flood Mitigation Structure | 120.3488 | 16.4281 | 48249999.19 | 48244241.98 | 2024 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | 845 | 2024 | 2024-10-21 | 04/03/2024 | 5757.21 | 0 | 2024-10-15 |  | 6
2023 | Region I | ILOCOS SUR | SANTA CATALINA (ILOCOS SUR) | P00725618LZ | Construction of Flood Mitigation Structure | 120.3489 | 17.6008 | 53075000 | 51458957.34 | 2023 | APP CONSTRUCTION AND SUPPLIES / A.C. SOLIVEN CONSTRUCTION & GENERAL MERCHANDISE | 846 | 2023 | 2023-11-27 | 02/23/2023 | 1616042.66 | 0 | 2023-11-26 |  | 1
2023 | Region I | PANGASINAN | CALASIAO (PANGASINAN) | P00726095LZ | Construction of Flood Mitigation Structure | 120.349 | 16.0021 | 19600000 | 19019455.46 | 2023 | MANIMELDS CONSTRUCTION & IRON WORKS | 847 | 2023 | 2023-09-18 | 05/12/2023 | 580544.54 | 0 | 2023-10-20 | 32
2024 | Region I | LA UNION | BACNOTAN (LA UNION) | P00824806LZ | Construction of Flood Mitigation Structure | 120.349 | 16.7053 | 154400000 | 154399996.7 | 2024 | RODEKOM GENERAL CONSTRUCTION AND ENTERPRISE | 848 | 2024 | 2024-11-05 | 06/14/2024 | 3.3 | 0 | 2025-03-09 | 124
2023 | Region I | LA UNION | CABA (LA UNION) | P00735958LZ | Construction of Flood Mitigation Structure | 120.3491 | 16.4283 | 115800000 | 115799320.9 | 2024 | C.T. LEONCIO CONSTRUCTION & TRADING | 849 | 2023 | 2024-05-31 | 02/14/2023 | 679.1 | 0 | 2024-05-30 |  | 1
2023 | Region I | PANGASINAN | CALASIAO (PANGASINAN) | P00726059LZ | Construction of Flood Mitigation Structure | 120.3492 | 16.006 | 49000000 | 47992273.56 | 2023 | ALCEL CONSTRUCTION | 850 | 2023 | 2023-07-17 | 02/13/2023 | 1007726.44 | 0 | 2023-08-30 | 44
2023 | Region I | PANGASINAN | CALASIAO (PANGASINAN) | P00737428LZ | Construction of Flood Mitigation Structure | 120.3495 | 16.0009 | 9900000 | 9608748.04 | 2023 | BALLESTEROS CONSTRUCTION AND SUPPLY | 851 | 2023 | 2023-09-25 | 05/12/2023 | 291251.96 | 0 | 2023-09-24 |  | 1
2023 | Region I | PANGASINAN | CALASIAO (PANGASINAN) | P00726093LZ | Construction of Flood Mitigation Structure | 120.3496 | 16.0054 | 19600000 | 19369726.57 | 2023 | JEUSMACK BUILDERS & CONSTRUCTION SUPPLY | 852 | 2023 | 2023-09-13 | 05/12/2023 | 230273.43 | 0 | 2023-10-20 | 37
2024 | Region I | LA UNION | CABA (LA UNION) | P00844720LZ | Construction of Flood Mitigation Structure | 120.3505 | 16.4293 | 48999993.44 | 48995000 | 2025 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | 853 | 2024 | 2025-02-16 | 02/16/2024 | 4993.44 | 0 | 2024-08-29 |  | 171
2023 | Region I | LA UNION | CITY OF SAN FERNANDO (CAPITAL) (LA UNION) | P00740568LZ | Construction of Flood Mitigation Structure | 120.3508 | 16.6256 | 4899998.98 | 4899991.63 | 2023 | RAPHAEIL CONSTRUCTION | 854 | 2023 | 2023-05-24 | 03/27/2023 | 7.35 | 0 | 2023-08-15 | 83
2023 | Region I | LA UNION | CITY OF SAN FERNANDO (CAPITAL) (LA UNION) | P00742115LZ | Construction of Flood Mitigation Structure | 120.3509 | 16.6402 | 99000000 | 98996959.56 | 2024 | ST. GERRARD CONSTRUCTION GEN. CONTRACTOR & DEVELOPMENT CORP. (FORMERLY:ST. GERRARD CONSTRUCTION) | 855 | 2023 | 2024-04-30 | 05/08/2023 | 3040.44 | 0 | 2024-03-16 |  | 45
2023 | Region I | PANGASINAN | CALASIAO (PANGASINAN) | P00726096LZ | Construction of Flood Mitigation Structure | 120.3519 | 15.9859 | 49000000 | 47554595.06 | 2023 | J.G. GARCIA CONSTRUCTION & SUPPLY (FOR: J.G. GARCIA CONST.) | 856 | 2023 | 2023-08-11 | 05/12/2023 | 1445404.94 | 0 | 2023-11-26 | 107
2023 | Region I | LA UNION | SANTO TOMAS (LA UNION) | P00727086LZ | Construction of Flood Mitigation Structure | 120.3537 | 16.2761 | 48999971.73 | 48754908.74 | 2024 | A.I.P. CONSTRUCTION / BMK CONSTRUCTION CORPORATION (FORMERLY B.M.K. CONSTRUCTION) | 857 | 2023 | 2024-02-11 | 02/23/2023 | 245062.99 | 0 | 2023-09-06 |  | 158
2023 | Region I | PANGASINAN | CALASIAO (PANGASINAN) | P00726094LZ | Construction of Flood Mitigation Structure | 120.3537 | 15.9948 | 19600000 | 19589753.85 | 2023 | JEUSMACK BUILDERS & CONSTRUCTION SUPPLY | 858 | 2023 | 2023-07-17 | 05/12/2023 | 10246.15 | 0 | 2023-10-20 | 95
2024 | Region I | LA UNION | BAUANG (LA UNION) | P00821101LZ | Construction of Flood Mitigation Structure | 120.3538 | 16.5182 | 96499994.18 | 96492001.36 | 2025 | ANORE CONSTRUCTION | 859 | 2024 | 2025-02-16 | 04/16/2024 | 7992.82 | 0 | 2025-01-14 |  | 33
2021 | Region III | TARLAC |  | P00561142LZ | Construction of Slope Protection Structure | 120.3546 | 15.5082 | 67550000 | 56776877.63 | 2022 | R-II BUILDERS, INC. | 860 | 2021 | 2022-11-27 | 03/30/2022 | 10773122.37 | 0 | 2022-09-24 |  | 64
2024 | Region I | LA UNION | BAUANG (LA UNION) | P00824817LZ | Construction of Flood Mitigation Structure | 120.3547 | 16.5191 | 89744997.81 | 89736445.72 | 2025 | SILVERWOLVES CONSTRUCTION CORPORATION | 861 | 2024 | 2025-03-16 | 04/16/2024 | 8552.09 | 0 | 2025-01-03 |  | 72
2021 | Region III | TARLAC |  | P00561141LZ | Construction of Slope Protection Structure | 120.3552 | 15.5081 | 67550000 | 64172013.74 | 2022 | R-II BUILDERS, INC. | 862 | 2021 | 2022-09-25 | 03/30/2022 | 3377986.26 | 0 | 2022-09-24 |  | 1
2024 | Region I | PANGASINAN | SAN CARLOS CITY (PANGASINAN) | P00845917LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.356 | 15.917 | 54450000 | 9899873.79 | 2024 | MIGHTYWAY CONSTRUCTION AND SUPPLY | 863 | 2024 | 2024-09-11 | 06/03/2024 | 44550126.21 | 0 | 2024-11-18 | 68
2023 | Region I | LA UNION | ARINGAY (LA UNION) | P00727233LZ | Construction of Flood Mitigation Structure | 120.3563 | 16.3915 | 72374998.02 | 72334509.64 | 2024 | SILVERWOLVES CONSTRUCTION CORPORATION | 864 | 2023 | 2024-02-11 | 04/19/2023 | 40488.38 | 0 | 2023-12-09 |  | 64
2023 | Region I | LA UNION | SAN JUAN (LA UNION) | P00726638LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.3568 | 16.6848 | 48999975.9 | 48998880.4 | 2023 | MY BUILDERS AND CONSTRUCTION | 865 | 2023 | 2023-08-30 | 02/14/2023 | 1095.5 | 0 | 2023-09-30 | 31
2023 | Region I | PANGASINAN | SAN CARLOS CITY (PANGASINAN) | P00726084LZ | Construction of Flood Mitigation Structure | 120.3576 | 15.9188 | 19600000 | 19031663.71 | 2023 | LEZA CONSTRUCTION & SUPPLY | 866 | 2023 | 2023-12-15 | 05/12/2023 | 568336.29 | 0 | 2023-12-19 | 4
2024 | Region I | ILOCOS SUR | SANTO DOMINGO (ILOCOS SUR) | P00839546LZ | Construction of Flood Mitigation Structure | 120.3587 | 17.6451 | 4950000 | 4920631.39 | 2024 | FIT CONSTRUCTION | 867 | 2024 | 2024-05-03 | 02/26/2024 | 29368.61 | 0 | 2024-05-06 | 3
2023 | Region I | LA UNION | ARINGAY (LA UNION) | P00727234LZ | Construction of Flood Mitigation Structure | 120.3598 | 16.3913 | 72374992.09 | 72334339.31 | 2024 | SILVERWOLVES CONSTRUCTION CORPORATION | 868 | 2023 | 2024-02-11 | 04/19/2023 | 40652.78 | 0 | 2023-12-09 |  | 64
2022 | Region III | TARLAC | SAN JOSE (TARLAC) | P00637030LZ | Construction of Slope Protection Structure | 120.3602 | 15.504 | 96500000 | 93815457.98 | 2022 | STO. CRISTO CONSTRUCTION & TRADING INC. (FOR: STO. CRISTO CONSTRUCTION & TRADING) | 869 | 2022 | 2022-11-25 | 03/31/2022 | 2684542.02 | 0 | 2022-11-24 |  | 1
2022 | Region III | TARLAC | SAN JOSE (TARLAC) | P00637031LZ | Construction of Slope Protection Structure | 120.3607 | 15.5036 | 96500000 | 94473488.06 | 2022 | STO. CRISTO CONSTRUCTION & TRADING INC. (FOR: STO. CRISTO CONSTRUCTION & TRADING) | 870 | 2022 | 2022-11-25 | 03/31/2022 | 2026511.94 | 0 | 2022-11-24 |  | 1
2022 | Region III | TARLAC | SAN JOSE (TARLAC) | P00639353LZ | Construction of Slope Protection Structure | 120.3607 | 15.5036 | 96500000 | 94270850 | 2022 | THREE W BUILDERS, INC. | 871 | 2022 | 2022-09-25 | 03/30/2022 | 2229150 | 0 | 2022-09-24 |  | 1
2024 | Region I | LA UNION | BAUANG (LA UNION) | P00824819LZ | Construction of Flood Mitigation Structure | 120.3607 | 16.5162 | 89744999.98 | 89736347.57 | 2025 | SILVERWOLVES CONSTRUCTION CORPORATION | 872 | 2024 | 2025-03-16 | 04/16/2024 | 8652.41 | 0 | 2025-01-03 |  | 72
2023 | Region I | PANGASINAN | CALASIAO (PANGASINAN) | P00726062LZ | Construction of Flood Mitigation Structure | 120.3614 | 16.0081 | 19600000 | 19599931.81 | 2023 | HIGH ROCK CONSTRUCTION AND SUPPLIES INCORPORATED | 873 | 2023 | 2023-07-17 | 06/21/2023 | 68.19 | 0 | 2023-11-29 | 135
2023 | Region I | LA UNION | ARINGAY (LA UNION) | P00727235LZ | Construction of Flood Mitigation Structure | 120.3623 | 16.3903 | 72374999.04 | 72334295.99 | 2024 | SILVERWOLVES CONSTRUCTION CORPORATION | 874 | 2023 | 2024-02-11 | 04/19/2023 | 40703.05 | 0 | 2023-12-09 |  | 64
2022 | Region I | PANGASINAN | CALASIAO (PANGASINAN) | P00620782LZ | Construction of Flood Mitigation Structure | 120.3631 | 16.0236 | 129562830 | 129562772 | 2022 | ARCINUE COMM'L CORPORATION | 875 | 2022 | 2022-12-04 | 04/12/2022 | 58 | 0 | 2023-03-24 | 110
2022 | Region I | LA UNION | SAN JUAN (LA UNION) | P00620948LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.3635 | 16.6833 | 48019927.13 | 48020000 | 2022 | MY BUILDERS AND CONSTRUCTION | 876 | 2022 | 2022-07-28 | 02/11/2022 | 0 | 72.87 | 2022-08-15 | 18
2023 | Region I | PANGASINAN | CALASIAO (PANGASINAN) | P00726064LZ | Construction of Flood Mitigation Structure | 120.3636 | 15.9817 | 9800000 | 9799989.13 | 2023 | HIGH ROCK CONSTRUCTION AND SUPPLIES INCORPORATED | 877 | 2023 | 2023-05-31 | 05/12/2023 | 10.87 | 0 | 2023-08-14 | 75
2023 | Region I | LA UNION | CITY OF SAN FERNANDO (CAPITAL) (LA UNION) | P00742274LZ | Construction of Slope Protection Structure | 120.3641 | 16.6187 | 4949992.07 | 4949512.1 | 2023 | FABRO CONSTRUCTION | 878 | 2023 | 2023-09-22 | 03/30/2023 | 479.97 | 0 | 2023-09-25 | 3
2022 | Region I | PANGASINAN | CALASIAO (PANGASINAN) | P00620783LZ | Construction of Flood Mitigation Structure | 120.3644 | 16.0187 | 128345000 | 128344991.7 | 2023 | ARCINUE COMM'L CORPORATION | 879 | 2022 | 2023-01-07 | 04/12/2022 | 8.3 | 0 | 2023-03-06 | 58
2024 | Region I | LA UNION | SANTO TOMAS (LA UNION) | P00821103LZ | Construction of Flood Mitigation Structure | 120.3653 | 16.5121 | 96499998.98 | 96494448.46 | 2025 | HIGH ROCK CONSTRUCTION AND SUPPLIES INCORPORATED / JHI CONSTRUCTION & SUPPLY | 880 | 2024 | 2025-03-16 | 12/24/2024 | 5550.52 | 0 | 2025-09-23 | 191
2024 | Region I | LA UNION | SAN JUAN (LA UNION) | P00824805LZ | Construction of Flood Mitigation Structure | 120.3658 | 16.6743 | 154400000 | 154399997.4 | 2024 | BALINTUGAN CONSTRUCTION | 881 | 2024 | 2024-11-11 | 03/07/2024 | 2.6 | 0 | 2024-11-30 | 19
2023 | Region I | PANGASINAN | SAN CARLOS CITY (PANGASINAN) | P00726072LZ | Construction of Flood Mitigation Structure | 120.3664 | 15.9604 | 19600000 | 19593200.89 | 2023 | JEUSMACK BUILDERS & CONSTRUCTION SUPPLY | 882 | 2023 | 2023-05-10 | 02/13/2023 | 6799.11 | 0 | 2023-07-24 | 75
2022 | Region I | LA UNION | AGOO (LA UNION) | P00631077LZ | Construction of Flood Mitigation Structure | 120.3665 | 16.3231 | 44099991.15 | 42775317.09 | 2022 | BONIMAR CONSTRUCTION ENTERPRISES | 883 | 2022 | 2022-08-15 | 02/18/2022 | 1324674.06 | 0 | 2022-08-21 | 6
2022 | Region I | LA UNION | AGOO (LA UNION) | P00630927LZ | Construction of Flood Mitigation Structure | 120.3665 | 16.3231 | 67549999.23 | 66191241.77 | 2023 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | 884 | 2022 | 2023-05-15 | 04/04/2022 | 1358757.46 | 0 | 2022-10-01 |  | 226
2023 | Region I | LA UNION | SAN JUAN (LA UNION) | P00726637LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.367 | 16.6815 | 49000000 | 48998252.87 | 2023 | MY BUILDERS AND CONSTRUCTION | 885 | 2023 | 2023-08-24 | 02/10/2023 | 1747.13 | 0 | 2023-10-02 | 39
2024 | Region I | PANGASINAN | BAYAMBANG (PANGASINAN) | P00825216LZ | Construction of Flood Mitigation Structure | 120.367 | 15.786 | 39200000 | 9533434.84 | 2024 | HIGH ROCK CONSTRUCTION AND SUPPLIES INCORPORATED / JHI CONSTRUCTION & SUPPLY | 886 | 2024 | 2024-08-05 | 05/06/2024 | 29666565.16 | 0 | 2024-10-14 | 70
2023 | Region I | LA UNION | ARINGAY (LA UNION) | P00727236LZ | Construction of Flood Mitigation Structure | 120.3676 | 16.3896 | 72374999.67 | 72334428.4 | 2024 | SILVERWOLVES CONSTRUCTION CORPORATION | 887 | 2023 | 2024-02-11 | 04/19/2023 | 40571.27 | 0 | 2023-12-09 |  | 64
2024 | Region I | LA UNION | BAUANG (LA UNION) | P00825211LZ | Construction of Flood Mitigation Structure | 120.3677 | 16.5121 | 48249993.13 | 48238274.49 | 2024 | UNIVERSAL DE LEON CONSTRUCTION AND AGGREGATES | 888 | 2024 | 2024-12-23 | 03/19/2024 | 11718.64 | 0 | 2024-09-30 |  | 84
2023 | Region I | PANGASINAN | CALASIAO (PANGASINAN) | P00726060LZ | Construction of Flood Mitigation Structure | 120.3683 | 15.9667 | 49000000 | 48999947.92 | 2023 | BERSON'S CONSTRUCTION & TRADING | 889 | 2023 | 2023-11-29 | 02/22/2023 | 52.08 | 0 | 2023-11-28 |  | 1
2023 | Region I | LA UNION | SAN JUAN (LA UNION) | P00742273LZ | Construction of Flood Mitigation Structure | 120.3685 | 16.6802 | 9900000 | 9898955.58 | 2023 | FABRO CONSTRUCTION | 890 | 2023 | 2023-12-15 | 04/04/2023 | 1044.42 | 0 | 2023-09-29 |  | 77
2023 | Region I | PANGASINAN | CALASIAO (PANGASINAN) | P00726061LZ | Construction of Flood Mitigation Structure | 120.3691 | 15.9575 | 49000000 | 48999998.83 | 2023 | ORIENTAL SALES CENTER AND CONTRACTOR / ALCEL CONSTRUCTION | 891 | 2023 | 2023-11-20 | 02/13/2023 | 1.17 | 0 | 2023-11-19 |  | 1
2024 | Region I | PANGASINAN | SAN CARLOS CITY (PANGASINAN) | P00844729LZ | Construction of Flood Mitigation Structure | 120.37 | 15.895 | 19600000 | 19197354.75 | 2024 | EXTENSIVE STEEL WORKS AND CONSTRUCTION | 892 | 2024 | 2024-07-17 | 03/25/2024 | 402645.25 | 0 | 2024-09-02 | 47
2023 | Region I | PANGASINAN | SAN CARLOS CITY (PANGASINAN) | P00726071LZ | Construction of Flood Mitigation Structure | 120.3704 | 15.8953 | 19600000 | 19212536.57 | 2023 | BALLESTEROS CONSTRUCTION AND SUPPLY | 893 | 2023 | 2023-03-24 | 02/13/2023 | 387463.43 | 0 | 2023-07-24 | 122
2022 | Region I | PANGASINAN | SAN CARLOS CITY (PANGASINAN) | P00621447LZ | Construction of Flood Mitigation Structure | 120.3705 | 15.8952 | 19600000 | 19594702.35 | 2022 | BALLESTEROS CONSTRUCTION AND SUPPLY | 894 | 2022 | 2022-08-08 | 03/24/2022 | 5297.65 | 0 | 2022-09-01 | 24
2023 | Region I | LA UNION | AGOO (LA UNION) | P00726827LZ | Construction of Flood Mitigation Structure | 120.3706 | 16.3275 | 72375000 | 72364531.35 | 2024 | SILVERWOLVES CONSTRUCTION CORPORATION | 895 | 2023 | 2024-04-05 | 05/12/2023 | 10468.65 | 0 | 2024-04-04 |  | 1
2023 | Region I | LA UNION | ARINGAY (LA UNION) | P00727237LZ | Construction of Flood Mitigation Structure | 120.3707 | 16.3901 | 72374998.57 | 72334998.57 | 2024 | MG SAMIDAN CONSTRUCTION | 896 | 2023 | 2024-02-11 | 04/19/2023 | 40000 | 0 | 2023-12-09 |  | 64
2023 | Region I | ILOCOS SUR | SAN VICENTE (ILOCOS SUR) | P00727066LZ | Construction of Flood Mitigation Structure | 120.3708 | 17.6121 | 29400000 | 29400000 | 2023 | FIT CONSTRUCTION | 897 | 2023 | 2023-07-17 | 03/10/2023 | 0 | 0 | 2023-07-16 |  | 1
2022 | Region I | ILOCOS SUR | SAN VICENTE (ILOCOS SUR) | P00620777LZ | Construction of Flood Mitigation Structure | 120.3712 | 17.6188 | 93100000 | 91675000 | 2022 | A.P.B. CONSTRUCTION / FIT CONSTRUCTION | 898 | 2022 | 2022-12-15 | 02/24/2022 | 1425000 | 0 | 2022-12-20 | 5
2023 | Region III | TARLAC | SAN CLEMENTE (TARLAC) | P00735973LZ | Construction of Flood Mitigation Structure | 120.3717 | 15.7366 | 72375000 | 70203757.24 | 2023 | R.R. RICAFORT CONSTRUCTION AND SUPPLIES | 899 | 2023 | 2023-11-08 | 02/10/2023 | 2171242.76 | 0 | 2023-11-07 |  | 1
2024 | Region I | PANGASINAN | CALASIAO (PANGASINAN) | P00845920LZ | Construction of Drainage Structure | 120.372 | 16.025 | 4950000 | 4815318.1 | 2024 | JEUSMACK BUILDERS & CONSTRUCTION SUPPLY | 900 | 2024 | 2024-09-03 | 03/25/2024 | 134681.9 | 0 | 2024-09-11 | 8
2022 | Region I | ILOCOS SUR | SANTIAGO (ILOCOS SUR) | P00632736LZ | Construction of Flood Mitigation Structure | 120.4296 | 17.2368 | 4900000 | 4899931.87 | 2022 | FIRST NORTHWAY DEVELOPMENT & CONSTRUCTION CORP. | 901 | 2022 | 2022-07-27 | 02/24/2022 | 68.13 | 0 | 2022-07-07 |  | 20
2022 | Region III | BATAAN | DINALUPIHAN (BATAAN) | P00631168LZ | Construction of Flood Mitigation Structure | 120.4297 | 14.8449 | 29399999.45 | 29399972.26 | 2022 | M.C.J. VALENZUELA CONSTRUCTION ENTERPRISES | 902 | 2022 | 2022-07-20 | 02/16/2022 | 27.19 | 0 | 2022-07-22 | 2
2023 | Region I | PANGASINAN | MANGALDAN (PANGASINAN) | P00726834LZ | Construction of Flood Mitigation Structure | 120.4297 | 16.0663 | 24125000 | 24121805.29 | 2023 | BET CONSTRUCTION & SUPPLY | 903 | 2023 | 2023-10-12 | 03/22/2023 | 3194.71 | 0 | 2023-10-28 | 16
2024 | Region I | LA UNION | TUBAO (LA UNION) | P00821472LZ | Construction of Flood Mitigation Structure | 120.4298 | 16.336 | 48999995.93 | 48938884.3 | 2025 | RODEKOM GENERAL CONSTRUCTION AND ENTERPRISE | 904 | 2024 | 2025-03-16 | 02/02/2024 | 61111.63 | 0 | 2024-08-15 |  | 213
2024 | Region I | LA UNION | TUBAO (LA UNION) | P00821097LZ | Construction of Flood Mitigation Structure | 120.4299 | 16.3671 | 144750000 | 144749743.4 | 2024 | RODEKOM GENERAL CONSTRUCTION AND ENTERPRISE | 905 | 2024 | 2024-07-26 | 03/15/2024 | 256.6 | 0 | 2025-01-10 | 168
2022 | Region III | BATAAN | DINALUPIHAN (BATAAN) | P00631169LZ | Construction of Flood Mitigation Structure | 120.4302 | 14.8468 | 29399999.89 | 29399973.04 | 2022 | M.C.J. VALENZUELA CONSTRUCTION ENTERPRISES | 906 | 2022 | 2022-07-25 | 02/21/2022 | 26.85 | 0 | 2022-07-26 | 1
2023 | Region I | LA UNION | TUBAO (LA UNION) | P00726337LZ | Construction of Flood Mitigation Structure | 120.4304 | 16.3543 | 96500000 | 96463694.46 | 2023 | RODEKOM GENERAL CONSTRUCTION AND ENTERPRISE | 907 | 2023 | 2023-11-13 | 02/14/2023 | 36305.54 | 0 | 2023-12-22 | 39
2024 | Region I | ILOCOS SUR | SAN JUAN (LAPOG) (ILOCOS SUR) | P00844711LZ | Construction of Flood Mitigation Structure | 120.4311 | 17.7522 | 49000000 | 48899824.9 | 2024 | FIT CONSTRUCTION | 908 | 2024 | 2024-12-16 | 05/13/2024 | 100175.1 | 0 | 2025-01-23 | 38
2024 | Region III | TARLAC | SANTA IGNACIA (TARLAC) | P00820251LZ | Construction of Slope Protection Structure | 120.4312 | 15.619 | 89401460 | 89400000 | 2025 | BIG BERTHA CONSTRUCTION & DEVELOPMENT | 909 | 2024 | 2025-01-02 | 02/13/2024 | 1460 | 0 | 2025-01-01 |  | 1
2022 | Region I | ILOCOS SUR | SANTA (ILOCOS SUR) | P00621516LZ | Construction of Flood Mitigation Structure | 120.4314 | 17.4861 | 9800000 | 9503087.02 | 2022 | M.V. SABALBURO CONSTRUCTION AND SUPPLY | 910 | 2022 | 2022-07-04 | 04/04/2022 | 296912.98 | 0 | 2022-07-06 | 2
2024 | Region I | PANGASINAN | BAYAMBANG (PANGASINAN) | P00825218LZ | Construction of Flood Mitigation Structure | 120.432 | 15.764 | 39200000 | 19599951.25 | 2025 | JEUSMACK BUILDERS & CONSTRUCTION SUPPLY | 911 | 2024 | 2025-01-24 | 06/18/2024 | 19600048.75 | 0 | 2025-01-25 | 1
2023 | Region I | PANGASINAN | SAN JACINTO (PANGASINAN) | P00737422LZ | Construction of Drainage Structure | 120.4321 | 16.0697 | 4950000 | 4945988.19 | 2023 | MIGHTYWAY CONSTRUCTION AND SUPPLY | 912 | 2023 | 2023-06-14 | 02/16/2023 | 4011.81 | 0 | 2023-06-13 |  | 1
2024 | Region III | TARLAC | SANTA IGNACIA (TARLAC) | P00839595LZ | Construction of Flood Mitigation Structure | 120.4325 | 15.617 | 49500000 | 50000000 | 2024 | LAMASIA BUILDERS AND SUPPLY CORP. | 913 | 2024 | 2024-07-24 | 01/26/2024 | 0 | 500000 | 2024-07-23 |  | 1
2024 | Region I | ILOCOS SUR | SANTA LUCIA (ILOCOS SUR) | P00844715LZ | Construction of Flood Mitigation Structure | 120.4333 | 17.1289 | 39200000 | 39199443.13 | 2025 | FIRST NORTHWAY DEVELOPMENT & CONSTRUCTION CORP. | 914 | 2024 | 2025-02-05 | 02/28/2024 | 556.87 | 0 | 2024-10-04 |  | 124
2022 | Region III | TARLAC | CAPAS (TARLAC) | P00621575LZ | Construction of Dike | 120.4336 | 15.3317 | 96499705.61 | 96011740.9 | 2022 | ROYAL CROWN MONARCH CONSTRUCTION & SUPPLIES CORP. | 915 | 2022 | 2022-11-24 | 03/26/2022 | 487964.71 | 0 | 2022-11-23 |  | 1
2025 | Region I | PANGASINAN | CITY OF ALAMINOS (PANGASINAN) | P00941152LZ | Construction of Flood Mitigation Structure | 120.4339 | 16.356 | 4950000 | 4850666.92 | 2025 | GED CONSTRUCTION | 916 | 2025 | 2025-05-21 | 02/10/2025 | 99333.08 | 0 | 2025-05-20 |  | 1
2023 | Region I | LA UNION | BAGULIN (LA UNION) | P00735956LZ | Construction of Flood Mitigation Structure | 120.4345 | 16.6042 | 144750000 | 144749988.7 | 2023 | MG SAMIDAN CONSTRUCTION / KRYPTONITE 6S BUILDERS INC. | 917 | 2023 | 2023-12-13 | 02/14/2023 | 11.3 | 0 | 2023-12-12 |  | 1
2024 | Region I | LA UNION | TUBAO (LA UNION) | P00839552LZ | Construction of Flood Mitigation Structure | 120.4348 | 16.3633 | 19800000 | 19798959.79 | 2024 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | 918 | 2024 | 2024-08-02 | 06/24/2024 | 1040.21 | 0 | 2024-12-04 | 124
2024 | Region III | TARLAC | CAPAS (TARLAC) | P00821288LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.4365 | 15.3348 | 96499511.41 | 96497009.7 | 2024 | ROYAL CROWN MONARCH CONSTRUCTION & SUPPLIES CORP. | 919 | 2024 | 2024-11-19 | 02/20/2024 | 2501.71 | 0 | 2024-11-18 |  | 1
2022 | Region I | ILOCOS SUR | CITY OF CANDON (ILOCOS SUR) | P00639423LZ | Construction of Flood Mitigation Structure | 120.437 | 17.1873 | 4900000 | 4899852.87 | 2023 | FIRST NORTHWAY DEVELOPMENT & CONSTRUCTION CORP. | 920 | 2022 | 2023-01-30 | 04/04/2022 | 147.13 | 0 | 2022-06-04 |  | 240
2024 | Region I | PANGASINAN | BAYAMBANG (PANGASINAN) | P00821521LZ | Construction of Flood Mitigation Structure | 120.4376 | 15.7657 | 48250000 | 48249996.93 | 2024 | ALCEL CONSTRUCTION | 921 | 2024 | 2024-10-11 | 04/19/2024 | 3.07 | 0 | 2024-12-05 | 55
2024 | Region I | LA UNION | BAGULIN (LA UNION) | P00821100LZ | Construction of Flood Mitigation Structure | 120.4391 | 16.6096 | 96499998.02 | 96403190.33 | 2025 | ANORE CONSTRUCTION | 922 | 2024 | 2025-03-16 | 04/16/2024 | 96807.69 | 0 | 2025-01-14 |  | 61
2024 | Region I | LA UNION | NAGUILIAN (LA UNION) | P00823293LZ | Construction of Flood Mitigation Structure | 120.4397 | 16.5185 | 115800000 | 115799760.4 | 2024 | SILVERWOLVES CONSTRUCTION CORPORATION | 923 | 2024 | 2024-11-11 | 05/03/2024 | 239.6 | 0 | 2025-02-01 | 82
2022 | Region I | ILOCOS SUR | CITY OF CANDON (ILOCOS SUR) | P00621507LZ | Construction of Flood Mitigation Structure | 120.4398 | 17.1914 | 19600000 | 19599909.79 | 2023 | ARM-ASIA CONSTRUCTION & ENGINEERING | 924 | 2022 | 2023-01-30 | 04/04/2022 | 90.21 | 0 | 2022-08-01 |  | 182
2024 | Region I | LA UNION | BURGOS (LA UNION) | P00820131LZ | Construction of Flood Mitigation Structure | 120.4399 | 16.5233 | 99680640 | 99646322.92 | 2025 | LATAWAN EDUARDO AP-O DEVELOPERS CONSTRUCTION SERVICES / E.T. LATAWAN CONSTRUCTION | 925 | 2024 | 2025-02-09 | 05/03/2024 | 34317.08 | 0 | 2025-02-08 |  | 1
2024 | Region I | PANGASINAN | BAYAMBANG (PANGASINAN) | P00839563LZ | Construction of Flood Mitigation Structure | 120.44 | 15.765 | 8910000 | 8688171.63 | 2024 | JEUSMACK BUILDERS & CONSTRUCTION SUPPLY | 926 | 2024 | 2024-04-17 | 02/06/2024 | 221828.37 | 0 | 2024-05-25 | 38
2023 | Region I | LA UNION | TUBAO (LA UNION) | P00726333LZ | Construction of Flood Mitigation Structure | 120.4403 | 16.3573 | 144750000 | 144719366.2 | 2023 | RODEKOM GENERAL CONSTRUCTION AND ENTERPRISE | 927 | 2023 | 2023-11-13 | 02/14/2023 | 30633.8 | 0 | 2024-01-12 | 60
2023 | Region I | ILOCOS SUR | CITY OF CANDON (ILOCOS SUR) | P00727072LZ | Construction of Drainage Structure | 120.4403 | 17.1642 | 19600000 | 19011839.42 | 2024 | FIRST NORTHWAY DEVELOPMENT & CONSTRUCTION CORP. | 928 | 2023 | 2024-10-02 | 04/20/2023 | 588160.58 | 0 | 2023-08-16 |  | 413
2024 | Region I | ILOCOS SUR | SANTA (ILOCOS SUR) | P00844713LZ | Construction of Revetment | 120.4407 | 17.5433 | 9800000 | 9765365.65 | 2024 | M.V. SABALBURO CONSTRUCTION AND SUPPLY | 929 | 2024 | 2024-07-27 | 05/07/2024 | 34634.35 | 0 | 2024-07-26 |  | 1
2024 | Region I | ILOCOS SUR | SANTA (ILOCOS SUR) | P00845899LZ | Construction of Revetment | 120.4408 | 17.5416 | 9900000 | 9899970.35 | 2024 | M.V. SABALBURO CONSTRUCTION AND SUPPLY | 930 | 2024 | 2024-07-02 | 04/12/2024 | 29.65 | 0 | 2024-07-01 |  | 1
2023 | Region I | LA UNION | TUBAO (LA UNION) | P00726334LZ | Construction of Flood Mitigation Structure | 120.4413 | 16.3585 | 144750000 | 144744232.5 | 2023 | RODEKOM GENERAL CONSTRUCTION AND ENTERPRISE | 931 | 2023 | 2023-11-13 | 02/14/2023 | 5767.5 | 0 | 2024-01-12 | 60
2023 | Region I | ILOCOS SUR | CITY OF CANDON (ILOCOS SUR) | P00727071LZ | Construction of Drainage Structure | 120.4415 | 17.1707 | 14700000 | 14258798.76 | 2024 | FIRST NORTHWAY DEVELOPMENT & CONSTRUCTION CORP. | 932 | 2023 | 2024-10-29 | 04/20/2023 | 441201.24 | 0 | 2023-08-16 |  | 440
2023 | Region III | TARLAC | CAPAS (TARLAC) | P00726528LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.4422 | 15.3467 | 66102097.11 | 66102126.33 | 2023 | STO. CRISTO CONSTRUCTION & TRADING INC. (FOR: STO. CRISTO CONSTRUCTION & TRADING) | 933 | 2023 | 2023-12-22 | 02/07/2023 | 0 | 29.22 | 2023-11-03 |  | 49
2022 | Region I | ILOCOS SUR | CITY OF CANDON (ILOCOS SUR) | P00621506LZ | Construction of Flood Mitigation Structure | 120.4422 | 17.1842 | 39200000 | 38024474.57 | 2023 | FIRST NORTHWAY DEVELOPMENT & CONSTRUCTION CORP. | 934 | 2022 | 2023-03-28 | 04/04/2022 | 1175525.43 | 0 | 2022-08-18 |  | 222
2023 | Region I | ILOCOS SUR | CITY OF CANDON (ILOCOS SUR) | P00742264LZ | Construction of Flood Mitigation Structure | 120.4424 | 17.1705 | 29700000 | 28808249.06 | 2024 | FIRST NORTHWAY DEVELOPMENT & CONSTRUCTION CORP. | 935 | 2023 | 2024-10-28 | 04/20/2023 | 891750.94 | 0 | 2023-11-14 |  | 349
2024 | Region I | LA UNION | BURGOS (LA UNION) | P00821102LZ | Construction of Flood Mitigation Structure | 120.4425 | 16.5155 | 96499981.95 | 96489333.05 | 2025 | ANORE CONSTRUCTION | 936 | 2024 | 2025-03-16 | 04/16/2024 | 10648.9 | 0 | 2025-01-14 |  | 61
2023 | Region I | ILOCOS SUR | TAGUDIN (ILOCOS SUR) | P00742266LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.4429 | 16.969 | 29700000 | 29698974.86 | 2023 | POWER K CONSTRUCTION SUPPLY & SERVICES | 937 | 2023 | 2023-11-15 | 06/30/2023 | 1025.14 | 0 | 2023-12-24 | 39
2023 | Region I | LA UNION | SANTOL (LA UNION) | P00737414LZ | Construction of Slope Protection Structure | 120.4435 | 16.8123 | 14849999.31 | 14690943.27 | 2023 | ARM-ASIA CONSTRUCTION & ENGINEERING | 938 | 2023 | 2023-09-22 | 02/13/2023 | 159056.04 | 0 | 2023-08-21 |  | 32
2023 | Region I | ILOCOS SUR | CITY OF CANDON (ILOCOS SUR) | P00727069LZ | Construction of Drainage Structure | 120.4437 | 17.1973 | 14700000 | 14258915.11 | 2024 | FIRST NORTHWAY DEVELOPMENT & CONSTRUCTION CORP. | 939 | 2023 | 2024-07-30 | 04/20/2023 | 441084.89 | 0 | 2023-10-10 |  | 294
2023 | Region I | PANGASINAN | MALASIQUI (PANGASINAN) | P00737426LZ | Construction of Flood Mitigation Structure | 120.4438 | 15.9207 | 9900000 | 9610931.99 | 2023 | HIGH ROCK CONSTRUCTION AND SUPPLIES INCORPORATED | 940 | 2023 | 2023-07-25 | 06/02/2023 | 289068.01 | 0 | 2023-09-04 | 41
2022 | Region I | ILOCOS SUR | CITY OF CANDON (ILOCOS SUR) | P00639425LZ | Construction of Flood Mitigation Structure | 120.444 | 17.2122 | 9800000 | 9505911.18 | 2023 | FIRST NORTHWAY DEVELOPMENT & CONSTRUCTION CORP. | 941 | 2022 | 2023-02-01 | 04/04/2022 | 294088.82 | 0 | 2022-06-23 |  | 223
2024 | Region I | PANGASINAN | SANTA BARBARA (PANGASINAN) | P00821511LZ | Construction of Flood Mitigation Structure | 120.444 | 16.0037 | 48250000 | 48075596.98 | 2024 | SYNDTITE CONSTRUCTION CORPORATION (FORMERLY: R.C. TAGALA CONSTRUCTION) | 942 | 2024 | 2024-09-19 | 04/19/2024 | 174403.02 | 0 | 2024-11-13 | 55
2023 | Region I | ILOCOS SUR | CITY OF CANDON (ILOCOS SUR) | P00727070LZ | Construction of Drainage Structure | 120.4441 | 17.1746 | 14700000 | 14258847.48 | 2024 | FIRST NORTHWAY DEVELOPMENT & CONSTRUCTION CORP. | 943 | 2023 | 2024-08-27 | 04/20/2023 | 441152.52 | 0 | 2023-09-10 |  | 352
2024 | Region I | ILOCOS SUR | SANTA (ILOCOS SUR) | P00824653LZ | Construction of Revetment | 120.4443 | 17.5272 | 4900000 | 4899693.22 | 2025 | M.V. SABALBURO CONSTRUCTION AND SUPPLY | 944 | 2024 | 2025-01-29 | 03/27/2024 | 306.78 | 0 | 2024-05-27 |  | 247
2024 | Region I | LA UNION | BURGOS (LA UNION) | P00825210LZ | Construction of Flood Mitigation Structure | 120.4448 | 16.5291 | 48999997.22 | 48264987.53 | 2024 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | 945 | 2024 | 2024-09-16 | 02/06/2024 | 735009.69 | 0 | 2024-08-10 |  | 37
2021 | Region I | ILOCOS SUR |  | P00525863LZ | Construction of Flood Mitigation Structure | 120.445 | 17.7229 | 29400000 | 29400000 | 2022 | R.B. PANO CONSTRUCTION CORP. (FORMERLY: R.B. PANO CONSTRUCTION AND SUPPLY) | 946 | 2021 | 2022-12-19 | 06/02/2022 | 0 | 0 | 2022-12-28 | 9
2022 | Region I | ILOCOS SUR | CITY OF CANDON (ILOCOS SUR) | P00639418LZ | Construction of Flood Mitigation Structure | 120.445 | 17.1728 | 9800000 | 9506344.81 | 2023 | FIRST NORTHWAY DEVELOPMENT & CONSTRUCTION CORP. | 947 | 2022 | 2023-02-15 | 04/04/2022 | 293655.19 | 0 | 2022-06-18 |  | 242
2023 | Region I | ILOCOS NORTE | CURRIMAO (ILOCOS NORTE) | P00727060LZ | Rehabilitation / Major Repair of Slope Protection Structure | 120.445 | 16.0937 | 19300000 | 19299781.31 | 2024 | CURRIMAO CONSTRUCTION & DEVELOPMENT, INC. | 948 | 2023 | 2024-02-11 | 06/30/2023 | 218.69 | 0 | 2024-02-10 |  | 1
2024 | Region I | PANGASINAN | SAN JACINTO (PANGASINAN) | P00820130LZ | Construction of Flood Mitigation Structure | 120.4451 | 16.0448 | 96500000 | 96499268.66 | 2024 | BET CONSTRUCTION & SUPPLY | 949 | 2024 | 2024-07-12 | 02/26/2024 | 731.34 | 0 | 2024-12-14 | 155
2023 | Region III | BATAAN | HERMOSA (BATAAN) | P00726147LZ | Construction of Flood Mitigation Structure | 120.4455 | 14.8549 | 29399999.37 | 29399999.37 | 2023 | PASCAL CONSTRUCTION | 950 | 2023 | 2023-06-16 | 02/16/2023 | 0 | 0 | 2023-07-23 | 37
2024 | Region I | PANGASINAN | MALASIQUI (PANGASINAN) | P00845918LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.446 | 15.892 | 54450000 | 9899990.31 | 2024 | MIGHTYWAY CONSTRUCTION AND SUPPLY | 951 | 2024 | 2024-09-11 | 06/03/2024 | 44550009.69 | 0 | 2024-11-18 | 68
2023 | Region I | ILOCOS SUR | CITY OF CANDON (ILOCOS SUR) | P00727073LZ | Construction of Flood Mitigation Structure | 120.4462 | 17.1851 | 25480000 | 13438847.87 | 2024 | M.V. SABALBURO CONSTRUCTION AND SUPPLY | 952 | 2023 | 2024-07-30 | 04/20/2023 | 12041152.13 | 0 | 2023-10-24 |  | 280
2021 | Region I | ILOCOS SUR |  | P00525861LZ | Construction of Revetment | 120.4462 | 17.8004 | 49000000 | 49000000 | 2022 | NORTH TECH BUILDERS AND CONSTRUCTION SUPPLY | 953 | 2021 | 2022-10-18 | 02/24/2022 | 0 | 0 | 2022-10-17 |  | 1
2022 | Region I | ILOCOS SUR | CITY OF CANDON (ILOCOS SUR) | P00621252LZ | Construction of Flood Mitigation Structure | 120.4464 | 17.2206 | 56840000 | 55969996.9 | 2023 | FIRST NORTHWAY DEVELOPMENT & CONSTRUCTION CORP. | 954 | 2022 | 2023-07-03 | 04/04/2022 | 870003.1 | 0 | 2022-11-24 |  | 221
2024 | Region III | TARLAC | CAPAS (TARLAC) | P00821302LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.4467 | 15.3691 | 96499565.7 | 96497506.83 | 2024 | E.L. ANOLIN CONSTRUCTION | 955 | 2024 | 2024-08-21 | 02/20/2024 | 2058.87 | 0 | 2024-08-20 |  | 1
2024 | Region I | ILOCOS SUR | CITY OF CANDON (ILOCOS SUR) | P00824652LZ | Construction of Revetment | 120.4469 | 17.2252 | 29400000 | 29399836.91 | 2024 | NORTH TECH BUILDERS AND CONSTRUCTION SUPPLY | 956 | 2024 | 2024-10-22 | 04/12/2024 | 163.09 | 0 | 2024-11-17 | 26
2024 | Region I | LA UNION | TUBAO (LA UNION) | P00821095LZ | Construction of Flood Mitigation Structure | 120.4475 | 16.3497 | 144750000 | 144749869.1 | 2024 | RODEKOM GENERAL CONSTRUCTION AND ENTERPRISE | 957 | 2024 | 2024-07-26 | 03/15/2024 | 130.9 | 0 | 2025-01-10 | 168
2024 | Region IV-B | OCCIDENTAL MINDORO | PALUAN (OCCIDENTAL MINDORO) | P00823578LZ | Construction of Flood Mitigation Structure | 120.4479 | 13.4234 | 241250000 | 241244808.2 | 2024 | D.T. RECIO INCORPORATED | 958 | 2024 | 2024-11-25 | 03/02/2024 | 5191.8 | 0 | 2025-02-23 | 90
2023 | Region I | PANGASINAN | SAN FABIAN (PANGASINAN) | P00725621LZ | Construction of Flood Mitigation Structure | 120.4481 | 16.0972 | 91675000 | 91672667.03 | 2023 | BET CONSTRUCTION & SUPPLY | 959 | 2023 | 2023-12-14 | 05/08/2023 | 2332.97 | 0 | 2024-01-25 | 42
2024 | Region I | PANGASINAN | MAPANDAN (PANGASINAN) | P00820100LZ | Construction of Flood Mitigation Structure | 120.4481 | 16.0393 | 120625000 | 120623086.5 | 2024 | BET CONSTRUCTION & SUPPLY / JEUSMACK BUILDERS & CONSTRUCTION SUPPLY | 960 | 2024 | 2024-10-11 | 02/26/2024 | 1913.5 | 0 | 2024-12-20 | 70
2022 | Region III | BATAAN | DINALUPIHAN (BATAAN) | P00621495LZ | Construction of Flood Mitigation Structure | 120.4484 | 14.9029 | 48019996.83 | 48019991.19 | 2022 | ROCKSTEEL CONSTRUCTION AND DEV'T CORPORATION / EGB CONSTRUCTION CORPORATION (FORMERLY: EGB CONSTRUCTION) | 961 | 2022 | 2022-12-14 | 07/21/2022 | 5.64 | 0 | 2023-01-31 | 48
2024 | Region I | LA UNION | TUBAO (LA UNION) | P00845901LZ | Construction of Flood Mitigation Structure | 120.4484 | 16.3489 | 19799995.18 | 19794859.75 | 2025 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | 962 | 2024 | 2025-02-16 | 02/27/2024 | 5135.43 | 0 | 2024-08-04 |  | 196
2022 | Region III | TARLAC | CAPAS (TARLAC) | P00640531LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.4484 | 15.36 | 48999892.46 | 48779814.7 | 2022 | HIGH STRENGTH DEV. CORPORATION | 963 | 2022 | 2022-10-11 | 03/24/2022 | 220077.76 | 0 | 2022-10-10 |  | 1
2024 | Region I | PANGASINAN | BAYAMBANG (PANGASINAN) | P00825217LZ | Construction of Flood Mitigation Structure | 120.449 | 15.758 | 39200000 | 19066880.39 | 2024 | HIGH ROCK CONSTRUCTION AND SUPPLIES INCORPORATED / JHI CONSTRUCTION & SUPPLY | 964 | 2024 | 2024-08-05 | 05/06/2024 | 20133119.61 | 0 | 2024-10-14 | 70
2022 | Region I | ILOCOS SUR | CITY OF CANDON (ILOCOS SUR) | P00639422LZ | Construction of Flood Mitigation Structure | 120.4493 | 17.1978 | 4900000 | 4898072.66 | 2022 | FIRST NORTHWAY DEVELOPMENT & CONSTRUCTION CORP. | 965 | 2022 | 2022-07-13 | 04/04/2022 | 1927.34 | 0 | 2022-05-31 |  | 43
2022 | Region I | ILOCOS SUR | CITY OF CANDON (ILOCOS SUR) | P00639419LZ | Construction of Flood Mitigation Structure | 120.4494 | 17.1889 | 9800000 | 9799414.09 | 2023 | FIRST NORTHWAY DEVELOPMENT & CONSTRUCTION CORP. | 966 | 2022 | 2023-01-30 | 04/04/2022 | 585.91 | 0 | 2022-06-24 |  | 220
2023 | Region III | TARLAC | CAPAS (TARLAC) | P00726908LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.4495 | 15.3716 | 72374439.79 | 72336770.79 | 2023 | 11-16 CONSTRUCTION / BOLTRON BUILDERS CORPORATION | 967 | 2023 | 2023-12-09 | 04/10/2023 | 37669 | 0 | 2023-12-08 |  | 1
2022 | Region I | PANGASINAN | SAN FABIAN (PANGASINAN) | P00620128LZ | Construction of Flood Mitigation Structure | 120.4497 | 16.0989 | 50192545 | 50192545 | 2023 | BET CONSTRUCTION & SUPPLY | 968 | 2022 | 2023-03-25 | 02/24/2022 | 0 | 0 | 2023-03-24 |  | 1
2022 | Region I | ILOCOS SUR | CITY OF CANDON (ILOCOS SUR) | P00639424LZ | Construction of Flood Mitigation Structure | 120.45 | 17.1947 | 4900000 | 4897303.83 | 2022 | FIRST NORTHWAY DEVELOPMENT & CONSTRUCTION CORP. | 969 | 2022 | 2022-09-19 | 04/04/2022 | 2696.17 | 0 | 2022-06-21 |  | 90
2022 | Region I | ILOCOS SUR | TAGUDIN (ILOCOS SUR) | P00621551LZ | Construction of Flood Mitigation Structure | 120.4501 | 16.9174 | 241250000 | 241248185.8 | 2023 | A.P.B. CONSTRUCTION / EGB CONSTRUCTION CORPORATION (FORMERLY: EGB CONSTRUCTION) | 970 | 2022 | 2023-02-28 | 04/07/2022 | 1814.2 | 0 | 2023-02-27 |  | 1
2024 | Region I | LA UNION | TUBAO (LA UNION) | P00821471LZ | Construction of Flood Mitigation Structure | 120.4501 | 16.3161 | 48999998.13 | 48989608.07 | 2024 | RODEKOM GENERAL CONSTRUCTION AND ENTERPRISE | 971 | 2024 | 2024-07-29 | 02/06/2024 | 10390.06 | 0 | 2024-08-19 | 21
2024 | Region IV-B | OCCIDENTAL MINDORO | PALUAN (OCCIDENTAL MINDORO) | P00823575LZ | Construction of Flood Mitigation Structure | 120.4508 | 13.4221 | 289500000 | 289494221.9 | 2024 | D.T. RECIO INCORPORATED | 972 | 2024 | 2024-11-25 | 03/02/2024 | 5778.1 | 0 | 2025-02-23 | 90
2023 | Region IV-B | OCCIDENTAL MINDORO | PALUAN (OCCIDENTAL MINDORO) | P00740654LZ | Construction of Flood Mitigation Structure | 120.451 | 13.4375 | 29400000 | 28695558.08 | 2023 | WAY MAKER GENERAL CONTRACTOR OPC | 973 | 2023 | 2023-12-15 | 05/30/2023 | 704441.92 | 0 | 2024-01-19 | 35
2023 | Region I | ILOCOS SUR | CITY OF CANDON (ILOCOS SUR) | P00742265LZ | Construction of Flood Mitigation Structure | 120.4514 | 17.1899 | 24750000 | 23995298.2 | 2024 | ARM-ASIA CONSTRUCTION & ENGINEERING | 974 | 2023 | 2024-01-22 | 05/11/2023 | 754701.8 | 0 | 2023-11-05 |  | 78
2024 | Region I | ILOCOS SUR | SANTA CRUZ (ILOCOS SUR) | P00838502LZ | Construction of Flood Mitigation Structure | 120.4519 | 17.0869 | 29915000 | 29853362.81 | 2024 | NORTH TECH BUILDERS AND CONSTRUCTION SUPPLY | 975 | 2024 | 2024-10-24 | 04/08/2024 | 61637.19 | 0 | 2024-10-23 |  | 1
2023 | Region I | ILOCOS SUR | CITY OF CANDON (ILOCOS SUR) | P00727084LZ | Construction of Flood Mitigation Structure | 120.4527 | 17.1798 | 49000000 | 47529939.93 | 2024 | FIRST NORTHWAY DEVELOPMENT & CONSTRUCTION CORP. | 976 | 2023 | 2024-10-29 | 06/08/2023 | 1470060.07 | 0 | 2023-12-26 |  | 308
2023 | Region I | PANGASINAN | MALASIQUI (PANGASINAN) | P00726080LZ | Construction of Flood Mitigation Structure | 120.4529 | 15.9208 | 19600000 | 19370790.58 | 2023 | MIGHTYWAY CONSTRUCTION AND SUPPLY | 977 | 2023 | 2023-07-17 | 02/13/2023 | 229209.42 | 0 | 2023-07-24 | 7
2023 | Region I | PANGASINAN | MAPANDAN (PANGASINAN) | P00726066LZ | Construction of Flood Mitigation Structure | 120.4529 | 16.0338 | 49000000 | 47574067.96 | 2023 | J.G. GARCIA CONSTRUCTION & SUPPLY (FOR: J.G. GARCIA CONST.) | 978 | 2023 | 2023-11-17 | 05/12/2023 | 1425932.04 | 0 | 2023-11-26 | 9
2024 | Region I | PANGASINAN | BAYAMBANG (PANGASINAN) | P00821516LZ | Construction of Flood Mitigation Structure | 120.453 | 15.76 | 49000000 | 48999993.3 | 2024 | MIGHTYWAY CONSTRUCTION AND SUPPLY | 979 | 2024 | 2024-06-14 | 02/23/2024 | 6.7 | 0 | 2024-09-08 | 86
2024 | Region I | ILOCOS SUR | SINAIT (ILOCOS SUR) | P00820708LZ | Construction of Flood Mitigation Structure | 120.4531 | 17.8674 | 33810000 | 33436397.22 | 2024 | 739 BUILDERS | 980 | 2024 | 2024-07-12 | 02/14/2024 | 373602.78 | 0 | 2024-07-13 | 1
2022 | Region III | TARLAC | CAPAS (TARLAC) | P00620547LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.4533 | 15.3689 | 48999323.9 | 48998948.62 | 2022 | RAIK CONSTRUCTION AND DEVELOPMENT CORPORATION (FORMERLY: RAIK CONSTRUCTION AND SUPPLY) | 981 | 2022 | 2022-08-23 | 01/29/2022 | 375.28 | 0 | 2022-08-22 |  | 1
2022 | Region I | PANGASINAN | SAN FABIAN (PANGASINAN) | P00620127LZ | Construction of Flood Mitigation Structure | 120.4535 | 16.098 | 101325000 | 101325000 | 2023 | BET CONSTRUCTION & SUPPLY | 982 | 2022 | 2023-03-24 | 02/24/2022 | 0 | 0 | 2023-04-26 | 33
2022 | Region I | ILOCOS SUR | SANTIAGO (ILOCOS SUR) | P00640497LZ | Construction of Flood Mitigation Structure | 120.4537 | 17.2338 | 19800000 | 19799604.18 | 2023 | EJIEV CONSTRUCTION SERVICES | 983 | 2022 | 2023-04-17 | 04/04/2022 | 395.82 | 0 | 2022-08-01 |  | 259
2024 | Region I | LA UNION | TUBAO (LA UNION) | P00845903LZ | Construction of Flood Mitigation Structure | 120.4538 | 16.3361 | 29699999.35 | 29693483.68 | 2025 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | 984 | 2024 | 2025-03-16 | 02/27/2024 | 6515.67 | 0 | 2024-08-18 |  | 210
2021 | Region I | ILOCOS SUR |  | P00525877LZ | Construction of Drainage Structure | 120.4539 | 17.1948 | 34300000 | 34299202.57 | 2022 | E.E. MADAYAG CONSTRUCTION | 985 | 2021 | 2022-08-30 | 10/19/2021 | 797.43 | 0 | 2022-09-12 | 13
2022 | Region I | ILOCOS SUR | CITY OF CANDON (ILOCOS SUR) | P00621505LZ | Construction of Flood Mitigation Structure | 120.4542 | 17.1808 | 49000000 | 47529460.53 | 2023 | FIRST NORTHWAY DEVELOPMENT & CONSTRUCTION CORP. | 986 | 2022 | 2023-11-03 | 04/04/2022 | 1470539.47 | 0 | 2022-08-27 |  | 433
2022 | Region I | ILOCOS SUR | CITY OF CANDON (ILOCOS SUR) | P00639426LZ | Construction of Flood Mitigation Structure | 120.4542 | 17.1808 | 9800000 | 9505903.16 | 2023 | FIRST NORTHWAY DEVELOPMENT & CONSTRUCTION CORP. | 987 | 2022 | 2023-01-31 | 04/04/2022 | 294096.84 | 0 | 2022-06-23 |  | 222
2023 | Region I | PANGASINAN | BAYAMBANG (PANGASINAN) | P00727340LZ | Construction of Flood Mitigation Structure | 120.4542 | 15.7606 | 49000000 | 9491249.25 | 2023 | BET CONSTRUCTION & SUPPLY / JEUSMACK BUILDERS & CONSTRUCTION SUPPLY | 988 | 2023 | 2023-12-18 | 06/21/2023 | 39508750.75 | 0 | 2024-02-17 | 61
2023 | Region III | TARLAC | CAPAS (TARLAC) | P00727148LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.4543 | 15.3692 | 47235498.37 | 47188039.2 | 2023 | RAIK CONSTRUCTION AND DEVELOPMENT CORPORATION (FORMERLY: RAIK CONSTRUCTION AND SUPPLY) | 989 | 2023 | 2023-10-26 | 02/28/2023 | 47459.17 | 0 | 2023-10-25 |  | 1
2022 | Region III | BATAAN | DINALUPIHAN (BATAAN) | P00620502LZ | Construction of Flood Mitigation Structure | 120.4547 | 14.9014 | 24499999.95 | 24499999.95 | 2022 | ORANI CONSTRUCTION AND SUPPLY CORPORATION (FORMERLY:ORANI BUILDERS & SUPPLY) | 990 | 2022 | 2022-07-16 | 02/14/2022 | 0 | 0 | 2022-07-16 | 0
2023 | Region III | TARLAC | CAPAS (TARLAC) | P00726909LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.455 | 15.3743 | 72374866.25 | 72344902.59 | 2023 | 11-16 CONSTRUCTION | 991 | 2023 | 2023-12-17 | 04/18/2023 | 29963.66 | 0 | 2023-12-16 |  | 1
2024 | Region I | ILOCOS SUR | SINAIT (ILOCOS SUR) | P00820102LZ | Construction of Flood Mitigation Structure | 120.4554 | 17.8384 | 36959500 | 36959500 | 2024 | A.P.B. CONSTRUCTION | 992 | 2024 | 2024-10-25 | 02/23/2024 | 0 | 0 | 2024-10-24 |  | 1
2022 | Region I | ILOCOS SUR | MAGSINGAL (ILOCOS SUR) | P00620935LZ | Construction of Flood Mitigation Structure | 120.456 | 17.723 | 45080000 | 45080000 | 2022 | A.P.B. CONSTRUCTION | 993 | 2022 | 2022-12-17 | 04/08/2022 | 0 | 0 | 2022-12-16 |  | 1
2022 | Region I | PANGASINAN | SAN FABIAN (PANGASINAN) | P00620126LZ | Construction of Flood Mitigation Structure | 120.4563 | 16.1096 | 101325000 | 101325000 | 2023 | BET CONSTRUCTION & SUPPLY | 994 | 2022 | 2023-01-31 | 02/24/2022 | 0 | 0 | 2023-04-26 | 85
2022 | Region I | ILOCOS SUR | CITY OF CANDON (ILOCOS SUR) | P00641866LZ | Construction of Flood Mitigation Structure | 120.4565 | 17.2234 | 9800000 | 9506079.06 | 2023 | M.V. SABALBURO CONSTRUCTION AND SUPPLY | 995 | 2022 | 2023-02-01 | 04/04/2022 | 293920.94 | 0 | 2022-06-17 |  | 229
2022 | Region I | ILOCOS SUR | SINAIT (ILOCOS SUR) | P00620936LZ | Construction of Flood Mitigation Structure | 120.4567 | 17.8377 | 45239740 | 45239740 | 2023 | A.P.B. CONSTRUCTION / R.B. PANO CONSTRUCTION CORP. (FORMERLY: R.B. PANO CONSTRUCTION AND SUPPLY) | 996 | 2022 | 2023-01-06 | 03/25/2022 | 0 | 0 | 2023-01-05 |  | 1
2023 | Region I | PANGASINAN | BAYAMBANG (PANGASINAN) | P00727338LZ | Construction of Flood Mitigation Structure | 120.4572 | 15.7731 | 49000000 | 9491560.96 | 2023 | BET CONSTRUCTION & SUPPLY / JEUSMACK BUILDERS & CONSTRUCTION SUPPLY | 997 | 2023 | 2023-12-18 | 06/21/2023 | 39508439.04 | 0 | 2024-02-17 | 61
2022 | Region I | ILOCOS SUR | SANTA CRUZ (ILOCOS SUR) | P00621515LZ | Construction of Flood Mitigation Structure | 120.4572 | 17.094 | 19600000 | 19599991.64 | 2022 | PRECIOUS CONSTRUCTION | 998 | 2022 | 2022-09-06 | 04/04/2022 | 8.36 | 0 | 2022-10-02 | 26
2023 | Region I | PANGASINAN | MAPANDAN (PANGASINAN) | P00737430LZ | Construction of Flood Mitigation Structure | 120.4575 | 16.0297 | 4950000 | 4803991.53 | 2023 | JEUSMACK BUILDERS & CONSTRUCTION SUPPLY | 999 | 2023 | 2023-06-23 | 05/12/2023 | 146008.47 | 0 | 2023-07-23 | 30
2023 | Region I | PANGASINAN | MALASIQUI (PANGASINAN) | P00726081LZ | Construction of Flood Mitigation Structure | 120.4576 | 15.9166 | 19600000 | 19599995.26 | 2023 | LXS BUILDERS & SUPPLIES | 1000 | 2023 | 2023-04-11 | 02/22/2023 | 4.74 | 0 | 2023-08-02 | 113
2024 | Region III | PAMPANGA | MAGALANG (PAMPANGA) | P00838533LZ | Construction of Slope Protection Structure | 120.6697 | 15.2281 | 48983545.27 | 48975497.41 | 2024 | D.R. ROBLES CONSTRUCTION | 1001 | 2024 | 2024-07-07 | 02/08/2024 | 8047.86 | 0 | 2024-07-22 | 15
2022 | Cordillera Administrative Region | ABRA | LA PAZ (ABRA) | P00637008LZ | Construction of Flood Mitigation Structure | 120.6698 | 17.6594 | 96499903.01 | 96497818.75 | 2023 | ST. TIMOTHY CONSTRUCTION CORPORATION | 1002 | 2022 | 2023-01-31 | 05/18/2022 | 2084.26 | 0 | 2023-02-18 | 18
2022 | Region III | BATAAN | CITY OF BALANGA (CAPITAL) (BATAAN) | P00620511LZ | Construction of Flood Mitigation Structure | 120.5306 | 14.6396 | 49000000 | 49000000 | 2022 | E.R. VENZON CONSTRUCTION / VF CONSTRUCTION | 1003 | 2022 | 2022-11-25 | 04/08/2022 | 0 | 0 | 2022-11-24 |  | 1
2022 | Region III | TARLAC | CONCEPCION (TARLAC) | P00621540LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.6704 | 15.3244 | 40179626.14 | 40068405.31 | 2022 | HIGH STRENGTH DEV. CORPORATION / T2B3 BUILDERS AND SUPPLIES CORP. | 1004 | 2022 | 2022-10-16 | 03/24/2022 | 111220.83 | 0 | 2022-10-15 |  | 1
2022 | Region III | PAMPANGA | BACOLOR (PAMPANGA) | P00631240LZ | Construction of Slope Protection Structure | 120.6707 | 14.9934 | 49000000 | 46549626.36 | 2022 | EDDMARI CONSTRUCTION & TRADING | 1005 | 2022 | 2022-08-28 | 02/24/2022 | 2450373.64 | 0 | 2022-08-21 |  | 7
2023 | Region III | TARLAC | CONCEPCION (TARLAC) | P00726905LZ | Construction of Groundsill | 120.6708 | 15.3035 | 72374965.2 | 72362396.98 | 2023 | RAIK CONSTRUCTION AND DEVELOPMENT CORPORATION (FORMERLY: RAIK CONSTRUCTION AND SUPPLY) | 1006 | 2023 | 2023-10-16 | 03/17/2023 | 12568.22 | 0 | 2023-10-15 |  | 1
2024 | Region I | ILOCOS SUR | QUIRINO (ANGKAKI) (ILOCOS SUR) | P00838500LZ | Construction of Flood Mitigation Structure | 120.671 | 17.1633 | 4825000 | 4810540.4 | 2024 | FIRST NORTHWAY DEVELOPMENT & CONSTRUCTION CORP. | 1007 | 2024 | 2024-10-08 | 07/02/2024 | 14459.6 | 0 | 2024-09-01 |  | 37
2024 | Region III | TARLAC | CAPAS (TARLAC) | P00821289LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.5306 | 15.4059 | 96499799.46 | 96482027.45 | 2024 | FLORDES CONSTRUCTION & TRADING CORP. (FORMERLY FLO | 1008 | 2024 | 2024-11-19 | 02/20/2024 | 17772.01 | 0 | 2024-11-18 |  | 1
2023 | Region III | PAMPANGA | ANGELES CITY (PAMPANGA) | P00740637LZ | Construction of Drainage Structure | 120.5793 | 15.1363 | 4899594.85 | 4893962.58 | 2023 | RD5 CONSTRUCTION | 1009 | 2023 | 2023-06-10 | 04/12/2023 | 5632.27 | 0 | 2023-06-09 |  | 1
2022 | Region I | ILOCOS NORTE | BANNA (ESPIRITU) (ILOCOS NORTE) | P00620125LZ | Construction of Flood Mitigation Structure | 120.6713 | 17.9356 | 48250000 | 48249980.91 | 2022 | BADOC BUILDERS & SUPPLY, INC. (FORMERLY: BADOC BUILDER & SUPPLY | 1010 | 2022 | 2022-10-19 | 03/25/2022 | 19.09 | 0 | 2022-10-18 |  | 1
2024 | Region I | PANGASINAN | POZORRUBIO (PANGASINAN) | P00843184LZ | Construction of Revetment | 120.5794 | 16.0896 | 86850000 | 86631574.25 | 2024 | R.G.TABIN CONSTRUCTION AND SUPPLY / AMP 723 CONSTRUCTION CORPORATION (FORMERLY: A.M.P. CONSTRUCTION) | 1011 | 2024 | 2024-07-25 | 06/07/2024 | 218425.75 | 0 | 2025-02-28 | 218
2023 | Region III | BATAAN | ABUCAY (BATAAN) | P00737449LZ | Construction of Flood Mitigation Structure | 120.5307 | 14.7227 | 4949994.47 | 4949986.96 | 2023 | HEBREWS BUILDERS AND CONSTRUCTION CORP. | 1012 | 2023 | 2023-09-20 | 04/24/2023 | 7.51 | 0 | 2023-09-21 | 1
2024 | Region III | TARLAC | CONCEPCION (TARLAC) | P00838440LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.6721 | 15.3241 | 96499192.04 | 96497898.96 | 2024 | FLORDES CONSTRUCTION & TRADING CORP. (FORMERLY FLO | 1013 | 2024 | 2024-08-21 | 02/20/2024 | 1293.08 | 0 | 2024-08-20 |  | 1
2022 | Cordillera Administrative Region | ABRA | BANGUED (CAPITAL) (ABRA) | P00637056LZ | Construction of Flood Mitigation Structure | 120.5798 | 17.614 | 48999972.54 | 48810861.7 | 2023 | MG SAMIDAN CONSTRUCTION | 1014 | 2022 | 2023-05-04 | 12/28/2022 | 189110.84 | 0 | 2023-07-01 | 58
2023 | Region III | TARLAC | CITY OF TARLAC (CAPITAL) (TARLAC) | P00727288LZ | Construction of Slope Protection Structure | 120.5799 | 15.5063 | 96500000 | 95504333.97 | 2023 | R.R. RICAFORT CONSTRUCTION AND SUPPLIES | 1015 | 2023 | 2023-11-20 | 03/22/2023 | 995666.03 | 0 | 2023-11-19 |  | 1
2024 | Region I | PANGASINAN | POZORRUBIO (PANGASINAN) | P00843185LZ | Construction of Revetment | 120.5799 | 16.0926 | 86850000 | 86674471.29 | 2024 | W.J.P. CONSTRUCTION AND SUPPLY | 1016 | 2024 | 2024-07-25 | 06/07/2024 | 175528.71 | 0 | 2025-02-28 | 218
2024 | Region III | BATAAN | ORION (BATAAN) | P00820807LZ | Construction of Flood Mitigation Structure | 120.5804 | 14.6064 | 49000000 | 49000000 | 2024 | BPQ CONSTRUCTION AND TRADING / POLYMER-VIC CONSTRUCTION | 1017 | 2024 | 2024-09-03 | 02/21/2024 | 0 | 0 | 2024-09-02 |  | 1
2023 | Region I | PANGASINAN | CITY OF URDANETA (PANGASINAN) | P00726056LZ | Construction of Dike | 120.5811 | 16.0156 | 39200000 | 39120577.49 | 2023 | R.A. MATIAS CONSTRUCTION AND DEVELOPERS INC. (FORMERLY : R.A. MATIAS CONSTRUCTION AND DEVELOPERS) | 1018 | 2023 | 2023-04-19 | 02/10/2023 | 79422.51 | 0 | 2023-08-16 | 119
2024 | Region I | PANGASINAN | ROSALES (PANGASINAN) | P00821491LZ | Construction of Revetment | 120.5815 | 15.8843 | 48250000 | 48248674.94 | 2024 | W.J.P. CONSTRUCTION AND SUPPLY | 1019 | 2024 | 2024-07-15 | 05/03/2024 | 1325.06 | 0 | 2024-11-01 | 109
2022 | Region III | PAMPANGA | MABALACAT CITY (PAMPANGA) | P00632852LZ | Construction of Slope Protection Structure | 120.5817 | 15.1993 | 19795564.92 | 19790645.85 | 2022 | M.C.J. VALENZUELA CONSTRUCTION ENTERPRISES | 1020 | 2022 | 2022-08-17 | 03/24/2022 | 4919.07 | 0 | 2022-08-16 |  | 1
2022 | Region I | ILOCOS NORTE | CITY OF BATAC (ILOCOS NORTE) | P00620786LZ | Construction of Flood Mitigation Structure | 120.5819 | 17.9826 | 72375000 | 72374999.88 | 2022 | MEGAPOLITAN BUILDERS AND CONSTRUCTION SUPPLY | 1021 | 2022 | 2022-12-09 | 04/12/2022 | 0.12 | 0 | 2022-12-08 |  | 1
2023 | Region III | PAMPANGA | MABALACAT CITY (PAMPANGA) | P00740640LZ | Construction of Drainage Structure | 120.5819 | 15.2071 | 9796511.77 | 9742198.4 | 2023 | CMDV CONSTRUCTION | 1022 | 2023 | 2023-08-21 | 04/24/2023 | 54313.37 | 0 | 2023-08-20 |  | 1
2023 | Region III | PAMPANGA | MABALACAT CITY (PAMPANGA) | P00742362LZ | Rehabilitation / Major Repair of Drainage Structure | 120.5819 | 15.2071 | 4948755.38 | 4929893.59 | 2023 | GEOHEART CONSTRUCTION & TRADING | 1023 | 2023 | 2023-09-18 | 05/22/2023 | 18861.79 | 0 | 2023-09-17 |  | 1
2022 | Cordillera Administrative Region | BENGUET | LA TRINIDAD (CAPITAL) (BENGUET) | P00620474LZ | Construction of Flood Mitigation Structure | 120.5822 | 16.4581 | 24500000 | 24489189.7 | 2022 | D.G.O. CONSTRUCTION | 1024 | 2022 | 2022-08-11 | 01/31/2022 | 10810.3 | 0 | 2022-09-24 | 44
2022 | Region III | PAMPANGA | MABALACAT CITY (PAMPANGA) | P00639484LZ | Construction of Flood Mitigation Structure | 120.5826 | 15.2295 | 48995974.4 | 48990447.35 | 2022 | IM CONSTRUCTION CORPORATION | 1025 | 2022 | 2022-09-24 | 03/24/2022 | 5527.05 | 0 | 2022-09-23 |  | 1
2023 | Cordillera Administrative Region | ABRA | BANGUED (CAPITAL) (ABRA) | P00726391LZ | Construction of Flood Mitigation Structure | 120.5827 | 17.6163 | 96499906.45 | 96500000 | 2024 | MG SAMIDAN CONSTRUCTION | 1026 | 2023 | 2024-01-02 | 03/30/2023 | 0 | 93.55 | 2023-12-15 |  | 18
2024 | Region IV-B | OCCIDENTAL MINDORO | MAMBURAO (CAPITAL) (OCCIDENTAL MINDORO) | P00824741LZ | Construction of Flood Mitigation Structure | 120.5829 | 13.228 | 24500000 | 24404898.79 | 2024 | KGB ENGINEERING AND CONSTRUCTION | 1027 | 2024 | 2024-06-21 | 02/14/2024 | 95101.21 | 0 | 2024-08-02 | 42
2023 | Region I | ILOCOS NORTE | BACARRA (ILOCOS NORTE) | P00740564LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.583 | 18.2694 | 19599844.23 | 19599844.23 | 2024 | BJMJB CONSTRUCTION & SUPPLY | 1028 | 2023 | 2024-02-09 | 05/24/2023 | 0 | 0 | 2024-02-08 |  | 1
2023 | Region I | ILOCOS NORTE | BACARRA (ILOCOS NORTE) | P00740545LZ | Construction of Slope Protection Structure | 120.5832 | 18.2763 | 4899907.67 | 4899902.53 | 2023 | TMT CONSTRUCTION | 1029 | 2023 | 2023-07-20 | 05/05/2023 | 5.14 | 0 | 2023-07-19 |  | 1
2023 | Region I | ILOCOS NORTE | BACARRA (ILOCOS NORTE) | P00740544LZ | Construction of Slope Protection Structure | 120.5833 | 18.2704 | 4899540.56 | 4899445.26 | 2023 | TMT CONSTRUCTION | 1030 | 2023 | 2023-07-17 | 04/25/2023 | 95.3 | 0 | 2023-07-23 | 6
2023 | Region III | PAMPANGA | ANGELES CITY (PAMPANGA) | P00740638LZ | Construction of Drainage Structure | 120.5833 | 15.1507 | 4944109.09 | 4892224.65 | 2023 | RD5 CONSTRUCTION | 1031 | 2023 | 2023-05-22 | 03/24/2023 | 51884.44 | 0 | 2023-05-21 |  | 1
2023 | Region III | TARLAC | CAPAS (TARLAC) | P00726192LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.5834 | 15.3278 | 47529668.4 | 46341067.43 | 2023 | T2B3 BUILDERS AND SUPPLIES CORP. | 1032 | 2023 | 2023-06-26 | 01/31/2023 | 1188600.97 | 0 | 2023-06-25 |  | 1
2024 | Region I | ILOCOS NORTE | BACARRA (ILOCOS NORTE) | P00820675LZ | Construction of Flood Mitigation Structure | 120.5835 | 18.2558 | 29399932.06 | 29399925.82 | 2024 | ZEDIK BUILDERS | 1033 | 2024 | 2024-04-16 | 02/29/2024 | 6.24 | 0 | 2024-08-20 | 126
2024 | Region III | PAMPANGA | ANGELES CITY (PAMPANGA) | P00838532LZ | Construction of Slope Protection Structure | 120.5837 | 15.1516 | 49483403.18 | 48992434.5 | 2024 | THREE-IN-ONE CONSTRUCTION & TRADING | 1034 | 2024 | 2024-06-24 | 02/08/2024 | 490968.68 | 0 | 2024-07-22 | 28
2024 | Region III | PAMPANGA | ANGELES CITY (PAMPANGA) | P00838359LZ | Construction of Slope Protection Structure | 120.5837 | 15.1516 | 96482277.85 | 96478456.8 | 2024 | AL-B DEVELOPMENT CORPORATION | 1035 | 2024 | 2024-10-08 | 03/14/2024 | 3821.05 | 0 | 2024-10-07 |  | 1
2024 | Region III | PAMPANGA | ANGELES CITY (PAMPANGA) | P00838360LZ | Construction of Slope Protection Structure | 120.5837 | 15.1516 | 67508966.65 | 67497735.16 | 2024 | TONKA CONSTRUCTION | 1036 | 2024 | 2024-12-05 | 02/16/2024 | 11231.49 | 0 | 2024-09-05 |  | 91
2023 | Region III | PAMPANGA | ANGELES CITY (PAMPANGA) | P00726183LZ | Construction of Groundsill | 120.5837 | 15.1515 | 29398758.28 | 29397875.38 | 2023 | ARROWHEAD CONSTRUCTION | 1037 | 2023 | 2023-06-09 | 02/10/2023 | 882.9 | 0 | 2023-06-08 |  | 1
2023 | Region III | PAMPANGA | ANGELES CITY (PAMPANGA) | P00727139LZ | Construction of Slope Protection Structure | 120.5837 | 15.1515 | 29395624.57 | 29205689.03 | 2023 | NEZIAH BUILDERS AND TRADING CORP. | 1038 | 2023 | 2023-05-22 | 03/20/2023 | 189935.54 | 0 | 2023-07-16 | 55
2023 | Region III | PAMPANGA | ANGELES CITY (PAMPANGA) | P00727140LZ | Construction of Slope Protection Structure | 120.5837 | 15.1515 | 24498744.06 | 24495203.65 | 2023 | TONKA CONSTRUCTION | 1039 | 2023 | 2023-04-23 | 03/06/2023 | 3540.41 | 0 | 2023-07-02 | 70
2023 | Region III | PAMPANGA | ANGELES CITY (PAMPANGA) | P00742359LZ | Construction of Slope Protection Structure | 120.5837 | 15.1515 | 17813921.54 | 17773537.48 | 2023 | RADIANS BUILDERS AND SUPPLY CORPORATION | 1040 | 2023 | 2023-07-01 | 04/03/2023 | 40384.06 | 0 | 2023-06-30 |  | 1
2023 | Region III | PAMPANGA | ANGELES CITY (PAMPANGA) | P00742358LZ | Construction of Slope Protection Structure | 120.5837 | 15.1515 | 11875217.83 | 11870351.08 | 2023 | RADIANS BUILDERS AND SUPPLY CORPORATION | 1041 | 2023 | 2023-06-10 | 04/12/2023 | 4866.75 | 0 | 2023-06-09 |  | 1
2023 | Region III | PAMPANGA | ANGELES CITY (PAMPANGA) | P00740359LZ | Construction of Slope Protection Structure | 120.5837 | 15.1515 | 53061678.21 | 53056624.6 | 2023 | THREE-IN-ONE CONSTRUCTION & TRADING / P.V.B. CONSTRUCTION & TRADING | 1042 | 2023 | 2023-10-20 | 05/24/2023 | 5053.61 | 0 | 2023-10-19 |  | 1
2024 | Region III | PAMPANGA | MABALACAT CITY (PAMPANGA) | P00844765LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.5837 | 15.1515 | 4897086.94 | 4791176.6 | 2024 | PRIME PAVE CONSTRUCTION AND ASPHALT CORPORATION | 1043 | 2024 | 2024-05-27 | 03/14/2024 | 105910.34 | 0 | 2024-05-26 |  | 1
2024 | Region III | TARLAC | CAPAS (TARLAC) | P00838433LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.5837 | 15.3181 | 96499387 | 96493753.29 | 2024 | HIGH STRENGTH DEV. CORPORATION | 1044 | 2024 | 2024-10-04 | 05/10/2024 | 5633.71 | 0 | 2024-11-08 | 35
2023 | Region III | TARLAC | CITY OF TARLAC (CAPITAL) (TARLAC) | P00742369LZ | Construction of Drainage Structure | 120.5839 | 15.4632 | 19800000 | 19399488.28 | 2023 | JAM-C BUILDERS | 1045 | 2023 | 2023-11-26 | 03/30/2023 | 400511.72 | 0 | 2023-11-21 |  | 5
2024 | Region I | ILOCOS NORTE | BACARRA (ILOCOS NORTE) | P00820706LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.5839 | 18.267 | 46039133.17 | 46039127.59 | 2024 | BJMJB CONSTRUCTION & SUPPLY | 1046 | 2024 | 2024-08-27 | 02/12/2024 | 5.58 | 0 | 2024-08-26 |  | 1
2024 | Region III | TARLAC | CAPAS (TARLAC) | P00838434LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.584 | 15.3187 | 96493935.38 | 96493309.27 | 2024 | RD8 BUILDERS CORPORATION UNDER THE NAME OF RD8 BUILDERS | 1047 | 2024 | 2024-11-09 | 05/10/2024 | 626.11 | 0 | 2024-11-08 |  | 1
2024 | Region III | TARLAC | CITY OF TARLAC (CAPITAL) (TARLAC) | P00848614LZ | Construction of Flood Mitigation Structure | 120.5842 | 15.5112 | 69300000 | 70000000 | 2024 | AMETHYST HORIZON BUILDERS AND GEN. CONTRACTOR AND DEVELOPMENT CORP. | 1048 | 2024 | 2024-09-08 | 02/16/2024 | 0 | 700000 | 2024-09-07 |  | 1
2024 | Region III | TARLAC | CITY OF TARLAC (CAPITAL) (TARLAC) | P00844767LZ | Construction of Slope Protection Structure | 120.5842 | 15.5112 | 49000000 | 50000000 | 2024 | T2B3 BUILDERS AND SUPPLIES CORP. | 1049 | 2024 | 2024-06-18 | 01/26/2024 | 0 | 1000000 | 2024-07-23 | 35
2023 | Region I | ILOCOS NORTE | SAN NICOLAS (ILOCOS NORTE) | P00726845LZ | Construction of Flood Mitigation Structure | 120.5844 | 18.1397 | 14475000 | 14475000 | 2024 | MEGAPOLITAN BUILDERS AND CONSTRUCTION SUPPLY | 1050 | 2023 | 2024-02-01 | 05/08/2023 | 0 | 0 | 2024-01-31 |  | 1
2024 | Region IV-B | OCCIDENTAL MINDORO | MAMBURAO (CAPITAL) (OCCIDENTAL MINDORO) | P00824742LZ | Construction of Flood Mitigation Structure | 120.5845 | 13.2243 | 11522840 | 11521786.89 | 2024 | NEW MINDORENOS LUMBER, HARDWARE AND GEN MERCHANDISE | 1051 | 2024 | 2024-09-02 | 04/08/2024 | 1053.11 | 0 | 2024-09-01 |  | 1
2024 | Region I | PANGASINAN | VILLASIS (PANGASINAN) | P00823284LZ | Construction of Flood Mitigation Structure | 120.5853 | 15.9061 | 48250000 | 48249366.52 | 2024 | UNIVERSAL DE LEON CONSTRUCTION AND AGGREGATES | 1052 | 2024 | 2024-07-15 | 04/26/2024 | 633.48 | 0 | 2024-10-15 | 92
2024 | Region I | PANGASINAN | VILLASIS (PANGASINAN) | P00823285LZ | Construction of Flood Mitigation Structure | 120.5853 | 15.9061 | 48250000 | 48249559.6 | 2024 | MG SAMIDAN CONSTRUCTION | 1053 | 2024 | 2024-07-15 | 04/26/2024 | 440.4 | 0 | 2024-10-15 | 92
2022 | Region III | PAMPANGA | PORAC (PAMPANGA) | P00620182LZ | Construction of Slope Protection Structure | 120.5853 | 15.1121 | 96149217.41 | 96143949.95 | 2022 | FERDSTAR BUILDERS INC. | 1054 | 2022 | 2022-11-11 | 03/02/2022 | 5267.46 | 0 | 2022-11-10 |  | 1
2024 | Region I | ILOCOS NORTE | BACARRA (ILOCOS NORTE) | P00820691LZ | Construction of Flood Mitigation Structure | 120.5854 | 18.2633 | 29399863.35 | 29399858.39 | 2024 | ZEDIK BUILDERS | 1055 | 2024 | 2024-08-21 | 02/29/2024 | 4.96 | 0 | 2024-08-20 |  | 1
2022 | Cordillera Administrative Region | BENGUET | LA TRINIDAD (CAPITAL) (BENGUET) | P00620473LZ | Construction of Flood Mitigation Structure | 120.5855 | 16.46 | 24500000 | 24487767.7 | 2022 | D.G.O. CONSTRUCTION | 1056 | 2022 | 2022-11-25 | 01/31/2022 | 12232.3 | 0 | 2022-12-03 | 8
2023 | Cordillera Administrative Region | BENGUET | LA TRINIDAD (CAPITAL) (BENGUET) | P00726407LZ | Construction of Flood Mitigation Structure | 120.5856 | 16.46 | 96500000 | 96480000 | 2023 | UNIVERSAL DE LEON CONSTRUCTION AND AGGREGATES | 1057 | 2023 | 2023-12-22 | 02/27/2023 | 20000 | 0 | 2024-02-24 | 64
2023 | Region III | PAMPANGA | ANGELES CITY (PAMPANGA) | P00726182LZ | Construction of Groundsill | 120.5858 | 15.1516 | 48789447.39 | 48693842.16 | 2023 | B-12 CONSTRUCTION AND TRADING CORPORATION | 1058 | 2023 | 2023-06-02 | 02/10/2023 | 95605.23 | 0 | 2023-07-08 | 36
2023 | Region III | PAMPANGA | ANGELES CITY (PAMPANGA) | P00725729LZ | Construction of Groundsill | 120.5858 | 15.1516 | 67535941.79 | 65559195.03 | 2023 | B-12 CONSTRUCTION AND TRADING CORPORATION / L.S.D. CONSTRUCTION & SUPPLIES | 1059 | 2023 | 2023-07-31 | 02/16/2023 | 1976746.76 | 0 | 2023-08-13 | 13
2024 | Region I | ILOCOS NORTE | BACARRA (ILOCOS NORTE) | P00839540LZ | Construction of Flood Mitigation Structure | 120.586 | 18.2615 | 48999742.96 | 48999740.13 | 2024 | BJMJB CONSTRUCTION & SUPPLY | 1060 | 2024 | 2024-08-27 | 02/13/2024 | 2.83 | 0 | 2024-08-30 | 3
2023 | Region III | PAMPANGA | ANGELES CITY (PAMPANGA) | P00740358LZ | Construction of Slope Protection Structure | 120.587 | 15.152 | 67548629.24 | 67506646.63 | 2023 | AL-B DEVELOPMENT CORPORATION | 1061 | 2023 | 2023-11-11 | 05/16/2023 | 41982.61 | 0 | 2023-11-10 |  | 1
2022 | Region III | TARLAC | CITY OF TARLAC (CAPITAL) (TARLAC) | P00620173LZ | Construction of Groundsill | 120.5875 | 15.4891 | 75270000 | 73765257.64 | 2022 | NORTHERN BUILDERS | 1062 | 2022 | 2022-07-18 | 02/22/2022 | 1504742.36 | 0 | 2022-09-24 | 68
2021 | Cordillera Administrative Region | BENGUET |  | P00525553LZ | Construction of Flood Mitigation Structure | 120.5877 | 16.4642 | 81078319.98 | 80869305.14 | 2022 | KVC CONSTRUCTION / UNIVERSAL DE LEON CONSTRUCTION AND AGGREGATES | 1063 | 2021 | 2022-12-20 | 06/23/2021 | 209014.84 | 0 | 2023-01-13 | 24
2023 | Region III | BATAAN | LIMAY (BATAAN) | P00742315LZ | Construction of Flood Mitigation Structure | 120.5881 | 14.5652 | 9899804.44 | 9900000 | 2023 | DE JESUS CONSTRUCTION | 1064 | 2023 | 2023-06-26 | 04/03/2023 | 0 | 195.56 | 2023-07-21 | 25
2024 | Region IV-B | OCCIDENTAL MINDORO | MAMBURAO (CAPITAL) (OCCIDENTAL MINDORO) | P00839656LZ | Construction of Flood Mitigation Structure | 120.5882 | 13.2229 | 9900000 | 9848740.48 | 2024 | STX ENTERPRISES | 1065 | 2024 | 2024-04-15 | 02/08/2024 | 51259.52 | 0 | 2024-05-04 | 19
2024 | Region III | PAMPANGA | MABALACAT CITY (PAMPANGA) | P00838356LZ | Construction of Slope Protection Structure | 120.5889 | 15.1937 | 96486616.8 | 96488518.31 | 2024 | M.G. SALAZAR CONSTRUCTION CORP. (FOR. M.G. SALAZAR / 525 CONSTRUCTION | 1066 | 2024 | 2024-10-29 | 04/04/2024 | 0 | 1901.51 | 2024-10-28 |  | 1
2024 | Cordillera Administrative Region | BENGUET | BOKOD (BENGUET) | P00821530LZ | Construction of Flood Mitigation Structure | 120.589 | 16.4627 | 39200000 | 39197620.93 | 2024 | UNIVERSAL DE LEON CONSTRUCTION AND AGGREGATES | 1067 | 2024 | 2024-10-28 | 06/03/2024 | 2379.07 | 0 | 2025-03-01 | 124
2023 | Region III | TARLAC | PANIQUI (TARLAC) | P00737486LZ | Construction of Drainage Structure | 120.5892 | 15.6812 | 19800000 | 19304999.69 | 2023 | R.R. RICAFORT CONSTRUCTION AND SUPPLIES | 1068 | 2023 | 2023-06-26 | 02/10/2023 | 495000.31 | 0 | 2023-07-31 | 35
2022 | Cordillera Administrative Region | BENGUET | LA TRINIDAD (CAPITAL) (BENGUET) | P00639443LZ | Construction of Flood Mitigation Structure | 120.5894 | 16.4831 | 2940000 | 2930210.39 | 2022 | POLO ENGINEERING & CONSTRUCTION | 1069 | 2022 | 2022-11-08 | 07/11/2022 | 9789.61 | 0 | 2022-11-07 |  | 1
2024 | Region I | ILOCOS NORTE | LAOAG CITY (CAPITAL) (ILOCOS NORTE) | P00839543LZ | Rehabilitation / Major Repair of Drainage Structure | 120.5895 | 18.2021 | 4949545.2 | 4949545.05 | 2024 | CAMBONG-BUILDERS INDUSTRIAL FACILITIES CONSTRUCTION | 1070 | 2024 | 2024-05-15 | 03/14/2024 | 0.15 | 0 | 2024-06-14 | 30
2023 | Region III | TARLAC | CITY OF TARLAC (CAPITAL) (TARLAC) | P00742133LZ | Construction of Slope Protection Structure | 120.5895 | 15.5154 | 57420000 | 57419383.62 | 2023 | HIGH STRENGTH DEV. CORPORATION / RCUBE ENGINEERING SERVICES | 1071 | 2023 | 2023-07-18 | 04/11/2023 | 616.38 | 0 | 2023-10-17 | 91
2024 | Region III | BATAAN | LIMAY (BATAAN) | P00820806LZ | Construction of Flood Mitigation Structure | 120.5897 | 14.5655 | 34300000 | 34300000 | 2024 | BPQ CONSTRUCTION AND TRADING / POLYMER-VIC CONSTRUCTION | 1072 | 2024 | 2024-11-15 | 02/20/2024 | 0 | 0 | 2024-11-16 | 1
2023 | Region III | PAMPANGA | LUBAO (PAMPANGA) | P00740614LZ | Construction of Slope Protection Structure | 120.5902 | 14.9219 | 19599120.01 | 19593827.54 | 2023 | RGZAMORA CONSTRUCTION AND TRADING | 1073 | 2023 | 2023-09-22 | 04/26/2023 | 5292.47 | 0 | 2023-09-21 |  | 1
2023 | Region III | PAMPANGA | ANGELES CITY (PAMPANGA) | P00740622LZ | Construction of Drainage Structure | 120.5905 | 15.1184 | 7834329.88 | 7825746.15 | 2023 | D.T. TIZON CONSTRUCTION AND TRADING | 1074 | 2023 | 2023-09-02 | 06/05/2023 | 8583.73 | 0 | 2023-09-01 |  | 1
2024 | Region III | TARLAC | CITY OF TARLAC (CAPITAL) (TARLAC) | P00823409LZ | Construction of Flood Mitigation Structure | 120.5907 | 15.5089 | 144750000 | 144750000 | 2024 | T2B3 BUILDERS AND SUPPLIES CORP. | 1075 | 2024 | 2024-09-23 | 02/23/2024 | 0 | 0 | 2024-11-21 | 59
2023 | Region III | PAMPANGA | ANGELES CITY (PAMPANGA) | P00740368LZ | Construction of Slope Protection Structure | 120.5907 | 15.1712 | 77192940.7 | 77191844.95 | 2023 | M.G. SALAZAR CONSTRUCTION CORP. (FOR. M.G. SALAZAR / 525 CONSTRUCTION | 1076 | 2023 | 2023-08-18 | 04/11/2023 | 1095.75 | 0 | 2023-10-06 | 49
2023 | Region III | PAMPANGA | MABALACAT CITY (PAMPANGA) | P00740619LZ | Construction of Drainage Structure | 120.5907 | 15.1833 | 4899846.7 | 4760182.02 | 2023 | AL-B DEVELOPMENT CORPORATION | 1077 | 2023 | 2023-08-19 | 05/22/2023 | 139664.68 | 0 | 2023-08-18 |  | 1
2023 | Region III | PAMPANGA | ANGELES CITY (PAMPANGA) | P00740628LZ | Rehabilitation / Major Repair of Drainage Structure | 120.5907 | 15.1712 | 29398271.13 | 29397781.56 | 2023 | PRIME PAVE CONSTRUCTION AND ASPHALT CORPORATION | 1078 | 2023 | 2023-10-02 | 06/05/2023 | 489.57 | 0 | 2023-10-01 |  | 1
2023 | Region I | ILOCOS NORTE | BACARRA (ILOCOS NORTE) | P00740543LZ | Construction of Slope Protection Structure | 120.5907 | 18.2738 | 4899853.21 | 4899850.31 | 2023 | ZEDIK BUILDERS | 1079 | 2023 | 2023-07-17 | 04/25/2023 | 2.9 | 0 | 2023-07-23 | 6
2024 | Cordillera Administrative Region | BENGUET | LA TRINIDAD (CAPITAL) (BENGUET) | P00821126LZ | Construction of Flood Mitigation Structure | 120.5909 | 16.4613 | 86850000 | 86820000 | 2024 | AKSUM CONTRACTING CORPORATION | 1080 | 2024 | 2024-11-22 | 02/21/2024 | 30000 | 0 | 2024-11-27 | 5
2024 | Region IV-B | OCCIDENTAL MINDORO | MAMBURAO (CAPITAL) (OCCIDENTAL MINDORO) | P00820406LZ | Construction of Flood Mitigation Structure | 120.5911 | 13.2275 | 96500000 | 94693310.64 | 2024 | ST. GERRARD CONSTRUCTION GEN. CONTRACTOR & DEVELOPMENT CORP. (FORMERLY:ST. GERRARD CONSTRUCTION) | 1081 | 2024 | 2024-09-15 | 02/14/2024 | 1806689.36 | 0 | 2024-11-25 | 71
2024 | Region I | PANGASINAN | BINALONAN (PANGASINAN) | P00844724LZ | Construction of Drainage Structure | 120.5911 | 16.0392 | 19600000 | 19548284 | 2024 | R.G.TABIN CONSTRUCTION AND SUPPLY | 1082 | 2024 | 2024-11-09 | 04/12/2024 | 51716 | 0 | 2024-11-08 |  | 1
2023 | Region III | TARLAC | CITY OF TARLAC (CAPITAL) (TARLAC) | P00726196LZ | Construction of Drainage Structure | 120.5912 | 15.4711 | 29400000 | 28663649.83 | 2023 | NORTHERN BUILDERS | 1083 | 2023 | 2023-06-16 | 03/09/2023 | 736350.17 | 0 | 2023-09-10 | 86
2023 | Region III | PAMPANGA | LUBAO (PAMPANGA) | P00740616LZ | Construction of Slope Protection Structure | 120.5912 | 14.936 | 19598843.36 | 19593178.51 | 2023 | M.C. GERONIMO CONSTRUCTION AND TRADING | 1084 | 2023 | 2023-06-15 | 04/11/2023 | 5664.85 | 0 | 2023-09-06 | 83
2023 | Region III | TARLAC | CAPAS (TARLAC) | P00726918LZ | Construction of Dike | 120.5912 | 15.3254 | 77199549.35 | 77196575.9 | 2023 | A.C. SOLIVEN CONSTRUCTION & GENERAL MERCHANDISE | 1085 | 2023 | 2023-09-16 | 03/17/2023 | 2973.45 | 0 | 2023-09-15 |  | 1
2023 | Region I | ILOCOS NORTE | LAOAG CITY (CAPITAL) (ILOCOS NORTE) | P00742254LZ | Construction of Drainage Structure | 120.5913 | 18.2129 | 4949469.37 | 4949436.79 | 2023 | DJCM CONSTRUCTION CORPORATION (FORMERLY: DJCM CONSTRUCTION) | 1086 | 2023 | 2023-06-30 | 04/12/2023 | 32.58 | 0 | 2023-07-10 | 10
2023 | Region I | PANGASINAN | BINALONAN (PANGASINAN) | P00740569LZ | Construction of Drainage Structure | 120.5914 | 16.0387 | 49000000 | 48936920.25 | 2023 | AMP 723 CONSTRUCTION CORPORATION (FORMERLY: A.M.P. CONSTRUCTION) | 1087 | 2023 | 2023-10-30 | 04/13/2023 | 63079.75 | 0 | 2023-10-29 |  | 1
2022 | Region III | BATAAN | LIMAY (BATAAN) | P00631175LZ | Construction of Flood Mitigation Structure | 120.5914 | 14.5656 | 9799999.66 | 9800000 | 2022 | R.Z. TIGAS CONSTRUCTION AND TRADING | 1088 | 2022 | 2022-08-10 | 03/24/2022 | 0 | 0.34 | 2022-08-09 |  | 1
2024 | Region IV-B | OCCIDENTAL MINDORO | MAMBURAO (CAPITAL) (OCCIDENTAL MINDORO) | P00839655LZ | Construction of Flood Mitigation Structure | 120.5914 | 13.2222 | 4950000 | 4948368.84 | 2024 | STX ENTERPRISES | 1089 | 2024 | 2024-04-22 | 02/08/2024 | 1631.16 | 0 | 2024-04-21 |  | 1
2023 | Region I | ILOCOS NORTE | LAOAG CITY (CAPITAL) (ILOCOS NORTE) | P00740558LZ | Construction of Flood Mitigation Structure | 120.5915 | 18.5103 | 48999860.86 | 48999809.17 | 2023 | IGWT-JAV CONSTRUCTION & DEVELOPMENT CORPORATION / EGB CONSTRUCTION CORPORATION (FORMERLY: EGB CONSTRUCTION) | 1090 | 2023 | 2023-10-26 | 05/05/2023 | 51.69 | 0 | 2024-01-07 | 73
2023 | Region III | TARLAC | CAPAS (TARLAC) | P00727151LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.5916 | 15.3255 | 32339147.58 | 32339347.92 | 2023 | A.R.T. DWELL LIFESTYLE STORE AND ECO BUILDERS | 1091 | 2023 | 2023-06-20 | 02/28/2023 | 0 | 200.34 | 2023-07-23 | 33
2023 | Region III | PAMPANGA | GUAGUA (PAMPANGA) | P00742346LZ | Construction of Slope Protection Structure | 120.5919 | 14.9903 | 29699208.33 | 29679049 | 2023 | R.D. SADSAD CONSTRUCTION & TRADING | 1092 | 2023 | 2023-09-13 | 04/17/2023 | 20159.33 | 0 | 2023-09-27 | 14
2023 | Region III | PAMPANGA | ANGELES CITY (PAMPANGA) | P00740636LZ | Construction of Drainage Structure | 120.5921 | 15.1518 | 4894824.65 | 4892626.47 | 2023 | NES-SAN BUILDERS | 1093 | 2023 | 2023-05-22 | 03/24/2023 | 2198.18 | 0 | 2023-05-21 |  | 1
2022 | Region III | PAMPANGA | ANGELES CITY (PAMPANGA) | P00631263LZ | Construction of Slope Protection Structure | 120.5923 | 15.1559 | 24498772.7 | 24151028.82 | 2022 | MICKAJETTE CONSTRUCTION AND TRADING | 1094 | 2022 | 2022-10-05 | 02/08/2022 | 347743.88 | 0 | 2022-10-04 |  | 1
2022 | Region I | PANGASINAN | BINALONAN (PANGASINAN) | P00620465LZ | Construction of Dike | 120.5925 | 16.0556 | 39200000 | 39109633.42 | 2022 | W.J.P. CONSTRUCTION AND SUPPLY | 1095 | 2022 | 2022-07-25 | 04/07/2022 | 90366.58 | 0 | 2022-10-11 | 78
2024 | Region I | PANGASINAN | BINALONAN (PANGASINAN) | P00821508LZ | Construction of Revetment | 120.5928 | 16.0641 | 49000000 | 48920129.97 | 2024 | W.J.P. CONSTRUCTION AND SUPPLY | 1096 | 2024 | 2024-05-31 | 02/21/2024 | 79870.03 | 0 | 2024-09-07 | 99
2024 | Region I | PANGASINAN | BINALONAN (PANGASINAN) | P00821501LZ | Construction of Revetment | 120.5928 | 16.0364 | 49000000 | 48919089.24 | 2024 | R.A. MATIAS CONSTRUCTION AND DEVELOPERS INC. (FORMERLY : R.A. MATIAS CONSTRUCTION AND DEVELOPERS) | 1097 | 2024 | 2024-03-26 | 02/14/2024 | 80910.76 | 0 | 2024-08-31 | 158
2021 | Cordillera Administrative Region | BENGUET |  | P00525552LZ | Construction of Flood Mitigation Structure | 120.593 | 16.4116 | 51660310 | 51660310 | 2022 | GOLDRICH CONSTRUCTION & TRADING | 1098 | 2021 | 2022-10-27 | 04/11/2022 | 0 | 0 | 2022-10-26 |  | 1
2022 | Cordillera Administrative Region | BENGUET | BAGUIO CITY (BENGUET) | P00620993LZ | Construction of Drainage Structure | 120.593 | 16.4116 | 49000000 | 49000000 | 2022 | GOLDRICH CONSTRUCTION & TRADING | 1099 | 2022 | 2022-11-07 | 02/11/2022 | 0 | 0 | 2022-11-06 |  | 1
2024 | Region I | PANGASINAN | BINALONAN (PANGASINAN) | P00821506LZ | Construction of Revetment | 120.5932 | 16.0677 | 49000000 | 48877781.14 | 2024 | SOLID STAR BUILDERS AND CONSTRUCTION SUPPLY | 1100 | 2024 | 2024-05-28 | 02/21/2024 | 122218.86 | 0 | 2024-09-07 | 102
2023 | Region I | ILOCOS NORTE | BACARRA (ILOCOS NORTE) | P00727043LZ | Construction of Flood Mitigation Structure | 120.5933 | 18.2527 | 29399735.53 | 29399734 | 2023 | BJMJB CONSTRUCTION & SUPPLY | 1101 | 2023 | 2023-08-15 | 03/29/2023 | 1.53 | 0 | 2023-09-28 | 44
2024 | Region III | TARLAC | CITY OF TARLAC (CAPITAL) (TARLAC) | P00825059LZ | Construction of Flood Mitigation Structure | 120.5934 | 15.5301 | 96500000 | 99000000 | 2024 | L.R. TIQUI BUILDERS, INC. | 1102 | 2024 | 2024-09-19 | 02/27/2024 | 0 | 2500000 | 2024-10-26 | 37
2023 | Region I | ILOCOS NORTE | LAOAG CITY (CAPITAL) (ILOCOS NORTE) | P00742252LZ | Construction of Drainage Structure | 120.5935 | 18.204 | 4949760.83 | 4949233.07 | 2023 | ZEDIK BUILDERS | 1103 | 2023 | 2023-08-13 | 04/20/2023 | 527.76 | 0 | 2023-08-12 |  | 1
2021 | Region III | PAMPANGA |  | P00526038LZ | Construction of Slope Protection Structure | 120.5935 | 14.8735 | 48999870.69 | 48244588.77 | 2022 | OMICRON CONSTRUCTION | 1104 | 2021 | 2022-08-24 | 03/09/2022 | 755281.92 | 0 | 2022-09-03 | 10
2024 | Region III | TARLAC | CITY OF TARLAC (CAPITAL) (TARLAC) | P00825058LZ | Construction of Flood Mitigation Structure | 120.594 | 15.5272 | 96500000 | 99000000 | 2024 | L.R. TIQUI BUILDERS, INC. | 1105 | 2024 | 2024-09-19 | 02/27/2024 | 0 | 2500000 | 2024-10-26 | 37
2024 | Region I | PANGASINAN | BINALONAN (PANGASINAN) | P00821507LZ | Construction of Revetment | 120.5941 | 16.0672 | 49000000 | 48883150.79 | 2024 | W.J.P. CONSTRUCTION AND SUPPLY | 1106 | 2024 | 2024-05-31 | 02/21/2024 | 116849.21 | 0 | 2024-09-07 | 99
2023 | Region III | PAMPANGA | ANGELES CITY (PAMPANGA) | P00740635LZ | Construction of Drainage Structure | 120.5943 | 15.1404 | 4897413.29 | 4881475.05 | 2023 | NES-SAN BUILDERS | 1107 | 2023 | 2023-07-21 | 03/24/2023 | 15938.24 | 0 | 2023-07-20 |  | 1
2023 | Region III | PAMPANGA | ANGELES CITY (PAMPANGA) | P00740621LZ | Construction of Drainage Structure | 120.5943 | 15.1404 | 4892793.3 | 4889105.41 | 2023 | QUANTUMWAYS BUILDERS ROAD CONSTRUCTION | 1108 | 2023 | 2023-07-20 | 05/22/2023 | 3687.89 | 0 | 2023-07-19 |  | 1
2022 | Region III | PAMPANGA | ANGELES CITY (PAMPANGA) | P00631253LZ | Construction of Slope Protection Structure | 120.5945 | 15.157 | 24497833.03 | 24472169.33 | 2022 | THREE-IN-ONE CONSTRUCTION & TRADING | 1109 | 2022 | 2022-10-31 | 03/24/2022 | 25663.7 | 0 | 2022-10-30 |  | 1
2022 | Region III | TARLAC | CITY OF TARLAC (CAPITAL) (TARLAC) | P00630939LZ | Construction of Drainage Structure | 120.595 | 15.4793 | 96500000 | 95052418.57 | 2022 | NORTHERN BUILDERS | 1110 | 2022 | 2022-11-12 | 03/10/2022 | 1447581.43 | 0 | 2022-11-11 |  | 1
2022 | Region III | TARLAC | CITY OF TARLAC (CAPITAL) (TARLAC) | P00640529LZ | Construction of Drainage Structure | 120.5953 | 15.4809 | 49500000 | 48515833 | 2022 | NORTHERN BUILDERS | 1111 | 2022 | 2022-10-28 | 03/30/2022 | 984167 | 0 | 2022-10-27 |  | 1
2023 | Region I | ILOCOS NORTE | PAOAY (ILOCOS NORTE) | P00726843LZ | Construction of Drainage Structure | 120.5309 | 18.0567 | 53075000 | 53074990.83 | 2024 | JLP CONSTRUCTION & SUPPLY (FORMERLY: JLP CONSTRUCT | 1112 | 2023 | 2024-03-07 | 03/22/2023 | 9.17 | 0 | 2024-03-06 |  | 1
2024 | Region I | ILOCOS NORTE | SARRAT (ILOCOS NORTE) | P00824638LZ | Construction of Flood Mitigation Structure | 120.6722 | 18.1487 | 48999745.89 | 48999653.83 | 2024 | IGWT-JAV CONSTRUCTION & DEVELOPMENT CORPORATION | 1113 | 2024 | 2024-09-27 | 03/01/2024 | 92.06 | 0 | 2024-09-26 |  | 1
2022 | Region III | BATAAN | PILAR (BATAAN) | P00620513LZ | Construction of Flood Mitigation Structure | 120.5311 | 14.6395 | 49000000 | 49000000 | 2022 | E.R. VENZON CONSTRUCTION / JVN CONSTRUCTION AND TRADING | 1114 | 2022 | 2022-12-22 | 04/04/2022 | 0 | 0 | 2022-12-14 |  | 8
2024 | Region I | ILOCOS SUR | QUIRINO (ANGKAKI) (ILOCOS SUR) | P00843216LZ | Construction of Flood Mitigation Structure | 120.673 | 17.1125 | 5880000 | 5688635.44 | 2024 | NABANEW CONSTRUCTION AND SUPPLY | 1115 | 2024 | 2024-10-07 | 04/30/2024 | 191364.56 | 0 | 2024-07-04 |  | 95
2021 | Region I | ILOCOS SUR |  | P00525873LZ | Construction of Flood Mitigation Structure | 120.5311 | 16.8259 | 9800000 | 9799998.61 | 2022 | A.I.P. CONSTRUCTION | 1116 | 2021 | 2022-08-31 | 10/11/2021 | 1.39 | 0 | 2022-02-26 |  | 186
2023 | Region I | ILOCOS NORTE | BANNA (ESPIRITU) (ILOCOS NORTE) | P00725581LZ | Construction of Flood Mitigation Structure | 120.6731 | 17.9589 | 48250000 | 48249410.43 | 2023 | JLP CONSTRUCTION & SUPPLY (FORMERLY: JLP CONSTRUCT | 1117 | 2023 | 2023-12-16 | 02/23/2023 | 589.57 | 0 | 2023-12-15 |  | 1
2024 | Region IV-A | BATANGAS | LIAN (BATANGAS) | P00820867LZ | Construction of Flood Mitigation Structure | 120.6731 | 14.0495 | 19600000 | 19600000 | 2024 | AMETHYST HORIZON BUILDERS AND GEN. CONTRACTOR AND DEVELOPMENT CORP. | 1118 | 2024 | 2024-08-05 | 02/08/2024 | 0 | 0 | 2024-08-04 |  | 1
2024 | Region I | ILOCOS NORTE | BANNA (ESPIRITU) (ILOCOS NORTE) | P00820134LZ | Construction of Flood Mitigation Structure | 120.6741 | 17.9529 | 72375000 | 72374725.65 | 2024 | JLP CONSTRUCTION & SUPPLY (FORMERLY: JLP CONSTRUCT | 1119 | 2024 | 2024-09-07 | 02/26/2024 | 274.35 | 0 | 2024-09-06 |  | 1
2024 | Region III | TARLAC | CAPAS (TARLAC) | P00821291LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.5312 | 15.4098 | 96498191.94 | 96492882.96 | 2024 | ROYAL CROWN MONARCH CONSTRUCTION & SUPPLIES CORP. | 1120 | 2024 | 2024-10-25 | 02/20/2024 | 5308.98 | 0 | 2024-10-24 |  | 1
2022 | Region III | PAMPANGA | ARAYAT (PAMPANGA) | P00632838LZ | Construction of Slope Protection Structure | 120.6742 | 15.1888 | 4950000 | 4687517 | 2022 | N.T. TULABUT CONSTRUCTION AND SUPPLY | 1121 | 2022 | 2022-09-07 | 06/10/2022 | 262483 | 0 | 2022-09-06 |  | 1
2024 | Region I | ILOCOS NORTE | SARRAT (ILOCOS NORTE) | P00820688LZ | Construction of Flood Mitigation Structure | 120.6743 | 18.1487 | 48999903.35 | 48999571.26 | 2024 | IGWT-JAV CONSTRUCTION & DEVELOPMENT CORPORATION | 1122 | 2024 | 2024-09-24 | 02/27/2024 | 332.09 | 0 | 2024-09-23 |  | 1
2023 | Region I | PANGASINAN | BALUNGAO (PANGASINAN) | P00742282LZ | Construction of Flood Mitigation Structure | 120.675 | 15.9084 | 9800000 | 9671787.53 | 2023 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | 1123 | 2023 | 2023-04-27 | 03/31/2023 | 128212.47 | 0 | 2023-06-27 | 61
2023 | Region I | ILOCOS NORTE | BANNA (ESPIRITU) (ILOCOS NORTE) | P00725582LZ | Construction of Flood Mitigation Structure | 120.6752 | 17.9581 | 48250000 | 48249997.02 | 2023 | JLP CONSTRUCTION & SUPPLY (FORMERLY: JLP CONSTRUCT | 1124 | 2023 | 2023-12-01 | 02/23/2023 | 2.98 | 0 | 2023-11-30 |  | 1
2024 | Region III | PAMPANGA | CITY OF SAN FERNANDO (CAPITAL) (PAMPANGA) | P00844759LZ | Construction of Slope Protection Structure | 120.6755 | 15.0695 | 49000000 | 46549904.52 | 2024 | EDDMARI CONSTRUCTION & TRADING | 1125 | 2024 | 2024-08-06 | 03/15/2024 | 2450095.48 | 0 | 2024-09-27 | 52
2024 | Region III | PAMPANGA | ARAYAT (PAMPANGA) | P00839589LZ | Construction of Slope Protection Structure | 120.6755 | 15.187 | 4950000 | 4677654.23 | 2024 | DAUNGAN CONSTRUCTION DEV'T. & GEN. SUPPLIES CO., INC. | 1126 | 2024 | 2024-04-29 | 02/07/2024 | 272345.77 | 0 | 2024-04-28 |  | 1
2022 | Region I | ILOCOS NORTE | BANNA (ESPIRITU) (ILOCOS NORTE) | P00620122LZ | Construction of Dike | 120.676 | 17.9982 | 55928505 | 55928505 | 2022 | VIKING CONSTRUCTION & SUPPLIES / BJMJB CONSTRUCTION & SUPPLY | 1127 | 2022 | 2022-11-30 | 03/25/2022 | 0 | 0 | 2022-12-20 | 20
2022 | Region III | PAMPANGA | BACOLOR (PAMPANGA) | P00631242LZ | Rehabilitation / Major Repair of Slope Protection Structure | 120.676 | 15.0136 | 19600000 | 18561193.12 | 2022 | R.S.C. CONSTRUCTION SERVICES | 1128 | 2022 | 2022-07-31 | 02/23/2022 | 1038806.88 | 0 | 2022-07-21 |  | 10
2022 | Region III | PAMPANGA | PORAC (PAMPANGA) | P00637783LZ | Construction of Slope Protection Structure | 120.5314 | 15.0574 | 19798253.91 | 19769166.53 | 2022 | R.D. SADSAD CONSTRUCTION & TRADING | 1129 | 2022 | 2022-11-15 | 04/13/2022 | 29087.38 | 0 | 2022-11-14 |  | 1
2022 | Region III | PAMPANGA | PORAC (PAMPANGA) | P00630938LZ | Construction of Slope Protection Structure | 120.5314 | 15.0572 | 241249381.9 | 241250000 | 2023 | NORTHERN BUILDERS | 1130 | 2022 | 2023-03-01 | 03/07/2022 | 0 | 618.1 | 2023-02-28 |  | 1
2024 | Region III | BATAAN | ORANI (BATAAN) | P00824693LZ | Construction of Revetment | 120.5315 | 14.7919 | 48999999.89 | 48999998.54 | 2025 | ORANI CONSTRUCTION AND SUPPLY CORPORATION (FORMERLY:ORANI BUILDERS & SUPPLY) | 1131 | 2024 | 2025-05-28 | 05/20/2024 | 1.35 | 0 | 2024-11-23 |  | 186
2022 | Region III | BATAAN | ORANI (BATAAN) | P00632803LZ | Construction of Drainage Structure | 120.5319 | 14.8033 | 14849997.48 | 14849989.69 | 2023 | AS MACHA CONSTRUCTION AND TRADING | 1132 | 2022 | 2023-01-28 | 04/04/2022 | 7.79 | 0 | 2023-01-29 | 1
2022 | Region I | PANGASINAN | BALUNGAO (PANGASINAN) | P00620970LZ | Construction of Dike | 120.6761 | 15.9092 | 29400000 | 29345730.44 | 2023 | RS RODRIGUEZ CONSTRUCTION & SUPPLIES | 1133 | 2022 | 2023-02-25 | 03/14/2022 | 54269.56 | 0 | 2022-09-06 |  | 172
2024 | Region III | BATAAN | CITY OF BALANGA (CAPITAL) (BATAAN) | P00820812LZ | Construction of Flood Mitigation Structure | 120.5321 | 14.6433 | 49000000 | 49000000 | 2024 | BPQ CONSTRUCTION AND TRADING / POLYMER-VIC CONSTRUCTION | 1134 | 2024 | 2024-10-10 | 02/27/2024 | 0 | 0 | 2024-10-03 |  | 7
2022 | Region III | BATAAN | PILAR (BATAAN) | P00620510LZ | Construction of Flood Mitigation Structure | 120.5323 | 14.6421 | 49000000 | 49000000 | 2022 | POLYMER-VIC CONSTRUCTION | 1135 | 2022 | 2022-11-21 | 04/04/2022 | 0 | 0 | 2022-11-20 |  | 1
2023 | Region III | BATAAN | PILAR (BATAAN) | P00726713LZ | Construction of Flood Mitigation Structure | 120.5323 | 14.6421 | 49000000 | 49000000 | 2023 | BPQ CONSTRUCTION AND TRADING / POLYMER-VIC CONSTRUCTION | 1136 | 2023 | 2023-06-26 | 02/14/2023 | 0 | 0 | 2023-10-02 | 98
2022 | Region III | BATAAN | ABUCAY (BATAAN) | P00621237LZ | Construction of Flood Mitigation Structure | 120.5325 | 14.7063 | 96499999.81 | 96500000 | 2023 | ROCKSTEEL CONSTRUCTION AND DEV'T CORPORATION / EGB CONSTRUCTION CORPORATION (FORMERLY: EGB CONSTRUCTION) | 1137 | 2022 | 2023-05-02 | 07/06/2022 | 0 | 0.19 | 2023-05-31 | 29
2022 | Region I | PANGASINAN | BALUNGAO (PANGASINAN) | P00620971LZ | Construction of Dike | 120.6764 | 15.9086 | 49000000 | 48950632.01 | 2022 | JHI CONSTRUCTION & SUPPLY | 1138 | 2022 | 2022-10-10 | 03/14/2022 | 49367.99 | 0 | 2022-09-29 |  | 11
2024 | Region III | TARLAC | CAPAS (TARLAC) | P00821292LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.5326 | 15.4078 | 96499373.58 | 96500000 | 2024 | ROYAL CROWN MONARCH CONSTRUCTION & SUPPLIES CORP. | 1139 | 2024 | 2024-11-25 | 02/20/2024 | 0 | 626.42 | 2024-08-20 |  | 97
2022 | Cordillera Administrative Region | ABRA | LA PAZ (ABRA) | P00632779LZ | Construction of Flood Mitigation Structure | 120.6768 | 17.6618 | 48999965.06 | 49497900 | 2022 | ST. TIMOTHY CONSTRUCTION CORPORATION | 1140 | 2022 | 2022-09-27 | 03/16/2022 | 0 | 497934.94 | 2022-09-26 |  | 1
2022 | Region III | PAMPANGA | FLORIDABLANCA (PAMPANGA) | P00621453LZ | Construction of Slope Protection Structure | 120.5327 | 14.9802 | 48852575.92 | 48844689.26 | 2022 | STO. CRISTO CONSTRUCTION & TRADING INC. (FOR: STO. CRISTO CONSTRUCTION & TRADING) | 1141 | 2022 | 2022-09-14 | 04/18/2022 | 7886.66 | 0 | 2022-09-13 |  | 1
2022 | Cordillera Administrative Region | ABRA | LA PAZ (ABRA) | P00632765LZ | Construction of Flood Mitigation Structure | 120.6776 | 17.6631 | 48999909.19 | 46352378.91 | 2022 | ST. TIMOTHY CONSTRUCTION CORPORATION | 1142 | 2022 | 2022-12-08 | 03/28/2022 | 2647530.28 | 0 | 2022-12-07 |  | 1
2023 | Region I | PANGASINAN | MANAOAG (PANGASINAN) | P00727088LZ | Construction of Flood Mitigation Structure | 120.5329 | 16.0087 | 49000000 | 48996410.44 | 2024 | BET CONSTRUCTION & SUPPLY | 1143 | 2023 | 2024-01-19 | 05/12/2023 | 3589.56 | 0 | 2024-01-18 |  | 1
2023 | Region I | ILOCOS NORTE | VINTAR (ILOCOS NORTE) | P00740512LZ | Construction of Flood Mitigation Structure | 120.6777 | 18.2416 | 29399927.25 | 29399903.6 | 2023 | HEKLER BUILDERS CORP. | 1144 | 2023 | 2023-12-15 | 03/29/2023 | 23.65 | 0 | 2023-10-28 |  | 48
2022 | Region I | PANGASINAN | MANAOAG (PANGASINAN) | P00631087LZ | Construction of Slope Protection Structure | 120.533 | 16.0086 | 14700000 | 14550366.98 | 2022 | BET CONSTRUCTION & SUPPLY | 1145 | 2022 | 2022-07-23 | 02/18/2022 | 149633.02 | 0 | 2022-06-22 |  | 31
2024 | Region III | BATAAN | PILAR (BATAAN) | P00820811LZ | Construction of Flood Mitigation Structure | 120.5332 | 14.6436 | 49000000 | 49000000 | 2024 | E.R. VENZON CONSTRUCTION / L.R. DE GUZMAN CONSTRUCTION | 1146 | 2024 | 2024-11-15 | 02/21/2024 | 0 | 0 | 2024-11-20 | 5
2022 | Region III | TARLAC | CONCEPCION (TARLAC) | P00621539LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.6777 | 15.3221 | 37239610.69 | 37228052.04 | 2022 | HIGH STRENGTH DEV. CORPORATION / T2B3 BUILDERS AND SUPPLIES CORP. | 1147 | 2022 | 2022-10-16 | 03/24/2022 | 11558.65 | 0 | 2022-10-15 |  | 1
2022 | Region III | PAMPANGA | PORAC (PAMPANGA) | P00621457LZ | Construction of Slope Protection Structure | 120.5332 | 15.0674 | 48852088.12 | 48840873.66 | 2022 | ARROW CONSTRUCTION | 1148 | 2022 | 2022-10-28 | 04/13/2022 | 11214.46 | 0 | 2022-11-07 | 10
2024 | Region III | TARLAC | CONCEPCION (TARLAC) | P00824708LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.6778 | 15.3221 | 46751014.15 | 46749922.54 | 2024 | RAIK CONSTRUCTION AND DEVELOPMENT CORPORATION (FORMERLY: RAIK CONSTRUCTION AND SUPPLY) | 1149 | 2024 | 2024-06-30 | 02/05/2024 | 1091.61 | 0 | 2024-06-29 |  | 1
2022 | Region III | PAMPANGA | MABALACAT CITY (PAMPANGA) | P00621461LZ | Construction of Flood Mitigation Structure | 120.5332 | 15.2144 | 24496149.16 | 24311437.71 | 2022 | ARROWHEAD CONSTRUCTION | 1150 | 2022 | 2022-09-11 | 03/24/2022 | 184711.45 | 0 | 2022-09-10 |  | 1
2022 | Region I | ILOCOS NORTE | VINTAR (ILOCOS NORTE) | P00621135LZ | Construction of Flood Mitigation Structure | 120.6788 | 18.2447 | 211335000 | 211334996.3 | 2022 | JOZEN BUILDERS AND CONSTRUCTION SUPPLY CORPORATION / EGB CONSTRUCTION CORPORATION (FORMERLY: EGB CONSTRUCTION) | 1151 | 2022 | 2022-10-10 | 04/01/2022 | 3.7 | 0 | 2023-01-24 | 106
2022 | Region I | ILOCOS NORTE | NUEVA ERA (ILOCOS NORTE) | P00621593LZ | Construction of Flood Mitigation Structure | 120.6789 | 17.9432 | 48999996.73 | 48999996.76 | 2022 | ST. MATTHEW GEN. CONTRACTOR & DEVELOPMENT CORP. | 1152 | 2022 | 2022-12-06 | 03/25/2022 | 0 | 0.03 | 2022-12-11 | 5
2024 | Region III | BATAAN | ORANI (BATAAN) | P00845962LZ | Construction of Flood Mitigation Structure | 120.5333 | 14.8079 | 9899999.72 | 9899999.72 | 2024 | SAN SEBASTIAN CONSTRUCTION | 1153 | 2024 | 2024-10-08 | 07/11/2024 | 0 | 0 | 2024-10-09 | 1
2022 | Region I | ILOCOS NORTE | NUEVA ERA (ILOCOS NORTE) | P00621558LZ | Construction of Flood Mitigation Structure | 120.6789 | 17.9435 | 80360000 | 79130000 | 2022 | ST. TIMOTHY CONSTRUCTION CORPORATION | 1154 | 2022 | 2022-10-28 | 04/07/2022 | 1230000 | 0 | 2022-10-27 |  | 1
2022 | Region III | PAMPANGA | MABALACAT CITY (PAMPANGA) | P00639485LZ | Construction of Flood Mitigation Structure | 120.5334 | 15.216 | 48998211.85 | 48534502.89 | 2022 | ARROWHEAD CONSTRUCTION | 1155 | 2022 | 2022-09-24 | 03/24/2022 | 463708.96 | 0 | 2022-09-23 |  | 1
2022 | Region I | ILOCOS NORTE | NUEVA ERA (ILOCOS NORTE) | P00621552LZ | Construction of Flood Mitigation Structure | 120.679 | 17.9434 | 80360000 | 79130000 | 2022 | ST. TIMOTHY CONSTRUCTION CORPORATION | 1156 | 2022 | 2022-10-28 | 04/07/2022 | 1230000 | 0 | 2022-10-27 |  | 1
2022 | Region I | ILOCOS SUR | SALCEDO (BAUGEN) (ILOCOS SUR) | P00621508LZ | Construction of Flood Mitigation Structure | 120.5335 | 17.1385 | 14700000 | 14699999.73 | 2022 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | 1157 | 2022 | 2022-08-28 | 04/04/2022 | 0.27 | 0 | 2022-08-28 | 0
2023 | Region I | ILOCOS SUR | BURGOS (ILOCOS SUR) | P00742269LZ | Construction of Flood Mitigation Structure | 120.5336 | 17.2919 | 9900000 | 9879986.49 | 2024 | A.I.P. CONSTRUCTION | 1158 | 2023 | 2024-07-02 | 04/20/2023 | 20013.51 | 0 | 2023-07-10 |  | 358
2023 | Region I | ILOCOS NORTE | SARRAT (ILOCOS NORTE) | P00726043LZ | Construction of Flood Mitigation Structure | 120.679 | 18.1474 | 39199899.27 | 39199115.51 | 2023 | IGWT-JAV CONSTRUCTION & DEVELOPMENT CORPORATION / EGB CONSTRUCTION CORPORATION (FORMERLY: EGB CONSTRUCTION) | 1159 | 2023 | 2023-06-23 | 02/13/2023 | 783.76 | 0 | 2023-09-01 | 70
2022 | Cordillera Administrative Region | BENGUET | SABLAN (BENGUET) | P00639451LZ | Construction of Slope Protection Structure | 120.5337 | 16.5443 | 14700000 | 14688347 | 2023 | UNIVERSAL DE LEON CONSTRUCTION AND AGGREGATES | 1160 | 2022 | 2023-12-01 | 09/07/2022 | 11653 | 0 | 2023-07-13 |  | 141
2022 | Region I | ILOCOS NORTE | NUEVA ERA (ILOCOS NORTE) | P00621603LZ | Construction of Flood Mitigation Structure | 120.6791 | 17.9428 | 49000000 | 48249999.1 | 2023 | ST. MATTHEW GEN. CONTRACTOR & DEVELOPMENT CORP. | 1161 | 2022 | 2023-03-15 | 11/03/2022 | 750000.9 | 0 | 2023-04-30 | 46
2023 | Region I | ILOCOS NORTE | PAOAY (ILOCOS NORTE) | P00726854LZ | Construction of Flood Mitigation Structure | 120.6799 | 18.1353 | 8299000 | 8288961.56 | 2023 | SOLSONA-GANAL CONSTRUCTION & SUPPLY | 1162 | 2023 | 2023-07-11 | 05/08/2023 | 10038.44 | 0 | 2023-07-29 | 18
2022 | Region I | ILOCOS NORTE | BADOC (ILOCOS NORTE) | P00621273LZ | Construction of Flood Mitigation Structure | 120.5337 | 17.9157 | 96500000 | 96499997.09 | 2022 | ST. MATTHEW GEN. CONTRACTOR & DEVELOPMENT CORP. | 1163 | 2022 | 2022-10-18 | 04/07/2022 | 2.91 | 0 | 2022-12-31 | 74
2022 | Region I | ILOCOS SUR | SALCEDO (BAUGEN) (ILOCOS SUR) | P00620134LZ | Construction of Flood Mitigation Structure | 120.5339 | 17.1295 | 49000000 | 48999995.79 | 2023 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | 1164 | 2022 | 2023-02-15 | 04/04/2022 | 4.21 | 0 | 2022-12-29 |  | 48
2021 | Cordillera Administrative Region | ABRA |  | P00561497LZ | Construction of Flood Mitigation Structure | 120.6801 | 17.668 | 48999808.84 | 48997500 | 2022 | ST. TIMOTHY CONSTRUCTION CORPORATION | 1165 | 2021 | 2022-07-12 | 01/07/2022 | 2308.84 | 0 | 2022-07-20 | 8
2023 | Region III | BATAAN | ORANI (BATAAN) | P00727125LZ | Construction of Flood Mitigation Structure | 120.5341 | 14.7935 | 48999999.04 | 49000000 | 2023 | AVE-MIRA CONSTRUCTION AND TRADING | 1166 | 2023 | 2023-10-16 | 03/13/2023 | 0 | 0.96 | 2023-10-20 | 4
2023 | Region I | ILOCOS SUR | BURGOS (ILOCOS SUR) | P00737413LZ | Construction of Flood Mitigation Structure | 120.5344 | 17.2914 | 9900000 | 9598259.55 | 2024 | JMCQ CONSTRUCTION AND SUPPLY | 1167 | 2023 | 2024-06-04 | 03/28/2023 | 301740.45 | 0 | 2023-06-17 |  | 353
2024 | Region III | TARLAC | CONCEPCION (TARLAC) | P00824707LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.6801 | 15.3026 | 46748976.2 | 46728726.02 | 2024 | HIGH STRENGTH DEV. CORPORATION | 1168 | 2024 | 2024-05-13 | 02/05/2024 | 20250.18 | 0 | 2024-06-29 | 47
2022 | Region III | PAMPANGA | FLORIDABLANCA (PAMPANGA) | P00637782LZ | Construction of Slope Protection Structure | 120.5347 | 14.9681 | 19799967.46 | 19779866.52 | 2022 | R.M. VITUG CONSTRUCTION | 1169 | 2022 | 2022-09-09 | 04/13/2022 | 20100.94 | 0 | 2022-09-08 |  | 1
2023 | Cordillera Administrative Region | ABRA | DOLORES (ABRA) | P00726375LZ | Construction of Flood Mitigation Structure | 120.681 | 17.6422 | 144749907.4 | 144744528.6 | 2024 | MG SAMIDAN CONSTRUCTION | 1170 | 2023 | 2024-04-10 | 04/14/2023 | 5378.8 | 0 | 2024-03-20 |  | 21
2024 | Region III | PAMPANGA | FLORIDABLANCA (PAMPANGA) | P00846005LZ | Construction of Slope Protection Structure | 120.5348 | 14.9806 | 14849616.15 | 14842087.89 | 2024 | J. LINGAT CONSTRUCTION | 1171 | 2024 | 2024-07-30 | 03/18/2024 | 7528.26 | 0 | 2024-07-29 |  | 1
2022 | Region I | ILOCOS NORTE | NUEVA ERA (ILOCOS NORTE) | P00621605LZ | Construction of Flood Mitigation Structure | 120.6811 | 17.9215 | 49000000 | 48249999.67 | 2023 | ST. MATTHEW GEN. CONTRACTOR & DEVELOPMENT CORP. | 1172 | 2022 | 2023-03-15 | 11/03/2022 | 750000.33 | 0 | 2023-04-30 | 46
2023 | Region III | PAMPANGA | FLORIDABLANCA (PAMPANGA) | P00740610LZ | Construction of Slope Protection Structure | 120.5349 | 14.973 | 29399126.19 | 29393302.38 | 2024 | RVR3 CONSTRUCTION SUPPLY AND SERVICES | 1173 | 2023 | 2024-04-09 | 04/20/2023 | 5823.81 | 0 | 2024-04-08 |  | 1
2022 | Region I | ILOCOS NORTE | NUEVA ERA (ILOCOS NORTE) | P00621606LZ | Construction of Flood Mitigation Structure | 120.6811 | 17.9214 | 49000000 | 48249996.9 | 2023 | ST. MATTHEW GEN. CONTRACTOR & DEVELOPMENT CORP. | 1174 | 2022 | 2023-03-15 | 11/03/2022 | 750003.1 | 0 | 2023-04-30 | 46
2024 | Region I | PANGASINAN | BALUNGAO (PANGASINAN) | P00843203LZ | Construction of Dike | 120.6815 | 15.939 | 96500000 | 96393183.69 | 2024 | RS RODRIGUEZ CONSTRUCTION & SUPPLIES / JHI CONSTRUCTION & SUPPLY | 1175 | 2024 | 2024-06-30 | 04/16/2024 | 106816.31 | 0 | 2025-01-23 | 207
2022 | Region III | TARLAC | CONCEPCION (TARLAC) | P00621291LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.6822 | 15.3248 | 60215392.55 | 60202410.54 | 2023 | HIGH STRENGTH DEV. CORPORATION / T2B3 BUILDERS AND SUPPLIES CORP. | 1176 | 2022 | 2023-01-05 | 03/26/2022 | 12982.01 | 0 | 2023-01-04 |  | 1
2022 | Region I | ILOCOS NORTE | NUEVA ERA (ILOCOS NORTE) | P00621592LZ | Construction of Flood Mitigation Structure | 120.6823 | 17.9413 | 48999997.76 | 48999997.76 | 2022 | ST. MATTHEW GEN. CONTRACTOR & DEVELOPMENT CORP. | 1177 | 2022 | 2022-12-08 | 03/29/2022 | 0 | 0 | 2022-12-15 | 7
2022 | Region I | ILOCOS NORTE | NUEVA ERA (ILOCOS NORTE) | P00621594LZ | Construction of Flood Mitigation Structure | 120.6823 | 17.9418 | 48999997.76 | 48999997.76 | 2022 | ST. MATTHEW GEN. CONTRACTOR & DEVELOPMENT CORP. | 1178 | 2022 | 2022-12-05 | 03/25/2022 | 0 | 0 | 2022-12-11 | 6
2024 | Region III | TARLAC | CAPAS (TARLAC) | P00821293LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.535 | 15.4054 | 96499828.21 | 96497531.14 | 2024 | ROYAL CROWN MONARCH CONSTRUCTION & SUPPLIES CORP. | 1179 | 2024 | 2024-10-25 | 02/20/2024 | 2297.07 | 0 | 2024-10-24 |  | 1
2022 | Region III | PAMPANGA | BACOLOR (PAMPANGA) | P00620542LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.6826 | 14.9917 | 29400000 | 27782198.84 | 2022 | DAUNGAN CONSTRUCTION DEV'T. & GEN. SUPPLIES CO., INC. | 1180 | 2022 | 2022-07-20 | 02/21/2022 | 1617801.16 | 0 | 2022-07-19 |  | 1
2022 | Region III | PAMPANGA | MABALACAT CITY (PAMPANGA) | P00631254LZ | Construction of Flood Mitigation Structure | 120.535 | 15.2157 | 24497798.6 | 23752035.93 | 2022 | ARROWHEAD CONSTRUCTION | 1181 | 2022 | 2022-07-07 | 02/25/2022 | 745762.67 | 0 | 2022-08-14 | 38
2023 | Region I | ILOCOS SUR | QUIRINO (ANGKAKI) (ILOCOS SUR) | P00727081LZ | Construction of Flood Mitigation Structure | 120.6834 | 17.1396 | 19600000 | 19599957.43 | 2023 | NABANEW CONSTRUCTION AND SUPPLY | 1182 | 2023 | 2023-12-26 | 03/22/2023 | 42.57 | 0 | 2023-07-19 |  | 160
2022 | Region III | PAMPANGA | MABALACAT CITY (PAMPANGA) | P00621460LZ | Construction of Flood Mitigation Structure | 120.535 | 15.2157 | 24493652.12 | 24304593.61 | 2022 | ARROWHEAD CONSTRUCTION | 1183 | 2022 | 2022-09-11 | 03/24/2022 | 189058.51 | 0 | 2022-09-10 |  | 1
2022 | Cordillera Administrative Region | BENGUET | ITOGON (BENGUET) | P00639446LZ | Construction of Flood Mitigation Structure | 120.6837 | 16.3658 | 5390000 | 5289578.4 | 2022 | NINETY ONE BUILDERS | 1184 | 2022 | 2022-11-04 | 07/18/2022 | 100421.6 | 0 | 2022-11-03 |  | 1
2024 | Region III | TARLAC | CONCEPCION (TARLAC) | P00824709LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.6841 | 15.3019 | 46749159.12 | 46736249.12 | 2024 | RAIK CONSTRUCTION AND DEVELOPMENT CORPORATION (FORMERLY: RAIK CONSTRUCTION AND SUPPLY) | 1185 | 2024 | 2024-05-20 | 02/05/2024 | 12910 | 0 | 2024-06-29 | 40
2022 | Region III | PAMPANGA | MABALACAT CITY (PAMPANGA) | P00637077LZ | Construction of Flood Mitigation Structure | 120.535 | 15.2157 | 24494456.68 | 24278801.96 | 2022 | ARROWHEAD CONSTRUCTION | 1186 | 2022 | 2022-11-11 | 05/24/2022 | 215654.72 | 0 | 2022-11-10 |  | 1
2024 | Region I | PANGASINAN | BALUNGAO (PANGASINAN) | P00843204LZ | Construction of Dike | 120.6846 | 15.9385 | 96500000 | 96390646.52 | 2024 | RS RODRIGUEZ CONSTRUCTION & SUPPLIES / JHI CONSTRUCTION & SUPPLY | 1187 | 2024 | 2024-06-30 | 04/16/2024 | 109353.48 | 0 | 2025-01-23 | 207
2024 | Region I | ILOCOS SUR | QUIRINO (ANGKAKI) (ILOCOS SUR) | P00838504LZ | Construction of Flood Mitigation Structure | 120.6848 | 17.0944 | 5880000 | 5688855.8 | 2024 | EJIEV CONSTRUCTION SERVICES | 1188 | 2024 | 2024-10-10 | 05/03/2024 | 191144.2 | 0 | 2024-07-07 |  | 95
2022 | Region I | ILOCOS NORTE | SARRAT (ILOCOS NORTE) | P00621585LZ | Construction of Flood Mitigation Structure | 120.6848 | 18.1442 | 11759923.14 | 11759084.34 | 2022 | ALTEC CONSTRUCTION | 1189 | 2022 | 2022-08-03 | 04/04/2022 | 838.8 | 0 | 2022-08-11 | 8
2022 | Cordillera Administrative Region | BENGUET | ATOK (BENGUET) | P00620809LZ | Construction of Flood Mitigation Structure | 120.6851 | 16.6001 | 51920860 | 51857438.1 | 2022 | ALMOND ENGINEERING & CONSTRUCTION / EGB CONSTRUCTION CORPORATION (FORMERLY: EGB CONSTRUCTION) | 1190 | 2022 | 2022-10-17 | 03/08/2022 | 63421.9 | 0 | 2022-11-03 | 17
2022 | Region I | PANGASINAN | SANTA MARIA (PANGASINAN) | P00620975LZ | Construction of Revetment | 120.6856 | 15.9392 | 29400000 | 28517854.91 | 2022 | R.A. MATIAS CONSTRUCTION AND DEVELOPERS INC. (FORMERLY : R.A. MATIAS CONSTRUCTION AND DEVELOPERS) | 1191 | 2022 | 2022-11-17 | 02/24/2022 | 882145.09 | 0 | 2022-08-11 |  | 98
2023 | Region I | ILOCOS NORTE | MARCOS (ILOCOS NORTE) | P00725596LZ | Construction of Flood Mitigation Structure | 120.6859 | 18.0259 | 48250000 | 48249058.58 | 2024 | MEGAPOLITAN BUILDERS AND CONSTRUCTION SUPPLY | 1192 | 2023 | 2024-01-31 | 03/03/2023 | 941.42 | 0 | 2024-01-31 | 0
2022 | Region I | ILOCOS SUR | QUIRINO (ANGKAKI) (ILOCOS SUR) | P00621510LZ | Construction of Flood Mitigation Structure | 120.6861 | 17.135 | 19600000 | 19599997.6 | 2023 | NABANEW CONSTRUCTION AND SUPPLY | 1193 | 2022 | 2023-08-30 | 04/04/2022 | 2.4 | 0 | 2022-08-01 |  | 394
2021 | Cordillera Administrative Region | BENGUET |  | P00561462LZ | Construction of Flood Mitigation Structure | 120.6864 | 16.6006 | 96493651 | 96500000 | 2022 | 4RMCONSTRUCTION & SUPPLIES / R.S. SEPIAN CONSTRUCTION & TRUCKING | 1194 | 2021 | 2022-09-03 | 01/07/2022 | 0 | 6349 | 2022-09-02 |  | 1
2023 | Region III | PAMPANGA | FLORIDABLANCA (PAMPANGA) | P00742344LZ | Construction of Slope Protection Structure | 120.535 | 14.9796 | 29699731.69 | 29692996.3 | 2023 | R.M. VITUG CONSTRUCTION | 1195 | 2023 | 2023-09-16 | 04/05/2023 | 6735.39 | 0 | 2023-09-15 |  | 1
2024 | Region III | BATAAN | ABUCAY (BATAAN) | P00845964LZ | Construction of Drainage Structure | 120.535 | 14.7295 | 9899999.1 | 9899999.1 | 2024 | DE JESUS CONSTRUCTION | 1196 | 2024 | 2024-09-19 | 04/22/2024 | 0 | 0 | 2024-09-21 | 2
2023 | Region III | PAMPANGA | FLORIDABLANCA (PAMPANGA) | P00742357LZ | Construction of Slope Protection Structure | 120.5352 | 14.9911 | 49499311.6 | 49489954.9 | 2023 | DMDANAN CONSTRUCTION AND TRADING | 1197 | 2023 | 2023-11-17 | 05/22/2023 | 9356.7 | 0 | 2023-11-16 |  | 1
2022 | Region III | PAMPANGA | GUAGUA (PAMPANGA) | P00639365LZ | Rehabilitation / Major Repair of Drainage Structure | 120.5353 | 15.0027 | 96499899.11 | 96492456.51 | 2022 | SOLFIO P. JACINTO CONSTRUCTION INC. | 1198 | 2022 | 2022-12-05 | 06/01/2022 | 7442.6 | 0 | 2023-02-09 | 66
2024 | Region III | BATAAN | PILAR (BATAAN) | P00820810LZ | Construction of Flood Mitigation Structure | 120.5353 | 14.6427 | 49000000 | 49000000 | 2024 | 4B CONSTRUCTION CORPORATION | 1199 | 2024 | 2024-10-10 | 02/27/2024 | 0 | 0 | 2024-10-09 |  | 1
2021 | Region III | PAMPANGA |  | P00526024LZ | Construction of Slope Protection Structure | 120.5353 | 14.9912 | 19599915.01 | 19594564.38 | 2022 | ARROW CONSTRUCTION | 1200 | 2021 | 2022-08-17 | 03/21/2022 | 5350.63 | 0 | 2022-08-16 |  | 1
2023 | Region I | ILOCOS SUR | SALCEDO (BAUGEN) (ILOCOS SUR) | P00727077LZ | Construction of Flood Mitigation Structure | 120.5354 | 17.1415 | 29400000 | 29399992.88 | 2024 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | 1201 | 2023 | 2024-06-24 | 03/22/2023 | 7.12 | 0 | 2023-10-19 |  | 249
2023 | Region III | PAMPANGA | GUAGUA (PAMPANGA) | P00740618LZ | Construction of Slope Protection Structure | 120.5355 | 15.0082 | 19599287.27 | 19545904.49 | 2023 | R.M. VITUG CONSTRUCTION | 1202 | 2023 | 2023-07-20 | 05/08/2023 | 53382.78 | 0 | 2023-10-03 | 75
2022 | Region I | ILOCOS SUR | NAGBUKEL (ILOCOS SUR) | P00640496LZ | Construction of Flood Mitigation Structure | 120.5359 | 17.4519 | 19800000 | 19202205.72 | 2023 | CZMAC CONSTRUCTION SERVICES | 1203 | 2022 | 2023-08-28 | 05/19/2022 | 597794.28 | 0 | 2022-09-15 |  | 347
2022 | Region III | PAMPANGA | GUAGUA (PAMPANGA) | P00639358LZ | Construction of Slope Protection Structure | 120.5361 | 15.5361 | 77199894.84 | 77188819.91 | 2023 | TOKWING CONSTRUCTION, CORP.(FOR; TOKWING CONSTRUC | 1204 | 2022 | 2023-01-19 | 07/04/2022 | 11074.93 | 0 | 2023-03-14 | 54
2023 | Region III | BATAAN | PILAR (BATAAN) | P00726714LZ | Construction of Flood Mitigation Structure | 120.5366 | 14.6587 | 34299504.65 | 34300000 | 2023 | JEK TRADING AND CONSTRUCTION / E.R. VENZON CONSTRUCTION | 1205 | 2023 | 2023-11-10 | 04/24/2023 | 0 | 495.35 | 2023-11-10 | 0
2022 | Region III | PAMPANGA | FLORIDABLANCA (PAMPANGA) | P00621455LZ | Construction of Slope Protection Structure | 120.5371 | 14.9844 | 48852725.9 | 48840963.08 | 2022 | TOKWING CONSTRUCTION, CORP.(FOR; TOKWING CONSTRUC | 1206 | 2022 | 2022-10-14 | 04/18/2022 | 11762.82 | 0 | 2022-10-13 |  | 1
2024 | Region III | TARLAC | CAPAS (TARLAC) | P00821294LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.5372 | 15.4033 | 96499464.69 | 96496366.23 | 2024 | T2B3 BUILDERS AND SUPPLIES CORP. | 1207 | 2024 | 2024-12-16 | 04/27/2024 | 3098.46 | 0 | 2025-01-12 | 27
2023 | Region III | BATAAN | PILAR (BATAAN) | P00726715LZ | Construction of Flood Mitigation Structure | 120.5378 | 14.6603 | 34299204.11 | 34300000 | 2023 | BPQ CONSTRUCTION AND TRADING / POLYMER-VIC CONSTRUCTION | 1208 | 2023 | 2023-12-27 | 04/24/2023 | 0 | 795.89 | 2024-01-04 | 8
2022 | Region I | ILOCOS NORTE | NUEVA ERA (ILOCOS NORTE) | P00621602LZ | Construction of Flood Mitigation Structure | 120.6867 | 17.9237 | 49000000 | 48249996.51 | 2023 | ST. MATTHEW GEN. CONTRACTOR & DEVELOPMENT CORP. | 1209 | 2022 | 2023-03-15 | 11/03/2022 | 750003.49 | 0 | 2023-04-30 | 46
2024 | Region III | PAMPANGA | MABALACAT CITY (PAMPANGA) | P00838419LZ | Construction of Flood Mitigation Structure | 120.5378 | 15.2143 | 96470759.6 | 96466323 | 2024 | TRICHES CONSTRUCTION & TRADING | 1210 | 2024 | 2024-11-16 | 04/22/2024 | 4436.6 | 0 | 2024-11-15 |  | 1
2024 | Region III | PAMPANGA | MABALACAT CITY (PAMPANGA) | P00838420LZ | Construction of Flood Mitigation Structure | 120.5378 | 15.2143 | 96486069.79 | 96477961.31 | 2024 | EDFROBON CONSTRUCTION SERVICES INCORPORATED | 1211 | 2024 | 2024-11-16 | 04/22/2024 | 8108.48 | 0 | 2024-11-15 |  | 1
2024 | Region I | ILOCOS SUR | SALCEDO (BAUGEN) (ILOCOS SUR) | P00823301LZ | Construction of Flood Mitigation Structure | 120.5381 | 17.1295 | 49000000 | 48249964.94 | 2024 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | 1212 | 2024 | 2024-11-15 | 04/12/2024 | 750035.06 | 0 | 2024-11-18 | 3
2022 | Region III | PAMPANGA | LUBAO (PAMPANGA) | P00637778LZ | Construction of Drainage Structure | 120.5382 | 14.9214 | 4949950.12 | 4791069.16 | 2022 | R.M. VITUG CONSTRUCTION | 1213 | 2022 | 2022-07-05 | 04/13/2022 | 158880.96 | 0 | 2022-07-10 | 5
2024 | Region III | BATAAN | ABUCAY (BATAAN) | P00845960LZ | Construction of Flood Mitigation Structure | 120.5383 | 14.7087 | 9899999.8 | 9899999.8 | 2024 | AVE-MIRA CONSTRUCTION AND TRADING | 1214 | 2024 | 2024-09-19 | 06/27/2024 | 0 | 0 | 2024-09-25 | 6
2022 | Region III | TARLAC | PANIQUI (TARLAC) | P00637784LZ | Construction of Flood Mitigation Structure | 120.5388 | 15.6514 | 34300000 | 33950858.49 | 2022 | BIG BERTHA CONSTRUCTION & DEVELOPMENT | 1215 | 2022 | 2022-09-10 | 03/30/2022 | 349141.51 | 0 | 2022-09-09 |  | 1
2022 | Region III | TARLAC | BAMBAN (TARLAC) | P00639369LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.6136 | 15.3281 | 96499727.17 | 94489688.9 | 2022 | ROYAL CROWN MONARCH CONSTRUCTION & SUPPLIES CORP. | 1216 | 2022 | 2022-11-27 | 03/26/2022 | 2010038.27 | 0 | 2022-11-26 |  | 1
2024 | Region I | PANGASINAN | BINALONAN (PANGASINAN) | P00823278LZ | Construction of Flood Mitigation Structure | 120.5394 | 16.0434 | 48250000 | 48249942.73 | 2025 | SILVERWOLVES CONSTRUCTION CORPORATION | 1217 | 2024 | 2025-01-12 | 05/03/2024 | 57.27 | 0 | 2025-01-11 |  | 1
2024 | Region I | PANGASINAN | BINALONAN (PANGASINAN) | P00823280LZ | Construction of Flood Mitigation Structure | 120.5394 | 16.0434 | 48250000 | 48249696.41 | 2024 | ROCK-WBL CONSTRUCTION CORP. (FOR: ROCK-WBL CONSTRUCTION TRADING & SERVICES) | 1218 | 2024 | 2024-12-12 | 05/03/2024 | 303.59 | 0 | 2024-12-11 |  | 1
2024 | Region I | PANGASINAN | BINALONAN (PANGASINAN) | P00823282LZ | Construction of Flood Mitigation Structure | 120.5394 | 16.0434 | 48250000 | 48249924.4 | 2024 | MG SAMIDAN CONSTRUCTION | 1219 | 2024 | 2024-12-10 | 04/26/2024 | 75.6 | 0 | 2024-12-09 |  | 1
2025 | Region III | TARLAC | CITY OF TARLAC (CAPITAL) (TARLAC) | P00921064LZ | Construction of Slope Protection Structure | 120.614 | 15.4275 | 14700000 | 14229719.67 | 2025 | BIG BERTHA CONSTRUCTION & DEVELOPMENT | 1220 | 2025 | 2025-05-22 | 01/27/2025 | 470280.33 | 0 | 2025-05-24 | 2
2022 | Region III | TARLAC | BAMBAN (TARLAC) | P00620195LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.6141 | 15.3287 | 57899105.79 | 57734172.99 | 2022 | B.P. CRUZ BUILDERS AND TRADING | 1221 | 2022 | 2022-08-02 | 02/16/2022 | 164932.8 | 0 | 2022-08-01 |  | 1
2022 | Cordillera Administrative Region | BENGUET | BAGUIO CITY (BENGUET) | P00620994LZ | Construction of Drainage Structure | 120.6143 | 16.3753 | 17640000 | 16673974.44 | 2022 | A.R.J. CIVIL ENGINEERING CONSTRUCTION | 1222 | 2022 | 2022-10-13 | 03/13/2022 | 966025.56 | 0 | 2022-10-12 |  | 1
2023 | Region III | PAMPANGA | MAGALANG (PAMPANGA) | P00742142LZ | Construction of Slope Protection Structure | 120.6877 | 15.2565 | 69286359.4 | 69214730.8 | 2023 | TRICHES CONSTRUCTION & TRADING / FRAMECON BUILDERS | 1223 | 2023 | 2023-11-11 | 05/16/2023 | 71628.6 | 0 | 2023-11-10 |  | 1
2022 | Region III | PAMPANGA | MABALACAT CITY (PAMPANGA) | P00632853LZ | Construction of Slope Protection Structure | 120.615 | 15.2077 | 19597072.83 | 19588065.3 | 2022 | SAN SEBASTIAN CONSTRUCTION | 1224 | 2022 | 2022-07-04 | 02/08/2022 | 9007.53 | 0 | 2022-07-03 |  | 1
2022 | Region III | PAMPANGA | ANGELES CITY (PAMPANGA) | P00620176LZ | Construction of Slope Protection Structure | 120.6151 | 15.1541 | 56838169.33 | 55968336.61 | 2022 | AL-B DEVELOPMENT CORPORATION | 1225 | 2022 | 2022-09-11 | 02/25/2022 | 869832.72 | 0 | 2022-09-10 |  | 1
2023 | Region III | PAMPANGA | MAGALANG (PAMPANGA) | P00742365LZ | Construction of Slope Protection Structure | 120.6877 | 15.2565 | 19785527.99 | 19721987.26 | 2023 | M.C.J. VALENZUELA CONSTRUCTION ENTERPRISES | 1226 | 2023 | 2023-09-10 | 05/24/2023 | 63540.73 | 0 | 2023-09-09 |  | 1
2022 | Cordillera Administrative Region | BENGUET | TUBLAY (BENGUET) | P00639459LZ | Construction of Flood Mitigation Structure | 120.6152 | 16.5265 | 9800000 | 9789992.93 | 2022 | TRIBAL MOVERS CONSTRUCTION | 1227 | 2022 | 2022-12-22 | 06/14/2022 | 10007.07 | 0 | 2022-12-27 | 5
2024 | Region I | PANGASINAN | ALCALA (PANGASINAN) | P00824800LZ | Construction of Flood Mitigation Structure | 120.5394 | 15.8546 | 96500000 | 96499995.51 | 2024 | SILVERWOLVES CONSTRUCTION CORPORATION | 1228 | 2024 | 2024-07-31 | 05/03/2024 | 4.49 | 0 | 2024-12-03 | 125
2024 | Region III | PAMPANGA | ANGELES CITY (PAMPANGA) | P00844764LZ | Construction of Drainage Structure | 120.6877 | 15.2565 | 9799337.71 | 9797939.97 | 2024 | AL-B DEVELOPMENT CORPORATION | 1229 | 2024 | 2024-08-27 | 04/02/2024 | 1397.74 | 0 | 2024-08-26 |  | 1
2023 | Region III | PAMPANGA | PORAC (PAMPANGA) | P00742353LZ | Construction of Slope Protection Structure | 120.5394 | 15.0383 | 24749084.09 | 24734901.6 | 2023 | SIX SILVERS CONSTRUCTION AND DEVELOPMENT CORP | 1230 | 2023 | 2023-10-18 | 05/22/2023 | 14182.49 | 0 | 2023-10-17 |  | 1
2024 | Region III | PAMPANGA | MAGALANG (PAMPANGA) | P00838531LZ | Construction of Slope Protection Structure | 120.6877 | 15.2565 | 48975379.79 | 48971773.59 | 2024 | TONKA CONSTRUCTION | 1231 | 2024 | 2024-09-11 | 04/22/2024 | 3606.2 | 0 | 2024-10-04 | 23
2021 | Cordillera Administrative Region | BENGUET |  | P00525911LZ | Construction of Flood Mitigation Structure | 120.6159 | 16.574 | 11649260 | 11489414.45 | 2022 | FAMILY CIRCLE CONSTRUCTION | 1232 | 2021 | 2022-12-02 | 03/13/2022 | 159845.55 | 0 | 2022-12-01 |  | 1
2024 | Region III | PAMPANGA | MAGALANG (PAMPANGA) | P00838358LZ | Construction of Slope Protection Structure | 120.6877 | 15.2565 | 86836843.23 | 86821821.41 | 2024 | THREE-IN-ONE CONSTRUCTION & TRADING | 1233 | 2024 | 2024-05-20 | 02/16/2024 | 15021.82 | 0 | 2024-09-13 | 116
2023 | Region III | PAMPANGA | PORAC (PAMPANGA) | P00742352LZ | Construction of Slope Protection Structure | 120.5395 | 15.0393 | 24749108.27 | 24738841.23 | 2023 | SIX SILVERS CONSTRUCTION AND DEVELOPMENT CORP | 1234 | 2023 | 2023-10-18 | 05/22/2023 | 10267.04 | 0 | 2023-10-17 |  | 1
2024 | Region III | PAMPANGA | MAGALANG (PAMPANGA) | P00838362LZ | Construction of Slope Protection Structure | 120.6877 | 15.2565 | 77186570.48 | 77183078.33 | 2024 | THREE-IN-ONE CONSTRUCTION & TRADING | 1235 | 2024 | 2024-05-20 | 02/16/2024 | 3492.15 | 0 | 2024-09-12 | 115
2022 | Region III | TARLAC | CONCEPCION (TARLAC) | P00639371LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.616 | 15.2856 | 96499429.74 | 94533425.98 | 2022 | ROYAL CROWN MONARCH CONSTRUCTION & SUPPLIES CORP. | 1236 | 2022 | 2022-09-25 | 03/26/2022 | 1966003.76 | 0 | 2022-09-24 |  | 1
2022 | Region III | TARLAC | PANIQUI (TARLAC) | P00640528LZ | Construction of Slope Protection Structure | 120.5397 | 15.6364 | 49500000 | 48511634.63 | 2022 | HIGH STRENGTH DEV. CORPORATION / RCUBE ENGINEERING SERVICES | 1237 | 2022 | 2022-09-24 | 03/28/2022 | 988365.37 | 0 | 2022-09-23 |  | 1
2022 | Region I | ILOCOS NORTE | NUEVA ERA (ILOCOS NORTE) | P00621604LZ | Construction of Flood Mitigation Structure | 120.6879 | 17.9238 | 49000000 | 48249996.92 | 2023 | ST. MATTHEW GEN. CONTRACTOR & DEVELOPMENT CORP. | 1238 | 2022 | 2023-03-15 | 11/03/2022 | 750003.08 | 0 | 2023-04-30 | 46
2023 | Region IV-A | BATANGAS | NASUGBU (BATANGAS) | P00742385LZ | Construction of Drainage Structure | 120.6163 | 14.1198 | 4255760 | 4255760 | 2023 | 816 EMBER CONSTRUCTION CORPORATION | 1239 | 2023 | 2023-07-21 | 04/19/2023 | 0 | 0 | 2023-07-20 |  | 1
2023 | Region III | PAMPANGA | MAGALANG (PAMPANGA) | P00727141LZ | Rehabilitation / Major Repair of Slope Protection Structure | 120.688 | 15.2564 | 26456586.43 | 26256800.55 | 2023 | NEZIAH BUILDERS AND TRADING CORP. | 1240 | 2023 | 2023-07-23 | 04/25/2023 | 199785.88 | 0 | 2023-07-22 |  | 1
2023 | Region I | ILOCOS NORTE | BACARRA (ILOCOS NORTE) | P00737409LZ | Rehabilitation / Major Repair of Drainage Structure | 120.6172 | 18.2536 | 4949912.17 | 4949912.02 | 2023 | ALTHEA CONSTRUCTION | 1241 | 2023 | 2023-06-19 | 02/13/2023 | 0.15 | 0 | 2023-06-18 |  | 1
2023 | Region III | TARLAC | CAMILING (TARLAC) | P00726197LZ | Construction of Flood Mitigation Structure | 120.5397 | 15.6366 | 49000000 | 48141038.91 | 2023 | A.C. SOLIVEN CONSTRUCTION & GENERAL MERCHANDISE | 1242 | 2023 | 2023-07-18 | 01/30/2023 | 858961.09 | 0 | 2023-07-28 | 10
2022 | Cordillera Administrative Region | ABRA | LA PAZ (ABRA) | P00632773LZ | Construction of Flood Mitigation Structure | 120.6883 | 17.6708 | 48999959.12 | 49497500 | 2022 | ST. TIMOTHY CONSTRUCTION CORPORATION | 1243 | 2022 | 2022-10-09 | 03/28/2022 | 0 | 497540.88 | 2022-10-08 |  | 1
2023 | Region III | TARLAC | PANIQUI (TARLAC) | P00736619LZ | Construction of Slope Protection Structure | 120.5397 | 15.6364 | 49000000 | 47530569.42 | 2023 | J.H.R. ENTERPRISES | 1244 | 2023 | 2023-05-24 | 01/30/2023 | 1469430.58 | 0 | 2023-07-28 | 65
2023 | Region III | PAMPANGA | ANGELES CITY (PAMPANGA) | P00740630LZ | Construction of Slope Protection Structure | 120.6177 | 15.1446 | 21063826.67 | 21061809.75 | 2023 | THREE-IN-ONE CONSTRUCTION & TRADING | 1245 | 2023 | 2023-08-13 | 05/16/2023 | 2016.92 | 0 | 2023-08-12 |  | 1
2018 | Region III | BATAAN |  | P00222127LZ | Construction of Flood Mitigation Structure | 120.54 | 14.82 | 143841300 | 136302210.2 | 2023 | TOKWING CONSTRUCTION, CORP.(FOR; TOKWING CONSTRUC | 1246 | 2018 | 2023-08-31 | 02/26/2018 | 7539089.8 | 0 | 2023-08-30 |  | 1
2023 | Region III | PAMPANGA | ANGELES CITY (PAMPANGA) | P00740634LZ | Construction of Slope Protection Structure | 120.6177 | 15.1446 | 4898988.19 | 4887932.85 | 2023 | AL-B DEVELOPMENT CORPORATION | 1247 | 2023 | 2023-07-20 | 05/22/2023 | 11055.34 | 0 | 2023-07-19 |  | 1
2023 | Region III | PAMPANGA | ANGELES CITY (PAMPANGA) | P00740632LZ | Construction of Drainage Structure | 120.6177 | 15.1446 | 4899261.31 | 4851646.26 | 2023 | THREE-IN-ONE CONSTRUCTION & TRADING | 1248 | 2023 | 2023-06-01 | 04/03/2023 | 47615.05 | 0 | 2023-05-31 |  | 1
2023 | Region III | PAMPANGA | MAGALANG (PAMPANGA) | P00740366LZ | Construction of Slope Protection Structure | 120.689 | 15.2193 | 67530313.95 | 67419722.43 | 2023 | THREE-IN-ONE CONSTRUCTION & TRADING | 1249 | 2023 | 2023-11-19 | 05/24/2023 | 110591.52 | 0 | 2023-11-18 |  | 1
2022 | Cordillera Administrative Region | ABRA | LA PAZ (ABRA) | P00632774LZ | Construction of Flood Mitigation Structure | 120.6894 | 17.6731 | 48999950.92 | 49497500 | 2022 | ST. TIMOTHY CONSTRUCTION CORPORATION | 1250 | 2022 | 2022-11-10 | 03/30/2022 | 0 | 497549.08 | 2022-10-10 |  | 31
2021 | Region IV-B | OCCIDENTAL MINDORO |  | P00561806LZ | Construction of Flood Mitigation Structure | 120.6181 | 13.2552 | 2970000 | 2450991.9 | 2022 | ORIENT STAR CONSTRUCTION, INC. (FORMERLY: ORIENT S | 1251 | 2021 | 2022-10-24 | 04/08/2022 | 519008.1 | 0 | 2022-10-23 |  | 1
2024 | Region I | ILOCOS SUR | QUIRINO (ANGKAKI) (ILOCOS SUR) | P00824830LZ | Construction of Flood Mitigation Structure | 120.6894 | 17.1404 | 157295000 | 157294568.6 | 2025 | A.I.P. CONSTRUCTION | 1252 | 2024 | 2025-01-07 | 02/26/2024 | 431.4 | 0 | 2025-01-06 |  | 1
2022 | Region III | BATAAN | SAMAL (BATAAN) | P00632805LZ | Construction of Drainage Structure | 120.5407 | 14.7833 | 9899999.99 | 9899999.99 | 2022 | PASCAL CONSTRUCTION | 1253 | 2022 | 2022-07-14 | 02/17/2022 | 0 | 0 | 2022-07-18 | 4
2022 | Cordillera Administrative Region | ABRA | LA PAZ (ABRA) | P00632770LZ | Construction of Flood Mitigation Structure | 120.6182 | 17.6279 | 48999905.92 | 49497500 | 2022 | 739 BUILDERS | 1254 | 2022 | 2022-12-05 | 05/24/2022 | 0 | 497594.08 | 2022-12-04 |  | 1
2022 | Region IV-A | BATANGAS | NASUGBU (BATANGAS) | P00620248LZ | Construction of Flood Mitigation Structure | 120.6895 | 14.0453 | 77200000 | 77200000 | 2022 | V.R. PATRON BUILDERS & DEVELOPERS CORP. (PREVIOUSL | 1255 | 2022 | 2022-11-18 | 02/23/2022 | 0 | 0 | 2022-11-23 | 5
2022 | Region III | PAMPANGA | ANGELES CITY (PAMPANGA) | P00621459LZ | Construction of Slope Protection Structure | 120.5414 | 15.1667 | 24498331.34 | 24482452.91 | 2022 | NES-SAN BUILDERS | 1256 | 2022 | 2022-10-06 | 03/24/2022 | 15878.43 | 0 | 2022-10-10 | 4
2024 | Region I | ILOCOS NORTE | BACARRA (ILOCOS NORTE) | P00838481LZ | Construction of Drainage Structure | 120.6183 | 18.2499 | 4899504.94 | 4899380.88 | 2024 | CAMBONG-BUILDERS INDUSTRIAL FACILITIES CONSTRUCTION | 1257 | 2024 | 2024-05-07 | 02/16/2024 | 124.06 | 0 | 2024-05-18 | 11
2024 | Region IV-B | OCCIDENTAL MINDORO | MAMBURAO (CAPITAL) (OCCIDENTAL MINDORO) | P00824747LZ | Construction of Flood Mitigation Structure | 120.6896 | 13.1522 | 4900000 | 4870149.83 | 2024 | KGB ENGINEERING AND CONSTRUCTION | 1258 | 2024 | 2024-05-21 | 03/06/2024 | 29850.17 | 0 | 2024-05-26 | 5
2023 | Region III | TARLAC | PANIQUI (TARLAC) | P00740369LZ | Construction of Flood Mitigation Structure | 120.5415 | 15.6344 | 77200000 | 77199671.49 | 2023 | A.C. SOLIVEN CONSTRUCTION & GENERAL MERCHANDISE | 1259 | 2023 | 2023-11-16 | 04/12/2023 | 328.51 | 0 | 2023-11-15 |  | 1
2022 | Region I | ILOCOS NORTE | NUEVA ERA (ILOCOS NORTE) | P00621610LZ | Construction of Flood Mitigation Structure | 120.6902 | 17.9406 | 48999997.76 | 48999997.76 | 2022 | DJCM CONSTRUCTION CORPORATION (FORMERLY: DJCM CONSTRUCTION) | 1260 | 2022 | 2022-10-13 | 03/25/2022 | 0 | 0 | 2022-10-12 |  | 1
2023 | Region III | BATAAN | CITY OF BALANGA (CAPITAL) (BATAAN) | P00742316LZ | Construction of Revetment | 120.5418 | 14.6708 | 6929955.1 | 6784428.58 | 2023 | VF CONSTRUCTION | 1261 | 2023 | 2023-07-05 | 04/05/2023 | 145526.52 | 0 | 2023-07-25 | 20
2024 | Region I | ILOCOS NORTE | BACARRA (ILOCOS NORTE) | P00820672LZ | Construction of Flood Mitigation Structure | 120.6183 | 18.2436 | 29399874.94 | 29399860.43 | 2024 | BJMJB CONSTRUCTION & SUPPLY | 1262 | 2024 | 2024-04-16 | 02/12/2024 | 14.51 | 0 | 2024-08-03 | 109
2022 | Region III | PAMPANGA | MASANTOL (PAMPANGA) | P00639483LZ | Construction of Slope Protection Structure | 120.6906 | 14.837 | 19600000 | 18541526.13 | 2022 | N-22 CONSTRUCTION AND TRADING | 1263 | 2022 | 2022-08-17 | 05/20/2022 | 1058473.87 | 0 | 2022-08-16 |  | 1
2022 | Region I | ILOCOS SUR | SUGPON (ILOCOS SUR) | P00640499LZ | Construction of Flood Mitigation Structure | 120.5419 | 16.7895 | 19800000 | 19799998.32 | 2023 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | 1264 | 2022 | 2023-08-29 | 04/04/2022 | 1.68 | 0 | 2022-08-07 |  | 387
2022 | Region III | PAMPANGA | MABALACAT CITY (PAMPANGA) | P00631259LZ | Construction of Slope Protection Structure | 120.6184 | 15.2084 | 48996557.84 | 47450440.65 | 2022 | L.S.D. CONSTRUCTION & SUPPLIES / PRIME PAVE CONSTRUCTION AND ASPHALT CORPORATION | 1265 | 2022 | 2022-10-01 | 02/08/2022 | 1546117.19 | 0 | 2022-09-30 |  | 1
2022 | Cordillera Administrative Region | BENGUET | ITOGON (BENGUET) | P00620998LZ | Construction of Flood Mitigation Structure | 120.6909 | 16.3834 | 24500000 | 24500000 | 2023 | GSIXTY CONSTRUCTION SERVICES | 1266 | 2022 | 2023-03-15 | 05/10/2022 | 0 | 0 | 2023-01-10 |  | 64
2021 | Region III | TARLAC |  | P00526052LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.5423 | 15.6135 | 14700000 | 13967566.61 | 2022 | ARCONIC INC. | 1267 | 2021 | 2022-07-24 | 03/28/2022 | 732433.39 | 0 | 2022-07-23 |  | 1
2023 | Region I | ILOCOS NORTE | CITY OF BATAC (ILOCOS NORTE) | P00725583LZ | Construction of Flood Mitigation Structure | 120.6188 | 18.071 | 11580000 | 11579999.2 | 2023 | MEGAPOLITAN BUILDERS AND CONSTRUCTION SUPPLY | 1268 | 2023 | 2023-07-11 | 03/03/2023 | 0.8 | 0 | 2023-07-10 |  | 1
2023 | Region III | PAMPANGA | MAGALANG (PAMPANGA) | P00726184LZ | Construction of Flood Mitigation Structure | 120.6911 | 15.2328 | 48993495.02 | 48940091.64 | 2023 | RADIANS BUILDERS AND SUPPLY CORPORATION | 1269 | 2023 | 2023-09-15 | 03/20/2023 | 53403.38 | 0 | 2023-09-14 |  | 1
2022 | Region III | PAMPANGA | ANGELES CITY (PAMPANGA) | P00637076LZ | Construction of Slope Protection Structure | 120.5432 | 15.166 | 24498017.95 | 24475221.98 | 2022 | RADIANS BUILDERS AND SUPPLY CORPORATION | 1270 | 2022 | 2022-11-11 | 05/24/2022 | 22795.97 | 0 | 2022-11-10 |  | 1
2022 | Cordillera Administrative Region | ABRA | LA PAZ (ABRA) | P00639320LZ | Construction of Flood Mitigation Structure | 120.6198 | 17.627 | 96499892.57 | 95238758.44 | 2023 | MG SAMIDAN CONSTRUCTION / RM30 PSG CONSTRUCTION CORPORATION | 1271 | 2022 | 2023-09-29 | 12/28/2022 | 1261134.13 | 0 | 2023-09-30 | 1
2023 | Region III | PAMPANGA | CITY OF SAN FERNANDO (CAPITAL) (PAMPANGA) | P00742340LZ | Construction of Slope Protection Structure | 120.6916 | 15.0331 | 9900000 | 9602952.08 | 2023 | EL KAPITAN CONSTRUCTION SERVICES | 1272 | 2023 | 2023-12-28 | 07/05/2023 | 297047.92 | 0 | 2023-12-27 |  | 1
2024 | Cordillera Administrative Region | ABRA | LA PAZ (ABRA) | P00823319LZ | Construction of Flood Mitigation Structure | 120.692 | 17.6749 | 96500000 | 96497500.15 | 2024 | MG SAMIDAN CONSTRUCTION | 1273 | 2024 | 2024-09-16 | 02/19/2024 | 2499.85 | 0 | 2024-09-15 |  | 1
2024 | Region III | PAMPANGA | PORAC (PAMPANGA) | P00848617LZ | Construction of Flood Mitigation Structure | 120.5435 | 15.0667 | 4949467.73 | 4945000 | 2024 | V. TRILLANA BUILDERS & TRADING | 1274 | 2024 | 2024-05-22 | 04/08/2024 | 4467.73 | 0 | 2024-05-21 |  | 1
2024 | Region III | PAMPANGA | ANGELES CITY (PAMPANGA) | P00846008LZ | Construction of Slope Protection Structure | 120.6201 | 15.1499 | 9888296.92 | 9885415.68 | 2024 | AYANA CONSTRUCTION AND TRADING | 1275 | 2024 | 2024-07-27 | 04/02/2024 | 2881.24 | 0 | 2024-07-26 |  | 1
2024 | Region III | BATAAN | CITY OF BALANGA (CAPITAL) (BATAAN) | P00824695LZ | Construction of Flood Mitigation Structure | 120.5436 | 14.6756 | 39200000 | 39200000 | 2025 | POLYMER-VIC CONSTRUCTION | 1276 | 2024 | 2025-02-13 | 05/14/2024 | 0 | 0 | 2025-02-12 |  | 1
2022 | Cordillera Administrative Region | ABRA | LA PAZ (ABRA) | P00632772LZ | Construction of Flood Mitigation Structure | 120.6924 | 17.6772 | 49000000 | 49497515.89 | 2022 | ST. TIMOTHY CONSTRUCTION CORPORATION | 1277 | 2022 | 2022-12-08 | 03/28/2022 | 0 | 497515.89 | 2022-12-07 |  | 1
2023 | Region I | PANGASINAN | BINALONAN (PANGASINAN) | P00726054LZ | Construction of Dike | 120.6208 | 16.0781 | 49000000 | 48900255.04 | 2023 | W.J.P. CONSTRUCTION AND SUPPLY | 1278 | 2023 | 2023-06-06 | 02/10/2023 | 99744.96 | 0 | 2023-08-19 | 74
2022 | Region III | TARLAC | CITY OF TARLAC (CAPITAL) (TARLAC) | P00621282LZ | Construction of Slope Protection Structure | 120.5443 | 15.4559 | 96500000 | 93605000 | 2022 | ROYAL CROWN MONARCH CONSTRUCTION & SUPPLIES CORP. / GJE BUILDERS CORPORATION (FORMERLY: GJE BUILDERS) | 1279 | 2022 | 2022-09-12 | 03/30/2022 | 2895000 | 0 | 2022-11-27 | 76
2022 | Cordillera Administrative Region | ABRA | LA PAZ (ABRA) | P00637061LZ | Construction of Flood Mitigation Structure | 120.693 | 17.6832 | 48999712.6 | 48997500 | 2022 | 739 BUILDERS | 1280 | 2022 | 2022-12-22 | 07/20/2022 | 2212.6 | 0 | 2022-12-21 |  | 1
2024 | Region I | PANGASINAN | ASINGAN (PANGASINAN) | P00824660LZ | Construction of Dike | 120.6216 | 16.0059 | 29400000 | 29354074.45 | 2024 | R.A. MATIAS CONSTRUCTION AND DEVELOPERS INC. (FORMERLY : R.A. MATIAS CONSTRUCTION AND DEVELOPERS) | 1281 | 2024 | 2024-05-24 | 02/26/2024 | 45925.55 | 0 | 2024-08-20 | 88
2022 | Cordillera Administrative Region | ABRA | DOLORES (ABRA) | P00639319LZ | Construction of Flood Mitigation Structure | 120.6934 | 17.6468 | 96499900.75 | 94135771.11 | 2023 | MG SAMIDAN CONSTRUCTION | 1282 | 2022 | 2023-01-30 | 12/28/2022 | 2364129.64 | 0 | 2023-09-30 | 243
2024 | Region I | ILOCOS NORTE | SARRAT (ILOCOS NORTE) | P00824637LZ | Construction of Flood Mitigation Structure | 120.6219 | 18.0903 | 4899955.25 | 4899952.42 | 2024 | BJMJB CONSTRUCTION & SUPPLY | 1283 | 2024 | 2024-04-19 | 03/04/2024 | 2.83 | 0 | 2024-06-09 | 51
2023 | Region III | PAMPANGA | FLORIDABLANCA (PAMPANGA) | P00727307LZ | Construction of Flood Mitigation Structure | 120.5447 | 14.9273 | 96498519.09 | 96493125.05 | 2024 | ARROW CONSTRUCTION / PENTAGON INDUSTRIAL DEVELOPMENT & CONSTRUCTION CO. | 1284 | 2023 | 2024-01-09 | 06/14/2023 | 5394.04 | 0 | 2024-03-08 | 59
2022 | Region I | ILOCOS NORTE | BACARRA (ILOCOS NORTE) | P00639414LZ | Construction of Flood Mitigation Structure | 120.6219 | 18.2514 | 24499953.37 | 24499951.39 | 2022 | REMIGIO GENERAL CONSTRUCTION | 1285 | 2022 | 2022-12-28 | 04/04/2022 | 1.98 | 0 | 2022-12-29 | 1
2022 | Region I | PANGASINAN | BALUNGAO (PANGASINAN) | P00620976LZ | Construction of Revetment | 120.6936 | 15.9339 | 39200000 | 39153721.46 | 2023 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | 1286 | 2022 | 2023-03-15 | 03/14/2022 | 46278.54 | 0 | 2022-09-09 |  | 187
2024 | Region I | PANGASINAN | CITY OF URDANETA (PANGASINAN) | P00843206LZ | Construction of Flood Mitigation Structure | 120.5455 | 15.9895 | 193000000 | 192999802.9 | 2024 | SILVERWOLVES CONSTRUCTION CORPORATION | 1287 | 2024 | 2024-11-11 | 06/24/2024 | 197.1 | 0 | 2025-04-18 | 158
2022 | Region III | PAMPANGA | MABALACAT CITY (PAMPANGA) | P00631252LZ | Construction of Drainage Structure | 120.6223 | 15.237 | 14683287.84 | 14680755.8 | 2022 | NES-SAN BUILDERS | 1288 | 2022 | 2022-08-20 | 03/24/2022 | 2532.04 | 0 | 2022-08-19 |  | 1
2024 | Region III | BATAAN | ORANI (BATAAN) | P00820210LZ | Construction of Flood Mitigation Structure | 120.5455 | 14.8169 | 96499999.66 | 96499999.66 | 2024 | PASCAL CONSTRUCTION | 1289 | 2024 | 2024-11-22 | 04/22/2024 | 0 | 0 | 2024-12-16 | 24
2023 | Region I | ILOCOS NORTE | BACARRA (ILOCOS NORTE) | P00737410LZ | Rehabilitation / Major Repair of Drainage Structure | 120.6225 | 18.2473 | 4949912.99 | 4949034.71 | 2023 | BJMJB CONSTRUCTION & SUPPLY | 1290 | 2023 | 2023-04-18 | 02/06/2023 | 878.28 | 0 | 2023-05-14 | 26
2022 | Region I | ILOCOS NORTE | NUEVA ERA (ILOCOS NORTE) | P00621611LZ | Construction of Flood Mitigation Structure | 120.6938 | 17.9398 | 48999997.76 | 48999997.76 | 2022 | DJCM CONSTRUCTION CORPORATION (FORMERLY: DJCM CONSTRUCTION) | 1291 | 2022 | 2022-10-13 | 03/25/2022 | 0 | 0 | 2022-10-12 |  | 1
2023 | Region III | PAMPANGA | ANGELES CITY (PAMPANGA) | P00727135LZ | Construction of Slope Protection Structure | 120.6231 | 15.1497 | 39180107.66 | 38075609.36 | 2023 | TOKWING CONSTRUCTION, CORP.(FOR; TOKWING CONSTRUC | 1292 | 2023 | 2023-06-27 | 03/06/2023 | 1104498.3 | 0 | 2023-08-01 | 35
2022 | Region III | PAMPANGA | ANGELES CITY (PAMPANGA) | P00637021LZ | Construction of Slope Protection Structure | 120.5461 | 15.1504 | 72372122.93 | 70651739.38 | 2022 | STRONGLANE BUILDERS AND TRADING CORPORATION (FORMERLY: STRONGLANE CONSTRUCTION & TRADING) | 1293 | 2022 | 2022-10-27 | 03/24/2022 | 1720383.55 | 0 | 2022-10-26 |  | 1
2022 | Cordillera Administrative Region | ABRA | LA PAZ (ABRA) | P00632778LZ | Construction of Flood Mitigation Structure | 120.694 | 17.6802 | 48999964.35 | 49497900 | 2022 | ST. TIMOTHY CONSTRUCTION CORPORATION | 1294 | 2022 | 2022-10-19 | 03/28/2022 | 0 | 497935.65 | 2022-10-08 |  | 11
2023 | Region III | PAMPANGA | SASMUAN (SEXMOAN) (PAMPANGA) | P00727129LZ | Construction of Flood Mitigation Structure | 120.6235 | 14.9402 | 29399446.89 | 29393763.68 | 2023 | R.D. SADSAD CONSTRUCTION & TRADING | 1295 | 2023 | 2023-06-19 | 03/20/2023 | 5683.21 | 0 | 2023-08-15 | 57
2023 | Region III | LA UNION | CITY OF SAN FERNANDO (CAPITAL) (LA UNION) | P00727306LZ | Construction of Flood Mitigation Structure | 120.6943 | 14.9903 | 257255442.4 | 257255490 | 2024 | A.D. GONZALES JR. CONSTRUCTION & TRADING CO. INC. | 1296 | 2023 | 2024-06-05 | 06/12/2023 | 0 | 47.6 | 2024-06-04 |  | 1
2022 | Region III | PAMPANGA | ANGELES CITY (PAMPANGA) | P00631255LZ | Construction of Slope Protection Structure | 120.6239 | 15.1496 | 24498672.13 | 23900621.1 | 2022 | THREE-IN-ONE CONSTRUCTION & TRADING | 1297 | 2022 | 2022-09-11 | 03/24/2022 | 598051.03 | 0 | 2022-09-10 |  | 1
2022 | Region III | BATAAN | SAMAL (BATAAN) | P00632806LZ | Construction of Flood Mitigation Structure | 120.5462 | 14.7538 | 9799999.76 | 9799999.76 | 2022 | M.C.J. VALENZUELA CONSTRUCTION ENTERPRISES | 1298 | 2022 | 2022-10-27 | 05/04/2022 | 0 | 0 | 2022-11-02 | 6
2022 | Region I | PANGASINAN | ROSALES (PANGASINAN) | P00620790LZ | Construction of Flood Mitigation Structure | 120.624 | 15.8919 | 48250000 | 48250000 | 2023 | BET CONSTRUCTION & SUPPLY / AQUINO-DELA CRUZ ENGINEERING & CONSTRUCTION | 1299 | 2022 | 2023-03-07 | 03/22/2022 | 0 | 0 | 2023-03-06 |  | 1
2022 | Region I | ILOCOS NORTE | VINTAR (ILOCOS NORTE) | P00637753LZ | Construction of Flood Mitigation Structure | 120.6946 | 18.2738 | 95040000 | 95039995.11 | 2022 | JCA CONSTRUCTION AND CONSTRUCTION SUPPLY / EGB CONSTRUCTION CORPORATION (FORMERLY: EGB CONSTRUCTION) | 1300 | 2022 | 2022-08-31 | 04/01/2022 | 4.89 | 0 | 2022-11-22 | 83
2022 | Region III | PAMPANGA | ANGELES CITY (PAMPANGA) | P00631262LZ | Construction of Slope Protection Structure | 120.5465 | 15.1506 | 24496581.71 | 23742805.14 | 2022 | N.M.D. CONSTRUCTION & TRADING | 1301 | 2022 | 2022-07-29 | 02/08/2022 | 753776.57 | 0 | 2022-07-28 |  | 1
2023 | Region I | PANGASINAN | ROSALES (PANGASINAN) | P00726369LZ | Construction of Flood Mitigation Structure | 120.624 | 15.8919 | 33775000 | 33773706.21 | 2023 | AQUINO-DELA CRUZ ENGINEERING & CONSTRUCTION | 1302 | 2023 | 2023-10-09 | 04/24/2023 | 1293.79 | 0 | 2023-10-08 |  | 1
2023 | Region III | TARLAC | CITY OF TARLAC (CAPITAL) (TARLAC) | P00726744LZ | Construction of Flood Mitigation Structure | 120.6951 | 15.6087 | 49000000 | 47530899.36 | 2023 | R.R. RICAFORT CONSTRUCTION AND SUPPLIES | 1303 | 2023 | 2023-07-24 | 01/30/2023 | 1469100.64 | 0
2022 | Region III | TARLAC | CONCEPCION (TARLAC) | P00639374LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.6241 | 15.3292 | 96499277.23 | 95657621 | 2022 | 11-16 CONSTRUCTION | 1304 | 2022 | 2022-12-29 | 03/26/2022 | 841656.23 | 0 | 2022-12-28 |  | 1
2023 | Region III | TARLAC | CITY OF TARLAC (CAPITAL) (TARLAC) | P00727289LZ | Construction of Slope Protection Structure | 120.5477 | 15.4651 | 96500000 | 95524711.75 | 2023 | R.R. RICAFORT CONSTRUCTION AND SUPPLIES | 1305 | 2023 | 2023-07-21 | 03/23/2023 | 975288.25 | 0 | 2023-11-20 | 122
2024 | Region III | TARLAC | ANAO (TARLAC) | P00846015LZ | Construction of Slope Protection Structure | 120.6241 | 15.7155 | 44550000 | 45000000 | 2025 | T2B3 BUILDERS AND SUPPLIES CORP. | 1306 | 2024 | 2025-05-14 | 02/27/2024 | 0 | 450000 | 2025-05-13 |  | 1
2022 | Region I | ILOCOS SUR | SALCEDO (BAUGEN) (ILOCOS SUR) | P00621509LZ | Construction of Flood Mitigation Structure | 120.5478 | 17.1458 | 14700000 | 14699994.91 | 2022 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | 1307 | 2022 | 2022-09-16 | 04/04/2022 | 5.09 | 0 | 2022-09-17 | 1
2024 | Region I | ILOCOS NORTE | SARRAT (ILOCOS NORTE) | P00820700LZ | Construction of Flood Mitigation Structure | 120.6244 | 18.092 | 6859906.41 | 6859904.93 | 2024 | BJMJB CONSTRUCTION & SUPPLY | 1308 | 2024 | 2024-06-29 | 02/27/2024 | 1.48 | 0 | 2024-06-28 |  | 1
2023 | Region I | ILOCOS SUR | SALCEDO (BAUGEN) (ILOCOS SUR) | P00727076LZ | Construction of Flood Mitigation Structure | 120.5478 | 17.1458 | 29400000 | 29399996.02 | 2024 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | 1309 | 2023 | 2024-07-08 | 03/22/2023 | 3.98 | 0 | 2023-10-18 |  | 264
2023 | Region III | PAMPANGA | GUAGUA (PAMPANGA) | P00726539LZ | Construction of Flood Mitigation Structure | 120.6244 | 14.9118 | 192999753.4 | 193000000 | 2023 | NORTHERN BUILDERS | 1310 | 2023 | 2023-11-28 | 04/18/2023 | 0 | 246.6 | 2024-05-25 | 179
2024 | Region III | TARLAC | CONCEPCION (TARLAC) | P00838435LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.6954 | 15.3301 | 96499339.15 | 96497825.29 | 2024 | ROYAL CROWN MONARCH CONSTRUCTION & SUPPLIES CORP. | 1311 | 2024 | 2024-06-18 | 02/20/2024 | 1513.86 | 0 | 2024-08-20 | 63
2023 | Region III | TARLAC | VICTORIA (TARLAC) | P00725735LZ | Construction of Flood Mitigation Structure | 120.6954 | 15.6135 | 96500000 | 93605792.49 | 2023 | ROYAL CROWN MONARCH CONSTRUCTION & SUPPLIES CORP. | 1312 | 2023 | 2023-08-18 | 02/06/2023 | 2894207.51 | 0 | 2023-10-06 | 49
2024 | Region I | ILOCOS SUR | SALCEDO (BAUGEN) (ILOCOS SUR) | P00823302LZ | Construction of Flood Mitigation Structure | 120.5478 | 17.1453 | 49000000 | 48249866.9 | 2024 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | 1313 | 2024 | 2024-11-15 | 04/12/2024 | 750133.1 | 0 | 2024-11-18 | 3
2022 | Cordillera Administrative Region | ABRA | LA PAZ (ABRA) | P00621616LZ | Construction of Flood Mitigation Structure | 120.696 | 17.6794 | 48999983.87 | 48997900 | 2022 | 739 BUILDERS | 1314 | 2022 | 2022-11-28 | 06/20/2022 | 2083.87 | 0 | 2022-12-31 | 33
2023 | Region III | PAMPANGA | SASMUAN (SEXMOAN) (PAMPANGA) | P00740362LZ | Rehabilitation / Major Repair of Slope Protection Structure | 120.6245 | 14.9314 | 96499684.4 | 96494018.96 | 2023 | FERDSTAR BUILDERS INC. | 1315 | 2023 | 2023-12-19 | 04/24/2023 | 5665.44 | 0 | 2023-12-18 |  | 1
2022 | Cordillera Administrative Region | ABRA | DOLORES (ABRA) | P00637053LZ | Construction of Flood Mitigation Structure | 120.6961 | 17.6487 | 48999959.67 | 48997500 | 2023 | MG SAMIDAN CONSTRUCTION | 1316 | 2022 | 2023-05-22 | 11/08/2022 | 2459.67 | 0 | 2023-05-21 |  | 1
2024 | Region III | TARLAC | CITY OF TARLAC (CAPITAL) (TARLAC) | P00823412LZ | Construction of Flood Mitigation Structure | 120.5482 | 15.6277 | 144750000 | 144750000 | 2024 | T2B3 BUILDERS AND SUPPLIES CORP. | 1317 | 2024 | 2024-10-18 | 02/23/2024 | 0 | 0 | 2024-12-23 | 66
2022 | Cordillera Administrative Region | ABRA | MANABO (ABRA) | P00631102LZ | Construction of Flood Mitigation Structure | 120.6961 | 17.4443 | 48999996.07 | 49000000 | 2022 | ST. TIMOTHY CONSTRUCTION CORPORATION | 1318 | 2022 | 2022-08-23 | 02/17/2022 | 0 | 3.93 | 2022-08-21 |  | 2
2024 | Region I | PANGASINAN | SAN NICOLAS (PANGASINAN) | P00824659LZ | Construction of Dike | 120.6252 | 16.0137 | 24500000 | 24468214.86 | 2024 | RIVBROS CONSTRUCTION FACTORS & DEVELOPMENT | 1319 | 2024 | 2024-07-22 | 02/26/2024 | 31785.14 | 0 | 2024-08-14 | 23
2023 | Region III | TARLAC | GERONA (TARLAC) | P00736620LZ | Construction of Flood Mitigation Structure | 120.5541 | 15.6179 | 49000000 | 47530047.71 | 2023 | R.R. RICAFORT CONSTRUCTION AND SUPPLIES | 1320 | 2023 | 2023-06-23 | 01/30/2023 | 1469952.29 | 0 | 2023-07-28 | 35
2023 | Region III | PAMPANGA | LUBAO (PAMPANGA) | P00727131LZ | Construction of Slope Protection Structure | 120.5482 | 14.9242 | 29399894.48 | 29393966.78 | 2023 | ARROW CONSTRUCTION | 1321 | 2023 | 2023-10-30 | 03/20/2023 | 5927.7 | 0 | 2023-10-29 |  | 1
2023 | Cordillera Administrative Region | ABRA | TAYUM (ABRA) | P00726393LZ | Construction of Flood Mitigation Structure | 120.6965 | 17.6282 | 96499890.55 | 96499891 | 2023 | MG SAMIDAN CONSTRUCTION | 1322 | 2023 | 2023-06-28 | 03/30/2023 | 0 | 0.45 | 2023-11-15 | 140
2024 | Region III | PAMPANGA | LUBAO (PAMPANGA) | P00820835LZ | Construction of Slope Protection Structure | 120.5545 | 14.9661 | 24499293.41 | 24492340.56 | 2024 | MCB ZAMORA CONSTRUCTION & SUPPLY | 1323 | 2024 | 2024-05-28 | 02/19/2024 | 6952.85 | 0 | 2024-07-16 | 49
2024 | Region III | TARLAC | RAMOS (TARLAC) | P00820862LZ | Construction of Slope Protection Structure | 120.6254 | 15.6878 | 49000000 | 50000000 | 2024 | GJE BUILDERS CORPORATION (FORMERLY: GJE BUILDERS) | 1324 | 2024 | 2024-07-24 | 01/26/2024 | 0 | 1000000 | 2024-07-23 |  | 1
2022 | Region I | ILOCOS NORTE | NUEVA ERA (ILOCOS NORTE) | P00621607LZ | Construction of Flood Mitigation Structure | 120.6966 | 17.9376 | 48999997.76 | 48999997.76 | 2022 | ALPHA & OMEGA GEN. CONTRACTOR & DEVELOPMENT CORP. | 1325 | 2022 | 2022-12-07 | 03/25/2022 | 0 | 0 | 2022-12-11 | 4
2024 | Region III | BATAAN | PILAR (BATAAN) | P00820200LZ | Construction of Flood Mitigation Structure | 120.5497 | 14.6444 | 29400000 | 28950000 | 2024 | RAM BUILDERS & TRADING | 1326 | 2024 | 2024-08-28 | 03/15/2024 | 450000 | 0 | 2024-08-27 |  | 1
2024 | Region III | TARLAC | CITY OF TARLAC (CAPITAL) (TARLAC) | P00821238LZ | Construction of Flood Mitigation Structure | 120.6254 | 15.6878 | 96500000 | 99000000 | 2024 | TRICHES CONSTRUCTION & TRADING | 1327 | 2024 | 2024-07-18 | 02/07/2024 | 0 | 2500000 | 2024-10-06 | 80
2022 | Region I | ILOCOS NORTE | NUEVA ERA (ILOCOS NORTE) | P00621609LZ | Construction of Flood Mitigation Structure | 120.6969 | 17.938 | 48999997.76 | 48999997.76 | 2022 | ALPHA & OMEGA GEN. CONTRACTOR & DEVELOPMENT CORP. | 1328 | 2022 | 2022-10-13 | 03/25/2022 | 0 | 0 | 2022-10-12 |  | 1
2021 | Region III | PAMPANGA |  | P00525588LZ | Construction of Slope Protection Structure | 120.555 | 15.1097 | 91578039.15 | 91558129.3 | 2022 | TONKA CONSTRUCTION / FERDSTAR BUILDERS INC. | 1329 | 2021 | 2022-12-11 | 04/11/2022 | 19909.85 | 0 | 2023-01-04 | 24
2023 | Region III | PAMPANGA | LUBAO (PAMPANGA) | P00740617LZ | Construction of Slope Protection Structure | 120.5497 | 14.9105 | 19599864.28 | 19571542.39 | 2023 | TOKWING CONSTRUCTION, CORP.(FOR; TOKWING CONSTRUC | 1330 | 2023 | 2023-11-15 | 06/19/2023 | 28321.89 | 0 | 2023-11-14 |  | 1
2022 | Cordillera Administrative Region | ABRA | BANGUED (CAPITAL) (ABRA) | P00637055LZ | Construction of Flood Mitigation Structure | 120.6265 | 17.5722 | 48999983.5 | 48998000 | 2025 | MG SAMIDAN CONSTRUCTION | 1331 | 2022 | 2025-02-03 | 10/24/2022 | 1983.5 | 0 | 2023-04-27 |  | 648
2023 | Region III | TARLAC | CITY OF TARLAC (CAPITAL) (TARLAC) | P00727287LZ | Construction of Slope Protection Structure | 120.5558 | 15.4659 | 96500000 | 94492060.39 | 2023 | E.L. ANOLIN CONSTRUCTION / T2B3 BUILDERS AND SUPPLIES CORP. | 1332 | 2023 | 2023-11-20 | 03/22/2023 | 2007939.61 | 0 | 2023-11-19 |  | 1
2022 | Region III | PAMPANGA | PORAC (PAMPANGA) | P00620183LZ | Construction of Slope Protection Structure | 120.5501 | 15.1158 | 96113891.43 | 96098491.37 | 2022 | TONKA CONSTRUCTION / FERDSTAR BUILDERS INC. | 1333 | 2022 | 2022-11-16 | 03/07/2022 | 15400.06 | 0 | 2022-11-15 |  | 1
2023 | Region III | TARLAC | VICTORIA (TARLAC) | P00727367LZ | Construction of Slope Protection Structure | 120.6972 | 15.6074 | 49000000 | 47999505.2 | 2023 | AMP 723 CONSTRUCTION CORPORATION (FORMERLY: A.M.P. CONSTRUCTION) / M.M. SERRANO CONSTRUCTION COMPANY | 1334 | 2023 | 2023-09-02 | 03/06/2023 | 1000494.8 | 0 | 2023-09-01 |  | 1
2023 | Region III | PAMPANGA | LUBAO (PAMPANGA) | P00727132LZ | Construction of Slope Protection Structure | 120.5558 | 14.8932 | 39198176.53 | 39193042.59 | 2023 | DMDANAN CONSTRUCTION AND TRADING | 1335 | 2023 | 2023-08-16 | 03/20/2023 | 5133.94 | 0 | 2023-08-15 |  | 1
2024 | Region I | ILOCOS NORTE | LAOAG CITY (CAPITAL) (ILOCOS NORTE) | P00845884LZ | Construction of Drainage Structure | 120.5511 | 18.1595 | 4949913.57 | 4949900.42 | 2024 | ZEDIK BUILDERS | 1336 | 2024 | 2024-09-08 | 06/07/2024 | 13.15 | 0 | 2024-09-07 |  | 1
2024 | Region III | NUEVA ECIJA | GUIMBA (NUEVA ECIJA) | P00823476LZ | Construction of Flood Mitigation Structure | 120.6979 | 15.6198 | 19300000 | 19105042.95 | 2024 | NIÃ‘AS CONSTRUCTION CORP. (FORMERLY: NINA'S CONSTRUCTION AND SUPPLIES) | 1337 | 2024 | 2024-09-20 | 04/01/2024 | 194957.05 | 0 | 2024-09-26 | 6
2024 | Region III | TARLAC | GERONA (TARLAC) | P00823411LZ | Construction of Flood Mitigation Structure | 120.5517 | 15.6237 | 144750000 | 144750000 | 2024 | T2B3 BUILDERS AND SUPPLIES CORP. | 1338 | 2024 | 2024-10-20 | 02/20/2024 | 0 | 0 | 2024-12-20 | 61
2024 | Region III | PAMPANGA | LUBAO (PAMPANGA) | P00820832LZ | Construction of Slope Protection Structure | 120.5558 | 14.893 | 41858551.09 | 41852777.94 | 2024 | V. TRILLANA BUILDERS & TRADING / RADIANS BUILDERS AND SUPPLY CORPORATION | 1339 | 2024 | 2024-08-16 | 02/19/2024 | 5773.15 | 0 | 2024-08-15 |  | 1
2024 | Region III | TARLAC | CITY OF TARLAC (CAPITAL) (TARLAC) | P00824712LZ | Construction of Flood Mitigation Structure | 120.6268 | 15.4554 | 24500000 | 25000000 | 2024 | T2B3 BUILDERS AND SUPPLIES CORP. | 1340 | 2024 | 2024-06-18 | 02/20/2024 | 0 | 500000 | 2024-07-21 | 33
2023 | Region III | PAMPANGA | LUBAO (PAMPANGA) | P00740607LZ | Construction of Slope Protection Structure | 120.5517 | 14.9218 | 48999848.66 | 48986593.16 | 2023 | ARROW CONSTRUCTION | 1341 | 2023 | 2023-11-10 | 05/15/2023 | 13255.5 | 0 | 2023-11-09 |  | 1
2022 | Region I | PANGASINAN | CITY OF URDANETA (PANGASINAN) | P00620469LZ | Construction of Dike | 120.5528 | 15.9747 | 39200000 | 39131477.44 | 2022 | J.G. GARCIA CONSTRUCTION & SUPPLY (FOR: J.G. GARCIA CONST.) | 1342 | 2022 | 2022-07-05 | 02/28/2022 | 68522.56 | 0 | 2022-09-29 | 86
2023 | Region I | ILOCOS NORTE | BACARRA (ILOCOS NORTE) | P00740538LZ | Construction of Slope Protection Structure | 120.6268 | 18.2704 | 4899951.32 | 4899866.03 | 2023 | BJMJB CONSTRUCTION & SUPPLY | 1343 | 2023 | 2023-06-20 | 04/11/2023 | 85.29 | 0 | 2023-08-14 | 55
2021 | Region III | PAMPANGA |  | P00526040LZ | Construction of Flood Mitigation Structure | 120.5568 | 14.9195 | 29399284.76 | 29390737.33 | 2022 | ARROW CONSTRUCTION | 1344 | 2021 | 2022-09-04 | 03/09/2022 | 8547.43 | 0 | 2022-09-03 |  | 1
2024 | Region III | TARLAC | VICTORIA (TARLAC) | P00821243LZ | Construction of Flood Mitigation Structure | 120.6982 | 15.591 | 96500000 | 99000000 | 2024 | ROYAL CROWN MONARCH CONSTRUCTION & SUPPLIES CORP. | 1345 | 2024 | 2024-10-13 | 02/13/2024 | 0 | 2500000 | 2024-10-12 |  | 1
2022 | Region III | PAMPANGA | PORAC (PAMPANGA) | P00620184LZ | Construction of Slope Protection Structure | 120.5578 | 15.1065 | 96210422.74 | 96204248.42 | 2022 | R.D. POLICARPIO & COMPANY INC. | 1346 | 2022 | 2022-11-16 | 03/07/2022 | 6174.32 | 0 | 2022-11-15 |  | 1
2023 | Region III | TARLAC | GERONA (TARLAC) | P00742371LZ | Construction of Slope Protection Structure | 120.5535 | 15.6204 | 49500000 | 49500000 | 2023 | RD8 BUILDERS CORPORATION UNDER THE NAME OF RD8 BUILDERS | 1347 | 2023 | 2023-05-24 | 03/23/2023 | 0 | 0 | 2023-09-18 | 117
2024 | Cordillera Administrative Region | BENGUET | BAGUIO CITY (BENGUET) | P00821132LZ | Construction of Flood Mitigation Structure | 120.5586 | 16.431 | 96500000 | 96500000 | 2024 | GOLDRICH CONSTRUCTION & TRADING | 1348 | 2024 | 2024-07-29 | 02/13/2024 | 0 | 0 | 2024-09-24 | 57
2022 | Region I | ILOCOS NORTE | SARRAT (ILOCOS NORTE) | P00621586LZ | Construction of Flood Mitigation Structure | 120.6273 | 18.1022 | 34299599.62 | 34299595.93 | 2022 | DJCM CONSTRUCTION CORPORATION (FORMERLY: DJCM CONSTRUCTION) | 1349 | 2022 | 2022-12-19 | 08/22/2022 | 3.69 | 0 | 2023-01-11 | 23
2023 | Region III | TARLAC | GERONA (TARLAC) | P00737485LZ | Construction of Flood Mitigation Structure | 120.5536 | 15.6204 | 49500000 | 48483371.91 | 2023 | TRICHES CONSTRUCTION & TRADING / FRAMECON BUILDERS | 1350 | 2023 | 2023-07-18 | 03/09/2023 | 1016628.09 | 0 | 2023-09-04 | 48
2024 | Region III | BATAAN | ORION (BATAAN) | P00820808LZ | Construction of Flood Mitigation Structure | 120.5588 | 14.6245 | 49000000 | 49000000 | 2024 | ORANI CONSTRUCTION AND SUPPLY CORPORATION (FORMERLY:ORANI BUILDERS & SUPPLY) | 1351 | 2024 | 2024-07-17 | 02/21/2024 | 0 | 0 | 2024-09-02 | 47
2023 | Region I | ILOCOS NORTE | CITY OF BATAC (ILOCOS NORTE) | P00727061LZ | Construction of Flood Mitigation Structure | 120.5588 | 18.076 | 30108000 | 30107779.91 | 2024 | MEGAPOLITAN BUILDERS AND CONSTRUCTION SUPPLY | 1352 | 2023 | 2024-02-09 | 06/30/2023 | 220.09 | 0 | 2024-02-08 |  | 1
2022 | Cordillera Administrative Region | ABRA | DOLORES (ABRA) | P00632760LZ | Construction of Flood Mitigation Structure | 120.6985 | 17.6505 | 48999811.47 | 49497200 | 2022 | ST. TIMOTHY CONSTRUCTION CORPORATION | 1353 | 2022 | 2022-10-20 | 02/17/2022 | 0 | 497388.53 | 2022-10-19 |  | 1
2022 | Cordillera Administrative Region | ABRA | LA PAZ (ABRA) | P00632781LZ | Construction of Flood Mitigation Structure | 120.6274 | 17.6309 | 48999974.62 | 49497500 | 2022 | ST. TIMOTHY CONSTRUCTION CORPORATION | 1354 | 2022 | 2022-10-11 | 03/30/2022 | 0 | 497525.38 | 2022-10-10 |  | 1
2022 | Region III | TARLAC | GERONA (TARLAC) | P00620552LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.5541 | 15.6105 | 48131720 | 47531186.78 | 2022 | A.C. SOLIVEN CONSTRUCTION & GENERAL MERCHANDISE | 1355 | 2022 | 2022-07-18 | 03/29/2022 | 600533.22 | 0 | 2022-09-23 | 67
2022 | Region I | ILOCOS NORTE | CITY OF BATAC (ILOCOS NORTE) | P00620930LZ | Construction of Flood Mitigation Structure | 120.559 | 18.0757 | 48250000 | 48249995.97 | 2023 | MEGAPOLITAN BUILDERS AND CONSTRUCTION SUPPLY | 1356 | 2022 | 2023-03-18 | 04/12/2022 | 4.03 | 0 | 2023-03-17 |  | 1
2024 | Region III | TARLAC | VICTORIA (TARLAC) | P00821244LZ | Construction of Flood Mitigation Structure | 120.6985 | 15.5948 | 96500000 | 99000000 | 2024 | ROYAL CROWN MONARCH CONSTRUCTION & SUPPLIES CORP. | 1357 | 2024 | 2024-09-19 | 02/13/2024 | 0 | 2500000 | 2024-10-12 | 23
2024 | Region III | TARLAC | CITY OF TARLAC (CAPITAL) (TARLAC) | P00846019LZ | Construction of Slope Protection Structure | 120.6279 | 15.4579 | 49500000 | 50000000 | 2024 | NORTHERN BUILDERS | 1358 | 2024 | 2024-05-10 | 02/07/2024 | 0 | 500000 | 2024-08-04 | 86
2022 | Region III | TARLAC | CITY OF TARLAC (CAPITAL) (TARLAC) | P00620551LZ | Construction of Flood Mitigation Structure | 120.5592 | 15.4695 | 37571240 | 37120120.86 | 2022 | A.C. SOLIVEN CONSTRUCTION & GENERAL MERCHANDISE | 1359 | 2022 | 2022-07-15 | 01/28/2022 | 451119.14 | 0 | 2022-07-14 |  | 1
2022 | Region III | TARLAC | CONCEPCION (TARLAC) | P00620196LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.6281 | 15.3301 | 57899359.76 | 57899409.79 | 2022 | R.R. RICAFORT CONSTRUCTION AND SUPPLIES | 1360 | 2022 | 2022-10-01 | 02/16/2022 | 0 | 50.03 | 2022-09-30 |  | 1
2024 | Region III | TARLAC | CITY OF TARLAC (CAPITAL) (TARLAC) | P00848629LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.5594 | 15.4449 | 99000000 | 99000000 | 2025 | JUSTBILT BUILDERS | 1361 | 2024 | 2025-01-17 | 02/27/2024 | 0 | 0 | 2025-01-24 | 7
2022 | Region III | TARLAC | CITY OF TARLAC (CAPITAL) (TARLAC) | P00621283LZ | Construction of Slope Protection Structure | 120.5596 | 15.4705 | 96500000 | 93605000 | 2022 | ROYAL CROWN MONARCH CONSTRUCTION & SUPPLIES CORP. | 1362 | 2022 | 2022-11-28 | 03/30/2022 | 2895000 | 0 | 2022-11-27 |  | 1
2022 | Cordillera Administrative Region | ABRA | LA PAZ (ABRA) | P00637060LZ | Construction of Flood Mitigation Structure | 120.6281 | 17.6343 | 48999930.33 | 48997500 | 2023 | MG SAMIDAN CONSTRUCTION | 1363 | 2022 | 2023-07-11 | 12/28/2022 | 2430.33 | 0 | 2023-07-10 |  | 1
2022 | Region III | PAMPANGA | ANGELES CITY (PAMPANGA) | P00637022LZ | Construction of Slope Protection Structure | 120.5597 | 15.157 | 57894554.79 | 57867366.65 | 2022 | NICLEDON CONSTRUCTION / GRACE CONSTRUCTION CORPORATION | 1364 | 2022 | 2022-11-10 | 03/24/2022 | 27188.14 | 0 | 2022-11-09 |  | 1
2021 | Cordillera Administrative Region | BENGUET |  | P00561460LZ | Construction of Flood Mitigation Structure | 120.6281 | 16.6141 | 96495738.04 | 96372298.9 | 2022 | RODEKOM GENERAL CONSTRUCTION AND ENTERPRISE / KALAHAN GENERAL CONSTRUCTION AND SUPPLIES | 1365 | 2021 | 2022-12-08 | 01/07/2022 | 123439.14 | 0 | 2022-12-07 |  | 1
2023 | Region III | PAMPANGA | ANGELES CITY (PAMPANGA) | P00727134LZ | Rehabilitation / Major Repair of Slope Protection Structure | 120.5599 | 15.1571 | 24497740.71 | 24436607.86 | 2023 | AL-B DEVELOPMENT CORPORATION | 1366 | 2023 | 2023-09-04 | 05/08/2023 | 61132.85 | 0 | 2023-09-03 |  | 1
2024 | Region III | TARLAC | CITY OF TARLAC (CAPITAL) (TARLAC) | P00845802LZ | Construction of Slope Protection Structure | 120.6282 | 15.4586 | 49500000 | 50000000 | 2024 | NORTHERN BUILDERS | 1367 | 2024 | 2024-05-10 | 02/12/2024 | 0 | 500000 | 2024-08-09 | 91
2024 | Region III | TARLAC | VICTORIA (TARLAC) | P00821278LZ | Construction of Dike | 120.6986 | 15.5895 | 90606745 | 92954070 | 2024 | T2B3 BUILDERS AND SUPPLIES CORP. / RPV RED MOUNTAIN KONSTRUCT, INC. | 1368 | 2024 | 2024-10-05 | 02/13/2024 | 0 | 2347325 | 2024-10-04 |  | 1
2024 | Region III | TARLAC | CITY OF TARLAC (CAPITAL) (TARLAC) | P00848628LZ | Construction of Flood Mitigation Structure | 120.5599 | 15.4466 | 99000000 | 99000000 | 2025 | JUSTBILT BUILDERS | 1369 | 2024 | 2025-01-17 | 02/27/2024 | 0 | 0 | 2025-01-24 | 7
2024 | Region III | TARLAC | CITY OF TARLAC (CAPITAL) (TARLAC) | P00848627LZ | Construction of Flood Mitigation Structure | 120.5608 | 15.449 | 99000000 | 99000000 | 2025 | JUSTBILT BUILDERS | 1370 | 2024 | 2025-01-17 | 02/27/2024 | 0 | 0 | 2025-01-24 | 7
2022 | Region I | ILOCOS NORTE | CITY OF BATAC (ILOCOS NORTE) | P00620929LZ | Construction of Flood Mitigation Structure | 120.5613 | 18.0759 | 48250000 | 48249996.03 | 2023 | MEGAPOLITAN BUILDERS AND CONSTRUCTION SUPPLY | 1371 | 2022 | 2023-03-18 | 04/12/2022 | 3.97 | 0 | 2023-03-17 |  | 1
2023 | Region I | ILOCOS NORTE | SAN NICOLAS (ILOCOS NORTE) | P00725589LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.5614 | 18.1378 | 193000000 | 192999797.1 | 2023 | BADOC BUILDERS & SUPPLY, INC. (FORMERLY: BADOC BUILDER & SUPPLY / ST. GERRARD CONSTRUCTION GEN. CONTRACTOR & DEVELOPMENT CORP. (FORMERLY:ST. GERRARD CONSTRUCTION) | 1372 | 2023 | 2023-08-17 | 03/30/2023 | 202.9 | 0 | 2024-01-22 | 158
2024 | Region III | TARLAC | GERONA (TARLAC) | P00823410LZ | Construction of Flood Mitigation Structure | 120.5616 | 15.572 | 144750000 | 144750000 | 2024 | T2B3 BUILDERS AND SUPPLIES CORP. | 1373 | 2024 | 2024-12-20 | 02/23/2024 | 0 | 0 | 2024-12-23 | 3
2022 | Region III | TARLAC | CITY OF TARLAC (CAPITAL) (TARLAC) | P00621284LZ | Construction of Slope Protection Structure | 120.5621 | 15.4723 | 96500000 | 93605000 | 2022 | ROYAL CROWN MONARCH CONSTRUCTION & SUPPLIES CORP. | 1374 | 2022 | 2022-11-22 | 03/24/2022 | 2895000 | 0 | 2022-11-21 |  | 1
2024 | Region III | TARLAC | CITY OF TARLAC (CAPITAL) (TARLAC) | P00820859LZ | Construction of Flood Mitigation Structure | 120.5624 | 15.4637 | 44100000 | 44099535.44 | 2024 | A.C. SOLIVEN CONSTRUCTION & GENERAL MERCHANDISE | 1375 | 2024 | 2024-07-19 | 01/26/2024 | 464.56 | 0 | 2024-07-18 |  | 1
2022 | Region III | PAMPANGA | LUBAO (PAMPANGA) | P00620185LZ | Construction of Slope Protection Structure | 120.5627 | 14.9589 | 77199710.56 | 74111721.84 | 2022 | OMICRON CONSTRUCTION | 1376 | 2022 | 2022-07-06 | 03/07/2022 | 3087988.72 | 0 | 2022-10-01 | 87
2023 | Region III | TARLAC | CITY OF TARLAC (CAPITAL) (TARLAC) | P00726745LZ | Construction of Flood Mitigation Structure | 120.563 | 15.4458 | 49000000 | 49000000 | 2023 | A.C. SOLIVEN CONSTRUCTION & GENERAL MERCHANDISE | 1377 | 2023 | 2023-07-29 | 01/30/2023 | 0 | 0 | 2023-07-28 |  | 1
2023 | Cordillera Administrative Region | BENGUET | LA TRINIDAD (CAPITAL) (BENGUET) | P00726406LZ | Construction of Flood Mitigation Structure | 120.563 | 16.4643 | 77200000 | 77190000 | 2023 | MG SAMIDAN CONSTRUCTION / JMJD CONSTRUCTION AND AGGREGATES | 1378 | 2023 | 2023-11-12 | 02/27/2023 | 10000 | 0 | 2023-11-11 |  | 1
2022 | Region I | ILOCOS NORTE | CITY OF BATAC (ILOCOS NORTE) | P00620931LZ | Construction of Flood Mitigation Structure | 120.563 | 18.0766 | 48250000 | 48249997.24 | 2023 | MEGAPOLITAN BUILDERS AND CONSTRUCTION SUPPLY | 1379 | 2022 | 2023-03-18 | 04/12/2022 | 2.76 | 0 | 2023-03-17 |  | 1
2024 | Region III | TARLAC | CITY OF TARLAC (CAPITAL) (TARLAC) | P00820209LZ | Construction of Flood Mitigation Structure | 120.563 | 15.4624 | 90606745 | 92954070 | 2024 | ROYAL CROWN MONARCH CONSTRUCTION & SUPPLIES CORP. | 1380 | 2024 | 2024-09-19 | 02/07/2024 | 0 | 2347325 | 2024-10-06 | 17
2024 | Region III | TARLAC | CITY OF TARLAC (CAPITAL) (TARLAC) | P00821247LZ | Construction of Flood Mitigation Structure | 120.5631 | 15.4603 | 96500000 | 99000000 | 2024 | 1FC DIZON CORP. / A.C. SOLIVEN CONSTRUCTION & GENERAL MERCHANDISE | 1381 | 2024 | 2024-09-19 | 02/22/2024 | 0 | 2500000 | 2024-10-21 | 32
2023 | Region III | TARLAC | CITY OF TARLAC (CAPITAL) (TARLAC) | P00727274LZ | Construction of Flood Mitigation Structure | 120.5631 | 15.4435 | 67550000 | 65522147.96 | 2023 | FLORDES CONSTRUCTION & TRADING CORP. (FORMERLY FLO | 1382 | 2023 | 2023-10-14 | 03/23/2023 | 2027852.04 | 0 | 2023-10-13 |  | 1
2023 | Region I | ILOCOS NORTE | LAOAG CITY (CAPITAL) (ILOCOS NORTE) | P00740559LZ | Construction of Flood Mitigation Structure | 120.5633 | 18.2341 | 48999888.76 | 48999812.73 | 2023 | 11-16 CONSTRUCTION | 1383 | 2023 | 2023-11-20 | 04/12/2023 | 76.03 | 0 | 2024-01-14 | 55
2024 | Region III | TARLAC | CITY OF TARLAC (CAPITAL) (TARLAC) | P00821248LZ | Construction of Flood Mitigation Structure | 120.5635 | 15.4579 | 96500000 | 99000000 | 2024 | GVDPM CONSTRUCTION CORP. (FORMERLY: ZM CONSTRUCTIO | 1384 | 2024 | 2024-09-19 | 02/22/2024 | 0 | 2500000 | 2024-10-21 | 32
2024 | Region III | TARLAC | CITY OF TARLAC (CAPITAL) (TARLAC) | P00821249LZ | Construction of Flood Mitigation Structure | 120.5637 | 15.4555 | 96500000 | 99000000 | 2024 | GVDPM CONSTRUCTION CORP. (FORMERLY: ZM CONSTRUCTIO | 1385 | 2024 | 2024-09-19 | 02/22/2024 | 0 | 2500000 | 2024-10-21 | 32
2022 | Region I | ILOCOS NORTE | CITY OF BATAC (ILOCOS NORTE) | P00620784LZ | Construction of Flood Mitigation Structure | 120.564 | 18.0056 | 77200000 | 77199998.73 | 2023 | MEGAPOLITAN BUILDERS AND CONSTRUCTION SUPPLY | 1386 | 2022 | 2023-01-26 | 04/12/2022 | 1.27 | 0 | 2023-01-25 |  | 1
2022 | Region I | ILOCOS NORTE | CITY OF BATAC (ILOCOS NORTE) | P00620785LZ | Construction of Flood Mitigation Structure | 120.564 | 18.0055 | 77200000 | 77199998.15 | 2023 | MEGAPOLITAN BUILDERS AND CONSTRUCTION SUPPLY | 1387 | 2022 | 2023-01-26 | 04/12/2022 | 1.85 | 0 | 2023-01-25 |  | 1
2023 | Region III | TARLAC | CITY OF TARLAC (CAPITAL) (TARLAC) | P00740374LZ | Construction of Flood Mitigation Structure | 120.5645 | 15.4504 | 96500000 | 94811038.77 | 2023 | A.C. SOLIVEN CONSTRUCTION & GENERAL MERCHANDISE | 1388 | 2023 | 2023-08-15 | 04/11/2023 | 1688961.23 | 0 | 2023-12-09 | 116
2022 | Region I | ILOCOS NORTE | CITY OF BATAC (ILOCOS NORTE) | P00620932LZ | Construction of Flood Mitigation Structure | 120.5648 | 18.0739 | 48250000 | 48249999.86 | 2023 | MEGAPOLITAN BUILDERS AND CONSTRUCTION SUPPLY | 1389 | 2022 | 2023-03-18 | 04/12/2022 | 0.14 | 0 | 2023-03-17 |  | 1
2024 | Cordillera Administrative Region | BENGUET | BAGUIO CITY (BENGUET) | P00821133LZ | Construction of Flood Mitigation Structure | 120.5653 | 16.4298 | 145500000 | 96500000 | 2024 | GOLDRICH CONSTRUCTION & TRADING | 1390 | 2024 | 2024-07-29 | 03/15/2024 | 49000000 | 0 | 2024-11-12 | 106
2024 | Region III | PAMPANGA | ANGELES CITY (PAMPANGA) | P00820849LZ | Construction of Slope Protection Structure | 120.5655 | 15.1564 | 48981179.2 | 48979865.38 | 2024 | NICLEDON CONSTRUCTION | 1391 | 2024 | 2024-04-19 | 02/16/2024 | 1313.82 | 0 | 2024-07-30 | 102
2024 | Region III | PAMPANGA | ANGELES CITY (PAMPANGA) | P00820848LZ | Construction of Slope Protection Structure | 120.5663 | 15.1556 | 48994615.49 | 48988462.52 | 2024 | B-12 CONSTRUCTION AND TRADING CORPORATION | 1392 | 2024 | 2024-07-19 | 03/04/2024 | 6152.97 | 0 | 2024-08-16 | 28
2023 | Region I | ILOCOS NORTE | CITY OF BATAC (ILOCOS NORTE) | P00742262LZ | Construction of Flood Mitigation Structure | 120.5664 | 18.057 | 5940000 | 5940000 | 2023 | MEGAPOLITAN BUILDERS AND CONSTRUCTION SUPPLY | 1393 | 2023 | 2023-09-01 | 03/22/2023 | 0 | 0 | 2023-09-02 | 1
2023 | Region III | TARLAC | CITY OF TARLAC (CAPITAL) (TARLAC) | P00740361LZ | Construction of Flood Mitigation Structure | 120.5666 | 15.5687 | 96500000 | 95530140.96 | 2023 | R.R. RICAFORT CONSTRUCTION AND SUPPLIES | 1394 | 2023 | 2023-09-18 | 04/11/2023 | 969859.04 | 0 | 2023-12-09 | 82
2022 | Region III | TARLAC | CITY OF TARLAC (CAPITAL) (TARLAC) | P00640530LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.5668 | 15.4725 | 24750000 | 24255000 | 2022 | NORTHERN BUILDERS | 1395 | 2022 | 2022-08-24 | 03/24/2022 | 495000 | 0 | 2022-08-23 |  | 1
2024 | Region III | TARLAC | CITY OF TARLAC (CAPITAL) (TARLAC) | P00821595LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.5671 | 15.4744 | 49000000 | 49000000 | 2024 | E.L. ANOLIN CONSTRUCTION | 1396 | 2024 | 2024-10-09 | 04/12/2024 | 0 | 0 | 2024-10-08 |  | 1
2024 | Region IV-B | OCCIDENTAL MINDORO | PALUAN (OCCIDENTAL MINDORO) | P00824743LZ | Construction of Flood Mitigation Structure | 120.5674 | 13.5044 | 9800000 | 9760904.14 | 2024 | KEJAMARENIK CONSTRUCTION & CONSTRUCTION SUPPLIES | 1397 | 2024 | 2024-07-10 | 03/25/2024 | 39095.86 | 0 | 2024-07-09 |  | 1
2023 | Region I | PANGASINAN | CITY OF URDANETA (PANGASINAN) | P00742285LZ | Construction of Drainage Structure | 120.5675 | 15.9695 | 4900000 | 4894253.08 | 2023 | R.F. FLORES CONSTRUCTION (FORMERLY PATRIOT CONSTRU | 1398 | 2023 | 2023-06-13 | 03/31/2023 | 5746.92 | 0 | 2023-06-12 |  | 1
2023 | Region III | TARLAC | CITY OF TARLAC (CAPITAL) (TARLAC) | P00727291LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.5675 | 15.4803 | 96500000 | 96500000 | 2023 | SPYS BUILDERS CORP. (FORMERLY: SPYS BUILDERS) / T2B3 BUILDERS AND SUPPLIES CORP. | 1399 | 2023 | 2023-07-18 | 03/17/2023 | 0 | 0 | 2023-11-14 | 119
2023 | Region III | TARLAC | CONCEPCION (TARLAC) | P00742132LZ | Construction of Slope Protection Structure | 120.5681 | 15.5676 | 58410000 | 57189172.97 | 2023 | T2B3 BUILDERS AND SUPPLIES CORP. | 1400 | 2023 | 2023-08-18 | 06/06/2023 | 1220827.03 | 0 | 2023-12-13 | 117
2022 | Region III | TARLAC | BAMBAN (TARLAC) | P00640532LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.5685 | 15.2633 | 29399533.78 | 29699966.66 | 2022 | RAIK CONSTRUCTION AND DEVELOPMENT CORPORATION (FORMERLY: RAIK CONSTRUCTION AND SUPPLY) | 1401 | 2022 | 2022-08-01 | 03/24/2022 | 0 | 300432.88 | 2022-07-31 |  | 1
2024 | Region I | PANGASINAN | BINALONAN (PANGASINAN) | P00820719LZ | Construction of Revetment | 120.5688 | 16.0801 | 49000000 | 48921063.43 | 2024 | W.J.P. CONSTRUCTION AND SUPPLY | 1402 | 2024 | 2024-03-26 | 02/14/2024 | 78936.57 | 0 | 2024-08-31 | 158
2022 | Region I | ILOCOS NORTE | CITY OF BATAC (ILOCOS NORTE) | P00620933LZ | Construction of Revetment | 120.5694 | 18.0561 | 48250000 | 48250000 | 2022 | MEGAPOLITAN BUILDERS AND CONSTRUCTION SUPPLY | 1403 | 2022 | 2022-07-15 | 04/12/2022 | 0 | 0 | 2022-09-28 | 75
2022 | Region I | ILOCOS NORTE | CITY OF BATAC (ILOCOS NORTE) | P00620934LZ | Construction of Revetment | 120.5696 | 18.056 | 48250000 | 48250000 | 2022 | MEGAPOLITAN BUILDERS AND CONSTRUCTION SUPPLY | 1404 | 2022 | 2022-07-15 | 03/25/2022 | 0 | 0 | 2022-09-10 | 57
2023 | Region III | TARLAC | CONCEPCION (TARLAC) | P00742131LZ | Construction of Slope Protection Structure | 120.5697 | 15.5663 | 60390000 | 59170297.08 | 2023 | RD8 BUILDERS CORPORATION UNDER THE NAME OF RD8 BUILDERS | 1405 | 2023 | 2023-08-18 | 06/06/2023 | 1219702.92 | 0 | 2023-12-16 | 120
2023 | Region I | ILOCOS NORTE | BACARRA (ILOCOS NORTE) | P00725608LZ | Construction of Flood Mitigation Structure | 120.5697 | 18.216 | 58799830.53 | 57899998.72 | 2023 | ZEDIK BUILDERS / MEGAPOLITAN BUILDERS AND CONSTRUCTION SUPPLY | 1406 | 2023 | 2023-08-15 | 03/13/2023 | 899831.81 | 0 | 2023-10-16 | 62
2023 | Region III | TARLAC | CAPAS (TARLAC) | P00726189LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.5701 | 15.3515 | 48999609.39 | 48979796.38 | 2023 | A.C. SOLIVEN CONSTRUCTION & GENERAL MERCHANDISE | 1407 | 2023 | 2023-06-13 | 01/31/2023 | 19813.01 | 0 | 2023-06-25 | 12
2023 | Region III | PAMPANGA | MABALACAT CITY (PAMPANGA) | P00726736LZ | Construction of Flood Mitigation Structure | 120.5705 | 15.2277 | 48992194.73 | 48991583 | 2023 | THREE-IN-ONE CONSTRUCTION & TRADING | 1408 | 2023 | 2023-05-23 | 02/03/2023 | 611.73 | 0 | 2023-07-01 | 39
2025 | Region III | TARLAC | MONCADA (TARLAC) | P00921065LZ | Rehabilitation / Major Repair of Slope Protection Structure | 120.5709 | 15.7165 | 14700000 | 14700000 | 2025 | RD8 BUILDERS CORPORATION UNDER THE NAME OF RD8 BUILDERS | 1409 | 2025 | 2025-04-16 | 01/27/2025 | 0 | 0 | 2025-05-24 | 38
2024 | Region III | PAMPANGA | ANGELES CITY (PAMPANGA) | P00823456LZ | Construction of Flood Mitigation Structure | 120.571 | 15.1458 | 48983729.91 | 48247379.4 | 2024 | B-12 CONSTRUCTION AND TRADING CORPORATION | 1410 | 2024 | 2024-04-30 | 02/12/2024 | 736350.51 | 0 | 2024-08-05 | 97
2023 | Region III | TARLAC | GERONA (TARLAC) | P00726541LZ | Construction of Flood Mitigation Structure | 120.5721 | 15.5633 | 72375000 | 70203784.94 | 2023 | R.R. RICAFORT CONSTRUCTION AND SUPPLIES | 1411 | 2023 | 2023-06-19 | 02/06/2023 | 2171215.06 | 0 | 2023-09-04 | 77
2024 | Region I | ILOCOS NORTE | LAOAG CITY (CAPITAL) (ILOCOS NORTE) | P00825209LZ | Construction of Flood Mitigation Structure | 120.5722 | 18.1827 | 9649127.11 | 9649102.48 | 2024 | RCD GEN. CONTRACTOR & CONSTRUCTION SUPPLY | 1412 | 2024 | 2024-04-18 | 03/04/2024 | 24.63 | 0 | 2024-05-31 | 43
2024 | Region I | PANGASINAN | BINALONAN (PANGASINAN) | P00820718LZ | Construction of Revetment | 120.5725 | 16.0829 | 49000000 | 48950141.11 | 2024 | W.J.P. CONSTRUCTION AND SUPPLY | 1413 | 2024 | 2024-03-26 | 02/14/2024 | 49858.89 | 0 | 2024-08-31 | 158
2023 | Region I | ILOCOS NORTE | BACARRA (ILOCOS NORTE) | P00725607LZ | Construction of Flood Mitigation Structure | 120.5727 | 18.2175 | 58799114.62 | 57899991.3 | 2023 | ZEDIK BUILDERS / MEGAPOLITAN BUILDERS AND CONSTRUCTION SUPPLY | 1414 | 2023 | 2023-08-15 | 03/13/2023 | 899123.32 | 0 | 2023-10-16 | 62
2024 | Region I | ILOCOS NORTE | LAOAG CITY (CAPITAL) (ILOCOS NORTE) | P00821464LZ | Construction of Flood Mitigation Structure | 120.573 | 18.1829 | 9799199.31 | 9799193.74 | 2024 | MEGAPOLITAN BUILDERS AND CONSTRUCTION SUPPLY | 1415 | 2024 | 2024-05-27 | 03/04/2024 | 5.57 | 0 | 2024-05-31 | 4
2022 | Region I | PANGASINAN | CITY OF URDANETA (PANGASINAN) | P00620464LZ | Construction of Dike | 120.5731 | 15.9888 | 44100000 | 43924227.04 | 2022 | R.A. MATIAS CONSTRUCTION AND DEVELOPERS INC. (FORMERLY : R.A. MATIAS CONSTRUCTION AND DEVELOPERS) | 1416 | 2022 | 2022-07-05 | 02/24/2022 | 175772.96 | 0 | 2022-09-05 | 62
2023 | Region I | ILOCOS NORTE | BACARRA (ILOCOS NORTE) | P00726041LZ | Construction of Flood Mitigation Structure | 120.5732 | 18.212 | 48999948.98 | 48999946.32 | 2023 | MEGAPOLITAN BUILDERS AND CONSTRUCTION SUPPLY / TMT CONSTRUCTION | 1417 | 2023 | 2023-08-15 | 02/13/2023 | 2.66 | 0 | 2023-09-11 | 27
2023 | Region I | ILOCOS NORTE | CITY OF BATAC (ILOCOS NORTE) | P00725584LZ | Construction of Revetment | 120.5735 | 18.065 | 19300000 | 19299446.77 | 2023 | MEGAPOLITAN BUILDERS AND CONSTRUCTION SUPPLY | 1418 | 2023 | 2023-12-07 | 03/03/2023 | 553.23 | 0 | 2023-12-06 |  | 1
2023 | Region III | TARLAC | GERONA (TARLAC) | P00726747LZ | Construction of Flood Mitigation Structure | 120.5735 | 15.561 | 49000000 | 48016060.76 | 2023 | A.C. SOLIVEN CONSTRUCTION & GENERAL MERCHANDISE | 1419 | 2023 | 2023-06-19 | 01/30/2023 | 983939.24 | 0 | 2023-07-28 | 39
2022 | Region I | PANGASINAN | BINALONAN (PANGASINAN) | P00620471LZ | Construction of Revetment | 120.5736 | 16.0491 | 29400000 | 28939954.5 | 2022 | W.J.P. CONSTRUCTION AND SUPPLY | 1420 | 2022 | 2022-09-18 | 02/28/2022 | 460045.5 | 0 | 2022-07-19 |  | 61
2023 | Region I | ILOCOS NORTE | BURGOS (ILOCOS NORTE) | P00725614LZ | Construction of Flood Mitigation Structure | 120.5743 | 18.5056 | 97999786.23 | 96499558.61 | 2023 | DJCM CONSTRUCTION CORPORATION (FORMERLY: DJCM CONSTRUCTION) | 1421 | 2023 | 2023-11-15 | 03/13/2023 | 1500227.62 | 0 | 2024-02-21 | 98
2024 | Region III | BATAAN | ORION (BATAAN) | P00820804LZ | Construction of Flood Mitigation Structure | 120.5744 | 14.6428 | 29400000 | 29400000 | 2024 | A.T.P. CONSTRUCTION | 1422 | 2024 | 2024-08-09 | 02/21/2024 | 0 | 0 | 2024-08-10 | 1
2023 | Region III | TARLAC | CITY OF TARLAC (CAPITAL) (TARLAC) | P00727290LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.5745 | 15.4833 | 96500000 | 95733748.94 | 2023 | R.R. RICAFORT CONSTRUCTION AND SUPPLIES | 1423 | 2023 | 2023-11-20 | 03/22/2023 | 766251.06 | 0 | 2023-11-19 |  | 1
2023 | Region III | PAMPANGA | ANGELES CITY (PAMPANGA) | P00727137LZ | Construction of Slope Protection Structure | 120.5745 | 15.1523 | 29397388.52 | 29357041.77 | 2023 | MJBZ BUILDERS AND TRADING | 1424 | 2023 | 2023-05-23 | 03/06/2023 | 40346.75 | 0 | 2023-07-02 | 40
2023 | Region III | PAMPANGA | ANGELES CITY (PAMPANGA) | P00740620LZ | Construction of Drainage Structure | 120.5746 | 15.1522 | 4899809.62 | 4755664.53 | 2023 | QUANTUMWAYS BUILDERS ROAD CONSTRUCTION | 1425 | 2023 | 2023-07-20 | 05/22/2023 | 144145.09 | 0 | 2023-07-19 |  | 1
2023 | Region I | PANGASINAN | BINALONAN (PANGASINAN) | P00726648LZ | Construction of Revetment | 120.5747 | 16.0836 | 49000000 | 48884891.57 | 2023 | W.J.P. CONSTRUCTION AND SUPPLY | 1426 | 2023 | 2023-03-28 | 02/10/2023 | 115108.43 | 0 | 2023-08-28 | 153
2021 | Region III | TARLAC |  | P00526053LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.5749 | 15.5764 | 44100000 | 41894120.84 | 2022 | R-II BUILDERS, INC. | 1427 | 2021 | 2022-09-19 | 03/28/2022 | 2205879.16 | 0 | 2022-09-18 |  | 1
2022 | Region I | ILOCOS NORTE | SAN NICOLAS (ILOCOS NORTE) | P00620779LZ | Construction of Flood Mitigation Structure | 120.575 | 18.1673 | 96500000 | 96499999.74 | 2022 | MEGAPOLITAN BUILDERS AND CONSTRUCTION SUPPLY | 1428 | 2022 | 2022-10-18 | 04/12/2022 | 0.26 | 0 | 2022-11-12 | 25
2024 | Region III | TARLAC | MONCADA (TARLAC) | P00823347LZ | Construction of Slope Protection Structure | 120.5751 | 15.7234 | 29400000 | 28950000 | 2024 | LAMASIA BUILDERS AND SUPPLY CORP. | 1429 | 2024 | 2024-11-15 | 03/11/2024 | 450000 | 0 | 2024-11-14 |  | 1
2023 | Region III | PAMPANGA | MABALACAT CITY (PAMPANGA) | P00740354LZ | Construction of Dike | 120.5752 | 15.2083 | 72367705.78 | 72344716.92 | 2023 | WRO CONST. CORP. / GRACE CONSTRUCTION CORPORATION | 1430 | 2023 | 2023-08-22 | 04/12/2023 | 22988.86 | 0 | 2023-10-07 | 46
2024 | Region III | PAMPANGA | MABALACAT CITY (PAMPANGA) | P00844763LZ | Construction of Flood Mitigation Structure | 120.5754 | 15.2251 | 48992753.92 | 48984910.79 | 2024 | ST. MATTHEW GEN. CONTRACTOR & DEVELOPMENT CORP. | 1431 | 2024 | 2024-10-09 | 04/26/2024 | 7843.13 | 0 | 2024-10-08 |  | 1
2023 | Region III | TARLAC | GERONA (TARLAC) | P00726746LZ | Construction of Flood Mitigation Structure | 120.5754 | 15.5589 | 49000000 | 48019996.41 | 2023 | T2B3 BUILDERS AND SUPPLIES CORP. | 1432 | 2023 | 2023-07-29 | 01/30/2023 | 980003.59 | 0 | 2023-07-28 |  | 1
2023 | Region I | PANGASINAN | BINALONAN (PANGASINAN) | P00726647LZ | Construction of Revetment | 120.5758 | 16.0844 | 49000000 | 48929299.85 | 2023 | W.J.P. CONSTRUCTION AND SUPPLY | 1433 | 2023 | 2023-03-28 | 02/10/2023 | 70700.15 | 0 | 2023-08-28 | 153
2024 | Region III | TARLAC | GERONA (TARLAC) | P00846017LZ | Construction of Flood Mitigation Structure | 120.5761 | 15.5758 | 99000000 | 100000000 | 2024 | RD8 BUILDERS CORPORATION UNDER THE NAME OF RD8 BUILDERS / T2B3 BUILDERS AND SUPPLIES CORP. | 1434 | 2024 | 2024-05-08 | 02/20/2024 | 0 | 1000000 | 2024-10-19 | 164
2023 | Region III | TARLAC | CITY OF TARLAC (CAPITAL) (TARLAC) | P00740370LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.5764 | 15.4831 | 72375000 | 70202319.37 | 2023 | FLORDES CONSTRUCTION & TRADING CORP. (FORMERLY FLO | 1435 | 2023 | 2023-11-09 | 04/12/2023 | 2172680.63 | 0 | 2023-11-08 |  | 1
2023 | Region I | ILOCOS NORTE | SAN NICOLAS (ILOCOS NORTE) | P00727058LZ | Construction of Flood Mitigation Structure | 120.5765 | 18.1391 | 34300000 | 33270657.32 | 2023 | BJMJB CONSTRUCTION & SUPPLY | 1436 | 2023 | 2023-12-13 | 04/24/2023 | 1029342.68 | 0 | 2023-12-13 | 0
2023 | Region III | PAMPANGA | ANGELES CITY (PAMPANGA) | P00727138LZ | Construction of Slope Protection Structure | 120.5767 | 15.1535 | 48789354.31 | 48786956.39 | 2023 | B-12 CONSTRUCTION AND TRADING CORPORATION | 1437 | 2023 | 2023-06-20 | 03/06/2023 | 2397.92 | 0 | 2023-08-01 | 42
2022 | Cordillera Administrative Region | BENGUET | BAGUIO CITY (BENGUET) | P00620991LZ | Construction of Revetment | 120.5768 | 16.3797 | 49000000 | 49000000 | 2023 | GOLDRICH CONSTRUCTION & TRADING | 1438 | 2022 | 2023-01-20 | 04/10/2022 | 0 | 0 | 2023-02-24 | 35
2023 | Region III | TARLAC | GERONA (TARLAC) | P00742370LZ | Construction of Slope Protection Structure | 120.5772 | 15.5753 | 49500000 | 48435773.97 | 2023 | L.S.D. CONSTRUCTION & SUPPLIES | 1439 | 2023 | 2023-06-23 | 03/23/2023 | 1064226.03 | 0 | 2023-09-18 | 87
2022 | Region III | PAMPANGA | MABALACAT CITY (PAMPANGA) | P00631256LZ | Construction of Drainage Structure | 120.5772 | 15.2152 | 24493886.45 | 24472978.8 | 2022 | WNR CONSTRUCTION AND TRADING | 1440 | 2022 | 2022-10-19 | 03/24/2022 | 20907.65 | 0 | 2022-10-18 |  | 1
2023 | Region III | PAMPANGA | GUAGUA (PAMPANGA) | P00740609LZ | Construction of Slope Protection Structure | 120.5777 | 14.9883 | 29399647.5 | 29393286.85 | 2023 | DMDANAN CONSTRUCTION AND TRADING | 1441 | 2023 | 2023-10-19 | 05/08/2023 | 6360.65 | 0 | 2023-10-18 |  | 1
2024 | Region III | TARLAC | PANIQUI (TARLAC) | P00823477LZ | Construction of Drainage Structure | 120.578 | 15.6684 | 144750000 | 144750000 | 2025 | R.R. RICAFORT CONSTRUCTION AND SUPPLIES | 1442 | 2024 | 2025-03-04 | 02/27/2024 | 0 | 0 | 2025-03-03 |  | 1
2022 | Region III | BATAAN | ORION (BATAAN) | P00640514LZ | Construction of Revetment | 120.5781 | 14.6082 | 34300000 | 34650000 | 2023 | ROCKSTEEL CONSTRUCTION AND DEV'T CORPORATION / R.R. ENCABO CONSTRUCTORS INCORPORATED (FORMERLY RR | 1443 | 2022 | 2023-01-25 | 04/08/2022 | 0 | 350000 | 2023-01-24 |  | 1
2023 | Region I | ILOCOS NORTE | BACARRA (ILOCOS NORTE) | P00727042LZ | Construction of Flood Mitigation Structure | 120.5786 | 18.2706 | 48999555.95 | 48999509.81 | 2023 | BJMJB CONSTRUCTION & SUPPLY | 1444 | 2023 | 2023-11-13 | 03/29/2023 | 46.14 | 0 | 2023-12-27 | 44
2023 | Region I | PANGASINAN | BINALONAN (PANGASINAN) | P00726646LZ | Construction of Revetment | 120.5786 | 16.0869 | 49000000 | 48909367.12 | 2023 | W.J.P. CONSTRUCTION AND SUPPLY | 1445 | 2023 | 2023-03-28 | 02/10/2023 | 90632.88 | 0 | 2023-08-28 | 153
2024 | Region I | PANGASINAN | POZORRUBIO (PANGASINAN) | P00820720LZ | Construction of Dike | 120.5787 | 16.0877 | 49000000 | 48926269.37 | 2024 | RANIA CONSTRUCTION AND SUPPLIES / J.G. GARCIA CONSTRUCTION & SUPPLY (FOR: J.G. GARCIA CONST.) | 1446 | 2024 | 2024-04-24 | 02/14/2024 | 73730.63 | 0 | 2024-08-31 | 129
2022 | Region III | BATAAN | MARIVELES (BATAAN) | P00631174LZ | Construction of Flood Mitigation Structure | 120.5788 | 14.4579 | 19962360 | 19760720 | 2022 | R.Z. TIGAS CONSTRUCTION AND TRADING | 1447 | 2022 | 2022-08-08 | 03/14/2022 | 201640 | 0 | 2022-08-07 |  | 1
2023 | Region I | ILOCOS NORTE | BACARRA (ILOCOS NORTE) | P00740547LZ | Construction of Flood Mitigation Structure | 120.579 | 18.2646 | 4899860.53 | 4899700.57 | 2023 | REMAR CONSTRUCTION | 1448 | 2023 | 2023-10-03 | 05/08/2023 | 159.96 | 0 | 2023-10-02 |  | 1
2024 | Region I | PANGASINAN | POZORRUBIO (PANGASINAN) | P00843186LZ | Construction of Revetment | 120.579 | 16.0956 | 86850000 | 86631647.76 | 2024 | R.A. MATIAS CONSTRUCTION AND DEVELOPERS INC. (FORMERLY : R.A. MATIAS CONSTRUCTION AND DEVELOPERS) | 1449 | 2024 | 2024-08-05 | 06/07/2024 | 218352.24 | 0 | 2025-02-28 | 207
2024 | Region I | PANGASINAN | ROSALES (PANGASINAN) | P00821490LZ | Construction of Revetment | 120.5792 | 15.883 | 48250000 | 48248752.17 | 2024 | W.J.P. CONSTRUCTION AND SUPPLY | 1450 | 2024 | 2024-07-15 | 05/03/2024 | 1247.83 | 0 | 2024-11-01 | 109
2023 | Region III | PAMPANGA | ANGELES CITY (PAMPANGA) | P00740639LZ | Construction of Drainage Structure | 120.5793 | 15.1363 | 39185560.29 | 38356262.46 | 2023 | MICKAJETTE CONSTRUCTION AND TRADING | 1451 | 2023 | 2023-08-20 | 03/24/2023 | 829297.83 | 0 | 2023-08-19 |  | 1
2022 | Cordillera Administrative Region | ABRA | LA PAZ (ABRA) | P00637010LZ | Construction of Flood Mitigation Structure | 120.6282 | 17.6319 | 96499974.86 | 92109279.07 | 2023 | 739 BUILDERS | 1452 | 2022 | 2023-10-01 | 12/28/2022 | 4390695.79 | 0 | 2023-09-30 |  | 1
2022 | Cordillera Administrative Region | ABRA | LA PAZ (ABRA) | P00632782LZ | Construction of Flood Mitigation Structure | 120.6282 | 17.632 | 49000000 | 48997500 | 2022 | ST. TIMOTHY CONSTRUCTION CORPORATION | 1453 | 2022 | 2022-07-21 | 01/07/2022 | 2500 | 0 | 2022-07-20 |  | 1
2024 | Region IV-A | BATANGAS | LIAN (BATANGAS) | P00845819LZ | Construction of Flood Mitigation Structure | 120.6284 | 14.0554 | 148500000 | 148500000 | 2024 | V.R. PATRON BUILDERS & DEVELOPERS CORP. (PREVIOUSL | 1454 | 2024 | 2024-11-15 | 08/07/2024 | 0 | 0 | 2025-07-01 | 228
2025 | Region III | TARLAC | RAMOS (TARLAC) | P00920485LZ | Construction of Flood Mitigation Structure | 120.6284 | 15.6828 | 72375000 | 70167867.76 | 2025 | ROYAL CROWN MONARCH CONSTRUCTION & SUPPLIES CORP. | 1455 | 2025 | 2025-04-18 | 02/11/2025 | 2207132.24 | 0 | 2025-09-09 | 144
2022 | Cordillera Administrative Region | ABRA | LA PAZ (ABRA) | P00637063LZ | Construction of Flood Mitigation Structure | 120.6287 | 17.6343 | 48999918.22 | 48997500 | 2023 | MG SAMIDAN CONSTRUCTION | 1456 | 2022 | 2023-06-05 | 12/28/2022 | 2418.22 | 0 | 2023-07-10 | 35
2024 | Region III | TARLAC | CITY OF TARLAC (CAPITAL) (TARLAC) | P00820860LZ | Construction of Flood Mitigation Structure | 120.6287 | 15.4607 | 44100000 | 45000000 | 2024 | A.C. SOLIVEN CONSTRUCTION & GENERAL MERCHANDISE | 1457 | 2024 | 2024-05-18 | 01/26/2024 | 0 | 900000 | 2024-07-18 | 61
2024 | Region III | TARLAC | CITY OF TARLAC (CAPITAL) (TARLAC) | P00838535LZ | Construction of Slope Protection Structure | 120.6292 | 15.4614 | 49000000 | 50000000 | 2024 | FLORDES CONSTRUCTION & TRADING CORP. (FORMERLY FLO | 1458 | 2024 | 2024-09-03 | 01/26/2024 | 0 | 1000000 | 2024-09-02 |  | 1
2023 | Region IV-A | BATANGAS | NASUGBU (BATANGAS) | P00726550LZ | Rehabilitation / Major Repair of Slope Protection Structure | 120.6295 | 14.0556 | 67550000 | 67500651.86 | 2023 | V.R. PATRON BUILDERS & DEVELOPERS CORP. (PREVIOUSL | 1459 | 2023 | 2023-09-19 | 03/24/2023 | 49348.14 | 0 | 2023-11-17 | 59
2023 | Region I | ILOCOS NORTE | VINTAR (ILOCOS NORTE) | P00725645LZ | Construction of Flood Mitigation Structure | 120.6296 | 18.238 | 62724665.91 | 62720200.89 | 2023 | ST. MATTHEW GEN. CONTRACTOR & DEVELOPMENT CORP. / HEKLER BUILDERS CORP. | 1460 | 2023 | 2023-12-15 | 03/13/2023 | 4465.02 | 0 | 2023-12-15 | 0
2024 | Region III | PAMPANGA | MAGALANG (PAMPANGA) | P00846009LZ | Construction of Flood Mitigation Structure | 120.6301 | 15.2541 | 9889938.72 | 9880733.74 | 2024 | ARROWHEAD CONSTRUCTION | 1461 | 2024 | 2024-08-20 | 04/26/2024 | 9204.98 | 0 | 2024-08-19 |  | 1
2023 | Region III | TARLAC | CITY OF TARLAC (CAPITAL) (TARLAC) | P00727286LZ | Construction of Flood Mitigation Structure | 120.6301 | 15.4617 | 96500000 | 96499308.66 | 2023 | CHIARA2300 INCORPORATED / HIGH STRENGTH DEV. CORPORATION | 1462 | 2023 | 2023-08-18 | 03/17/2023 | 691.34 | 0 | 2023-11-14 | 88
2022 | Region III | PAMPANGA | BACOLOR (PAMPANGA) | P00631233LZ | Construction of Drainage Structure | 120.6308 | 15.0612 | 39200000 | 37228187 | 2022 | REPOLMAN CONSTRUCTION CORP. (FORMERLY: REPOLMAN CONSTRUCTION) / STARDON CONSTRUCTION AND TRADING | 1463 | 2022 | 2022-08-19 | 02/21/2022 | 1971813 | 0 | 2022-08-18 |  | 1
2022 | Region III | PAMPANGA | MABALACAT CITY (PAMPANGA) | P00632841LZ | Construction of Slope Protection Structure | 120.6309 | 15.2549 | 48994185.72 | 48993897.23 | 2022 | M.C.J. VALENZUELA CONSTRUCTION ENTERPRISES | 1464 | 2022 | 2022-08-06 | 02/08/2022 | 288.49 | 0 | 2022-08-05 |  | 1
2023 | Region III | TARLAC | CITY OF TARLAC (CAPITAL) (TARLAC) | P00727285LZ | Construction of Flood Mitigation Structure | 120.6313 | 15.463 | 96500000 | 95495483.68 | 2023 | R.R. RICAFORT CONSTRUCTION AND SUPPLIES | 1465 | 2023 | 2023-11-20 | 03/22/2023 | 1004516.32 | 0 | 2023-11-19 |  | 1
2022 | Region I | ILOCOS NORTE | VINTAR (ILOCOS NORTE) | P00621440LZ | Construction of Flood Mitigation Structure | 120.6316 | 18.2364 | 48999741.48 | 48999741.36 | 2022 | JCA CONSTRUCTION AND CONSTRUCTION SUPPLY | 1466 | 2022 | 2022-11-15 | 04/04/2022 | 0.12 | 0 | 2022-12-19 | 34
2024 | Region IV-B | OCCIDENTAL MINDORO | ABRA DE ILOG (OCCIDENTAL MINDORO) | P00821359LZ | Construction of Flood Mitigation Structure | 120.6318 | 13.3135 | 241249999.9 | 241246624.5 | 2024 | GOLDEN J'S CONSTRUCTION SERVICES | 1467 | 2024 | 2024-11-15 | 03/02/2024 | 3375.4 | 0 | 2025-02-23 | 100
2023 | Region III | TARLAC | CONCEPCION (TARLAC) | P00725736LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.6319 | 15.3313 | 49214647.49 | 49214625.15 | 2023 | A.C. SOLIVEN CONSTRUCTION & GENERAL MERCHANDISE | 1468 | 2023 | 2023-07-03 | 02/07/2023 | 22.34 | 0 | 2023-07-02 |  | 1
2023 | Region III | PAMPANGA | MABALACAT CITY (PAMPANGA) | P00742367LZ | Construction of Slope Protection Structure | 120.6322 | 15.2156 | 19776927.35 | 19769259.83 | 2023 | M.C.J. VALENZUELA CONSTRUCTION ENTERPRISES | 1469 | 2023 | 2023-10-05 | 05/24/2023 | 7667.52 | 0 | 2023-10-04 |  | 1
2023 | Region III | PAMPANGA | MABALACAT CITY (PAMPANGA) | P00740320LZ | Construction of Slope Protection Structure | 120.6322 | 15.2156 | 67547937.63 | 67547874.33 | 2023 | R.D. POLICARPIO & COMPANY INC. | 1470 | 2023 | 2023-11-17 | 05/22/2023 | 63.3 | 0 | 2023-11-16 |  | 1
2024 | Region III | PAMPANGA | MABALACAT CITY (PAMPANGA) | P00838357LZ | Construction of Slope Protection Structure | 120.6322 | 15.2156 | 96483457.97 | 96464724.6 | 2024 | THREE-IN-ONE CONSTRUCTION & TRADING / P.V.B. CONSTRUCTION & TRADING | 1471 | 2024 | 2024-09-11 | 03/14/2024 | 18733.37 | 0 | 2024-10-07 | 26
2022 | Cordillera Administrative Region | ABRA | LA PAZ (ABRA) | P00639322LZ | Construction of Flood Mitigation Structure | 120.6324 | 17.6364 | 96499977.01 | 94102968.15 | 2023 | 739 BUILDERS | 1472 | 2022 | 2023-10-01 | 12/28/2022 | 2397008.86 | 0 | 2023-09-30 |  | 1
2024 | Region I | ILOCOS NORTE | SARRAT (ILOCOS NORTE) | P00820689LZ | Construction of Flood Mitigation Structure | 120.6328 | 18.132 | 19599490.62 | 19599469.7 | 2024 | BJMJB CONSTRUCTION & SUPPLY | 1473 | 2024 | 2024-07-03 | 02/14/2024 | 20.92 | 0 | 2024-07-02 |  | 1
2024 | Region III | TARLAC | SAN JOSE (TARLAC) | P00821237LZ | Construction of Flood Mitigation Structure | 120.633 | 15.6847 | 96500000 | 99000000 | 2024 | TRICHES CONSTRUCTION & TRADING | 1474 | 2024 | 2024-07-18 | 02/07/2024 | 0 | 2500000 | 2024-10-06 | 80
2024 | Region III | TARLAC | RAMOS (TARLAC) | P00820861LZ | Construction of Slope Protection Structure | 120.6331 | 15.6846 | 49000000 | 50000000 | 2024 | GJE BUILDERS CORPORATION (FORMERLY: GJE BUILDERS) | 1475 | 2024 | 2024-07-24 | 01/26/2024 | 0 | 1000000 | 2024-07-23 |  | 1
2024 | Region I | ILOCOS NORTE | PASUQUIN (ILOCOS NORTE) | P00844697LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.6332 | 18.3465 | 19599954.89 | 19599951.64 | 2024 | R.A. PAHATI CONST. & SUPPLY, INC. | 1476 | 2024 | 2024-08-21 | 04/01/2024 | 3.25 | 0 | 2024-09-11 | 21
2022 | Region III | PAMPANGA | GUAGUA (PAMPANGA) | P00639360LZ | Construction of Slope Protection Structure | 120.6333 | 14.9796 | 72374318.55 | 72358811.49 | 2022 | FERDSTAR BUILDERS INC. | 1477 | 2022 | 2022-11-27 | 06/01/2022 | 15507.06 | 0 | 2022-11-26 |  | 1
2022 | Region I | ILOCOS NORTE | SARRAT (ILOCOS NORTE) | P00621587LZ | Construction of Flood Mitigation Structure | 120.6334 | 18.1364 | 34299755.73 | 34299755.73 | 2023 | JCA CONSTRUCTION AND CONSTRUCTION SUPPLY / JOZEN BUILDERS AND CONSTRUCTION SUPPLY CORPORATION | 1478 | 2022 | 2023-03-02 | 04/04/2022 | 0 | 0 | 2023-03-05 | 3
2023 | Region III | PAMPANGA | GUAGUA (PAMPANGA) | P00727130LZ | Construction of Slope Protection Structure | 120.6335 | 14.9791 | 19599212.92 | 18818006.65 | 2023 | CEDAR CONSTRUCTION | 1479 | 2023 | 2023-08-18 | 03/22/2023 | 781206.27 | 0 | 2023-08-17 |  | 1
2023 | Region I | PANGASINAN | ROSALES (PANGASINAN) | P00742279LZ | Construction of Drainage Structure | 120.6336 | 15.8947 | 9800000 | 9669550.35 | 2023 | W.J.P. CONSTRUCTION AND SUPPLY | 1480 | 2023 | 2023-07-07 | 03/31/2023 | 130449.65 | 0 | 2023-07-06 |  | 1
2024 | Region I | PANGASINAN | BALUNGAO (PANGASINAN) | P00824656LZ | Construction of Dike | 120.6341 | 15.8909 | 22540000 | 22481351.38 | 2024 | A.C. SOLIVEN CONSTRUCTION & GENERAL MERCHANDISE | 1481 | 2024 | 2024-07-15 | 02/21/2024 | 58648.62 | 0 | 2024-08-07 | 23
2023 | Region I | ILOCOS NORTE | SARRAT (ILOCOS NORTE) | P00726634LZ | Construction of Flood Mitigation Structure | 120.6341 | 18.1378 | 19599637.27 | 19598647.33 | 2023 | NORTH TECH BUILDERS AND CONSTRUCTION SUPPLY / BJMJB CONSTRUCTION & SUPPLY | 1482 | 2023 | 2023-06-20 | 02/13/2023 | 989.94 | 0 | 2023-08-02 | 43
2024 | Region III | PAMPANGA | GUAGUA (PAMPANGA) | P00823368LZ | Rehabilitation / Major Repair of Slope Protection Structure | 120.6341 | 14.9759 | 96499802.02 | 96494237.11 | 2025 | FERDSTAR BUILDERS INC. | 1483 | 2024 | 2025-01-18 | 05/09/2024 | 5564.91 | 0 | 2025-01-17 |  | 1
2022 | Region III | PAMPANGA | GUAGUA (PAMPANGA) | P00621456LZ | Construction of Slope Protection Structure | 120.6342 | 14.9612 | 48850032.21 | 48842884.77 | 2022 | 11-16 CONSTRUCTION | 1484 | 2022 | 2022-10-09 | 04/13/2022 | 7147.44 | 0 | 2022-10-08 |  | 1
2023 | Region III | PAMPANGA | MABALACAT CITY (PAMPANGA) | P00727136LZ | Construction of Slope Protection Structure | 120.6345 | 15.2569 | 48993983.79 | 48990144.99 | 2023 | MCB ZAMORA CONSTRUCTION & SUPPLY | 1485 | 2023 | 2023-05-22 | 03/06/2023 | 3838.8 | 0 | 2023-08-01 | 71
2023 | Region III | PAMPANGA | MABALACAT CITY (PAMPANGA) | P00742143LZ | Construction of Slope Protection Structure | 120.6345 | 15.2569 | 69286137 | 69284656.96 | 2023 | TRICHES CONSTRUCTION & TRADING / FRAMECON BUILDERS | 1486 | 2023 | 2023-11-11 | 05/16/2023 | 1480.04 | 0 | 2023-11-10 |  | 1
2024 | Region III | PAMPANGA | MAGALANG (PAMPANGA) | P00838530LZ | Construction of Drainage Structure | 120.6345 | 15.2569 | 19585897.93 | 19576592.61 | 2025 | RADIANS BUILDERS AND SUPPLY CORPORATION | 1487 | 2024 | 2025-01-15 | 04/02/2024 | 9305.32 | 0 | 2025-02-05 | 21
2023 | Region I | ILOCOS NORTE | SARRAT (ILOCOS NORTE) | P00726047LZ | Construction of Flood Mitigation Structure | 120.6345 | 18.1281 | 48999871.69 | 48999776.7 | 2023 | NORTH TECH BUILDERS AND CONSTRUCTION SUPPLY | 1488 | 2023 | 2023-08-17 | 02/17/2023 | 94.99 | 0 | 2023-09-18 | 32
2023 | Region I | ILOCOS NORTE | SARRAT (ILOCOS NORTE) | P00726046LZ | Construction of Flood Mitigation Structure | 120.6347 | 18.1385 | 48999623.74 | 48999159.08 | 2023 | MEGAPOLITAN BUILDERS AND CONSTRUCTION SUPPLY | 1489 | 2023 | 2023-07-17 | 02/17/2023 | 464.66 | 0 | 2023-09-18 | 63
2022 | Region III | PAMPANGA | GUAGUA (PAMPANGA) | P00637025LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.6347 | 14.9642 | 96499816.45 | 96489698.91 | 2023 | FERDSTAR BUILDERS INC. / CEDAR CONSTRUCTION | 1490 | 2022 | 2023-02-11 | 04/18/2022 | 10117.54 | 0 | 2023-02-10 |  | 1
2025 | Region III | TARLAC | CITY OF TARLAC (CAPITAL) (TARLAC) | P00941410LZ | Construction of Flood Mitigation Structure | 120.6347 | 15.4786 | 24125000 | 24125000 | 2025 | WHITE OAK CONSTRUCTION & DEVELOPMENT CORP. | 1491 | 2025 | 2025-03-19 | 02/17/2025 | 0 | 0 | 2025-07-19 | 122
2024 | Region III | TARLAC | RAMOS (TARLAC) | P00820864LZ | Construction of Slope Protection Structure | 120.6356 | 15.6864 | 49000000 | 50000000 | 2024 | GJE BUILDERS CORPORATION (FORMERLY: GJE BUILDERS) | 1492 | 2024 | 2024-11-06 | 01/26/2024 | 0 | 1000000 | 2024-11-05 |  | 1
2023 | Region I | PANGASINAN | SAN NICOLAS (PANGASINAN) | P00727335LZ | Construction of Revetment | 120.6356 | 16.0198 | 39200000 | 39113562.58 | 2023 | A.C. SOLIVEN CONSTRUCTION & GENERAL MERCHANDISE | 1493 | 2023 | 2023-09-28 | 03/24/2023 | 86437.42 | 0 | 2023-09-27 |  | 1
2023 | Region I | ILOCOS NORTE | SARRAT (ILOCOS NORTE) | P00726635LZ | Construction of Flood Mitigation Structure | 120.6356 | 18.1239 | 19599772.27 | 19599364.97 | 2023 | A.P.B. CONSTRUCTION | 1494 | 2023 | 2023-06-23 | 02/17/2023 | 407.3 | 0 | 2023-08-06 | 44
2023 | Region I | ILOCOS NORTE | SARRAT (ILOCOS NORTE) | P00726045LZ | Construction of Flood Mitigation Structure | 120.6361 | 18.1232 | 39199668.35 | 39199013.19 | 2023 | CMG JR. BUILDERS | 1495 | 2023 | 2023-06-20 | 02/13/2023 | 655.16 | 0 | 2023-09-01 | 73
2023 | Cordillera Administrative Region | ABRA | LA PAZ (ABRA) | P00740307LZ | Construction of Flood Mitigation Structure | 120.6364 | 17.6332 | 144749894.4 | 144747500 | 2024 | MG SAMIDAN CONSTRUCTION / RM30 PSG CONSTRUCTION CORPORATION | 1496 | 2023 | 2024-06-24 | 11/23/2023 | 2394.4 | 0 | 2024-09-11 | 79
2024 | Region I | ILOCOS NORTE | SARRAT (ILOCOS NORTE) | P00820683LZ | Construction of Flood Mitigation Structure | 120.6366 | 18.1249 | 19599501.89 | 19599501.36 | 2024 | BJMJB CONSTRUCTION & SUPPLY | 1497 | 2024 | 2024-06-25 | 03/01/2024 | 0.53 | 0 | 2024-07-18 | 23
2024 | Region I | ILOCOS NORTE | SARRAT (ILOCOS NORTE) | P00820685LZ | Construction of Flood Mitigation Structure | 120.6368 | 18.1248 | 29399924.1 | 29399919.49 | 2024 | BJMJB CONSTRUCTION & SUPPLY | 1498 | 2024 | 2024-08-13 | 02/27/2024 | 4.61 | 0 | 2024-08-12 |  | 1
2024 | Region III | TARLAC | RAMOS (TARLAC) | P00846014LZ | Construction of Slope Protection Structure | 120.6371 | 15.6844 | 54450000 | 55000000 | 2024 | T2B3 BUILDERS AND SUPPLIES CORP. | 1499 | 2024 | 2024-08-27 | 02/23/2024 | 0 | 550000 | 2024-08-26 |  | 1
2024 | Region III | TARLAC | RAMOS (TARLAC) | P00846010LZ | Construction of Slope Protection Structure | 120.6372 | 15.6772 | 49500000 | 50000000 | 2024 | CDC CONSTRUCTION & SUPPLIES / NIECER TRADING AND BUILDER COMPANY INC. | 1500 | 2024 | 2024-08-10 | 02/16/2024 | 0 | 500000 | 2024-08-13 | 3
2022 | Cordillera Administrative Region | ABRA | BUCAY (ABRA) | P00632771LZ | Construction of Flood Mitigation Structure | 120.7202 | 17.5653 | 48999893.66 | 49498000 | 2023 | 739 BUILDERS | 1501 | 2022 | 2023-02-21 | 06/20/2022 | 0 | 498106.34 | 2023-02-20 |  | 1
2023 | Region I | ILOCOS NORTE | BANGUI (ILOCOS NORTE) | P00727044LZ | Construction of Flood Mitigation Structure | 120.7202 | 18.5002 | 19599851.76 | 19599856.52 | 2023 | ST. MATTHEW GEN. CONTRACTOR & DEVELOPMENT CORP. / HERCULES VENTURES INC. | 1502 | 2023 | 2023-07-24 | 05/18/2023 | 0 | 4.76 | 2023-12-03 | 132
2023 | Region III | BULACAN | HAGONOY (BULACAN) | P00726897LZ | Construction of Revetment | 120.7206 | 14.8159 | 72374954.93 | 72374578.69 | 2023 | M.S. RAMOS CONSTRUCTION INC. (FORMERLY: M.S. RAMOS / 121 CONSTRUCTION CORPORATION (FORMERLY 121 CONSTUC | 1503 | 2023 | 2023-09-07 | 03/14/2023 | 376.24 | 0 | 2024-01-06 | 121
2023 | Region III | NUEVA ECIJA | CUYAPO (NUEVA ECIJA) | P00737468LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.7209 | 15.7421 | 9900000 | 9895000 | 2023 | KEVIN PAUL CONSTRUCTION | 1504 | 2023 | 2023-04-10 | 02/13/2023 | 5000 | 0 | 2023-05-12 | 32
2023 | Region III | PAMPANGA | MAGALANG (PAMPANGA) | P00740356LZ | Construction of Dike | 120.721 | 15.2369 | 72366734.57 | 72308180.47 | 2023 | ALPIZ CONSTRUCTION & DEVELOPMENT CORPORATION | 1505 | 2023 | 2023-11-03 | 05/08/2023 | 58554.1 | 0 | 2023-11-02 |  | 1
2023 | Cordillera Administrative Region | ABRA | BUCAY (ABRA) | P00726395LZ | Construction of Flood Mitigation Structure | 120.7212 | 17.5397 | 96499987.07 | 96500000 | 2024 | MG SAMIDAN CONSTRUCTION | 1506 | 2023 | 2024-01-13 | 04/11/2023 | 0 | 12.93 | 2024-01-12 |  | 1
2023 | Region IV-B | OCCIDENTAL MINDORO | SANTA CRUZ (OCCIDENTAL MINDORO) | P00740422LZ | Construction of Revetment | 120.722 | 13.0697 | 241249999.3 | 241246327.9 | 2024 | ST. MATTHEW GEN. CONTRACTOR & DEVELOPMENT CORP. | 1507 | 2023 | 2024-04-06 | 04/13/2023 | 3671.4 | 0 | 2024-04-05 |  | 1
2022 | Region I | PANGASINAN | TAYUG (PANGASINAN) | P00620964LZ | Construction of Revetment | 120.7225 | 16.0175 | 29400000 | 28959119.49 | 2022 | RIVBROS CONSTRUCTION FACTORS & DEVELOPMENT | 1508 | 2022 | 2022-08-17 | 02/24/2022 | 440880.51 | 0 | 2022-08-11 |  | 6
2022 | Cordillera Administrative Region | ABRA | BUCAY (ABRA) | P00632754LZ | Construction of Flood Mitigation Structure | 120.7227 | 17.5238 | 49499860.24 | 49496925.65 | 2023 | 739 BUILDERS | 1509 | 2022 | 2023-01-26 | 06/15/2022 | 2934.59 | 0 | 2023-01-25 |  | 1
2023 | Region I | ILOCOS NORTE | VINTAR (ILOCOS NORTE) | P00726350LZ | Construction of Flood Mitigation Structure | 120.7227 | 18.3405 | 58799632.98 | 57899818.55 | 2023 | MEGAPOLITAN BUILDERS AND CONSTRUCTION SUPPLY | 1510 | 2023 | 2023-10-12 | 03/13/2023 | 899814.43 | 0 | 2023-10-16 | 4
2022 | Region IV-A | BATANGAS | BALAYAN (BATANGAS) | P00620247LZ | Construction of Flood Mitigation Structure | 120.7231 | 13.9359 | 88142135 | 88142135 | 2022 | ALPHA & OMEGA GEN. CONTRACTOR & DEVELOPMENT CORP. | 1511 | 2022 | 2022-09-19 | 02/23/2022 | 0 | 0 | 2022-10-19 | 30
2023 | Region III | BULACAN | HAGONOY (BULACAN) | P00726896LZ | Construction of Revetment | 120.7231 | 14.8154 | 72374906.57 | 72374651.62 | 2023 | GREAT PACIFIC BUILDERS AND GEN. CONTRACTOR INC. | 1512 | 2023 | 2023-09-28 | 03/14/2023 | 254.95 | 0 | 2024-01-06 | 100
2023 | Region IV-A | BATANGAS | BALAYAN (BATANGAS) | P00725836LZ | Construction of Flood Mitigation Structure | 120.7232 | 13.9361 | 77198760 | 77198760 | 2023 | VICMAR CONSTRUCTION, INC. / FRANDEL CONSTRUCTION AND DEVELOPMENT CORP. | 1513 | 2023 | 2023-12-14 | 04/03/2023 | 0 | 0 | 2023-12-27 | 13
2023 | Cordillera Administrative Region | ABRA | LAGANGILANG (ABRA) | P00726378LZ | Construction of Flood Mitigation Structure | 120.7233 | 17.6249 | 144749975.5 | 144750000 | 2024 | MG SAMIDAN CONSTRUCTION | 1514 | 2023 | 2024-03-12 | 07/04/2023 | 0 | 24.5 | 2024-06-09 | 89
2022 | Region III | TARLAC | CONCEPCION (TARLAC) | P00621163LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.7233 | 15.3336 | 57899344.21 | 57894990.72 | 2022 | HIGH STRENGTH DEV. CORPORATION / T2B3 BUILDERS AND SUPPLIES CORP. | 1515 | 2022 | 2022-10-22 | 03/26/2022 | 4353.49 | 0 | 2022-11-07 | 16
2022 | Cordillera Administrative Region | ABRA | SAN JUAN (ABRA) | P00639435LZ | Construction of Flood Mitigation Structure | 120.7235 | 17.6725 | 48999903.97 | 48998714 | 2022 | ROCK-WBL CONSTRUCTION CORP. (FOR: ROCK-WBL CONSTRUCTION TRADING & SERVICES) | 1516 | 2022 | 2022-08-23 | 06/14/2022 | 1189.97 | 0 | 2022-12-25 | 124
2022 | Cordillera Administrative Region | BENGUET | ITOGON (BENGUET) | P00639444LZ | Construction of Slope Protection Structure | 120.7235 | 16.3577 | 2940000 | 2936230.11 | 2022 | CLEB CONSTRUCTION | 1517 | 2022 | 2022-11-12 | 09/19/2022 | 3769.89 | 0 | 2022-11-11 |  | 1
2023 | Region I | ILOCOS NORTE | MARCOS (ILOCOS NORTE) | P00725585LZ | Construction of Drainage Structure | 120.7236 | 17.9786 | 11580000 | 11234908.42 | 2023 | RCD GEN. CONTRACTOR & CONSTRUCTION SUPPLY | 1518 | 2023 | 2023-05-31 | 03/14/2023 | 345091.58 | 0 | 2023-07-02 | 32
2022 | Cordillera Administrative Region | ABRA | BUCAY (ABRA) | P00632753LZ | Construction of Flood Mitigation Structure | 120.7241 | 17.5254 | 49499923.64 | 49497477.49 | 2023 | 739 BUILDERS | 1519 | 2022 | 2023-01-26 | 06/15/2022 | 2446.15 | 0 | 2023-01-25 |  | 1
2022 | Cordillera Administrative Region | ABRA | BUCAY (ABRA) | P00639438LZ | Construction of Flood Mitigation Structure | 120.7246 | 17.526 | 19599978.46 | 19597172.35 | 2023 | 739 BUILDERS | 1520 | 2022 | 2023-01-10 | 06/20/2022 | 2806.11 | 0 | 2023-01-09 |  | 1
2023 | Region III | BULACAN | HAGONOY (BULACAN) | P00742322LZ | Construction of Flood Mitigation Structure | 120.7246 | 14.8151 | 52469764.51 | 52469994.43 | 2023 | RVR3 CONSTRUCTION SUPPLY AND SERVICES | 1521 | 2023 | 2023-11-21 | 03/27/2023 | 0 | 229.92 | 2023-11-20 |  | 1
2023 | Region I | ILOCOS NORTE | PIDDIG (ILOCOS NORTE) | P00727250LZ | Construction of Flood Mitigation Structure | 120.7251 | 18.2015 | 97465000 | 97464828.98 | 2023 | NORTH TECH BUILDERS AND CONSTRUCTION SUPPLY / SOLID NORTH CONSTRUCTION | 1522 | 2023 | 2023-07-24 | 03/22/2023 | 171.02 | 0 | 2023-10-22 | 90
2024 | Region III | BULACAN | HAGONOY (BULACAN) | P00823357LZ | Construction of Flood Mitigation Structure | 120.726 | 14.8229 | 77199917 | 77194894.02 | 2024 | 11-16 CONSTRUCTION | 1523 | 2024 | 2024-10-24 | 02/28/2024 | 5022.98 | 0 | 2024-10-23 |  | 1
2023 | Cordillera Administrative Region | ABRA | LAGANGILANG (ABRA) | P00727258LZ | Construction of Flood Mitigation Structure | 120.7263 | 17.6093 | 48249882.28 | 48248433 | 2023 | MG SAMIDAN CONSTRUCTION | 1524 | 2023 | 2023-10-07 | 04/04/2023 | 1449.28 | 0 | 2023-10-06 |  | 1
2024 | Region I | PANGASINAN | UMINGAN (PANGASINAN) | P00843199LZ | Construction of Dike | 120.7263 | 15.9129 | 96500000 | 96351208.8 | 2024 | ANORE CONSTRUCTION | 1525 | 2024 | 2024-09-07 | 04/19/2024 | 148791.2 | 0 | 2025-01-26 | 141
2022 | Cordillera Administrative Region | ABRA | SAN JUAN (ABRA) | P00632769LZ | Construction of Flood Mitigation Structure | 120.7265 | 17.6721 | 48999991.51 | 49497111.11 | 2022 | 739 BUILDERS | 1526 | 2022 | 2022-11-28 | 05/31/2022 | 0 | 497119.6 | 2022-12-02 | 4
2022 | Cordillera Administrative Region | BENGUET | BAKUN (BENGUET) | P00639457LZ | Construction of Flood Mitigation Structure | 120.7275 | 16.7769 | 19600000 | 19600000 | 2022 | APAKLO KIN CONSTRUCTION AND ENG'G SERVICES | 1527 | 2022 | 2022-09-30 | 04/17/2022 | 0 | 0 | 2022-12-03 | 64
2023 | Region III | BULACAN | HAGONOY (BULACAN) | P00735987LZ | Construction of Flood Mitigation Structure | 120.7277 | 14.8278 | 77199812.02 | 77199997.92 | 2023 | WAWAO BUILDERS | 1528 | 2023 | 2023-07-03 | 02/13/2023 | 0 | 185.9 | 2023-12-08 | 158
2024 | Region III | TARLAC | CONCEPCION (TARLAC) | P00838444LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.7293 | 15.3004 | 96499524.36 | 96478501.75 | 2024 | STO. CRISTO CONSTRUCTION & TRADING INC. (FOR: STO. CRISTO CONSTRUCTION & TRADING) | 1529 | 2024 | 2024-09-15 | 03/16/2024 | 21022.61 | 0 | 2024-09-14 |  | 1
2023 | Region I | ILOCOS NORTE | VINTAR (ILOCOS NORTE) | P00726351LZ | Construction of Flood Mitigation Structure | 120.7283 | 18.3371 | 48999836.4 | 48216067 | 2023 | KATHA BUILDERS & SUPPLIES INC. | 1530 | 2023 | 2023-10-10 | 03/13/2023 | 783769.4 | 0 | 2023-10-09 |  | 1
2022 | Region I | PANGASINAN | SAN QUINTIN (PANGASINAN) | P00620974LZ | Construction of Revetment | 120.7283 | 15.9544 | 19600000 | 19584259.92 | 2022 | ROGENOX CONSTRUCTION AND SUPPLY CORP. | 1531 | 2022 | 2022-10-15 | 02/24/2022 | 15740.08 | 0 | 2022-07-31 |  | 76
2024 | Region III | TARLAC | LA PAZ (TARLAC) | P00824705LZ | Construction of Dike | 120.7286 | 15.5268 | 46749376.93 | 45300247.26 | 2024 | A.R.T. DWELL LIFESTYLE STORE AND ECO BUILDERS | 1532 | 2024 | 2024-06-25 | 03/23/2024 | 1449129.67 | 0 | 2024-08-17 | 53
2023 | Region I | ILOCOS NORTE | VINTAR (ILOCOS NORTE) | P00725640LZ | Construction of Flood Mitigation Structure | 120.7289 | 18.3339 | 62724846.85 | 62724832.36 | 2023 | KATHA BUILDERS & SUPPLIES INC. | 1533 | 2023 | 2023-10-12 | 04/12/2023 | 14.49 | 0 | 2023-11-27 | 46
2021 | Cordillera Administrative Region | BENGUET |  | P00561461LZ | Construction of Flood Mitigation Structure | 120.7294 | 16.7829 | 96487461.5 | 96500000 | 2023 | TRYST BUILDERS ENTERPRISES / RODEKOM GENERAL CONSTRUCTION AND ENTERPRISE | 1534 | 2021 | 2023-03-15 | 07/02/2021 | 0 | 12538.5 | 2023-01-05 |  | 69
2023 | Region III | BULACAN | HAGONOY (BULACAN) | P00726898LZ | Construction of Revetment | 120.7295 | 14.8165 | 67549507.61 | 67549976.37 | 2023 | DARCY & ANNA BUILDERS & TRADING | 1535 | 2023 | 2023-07-03 | 03/14/2023 | 0 | 468.76 | 2024-01-06 | 187
2023 | Region III | NUEVA ECIJA | GUIMBA (NUEVA ECIJA) | P00742336LZ | Construction of Flood Mitigation Structure | 120.7296 | 15.6502 | 14850000 | 14845001.02 | 2023 | MJ O. BETIS BUILDERS | 1536 | 2023 | 2023-12-02 | 06/06/2023 | 4998.98 | 0 | 2023-12-01 |  | 1
2024 | Region IV-B | OCCIDENTAL MINDORO | ABRA DE ILOG (OCCIDENTAL MINDORO) | P00824737LZ | Construction of Flood Mitigation Structure | 120.7296 | 13.455 | 19600000 | 19511207.94 | 2024 | SIXTEEN ENTERPRISES-CALAPAN BRANCH | 1537 | 2024 | 2024-08-26 | 03/22/2024 | 88792.06 | 0 | 2024-08-25 |  | 1
2024 | Region III | BULACAN | CALUMPIT (BULACAN) | P00844500LZ | Construction of Flood Mitigation Structure | 120.7299 | 14.8932 | 77199806.32 | 77199237.53 | 2024 | IM CONSTRUCTION CORPORATION | 1538 | 2024 | 2024-11-05 | 03/11/2024 | 568.79 | 0 | 2024-11-04 |  | 1
2023 | Region III | BULACAN | CALUMPIT (BULACAN) | P00740585LZ | Construction of Flood Mitigation Structure | 120.73 | 14.8928 | 48999667.96 | 47022470.19 | 2023 | C.E.M. CONSTRUCTION, INC. | 1539 | 2023 | 2023-11-28 | 04/03/2023 | 1977197.77 | 0 | 2023-11-27 |  | 1
2023 | Region III | BULACAN | CALUMPIT (BULACAN) | P00740598LZ | Construction of Flood Mitigation Structure | 120.73 | 14.8919 | 24499722.62 | 24499119.13 | 2023 | SYMS CONSTRUCTION TRADING | 1540 | 2023 | 2023-09-16 | 03/21/2023 | 603.49 | 0 | 2023-09-15 |  | 1
2022 | Cordillera Administrative Region | ABRA | SAN JUAN (ABRA) | P00639325LZ | Construction of Flood Mitigation Structure | 120.7304 | 17.6799 | 96499918.09 | 96495674 | 2022 | ROCK-WBL CONSTRUCTION CORP. (FOR: ROCK-WBL CONSTRUCTION TRADING & SERVICES) / UNIMAX STEEL STRUCTURE AND CONSTRUCTION CORP. | 1541 | 2022 | 2022-08-23 | 05/26/2022 | 4244.09 | 0 | 2023-02-26 | 187
2023 | Region I | PANGASINAN | SAN NICOLAS (PANGASINAN) | P00726831LZ | Construction of Flood Mitigation Structure | 120.7305 | 16.0604 | 67550000 | 67536444.52 | 2023 | R.A. MATIAS CONSTRUCTION AND DEVELOPERS INC. (FORMERLY : R.A. MATIAS CONSTRUCTION AND DEVELOPERS) / ARCINUE COMM'L CORPORATION | 1542 | 2023 | 2023-10-05 | 05/12/2023 | 13555.48 | 0 | 2024-01-19 | 106
2023 | Region III | BULACAN | CALUMPIT (BULACAN) | P00726155LZ | Construction of Flood Mitigation Structure | 120.7305 | 14.8869 | 48999837.9 | 48999319.76 | 2023 | TOPNOTCH CATALYST BUILDERS INC. | 1543 | 2023 | 2023-04-26 | 02/06/2023 | 518.14 | 0 | 2023-10-02 | 159
2023 | Region III | BULACAN | CALUMPIT (BULACAN) | P00727275LZ | Construction of Revetment | 120.7306 | 14.8868 | 72374881.78 | 72374980.21 | 2023 | DARCY & ANNA BUILDERS & TRADING | 1544 | 2023 | 2023-07-03 | 03/14/2023 | 0 | 98.43 | 2024-01-06 | 187
2024 | Region III | TARLAC | CONCEPCION (TARLAC) | P00838445LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.7309 | 15.3 | 96499653.63 | 96461259.27 | 2024 | RAIK CONSTRUCTION AND DEVELOPMENT CORPORATION (FORMERLY: RAIK CONSTRUCTION AND SUPPLY) | 1545 | 2024 | 2024-09-15 | 03/16/2024 | 38394.36 | 0 | 2024-09-14 |  | 1
2022 | Cordillera Administrative Region | ABRA | LAGAYAN (ABRA) | P00637058LZ | Construction of Flood Mitigation Structure | 120.731 | 17.744 | 48999966.62 | 48998000 | 2022 | 739 BUILDERS | 1546 | 2022 | 2022-11-28 | 05/26/2022 | 1966.62 | 0 | 2022-11-27 |  | 1
2022 | Region III | NUEVA ECIJA | CUYAPO (NUEVA ECIJA) | P00640523LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.731 | 15.7379 | 19800000 | 19403996.4 | 2022 | AMP 723 CONSTRUCTION CORPORATION (FORMERLY: A.M.P. CONSTRUCTION) | 1547 | 2022 | 2022-11-24 | 04/08/2022 | 396003.6 | 0 | 2022-12-02 | 8
2024 | Region III | BULACAN | CALUMPIT (BULACAN) | P00845971LZ | Construction of Slope Protection Structure | 120.731 | 14.8851 | 98999760.15 | 98998602.6 | 2024 | TOPNOTCH CATALYST BUILDERS INC. / ONE FRAME CONSTRUCTION INC. | 1548 | 2024 | 2024-12-11 | 05/21/2024 | 1157.55 | 0 | 2025-02-13 | 64
2022 | Region III | TARLAC | CONCEPCION (TARLAC) | P00640534LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.731 | 15.3325 | 48249708.61 | 48342638.69 | 2022 | HIGH STRENGTH DEV. CORPORATION / T2B3 BUILDERS AND SUPPLIES CORP. | 1549 | 2022 | 2022-10-16 | 03/24/2022 | 0 | 92930.08 | 2022-10-15 |  | 1
2023 | Region III | PAMPANGA | MAGALANG (PAMPANGA) | P00727146LZ | Rehabilitation / Major Repair of Slope Protection Structure | 120.7312 | 15.2446 | 29396715.71 | 29381453.57 | 2023 | 3-SIDES BUILDERS & TRADING CORP. | 1550 | 2023 | 2023-10-13 | 06/16/2023 | 15262.14 | 0 | 2023-10-12 |  | 1
2024 | Region III | BULACAN | CALUMPIT (BULACAN) | P00844504LZ | Construction of Flood Mitigation Structure | 120.7317 | 14.889 | 77199843.7 | 77146300.03 | 2024 | TRIPLE 8 CONSTRUCTION & SUPPLY, INC. (FORMERLY TRIPLE 8 CONST. & SUPPLY) | 1551 | 2024 | 2024-11-05 | 03/11/2024 | 53543.67 | 0 | 2024-11-04 |  | 1
2022 | Region III | PAMPANGA | MABALACAT CITY (PAMPANGA) | P00630943LZ | Rehabilitation / Major Repair of Slope Protection Structure | 120.7319 | 15.2469 | 68594579.47 | 67535048.42 | 2022 | SPIDERONE CONSTRUCTION COMPANY LTD. / EGB CONSTRUCTION CORPORATION (FORMERLY: EGB CONSTRUCTION) | 1552 | 2022 | 2022-08-23 | 02/25/2022 | 1059531.05 | 0 | 2022-10-21 | 59
2022 | Region III | PAMPANGA | MABALACAT CITY (PAMPANGA) | P00620546LZ | Construction of Slope Protection Structure | 120.7319 | 15.2469 | 48994980.97 | 48986736.23 | 2022 | THREE-IN-ONE CONSTRUCTION & TRADING | 1553 | 2022 | 2022-10-19 | 03/24/2022 | 8244.74 | 0 | 2022-10-18 |  | 1
2023 | Region III | BULACAN | HAGONOY (BULACAN) | P00737367LZ | Construction of Flood Mitigation Structure | 120.7319 | 14.818 | 59399669.22 | 59399974.1 | 2023 | TOPNOTCH CATALYST BUILDERS INC. / BLACK HARDHAT INC. (FORMERLY: JCHARDHAT INC.) | 1554 | 2023 | 2023-11-29 | 02/13/2023 | 0 | 304.88 | 2023-12-08 | 9
2023 | Region III | BULACAN | CALUMPIT (BULACAN) | P00740584LZ | Construction of Flood Mitigation Structure | 120.732 | 14.8876 | 48999759.07 | 48999930.61 | 2023 | RVR3 CONSTRUCTION SUPPLY AND SERVICES | 1555 | 2023 | 2023-08-31 | 04/03/2023 | 0 | 171.54 | 2023-11-27 | 88
2024 | Region III | BULACAN | HAGONOY (BULACAN) | P00823361LZ | Construction of Flood Mitigation Structure | 120.7322 | 14.8545 | 77199799.22 | 77199973.8 | 2024 | 11-16 CONSTRUCTION | 1556 | 2024 | 2024-11-05 | 03/11/2024 | 0 | 174.58 | 2024-11-04 |  | 1
2022 | Region I | PANGASINAN | UMINGAN (PANGASINAN) | P00631096LZ | Construction of Revetment | 120.7325 | 15.9128 | 49000000 | 48960181.18 | 2022 | RS RODRIGUEZ CONSTRUCTION & SUPPLIES / JHI CONSTRUCTION & SUPPLY | 1557 | 2022 | 2022-10-10 | 03/23/2022 | 39818.82 | 0 | 2022-09-29 |  | 11
2022 | Region I | ILOCOS NORTE | SOLSONA (ILOCOS NORTE) | P00640491LZ | Construction of Flood Mitigation Structure | 120.7326 | 18.098 | 9800000 | 9800000 | 2022 | VCD CONSTRUCTION | 1558 | 2022 | 2022-09-08 | 03/25/2022 | 0 | 0 | 2022-09-07 |  | 1
2022 | Cordillera Administrative Region | ABRA | BUCAY (ABRA) | P00639439LZ | Construction of Flood Mitigation Structure | 120.7327 | 17.5762 | 29399917.48 | 28998220.94 | 2023 | MG SAMIDAN CONSTRUCTION / RM30 PSG CONSTRUCTION CORPORATION | 1559 | 2022 | 2023-07-02 | 01/11/2023 | 401696.54 | 0 | 2023-07-01 |  | 1
2024 | Region III | BULACAN | HAGONOY (BULACAN) | P00844742LZ | Construction of Revetment | 120.733 | 14.8532 | 29399980.74 | 29399600.57 | 2024 | SAMJS CONSTRUCTION SERVICES | 1560 | 2024 | 2024-08-29 | 04/02/2024 | 380.17 | 0 | 2024-08-28 |  | 1
2022 | Cordillera Administrative Region | BENGUET | ATOK (BENGUET) | P00639454LZ | Construction of Flood Mitigation Structure | 120.7333 | 16.5772 | 2940000 | 2934995.04 | 2022 | QPJ GENERAL ENGINEERING CONSTRUCTION AND SUPPLY | 1561 | 2022 | 2022-10-16 | 06/20/2022 | 5004.96 | 0 | 2022-10-15 |  | 1
2023 | Region I | ILOCOS NORTE | VINTAR (ILOCOS NORTE) | P00726352LZ | Construction of Flood Mitigation Structure | 120.734 | 18.3206 | 83087290.78 | 81815539.49 | 2023 | MEGAPOLITAN BUILDERS AND CONSTRUCTION SUPPLY | 1562 | 2023 | 2023-10-12 | 03/13/2023 | 1271751.29 | 0 | 2024-01-22 | 102
2024 | Region III | BULACAN | CALUMPIT (BULACAN) | P00823365LZ | Construction of Flood Mitigation Structure | 120.7342 | 14.8821 | 77199924.6 | 77182692.83 | 2024 | FERDSTAR BUILDERS INC. | 1563 | 2024 | 2024-10-24 | 02/28/2024 | 17231.77 | 0 | 2024-10-23 |  | 1
2024 | Region III | BULACAN | CALUMPIT (BULACAN) | P00838404LZ | Construction of Slope Protection Structure | 120.7346 | 14.9021 | 77199993.39 | 77198007.55 | 2024 | DARCY & ANNA BUILDERS & TRADING | 1564 | 2024 | 2024-10-03 | 02/07/2024 | 1985.84 | 0 | 2024-10-02 |  | 1
2022 | Region IV-B | OCCIDENTAL MINDORO | SANTA CRUZ (OCCIDENTAL MINDORO) | P00632930LZ | Construction of Flood Mitigation Structure | 120.7347 | 13.1631 | 29700000 | 22559787.41 | 2022 | E.R. DELA CRUZ CONSTRUCTION & SUPPLY | 1565 | 2022 | 2022-10-10 | 02/22/2022 | 7140212.59 | 0 | 2022-10-09 |  | 1
2024 | Region III | TARLAC | CONCEPCION (TARLAC) | P00824710LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.735 | 15.2956 | 46750481.51 | 46745172.42 | 2024 | T2B3 BUILDERS AND SUPPLIES CORP. | 1566 | 2024 | 2024-09-30 | 05/07/2024 | 5309.09 | 0 | 2024-09-29 |  | 1
2022 | Cordillera Administrative Region | BENGUET | ITOGON (BENGUET) | P00620995LZ | Construction of Flood Mitigation Structure | 120.7354 | 16.3001 | 24500000 | 24500000 | 2022 | CLIFF CONSTRUCTION & AGGREGATES | 1567 | 2022 | 2022-11-12 | 05/10/2022 | 0 | 0 | 2022-11-11 |  | 1
2023 | Region III | TARLAC | CONCEPCION (TARLAC) | P00725737LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.7361 | 15.3303 | 50179372.68 | 50142663.46 | 2023 | A.C. SOLIVEN CONSTRUCTION & GENERAL MERCHANDISE | 1568 | 2023 | 2023-06-26 | 02/07/2023 | 36709.22 | 0 | 2023-07-03 | 7
2022 | Region I | PANGASINAN | UMINGAN (PANGASINAN) | P00631095LZ | Construction of Revetment | 120.7369 | 15.9178 | 49000000 | 48958847.19 | 2022 | RS RODRIGUEZ CONSTRUCTION & SUPPLIES / JHI CONSTRUCTION & SUPPLY | 1569 | 2022 | 2022-10-10 | 03/23/2022 | 41152.81 | 0 | 2022-09-29 |  | 11
2023 | Region III | BULACAN | CALUMPIT (BULACAN) | P00740595LZ | Construction of Flood Mitigation Structure | 120.7371 | 14.8797 | 48999618.05 | 48995370.37 | 2023 | JAGONBUILD CONSTRUCTION CORP. (FOR. JAGON BUILDERS | 1570 | 2023 | 2023-11-15 | 03/21/2023 | 4247.68 | 0 | 2023-11-14 |  | 1
2022 | Region III | TARLAC | CONCEPCION (TARLAC) | P00639370LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.7375 | 15.2916 | 96499884.74 | 94527725.51 | 2023 | FLORDES CONSTRUCTION & TRADING CORP. (FORMERLY FLO | 1571 | 2022 | 2023-03-15 | 03/26/2022 | 1972159.23 | 0 | 2022-12-08 |  | 97
2024 | Region III | BULACAN | HAGONOY (BULACAN) | P00844509LZ | Construction of Flood Mitigation Structure | 120.7376 | 14.8384 | 67549816.1 | 67549830.35 | 2024 | SYMS CONSTRUCTION TRADING | 1572 | 2024 | 2024-06-11 | 04/18/2024 | 0 | 14.25 | 2024-12-12 | 184
2022 | Region III | TARLAC | LA PAZ (TARLAC) | P00621541LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.7378 | 15.3828 | 19599422.68 | 19191837.84 | 2023 | RAIK CONSTRUCTION AND DEVELOPMENT CORPORATION (FORMERLY: RAIK CONSTRUCTION AND SUPPLY) | 1573 | 2022 | 2023-04-12 | 06/29/2022 | 407584.84 | 0 | 2023-04-11 |  | 1
2024 | Region III | BULACAN | HAGONOY (BULACAN) | P00838411LZ | Construction of Slope Protection Structure | 120.738 | 14.8593 | 77199979.68 | 77194570.6 | 2024 | JUSTBILT BUILDERS | 1574 | 2024 | 2024-12-02 | 02/07/2024 | 5409.08 | 0 | 2024-12-01 |  | 1
2022 | Region III | TARLAC | LA PAZ (TARLAC) | P00640533LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.738 | 15.4049 | 34299837.35 | 34642609.17 | 2022 | N.C. AGUILAR CONST. & SUPPLY INC. / GVDPM CONSTRUCTION CORP. (FORMERLY: ZM CONSTRUCTIO | 1575 | 2022 | 2022-12-28 | 03/24/2022 | 0 | 342771.82 | 2022-12-27 |  | 1
2022 | Region III | TARLAC | LA PAZ (TARLAC) | P00621538LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.738 | 15.379 | 48999441.46 | 48997737.39 | 2023 | TARLAC 3-G CONSTRUCTION & DEVELOPMENT CORPORATION | 1576 | 2022 | 2023-01-03 | 03/24/2022 | 1704.07 | 0 | 2023-01-02 |  | 1
2024 | Region I | PANGASINAN | SAN NICOLAS (PANGASINAN) | P00848606LZ | Construction of Dike | 120.7385 | 16.1061 | 99000000 | 98767177.79 | 2024 | FLORDES CONSTRUCTION & TRADING CORP. (FORMERLY FLO | 1577 | 2024 | 2024-11-15 | 05/14/2024 | 232822.21 | 0 | 2025-02-20 | 97
2023 | Region III | BULACAN | CALUMPIT (BULACAN) | P00726156LZ | Construction of Flood Mitigation Structure | 120.7389 | 14.8743 | 48999773.77 | 48999996.14 | 2023 | TOPNOTCH CATALYST BUILDERS INC. | 1578 | 2023 | 2023-05-04 | 02/06/2023 | 0 | 222.37 | 2023-10-02 | 151
2022 | Region I | PANGASINAN | BALUNGAO (PANGASINAN) | P00621446LZ | Construction of Dike | 120.7392 | 15.9172 | 19600000 | 19579834.04 | 2022 | RS RODRIGUEZ CONSTRUCTION & SUPPLIES | 1579 | 2022 | 2022-12-13 | 04/07/2022 | 20165.96 | 0 | 2022-09-17 |  | 87
2023 | Region III | BULACAN | HAGONOY (BULACAN) | P00726160LZ | Construction of Flood Mitigation Structure | 120.7392 | 14.8398 | 48999866.04 | 48999614.38 | 2023 | E.M. CUERPO, INC. | 1580 | 2023 | 2023-10-03 | 02/06/2023 | 251.66 | 0 | 2023-10-02 |  | 1
2023 | Region III | BULACAN | HAGONOY (BULACAN) | P00735991LZ | Construction of Flood Mitigation Structure | 120.7392 | 14.8398 | 77199801.52 | 77140881.95 | 2023 | WAWAO BUILDERS | 1581 | 2023 | 2023-07-03 | 02/13/2023 | 58919.57 | 0 | 2023-12-08 | 158
2023 | Region III | BULACAN | HAGONOY (BULACAN) | P00735985LZ | Construction of Flood Mitigation Structure | 120.7393 | 14.8401 | 77199734.91 | 77199989.04 | 2023 | WAWAO BUILDERS | 1582 | 2023 | 2023-07-03 | 02/13/2023 | 0 | 254.13 | 2023-12-08 | 158
2022 | Cordillera Administrative Region | ABRA | SAN JUAN (ABRA) | P00639324LZ | Construction of Flood Mitigation Structure | 120.7393 | 17.6862 | 96499925.87 | 96496036 | 2022 | ROCK-WBL CONSTRUCTION CORP. (FOR: ROCK-WBL CONSTRUCTION TRADING & SERVICES) | 1583 | 2022 | 2022-08-23 | 06/20/2022 | 3889.87 | 0 | 2023-03-23 | 212
2023 | Region I | ILOCOS NORTE | VINTAR (ILOCOS NORTE) | P00725639LZ | Construction of Flood Mitigation Structure | 120.7395 | 18.3553 | 62724602.58 | 62724598.75 | 2023 | MEGAPOLITAN BUILDERS AND CONSTRUCTION SUPPLY | 1584 | 2023 | 2023-10-12 | 03/13/2023 | 3.83 | 0 | 2023-12-15 | 64
2023 | Region III | BULACAN | HAGONOY (BULACAN) | P00740377LZ | Construction of Flood Mitigation Structure | 120.7395 | 14.8174 | 144749717.3 | 144749489.9 | 2023 | FLORDES CONSTRUCTION & TRADING CORP. (FORMERLY FLO | 1585 | 2023 | 2023-10-24 | 03/28/2023 | 227.4 | 0 | 2024-03-20 | 148
2023 | Region III | BULACAN | CALUMPIT (BULACAN) | P00735984LZ | Construction of Flood Mitigation Structure | 120.7396 | 14.9037 | 77199881.36 | 77199980.44 | 2023 | WAWAO BUILDERS | 1586 | 2023 | 2023-07-03 | 02/13/2023 | 0 | 99.08 | 2023-12-08 | 158
2024 | Region III | BULACAN | HAGONOY (BULACAN) | P00844506LZ | Construction of Flood Mitigation Structure | 120.7396 | 14.8589 | 77199783.85 | 77192596.4 | 2025 | TRIPLE 8 CONSTRUCTION & SUPPLY, INC. (FORMERLY TRIPLE 8 CONST. & SUPPLY) | 1587 | 2024 | 2025-01-03 | 03/11/2024 | 7187.45 | 0 | 2025-01-03 | 0
2023 | Region III | BULACAN | HAGONOY (BULACAN) | P00735989LZ | Construction of Flood Mitigation Structure | 120.74 | 14.8587 | 77199770.63 | 77199994.01 | 2023 | WAWAO BUILDERS | 1588 | 2023 | 2023-07-03 | 02/13/2023 | 0 | 223.38 | 2023-12-08 | 158
2022 | Region I | PANGASINAN | TAYUG (PANGASINAN) | P00637765LZ | Construction of Drainage Structure | 120.7406 | 16.0281 | 4950000 | 4880078.07 | 2022 | DMGR BUILDERS | 1589 | 2022 | 2022-08-27 | 04/07/2022 | 69921.93 | 0 | 2022-06-27 |  | 61
2023 | Region III | BULACAN | HAGONOY (BULACAN) | P00735986LZ | Construction of Flood Mitigation Structure | 120.741 | 14.8659 | 77199730.36 | 77199987.19 | 2023 | WAWAO BUILDERS | 1590 | 2023 | 2023-07-03 | 02/13/2023 | 0 | 256.83 | 2023-12-08 | 158
2022 | Cordillera Administrative Region | ABRA | SAN JUAN (ABRA) | P00639434LZ | Construction of Flood Mitigation Structure | 120.7412 | 17.6842 | 48249912.79 | 48997532 | 2022 | ROCK-WBL CONSTRUCTION CORP. (FOR: ROCK-WBL CONSTRUCTION TRADING & SERVICES) | 1591 | 2022 | 2022-12-01 | 06/14/2022 | 0 | 747619.21 | 2022-12-25 | 24
2023 | Region III | BULACAN | HAGONOY (BULACAN) | P00726895LZ | Construction of Revetment | 120.7413 | 14.8179 | 72372971.4 | 72372260.41 | 2024 | TRIPLE 8 CONSTRUCTION & SUPPLY, INC. (FORMERLY TRIPLE 8 CONST. & SUPPLY) | 1592 | 2023 | 2024-03-07 | 03/14/2023 | 710.99 | 0 | 2024-03-06 |  | 1
2023 | Region III | TARLAC | LA PAZ (TARLAC) | P00727294LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.7413 | 15.4708 | 96499745.33 | 93594755.18 | 2023 | HIGH STRENGTH DEV. CORPORATION | 1593 | 2023 | 2023-10-19 | 03/17/2023 | 2904990.15 | 0 | 2023-11-14 | 26
2023 | Region III | TARLAC | LA PAZ (TARLAC) | P00727293LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.7416 | 15.4666 | 96499656.21 | 96494805.62 | 2023 | JAM-C BUILDERS / AMP 723 CONSTRUCTION CORPORATION (FORMERLY: A.M.P. CONSTRUCTION) | 1594 | 2023 | 2023-10-19 | 03/17/2023 | 4850.59 | 0 | 2023-12-06 | 48
2023 | Region III | TARLAC | LA PAZ (TARLAC) | P00727292LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.7417 | 15.4494 | 96499749.73 | 96494393.08 | 2023 | NORTHERN BUILDERS | 1595 | 2023 | 2023-09-25 | 03/17/2023 | 5356.65 | 0 | 2023-12-22 | 88
2023 | Region I | ILOCOS NORTE | VINTAR (ILOCOS NORTE) | P00725613LZ | Construction of Flood Mitigation Structure | 120.7417 | 18.3115 | 58799833.23 | 57899479.86 | 2023 | MEGAPOLITAN BUILDERS AND CONSTRUCTION SUPPLY | 1596 | 2023 | 2023-10-12 | 03/13/2023 | 900353.37 | 0 | 2023-12-07 | 56
2024 | Region III | BULACAN | HAGONOY (BULACAN) | P00844505LZ | Construction of Flood Mitigation Structure | 120.7417 | 14.8615 | 77199805.39 | 77195463 | 2024 | TRIPLE 8 CONSTRUCTION & SUPPLY, INC. (FORMERLY TRIPLE 8 CONST. & SUPPLY) | 1597 | 2024 | 2024-11-05 | 03/11/2024 | 4342.39 | 0 | 2024-11-04 |  | 1
2022 | Region IV-A | CAVITE | NAIC (CAVITE) | P00631292LZ | Construction of Flood Mitigation Structure | 120.7419 | 14.3097 | 19599872.23 | 18997097.04 | 2023 | MORTAR MASTERS & CONCRETE BUILDERS | 1598 | 2022 | 2023-10-05 | 02/14/2022 | 602775.19 | 0 | 2023-08-22 |  | 44
2023 | Region III | TARLAC | LA PAZ (TARLAC) | P00727295LZ | Construction of Flood Mitigation Structure | 120.7426 | 15.3826 | 96499644.55 | 96497151.81 | 2023 | ROYAL CROWN MONARCH CONSTRUCTION & SUPPLIES CORP. | 1599 | 2023 | 2023-06-09 | 03/17/2023 | 2492.74 | 0 | 2023-09-15 | 98
2023 | Region III | BULACAN | CALUMPIT (BULACAN) | P00735982LZ | Construction of Flood Mitigation Structure | 120.7429 | 14.9126 | 77199771.87 | 77199991.76 | 2023 | WAWAO BUILDERS | 1600 | 2023 | 2023-07-03 | 02/13/2023 | 0 | 219.89 | 2023-12-08 | 158
2024 | Region III | TARLAC | VICTORIA (TARLAC) | P00846016LZ | Construction of Flood Mitigation Structure | 120.6987 | 15.6003 | 49500000 | 50000000 | 2024 | T2B3 BUILDERS AND SUPPLIES CORP. | 1601 | 2024 | 2024-08-14 | 02/16/2024 | 0 | 500000 | 2024-08-13 |  | 1
2024 | Region III | TARLAC | VICTORIA (TARLAC) | P00821594LZ | Construction of Flood Mitigation Structure | 120.6988 | 15.5986 | 44100000 | 45000000 | 2024 | A.C. SOLIVEN CONSTRUCTION & GENERAL MERCHANDISE | 1602 | 2024 | 2024-06-21 | 01/26/2024 | 0 | 900000 | 2024-07-18 | 27
2022 | Region I | ILOCOS NORTE | NUEVA ERA (ILOCOS NORTE) | P00621596LZ | Construction of Flood Mitigation Structure | 120.6992 | 17.9554 | 48999996.73 | 48999996.73 | 2022 | ST. MATTHEW GEN. CONTRACTOR & DEVELOPMENT CORP. | 1603 | 2022 | 2022-10-13 | 03/25/2022 | 0 | 0 | 2022-10-12 |  | 1
2024 | Region III | TARLAC | VICTORIA (TARLAC) | P00821242LZ | Construction of Flood Mitigation Structure | 120.6992 | 15.5875 | 90606745 | 92954070 | 2024 | ROYAL CROWN MONARCH CONSTRUCTION & SUPPLIES CORP. | 1604 | 2024 | 2024-10-05 | 02/13/2024 | 0 | 2347325 | 2024-10-04 |  | 1
2022 | Region IV-B | OCCIDENTAL MINDORO | MAMBURAO (CAPITAL) (OCCIDENTAL MINDORO) | P00621111LZ | Construction of Flood Mitigation Structure | 120.6994 | 13.1393 | 44100000 | 29761702.43 | 2022 | SIXTEEN ENTERPRISES-CALAPAN BRANCH | 1605 | 2022 | 2022-11-07 | 02/24/2022 | 14338297.57 | 0 | 2022-10-25 |  | 13
2024 | Region III | PAMPANGA | MAGALANG (PAMPANGA) | P00821592LZ | Construction of Slope Protection Structure | 120.6999 | 15.2413 | 48983067.58 | 48967467.66 | 2024 | ALPIZ CONSTRUCTION & DEVELOPMENT CORPORATION | 1606 | 2024 | 2024-05-20 | 02/08/2024 | 15599.92 | 0 | 2024-07-22 | 63
2024 | Region III | NUEVA ECIJA | GUIMBA (NUEVA ECIJA) | P00823433LZ | Construction of Flood Mitigation Structure | 120.7 | 15.6198 | 28950000 | 28660430.44 | 2024 | NIÃ‘AS CONSTRUCTION CORP. (FORMERLY: NINA'S CONSTRUCTION AND SUPPLIES) | 1607 | 2024 | 2024-09-20 | 04/01/2024 | 289569.56 | 0 | 2024-09-26 | 6
2024 | Region III | PAMPANGA | MINALIN (PAMPANGA) | P00820253LZ | Construction of Flood Mitigation Structure | 120.7002 | 14.9451 | 77200000 | 73108547.48 | 2024 | R.D. TALENS CONSTRUCTION AND TRADING | 1608 | 2024 | 2024-12-13 | 03/01/2024 | 4091452.52 | 0 | 2024-12-12 |  | 1
2021 | Cordillera Administrative Region | ABRA |  | P00561513LZ | Construction of Flood Mitigation Structure | 120.7003 | 17.4229 | 48999958.81 | 48998000 | 2022 | PHESCO, INCORPORATED | 1609 | 2021 | 2022-07-21 | 01/07/2022 | 1958.81 | 0 | 2022-07-20 |  | 1
2024 | Region III | PAMPANGA | MACABEBE (PAMPANGA) | P00844761LZ | Construction of Dike | 120.7003 | 14.876 | 9800000 | 9270792.62 | 2024 | N-22 CONSTRUCTION AND TRADING | 1610 | 2024 | 2024-12-10 | 07/31/2024 | 529207.38 | 0 | 2024-12-09 |  | 1
2024 | Region I | ILOCOS SUR | QUIRINO (ANGKAKI) (ILOCOS SUR) | P00838505LZ | Construction of Flood Mitigation Structure | 120.7004 | 17.1162 | 5880000 | 5688635.44 | 2024 | NABANEW CONSTRUCTION AND SUPPLY | 1611 | 2024 | 2024-10-08 | 05/03/2024 | 191364.56 | 0 | 2024-07-07 |  | 93
2022 | Region IV-B | OCCIDENTAL MINDORO | SANTA CRUZ (OCCIDENTAL MINDORO) | P00621105LZ | Construction of Flood Mitigation Structure | 120.7007 | 13.138 | 44100000 | 30638155.99 | 2022 | KEJAMARENIK CONSTRUCTION & CONSTRUCTION SUPPLIES | 1612 | 2022 | 2022-10-12 | 04/08/2022 | 13461844.01 | 0 | 2022-11-17 | 36
2021 | Cordillera Administrative Region | ABRA |  | P00561512LZ | Construction of Flood Mitigation Structure | 120.7007 | 17.4235 | 97999911.98 | 96498000 | 2022 | PHESCO, INCORPORATED | 1613 | 2021 | 2022-10-01 | 12/28/2021 | 1501911.98 | 0 | 2022-09-30 |  | 1
2023 | Region I | ILOCOS NORTE | DINGRAS (ILOCOS NORTE) | P00727059LZ | Rehabilitation / Major Repair of Slope Protection Structure | 120.7008 | 18.1073 | 38600000 | 38599865.84 | 2024 | MEGAPOLITAN BUILDERS AND CONSTRUCTION SUPPLY | 1614 | 2023 | 2024-03-10 | 06/30/2023 | 134.16 | 0 | 2024-03-09 |  | 1
2024 | Region III | TARLAC | CONCEPCION (TARLAC) | P00838436LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.701 | 15.3304 | 96499501.88 | 96494883.37 | 2024 | A.R.T. DWELL LIFESTYLE STORE AND ECO BUILDERS / T2B3 BUILDERS AND SUPPLIES CORP. | 1615 | 2024 | 2024-10-23 | 02/20/2024 | 4618.51 | 0 | 2024-10-22 |  | 1
2022 | Region I | ILOCOS NORTE | DINGRAS (ILOCOS NORTE) | P00637048LZ | Construction of Flood Mitigation Structure | 120.7014 | 18.0695 | 49000000 | 49000000 | 2022 | JLP CONSTRUCTION & SUPPLY (FORMERLY: JLP CONSTRUCT | 1616 | 2022 | 2022-11-07 | 03/25/2022 | 0 | 0 | 2022-12-15 | 38
2022 | Region I | ILOCOS NORTE | VINTAR (ILOCOS NORTE) | P00637763LZ | Construction of Flood Mitigation Structure | 120.7017 | 18.281 | 43559791.2 | 43559717.83 | 2022 | JCA CONSTRUCTION AND CONSTRUCTION SUPPLY | 1617 | 2022 | 2022-10-04 | 03/24/2022 | 73.37 | 0 | 2022-10-03 |  | 1
2021 | Region III | TARLAC |  | P00561539LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.7029 | 15.3663 | 67549246.12 | 67548125.86 | 2023 | STO. CRISTO CONSTRUCTION & TRADING INC. (FOR: STO. CRISTO CONSTRUCTION & TRADING) | 1618 | 2021 | 2023-04-22 | 03/24/2022 | 1120.26 | 0 | 2023-04-21 |  | 1
2022 | Region I | ILOCOS NORTE | VINTAR (ILOCOS NORTE) | P00621443LZ | Construction of Flood Mitigation Structure | 120.7029 | 18.2828 | 48999390.16 | 48998688.75 | 2022 | JCA CONSTRUCTION AND CONSTRUCTION SUPPLY | 1619 | 2022 | 2022-10-10 | 03/24/2022 | 701.41 | 0 | 2022-10-09 |  | 1
2022 | Region I | ILOCOS NORTE | NUEVA ERA (ILOCOS NORTE) | P00621597LZ | Construction of Flood Mitigation Structure | 120.7031 | 17.9537 | 48999997.76 | 48999997.76 | 2022 | ST. TIMOTHY CONSTRUCTION CORPORATION | 1620 | 2022 | 2022-10-13 | 03/25/2022 | 0 | 0 | 2022-10-12 |  | 1
2022 | Region I | ILOCOS NORTE | NUEVA ERA (ILOCOS NORTE) | P00621600LZ | Construction of Flood Mitigation Structure | 120.7032 | 17.954 | 48999997.76 | 48999997.76 | 2022 | ST. TIMOTHY CONSTRUCTION CORPORATION | 1621 | 2022 | 2022-12-07 | 03/25/2022 | 0 | 0 | 2022-12-11 | 4
2023 | Cordillera Administrative Region | ABRA | MANABO (ABRA) | P00726387LZ | Construction of Flood Mitigation Structure | 120.7034 | 17.4443 | 141940493.4 | 144750000 | 2024 | MG SAMIDAN CONSTRUCTION | 1622 | 2023 | 2024-09-12 | 11/23/2023 | 0 | 2809506.6 | 2024-09-11 |  | 1
2023 | Region III | PAMPANGA | MAGALANG (PAMPANGA) | P00740599LZ | Construction of Drainage Structure | 120.7037 | 15.2549 | 19585058.35 | 19583561.5 | 2023 | CMDV CONSTRUCTION | 1623 | 2023 | 2023-09-23 | 06/26/2023 | 1496.85 | 0 | 2023-09-22 |  | 1
2024 | Cordillera Administrative Region | ABRA | LA PAZ (ABRA) | P00824667LZ | Construction of Flood Mitigation Structure | 120.7042 | 17.6962 | 48250000 | 48997499.86 | 2024 | MG SAMIDAN CONSTRUCTION | 1624 | 2024 | 2024-09-18 | 04/17/2024 | 0 | 747499.86 | 2024-09-30 | 12
2024 | Region III | PAMPANGA | MAGALANG (PAMPANGA) | P00823457LZ | Construction of Flood Mitigation Structure | 120.7043 | 15.244 | 43863032.91 | 43422127.93 | 2024 | WNR CONSTRUCTION AND TRADING | 1625 | 2024 | 2024-09-25 | 04/04/2024 | 440904.98 | 0 | 2024-09-24 |  | 1
2022 | Region I | ILOCOS NORTE | VINTAR (ILOCOS NORTE) | P00621441LZ | Construction of Flood Mitigation Structure | 120.7044 | 18.2844 | 48999463.29 | 48999368.12 | 2022 | JCA CONSTRUCTION AND CONSTRUCTION SUPPLY | 1626 | 2022 | 2022-10-10 | 03/24/2022 | 95.17 | 0 | 2022-10-09 |  | 1
2023 | Region III | PAMPANGA | MEXICO (PAMPANGA) | P00725699LZ | Construction of Flood Mitigation Structure | 120.7049 | 15.1197 | 96499804.52 | 96496469.38 | 2023 | A.D. GONZALES JR. CONSTRUCTION & TRADING CO. INC. | 1627 | 2023 | 2023-11-23 | 02/27/2023 | 3335.14 | 0 | 2023-11-22 |  | 1
2021 | Cordillera Administrative Region | ABRA |  | P00561519LZ | Construction of Flood Mitigation Structure | 120.7049 | 17.6789 | 29399855.69 | 29397900 | 2022 | ST. TIMOTHY CONSTRUCTION CORPORATION | 1628 | 2021 | 2022-11-16 | 03/29/2022 | 1955.69 | 0 | 2022-11-15 |  | 1
2023 | Cordillera Administrative Region | ABRA | LAGANGILANG (ABRA) | P00727256LZ | Construction of Flood Mitigation Structure | 120.7051 | 17.4553 | 96499917.08 | 96500000 | 2024 | MG SAMIDAN CONSTRUCTION | 1629 | 2023 | 2024-04-16 | 08/29/2023 | 0 | 82.92 | 2024-04-15 |  | 1
2023 | Cordillera Administrative Region | ABRA | LAGANGILANG (ABRA) | P00727252LZ | Construction of Flood Mitigation Structure | 120.7051 | 17.6762 | 96499963.91 | 96497500 | 2024 | MG SAMIDAN CONSTRUCTION | 1630 | 2023 | 2024-01-10 | 06/14/2023 | 2463.91 | 0 | 2024-01-09 |  | 1
2022 | Cordillera Administrative Region | ABRA | DOLORES (ABRA) | P00639318LZ | Construction of Flood Mitigation Structure | 120.7053 | 17.675 | 96499903.75 | 96500000 | 2023 | ST. TIMOTHY CONSTRUCTION CORPORATION | 1631 | 2022 | 2023-04-21 | 07/20/2022 | 0 | 96.25 | 2023-04-22 | 1
2022 | Region I | ILOCOS NORTE | VINTAR (ILOCOS NORTE) | P00621439LZ | Construction of Flood Mitigation Structure | 120.7053 | 18.2864 | 48999440.19 | 48999395.18 | 2022 | JCA CONSTRUCTION AND CONSTRUCTION SUPPLY | 1632 | 2022 | 2022-10-10 | 03/24/2022 | 45.01 | 0 | 2022-10-09 |  | 1
2023 | Region III | TARLAC | CONCEPCION (TARLAC) | P00740328LZ | Construction of Dike | 120.7054 | 15.272 | 96499240.76 | 96476890.4 | 2023 | ALPHA & OMEGA GEN. CONTRACTOR & DEVELOPMENT CORP. / LAP GLOBAL CONSTRUCTION CORPORATION(FORMERLY LAP GLOBAL CONSTRUCTION) | 1633 | 2023 | 2023-10-24 | 04/04/2023 | 22350.36 | 0 | 2023-11-22 | 29
2024 | Region III | TARLAC | CONCEPCION (TARLAC) | P00824711LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.7055 | 15.3315 | 29399493.93 | 29397276.44 | 2024 | R.R. RICAFORT CONSTRUCTION AND SUPPLIES | 1634 | 2024 | 2024-05-16 | 02/05/2024 | 2217.49 | 0 | 2024-06-28 | 43
2022 | Region I | PANGASINAN | BALUNGAO (PANGASINAN) | P00631099LZ | Construction of Dike | 120.7056 | 15.9028 | 49000000 | 48954297.03 | 2023 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES / RS RODRIGUEZ CONSTRUCTION & SUPPLIES | 1635 | 2022 | 2023-02-25 | 03/14/2022 | 45702.97 | 0 | 2022-09-29 |  | 149
2022 | Cordillera Administrative Region | ABRA | LA PAZ (ABRA) | P00639323LZ | Construction of Flood Mitigation Structure | 120.7056 | 17.6883 | 91406704.68 | 91407703.92 | 2023 | MG SAMIDAN CONSTRUCTION | 1636 | 2022 | 2023-11-17 | 02/15/2023 | 0 | 999.24 | 2023-11-18 | 1
2022 | Cordillera Administrative Region | ABRA | DOLORES (ABRA) | P00637011LZ | Construction of Flood Mitigation Structure | 120.7057 | 17.6705 | 95928688.12 | 95556743.85 | 2023 | MG SAMIDAN CONSTRUCTION | 1637 | 2022 | 2023-11-25 | 02/21/2023 | 371944.27 | 0 | 2023-11-24 |  | 1
2022 | Region I | ILOCOS NORTE | NUEVA ERA (ILOCOS NORTE) | P00621608LZ | Construction of Flood Mitigation Structure | 120.7058 | 17.9307 | 48999996.73 | 48999996.73 | 2022 | ALPHA & OMEGA GEN. CONTRACTOR & DEVELOPMENT CORP. | 1638 | 2022 | 2022-12-07 | 03/25/2022 | 0 | 0 | 2022-12-11 | 4
2022 | Cordillera Administrative Region | ABRA | LA PAZ (ABRA) | P00621275LZ | Construction of Flood Mitigation Structure | 120.7058 | 17.6906 | 91539341.71 | 91539920.25 | 2023 | MG SAMIDAN CONSTRUCTION | 1639 | 2022 | 2023-07-14 | 02/15/2023 | 0 | 578.54 | 2023-11-18 | 127
2022 | Cordillera Administrative Region | ABRA | BUCAY (ABRA) | P00630931LZ | Construction of Flood Mitigation Structure | 120.7059 | 17.4516 | 96499807 | 96498000 | 2022 | PHESCO, INCORPORATED | 1640 | 2022 | 2022-11-10 | 03/24/2022 | 1807 | 0 | 2022-11-09 |  | 1
2022 | Cordillera Administrative Region | ABRA | LA PAZ (ABRA) | P00637012LZ | Construction of Flood Mitigation Structure | 120.706 | 17.6954 | 96499940.76 | 96497500 | 2023 | MG SAMIDAN CONSTRUCTION | 1641 | 2022 | 2023-07-11 | 12/01/2022 | 2440.76 | 0 | 2023-07-19 | 8
2023 | Region I | PANGASINAN | BALUNGAO (PANGASINAN) | P00742281LZ | Construction of Flood Mitigation Structure | 120.7064 | 15.9408 | 14700000 | 14509105.66 | 2023 | JHI CONSTRUCTION & SUPPLY | 1642 | 2023 | 2023-04-27 | 03/31/2023 | 190894.34 | 0 | 2023-08-05 | 100
2022 | Region I | ILOCOS NORTE | NUEVA ERA (ILOCOS NORTE) | P00621595LZ | Construction of Flood Mitigation Structure | 120.7064 | 17.9513 | 48999997.76 | 48999997.76 | 2022 | DJCM CONSTRUCTION CORPORATION (FORMERLY: DJCM CONSTRUCTION) | 1643 | 2022 | 2022-10-27 | 03/25/2022 | 0 | 0 | 2022-10-12 |  | 15
2025 | Region IV-A | BATANGAS | TUY (BATANGAS) | P00941618LZ | Construction of Flood Mitigation Structure | 120.7065 | 13.9969 | 4900000 | 4753000 | 2025 | 830 BUILDERS & DEVELOPERS CORP. | 1644 | 2025 | 2025-05-19 | 03/03/2025 | 147000 | 0 | 2025-06-29 | 41
2022 | Region I | ILOCOS NORTE | NUEVA ERA (ILOCOS NORTE) | P00621601LZ | Construction of Flood Mitigation Structure | 120.7066 | 17.9517 | 48999997.76 | 48999997.76 | 2022 | ST. TIMOTHY CONSTRUCTION CORPORATION | 1645 | 2022 | 2022-10-13 | 03/25/2022 | 0 | 0 | 2022-10-12 |  | 1
2022 | Region I | ILOCOS NORTE | VINTAR (ILOCOS NORTE) | P00639416LZ | Construction of Drainage Structure | 120.7066 | 18.5166 | 49000000 | 48249612.44 | 2023 | JLP CONSTRUCTION & SUPPLY (FORMERLY: JLP CONSTRUCT | 1646 | 2022 | 2023-04-25 | 10/25/2022 | 750387.56 | 0 | 2023-04-25 | 0
2023 | Cordillera Administrative Region | ABRA | LAGAYAN (ABRA) | P00726857LZ | Construction of Flood Mitigation Structure | 120.7078 | 17.7709 | 96499996.55 | 96500000 | 2024 | MG SAMIDAN CONSTRUCTION | 1647 | 2023 | 2024-01-03 | 05/17/2023 | 0 | 3.45 | 2024-01-02 |  | 1
2022 | Region I | ILOCOS NORTE | NUEVA ERA (ILOCOS NORTE) | P00621598LZ | Construction of Flood Mitigation Structure | 120.7082 | 17.948 | 48999997.76 | 48999997.76 | 2022 | ST. TIMOTHY CONSTRUCTION CORPORATION | 1648 | 2022 | 2022-10-13 | 03/25/2022 | 0 | 0 | 2022-10-12 |  | 1
2024 | Region I | ILOCOS SUR | QUIRINO (ANGKAKI) (ILOCOS SUR) | P00838499LZ | Construction of Flood Mitigation Structure | 120.7083 | 17.1417 | 5880000 | 5688855.8 | 2024 | EJIEV CONSTRUCTION SERVICES | 1649 | 2024 | 2024-10-08 | 05/07/2024 | 191144.2 | 0 | 2024-07-11 |  | 89
2022 | Region I | ILOCOS NORTE | NUEVA ERA (ILOCOS NORTE) | P00621599LZ | Construction of Flood Mitigation Structure | 120.7083 | 17.9484 | 48999996.73 | 48999996.73 | 2022 | DJCM CONSTRUCTION CORPORATION (FORMERLY: DJCM CONSTRUCTION) | 1650 | 2022 | 2022-10-13 | 03/25/2022 | 0 | 0 | 2022-10-12 |  | 1
2023 | Region III | NUEVA ECIJA | GUIMBA (NUEVA ECIJA) | P00726732LZ | Construction of Flood Mitigation Structure | 120.7085 | 15.6269 | 49000000 | 48010181.1 | 2023 | R.D. TALENS CONSTRUCTION AND TRADING | 1651 | 2023 | 2023-07-27 | 02/13/2023 | 989818.9 | 0 | 2023-09-09 | 44
2022 | Cordillera Administrative Region | ABRA | LAGAYAN (ABRA) | P00639436LZ | Construction of Flood Mitigation Structure | 120.7086 | 17.7155 | 48999942.25 | 48997999.8 | 2023 | 739 BUILDERS | 1652 | 2022 | 2023-01-27 | 07/25/2022 | 1942.45 | 0 | 2023-01-26 |  | 1
2023 | Region I | ILOCOS NORTE | DINGRAS (ILOCOS NORTE) | P00725595LZ | Construction of Flood Mitigation Structure | 120.7088 | 18.0831 | 48250000 | 48248180.2 | 2024 | AJ TAYLAN CONSTRUCTION CORPORATION | 1653 | 2023 | 2024-01-19 | 02/14/2023 | 1819.8 | 0 | 2024-01-18 |  | 1
2023 | Region I | ILOCOS NORTE | BANGUI (ILOCOS NORTE) | P00735959LZ | Construction of Flood Mitigation Structure | 120.7092 | 18.5186 | 58799832.12 | 57899999.88 | 2023 | DJCM CONSTRUCTION CORPORATION (FORMERLY: DJCM CONSTRUCTION) | 1654 | 2023 | 2023-11-17 | 03/13/2023 | 899832.24 | 0 | 2023-12-07 | 20
2022 | Cordillera Administrative Region | ABRA | DOLORES (ABRA) | P00632757LZ | Construction of Flood Mitigation Structure | 120.7093 | 17.6545 | 48999939.93 | 49497200 | 2022 | ST. TIMOTHY CONSTRUCTION CORPORATION | 1655 | 2022 | 2022-11-05 | 02/17/2022 | 0 | 497260.07 | 2022-10-20 |  | 16
2023 | Cordillera Administrative Region | ABRA | LUBA (ABRA) | P00726388LZ | Construction of Flood Mitigation Structure | 120.71 | 17.3547 | 144749971.4 | 144750000 | 2024 | MG SAMIDAN CONSTRUCTION | 1656 | 2023 | 2024-03-04 | 04/27/2023 | 0 | 28.6 | 2024-03-03 |  | 1
2023 | Region I | ILOCOS NORTE | NUEVA ERA (ILOCOS NORTE) | P00725649LZ | Construction of Flood Mitigation Structure | 120.7102 | 17.9445 | 18721000 | 18533050.52 | 2023 | WAY MAKER GENERAL CONTRACTOR OPC | 1657 | 2023 | 2023-10-16 | 05/08/2023 | 187949.48 | 0 | 2023-10-15 |  | 1
2022 | Region I | PANGASINAN | BALUNGAO (PANGASINAN) | P00621445LZ | Construction of Dike | 120.7106 | 15.9028 | 24500000 | 24473376.44 | 2022 | RS RODRIGUEZ CONSTRUCTION & SUPPLIES | 1658 | 2022 | 2022-10-10 | 04/08/2022 | 26623.56 | 0 | 2022-09-25 |  | 15
2022 | Region III | PAMPANGA | MAGALANG (PAMPANGA) | P00640525LZ | Construction of Slope Protection Structure | 120.7107 | 15.2554 | 48994961.58 | 48978136.7 | 2022 | 3-SIDES BUILDERS & TRADING CORP. | 1659 | 2022 | 2022-10-19 | 03/24/2022 | 16824.88 | 0 | 2022-10-18 |  | 1
2024 | Region I | PANGASINAN | BALUNGAO (PANGASINAN) | P00824661LZ | Construction of Dike | 120.7109 | 15.9025 | 24500000 | 24477326.91 | 2024 | RS RODRIGUEZ CONSTRUCTION & SUPPLIES | 1660 | 2024 | 2024-07-15 | 02/28/2024 | 22673.09 | 0 | 2024-08-16 | 32
2022 | Cordillera Administrative Region | BENGUET | ATOK (BENGUET) | P00620479LZ | Construction of Flood Mitigation Structure | 120.7109 | 16.633 | 24500000 | 24500000 | 2022 | OLSIM CONSTRUCTION | 1661 | 2022 | 2022-09-05 | 03/07/2022 | 0 | 0 | 2022-09-04 |  | 1
2024 | Region III | NUEVA ECIJA | GUIMBA (NUEVA ECIJA) | P00823431LZ | Construction of Flood Mitigation Structure | 120.7112 | 15.6309 | 53075000 | 52544201.3 | 2024 | MIVICO BUILDERS & DEVELOPERS | 1662 | 2024 | 2024-11-03 | 04/08/2024 | 530798.7 | 0 | 2024-11-02 |  | 1
2023 | Region III | PAMPANGA | MAGALANG (PAMPANGA) | P00742144LZ | Construction of Slope Protection Structure | 120.7113 | 15.2392 | 69291530.47 | 69224573.34 | 2023 | TRICHES CONSTRUCTION & TRADING / FRAMECON BUILDERS | 1663 | 2023 | 2023-11-25 | 06/05/2023 | 66957.13 | 0 | 2023-11-30 | 5
2023 | Region III | PAMPANGA | MAGALANG (PAMPANGA) | P00727144LZ | Construction of Flood Mitigation Structure | 120.7113 | 15.2392 | 44096687.9 | 44085596.84 | 2023 | 3-SIDES BUILDERS & TRADING CORP. | 1664 | 2023 | 2023-09-21 | 04/25/2023 | 11091.06 | 0 | 2023-09-20 |  | 1
2023 | Region III | PAMPANGA | MAGALANG (PAMPANGA) | P00742366LZ | Construction of Slope Protection Structure | 120.7113 | 15.2392 | 19788565.59 | 19762442.35 | 2023 | M.C.J. VALENZUELA CONSTRUCTION ENTERPRISES | 1665 | 2023 | 2023-09-02 | 06/05/2023 | 26123.24 | 0 | 2023-09-01 |  | 1
2023 | Region III | PAMPANGA | MAGALANG (PAMPANGA) | P00742361LZ | Construction of Slope Protection Structure | 120.7113 | 15.2392 | 48493196.02 | 48379510.98 | 2023 | RADIANS BUILDERS AND SUPPLY CORPORATION | 1666 | 2023 | 2023-10-12 | 05/16/2023 | 113685.04 | 0 | 2023-10-11 |  | 1
2023 | Region III | PAMPANGA | MAGALANG (PAMPANGA) | P00742363LZ | Construction of Slope Protection Structure | 120.7113 | 15.2392 | 49499419.34 | 49493704.83 | 2023 | J.H.R. ENTERPRISES | 1667 | 2023 | 2023-10-12 | 05/16/2023 | 5714.51 | 0 | 2023-10-11 |  | 1
2023 | Region III | PAMPANGA | MAGALANG (PAMPANGA) | P00742360LZ | Construction of Slope Protection Structure | 120.7113 | 15.2392 | 19791971.99 | 19751041.93 | 2023 | RADIANS BUILDERS AND SUPPLY CORPORATION | 1668 | 2023 | 2023-08-31 | 05/24/2023 | 40930.06 | 0 | 2023-08-20 |  | 11
2023 | Region III | PAMPANGA | MAGALANG (PAMPANGA) | P00740626LZ | Construction of Slope Protection Structure | 120.7113 | 15.2392 | 4998075.77 | 4850873.57 | 2023 | RD5 CONSTRUCTION | 1669 | 2023 | 2023-08-03 | 06/05/2023 | 147202.2 | 0 | 2023-08-02 |  | 1
2023 | Cordillera Administrative Region | ABRA | SAN JUAN (ABRA) | P00726389LZ | Construction of Flood Mitigation Structure | 120.7118 | 17.693 | 77199901.54 | 77194438 | 2023 | MG SAMIDAN CONSTRUCTION | 1670 | 2023 | 2023-07-21 | 04/14/2023 | 5463.54 | 0 | 2023-11-12 | 114
2022 | Cordillera Administrative Region | ABRA | BUCAY (ABRA) | P00620984LZ | Construction of Flood Mitigation Structure | 120.7119 | 17.4538 | 30178018.22 | 30176120 | 2022 | ST. TIMOTHY CONSTRUCTION CORPORATION | 1671 | 2022 | 2022-08-01 | 02/17/2022 | 1898.22 | 0 | 2022-07-31 |  | 1
2022 | Cordillera Administrative Region | ABRA | BUCAY (ABRA) | P00631101LZ | Construction of Flood Mitigation Structure | 120.7121 | 17.4531 | 29399906.75 | 29398000 | 2022 | A.D. MARRERO GENERAL CONSTRUCTION | 1672 | 2022 | 2022-08-07 | 02/17/2022 | 1906.75 | 0 | 2022-07-30 |  | 8
2022 | Cordillera Administrative Region | ABRA | LAGAYAN (ABRA) | P00632776LZ | Construction of Flood Mitigation Structure | 120.7125 | 17.7256 | 48999938.48 | 49498000 | 2022 | MG SAMIDAN CONSTRUCTION / SEJ CONSTRUCTION & AGGREGATES | 1673 | 2022 | 2022-09-03 | 03/01/2022 | 0 | 498061.52 | 2022-09-02 |  | 1
2021 | Cordillera Administrative Region | ABRA |  | P00561504LZ | Construction of Flood Mitigation Structure | 120.7136 | 17.5165 | 98000000 | 96497003.85 | 2022 | ST. TIMOTHY CONSTRUCTION CORPORATION | 1674 | 2021 | 2022-09-24 | 12/28/2021 | 1502996.15 | 0 | 2022-09-30 | 6
2021 | Region I | ILOCOS NORTE |  | P00525856LZ | Construction of Flood Mitigation Structure | 120.7138 | 18.518 | 9799929.29 | 9799889.76 | 2022 | JLP CONSTRUCTION & SUPPLY (FORMERLY: JLP CONSTRUCT | 1675 | 2021 | 2022-07-15 | 08/18/2021 | 39.53 | 0 | 2022-06-17 |  | 28
2022 | Cordillera Administrative Region | ABRA | LAGAYAN (ABRA) | P00632767LZ | Construction of Flood Mitigation Structure | 120.714 | 17.7287 | 48999918.77 | 49000000 | 2022 | SEJ CONSTRUCTION & AGGREGATES / EGB CONSTRUCTION CORPORATION (FORMERLY: EGB CONSTRUCTION) | 1676 | 2022 | 2022-09-12 | 03/10/2022 | 0 | 81.23 | 2022-09-11 |  | 1
2021 | Cordillera Administrative Region | ABRA |  | P00561509LZ | Construction of Flood Mitigation Structure | 120.7141 | 17.7314 | 98000000 | 96498000 | 2022 | SEJ CONSTRUCTION & AGGREGATES / EGB CONSTRUCTION CORPORATION (FORMERLY: EGB CONSTRUCTION) | 1677 | 2021 | 2022-09-24 | 12/28/2021 | 1502000 | 0 | 2022-09-23 |  | 1
2021 | Cordillera Administrative Region | ABRA |  | P00561502LZ | Construction of Flood Mitigation Structure | 120.7142 | 17.5579 | 97999827.95 | 96497238.95 | 2022 | ST. TIMOTHY CONSTRUCTION CORPORATION | 1678 | 2021 | 2022-09-24 | 12/28/2021 | 1502589 | 0 | 2022-09-23 |  | 1
2023 | Region III | PAMPANGA | ARAYAT (PAMPANGA) | P00725732LZ | Construction of Flood Mitigation Structure | 120.7144 | 15.1163 | 270199419.4 | 270194706 | 2024 | A.D. GONZALES JR. CONSTRUCTION & TRADING CO. INC. | 1679 | 2023 | 2024-03-06 | 03/13/2023 | 4713.4 | 0 | 2024-03-05 |  | 1
2023 | Region III | BULACAN | HAGONOY (BULACAN) | P00740375LZ | Construction of Revetment | 120.7145 | 14.8116 | 144749632.8 | 144749439.7 | 2023 | FLORDES CONSTRUCTION & TRADING CORP. (FORMERLY FLO | 1680 | 2023 | 2023-10-24 | 03/28/2023 | 193.1 | 0 | 2024-03-20 | 148
2023 | Region III | PAMPANGA | MAGALANG (PAMPANGA) | P00727143LZ | Construction of Flood Mitigation Structure | 120.7151 | 15.2526 | 46040632.7 | 46024057.5 | 2023 | GEOHEART CONSTRUCTION & TRADING / THREE-IN-ONE CONSTRUCTION & TRADING | 1681 | 2023 | 2023-09-21 | 04/25/2023 | 16575.2 | 0 | 2023-09-20 |  | 1
2023 | Region III | NUEVA ECIJA | GUIMBA (NUEVA ECIJA) | P00726733LZ | Construction of Flood Mitigation Structure | 120.7152 | 15.6416 | 49000000 | 48994000 | 2023 | MIVICO BUILDERS & DEVELOPERS | 1682 | 2023 | 2023-10-10 | 02/13/2023 | 6000 | 0 | 2023-10-09 |  | 1
2024 | Region III | NUEVA ECIJA | GUIMBA (NUEVA ECIJA) | P00823430LZ | Construction of Flood Mitigation Structure | 120.7152 | 15.6416 | 67550000 | 66867803.43 | 2025 | NIÃ‘AS CONSTRUCTION CORP. (FORMERLY: NINA'S CONSTRUCTION AND SUPPLIES) | 1683 | 2024 | 2025-01-24 | 04/29/2024 | 682196.57 | 0 | 2025-02-10 | 17
2021 | Cordillera Administrative Region | ABRA |  | P00561506LZ | Construction of Flood Mitigation Structure | 120.7158 | 17.4546 | 98000000 | 96497977.23 | 2022 | PHESCO, INCORPORATED | 1684 | 2021 | 2022-09-26 | 12/28/2021 | 1502022.77 | 0 | 2022-09-30 | 4
2022 | Region III | TARLAC | CONCEPCION (TARLAC) | P00631265LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.7159 | 15.333 | 48999706.34 | 47916435.66 | 2022 | RAIK CONSTRUCTION AND DEVELOPMENT CORPORATION (FORMERLY: RAIK CONSTRUCTION AND SUPPLY) | 1685 | 2022 | 2022-09-06 | 01/29/2022 | 1083270.68 | 0 | 2022-09-05 |  | 1
2022 | Cordillera Administrative Region | BENGUET | BAKUN (BENGUET) | P00620476LZ | Construction of Flood Mitigation Structure | 120.7161 | 16.7984 | 24500000 | 24500000 | 2022 | M.P. TABERAO CONSTRUCTION SERVICES AND SUPPLIES | 1686 | 2022 | 2022-10-13 | 04/12/2022 | 0 | 0 | 2022-10-12 |  | 1
2022 | Cordillera Administrative Region | ABRA | BUCAY (ABRA) | P00637059LZ | Construction of Drainage Structure | 120.7163 | 17.5309 | 48999593.41 | 48997065.54 | 2023 | A.D. MARRERO GENERAL CONSTRUCTION | 1687 | 2022 | 2023-01-04 | 08/02/2022 | 2527.87 | 0 | 2023-01-03 |  | 1
2022 | Cordillera Administrative Region | ABRA | BUCAY (ABRA) | P00632756LZ | Construction of Flood Mitigation Structure | 120.7171 | 17.5613 | 48999962.04 | 49498000 | 2022 | 739 BUILDERS | 1688 | 2022 | 2022-12-18 | 06/15/2022 | 0 | 498037.96 | 2022-12-17 |  | 1
2022 | Cordillera Administrative Region | ABRA | BUCAY (ABRA) | P00637062LZ | Construction of Flood Mitigation Structure | 120.7173 | 17.5535 | 48999954.11 | 48998000 | 2023 | 739 BUILDERS | 1689 | 2022 | 2023-01-22 | 07/20/2022 | 1954.11 | 0 | 2023-01-21 |  | 1
2023 | Region IV-B | OCCIDENTAL MINDORO | SANTA CRUZ (OCCIDENTAL MINDORO) | P00740424LZ | Construction of Revetment | 120.7174 | 13.0788 | 241249999.5 | 241247329.3 | 2024 | YPR GEN. CONTRACTOR AND CONSTRUCTION SUPPLY INC. | 1690 | 2023 | 2024-02-10 | 04/13/2023 | 2670.2 | 0 | 2024-04-05 | 55
2023 | Region IV-A | BATANGAS | BALAYAN (BATANGAS) | P00725838LZ | Construction of Flood Mitigation Structure | 120.7178 | 13.9412 | 77198760 | 77198760 | 2023 | VICMAR CONSTRUCTION, INC. | 1691 | 2023 | 2023-11-16 | 04/03/2023 | 0 | 0 | 2023-12-27 | 41
2024 | Region IV-A | BATANGAS | BALAYAN (BATANGAS) | P00846031LZ | Construction of Drainage Structure | 120.7187 | 13.9453 | 19800000 | 19800000 | 2024 | V.R. PATRON BUILDERS & DEVELOPERS CORP. (PREVIOUSL | 1692 | 2024 | 2024-11-10 | 09/02/2024 | 0 | 0 | 2025-03-14 | 124
2022 | Cordillera Administrative Region | ABRA | SAN JUAN (ABRA) | P00632777LZ | Construction of Flood Mitigation Structure | 120.7191 | 17.719 | 48999946.28 | 49498154 | 2022 | ST. TIMOTHY CONSTRUCTION CORPORATION | 1693 | 2022 | 2022-11-08 | 02/17/2022 | 0 | 498207.72 | 2022-10-20 |  | 19
2023 | Region III | PAMPANGA | SANTO TOMAS (PAMPANGA) | P00740325LZ | Construction of Flood Mitigation Structure | 120.7191 | 15.0047 | 96500000 | 91674954.68 | 2024 | EDDMARI CONSTRUCTION & TRADING | 1694 | 2023 | 2024-02-22 | 06/05/2023 | 4825045.32 | 0 | 2024-02-21 |  | 1
2024 | Region III | TARLAC | LA PAZ (TARLAC) | P00838443LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.7194 | 15.4581 | 96499278.07 | 96497704.17 | 2024 | HIGH ROCK CONSTRUCTION AND SUPPLIES INCORPORATED / JHI CONSTRUCTION & SUPPLY | 1695 | 2024 | 2024-07-17 | 02/20/2024 | 1573.9 | 0 | 2024-08-20 | 34
2023 | Region IV-B | OCCIDENTAL MINDORO | SANTA CRUZ (OCCIDENTAL MINDORO) | P00740423LZ | Construction of Revetment | 120.7196 | 13.0749 | 241249999.1 | 241246839.2 | 2024 | GREAT PACIFIC BUILDERS AND GEN. CONTRACTOR INC. | 1696 | 2023 | 2024-02-10 | 04/13/2023 | 3159.9 | 0 | 2024-04-05 | 55
2023 | Region IV-A | BATANGAS | BALAYAN (BATANGAS) | P00725837LZ | Construction of Flood Mitigation Structure | 120.7196 | 13.9389 | 96498760 | 96067745.81 | 2023 | VICMAR CONSTRUCTION, INC. / FRANDEL CONSTRUCTION AND DEVELOPMENT CORP. | 1697 | 2023 | 2023-12-12 | 04/03/2023 | 431014.19 | 0 | 2024-01-26 | 45
2022 | Cordillera Administrative Region | ABRA | DOLORES (ABRA) | P00639326LZ | Construction of Flood Mitigation Structure | 120.7197 | 17.6688 | 95534927.27 | 95532900 | 2023 | MG SAMIDAN CONSTRUCTION | 1698 | 2022 | 2023-01-06 | 11/08/2022 | 2027.27 | 0 | 2023-06-05 | 150
2023 | Region I | ILOCOS NORTE | BANGUI (ILOCOS NORTE) | P00727047LZ | Construction of Flood Mitigation Structure | 120.72 | 18.486 | 19599805.86 | 19599805.45 | 2023 | ZEDIK BUILDERS | 1699 | 2023 | 2023-09-13 | 03/29/2023 | 0.41 | 0 | 2023-09-15 | 2
2022 | Cordillera Administrative Region | ABRA | BUCAY (ABRA) | P00631100LZ | Construction of Flood Mitigation Structure | 120.7201 | 17.5369 | 41159987.8 | 41158000 | 2022 | ST. TIMOTHY CONSTRUCTION CORPORATION | 1700 | 2022 | 2022-09-10 | 03/16/2022 | 1987.8 | 0 | 2022-09-09 |  | 1
2023 | Region III | TARLAC | CITY OF TARLAC (CAPITAL) (TARLAC) | P00742163LZ | Construction of Drainage Structure | 120.5953 | 15.5028 | 98999074.83 | 99000000 | 2024 | NORTHERN BUILDERS | 1701 | 2023 | 2024-06-06 | 09/11/2023 | 0 | 925.17 | 2024-06-05 |  | 1
2023 | Region III | TARLAC | CITY OF TARLAC (CAPITAL) (TARLAC) | P00742140LZ | Construction of Drainage Structure | 120.5954 | 15.5009 | 74249807.83 | 74250000 | 2024 | NORTHERN BUILDERS | 1702 | 2023 | 2024-03-12 | 07/17/2023 | 0 | 192.17 | 2024-03-11 |  | 1
2023 | Region III | TARLAC | CITY OF TARLAC (CAPITAL) (TARLAC) | P00742129LZ | Construction of Drainage Structure | 120.5956 | 15.4924 | 148499594.2 | 148500000 | 2024 | NORTHERN BUILDERS | 1703 | 2023 | 2024-10-29 | 12/05/2023 | 0 | 405.8 | 2024-10-28 |  | 1
2024 | Cordillera Administrative Region | BENGUET | KAPANGAN (BENGUET) | P00824668LZ | Construction of Flood Mitigation Structure | 120.5957 | 16.5728 | 14700000 | 14670528.86 | 2024 | DJ AND C CONSTRUCTION SERVICES | 1704 | 2024 | 2024-09-23 | 06/20/2024 | 29471.14 | 0 | 2024-12-08 | 76
2023 | Region I | PANGASINAN | CITY OF URDANETA (PANGASINAN) | P00726058LZ | Construction of Dike | 120.5958 | 16.0392 | 49000000 | 48895892.15 | 2023 | W.J.P. CONSTRUCTION AND SUPPLY | 1705 | 2023 | 2023-03-28 | 02/10/2023 | 104107.85 | 0 | 2023-08-28 | 153
2024 | Region I | PANGASINAN | BINALONAN (PANGASINAN) | P00821505LZ | Construction of Revetment | 120.5959 | 16.0704 | 49000000 | 48905055.49 | 2024 | SOLID STAR BUILDERS AND CONSTRUCTION SUPPLY | 1706 | 2024 | 2024-05-30 | 02/21/2024 | 94944.51 | 0 | 2024-09-07 | 100
2024 | Region III | BULACAN | HAGONOY (BULACAN) | P00844503LZ | Construction of Flood Mitigation Structure | 120.7429 | 14.8592 | 77199816.66 | 77198834.6 | 2024 | TRIPLE 8 CONSTRUCTION & SUPPLY, INC. (FORMERLY TRIPLE 8 CONST. & SUPPLY) | 1707 | 2024 | 2024-11-05 | 03/11/2024 | 982.06 | 0 | 2024-11-04 |  | 1
2023 | Region III | PAMPANGA | LUBAO (PAMPANGA) | P00742349LZ | Construction of Slope Protection Structure | 120.5959 | 14.9631 | 21779169.77 | 21769230 | 2023 | RADIANS BUILDERS AND SUPPLY CORPORATION | 1708 | 2023 | 2023-09-16 | 04/20/2023 | 9939.77 | 0 | 2023-09-15 |  | 1
2023 | Region III | TARLAC | CITY OF TARLAC (CAPITAL) (TARLAC) | P00742138LZ | Construction of Drainage Structure | 120.596 | 15.4967 | 148499489.5 | 148500000 | 2024 | NORTHERN BUILDERS | 1709 | 2023 | 2024-06-10 | 07/17/2023 | 0 | 510.5 | 2024-06-09 |  | 1
2022 | Region III | TARLAC | CITY OF TARLAC (CAPITAL) (TARLAC) | P00630940LZ | Construction of Drainage Structure | 120.5961 | 15.486 | 96500000 | 94570289.88 | 2022 | NORTHERN BUILDERS | 1710 | 2022 | 2022-11-20 | 03/10/2022 | 1929710.12 | 0 | 2022-11-11 |  | 9
2023 | Region III | PAMPANGA | LUBAO (PAMPANGA) | P00740611LZ | Construction of Slope Protection Structure | 120.5963 | 14.963 | 19599133.43 | 19592188.67 | 2023 | ARROW CONSTRUCTION | 1711 | 2023 | 2023-07-31 | 04/26/2023 | 6944.76 | 0 | 2023-09-21 | 52
2023 | Region I | PANGASINAN | BINALONAN (PANGASINAN) | P00726057LZ | Construction of Dike | 120.5964 | 16.04 | 49000000 | 48873501.74 | 2023 | W.J.P. CONSTRUCTION AND SUPPLY | 1712 | 2023 | 2023-03-28 | 02/10/2023 | 126498.26 | 0 | 2023-08-28 | 153
2024 | Region III | PAMPANGA | ANGELES CITY (PAMPANGA) | P00838368LZ | Construction of Flood Mitigation Structure | 120.5964 | 15.1573 | 77195004.5 | 77193423.34 | 2024 | THREE-IN-ONE CONSTRUCTION & TRADING | 1713 | 2024 | 2024-08-22 | 03/14/2024 | 1581.16 | 0 | 2024-10-09 | 48
2024 | Region I | PANGASINAN | BINALONAN (PANGASINAN) | P00820728LZ | Construction of Revetment | 120.5966 | 16.0856 | 49000000 | 48922351.16 | 2024 | W.J.P. CONSTRUCTION AND SUPPLY | 1714 | 2024 | 2024-03-18 | 02/14/2024 | 77648.84 | 0 | 2024-08-31 | 166
2022 | Region I | PANGASINAN | BINALONAN (PANGASINAN) | P00620466LZ | Construction of Dike | 120.5967 | 16.0456 | 44100000 | 44023866.89 | 2022 | W.J.P. CONSTRUCTION AND SUPPLY | 1715 | 2022 | 2022-07-01 | 02/24/2022 | 76133.11 | 0 | 2022-09-05 | 66
2022 | Region III | TARLAC | BAMBAN (TARLAC) | P00639348LZ | Construction of Slope Protection Structure | 120.5968 | 15.275 | 96499392.07 | 96470264.1 | 2023 | 11-16 CONSTRUCTION | 1716 | 2022 | 2023-03-08 | 03/26/2022 | 29127.97 | 0 | 2023-03-07 |  | 1
2022 | Region I | ILOCOS NORTE | LAOAG CITY (CAPITAL) (ILOCOS NORTE) | P00641835LZ | Construction of Slope Protection Structure | 120.597 | 18.222 | 33775000 | 33599149.35 | 2023 | JCA CONSTRUCTION AND CONSTRUCTION SUPPLY | 1717 | 2022 | 2023-05-03 | 03/25/2022 | 175850.65 | 0 | 2022-12-24 |  | 130
2024 | Region I | PANGASINAN | SISON (PANGASINAN) | P00823277LZ | Construction of Flood Mitigation Structure | 120.597 | 16.0659 | 48250000 | 48249872.89 | 2024 | UNIVERSAL DE LEON CONSTRUCTION AND AGGREGATES | 1718 | 2024 | 2024-07-31 | 05/03/2024 | 127.11 | 0 | 2024-10-22 | 83
2024 | Region I | PANGASINAN | SISON (PANGASINAN) | P00823279LZ | Construction of Flood Mitigation Structure | 120.597 | 16.0659 | 48250000 | 48249924.65 | 2024 | ROCK-WBL CONSTRUCTION CORP. (FOR: ROCK-WBL CONSTRUCTION TRADING & SERVICES) | 1719 | 2024 | 2024-07-31 | 05/03/2024 | 75.35 | 0 | 2024-10-22 | 83
2024 | Region I | PANGASINAN | SISON (PANGASINAN) | P00823281LZ | Construction of Flood Mitigation Structure | 120.597 | 16.0659 | 48250000 | 48249532.57 | 2024 | ROCK-WBL CONSTRUCTION CORP. (FOR: ROCK-WBL CONSTRUCTION TRADING & SERVICES) | 1720 | 2024 | 2024-07-15 | 05/03/2024 | 467.43 | 0 | 2024-10-22 | 99
2024 | Region I | PANGASINAN | SISON (PANGASINAN) | P00823283LZ | Construction of Flood Mitigation Structure | 120.597 | 16.0659 | 48250000 | 48249428.51 | 2024 | ROCK-WBL CONSTRUCTION CORP. (FOR: ROCK-WBL CONSTRUCTION TRADING & SERVICES) | 1721 | 2024 | 2024-07-15 | 04/26/2024 | 571.49 | 0 | 2024-10-15 | 92
2024 | Region I | PANGASINAN | BINALONAN (PANGASINAN) | P00820727LZ | Construction of Revetment | 120.5971 | 16.0864 | 49000000 | 48919930.89 | 2024 | W.J.P. CONSTRUCTION AND SUPPLY | 1722 | 2024 | 2024-03-15 | 02/14/2024 | 80069.11 | 0 | 2024-08-31 | 169
2024 | Region I | PANGASINAN | BINALONAN (PANGASINAN) | P00820722LZ | Construction of Revetment | 120.5971 | 16.0864 | 49000000 | 48248509.43 | 2024 | AMP 723 CONSTRUCTION CORPORATION (FORMERLY: A.M.P. CONSTRUCTION) | 1723 | 2024 | 2024-05-15 | 02/28/2024 | 751490.57 | 0 | 2024-09-14 | 122
2022 | Region III | PAMPANGA | MABALACAT CITY (PAMPANGA) | P00632854LZ | Construction of Slope Protection Structure | 120.5972 | 15.1983 | 29399837.47 | 29399679.61 | 2022 | M.C.J. VALENZUELA CONSTRUCTION ENTERPRISES | 1724 | 2022 | 2022-08-06 | 02/08/2022 | 157.86 | 0 | 2022-08-05 |  | 1
2022 | Region III | PAMPANGA | MABALACAT CITY (PAMPANGA) | P00631260LZ | Construction of Slope Protection Structure | 120.5975 | 15.2449 | 26455269.83 | 26411453.9 | 2022 | WNR CONSTRUCTION AND TRADING | 1725 | 2022 | 2022-08-06 | 02/08/2022 | 43815.93 | 0 | 2022-08-05 |  | 1
2023 | Region I | ILOCOS NORTE | LAOAG CITY (CAPITAL) (ILOCOS NORTE) | P00742253LZ | Construction of Drainage Structure | 120.5975 | 18.1939 | 4949525.13 | 4948884.77 | 2023 | BJMJB CONSTRUCTION & SUPPLY | 1726 | 2023 | 2023-07-25 | 04/12/2023 | 640.36 | 0 | 2023-08-09 | 15
2022 | Region I | ILOCOS NORTE | VINTAR (ILOCOS NORTE) | P00632724LZ | Construction of Slope Protection Structure | 120.5977 | 18.2227 | 29699636.26 | 29699636.24 | 2023 | JCA CONSTRUCTION AND CONSTRUCTION SUPPLY | 1727 | 2022 | 2023-02-17 | 02/18/2022 | 0.02 | 0 | 2022-11-01 |  | 108
2023 | Region III | PAMPANGA | LUBAO (PAMPANGA) | P00742356LZ | Construction of Drainage Structure | 120.5977 | 14.9389 | 4949796.44 | 4831150.28 | 2023 | SUPREME BUILDERS CONSTRUCTION AND TRADING | 1728 | 2023 | 2023-09-26 | 06/14/2023 | 118646.16 | 0 | 2023-09-25 |  | 1
2023 | Cordillera Administrative Region | BENGUET | BAGUIO CITY (BENGUET) | P00726403LZ | Construction of Flood Mitigation Structure | 120.5978 | 16.4315 | 82025000 | 82025000 | 2023 | GOLDRICH CONSTRUCTION & TRADING | 1729 | 2023 | 2023-11-27 | 02/10/2023 | 0 | 0 | 2024-01-26 | 60
2023 | Cordillera Administrative Region | BENGUET | BAGUIO CITY (BENGUET) | P00726656LZ | Construction of Revetment | 120.5978 | 16.3885 | 126200000 | 49000000 | 2023 | GOLDRICH CONSTRUCTION & TRADING | 1730 | 2023 | 2023-11-27 | 02/10/2023 | 77200000 | 0 | 2024-01-22 | 56
2025 | Region III | TARLAC | MONCADA (TARLAC) | P00921066LZ | Rehabilitation / Major Repair of Slope Protection Structure | 120.5979 | 15.7485 | 14700000 | 14700000 | 2025 | T2B3 BUILDERS AND SUPPLIES CORP. | 1731 | 2025 | 2025-05-19 | 01/27/2025 | 0 | 0 | 2025-05-24 | 5
2024 | Region I | PANGASINAN | BINALONAN (PANGASINAN) | P00821504LZ | Construction of Revetment | 120.598 | 16.0713 | 49000000 | 48819534.05 | 2024 | W.J.P. CONSTRUCTION AND SUPPLY | 1732 | 2024 | 2024-04-29 | 02/21/2024 | 180465.95 | 0 | 2024-09-07 | 131
2022 | Cordillera Administrative Region | BENGUET | LA TRINIDAD (CAPITAL) (BENGUET) | P00639452LZ | Rehabilitation / Major Repair of Drainage Structure | 120.5982 | 16.4332 | 2940000 | 2934796.4 | 2023 | 8-10 NEHEMIAH CONSTRUCTION | 1733 | 2022 | 2023-02-07 | 10/21/2022 | 5203.6 | 0 | 2022-12-04 |  | 65
2023 | Region I | ILOCOS NORTE | BACARRA (ILOCOS NORTE) | P00737412LZ | Construction of Slope Protection Structure | 120.5984 | 18.277 | 4949920.42 | 4949915.3 | 2023 | REMAR CONSTRUCTION | 1734 | 2023 | 2023-03-17 | 02/14/2023 | 5.12 | 0 | 2023-06-19 | 94
2023 | Region I | ILOCOS NORTE | LAOAG CITY (CAPITAL) (ILOCOS NORTE) | P00727332LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.5984 | 18.2044 | 9799314.63 | 9799234.59 | 2023 | ZEDIK BUILDERS | 1735 | 2023 | 2023-10-23 | 04/20/2023 | 80.04 | 0 | 2023-12-17 | 55
2024 | Region I | ILOCOS NORTE | PASUQUIN (ILOCOS NORTE) | P00844705LZ | Construction of Flood Mitigation Structure | 120.5985 | 18.3843 | 48999625.76 | 48999619.58 | 2024 | HAUSLAND CONSTRUCTION | 1736 | 2024 | 2024-04-17 | 02/12/2024 | 6.18 | 0 | 2024-08-29 | 134
2023 | Region III | PAMPANGA | ANGELES CITY (PAMPANGA) | P00740633LZ | Construction of Drainage Structure | 120.5987 | 15.1581 | 4899762.68 | 4895353.6 | 2023 | P.V.B. CONSTRUCTION AND DEVELOPMENT CORP. | 1737 | 2023 | 2023-06-10 | 04/12/2023 | 4409.08 | 0 | 2023-06-09 |  | 1
2022 | Region III | PAMPANGA | LUBAO (PAMPANGA) | P00637781LZ | Construction of Slope Protection Structure | 120.5993 | 14.8877 | 19798731.75 | 19790941.34 | 2022 | OMICRON CONSTRUCTION | 1738 | 2022 | 2022-09-09 | 04/13/2022 | 7790.41 | 0 | 2022-09-08 |  | 1
2024 | Cordillera Administrative Region | BENGUET | BAGUIO CITY (BENGUET) | P00821529LZ | Construction of Flood Mitigation Structure | 120.5998 | 16.4267 | 145500000 | 49000000 | 2024 | GOLDRICH CONSTRUCTION & TRADING | 1739 | 2024 | 2024-07-29 | 03/15/2024 | 96500000 | 0 | 2024-11-12 | 106
2023 | Region I | ILOCOS NORTE | VINTAR (ILOCOS NORTE) | P00725641LZ | Construction of Flood Mitigation Structure | 120.6 | 18.2761 | 57899987.46 | 57899902.46 | 2023 | MEGAPOLITAN BUILDERS AND CONSTRUCTION SUPPLY | 1740 | 2023 | 2023-09-15 | 03/13/2023 | 85 | 0 | 2024-01-11 | 118
2021 | Region III | TARLAC |  | P00526056LZ | Construction of Flood Mitigation Structure | 120.6001 | 15.3448 | 14699690.43 | 14028306.54 | 2022 | P.C. PANOPIO CONSTRUCTION AND TRADING | 1741 | 2021 | 2022-09-20 | 03/24/2022 | 671383.89 | 0 | 2022-09-19 |  | 1
2024 | Region I | PANGASINAN | BINALONAN (PANGASINAN) | P00821503LZ | Construction of Revetment | 120.6003 | 16.0718 | 49000000 | 48831908.98 | 2024 | W.J.P. CONSTRUCTION AND SUPPLY | 1742 | 2024 | 2024-04-29 | 02/21/2024 | 168091.02 | 0 | 2024-09-07 | 131
2024 | Region I | PANGASINAN | BINALONAN (PANGASINAN) | P00821502LZ | Construction of Revetment | 120.6003 | 16.0717 | 49000000 | 48813804.25 | 2024 | W.J.P. CONSTRUCTION AND SUPPLY | 1743 | 2024 | 2024-04-29 | 02/14/2024 | 186195.75 | 0 | 2024-08-31 | 124
2023 | Region III | TARLAC | CITY OF TARLAC (CAPITAL) (TARLAC) | P00742368LZ | Construction of Drainage Structure | 120.6006 | 15.4191 | 14850000 | 14550786.21 | 2023 | NORTHERN BUILDERS | 1744 | 2023 | 2023-09-13 | 04/11/2023 | 299213.79 | 0 | 2023-09-12 |  | 1
2024 | Region I | ILOCOS NORTE | PASUQUIN (ILOCOS NORTE) | P00838492LZ | Construction of Flood Mitigation Structure | 120.6006 | 18.3549 | 48999942.46 | 48999933.39 | 2024 | LINEAR CONSTRUCTION CORP. | 1745 | 2024 | 2024-08-30 | 02/14/2024 | 9.07 | 0 | 2024-08-31 | 1
2022 | Region III | TARLAC | CAPAS (TARLAC) | P00639372LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.6008 | 15.3243 | 96499582.63 | 96483776.97 | 2023 | 11-16 CONSTRUCTION | 1746 | 2022 | 2023-02-19 | 03/26/2022 | 15805.66 | 0 | 2023-02-18 |  | 1
2022 | Cordillera Administrative Region | ABRA | BUCAY (ABRA) | P00632759LZ | Construction of Flood Mitigation Structure | 120.6014 | 17.5539 | 29700000 | 29700000 | 2023 | MG SAMIDAN CONSTRUCTION / RM30 PSG CONSTRUCTION CORPORATION | 1747 | 2022 | 2023-04-07 | 09/12/2022 | 0 | 0 | 2023-01-26 |  | 71
2023 | Region III | PAMPANGA | MABALACAT CITY (PAMPANGA) | P00727145LZ | Rehabilitation / Major Repair of Slope Protection Structure | 120.6018 | 15.2479 | 48987107.08 | 48938754.63 | 2023 | THREE-IN-ONE CONSTRUCTION & TRADING / P.V.B. CONSTRUCTION & TRADING | 1748 | 2023 | 2023-07-31 | 03/16/2023 | 48352.45 | 0 | 2023-08-11 | 11
2024 | Region I | PANGASINAN | BINALONAN (PANGASINAN) | P00821500LZ | Construction of Revetment | 120.602 | 16.0712 | 49000000 | 48866052.4 | 2024 | W.J.P. CONSTRUCTION AND SUPPLY | 1749 | 2024 | 2024-04-29 | 02/14/2024 | 133947.6 | 0 | 2024-08-31 | 124
2022 | Region III | PAMPANGA | ANGELES CITY (PAMPANGA) | P00620545LZ | Construction of Slope Protection Structure | 120.6022 | 15.1591 | 48994400.11 | 48988710.51 | 2022 | EGB CONSTRUCTION CORPORATION (FORMERLY: EGB CONSTRUCTION) | 1750 | 2022 | 2022-10-19 | 03/24/2022 | 5689.6 | 0 | 2022-10-18 |  | 1
2023 | Region III | PAMPANGA | MABALACAT CITY (PAMPANGA) | P00740631LZ | Construction of Dike | 120.6022 | 15.2473 | 34291087.27 | 34289957.79 | 2023 | GCLT CONSTRUCTION INCORPORATED (FORMERLY: GCLT CONSTRUCTION) | 1751 | 2023 | 2023-11-01 | 06/05/2023 | 1129.48 | 0 | 2023-10-31 |  | 1
2023 | Cordillera Administrative Region | BENGUET | BAGUIO CITY (BENGUET) | P00726404LZ | Construction of Revetment | 120.6024 | 16.3943 | 126200000 | 77200000 | 2023 | GOLDRICH CONSTRUCTION & TRADING | 1752 | 2023 | 2023-11-27 | 02/10/2023 | 49000000 | 0 | 2024-01-22 | 56
2023 | Region III | PAMPANGA | LUBAO (PAMPANGA) | P00740613LZ | Construction of Slope Protection Structure | 120.6024 | 14.9159 | 29399894.38 | 29395338.07 | 2023 | DMDANAN CONSTRUCTION AND TRADING | 1753 | 2023 | 2023-07-04 | 04/11/2023 | 4556.31 | 0 | 2023-09-06 | 64
2024 | Region I | ILOCOS SUR | GREGORIO DEL PILAR (CONCEPCION) (ILOCOS SUR) | P00823300LZ | Construction of Flood Mitigation Structure | 120.6029 | 17.1324 | 49000000 | 48249997.37 | 2024 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | 1754 | 2024 | 2024-12-03 | 04/12/2024 | 750002.63 | 0 | 2024-11-03 |  | 30
2024 | Region III | PAMPANGA | MABALACAT CITY (PAMPANGA) | P00821591LZ | Construction of Slope Protection Structure | 120.6035 | 15.2322 | 48983457.55 | 48972719.95 | 2024 | D.R. ROBLES CONSTRUCTION | 1755 | 2024 | 2024-07-18 | 04/26/2024 | 10737.6 | 0 | 2024-10-08 | 82
2024 | Region III | TARLAC | BAMBAN (TARLAC) | P00820241LZ | Construction of Groundsill | 120.6038 | 15.2772 | 96499283.27 | 96491125.42 | 2024 | 11-16 CONSTRUCTION | 1756 | 2024 | 2024-11-19 | 02/20/2024 | 8157.85 | 0 | 2024-11-18 |  | 1
2022 | Region I | PANGASINAN | ALCALA (PANGASINAN) | P00620966LZ | Construction of Revetment | 120.6039 | 15.8969 | 19600000 | 19304256.05 | 2022 | Z-5 CONSTRUCTION, INC. | 1757 | 2022 | 2022-07-01 | 02/28/2022 | 295743.95 | 0 | 2022-08-04 | 34
2023 | Region I | ILOCOS SUR | GREGORIO DEL PILAR (CONCEPCION) (ILOCOS SUR) | P00727078LZ | Construction of Flood Mitigation Structure | 120.6044 | 17.1355 | 29400000 | 29398146.03 | 2024 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | 1758 | 2023 | 2024-05-28 | 03/22/2023 | 1853.97 | 0 | 2023-10-18 |  | 223
2022 | Region III | PAMPANGA | LUBAO (PAMPANGA) | P00637780LZ | Construction of Slope Protection Structure | 120.6047 | 14.9004 | 19799903.32 | 19794064.91 | 2022 | VERET CONSTRUCTION | 1759 | 2022 | 2022-09-09 | 04/13/2022 | 5838.41 | 0 | 2022-09-08 |  | 1
2023 | Region III | PAMPANGA | MAGALANG (PAMPANGA) | P00740625LZ | Construction of Drainage Structure | 120.6048 | 15.1944 | 4895142.01 | 4893938.64 | 2023 | RD5 CONSTRUCTION | 1760 | 2023 | 2023-07-14 | 05/16/2023 | 1203.37 | 0 | 2023-07-13 |  | 1
2023 | Region III | PAMPANGA | MAGALANG (PAMPANGA) | P00740627LZ | Construction of Drainage Structure | 120.6048 | 15.1944 | 4899485.6 | 4896774.66 | 2023 | RD5 CONSTRUCTION | 1761 | 2023 | 2023-07-14 | 05/16/2023 | 2710.94 | 0 | 2023-07-13 |  | 1
2023 | Region III | PAMPANGA | LUBAO (PAMPANGA) | P00742348LZ | Construction of Slope Protection Structure | 120.6053 | 14.9593 | 17819287.97 | 17813873.03 | 2023 | RADIANS BUILDERS AND SUPPLY CORPORATION | 1762 | 2023 | 2023-09-16 | 04/20/2023 | 5414.94 | 0 | 2023-09-15 |  | 1
2022 | Cordillera Administrative Region | BENGUET | BAGUIO CITY (BENGUET) | P00620992LZ | Construction of Revetment | 120.6053 | 16.3808 | 49000000 | 49000000 | 2023 | GOLDRICH CONSTRUCTION & TRADING | 1763 | 2022 | 2023-01-20 | 03/21/2022 | 0 | 0 | 2023-02-06 | 17
2023 | Region III | PAMPANGA | ANGELES CITY (PAMPANGA) | P00740629LZ | Rehabilitation / Major Repair of Drainage Structure | 120.6054 | 15.1546 | 6856100.56 | 6655358.9 | 2023 | RD5 CONSTRUCTION | 1764 | 2023 | 2023-08-19 | 05/22/2023 | 200741.66 | 0 | 2023-08-18 |  | 1
2024 | Region III | PAMPANGA | MABALACAT CITY (PAMPANGA) | P00823439LZ | Construction of Flood Mitigation Structure | 120.6057 | 15.25 | 96492979.08 | 96473359.74 | 2024 | THREE-IN-ONE CONSTRUCTION & TRADING | 1765 | 2024 | 2024-06-18 | 03/04/2024 | 19619.34 | 0 | 2024-09-27 | 101
2022 | Region III | PAMPANGA | MABALACAT CITY (PAMPANGA) | P00632855LZ | Construction of Slope Protection Structure | 120.6058 | 15.2008 | 19598113.63 | 19592440.23 | 2022 | M.C.J. VALENZUELA CONSTRUCTION ENTERPRISES | 1766 | 2022 | 2022-07-04 | 02/08/2022 | 5673.4 | 0 | 2022-07-03 |  | 1
2022 | Region III | PAMPANGA | MABALACAT CITY (PAMPANGA) | P00631258LZ | Construction of Slope Protection Structure | 120.606 | 15.2008 | 25478844.55 | 25460698.55 | 2022 | SOLFIO P. JACINTO CONSTRUCTION INC. | 1767 | 2022 | 2022-09-09 | 03/24/2022 | 18146 | 0 | 2022-09-08 |  | 1
2023 | Region III | PAMPANGA | ANGELES CITY (PAMPANGA) | P00726186LZ | Construction of Flood Mitigation Structure | 120.6061 | 15.1588 | 9797066.56 | 9793241.05 | 2023 | R.G. DIAZ BUILDERS & TRADING | 1768 | 2023 | 2023-04-17 | 02/08/2023 | 3825.51 | 0 | 2023-05-07 | 20
2023 | Region III | PAMPANGA | ANGELES CITY (PAMPANGA) | P00727147LZ | Construction of Groundsill | 120.6061 | 15.1588 | 48990974.53 | 48990187.47 | 2023 | GCLT CONSTRUCTION INCORPORATED (FORMERLY: GCLT CONSTRUCTION) | 1769 | 2023 | 2023-09-21 | 04/25/2023 | 787.06 | 0 | 2023-09-20 |  | 1
2022 | Region III | PAMPANGA | BACOLOR (PAMPANGA) | P00631234LZ | Construction of Drainage Structure | 120.6063 | 15.0328 | 29400000 | 27841795.85 | 2022 | DAUNGAN CONSTRUCTION DEV'T. & GEN. SUPPLIES CO., INC. | 1770 | 2022 | 2022-07-31 | 02/24/2022 | 1558204.15 | 0 | 2022-07-22 |  | 9
2023 | Region I | ILOCOS NORTE | BACARRA (ILOCOS NORTE) | P00740541LZ | Construction of Slope Protection Structure | 120.6067 | 18.2911 | 4899995.68 | 4898846.44 | 2023 | BJMJB CONSTRUCTION & SUPPLY | 1771 | 2023 | 2023-07-17 | 03/29/2023 | 1149.24 | 0 | 2023-08-01 | 15
2023 | Region III | PAMPANGA | ANGELES CITY (PAMPANGA) | P00740357LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.6067 | 15.1583 | 57886159.41 | 57846215.82 | 2023 | MCB ZAMORA CONSTRUCTION & SUPPLY | 1772 | 2023 | 2023-11-11 | 05/16/2023 | 39943.59 | 0 | 2023-11-10 |  | 1
2023 | Region I | ILOCOS NORTE | BACARRA (ILOCOS NORTE) | P00740539LZ | Construction of Flood Mitigation Structure | 120.607 | 18.2702 | 4899938.43 | 4899922.26 | 2023 | BJMJB CONSTRUCTION & SUPPLY | 1773 | 2023 | 2023-06-08 | 04/11/2023 | 16.17 | 0 | 2023-06-07 |  | 1
2023 | Region I | ILOCOS NORTE | BACARRA (ILOCOS NORTE) | P00742260LZ | Construction of Flood Mitigation Structure | 120.6071 | 18.2503 | 19800000 | 19799998.66 | 2023 | BJMJB CONSTRUCTION & SUPPLY | 1774 | 2023 | 2023-08-25 | 06/30/2023 | 1.34 | 0 | 2023-11-19 | 86
2023 | Region III | TARLAC | CITY OF TARLAC (CAPITAL) (TARLAC) | P00742375LZ | Construction of Drainage Structure | 120.6072 | 15.4723 | 99000000 | 98193228.59 | 2024 | NORTHERN BUILDERS | 1775 | 2023 | 2024-01-09 | 03/16/2023 | 806771.41 | 0 | 2024-01-08 |  | 1
2024 | Region I | ILOCOS NORTE | LAOAG CITY (CAPITAL) (ILOCOS NORTE) | P00838488LZ | Construction of Drainage Structure | 120.6075 | 18.1955 | 4899792.29 | 4899791.75 | 2024 | TMT CONSTRUCTION | 1776 | 2024 | 2024-05-15 | 02/12/2024 | 0.54 | 0 | 2024-05-14 |  | 1
2023 | Region III | PAMPANGA | GUAGUA (PAMPANGA) | P00740604LZ | Construction of Slope Protection Structure | 120.6078 | 14.9819 | 48999196.33 | 48956417.43 | 2023 | R.D. SADSAD CONSTRUCTION & TRADING | 1777 | 2023 | 2023-10-20 | 04/24/2023 | 42778.9 | 0 | 2023-10-19 |  | 1
2023 | Region III | PAMPANGA | GUAGUA (PAMPANGA) | P00742347LZ | Construction of Slope Protection Structure | 120.6079 | 14.9818 | 29699360.14 | 29687166.72 | 2023 | RADIANS BUILDERS AND SUPPLY CORPORATION | 1778 | 2023 | 2023-09-07 | 04/11/2023 | 12193.42 | 0 | 2023-09-06 |  | 1
2024 | Region III | PAMPANGA | MAGALANG (PAMPANGA) | P00823441LZ | Construction of Flood Mitigation Structure | 120.6081 | 15.2505 | 96479050.1 | 96475660.29 | 2024 | THREE-IN-ONE CONSTRUCTION & TRADING | 1779 | 2024 | 2024-06-18 | 03/04/2024 | 3389.81 | 0 | 2024-09-27 | 101
2024 | Region III | PAMPANGA | MABALACAT CITY (PAMPANGA) | P00823440LZ | Construction of Flood Mitigation Structure | 120.6085 | 15.2504 | 96488637.04 | 96485405.27 | 2024 | THREE-IN-ONE CONSTRUCTION & TRADING / P.V.B. CONSTRUCTION & TRADING | 1780 | 2024 | 2024-07-18 | 03/04/2024 | 3231.77 | 0 | 2024-09-27 | 71
2023 | Region III | PAMPANGA | LUBAO (PAMPANGA) | P00727133LZ | Construction of Slope Protection Structure | 120.6086 | 14.9381 | 29398342.86 | 29393193.05 | 2023 | R.M. VITUG CONSTRUCTION | 1781 | 2023 | 2023-05-22 | 03/20/2023 | 5149.81 | 0 | 2023-08-30 | 100
2022 | Region III | PAMPANGA | BACOLOR (PAMPANGA) | P00631245LZ | Rehabilitation / Major Repair of Slope Protection Structure | 120.6088 | 15.0838 | 29400000 | 27846124.16 | 2022 | STAR PRIME PROPERTY DEVELOPERS, INC. | 1782 | 2022 | 2022-08-19 | 03/23/2022 | 1553875.84 | 0 | 2022-08-18 |  | 1
2024 | Region III | TARLAC | SAN MANUEL (TARLAC) | P00846012LZ | Construction of Drainage Structure | 120.6088 | 15.7751 | 4950000 | 5000000 | 2024 | HOR-VERT ENTERPRISES | 1783 | 2024 | 2024-06-24 | 02/16/2024 | 0 | 50000 | 2024-06-23 |  | 1
2024 | Region III | TARLAC | CITY OF TARLAC (CAPITAL) (TARLAC) | P00820858LZ | Construction of Flood Mitigation Structure | 120.6091 | 15.4798 | 44100000 | 45000000 | 2024 | A.C. SOLIVEN CONSTRUCTION & GENERAL MERCHANDISE | 1784 | 2024 | 2024-04-19 | 01/26/2024 | 0 | 900000 | 2024-07-18 | 90
2023 | Region III | TARLAC | CAMILING (TARLAC) | P00726198LZ | Construction of Flood Mitigation Structure | 120.6091 | 15.4798 | 49000000 | 48139898.83 | 2023 | A.C. SOLIVEN CONSTRUCTION & GENERAL MERCHANDISE | 1785 | 2023 | 2023-04-24 | 01/30/2023 | 860101.17 | 0 | 2023-07-28 | 95
2023 | Region III | TARLAC | CITY OF TARLAC (CAPITAL) (TARLAC) | P00725733LZ | Construction of Flood Mitigation Structure | 120.6091 | 15.4798 | 96500000 | 93605343.32 | 2023 | ROYAL CROWN MONARCH CONSTRUCTION & SUPPLIES CORP. | 1786 | 2023 | 2023-08-18 | 02/06/2023 | 2894656.68 | 0 | 2023-10-06 | 49
2023 | Region I | ILOCOS NORTE | BACARRA (ILOCOS NORTE) | P00725606LZ | Construction of Flood Mitigation Structure | 120.6096 | 18.2487 | 58799445.2 | 57899975.88 | 2023 | ZEDIK BUILDERS / MEGAPOLITAN BUILDERS AND CONSTRUCTION SUPPLY | 1787 | 2023 | 2023-05-15 | 03/13/2023 | 899469.32 | 0 | 2023-10-16 | 154
2024 | Region III | TARLAC | SAN MANUEL (TARLAC) | P00844766LZ | Construction of Flood Mitigation Structure | 120.6096 | 15.7979 | 29400000 | 30000000 | 2024 | RD8 BUILDERS CORPORATION UNDER THE NAME OF RD8 BUILDERS / T2B3 BUILDERS AND SUPPLIES CORP. | 1788 | 2024 | 2024-08-04 | 02/27/2024 | 0 | 600000 | 2024-08-03 |  | 1
2022 | Region III | PAMPANGA | MABALACAT CITY (PAMPANGA) | P00632851LZ | Construction of Slope Protection Structure | 120.6098 | 15.2044 | 19597663.45 | 19597211.89 | 2022 | M.C.J. VALENZUELA CONSTRUCTION ENTERPRISES | 1789 | 2022 | 2022-07-04 | 02/08/2022 | 451.56 | 0 | 2022-07-03 |  | 1
2023 | Region I | PANGASINAN | BINALONAN (PANGASINAN) | P00726055LZ | Construction of Dike | 120.61 | 16.0728 | 49000000 | 48901434.15 | 2023 | W.J.P. CONSTRUCTION AND SUPPLY | 1790 | 2023 | 2023-06-06 | 02/10/2023 | 98565.85 | 0 | 2023-08-19 | 74
2023 | Region I | ILOCOS NORTE | BACARRA (ILOCOS NORTE) | P00726040LZ | Construction of Flood Mitigation Structure | 120.6106 | 18.2481 | 19599783.21 | 19599686.15 | 2023 | ZEDIK BUILDERS | 1791 | 2023 | 2023-03-27 | 02/13/2023 | 97.06 | 0 | 2023-08-31 | 157
2024 | Region III | TARLAC | CITY OF TARLAC (CAPITAL) (TARLAC) | P00838534LZ | Construction of Flood Mitigation Structure | 120.6106 | 15.4796 | 49000000 | 50000000 | 2024 | FLORDES CONSTRUCTION & TRADING CORP. (FORMERLY FLO | 1792 | 2024 | 2024-07-24 | 01/26/2024 | 0 | 1000000 | 2024-07-23 |  | 1
2023 | Region I | ILOCOS NORTE | BACARRA (ILOCOS NORTE) | P00737407LZ | Construction of Drainage Structure | 120.611 | 18.2517 | 4949444.13 | 4949131.55 | 2023 | TMT CONSTRUCTION | 1793 | 2023 | 2023-05-13 | 02/13/2023 | 312.58 | 0 | 2023-05-12 |  | 1
2023 | Region I | ILOCOS NORTE | BACARRA (ILOCOS NORTE) | P00737408LZ | Rehabilitation / Major Repair of Drainage Structure | 120.6111 | 18.2504 | 4949761.34 | 4949734.69 | 2023 | BJMJB CONSTRUCTION & SUPPLY | 1794 | 2023 | 2023-03-17 | 02/06/2023 | 26.65 | 0 | 2023-06-11 | 86
2022 | Region I | ILOCOS NORTE | SAN NICOLAS (ILOCOS NORTE) | P00620781LZ | Construction of Flood Mitigation Structure | 120.6121 | 18.1712 | 96500000 | 96499998.07 | 2022 | MEGAPOLITAN BUILDERS AND CONSTRUCTION SUPPLY | 1795 | 2022 | 2022-10-24 | 04/12/2022 | 1.93 | 0 | 2022-11-12 | 19
2023 | Region III | PAMPANGA | ANGELES CITY (PAMPANGA) | P00740367LZ | Construction of Slope Protection Structure | 120.6129 | 15.1732 | 57896117.94 | 57406420.66 | 2023 | 525 CONSTRUCTION | 1796 | 2023 | 2023-09-07 | 05/08/2023 | 489697.28 | 0 | 2023-11-02 | 56
2024 | Region I | ILOCOS NORTE | BACARRA (ILOCOS NORTE) | P00838486LZ | Construction of Flood Mitigation Structure | 120.6129 | 18.2756 | 9799440.4 | 9799416.2 | 2024 | BJMJB CONSTRUCTION & SUPPLY | 1797 | 2024 | 2024-04-16 | 02/13/2024 | 24.2 | 0 | 2024-05-11 | 25
2023 | Cordillera Administrative Region | BENGUET | BAGUIO CITY (BENGUET) | P00726405LZ | Construction of Revetment | 120.6129 | 16.4204 | 67550000 | 67550000 | 2023 | GOLDRICH CONSTRUCTION & TRADING | 1798 | 2023 | 2023-11-27 | 02/10/2023 | 0 | 0 | 2024-01-12 | 46
2022 | Region III | TARLAC | CAPAS (TARLAC) | P00639368LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.6133 | 15.3282 | 96499354.1 | 94756155 | 2022 | FLORDES CONSTRUCTION & TRADING CORP. (FORMERLY FLO | 1799 | 2022 | 2022-11-27 | 03/26/2022 | 1743199.1 | 0 | 2022-11-26 |  | 1
2023 | Region I | ILOCOS NORTE | BACARRA (ILOCOS NORTE) | P00740540LZ | Construction of Slope Protection Structure | 120.6134 | 18.2763 | 4899041.58 | 4898896.53 | 2023 | REMAR CONSTRUCTION | 1800 | 2023 | 2023-09-17 | 04/20/2023 | 145.05 | 0 | 2023-09-16 |  | 1
2023 | Region III | PAMPANGA | PORAC (PAMPANGA) | P00726540LZ | Construction of Flood Mitigation Structure | 120.6136 | 15.0722 | 144749529.5 | 144750000 | 2024 | FERDSTAR BUILDERS INC. | 1801 | 2023 | 2024-03-07 | 06/12/2023 | 0 | 470.5 | 2024-03-06 |  | 1
2023 | Region III | PAMPANGA | SANTA ANA (PAMPANGA) | P00740602LZ | Construction of Flood Mitigation Structure | 120.743 | 15.1029 | 39200000 | 37239843.68 | 2023 | CHOLO CONSTRUCTION AND TRADING | 1802 | 2023 | 2023-10-17 | 03/22/2023 | 1960156.32 | 0 | 2023-10-16 |  | 1
2022 | Region III | BULACAN | CALUMPIT (BULACAN) | P00620203LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.7431 | 14.913 | 91467420.21 | 91467153.21 | 2022 | TOPNOTCH CATALYST BUILDERS INC. | 1803 | 2022 | 2022-10-24 | 02/18/2022 | 267 | 0 | 2023-02-11 | 110
2023 | Region I | ILOCOS NORTE | VINTAR (ILOCOS NORTE) | P00725610LZ | Construction of Flood Mitigation Structure | 120.7434 | 18.3531 | 48999715.77 | 48249976.85 | 2023 | MEGAPOLITAN BUILDERS AND CONSTRUCTION SUPPLY | 1804 | 2023 | 2023-10-12 | 03/13/2023 | 749738.92 | 0 | 2024-01-11 | 91
2022 | Region III | TARLAC | LA PAZ (TARLAC) | P00620851LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.7439 | 15.4632 | 72857361.9 | 72855158.85 | 2022 | GVDPM CONSTRUCTION CORP. (FORMERLY: ZM CONSTRUCTIO | 1805 | 2022 | 2022-08-16 | 02/16/2022 | 2203.05 | 0 | 2022-08-15 |  | 1
2022 | Region III | PAMPANGA | MAGALANG (PAMPANGA) | P00637020LZ | Construction of Slope Protection Structure | 120.744 | 15.258 | 72373496.9 | 70946981.78 | 2022 | THREE-IN-ONE CONSTRUCTION & TRADING / P.V.B. CONSTRUCTION & TRADING | 1806 | 2022 | 2022-10-27 | 03/24/2022 | 1426515.12 | 0 | 2022-10-26 |  | 1
2022 | Region I | ILOCOS SUR | QUIRINO (ANGKAKI) (ILOCOS SUR) | P00632737LZ | Construction of Drainage Structure | 120.7445 | 17.1103 | 4950000 | 4949972.9 | 2023 | EJIEV CONSTRUCTION SERVICES | 1807 | 2022 | 2023-04-05 | 02/18/2022 | 27.1 | 0 | 2022-06-03 |  | 306
2024 | Cordillera Administrative Region | BENGUET | BOKOD (BENGUET) | P00848608LZ | Construction of Flood Mitigation Structure | 120.7447 | 16.4484 | 69300000 | 69235331.85 | 2024 | M.P. TABERAO CONSTRUCTION SERVICES AND SUPPLIES | 1808 | 2024 | 2024-12-16 | 06/19/2024 | 64668.15 | 0 | 2025-02-22 | 68
2022 | Region III | BULACAN | CALUMPIT (BULACAN) | P00630945LZ | Rehabilitation / Major Repair of Slope Protection Structure | 120.7449 | 14.9152 | 96499829.8 | 96498200.7 | 2023 | ST. TIMOTHY CONSTRUCTION CORPORATION | 1809 | 2022 | 2023-02-12 | 02/18/2022 | 1629.1 | 0 | 2023-02-11 |  | 1
2023 | Region III | TARLAC | LA PAZ (TARLAC) | P00727366LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.745 | 15.4475 | 48999752.63 | 47951981.5 | 2023 | L.S.D. CONSTRUCTION & SUPPLIES | 1810 | 2023 | 2023-09-18 | 02/28/2023 | 1047771.13 | 0 | 2023-09-21 | 3
2024 | Region III | NUEVA ECIJA | ZARAGOZA (NUEVA ECIJA) | P00845998LZ | Construction of Flood Mitigation Structure | 120.7452 | 15.4593 | 9900000 | 9800000 | 2025 | KYRO BUILDERS, INC. | 1811 | 2024 | 2025-02-24 | 08/01/2024 | 100000 | 0 | 2025-02-23 |  | 1
2023 | Region III | BULACAN | CALUMPIT (BULACAN) | P00740594LZ | Construction of Flood Mitigation Structure | 120.7453 | 14.9157 | 48999726.89 | 48999897.9 | 2023 | IM CONSTRUCTION CORPORATION | 1812 | 2023 | 2023-11-15 | 03/21/2023 | 0 | 171.01 | 2023-11-14 |  | 1
2023 | Region III | NUEVA ECIJA | GUIMBA (NUEVA ECIJA) | P00726509LZ | Construction of Flood Mitigation Structure | 120.7454 | 15.6656 | 96500000 | 96490005.53 | 2023 | AMP 723 CONSTRUCTION CORPORATION (FORMERLY: A.M.P. CONSTRUCTION) / M.M. SERRANO CONSTRUCTION COMPANY | 1813 | 2023 | 2023-12-14 | 02/28/2023 | 9994.47 | 0 | 2023-12-19 | 5
2022 | Region III | BULACAN | CALUMPIT (BULACAN) | P00631185LZ | Construction of Flood Mitigation Structure | 120.7454 | 14.918 | 44099230.86 | 44076500.35 | 2022 | J. SIMEON CONSTRUCTION | 1814 | 2022 | 2022-11-10 | 01/28/2022 | 22730.51 | 0 | 2022-12-22 | 42
2023 | Region III | BULACAN | HAGONOY (BULACAN) | P00737368LZ | Construction of Flood Mitigation Structure | 120.7458 | 14.8621 | 69299709.02 | 69298893.2 | 2023 | TOPNOTCH CATALYST BUILDERS INC. / BLACK HARDHAT INC. (FORMERLY: JCHARDHAT INC.) | 1815 | 2023 | 2023-09-07 | 02/13/2023 | 815.82 | 0 | 2023-12-08 | 92
2022 | Region IV-B | OCCIDENTAL MINDORO | ABRA DE ILOG (OCCIDENTAL MINDORO) | P00632929LZ | Construction of Flood Mitigation Structure | 120.7461 | 13.4477 | 44550000 | 27102768.74 | 2023 | SIXTEEN ENTERPRISES-CALAPAN BRANCH | 1816 | 2022 | 2023-10-16 | 02/24/2022 | 17447231.26 | 0 | 2022-10-28 |  | 353
2024 | Region I | PANGASINAN | TAYUG (PANGASINAN) | P00824655LZ | Construction of Dike | 120.7462 | 16.0319 | 19600000 | 19567078.7 | 2024 | R.A. MATIAS CONSTRUCTION AND DEVELOPERS INC. (FORMERLY : R.A. MATIAS CONSTRUCTION AND DEVELOPERS) | 1817 | 2024 | 2024-06-30 | 03/11/2024 | 32921.3 | 0 | 2024-08-15 | 46
2024 | Region I | PANGASINAN | TAYUG (PANGASINAN) | P00824796LZ | Construction of Flood Mitigation Structure | 120.7464 | 16.0312 | 19300000 | 19299456.67 | 2024 | R.A. MATIAS CONSTRUCTION AND DEVELOPERS INC. (FORMERLY : R.A. MATIAS CONSTRUCTION AND DEVELOPERS) | 1818 | 2024 | 2024-10-25 | 05/03/2024 | 543.33 | 0 | 2024-12-05 | 41
2024 | Region I | PANGASINAN | TAYUG (PANGASINAN) | P00825213LZ | Construction of Dike | 120.7466 | 16.0161 | 49000000 | 48257831.51 | 2024 | R.A. MATIAS CONSTRUCTION AND DEVELOPERS INC. (FORMERLY : R.A. MATIAS CONSTRUCTION AND DEVELOPERS) | 1819 | 2024 | 2024-08-15 | 02/21/2024 | 742168.49 | 0 | 2024-08-29 | 14
2023 | Region III | NUEVA ECIJA | GUIMBA (NUEVA ECIJA) | P00742334LZ | Construction of Flood Mitigation Structure | 120.7467 | 15.6733 | 4950000 | 4899504.18 | 2023 | R.D. TALENS CONSTRUCTION AND TRADING | 1820 | 2023 | 2023-07-27 | 06/07/2023 | 50495.82 | 0 | 2023-08-04 | 8
2024 | Region III | NUEVA ECIJA | GUIMBA (NUEVA ECIJA) | P00824702LZ | Construction of Flood Mitigation Structure | 120.7467 | 15.6233 | 24846920 | 24601942.33 | 2024 | MIVICO BUILDERS & DEVELOPERS | 1821 | 2024 | 2024-07-24 | 02/26/2024 | 244977.67 | 0 | 2024-07-23 |  | 1
2023 | Region III | NUEVA ECIJA | GUIMBA (NUEVA ECIJA) | P00726508LZ | Construction of Flood Mitigation Structure | 120.7467 | 15.6678 | 96500000 | 96494000 | 2023 | NIÃ‘AS CONSTRUCTION CORP. (FORMERLY: NINA'S CONSTRUCTION AND SUPPLIES) / SOLFIO P. JACINTO CONSTRUCTION INC. | 1822 | 2023 | 2023-12-14 | 02/22/2023 | 6000 | 0 | 2023-12-13 |  | 1
2024 | Region I | PANGASINAN | UMINGAN (PANGASINAN) | P00845911LZ | Construction of Dike | 120.7467 | 15.916 | 49500000 | 49443875.72 | 2024 | RS RODRIGUEZ CONSTRUCTION & SUPPLIES | 1823 | 2024 | 2024-06-15 | 02/29/2024 | 56124.28 | 0 | 2024-09-06 | 83
2023 | Region III | NUEVA ECIJA | GUIMBA (NUEVA ECIJA) | P00742335LZ | Construction of Flood Mitigation Structure | 120.7468 | 15.6678 | 9900000 | 9800528.41 | 2023 | R.D. TALENS CONSTRUCTION AND TRADING | 1824 | 2023 | 2023-10-04 | 06/07/2023 | 99471.59 | 0 | 2023-10-03 |  | 1
2024 | Region III | NUEVA ECIJA | GUIMBA (NUEVA ECIJA) | P00823429LZ | Construction of Flood Mitigation Structure | 120.747 | 15.6684 | 48250000 | 47767411.9 | 2024 | MIVICO BUILDERS & DEVELOPERS | 1825 | 2024 | 2024-12-09 | 04/29/2024 | 482588.1 | 0 | 2024-12-23 | 14
2024 | Region III | BULACAN | HAGONOY (BULACAN) | P00844501LZ | Construction of Flood Mitigation Structure | 120.7478 | 14.8159 | 67549804.71 | 67549901.28 | 2024 | SYMS CONSTRUCTION TRADING | 1826 | 2024 | 2024-06-11 | 03/11/2024 | 0 | 96.57 | 2024-11-04 | 146
2023 | Region I | ILOCOS NORTE | PIDDIG (ILOCOS NORTE) | P00726356LZ | Construction of Flood Mitigation Structure | 120.7478 | 18.1974 | 97465000 | 97464756.05 | 2023 | MGB CONSTRUCTION & TRADING | 1827 | 2023 | 2023-12-12 | 02/14/2023 | 243.95 | 0 | 2023-12-11 |  | 1
2024 | Region III | BULACAN | CALUMPIT (BULACAN) | P00843321LZ | Construction of Flood Mitigation Structure | 120.7478 | 14.9183 | 77199825.91 | 77187426.47 | 2024 | JAGONBUILD CONSTRUCTION CORP. (FOR. JAGON BUILDERS | 1828 | 2024 | 2024-11-05 | 03/11/2024 | 12399.44 | 0 | 2024-11-04 |  | 1
2024 | Region III | NUEVA ECIJA | GUIMBA (NUEVA ECIJA) | P00845997LZ | Construction of Flood Mitigation Structure | 120.748 | 15.673 | 4950000 | 4900498.26 | 2024 | MIVICO BUILDERS & DEVELOPERS | 1829 | 2024 | 2024-07-20 | 04/22/2024 | 49501.74 | 0 | 2024-07-19 |  | 1
2024 | Region III | BULACAN | CALUMPIT (BULACAN) | P00823465LZ | Construction of Flood Mitigation Structure | 120.7484 | 14.9173 | 67549958.68 | 67549453.28 | 2024 | 11-16 CONSTRUCTION | 1830 | 2024 | 2024-10-17 | 02/21/2024 | 505.4 | 0 | 2024-10-16 |  | 1
2022 | Cordillera Administrative Region | ABRA | LAGANGILANG (ABRA) | P00621563LZ | Construction of Flood Mitigation Structure | 120.7485 | 17.578 | 96500000 | 96497135 | 2023 | ST. TIMOTHY CONSTRUCTION CORPORATION | 1831 | 2022 | 2023-01-27 | 07/20/2022 | 2865 | 0 | 2023-03-12 | 44
2023 | Region I | ILOCOS NORTE | PIDDIG (ILOCOS NORTE) | P00726357LZ | Construction of Flood Mitigation Structure | 120.7486 | 18.1972 | 97465000 | 97464915.68 | 2023 | MGB CONSTRUCTION & TRADING | 1832 | 2023 | 2023-11-22 | 02/14/2023 | 84.32 | 0 | 2023-12-11 | 19
2024 | Region III | BULACAN | HAGONOY (BULACAN) | P00824697LZ | Construction of Revetment | 120.7487 | 14.8165 | 39199794.91 | 39199307.6 | 2024 | MICHARIAN BUILDERS AND TRADING | 1833 | 2024 | 2024-10-04 | 04/02/2024 | 487.31 | 0 | 2024-09-27 |  | 7
2022 | Region III | PAMPANGA | APALIT (PAMPANGA) | P00637777LZ | Construction of Drainage Structure | 120.7488 | 14.9426 | 4950000 | 4702569.67 | 2022 | LATO BUILDERS | 1834 | 2022 | 2022-07-11 | 05/26/2022 | 247430.33 | 0 | 2022-07-08 |  | 3
2024 | Region III | BULACAN | HAGONOY (BULACAN) | P00824696LZ | Construction of Revetment | 120.7489 | 14.8173 | 39199955.55 | 39199511.58 | 2024 | STAR WILLIAM CONSTRUCTION | 1835 | 2024 | 2024-10-12 | 04/16/2024 | 443.97 | 0 | 2024-10-11 |  | 1
2023 | Region III | TARLAC | LA PAZ (TARLAC) | P00727150LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.7492 | 15.4775 | 47627563.65 | 46436450.98 | 2023 | T2B3 BUILDERS AND SUPPLIES CORP. | 1836 | 2023 | 2023-06-11 | 02/28/2023 | 1191112.67 | 0 | 2023-07-23 | 42
2022 | Region I | ILOCOS NORTE | LAOAG CITY (CAPITAL) (ILOCOS NORTE) | P00620780LZ | Construction of Flood Mitigation Structure | 120.7496 | 18.2902 | 86850000 | 86850000 | 2023 | DYLAN EQUIPMENT CONSTRUCTION AND SUPPLIES / SKYLINE CONSTRUCTION, EQUIPMENT AND DEVELOPMENT CORPORATION(FORMERLY: EDDIE G. GUILLEN BUILDERS INC. | 1837 | 2022 | 2023-01-08 | 03/04/2022 | 0 | 0 | 2023-01-07 |  | 1
2024 | Region III | PAMPANGA | SANTA ANA (PAMPANGA) | P00846002LZ | Construction of Slope Protection Structure | 120.7498 | 15.0951 | 9900000 | 9345618.93 | 2025 | JKOJ CONSTRUCTION SUPPLIES TRADING | 1838 | 2024 | 2025-02-03 | 09/13/2024 | 554381.07 | 0 | 2025-01-27 |  | 7
2024 | Region I | PANGASINAN | TAYUG (PANGASINAN) | P00825214LZ | Construction of Dike | 120.75 | 16.0329 | 19600000 | 19563819.79 | 2024 | R.A. MATIAS CONSTRUCTION AND DEVELOPERS INC. (FORMERLY : R.A. MATIAS CONSTRUCTION AND DEVELOPERS) | 1839 | 2024 | 2024-09-26 | 05/27/2024 | 36180.21 | 0 | 2024-11-06 | 41
2024 | Region I | PANGASINAN | UMINGAN (PANGASINAN) | P00845912LZ | Construction of Dike | 120.7503 | 15.9178 | 49500000 | 49442175.71 | 2024 | RS RODRIGUEZ CONSTRUCTION & SUPPLIES | 1840 | 2024 | 2024-07-04 | 03/18/2024 | 57824.29 | 0 | 2024-09-24 | 82
2024 | Region III | TARLAC | CONCEPCION (TARLAC) | P00838446LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.7507 | 15.2788 | 96499329.91 | 96494656.2 | 2024 | JAGONBUILD CONSTRUCTION CORP. (FOR. JAGON BUILDERS | 1841 | 2024 | 2024-10-15 | 03/16/2024 | 4673.71 | 0 | 2024-10-14 |  | 1
2022 | Region III | TARLAC | CONCEPCION (TARLAC) | P00639373LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.7509 | 15.2626 | 50179743.9 | 50168947.82 | 2023 | 11-16 CONSTRUCTION | 1842 | 2022 | 2023-01-31 | 03/26/2022 | 10796.08 | 0 | 2022-12-07 |  | 55
2023 | Region III | BULACAN | HAGONOY (BULACAN) | P00735988LZ | Construction of Flood Mitigation Structure | 120.7511 | 14.8315 | 77199802.36 | 77199981.45 | 2023 | WAWAO BUILDERS | 1843 | 2023 | 2023-07-03 | 02/13/2023 | 0 | 179.09 | 2023-12-08 | 158
2024 | Region III | BULACAN | HAGONOY (BULACAN) | P00843302LZ | Construction of Flood Mitigation Structure | 120.7512 | 14.8394 | 72374787.39 | 72374051.06 | 2024 | TRICHES CONSTRUCTION & TRADING | 1844 | 2024 | 2024-11-05 | 03/11/2024 | 736.33 | 0 | 2024-11-04 |  | 1
2023 | Region III | BULACAN | HAGONOY (BULACAN) | P00726894LZ | Construction of Revetment | 120.7524 | 14.8171 | 57899792.13 | 57899990.29 | 2023 | TOPNOTCH CATALYST BUILDERS INC. | 1845 | 2023 | 2023-07-03 | 03/14/2023 | 0 | 198.16 | 2023-11-07 | 127
2023 | Region III | BULACAN | CALUMPIT (BULACAN) | P00735983LZ | Construction of Flood Mitigation Structure | 120.7524 | 14.915 | 77199864.07 | 77199999.65 | 2023 | WAWAO BUILDERS | 1846 | 2023 | 2023-07-03 | 02/13/2023 | 0 | 135.58 | 2023-12-08 | 158
2023 | Region III | BULACAN | HAGONOY (BULACAN) | P00735990LZ | Construction of Flood Mitigation Structure | 120.7524 | 14.8171 | 77199948.45 | 77199935.07 | 2023 | ALL EML CONSTRUCTION CORPORATION (FORMERLY: E.M.L. CONSTRUCTION & TRADING) | 1847 | 2023 | 2023-08-17 | 02/13/2023 | 13.38 | 0 | 2023-12-08 | 113
2023 | Region III | BULACAN | CALUMPIT (BULACAN) | P00740586LZ | Construction of Flood Mitigation Structure | 120.7528 | 14.915 | 48999719.21 | 48999979.8 | 2023 | DARCY & ANNA BUILDERS & TRADING | 1848 | 2023 | 2023-08-31 | 04/03/2023 | 0 | 260.59 | 2023-11-27 | 88
2023 | Region III | BULACAN | HAGONOY (BULACAN) | P00740378LZ | Construction of Flood Mitigation Structure | 120.7528 | 14.8158 | 144749736.4 | 144199874.9 | 2023 | FLORDES CONSTRUCTION & TRADING CORP. (FORMERLY FLO | 1849 | 2023 | 2023-10-24 | 03/28/2023 | 549861.5 | 0 | 2024-03-20 | 148
2023 | Region III | TARLAC | CONCEPCION (TARLAC) | P00727149LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.7529 | 15.3253 | 47725788.75 | 47696993.3 | 2023 | RAIK CONSTRUCTION AND DEVELOPMENT CORPORATION (FORMERLY: RAIK CONSTRUCTION AND SUPPLY) | 1850 | 2023 | 2023-05-05 | 02/28/2023 | 28795.45 | 0 | 2023-07-23 | 79
2022 | Region III | TARLAC | LA PAZ (TARLAC) | P00620849LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.7534 | 15.4405 | 72374727.06 | 72842742.3 | 2023 | STO. CRISTO CONSTRUCTION & TRADING INC. (FOR: STO. CRISTO CONSTRUCTION & TRADING) | 1851 | 2022 | 2023-02-28 | 02/16/2022 | 0 | 468015.24 | 2023-02-27 |  | 1
2022 | Region III | BULACAN | CALUMPIT (BULACAN) | P00632821LZ | Construction of Slope Protection Structure | 120.7537 | 14.9149 | 49499344.49 | 49498943.04 | 2022 | J. SIMEON CONSTRUCTION | 1852 | 2022 | 2022-09-21 | 01/28/2022 | 401.45 | 0 | 2022-11-22 | 62
2022 | Region III | PAMPANGA | APALIT (PAMPANGA) | P00640524LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.7544 | 14.9563 | 39600000 | 37619894 | 2022 | ALPHA & OMEGA GEN. CONTRACTOR & DEVELOPMENT CORP. | 1853 | 2022 | 2022-10-06 | 06/09/2022 | 1980106 | 0 | 2022-10-05 |  | 1
2023 | Region I | ILOCOS NORTE | VINTAR (ILOCOS NORTE) | P00725642LZ | Construction of Flood Mitigation Structure | 120.7544 | 18.3527 | 53074892.22 | 53074891.66 | 2023 | MEGAPOLITAN BUILDERS AND CONSTRUCTION SUPPLY | 1854 | 2023 | 2023-09-15 | 04/20/2023 | 0.56 | 0 | 2023-12-31 | 107
2024 | Region III | NUEVA ECIJA | LICAB (NUEVA ECIJA) | P00824701LZ | Construction of Flood Mitigation Structure | 120.7549 | 15.5515 | 24500000 | 24254959.8 | 2024 | AMP 723 CONSTRUCTION CORPORATION (FORMERLY: A.M.P. CONSTRUCTION) | 1855 | 2024 | 2024-08-21 | 05/03/2024 | 245040.2 | 0 | 2024-10-28 | 68
2022 | Region III | NUEVA ECIJA | GUIMBA (NUEVA ECIJA) | P00620167LZ | Construction of Flood Mitigation Structure | 120.7551 | 15.588 | 67550000 | 67550000 | 2023 | SOLFIO P. JACINTO CONSTRUCTION INC. / MIVICO BUILDERS & DEVELOPERS | 1856 | 2022 | 2023-03-26 | 03/02/2022 | 0 | 0 | 2023-03-25 |  | 1
2024 | Region III | NUEVA ECIJA | GUIMBA (NUEVA ECIJA) | P00824700LZ | Construction of Flood Mitigation Structure | 120.7553 | 15.5893 | 49000000 | 48514625.05 | 2024 | IJK MAE CONSTRUCTION INC. | 1857 | 2024 | 2024-12-10 | 03/06/2024 | 485374.95 | 0 | 2024-12-09 |  | 1
2024 | Region III | PAMPANGA | APALIT (PAMPANGA) | P00820260LZ | Construction of Slope Protection Structure | 120.7556 | 14.9566 | 77200000 | 74883257.96 | 2024 | STO. CRISTO CONSTRUCTION & TRADING INC. (FOR: STO. CRISTO CONSTRUCTION & TRADING) | 1858 | 2024 | 2024-11-11 | 03/01/2024 | 2316742.04 | 0 | 2024-12-12 | 31
2022 | Region III | PAMPANGA | SAN SIMON (PAMPANGA) | P00631241LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.7556 | 15.0029 | 39200000 | 37239412.88 | 2022 | NES-SAN BUILDERS | 1859 | 2022 | 2022-10-02 | 03/25/2022 | 1960587.12 | 0 | 2022-07-21 |  | 73
2022 | Region I | PANGASINAN | UMINGAN (PANGASINAN) | P00620969LZ | Construction of Revetment | 120.7558 | 15.9297 | 19600000 | 19403532.01 | 2023 | A.C. SOLIVEN CONSTRUCTION & GENERAL MERCHANDISE | 1860 | 2022 | 2023-02-21 | 02/24/2022 | 196467.99 | 0 | 2022-07-31 |  | 205
2022 | Region III | NUEVA ECIJA | LICAB (NUEVA ECIJA) | P00621162LZ | Construction of Flood Mitigation Structure | 120.7559 | 15.5463 | 96500000 | 96500000 | 2023 | NIÃ‘AS CONSTRUCTION CORP. (FORMERLY: NINA'S CONSTRUCTION AND SUPPLIES) / SOLFIO P. JACINTO CONSTRUCTION INC. | 1861 | 2022 | 2023-01-29 | 04/05/2022 | 0 | 0 | 2023-02-27 | 29
2023 | Region I | ILOCOS NORTE | SOLSONA (ILOCOS NORTE) | P00726841LZ | Construction of Flood Mitigation Structure | 120.756 | 18.0742 | 96500000 | 96499954.31 | 2023 | RCD GEN. CONTRACTOR & CONSTRUCTION SUPPLY / A.P.B. CONSTRUCTION | 1862 | 2023 | 2023-06-26 | 03/17/2023 | 45.69 | 0 | 2023-10-27 | 123
2023 | Region III | NUEVA ECIJA | LICAB (NUEVA ECIJA) | P00725725LZ | Construction of Flood Mitigation Structure | 120.756 | 15.5455 | 96500000 | 96495000 | 2023 | AMP 723 CONSTRUCTION CORPORATION (FORMERLY: A.M.P. CONSTRUCTION) / IJK MAE CONSTRUCTION INC. | 1863 | 2023 | 2023-09-08 | 02/22/2023 | 5000 | 0 | 2023-11-17 | 70
2023 | Region III | NUEVA ECIJA | LICAB (NUEVA ECIJA) | P00725709LZ | Construction of Flood Mitigation Structure | 120.7563 | 15.546 | 96500000 | 96494899.85 | 2023 | AMP 723 CONSTRUCTION CORPORATION (FORMERLY: A.M.P. CONSTRUCTION) / KEVIN PAUL CONSTRUCTION | 1864 | 2023 | 2023-11-15 | 02/22/2023 | 5100.15 | 0 | 2024-01-16 | 62
2024 | Region III | BULACAN | HAGONOY (BULACAN) | P00844511LZ | Construction of Flood Mitigation Structure | 120.7565 | 14.775 | 72374731.83 | 72371115.87 | 2024 | FRAMECON BUILDERS | 1865 | 2024 | 2024-12-13 | 04/18/2024 | 3615.96 | 0 | 2024-12-12 |  | 1
2023 | Region III | NUEVA ECIJA | LICAB (NUEVA ECIJA) | P00726164LZ | Construction of Flood Mitigation Structure | 120.7567 | 15.5438 | 49000000 | 48993969 | 2023 | DGSARM BUILDERS INC. (FORMERLY: D.G. SARMENTA CONSTRUCTION) | 1866 | 2023 | 2023-08-25 | 02/15/2023 | 6031 | 0 | 2023-09-11 | 17
2022 | Region III | TARLAC | LA PAZ (TARLAC) | P00621576LZ | Construction of Dike | 120.7568 | 15.4395 | 96499475.97 | 94547166.18 | 2022 | ROYAL CROWN MONARCH CONSTRUCTION & SUPPLIES CORP. | 1867 | 2022 | 2022-11-24 | 03/26/2022 | 1952309.79 | 0 | 2022-11-23 |  | 1
2023 | Region I | ILOCOS NORTE | VINTAR (ILOCOS NORTE) | P00725643LZ | Construction of Flood Mitigation Structure | 120.757 | 18.3537 | 57899735.81 | 57899734.38 | 2023 | MEGAPOLITAN BUILDERS AND CONSTRUCTION SUPPLY | 1868 | 2023 | 2023-09-15 | 03/13/2023 | 1.43 | 0 | 2023-12-07 | 83
2024 | Region III | TARLAC | LA PAZ (TARLAC) | P00821307LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.7574 | 15.4091 | 96498897.46 | 96497852.71 | 2024 | A.C. SOLIVEN CONSTRUCTION & GENERAL MERCHANDISE | 1869 | 2024 | 2024-05-23 | 02/20/2024 | 1044.75 | 0 | 2024-08-20 | 89
2024 | Region III | BULACAN | CALUMPIT (BULACAN) | P00823466LZ | Construction of Flood Mitigation Structure | 120.7576 | 14.9146 | 77199988.14 | 77199509.85 | 2024 | 11-16 CONSTRUCTION | 1870 | 2024 | 2024-10-17 | 02/21/2024 | 478.29 | 0 | 2024-10-16 |  | 1
2024 | Region IV-B | DAVAO DEL SUR | SANTA CRUZ (DAVAO DEL SUR) | P00820969LZ | Construction of Flood Mitigation Structure | 120.7581 | 13.0976 | 49000000 | 48995667.09 | 2024 | AMETHYST HORIZON BUILDERS AND GEN. CONTRACTOR AND DEVELOPMENT CORP. | 1871 | 2024 | 2024-07-24 | 02/06/2024 | 4332.91 | 0 | 2024-08-24 | 31
2023 | Region I | ILOCOS NORTE | VINTAR (ILOCOS NORTE) | P00725638LZ | Construction of Flood Mitigation Structure | 120.7582 | 18.39 | 53074754.2 | 53074753.39 | 2023 | KATHA BUILDERS & SUPPLIES INC. | 1872 | 2023 | 2023-09-18 | 03/13/2023 | 0.81 | 0 | 2023-11-23 | 66
2024 | Region III | TARLAC | CONCEPCION (TARLAC) | P00838438LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.7582 | 15.3226 | 96499387.14 | 96497823.04 | 2025 | ROYAL CROWN MONARCH CONSTRUCTION & SUPPLIES CORP. | 1873 | 2024 | 2025-01-27 | 02/24/2024 | 1564.1 | 0 | 2024-08-24 |  | 156
2024 | Region III | NUEVA ECIJA | LICAB (NUEVA ECIJA) | P00823471LZ | Construction of Flood Mitigation Structure | 120.7589 | 15.5375 | 48250000 | 47767298.86 | 2024 | M.M. SERRANO CONSTRUCTION COMPANY | 1874 | 2024 | 2024-08-28 | 04/01/2024 | 482701.14 | 0 | 2024-10-26 | 59
2023 | Region I | ILOCOS NORTE | SOLSONA (ILOCOS NORTE) | P00725590LZ | Construction of Drainage Structure | 120.759 | 18.112 | 9650000 | 9649819.12 | 2023 | RCD GEN. CONTRACTOR & CONSTRUCTION SUPPLY | 1875 | 2023 | 2023-06-15 | 03/14/2023 | 180.88 | 0 | 2023-06-22 | 7
2022 | Region IV-A | BATANGAS | BALAYAN (BATANGAS) | P00631279LZ | Construction of Flood Mitigation Structure | 120.7594 | 13.9332 | 49000000 | 49000000 | 2022 | HGG BUILDERS & SUPPLY | 1876 | 2022 | 2022-11-30 | 03/28/2022 | 0 | 0 | 2022-12-07 | 7
2023 | Cordillera Administrative Region | ABRA | SALLAPADAN (ABRA) | P00726390LZ | Construction of Flood Mitigation Structure | 120.7594 | 17.44 | 77199923.53 | 77200000 | 2023 | MG SAMIDAN CONSTRUCTION | 1877 | 2023 | 2023-12-07 | 04/17/2023 | 0 | 76.47 | 2024-01-14 | 38
2024 | Region III | TARLAC | LA PAZ (TARLAC) | P00821306LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.7595 | 15.4124 | 96499491.16 | 96497236.09 | 2024 | ROYAL CROWN MONARCH CONSTRUCTION & SUPPLIES CORP. | 1878 | 2024 | 2024-08-25 | 02/24/2024 | 2255.07 | 0 | 2024-08-24 |  | 1
2023 | Region I | ILOCOS NORTE | VINTAR (ILOCOS NORTE) | P00725611LZ | Construction of Flood Mitigation Structure | 120.7596 | 18.3551 | 58799628.16 | 57899999.73 | 2023 | MEGAPOLITAN BUILDERS AND CONSTRUCTION SUPPLY | 1879 | 2023 | 2023-10-12 | 03/13/2023 | 899628.43 | 0 | 2023-10-16 | 4
2022 | Region III | NUEVA ECIJA | GUIMBA (NUEVA ECIJA) | P00620149LZ | Construction of Flood Mitigation Structure | 120.7598 | 15.5727 | 91675000 | 91675000 | 2022 | AMP 723 CONSTRUCTION CORPORATION (FORMERLY: A.M.P. CONSTRUCTION) | 1880 | 2022 | 2022-12-12 | 02/15/2022 | 0 | 0 | 2023-01-09 | 28
2024 | Region III | NUEVA ECIJA | LICAB (NUEVA ECIJA) | P00823436LZ | Construction of Flood Mitigation Structure | 120.7602 | 15.5339 | 38600000 | 38217763.57 | 2024 | M.M. SERRANO CONSTRUCTION COMPANY | 1881 | 2024 | 2024-08-28 | 04/01/2024 | 382236.43 | 0 | 2024-09-26 | 29
2023 | Region III | BULACAN | HAGONOY (BULACAN) | P00726899LZ | Construction of Revetment | 120.7603 | 14.8128 | 67549800.48 | 67531685.86 | 2023 | TRIPLE 8 CONSTRUCTION & SUPPLY, INC. (FORMERLY TRIPLE 8 CONST. & SUPPLY) | 1882 | 2023 | 2023-12-18 | 03/14/2023 | 18114.62 | 0 | 2024-01-06 | 19
2024 | Region IV-B | DAVAO DEL SUR | SANTA CRUZ (DAVAO DEL SUR) | P00824744LZ | Construction of Flood Mitigation Structure | 120.7605 | 13.0627 | 14700000 | 14699104.72 | 2024 | D. DOLOR CONSTRUCTION | 1883 | 2024 | 2024-06-25 | 02/14/2024 | 895.28 | 0 | 2024-06-24 |  | 1
2023 | Region III | BULACAN | HAGONOY (BULACAN) | P00726900LZ | Construction of Revetment | 120.7607 | 14.8148 | 72374969.24 | 72373326.83 | 2024 | TRIPLE 8 CONSTRUCTION & SUPPLY, INC. (FORMERLY TRIPLE 8 CONST. & SUPPLY) | 1884 | 2023 | 2024-01-07 | 03/14/2023 | 1642.41 | 0 | 2024-01-06 |  | 1
2024 | Region III | TARLAC | LA PAZ (TARLAC) | P00821222LZ | Construction of Slope Protection Structure | 120.7609 | 15.4246 | 62724566.22 | 62593237.4 | 2024 | T2B3 BUILDERS AND SUPPLIES CORP. / RPV RED MOUNTAIN KONSTRUCT, INC. | 1885 | 2024 | 2024-08-11 | 02/20/2024 | 131328.82 | 0 | 2024-08-10 |  | 1
2024 | Region III | BULACAN | HAGONOY (BULACAN) | P00823452LZ | Construction of Revetment | 120.761 | 14.8183 | 38599906.81 | 38599137.21 | 2024 | SYMS CONSTRUCTION TRADING | 1886 | 2024 | 2024-10-19 | 04/23/2024 | 769.6 | 0 | 2024-10-18 |  | 1
2023 | Region I | ILOCOS NORTE | VINTAR (ILOCOS NORTE) | P00726354LZ | Construction of Flood Mitigation Structure | 120.761 | 18.3953 | 78399736.25 | 77199998.67 | 2023 | KATHA BUILDERS & SUPPLIES INC. | 1887 | 2023 | 2023-10-12 | 03/13/2023 | 1199737.58 | 0 | 2024-01-14 | 94
2022 | Region III | TARLAC | LA PAZ (TARLAC) | P00620848LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.7611 | 15.4163 | 73214793.89 | 73212660.32 | 2023 | STO. CRISTO CONSTRUCTION & TRADING INC. (FOR: STO. CRISTO CONSTRUCTION & TRADING) | 1888 | 2022 | 2023-03-15 | 02/16/2022 | 2133.57 | 0 | 2023-03-14 |  | 1
2024 | Region III | PAMPANGA | APALIT (PAMPANGA) | P00820245LZ | Construction of Revetment | 120.7617 | 14.936 | 77200000 | 74883912.45 | 2025 | EDDMARI CONSTRUCTION & TRADING | 1889 | 2024 | 2025-03-05 | 05/22/2024 | 2316087.55 | 0 | 2025-03-04 |  | 1
2023 | Region III | TARLAC | LA PAZ (TARLAC) | P00726739LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.7618 | 15.4176 | 46059071.4 | 44466852.2 | 2023 | A.C. SOLIVEN CONSTRUCTION & GENERAL MERCHANDISE | 1890 | 2023 | 2023-05-09 | 01/31/2023 | 1592219.2 | 0 | 2023-06-25 | 47
2023 | Region III | BULACAN | HAGONOY (BULACAN) | P00736008LZ | Construction of Revetment | 120.7622 | 14.878 | 28949304.9 | 28949442.09 | 2023 | MICHARIAN BUILDERS AND TRADING | 1891 | 2023 | 2023-09-10 | 02/13/2023 | 0 | 137.19 | 2023-09-09 |  | 1
2023 | Region I | ILOCOS NORTE | BANGUI (ILOCOS NORTE) | P00726048LZ | Construction of Flood Mitigation Structure | 120.7635 | 18.5353 | 29399646.31 | 29399566.58 | 2023 | BADOC BUILDERS & SUPPLY, INC. (FORMERLY: BADOC BUILDER & SUPPLY | 1892 | 2023 | 2023-06-20 | 02/13/2023 | 79.73 | 0 | 2023-09-14 | 86
2024 | Region III | BULACAN | HAGONOY (BULACAN) | P00838395LZ | Construction of Slope Protection Structure | 120.7641 | 14.8609 | 77199986.3 | 77199918.56 | 2024 | DARCY & ANNA BUILDERS & TRADING | 1893 | 2024 | 2024-04-19 | 02/07/2024 | 67.74 | 0 | 2024-10-02 | 166
2024 | Region IV-B | DAVAO DEL SUR | SANTA CRUZ (DAVAO DEL SUR) | P00820967LZ | Construction of Flood Mitigation Structure | 120.7649 | 13.0621 | 19600000 | 19598756.65 | 2024 | KEJAMARENIK CONSTRUCTION & CONSTRUCTION SUPPLIES | 1894 | 2024 | 2024-07-19 | 02/06/2024 | 1243.35 | 0 | 2024-07-18 |  | 1
2024 | Region I | PANGASINAN | UMINGAN (PANGASINAN) | P00845908LZ | Construction of Dike | 120.7652 | 15.9136 | 29700000 | 29635732.16 | 2024 | AMP 723 CONSTRUCTION CORPORATION (FORMERLY: A.M.P. CONSTRUCTION) | 1895 | 2024 | 2024-10-13 | 04/19/2024 | 64267.84 | 0 | 2024-10-12 |  | 1
2022 | Region I | PANGASINAN | TAYUG (PANGASINAN) | P00620978LZ | Construction of Revetment | 120.7653 | 16.0231 | 49000000 | 47518542.66 | 2022 | R.A. MATIAS CONSTRUCTION AND DEVELOPERS INC. (FORMERLY : R.A. MATIAS CONSTRUCTION AND DEVELOPERS) | 1896 | 2022 | 2022-09-03 | 02/24/2022 | 1481457.34 | 0 | 2022-09-02 |  | 1
2024 | Region III | BULACAN | HAGONOY (BULACAN) | P00823356LZ | Construction of Flood Mitigation Structure | 120.7656 | 14.8604 | 77199919.57 | 77199909.53 | 2024 | 11-16 CONSTRUCTION | 1897 | 2024 | 2024-10-24 | 02/28/2024 | 10.04 | 0 | 2024-10-23 |  | 1
2021 | Cordillera Administrative Region | ABRA |  | P00561499LZ | Construction of Flood Mitigation Structure | 120.7656 | 17.4558 | 97999929.55 | 96500000 | 2022 | 739 BUILDERS | 1898 | 2021 | 2022-10-08 | 01/11/2022 | 1499929.55 | 0 | 2022-10-07 |  | 1
2024 | Region III | BULACAN | HAGONOY (BULACAN) | P00838384LZ | Construction of Slope Protection Structure | 120.7657 | 14.8535 | 77199985.83 | 77199988.25 | 2024 | DARCY & ANNA BUILDERS & TRADING | 1899 | 2024 | 2024-04-22 | 02/07/2024 | 0 | 2.42 | 2024-10-02 | 163
2021 | Cordillera Administrative Region | BENGUET |  | P00561458LZ | Construction of Flood Mitigation Structure | 120.7658 | 16.9181 | 96486192.7 | 96500000 | 2022 | RODEKOM GENERAL CONSTRUCTION AND ENTERPRISE | 1900 | 2021 | 2022-09-03 | 01/07/2022 | 0 | 13807.3 | 2022-09-02 |  | 1
2024 | Region III | PAMPANGA | GUAGUA (PAMPANGA) | P00823367LZ | Construction of Slope Protection Structure | 120.6372 | 14.9752 | 96499033.02 | 96493832.58 | 2024 | FERDSTAR BUILDERS INC. | 1901 | 2024 | 2024-12-25 | 04/15/2024 | 5200.44 | 0 | 2024-12-24 |  | 1
2024 | Region I | ILOCOS NORTE | SARRAT (ILOCOS NORTE) | P00820684LZ | Construction of Flood Mitigation Structure | 120.6375 | 18.1246 | 48999925.42 | 48999922.21 | 2024 | NORTH TECH BUILDERS AND CONSTRUCTION SUPPLY / RED JEWEL BUILDERS | 1902 | 2024 | 2024-06-07 | 02/13/2024 | 3.21 | 0 | 2024-08-01 | 55
2022 | Region III | PAMPANGA | BACOLOR (PAMPANGA) | P00631238LZ | Construction of Dike | 120.6379 | 15.0373 | 46500000 | 44174884 | 2022 | B-12 CONSTRUCTION AND TRADING CORPORATION | 1903 | 2022 | 2022-08-19 | 03/23/2022 | 2325116 | 0 | 2022-08-18 |  | 1
2022 | Region III | PAMPANGA | MAGALANG (PAMPANGA) | P00632840LZ | Construction of Slope Protection Structure | 120.6381 | 15.2676 | 19597956.57 | 18974602.76 | 2022 | M.C.J. VALENZUELA CONSTRUCTION ENTERPRISES | 1904 | 2022 | 2022-07-04 | 02/08/2022 | 623353.81 | 0 | 2022-07-03 |  | 1
2022 | Region III | PAMPANGA | ANGELES CITY (PAMPANGA) | P00630942LZ | Rehabilitation / Major Repair of Slope Protection Structure | 120.6387 | 15.1507 | 58791612.58 | 57866110.17 | 2022 | HGG BUILDERS & SUPPLY | 1905 | 2022 | 2022-11-11 | 03/17/2022 | 925502.41 | 0 | 2022-11-10 |  | 1
2023 | Region III | TARLAC | CONCEPCION (TARLAC) | P00726515LZ | Construction of Groundsill | 120.6396 | 15.2936 | 86849910.65 | 86826737.78 | 2023 | STO. CRISTO CONSTRUCTION & TRADING INC. (FOR: STO. CRISTO CONSTRUCTION & TRADING) | 1906 | 2023 | 2023-08-09 | 02/07/2023 | 23172.87 | 0 | 2023-08-08 |  | 1
2023 | Region III | TARLAC | RAMOS (TARLAC) | P00742374LZ | Construction of Slope Protection Structure | 120.6396 | 15.6636 | 14850000 | 14850000 | 2023 | NIECER TRADING AND BUILDER COMPANY INC. | 1907 | 2023 | 2023-07-18 | 03/29/2023 | 0 | 0 | 2023-07-24 | 6
2025 | Region III | TARLAC | RAMOS (TARLAC) | P00921072LZ | Construction of Flood Mitigation Structure | 120.6398 | 15.6841 | 49000000 | 47496290.56 | 2025 | GJE BUILDERS CORPORATION (FORMERLY: GJE BUILDERS) | 1908 | 2025 | 2025-04-16 | 01/27/2025 | 1503709.44 | 0 | 2025-07-25 | 100
2023 | Region III | PAMPANGA | GUAGUA (PAMPANGA) | P00742343LZ | Construction of Slope Protection Structure | 120.6401 | 14.9513 | 29699359.49 | 29694402.01 | 2023 | CEDAR CONSTRUCTION | 1909 | 2023 | 2023-09-01 | 04/05/2023 | 4957.48 | 0 | 2023-08-31 |  | 1
2024 | Region III | NUEVA ECIJA | NAMPICUAN (NUEVA ECIJA) | P00845995LZ | Construction of Drainage Structure | 120.6401 | 15.7412 | 4950000 | 4900504 | 2024 | MJ O. BETIS BUILDERS | 1910 | 2024 | 2024-08-19 | 06/21/2024 | 49496 | 0 | 2024-08-18 |  | 1
2023 | Cordillera Administrative Region | ABRA | LA PAZ (ABRA) | P00740305LZ | Construction of Flood Mitigation Structure | 120.6412 | 17.6335 | 144749968.2 | 144747500 | 2023 | 739 BUILDERS | 1911 | 2023 | 2023-12-24 | 04/14/2023 | 2468.2 | 0 | 2023-12-23 |  | 1
2022 | Cordillera Administrative Region | ABRA | LA PAZ (ABRA) | P00637009LZ | Construction of Flood Mitigation Structure | 120.6412 | 17.6339 | 96499992.73 | 96497000 | 2022 | 739 BUILDERS | 1912 | 2022 | 2022-12-05 | 06/20/2022 | 2992.73 | 0 | 2023-03-23 | 108
2022 | Region III | PAMPANGA | BACOLOR (PAMPANGA) | P00631239LZ | Construction of Dike | 120.6417 | 15.0285 | 49000000 | 47284965.33 | 2022 | ROYAL CROWN MONARCH CONSTRUCTION & SUPPLIES CORP. | 1913 | 2022 | 2022-07-23 | 02/24/2022 | 1715034.67 | 0 | 2022-07-22 |  | 1
2024 | Cordillera Administrative Region | ABRA | LA PAZ (ABRA) | P00839466LZ | Construction of Flood Mitigation Structure | 120.642 | 17.6551 | 144750000 | 148497500.8 | 2024 | MG SAMIDAN CONSTRUCTION | 1914 | 2024 | 2024-09-18 | 02/19/2024 | 0 | 3747500.8 | 2024-11-26 | 69
2023 | Region III | PAMPANGA | SASMUAN (SEXMOAN) (PAMPANGA) | P00726175LZ | Construction of Slope Protection Structure | 120.6421 | 14.9227 | 29399219.48 | 29392979.38 | 2023 | R.M. VITUG CONSTRUCTION | 1915 | 2023 | 2023-06-07 | 02/27/2023 | 6240.1 | 0 | 2023-07-25 | 48
2021 | Cordillera Administrative Region | ABRA |  | P00561514LZ | Construction of Flood Mitigation Structure | 120.6422 | 17.5553 | 97999990 | 96497036.15 | 2022 | ST. TIMOTHY CONSTRUCTION CORPORATION | 1916 | 2021 | 2022-07-28 | 01/17/2022 | 1502953.85 | 0 | 2022-10-20 | 84
2024 | Region III | TARLAC | CAPAS (TARLAC) | P00821301LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.6422 | 15.2812 | 96499518.55 | 96497427.33 | 2024 | ALPIZ CONSTRUCTION & DEVELOPMENT CORPORATION | 1917 | 2024 | 2024-08-21 | 02/20/2024 | 2091.22 | 0 | 2024-08-20 |  | 1
2021 | Region III | TARLAC |  | P00526057LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.6426 | 15.38 | 14699370.29 | 14031745.6 | 2022 | LAP GLOBAL CONSTRUCTION CORPORATION(FORMERLY LAP GLOBAL CONSTRUCTION) | 1918 | 2021 | 2022-07-17 | 03/24/2022 | 667624.69 | 0 | 2022-07-21 | 4
2024 | Region I | ILOCOS NORTE | VINTAR (ILOCOS NORTE) | P00820679LZ | Construction of Flood Mitigation Structure | 120.644 | 18.2367 | 24499913.15 | 24499910.02 | 2024 | HEKLER BUILDERS CORP. | 1919 | 2024 | 2024-08-14 | 02/27/2024 | 3.13 | 0 | 2024-08-13 |  | 1
2024 | Region III | TARLAC | RAMOS (TARLAC) | P00820863LZ | Construction of Slope Protection Structure | 120.6447 | 15.6815 | 49000000 | 50000000 | 2024 | GJE BUILDERS CORPORATION (FORMERLY: GJE BUILDERS) | 1920 | 2024 | 2024-08-19 | 01/26/2024 | 0 | 1000000 | 2024-09-21 | 33
2022 | Region III | PAMPANGA | MAGALANG (PAMPANGA) | P00632839LZ | Construction of Slope Protection Structure | 120.6448 | 15.259 | 19597353.47 | 19589296.02 | 2022 | SAN SEBASTIAN CONSTRUCTION | 1921 | 2022 | 2022-07-04 | 02/08/2022 | 8057.45 | 0 | 2022-07-03 |  | 1
2023 | Region III | PAMPANGA | MAGALANG (PAMPANGA) | P00740360LZ | Construction of Slope Protection Structure | 120.645 | 15.2593 | 62710621.21 | 62698462.89 | 2023 | THREE-IN-ONE CONSTRUCTION & TRADING / P.V.B. CONSTRUCTION & TRADING | 1922 | 2023 | 2023-11-09 | 05/24/2023 | 12158.32 | 0 | 2023-11-08 |  | 1
2024 | Region I | ILOCOS NORTE | SARRAT (ILOCOS NORTE) | P00824639LZ | Construction of Flood Mitigation Structure | 120.645 | 18.1336 | 39199950.6 | 39199934.38 | 2024 | BJMJB CONSTRUCTION & SUPPLY | 1923 | 2024 | 2024-06-07 | 03/04/2024 | 16.22 | 0 | 2024-09-04 | 89
2022 | Region I | ILOCOS NORTE | BURGOS (ILOCOS NORTE) | P00639417LZ | Construction of Dike | 120.6452 | 18.5103 | 48999686.33 | 48251876.53 | 2023 | ASIAN PEARL CONSTRUCTION & DEVT. CORP. | 1924 | 2022 | 2023-02-07 | 04/04/2022 | 747809.8 | 0 | 2023-02-06 |  | 1
2023 | Region III | TARLAC | CITY OF TARLAC (CAPITAL) (TARLAC) | P00742376LZ | Construction of Slope Protection Structure | 120.6459 | 15.4776 | 74250000 | 73134542.26 | 2023 | CDC CONSTRUCTION & SUPPLIES | 1925 | 2023 | 2023-08-18 | 03/23/2023 | 1115457.74 | 0 | 2023-10-19 | 62
2023 | Region I | ILOCOS NORTE | SARRAT (ILOCOS NORTE) | P00726042LZ | Construction of Flood Mitigation Structure | 120.6462 | 18.1315 | 39199472.83 | 39198999.12 | 2023 | CMG JR. BUILDERS | 1926 | 2023 | 2023-06-21 | 02/17/2023 | 473.71 | 0 | 2023-06-20 |  | 1
2022 | Cordillera Administrative Region | BENGUET | ITOGON (BENGUET) | P00639442LZ | Construction of Flood Mitigation Structure | 120.6469 | 16.3795 | 1960000 | 1957356.76 | 2022 | NINETY ONE BUILDERS | 1927 | 2022 | 2022-09-14 | 07/18/2022 | 2643.24 | 0 | 2022-09-13 |  | 1
2023 | Region III | PAMPANGA | GUAGUA (PAMPANGA) | P00740612LZ | Construction of Slope Protection Structure | 120.6469 | 14.9814 | 29398018.42 | 28663290.77 | 2023 | M.C. GERONIMO CONSTRUCTION AND TRADING | 1928 | 2023 | 2023-06-15 | 04/26/2023 | 734727.65 | 0 | 2023-08-22 | 68
2022 | Region III | PAMPANGA | GUAGUA (PAMPANGA) | P00639359LZ | Construction of Slope Protection Structure | 120.6469 | 14.9812 | 96499993.68 | 96491313.16 | 2022 | FERDSTAR BUILDERS INC. | 1929 | 2022 | 2022-11-27 | 06/01/2022 | 8680.52 | 0 | 2022-11-26 |  | 1
2022 | Region III | TARLAC | CONCEPCION (TARLAC) | P00637023LZ | Construction of Slope Protection Structure | 120.6472 | 15.2999 | 96499518.84 | 93169679.22 | 2022 | FERDSTAR BUILDERS INC. | 1930 | 2022 | 2022-11-24 | 03/26/2022 | 3329839.62 | 0 | 2022-11-23 |  | 1
2021 | Cordillera Administrative Region | ABRA |  | P00561505LZ | Construction of Flood Mitigation Structure | 120.6474 | 17.5548 | 97999951.72 | 96497024.03 | 2022 | ST. TIMOTHY CONSTRUCTION CORPORATION | 1931 | 2021 | 2022-07-21 | 01/13/2022 | 1502927.69 | 0 | 2022-10-16 | 87
2024 | Region III | PAMPANGA | MEXICO (PAMPANGA) | P00839588LZ | Construction of Drainage Structure | 120.648 | 15.1702 | 6930000 | 6562708.65 | 2024 | DAUNGAN CONSTRUCTION DEV'T. & GEN. SUPPLIES CO., INC. | 1932 | 2024 | 2024-10-21 | 02/07/2024 | 367291.35 | 0 | 2024-06-06 |  | 137
2022 | Region III | PAMPANGA | GUAGUA (PAMPANGA) | P00637026LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.648 | 14.9655 | 96499419.88 | 96476999.14 | 2022 | FERDSTAR BUILDERS INC. | 1933 | 2022 | 2022-12-13 | 04/18/2022 | 22420.74 | 0 | 2022-12-12 |  | 1
2023 | Cordillera Administrative Region | ABRA | TAYUM (ABRA) | P00726394LZ | Construction of Flood Mitigation Structure | 120.6483 | 17.6214 | 96499879.44 | 96500000 | 2023 | MG SAMIDAN CONSTRUCTION | 1934 | 2023 | 2023-07-28 | 03/30/2023 | 0 | 120.56 | 2023-12-31 | 156
2023 | Region III | PAMPANGA | MAGALANG (PAMPANGA) | P00742364LZ | Construction of Slope Protection Structure | 120.6484 | 15.261 | 19777019.85 | 19797019.05 | 2023 | M.C.J. VALENZUELA CONSTRUCTION ENTERPRISES | 1935 | 2023 | 2023-10-20 | 05/24/2023 | 0 | 19999.2 | 2023-10-19 |  | 1
2023 | Region III | PAMPANGA | MABALACAT CITY (PAMPANGA) | P00740321LZ | Construction of Flood Mitigation Structure | 120.6484 | 15.261 | 67541764.68 | 67541531.91 | 2023 | R.D. POLICARPIO & COMPANY INC. | 1936 | 2023 | 2023-11-17 | 05/22/2023 | 232.77 | 0 | 2023-11-16 |  | 1
2023 | Region III | PAMPANGA | MAGALANG (PAMPANGA) | P00727142LZ | Construction of Slope Protection Structure | 120.6497 | 15.225 | 48994284.98 | 48938390.76 | 2023 | C.L. MORALES CONSTRUCTION AND TRADING | 1937 | 2023 | 2023-09-29 | 04/25/2023 | 55894.22 | 0 | 2023-09-20 |  | 9
2023 | Region III | PAMPANGA | MAGALANG (PAMPANGA) | P00740322LZ | Construction of Slope Protection Structure | 120.6497 | 15.225 | 57890506.12 | 57889523.69 | 2023 | R.D. POLICARPIO & COMPANY INC. | 1938 | 2023 | 2023-10-28 | 05/22/2023 | 982.43 | 0 | 2023-10-27 |  | 1
2022 | Region III | PAMPANGA | MAGALANG (PAMPANGA) | P00637019LZ | Construction of Slope Protection Structure | 120.6498 | 15.2249 | 72368249.63 | 72354878.48 | 2022 | ALEXI LOUISSE CONSTRUCTION & GENERAL MERCHANDISE / THREE-IN-ONE CONSTRUCTION & TRADING | 1939 | 2022 | 2022-11-26 | 03/24/2022 | 13371.15 | 0 | 2022-11-25 |  | 1
2024 | Region III | PAMPANGA | MAGALANG (PAMPANGA) | P00838345LZ | Construction of Flood Mitigation Structure | 120.6507 | 15.2259 | 72373866.69 | 72368655.53 | 2024 | AKN CONSTRUCTION CORPORATION | 1940 | 2024 | 2024-08-22 | 02/16/2024 | 5211.16 | 0 | 2024-09-10 | 19
2023 | Region III | PAMPANGA | MAGALANG (PAMPANGA) | P00740623LZ | Construction of Drainage Structure | 120.6507 | 15.2259 | 39191360.09 | 39189328.1 | 2023 | MICKAJETTE CONSTRUCTION AND TRADING | 1941 | 2023 | 2023-08-20 | 03/24/2023 | 2031.99 | 0 | 2023-08-19 |  | 1
2023 | Region I | PANGASINAN | SANTA MARIA (PANGASINAN) | P00726368LZ | Construction of Flood Mitigation Structure | 120.6509 | 15.9268 | 48250000 | 48249667.67 | 2023 | RIVBROS CONSTRUCTION FACTORS & DEVELOPMENT | 1942 | 2023 | 2023-06-15 | 02/09/2023 | 332.33 | 0 | 2023-08-10 | 56
2023 | Region III | PAMPANGA | MABALACAT CITY (PAMPANGA) | P00740353LZ | Construction of Groundsill | 120.6514 | 15.1916 | 72356515.73 | 72350622.14 | 2023 | R.A. PAHATI CONST. & SUPPLY, INC. | 1943 | 2023 | 2023-11-21 | 05/16/2023 | 5893.59 | 0 | 2023-11-20 |  | 1
2021 | Cordillera Administrative Region | ABRA |  | P00561520LZ | Construction of Flood Mitigation Structure | 120.6517 | 17.5475 | 29400000 | 29397162.42 | 2022 | A.D. MARRERO GENERAL CONSTRUCTION | 1944 | 2021 | 2022-09-19 | 03/29/2022 | 2837.58 | 0 | 2022-09-18 |  | 1
2024 | Region III | TARLAC | CONCEPCION (TARLAC) | P00838422LZ | Construction of Slope Protection Structure | 120.6517 | 15.3019 | 96499561.09 | 96417364.16 | 2024 | T2B3 BUILDERS AND SUPPLIES CORP. / ERA CONSTRUCTION INC. | 1945 | 2024 | 2024-08-21 | 02/20/2024 | 82196.93 | 0 | 2024-08-20 |  | 1
2023 | Region I | PANGASINAN | ROSALES (PANGASINAN) | P00742284LZ | Construction of Dike | 120.652 | 15.8844 | 19600000 | 19570622.22 | 2023 | W.J.P. CONSTRUCTION AND SUPPLY | 1946 | 2023 | 2023-05-22 | 03/31/2023 | 29377.78 | 0 | 2023-09-10 | 111
2022 | Cordillera Administrative Region | ABRA | PEÃ‘ARRUBIA (ABRA) | P00632780LZ | Construction of Flood Mitigation Structure | 120.6527 | 17.5439 | 48999933.68 | 49497153.28 | 2023 | 739 BUILDERS | 1947 | 2022 | 2023-01-20 | 05/24/2022 | 0 | 497219.6 | 2023-01-14 |  | 6
2024 | Region IV-B | OCCIDENTAL MINDORO | ABRA DE ILOG (OCCIDENTAL MINDORO) | P00824735LZ | Construction of Flood Mitigation Structure | 120.6534 | 13.3464 | 39200000 | 38026008.01 | 2024 | SIXTEEN ENTERPRISES-CALAPAN BRANCH | 1948 | 2024 | 2024-09-21 | 02/14/2024 | 1173991.99 | 0 | 2024-09-20 |  | 1
2024 | Region III | PAMPANGA | CITY OF SAN FERNANDO (CAPITAL) (PAMPANGA) | P00844757LZ | Construction of Slope Protection Structure | 120.6545 | 15.0764 | 49000000 | 46549941.34 | 2024 | THREE-IN-ONE CONSTRUCTION & TRADING | 1949 | 2024 | 2024-09-18 | 03/05/2024 | 2450058.66 | 0 | 2024-09-17 |  | 1
2024 | Region III | PAMPANGA | MEXICO (PAMPANGA) | P00824704LZ | Construction of Slope Protection Structure | 120.6546 | 15.0938 | 49000000 | 46451991.76 | 2024 | PRIME PAVE CONSTRUCTION AND ASPHALT CORPORATION / MAYFLOWER CONSTRUCTION AND DEVELOPMENT CORPORATION | 1950 | 2024 | 2024-10-05 | 03/22/2024 | 2548008.24 | 0 | 2024-10-04 |  | 1
2023 | Cordillera Administrative Region | ABRA | TAYUM (ABRA) | P00740310LZ | Construction of Flood Mitigation Structure | 120.6552 | 17.6311 | 96499975.99 | 96497132 | 2023 | MG SAMIDAN CONSTRUCTION | 1951 | 2023 | 2023-06-28 | 04/05/2023 | 2843.99 | 0 | 2023-11-21 | 146
2022 | Region III | PAMPANGA | BACOLOR (PAMPANGA) | P00631237LZ | Construction of Drainage Structure | 120.6552 | 14.9949 | 29400000 | 27753512 | 2022 | MAYFLOWER CONSTRUCTION AND DEVELOPMENT CORPORATION | 1952 | 2022 | 2022-10-03 | 02/23/2022 | 1646488 | 0 | 2022-07-21 |  | 74
2024 | Cordillera Administrative Region | BENGUET | ITOGON (BENGUET) | P00821130LZ | Construction of Flood Mitigation Structure | 120.6553 | 16.3681 | 59830000 | 59820000 | 2024 | UNIVERSAL DE LEON CONSTRUCTION AND AGGREGATES / TSAI SHEN CONSTRUCTION | 1953 | 2024 | 2024-11-25 | 03/19/2024 | 10000 | 0 | 2024-11-28 | 3
2022 | Region I | PANGASINAN | ROSALES (PANGASINAN) | P00620968LZ | Construction of Revetment | 120.6553 | 15.8961 | 29400000 | 28960229.12 | 2022 | RIVBROS CONSTRUCTION FACTORS & DEVELOPMENT | 1954 | 2022 | 2022-09-05 | 03/08/2022 | 439770.88 | 0 | 2022-08-23 |  | 13
2022 | Region IV-B | OCCIDENTAL MINDORO | ABRA DE ILOG (OCCIDENTAL MINDORO) | P00637085LZ | Construction of Flood Mitigation Structure | 120.6556 | 13.3367 | 9900000 | 7133814.55 | 2022 | JUAN ANTONIO CONSTRUCTION | 1955 | 2022 | 2022-08-15 | 04/11/2022 | 2766185.45 | 0 | 2022-08-25 | 10
2022 | Region I | PANGASINAN | BALUNGAO (PANGASINAN) | P00621615LZ | Construction of Dike | 120.6558 | 15.8969 | 49000000 | 43155998.93 | 2023 | FLORDES CONSTRUCTION & TRADING CORP. (FORMERLY FLO | 1956 | 2022 | 2023-04-28 | 04/08/2022 | 5844001.07 | 0 | 2023-04-17 |  | 11
2023 | Region III | TARLAC | CONCEPCION (TARLAC) | P00737484LZ | Construction of Drainage Structure | 120.6561 | 15.3256 | 4949840.78 | 4848693.6 | 2023 | RA3N CONSTRUCTION AND SUPPLY | 1957 | 2023 | 2023-03-31 | 01/31/2023 | 101147.18 | 0 | 2023-03-30 |  | 1
2022 | Region III | TARLAC | CONCEPCION (TARLAC) | P00637024LZ | Construction of Slope Protection Structure | 120.6562 | 15.304 | 96499329.29 | 93168832.14 | 2022 | FERDSTAR BUILDERS INC. | 1958 | 2022 | 2022-12-05 | 03/26/2022 | 3330497.15 | 0 | 2022-11-23 |  | 12
2024 | Region III | PAMPANGA | CITY OF SAN FERNANDO (CAPITAL) (PAMPANGA) | P00844758LZ | Construction of Slope Protection Structure | 120.6564 | 15.0875 | 49000000 | 46451987.21 | 2024 | R.G. DIAZ BUILDERS & TRADING | 1959 | 2024 | 2024-09-14 | 03/01/2024 | 2548012.79 | 0 | 2024-09-13 |  | 1
2022 | Region III | PAMPANGA | BACOLOR (PAMPANGA) | P00631244LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.6584 | 15.0307 | 29400000 | 27871185.41 | 2022 | N.T. TULABUT CONSTRUCTION AND SUPPLY | 1960 | 2022 | 2022-07-22 | 02/23/2022 | 1528814.59 | 0 | 2022-07-21 |  | 1
2022 | Region I | PANGASINAN | BALUNGAO (PANGASINAN) | P00621614LZ | Construction of Dike | 120.6586 | 15.8975 | 49000000 | 43033678.5 | 2023 | FLORDES CONSTRUCTION & TRADING CORP. (FORMERLY FLO | 1961 | 2022 | 2023-04-28 | 04/08/2022 | 5966321.5 | 0 | 2023-04-17 |  | 11
2024 | Cordillera Administrative Region | ABRA | TAYUM (ABRA) | P00821144LZ | Construction of Flood Mitigation Structure | 120.6586 | 17.632 | 144750000 | 144710474.2 | 2024 | MG SAMIDAN CONSTRUCTION / TWINFORMERS CONSTRUCTION SERVICES | 1962 | 2024 | 2024-08-16 | 02/13/2024 | 39525.8 | 0 | 2024-12-02 | 108
2022 | Region I | ILOCOS NORTE | NUEVA ERA (ILOCOS NORTE) | P00621557LZ | Construction of Flood Mitigation Structure | 120.659 | 17.9014 | 96500000 | 96499962.97 | 2023 | ST. TIMOTHY CONSTRUCTION CORPORATION | 1963 | 2022 | 2023-01-06 | 04/07/2022 | 37.03 | 0 | 2023-01-09 | 3
2022 | Region I | ILOCOS NORTE | BANNA (ESPIRITU) (ILOCOS NORTE) | P00640490LZ | Construction of Flood Mitigation Structure | 120.6593 | 17.9707 | 39200000 | 39200000 | 2022 | JLP CONSTRUCTION & SUPPLY (FORMERLY: JLP CONSTRUCT | 1964 | 2022 | 2022-12-16 | 03/25/2022 | 0 | 0 | 2022-10-17 |  | 60
2022 | Region I | PANGASINAN | BALUNGAO (PANGASINAN) | P00621613LZ | Construction of Dike | 120.6606 | 15.8992 | 49000000 | 45391096.08 | 2022 | A.C. SOLIVEN CONSTRUCTION & GENERAL MERCHANDISE | 1965 | 2022 | 2022-10-25 | 04/08/2022 | 3608903.92 | 0 | 2022-10-24 |  | 1
2024 | Region III | PAMPANGA | CITY OF SAN FERNANDO (CAPITAL) (PAMPANGA) | P00844760LZ | Construction of Slope Protection Structure | 120.6609 | 15.0917 | 49000000 | 45549879.24 | 2024 | CHOLO CONSTRUCTION AND TRADING | 1966 | 2024 | 2024-09-28 | 03/15/2024 | 3450120.76 | 0 | 2024-09-27 |  | 1
2022 | Region I | ILOCOS NORTE | NUEVA ERA (ILOCOS NORTE) | P00621559LZ | Construction of Flood Mitigation Structure | 120.6615 | 17.8949 | 96500000 | 96499986.02 | 2023 | ST. GERRARD CONSTRUCTION GEN. CONTRACTOR & DEVELOPMENT CORP. (FORMERLY:ST. GERRARD CONSTRUCTION) | 1967 | 2022 | 2023-01-06 | 04/07/2022 | 13.98 | 0 | 2023-01-09 | 3
2023 | Region III | PAMPANGA | MAGALANG (PAMPANGA) | P00740355LZ | Construction of Dike | 120.6617 | 15.2233 | 72374572.82 | 72349038.58 | 2023 | ALPIZ CONSTRUCTION & DEVELOPMENT CORPORATION / D.R. ROBLES CONSTRUCTION | 1968 | 2023 | 2023-11-03 | 05/08/2023 | 25534.24 | 0 | 2023-11-02 |  | 1
2022 | Region I | ILOCOS NORTE | NUEVA ERA (ILOCOS NORTE) | P00621560LZ | Construction of Flood Mitigation Structure | 120.6618 | 17.9019 | 96500000 | 96499995.44 | 2022 | ST. GERRARD CONSTRUCTION GEN. CONTRACTOR & DEVELOPMENT CORP. (FORMERLY:ST. GERRARD CONSTRUCTION) | 1969 | 2022 | 2022-11-11 | 04/07/2022 | 4.56 | 0 | 2022-11-10 |  | 1
2021 | Cordillera Administrative Region | BENGUET |  | P00525914LZ | Construction of Flood Mitigation Structure | 120.6621 | 16.7229 | 9800000 | 8704178.48 | 2022 | AKIP CONSTRUCTION AND ENTERPRISE | 1970 | 2021 | 2022-09-02 | 01/18/2022 | 1095821.52 | 0 | 2022-09-01 |  | 1
2024 | Region I | ILOCOS NORTE | LAOAG CITY (CAPITAL) (ILOCOS NORTE) | P00838489LZ | Construction of Drainage Structure | 120.6622 | 18.1777 | 4899839.02 | 4899838.8 | 2024 | KRB CONSTRUCTION | 1971 | 2024 | 2024-04-22 | 03/01/2024 | 0.22 | 0 | 2024-06-01 | 40
2022 | Region I | ILOCOS NORTE | NUEVA ERA (ILOCOS NORTE) | P00621553LZ | Construction of Flood Mitigation Structure | 120.6623 | 17.8979 | 96500000 | 96499990.96 | 2023 | ST. GERRARD CONSTRUCTION GEN. CONTRACTOR & DEVELOPMENT CORP. (FORMERLY:ST. GERRARD CONSTRUCTION) | 1972 | 2022 | 2023-01-10 | 04/07/2022 | 9.04 | 0 | 2023-01-09 |  | 1
2023 | Cordillera Administrative Region | ABRA | TAYUM (ABRA) | P00740306LZ | Construction of Flood Mitigation Structure | 120.6624 | 17.6326 | 146999974.5 | 144747542 | 2023 | MG SAMIDAN CONSTRUCTION | 1973 | 2023 | 2023-06-29 | 04/05/2023 | 2252432.5 | 0 | 2024-01-11 | 196
2022 | Region I | ILOCOS NORTE | NUEVA ERA (ILOCOS NORTE) | P00621590LZ | Construction of Flood Mitigation Structure | 120.6624 | 17.8998 | 44100000 | 43424813.95 | 2023 | ST. TIMOTHY CONSTRUCTION CORPORATION | 1974 | 2022 | 2023-03-15 | 11/03/2022 | 675186.05 | 0 | 2023-04-25 | 41
2022 | Region I | ILOCOS NORTE | NUEVA ERA (ILOCOS NORTE) | P00621555LZ | Construction of Flood Mitigation Structure | 120.6626 | 17.9072 | 96500000 | 96499983.03 | 2022 | ALPHA & OMEGA GEN. CONTRACTOR & DEVELOPMENT CORP. | 1975 | 2022 | 2022-11-11 | 04/07/2022 | 16.97 | 0 | 2022-11-10 |  | 1
2022 | Region I | ILOCOS NORTE | NUEVA ERA (ILOCOS NORTE) | P00621588LZ | Construction of Flood Mitigation Structure | 120.6627 | 17.8949 | 24500000 | 24124998.35 | 2023 | ST. TIMOTHY CONSTRUCTION CORPORATION | 1976 | 2022 | 2023-03-15 | 11/03/2022 | 375001.65 | 0 | 2023-04-05 | 21
2022 | Region I | PANGASINAN | BALUNGAO (PANGASINAN) | P00621612LZ | Construction of Dike | 120.6628 | 15.9014 | 49000000 | 45513250.28 | 2022 | A.C. SOLIVEN CONSTRUCTION & GENERAL MERCHANDISE | 1977 | 2022 | 2022-10-25 | 04/08/2022 | 3486749.72 | 0 | 2022-10-24 |  | 1
2022 | Region I | ILOCOS NORTE | NUEVA ERA (ILOCOS NORTE) | P00621561LZ | Construction of Flood Mitigation Structure | 120.6631 | 17.9059 | 96500000 | 96499985.94 | 2022 | ALPHA & OMEGA GEN. CONTRACTOR & DEVELOPMENT CORP. | 1978 | 2022 | 2022-11-11 | 04/07/2022 | 14.06 | 0 | 2022-11-10 |  | 1
2022 | Region I | ILOCOS NORTE | NUEVA ERA (ILOCOS NORTE) | P00621589LZ | Construction of Flood Mitigation Structure | 120.6631 | 17.8919 | 30380000 | 29914933.06 | 2023 | ST. GERRARD CONSTRUCTION GEN. CONTRACTOR & DEVELOPMENT CORP. (FORMERLY:ST. GERRARD CONSTRUCTION) | 1979 | 2022 | 2023-04-12 | 11/03/2022 | 465066.94 | 0 | 2023-04-11 |  | 1
2022 | Region I | ILOCOS NORTE | NUEVA ERA (ILOCOS NORTE) | P00621591LZ | Construction of Flood Mitigation Structure | 120.6633 | 17.9024 | 34300000 | 33774845.17 | 2023 | ALPHA & OMEGA GEN. CONTRACTOR & DEVELOPMENT CORP. | 1980 | 2022 | 2023-03-15 | 11/03/2022 | 525154.83 | 0 | 2023-04-11 | 27
2022 | Region I | ILOCOS NORTE | NUEVA ERA (ILOCOS NORTE) | P00621556LZ | Construction of Flood Mitigation Structure | 120.6633 | 17.9104 | 96500000 | 96499966.26 | 2022 | ALPHA & OMEGA GEN. CONTRACTOR & DEVELOPMENT CORP. | 1981 | 2022 | 2022-11-11 | 04/07/2022 | 33.74 | 0 | 2022-11-10 |  | 1
2023 | Region III | PAMPANGA | MACABEBE (PAMPANGA) | P00726174LZ | Construction of Flood Mitigation Structure | 120.6634 | 14.7891 | 49000000 | 47284732 | 2023 | EDDMARI CONSTRUCTION & TRADING | 1982 | 2023 | 2023-11-05 | 02/09/2023 | 1715268 | 0 | 2023-11-04 |  | 1
2022 | Region I | ILOCOS NORTE | NUEVA ERA (ILOCOS NORTE) | P00621554LZ | Construction of Flood Mitigation Structure | 120.6637 | 17.9035 | 96500000 | 96499933.26 | 2023 | ST. GERRARD CONSTRUCTION GEN. CONTRACTOR & DEVELOPMENT CORP. (FORMERLY:ST. GERRARD CONSTRUCTION) | 1983 | 2022 | 2023-01-10 | 04/07/2022 | 66.74 | 0 | 2023-01-09 |  | 1
2024 | Region IV-B | OCCIDENTAL MINDORO | ABRA DE ILOG (OCCIDENTAL MINDORO) | P00824733LZ | Construction of Flood Mitigation Structure | 120.6638 | 13.3348 | 39200000 | 38959921.61 | 2024 | F.A. TORRES CONSTRUCTION | 1984 | 2024 | 2024-08-21 | 02/14/2024 | 240078.39 | 0 | 2024-08-20 |  | 1
2022 | Region I | ILOCOS NORTE | NUEVA ERA (ILOCOS NORTE) | P00621562LZ | Construction of Flood Mitigation Structure | 120.665 | 17.9093 | 96500000 | 96499973.59 | 2023 | ALPHA & OMEGA GEN. CONTRACTOR & DEVELOPMENT CORP. | 1985 | 2022 | 2023-01-10 | 04/07/2022 | 26.41 | 0 | 2023-01-09 |  | 1
2022 | Cordillera Administrative Region | ABRA | LA PAZ (ABRA) | P00639321LZ | Construction of Flood Mitigation Structure | 120.6658 | 17.6564 | 96500000 | 96497900 | 2023 | ST. TIMOTHY CONSTRUCTION CORPORATION | 1986 | 2022 | 2023-01-24 | 05/24/2022 | 2100 | 0 | 2023-02-24 | 31
2024 | Region I | PANGASINAN | BALUNGAO (PANGASINAN) | P00845914LZ | Construction of Dike | 120.6665 | 15.9019 | 49500000 | 49446862.94 | 2024 | RS RODRIGUEZ CONSTRUCTION & SUPPLIES | 1987 | 2024 | 2024-05-15 | 03/18/2024 | 53137.06 | 0 | 2024-09-24 | 132
2024 | Region I | PANGASINAN | BALUNGAO (PANGASINAN) | P00843202LZ | Construction of Dike | 120.6667 | 15.8973 | 96500000 | 96389680.11 | 2024 | JHI CONSTRUCTION & SUPPLY | 1988 | 2024 | 2024-06-30 | 04/16/2024 | 110319.89 | 0 | 2025-01-23 | 207
2024 | Region I | PANGASINAN | BALUNGAO (PANGASINAN) | P00824663LZ | Construction of Dike | 120.667 | 15.899 | 39200000 | 39152848.87 | 2024 | JHI CONSTRUCTION & SUPPLY | 1989 | 2024 | 2024-06-30 | 02/26/2024 | 47151.13 | 0 | 2024-08-31 | 62
2022 | Region III | PAMPANGA | BACOLOR (PAMPANGA) | P00631235LZ | Construction of Drainage Structure | 120.6672 | 15.032 | 39200000 | 37827625.19 | 2022 | ROYAL CROWN MONARCH CONSTRUCTION & SUPPLIES CORP. | 1990 | 2022 | 2022-08-22 | 02/24/2022 | 1372374.81 | 0 | 2022-08-21 |  | 1
2024 | Region III | PAMPANGA | BACOLOR (PAMPANGA) | P00844756LZ | Construction of Slope Protection Structure | 120.6675 | 15.0062 | 34300000 | 32482100 | 2024 | THREE-IN-ONE CONSTRUCTION & TRADING | 1991 | 2024 | 2024-08-05 | 02/08/2024 | 1817900 | 0 | 2024-08-04 |  | 1
2024 | Region IV-B | OCCIDENTAL MINDORO | ABRA DE ILOG (OCCIDENTAL MINDORO) | P00821357LZ | Construction of Flood Mitigation Structure | 120.6678 | 13.333 | 241250000 | 241234859.2 | 2024 | GOLDEN J'S CONSTRUCTION SERVICES | 1992 | 2024 | 2024-11-25 | 03/02/2024 | 15140.8 | 0 | 2025-02-23 | 90
2022 | Cordillera Administrative Region | BENGUET | ITOGON (BENGUET) | P00620999LZ | Construction of Flood Mitigation Structure | 120.6679 | 16.3652 | 24500000 | 24500000 | 2022 | GSIXTY CONSTRUCTION SERVICES | 1993 | 2022 | 2022-08-12 | 01/31/2022 | 0 | 0 | 2022-08-11 |  | 1
2024 | Cordillera Administrative Region | ABRA | TAYUM (ABRA) | P00838338LZ | Construction of Flood Mitigation Structure | 120.668 | 17.6351 | 144750000 | 144750000 | 2024 | MG SAMIDAN CONSTRUCTION | 1994 | 2024 | 2024-08-19 | 02/13/2024 | 0 | 0 | 2024-12-02 | 105
2022 | Cordillera Administrative Region | ABRA | TAYUM (ABRA) | P00632762LZ | Construction of Flood Mitigation Structure | 120.6681 | 17.6192 | 48999957.44 | 49497500 | 2022 | 739 BUILDERS | 1995 | 2022 | 2022-09-09 | 05/31/2022 | 0 | 497542.56 | 2022-12-11 | 93
2024 | Region I | PANGASINAN | BALUNGAO (PANGASINAN) | P00824657LZ | Construction of Dike | 120.6683 | 15.9091 | 49000000 | 48944869.3 | 2024 | RS RODRIGUEZ CONSTRUCTION & SUPPLIES | 1996 | 2024 | 2024-06-30 | 02/26/2024 | 55130.7 | 0 | 2024-09-12 | 74
2022 | Cordillera Administrative Region | ABRA | LA PAZ (ABRA) | P00620985LZ | Construction of Flood Mitigation Structure | 120.6685 | 17.6578 | 48999972.12 | 48997900 | 2022 | ST. TIMOTHY CONSTRUCTION CORPORATION | 1997 | 2022 | 2022-10-22 | 03/16/2022 | 2072.12 | 0 | 2022-09-26 |  | 26
2022 | Cordillera Administrative Region | BENGUET | KIBUNGAN (BENGUET) | P00639458LZ | Construction of Flood Mitigation Structure | 120.6686 | 16.7055 | 29400000 | 29400000 | 2022 | M.P. TABERAO CONSTRUCTION SERVICES AND SUPPLIES | 1998 | 2022 | 2022-11-18 | 04/17/2022 | 0 | 0 | 2022-12-21 | 33
2022 | Region III | PAMPANGA | BACOLOR (PAMPANGA) | P00631232LZ | Construction of Drainage Structure | 120.6692 | 15.007 | 39200000 | 37239841 | 2022 | EDDMARI CONSTRUCTION & TRADING | 1999 | 2022 | 2022-08-07 | 02/24/2022 | 1960159 | 0 | 2022-07-22 |  | 16
2024 | Region III | PAMPANGA | MAGALANG (PAMPANGA) | P00838361LZ | Construction of Slope Protection Structure | 120.6697 | 15.2281 | 77191006.28 | 77186878.15 | 2024 | MCB ZAMORA CONSTRUCTION & SUPPLY | 2000 | 2024 | 2024-07-22 | 02/26/2024 | 4128.13 | 0 | 2024-09-22 | 62
2023 | Cordillera Administrative Region | BENGUET | BUGUIAS (BENGUET) | P00726409LZ | Construction of Flood Mitigation Structure | 120.8379 | 16.8053 | 72375000 | 72324030.27 | 2023 | MG SAMIDAN CONSTRUCTION / JAN-REAL CONSTRUCTION SERVICES | 2001 | 2023 | 2023-12-22 | 05/22/2023 | 50969.73 | 0 | 2024-03-10 | 79
2023 | Region III | BULACAN | PULILAN (BULACAN) | P00742323LZ | Construction of Drainage Structure | 120.8381 | 14.9034 | 19799956.98 | 19798438.81 | 2023 | BIG BEN CONSTRUCTION | 2002 | 2023 | 2023-11-21 | 03/27/2023 | 1518.17 | 0 | 2023-11-20 |  | 1
2022 | Region IV-B | OCCIDENTAL MINDORO | SABLAYAN (OCCIDENTAL MINDORO) | P00621104LZ | Construction of Flood Mitigation Structure | 120.8382 | 12.7833 | 44100000 | 32557644.6 | 2023 | ST. TIMOTHY CONSTRUCTION CORPORATION | 2003 | 2022 | 2023-07-15 | 05/30/2022 | 11542355.4 | 0 | 2023-02-04 |  | 161
2024 | Cordillera Administrative Region | BENGUET | BUGUIAS (BENGUET) | P00821131LZ | Construction of Flood Mitigation Structure | 120.8384 | 16.804 | 67550000 | 67462363.43 | 2024 | DJY CONSTRUCTION / NORJOHN CONSTRUCTION | 2004 | 2024 | 2024-07-25 | 05/15/2024 | 87636.57 | 0 | 2025-03-04 | 222
2023 | Region III | PAMPANGA | CANDABA (PAMPANGA) | P00726893LZ | Construction of Flood Mitigation Structure | 120.8387 | 15.0887 | 96500000 | 91192478.11 | 2024 | STO. CRISTO CONSTRUCTION & TRADING INC. (FOR: STO. CRISTO CONSTRUCTION & TRADING) | 2005 | 2023 | 2024-02-03 | 04/12/2023 | 5307521.89 | 0 | 2024-02-02 |  | 1
2022 | Cordillera Administrative Region | BENGUET | KABAYAN (BENGUET) | P00639448LZ | Construction of Flood Mitigation Structure | 120.8398 | 16.6195 | 9800000 | 9793460.31 | 2023 | AROBOAN CONSTRUCTION AND SUPPLY | 2006 | 2022 | 2023-01-24 | 07/26/2022 | 6539.69 | 0 | 2023-01-25 | 1
2023 | Region III | BULACAN | PULILAN (BULACAN) | P00740596LZ | Construction of Flood Mitigation Structure | 120.84 | 14.9553 | 29399023.84 | 29398745.78 | 2023 | A.L. SALAZAR CONSTRUCTION, INC. | 2007 | 2023 | 2023-10-09 | 03/21/2023 | 278.06 | 0 | 2023-11-14 | 36
2023 | Region IV-B | OCCIDENTAL MINDORO | SABLAYAN (OCCIDENTAL MINDORO) | P00736044LZ | Construction of Revetment | 120.8407 | 12.7904 | 217124999.6 | 217122319.5 | 2024 | ANORE CONSTRUCTION | 2008 | 2023 | 2024-02-05 | 02/11/2023 | 2680.1 | 0 | 2024-02-04 |  | 1
2023 | Region III | BULACAN | CITY OF MALOLOS (CAPITAL) (BULACAN) | P00736613LZ | Construction of Flood Mitigation Structure | 120.8412 | 14.814 | 48999842.99 | 48999995.78 | 2023 | WAWAO BUILDERS | 2009 | 2023 | 2023-07-03 | 02/06/2023 | 0 | 152.79 | 2023-10-02 | 91
2022 | Region IV-B | OCCIDENTAL MINDORO | SANTA CRUZ (OCCIDENTAL MINDORO) | P00637084LZ | Construction of Flood Mitigation Structure | 120.8415 | 12.9888 | 9900000 | 6085928.06 | 2022 | DAYBREAK ENTERPRISES - ENGINEERING & CONSTRUCTION | 2010 | 2022 | 2022-07-25 | 04/11/2022 | 3814071.94 | 0 | 2022-07-27 | 2
2023 | Region IV-B | OCCIDENTAL MINDORO | SANTA CRUZ (OCCIDENTAL MINDORO) | P00725866LZ | Construction of Revetment | 120.8425 | 12.989 | 96499999.27 | 96497025.69 | 2023 | GREAT PACIFIC BUILDERS AND GEN. CONTRACTOR INC. | 2011 | 2023 | 2023-11-10 | 02/11/2023 | 2973.58 | 0 | 2023-11-09 |  | 1
2023 | Cordillera Administrative Region | BENGUET | BUGUIAS (BENGUET) | P00726408LZ | Construction of Flood Mitigation Structure | 120.8429 | 16.8117 | 72375000 | 72375000 | 2023 | JYP GENERAL CONSTRUCTION / R.S. SEPIAN CONSTRUCTION & TRUCKING | 2012 | 2023 | 2023-10-23 | 05/11/2023 | 0 | 0 | 2024-03-01 | 130
2022 | Cordillera Administrative Region | BENGUET | KABAYAN (BENGUET) | P00639447LZ | Construction of Flood Mitigation Structure | 120.8453 | 16.5948 | 9800000 | 9679857.68 | 2022 | AROBOAN CONSTRUCTION AND SUPPLY | 2013 | 2022 | 2022-11-21 | 07/19/2022 | 120142.32 | 0 | 2022-11-17 |  | 4
2023 | Region III | BULACAN | CITY OF MALOLOS (CAPITAL) (BULACAN) | P00742135LZ | Construction of Slope Protection Structure | 120.846 | 14.8115 | 74249746.88 | 74249916.8 | 2023 | TOPNOTCH CATALYST BUILDERS INC. / BLACK HARDHAT INC. (FORMERLY: JCHARDHAT INC.) | 2014 | 2023 | 2023-12-07 | 03/28/2023 | 0 | 169.92 | 2024-01-20 | 44
2024 | Region III | BULACAN | CITY OF MALOLOS (CAPITAL) (BULACAN) | P00845984LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.8467 | 14.8074 | 74249936.6 | 74247158.51 | 2024 | DMLC BUILDERS | 2015 | 2024 | 2024-12-11 | 04/16/2024 | 2778.09 | 0 | 2024-12-10 |  | 1
2024 | Region III | BULACAN | CITY OF MALOLOS (CAPITAL) (BULACAN) | P00823363LZ | Construction of Flood Mitigation Structure | 120.8467 | 14.8092 | 77199808.55 | 77180485.93 | 2024 | 11-16 CONSTRUCTION | 2016 | 2024 | 2024-11-05 | 03/11/2024 | 19322.62 | 0 | 2024-11-04 |  | 1
2024 | Region III | BULACAN | CITY OF MALOLOS (CAPITAL) (BULACAN) | P00838402LZ | Construction of Slope Protection Structure | 120.8478 | 14.808 | 77199984.38 | 77199984.52 | 2024 | DARCY & ANNA BUILDERS & TRADING | 2017 | 2024 | 2024-04-19 | 02/07/2024 | 0 | 0.14 | 2024-10-02 | 166
2024 | Region IV-A | BATANGAS | CITY OF CALACA (BATANGAS) | P00839598LZ | Construction of Flood Mitigation Structure | 120.8483 | 14.1387 | 4950000 | 4950000 | 2024 | FILCAN UNITED CONSTRUCTION & GENERAL MERCHANDISE CORP. | 2018 | 2024 | 2024-05-07 | 02/08/2024 | 0 | 0 | 2024-05-06 |  | 1
2022 | Region III | NUEVA ECIJA | ALIAGA (NUEVA ECIJA) | P00620530LZ | Construction of Flood Mitigation Structure | 120.8486 | 15.5296 | 45080000 | 45080000 | 2022 | AMP 723 CONSTRUCTION CORPORATION (FORMERLY: A.M.P. CONSTRUCTION) | 2019 | 2022 | 2022-08-02 | 02/04/2022 | 0 | 0 | 2022-08-01 |  | 1
2023 | Region III | NUEVA ECIJA | ALIAGA (NUEVA ECIJA) | P00725704LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.8486 | 15.5294 | 96500000 | 96496000 | 2023 | AMP 723 CONSTRUCTION CORPORATION (FORMERLY: A.M.P. CONSTRUCTION) | 2020 | 2023 | 2023-08-01 | 02/22/2023 | 4000 | 0 | 2023-11-17 | 108
2023 | Region IV-A | CAVITE | TANZA (CAVITE) | P00727162LZ | Construction of Flood Mitigation Structure | 120.8503 | 14.2898 | 49000000 | 48999623.34 | 2024 | DEVEX INCORPORATED / N.B. AVILA CONSTRUCTION | 2021 | 2023 | 2024-03-17 | 08/06/2023 | 376.66 | 0 | 2024-03-16 |  | 1
2024 | Region III | NUEVA ECIJA | QUEZON (NUEVA ECIJA) | P00820275LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.8504 | 15.5325 | 96500000 | 95533042.22 | 2024 | AMP 723 CONSTRUCTION CORPORATION (FORMERLY: A.M.P. CONSTRUCTION) / BRYAN PAUL P. PACHECO CONST. CORP. | 2022 | 2024 | 2024-08-12 | 02/06/2024 | 966957.78 | 0 | 2024-10-31 | 80
2024 | Region III | BULACAN | PLARIDEL (BULACAN) | P00821268LZ | Construction of Slope Protection Structure | 120.8506 | 14.8973 | 96499925.68 | 96499699.7 | 2024 | TOPNOTCH CATALYST BUILDERS INC. | 2023 | 2024 | 2024-10-30 | 02/07/2024 | 225.98 | 0 | 2024-11-01 | 2
2022 | Region IV-A | CAVITE | TRECE MARTIRES CITY (CAPITAL) (CAVITE) | P00620572LZ | Construction of Dike | 120.8509 | 14.2886 | 49000000 | 46542408.71 | 2022 | HAUSLAND CONSTRUCTION | 2024 | 2022 | 2022-11-05 | 02/24/2022 | 2457591.29 | 0 | 2022-11-04 |  | 1
2024 | Region III | BULACAN | PLARIDEL (BULACAN) | P00825074LZ | Construction of Flood Mitigation Structure | 120.8512 | 14.8976 | 77199982.7 | 77199672.06 | 2024 | TOPNOTCH CATALYST BUILDERS INC. | 2025 | 2024 | 2024-11-05 | 04/23/2024 | 310.64 | 0 | 2024-12-17 | 42
2022 | Cordillera Administrative Region | ABRA | LICUAN-BAAY (LICUAN) (ABRA) | P00632768LZ | Construction of Flood Mitigation Structure | 120.8513 | 17.5458 | 48999965.97 | 49497000 | 2022 | A.D. MARRERO GENERAL CONSTRUCTION | 2026 | 2022 | 2022-07-12 | 02/09/2022 | 0 | 497034.03 | 2022-07-13 | 1
2023 | Region IV-A | CAVITE | TANZA (CAVITE) | P00727161LZ | Construction of Flood Mitigation Structure | 120.8515 | 14.2883 | 49000000 | 48999203.03 | 2024 | DEVEX INCORPORATED / N.B. AVILA CONSTRUCTION | 2027 | 2023 | 2024-03-17 | 08/06/2023 | 796.97 | 0 | 2024-03-16 |  | 1
2023 | Region III | BULACAN | PLARIDEL (BULACAN) | P00727277LZ | Construction of Flood Mitigation Structure | 120.8522 | 14.8985 | 72374751.31 | 72374590.51 | 2023 | TOPNOTCH CATALYST BUILDERS INC. | 2028 | 2023 | 2023-09-19 | 03/14/2023 | 160.8 | 0 | 2023-12-07 | 79
2023 | Region IV-A | CAVITE | TANZA (CAVITE) | P00742420LZ | Rehabilitation / Major Repair of Drainage Structure | 120.8523 | 14.3925 | 7177500 | 7101451.84 | 2023 | J.S. GENERAL CONTRACTOR | 2029 | 2023 | 2023-07-14 | 04/06/2023 | 76048.16 | 0 | 2023-07-13 |  | 1
2022 | Region IV-A | CAVITE | CITY OF GENERAL TRIAS (CAVITE) | P00620871LZ | Construction of Revetment | 120.8819 | 14.3629 | 81832000 | 81832000 | 2022 | BAQPRINCE CONSTRUCTION AND TRADING CORP. | 2030 | 2022 | 2022-11-12 | 02/28/2022 | 0 | 0 | 2022-11-11 |  | 1
2022 | Region IV-A | CAVITE | TRECE MARTIRES CITY (CAPITAL) (CAVITE) | P00620571LZ | Construction of Dike | 120.8529 | 14.2876 | 49000000 | 46533152.26 | 2022 | BAQPRINCE CONSTRUCTION AND TRADING CORP. | 2031 | 2022 | 2022-11-05 | 02/24/2022 | 2466847.74 | 0 | 2022-11-04 |  | 1
2022 | Region IV-A | CAVITE | TRECE MARTIRES CITY (CAPITAL) (CAVITE) | P00620570LZ | Construction of Dike | 120.8529 | 14.284 | 49000000 | 48887751.08 | 2022 | DEVEX INCORPORATED / N.B. AVILA CONSTRUCTION | 2032 | 2022 | 2022-12-05 | 02/24/2022 | 112248.92 | 0 | 2022-12-04 |  | 1
2023 | Region IV-A | CAVITE | TANZA (CAVITE) | P00727160LZ | Construction of Flood Mitigation Structure | 120.8533 | 14.2873 | 49000000 | 48999307.5 | 2024 | DEVEX INCORPORATED / N.B. AVILA CONSTRUCTION | 2033 | 2023 | 2024-03-18 | 08/07/2023 | 692.5 | 0 | 2024-03-17 |  | 1
2025 | Region III | NUEVA ECIJA | SCIENCE CITY OF MUÃ‘OZ (NUEVA ECIJA) | P00921035LZ | Construction of Flood Mitigation Structure | 120.8533 | 15.677 | 9800000 | 9701851.92 | 2025 | IJK MAE CONSTRUCTION INC. | 2034 | 2025 | 2025-04-07 | 02/11/2025 | 98148.08 | 0 | 2025-05-10 | 33
2024 | Region III | NUEVA ECIJA | SCIENCE CITY OF MUÃ‘OZ (NUEVA ECIJA) | P00820827LZ | Construction of Flood Mitigation Structure | 120.8535 | 15.6772 | 19600000 | 19403906.2 | 2024 | IJK MAE CONSTRUCTION INC. | 2035 | 2024 | 2024-07-30 | 02/02/2024 | 196093.8 | 0 | 2024-07-29 |  | 1
2022 | Region IV-A | CAVITE | TRECE MARTIRES CITY (CAPITAL) (CAVITE) | P00620569LZ | Construction of Dike | 120.8538 | 14.284 | 49000000 | 48869615.47 | 2022 | DEVEX INCORPORATED / N.B. AVILA CONSTRUCTION | 2036 | 2022 | 2022-12-05 | 02/24/2022 | 130384.53 | 0 | 2022-12-04 |  | 1
2023 | Region IV-A | CAVITE | TANZA (CAVITE) | P00727163LZ | Construction of Flood Mitigation Structure | 120.8538 | 14.284 | 49000000 | 48999261.63 | 2024 | DEVEX INCORPORATED / N.B. AVILA CONSTRUCTION | 2037 | 2023 | 2024-03-18 | 08/07/2023 | 738.37 | 0 | 2024-03-17 |  | 1
2023 | Region III | BULACAN | CITY OF MALOLOS (CAPITAL) (BULACAN) | P00742152LZ | Construction of Flood Mitigation Structure | 120.8542 | 14.8436 | 59399786.07 | 59398979.93 | 2023 | JTC CRUZ CONSTRUCTION CO., INC. | 2038 | 2023 | 2023-11-21 | 03/28/2023 | 806.14 | 0 | 2024-01-20 | 60
2024 | Region III | BULACAN | PLARIDEL (BULACAN) | P00825105LZ | Construction of Flood Mitigation Structure | 120.8543 | 14.8989 | 96499809.83 | 96499893.19 | 2024 | WAWAO BUILDERS | 2039 | 2024 | 2024-07-31 | 05/28/2024 | 0 | 83.36 | 2025-02-20 | 204
2023 | Region IV-A | CAVITE | ROSARIO (CAVITE) | P00737504LZ | Construction of Drainage Structure | 120.8543 | 14.4165 | 4950000 | 4898131.51 | 2023 | REND ENTERPRISES & GENERAL CONTRACTOR | 2040 | 2023 | 2023-05-19 | 02/19/2023 | 51868.49 | 0 | 2023-05-18 |  | 1
2023 | Region III | BULACAN | PLARIDEL (BULACAN) | P00727276LZ | Construction of Flood Mitigation Structure | 120.8548 | 14.8993 | 77199968.39 | 77199391.48 | 2023 | DARCY & ANNA BUILDERS & TRADING | 2041 | 2023 | 2023-12-08 | 03/14/2023 | 576.91 | 0 | 2023-12-07 |  | 1
2022 | Region III | BULACAN | PLARIDEL (BULACAN) | P00621452LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.855 | 14.8909 | 14699511.91 | 14699511.91 | 2022 | TBB CONSTRUCTION CORP. | 2042 | 2022 | 2022-08-31 | 04/04/2022 | 0 | 0 | 2022-08-30 |  | 1
2023 | Region III | BULACAN | PLARIDEL (BULACAN) | P00726718LZ | Construction of Flood Mitigation Structure | 120.8552 | 14.8993 | 29399509.57 | 29399001.49 | 2023 | TOPNOTCH CATALYST BUILDERS INC. | 2043 | 2023 | 2023-04-18 | 02/06/2023 | 508.08 | 0 | 2023-09-02 | 137
2024 | Region III | BULACAN | CITY OF MALOLOS (CAPITAL) (BULACAN) | P00838367LZ | Construction of Revetment | 120.8555 | 14.844 | 67549854.67 | 67549811.86 | 2024 | SYMS CONSTRUCTION TRADING | 2044 | 2024 | 2024-09-30 | 05/21/2024 | 42.81 | 0 | 2025-01-14 | 106
2024 | Region III | BULACAN | CITY OF BALIUAG (BULACAN) | P00820813LZ | Construction of Flood Mitigation Structure | 120.8556 | 14.9806 | 32666819.02 | 32666424.01 | 2024 | ANORE CONSTRUCTION | 2045 | 2024 | 2024-08-29 | 05/28/2024 | 395.01 | 0 | 2024-10-23 | 55
2024 | Cordillera Administrative Region | BENGUET | BUGUIAS (BENGUET) | P00821129LZ | Construction of Flood Mitigation Structure | 120.8564 | 16.7521 | 62725000 | 62628581.73 | 2024 | DJY CONSTRUCTION / NORJOHN CONSTRUCTION | 2046 | 2024 | 2024-10-22 | 06/14/2024 | 96418.27 | 0 | 2025-03-16 | 145
2022 | Region IV-A | CAVITE | TANZA (CAVITE) | P00637796LZ | Construction of Drainage Structure | 120.8564 | 14.3995 | 4950000 | 4950000 | 2022 | R.C. SIMON CONSTRUCTION | 2047 | 2022 | 2022-07-14 | 03/31/2022 | 0 | 0 | 2022-07-13 |  | 1
2022 | Region IV-A | CAVITE | TANZA (CAVITE) | P00637794LZ | Construction of Drainage Structure | 120.8564 | 14.3995 | 4950000 | 4950000 | 2022 | FE S. REYES GENERAL CONTRACTOR CORP. | 2048 | 2022 | 2022-07-14 | 03/31/2022 | 0 | 0 | 2022-07-13 |  | 1
2022 | Region IV-A | CAVITE | TANZA (CAVITE) | P00637797LZ | Construction of Drainage Structure | 120.8569 | 14.3999 | 4950000 | 4950000 | 2022 | R.C. SIMON CONSTRUCTION | 2049 | 2022 | 2022-07-14 | 03/31/2022 | 0 | 0 | 2022-07-13 |  | 1
2023 | Region IV-A | CAVITE | ROSARIO (CAVITE) | P00737505LZ | Construction of Drainage Structure | 120.8572 | 14.4166 | 4950000 | 4899147.67 | 2023 | TWO DEGREES CONSTRUCTION AND SUPPLY | 2050 | 2023 | 2023-05-19 | 02/19/2023 | 50852.33 | 0 | 2023-05-18 |  | 1
2022 | Region IV-A | BATANGAS | LEMERY (BATANGAS) | P00620557LZ | Construction of Flood Mitigation Structure | 120.8573 | 13.9073 | 49000000 | 49000000 | 2022 | ALPHA & OMEGA GEN. CONTRACTOR & DEVELOPMENT CORP. | 2051 | 2022 | 2022-12-07 | 02/11/2022 | 0 | 0 | 2022-12-06 |  | 1
2022 | Region IV-A | BATANGAS | LEMERY (BATANGAS) | P00631280LZ | Construction of Flood Mitigation Structure | 120.8573 | 13.9073 | 49000000 | 49000000 | 2023 | HGG BUILDERS & SUPPLY | 2052 | 2022 | 2023-01-07 | 03/28/2022 | 0 | 0 | 2023-01-06 |  | 1
2024 | Region III | BULACAN | PULILAN (BULACAN) | P00838526LZ | Construction of Slope Protection Structure | 120.8581 | 14.9017 | 19299750.99 | 19299673.25 | 2024 | TBB CONSTRUCTION CORP. | 2053 | 2024 | 2024-09-03 | 04/23/2024 | 77.74 | 0 | 2024-09-18 | 15
2021 | Cordillera Administrative Region | BENGUET |  | P00561459LZ | Construction of Flood Mitigation Structure | 120.8581 | 16.752 | 96496794.18 | 96500000 | 2022 | JOMARCANN GENERAL CONSTRUCTION / EGB CONSTRUCTION CORPORATION (FORMERLY: EGB CONSTRUCTION) | 2054 | 2021 | 2022-12-03 | 01/07/2022 | 0 | 3205.82 | 2022-12-02 |  | 1
2022 | Region IV-B | OCCIDENTAL MINDORO | SABLAYAN (OCCIDENTAL MINDORO) | P00632931LZ | Construction of Flood Mitigation Structure | 120.8583 | 12.812 | 24750000 | 15725595.48 | 2022 | R.S. TAGALA CONSTRUCTION AND EQUIPMENT RENTALS | 2055 | 2022 | 2022-10-12 | 02/24/2022 | 9024404.52 | 0 | 2022-10-11 |  | 1
2024 | Region IV-B | OCCIDENTAL MINDORO | SABLAYAN (OCCIDENTAL MINDORO) | P00824745LZ | Construction of Flood Mitigation Structure | 120.8586 | 12.9308 | 19600000 | 19594346.03 | 2024 | KEJAMARENIK CONSTRUCTION & CONSTRUCTION SUPPLIES | 2056 | 2024 | 2024-05-15 | 02/14/2024 | 5653.97 | 0 | 2024-07-19 | 65
2024 | Region III | BULACAN | PLARIDEL (BULACAN) | P00821270LZ | Construction of Slope Protection Structure | 120.8586 | 14.8876 | 72374911.2 | 72374778.18 | 2024 | WAWAO BUILDERS | 2057 | 2024 | 2024-10-03 | 02/07/2024 | 133.02 | 0 | 2024-10-02 |  | 1
2023 | Region IV-B | OCCIDENTAL MINDORO | SABLAYAN (OCCIDENTAL MINDORO) | P00727376LZ | Construction of Flood Mitigation Structure | 120.8586 | 12.9628 | 45080000 | 43768024.75 | 2023 | F.A. TORRES CONSTRUCTION | 2058 | 2023 | 2023-11-20 | 03/08/2023 | 1311975.25 | 0 | 2023-11-19 |  | 1
2023 | Region IV-B | OCCIDENTAL MINDORO | SABLAYAN (OCCIDENTAL MINDORO) | P00726758LZ | Construction of Flood Mitigation Structure | 120.8586 | 12.9628 | 45080000 | 45078142.89 | 2023 | STX ENTERPRISES | 2059 | 2023 | 2023-10-10 | 02/10/2023 | 1857.11 | 0 | 2023-10-15 | 5
2022 | Region III | BULACAN | PLARIDEL (BULACAN) | P00621565LZ | Construction of Flood Mitigation Structure | 120.8586 | 14.8969 | 95534880.67 | 95534975.45 | 2023 | AZUL BUILDERS / JB CONSTRUCTION AND SUPPLY INC. (FORMERLY:JB CONSTRUCTION AND SUPPLY) | 2060 | 2022 | 2023-02-24 | 04/01/2022 | 0 | 94.78 | 2023-02-23 |  | 1
2022 | Region III | NUEVA ECIJA | ALIAGA (NUEVA ECIJA) | P00620528LZ | Construction of Flood Mitigation Structure | 120.8591 | 15.5315 | 45320100 | 45320100 | 2022 | IJK MAE CONSTRUCTION INC. / NIÃ‘AS CONSTRUCTION CORP. (FORMERLY: NINA'S CONSTRUCTION AND SUPPLIES) | 2061 | 2022 | 2022-08-07 | 02/09/2022 | 0 | 0 | 2022-08-06 |  | 1
2023 | Region III | BULACAN | GUIGUINTO (BULACAN) | P00736015LZ | Construction of Slope Protection Structure | 120.8593 | 14.8343 | 48249532.61 | 48249480.18 | 2023 | GREAT PACIFIC BUILDERS AND GEN. CONTRACTOR INC. | 2062 | 2023 | 2023-10-10 | 02/13/2023 | 52.43 | 0 | 2023-10-09 |  | 1
2023 | Region III | BULACAN | PLARIDEL (BULACAN) | P00726723LZ | Construction of Flood Mitigation Structure | 120.8593 | 14.8873 | 22784738.09 | 22784396.87 | 2023 | EIGHT KIDS CONSTRUCTION AND TRADING | 2063 | 2023 | 2023-08-04 | 02/06/2023 | 341.22 | 0 | 2023-08-03 |  | 1
2024 | Region IV-B | OCCIDENTAL MINDORO | SABLAYAN (OCCIDENTAL MINDORO) | P00824736LZ | Construction of Flood Mitigation Structure | 120.8593 | 12.813 | 39200000 | 39197204.13 | 2024 | F.A. TORRES CONSTRUCTION | 2064 | 2024 | 2024-08-15 | 03/07/2024 | 2795.87 | 0 | 2024-09-02 | 18
2022 | Region IV-A | CAVITE | ROSARIO (CAVITE) | P00620233LZ | Construction of Revetment | 120.8594 | 14.4211 | 89745000 | 89745000 | 2023 | TRIPLE 8 CONSTRUCTION & SUPPLY, INC. (FORMERLY TRIPLE 8 CONST. & SUPPLY) | 2065 | 2022 | 2023-03-20 | 02/28/2022 | 0 | 0 | 2023-05-18 | 59
2022 | Region IV-B | OCCIDENTAL MINDORO | SABLAYAN (OCCIDENTAL MINDORO) | P00621108LZ | Construction of Flood Mitigation Structure | 120.8599 | 12.9597 | 226774789.4 | 43424892.57 | 2023 | ANORE CONSTRUCTION | 2066 | 2022 | 2023-07-03 | 07/06/2022 | 183349896.83 | 0 | 2023-07-02 |  | 1
2023 | Region III | BULACAN | GUIGUINTO (BULACAN) | P00726478LZ | Construction of Flood Mitigation Structure | 120.8608 | 14.8349 | 96499425.96 | 96497527 | 2023 | A.R.L. CONSTRUCTION | 2067 | 2023 | 2023-10-09 | 02/13/2023 | 1898.96 | 0 | 2023-12-08 | 60
2022 | Region IV-A | CAVITE | TANZA (CAVITE) | P00620567LZ | Construction of Revetment | 120.8608 | 14.3978 | 49000000 | 49000000 | 2022 | AD PINEDA CONSTRUCTION / N.B. AVILA CONSTRUCTION | 2068 | 2022 | 2022-11-21 | 02/24/2022 | 0 | 0 | 2022-11-20 |  | 1
2022 | Region IV-A | CAVITE | TANZA (CAVITE) | P00620568LZ | Construction of Revetment | 120.8609 | 14.3978 | 49000000 | 47629922.43 | 2023 | BAQPRINCE CONSTRUCTION AND TRADING CORP. | 2069 | 2022 | 2023-01-05 | 02/24/2022 | 1370077.57 | 0 | 2022-12-20 |  | 16
2022 | Region I | PANGASINAN | UMINGAN (PANGASINAN) | P00620462LZ | Construction of Revetment | 120.8614 | 15.9328 | 29400000 | 29374620.62 | 2022 | RS RODRIGUEZ CONSTRUCTION & SUPPLIES | 2070 | 2022 | 2022-10-10 | 03/23/2022 | 25379.38 | 0 | 2022-09-07 |  | 33
2023 | Region III | BULACAN | PLARIDEL (BULACAN) | P00727279LZ | Construction of Flood Mitigation Structure | 120.8616 | 14.8879 | 72374620.55 | 69841235.75 | 2023 | L.R. TIQUI BUILDERS, INC. | 2071 | 2023 | 2023-12-08 | 03/14/2023 | 2533384.8 | 0 | 2023-12-07 |  | 1
2022 | Region IV-B | OCCIDENTAL MINDORO | SABLAYAN (OCCIDENTAL MINDORO) | P00620653LZ | Construction of Flood Mitigation Structure | 120.8624 | 12.9307 | 49000000 | 30933863.5 | 2023 | SIXTEEN ENTERPRISES-CALAPAN BRANCH | 2072 | 2022 | 2023-01-09 | 05/31/2022 | 18066136.5 | 0 | 2023-01-08 |  | 1
2024 | Region III | BULACAN | CITY OF MALOLOS (CAPITAL) (BULACAN) | P00838389LZ | Construction of Slope Protection Structure | 120.8026 | 14.8493 | 77199964.5 | 77188533.89 | 2024 | WAWAO BUILDERS | 2073 | 2024 | 2024-04-19 | 02/07/2024 | 11430.61 | 0 | 2024-10-02 | 166
2023 | Region III | BULACAN | GUIGUINTO (BULACAN) | P00726488LZ | Construction of Flood Mitigation Structure | 120.8626 | 14.8365 | 96499425.96 | 96497876.83 | 2023 | AZUL BUILDERS / JB CONSTRUCTION AND SUPPLY INC. (FORMERLY:JB CONSTRUCTION AND SUPPLY) | 2074 | 2023 | 2023-08-22 | 02/13/2023 | 1549.13 | 0 | 2023-12-08 | 108
2022 | Cordillera Administrative Region | ABRA | LICUAN-BAAY (LICUAN) (ABRA) | P00637052LZ | Construction of Flood Mitigation Structure | 120.8627 | 17.5442 | 48999940.99 | 48996810.89 | 2022 | ST. TIMOTHY CONSTRUCTION CORPORATION | 2075 | 2022 | 2022-09-15 | 04/13/2022 | 3130.1 | 0 | 2022-09-14 |  | 1
2022 | Region III | NUEVA ECIJA | SAN ANTONIO (NUEVA ECIJA) | P00620541LZ | Construction of Flood Mitigation Structure | 120.863 | 15.2648 | 24499928.44 | 24499995.94 | 2022 | IJK MAE CONSTRUCTION INC. | 2076 | 2022 | 2022-11-03 | 02/14/2022 | 0 | 67.5 | 2022-11-02 |  | 1
2023 | Region IV-A | CAVITE | ROSARIO (CAVITE) | P00725810LZ | Construction of Revetment | 120.8633 | 14.4257 | 75035505 | 75035504.1 | 2024 | ALMAKAR BUILDERS & METAL WORKS | 2077 | 2023 | 2024-01-03 | 02/19/2023 | 0.9 | 0 | 2024-01-02 |  | 1
2024 | Region III | BULACAN | PLARIDEL (BULACAN) | P00821264LZ | Construction of Slope Protection Structure | 120.8636 | 14.8895 | 72374940.39 | 72373592.08 | 2024 | TBB CONSTRUCTION CORP. | 2078 | 2024 | 2024-10-03 | 02/07/2024 | 1348.31 | 0 | 2024-10-02 |  | 1
2022 | Region IV-A | CAVITE | ROSARIO (CAVITE) | P00621543LZ | Construction of Drainage Structure | 120.8636 | 14.4231 | 24500000 | 24500000 | 2023 | ALMAKAR BUILDERS & METAL WORKS | 2079 | 2022 | 2023-03-15 | 03/31/2022 | 0 | 0 | 2023-03-14 |  | 1
2023 | Region III | BULACAN | PLARIDEL (BULACAN) | P00726719LZ | Construction of Flood Mitigation Structure | 120.8657 | 14.8907 | 29399673.58 | 29399409.16 | 2023 | 5-1 CONSTRUCTION CORPORATION | 2080 | 2023 | 2023-06-05 | 02/06/2023 | 264.42 | 0 | 2023-11-01 | 149
2023 | Region IV-A | CAVITE | ROSARIO (CAVITE) | P00737506LZ | Construction of Drainage Structure | 120.8659 | 14.4207 | 4950000 | 4899144.03 | 2023 | TWO DEGREES CONSTRUCTION AND SUPPLY | 2081 | 2023 | 2023-05-19 | 02/19/2023 | 50855.97 | 0 | 2023-05-18 |  | 1
2023 | Region IV-A | CAVITE | IMUS CITY (CAVITE) | P00726553LZ | Construction of Revetment | 120.9139 | 14.3754 | 91675000 | 91674088.89 | 2023 | N.B. AVILA CONSTRUCTION | 2082 | 2023 | 2023-11-20 | 02/19/2023 | 911.11 | 0 | 2023-11-19 |  | 1
2024 | Region III | BULACAN | PLARIDEL (BULACAN) | P00821265LZ | Construction of Slope Protection Structure | 120.8682 | 14.8917 | 72374905.39 | 72374848.46 | 2024 | BELL CONSTRUCTION | 2083 | 2024 | 2024-04-26 | 02/07/2024 | 56.93 | 0 | 2024-10-02 | 159
2022 | Region I | PANGASINAN | UMINGAN (PANGASINAN) | P00631094LZ | Construction of Revetment | 120.8686 | 15.9297 | 49000000 | 48960218.92 | 2022 | RS RODRIGUEZ CONSTRUCTION & SUPPLIES / JHI CONSTRUCTION & SUPPLY | 2084 | 2022 | 2022-10-10 | 03/23/2022 | 39781.08 | 0 | 2022-09-29 |  | 11
2025 | Region III | NUEVA ECIJA | SAN ISIDRO (NUEVA ECIJA) | P00921788LZ | Construction of Flood Mitigation Structure | 120.8687 | 15.304 | 34299998.36 | 34128123.18 | 2025 | TRIPLE S BUILDERS INC. | 2085 | 2025 | 2025-03-25 | 02/11/2025 | 171875.18 | 0 | 2025-10-04 | 193
2024 | Region IV-A | BATANGAS | LEMERY (BATANGAS) | P00839597LZ | Construction of Flood Mitigation Structure | 120.8704 | 13.948 | 4950000 | 4950000 | 2024 | SANDBANK CONSTRUCTION CORP. | 2086 | 2024 | 2024-04-15 | 02/19/2024 | 0 | 0 | 2024-05-22 | 37
2022 | National Capital Region | NAVOTAS CITY | CITY OF NAVOTAS (METROPOLITAN MANILA) | P00640484LZ | Construction of Flood Mitigation Structure | 120.9351 | 14.6867 | 48997250.26 | 49414754.65 | 2022 | ST. TIMOTHY CONSTRUCTION CORPORATION | 2087 | 2022 | 2022-11-18 | 03/24/2022 | 0 | 417504.39 | 2022-11-17 |  | 1
2023 | Region IV-A | CAVITE | NOVELETA (CAVITE) | P00725809LZ | Construction of Revetment | 120.8707 | 14.4323 | 77200000 | 77200000 | 2024 | GRAIA CONSTRUCTION CORPORATION | 2088 | 2023 | 2024-01-05 | 02/19/2023 | 0 | 0 | 2024-01-04 |  | 1
2023 | Region III | NUEVA ECIJA | SAN ISIDRO (NUEVA ECIJA) | P00727300LZ | Construction of Flood Mitigation Structure | 120.8712 | 15.3051 | 72374944.92 | 72374938.44 | 2023 | AMP 723 CONSTRUCTION CORPORATION (FORMERLY: A.M.P. CONSTRUCTION) / R.G. DELA CRUZ CONSTRUCTION | 2089 | 2023 | 2023-06-13 | 03/24/2023 | 6.48 | 0 | 2023-12-17 | 187
2023 | Region IV-A | CAVITE | NOVELETA (CAVITE) | P00725808LZ | Construction of Revetment | 120.8713 | 14.4331 | 96500000 | 96500000 | 2024 | GRAIA CONSTRUCTION CORPORATION | 2090 | 2023 | 2024-01-22 | 02/19/2023 | 0 | 0 | 2024-01-21 |  | 1
2023 | Region III | BULACAN | PLARIDEL (BULACAN) | P00726724LZ | Construction of Flood Mitigation Structure | 120.872 | 14.8917 | 22784568.69 | 22784013.43 | 2023 | NICLEDON CONSTRUCTION | 2091 | 2023 | 2023-09-03 | 02/06/2023 | 555.26 | 0 | 2023-09-02 |  | 1
2023 | Region III | BULACAN | GUIGUINTO (BULACAN) | P00726154LZ | Construction of Flood Mitigation Structure | 120.8721 | 14.8631 | 48999237.11 | 48999690.4 | 2023 | TOPNOTCH CATALYST BUILDERS INC. | 2092 | 2023 | 2023-06-26 | 02/06/2023 | 0 | 453.29 | 2023-08-03 | 38
2022 | Region III | BULACAN | GUIGUINTO (BULACAN) | P00620517LZ | Construction of Flood Mitigation Structure | 120.8721 | 14.8631 | 43119227.76 | 43119406.29 | 2022 | M.S. RAMOS CONSTRUCTION INC. (FORMERLY: M.S. RAMOS | 2093 | 2022 | 2022-12-22 | 05/27/2022 | 0 | 178.53 | 2022-12-21 |  | 1
2023 | Region III | BULACAN | GUIGUINTO (BULACAN) | P00726474LZ | Construction of Flood Mitigation Structure | 120.8723 | 14.8614 | 96499315.82 | 96497659.5 | 2023 | ORANI CONSTRUCTION AND SUPPLY CORPORATION (FORMERLY:ORANI BUILDERS & SUPPLY) | 2094 | 2023 | 2023-12-19 | 02/13/2023 | 1656.32 | 0 | 2024-02-06 | 49
2022 | Region IV-A | CAVITE | ROSARIO (CAVITE) | P00621542LZ | Construction of Drainage Structure | 120.8723 | 14.425 | 24500000 | 24500000 | 2023 | ALMAKAR BUILDERS & METAL WORKS | 2095 | 2022 | 2023-03-15 | 03/31/2022 | 0 | 0 | 2023-03-14 |  | 1
2024 | Region III | NUEVA ECIJA | QUEZON (NUEVA ECIJA) | P00820274LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.8726 | 15.5483 | 96500000 | 95534525.49 | 2024 | AMP 723 CONSTRUCTION CORPORATION (FORMERLY: A.M.P. CONSTRUCTION) / BRYAN PAUL P. PACHECO CONST. CORP. | 2096 | 2024 | 2024-08-12 | 02/06/2024 | 965474.51 | 0 | 2024-10-31 | 80
2024 | Region III | BULACAN | GUIGUINTO (BULACAN) | P00839481LZ | Construction of Slope Protection Structure | 120.8726 | 14.8502 | 59399968.49 | 59399639.41 | 2024 | TOPNOTCH CATALYST BUILDERS INC. / BEAM TEAM DEVELOPER SPECIALIST INC. | 2097 | 2024 | 2024-09-17 | 03/20/2024 | 329.08 | 0 | 2024-11-13 | 57
2024 | Region III | BULACAN | GUIGUINTO (BULACAN) | P00823460LZ | Construction of Flood Mitigation Structure | 120.8727 | 14.8569 | 77199462.44 | 77199409.66 | 2024 | TOPNOTCH CATALYST BUILDERS INC. | 2098 | 2024 | 2024-09-23 | 02/28/2024 | 52.78 | 0 | 2024-10-23 | 30
2024 | Region III | BULACAN | GUIGUINTO (BULACAN) | P00845969LZ | Construction of Flood Mitigation Structure | 120.8727 | 14.8565 | 19799487.72 | 19799198.1 | 2024 | JOSE RUBI CONSTRUCTION | 2099 | 2024 | 2024-06-28 | 03/01/2024 | 289.62 | 0 | 2024-06-27 |  | 1
2024 | Region III | BULACAN | GUIGUINTO (BULACAN) | P00839577LZ | Construction of Flood Mitigation Structure | 120.8728 | 14.8565 | 19799974.88 | 19739693.36 | 2024 | TBB CONSTRUCTION CORP. | 2100 | 2024 | 2024-06-11 | 02/02/2024 | 60281.52 | 0 | 2024-07-29 | 48
2024 | Region III | BULACAN | GUIGUINTO (BULACAN) | P00845803LZ | Construction of Slope Protection Structure | 120.8728 | 14.8565 | 98999813.35 | 98999656.35 | 2024 | TOPNOTCH CATALYST BUILDERS INC. / ONE FRAME CONSTRUCTION INC. | 2101 | 2024 | 2024-10-14 | 04/25/2024 | 157 | 0 | 2025-01-18 | 96
2024 | Region III | BULACAN | GUIGUINTO (BULACAN) | P00839476LZ | Construction of Slope Protection Structure | 120.8729 | 14.849 | 98999868.17 | 98999939.04 | 2024 | WAWAO BUILDERS | 2102 | 2024 | 2024-09-19 | 02/07/2024 | 0 | 70.87 | 2024-11-01 | 43
2023 | Region III | BULACAN | GUIGUINTO (BULACAN) | P00740348LZ | Construction of Flood Mitigation Structure | 120.8729 | 14.8581 | 72374068.34 | 72374703.78 | 2023 | M.S. RAMOS CONSTRUCTION INC. (FORMERLY: M.S. RAMOS | 2103 | 2023 | 2023-12-18 | 03/28/2023 | 0 | 635.44 | 2024-01-20 | 33
2023 | Region IV-A | CAVITE | TANZA (CAVITE) | P00726213LZ | Construction of Revetment | 120.8729 | 14.3565 | 49000000 | 48484888.32 | 2023 | R2A CONSTRUCTION & TRADING CORPORATION / J.V. SARIGNAYA CONSTRUCTION CORPORATION | 2104 | 2023 | 2023-06-02 | 03/06/2023 | 515111.68 | 0 | 2023-09-15 | 105
2024 | Region III | NUEVA ECIJA | LICAB (NUEVA ECIJA) | P00823432LZ | Construction of Flood Mitigation Structure | 120.7659 | 15.5759 | 48250000 | 47767302.32 | 2024 | IJK MAE CONSTRUCTION INC. | 2105 | 2024 | 2024-09-20 | 04/11/2024 | 482697.68 | 0 | 2024-11-05 | 46
2023 | Region III | BULACAN | CITY OF BALIUAG (BULACAN) | P00726460LZ | Construction of Flood Mitigation Structure | 120.8823 | 14.9819 | 96499679.61 | 96499420.64 | 2023 | L.R. TIQUI BUILDERS, INC. | 2106 | 2023 | 2023-11-10 | 02/13/2023 | 258.97 | 0 | 2023-12-08 | 28
2023 | Region III | BULACAN | HAGONOY (BULACAN) | P00740597LZ | Construction of Flood Mitigation Structure | 120.7662 | 14.8565 | 24499668.93 | 24499212.65 | 2023 | MICHARIAN BUILDERS AND TRADING | 2107 | 2023 | 2023-08-08 | 03/21/2023 | 456.28 | 0 | 2023-09-15 | 38
2024 | Region IV-A | BATANGAS | TAAL (BATANGAS) | P00846030LZ | Construction of Flood Mitigation Structure | 120.914 | 13.8607 | 4950000 | 4950000 | 2024 | L.P.O. ENTERPRISES | 2108 | 2024 | 2024-07-10 | 04/24/2024 | 0 | 0 | 2024-07-21 | 11
2022 | Region III | BULACAN | GUIGUINTO (BULACAN) | P00631214LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.8824 | 14.8426 | 45079678.05 | 45077524.96 | 2022 | TOPNOTCH CATALYST BUILDERS INC. / BLACK HARDHAT INC. (FORMERLY: JCHARDHAT INC.) | 2109 | 2022 | 2022-11-21 | 03/04/2022 | 2153.09 | 0 | 2022-12-27 | 36
2024 | Region III | BULACAN | CITY OF MALOLOS (CAPITAL) (BULACAN) | P00838363LZ | Construction of Revetment | 120.8039 | 14.8496 | 62724787.72 | 62724643.44 | 2024 | SYMS CONSTRUCTION TRADING | 2110 | 2024 | 2024-09-10 | 03/20/2024 | 144.28 | 0 | 2024-11-13 | 64
2022 | Region IV-A | CAVITE | NOVELETA (CAVITE) | P00631289LZ | Construction of Flood Mitigation Structure | 120.9142 | 14.4214 | 49000000 | 49000000 | 2023 | JAGONBUILD CONSTRUCTION CORP. (FOR. JAGON BUILDERS | 2111 | 2022 | 2023-01-04 | 02/24/2022 | 0 | 0 | 2023-01-03 |  | 1
2022 | Region IV-A | CAVITE | NAIC (CAVITE) | P00631291LZ | Construction of Flood Mitigation Structure | 120.7662 | 14.3199 | 34299950.11 | 30582429.65 | 2023 | MORTAR MASTERS & CONCRETE BUILDERS | 2112 | 2022 | 2023-11-29 | 03/14/2022 | 3717520.46 | 0 | 2023-07-29 |  | 123
2022 | Region IV-A | CAVITE | BACOOR CITY (CAVITE) | P00631295LZ | Construction of Flood Mitigation Structure | 120.9351 | 14.4556 | 48999988.37 | 48995805.15 | 2022 | E.R. RODRIGUEZ CONSTRUCTION CORPORATION (FORMERLY: E.R. RODRIGUEZ CONSTRUCTION) | 2113 | 2022 | 2022-12-02 | 02/24/2022 | 4183.22 | 0 | 2022-12-19 | 17
2022 | Region IV-A | CAVITE | KAWIT (CAVITE) | P00620881LZ | Construction of Revetment | 120.9256 | 14.4581 | 89745000 | 89745000 | 2022 | BAQPRINCE CONSTRUCTION AND TRADING CORP. / R.V. RIETA TRADING & GENERAL CONSTRUCTION | 2114 | 2022 | 2022-12-05 | 02/28/2022 | 0 | 0 | 2022-12-04 |  | 1
2024 | Region III | BULACAN | HAGONOY (BULACAN) | P00838397LZ | Construction of Slope Protection Structure | 120.7663 | 14.8602 | 77199982.41 | 77199192.34 | 2024 | WAWAO BUILDERS | 2115 | 2024 | 2024-09-03 | 02/07/2024 | 790.07 | 0 | 2024-10-02 | 29
2023 | Region III | BULACAN | BOCAUE (BULACAN) | P00726153LZ | Construction of Flood Mitigation Structure | 120.9259 | 14.7695 | 48999477.41 | 48999126.15 | 2023 | M.G. FRANCISCO CONSTRUCTION | 2116 | 2023 | 2023-10-20 | 02/06/2023 | 351.26 | 0 | 2023-11-01 | 12
2022 | Region III | BULACAN | SAN RAFAEL (BULACAN) | P00620156LZ | Construction of Flood Mitigation Structure | 120.9352 | 15.031 | 55004758.48 | 54171436.39 | 2022 | EIRISH BUILDERS & SUPPLY INC. | 2117 | 2022 | 2022-10-05 | 03/07/2022 | 833322.09 | 0 | 2022-10-04 |  | 1
2022 | Region III | BULACAN | BALAGTAS (BIGAA) (BULACAN) | P00621285LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.9144 | 14.8239 | 86849958.13 | 86849456.87 | 2023 | AZUL BUILDERS / JB CONSTRUCTION AND SUPPLY INC. (FORMERLY:JB CONSTRUCTION AND SUPPLY) | 2118 | 2022 | 2023-01-25 | 04/01/2022 | 501.26 | 0 | 2023-01-24 |  | 1
2022 | Region IV-A | CAVITE | CITY OF GENERAL TRIAS (CAVITE) | P00620874LZ | Construction of Revetment | 120.8824 | 14.3501 | 81542500 | 81542500 | 2022 | TRIPLE 8 CONSTRUCTION & SUPPLY, INC. (FORMERLY TRIPLE 8 CONST. & SUPPLY) | 2119 | 2022 | 2022-11-12 | 02/28/2022 | 0 | 0 | 2022-11-11 |  | 1
2022 | Region I | ILOCOS NORTE | DUMALNEG (ILOCOS NORTE) | P00620799LZ | Construction of Flood Mitigation Structure | 120.804 | 18.5115 | 85884919.01 | 85884916.66 | 2023 | FR ESPIRITU BUILDERS AND DEVELOPMENT CORP. (FORMERLY: FR ESPIRITU JR BUILDERS) | 2120 | 2022 | 2023-04-24 | 03/03/2022 | 2.35 | 0 | 2023-05-01 | 7
2023 | National Capital Region | MALABON CITY | CITY OF MALABON (METROPOLITAN MANILA) | P00725924LZ | Construction of Flood Mitigation Structure | 120.9261 | 14.6987 | 48998975.15 | 49000000 | 2023 | E.L. TORRES CONSTRUCTION AND TRADING INC. (FORMERLY : E. L. TORRES CONSTRUCTION & TRADING | 2121 | 2023 | 2023-10-12 | 02/15/2023 | 0 | 1024.85 | 2023-10-11 |  | 1
2022 | Region III | BULACAN | BULACAN (BULACAN) | P00640521LZ | Construction of Slope Protection Structure | 120.8825 | 14.7855 | 19799549.97 | 19798932.24 | 2022 | A.R.L. CONSTRUCTION | 2122 | 2022 | 2022-08-18 | 04/05/2022 | 617.73 | 0 | 2022-09-30 | 43
2024 | Cordillera Administrative Region | MOUNTAIN PROVINCE | BAUKO (MOUNTAIN PROVINCE) | P00821543LZ | Construction of Flood Mitigation Structure | 120.9146 | 16.8949 | 39199999.6 | 39200000 | 2024 | OLSIM CONSTRUCTION / GELLE CONSTRUCTION SERVICES | 2123 | 2024 | 2024-05-13 | 02/18/2024 | 0 | 0.4 | 2024-08-29 | 108
2022 | Region III | NUEVA ECIJA | GUIMBA (NUEVA ECIJA) | P00640522LZ | Construction of Drainage Structure | 120.7665 | 15.6611 | 4950000 | 4850929.84 | 2022 | KEVIN PAUL CONSTRUCTION | 2124 | 2022 | 2022-08-29 | 04/08/2022 | 99070.16 | 0 | 2022-08-28 |  | 1
2022 | Region IV-A | CAVITE | IMUS CITY (CAVITE) | P00621095LZ | Construction of Revetment | 120.9353 | 14.4398 | 9800000 | 9308892.5 | 2022 | KLDS TRADING & CONSTRUCTION | 2125 | 2022 | 2022-07-18 | 02/24/2022 | 491107.5 | 0 | 2022-07-17 |  | 1
2022 | Region III | BULACAN | BULACAN (BULACAN) | P00631202LZ | Construction of Slope Protection Structure | 120.8825 | 14.7856 | 19599653.99 | 19599146.33 | 2022 | A.R.L. CONSTRUCTION | 2126 | 2022 | 2022-08-16 | 01/28/2022 | 507.66 | 0 | 2022-08-24 | 8
2022 | Region III | BULACAN | PULILAN (BULACAN) | P00632820LZ | Construction of Slope Protection Structure | 120.8041 | 14.9022 | 13859739.33 | 13859903.3 | 2022 | A.C. SOLIVEN CONSTRUCTION & GENERAL MERCHANDISE | 2127 | 2022 | 2022-07-04 | 01/28/2022 | 0 | 163.97 | 2022-07-25 | 21
2023 | Region III | BULACAN | PANDI (BULACAN) | P00726483LZ | Construction of Flood Mitigation Structure | 120.9261 | 14.8322 | 96499971 | 96447739.58 | 2023 | WAWAO BUILDERS | 2128 | 2023 | 2023-09-11 | 02/13/2023 | 52231.42 | 0 | 2024-01-07 | 118
2023 | Region I | ILOCOS NORTE | PAGUDPUD (ILOCOS NORTE) | P00725630LZ | Construction of Flood Mitigation Structure | 120.9355 | 18.5435 | 57899962.12 | 57899823.82 | 2023 | ZEDIK BUILDERS / LINEAR CONSTRUCTION CORP. | 2129 | 2023 | 2023-11-17 | 04/12/2023 | 138.3 | 0 | 2024-01-06 | 50
2022 | Region III | BULACAN | BULACAN (BULACAN) | P00631205LZ | Construction of Slope Protection Structure | 120.8826 | 14.7856 | 26459498.59 | 26459286.24 | 2022 | SAMJS CONSTRUCTION SERVICES | 2130 | 2022 | 2022-10-06 | 04/05/2022 | 212.35 | 0 | 2022-11-29 | 54
2024 | National Capital Region | MALABON CITY | CITY OF MALABON (METROPOLITAN MANILA) | P00820543LZ | Construction of Flood Mitigation Structure | 120.9262 | 14.7002 | 48998648.85 | 49000000 | 2024 | JTC CRUZ CONSTRUCTION CO., INC. | 2131 | 2024 | 2024-10-08 | 02/12/2024 | 0 | 1351.15 | 2024-10-07 |  | 1
2021 | Cordillera Administrative Region | ABRA |  | P00561489LZ | Construction of Flood Mitigation Structure | 120.8042 | 17.8236 | 48999802.15 | 48997193.69 | 2022 | R.A. FANGLAYAN (RAF) GENERAL CONSTRUCTION INC. (FORMERLY:RAF GENERAL CONSTRUCTION) | 2132 | 2021 | 2022-10-05 | 01/20/2022 | 2608.46 | 0 | 2022-10-04 |  | 1
2022 | Region III | BULACAN | BALAGTAS (BIGAA) (BULACAN) | P00621482LZ | Construction of Flood Mitigation Structure | 120.9147 | 14.8248 | 29399093.26 | 29398972.04 | 2022 | SAMJS CONSTRUCTION SERVICES | 2133 | 2022 | 2022-11-30 | 04/05/2022 | 121.22 | 0 | 2022-11-29 |  | 1
2023 | National Capital Region | NAVOTAS CITY | CITY OF NAVOTAS (METROPOLITAN MANILA) | P00742221LZ | Construction of Flood Mitigation Facility | 120.9355 | 14.6689 | 19798724.75 | 19799376.22 | 2023 | TWO DIMENSION CONSTRUCTION | 2134 | 2023 | 2023-10-10 | 03/27/2023 | 0 | 651.47 | 2023-10-21 | 11
2024 | Region III | BULACAN | HAGONOY (BULACAN) | P00823451LZ | Construction of Revetment | 120.7665 | 14.8598 | 38599883.49 | 38599219.72 | 2024 | SYMS CONSTRUCTION TRADING | 2135 | 2024 | 2024-10-14 | 04/18/2024 | 663.77 | 0 | 2024-10-13 |  | 1
2023 | Region III | BULACAN | BOCAUE (BULACAN) | P00740587LZ | Construction of Flood Mitigation Structure | 120.9358 | 14.8103 | 48999812.59 | 48999923.37 | 2023 | 11-16 CONSTRUCTION / BOLTRON BUILDERS CORPORATION | 2136 | 2023 | 2023-11-13 | 03/21/2023 | 0 | 110.78 | 2023-11-14 | 1
2021 | Region I | ILOCOS NORTE |  | P00526252LZ | Construction of Flood Mitigation Structure | 120.8045 | 18.5354 | 81059648.98 | 81059647.56 | 2022 | BLUE MOUNTAIN BUILDERS & GENERAL MDSE.(FOR. BLUE M | 2137 | 2021 | 2022-07-15 | 12/24/2021 | 1.42 | 0 | 2022-09-03 | 50
2022 | Region IV-A | CAVITE | IMUS CITY (CAVITE) | P00620873LZ | Construction of Revetment | 120.9147 | 14.3689 | 90710000 | 90709000 | 2022 | FROMARC BUILDERS & GEN. MERCHANDISE / TRIPLE 8 CONSTRUCTION & SUPPLY, INC. (FORMERLY TRIPLE 8 CONST. & SUPPLY) | 2138 | 2022 | 2022-12-11 | 02/28/2022 | 1000 | 0 | 2022-12-10 |  | 1
2023 | Region III | BULACAN | BULACAN (BULACAN) | P00735979LZ | Construction of Flood Mitigation Structure | 120.8827 | 14.7767 | 77199601.04 | 77199976.53 | 2023 | WAWAO BUILDERS | 2139 | 2023 | 2023-11-13 | 02/13/2023 | 0 | 375.49 | 2023-12-08 | 25
2024 | Region III | NUEVA ECIJA | GUIMBA (NUEVA ECIJA) | P00823470LZ | Construction of Flood Mitigation Structure | 120.7667 | 15.5774 | 48250000 | 47767320.74 | 2024 | DGSARM BUILDERS INC. (FORMERLY: D.G. SARMENTA CONSTRUCTION) | 2140 | 2024 | 2024-09-26 | 03/01/2024 | 482679.26 | 0 | 2024-09-25 |  | 1
2023 | Region IV-B | OCCIDENTAL MINDORO | SABLAYAN (OCCIDENTAL MINDORO) | P00726263LZ | Construction of Flood Mitigation Structure | 120.805 | 12.9247 | 45080000 | 45073999.67 | 2023 | GREAT PACIFIC BUILDERS AND GEN. CONTRACTOR INC. | 2141 | 2023 | 2023-12-12 | 04/14/2023 | 6000.33 | 0 | 2023-12-26 | 14
2022 | Region IV-A | CAVITE | AMADEO (CAVITE) | P00631288LZ | Construction of Flood Mitigation Structure | 120.9263 | 14.168 | 9800000 | 9304769.1 | 2022 | R.V. RIETA TRADING & GENERAL CONSTRUCTION | 2142 | 2022 | 2022-08-06 | 03/06/2022 | 495230.9 | 0 | 2022-08-05 |  | 1
2022 | Region IV-A | CAVITE | CITY OF GENERAL TRIAS (CAVITE) | P00620875LZ | Construction of Revetment | 120.8827 | 14.3745 | 81924640 | 81924640 | 2022 | TRIPLE 8 CONSTRUCTION & SUPPLY, INC. (FORMERLY TRIPLE 8 CONST. & SUPPLY) | 2143 | 2022 | 2022-11-12 | 02/28/2022 | 0 | 0 | 2022-11-11 |  | 1
2023 | National Capital Region | NAVOTAS CITY | CITY OF NAVOTAS (METROPOLITAN MANILA) | P00742227LZ | Construction of Flood Mitigation Structure | 120.9359 | 14.6749 | 49495301.45 | 49499652.24 | 2024 | TOPNOTCH CATALYST BUILDERS INC. | 2144 | 2023 | 2024-01-20 | 03/27/2023 | 0 | 4350.79 | 2024-01-19 |  | 1
2023 | Region IV-A | BATANGAS | CITY OF CALACA (BATANGAS) | P00737489LZ | Construction of Flood Mitigation Structure | 120.8052 | 13.9706 | 6930000 | 6930000 | 2023 | W. GOMEZ TRADING AND CONSTRUCTION | 2145 | 2023 | 2023-08-27 | 05/25/2023 | 0 | 0 | 2023-08-26 |  | 1
2024 | Region III | NUEVA ECIJA | TALAVERA (NUEVA ECIJA) | P00844536LZ | Construction of Drainage Structure | 120.9148 | 15.5591 | 19300000 | 19107581.48 | 2025 | DGSARM BUILDERS INC. (FORMERLY: D.G. SARMENTA CONSTRUCTION) | 2146 | 2024 | 2025-01-09 | 06/14/2024 | 192418.52 | 0 | 2025-01-08 |  | 1
2021 | Cordillera Administrative Region | ABRA |  | P00561517LZ | Construction of Flood Mitigation Structure | 120.7669 | 17.4558 | 97999983.85 | 96496961.02 | 2022 | 739 BUILDERS | 2147 | 2021 | 2022-11-21 | 12/28/2021 | 1503022.83 | 0 | 2022-11-22 | 1
2022 | Region IV-B | OCCIDENTAL MINDORO | SABLAYAN (OCCIDENTAL MINDORO) | P00621109LZ | Construction of Flood Mitigation Structure | 120.9153 | 12.9754 | 226774789.4 | 43424984.72 | 2023 | ANORE CONSTRUCTION | 2148 | 2022 | 2023-07-03 | 07/06/2022 | 183349804.68 | 0 | 2023-07-02 |  | 1
2024 | Region IV-A | BATANGAS | MABINI (BATANGAS) | P00823538LZ | Construction of Flood Mitigation Structure | 120.8833 | 13.7034 | 24500000 | 24125000 | 2024 | V.R. PATRON BUILDERS & DEVELOPERS CORP. (PREVIOUSL | 2149 | 2024 | 2024-05-15 | 02/07/2024 | 375000 | 0 | 2024-06-28 | 44
2023 | Region III | BULACAN | BOCAUE (BULACAN) | P00726484LZ | Construction of Flood Mitigation Structure | 120.9263 | 14.7694 | 96499156.63 | 96499970.89 | 2023 | WAWAO BUILDERS | 2150 | 2023 | 2023-06-07 | 02/13/2023 | 0 | 814.26 | 2023-12-08 | 184
2022 | Region IV-A | BATANGAS | LEMERY (BATANGAS) | P00620892LZ | Construction of Flood Mitigation Structure | 120.9154 | 13.8871 | 86850000 | 86850000 | 2022 | ALPHA & OMEGA GEN. CONTRACTOR & DEVELOPMENT CORP. | 2151 | 2022 | 2022-10-01 | 02/23/2022 | 0 | 0 | 2022-10-19 | 18
2022 | Region III | NUEVA ECIJA | GUIMBA (NUEVA ECIJA) | P00620168LZ | Construction of Flood Mitigation Structure | 120.7682 | 15.5781 | 67550000 | 67550000 | 2022 | DGSARM BUILDERS INC. (FORMERLY: D.G. SARMENTA CONSTRUCTION) | 2152 | 2022 | 2022-08-17 | 02/24/2022 | 0 | 0 | 2022-10-20 | 64
2022 | National Capital Region | NAVOTAS CITY | CITY OF NAVOTAS (METROPOLITAN MANILA) | P00620340LZ | Construction of Flood Mitigation Structure | 120.936 | 14.686 | 48999504.27 | 48989387.07 | 2022 | A.L. SALAZAR CONSTRUCTION, INC. / TOPNOTCH CATALYST BUILDERS INC. | 2153 | 2022 | 2022-09-23 | 02/14/2022 | 10117.2 | 0 | 2022-10-10 | 17
2023 | Region IV-A | BATANGAS | SAN LUIS (BATANGAS) | P00725779LZ | Construction of Flood Mitigation Structure | 120.916 | 13.8364 | 50509065 | 50509065 | 2023 | GREENFIELD CONSTRUCTION / THREE W BUILDERS, INC. | 2154 | 2023 | 2023-10-31 | 02/10/2023 | 0 | 0 | 2023-10-30 |  | 1
2023 | Region III | BULACAN | CITY OF MALOLOS (CAPITAL) (BULACAN) | P00742157LZ | Construction of Flood Mitigation Structure | 120.8075 | 14.7713 | 69299992.13 | 69295781.68 | 2024 | DMLC BUILDERS | 2155 | 2023 | 2024-01-21 | 03/28/2023 | 4210.45 | 0 | 2024-01-20 |  | 1
2023 | Region III | BULACAN | BUSTOS (BULACAN) | P00737455LZ | Construction of Drainage Structure | 120.9361 | 14.9519 | 4949760.23 | 4948539.44 | 2023 | PLL BUILDERS INC. | 2156 | 2023 | 2023-07-05 | 02/06/2023 | 1220.79 | 0 | 2023-07-04 |  | 1
2023 | Region III | PAMPANGA | CANDABA (PAMPANGA) | P00726911LZ | Construction of Slope Protection Structure | 120.9163 | 15.0458 | 72375000 | 68321428.5 | 2024 | STO. CRISTO CONSTRUCTION & TRADING INC. (FOR: STO. CRISTO CONSTRUCTION & TRADING) | 2157 | 2023 | 2024-01-11 | 04/04/2023 | 4053571.5 | 0 | 2024-01-10 |  | 1
2023 | Region III | BULACAN | BUSTOS (BULACAN) | P00737454LZ | Construction of Drainage Structure | 120.9263 | 14.9067 | 4949642.02 | 4949134.05 | 2023 | TIONGCO MENDOZA CONSTRUCTION CO. INC. | 2158 | 2023 | 2023-03-21 | 02/06/2023 | 507.97 | 0 | 2023-06-04 | 75
2023 | Region III | BULACAN | CITY OF MALOLOS (CAPITAL) (BULACAN) | P00742326LZ | Construction of Flood Mitigation Structure | 120.8075 | 14.7711 | 49499836.75 | 49498339.64 | 2023 | TOPNOTCH CATALYST BUILDERS INC. | 2159 | 2023 | 2023-11-08 | 03/27/2023 | 1497.11 | 0 | 2024-01-19 | 72
2022 | Region III | BULACAN | CITY OF BALIUAG (BULACAN) | P00621279LZ | Construction of Flood Mitigation Structure | 120.8834 | 14.9837 | 67549939.97 | 67550000 | 2023 | DMLC BUILDERS | 2160 | 2022 | 2023-09-28 | 04/04/2022 | 0 | 60.03 | 2023-09-27 |  | 1
2022 | Region III | BULACAN | CALUMPIT (BULACAN) | P00631184LZ | Construction of Flood Mitigation Structure | 120.7683 | 14.9183 | 19599454.59 | 19595787.01 | 2022 | SAMJS CONSTRUCTION SERVICES | 2161 | 2022 | 2022-10-24 | 01/28/2022 | 3667.58 | 0 | 2022-10-23 |  | 1
2022 | Region III | NUEVA ECIJA | LICAB (NUEVA ECIJA) | P00639361LZ | Construction of Flood Mitigation Structure | 120.8087 | 15.5122 | 96500000 | 96500000 | 2022 | AMP 723 CONSTRUCTION CORPORATION (FORMERLY: A.M.P. CONSTRUCTION) | 2162 | 2022 | 2022-12-07 | 04/04/2022 | 0 | 0 | 2022-12-28 | 21
2024 | Region III | BULACAN | OBANDO (BULACAN) | P00825062LZ | Construction of Flood Mitigation Structure | 120.9168 | 14.7458 | 96499852.52 | 96499745.71 | 2025 | L.R. TIQUI BUILDERS, INC. / 729 CONSTRUCTION, INC. (FORMERLY 722 CONSTRUCTION, INC.) | 2163 | 2024 | 2025-01-26 | 03/18/2024 | 106.81 | 0 | 2025-01-25 |  | 1
2023 | National Capital Region | NAVOTAS CITY | CITY OF NAVOTAS (METROPOLITAN MANILA) | P00726996LZ | Construction of Flood Mitigation Facility | 120.9361 | 14.6817 | 23270195.15 | 23272477.27 | 2023 | 5-1 CONSTRUCTION CORPORATION | 2164 | 2023 | 2023-12-27 | 03/08/2023 | 0 | 2282.12 | 2023-12-26 |  | 1
2023 | Region III | BULACAN | CALUMPIT (BULACAN) | P00726157LZ | Construction of Flood Mitigation Structure | 120.7685 | 14.9202 | 48999752.5 | 48999697.32 | 2023 | TOPNOTCH CATALYST BUILDERS INC. | 2165 | 2023 | 2023-06-23 | 02/06/2023 | 55.18 | 0 | 2023-10-02 | 101
2024 | Region III | NUEVA ECIJA | CABANATUAN CITY (NUEVA ECIJA) | P00821255LZ | Construction of Flood Mitigation Structure | 120.917 | 15.4707 | 86849964.87 | 86849964.84 | 2024 | DGSARM BUILDERS INC. (FORMERLY: D.G. SARMENTA CONSTRUCTION) | 2166 | 2024 | 2024-08-06 | 02/13/2024 | 0.03 | 0 | 2024-11-16 | 102
2024 | Region III | TARLAC | MONCADA (TARLAC) | P00823400LZ | Construction of Flood Mitigation Structure | 120.8088 | 15.7218 | 96500000 | 99000000 | 2024 | T2B3 BUILDERS AND SUPPLIES CORP. | 2167 | 2024 | 2024-10-16 | 02/16/2024 | 0 | 2500000 | 2024-10-15 |  | 1
2022 | Region III | NUEVA ECIJA | SAN LEONARDO (NUEVA ECIJA) | P00637075LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.9263 | 15.3661 | 39199931.37 | 38213807.11 | 2022 | E.D. LIBUNAO CONSTRUCTION & TRADING | 2168 | 2022 | 2022-07-12 | 04/04/2022 | 986124.26 | 0 | 2022-10-29 | 109
2024 | Region III | BULACAN | CITY OF BALIUAG (BULACAN) | P00838373LZ | Construction of Slope Protection Structure | 120.8835 | 14.9994 | 72374963.73 | 72374388.95 | 2024 | WAWAO BUILDERS | 2169 | 2024 | 2024-11-02 | 02/07/2024 | 574.78 | 0 | 2024-11-01 |  | 1
2024 | Cordillera Administrative Region | BENGUET | MANKAYAN (BENGUET) | P00820736LZ | Construction of Flood Mitigation Structure | 120.7687 | 16.9173 | 14700000 | 14691603 | 2024 | LAYAD GENERAL ENGINEERING CONSTRUCTION AND AGGREGATES | 2170 | 2024 | 2024-06-19 | 02/26/2024 | 8397 | 0 | 2024-08-15 | 57
2023 | Region III | BULACAN | CITY OF MALOLOS (CAPITAL) (BULACAN) | P00742151LZ | Construction of Flood Mitigation Structure | 120.8091 | 14.8429 | 69299888.11 | 69299784.14 | 2024 | DMLC BUILDERS | 2171 | 2023 | 2024-01-21 | 03/28/2023 | 103.97 | 0 | 2024-01-20 |  | 1
2024 | Region III | BULACAN | BALAGTAS (BIGAA) (BULACAN) | P00838374LZ | Construction of Slope Protection Structure | 120.917 | 14.8659 | 96499945.03 | 96499114.57 | 2024 | A.R.L. CONSTRUCTION | 2172 | 2024 | 2024-11-18 | 02/07/2024 | 830.46 | 0 | 2024-12-01 | 13
2024 | Region III | BULACAN | CITY OF BALIUAG (BULACAN) | P00838418LZ | Construction of Slope Protection Structure | 120.8837 | 14.9711 | 96499834.68 | 96498805.78 | 2024 | TOPNOTCH CATALYST BUILDERS INC. | 2173 | 2024 | 2024-10-29 | 02/07/2024 | 1028.9 | 0 | 2024-11-01 | 3
2023 | Region III | BULACAN | CITY OF MALOLOS (CAPITAL) (BULACAN) | P00742155LZ | Construction of Flood Mitigation Structure | 120.8105 | 14.783 | 79199623.63 | 79197823.4 | 2024 | JTC CRUZ CONSTRUCTION CO., INC. | 2174 | 2023 | 2024-01-21 | 03/28/2023 | 1800.23 | 0 | 2024-01-20 |  | 1
2024 | Region III | BULACAN | HAGONOY (BULACAN) | P00838398LZ | Construction of Slope Protection Structure | 120.7703 | 14.8717 | 77199993.32 | 77197558.67 | 2024 | WAWAO BUILDERS | 2175 | 2024 | 2024-10-03 | 02/07/2024 | 2434.65 | 0 | 2024-10-02 |  | 1
2021 | National Capital Region | MALABON CITY |  | P00525712LZ | Construction of Dike | 120.9264 | 14.6918 | 34789361 | 34790000 | 2022 | JUSTBILT BUILDERS | 2176 | 2021 | 2022-09-19 | 03/24/2022 | 0 | 639 | 2022-09-18 |  | 1
2023 | Cordillera Administrative Region | MOUNTAIN PROVINCE | BONTOC (CAPITAL) (MOUNTAIN PROVINCE) | P00727403LZ | Construction of Flood Mitigation Structure | 120.9361 | 17.0419 | 48999999.5 | 49000000 | 2023 | JBA CONSTRUCTION AND BUILDERS | 2177 | 2023 | 2023-10-14 | 05/24/2023 | 0 | 0.5 | 2023-12-02 | 49
2022 | Region IV-A | CAVITE | NAIC (CAVITE) | P00620573LZ | Construction of Flood Mitigation Structure | 120.7706 | 14.3156 | 32835021.45 | 32073418.52 | 2022 | HAUSLAND CONSTRUCTION | 2178 | 2022 | 2022-08-01 | 03/14/2022 | 761602.93 | 0 | 2022-10-02 | 62
2022 | Region IV-A | CAVITE | BACOOR CITY (CAVITE) | P00631296LZ | Construction of Revetment | 120.9362 | 14.4542 | 55859954.92 | 55858753.16 | 2022 | GRAIA CONSTRUCTION CORPORATION | 2179 | 2022 | 2022-11-07 | 04/07/2022 | 1201.76 | 0 | 2022-11-06 |  | 1
2023 | Region III | PAMPANGA | CANDABA (PAMPANGA) | P00726890LZ | Construction of Slope Protection Structure | 120.9172 | 15.1242 | 144749227 | 144750000 | 2024 | STO. CRISTO CONSTRUCTION & TRADING INC. (FOR: STO. CRISTO CONSTRUCTION & TRADING) | 2180 | 2023 | 2024-05-16 | 08/21/2023 | 0 | 773 | 2024-05-15 |  | 1
2023 | Region III | NUEVA ECIJA | CITY OF GAPAN (NUEVA ECIJA) | P00727303LZ | Construction of Flood Mitigation Structure | 120.9266 | 15.3084 | 96499990.95 | 96499840.4 | 2023 | ITP CONSTRUCTION, INC. / PAN AQUARIUS CONSTRUCTION AND DEVELOPMENT CORPORATION | 2181 | 2023 | 2023-09-19 | 04/03/2023 | 150.55 | 0 | 2024-01-20 | 123
2024 | Region III | BULACAN | CITY OF BALIUAG (BULACAN) | P00843305LZ | Construction of Flood Mitigation Structure | 120.8838 | 14.9712 | 77199926.2 | 77199553.69 | 2024 | GLOBALCRETE BUILDERS INC. | 2182 | 2024 | 2024-10-24 | 02/28/2024 | 372.51 | 0 | 2024-10-23 |  | 1
2023 | National Capital Region | NAVOTAS CITY | CITY OF NAVOTAS (METROPOLITAN MANILA) | P00726995LZ | Construction of Flood Mitigation Facility | 120.9362 | 14.6746 | 23265138.75 | 22560205.05 | 2024 | BLACK HARDHAT INC. (FORMERLY: JCHARDHAT INC.) | 2183 | 2023 | 2024-11-21 | 03/08/2023 | 704933.7 | 0 | 2024-11-22 | 1
2024 | Region III | BULACAN | CALUMPIT (BULACAN) | P00823359LZ | Construction of Flood Mitigation Structure | 120.7708 | 14.9164 | 67549855.79 | 67547497.79 | 2024 | FERDSTAR BUILDERS INC. | 2184 | 2024 | 2024-11-05 | 03/11/2024 | 2358 | 0 | 2024-11-04 |  | 1
2022 | Region III | BULACAN | BALAGTAS (BIGAA) (BULACAN) | P00639473LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.9173 | 14.8631 | 48999538.61 | 48997800.81 | 2023 | 729 CONSTRUCTION, INC. (FORMERLY 722 CONSTRUCTION, INC.) | 2185 | 2022 | 2023-01-28 | 04/04/2022 | 1737.8 | 0 | 2023-01-27 |  | 1
2024 | Region III | BULACAN | CITY OF MALOLOS (CAPITAL) (BULACAN) | P00843318LZ | Construction of Flood Mitigation Structure | 120.8107 | 14.7684 | 72374675.3 | 72366243.51 | 2024 | SYMS CONSTRUCTION TRADING | 2186 | 2024 | 2024-06-24 | 04/23/2024 | 8431.79 | 0 | 2024-12-17 | 176
2024 | Region III | BULACAN | CITY OF BALIUAG (BULACAN) | P00821263LZ | Construction of Slope Protection Structure | 120.8838 | 14.9711 | 72374961.51 | 72374160.68 | 2024 | BELL CONSTRUCTION | 2187 | 2024 | 2024-11-02 | 02/07/2024 | 800.83 | 0 | 2024-11-01 |  | 1
2023 | National Capital Region | MALABON CITY | CITY OF MALABON (METROPOLITAN MANILA) | P00725570LZ | Construction of Flood Mitigation Facility | 120.9364 | 14.6862 | 134185393.7 | 134190886.8 | 2024 | E. F. CHUA CONSTRUCTION, INC. | 2188 | 2023 | 2024-03-21 | 03/28/2023 | 0 | 5493.1 | 2024-03-20 |  | 1
2023 | National Capital Region | MALABON CITY | CITY OF MALABON (METROPOLITAN MANILA) | P00725922LZ | Construction of Flood Mitigation Structure | 120.9267 | 14.7007 | 48997939.44 | 49000000 | 2023 | JAGONBUILD CONSTRUCTION CORP. (FOR. JAGON BUILDERS | 2189 | 2023 | 2023-05-22 | 02/15/2023 | 0 | 2060.56 | 2023-10-11 | 142
2023 | Region III | BULACAN | CITY OF MALOLOS (CAPITAL) (BULACAN) | P00736007LZ | Construction of Revetment | 120.8108 | 14.7578 | 28949433.03 | 28946436.68 | 2023 | EL KAPITAN CONSTRUCTION SERVICES | 2190 | 2023 | 2023-10-10 | 02/13/2023 | 2996.35 | 0 | 2023-10-09 |  | 1
2022 | Region III | BULACAN | CITY OF BALIUAG (BULACAN) | P00639469LZ | Construction of Flood Mitigation Structure | 120.8839 | 14.9836 | 48999297.77 | 48999405.84 | 2023 | ST. MATTHEW GEN. CONTRACTOR & DEVELOPMENT CORP. | 2191 | 2022 | 2023-01-26 | 04/05/2022 | 0 | 108.07 | 2023-01-28 | 2
2022 | Region IV-A | BATANGAS | MABINI (BATANGAS) | P00632868LZ | Construction of Flood Mitigation Structure | 120.9364 | 13.7341 | 4950000 | 4950000 | 2022 | GREENFIELD CONSTRUCTION | 2192 | 2022 | 2022-07-30 | 02/09/2022 | 0 | 0 | 2022-07-29 |  | 1
2022 | Region III | NUEVA ECIJA | JAEN (NUEVA ECIJA) | P00621417LZ | Construction of Flood Mitigation Structure | 120.9174 | 15.3792 | 72374963.74 | 62301773.29 | 2023 | R.D. TALENS CONSTRUCTION AND TRADING | 2193 | 2022 | 2023-02-24 | 04/07/2022 | 10073190.45 | 0 | 2023-02-23 |  | 1
2023 | Region III | BULACAN | CITY OF MALOLOS (CAPITAL) (BULACAN) | P00740331LZ | Construction of Revetment | 120.8109 | 14.83 | 72374649.03 | 72374406.26 | 2024 | TRIPLE 8 CONSTRUCTION & SUPPLY, INC. (FORMERLY TRIPLE 8 CONST. & SUPPLY) | 2194 | 2023 | 2024-01-21 | 03/28/2023 | 242.77 | 0 | 2024-01-20 |  | 1
2023 | Region III | PAMPANGA | SANTA ANA (PAMPANGA) | P00740603LZ | Construction of Drainage Structure | 120.771 | 15.108 | 14700000 | 13957614.2 | 2024 | THREE-IN-ONE CONSTRUCTION & TRADING | 2195 | 2023 | 2024-02-19 | 07/05/2023 | 742385.8 | 0 | 2023-12-06 |  | 75
2023 | Region III | BULACAN | SAN RAFAEL (BULACAN) | P00744233LZ | Construction of Flood Mitigation Structure | 120.9364 | 15.0354 | 96499964.52 | 96498885.9 | 2024 | EIRISH BUILDERS & SUPPLY INC. | 2196 | 2023 | 2024-03-15 | 06/20/2023 | 1078.62 | 0 | 2024-03-14 |  | 1
2024 | Region III | BULACAN | CITY OF BALIUAG (BULACAN) | P00839475LZ | Construction of Slope Protection Structure | 120.8839 | 14.9691 | 98999833.32 | 98999220.54 | 2024 | JAGONBUILD CONSTRUCTION CORP. (FOR. JAGON BUILDERS | 2197 | 2024 | 2024-11-02 | 02/07/2024 | 612.78 | 0 | 2024-11-01 |  | 1
2022 | Region III | PAMPANGA | SANTA ANA (PAMPANGA) | P00639362LZ | Rehabilitation / Major Repair of Drainage Structure | 120.7715 | 15.1098 | 96500000 | 93122497.85 | 2023 | ROYAL CROWN MONARCH CONSTRUCTION & SUPPLIES CORP. | 2198 | 2022 | 2023-03-30 | 05/20/2022 | 3377502.15 | 0 | 2023-03-29 |  | 1
2023 | Region III | BULACAN | SAN RAFAEL (BULACAN) | P00744234LZ | Construction of Flood Mitigation Structure | 120.9364 | 15.0354 | 96499964.52 | 96499463.56 | 2024 | EIRISH BUILDERS & SUPPLY INC. | 2199 | 2023 | 2024-05-14 | 06/20/2023 | 500.96 | 0 | 2024-05-13 |  | 1
2023 | Region III | BULACAN | BOCAUE (BULACAN) | P00740346LZ | Construction of Flood Mitigation Structure | 120.9267 | 14.7715 | 72374745.82 | 72374656.27 | 2024 | DARCY & ANNA BUILDERS & TRADING | 2200 | 2023 | 2024-01-21 | 03/28/2023 | 89.55 | 0 | 2024-01-20 |  | 1
2023 | Region III | BULACAN | CITY OF MALOLOS (CAPITAL) (BULACAN) | P00740363LZ | Construction of Flood Mitigation Structure | 120.811 | 14.7847 | 96499571.86 | 96497317.65 | 2023 | FERDSTAR BUILDERS INC. | 2201 | 2023 | 2023-12-11 | 03/28/2023 | 2254.21 | 0 | 2024-03-20 | 100
2021 | Region III | BULACAN |  | P00525568LZ | Construction of Flood Mitigation Structure | 120.7718 | 14.9014 | 96499775.9 | 96499940.4 | 2023 | TOPNOTCH CATALYST BUILDERS INC. | 2202 | 2021 | 2023-01-22 | 01/28/2022 | 0 | 164.5 | 2023-01-21 |  | 1
2023 | National Capital Region | MALABON CITY | CITY OF MALABON (METROPOLITAN MANILA) | P00725491LZ | Construction of Flood Mitigation Facility | 120.9365 | 14.6863 | 96487124.65 | 96500000 | 2024 | NEWBIG FOUR J CONSTRUCTION INC., (FORMERLY FOUR J | 2203 | 2023 | 2024-02-17 | 02/23/2023 | 0 | 12875.35 | 2024-02-16 |  | 1
2024 | Region III | BULACAN | BALAGTAS (BIGAA) (BULACAN) | P00838377LZ | Construction of Slope Protection Structure | 120.9175 | 14.8649 | 96499972.77 | 96499907.13 | 2024 | A.R.L. CONSTRUCTION | 2204 | 2024 | 2024-12-02 | 02/07/2024 | 65.64 | 0 | 2024-12-01 |  | 1
2023 | Region III | NUEVA ECIJA | JAEN (NUEVA ECIJA) | P00727299LZ | Construction of Flood Mitigation Structure | 120.9268 | 15.3642 | 72374949.98 | 72374624.95 | 2023 | ITP CONSTRUCTION, INC. | 2205 | 2023 | 2023-12-14 | 03/29/2023 | 325.03 | 0 | 2023-12-22 | 8
2022 | Region III | BULACAN | CITY OF MALOLOS (CAPITAL) (BULACAN) | P00631195LZ | Construction of Flood Mitigation Structure | 120.8111 | 14.7853 | 34299947.39 | 34299237.64 | 2022 | WAWAO BUILDERS | 2206 | 2022 | 2022-07-26 | 01/28/2022 | 709.75 | 0 | 2022-07-25 |  | 1
2024 | Region III | BULACAN | CALUMPIT (BULACAN) | P00838416LZ | Construction of Slope Protection Structure | 120.7722 | 14.9164 | 77199984.79 | 77199865.91 | 2024 | TOPNOTCH CATALYST BUILDERS INC. | 2207 | 2024 | 2024-03-18 | 02/07/2024 | 118.88 | 0 | 2024-10-02 | 198
2023 | Region III | BULACAN | GUIGUINTO (BULACAN) | P00726477LZ | Construction of Flood Mitigation Structure | 120.8839 | 14.8539 | 96499351.52 | 96498376.03 | 2023 | A.R.L. CONSTRUCTION | 2208 | 2023 | 2023-10-11 | 02/13/2023 | 975.49 | 0 | 2024-02-06 | 118
2024 | Region III | BULACAN | BALAGTAS (BIGAA) (BULACAN) | P00838376LZ | Construction of Slope Protection Structure | 120.9268 | 14.8324 | 96499903.14 | 96499605.25 | 2025 | AMETHYST HORIZON BUILDERS AND GEN. CONTRACTOR AND DEVELOPMENT CORP. | 2209 | 2024 | 2025-01-31 | 02/07/2024 | 297.89 | 0 | 2025-01-30 |  | 1
2023 | Region III | BULACAN | CITY OF MALOLOS (CAPITAL) (BULACAN) | P00736612LZ | Construction of Flood Mitigation Structure | 120.8111 | 14.7858 | 48999797.63 | 48999995.09 | 2023 | WAWAO BUILDERS | 2210 | 2023 | 2023-07-03 | 02/06/2023 | 0 | 197.46 | 2023-10-02 | 91
2023 | National Capital Region | NAVOTAS CITY | CITY OF NAVOTAS (METROPOLITAN MANILA) | P00742225LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.9366 | 14.6746 | 19793401.75 | 19799811 | 2023 | TOPNOTCH CATALYST BUILDERS INC. | 2211 | 2023 | 2023-10-22 | 03/27/2023 | 0 | 6409.25 | 2023-10-21 |  | 1
2022 | Cordillera Administrative Region | ABRA | BUCLOC (ABRA) | P00632766LZ | Construction of Flood Mitigation Structure | 120.884 | 17.4444 | 48999807.43 | 49497342 | 2022 | ST. TIMOTHY CONSTRUCTION CORPORATION | 2212 | 2022 | 2022-11-03 | 04/13/2022 | 0 | 497534.57 | 2022-11-02 |  | 1
2021 | Region III | BULACAN |  | P00561530LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.8114 | 14.8439 | 48999916.72 | 48998928.29 | 2022 | PRECIOUS CONSTRUCTION | 2213 | 2021 | 2022-09-10 | 01/14/2022 | 988.43 | 0 | 2022-09-09 |  | 1
2021 | Region III | BULACAN |  | P00561692LZ | Construction of Flood Mitigation Structure | 120.7735 | 14.9027 | 24749152.7 | 24749752.99 | 2022 | RVR3 CONSTRUCTION SUPPLY AND SERVICES | 2214 | 2021 | 2022-08-19 | 01/10/2022 | 0 | 600.29 | 2022-09-11 | 23
2024 | Region III | BULACAN | CITY OF MALOLOS (CAPITAL) (BULACAN) | P00843301LZ | Construction of Flood Mitigation Structure | 120.8119 | 14.8292 | 72374757.99 | 72374715.15 | 2024 | C & F CONSTRUCTION & DEVELOPMENT CORPORATION | 2215 | 2024 | 2024-11-27 | 04/02/2024 | 42.84 | 0 | 2024-11-26 |  | 1
2023 | Region III | PAMPANGA | SAN SIMON (PAMPANGA) | P00742342LZ | Construction of Flood Mitigation Structure | 120.7737 | 14.9942 | 22747230 | 21585947.35 | 2023 | V. TRILLANA BUILDERS & TRADING | 2216 | 2023 | 2023-08-31 | 04/04/2023 | 1161282.65 | 0 | 2023-08-30 |  | 1
2024 | Region III | BULACAN | PANDI (BULACAN) | P00838403LZ | Construction of Slope Protection Structure | 120.9176 | 14.8641 | 96499919.67 | 96499585.89 | 2024 | FLORDES CONSTRUCTION & TRADING CORP. (FORMERLY FLO | 2217 | 2024 | 2024-10-30 | 02/07/2024 | 333.78 | 0 | 2024-11-01 | 2
2023 | National Capital Region | MALABON CITY | CITY OF MALABON (METROPOLITAN MANILA) | P00726810LZ | Construction of Flood Mitigation Structure | 120.9366 | 14.6828 | 62719579.2 | 62725000 | 2024 | AZUL BUILDERS | 2218 | 2023 | 2024-02-14 | 03/22/2023 | 0 | 5420.8 | 2024-02-13 |  | 1
2022 | Region III | BULACAN | BOCAUE (BULACAN) | P00632817LZ | Construction of Revetment | 120.9269 | 14.8026 | 49499531.19 | 49499410.85 | 2022 | M.G. FRANCISCO CONSTRUCTION | 2219 | 2022 | 2022-09-24 | 01/28/2022 | 120.34 | 0 | 2022-09-23 |  | 1
2022 | Region III | NUEVA ECIJA | SAN LEONARDO (NUEVA ECIJA) | P00621577LZ | Construction of Flood Mitigation Structure | 120.9178 | 15.3143 | 72374957.23 | 63067150.72 | 2022 | FRAMECON BUILDERS | 2220 | 2022 | 2022-12-30 | 04/11/2022 | 9307806.51 | 0 | 2022-12-29 |  | 1
2024 | Region III | PAMPANGA | ARAYAT (PAMPANGA) | P00820280LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.7751 | 15.1696 | 96500000 | 93604758.63 | 2024 | ROYAL CROWN MONARCH CONSTRUCTION & SUPPLIES CORP. | 2221 | 2024 | 2024-11-05 | 03/01/2024 | 2895241.37 | 0 | 2024-11-04 |  | 1
2024 | National Capital Region | NAVOTAS CITY | CITY OF NAVOTAS (METROPOLITAN MANILA) | P00820523LZ | Construction of Flood Mitigation Facility | 120.9368 | 14.6742 | 48995077.58 | 48999201.71 | 2025 | ST. TIMOTHY CONSTRUCTION CORPORATION | 2222 | 2024 | 2025-03-17 | 02/12/2024 | 0 | 4124.13 | 2025-03-16 |  | 1
2023 | Region III | BULACAN | CITY OF BALIUAG (BULACAN) | P00726470LZ | Construction of Flood Mitigation Structure | 120.8841 | 14.9692 | 96499679.61 | 96499500.7 | 2023 | TRIPLE 8 CONSTRUCTION & SUPPLY, INC. (FORMERLY TRIPLE 8 CONST. & SUPPLY) | 2223 | 2023 | 2023-12-09 | 02/13/2023 | 178.91 | 0 | 2023-12-08 |  | 1
2023 | Region III | BULACAN | BOCAUE (BULACAN) | P00742328LZ | Construction of Flood Mitigation Structure | 120.927 | 14.7703 | 74249585.35 | 74249977.42 | 2023 | M.S. RAMOS CONSTRUCTION INC. (FORMERLY: M.S. RAMOS | 2224 | 2023 | 2023-11-08 | 03/27/2023 | 0 | 392.07 | 2024-01-19 | 72
2023 | Region IV-A | BATANGAS | LEMERY (BATANGAS) | P00726930LZ | Construction of Flood Mitigation Structure | 120.9178 | 13.8842 | 96500000 | 96500000 | 2024 | 515 LIFE CONSTRUCTION CORP. / V.R. PATRON BUILDERS & DEVELOPERS CORP. (PREVIOUSL | 2225 | 2023 | 2024-03-07 | 06/15/2023 | 0 | 0 | 2024-04-08 | 32
2021 | Region IV-B | OCCIDENTAL MINDORO |  | P00561807LZ | Construction of Flood Mitigation Structure | 120.7758 | 12.8452 | 29700000 | 29255752.25 | 2022 | JRMX CONSTRUCTION & GENERAL MERCHANDISE | 2226 | 2021 | 2022-11-30 | 03/25/2021 | 444247.75 | 0 | 2022-02-15 |  | 288
2024 | Region III | BULACAN | CITY OF MALOLOS (CAPITAL) (BULACAN) | P00838393LZ | Construction of Slope Protection Structure | 120.8119 | 14.8291 | 77199990.41 | 77197885.27 | 2024 | WAWAO BUILDERS | 2227 | 2024 | 2024-04-19 | 02/07/2024 | 2105.14 | 0 | 2024-10-02 | 166
2023 | Region III | BULACAN | PLARIDEL (BULACAN) | P00742327LZ | Construction of Flood Mitigation Structure | 120.8841 | 14.9001 | 73499946.25 | 74249103.11 | 2023 | DOUBLE 12 CONSTRUCTION & SUPPLY | 2228 | 2023 | 2023-12-21 | 03/27/2023 | 0 | 749156.86 | 2023-12-20 |  | 1
2021 | National Capital Region | MALABON CITY |  | P00525711LZ | Construction of Dike | 120.927 | 14.6915 | 34789759.78 | 34790000 | 2022 | TWO DIMENSION CONSTRUCTION | 2229 | 2021 | 2022-09-19 | 03/24/2022 | 0 | 240.22 | 2022-09-18 |  | 1
2023 | Region III | BULACAN | BALAGTAS (BIGAA) (BULACAN) | P00740350LZ | Construction of Flood Mitigation Structure | 120.9179 | 14.8611 | 72374293.86 | 72373876.28 | 2023 | STAR WILLIAM CONSTRUCTION | 2230 | 2023 | 2023-12-04 | 03/28/2023 | 417.58 | 0 | 2023-12-21 | 17
2023 | National Capital Region | MALABON CITY | CITY OF MALABON (METROPOLITAN MANILA) | P00726811LZ | Construction of Flood Mitigation Structure | 120.9372 | 14.6818 | 62717848.6 | 62725000 | 2024 | AZUL BUILDERS | 2231 | 2023 | 2024-02-14 | 03/22/2023 | 0 | 7151.4 | 2024-02-13 |  | 1
2022 | Region III | NUEVA ECIJA | ALIAGA (NUEVA ECIJA) | P00620531LZ | Construction of Flood Mitigation Structure | 120.8121 | 15.5136 | 45080000 | 45080000 | 2022 | R.D. TALENS CONSTRUCTION AND TRADING | 2232 | 2022 | 2022-08-22 | 02/24/2022 | 0 | 0 | 2022-08-21 |  | 1
2023 | Region IV-A | CAVITE | NOVELETA (CAVITE) | P00737501LZ | Construction of Drainage Structure | 120.8842 | 14.4217 | 4950000 | 4897964.42 | 2023 | TWO DEGREES CONSTRUCTION AND SUPPLY | 2233 | 2023 | 2023-05-19 | 02/19/2023 | 52035.58 | 0 | 2023-05-18 |  | 1
2022 | Region I | PANGASINAN | NATIVIDAD (PANGASINAN) | P00620977LZ | Construction of Revetment | 120.7764 | 16.0253 | 49000000 | 47532817.01 | 2022 | RIVBROS CONSTRUCTION FACTORS & DEVELOPMENT | 2234 | 2022 | 2022-09-03 | 02/24/2022 | 1467182.99 | 0 | 2022-09-02 |  | 1
2023 | Cordillera Administrative Region | MOUNTAIN PROVINCE | BONTOC (CAPITAL) (MOUNTAIN PROVINCE) | P00727402LZ | Construction of Flood Mitigation Structure | 120.9373 | 17.0528 | 39199999.6 | 39200000 | 2023 | CHAO-MING CONSTRUCTION SERVICES / E.T. LATAWAN CONSTRUCTION | 2235 | 2023 | 2023-09-27 | 02/27/2023 | 0 | 0.4 | 2023-09-26 |  | 1
2024 | Region IV-A | BATANGAS | CITY OF CALACA (BATANGAS) | P00820322LZ | Construction of Flood Mitigation Structure | 120.8122 | 13.9195 | 49117535 | 49117535 | 2024 | FRANDEL CONSTRUCTION AND DEVELOPMENT CORP. / V.R. PATRON BUILDERS & DEVELOPERS CORP. (PREVIOUSL | 2236 | 2024 | 2024-12-12 | 02/14/2024 | 0 | 0 | 2024-12-31 | 19
2024 | Region III | BULACAN | BOCAUE (BULACAN) | P00845811LZ | Construction of Slope Protection Structure | 120.9179 | 14.7657 | 98999770.49 | 98999012.87 | 2025 | TOPNOTCH CATALYST BUILDERS INC. / ONE FRAME CONSTRUCTION INC. | 2237 | 2024 | 2025-01-17 | 04/23/2024 | 757.62 | 0 | 2025-01-16 |  | 1
2023 | Region I | ILOCOS NORTE | VINTAR (ILOCOS NORTE) | P00726353LZ | Construction of Flood Mitigation Structure | 120.777 | 18.396 | 78399767.14 | 77199999.99 | 2023 | KATHA BUILDERS & SUPPLIES INC. | 2238 | 2023 | 2023-10-12 | 03/13/2023 | 1199767.15 | 0 | 2024-01-14 | 94
2021 | Cordillera Administrative Region | BENGUET |  | P00525910LZ | Construction of Flood Mitigation Structure | 120.8123 | 16.8368 | 9800000 | 9505756.45 | 2022 | TIMENCLEAN BUILDERS AND AGGREGATES | 2239 | 2021 | 2022-12-08 | 01/16/2022 | 294243.55 | 0 | 2022-10-07 |  | 62
2024 | National Capital Region | NAVOTAS CITY | CITY OF NAVOTAS (METROPOLITAN MANILA) | P00820528LZ | Construction of Drainage Structure | 120.9373 | 14.67 | 6859359.22 | 6858007.76 | 2024 | EARTHWORK BUILDERS, INC. (FORMERLY: EARTHWORK MOVERS) | 2240 | 2024 | 2024-06-10 | 02/12/2024 | 1351.46 | 0 | 2024-06-09 |  | 1
2023 | Region III | BULACAN | BOCAUE (BULACAN) | P00737457LZ | Construction of Flood Mitigation Structure | 120.9271 | 14.7983 | 19799705.53 | 19798050.14 | 2023 | TIONGCO MENDOZA CONSTRUCTION CO. INC. | 2241 | 2023 | 2023-05-17 | 02/06/2023 | 1655.39 | 0 | 2023-08-03 | 78
2023 | Region III | BULACAN | GUIGUINTO (BULACAN) | P00737460LZ | Construction of Flood Mitigation Structure | 120.8843 | 14.8538 | 19799614.68 | 19799558.46 | 2023 | D.C. SANDIL CONSTRUCTION AND REALTY DEVELOPMENT, I | 2242 | 2023 | 2023-08-04 | 02/06/2023 | 56.22 | 0 | 2023-08-03 |  | 1
2024 | Region III | TARLAC | CONCEPCION (TARLAC) | P00821308LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.7771 | 15.2813 | 96499377.51 | 96497131.99 | 2024 | RAIK CONSTRUCTION AND DEVELOPMENT CORPORATION (FORMERLY: RAIK CONSTRUCTION AND SUPPLY) | 2243 | 2024 | 2024-10-10 | 02/20/2024 | 2245.52 | 0 | 2024-10-09 |  | 1
2023 | Region III | BULACAN | SAN RAFAEL (BULACAN) | P00744261LZ | Construction of Flood Mitigation Structure | 120.9374 | 15.0398 | 9899955.33 | 9899493.31 | 2024 | EIRISH BUILDERS & SUPPLY INC. | 2244 | 2023 | 2024-03-22 | 11/24/2023 | 462.02 | 0 | 2024-03-21 |  | 1
2023 | Region III | BULACAN | BALAGTAS (BIGAA) (BULACAN) | P00740588LZ | Construction of Flood Mitigation Structure | 120.918 | 14.8629 | 48999952.69 | 48999814.12 | 2023 | 11-16 CONSTRUCTION | 2245 | 2023 | 2023-12-04 | 03/21/2023 | 138.57 | 0 | 2024-01-13 | 40
2023 | Region III | BULACAN | BOCAUE (BULACAN) | P00742321LZ | Construction of Drainage Structure | 120.9271 | 14.7956 | 4949581.45 | 4944925.2 | 2023 | LARSEN-DUTCHER CONSTRACTOR CORPORATION (FORMERLY:LARSEN-DUTCHER CONSTRACTOR) | 2246 | 2023 | 2023-07-14 | 03/27/2023 | 4656.25 | 0 | 2023-07-23 | 9
2022 | Region III | NUEVA ECIJA | QUEZON (NUEVA ECIJA) | P00632834LZ | Construction of Flood Mitigation Structure | 120.8126 | 15.5548 | 9800000 | 9800000 | 2022 | R.A. PAHATI CONST. & SUPPLY, INC. | 2247 | 2022 | 2022-12-18 | 02/22/2022 | 0 | 0 | 2022-12-17 |  | 1
2023 | Region III | BULACAN | CITY OF BALIUAG (BULACAN) | P00740334LZ | Construction of Flood Mitigation Structure | 120.8843 | 14.9768 | 72374734.39 | 71915112.64 | 2023 | L.R. TIQUI BUILDERS, INC. | 2248 | 2023 | 2023-12-06 | 03/28/2023 | 459621.75 | 0 | 2023-12-21 | 15
2024 | Region III | NUEVA ECIJA | CITY OF GAPAN (NUEVA ECIJA) | P00825088LZ | Construction of Flood Mitigation Structure | 120.9375 | 15.3058 | 96499940.57 | 96499860.47 | 2024 | DGSARM BUILDERS INC. (FORMERLY: D.G. SARMENTA CONSTRUCTION) | 2249 | 2024 | 2024-06-18 | 04/02/2024 | 80.1 | 0 | 2025-01-19 | 215
2023 | Region III | BULACAN | PAOMBONG (BULACAN) | P00740371LZ | Construction of Flood Mitigation Structure | 120.7774 | 14.8294 | 77199910.16 | 77194184.92 | 2023 | WAWAO BUILDERS | 2250 | 2023 | 2023-08-09 | 03/28/2023 | 5725.24 | 0 | 2024-01-20 | 164
2023 | Region IV-A | CAVITE | TANZA (CAVITE) | P00726215LZ | Construction of Revetment | 120.8844 | 14.3214 | 49000000 | 49000000 | 2023 | N.B. AVILA CONSTRUCTION | 2251 | 2023 | 2023-11-30 | 03/06/2023 | 0 | 0 | 2023-11-29 |  | 1
2022 | Region III | NUEVA ECIJA | SAN LEONARDO (NUEVA ECIJA) | P00621416LZ | Construction of Flood Mitigation Structure | 120.918 | 15.3797 | 72374991.52 | 63054123.04 | 2023 | FRAMECON BUILDERS | 2252 | 2022 | 2023-02-28 | 04/11/2022 | 9320868.48 | 0 | 2023-02-27 |  | 1
2024 | National Capital Region | MALABON CITY | CITY OF MALABON (METROPOLITAN MANILA) | P00820542LZ | Construction of Flood Mitigation Structure | 120.9272 | 14.7009 | 48999376.86 | 48998274.82 | 2024 | ROTAFLEX CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY:ROTA FLEX CONSTRUCTION) | 2253 | 2024 | 2024-10-08 | 02/12/2024 | 1102.04 | 0 | 2024-10-07 |  | 1
2022 | Region IV-A | BATANGAS | CITY OF CALACA (BATANGAS) | P00642359LZ | Rehabilitation / Major Repair of Slope Protection Structure | 120.8133 | 13.927 | 49000000 | 49000000 | 2022 | X.Y.Z. CONSTRUCTION & SUPPLIES / V.R. PATRON BUILDERS & DEVELOPERS CORP. (PREVIOUSL | 2254 | 2022 | 2022-11-22 | 03/28/2022 | 0 | 0 | 2022-11-21 |  | 1
2023 | National Capital Region | NAVOTAS CITY | CITY OF NAVOTAS (METROPOLITAN MANILA) | P00742224LZ | Construction of Flood Mitigation Structure | 120.9375 | 14.6701 | 17819774.75 | 17819581.35 | 2023 | EARTHWORK BUILDERS, INC. (FORMERLY: EARTHWORK MOVERS) | 2255 | 2023 | 2023-11-24 | 03/27/2023 | 193.4 | 0 | 2023-12-20 | 26
2024 | National Capital Region | NAVOTAS CITY | CITY OF NAVOTAS (METROPOLITAN MANILA) | P00820553LZ | Construction of Revetment | 120.9375 | 14.674 | 48993207.97 | 49000000 | 2024 | TOPNOTCH CATALYST BUILDERS INC. | 2256 | 2024 | 2024-09-11 | 02/12/2024 | 0 | 6792.03 | 2024-10-07 | 26
2023 | Region III | BULACAN | CITY OF BALIUAG (BULACAN) | P00726467LZ | Construction of Flood Mitigation Structure | 120.8846 | 14.9844 | 96499679.61 | 96498956.85 | 2023 | L.R. TIQUI BUILDERS, INC. | 2257 | 2023 | 2023-11-10 | 02/13/2023 | 722.76 | 0 | 2023-12-08 | 28
2023 | Region IV-A | BATANGAS | SAN LUIS (BATANGAS) | P00740397LZ | Construction of Flood Mitigation Structure | 120.9181 | 13.8372 | 22540000 | 22195000 | 2023 | VICMAR CONSTRUCTION, INC. | 2258 | 2023 | 2023-12-13 | 04/03/2023 | 345000 | 0 | 2023-12-12 |  | 1
2021 | Region I | ILOCOS NORTE |  | P00526253LZ | Construction of Flood Mitigation Structure | 120.7789 | 18.5434 | 81059850.65 | 81059849.91 | 2022 | BLUE MOUNTAIN BUILDERS & GENERAL MDSE.(FOR. BLUE M | 2259 | 2021 | 2022-07-15 | 12/24/2021 | 0.74 | 0 | 2022-09-03 | 50
2023 | Region III | BULACAN | OBANDO (BULACAN) | P00727361LZ | Rehabilitation / Major Repair of Flood Mitigation Facility | 120.9376 | 14.7074 | 14699743.82 | 14479247.66 | 2023 | JB CONSTRUCTION AND SUPPLY INC. (FORMERLY:JB CONSTRUCTION AND SUPPLY) | 2260 | 2023 | 2023-04-30 | 03/13/2023 | 220496.16 | 0 | 2023-07-31 | 92
2022 | Region I | PANGASINAN | BALUNGAO (PANGASINAN) | P00637051LZ | Construction of Dike | 120.8136 | 15.8917 | 24500000 | 24474875.68 | 2022 | RS RODRIGUEZ CONSTRUCTION & SUPPLIES | 2261 | 2022 | 2022-10-10 | 04/07/2022 | 25124.32 | 0 | 2022-09-24 |  | 16
2023 | Region IV-A | CAVITE | BACOOR CITY (CAVITE) | P00726556LZ | Construction of Revetment | 120.9273 | 14.4583 | 96499968.82 | 96479788.33 | 2024 | GRAIA CONSTRUCTION CORPORATION | 2262 | 2023 | 2024-01-31 | 03/08/2023 | 20180.49 | 0 | 2024-01-30 |  | 1
2024 | Region III | NUEVA ECIJA | ZARAGOZA (NUEVA ECIJA) | P00823426LZ | Construction of Flood Mitigation Structure | 120.7794 | 15.4855 | 96500000 | 95534900.78 | 2024 | M.M. SERRANO CONSTRUCTION COMPANY | 2263 | 2024 | 2024-11-25 | 03/01/2024 | 965099.22 | 0 | 2024-11-24 |  | 1
2024 | Region III | BULACAN | CITY OF MALOLOS (CAPITAL) (BULACAN) | P00838413LZ | Construction of Slope Protection Structure | 120.8138 | 14.8449 | 77199993.42 | 77199461.62 | 2024 | DARCY & ANNA BUILDERS & TRADING | 2264 | 2024 | 2024-07-04 | 02/07/2024 | 531.8 | 0 | 2024-10-02 | 90
2022 | Region III | BULACAN | SAN MIGUEL (BULACAN) | P00621536LZ | Construction of Flood Mitigation Structure | 120.9378 | 15.1693 | 48999830.95 | 48995909.06 | 2022 | LEGACY CONSTRUCTION CORPORATION (FORMERLY: LEGACY CONSTRUCTION) | 2265 | 2022 | 2022-10-15 | 03/30/2022 | 3921.89 | 0 | 2022-10-14 |  | 1
2024 | Region III | BULACAN | CITY OF BALIUAG (BULACAN) | P00838412LZ | Construction of Slope Protection Structure | 120.8846 | 14.9987 | 96499961.09 | 96499378.64 | 2024 | M3 KONSTRACT CORPORATION (FORMERLY:MARGARITA CONSTRUCTION) | 2266 | 2024 | 2024-11-02 | 02/07/2024 | 582.45 | 0 | 2024-11-01 |  | 1
2021 | Region III | BULACAN |  | P00526004LZ | Construction of Flood Mitigation Structure | 120.9275 | 14.771 | 19599708.96 | 19599996.35 | 2022 | GENUINE BUILDERS | 2267 | 2021 | 2022-09-10 | 01/14/2022 | 0 | 287.39 | 2022-09-09 |  | 1
2022 | National Capital Region | NAVOTAS CITY | CITY OF NAVOTAS (METROPOLITAN MANILA) | P00620338LZ | Construction of Drainage Structure | 120.9378 | 14.6721 | 24499998.6 | 24499335.42 | 2023 | CATTECORYLL CONSTRUCTION & TRADING CORP | 2268 | 2022 | 2023-01-23 | 02/14/2022 | 663.18 | 0 | 2023-01-27 | 4
2024 | Region III | PAMPANGA | ARAYAT (PAMPANGA) | P00820279LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.8147 | 15.1484 | 96500000 | 91841987.52 | 2024 | EDDMARI CONSTRUCTION & TRADING | 2269 | 2024 | 2024-11-05 | 03/01/2024 | 4658012.48 | 0 | 2024-11-04 |  | 1
2024 | Region III | NUEVA ECIJA | TALAVERA (NUEVA ECIJA) | P00824703LZ | Construction of Flood Mitigation Structure | 120.9181 | 15.5976 | 20090000 | 19889072.16 | 2024 | IJK MAE CONSTRUCTION INC. | 2270 | 2024 | 2024-10-01 | 04/24/2024 | 200927.84 | 0 | 2024-10-19 | 18
2022 | Region III | BULACAN | BOCAUE (BULACAN) | P00631216LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.9276 | 14.7946 | 45079581.87 | 45079631.44 | 2022 | TOPNOTCH CATALYST BUILDERS INC. / BLACK HARDHAT INC. (FORMERLY: JCHARDHAT INC.) | 2271 | 2022 | 2022-11-21 | 02/04/2022 | 0 | 49.57 | 2022-11-29 | 8
2024 | Region III | BULACAN | CITY OF BALIUAG (BULACAN) | P00839478LZ | Construction of Slope Protection Structure | 120.8852 | 14.9842 | 98999953.38 | 98999764.29 | 2024 | IM CONSTRUCTION CORPORATION | 2272 | 2024 | 2024-11-02 | 02/07/2024 | 189.09 | 0 | 2024-11-01 |  | 1
2024 | Region III | TARLAC | CONCEPCION (TARLAC) | P00825241LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.7795 | 15.2839 | 46750609.99 | 46750558.17 | 2024 | A.C. SOLIVEN CONSTRUCTION & GENERAL MERCHANDISE | 2273 | 2024 | 2024-06-30 | 02/05/2024 | 51.82 | 0 | 2024-06-29 |  | 1
2023 | Region III | BULACAN | OBANDO (BULACAN) | P00727296LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.9183 | 14.7436 | 48998853.56 | 48249000 | 2023 | G.F. FABIAN CONSTRUCTION | 2274 | 2023 | 2023-09-17 | 03/30/2023 | 749853.56 | 0 | 2023-09-16 |  | 1
2022 | Region III | BULACAN | BOCAUE (BULACAN) | P00631217LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.9276 | 14.795 | 45079581.87 | 45079631.44 | 2022 | TOPNOTCH CATALYST BUILDERS INC. / BLACK HARDHAT INC. (FORMERLY: JCHARDHAT INC.) | 2275 | 2022 | 2022-11-21 | 02/04/2022 | 0 | 49.57 | 2022-11-29 | 8
2023 | Region III | BULACAN | CITY OF BALIUAG (BULACAN) | P00740335LZ | Construction of Flood Mitigation Structure | 120.8852 | 14.972 | 72374797.38 | 72374738.66 | 2023 | ALPHA & OMEGA GEN. CONTRACTOR & DEVELOPMENT CORP. | 2276 | 2023 | 2023-10-13 | 03/28/2023 | 58.72 | 0 | 2023-12-21 | 69
2023 | Region III | BULACAN | CITY OF MALOLOS (CAPITAL) (BULACAN) | P00742150LZ | Construction of Flood Mitigation Structure | 120.8147 | 14.8424 | 69299766.06 | 69223394.29 | 2024 | JTC CRUZ CONSTRUCTION CO., INC. | 2277 | 2023 | 2024-01-21 | 03/28/2023 | 76371.77 | 0 | 2024-01-20 |  | 1
2024 | Region III | BULACAN | CALUMPIT (BULACAN) | P00838410LZ | Construction of Slope Protection Structure | 120.9183 | 14.9183 | 77199983.77 | 77197298.97 | 2024 | WAWAO BUILDERS | 2278 | 2024 | 2024-04-19 | 02/07/2024 | 2684.8 | 0 | 2024-10-02 | 166
2022 | National Capital Region | MALABON CITY | CITY OF MALABON (METROPOLITAN MANILA) | P00632705LZ | Construction of Flood Mitigation Structure | 120.9277 | 14.7015 | 48999208.88 | 49500000 | 2023 | JAGONBUILD CONSTRUCTION CORP. (FOR. JAGON BUILDERS | 2279 | 2022 | 2023-01-27 | 02/15/2022 | 0 | 500791.12 | 2023-01-26 |  | 1
2022 | Region III | BULACAN | CITY OF BALIUAG (BULACAN) | P00621278LZ | Construction of Flood Mitigation Structure | 120.9184 | 14.9623 | 67549860.4 | 65273430.18 | 2023 | DMLC BUILDERS | 2280 | 2022 | 2023-01-28 | 04/04/2022 | 2276430.22 | 0 | 2023-01-27 |  | 1
2023 | Region IV-A | CAVITE | BACOOR CITY (CAVITE) | P00742184LZ | Construction of Flood Mitigation Structure | 120.9381 | 14.4546 | 98999944.05 | 98980509.66 | 2024 | GRAIA CONSTRUCTION CORPORATION | 2281 | 2023 | 2024-05-23 | 06/29/2023 | 19434.39 | 0 | 2024-05-22 |  | 1
2024 | Region III | PAMPANGA | CANDABA (PAMPANGA) | P00820283LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.8147 | 15.0921 | 96500000 | 91096456.9 | 2024 | STO. CRISTO CONSTRUCTION & TRADING INC. (FOR: STO. CRISTO CONSTRUCTION & TRADING) | 2282 | 2024 | 2024-11-06 | 03/04/2024 | 5403543.1 | 0 | 2024-11-05 |  | 1
2022 | Region IV-A | CAVITE | BACOOR CITY (CAVITE) | P00620882LZ | Construction of Revetment | 120.9278 | 14.4537 | 57899993.17 | 57895300.07 | 2022 | GRAIA CONSTRUCTION CORPORATION | 2283 | 2022 | 2022-11-18 | 03/22/2022 | 4693.1 | 0 | 2023-01-23 | 66
2023 | Region III | BULACAN | PAOMBONG (BULACAN) | P00740592LZ | Construction of Flood Mitigation Structure | 120.78 | 14.8357 | 48999799.84 | 48999661.43 | 2023 | GREAT PACIFIC BUILDERS AND GEN. CONTRACTOR INC. | 2284 | 2023 | 2023-11-15 | 03/21/2023 | 138.41 | 0 | 2023-11-14 |  | 1
2022 | Region IV-A | CAVITE | CITY OF GENERAL TRIAS (CAVITE) | P00644739LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.8859 | 14.3997 | 9650000 | 9650000 | 2023 | TRIPLE 8 CONSTRUCTION & SUPPLY, INC. (FORMERLY TRIPLE 8 CONST. & SUPPLY) | 2285 | 2022 | 2023-03-15 | 01/09/2023 | 0 | 0 | 2023-04-06 | 22
2022 | Cordillera Administrative Region | BENGUET | KABAYAN (BENGUET) | P00639441LZ | Construction of Flood Mitigation Structure | 120.7808 | 16.6052 | 2940000 | 2919512.6 | 2022 | QPJ GENERAL ENGINEERING CONSTRUCTION AND SUPPLY | 2286 | 2022 | 2022-12-20 | 08/16/2022 | 20487.4 | 0 | 2022-12-09 |  | 11
2023 | Region III | BULACAN | BALAGTAS (BIGAA) (BULACAN) | P00740351LZ | Construction of Flood Mitigation Structure | 120.9185 | 14.8599 | 72374293.86 | 72373012.16 | 2023 | STAR WILLIAM CONSTRUCTION | 2287 | 2023 | 2023-12-04 | 03/28/2023 | 1281.7 | 0 | 2023-12-21 | 17
2023 | Region I | ILOCOS NORTE | BANGUI (ILOCOS NORTE) | P00727045LZ | Construction of Flood Mitigation Structure | 120.7808 | 18.535 | 19599752.22 | 18815685.07 | 2023 | ST. MATTHEW GEN. CONTRACTOR & DEVELOPMENT CORP. / HERCULES VENTURES INC. | 2288 | 2023 | 2023-07-24 | 05/18/2023 | 784067.15 | 0 | 2023-11-04 | 103
2023 | Region III | BULACAN | BOCAUE (BULACAN) | P00726921LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.9278 | 14.7732 | 77681873.8 | 77682498.59 | 2023 | L.R. TIQUI BUILDERS, INC. | 2289 | 2023 | 2023-11-28 | 03/14/2023 | 0 | 624.79 | 2023-12-07 | 9
2024 | Region IV-B | OCCIDENTAL MINDORO | SABLAYAN (OCCIDENTAL MINDORO) | P00825118LZ | Construction of Flood Mitigation Structure | 120.8152 | 12.7468 | 289500000 | 289496842.1 | 2024 | GREAT PACIFIC BUILDERS AND GEN. CONTRACTOR INC. | 2290 | 2024 | 2024-07-22 | 03/09/2024 | 3157.9 | 0 | 2025-03-02 | 223
2023 | Region III | BULACAN | OBANDO (BULACAN) | P00727365LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.9185 | 14.7427 | 46058879 | 46058208.67 | 2023 | JB CONSTRUCTION AND SUPPLY INC. (FORMERLY:JB CONSTRUCTION AND SUPPLY) | 2291 | 2023 | 2023-08-28 | 03/13/2023 | 670.33 | 0 | 2023-08-27 |  | 1
2023 | National Capital Region | MALABON CITY | CITY OF MALABON (METROPOLITAN MANILA) | P00726812LZ | Construction of Flood Mitigation Structure | 120.9381 | 14.6809 | 62719315.3 | 62725000 | 2024 | DMLC BUILDERS | 2292 | 2023 | 2024-03-25 | 03/22/2023 | 0 | 5684.7 | 2024-03-24 |  | 1
2023 | Region III | BULACAN | OBANDO (BULACAN) | P00727362LZ | Construction of Flood Mitigation Structure | 120.9185 | 14.7427 | 48999465.41 | 48262023.44 | 2023 | JB CONSTRUCTION AND SUPPLY INC. (FORMERLY:JB CONSTRUCTION AND SUPPLY) | 2293 | 2023 | 2023-10-08 | 04/05/2023 | 737441.97 | 0 | 2023-10-07 |  | 1
2022 | Region III | BULACAN | GUIGUINTO (BULACAN) | P00631181LZ | Construction of Flood Mitigation Structure | 120.886 | 14.8556 | 45079492.61 | 45079811 | 2022 | STAR WILLIAM CONSTRUCTION | 2294 | 2022 | 2022-10-30 | 04/04/2022 | 0 | 318.39 | 2022-10-29 |  | 1
2024 | Region III | PAMPANGA | APALIT (PAMPANGA) | P00821317LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.781 | 14.9767 | 96500000 | 93604874.52 | 2024 | 11-16 CONSTRUCTION | 2295 | 2024 | 2024-11-03 | 03/01/2024 | 2895125.48 | 0 | 2024-11-02 |  | 1
2023 | Region IV-A | BATANGAS | SAN LUIS (BATANGAS) | P00740399LZ | Construction of Flood Mitigation Structure | 120.9186 | 13.8531 | 22540000 | 22195000 | 2023 | OIC CONZTRUCT AND SUPPLY CORPORATION(FORMERLY:OIC CONST.) | 2296 | 2023 | 2023-08-18 | 04/03/2023 | 345000 | 0 | 2023-08-17 |  | 1
2023 | Region III | BULACAN | CITY OF BALIUAG (BULACAN) | P00737452LZ | Construction of Drainage Structure | 120.8861 | 14.9193 | 4949834.42 | 4949902.4 | 2023 | DOUBLE Z CONSTRUCTION AND SUPPLY | 2297 | 2023 | 2023-05-19 | 02/06/2023 | 0 | 67.98 | 2023-06-04 | 16
2022 | Region IV-A | CAVITE | BACOOR CITY (CAVITE) | P00640463LZ | Construction of Revetment | 120.9382 | 14.4564 | 98999994.6 | 98999931.03 | 2023 | GRAIA CONSTRUCTION CORPORATION | 2298 | 2022 | 2023-04-01 | 04/07/2022 | 63.57 | 0 | 2023-03-31 |  | 1
2023 | Region IV-A | CAVITE | BACOOR CITY (CAVITE) | P00726557LZ | Construction of Revetment | 120.9279 | 14.4477 | 96499989.44 | 96476338.22 | 2024 | GRAIA CONSTRUCTION CORPORATION | 2299 | 2023 | 2024-03-31 | 03/08/2023 | 23651.22 | 0 | 2024-03-30 |  | 1
2022 | Region IV-A | CAVITE | BACOOR CITY (CAVITE) | P00640462LZ | Construction of Revetment | 120.9382 | 14.4545 | 98999994.73 | 98999980.77 | 2023 | GRAIA CONSTRUCTION CORPORATION | 2300 | 2022 | 2023-04-01 | 04/07/2022 | 13.96 | 0 | 2023-03-31 |  | 1
2022 | Region IV-A | BATANGAS | CITY OF CALACA (BATANGAS) | P00632861LZ | Construction of Flood Mitigation Structure | 120.8154 | 13.9707 | 4950000 | 4950000 | 2022 | JOMZKI CONSTRUCTION AND SUPPLY | 2301 | 2022 | 2022-08-03 | 03/21/2022 | 0 | 0 | 2022-08-02 |  | 1
2023 | Region III | BULACAN | CITY OF BALIUAG (BULACAN) | P00726463LZ | Construction of Flood Mitigation Structure | 120.8864 | 14.9672 | 96499679.61 | 96499709.18 | 2023 | L.R. TIQUI BUILDERS, INC. | 2302 | 2023 | 2023-12-06 | 02/13/2023 | 0 | 29.57 | 2023-12-08 | 2
2024 | Region III | BULACAN | BALAGTAS (BIGAA) (BULACAN) | P00823405LZ | Construction of Flood Mitigation Structure | 120.9186 | 14.86 | 77199663.46 | 77198851.79 | 2024 | JB CONSTRUCTION AND SUPPLY INC. (FORMERLY:JB CONSTRUCTION AND SUPPLY) | 2303 | 2024 | 2024-06-19 | 02/28/2024 | 811.67 | 0 | 2024-10-23 | 126
2022 | National Capital Region | NAVOTAS CITY | CITY OF NAVOTAS (METROPOLITAN MANILA) | P00620018LZ | Construction of Flood Mitigation Structure | 120.9382 | 14.6705 | 51939997.47 | 51138435.86 | 2022 | IM CONSTRUCTION CORPORATION | 2304 | 2022 | 2022-12-08 | 02/14/2022 | 801561.61 | 0 | 2022-12-09 | 1
2023 | Region III | PAMPANGA | ARAYAT (PAMPANGA) | P00726512LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.8155 | 15.1478 | 96500000 | 91626654.28 | 2023 | EDDMARI CONSTRUCTION & TRADING | 2305 | 2023 | 2023-10-17 | 02/20/2023 | 4873345.72 | 0 | 2023-10-16 |  | 1
2023 | Region IV-A | CAVITE | CITY OF GENERAL TRIAS (CAVITE) | P00744299LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.8864 | 14.3992 | 18128490 | 18128490 | 2023 | F316 CONSTRUCTION CORP. | 2306 | 2023 | 2023-08-11 | 03/15/2023 | 0 | 0 | 2023-08-10 |  | 1
2023 | Region I | ILOCOS NORTE | PAGUDPUD (ILOCOS NORTE) | P00740518LZ | Construction of Flood Mitigation Structure | 120.781 | 18.5573 | 19599927.59 | 19599921.21 | 2023 | ZEDIK BUILDERS | 2307 | 2023 | 2023-10-23 | 04/25/2023 | 6.38 | 0 | 2023-11-10 | 18
2022 | Region III | BULACAN | CITY OF MEYCAUAYAN (BULACAN) | P00639346LZ | Construction of Flood Mitigation Structure | 120.928 | 14.7367 | 96499091.88 | 96498187.66 | 2023 | L.R. TIQUI BUILDERS, INC. | 2308 | 2022 | 2023-07-14 | 06/09/2022 | 904.22 | 0 | 2023-07-13 |  | 1
2024 | Region III | BULACAN | OBANDO (BULACAN) | P00825082LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.9187 | 14.7416 | 96499640.32 | 96499808.15 | 2025 | G.F. FABIAN CONSTRUCTION / F316 CONSTRUCTION CORP. | 2309 | 2024 | 2025-03-01 | 04/25/2024 | 0 | 167.83 | 2025-02-28 |  | 1
2024 | Region III | BULACAN | GUIGUINTO (BULACAN) | P00838414LZ | Construction of Slope Protection Structure | 120.8157 | 14.8449 | 96499932.03 | 96499302.69 | 2024 | WAWAO BUILDERS | 2310 | 2024 | 2024-06-19 | 02/07/2024 | 629.34 | 0 | 2024-11-01 | 135
2023 | Region III | PAMPANGA | ARAYAT (PAMPANGA) | P00726173LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.781 | 15.1409 | 26460000 | 25123741.7 | 2024 | N.T. TULABUT CONSTRUCTION AND SUPPLY | 2311 | 2023 | 2024-07-02 | 05/31/2023 | 1336258.3 | 0 | 2024-07-01 |  | 1
2024 | Region III | BULACAN | CITY OF BALIUAG (BULACAN) | P00843311LZ | Construction of Flood Mitigation Structure | 120.8864 | 14.9722 | 77199974.8 | 77199953.41 | 2024 | PRECIOUS CONSTRUCTION | 2312 | 2024 | 2024-08-09 | 02/28/2024 | 21.39 | 0 | 2024-10-23 | 75
2024 | Region III | PAMPANGA | ARAYAT (PAMPANGA) | P00823486LZ | Construction of Slope Protection Structure | 120.781 | 15.1409 | 96500000 | 91578481.02 | 2025 | EDDMARI CONSTRUCTION & TRADING | 2313 | 2024 | 2025-01-19 | 05/22/2024 | 4921518.98 | 0 | 2025-01-18 |  | 1
2024 | Region III | BULACAN | BOCAUE (BULACAN) | P00845810LZ | Construction of Slope Protection Structure | 120.919 | 14.7649 | 98999334.23 | 98999038.56 | 2025 | TOPNOTCH CATALYST BUILDERS INC. / ONE FRAME CONSTRUCTION INC. | 2314 | 2024 | 2025-01-17 | 04/23/2024 | 295.67 | 0 | 2025-01-16 |  | 1
2022 | National Capital Region | NAVOTAS CITY | CITY OF NAVOTAS (METROPOLITAN MANILA) | P00631013LZ | Construction of Flood Mitigation Facility | 120.9383 | 14.6657 | 19599707.05 | 19599571.94 | 2022 | AYANA CONSTRUCTION AND TRADING | 2315 | 2022 | 2022-12-26 | 02/14/2022 | 135.11 | 0 | 2022-12-25 |  | 1
2024 | Region III | BULACAN | CITY OF MALOLOS (CAPITAL) (BULACAN) | P00845797LZ | Construction of Slope Protection Structure | 120.8158 | 14.8429 | 98999733.77 | 98999728.26 | 2024 | TOPNOTCH CATALYST BUILDERS INC. / ONE FRAME CONSTRUCTION INC. | 2316 | 2024 | 2024-12-06 | 05/21/2024 | 5.51 | 0 | 2025-02-13 | 69
2024 | Region III | BULACAN | CITY OF MEYCAUAYAN (BULACAN) | P00820204LZ | Construction of Flood Mitigation Structure | 120.9281 | 14.7377 | 67549676.95 | 67535330.1 | 2024 | AZUL BUILDERS | 2317 | 2024 | 2024-11-02 | 02/14/2024 | 14346.85 | 0 | 2024-11-01 |  | 1
2024 | Region III | BULACAN | OBANDO (BULACAN) | P00825083LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.9197 | 14.7397 | 96499402.61 | 96499858.85 | 2025 | 729 CONSTRUCTION, INC. (FORMERLY 722 CONSTRUCTION, INC.) | 2318 | 2024 | 2025-01-11 | 06/05/2024 | 0 | 456.24 | 2025-01-10 |  | 1
2023 | Region IV-A | BATANGAS | SAN NICOLAS (BATANGAS) | P00725766LZ | Construction of Flood Mitigation Structure | 120.9384 | 13.9221 | 96500000 | 96499113 | 2024 | LOUREL DEVELOPMENT CORPORATION (FORMERLY :LOUREL D / THREE W BUILDERS, INC. | 2319 | 2023 | 2024-05-30 | 03/07/2023 | 887 | 0 | 2024-05-29 |  | 1
2024 | Region III | BULACAN | GUIGUINTO (BULACAN) | P00838383LZ | Construction of Slope Protection Structure | 120.8869 | 14.8566 | 96499956.74 | 96499234.24 | 2024 | M.S. RAMOS CONSTRUCTION INC. (FORMERLY: M.S. RAMOS | 2320 | 2024 | 2024-09-19 | 02/07/2024 | 722.5 | 0 | 2024-11-01 | 43
2023 | Region III | BULACAN | CALUMPIT (BULACAN) | P00740583LZ | Construction of Flood Mitigation Structure | 120.7811 | 14.9031 | 48999769.65 | 48999754.81 | 2023 | FERDSTAR BUILDERS INC. | 2321 | 2023 | 2023-08-09 | 03/21/2023 | 14.84 | 0 | 2023-11-14 | 97
2024 | Region III | PAMPANGA | ARAYAT (PAMPANGA) | P00823463LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.816 | 15.1469 | 96500000 | 91485522.95 | 2024 | EDDMARI CONSTRUCTION & TRADING | 2322 | 2024 | 2024-11-04 | 03/04/2024 | 5014477.05 | 0 | 2024-11-03 |  | 1
2024 | National Capital Region | MALABON CITY | CITY OF MALABON (METROPOLITAN MANILA) | P00820541LZ | Construction of Revetment | 120.9281 | 14.7017 | 48996824.5 | 48999924.88 | 2024 | ROTAFLEX CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY:ROTA FLEX CONSTRUCTION) | 2323 | 2024 | 2024-10-21 | 02/12/2024 | 0 | 3100.38 | 2024-11-06 | 16
2022 | Region III | BULACAN | SAN MIGUEL (BULACAN) | P00632698LZ | Construction of Flood Mitigation Structure | 120.9385 | 15.1701 | 98999673.82 | 98996230.29 | 2023 | IM CONSTRUCTION CORPORATION | 2324 | 2022 | 2023-02-16 | 03/30/2022 | 3443.53 | 0 | 2023-03-07 | 19
2023 | Region III | BULACAN | CITY OF BALIUAG (BULACAN) | P00736009LZ | Construction of Slope Protection Structure | 120.8869 | 14.9684 | 38599553.69 | 38599392.15 | 2023 | DMLC BUILDERS | 2325 | 2023 | 2023-09-21 | 02/13/2023 | 161.54 | 0 | 2023-10-09 | 18
2022 | Region III | BULACAN | CITY OF BALIUAG (BULACAN) | P00640515LZ | Construction of Flood Mitigation Structure | 120.8961 | 14.9454 | 48999274.47 | 48999991.09 | 2023 | L.R. TIQUI BUILDERS, INC. | 2326 | 2022 | 2023-03-30 | 04/05/2022 | 0 | 716.62 | 2023-03-29 |  | 1
2023 | Region III | PAMPANGA | CANDABA (PAMPANGA) | P00726915LZ | Construction of Slope Protection Structure | 120.8963 | 15.0414 | 72375000 | 68394362.92 | 2024 | STO. CRISTO CONSTRUCTION & TRADING INC. (FOR: STO. CRISTO CONSTRUCTION & TRADING) | 2327 | 2023 | 2024-01-19 | 04/14/2023 | 3980637.08 | 0 | 2024-01-18 |  | 1
2022 | Cordillera Administrative Region | BENGUET | KABAYAN (BENGUET) | P00639450LZ | Construction of Flood Mitigation Structure | 120.8161 | 16.6406 | 2940000 | 2937836 | 2022 | CHRISHUA CONSTRUCTION SERVICES | 2328 | 2022 | 2022-11-11 | 09/19/2022 | 2164 | 0 | 2022-11-10 |  | 1
2024 | Region III | BULACAN | CITY OF MEYCAUAYAN (BULACAN) | P00820205LZ | Construction of Flood Mitigation Structure | 120.9282 | 14.7389 | 67549529.17 | 67549262.71 | 2024 | A.J. LAVA BUILDERS CORP. (FORMERLY: A.J. LAVA BUIL | 2329 | 2024 | 2024-11-04 | 02/14/2024 | 266.46 | 0 | 2024-11-01 |  | 3
2024 | Region III | PAMPANGA | APALIT (PAMPANGA) | P00821589LZ | Construction of Flood Mitigation Structure | 120.7813 | 14.9758 | 49000000 | 46554004.9 | 2024 | 11-16 CONSTRUCTION | 2330 | 2024 | 2024-09-20 | 03/04/2024 | 2445995.1 | 0 | 2024-09-19 |  | 1
2023 | Region III | BULACAN | CITY OF BALIUAG (BULACAN) | P00727281LZ | Construction of Flood Mitigation Structure | 120.8966 | 14.9384 | 72374701.07 | 72373023.56 | 2023 | L.R. TIQUI BUILDERS, INC. | 2331 | 2023 | 2023-12-08 | 03/14/2023 | 1677.51 | 0 | 2023-12-07 |  | 1
2023 | Region III | BULACAN | CITY OF BALIUAG (BULACAN) | P00740333LZ | Construction of Flood Mitigation Structure | 120.8872 | 14.9674 | 72374734.39 | 72374463.63 | 2023 | GREAT PACIFIC BUILDERS AND GEN. CONTRACTOR INC. | 2332 | 2023 | 2023-12-06 | 03/28/2023 | 270.76 | 0 | 2023-12-21 | 15
2022 | Region III | PAMPANGA | CANDABA (PAMPANGA) | P00620207LZ | Construction of Slope Protection Structure | 120.9386 | 15.1239 | 86850000 | 82072158.49 | 2022 | CHOLO CONSTRUCTION AND TRADING | 2333 | 2022 | 2022-11-27 | 03/03/2022 | 4777841.51 | 0 | 2022-11-26 |  | 1
2024 | Region III | NUEVA ECIJA | TALAVERA (NUEVA ECIJA) | P00823435LZ | Construction of Flood Mitigation Structure | 120.92 | 15.6081 | 28950000 | 28659917.78 | 2024 | IJK MAE CONSTRUCTION INC. | 2334 | 2024 | 2024-10-01 | 04/24/2024 | 290082.22 | 0 | 2024-10-19 | 18
2022 | Region III | BULACAN | BOCAUE (BULACAN) | P00631191LZ | Construction of Flood Mitigation Structure | 120.9282 | 14.78 | 27439044.19 | 27439393.37 | 2022 | BLACK HARDHAT INC. (FORMERLY: JCHARDHAT INC.) | 2335 | 2022 | 2022-11-21 | 04/04/2022 | 0 | 349.18 | 2022-11-28 | 7
2024 | Region III | BULACAN | OBANDO (BULACAN) | P00820826LZ | Rehabilitation / Major Repair of Flood Mitigation Facility | 120.9206 | 14.7303 | 29398157.2 | 29399826.65 | 2024 | JB CONSTRUCTION AND SUPPLY INC. (FORMERLY:JB CONSTRUCTION AND SUPPLY) | 2336 | 2024 | 2024-08-03 | 02/12/2024 | 0 | 1669.45 | 2024-08-02 |  | 1
2023 | Region III | BULACAN | CITY OF BALIUAG (BULACAN) | P00725683LZ | Construction of Revetment | 120.8873 | 14.982 | 96499679.61 | 96499443.56 | 2023 | M.S. RAMOS CONSTRUCTION INC. (FORMERLY: M.S. RAMOS | 2337 | 2023 | 2023-11-21 | 02/13/2023 | 236.05 | 0 | 2023-12-08 | 17
2023 | National Capital Region | MALABON CITY | CITY OF MALABON (METROPOLITAN MANILA) | P00726813LZ | Construction of Flood Mitigation Structure | 120.9387 | 14.68 | 62718157.5 | 62725000 | 2024 | A.L. SALAZAR CONSTRUCTION, INC. / ROTAFLEX CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY:ROTA FLEX CONSTRUCTION) | 2338 | 2023 | 2024-06-29 | 03/22/2023 | 0 | 6842.5 | 2024-06-28 |  | 1
2024 | Region III | BULACAN | GUIGUINTO (BULACAN) | P00845982LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.8966 | 14.8261 | 49499698.53 | 49499959.76 | 2024 | A.L. SALAZAR CONSTRUCTION, INC. | 2339 | 2024 | 2024-08-25 | 02/28/2024 | 0 | 261.23 | 2024-08-24 |  | 1
2022 | Region III | PAMPANGA | SAN LUIS (PAMPANGA) | P00620846LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.8162 | 15.0616 | 86850000 | 83810211.36 | 2022 | NULAS BUILDERS / EDDMARI CONSTRUCTION & TRADING | 2340 | 2022 | 2022-10-28 | 03/03/2022 | 3039788.64 | 0 | 2022-10-27 |  | 1
2023 | Region III | BULACAN | PAOMBONG (BULACAN) | P00740591LZ | Construction of Flood Mitigation Structure | 120.7827 | 14.7939 | 48999739.7 | 47006762.89 | 2023 | GREAT PACIFIC BUILDERS AND GEN. CONTRACTOR INC. | 2341 | 2023 | 2023-11-22 | 03/28/2023 | 1992976.81 | 0 | 2023-11-21 |  | 1
2022 | Region IV-A | CAVITE | BACOOR CITY (CAVITE) | P00620880LZ | Construction of Revetment | 120.9283 | 14.4558 | 67225751.21 | 67225751.21 | 2022 | N.B. AVILA CONSTRUCTION | 2342 | 2022 | 2022-12-13 | 03/08/2022 | 0 | 0 | 2023-01-18 | 36
2022 | Region IV-B | OCCIDENTAL MINDORO | SABLAYAN (OCCIDENTAL MINDORO) | P00620654LZ | Construction of Flood Mitigation Structure | 120.8169 | 12.9267 | 226774789.4 | 48249953.59 | 2023 | ANORE CONSTRUCTION | 2343 | 2022 | 2023-07-03 | 07/06/2022 | 178524835.81 | 0 | 2023-07-02 |  | 1
2023 | Region IV-A | BATANGAS | LEMERY (BATANGAS) | P00742386LZ | Construction of Slope Protection Structure | 120.8967 | 14.0019 | 4950000 | 4800000 | 2023 | 830 BUILDERS & DEVELOPERS CORP. | 2344 | 2023 | 2023-09-15 | 05/19/2023 | 150000 | 0 | 2023-09-14 |  | 1
2024 | Region III | BULACAN | BOCAUE (BULACAN) | P00845798LZ | Construction of Slope Protection Structure | 120.9207 | 14.7636 | 98999020.79 | 98998749.59 | 2025 | TOPNOTCH CATALYST BUILDERS INC. / BEAM TEAM DEVELOPER SPECIALIST INC. | 2345 | 2024 | 2025-01-17 | 04/23/2024 | 271.2 | 0 | 2025-01-16 |  | 1
2024 | Region III | BULACAN | PLARIDEL (BULACAN) | P00821266LZ | Construction of Slope Protection Structure | 120.8875 | 14.9037 | 72374577.29 | 72374404.74 | 2024 | BELL CONSTRUCTION | 2346 | 2024 | 2024-06-24 | 02/07/2024 | 172.55 | 0 | 2024-10-02 | 100
2024 | Region III | BULACAN | CALUMPIT (BULACAN) | P00824698LZ | Construction of Revetment | 120.7831 | 14.9028 | 39199931.48 | 39199921.38 | 2024 | PTM DEVELOPMENT CORP. | 2347 | 2024 | 2024-07-08 | 02/02/2024 | 10.1 | 0 | 2024-07-29 | 21
2021 | National Capital Region | MALABON CITY |  | P00525709LZ | Construction of Dike | 120.9284 | 14.6911 | 34787975.95 | 34790000 | 2022 | E.L. TORRES CONSTRUCTION AND TRADING INC. (FORMERLY : E. L. TORRES CONSTRUCTION & TRADING | 2348 | 2021 | 2022-10-01 | 02/28/2022 | 0 | 2024.05 | 2022-09-30 |  | 1
2023 | Region III | BULACAN | SAN RAFAEL (BULACAN) | P00744230LZ | Construction of Flood Mitigation Structure | 120.9389 | 15.0162 | 96499951.99 | 96499871.18 | 2024 | EIRISH BUILDERS & SUPPLY INC. | 2349 | 2023 | 2024-03-15 | 06/20/2023 | 80.81 | 0 | 2024-03-14 |  | 1
2024 | Region III | BULACAN | CITY OF MALOLOS (CAPITAL) (BULACAN) | P00838388LZ | Construction of Slope Protection Structure | 120.8175 | 14.782 | 77199919.17 | 77199938.27 | 2024 | DARCY & ANNA BUILDERS & TRADING | 2350 | 2024 | 2024-04-19 | 02/07/2024 | 0 | 19.1 | 2024-10-02 | 166
2022 | Region IV-A | BATANGAS | SAN LUIS (BATANGAS) | P00640459LZ | Construction of Flood Mitigation Structure | 120.9208 | 13.8541 | 99000000 | 78404898.22 | 2023 | TCSC CORP. | 2351 | 2022 | 2023-01-24 | 03/31/2022 | 20595101.78 | 0 | 2023-01-23 |  | 1
2024 | Region III | BULACAN | BUSTOS (BULACAN) | P00843304LZ | Construction of Flood Mitigation Structure | 120.8969 | 14.932 | 77199961.67 | 77199088.96 | 2024 | ORANI CONSTRUCTION AND SUPPLY CORPORATION (FORMERLY:ORANI BUILDERS & SUPPLY) | 2352 | 2024 | 2024-11-28 | 04/16/2024 | 872.71 | 0 | 2024-12-10 | 12
2022 | Region III | BULACAN | CITY OF BALIUAG (BULACAN) | P00621075LZ | Construction of Flood Mitigation Structure | 120.8876 | 14.9257 | 48999081.39 | 48998739.19 | 2023 | TOPNOTCH CATALYST BUILDERS INC. | 2353 | 2022 | 2023-05-13 | 02/18/2022 | 342.2 | 0 | 2023-05-12 |  | 1
2022 | Region III | NUEVA ECIJA | SAN LEONARDO (NUEVA ECIJA) | P00620841LZ | Construction of Flood Mitigation Structure | 120.9286 | 15.3647 | 96499996.54 | 96499987.67 | 2023 | FRAMECON BUILDERS | 2354 | 2022 | 2023-03-14 | 03/02/2022 | 8.87 | 0 | 2023-03-13 |  | 1
2022 | Region III | BULACAN | CITY OF BALIUAG (BULACAN) | P00621566LZ | Construction of Flood Mitigation Structure | 120.8876 | 14.9257 | 95534935.86 | 95534903.44 | 2022 | A.R.L. CONSTRUCTION | 2355 | 2022 | 2022-12-12 | 04/04/2022 | 32.42 | 0 | 2023-02-26 | 76
2022 | Region III | NUEVA ECIJA | LUPAO (NUEVA ECIJA) | P00631226LZ | Construction of Flood Mitigation Structure | 120.897 | 15.8065 | 49000000 | 48816551.04 | 2022 | P.S. AQUINO CONSTRUCTION / NIÃ‘AS CONSTRUCTION CORP. (FORMERLY: NINA'S CONSTRUCTION AND SUPPLIES) | 2356 | 2022 | 2022-09-08 | 03/02/2022 | 183448.96 | 0 | 2022-09-26 | 18
2024 | Region III | BULACAN | CALUMPIT (BULACAN) | P00820823LZ | Construction of Revetment | 120.7831 | 14.9028 | 48999945.81 | 48999926.03 | 2024 | PTM DEVELOPMENT CORP. | 2357 | 2024 | 2024-08-29 | 02/02/2024 | 19.78 | 0 | 2024-08-28 |  | 1
2022 | Region IV-B | OCCIDENTAL MINDORO | CALINTAAN (OCCIDENTAL MINDORO) | P00621103LZ | Construction of Flood Mitigation Structure | 120.9391 | 12.5799 | 49000000 | 39978536.26 | 2023 | KGB ENGINEERING AND CONSTRUCTION / N. SALES CONSTRUCTION | 2358 | 2022 | 2023-03-28 | 05/30/2022 | 9021463.74 | 0 | 2023-03-27 |  | 1
2021 | Cordillera Administrative Region | BENGUET |  | P00525908LZ | Construction of Flood Mitigation Structure | 120.8176 | 16.8618 | 29400000 | 29400000 | 2022 | LAYAD GENERAL ENGINEERING CONSTRUCTION AND AGGREGATES | 2359 | 2021 | 2022-10-20 | 02/20/2022 | 0 | 0 | 2022-10-19 |  | 1
2025 | Region III | NUEVA ECIJA | JAEN (NUEVA ECIJA) | P00921446LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.921 | 15.382 | 96499998.78 | 96013671.84 | 2025 | NUEDA BUILDERS CONSTRUCTION & SUPPLY INC. | 2360 | 2025 | 2025-04-24 | 02/20/2025 | 486326.94 | 0 | 2026-02-04 | 286
2022 | Region III | BULACAN | CALUMPIT (BULACAN) | P00631196LZ | Construction of Flood Mitigation Structure | 120.7836 | 14.8764 | 39199665.51 | 39198299.28 | 2022 | MCB ZAMORA CONSTRUCTION & SUPPLY | 2361 | 2022 | 2022-09-30 | 01/28/2022 | 1366.23 | 0 | 2022-09-29 |  | 1
2022 | National Capital Region | MALABON CITY | CITY OF MALABON (METROPOLITAN MANILA) | P00632704LZ | Construction of Flood Mitigation Structure | 120.9287 | 14.7022 | 40179561.14 | 40590000 | 2022 | ALPHA & OMEGA GEN. CONTRACTOR & DEVELOPMENT CORP. | 2362 | 2022 | 2022-10-07 | 02/14/2022 | 0 | 410438.86 | 2022-10-10 | 3
2023 | Region IV-B | OCCIDENTAL MINDORO | PALUAN (OCCIDENTAL MINDORO) | P00740435LZ | Construction of Revetment | 120.7836 | 12.8246 | 207474999.8 | 207472845.6 | 2023 | GREAT PACIFIC BUILDERS AND GEN. CONTRACTOR INC. | 2363 | 2023 | 2023-12-20 | 04/13/2023 | 2154.2 | 0 | 2024-04-05 | 107
2022 | Region III | BULACAN | CITY OF BALIUAG (BULACAN) | P00639471LZ | Construction of Slope Protection Structure | 120.8876 | 14.9257 | 29399862.89 | 29399996.63 | 2022 | M3 KONSTRACT CORPORATION (FORMERLY:MARGARITA CONSTRUCTION) | 2364 | 2022 | 2022-09-01 | 04/05/2022 | 0 | 133.74 | 2022-08-31 |  | 1
2022 | National Capital Region | MALABON CITY | CITY OF MALABON (METROPOLITAN MANILA) | P00620354LZ | Construction of Flood Mitigation Structure | 120.9211 | 14.6998 | 48979511.1 | 49000000 | 2022 | A.L. SALAZAR CONSTRUCTION, INC. / ROTAFLEX CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY:ROTA FLEX CONSTRUCTION) | 2365 | 2022 | 2022-10-11 | 02/14/2022 | 0 | 20488.9 | 2022-10-10 |  | 1
2023 | Region IV-A | BATANGAS | LAUREL (BATANGAS) | P00746108LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.9391 | 14.0698 | 7237500 | 7236836 | 2024 | RGB CONSTRUCTION (FORMERLY:REYBER CONSTRUCTION AND SUPPLY) | 2366 | 2023 | 2024-04-02 | 01/05/2024 | 664 | 0 | 2024-05-02 | 30
2023 | Region III | BULACAN | CITY OF BALIUAG (BULACAN) | P00726466LZ | Construction of Flood Mitigation Structure | 120.8973 | 14.9408 | 96499205.41 | 96498922.73 | 2023 | M3 KONSTRACT CORPORATION (FORMERLY:MARGARITA CONSTRUCTION) | 2367 | 2023 | 2023-08-28 | 02/13/2023 | 282.68 | 0 | 2024-02-06 | 162
2024 | Region III | BULACAN | CITY OF MALOLOS (CAPITAL) (BULACAN) | P00843313LZ | Construction of Flood Mitigation Structure | 120.8178 | 14.8278 | 72374985.26 | 72374953.65 | 2024 | SYMS CONSTRUCTION TRADING | 2368 | 2024 | 2024-06-11 | 04/02/2024 | 31.61 | 0 | 2024-11-26 | 168
2024 | Region III | BULACAN | PLARIDEL (BULACAN) | P00825070LZ | Construction of Flood Mitigation Structure | 120.8879 | 14.9056 | 77199763.25 | 77199741.94 | 2024 | TOPNOTCH CATALYST BUILDERS INC. | 2369 | 2024 | 2024-07-25 | 05/14/2024 | 21.31 | 0 | 2025-01-07 | 166
2024 | Region III | BULACAN | BALAGTAS (BIGAA) (BULACAN) | P00839578LZ | Construction of Revetment | 120.9213 | 14.85 | 49499908.39 | 49499812.33 | 2024 | M.G. FRANCISCO CONSTRUCTION | 2370 | 2024 | 2024-09-18 | 03/20/2024 | 96.06 | 0 | 2024-11-13 | 56
2024 | Cordillera Administrative Region | MOUNTAIN PROVINCE | SABANGAN (MOUNTAIN PROVINCE) | P00821541LZ | Construction of Flood Mitigation Structure | 120.9213 | 16.9618 | 39199999.5 | 39200000 | 2024 | FJ MIRANDA CONSTRUCTION | 2371 | 2024 | 2024-06-08 | 02/18/2024 | 0 | 0.5 | 2024-08-22 | 75
2024 | Region III | BULACAN | CITY OF MEYCAUAYAN (BULACAN) | P00820206LZ | Construction of Flood Mitigation Structure | 120.9288 | 14.7377 | 67549578.43 | 67549945.46 | 2024 | JB CONSTRUCTION AND SUPPLY INC. (FORMERLY:JB CONSTRUCTION AND SUPPLY) | 2372 | 2024 | 2024-09-03 | 02/14/2024 | 0 | 367.03 | 2024-09-02 |  | 1
2024 | National Capital Region | NAVOTAS CITY | CITY OF NAVOTAS (METROPOLITAN MANILA) | P00820556LZ | Construction of Flood Mitigation Facility | 120.9396 | 14.6768 | 29399296.33 | 29399282.43 | 2025 | 721 BUILDERS CORPORATION | 2373 | 2024 | 2025-04-08 | 02/12/2024 | 13.9 | 0 | 2025-04-07 |  | 1
2024 | Region III | BULACAN | BALAGTAS (BIGAA) (BULACAN) | P00838379LZ | Construction of Slope Protection Structure | 120.9213 | 14.8502 | 96499888.93 | 96499536.28 | 2025 | ELITE GENERAL CONTRACTOR AND DEVELOPMENT CORP. | 2374 | 2024 | 2025-01-31 | 02/07/2024 | 352.65 | 0 | 2025-01-30 |  | 1
2023 | Region I | ILOCOS NORTE | PAGUDPUD (ILOCOS NORTE) | P00740516LZ | Construction of Flood Mitigation Structure | 120.8179 | 18.578 | 48999547.34 | 48999546.39 | 2023 | 11-16 CONSTRUCTION | 2375 | 2023 | 2023-12-06 | 04/25/2023 | 0.95 | 0 | 2023-12-28 | 22
2022 | Region III | BULACAN | PLARIDEL (BULACAN) | P00639349LZ | Construction of Slope Protection Structure | 120.8884 | 14.9271 | 57898808.89 | 57899336.29 | 2022 | M3 KONSTRACT CORPORATION (FORMERLY:MARGARITA CONSTRUCTION) | 2376 | 2022 | 2022-11-29 | 04/04/2022 | 0 | 527.4 | 2022-11-28 |  | 1
2022 | Region III | PAMPANGA | APALIT (PAMPANGA) | P00620847LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.7836 | 14.9669 | 86850000 | 84244493.37 | 2022 | 11-16 CONSTRUCTION | 2377 | 2022 | 2022-10-30 | 02/28/2022 | 2605506.63 | 0 | 2022-10-24 |  | 6
2023 | Region III | BULACAN | BALAGTAS (BIGAA) (BULACAN) | P00736003LZ | Construction of Revetment | 120.8973 | 14.807 | 57899152.08 | 57899547.58 | 2023 | RDBT CONSTRUCTION CORP. / C.B. GARAY PHILWIDE BUILDERS | 2378 | 2023 | 2023-12-01 | 02/13/2023 | 0 | 395.5 | 2024-01-07 | 37
2022 | Cordillera Administrative Region | BENGUET | KABAYAN (BENGUET) | P00620997LZ | Construction of Flood Mitigation Structure | 120.8188 | 16.6536 | 24500000 | 24445135.58 | 2022 | CABUGUIASAN BUILDERS | 2379 | 2022 | 2022-11-14 | 05/10/2022 | 54864.42 | 0 | 2022-11-11 |  | 3
2024 | Region III | NUEVA ECIJA | ALIAGA (NUEVA ECIJA) | P00820276LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.8193 | 15.5187 | 96500000 | 95535356 | 2024 | AMP 723 CONSTRUCTION CORPORATION (FORMERLY: A.M.P. CONSTRUCTION) / RPP 928 CONSTRUCTION CORPORATION | 2380 | 2024 | 2024-08-12 | 02/06/2024 | 964644 | 0 | 2024-10-31 | 80
2022 | Region IV-A | CAVITE | IMUS CITY (CAVITE) | P00621094LZ | Construction of Revetment | 120.9396 | 14.4319 | 43120000 | 40959552.51 | 2022 | KLDS TRADING & CONSTRUCTION | 2381 | 2022 | 2022-10-28 | 02/24/2022 | 2160447.49 | 0 | 2022-10-27 |  | 1
2023 | Region III | BULACAN | CITY OF BALIUAG (BULACAN) | P00726469LZ | Construction of Flood Mitigation Structure | 120.8887 | 14.9795 | 96499679.61 | 96498859.48 | 2023 | L.R. TIQUI BUILDERS, INC. | 2382 | 2023 | 2023-12-05 | 02/13/2023 | 820.13 | 0 | 2023-12-08 | 3
2023 | Region III | BULACAN | PLARIDEL (BULACAN) | P00742324LZ | Construction of Flood Mitigation Structure | 120.8195 | 14.901 | 49499971.11 | 49499463.32 | 2023 | DARCY & ANNA BUILDERS & TRADING | 2383 | 2023 | 2023-11-21 | 03/27/2023 | 507.79 | 0 | 2023-11-20 |  | 1
2023 | Region III | BULACAN | BALAGTAS (BIGAA) (BULACAN) | P00740352LZ | Construction of Flood Mitigation Structure | 120.8974 | 14.8091 | 72374857.02 | 72374635.68 | 2023 | M.S. RAMOS CONSTRUCTION INC. (FORMERLY: M.S. RAMOS | 2384 | 2023 | 2023-12-11 | 03/28/2023 | 221.34 | 0 | 2023-12-21 | 10
2023 | Region IV-A | BATANGAS | AGONCILLO (BATANGAS) | P00742395LZ | Rehabilitation / Major Repair of Drainage Structure | 120.9289 | 13.9338 | 4950000 | 4949338.6 | 2023 | VAN MAKJAY CONSTRUCTION | 2385 | 2023 | 2023-08-15 | 03/21/2023 | 661.4 | 0 | 2023-07-21 |  | 25
2024 | Region III | BULACAN | OBANDO (BULACAN) | P00825084LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.9214 | 14.7384 | 96499677.33 | 96499819.35 | 2025 | EDFROBON CONSTRUCTION SERVICES INCORPORATED | 2386 | 2024 | 2025-01-10 | 06/05/2024 | 0 | 142.02 | 2025-01-10 | 0
2023 | Region III | NUEVA ECIJA | SANTO DOMINGO (NUEVA ECIJA) | P00726920LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.7837 | 15.4913 | 96500000 | 96496000 | 2023 | AMP 723 CONSTRUCTION CORPORATION (FORMERLY: A.M.P. CONSTRUCTION) | 2387 | 2023 | 2023-08-01 | 03/20/2023 | 4000 | 0 | 2023-12-13 | 134
2024 | Region IV-A | BATANGAS | LAUREL (BATANGAS) | P00839602LZ | Construction of Drainage Structure | 120.929 | 14.0575 | 4950000 | 4949382.55 | 2024 | NDA BUILDERS AND DEVELOPERS | 2388 | 2024 | 2024-06-11 | 04/29/2024 | 617.45 | 0 | 2024-08-25 | 75
2022 | Region IV-A | CAVITE | BACOOR CITY (CAVITE) | P00631298LZ | Construction of Flood Mitigation Structure | 120.9397 | 14.4482 | 19599972.66 | 9799196.02 | 2023 | OMNICON BUILDERS | 2389 | 2022 | 2023-10-24 | 04/04/2022 | 9800776.64 | 0 | 2023-10-23 |  | 1
2022 | National Capital Region | MALABON CITY | CITY OF MALABON (METROPOLITAN MANILA) | P00620353LZ | Construction of Flood Mitigation Structure | 120.9214 | 14.699 | 48916982.48 | 49000000 | 2022 | A.L. SALAZAR CONSTRUCTION, INC. | 2390 | 2022 | 2022-10-11 | 02/14/2022 | 0 | 83017.52 | 2022-10-10 |  | 1
2023 | Region IV-B | OCCIDENTAL MINDORO | SABLAYAN (OCCIDENTAL MINDORO) | P00736039LZ | Construction of Dike | 120.82 | 12.9266 | 217124999.5 | 217122476.3 | 2023 | SUNWEST, INC. (FORMERLY: SUNWEST CONSTRUCTION & DEVELOPMENT CORPORATION) | 2391 | 2023 | 2023-12-15 | 04/13/2023 | 2523.2 | 0 | 2024-05-25 | 162
2024 | Region III | BULACAN | CITY OF BALIUAG (BULACAN) | P00838417LZ | Construction of Slope Protection Structure | 120.889 | 14.9717 | 96499950.8 | 96499932.39 | 2024 | IM CONSTRUCTION CORPORATION | 2392 | 2024 | 2024-09-09 | 02/07/2024 | 18.41 | 0 | 2024-11-01 | 53
2022 | Region III | BULACAN | OBANDO (BULACAN) | P00620148LZ | Construction of Flood Mitigation Structure | 120.9291 | 14.7032 | 96499433.06 | 92639455.74 | 2022 | AZUL BUILDERS | 2393 | 2022 | 2022-09-05 | 03/07/2022 | 3859977.32 | 0 | 2022-09-04 |  | 1
2022 | Cordillera Administrative Region | BENGUET | BAKUN (BENGUET) | P00620478LZ | Construction of Flood Mitigation Structure | 120.784 | 16.7692 | 24500000 | 24500000 | 2022 | JUDAN BUILDERS | 2394 | 2022 | 2022-11-06 | 03/07/2022 | 0 | 0 | 2022-11-05 |  | 1
2023 | National Capital Region | MALABON CITY | CITY OF MALABON (METROPOLITAN MANILA) | P00725574LZ | Construction of Flood Mitigation Structure | 120.9398 | 14.6838 | 96497458.4 | 96500000 | 2024 | A.L. SALAZAR CONSTRUCTION, INC. / AL-REM KONSTRUCT INC. | 2395 | 2023 | 2024-12-06 | 04/19/2023 | 0 | 2541.6 | 2025-03-23 | 107
2022 | Region III | BULACAN | BALAGTAS (BIGAA) (BULACAN) | P00631189LZ | Construction of Flood Mitigation Structure | 120.8975 | 14.8084 | 37239196.33 | 37239159.73 | 2022 | TOPNOTCH CATALYST BUILDERS INC. / BLACK HARDHAT INC. (FORMERLY: JCHARDHAT INC.) | 2396 | 2022 | 2022-11-20 | 02/24/2022 | 36.6 | 0 | 2022-11-19 |  | 1
2022 | National Capital Region | MALABON CITY | CITY OF MALABON (METROPOLITAN MANILA) | P00631021LZ | Construction of Dike | 120.9216 | 14.7005 | 48909696.09 | 49000000 | 2022 | TWO DIMENSION CONSTRUCTION | 2397 | 2022 | 2022-10-11 | 02/14/2022 | 0 | 90303.91 | 2022-10-10 |  | 1
2023 | Region III | BULACAN | CITY OF BALIUAG (BULACAN) | P00740343LZ | Construction of Flood Mitigation Structure | 120.889 | 14.9788 | 72374734.39 | 72374627.31 | 2023 | GREAT PACIFIC BUILDERS AND GEN. CONTRACTOR INC. | 2398 | 2023 | 2023-12-05 | 03/28/2023 | 107.08 | 0 | 2023-12-21 | 16
2023 | National Capital Region | MALABON CITY | CITY OF MALABON (METROPOLITAN MANILA) | P00726814LZ | Construction of Flood Mitigation Structure | 120.94 | 14.6774 | 62720345.05 | 62725000 | 2024 | MEGAY CONSTRUCTION INC. (FORMERLY: MEGAY CONSTRUCTION) | 2399 | 2023 | 2024-05-30 | 03/22/2023 | 0 | 4654.95 | 2024-05-29 |  | 1
2023 | Cordillera Administrative Region | BENGUET | BUGUIAS (BENGUET) | P00726410LZ | [11 empty] | 0 | 0
[16 empty] | 0 | 0
2021 | National Capital Region | MALABON CITY |  | P00525710LZ | Construction of Flood Mitigation Structure | 120.9295 | 14.6928 | 34789815.44 | 34790000 | 2022 | DREAMWORX BUILDER & TRADING, INC. / QUATRIX CONSTRUCTION AND SUPPLY INC. | 2401 | 2021 | 2022-09-19 | 03/24/2022 | 0 | 184.56 | 2022-09-18 |  | 1
2024 | Region III | BULACAN | BOCAUE (BULACAN) | P00820819LZ | Construction of Flood Mitigation Structure | 120.9217 | 14.767 | 28949974.76 | 28949931.66 | 2024 | GREAT PACIFIC BUILDERS AND GEN. CONTRACTOR INC. | 2402 | 2024 | 2024-10-15 | 03/20/2024 | 43.1 | 0 | 2024-10-14 |  | 1
2023 | Region III | BULACAN | CITY OF BALIUAG (BULACAN) | P00740341LZ | Construction of Flood Mitigation Structure | 120.8891 | 14.9764 | 72374988.4 | 72373564.32 | 2024 | M3 KONSTRACT CORPORATION (FORMERLY:MARGARITA CONSTRUCTION) | 2403 | 2023 | 2024-02-20 | 03/28/2023 | 1424.08 | 0 | 2024-02-19 |  | 1
2023 | Region IV-B | OCCIDENTAL MINDORO | SABLAYAN (OCCIDENTAL MINDORO) | P00736041LZ | Construction of Dike | 120.8214 | 12.9255 | 207474999.8 | 207472980.3 | 2023 | SUNWEST, INC. (FORMERLY: SUNWEST CONSTRUCTION & DEVELOPMENT CORPORATION) | 2404 | 2023 | 2023-12-15 | 02/11/2023 | 2019.5 | 0 | 2024-03-25 | 101
2024 | Region III | BULACAN | CITY OF MEYCAUAYAN (BULACAN) | P00825064LZ | Construction of Flood Mitigation Structure | 120.9296 | 14.7382 | 96499621.49 | 96423430.86 | 2024 | L.R. TIQUI BUILDERS, INC. / 729 CONSTRUCTION, INC. (FORMERLY 722 CONSTRUCTION, INC.) | 2405 | 2024 | 2024-12-17 | 03/14/2024 | 76190.63 | 0 | 2025-01-21 | 35
2022 | National Capital Region | MALABON CITY | CITY OF MALABON (METROPOLITAN MANILA) | P00620352LZ | Construction of Flood Mitigation Structure | 120.922 | 14.698 | 48921423.86 | 49000000 | 2022 | A.L. SALAZAR CONSTRUCTION, INC. | 2406 | 2022 | 2022-10-11 | 02/14/2022 | 0 | 78576.14 | 2022-10-10 |  | 1
2022 | National Capital Region | MALABON CITY | CITY OF MALABON (METROPOLITAN MANILA) | P00631022LZ | Construction of Flood Mitigation Facility | 120.94 | 14.6776 | 29395689.6 | 29398759.41 | 2023 | ROTAFLEX CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY:ROTA FLEX CONSTRUCTION) | 2407 | 2022 | 2023-01-13 | 02/28/2022 | 0 | 3069.81 | 2023-01-14 | 1
2022 | Cordillera Administrative Region | BENGUET | BOKOD (BENGUET) | P00639445LZ | Construction of Flood Mitigation Structure | 120.7841 | 16.5352 | 19600000 | 19510507.33 | 2022 | POLO ENGINEERING & CONSTRUCTION | 2408 | 2022 | 2022-11-29 | 06/22/2022 | 89492.67 | 0 | 2022-11-30 | 1
2024 | Region III | BULACAN | BUSTOS (BULACAN) | P00843319LZ | Construction of Flood Mitigation Structure | 120.8976 | 14.9316 | 77199950.08 | 77199050.27 | 2024 | JAGONBUILD CONSTRUCTION CORP. (FOR. JAGON BUILDERS | 2409 | 2024 | 2024-11-27 | 04/02/2024 | 899.81 | 0 | 2024-11-26 |  | 1
2023 | National Capital Region | NAVOTAS CITY | CITY OF NAVOTAS (METROPOLITAN MANILA) | P00742223LZ | Construction of Flood Mitigation Facility | 120.9403 | 14.6751 | 19795322.25 | 19799819.78 | 2023 | 816 EMBER CONSTRUCTION CORPORATION | 2410 | 2023 | 2023-10-20 | 03/27/2023 | 0 | 4497.53 | 2023-10-21 | 1
2024 | Region III | PAMPANGA | APALIT (PAMPANGA) | P00825097LZ | Construction of Flood Mitigation Structure | 120.7842 | 14.9636 | 77200000 | 73322904.7 | 2025 | ANGEL BUILDERS & CONSTRUCTION SUPPLY / FRAMECON BUILDERS | 2411 | 2024 | 2025-01-08 | 05/29/2024 | 3877095.3 | 0 | 2025-01-07 |  | 1
2022 | Region III | BULACAN | CITY OF MALOLOS (CAPITAL) (BULACAN) | P00631200LZ | Construction of Slope Protection Structure | 120.8216 | 14.8048 | 48999825.71 | 48999585.71 | 2022 | J. SIMEON CONSTRUCTION | 2412 | 2022 | 2022-09-14 | 01/28/2022 | 240 | 0 | 2023-01-21 | 129
2023 | Region III | BULACAN | CITY OF BALIUAG (BULACAN) | P00726464LZ | Construction of Flood Mitigation Structure | 120.8892 | 14.9794 | 96499679.61 | 96499304.28 | 2023 | L.R. TIQUI BUILDERS, INC. | 2413 | 2023 | 2023-11-30 | 02/13/2023 | 375.33 | 0 | 2023-12-08 | 8
2022 | Region III | BULACAN | BOCAUE (BULACAN) | P00621281LZ | Construction of Slope Protection Structure | 120.9296 | 14.7754 | 67549761.13 | 67549750.2 | 2022 | JTC CRUZ CONSTRUCTION CO., INC. | 2414 | 2022 | 2022-11-04 | 04/04/2022 | 10.93 | 0 | 2023-01-27 | 84
2024 | Region III | NUEVA ECIJA | TALAVERA (NUEVA ECIJA) | P00844537LZ | Construction of Drainage Structure | 120.922 | 15.5676 | 33766315 | 33428392.22 | 2025 | IJK MAE CONSTRUCTION INC. | 2415 | 2024 | 2025-01-02 | 06/07/2024 | 337922.78 | 0 | 2025-01-01 |  | 1
2022 | Cordillera Administrative Region | ABRA | LICUAN-BAAY (LICUAN) (ABRA) | P00639437LZ | Construction of Flood Mitigation Structure | 120.8977 | 17.6199 | 48999929.5 | 48998000 | 2023 | 739 BUILDERS | 2416 | 2022 | 2023-01-19 | 07/13/2022 | 1929.5 | 0 | 2023-01-13 |  | 6
2022 | Region III | BULACAN | SAN ILDEFONSO (BULACAN) | P00620159LZ | Construction of Flood Mitigation Structure | 120.9403 | 15.0637 | 67549339.87 | 67547136.97 | 2022 | L.R. TIQUI BUILDERS, INC. | 2417 | 2022 | 2022-10-26 | 03/07/2022 | 2202.9 | 0 | 2022-10-25 |  | 1
2024 | Region III | PAMPANGA | SAN LUIS (PAMPANGA) | P00821286LZ | Construction of Flood Mitigation Structure | 120.7843 | 15.0388 | 96500000 | 93604726.13 | 2024 | 11-16 CONSTRUCTION | 2418 | 2024 | 2024-11-07 | 03/05/2024 | 2895273.87 | 0 | 2024-11-06 |  | 1
2023 | Region III | BULACAN | BOCAUE (BULACAN) | P00736013LZ | Construction of Slope Protection Structure | 120.9407 | 14.7924 | 48249682.67 | 48249969.22 | 2023 | TOPNOTCH CATALYST BUILDERS INC. | 2419 | 2023 | 2023-08-16 | 02/13/2023 | 0 | 286.55 | 2023-10-09 | 54
2023 | Region III | BULACAN | CITY OF BALIUAG (BULACAN) | P00726462LZ | Construction of Flood Mitigation Structure | 120.8893 | 14.9763 | 96499679.61 | 96498762.72 | 2024 | L.R. TIQUI BUILDERS, INC. | 2420 | 2023 | 2024-02-01 | 02/13/2023 | 916.89 | 0 | 2024-02-06 | 5
2024 | National Capital Region | NAVOTAS CITY | CITY OF NAVOTAS (METROPOLITAN MANILA) | P00820554LZ | Construction of Revetment | 120.93 | 14.6807 | 48975647.1 | 48999818.48 | 2024 | JAGONBUILD CONSTRUCTION CORP. (FOR. JAGON BUILDERS | 2421 | 2024 | 2024-07-25 | 02/12/2024 | 0 | 24171.38 | 2024-10-07 | 74
2024 | Region III | BULACAN | PANDI (BULACAN) | P00838391LZ | Construction of Slope Protection Structure | 120.9221 | 14.8552 | 96499990.48 | 96499509.1 | 2024 | TOPNOTCH CATALYST BUILDERS INC. | 2422 | 2024 | 2024-10-16 | 02/07/2024 | 481.38 | 0 | 2024-11-01 | 16
2023 | Region III | BULACAN | SAN ILDEFONSO (BULACAN) | P00725749LZ | Construction of Flood Mitigation Structure | 120.9407 | 15.0963 | 57899328.22 | 57898871.17 | 2024 | M3 KONSTRACT CORPORATION (FORMERLY:MARGARITA CONSTRUCTION) | 2423 | 2023 | 2024-01-30 | 06/05/2023 | 457.05 | 0 | 2024-01-29 |  | 1
2022 | Region III | PAMPANGA | APALIT (PAMPANGA) | P00630061LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.7845 | 14.9698 | 77200000 | 74883998.26 | 2022 | 11-16 CONSTRUCTION | 2424 | 2022 | 2022-10-28 | 03/03/2022 | 2316001.74 | 0 | 2022-10-27 |  | 1
2023 | Region IV-A | CAVITE | KAWIT (CAVITE) | P00737507LZ | Construction of Drainage Structure | 120.8978 | 14.4431 | 11880000 | 11758071.49 | 2023 | T.E. TRINIDAD CONSTRUCTION | 2425 | 2023 | 2023-07-29 | 02/19/2023 | 121928.51 | 0 | 2023-07-28 |  | 1
2024 | Cordillera Administrative Region | BENGUET | BUGUIAS (BENGUET) | P00845925LZ | Construction of Flood Mitigation Structure | 120.822 | 16.7046 | 49500000 | 49480290 | 2024 | ALMOND ENGINEERING & CONSTRUCTION | 2426 | 2024 | 2024-08-21 | 04/29/2024 | 19710 | 0 | 2025-01-21 | 153
2023 | Region III | BULACAN | CITY OF BALIUAG (BULACAN) | P00726471LZ | Construction of Flood Mitigation Structure | 120.8895 | 14.9763 | 96499679.61 | 96499642.53 | 2024 | TRIPLE 8 CONSTRUCTION & SUPPLY, INC. (FORMERLY TRIPLE 8 CONST. & SUPPLY) | 2427 | 2023 | 2024-02-07 | 02/13/2023 | 37.08 | 0 | 2024-02-06 |  | 1
2023 | Region III | PAMPANGA | CANDABA (PAMPANGA) | P00726891LZ | Construction of Slope Protection Structure | 120.9223 | 15.1221 | 144749614.8 | 144750000 | 2024 | STO. CRISTO CONSTRUCTION & TRADING INC. (FOR: STO. CRISTO CONSTRUCTION & TRADING) | 2428 | 2023 | 2024-05-16 | 08/21/2023 | 0 | 385.2 | 2024-05-15 |  | 1
2023 | Region III | BULACAN | CITY OF MALOLOS (CAPITAL) (BULACAN) | P00726149LZ | Construction of Revetment | 120.8223 | 14.8281 | 33319902.3 | 33319346.58 | 2023 | EL KAPITAN CONSTRUCTION SERVICES | 2429 | 2023 | 2023-06-29 | 02/06/2023 | 555.72 | 0 | 2023-08-03 | 35
2024 | Region III | PAMPANGA | SANTA ANA (PAMPANGA) | P00839587LZ | Construction of Drainage Structure | 120.7849 | 15.0934 | 4950000 | 4704444.99 | 2024 | UNI-FIVE CONSTRUCTION AND TRADING | 2430 | 2024 | 2024-08-14 | 05/03/2024 | 245555.01 | 0 | 2024-08-13 |  | 1
2023 | Region III | BULACAN | CITY OF MALOLOS (CAPITAL) (BULACAN) | P00726158LZ | Construction of Flood Mitigation Structure | 120.8223 | 14.828 | 48999904.49 | 48999864.47 | 2023 | TOPNOTCH CATALYST BUILDERS INC. | 2431 | 2023 | 2023-10-03 | 02/06/2023 | 40.02 | 0 | 2023-10-02 |  | 1
2023 | Region III | BULACAN | CITY OF BALIUAG (BULACAN) | P00740342LZ | Construction of Flood Mitigation Structure | 120.8895 | 14.9162 | 72374734.39 | 72374674.87 | 2023 | YPR GEN. CONTRACTOR AND CONSTRUCTION SUPPLY INC. | 2432 | 2023 | 2023-12-05 | 03/28/2023 | 59.52 | 0 | 2023-12-21 | 16
2023 | Region I | ILOCOS NORTE | PAGUDPUD (ILOCOS NORTE) | P00740514LZ | Construction of Flood Mitigation Structure | 120.7856 | 18.5776 | 29399804.98 | 29399790.15 | 2023 | JLP CONSTRUCTION & SUPPLY (FORMERLY: JLP CONSTRUCT | 2433 | 2023 | 2023-10-16 | 04/28/2023 | 14.83 | 0 | 2023-10-23 | 7
2024 | Region III | NUEVA ECIJA | JAEN (NUEVA ECIJA) | P00846001LZ | Construction of Drainage Structure | 120.9223 | 15.3378 | 24749937.78 | 24495731.43 | 2024 | R.D. TALENS CONSTRUCTION AND TRADING | 2434 | 2024 | 2024-12-05 | 05/17/2024 | 254206.35 | 0 | 2024-12-04 |  | 1
2023 | Region III | NUEVA ECIJA | SAN ISIDRO (NUEVA ECIJA) | P00727301LZ | Construction of Flood Mitigation Structure | 120.8979 | 15.3126 | 72374973.41 | 72374903.94 | 2023 | F-DEY CONSTRUCTION AND TRADING / JERRY R. SANTIAGO CONSTRUCTION CORP. (FORMERLY: JERRY SANTIAGO CONSTRUCTION) | 2435 | 2023 | 2023-10-10 | 03/24/2023 | 69.47 | 0 | 2023-12-17 | 68
2022 | Region IV-A | CAVITE | IMUS CITY (CAVITE) | P00620226LZ | Construction of Revetment | 120.93 | 14.3829 | 89745000 | 89745000 | 2022 | C.S. RAMOS CONSTRUCTION / ALMAKAR BUILDERS & METAL WORKS | 2436 | 2022 | 2022-11-19 | 02/28/2022 | 0 | 0 | 2022-11-18 |  | 1
2023 | Region III | BULACAN | SAN ILDEFONSO (BULACAN) | P00727394LZ | Construction of Flood Mitigation Structure | 120.9407 | 15.0963 | 86849532.71 | 86848839.48 | 2024 | M3 KONSTRACT CORPORATION (FORMERLY:MARGARITA CONSTRUCTION) | 2437 | 2023 | 2024-04-14 | 06/20/2023 | 693.23 | 0 | 2024-04-13 |  | 1
2022 | Region III | BULACAN | BOCAUE (BULACAN) | P00632825LZ | Rehabilitation / Major Repair of Drainage Structure | 120.9223 | 14.7984 | 4949445.41 | 4850344.04 | 2022 | TBB CONSTRUCTION CORP. | 2438 | 2022 | 2022-11-07 | 01/28/2022 | 99101.37 | 0 | 2022-05-26 |  | 165
2024 | Region III | BULACAN | CITY OF MEYCAUAYAN (BULACAN) | P00825063LZ | Construction of Flood Mitigation Structure | 120.9301 | 14.7386 | 96499785.54 | 96499280.93 | 2024 | L.R. TIQUI BUILDERS, INC. / 729 CONSTRUCTION, INC. (FORMERLY 722 CONSTRUCTION, INC.) | 2439 | 2024 | 2024-12-16 | 03/14/2024 | 504.61 | 0 | 2025-01-21 | 36
2022 | Region IV-A | CAVITE | CITY OF GENERAL TRIAS (CAVITE) | P00620877LZ | Construction of Revetment | 120.8898 | 14.3231 | 81542500 | 81542500 | 2022 | TRIPLE 8 CONSTRUCTION & SUPPLY, INC. (FORMERLY TRIPLE 8 CONST. & SUPPLY) | 2440 | 2022 | 2022-11-12 | 02/28/2022 | 0 | 0 | 2022-11-11 |  | 1
2022 | Region I | PANGASINAN | NATIVIDAD (PANGASINAN) | P00620972LZ | Construction of Revetment | 120.7861 | 16.0536 | 29400000 | 29047823.6 | 2022 | ORIENTAL SALES CENTER AND CONTRACTOR | 2441 | 2022 | 2022-11-27 | 03/08/2022 | 352176.4 | 0 | 2022-08-23 |  | 96
2024 | Region III | BULACAN | CITY OF MALOLOS (CAPITAL) (BULACAN) | P00838386LZ | Construction of Slope Protection Structure | 120.8223 | 14.8282 | 77199973 | 77199896.46 | 2024 | DARCY & ANNA BUILDERS & TRADING | 2442 | 2024 | 2024-04-19 | 02/07/2024 | 76.54 | 0 | 2024-10-02 | 166
2023 | Region III | BULACAN | BALAGTAS (BIGAA) (BULACAN) | P00740349LZ | Construction of Flood Mitigation Structure | 120.9223 | 14.837 | 72374293.86 | 72372099.18 | 2023 | STAR WILLIAM CONSTRUCTION | 2443 | 2023 | 2023-12-04 | 03/28/2023 | 2194.68 | 0 | 2023-12-21 | 17
2022 | Region IV-A | CAVITE | IMUS CITY (CAVITE) | P00620249LZ | Construction of Flood Mitigation Structure | 120.9301 | 14.3828 | 90665610 | 90665610 | 2022 | N.B. AVILA CONSTRUCTION | 2444 | 2022 | 2022-11-21 | 02/28/2022 | 0 | 0 | 2022-11-20 |  | 1
2023 | Region III | BULACAN | BOCAUE (BULACAN) | P00726485LZ | Construction of Flood Mitigation Structure | 120.9409 | 14.7926 | 96499473.1 | 96499997.89 | 2023 | WAWAO BUILDERS / SYMS CONSTRUCTION TRADING | 2445 | 2023 | 2023-06-07 | 02/13/2023 | 0 | 524.79 | 2023-12-08 | 184
2024 | Region III | BULACAN | BUSTOS (BULACAN) | P00838394LZ | Construction of Slope Protection Structure | 120.898 | 14.9309 | 72374887.61 | 72374583.56 | 2024 | C & F CONSTRUCTION & DEVELOPMENT CORPORATION | 2446 | 2024 | 2024-07-22 | 02/07/2024 | 304.05 | 0 | 2024-10-02 | 72
2022 | Region III | BULACAN | PLARIDEL (BULACAN) | P00621568LZ | Construction of Slope Protection Structure | 120.8898 | 14.9217 | 82024885.78 | 78743785.69 | 2023 | A.R.L. CONSTRUCTION | 2447 | 2022 | 2023-02-24 | 04/01/2022 | 3281100.09 | 0 | 2023-02-23 |  | 1
2023 | Region III | BULACAN | BOCAUE (BULACAN) | P00742320LZ | Construction of Flood Mitigation Structure | 120.9412 | 14.793 | 4949041.01 | 4949455.31 | 2023 | RVR3 CONSTRUCTION SUPPLY AND SERVICES | 2448 | 2023 | 2023-09-21 | 06/13/2023 | 0 | 414.3 | 2023-10-09 | 18
2024 | Region III | BULACAN | OBANDO (BULACAN) | P00820234LZ | Construction of Flood Mitigation Structure | 120.9303 | 14.7158 | 144749213.8 | 144749071.8 | 2024 | G.F. FABIAN CONSTRUCTION | 2449 | 2024 | 2024-11-18 | 02/22/2024 | 142 | 0 | 2024-11-17 |  | 1
2023 | Region I | ILOCOS NORTE | PAGUDPUD (ILOCOS NORTE) | P00742258LZ | Construction of Flood Mitigation Structure | 120.7866 | 18.5769 | 19799572.38 | 19799555.93 | 2023 | JLP CONSTRUCTION & SUPPLY (FORMERLY: JLP CONSTRUCT | 2450 | 2023 | 2023-10-16 | 05/05/2023 | 16.45 | 0 | 2023-10-15 |  | 1
2023 | Region III | BULACAN | PULILAN (BULACAN) | P00736618LZ | Construction of Flood Mitigation Structure | 120.8899 | 14.9066 | 48999799.64 | 48999988.7 | 2023 | WAWAO BUILDERS | 2451 | 2023 | 2023-07-03 | 02/06/2023 | 0 | 189.06 | 2023-10-02 | 91
2023 | Region I | ILOCOS NORTE | PAGUDPUD (ILOCOS NORTE) | P00727053LZ | Construction of Flood Mitigation Structure | 120.9413 | 18.5578 | 48999700.63 | 48999695.49 | 2023 | 11-16 CONSTRUCTION | 2452 | 2023 | 2023-11-17 | 04/20/2023 | 5.14 | 0 | 2023-12-23 | 36
2024 | Region III | NUEVA ECIJA | CITY OF GAPAN (NUEVA ECIJA) | P00821260LZ | Construction of Flood Mitigation Structure | 120.9304 | 15.3072 | 96499905.21 | 94567339.01 | 2024 | R.A. PAHATI CONST. & SUPPLY, INC. | 2453 | 2024 | 2024-05-24 | 02/12/2024 | 1932566.2 | 0 | 2024-11-30 | 190
2023 | Region III | BULACAN | CITY OF MALOLOS (CAPITAL) (BULACAN) | P00740364LZ | Construction of Flood Mitigation Structure | 120.8223 | 14.8281 | 96499716.43 | 96498343.32 | 2023 | FERDSTAR BUILDERS INC. | 2454 | 2023 | 2023-12-08 | 03/28/2023 | 1373.11 | 0 | 2024-03-20 | 103
2022 | Region IV-B | OCCIDENTAL MINDORO | SABLAYAN (OCCIDENTAL MINDORO) | P00620652LZ | Construction of Drainage Structure | 120.7872 | 12.8464 | 39200000 | 33972197.78 | 2022 | F.A. TORRES CONSTRUCTION | 2455 | 2022 | 2022-11-22 | 03/07/2022 | 5227802.22 | 0 | 2022-12-30 | 38
2022 | Region IV-A | CAVITE | KAWIT (CAVITE) | P00640554LZ | Construction of Slope Protection Structure | 120.8902 | 14.4114 | 21780000 | 21780000 | 2022 | ALMAKAR BUILDERS & METAL WORKS | 2456 | 2022 | 2022-11-07 | 03/31/2022 | 0 | 0 | 2022-11-06 |  | 1
2023 | Cordillera Administrative Region | MOUNTAIN PROVINCE | BONTOC (CAPITAL) (MOUNTAIN PROVINCE) | P00727404LZ | Construction of Flood Mitigation Structure | 120.9414 | 17.65 | 29399999.6 | 29400000 | 2023 | ALPHA SIX CONSTRUCTION | 2457 | 2023 | 2023-09-07 | 04/10/2023 | 0 | 0.4 | 2023-09-06 |  | 1
2024 | Region III | BULACAN | PANDI (BULACAN) | P00845805LZ | Construction of Slope Protection Structure | 120.9224 | 14.8579 | 98999999.32 | 98999713.4 | 2024 | TOPNOTCH CATALYST BUILDERS INC. / ONE FRAME CONSTRUCTION INC. | 2458 | 2024 | 2024-11-29 | 04/23/2024 | 285.92 | 0 | 2025-01-16 | 48
2024 | Region III | NUEVA ECIJA | TALAVERA (NUEVA ECIJA) | P00823475LZ | Construction of Flood Mitigation Structure | 120.9304 | 15.6401 | 19300000 | 19106668.98 | 2024 | BRYAN PAUL P. PACHECO CONST. CORP. | 2459 | 2024 | 2024-07-31 | 03/04/2024 | 193331.02 | 0 | 2024-07-30 |  | 1
2023 | Region III | BULACAN | CITY OF BALIUAG (BULACAN) | P00727357LZ | Construction of Flood Mitigation Structure | 120.8981 | 14.9419 | 48999213.44 | 48999068.63 | 2023 | CEDAR CONSTRUCTION | 2460 | 2023 | 2023-07-18 | 03/07/2023 | 144.81 | 0 | 2023-10-31 | 105
2023 | Region III | BULACAN | CITY OF MALOLOS (CAPITAL) (BULACAN) | P00726159LZ | Construction of Flood Mitigation Structure | 120.823 | 14.8192 | 48999711.67 | 48999979.94 | 2023 | M.G. FRANCISCO CONSTRUCTION | 2461 | 2023 | 2023-06-05 | 02/06/2023 | 0 | 268.27 | 2023-10-02 | 119
2021 | Region IV-B | OCCIDENTAL MINDORO |  | P00561805LZ | Construction of Flood Mitigation Structure | 120.7875 | 12.9599 | 19800000 | 18802621.46 | 2022 | JRMX CONSTRUCTION & GENERAL MERCHANDISE | 2462 | 2021 | 2022-10-20 | 03/22/2021 | 997378.54 | 0 | 2022-01-31 |  | 262
2023 | Region III | BULACAN | CITY OF BALIUAG (BULACAN) | P00736010LZ | Construction of Slope Protection Structure | 120.8903 | 14.9748 | 38599729.27 | 38599056.57 | 2023 | JUSTBILT BUILDERS | 2463 | 2023 | 2023-06-22 | 02/13/2023 | 672.7 | 0 | 2023-10-09 | 109
2023 | Region III | BULACAN | CITY OF BALIUAG (BULACAN) | P00740340LZ | Construction of Flood Mitigation Structure | 120.8903 | 14.9748 | 72374988.4 | 72374149.96 | 2023 | ST. MATTHEW GEN. CONTRACTOR & DEVELOPMENT CORP. | 2464 | 2023 | 2023-12-12 | 03/28/2023 | 838.44 | 0 | 2023-12-21 | 9
2024 | Region III | NUEVA ECIJA | SANTO DOMINGO (NUEVA ECIJA) | P00820273LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.8903 | 15.5568 | 96500000 | 95523979.74 | 2024 | AMP 723 CONSTRUCTION CORPORATION (FORMERLY: A.M.P. CONSTRUCTION) / KEVIN PAUL CONSTRUCTION | 2465 | 2024 | 2024-08-12 | 02/06/2024 | 976020.26 | 0 | 2024-10-31 | 80
2023 | Region III | BULACAN | CALUMPIT (BULACAN) | P00727127LZ | Construction of Flood Mitigation Structure | 120.7876 | 14.9054 | 39199829.45 | 39192632.83 | 2023 | ST. TIMOTHY CONSTRUCTION CORPORATION | 2466 | 2023 | 2023-08-15 | 02/06/2023 | 7196.62 | 0 | 2023-09-02 | 18
2023 | Region IV-B | OCCIDENTAL MINDORO | RIZAL (OCCIDENTAL MINDORO) | P00726598LZ | Construction of Flood Mitigation Structure | 120.9416 | 12.5161 | 193736209.4 | 193730726.8 | 2023 | ST. MATTHEW GEN. CONTRACTOR & DEVELOPMENT CORP. / D.T. RECIO INCORPORATED | 2467 | 2023 | 2023-12-10 | 04/13/2023 | 5482.6 | 0 | 2024-04-05 | 117
2022 | Region III | BULACAN | CITY OF MEYCAUAYAN (BULACAN) | P00639347LZ | Construction of Flood Mitigation Structure | 120.9309 | 14.7348 | 96499091.88 | 96497603.14 | 2023 | L.R. TIQUI BUILDERS, INC. | 2468 | 2022 | 2023-07-31 | 06/09/2022 | 1488.74 | 0 | 2023-07-30 |  | 1
2024 | Region III | BULACAN | CITY OF MALOLOS (CAPITAL) (BULACAN) | P00845985LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.8231 | 14.8145 | 74249963.15 | 74248363.79 | 2024 | DMLC BUILDERS | 2469 | 2024 | 2024-11-12 | 04/02/2024 | 1599.36 | 0 | 2024-11-26 | 14
2022 | Region III | BULACAN | PANDI (BULACAN) | P00632696LZ | Construction of Flood Mitigation Structure | 120.9226 | 14.8416 | 59399331.24 | 59396408.04 | 2022 | TOPNOTCH CATALYST BUILDERS INC. | 2470 | 2022 | 2022-11-01 | 03/07/2022 | 2923.2 | 0 | 2022-10-31 |  | 1
2023 | Region III | NUEVA ECIJA | CITY OF GAPAN (NUEVA ECIJA) | P00727304LZ | Construction of Flood Mitigation Structure | 120.9417 | 15.3093 | 96499989.02 | 96499920 | 2023 | DGSARM BUILDERS INC. (FORMERLY: D.G. SARMENTA CONSTRUCTION) | 2471 | 2023 | 2023-08-24 | 03/27/2023 | 69.02 | 0 | 2024-01-13 | 142
2024 | Region III | BULACAN | BUSTOS (BULACAN) | P00825068LZ | Construction of Flood Mitigation Structure | 120.8982 | 14.9383 | 77199954.28 | 77198882.23 | 2024 | A.R.L. CONSTRUCTION | 2472 | 2024 | 2024-11-27 | 04/23/2024 | 1072.05 | 0 | 2024-12-17 | 20
2023 | Region IV-A | CAVITE | IMUS CITY (CAVITE) | P00725805LZ | Construction of Revetment | 120.9309 | 14.3876 | 91675000 | 91675000 | 2023 | MONTADEL ENTERPRISES | 2473 | 2023 | 2023-11-14 | 02/19/2023 | 0 | 0 | 2023-11-13 |  | 1
2022 | Region III | NUEVA ECIJA | QUEZON (NUEVA ECIJA) | P00632832LZ | Construction of Flood Mitigation Structure | 120.8231 | 15.5709 | 11760000 | 11760000 | 2022 | R.A. PAHATI CONST. & SUPPLY, INC. | 2474 | 2022 | 2022-12-12 | 02/17/2022 | 0 | 0 | 2022-12-11 |  | 1
2022 | Region III | BULACAN | BALAGTAS (BIGAA) (BULACAN) | P00639350LZ | Construction of Slope Protection Structure | 120.9228 | 14.8554 | 57899762.54 | 57899969.25 | 2023 | 729 CONSTRUCTION, INC. (FORMERLY 722 CONSTRUCTION, INC.) | 2475 | 2022 | 2023-02-27 | 04/04/2022 | 0 | 206.71 | 2023-02-26 |  | 1
2024 | Region I | ILOCOS NORTE | PAGUDPUD (ILOCOS NORTE) | P00844700LZ | Construction of Flood Mitigation Structure | 120.7879 | 18.5705 | 48999920.64 | 48999907.06 | 2024 | NORTH TECH BUILDERS AND CONSTRUCTION SUPPLY / RED JEWEL BUILDERS | 2476 | 2024 | 2024-08-19 | 02/23/2024 | 13.58 | 0 | 2024-09-09 | 21
2021 | Cordillera Administrative Region | BENGUET |  | P00525907LZ | Construction of Flood Mitigation Structure | 120.788 | 16.7879 | 29400000 | 23831587.47 | 2022 | MALCO CONSTRUCTION | 2477 | 2021 | 2022-12-14 | 01/16/2022 | 5568412.53 | 0 | 2022-12-13 |  | 1
2024 | Region III | BULACAN | BALAGTAS (BIGAA) (BULACAN) | P00838378LZ | Construction of Slope Protection Structure | 120.8982 | 14.8136 | 96499973.3 | 96499958.97 | 2024 | JB CONSTRUCTION AND SUPPLY INC. (FORMERLY:JB CONSTRUCTION AND SUPPLY) | 2478 | 2024 | 2024-09-18 | 02/07/2024 | 14.33 | 0 | 2024-11-01 | 44
2023 | Region IV-A | CAVITE | BACOOR CITY (CAVITE) | P00726754LZ | Construction of Revetment | 120.931 | 14.4428 | 47529993.16 | 47518195.33 | 2023 | AARCON BUILDERS | 2479 | 2023 | 2023-10-12 | 02/15/2023 | 11797.83 | 0 | 2023-10-11 |  | 1
2024 | Region III | BULACAN | PLARIDEL (BULACAN) | P00825072LZ | Construction of Flood Mitigation Structure | 120.8907 | 14.9211 | 77199945.38 | 77199815.33 | 2024 | TOPNOTCH CATALYST BUILDERS INC. | 2480 | 2024 | 2024-08-02 | 04/23/2024 | 130.05 | 0 | 2024-12-17 | 137
2023 | Region IV-A | BATANGAS | AGONCILLO (BATANGAS) | P00746107LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.9419 | 13.9449 | 3667000 | 3666700 | 2024 | NDA BUILDERS AND DEVELOPERS | 2481 | 2023 | 2024-04-03 | 01/05/2024 | 300 | 0 | 2024-04-02 |  | 1
2024 | Region III | BULACAN | BUSTOS (BULACAN) | P00843320LZ | Construction of Flood Mitigation Structure | 120.8983 | 14.931 | 77199978.44 | 77199023.96 | 2024 | TOPNOTCH CATALYST BUILDERS INC. | 2482 | 2024 | 2024-06-24 | 04/16/2024 | 954.48 | 0 | 2024-12-10 | 169
2024 | Region III | BULACAN | CALUMPIT (BULACAN) | P00820244LZ | Construction of Revetment | 120.7881 | 14.9004 | 57899980.17 | 57892233.56 | 2024 | PTM DEVELOPMENT CORP. | 2483 | 2024 | 2024-08-08 | 02/07/2024 | 7746.61 | 0 | 2024-09-02 | 25
2022 | Region III | NUEVA ECIJA | QUEZON (NUEVA ECIJA) | P00632833LZ | Construction of Flood Mitigation Structure | 120.8233 | 15.5708 | 11760000 | 11431950.66 | 2022 | R.A. PAHATI CONST. & SUPPLY, INC. | 2484 | 2022 | 2022-12-12 | 02/17/2022 | 328049.34 | 0 | 2022-12-11 |  | 1
2023 | Region III | BULACAN | BALAGTAS (BIGAA) (BULACAN) | P00726479LZ | Construction of Flood Mitigation Structure | 120.9228 | 14.8564 | 96499523.36 | 96496501.75 | 2023 | A.R.L. CONSTRUCTION | 2485 | 2023 | 2023-09-01 | 02/13/2023 | 3021.61 | 0 | 2023-12-08 | 98
2023 | Region III | BULACAN | CITY OF MALOLOS (CAPITAL) (BULACAN) | P00742134LZ | Construction of Slope Protection Structure | 120.8234 | 14.8171 | 74249789.19 | 74249313.37 | 2023 | TOPNOTCH CATALYST BUILDERS INC. / BLACK HARDHAT INC. (FORMERLY: JCHARDHAT INC.) | 2486 | 2023 | 2023-12-06 | 03/28/2023 | 475.82 | 0 | 2024-01-20 | 45
2023 | Region III | BULACAN | PAOMBONG (BULACAN) | P00740373LZ | Construction of Flood Mitigation Structure | 120.7885 | 14.8273 | 77199922.45 | 77197446.53 | 2023 | WAWAO BUILDERS | 2487 | 2023 | 2023-12-27 | 03/28/2023 | 2475.92 | 0 | 2024-01-20 | 24
2023 | Region III | PAMPANGA | CANDABA (PAMPANGA) | P00726914LZ | Construction of Slope Protection Structure | 120.8908 | 15.0366 | 72375000 | 68321554.89 | 2024 | STO. CRISTO CONSTRUCTION & TRADING INC. (FOR: STO. CRISTO CONSTRUCTION & TRADING) | 2488 | 2023 | 2024-01-25 | 04/20/2023 | 4053445.11 | 0 | 2024-01-24 |  | 1
2023 | Region IV-A | BATANGAS | TAAL (BATANGAS) | P00737490LZ | Construction of Drainage Structure | 120.9311 | 13.8927 | 5938760 | 5938760 | 2023 | RICH ADS CONSTRUCTION CORP. (FORMERLY RICH ADS CON | 2489 | 2023 | 2023-06-21 | 03/24/2023 | 0 | 0 | 2023-06-20 |  | 1
2022 | Region III | BULACAN | PAOMBONG (BULACAN) | P00631198LZ | Construction of Slope Protection Structure | 120.7887 | 14.8273 | 44099219.73 | 44099245.32 | 2022 | J. SIMEON CONSTRUCTION | 2490 | 2022 | 2022-09-24 | 01/28/2022 | 0 | 25.59 | 2022-09-23 |  | 1
2022 | National Capital Region | MALABON CITY | CITY OF MALABON (METROPOLITAN MANILA) | P00620351LZ | Construction of Flood Mitigation Structure | 120.9228 | 14.6976 | 48904843.78 | 49000000 | 2022 | B. BERNARDO CONST., INC. | 2491 | 2022 | 2022-11-16 | 02/14/2022 | 0 | 95156.22 | 2022-11-24 | 8
2023 | Region III | BULACAN | BALAGTAS (BIGAA) (BULACAN) | P00736014LZ | Construction of Slope Protection Structure | 120.8984 | 14.8076 | 48249571.88 | 48248648.06 | 2023 | TOPNOTCH CATALYST BUILDERS INC. | 2492 | 2023 | 2023-10-10 | 02/13/2023 | 923.82 | 0 | 2023-11-08 | 29
2023 | Region IV-A | CAVITE | IMUS CITY (CAVITE) | P00725804LZ | Construction of Dike | 120.9311 | 14.3844 | 91675000 | 91675000 | 2024 | R2A CONSTRUCTION & TRADING CORPORATION | 2493 | 2023 | 2024-01-13 | 02/19/2023 | 0 | 0 | 2024-01-12 |  | 1
2023 | Region III | BULACAN | BALAGTAS (BIGAA) (BULACAN) | P00726491LZ | Construction of Flood Mitigation Structure | 120.8985 | 14.8037 | 96499396.54 | 96499913.18 | 2023 | AZUL BUILDERS / JB CONSTRUCTION AND SUPPLY INC. (FORMERLY:JB CONSTRUCTION AND SUPPLY) | 2494 | 2023 | 2023-08-22 | 02/13/2023 | 0 | 516.64 | 2023-12-08 | 108
2021 | Region III | BULACAN |  | P00561468LZ | Construction of Flood Mitigation Structure | 120.9228 | 14.8404 | 144749403.6 | 142350971.2 | 2023 | PERRC INC. (FORMERLY: P.E.R.R.C. CONSTRUCTION & DEVELOPMENT CORPORATION) | 2495 | 2021 | 2023-12-05 | 11/29/2021 | 2398432.4 | 0 | 2023-12-04 |  | 1
2024 | National Capital Region | MALABON CITY | CITY OF MALABON (METROPOLITAN MANILA) | P00839457LZ | Construction of Flood Mitigation Structure | 120.9419 | 14.6826 | 69298188.53 | 69298883.78 | 2024 | AMETHYST HORIZON BUILDERS AND GEN. CONTRACTOR AND DEVELOPMENT CORP. | 2496 | 2024 | 2024-10-21 | 02/21/2024 | 0 | 695.25 | 2024-12-15 | 55
2021 | Region I | ILOCOS NORTE |  | P00561449LZ | Construction of Flood Mitigation Structure | 120.7887 | 18.5903 | 96499801.86 | 96499801.28 | 2022 | FR ESPIRITU BUILDERS AND DEVELOPMENT CORP. (FORMERLY: FR ESPIRITU JR BUILDERS) | 2497 | 2021 | 2022-09-05 | 12/24/2021 | 0.58 | 0 | 2022-10-01 | 26
2023 | Region III | BULACAN | CITY OF MALOLOS (CAPITAL) (BULACAN) | P00742156LZ | Construction of Flood Mitigation Structure | 120.8234 | 14.8171 | 69299956.56 | 69288166.96 | 2024 | JTC CRUZ CONSTRUCTION CO., INC. | 2498 | 2023 | 2024-01-21 | 03/28/2023 | 11789.6 | 0 | 2024-01-20 |  | 1
2024 | Region III | BULACAN | BOCAUE (BULACAN) | P00845973LZ | Construction of Drainage Structure | 120.9229 | 14.801 | 24749834.81 | 24749402.32 | 2024 | 121 CONSTRUCTION CORPORATION (FORMERLY 121 CONSTUC | 2499 | 2024 | 2024-07-08 | 03/11/2024 | 432.49 | 0 | 2024-07-07 |  | 1
2022 | National Capital Region | NAVOTAS CITY | CITY OF NAVOTAS (METROPOLITAN MANILA) | P00621270LZ | Construction of Flood Mitigation Facility | 120.942 | 14.6597 | 96483205.69 | 96499355.46 | 2023 | EIGHT J'S CONSTRUCTION SERVICES | 2500 | 2022 | 2023-03-13 | 03/24/2022 | 0 | 16149.77 | 2023-05-16 | 64
2022 | Region III | BULACAN | BALAGTAS (BIGAA) (BULACAN) | P00620518LZ | Construction of Flood Mitigation Structure | 120.8986 | 14.8166 | 48999809.79 | 47039817.09 | 2022 | M.C.J. VALENZUELA CONSTRUCTION ENTERPRISES | 2501 | 2022 | 2022-09-24 | 01/28/2022 | 1959992.7 | 0 | 2022-09-23 |  | 1
2023 | Region IV-A | CAVITE | BACOOR CITY (CAVITE) | P00726558LZ | Construction of Revetment | 120.9312 | 14.4461 | 96499995.54 | 96458053.16 | 2024 | GRAIA CONSTRUCTION CORPORATION | 2502 | 2023 | 2024-03-31 | 03/08/2023 | 41942.38 | 0 | 2024-03-30 |  | 1
2022 | National Capital Region | VALENZUELA CITY | CITY OF VALENZUELA (METROPOLITAN MANILA) | P00620412LZ | Construction of Flood Mitigation Structure | 120.9312 | 14.7337 | 21544226.33 | 20898647.14 | 2022 | J. SIMEON CONSTRUCTION | 2503 | 2022 | 2022-09-15 | 02/08/2022 | 645579.19 | 0 | 2022-11-03 | 49
2023 | Region III | BULACAN | BALAGTAS (BIGAA) (BULACAN) | P00726481LZ | Construction of Flood Mitigation Structure | 120.8986 | 14.8159 | 96499879.6 | 96499702 | 2023 | A.R.L. CONSTRUCTION | 2504 | 2023 | 2023-12-09 | 02/13/2023 | 177.6 | 0 | 2023-12-08 |  | 1
2022 | Region IV-A | CAVITE | CITY OF GENERAL TRIAS (CAVITE) | P00621583LZ | Construction of Revetment | 120.8909 | 14.3134 | 144750000 | 144733536.2 | 2023 | L.R. TIQUI BUILDERS, INC. | 2505 | 2022 | 2023-12-28 | 01/10/2023 | 16463.8 | 0 | 2023-12-30 | 2
2021 | Cordillera Administrative Region | BENGUET |  | P00525909LZ | Construction of Flood Mitigation Structure | 120.7891 | 16.8416 | 9800000 | 9750603.31 | 2022 | DONATO - SAKIWAT CONSTRUCTION | 2506 | 2021 | 2022-07-02 | 01/16/2022 | 49396.69 | 0 | 2022-07-01 |  | 1
2023 | National Capital Region | VALENZUELA CITY | CITY OF VALENZUELA (METROPOLITAN MANILA) | P00725992LZ | Construction of Flood Mitigation Structure | 120.9312 | 14.7336 | 44080512.13 | 44100000 | 2023 | J. SIMEON CONSTRUCTION | 2507 | 2023 | 2023-12-17 | 02/21/2023 | 0 | 19487.87 | 2023-12-16 |  | 1
2023 | Region III | BULACAN | BALAGTAS (BIGAA) (BULACAN) | P00726490LZ | Construction of Flood Mitigation Structure | 120.8988 | 14.8165 | 96499429.13 | 96497777.93 | 2023 | AZUL BUILDERS / JB CONSTRUCTION AND SUPPLY INC. (FORMERLY:JB CONSTRUCTION AND SUPPLY) | 2508 | 2023 | 2023-08-22 | 02/13/2023 | 1651.2 | 0 | 2023-12-08 | 108
2023 | Region III | BULACAN | CITY OF BALIUAG (BULACAN) | P00737453LZ | Construction of Drainage Structure | 120.891 | 14.9673 | 4949493.42 | 4836095.72 | 2023 | TBB CONSTRUCTION CORP. | 2509 | 2023 | 2023-04-04 | 02/06/2023 | 113397.7 | 0 | 2023-07-04 | 91
2022 | Cordillera Administrative Region | BENGUET | BUGUIAS (BENGUET) | P00620477LZ | Construction of Flood Mitigation Structure | 120.8238 | 16.7149 | 24500000 | 24469548.92 | 2022 | BTCJR CONSTRUCTION AND ENGINEERING SERVICES | 2510 | 2022 | 2022-11-24 | 04/12/2022 | 30451.08 | 0 | 2022-12-11 | 17
2024 | Region III | BULACAN | PLARIDEL (BULACAN) | P00825073LZ | Construction of Flood Mitigation Structure | 120.891 | 14.9192 | 77199968.98 | 77199805.7 | 2024 | TBB CONSTRUCTION CORP. | 2511 | 2024 | 2024-08-13 | 04/23/2024 | 163.28 | 0 | 2024-12-17 | 126
2024 | Region III | BULACAN | PANDI (BULACAN) | P00845789LZ | Construction of Slope Protection Structure | 120.923 | 14.8564 | 98999851.21 | 98999508.95 | 2025 | TOPNOTCH CATALYST BUILDERS INC. / ONE FRAME CONSTRUCTION INC. | 2512 | 2024 | 2025-01-02 | 04/23/2024 | 342.26 | 0 | 2025-01-16 | 14
2023 | Region III | BULACAN | BALAGTAS (BIGAA) (BULACAN) | P00726482LZ | Construction of Flood Mitigation Structure | 120.899 | 14.8074 | 96499358.66 | 96499923.27 | 2023 | A.R.L. CONSTRUCTION | 2513 | 2023 | 2023-12-04 | 02/13/2023 | 0 | 564.61 | 2023-12-08 | 4
2023 | Region I | ILOCOS NORTE | PAGUDPUD (ILOCOS NORTE) | P00725629LZ | Construction of Flood Mitigation Structure | 120.7893 | 18.5773 | 58799849.67 | 57899998.85 | 2023 | MEGAPOLITAN BUILDERS AND CONSTRUCTION SUPPLY | 2514 | 2023 | 2023-11-17 | 03/13/2023 | 899850.82 | 0 | 2023-12-07 | 20
2022 | National Capital Region | NAVOTAS CITY | CITY OF NAVOTAS (METROPOLITAN MANILA) | P00621271LZ | Construction of Flood Mitigation Facility | 120.942 | 14.6597 | 96491043.33 | 96499715.98 | 2023 | EIGHT J'S CONSTRUCTION SERVICES | 2515 | 2022 | 2023-03-13 | 03/24/2022 | 0 | 8672.65 | 2023-05-16 | 64
2024 | Region III | NUEVA ECIJA | LICAB (NUEVA ECIJA) | P00820277LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.7897 | 15.4962 | 96500000 | 95534944.05 | 2024 | AMP 723 CONSTRUCTION CORPORATION (FORMERLY: A.M.P. CONSTRUCTION) / BRYAN PAUL P. PACHECO CONST. CORP. | 2516 | 2024 | 2024-10-10 | 02/06/2024 | 965055.95 | 0 | 2024-10-31 | 21
2022 | National Capital Region | VALENZUELA CITY | CITY OF VALENZUELA (METROPOLITAN MANILA) | P00620081LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.9313 | 14.7314 | 91655826.07 | 89832638.99 | 2023 | J. SIMEON CONSTRUCTION | 2517 | 2022 | 2023-02-10 | 02/11/2022 | 1823187.08 | 0 | 2023-02-04 |  | 6
2023 | Region III | BULACAN | PAOMBONG (BULACAN) | P00740372LZ | Construction of Flood Mitigation Structure | 120.7902 | 14.8246 | 77199940.5 | 77198857.79 | 2024 | GREAT PACIFIC BUILDERS AND GEN. CONTRACTOR INC. | 2518 | 2023 | 2024-01-21 | 03/28/2023 | 1082.71 | 0 | 2024-01-20 |  | 1
2024 | Region III | NUEVA ECIJA | SANTO DOMINGO (NUEVA ECIJA) | P00844538LZ | Construction of Drainage Structure | 120.8915 | 15.5942 | 4825000 | 4776807.36 | 2024 | R.S.C. CONSTRUCTION SERVICES | 2519 | 2024 | 2024-08-12 | 06/14/2024 | 48192.64 | 0 | 2024-08-11 |  | 1
2024 | Region III | BULACAN | PANDI (BULACAN) | P00838390LZ | Construction of Slope Protection Structure | 120.923 | 14.8563 | 96499815.35 | 96499112.67 | 2024 | TOPNOTCH CATALYST BUILDERS INC. | 2520 | 2024 | 2024-10-16 | 02/07/2024 | 702.68 | 0 | 2024-11-01 | 16
2022 | Cordillera Administrative Region | ABRA | DAGUIOMAN (ABRA) | P00620986LZ | Construction of Flood Mitigation Structure | 120.8991 | 17.4489 | 48999938.86 | 48997987.95 | 2022 | A.D. MARRERO GENERAL CONSTRUCTION | 2521 | 2022 | 2022-07-22 | 02/17/2022 | 1950.91 | 0 | 2022-07-21 |  | 1
2022 | Region III | BULACAN | BALAGTAS (BIGAA) (BULACAN) | P00621451LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.824 | 14.824 | 14699992.17 | 14699022.84 | 2022 | TBB CONSTRUCTION CORP. | 2522 | 2022 | 2022-09-30 | 04/04/2022 | 969.33 | 0 | 2022-09-29 |  | 1
2023 | Region IV-A | CAVITE | BACOOR CITY (CAVITE) | P00725816LZ | Construction of Revetment | 120.942 | 14.4537 | 96499994.4 | 96495747.2 | 2023 | OMNICON BUILDERS | 2523 | 2023 | 2023-11-02 | 02/21/2023 | 4247.2 | 0 | 2024-02-14 | 104
2023 | Region IV-B | OCCIDENTAL MINDORO | SABLAYAN (OCCIDENTAL MINDORO) | P00727375LZ | Construction of Flood Mitigation Structure | 120.8242 | 12.9566 | 45080000 | 45079792.51 | 2023 | SIXTEEN ENTERPRISES-CALAPAN BRANCH | 2524 | 2023 | 2023-11-15 | 03/20/2023 | 207.49 | 0 | 2023-11-15 | 0
2024 | Region III | BULACAN | PLARIDEL (BULACAN) | P00821271LZ | Construction of Slope Protection Structure | 120.8915 | 14.9071 | 72374199.16 | 72373026.04 | 2024 | BELL CONSTRUCTION | 2525 | 2024 | 2024-08-12 | 02/07/2024 | 1173.12 | 0 | 2024-10-02 | 51
2024 | Region III | BULACAN | CITY OF MEYCAUAYAN (BULACAN) | P00820208LZ | Construction of Flood Mitigation Structure | 120.923 | 14.7395 | 67549591.85 | 67549934.92 | 2025 | A.C. SOLIVEN CONSTRUCTION & GENERAL MERCHANDISE | 2526 | 2024 | 2025-01-08 | 02/14/2024 | 0 | 343.07 | 2025-01-07 |  | 1
2023 | Region IV-A | CAVITE | IMUS CITY (CAVITE) | P00726210LZ | Construction of Revetment | 120.9314 | 14.3973 | 49000000 | 49000000 | 2023 | FROMARC BUILDERS & GEN. MERCHANDISE | 2527 | 2023 | 2023-09-21 | 02/19/2023 | 0 | 0 | 2023-09-20 |  | 1
2023 | Region III | BULACAN | PAOMBONG (BULACAN) | P00740593LZ | Construction of Flood Mitigation Structure | 120.7903 | 14.8445 | 48999861.74 | 48999664.71 | 2023 | YPR GEN. CONTRACTOR AND CONSTRUCTION SUPPLY INC. | 2528 | 2023 | 2023-11-15 | 03/21/2023 | 197.03 | 0 | 2023-11-14 |  | 1
2022 | Region IV-A | BATANGAS | LAUREL (BATANGAS) | P00620001LZ | Construction of Flood Mitigation Structure | 120.942 | 14.0499 | 39200000 | 39197310 | 2022 | GAWANATO CONSTRUCTION CORPORATION / N.D.M. SANCHEZ BUILDERS & DEVELOPMENT CORPORATION | 2529 | 2022 | 2022-11-11 | 02/23/2022 | 2690 | 0 | 2022-11-28 | 17
2023 | Region III | BULACAN | BALAGTAS (BIGAA) (BULACAN) | P00726489LZ | Construction of Flood Mitigation Structure | 120.8991 | 14.8154 | 96499574.6 | 96499467.81 | 2023 | AZUL BUILDERS / JB CONSTRUCTION AND SUPPLY INC. (FORMERLY:JB CONSTRUCTION AND SUPPLY) | 2530 | 2023 | 2023-08-22 | 02/13/2023 | 106.79 | 0 | 2023-12-08 | 108
2022 | Region I | ILOCOS NORTE | VINTAR (ILOCOS NORTE) | P00639415LZ | Construction of Flood Mitigation Structure | 120.792 | 18.3066 | 48999333.79 | 48346397.71 | 2022 | ASIAN PEARL CONSTRUCTION & DEVT. CORP. | 2531 | 2022 | 2022-12-19 | 04/04/2022 | 652936.08 | 0 | 2022-12-19 | 0
2023 | Region III | NUEVA ECIJA | CITY OF GAPAN (NUEVA ECIJA) | P00727305LZ | Construction of Flood Mitigation Structure | 120.9422 | 15.3096 | 96499970.57 | 96499967.4 | 2023 | R.A. PAHATI CONST. & SUPPLY, INC. / N.C. AGUILAR CONST. & SUPPLY INC. | 2532 | 2023 | 2023-06-13 | 03/24/2023 | 3.17 | 0 | 2024-01-10 | 211
2024 | Region IV-A | CAVITE | IMUS CITY (CAVITE) | P00820344LZ | Construction of Flood Mitigation Structure | 120.9314 | 14.3735 | 96500000 | 96500000 | 2024 | TRIPLE 8 CONSTRUCTION & SUPPLY, INC. (FORMERLY TRIPLE 8 CONST. & SUPPLY) | 2533 | 2024 | 2024-12-06 | 03/05/2024 | 0 | 0 | 2024-12-05 |  | 1
2023 | Region III | BULACAN | PULILAN (BULACAN) | P00736004LZ | Construction of Revetment | 120.8916 | 14.9082 | 28949608.55 | 28949154.09 | 2023 | MICHARIAN BUILDERS AND TRADING | 2534 | 2023 | 2023-05-16 | 02/13/2023 | 454.46 | 0 | 2023-09-09 | 116
2024 | Region III | BULACAN | BOCAUE (BULACAN) | P00845974LZ | Construction of Drainage Structure | 120.9232 | 14.799 | 4949682.88 | 4949180.63 | 2024 | 121 CONSTRUCTION CORPORATION (FORMERLY 121 CONSTUC | 2535 | 2024 | 2024-06-03 | 03/11/2024 | 502.25 | 0 | 2024-07-07 | 34
2022 | National Capital Region | MALABON CITY | CITY OF MALABON (METROPOLITAN MANILA) | P00620011LZ | Construction of Flood Mitigation Structure | 120.9422 | 14.6725 | 92104372.56 | 90661657.44 | 2023 | NEWBIG FOUR J CONSTRUCTION INC., (FORMERLY FOUR J | 2536 | 2022 | 2023-02-15 | 02/21/2022 | 1442715.12 | 0 | 2023-02-14 |  | 1
2022 | Cordillera Administrative Region | BENGUET | KABAYAN (BENGUET) | P00620996LZ | Construction of Flood Mitigation Structure | 120.825 | 16.6705 | 24500000 | 24447245.69 | 2022 | CABUGUIASAN BUILDERS | 2537 | 2022 | 2022-07-29 | 01/31/2022 | 52754.31 | 0 | 2022-08-04 | 6
2024 | Region III | BULACAN | OBANDO (BULACAN) | P00825085LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.9233 | 14.7373 | 96499964.52 | 96499915.95 | 2024 | JB CONSTRUCTION AND SUPPLY INC. (FORMERLY:JB CONSTRUCTION AND SUPPLY) | 2538 | 2024 | 2024-11-26 | 04/22/2024 | 48.57 | 0 | 2024-11-27 | 1
2023 | Region III | BULACAN | PLARIDEL (BULACAN) | P00726465LZ | Construction of Flood Mitigation Structure | 120.8916 | 14.9069 | 96499724.83 | 96498661.72 | 2023 | IM CONSTRUCTION CORPORATION | 2539 | 2023 | 2023-05-24 | 02/13/2023 | 1063.11 | 0 | 2023-12-08 | 198
2024 | Region III | NUEVA ECIJA | CITY OF GAPAN (NUEVA ECIJA) | P00825057LZ | Construction of Flood Mitigation Structure | 120.9315 | 15.3065 | 96499992.23 | 94569740.12 | 2024 | AMP 723 CONSTRUCTION CORPORATION (FORMERLY: A.M.P. CONSTRUCTION) / R.G. DELA CRUZ CONSTRUCTION | 2540 | 2024 | 2024-06-18 | 04/02/2024 | 1930252.11 | 0 | 2025-01-19 | 215
2023 | Region I | ILOCOS NORTE | BANGUI (ILOCOS NORTE) | P00740550LZ | Construction of Flood Mitigation Structure | 120.792 | 18.529 | 16169715.39 | 16169714.94 | 2023 | ZEDIK BUILDERS | 2541 | 2023 | 2023-09-20 | 05/05/2023 | 0.45 | 0 | 2023-10-18 | 28
2023 | Region III | BULACAN | PAOMBONG (BULACAN) | P00736006LZ | Construction of Revetment | 120.7926 | 14.8219 | 28949821.3 | 28949739.38 | 2023 | EL KAPITAN CONSTRUCTION SERVICES | 2542 | 2023 | 2023-05-29 | 02/13/2023 | 81.92 | 0 | 2023-09-09 | 103
2021 | Region IV-B | OCCIDENTAL MINDORO |  | P00526447LZ | Construction of Flood Mitigation Structure | 120.8253 | 12.9575 | 44100000 | 40925466.93 | 2022 | DELPAR CONSTRUCTION & SUPPLIES | 2543 | 2021 | 2022-08-22 | 03/22/2021 | 3174533.07 | 0 | 2022-02-21 |  | 182
2022 | Region III | BULACAN | PANDI (BULACAN) | P00632697LZ | Construction of Flood Mitigation Structure | 120.9235 | 14.8396 | 69299553.79 | 69295690.87 | 2022 | TOPNOTCH CATALYST BUILDERS INC. | 2544 | 2022 | 2022-11-20 | 02/24/2022 | 3862.92 | 0 | 2022-11-19 |  | 1
2024 | Region III | NUEVA ECIJA | ALIAGA (NUEVA ECIJA) | P00820278LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.8994 | 15.5521 | 96500000 | 95525406.04 | 2024 | AMP 723 CONSTRUCTION CORPORATION (FORMERLY: A.M.P. CONSTRUCTION) / RPP 928 CONSTRUCTION CORPORATION | 2545 | 2024 | 2024-08-12 | 02/06/2024 | 974593.96 | 0 | 2024-10-31 | 80
2022 | Cordillera Administrative Region | ABRA | LACUB (ABRA) | P00632758LZ | Construction of Flood Mitigation Structure | 120.9423 | 17.6652 | 48999991.34 | 46607719.18 | 2022 | ST. TIMOTHY CONSTRUCTION CORPORATION | 2546 | 2022 | 2022-09-03 | 03/01/2022 | 2392272.16 | 0 | 2022-09-02 |  | 1
2023 | Region III | BULACAN | CITY OF BALIUAG (BULACAN) | P00727359LZ | Construction of Flood Mitigation Structure | 120.8996 | 14.9429 | 48999213.44 | 48999152.97 | 2023 | CEDAR CONSTRUCTION | 2547 | 2023 | 2023-09-20 | 03/07/2023 | 60.47 | 0 | 2023-10-31 | 41
2023 | Region III | NUEVA ECIJA | CABIAO (NUEVA ECIJA) | P00726735LZ | Construction of Flood Mitigation Structure | 120.8261 | 15.2481 | 29399953.8 | 28666092.37 | 2023 | D.B. BARAQUIEL CONSTRUCTION | 2548 | 2023 | 2023-08-18 | 02/07/2023 | 733861.43 | 0 | 2023-08-16 |  | 2
2023 | Region IV-B | OCCIDENTAL MINDORO | SABLAYAN (OCCIDENTAL MINDORO) | P00736045LZ | Construction of Revetment | 120.7926 | 12.9585 | 217125000 | 217120406.7 | 2024 | SUNWEST, INC. (FORMERLY: SUNWEST CONSTRUCTION & DEVELOPMENT CORPORATION) | 2549 | 2023 | 2024-03-25 | 02/11/2023 | 4593.3 | 0 | 2024-03-25 | 0
2022 | Region III | BULACAN | BALAGTAS (BIGAA) (BULACAN) | P00621532LZ | Construction of Flood Mitigation Structure | 120.9236 | 14.8373 | 24499898.64 | 24498166.71 | 2022 | WBX CONSTRUCTION, INC (FORMERLY WBX CONSTRUCTION) | 2550 | 2022 | 2022-11-22 | 04/04/2022 | 1731.93 | 0 | 2022-11-28 | 6
2023 | Cordillera Administrative Region | MOUNTAIN PROVINCE | BAUKO (MOUNTAIN PROVINCE) | P00726413LZ | Construction of Flood Mitigation Structure | 120.8917 | 16.86 | 86849999.4 | 86850000 | 2023 | OLSIM CONSTRUCTION / RODEKOM GENERAL CONSTRUCTION AND ENTERPRISE | 2551 | 2023 | 2023-11-28 | 05/24/2023 | 0 | 0.6 | 2024-01-02 | 35
2024 | Region III | BULACAN | PAOMBONG (BULACAN) | P00844743LZ | Construction of Revetment | 120.7927 | 14.8219 | 27633051.33 | 26533190.34 | 2024 | TOUGHBILT CONSTRUCTION & TRADING, INC. | 2552 | 2024 | 2024-08-16 | 04/18/2024 | 1099860.99 | 0 | 2024-09-13 | 28
2023 | Region IV-A | BATANGAS | LAUREL (BATANGAS) | P00725803LZ | Construction of Flood Mitigation Structure | 120.9316 | 14.047 | 67550000 | 67549500 | 2023 | V.R. PATRON BUILDERS & DEVELOPERS CORP. (PREVIOUSL | 2553 | 2023 | 2023-12-12 | 03/07/2023 | 500 | 0 | 2023-12-30 | 18
2024 | Region III | BULACAN | CITY OF BALIUAG (BULACAN) | P00838406LZ | Construction of Slope Protection Structure | 120.8918 | 14.9654 | 72374960.15 | 72374181.8 | 2024 | FERDSTAR BUILDERS INC. | 2554 | 2024 | 2024-09-18 | 02/07/2024 | 778.35 | 0 | 2024-10-02 | 14
2024 | Region III | BULACAN | PANDI (BULACAN) | P00845793LZ | Construction of Slope Protection Structure | 120.9236 | 14.8442 | 98999815.9 | 98998994.07 | 2025 | TOPNOTCH CATALYST BUILDERS INC. / ONE FRAME CONSTRUCTION INC. | 2555 | 2024 | 2025-01-08 | 04/23/2024 | 821.83 | 0 | 2025-01-16 | 8
2022 | National Capital Region | MALABON CITY | CITY OF MALABON (METROPOLITAN MANILA) | P00631014LZ | Construction of Flood Mitigation Facility | 120.9423 | 14.6725 | 19599988.16 | 19598678.11 | 2022 | AL-REM KONSTRUCT INC. | 2556 | 2022 | 2022-09-12 | 02/15/2022 | 1310.05 | 0 | 2022-09-11 |  | 1
2022 | Region I | PANGASINAN | NATIVIDAD (PANGASINAN) | P00620973LZ | Construction of Revetment | 120.7928 | 16.0669 | 29400000 | 29390746.66 | 2022 | RIVBROS CONSTRUCTION FACTORS & DEVELOPMENT | 2557 | 2022 | 2022-11-30 | 02/24/2022 | 9253.34 | 0 | 2022-08-11 |  | 111
2023 | Region III | BULACAN | BALAGTAS (BIGAA) (BULACAN) | P00726480LZ | Construction of Flood Mitigation Structure | 120.8998 | 14.805 | 96499429.13 | 96499347.85 | 2023 | A.R.L. CONSTRUCTION | 2558 | 2023 | 2023-12-09 | 02/13/2023 | 81.28 | 0 | 2023-12-08 |  | 1
2024 | Region III | BULACAN | CITY OF MEYCAUAYAN (BULACAN) | P00825065LZ | Construction of Flood Mitigation Structure | 120.9317 | 14.739 | 96499598.17 | 96499747.83 | 2024 | L.R. TIQUI BUILDERS, INC. / 729 CONSTRUCTION, INC. (FORMERLY 722 CONSTRUCTION, INC.) | 2559 | 2024 | 2024-12-06 | 03/18/2024 | 0 | 149.66 | 2024-12-06 | 0
2024 | Cordillera Administrative Region | BENGUET | KABAYAN (BENGUET) | P00821531LZ | Construction of Flood Mitigation Structure | 120.8261 | 16.6569 | 39200000 | 39193427.02 | 2024 | UNIVERSAL DE LEON CONSTRUCTION AND AGGREGATES | 2560 | 2024 | 2024-10-08 | 02/21/2024 | 6572.98 | 0 | 2024-10-07 |  | 1
2023 | Region III | BULACAN | CITY OF BALIUAG (BULACAN) | P00725684LZ | Construction of Revetment | 120.8919 | 14.9735 | 96499834.19 | 96499915.59 | 2023 | M.S. RAMOS CONSTRUCTION INC. (FORMERLY: M.S. RAMOS | 2561 | 2023 | 2023-12-09 | 02/13/2023 | 0 | 81.4 | 2023-12-08 |  | 1
2024 | Region III | BULACAN | BUSTOS (BULACAN) | P00825078LZ | Construction of Flood Mitigation Structure | 120.9 | 14.9424 | 77199992.37 | 77199087.48 | 2024 | SYMS CONSTRUCTION TRADING | 2562 | 2024 | 2024-08-02 | 04/23/2024 | 904.89 | 0 | 2024-12-17 | 137
2024 | Region III | BULACAN | PLARIDEL (BULACAN) | P00825102LZ | Construction of Flood Mitigation Structure | 120.8264 | 14.9036 | 96499940.15 | 96499992.1 | 2024 | WAWAO BUILDERS | 2563 | 2024 | 2024-06-11 | 03/20/2024 | 0 | 51.95 | 2024-12-13 | 185
2022 | National Capital Region | MALABON CITY | CITY OF MALABON (METROPOLITAN MANILA) | P00621132LZ | Construction of Flood Mitigation Structure | 120.9236 | 14.701 | 58789577.78 | 57900000 | 2022 | A.L. SALAZAR CONSTRUCTION, INC. | 2564 | 2022 | 2022-11-18 | 03/24/2022 | 889577.78 | 0 | 2022-11-17 |  | 1
2022 | Region I | ILOCOS NORTE | VINTAR (ILOCOS NORTE) | P00637764LZ | Construction of Flood Mitigation Structure | 120.7931 | 18.3022 | 49499628.27 | 48360631.63 | 2022 | ASIAN PEARL CONSTRUCTION & DEVT. CORP. | 2565 | 2022 | 2022-10-21 | 04/04/2022 | 1138996.64 | 0 | 2022-10-20 |  | 1
2024 | Region IV-A | CAVITE | IMUS CITY (CAVITE) | P00845829LZ | Construction of Flood Mitigation Structure | 120.9317 | 14.4215 | 99000000 | 99000000 | 2024 | MOTIONTRADE DEVELOPMENT CORPORATION / OMNICON BUILDERS | 2566 | 2024 | 2024-12-21 | 03/20/2024 | 0 | 0 | 2024-12-20 |  | 1
2023 | Region IV-B | OCCIDENTAL MINDORO | SABLAYAN (OCCIDENTAL MINDORO) | P00736038LZ | Construction of Dike | 120.827 | 12.9263 | 217124999.5 | 217123478.2 | 2023 | SUNWEST, INC. (FORMERLY: SUNWEST CONSTRUCTION & DEVELOPMENT CORPORATION) | 2567 | 2023 | 2023-12-15 | 02/11/2023 | 1521.3 | 0 | 2024-03-25 | 101
2024 | Region III | NUEVA ECIJA | LUPAO (NUEVA ECIJA) | P00823449LZ | Construction of Flood Mitigation Structure | 120.892 | 15.8022 | 48250000 | 47767657.74 | 2024 | IJK MAE CONSTRUCTION INC. / P.S. AQUINO CONSTRUCTION | 2568 | 2024 | 2024-08-28 | 03/15/2024 | 482342.26 | 0 | 2024-10-09 | 42
2021 | Region III | BULACAN |  | P00526013LZ | Construction of Flood Mitigation Structure | 120.9426 | 15.1059 | 36397195.7 | 36389489.38 | 2022 | EIRISH BUILDERS & SUPPLY INC. | 2569 | 2021 | 2022-08-30 | 03/30/2022 | 7706.32 | 0 | 2022-08-29 |  | 1
2023 | Region IV-A | CAVITE | KAWIT (CAVITE) | P00742419LZ | Construction of Flood Mitigation Structure | 120.9001 | 14.4466 | 41580000 | 41125223.87 | 2023 | ALMAKAR BUILDERS & METAL WORKS | 2570 | 2023 | 2023-12-19 | 03/29/2023 | 454776.13 | 0 | 2023-12-18 |  | 1
2022 | Region IV-A | CAVITE | IMUS CITY (CAVITE) | P00620228LZ | Construction of Revetment | 120.9317 | 14.3763 | 90710000 | 90710000 | 2022 | MONTADEL ENTERPRISES | 2571 | 2022 | 2022-11-21 | 02/28/2022 | 0 | 0 | 2022-11-20 |  | 1
2023 | Region III | BULACAN | PAOMBONG (BULACAN) | P00742318LZ | Construction of Revetment | 120.7933 | 14.8212 | 14849762.77 | 14847428.18 | 2023 | SYMS CONSTRUCTION TRADING | 2572 | 2023 | 2023-11-21 | 03/27/2023 | 2334.59 | 0 | 2023-11-20 |  | 1
2023 | Region III | BULACAN | PLARIDEL (BULACAN) | P00726717LZ | Construction of Flood Mitigation Structure | 120.8921 | 14.9066 | 48999386.12 | 48999034.31 | 2023 | TOPNOTCH CATALYST BUILDERS INC. | 2573 | 2023 | 2023-05-19 | 02/06/2023 | 351.81 | 0 | 2023-10-02 | 136
2022 | National Capital Region | MALABON CITY | CITY OF MALABON (METROPOLITAN MANILA) | P00620350LZ | Construction of Flood Mitigation Structure | 120.9236 | 14.6972 | 48952560.92 | 49000000 | 2022 | B. BERNARDO CONST., INC. | 2574 | 2022 | 2022-11-16 | 02/14/2022 | 0 | 47439.08 | 2022-11-23 | 7
2024 | Region III | BULACAN | BOCAUE (BULACAN) | P00823425LZ | Construction of Flood Mitigation Structure | 120.9427 | 14.8133 | 78164396.48 | 78161014.06 | 2024 | A.R.L. CONSTRUCTION | 2575 | 2024 | 2024-11-23 | 02/28/2024 | 3382.42 | 0 | 2024-11-22 |  | 1
2023 | Region IV-B | OCCIDENTAL MINDORO | SABLAYAN (OCCIDENTAL MINDORO) | P00726261LZ | Construction of Flood Mitigation Structure | 120.8272 | 12.9242 | 45080000 | 45079105.81 | 2023 | F.A. TORRES CONSTRUCTION | 2576 | 2023 | 2023-09-12 | 02/10/2023 | 894.19 | 0 | 2023-09-11 |  | 1
2022 | Region IV-A | CAVITE | IMUS CITY (CAVITE) | P00620227LZ | Construction of Revetment | 120.9318 | 14.3797 | 90710000 | 90710000 | 2022 | N.B. AVILA CONSTRUCTION | 2577 | 2022 | 2022-11-21 | 02/28/2022 | 0 | 0 | 2022-11-20 |  | 1
2024 | Region III | BULACAN | BALAGTAS (BIGAA) (BULACAN) | P00838375LZ | Construction of Slope Protection Structure | 120.9002 | 14.8137 | 96499911.14 | 96499691.57 | 2024 | JB CONSTRUCTION AND SUPPLY INC. (FORMERLY:JB CONSTRUCTION AND SUPPLY) | 2578 | 2024 | 2024-09-18 | 02/07/2024 | 219.57 | 0 | 2024-11-01 | 44
2024 | Region III | NUEVA ECIJA | ALIAGA (NUEVA ECIJA) | P00823427LZ | Construction of Flood Mitigation Structure | 120.7935 | 15.496 | 48381240 | 47897330.68 | 2024 | AMP 723 CONSTRUCTION CORPORATION (FORMERLY: A.M.P. CONSTRUCTION) | 2579 | 2024 | 2024-09-27 | 02/21/2024 | 483909.32 | 0 | 2024-09-16 |  | 11
2022 | Region IV-A | CAVITE | IMUS CITY (CAVITE) | P00620251LZ | Construction of Flood Mitigation Structure | 120.9318 | 14.3763 | 90710000 | 90710000 | 2022 | TRIPLE 8 CONSTRUCTION & SUPPLY, INC. (FORMERLY TRIPLE 8 CONST. & SUPPLY) | 2580 | 2022 | 2022-11-21 | 02/28/2022 | 0 | 0 | 2022-11-20 |  | 1
2023 | Region III | NUEVA ECIJA | CABIAO (NUEVA ECIJA) | P00727297LZ | Construction of Flood Mitigation Structure | 120.8272 | 15.2321 | 64770773.75 | 65342020.1 | 2023 | D.B. BARAQUIEL CONSTRUCTION / JERRY R. SANTIAGO CONSTRUCTION CORP. (FORMERLY: JERRY SANTIAGO CONSTRUCTION) | 2581 | 2023 | 2023-12-05 | 03/29/2023 | 0 | 571246.35 | 2024-01-27 | 53
2023 | Region III | NUEVA ECIJA | LUPAO (NUEVA ECIJA) | P00742338LZ | Construction of Drainage Structure | 120.9002 | 15.8547 | 4950000 | 4850999.14 | 2023 | IJK MAE CONSTRUCTION INC. | 2582 | 2023 | 2023-05-15 | 03/28/2023 | 99000.86 | 0 | 2023-08-23 | 100
2022 | Region IV-A | CAVITE | BACOOR CITY (CAVITE) | P00644779LZ | Construction of Revetment | 120.9318 | 14.4423 | 11097468.73 | 11097413.02 | 2023 | ALMAKAR BUILDERS & METAL WORKS | 2583 | 2022 | 2023-05-10 | 02/01/2023 | 55.71 | 0 | 2023-05-24 | 14
2022 | Region III | BULACAN | GUIGUINTO (BULACAN) | P00639475LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.9237 | 14.8353 | 48999297.93 | 48999277.98 | 2023 | 729 CONSTRUCTION, INC. (FORMERLY 722 CONSTRUCTION, INC.) | 2584 | 2022 | 2023-01-27 | 04/05/2022 | 19.95 | 0 | 2023-01-28 | 1
2024 | Region III | PAMPANGA | SAN SIMON (PAMPANGA) | P00820831LZ | Construction of Slope Protection Structure | 120.7939 | 14.9934 | 29400000 | 27841800 | 2024 | JMSKI CONSTRUCTION AND TRADING | 2585 | 2024 | 2024-08-29 | 02/08/2024 | 1558200 | 0 | 2024-08-28 |  | 1
2024 | Region III | BULACAN | CITY OF BALIUAG (BULACAN) | P00843307LZ | Construction of Flood Mitigation Structure | 120.8921 | 14.9649 | 77199928.71 | 77199166.63 | 2024 | L.R. TIQUI BUILDERS, INC. | 2586 | 2024 | 2024-10-24 | 02/28/2024 | 762.08 | 0 | 2024-10-23 |  | 1
2024 | Region III | NUEVA ECIJA | CITY OF GAPAN (NUEVA ECIJA) | P00825091LZ | Construction of Flood Mitigation Structure | 120.9428 | 15.3128 | 144749991.2 | 144749663 | 2024 | R.A. PAHATI CONST. & SUPPLY, INC. | 2587 | 2024 | 2024-05-27 | 02/12/2024 | 328.2 | 0 | 2024-12-15 | 202
2023 | Region III | BULACAN | PANDI (BULACAN) | P00742137LZ | Construction of Flood Mitigation Structure | 120.9237 | 14.8787 | 74249461.32 | 74249006.72 | 2023 | TOPNOTCH CATALYST BUILDERS INC. / BLACK HARDHAT INC. (FORMERLY: JCHARDHAT INC.) | 2588 | 2023 | 2023-11-07 | 03/28/2023 | 454.6 | 0 | 2023-12-21 | 44
2024 | Region III | NUEVA ECIJA | CITY OF GAPAN (NUEVA ECIJA) | P00848621LZ | Construction of Flood Mitigation Structure | 120.9428 | 15.3128 | 72375034.8 | 70927178.54 | 2024 | F-DEY CONSTRUCTION AND TRADING / JERRY R. SANTIAGO CONSTRUCTION CORP. (FORMERLY: JERRY SANTIAGO CONSTRUCTION) | 2589 | 2024 | 2024-10-09 | 05/14/2024 | 1447856.26 | 0 | 2025-03-02 | 144
2022 | Region III | NUEVA ECIJA | ALIAGA (NUEVA ECIJA) | P00620534LZ | Construction of Flood Mitigation Structure | 120.7944 | 15.4966 | 45080000 | 45073229.89 | 2022 | R.D. TALENS CONSTRUCTION AND TRADING | 2590 | 2022 | 2022-08-22 | 03/02/2022 | 6770.11 | 0 | 2022-08-27 | 5
2023 | Region III | BULACAN | PLARIDEL (BULACAN) | P00727358LZ | Construction of Flood Mitigation Structure | 120.8923 | 14.9073 | 48999982.17 | 48999608.65 | 2023 | CEDAR CONSTRUCTION | 2591 | 2023 | 2023-09-11 | 03/07/2023 | 373.52 | 0 | 2023-10-31 | 50
2024 | Region IV-A | BATANGAS | MABINI (BATANGAS) | P00823543LZ | Construction of Flood Mitigation Structure | 120.9002 | 13.6912 | 9650000 | 9650000 | 2024 | VICMAR CONSTRUCTION, INC. | 2592 | 2024 | 2024-05-15 | 03/05/2024 | 0 | 0 | 2024-06-07 | 23
2022 | Region IV-B | OCCIDENTAL MINDORO | SABLAYAN (OCCIDENTAL MINDORO) | P00621106LZ | Construction of Flood Mitigation Structure | 120.8274 | 12.9479 | 226774789.4 | 48249983.48 | 2023 | ANORE CONSTRUCTION | 2593 | 2022 | 2023-07-03 | 07/06/2022 | 178524805.92 | 0 | 2023-07-02 |  | 1
2023 | Region I | ILOCOS NORTE | BANGUI (ILOCOS NORTE) | P00737411LZ | Construction of Slope Protection Structure | 120.7944 | 18.5312 | 14849740.45 | 14849740.15 | 2023 | TMT CONSTRUCTION | 2594 | 2023 | 2023-04-18 | 02/13/2023 | 0.3 | 0 | 2023-09-03 | 138
2023 | National Capital Region | NAVOTAS CITY | CITY OF NAVOTAS (METROPOLITAN MANILA) | P00726994LZ | Construction of Flood Mitigation Facility | 120.9318 | 14.6756 | 23268464.45 | 23267355.14 | 2023 | TWO DIMENSION CONSTRUCTION | 2595 | 2023 | 2023-11-02 | 03/08/2023 | 1109.31 | 0 | 2023-11-01 |  | 1
2022 | Region III | BULACAN | BOCAUE (BULACAN) | P00640455LZ | Construction of Flood Mitigation Structure | 120.9431 | 14.8 | 148498661.7 | 148498575.1 | 2023 | L.R. TIQUI BUILDERS, INC. | 2596 | 2022 | 2023-05-06 | 07/11/2022 | 86.6 | 0 | 2023-05-05 |  | 1
2024 | Region IV-A | CAVITE | TRECE MARTIRES CITY (CAPITAL) (CAVITE) | P00846049LZ | Construction of Slope Protection Structure | 120.8926 | 14.2877 | 6930000 | 6877933.95 | 2024 | N.B. AVILA CONSTRUCTION | 2597 | 2024 | 2024-06-18 | 02/14/2024 | 52066.05 | 0 | 2024-06-17 |  | 1
2022 | National Capital Region | MALABON CITY | CITY OF MALABON (METROPOLITAN MANILA) | P00620349LZ | Construction of Flood Mitigation Structure | 120.9238 | 14.6962 | 48918768.51 | 49000000 | 2022 | AZUL BUILDERS | 2598 | 2022 | 2022-10-11 | 02/14/2022 | 0 | 81231.49 | 2022-10-10 |  | 1
2023 | Region IV-A | CAVITE | IMUS CITY (CAVITE) | P00726212LZ | Construction of Revetment | 120.9319 | 14.4064 | 49000000 | 49000000 | 2023 | TRIPLE 8 CONSTRUCTION & SUPPLY, INC. (FORMERLY TRIPLE 8 CONST. & SUPPLY) | 2599 | 2023 | 2023-06-26 | 02/19/2023 | 0 | 0 | 2023-08-31 | 66
2024 | Region III | BULACAN | BALAGTAS (BIGAA) (BULACAN) | P00845977LZ | Construction of Slope Protection Structure | 120.9009 | 14.8191 | 49499863.67 | 49499483 | 2024 | JB CONSTRUCTION AND SUPPLY INC. (FORMERLY:JB CONSTRUCTION AND SUPPLY) | 2600 | 2024 | 2024-05-22 | 02/28/2024 | 380.67 | 0 | 2024-08-24 | 94
2022 | Region IV-B | OCCIDENTAL MINDORO | SABLAYAN (OCCIDENTAL MINDORO) | P00621107LZ | Construction of Flood Mitigation Structure | 120.8274 | 12.9479 | 226774789.4 | 43424883.41 | 2023 | ANORE CONSTRUCTION | 2601 | 2022 | 2023-07-03 | 07/06/2022 | 183349905.99 | 0 | 2023-07-02 |  | 1
2023 | Region III | BULACAN | PLARIDEL (BULACAN) | P00726151LZ | Construction of Flood Mitigation Structure | 120.8926 | 14.9069 | 48999386.12 | 48998832.05 | 2023 | M3 KONSTRACT CORPORATION (FORMERLY:MARGARITA CONSTRUCTION) | 2602 | 2023 | 2023-12-02 | 02/06/2023 | 554.07 | 0 | 2023-12-01 |  | 1
2022 | Region III | BULACAN | CITY OF MALOLOS (CAPITAL) (BULACAN) | P00630512LZ | Construction of Flood Mitigation Structure | 120.7945 | 14.8788 | 48999404.39 | 48998604.86 | 2023 | FRAMECON BUILDERS | 2603 | 2022 | 2023-02-12 | 02/18/2022 | 799.53 | 0 | 2023-02-11 |  | 1
2024 | National Capital Region | MALABON CITY | CITY OF MALABON (METROPOLITAN MANILA) | P00839458LZ | Construction of Flood Mitigation Structure | 120.9432 | 14.6814 | 59389785.02 | 59397439.53 | 2024 | ELITE GENERAL CONTRACTOR AND DEVELOPMENT CORP. | 2604 | 2024 | 2024-11-12 | 02/21/2024 | 0 | 7654.51 | 2024-12-15 | 33
2023 | Region IV-A | CAVITE | CITY OF GENERAL TRIAS (CAVITE) | P00725783LZ | Construction of Flood Mitigation Structure | 120.8926 | 14.3198 | 99608747.5 | 99604433.44 | 2024 | TRIPLE 8 CONSTRUCTION & SUPPLY, INC. (FORMERLY TRIPLE 8 CONST. & SUPPLY) | 2605 | 2023 | 2024-02-19 | 03/24/2023 | 4314.06 | 0 | 2024-02-18 |  | 1
2023 | Region I | PANGASINAN | ROSALES (PANGASINAN) | P00727334LZ | Construction of Dike | 120.828 | 16.0554 | 34300000 | 33604549.09 | 2023 | R.A. MATIAS CONSTRUCTION AND DEVELOPERS INC. (FORMERLY : R.A. MATIAS CONSTRUCTION AND DEVELOPERS) | 2606 | 2023 | 2023-09-15 | 03/24/2023 | 695450.91 | 0 | 2023-09-14 |  | 1
2024 | Region III | BULACAN | BUSTOS (BULACAN) | P00821267LZ | Construction of Slope Protection Structure | 120.8927 | 14.9308 | 96499995.73 | 96499726.23 | 2024 | J. SIMEON CONSTRUCTION | 2607 | 2024 | 2024-09-16 | 02/07/2024 | 269.5 | 0 | 2024-11-01 | 46
2024 | Region III | NUEVA ECIJA | QUEZON (NUEVA ECIJA) | P00820285LZ | Construction of Slope Protection Structure | 120.7948 | 15.5839 | 48250000 | 47766812.33 | 2024 | R.A. PAHATI CONST. & SUPPLY, INC. | 2608 | 2024 | 2024-06-18 | 03/01/2024 | 483187.67 | 0 | 2024-09-25 | 99
2023 | Cordillera Administrative Region | IFUGAO | TINOC (IFUGAO) | P00727097LZ | [11 empty] | 0 | 0
| Sta. | [14 empty] | 0 | 0
2024 | Region III | BULACAN | OBANDO (BULACAN) | P00820233LZ | Construction of Flood Mitigation Structure | 120.9319 | 14.7167 | 144749118.6 | 144749905.8 | 2025 | G.F. FABIAN CONSTRUCTION | 2610 | 2024 | 2025-01-06 | 02/22/2024 | 0 | 787.2 | 2025-06-27 | 172
2023 | Region III | BULACAN | CITY OF BALIUAG (BULACAN) | P00726459LZ | Construction of Flood Mitigation Structure | 120.9009 | 14.9451 | 96499205.41 | 96498901.91 | 2024 | M3 KONSTRACT CORPORATION (FORMERLY:MARGARITA CONSTRUCTION) | 2611 | 2023 | 2024-02-07 | 02/13/2023 | 303.5 | 0 | 2024-02-06 |  | 1
2024 | Region III | NUEVA ECIJA | TALAVERA (NUEVA ECIJA) | P00823474LZ | Construction of Flood Mitigation Structure | 120.924 | 15.6292 | 48250000 | 47771977.22 | 2024 | IJK MAE CONSTRUCTION INC. | 2612 | 2024 | 2024-08-30 | 03/04/2024 | 478022.78 | 0 | 2024-08-29 |  | 1
2022 | National Capital Region | VALENZUELA CITY | CITY OF VALENZUELA (METROPOLITAN MANILA) | P00620082LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.9319 | 14.7316 | 91655961.31 | 89830037.3 | 2023 | J. SIMEON CONSTRUCTION | 2613 | 2022 | 2023-02-10 | 02/11/2022 | 1825924.01 | 0 | 2023-03-06 | 24
2022 | Region III | BULACAN | PANDI (BULACAN) | P00620516LZ | Construction of Flood Mitigation Structure | 120.924 | 14.8384 | 43209570.77 | 43201412.48 | 2022 | M.S. RAMOS CONSTRUCTION INC. (FORMERLY: M.S. RAMOS | 2614 | 2022 | 2022-08-25 | 01/28/2022 | 8158.29 | 0 | 2022-08-24 |  | 1
2024 | Region III | BULACAN | PLARIDEL (BULACAN) | P00825077LZ | Construction of Flood Mitigation Structure | 120.893 | 14.9083 | 77199162.86 | 77199523.04 | 2024 | TOPNOTCH CATALYST BUILDERS INC. | 2615 | 2024 | 2024-09-26 | 05/14/2024 | 0 | 360.18 | 2025-01-07 | 103
2024 | National Capital Region | NAVOTAS CITY | CITY OF NAVOTAS (METROPOLITAN MANILA) | P00820551LZ | Construction of Flood Mitigation Facility | 120.9438 | 14.6697 | 29395794.54 | 29400000 | 2024 | P7 BUILDERS INC. | 2616 | 2024 | 2024-08-09 | 02/12/2024 | 0 | 4205.46 | 2024-08-08 |  | 1
2023 | Region I | ILOCOS NORTE | ADAMS (ILOCOS NORTE) | P00726829LZ | Construction of Flood Mitigation Structure | 120.901 | 18.4693 | 96500000 | 96499992.55 | 2024 | J.C. PINON CONSTRUCTION INC.(FORMERLY J.C. PINON CONST) / WAWAO BUILDERS | 2617 | 2023 | 2024-06-30 | 03/22/2023 | 7.45 | 0 | 2024-07-04 | 4
2024 | Region IV-A | BATANGAS | MABINI (BATANGAS) | P00839600LZ | Construction of Flood Mitigation Structure | 120.924 | 13.716 | 4950000 | 4950000 | 2024 | VICMAR CONSTRUCTION, INC. | 2618 | 2024 | 2024-03-19 | 02/07/2024 | 0 | 0 | 2024-04-20 | 32
2023 | Region III | BULACAN | BUSTOS (BULACAN) | P00726150LZ | Construction of Slope Protection Structure | 120.8931 | 14.9321 | 22784483.17 | 22784390.77 | 2023 | WBX CONSTRUCTION, INC (FORMERLY WBX CONSTRUCTION) | 2619 | 2023 | 2023-07-05 | 02/06/2023 | 92.4 | 0 | 2023-07-04 |  | 1
2022 | Region IV-A | CAVITE | IMUS CITY (CAVITE) | P00620250LZ | Construction of Flood Mitigation Structure | 120.932 | 14.3797 | 90710000 | 90710000 | 2023 | HAUSLAND CONSTRUCTION | 2620 | 2022 | 2023-01-20 | 02/28/2022 | 0 | 0 | 2023-01-19 |  | 1
2022 | Region IV-A | CAVITE | NAIC (CAVITE) | P00631290LZ | Construction of Flood Mitigation Structure | 120.795 | 14.2915 | 34299948.53 | 33105536.48 | 2023 | MORTAR MASTERS & CONCRETE BUILDERS | 2621 | 2022 | 2023-08-03 | 02/14/2022 | 1194412.05 | 0 | 2023-05-22 |  | 73
2024 | Region III | BULACAN | CITY OF MEYCAUAYAN (BULACAN) | P00820207LZ | Construction of Flood Mitigation Structure | 120.9242 | 14.7388 | 67549368.56 | 67549893.33 | 2024 | A.C. SOLIVEN CONSTRUCTION & GENERAL MERCHANDISE | 2622 | 2024 | 2024-12-12 | 02/14/2024 | 0 | 524.77 | 2025-01-07 | 26
2023 | Region I | PANGASINAN | TAYUG (PANGASINAN) | P00742283LZ | Construction of Flood Mitigation Structure | 120.828 | 16.0554 | 19600000 | 19754526.15 | 2023 | HIGH ROCK CONSTRUCTION AND SUPPLIES INCORPORATED | 2623 | 2023 | 2023-05-31 | 03/31/2023 | 0 | 154526.15 | 2023-09-04 | 96
2023 | Region III | BULACAN | PANDI (BULACAN) | P00726486LZ | Construction of Flood Mitigation Structure | 120.9244 | 14.8315 | 96499971 | 96317780.07 | 2023 | WAWAO BUILDERS | 2624 | 2023 | 2023-09-11 | 02/13/2023 | 182190.93 | 0 | 2024-01-07 | 118
2023 | Region IV-A | CAVITE | KAWIT (CAVITE) | P00727313LZ | Construction of Flood Mitigation Structure | 120.8931 | 14.4377 | 67550000 | 67549748.33 | 2023 | ALMAKAR BUILDERS & METAL WORKS | 2625 | 2023 | 2023-11-29 | 03/27/2023 | 251.67 | 0 | 2023-11-28 |  | 1
2023 | Region III | NUEVA ECIJA | ALIAGA (NUEVA ECIJA) | P00725705LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.8281 | 15.524 | 96500000 | 96495000 | 2023 | AMP 723 CONSTRUCTION CORPORATION (FORMERLY: A.M.P. CONSTRUCTION) | 2626 | 2023 | 2023-08-01 | 02/22/2023 | 5000 | 0 | 2023-11-17 | 108
2023 | Region III | BULACAN | CITY OF BALIUAG (BULACAN) | P00726720LZ | Construction of Flood Mitigation Structure | 120.9013 | 14.9459 | 39199454.62 | 39197381.73 | 2023 | TRIPLE 8 CONSTRUCTION & SUPPLY, INC. (FORMERLY TRIPLE 8 CONST. & SUPPLY) | 2627 | 2023 | 2023-05-09 | 02/06/2023 | 2072.89 | 0 | 2023-11-01 | 176
2024 | Region III | BULACAN | BALAGTAS (BIGAA) (BULACAN) | P00839479LZ | Construction of Slope Protection Structure | 120.9015 | 14.8186 | 98999943.2 | 98999609.48 | 2024 | FLORDES CONSTRUCTION & TRADING CORP. (FORMERLY FLO | 2628 | 2024 | 2024-11-02 | 02/07/2024 | 333.72 | 0 | 2024-11-01 |  | 1
2024 | National Capital Region | NAVOTAS CITY | CITY OF NAVOTAS (METROPOLITAN MANILA) | P00820557LZ | Rehabilitation / Major Repair of Drainage Structure | 120.944 | 14.6623 | 4896005.68 | 4899444.87 | 2024 | EARTHWORK BUILDERS, INC. (FORMERLY: EARTHWORK MOVERS) | 2629 | 2024 | 2024-06-10 | 02/12/2024 | 0 | 3439.19 | 2024-06-09 |  | 1
2024 | Cordillera Administrative Region | BENGUET | BUGUIAS (BENGUET) | P00821533LZ | Construction of Flood Mitigation Structure | 120.8282 | 16.794 | 19600000 | 19550030.78 | 2024 | GELLE CONSTRUCTION SERVICES | 2630 | 2024 | 2024-11-20 | 07/01/2024 | 49969.22 | 0 | 2025-01-16 | 57
2022 | Region III | BULACAN | CITY OF BALIUAG (BULACAN) | P00639468LZ | Construction of Flood Mitigation Structure | 120.8937 | 14.9614 | 48999726.61 | 48999769.37 | 2023 | ST. MATTHEW GEN. CONTRACTOR & DEVELOPMENT CORP. | 2631 | 2022 | 2023-01-28 | 04/05/2022 | 0 | 42.76 | 2023-01-28 | 0
2023 | Region III | BULACAN | PANDI (BULACAN) | P00737456LZ | Construction of Flood Mitigation Structure | 120.9244 | 14.8316 | 19799993.71 | 19798628.36 | 2023 | JAGONBUILD CONSTRUCTION CORP. (FOR. JAGON BUILDERS | 2632 | 2023 | 2023-08-10 | 02/06/2023 | 1365.35 | 0 | 2023-09-02 | 23
2022 | Region III | BULACAN | CITY OF MALOLOS (CAPITAL) (BULACAN) | P00640520LZ | Construction of Drainage Structure | 120.7952 | 14.876 | 47519522.48 | 47518704.12 | 2023 | TOPNOTCH CATALYST BUILDERS INC. | 2633 | 2022 | 2023-01-29 | 04/05/2022 | 818.36 | 0 | 2023-01-28 |  | 1
2024 | Region III | BULACAN | BOCAUE (BULACAN) | P00845816LZ | Construction of Slope Protection Structure | 120.9441 | 14.8124 | 98999654.86 | 98994958.26 | 2025 | TOPNOTCH CATALYST BUILDERS INC. / ONE FRAME CONSTRUCTION INC. | 2634 | 2024 | 2025-01-17 | 04/23/2024 | 4696.6 | 0 | 2025-01-16 |  | 1
2023 | Region IV-A | CAVITE | IMUS CITY (CAVITE) | P00726211LZ | Construction of Dike | 120.9321 | 14.4065 | 49000000 | 48475958.6 | 2023 | N.B. AVILA CONSTRUCTION | 2635 | 2023 | 2023-09-01 | 02/19/2023 | 524041.4 | 0 | 2023-08-31 |  | 1
2023 | Region III | BULACAN | CITY OF BALIUAG (BULACAN) | P00726902LZ | Construction of Flood Mitigation Structure | 120.8937 | 14.9614 | 77199405.85 | 77188797.98 | 2023 | DARCY & ANNA BUILDERS & TRADING | 2636 | 2023 | 2023-10-02 | 03/14/2023 | 10607.87 | 0 | 2023-12-07 | 66
2023 | Region III | PAMPANGA | SAN LUIS (PAMPANGA) | P00742341LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.7959 | 15.0547 | 14850000 | 14478626.94 | 2023 | CEDAR CONSTRUCTION | 2637 | 2023 | 2023-09-27 | 05/16/2023 | 371373.06 | 0 | 2023-09-26 |  | 1
2023 | Region IV-A | CAVITE | KAWIT (CAVITE) | P00742421LZ | Construction of Drainage Structure | 120.9017 | 14.4445 | 6930000 | 6855432.89 | 2023 | T.E. TRINIDAD CONSTRUCTION | 2638 | 2023 | 2023-07-26 | 03/29/2023 | 74567.11 | 0 | 2023-07-25 |  | 1
2024 | Region III | BULACAN | MARILAO (BULACAN) | P00821232LZ | Construction of Flood Mitigation Structure | 120.9442 | 14.7486 | 106149886.5 | 106149931.6 | 2024 | ALPHA & OMEGA GEN. CONTRACTOR & DEVELOPMENT CORP. / JB CONSTRUCTION AND SUPPLY INC. (FORMERLY:JB CONSTRUCTION AND SUPPLY) | 2639 | 2024 | 2024-10-05 | 02/14/2024 | 0 | 45.1 | 2024-10-04 |  | 1
2022 | Region III | BULACAN | PLARIDEL (BULACAN) | P00621530LZ | Construction of Flood Mitigation Structure | 120.8283 | 14.9004 | 24499991.38 | 23521006.99 | 2022 | TBB CONSTRUCTION CORP. | 2640 | 2022 | 2022-10-30 | 04/04/2022 | 978984.39 | 0 | 2022-10-29 |  | 1
2022 | Region I | ILOCOS NORTE | VINTAR (ILOCOS NORTE) | P00621442LZ | Construction of Flood Mitigation Structure | 120.796 | 18.3124 | 48999549.26 | 48343757.01 | 2023 | ASIAN PEARL CONSTRUCTION & DEVT. CORP. | 2641 | 2022 | 2023-02-18 | 04/04/2022 | 655792.25 | 0 | 2023-02-17 |  | 1
2022 | Region III | BULACAN | BUSTOS (BULACAN) | P00631215LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.9244 | 14.9611 | 45079476.32 | 45079027.76 | 2022 | TOPNOTCH CATALYST BUILDERS INC. / BLACK HARDHAT INC. (FORMERLY: JCHARDHAT INC.) | 2642 | 2022 | 2022-07-15 | 03/04/2022 | 448.56 | 0 | 2022-12-27 | 165
2023 | Region III | BULACAN | CITY OF BALIUAG (BULACAN) | P00736012LZ | Construction of Slope Protection Structure | 120.894 | 14.9708 | 28949533.47 | 28948920.97 | 2023 | DMLC BUILDERS | 2643 | 2023 | 2023-09-10 | 02/13/2023 | 612.5 | 0 | 2023-09-09 |  | 1
2023 | Region I | ILOCOS NORTE | PAGUDPUD (ILOCOS NORTE) | P00725631LZ | Construction of Flood Mitigation Structure | 120.9322 | 18.5533 | 63699729.25 | 62724999.57 | 2023 | JLP CONSTRUCTION & SUPPLY (FORMERLY: JLP CONSTRUCT | 2644 | 2023 | 2023-08-29 | 03/13/2023 | 974729.68 | 0 | 2023-12-15 | 108
2022 | Region III | BULACAN | CITY OF BALIUAG (BULACAN) | P00632810LZ | Construction of Drainage Structure | 120.894 | 14.9508 | 29699837.86 | 29699999.52 | 2022 | C & F CONSTRUCTION & DEVELOPMENT CORPORATION | 2645 | 2022 | 2022-10-14 | 01/28/2022 | 0 | 161.66 | 2022-10-13 |  | 1
2024 | Region III | BULACAN | BALAGTAS (BIGAA) (BULACAN) | P00845972LZ | Construction of Flood Mitigation Structure | 120.902 | 14.8137 | 49499919.36 | 49499511.04 | 2024 | TOPNOTCH CATALYST BUILDERS INC. | 2646 | 2024 | 2024-08-05 | 02/28/2024 | 408.32 | 0 | 2024-08-24 | 19
2024 | Cordillera Administrative Region | BENGUET | KABAYAN (BENGUET) | P00820735LZ | Construction of Flood Mitigation Structure | 120.8287 | 16.6514 | 29400000 | 29396000 | 2024 | CHRISHUA CONSTRUCTION SERVICES | 2647 | 2024 | 2024-11-19 | 04/18/2024 | 4000 | 0 | 2024-11-18 |  | 1
2022 | Cordillera Administrative Region | BENGUET | BOKOD (BENGUET) | P00639449LZ | Construction of Flood Mitigation Structure | 120.8306 | 16.4895 | 9800000 | 9789790.48 | 2022 | AG CHUNGALAN CONSTRUCTION | 2648 | 2022 | 2022-12-05 | 06/22/2022 | 10209.52 | 0 | 2022-10-21 |  | 45
2024 | Region III | BULACAN | BUSTOS (BULACAN) | P00825079LZ | Construction of Flood Mitigation Structure | 120.9245 | 14.9616 | 77199992.23 | 77199138.89 | 2024 | WAWAO BUILDERS | 2649 | 2024 | 2024-12-18 | 04/23/2024 | 853.34 | 0 | 2024-12-17 |  | 1
2021 | Cordillera Administrative Region | BENGUET |  | P00526376LZ | Construction of Flood Mitigation Structure | 120.8307 | 16.7718 | 29400000 | 29377392.06 | 2022 | BTCJR CONSTRUCTION AND ENGINEERING SERVICES | 2650 | 2021 | 2022-07-18 | 01/16/2022 | 22607.94 | 0 | 2022-07-17 |  | 1
2024 | Region III | PAMPANGA | ARAYAT (PAMPANGA) | P00820281LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.7961 | 15.2043 | 96500000 | 91095785.63 | 2024 | STO. CRISTO CONSTRUCTION & TRADING INC. (FOR: STO. CRISTO CONSTRUCTION & TRADING) | 2651 | 2024 | 2024-11-16 | 03/12/2024 | 5404214.37 | 0 | 2024-11-15 |  | 1
2022 | Region IV-A | CAVITE | BACOOR CITY (CAVITE) | P00621504LZ | Construction of Revetment | 120.9443 | 14.4521 | 77199995.2 | 77195492.58 | 2022 | GRAIA CONSTRUCTION CORPORATION | 2652 | 2022 | 2022-10-14 | 04/07/2022 | 4502.62 | 0 | 2023-02-19 | 128
2024 | Region III | BULACAN | BALAGTAS (BIGAA) (BULACAN) | P00823423LZ | Construction of Flood Mitigation Structure | 120.902 | 14.8136 | 78164895.56 | 78164572.3 | 2024 | JB CONSTRUCTION AND SUPPLY INC. (FORMERLY:JB CONSTRUCTION AND SUPPLY) | 2653 | 2024 | 2024-10-24 | 02/28/2024 | 323.26 | 0 | 2024-10-23 |  | 1
2022 | National Capital Region | NAVOTAS CITY | CITY OF NAVOTAS (METROPOLITAN MANILA) | P00632706LZ | Construction of Dike | 120.9322 | 14.6836 | 48994575 | 49497745.13 | 2022 | JAGONBUILD CONSTRUCTION CORP. (FOR. JAGON BUILDERS | 2654 | 2022 | 2022-10-12 | 02/15/2022 | 0 | 503170.13 | 2022-10-11 |  | 1
2025 | Region III | NUEVA ECIJA | SAN ISIDRO (NUEVA ECIJA) | P00921786LZ | Construction of Flood Mitigation Structure | 120.8941 | 15.3115 | 48999997.85 | 48754753.43 | 2025 | R.A. PAHATI CONST. & SUPPLY, INC. | 2655 | 2025 | 2025-04-25 | 02/11/2025 | 245244.42 | 0 | 2025-10-25 | 183
2023 | Region III | BULACAN | CITY OF MEYCAUAYAN (BULACAN) | P00726728LZ | Construction of Flood Mitigation Structure | 120.9323 | 14.7343 | 48998667.35 | 48990823.63 | 2024 | AZUL BUILDERS | 2656 | 2023 | 2024-04-02 | 02/22/2023 | 7843.72 | 0 | 2024-04-01 |  | 1
2023 | Region III | NUEVA ECIJA | SANTO DOMINGO (NUEVA ECIJA) | P00725706LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.9023 | 15.5753 | 96500000 | 96495000 | 2023 | AMP 723 CONSTRUCTION CORPORATION (FORMERLY: A.M.P. CONSTRUCTION) | 2657 | 2023 | 2023-09-04 | 02/22/2023 | 5000 | 0 | 2023-11-17 | 74
2023 | Region IV-B | OCCIDENTAL MINDORO | SABLAYAN (OCCIDENTAL MINDORO) | P00736043LZ | Construction of Flood Mitigation Structure | 120.831 | 12.9219 | 217124991.8 | 217123574.4 | 2023 | SUNWEST, INC. (FORMERLY: SUNWEST CONSTRUCTION & DEVELOPMENT CORPORATION) | 2658 | 2023 | 2023-12-15 | 02/11/2023 | 1417.4 | 0 | 2024-03-25 | 101
2022 | National Capital Region | MALABON CITY | CITY OF MALABON (METROPOLITAN MANILA) | P00621133LZ | Construction of Flood Mitigation Structure | 120.9245 | 14.7015 | 58798945.85 | 57900000 | 2022 | A.L. SALAZAR CONSTRUCTION, INC. / ROTAFLEX CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY:ROTA FLEX CONSTRUCTION) | 2659 | 2022 | 2022-11-18 | 03/24/2022 | 898945.85 | 0 | 2022-11-17 |  | 1
2024 | Region III | BULACAN | CITY OF MALOLOS (CAPITAL) (BULACAN) | P00843312LZ | Construction of Flood Mitigation Structure | 120.7964 | 14.8478 | 72374989.85 | 72373936.89 | 2024 | MICHARIAN BUILDERS AND TRADING | 2660 | 2024 | 2024-10-22 | 05/14/2024 | 1052.96 | 0 | 2025-01-07 | 77
2023 | Region III | BULACAN | PLARIDEL (BULACAN) | P00742325LZ | Construction of Flood Mitigation Structure | 120.8941 | 14.911 | 49499902.55 | 49499465.67 | 2023 | JB CONSTRUCTION AND SUPPLY INC. (FORMERLY:JB CONSTRUCTION AND SUPPLY) | 2661 | 2023 | 2023-07-26 | 03/27/2023 | 436.88 | 0 | 2023-11-20 | 117
2024 | National Capital Region | NAVOTAS CITY | CITY OF NAVOTAS (METROPOLITAN MANILA) | P00820539LZ | Construction of Drainage Structure | 120.9324 | 14.6812 | 15679433.12 | 15678833.77 | 2024 | 721 BUILDERS CORPORATION | 2662 | 2024 | 2024-08-09 | 02/12/2024 | 599.35 | 0 | 2024-08-08 |  | 1
2022 | National Capital Region | MALABON CITY | CITY OF MALABON (METROPOLITAN MANILA) | P00620348LZ | Construction of Flood Mitigation Structure | 120.9246 | 14.6956 | 48904843.78 | 49000000 | 2022 | AZUL BUILDERS | 2663 | 2022 | 2022-10-11 | 02/14/2022 | 0 | 95156.22 | 2022-10-10 |  | 1
2022 | Region IV-A | CAVITE | IMUS CITY (CAVITE) | P00620872LZ | Construction of Revetment | 120.9029 | 14.3965 | 90710000 | 90710000 | 2023 | ALMAKAR BUILDERS & METAL WORKS | 2664 | 2022 | 2023-02-09 | 02/28/2022 | 0 | 0 | 2023-02-08 |  | 1
2021 | Region III | BULACAN |  | P00561463LZ | Construction of Flood Mitigation Structure | 120.7965 | 14.8756 | 96499269.8 | 96498474.65 | 2023 | TRICHES CONSTRUCTION & TRADING / FRAMECON BUILDERS | 2665 | 2021 | 2023-06-23 | 02/02/2022 | 795.15 | 0 | 2023-06-22 |  | 1
2023 | Region IV-A | CAVITE | CITY OF GENERAL TRIAS (CAVITE) | P00726945LZ | Construction of Flood Mitigation Structure | 120.8947 | 14.3177 | 96500000 | 96498165.29 | 2024 | I&E CONSTRUCTION CORPORATION (FORMERLY: I&E CONSTR / MOTIONTRADE DEVELOPMENT CORPORATION | 2666 | 2023 | 2024-04-01 | 07/07/2023 | 1834.71 | 0 | 2024-03-31 |  | 1
2024 | Region III | BULACAN | OBANDO (BULACAN) | P00844531LZ | Construction of Flood Mitigation Structure | 120.9325 | 14.7007 | 67549476.8 | 67549063.5 | 2024 | JB CONSTRUCTION AND SUPPLY INC. (FORMERLY:JB CONSTRUCTION AND SUPPLY) | 2667 | 2024 | 2024-09-28 | 03/14/2024 | 413.3 | 0 | 2024-09-27 |  | 1
2023 | Region III | NUEVA ECIJA | CITY OF GAPAN (NUEVA ECIJA) | P00740327LZ | Construction of Flood Mitigation Structure | 120.9249 | 15.3095 | 96499976.45 | 96497742.64 | 2024 | F-DEY CONSTRUCTION AND TRADING / DGSARM BUILDERS INC. (FORMERLY: D.G. SARMENTA CONSTRUCTION) | 2668 | 2023 | 2024-02-04 | 04/17/2023 | 2233.81 | 0 | 2024-02-03 |  | 1
2021 | Cordillera Administrative Region | BENGUET |  | P00526380LZ | Construction of Flood Mitigation Structure | 120.8314 | 16.7772 | 19600000 | 19600000 | 2022 | AAAL CONSTRUCTION | 2669 | 2021 | 2022-07-22 | 01/19/2022 | 0 | 0 | 2022-07-29 | 7
2022 | Region IV-A | CAVITE | TANZA (CAVITE) | P00637795LZ | Construction of Drainage Structure | 120.8315 | 14.3852 | 4950000 | 4950000 | 2022 | FE S. REYES GENERAL CONTRACTOR CORP. | 2670 | 2022 | 2022-07-14 | 03/31/2022 | 0 | 0 | 2022-07-13 |  | 1
2024 | Region IV-A | CAVITE | CITY OF GENERAL TRIAS (CAVITE) | P00846047LZ | Construction of Drainage Structure | 120.9029 | 14.2317 | 4950000 | 4899267.71 | 2024 | FE S. REYES GENERAL CONTRACTOR CORP. | 2671 | 2024 | 2024-07-23 | 04/25/2024 | 50732.29 | 0 | 2024-07-22 |  | 1
2024 | Region III | BULACAN | MARILAO (BULACAN) | P00821231LZ | Construction of Flood Mitigation Structure | 120.9447 | 14.7457 | 94569810.09 | 94569987.5 | 2024 | JB CONSTRUCTION AND SUPPLY INC. (FORMERLY:JB CONSTRUCTION AND SUPPLY) | 2672 | 2024 | 2024-09-24 | 02/14/2024 | 0 | 177.41 | 2024-09-23 |  | 1
2023 | Cordillera Administrative Region | MOUNTAIN PROVINCE | TADIAN (MOUNTAIN PROVINCE) | P00735968LZ | Construction of Flood Mitigation Structure | 120.8331 | 16.9553 | 28949999.4 | 28950000 | 2023 | FJ MIRANDA CONSTRUCTION | 2673 | 2023 | 2023-06-30 | 04/10/2023 | 0 | 0.6 | 2023-09-06 | 68
2023 | Region IV-B | OCCIDENTAL MINDORO | CALINTAAN (OCCIDENTAL MINDORO) | P00736060LZ | Construction of Flood Mitigation Structure | 120.9447 | 12.6105 | 96500000 | 96495414.86 | 2023 | JELSIE CONSTRUCTION & SUPPLY | 2674 | 2023 | 2023-10-15 | 03/11/2023 | 4585.14 | 0 | 2023-10-14 |  | 1
2022 | Region III | BULACAN | CALUMPIT (BULACAN) | P00632822LZ | Construction of Slope Protection Structure | 120.7969 | 14.9004 | 13859396.02 | 13853245.52 | 2022 | A.R.L. CONSTRUCTION | 2675 | 2022 | 2022-07-13 | 01/28/2022 | 6150.5 | 0 | 2022-07-25 | 12
2022 | Region IV-A | CAVITE | KAWIT (CAVITE) | P00620236LZ | Construction of Revetment | 120.8947 | 14.4353 | 60795000 | 59938901.12 | 2022 | CAVDEAL-CAVITE IDEAL INT'L. CONST. & DEV'T. CORP. | 2676 | 2022 | 2022-10-02 | 02/28/2022 | 856098.88 | 0 | 2022-10-01 |  | 1
2024 | Region III | NUEVA ECIJA | SANTO DOMINGO (NUEVA ECIJA) | P00820272LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.903 | 15.5757 | 96500000 | 95533838.11 | 2024 | AMP 723 CONSTRUCTION CORPORATION (FORMERLY: A.M.P. CONSTRUCTION) / KEVIN PAUL CONSTRUCTION | 2677 | 2024 | 2024-08-12 | 02/06/2024 | 966161.89 | 0 | 2024-10-31 | 80
2022 | National Capital Region | MALABON CITY | CITY OF MALABON (METROPOLITAN MANILA) | P00620346LZ | Construction of Flood Mitigation Structure | 120.925 | 14.694 | 48994869.4 | 49000000 | 2022 | JAGONBUILD CONSTRUCTION CORP. (FOR. JAGON BUILDERS | 2678 | 2022 | 2022-10-11 | 02/14/2022 | 0 | 5130.6 | 2022-10-10 |  | 1
2021 | Region III | BULACAN |  | P00561527LZ | Construction of Flood Mitigation Structure | 120.797 | 14.8403 | 24499396.48 | 24499443.85 | 2022 | STAR WILLIAM CONSTRUCTION | 2679 | 2021 | 2022-08-11 | 01/14/2022 | 0 | 47.37 | 2022-08-10 |  | 1
2023 | Region IV-A | CAVITE | IMUS CITY (CAVITE) | P00725806LZ | Construction of Revetment | 120.9325 | 14.3946 | 91675000 | 91675000 | 2023 | TRIPLE 8 CONSTRUCTION & SUPPLY, INC. (FORMERLY TRIPLE 8 CONST. & SUPPLY) | 2680 | 2023 | 2023-11-14 | 02/19/2023 | 0 | 0 | 2023-11-13 |  | 1
2024 | Region III | BULACAN | BALAGTAS (BIGAA) (BULACAN) | P00823422LZ | Construction of Flood Mitigation Structure | 120.9031 | 14.8022 | 78164870.89 | 78163573.63 | 2024 | JB CONSTRUCTION AND SUPPLY INC. (FORMERLY:JB CONSTRUCTION AND SUPPLY) | 2681 | 2024 | 2024-06-17 | 02/28/2024 | 1297.26 | 0 | 2024-10-23 | 128
2024 | Region III | BULACAN | CITY OF MALOLOS (CAPITAL) (BULACAN) | P00838385LZ | Construction of Slope Protection Structure | 120.7983 | 14.8469 | 77199977.27 | 77199993.5 | 2024 | DARCY & ANNA BUILDERS & TRADING | 2682 | 2024 | 2024-04-19 | 02/07/2024 | 0 | 16.23 | 2024-10-02 | 166
2022 | Region III | NUEVA ECIJA | ALIAGA (NUEVA ECIJA) | P00620154LZ | Construction of Flood Mitigation Structure | 120.8949 | 15.557 | 91675000 | 91675000 | 2022 | AMP 723 CONSTRUCTION CORPORATION (FORMERLY: A.M.P. CONSTRUCTION) | 2683 | 2022 | 2022-09-05 | 02/15/2022 | 0 | 0 | 2022-11-10 | 66
2024 | Cordillera Administrative Region | BENGUET | BUGUIAS (BENGUET) | P00821532LZ | Construction of Flood Mitigation Structure | 120.8333 | 16.7986 | 29400000 | 29352752.8 | 2024 | NORJOHN CONSTRUCTION | 2684 | 2024 | 2024-07-25 | 04/02/2024 | 47247.2 | 0 | 2024-11-06 | 104
2023 | Region IV-A | BATANGAS | LAUREL (BATANGAS) | P00746109LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.9325 | 14.0573 | 3474000 | 3471370 | 2024 | JANRA8 BUILDERS AND CONSTRUCTION SUPPLY, INC. | 2685 | 2023 | 2024-02-15 | 01/05/2024 | 2630 | 0 | 2024-04-02 | 47
2023 | Region III | BULACAN | BALAGTAS (BIGAA) (BULACAN) | P00742130LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.9036 | 14.8191 | 79199522.19 | 79199187.57 | 2024 | R2A CONSTRUCTION & TRADING CORPORATION | 2686 | 2023 | 2024-04-08 | 05/15/2023 | 334.62 | 0 | 2024-04-07 |  | 1
2023 | Region I | ILOCOS NORTE | BANGUI (ILOCOS NORTE) | P00740560LZ | Construction of Flood Mitigation Structure | 120.7984 | 18.5239 | 19599856.14 | 19599827.98 | 2023 | RCD GEN. CONTRACTOR & CONSTRUCTION SUPPLY | 2687 | 2023 | 2023-10-27 | 04/12/2023 | 28.16 | 0 | 2023-10-28 | 1
2024 | Region III | BULACAN | MARILAO (BULACAN) | P00825103LZ | Construction of Flood Mitigation Structure | 120.9448 | 14.7504 | 57899739.64 | 57899912.04 | 2024 | JB CONSTRUCTION AND SUPPLY INC. (FORMERLY:JB CONSTRUCTION AND SUPPLY) | 2688 | 2024 | 2024-09-25 | 03/18/2024 | 0 | 172.4 | 2024-09-24 |  | 1
2022 | Region III | BULACAN | BUSTOS (BULACAN) | P00631178LZ | Construction of Flood Mitigation Structure | 120.925 | 14.9056 | 45079668.57 | 45078595.32 | 2022 | TOPNOTCH CATALYST BUILDERS INC. / BLACK HARDHAT INC. (FORMERLY: JCHARDHAT INC.) | 2689 | 2022 | 2022-07-15 | 03/04/2022 | 1073.25 | 0 | 2022-12-27 | 165
2023 | Region III | NUEVA ECIJA | ALIAGA (NUEVA ECIJA) | P00742333LZ | Construction of Drainage Structure | 120.8337 | 15.5189 | 5940000 | 5880040.72 | 2023 | IJK MAE CONSTRUCTION INC. | 2690 | 2023 | 2023-08-24 | 03/28/2023 | 59959.28 | 0 | 2023-08-23 |  | 1
2022 | National Capital Region | NAVOTAS CITY | CITY OF NAVOTAS (METROPOLITAN MANILA) | P00632702LZ | Construction of Flood Mitigation Facility | 120.9325 | 14.6772 | 21525792.58 | 21753596.88 | 2022 | DOUBLE Z CONSTRUCTION AND SUPPLY | 2691 | 2022 | 2022-09-09 | 02/14/2022 | 0 | 227804.3 | 2022-09-10 | 1
2023 | Region III | BULACAN | CITY OF MALOLOS (CAPITAL) (BULACAN) | P00742154LZ | Construction of Flood Mitigation Structure | 120.7984 | 14.8471 | 98999963.07 | 98999191.47 | 2024 | JTC CRUZ CONSTRUCTION CO., INC. | 2692 | 2023 | 2024-03-21 | 03/28/2023 | 771.6 | 0 | 2024-03-20 |  | 1
2021 | Cordillera Administrative Region | MOUNTAIN PROVINCE |  | P00526267LZ | Construction of Flood Mitigation Structure | 120.895 | 16.8835 | 70693004.5 | 70693005 | 2022 | 3K ROCK ENGINEERING / OLSIM CONSTRUCTION | 2693 | 2021 | 2022-11-30 | 04/13/2022 | 0 | 0.5 | 2022-12-15 | 15
2021 | Region I | ILOCOS NORTE |  | P00561623LZ | Construction of Flood Mitigation Structure | 120.8344 | 18.5336 | 9900000 | 9599225.3 | 2022 | N.A. IBARRA CONSTRUCTION(FOR. DIOCLETIANS CONST.) | 2694 | 2021 | 2022-09-14 | 07/09/2021 | 300774.7 | 0 | 2022-06-23 |  | 83
2024 | Region IV-B | OCCIDENTAL MINDORO | SABLAYAN (OCCIDENTAL MINDORO) | P00824734LZ | Construction of Flood Mitigation Structure | 120.8001 | 12.7412 | 39200000 | 39198579.92 | 2024 | F.A. TORRES CONSTRUCTION | 2695 | 2024 | 2024-11-11 | 03/07/2024 | 1420.08 | 0 | 2024-11-10 |  | 1
2023 | Region III | BULACAN | BOCAUE (BULACAN) | P00742319LZ | Rehabilitation / Major Repair of Drainage Structure | 120.925 | 14.7978 | 4949838.29 | 4949400.06 | 2023 | AVE-MIRA CONSTRUCTION AND TRADING | 2696 | 2023 | 2023-08-29 | 05/02/2023 | 438.23 | 0 | 2023-08-28 |  | 1
2023 | Region IV-A | CAVITE | BACOOR CITY (CAVITE) | P00742182LZ | Construction of Flood Mitigation Structure | 120.9327 | 14.4429 | 98999995.95 | 98973894.38 | 2024 | GRAIA CONSTRUCTION CORPORATION | 2697 | 2023 | 2024-03-04 | 05/03/2023 | 26101.57 | 0 | 2024-03-26 | 22
2022 | Region IV-A | CAVITE | IMUS CITY (CAVITE) | P00621096LZ | Construction of Revetment | 120.9448 | 14.4205 | 43120000 | 43120000 | 2022 | FROMARC BUILDERS & GEN. MERCHANDISE | 2698 | 2022 | 2022-08-29 | 02/24/2022 | 0 | 0 | 2022-08-28 |  | 1
2024 | Region III | PAMPANGA | SAN LUIS (PAMPANGA) | P00846003LZ | Construction of Slope Protection Structure | 120.8005 | 15.0502 | 39600000 | 37897215.45 | 2024 | R.D. TALENS CONSTRUCTION AND TRADING | 2699 | 2024 | 2024-11-22 | 04/25/2024 | 1702784.55 | 0 | 2024-11-21 |  | 1
2024 | Region III | BULACAN | SAN RAFAEL (BULACAN) | P00845989LZ | Construction of Revetment | 120.9329 | 15.0176 | 9899078.75 | 9899927.01 | 2024 | CALCON ENGINEERING | 2700 | 2024 | 2024-11-25 | 07/29/2024 | 0 | 848.26 | 2024-11-24 |  | 1
2025 | Region III | NUEVA ECIJA | SAN ISIDRO (NUEVA ECIJA) | P00921485LZ | Construction of Flood Mitigation Structure | 120.9251 | 15.3096 | 96499900.04 | 96017500.53 | 2025 | F-DEY CONSTRUCTION AND TRADING | 2701 | 2025 | 2025-04-24 | 02/20/2025 | 482399.51 | 0 | 2026-02-04 | 286
2023 | Region III | NUEVA ECIJA | TALAVERA (NUEVA ECIJA) | P00726165LZ | Construction of Flood Mitigation Structure | 120.9037 | 15.5668 | 49000000 | 48994113.37 | 2023 | AMP 723 CONSTRUCTION CORPORATION (FORMERLY: A.M.P. CONSTRUCTION) | 2702 | 2023 | 2023-10-10 | 02/13/2023 | 5886.63 | 0 | 2023-11-08 | 29
2023 | Region IV-B | OCCIDENTAL MINDORO | CALINTAAN (OCCIDENTAL MINDORO) | P00736059LZ | Construction of Flood Mitigation Structure | 120.9448 | 12.6097 | 96500000 | 96497636.2 | 2023 | JELSIE CONSTRUCTION & SUPPLY | 2703 | 2023 | 2023-10-15 | 03/11/2023 | 2363.8 | 0 | 2023-10-14 |  | 1
2024 | Region III | BULACAN | CITY OF MALOLOS (CAPITAL) (BULACAN) | P00838364LZ | Construction of Revetment | 120.8007 | 14.8387 | 62724977.17 | 62724600 | 2024 | SYMS CONSTRUCTION TRADING | 2704 | 2024 | 2024-09-30 | 03/20/2024 | 377.17 | 0 | 2024-10-14 | 14
2023 | Region IV-A | BATANGAS | LEMERY (BATANGAS) | P00726931LZ | Construction of Flood Mitigation Structure | 120.895 | 13.9204 | 96500000 | 96500000 | 2024 | AARCON BUILDERS | 2705 | 2023 | 2024-11-20 | 08/01/2023 | 0 | 0 | 2024-11-19 |  | 1
2021 | Region I | ILOCOS NORTE |  | P00561456LZ | Construction of Flood Mitigation Structure | 120.8351 | 18.5332 | 96499540.54 | 96499537.05 | 2022 | FR ESPIRITU BUILDERS AND DEVELOPMENT CORP. (FORMERLY: FR ESPIRITU JR BUILDERS) | 2706 | 2021 | 2022-07-15 | 12/24/2021 | 3.49 | 0 | 2022-10-02 | 79
2024 | Region III | BULACAN | OBANDO (BULACAN) | P00825086LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.9252 | 14.7364 | 96499997.69 | 96499979.13 | 2025 | IM CONSTRUCTION CORPORATION | 2707 | 2024 | 2025-02-26 | 06/05/2024 | 18.56 | 0 | 2025-02-25 |  | 1
2023 | Region IV-B | OCCIDENTAL MINDORO | SABLAYAN (OCCIDENTAL MINDORO) | P00736042LZ | Construction of Revetment | 120.8354 | 12.8765 | 212299999.9 | 212298471.2 | 2023 | SUNWEST, INC. (FORMERLY: SUNWEST CONSTRUCTION & DEVELOPMENT CORPORATION) | 2708 | 2023 | 2023-12-15 | 04/13/2023 | 1528.7 | 0 | 2024-05-25 | 162
2022 | Cordillera Administrative Region | BENGUET | BUGUIAS (BENGUET) | P00639460LZ | Construction of Flood Mitigation Structure | 120.801 | 16.7057 | 49000000 | 48990442.38 | 2023 | CABUGUIASAN BUILDERS | 2709 | 2022 | 2023-05-27 | 08/15/2022 | 9557.62 | 0 | 2023-05-26 |  | 1
2023 | Region III | BULACAN | PLARIDEL (BULACAN) | P00727128LZ | Construction of Flood Mitigation Structure | 120.8953 | 14.9331 | 48999900.38 | 48999700.67 | 2023 | 729 CONSTRUCTION, INC. (FORMERLY 722 CONSTRUCTION, INC.) | 2710 | 2023 | 2023-09-25 | 03/07/2023 | 199.71 | 0 | 2023-10-01 | 6
2022 | Region III | BULACAN | BOCAUE (BULACAN) | P00621533LZ | Construction of Flood Mitigation Structure | 120.9329 | 14.8094 | 24499419.14 | 24497191.23 | 2022 | TOPNOTCH CATALYST BUILDERS INC. | 2711 | 2022 | 2022-09-30 | 04/04/2022 | 2227.91 | 0 | 2022-09-29 |  | 1
2024 | Region III | NUEVA ECIJA | SAN ISIDRO (NUEVA ECIJA) | P00839586LZ | Construction of Drainage Structure | 120.904 | 15.3113 | 4949990.75 | 4875082.5 | 2024 | TRIPLE S BUILDERS INC. | 2712 | 2024 | 2024-12-20 | 02/16/2024 | 74908.25 | 0 | 2024-12-19 |  | 1
2023 | National Capital Region | VALENZUELA CITY | CITY OF VALENZUELA (METROPOLITAN MANILA) | P00726806LZ | Construction of Flood Mitigation Structure | 120.945 | 14.7127 | 96494257.32 | 94371376.95 | 2024 | TOUGHBUILT CONSTRUCTION & TRADING, INC. | 2713 | 2023 | 2024-06-11 | 04/20/2023 | 2122880.37 | 0 | 2024-06-11 | 0
2023 | Region IV-A | CAVITE | TANZA (CAVITE) | P00742181LZ | Construction of Flood Mitigation Structure | 120.8021 | 14.3701 | 49500000 | 49478805.76 | 2023 | TRIPLE 8 CONSTRUCTION & SUPPLY, INC. (FORMERLY TRIPLE 8 CONST. & SUPPLY) | 2714 | 2023 | 2023-12-31 | 04/11/2023 | 21194.24 | 0 | 2023-12-30 |  | 1
2023 | Region III | BULACAN | BUSTOS (BULACAN) | P00726721LZ | Construction of Flood Mitigation Structure | 120.933 | 14.96 | 48999788.21 | 48999985.43 | 2023 | WAWAO BUILDERS | 2715 | 2023 | 2023-07-03 | 02/06/2023 | 0 | 197.22 | 2023-09-02 | 61
2023 | Region III | BULACAN | BUSTOS (BULACAN) | P00726458LZ | Construction of Flood Mitigation Structure | 120.9252 | 14.9605 | 96499408.05 | 96499992.4 | 2023 | JTC CRUZ CONSTRUCTION CO., INC. | 2716 | 2023 | 2023-07-03 | 02/13/2023 | 0 | 584.35 | 2023-12-08 | 158
2022 | Region III | BULACAN | BALAGTAS (BIGAA) (BULACAN) | P00621286LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.9044 | 14.8194 | 69478084.33 | 69479572.96 | 2023 | R2A CONSTRUCTION & TRADING CORPORATION | 2717 | 2022 | 2023-01-29 | 04/05/2022 | 0 | 1488.63 | 2023-01-28 |  | 1
2022 | National Capital Region | MALABON CITY | CITY OF MALABON (METROPOLITAN MANILA) | P00620345LZ | Construction of Flood Mitigation Structure | 120.9451 | 14.6872 | 48987115.38 | 49000000 | 2022 | AKN CONSTRUCTION CORPORATION | 2718 | 2022 | 2022-10-26 | 02/14/2022 | 0 | 12884.62 | 2022-10-25 |  | 1
2021 | Cordillera Administrative Region | BENGUET |  | P00526377LZ | Construction of Flood Mitigation Structure | 120.836 | 16.7477 | 29400000 | 29400000 | 2022 | NORJOHN CONSTRUCTION | 2719 | 2021 | 2022-09-29 | 02/27/2022 | 0 | 0 | 2022-09-28 |  | 1
2024 | Region III | BULACAN | BUSTOS (BULACAN) | P00821577LZ | Construction of Flood Mitigation Structure | 120.8954 | 14.9331 | 48999906.9 | 48999725.3 | 2024 | WBX CONSTRUCTION, INC (FORMERLY WBX CONSTRUCTION) | 2720 | 2024 | 2024-09-23 | 04/18/2024 | 181.6 | 0 | 2024-12-12 | 80
2022 | Cordillera Administrative Region | MOUNTAIN PROVINCE | TADIAN (MOUNTAIN PROVINCE) | P00630930LZ | Construction of Flood Mitigation Structure | 120.8364 | 16.9544 | 96499999.4 | 96500000 | 2023 | OLSIM CONSTRUCTION / BALLIGI CONSTRUCTION DEVELOPMENT CORPORATION (FORMERLY:BALLIGI CONSTRUCTION / RODEKOM GENERAL CONSTRUCTION AND ENTERPRISE | 2721 | 2022 | 2023-01-03 | 03/01/2022 | 0 | 0.6 | 2023-01-02 |  | 1
2023 | Region III | PAMPANGA | CANDABA (PAMPANGA) | P00726888LZ | Construction of Slope Protection Structure | 120.9331 | 15.1229 | 144749616.9 | 144750000 | 2024 | STO. CRISTO CONSTRUCTION & TRADING INC. (FOR: STO. CRISTO CONSTRUCTION & TRADING) / DAUNGAN CONSTRUCTION DEV'T. & GEN. SUPPLIES CO., INC. | 2722 | 2023 | 2024-05-16 | 08/21/2023 | 0 | 383.1 | 2024-05-15 |  | 1
2022 | National Capital Region | MALABON CITY | CITY OF MALABON (METROPOLITAN MANILA) | P00621153LZ | Construction of Flood Mitigation Structure | 120.9252 | 14.7021 | 58792739.32 | 57900000 | 2022 | A.L. SALAZAR CONSTRUCTION, INC. | 2723 | 2022 | 2022-11-18 | 03/24/2022 | 892739.32 | 0 | 2022-11-17 |  | 1
2024 | National Capital Region | NAVOTAS CITY | CITY OF NAVOTAS (METROPOLITAN MANILA) | P00820529LZ | Construction of Drainage Structure | 120.9454 | 14.6629 | 48999809.05 | 48999918.01 | 2024 | IM CONSTRUCTION CORPORATION | 2724 | 2024 | 2024-12-09 | 02/12/2024 | 0 | 108.96 | 2025-02-04 | 57
2022 | Region III | BULACAN | CITY OF BALIUAG (BULACAN) | P00639470LZ | Construction of Flood Mitigation Structure | 120.8955 | 14.9407 | 49499858.85 | 47519329.41 | 2022 | WAWAO BUILDERS / SYMS CONSTRUCTION TRADING | 2725 | 2022 | 2022-11-04 | 04/05/2022 | 1980529.44 | 0 | 2022-11-29 | 25
2022 | National Capital Region | MALABON CITY | CITY OF MALABON (METROPOLITAN MANILA) | P00620347LZ | Construction of Flood Mitigation Structure | 120.9253 | 14.6949 | 48942382.1 | 49000000 | 2022 | MEGAY CONSTRUCTION INC. (FORMERLY: MEGAY CONSTRUCTION) | 2726 | 2022 | 2022-10-11 | 02/14/2022 | 0 | 57617.9 | 2022-10-10 |  | 1
2021 | National Capital Region | NAVOTAS CITY |  | P00561465LZ | Construction of Flood Mitigation Structure | 120.9336 | 14.6797 | 68594595.17 | 67504048.83 | 2022 | IM CONSTRUCTION CORPORATION | 2727 | 2021 | 2022-11-16 | 11/15/2021 | 1090546.34 | 0 | 2022-12-06 | 20
2023 | Region IV-B | OCCIDENTAL MINDORO | SABLAYAN (OCCIDENTAL MINDORO) | P00726262LZ | Construction of Flood Mitigation Structure | 120.8365 | 12.9192 | 45080000 | 45078037.4 | 2023 | YPR GEN. CONTRACTOR AND CONSTRUCTION SUPPLY INC. | 2728 | 2023 | 2023-08-22 | 02/10/2023 | 1962.6 | 0 | 2023-09-05 | 14
2022 | Region IV-A | CAVITE | IMUS CITY (CAVITE) | P00637079LZ | Construction of Drainage Structure | 120.9454 | 14.4136 | 4900000 | 4900000 | 2022 | R2A CONSTRUCTION & TRADING CORPORATION | 2729 | 2022 | 2022-09-05 | 03/31/2022 | 0 | 0 | 2022-09-13 | 8
2023 | Cordillera Administrative Region | MOUNTAIN PROVINCE | BAUKO (MOUNTAIN PROVINCE) | P00736184LZ | Construction of Flood Mitigation Structure | 120.8956 | 16.8814 | 48999999.5 | 49000000 | 2023 | OLSIM CONSTRUCTION / RODEKOM GENERAL CONSTRUCTION AND ENTERPRISE | 2730 | 2023 | 2023-08-23 | 02/20/2023 | 0 | 0.5 | 2023-09-08 | 16
2024 | Region III | BULACAN | PANDI (BULACAN) | P00838387LZ | Construction of Slope Protection Structure | 120.9047 | 14.8817 | 96499868.11 | 96499404.34 | 2024 | M.S. RAMOS CONSTRUCTION INC. (FORMERLY: M.S. RAMOS | 2731 | 2024 | 2024-11-02 | 02/07/2024 | 463.77 | 0 | 2024-11-01 |  | 1
2022 | Region IV-A | BATANGAS | MABINI (BATANGAS) | P00631281LZ | Construction of Flood Mitigation Structure | 120.9047 | 13.7431 | 19600000 | 14550732.41 | 2022 | W. RIVERA CONST. AND EQUIPT. RENTALS, INC. (FORMERLY: W. RIVERA CONSTRUCTION & EQUIPMENT RENTALS) | 2732 | 2022 | 2022-09-17 | 03/30/2022 | 5049267.59 | 0 | 2022-09-16 |  | 1
2024 | Region III | PAMPANGA | CANDABA (PAMPANGA) | P00820254LZ | Construction of Flood Mitigation Structure | 120.837 | 15.0875 | 83535225 | 78857241.02 | 2024 | STO. CRISTO CONSTRUCTION & TRADING INC. (FOR: STO. CRISTO CONSTRUCTION & TRADING) | 2733 | 2024 | 2024-10-21 | 03/01/2024 | 4677983.98 | 0 | 2024-10-20 |  | 1
2024 | Region III | BULACAN | BUSTOS (BULACAN) | P00825071LZ | Construction of Flood Mitigation Structure | 120.8957 | 14.9338 | 77199978.6 | 77199080.42 | 2024 | TOPNOTCH CATALYST BUILDERS INC. | 2734 | 2024 | 2024-08-29 | 04/23/2024 | 898.18 | 0 | 2024-12-17 | 110
2024 | Region III | BULACAN | BALAGTAS (BIGAA) (BULACAN) | P00823406LZ | Construction of Flood Mitigation Structure | 120.9254 | 14.8338 | 77199806.99 | 77199558.49 | 2024 | MRB11 CONSTRUCTION CORPORATION (FORMERLY:MRB CONS | 2735 | 2024 | 2024-11-05 | 03/11/2024 | 248.5 | 0 | 2024-11-04 |  | 1
2022 | Region III | BULACAN | BOCAUE (BULACAN) | P00639352LZ | Construction of Slope Protection Structure | 120.9336 | 14.8093 | 57899164.78 | 57899155.37 | 2023 | M3 KONSTRACT CORPORATION (FORMERLY:MARGARITA CONSTRUCTION) | 2736 | 2022 | 2023-01-27 | 04/04/2022 | 9.41 | 0 | 2023-01-27 | 0
2023 | Region III | BULACAN | CITY OF MEYCAUAYAN (BULACAN) | P00726727LZ | Construction of Flood Mitigation Structure | 120.9456 | 14.7397 | 48999460.17 | 48999966.54 | 2023 | TRIPLE 8 CONSTRUCTION & SUPPLY, INC. (FORMERLY TRIPLE 8 CONST. & SUPPLY) | 2737 | 2023 | 2023-08-12 | 02/22/2023 | 0 | 506.37 | 2023-08-11 |  | 1
2024 | Region IV-B | OCCIDENTAL MINDORO | SABLAYAN (OCCIDENTAL MINDORO) | P00824746LZ | Construction of Flood Mitigation Structure | 120.8959 | 12.9402 | 24500000 | 24499178.88 | 2024 | J.H.R. ENTERPRISES | 2738 | 2024 | 2024-09-07 | 03/06/2024 | 821.12 | 0 | 2024-09-06 |  | 1
2023 | Region III | PAMPANGA | CANDABA (PAMPANGA) | P00726892LZ | Construction of Flood Mitigation Structure | 120.8372 | 15.0879 | 96500000 | 91095254.13 | 2024 | STO. CRISTO CONSTRUCTION & TRADING INC. (FOR: STO. CRISTO CONSTRUCTION & TRADING) | 2739 | 2023 | 2024-02-11 | 04/20/2023 | 5404745.87 | 0 | 2024-02-10 |  | 1
2022 | Region III | NUEVA ECIJA | SAN ISIDRO (NUEVA ECIJA) | P00621578LZ | Construction of Flood Mitigation Structure | 120.9048 | 15.3123 | 72374980.66 | 63685822.86 | 2023 | JPB CONSTRUCTION / FRAMECON BUILDERS | 2740 | 2022 | 2023-12-24 | 04/05/2022 | 8689157.8 | 0 | 2022-12-23 |  | 366
2024 | National Capital Region | MALABON CITY | CITY OF MALABON (METROPOLITAN MANILA) | P00839459LZ | Construction of Flood Mitigation Structure | 120.9457 | 14.6785 | 59353337.37 | 59399880.03 | 2024 | A.L. SALAZAR CONSTRUCTION, INC. / ROTAFLEX CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY:ROTA FLEX CONSTRUCTION) | 2741 | 2024 | 2024-09-20 | 02/21/2024 | 0 | 46542.66 | 2024-12-15 | 86
2023 | National Capital Region | MALABON CITY | CITY OF MALABON (METROPOLITAN MANILA) | P00725923LZ | Construction of Flood Mitigation Structure | 120.9255 | 14.6998 | 48998795.7 | 49000000 | 2023 | GREAT PACIFIC BUILDERS AND GEN. CONTRACTOR INC. | 2742 | 2023 | 2023-10-12 | 02/15/2023 | 0 | 1204.3 | 2023-10-11 |  | 1
2024 | Region III | BULACAN | OBANDO (BULACAN) | P00844745LZ | Construction of Flood Mitigation Structure | 120.9337 | 14.7024 | 48999963.58 | 48998769.87 | 2024 | JB CONSTRUCTION AND SUPPLY INC. (FORMERLY:JB CONSTRUCTION AND SUPPLY) | 2743 | 2024 | 2024-09-10 | 03/14/2024 | 1193.71 | 0 | 2024-09-09 |  | 1
2023 | Region I | ILOCOS NORTE | PAGUDPUD (ILOCOS NORTE) | P00740562LZ | Construction of Flood Mitigation Structure | 120.8376 | 18.6222 | 48999699.95 | 48999699.11 | 2023 | 11-16 CONSTRUCTION | 2744 | 2023 | 2023-12-06 | 05/05/2023 | 0.84 | 0 | 2024-01-07 | 32
2023 | Region III | BULACAN | BALAGTAS (BIGAA) (BULACAN) | P00726492LZ | Construction of Flood Mitigation Structure | 120.9054 | 14.8127 | 96499358.66 | 96498811.15 | 2023 | AZUL BUILDERS / JB CONSTRUCTION AND SUPPLY INC. (FORMERLY:JB CONSTRUCTION AND SUPPLY) | 2745 | 2023 | 2023-07-26 | 02/13/2023 | 547.51 | 0 | 2023-12-08 | 135
2024 | National Capital Region | MALABON CITY | CITY OF MALABON (METROPOLITAN MANILA) | P00820550LZ | Construction of Flood Mitigation Structure | 120.9458 | 14.6785 | 45329878.09 | 45332528.34 | 2024 | ROTAFLEX CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY:ROTA FLEX CONSTRUCTION) | 2746 | 2024 | 2024-10-09 | 02/21/2024 | 0 | 2650.25 | 2024-11-15 | 37
2024 | Region III | BULACAN | BUSTOS (BULACAN) | P00821576LZ | Construction of Flood Mitigation Structure | 120.9339 | 14.9599 | 48999914.7 | 48999739.43 | 2024 | WRO CONST. CORP. / GRACE CONSTRUCTION CORPORATION | 2747 | 2024 | 2024-08-20 | 04/18/2024 | 175.27 | 0 | 2024-12-12 | 114
2023 | National Capital Region | NAVOTAS CITY | CITY OF NAVOTAS (METROPOLITAN MANILA) | P00742228LZ | Construction of Flood Mitigation Structure | 120.9345 | 14.6748 | 21779824.36 | 21778384.66 | 2024 | 721 BUILDERS CORPORATION | 2748 | 2023 | 2024-06-30 | 03/27/2023 | 1439.7 | 0 | 2024-06-29 |  | 1
2023 | Region IV-A | CAVITE | IMUS CITY (CAVITE) | P00726554LZ | Construction of Revetment | 120.9056 | 14.3931 | 91675000 | 91675000 | 2024 | FROMARC BUILDERS & GEN. MERCHANDISE | 2749 | 2023 | 2024-01-01 | 04/02/2023 | 0 | 0 | 2023-12-31 |  | 1
2023 | Region IV-A | CAVITE | IMUS CITY (CAVITE) | P00745428LZ | Construction of Revetment | 120.9459 | 14.3695 | 38971525 | 38971524.94 | 2024 | G.F. FABIAN CONSTRUCTION | 2750 | 2023 | 2024-01-03 | 07/03/2023 | 0.06 | 0 | 2024-01-02 |  | 1
2024 | Region IV-A | BATANGAS | AGONCILLO (BATANGAS) | P00820372LZ | Construction of Flood Mitigation Structure | 120.9346 | 13.9212 | 86850000 | 57263814.85 | 2024 | V.R. PATRON BUILDERS & DEVELOPERS CORP. (PREVIOUSL | 2751 | 2024 | 2024-09-09 | 04/03/2024 | 29586185.15 | 0 | 2025-01-26 | 139
2024 | Region IV-B | OCCIDENTAL MINDORO | CALINTAAN (OCCIDENTAL MINDORO) | P00820397LZ | Construction of Flood Mitigation Structure | 120.946 | 12.6468 | 191070000 | 191067795.2 | 2024 | MARCBILT CONSTRUCTION, INC. | 2752 | 2024 | 2024-08-15 | 03/02/2024 | 2204.8 | 0 | 2025-02-23 | 192
2022 | Region III | BULACAN | BALAGTAS (BIGAA) (BULACAN) | P00639472LZ | Construction of Slope Protection Structure | 120.9057 | 14.813 | 29399973.33 | 29390679.34 | 2022 | 729 CONSTRUCTION, INC. (FORMERLY 722 CONSTRUCTION, INC.) | 2753 | 2022 | 2022-09-01 | 04/05/2022 | 9293.99 | 0 | 2022-08-31 |  | 1
2023 | National Capital Region | NAVOTAS CITY | CITY OF NAVOTAS (METROPOLITAN MANILA) | P00742220LZ | Construction of Flood Mitigation Facility | 120.9347 | 14.6761 | 24745215.8 | 24746253.23 | 2023 | 5-1 CONSTRUCTION CORPORATION | 2754 | 2023 | 2023-11-21 | 03/27/2023 | 0 | 1037.43 | 2023-11-20 |  | 1
2023 | Region IV-B | OCCIDENTAL MINDORO | CALINTAAN (OCCIDENTAL MINDORO) | P00740425LZ | Construction of Flood Mitigation Structure | 120.9461 | 12.6117 | 192999992 | 192981036.1 | 2023 | MARCBILT CONSTRUCTION, INC. / SAN MARCELINO BUILDERS, INC. | 2755 | 2023 | 2023-12-10 | 04/13/2023 | 18955.9 | 0 | 2024-04-05 | 117
2022 | Region III | BULACAN | BALAGTAS (BIGAA) (BULACAN) | P00621280LZ | Construction of Slope Protection Structure | 120.9057 | 14.8125 | 67549623.79 | 67548651.76 | 2022 | DMLC BUILDERS | 2756 | 2022 | 2022-12-29 | 04/04/2022 | 972.03 | 0 | 2022-12-28 |  | 1
2022 | Region III | BULACAN | SAN RAFAEL (BULACAN) | P00620152LZ | Construction of Flood Mitigation Structure | 120.9347 | 15.0182 | 55004786.39 | 48173390.52 | 2022 | EIRISH BUILDERS & SUPPLY INC. | 2757 | 2022 | 2022-10-05 | 03/07/2022 | 6831395.87 | 0 | 2022-10-04 |  | 1
2023 | Region IV-A | CAVITE | BACOOR CITY (CAVITE) | P00725813LZ | Construction of Revetment | 120.9461 | 14.4567 | 86849994.61 | 86849658.99 | 2023 | ALMAKAR BUILDERS & METAL WORKS | 2758 | 2023 | 2023-12-29 | 02/15/2023 | 335.62 | 0 | 2024-01-01 | 3
2022 | Region III | BULACAN | CITY OF BALIUAG (BULACAN) | P00632811LZ | Construction of Drainage Structure | 120.9057 | 14.9624 | 19799143.86 | 19799997.15 | 2022 | WBX CONSTRUCTION, INC (FORMERLY WBX CONSTRUCTION) | 2759 | 2022 | 2022-10-11 | 02/14/2022 | 0 | 853.29 | 2022-10-10 |  | 1
2023 | Region IV-A | BATANGAS | LEMERY (BATANGAS) | P00742384LZ | Construction of Flood Mitigation Structure | 120.906 | 13.8966 | 9898760 | 9601500 | 2023 | VICMAR CONSTRUCTION, INC. | 2760 | 2023 | 2023-07-20 | 03/23/2023 | 297260 | 0 | 2023-07-19 |  | 1
2022 | Region IV-A | BATANGAS | LAUREL (BATANGAS) | P00620561LZ | Construction of Flood Mitigation Structure | 120.9349 | 14.0479 | 38952060 | 38947059.61 | 2022 | V.R. PATRON BUILDERS & DEVELOPERS CORP. (PREVIOUSL | 2761 | 2022 | 2022-10-11 | 02/04/2022 | 5000.39 | 0 | 2022-10-10 |  | 1
2024 | Region III | BULACAN | BALAGTAS (BIGAA) (BULACAN) | P00820228LZ | Construction of Flood Mitigation Structure | 120.9063 | 14.8254 | 151504915.2 | 151504905.3 | 2024 | WAWAO BUILDERS | 2762 | 2024 | 2024-09-30 | 04/23/2024 | 9.9 | 0 | 2025-01-16 | 108
2022 | National Capital Region | NAVOTAS CITY | CITY OF NAVOTAS (METROPOLITAN MANILA) | P00639402LZ | Rehabilitation / Major Repair of Drainage Structure | 120.935 | 14.6732 | 1955438.57 | 1959713.52 | 2022 | SAMARAH CONSTRUCTION AND SUPPLY | 2763 | 2022 | 2022-08-12 | 03/24/2022 | 0 | 4274.95 | 2022-09-18 | 37
2024 | Region IV-A | CAVITE | IMUS CITY (CAVITE) | P00821334LZ | Construction of Revetment | 120.9065 | 14.3859 | 96500000 | 95536158.53 | 2024 | FROMARC BUILDERS & GEN. MERCHANDISE | 2764 | 2024 | 2024-11-16 | 02/14/2024 | 963841.47 | 0 | 2024-11-15 |  | 1
2023 | Region III | NUEVA ECIJA | TALAVERA (NUEVA ECIJA) | P00742128LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.9072 | 15.5744 | 99000000 | 98995000 | 2023 | AMP 723 CONSTRUCTION CORPORATION (FORMERLY: A.M.P. CONSTRUCTION) / KEVIN PAUL CONSTRUCTION | 2765 | 2023 | 2023-11-17 | 04/11/2023 | 5000 | 0 | 2024-01-04 | 48
2022 | Region III | BULACAN | CITY OF BALIUAG (BULACAN) | P00631176LZ | Construction of Flood Mitigation Structure | 120.9076 | 14.9564 | 45079268.16 | 45073035.02 | 2022 | TBB CONSTRUCTION CORP. | 2766 | 2022 | 2022-11-28 | 03/04/2022 | 6233.14 | 0 | 2022-11-27 |  | 1
2023 | Region IV-B | OCCIDENTAL MINDORO | SABLAYAN (OCCIDENTAL MINDORO) | P00726260LZ | Construction of Flood Mitigation Structure | 120.9076 | 12.8976 | 45080000 | 45079616.63 | 2023 | KEJAMARENIK CONSTRUCTION & CONSTRUCTION SUPPLIES | 2767 | 2023 | 2023-09-17 | 02/10/2023 | 383.37 | 0 | 2023-09-16 |  | 1
2023 | Region III | NUEVA ECIJA | SANTO DOMINGO (NUEVA ECIJA) | P00725707LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.9077 | 15.5848 | 96500000 | 96495000 | 2023 | AMP 723 CONSTRUCTION CORPORATION (FORMERLY: A.M.P. CONSTRUCTION) / KEVIN PAUL CONSTRUCTION | 2768 | 2023 | 2023-09-04 | 02/22/2023 | 5000 | 0 | 2023-11-17 | 74
2023 | Region III | BULACAN | BALAGTAS (BIGAA) (BULACAN) | P00740589LZ | Construction of Flood Mitigation Structure | 120.9084 | 14.8135 | 48999715.39 | 48998428.1 | 2023 | 11-16 CONSTRUCTION | 2769 | 2023 | 2023-12-13 | 03/21/2023 | 1287.29 | 0 | 2023-12-14 | 1
2023 | Region III | PAMPANGA | CANDABA (PAMPANGA) | P00726925LZ | Rehabilitation / Major Repair of Slope Protection Structure | 120.9086 | 15.044 | 96500000 | 91192428.63 | 2024 | EDDMARI CONSTRUCTION & TRADING | 2770 | 2023 | 2024-06-07 | 08/16/2023 | 5307571.37 | 0 | 2024-06-07 | 0
2024 | Region III | PAMPANGA | CANDABA (PAMPANGA) | P00820255LZ | Construction of Slope Protection Structure | 120.9088 | 15.1211 | 83472500 | 78798026.13 | 2024 | STO. CRISTO CONSTRUCTION & TRADING INC. (FOR: STO. CRISTO CONSTRUCTION & TRADING) | 2771 | 2024 | 2024-11-01 | 03/12/2024 | 4674473.87 | 0 | 2024-10-31 |  | 1
2023 | Region III | PAMPANGA | CANDABA (PAMPANGA) | P00726917LZ | Construction of Slope Protection Structure | 120.9089 | 15.1215 | 72375000 | 68394358.97 | 2024 | STO. CRISTO CONSTRUCTION & TRADING INC. (FOR: STO. CRISTO CONSTRUCTION & TRADING) | 2772 | 2023 | 2024-04-25 | 08/16/2023 | 3980641.03 | 0 | 2024-04-24 |  | 1
2022 | Region III | BULACAN | BALAGTAS (BIGAA) (BULACAN) | P00630944LZ | Construction of Flood Mitigation Structure | 120.9089 | 14.8125 | 62724868.57 | 62724996.89 | 2022 | L.R. TIQUI BUILDERS, INC. | 2773 | 2022 | 2022-11-20 | 02/24/2022 | 0 | 128.32 | 2022-11-19 |  | 1
2023 | Region IV-A | BATANGAS | LEMERY (BATANGAS) | P00742383LZ | Construction of Flood Mitigation Structure | 120.909 | 13.8972 | 5940000 | 5940000 | 2023 | OMNICON BUILDERS | 2774 | 2023 | 2023-08-31 | 05/04/2023 | 0 | 0 | 2023-08-30 |  | 1
2023 | Region III | PAMPANGA | CANDABA (PAMPANGA) | P00740329LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.909 | 15.1219 | 96500000 | 91095547.48 | 2024 | STO. CRISTO CONSTRUCTION & TRADING INC. (FOR: STO. CRISTO CONSTRUCTION & TRADING) | 2775 | 2023 | 2024-02-15 | 04/24/2023 | 5404452.52 | 0 | 2024-02-14 |  | 1
2024 | Cordillera Administrative Region | MOUNTAIN PROVINCE | SABANGAN (MOUNTAIN PROVINCE) | P00821544LZ | Construction of Flood Mitigation Structure | 120.9092 | 17.0079 | 19599999.5 | 19600000 | 2024 | DD LIKIGAN CONSTRUCTION | 2776 | 2024 | 2024-06-07 | 02/18/2024 | 0 | 0.5 | 2024-06-06 |  | 1
2024 | Region III | PAMPANGA | CANDABA (PAMPANGA) | P00820256LZ | Construction of Slope Protection Structure | 120.9094 | 15.1204 | 83472500 | 78798035.64 | 2024 | STO. CRISTO CONSTRUCTION & TRADING INC. (FOR: STO. CRISTO CONSTRUCTION & TRADING) | 2777 | 2024 | 2024-11-01 | 03/12/2024 | 4674464.36 | 0 | 2024-10-31 |  | 1
2024 | Region III | BULACAN | CITY OF MEYCAUAYAN (BULACAN) | P00823401LZ | Construction of Flood Mitigation Structure | 120.9095 | 14.759 | 96499639.1 | 96499969.85 | 2025 | M3 KONSTRACT CORPORATION (FORMERLY:MARGARITA CONSTRUCTION) | 2778 | 2024 | 2025-02-20 | 03/14/2024 | 0 | 330.75 | 2025-04-20 | 59
2024 | Region III | BULACAN | CITY OF MEYCAUAYAN (BULACAN) | P00823403LZ | Construction of Flood Mitigation Structure | 120.9097 | 14.7608 | 96499814.82 | 96499750.1 | 2025 | M3 KONSTRACT CORPORATION (FORMERLY:MARGARITA CONSTRUCTION) | 2779 | 2024 | 2025-01-06 | 03/14/2024 | 64.72 | 0 | 2025-04-20 | 104
2023 | Region III | PAMPANGA | CANDABA (PAMPANGA) | P00726916LZ | Construction of Slope Protection Structure | 120.9099 | 15.1234 | 72375000 | 70203736.33 | 2023 | GREAT PACIFIC BUILDERS AND GEN. CONTRACTOR INC. | 2780 | 2023 | 2023-12-21 | 04/12/2023 | 2171263.67 | 0 | 2023-12-20 |  | 1
2024 | Region III | BULACAN | CITY OF MEYCAUAYAN (BULACAN) | P00823402LZ | Construction of Flood Mitigation Structure | 120.91 | 14.7572 | 96499652.61 | 96499989.7 | 2025 | M3 KONSTRACT CORPORATION (FORMERLY:MARGARITA CONSTRUCTION) | 2781 | 2024 | 2025-02-20 | 03/14/2024 | 0 | 337.09 | 2025-03-08 | 16
2022 | Region III | NUEVA ECIJA | JAEN (NUEVA ECIJA) | P00644777LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.91 | 15.3835 | 17427890.13 | 17237694.73 | 2023 | F-DEY CONSTRUCTION AND TRADING | 2782 | 2022 | 2023-08-30 | 03/20/2023 | 190195.4 | 0 | 2023-10-14 | 45
2022 | Region IV-A | CAVITE | KAWIT (CAVITE) | P00621097LZ | Construction of Revetment | 120.9102 | 14.4482 | 43547280 | 43547280 | 2022 | HONEYVILLECONST AND DEVELOPMENT CORPORATION | 2783 | 2022 | 2022-08-30 | 02/24/2022 | 0 | 0 | 2022-08-29 |  | 1
2024 | Region IV-B | ORIENTAL MINDORO | PUERTO GALERA (ORIENTAL MINDORO) | P00825129LZ | Construction of Drainage Structure | 120.9103 | 13.5058 | 54450000 | 53074970.85 | 2025 | L.N. SALVADOR CONSTRUCTION CORP. (FOR: L.N. SALVADOR CONSTRUCTION) | 2784 | 2024 | 2025-04-02 | 02/08/2024 | 1375029.15 | 0 | 2025-04-01 |  | 1
2023 | Region III | BULACAN | CITY OF BALIUAG (BULACAN) | P00727280LZ | Construction of Flood Mitigation Structure | 120.9104 | 14.9629 | 72374988.4 | 72373243.31 | 2023 | DARCY & ANNA BUILDERS & TRADING | 2785 | 2023 | 2023-12-08 | 03/14/2023 | 1745.09 | 0 | 2023-12-07 |  | 1
2024 | Region III | BULACAN | CITY OF MEYCAUAYAN (BULACAN) | P00838341LZ | Construction of Flood Mitigation Structure | 120.9105 | 14.7562 | 97999204.42 | 96499973.82 | 2024 | L.R. TIQUI BUILDERS, INC. | 2786 | 2024 | 2024-12-28 | 02/22/2024 | 1499230.6 | 0 | 2024-12-27 |  | 1
2023 | Region III | BULACAN | OBANDO (BULACAN) | P00726731LZ | Construction of Flood Mitigation Structure | 120.9107 | 14.7466 | 28418777.98 | 28419783.13 | 2023 | HALREY CONSTRUCTION INC. | 2787 | 2023 | 2023-07-27 | 02/27/2023 | 0 | 1005.15 | 2023-07-26 |  | 1
2024 | Region III | BULACAN | CITY OF MEYCAUAYAN (BULACAN) | P00838340LZ | Construction of Flood Mitigation Structure | 120.9112 | 14.7543 | 97999751.16 | 96499880.38 | 2024 | L.R. TIQUI BUILDERS, INC. | 2788 | 2024 | 2024-12-20 | 02/14/2024 | 1499870.78 | 0 | 2024-12-19 |  | 1
2023 | Region III | BULACAN | CITY OF MEYCAUAYAN (BULACAN) | P00725715LZ | Construction of Flood Mitigation Structure | 120.9113 | 14.753 | 96498946.24 | 96499601.54 | 2024 | L.R. TIQUI BUILDERS, INC. | 2789 | 2023 | 2024-01-22 | 02/27/2023 | 0 | 655.3 | 2024-01-21 |  | 1
2022 | Region III | NUEVA ECIJA | SAN LEONARDO (NUEVA ECIJA) | P00620840LZ | Construction of Flood Mitigation Structure | 120.9118 | 15.3408 | 74427940.69 | 74428469.97 | 2022 | FRAMECON BUILDERS | 2790 | 2022 | 2022-11-27 | 03/02/2022 | 0 | 529.28 | 2022-11-26 |  | 1
2024 | Region III | BULACAN | BUSTOS (BULACAN) | P00839576LZ | Construction of Drainage Structure | 120.9122 | 14.9556 | 9899302.8 | 9899242.37 | 2024 | PLL BUILDERS INC. | 2791 | 2024 | 2024-08-08 | 04/25/2024 | 60.43 | 0 | 2024-08-21 | 13
2023 | Region III | PAMPANGA | CANDABA (PAMPANGA) | P00726910LZ | Construction of Slope Protection Structure | 120.9122 | 15.0463 | 72375000 | 70203652.16 | 2024 | NES-SAN BUILDERS | 2792 | 2023 | 2024-05-23 | 03/22/2023 | 2171347.84 | 0 | 2024-06-14 | 22
2023 | Region III | PAMPANGA | CANDABA (PAMPANGA) | P00726889LZ | Construction of Slope Protection Structure | 120.9124 | 15.1263 | 144749318.9 | 144750000 | 2024 | STO. CRISTO CONSTRUCTION & TRADING INC. (FOR: STO. CRISTO CONSTRUCTION & TRADING) | 2793 | 2023 | 2024-05-16 | 08/21/2023 | 0 | 681.1 | 2024-05-15 |  | 1
2023 | Region IV-A | BATANGAS | SAN LUIS (BATANGAS) | P00725778LZ | Construction of Flood Mitigation Structure | 120.9124 | 13.8263 | 67550000 | 67550000 | 2023 | VICMAR CONSTRUCTION, INC. | 2794 | 2023 | 2023-10-14 | 02/14/2023 | 0 | 0 | 2023-10-13 |  | 1
2024 | Region III | BULACAN | OBANDO (BULACAN) | P00820247LZ | Construction of Dike | 120.9125 | 14.7422 | 144749833.4 | 144749396.6 | 2024 | HALREY CONSTRUCTION INC. | 2795 | 2024 | 2024-09-11 | 02/22/2024 | 436.8 | 0 | 2024-11-17 | 67
2024 | Region III | NUEVA ECIJA | TALAVERA (NUEVA ECIJA) | P00823428LZ | Construction of Flood Mitigation Structure | 120.9126 | 15.5872 | 72375000 | 71651197.07 | 2024 | SPECO BUILDERS INC. (FORMERLY VRF CONSTRUCTION) | 2796 | 2024 | 2024-08-12 | 03/19/2024 | 723802.93 | 0 | 2024-11-12 | 92
2023 | Region IV-A | BATANGAS | TAAL (BATANGAS) | P00727310LZ | Construction of Flood Mitigation Structure | 120.9133 | 13.899 | 72375000 | 72375000 | 2024 | BICOL GOLDROCK CONSTRUCTION CORPORATION | 2797 | 2023 | 2024-03-04 | 05/24/2023 | 0 | 0 | 2024-03-19 | 15
2022 | Region III | BULACAN | BUSTOS (BULACAN) | P00631177LZ | Construction of Flood Mitigation Structure | 120.9133 | 14.9636 | 45079929.58 | 45079980.9 | 2022 | JB CONSTRUCTION AND SUPPLY INC. (FORMERLY:JB CONSTRUCTION AND SUPPLY) | 2798 | 2022 | 2022-10-27 | 04/01/2022 | 0 | 51.32 | 2022-10-26 |  | 1
2024 | Region III | NUEVA ECIJA | SANTO DOMINGO (NUEVA ECIJA) | P00823472LZ | Construction of Flood Mitigation Structure | 120.9135 | 15.6704 | 48250000 | 47767129 | 2024 | DGSARM BUILDERS INC. (FORMERLY: D.G. SARMENTA CONSTRUCTION) | 2799 | 2024 | 2024-12-03 | 05/08/2024 | 482871 | 0 | 2024-12-02 |  | 1
2023 | Region IV-A | CAVITE | IMUS CITY (CAVITE) | P00742170LZ | Construction of Flood Mitigation Structure | 120.9139 | 14.3742 | 99000000 | 99000000 | 2024 | OMNICON BUILDERS | 2800 | 2023 | 2024-02-19 | 04/11/2023 | 0 | 0 | 2024-02-18 |  | 1
2024 | Region III | BULACAN | GUIGUINTO (BULACAN) | P00845976LZ | Construction of Flood Mitigation Structure | 120.873 | 14.8472 | 39599692.14 | 39599067.05 | 2024 | TOPNOTCH CATALYST BUILDERS INC. | 2801 | 2024 | 2024-08-14 | 02/28/2024 | 625.09 | 0 | 2024-08-24 | 10
2024 | Region III | BULACAN | GUIGUINTO (BULACAN) | P00838408LZ | Construction of Slope Protection Structure | 120.8733 | 14.8545 | 96499938.94 | 96499556.14 | 2024 | TOPNOTCH CATALYST BUILDERS INC. | 2802 | 2024 | 2024-08-28 | 02/07/2024 | 382.8 | 0 | 2024-11-01 | 65
2022 | Region I | PANGASINAN | UMINGAN (PANGASINAN) | P00620463LZ | Construction of Revetment | 120.8733 | 15.9281 | 29400000 | 29157900.26 | 2022 | RS RODRIGUEZ CONSTRUCTION & SUPPLIES | 2803 | 2022 | 2022-11-08 | 03/23/2022 | 242099.74 | 0 | 2022-09-07 |  | 62
2022 | Region IV-A | CAVITE | NOVELETA (CAVITE) | P00620232LZ | Construction of Revetment | 120.8734 | 14.4279 | 89745000 | 89745000 | 2023 | TRIPLE 8 CONSTRUCTION & SUPPLY, INC. (FORMERLY TRIPLE 8 CONST. & SUPPLY) | 2804 | 2022 | 2023-01-19 | 02/28/2022 | 0 | 0 | 2023-01-18 |  | 1
2023 | Region III | BULACAN | GUIGUINTO (BULACAN) | P00742141LZ | Construction of Flood Mitigation Structure | 120.8735 | 14.8366 | 74249628.75 | 74248853.83 | 2023 | TOPNOTCH CATALYST BUILDERS INC. / BLACK HARDHAT INC. (FORMERLY: JCHARDHAT INC.) | 2805 | 2023 | 2023-12-04 | 04/03/2023 | 774.92 | 0 | 2024-01-26 | 53
2024 | Region III | BULACAN | GUIGUINTO (BULACAN) | P00838401LZ | Construction of Slope Protection Structure | 120.8739 | 14.8467 | 96499852.85 | 96499176.96 | 2024 | A.R.L. CONSTRUCTION | 2806 | 2024 | 2024-11-02 | 02/07/2024 | 675.89 | 0 | 2024-11-01 |  | 1
2024 | Region III | BULACAN | GUIGUINTO (BULACAN) | P00845799LZ | Construction of Slope Protection Structure | 120.8742 | 14.8462 | 98999209.09 | 98998914.62 | 2025 | TOPNOTCH CATALYST BUILDERS INC. / ONE FRAME CONSTRUCTION INC. | 2807 | 2024 | 2025-01-08 | 04/23/2024 | 294.47 | 0 | 2025-01-16 | 8
2022 | Region IV-A | CAVITE | TANZA (CAVITE) | P00620565LZ | Construction of Revetment | 120.8744 | 14.3653 | 49000000 | 49000000 | 2022 | R2A CONSTRUCTION & TRADING CORPORATION | 2808 | 2022 | 2022-07-12 | 02/24/2022 | 0 | 0 | 2022-09-06 | 56
2024 | Region III | BULACAN | BULACAN (BULACAN) | P00844499LZ | Construction of Flood Mitigation Structure | 120.8745 | 14.8 | 77199815.96 | 77199800.47 | 2024 | FLORDES CONSTRUCTION & TRADING CORP. (FORMERLY FLO | 2809 | 2024 | 2024-12-13 | 04/18/2024 | 15.49 | 0 | 2024-12-12 |  | 1
2024 | Region III | BULACAN | PLARIDEL (BULACAN) | P00839575LZ | Construction of Drainage Structure | 120.8746 | 14.8915 | 4949973.65 | 4949713.95 | 2024 | RVR3 CONSTRUCTION SUPPLY AND SERVICES | 2810 | 2024 | 2024-09-24 | 05/28/2024 | 259.7 | 0 | 2024-09-23 |  | 1
2022 | Region III | BULACAN | GUIGUINTO (BULACAN) | P00631218LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.8746 | 14.8386 | 45079393.62 | 45079969.53 | 2022 | TOPNOTCH CATALYST BUILDERS INC. / BLACK HARDHAT INC. (FORMERLY: JCHARDHAT INC.) | 2811 | 2022 | 2022-11-21 | 03/04/2022 | 0 | 575.91 | 2022-12-27 | 36
2023 | Region III | PAMPANGA | CANDABA (PAMPANGA) | P00726912LZ | Construction of Flood Mitigation Structure | 120.8747 | 15.0341 | 72375000 | 68321524.36 | 2024 | STO. CRISTO CONSTRUCTION & TRADING INC. (FOR: STO. CRISTO CONSTRUCTION & TRADING) | 2812 | 2023 | 2024-01-11 | 04/06/2023 | 4053475.64 | 0 | 2024-01-10 |  | 1
2022 | Region IV-A | CAVITE | TRECE MARTIRES CITY (CAPITAL) (CAVITE) | P00620564LZ | Construction of Revetment | 120.8749 | 14.2696 | 49000000 | 48999982.61 | 2022 | TRIPLE 8 CONSTRUCTION & SUPPLY, INC. (FORMERLY TRIPLE 8 CONST. & SUPPLY) | 2813 | 2022 | 2022-10-22 | 02/24/2022 | 17.39 | 0 | 2022-10-21 |  | 1
2024 | Region III | BULACAN | PLARIDEL (BULACAN) | P00821262LZ | Construction of Slope Protection Structure | 120.875 | 14.8917 | 72374930.84 | 72374885.43 | 2024 | ROAD EDGE TRADING & DEVELOPMENT SERVICES | 2814 | 2024 | 2024-10-03 | 02/07/2024 | 45.41 | 0 | 2024-10-02 |  | 1
2023 | Region IV-A | CAVITE | TANZA (CAVITE) | P00727158LZ | Construction of Revetment | 120.8752 | 14.1789 | 49000000 | 48465438.33 | 2024 | N.B. AVILA CONSTRUCTION | 2815 | 2023 | 2024-03-19 | 09/07/2023 | 534561.67 | 0 | 2024-03-18 |  | 1
2023 | Region III | BULACAN | PULILAN (BULACAN) | P00736617LZ | Construction of Flood Mitigation Structure | 120.8752 | 14.8926 | 48999799.64 | 48999986.25 | 2023 | WAWAO BUILDERS | 2816 | 2023 | 2023-07-11 | 02/06/2023 | 0 | 186.61 | 2023-10-02 | 83
2023 | Region III | BULACAN | CITY OF BALIUAG (BULACAN) | P00736011LZ | Construction of Slope Protection Structure | 120.8754 | 15.0093 | 38599729.27 | 38599762.52 | 2023 | JUSTBILT BUILDERS | 2817 | 2023 | 2023-08-17 | 02/13/2023 | 0 | 33.25 | 2023-10-09 | 53
2022 | Region III | BULACAN | GUIGUINTO (BULACAN) | P00631211LZ | Construction of Slope Protection Structure | 120.8755 | 14.8399 | 45079314.63 | 45079451.15 | 2022 | A.R.L. CONSTRUCTION | 2818 | 2022 | 2022-10-24 | 01/28/2022 | 0 | 136.52 | 2022-10-23 |  | 1
2022 | Cordillera Administrative Region | MOUNTAIN PROVINCE | BAUKO (MOUNTAIN PROVINCE) | P00620804LZ | Construction of Flood Mitigation Structure | 120.8756 | 16.9969 | 96499997 | 96500000 | 2022 | MG SAMIDAN CONSTRUCTION / R.S. SEPIAN CONSTRUCTION & TRUCKING | 2819 | 2022 | 2022-10-06 | 03/01/2022 | 0 | 3 | 2022-10-28 | 22
2022 | Region III | BULACAN | GUIGUINTO (BULACAN) | P00631188LZ | Construction of Flood Mitigation Structure | 120.8756 | 14.8452 | 45079553.36 | 45079500.38 | 2022 | L.R. TIQUI BUILDERS, INC. | 2820 | 2022 | 2022-10-24 | 01/28/2022 | 52.98 | 0 | 2022-10-23 |  | 1
2023 | Region III | BULACAN | GUIGUINTO (BULACAN) | P00726475LZ | Construction of Flood Mitigation Structure | 120.8756 | 14.8369 | 96499368.08 | 96499623.93 | 2023 | A.R.L. CONSTRUCTION | 2821 | 2023 | 2023-11-30 | 02/13/2023 | 0 | 255.85 | 2024-02-06 | 68
2022 | Cordillera Administrative Region | BENGUET | BOKOD (BENGUET) | P00621000LZ | Construction of Flood Mitigation Structure | 120.8757 | 16.5236 | 24500000 | 23765066.81 | 2022 | CLIFF CONSTRUCTION & AGGREGATES | 2822 | 2022 | 2022-11-11 | 05/10/2022 | 734933.19 | 0 | 2022-11-11 | 0
2023 | Region III | BULACAN | GUIGUINTO (BULACAN) | P00725752LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.8758 | 14.8378 | 77682407.82 | 77682237.38 | 2024 | L.R. TIQUI BUILDERS, INC. | 2823 | 2023 | 2024-01-08 | 02/13/2023 | 170.44 | 0 | 2024-01-07 |  | 1
2023 | Region IV-A | CAVITE | CITY OF GENERAL TRIAS (CAVITE) | P00744303LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.8758 | 14.3753 | 36537795 | 36537795 | 2023 | M.S. RAMOS CONSTRUCTION INC. (FORMERLY: M.S. RAMOS | 2824 | 2023 | 2023-10-06 | 03/15/2023 | 0 | 0 | 2023-10-05 |  | 1
2023 | Region III | BULACAN | GUIGUINTO (BULACAN) | P00740590LZ | Construction of Flood Mitigation Structure | 120.8763 | 14.826 | 48999946.5 | 47039948.6 | 2023 | 11-16 CONSTRUCTION | 2825 | 2023 | 2023-12-08 | 03/21/2023 | 1959997.9 | 0 | 2023-12-14 | 6
2023 | Region III | BULACAN | GUIGUINTO (BULACAN) | P00725751LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.8764 | 14.8241 | 96499417.73 | 96495872.05 | 2024 | L.R. TIQUI BUILDERS, INC. | 2826 | 2023 | 2024-02-07 | 02/13/2023 | 3545.68 | 0 | 2024-02-06 |  | 1
2023 | Region III | BULACAN | GUIGUINTO (BULACAN) | P00742317LZ | Construction of Flood Mitigation Structure | 120.8764 | 14.8241 | 19799983.14 | 19006075.94 | 2023 | TOPNOTCH CATALYST BUILDERS INC. | 2827 | 2023 | 2023-10-02 | 03/27/2023 | 793907.2 | 0 | 2023-11-20 | 49
2023 | Region III | PAMPANGA | CANDABA (PAMPANGA) | P00726913LZ | Construction of Flood Mitigation Structure | 120.8765 | 15.0332 | 72375000 | 68321985.46 | 2024 | STO. CRISTO CONSTRUCTION & TRADING INC. (FOR: STO. CRISTO CONSTRUCTION & TRADING) | 2828 | 2023 | 2024-02-12 | 04/06/2023 | 4053014.54 | 0 | 2024-02-11 |  | 1
2023 | Region III | BULACAN | GUIGUINTO (BULACAN) | P00726473LZ | Construction of Flood Mitigation Structure | 120.8765 | 14.8238 | 96499880.44 | 96405861.59 | 2023 | GREAT PACIFIC BUILDERS AND GEN. CONTRACTOR INC. | 2829 | 2023 | 2023-12-20 | 02/13/2023 | 94018.85 | 0 | 2024-02-06 | 48
2023 | Region IV-A | CAVITE | NOVELETA (CAVITE) | P00737502LZ | Construction of Drainage Structure | 120.8765 | 14.4225 | 4950000 | 4897878.72 | 2023 | TWO DEGREES CONSTRUCTION AND SUPPLY | 2830 | 2023 | 2023-07-18 | 02/19/2023 | 52121.28 | 0 | 2023-07-17 |  | 1
2022 | Region III | BULACAN | CITY OF BALIUAG (BULACAN) | P00621450LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.8766 | 14.9656 | 4899128.13 | 4899975.59 | 2022 | I.F. CLEMENTE CONSTRUCTION CORPORATION | 2831 | 2022 | 2022-07-01 | 04/06/2022 | 0 | 847.46 | 2022-08-02 | 32
2023 | Region III | BULACAN | GUIGUINTO (BULACAN) | P00740582LZ | Construction of Flood Mitigation Structure | 120.8766 | 14.8407 | 48249917.79 | 48999246.3 | 2023 | A.R.L. CONSTRUCTION | 2832 | 2023 | 2023-12-06 | 03/21/2023 | 0 | 749328.51 | 2023-12-14 | 8
2023 | Region IV-B | OCCIDENTAL MINDORO | SABLAYAN (OCCIDENTAL MINDORO) | P00742459LZ | Construction of Flood Mitigation Structure | 120.8766 | 12.871 | 99000000 | 98999995.37 | 2024 | JELSIE CONSTRUCTION & SUPPLY | 2833 | 2023 | 2024-05-04 | 05/29/2023 | 4.63 | 0 | 2024-05-03 |  | 1
2022 | Region III | BULACAN | CITY OF BALIUAG (BULACAN) | P00637069LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.8766 | 14.9606 | 4899660.77 | 4899893.64 | 2022 | I.F. CLEMENTE CONSTRUCTION CORPORATION | 2834 | 2022 | 2022-07-01 | 04/06/2022 | 0 | 232.87 | 2022-08-02 | 32
2023 | Region III | BULACAN | GUIGUINTO (BULACAN) | P00737459LZ | Construction of Flood Mitigation Structure | 120.8767 | 14.8265 | 19799578.31 | 19799878.83 | 2023 | TIONGCO MENDOZA CONSTRUCTION CO. INC. | 2835 | 2023 | 2023-07-05 | 02/06/2023 | 0 | 300.52 | 2023-07-04 |  | 1
2022 | Region III | BULACAN | GUIGUINTO (BULACAN) | P00631192LZ | Construction of Flood Mitigation Structure | 120.8769 | 14.8278 | 22539714.91 | 22539929.3 | 2022 | F.R. MAPILISAN CONSTRUCTION | 2836 | 2022 | 2022-07-22 | 04/06/2022 | 0 | 214.39 | 2022-09-01 | 41
2023 | Region III | BULACAN | GUIGUINTO (BULACAN) | P00737458LZ | Construction of Flood Mitigation Structure | 120.8769 | 14.8234 | 19799097.14 | 19798773.41 | 2023 | ROSSLANCE CONSTRUCTION AND DEVELOPMENT | 2837 | 2023 | 2023-10-03 | 02/06/2023 | 323.73 | 0 | 2023-10-02 |  | 1
2024 | Region III | BULACAN | CITY OF BALIUAG (BULACAN) | P00843310LZ | Construction of Flood Mitigation Structure | 120.877 | 15.0008 | 77199942.32 | 77199677.98 | 2024 | M3 KONSTRACT CORPORATION (FORMERLY:MARGARITA CONSTRUCTION) | 2838 | 2024 | 2024-10-24 | 02/28/2024 | 264.34 | 0 | 2024-10-23 |  | 1
2024 | Region III | BULACAN | GUIGUINTO (BULACAN) | P00823459LZ | Construction of Flood Mitigation Structure | 120.877 | 14.827 | 77199485.73 | 77198841 | 2024 | ORANI CONSTRUCTION AND SUPPLY CORPORATION (FORMERLY:ORANI BUILDERS & SUPPLY) | 2839 | 2024 | 2024-10-27 | 02/28/2024 | 644.73 | 0 | 2024-10-23 |  | 4
2024 | Region III | BULACAN | GUIGUINTO (BULACAN) | P00820229LZ | Construction of Flood Mitigation Structure | 120.8771 | 14.844 | 72374968.39 | 72374267.49 | 2024 | WAWAO BUILDERS | 2840 | 2024 | 2024-06-19 | 02/07/2024 | 700.9 | 0 | 2024-10-02 | 105
2024 | Region III | BULACAN | CITY OF BALIUAG (BULACAN) | P00838366LZ | Construction of Revetment | 120.8772 | 14.9993 | 72374977.69 | 72374803.73 | 2024 | S-ANG CONSTRUCTION & GENERAL TRADING, INC. / C.T. LEONCIO CONSTRUCTION & TRADING | 2841 | 2024 | 2024-11-14 | 03/20/2024 | 173.96 | 0 | 2024-11-13 |  | 1
2023 | Region IV-B | OCCIDENTAL MINDORO | SABLAYAN (OCCIDENTAL MINDORO) | P00726767LZ | Construction of Flood Mitigation Structure | 120.8776 | 12.9564 | 45080000 | 45073624.75 | 2023 | STX ENTERPRISES | 2842 | 2023 | 2023-09-02 | 02/10/2023 | 6375.25 | 0 | 2023-09-01 |  | 1
2024 | Region III | BULACAN | GUIGUINTO (BULACAN) | P00823467LZ | Construction of Flood Mitigation Structure | 120.8777 | 14.8325 | 96499971.1 | 96499968.29 | 2024 | WAWAO BUILDERS | 2843 | 2024 | 2024-06-11 | 03/20/2024 | 2.81 | 0 | 2024-12-13 | 185
2022 | Region III | BULACAN | GUIGUINTO (BULACAN) | P00631219LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.8777 | 14.8426 | 45079769.3 | 45079969.52 | 2022 | TOPNOTCH CATALYST BUILDERS INC. / BLACK HARDHAT INC. (FORMERLY: JCHARDHAT INC.) | 2844 | 2022 | 2022-11-21 | 03/04/2022 | 0 | 200.22 | 2022-12-27 | 36
2024 | Region III | BULACAN | CITY OF BALIUAG (BULACAN) | P00821224LZ | Construction of Flood Mitigation Structure | 120.8778 | 14.8984 | 96499927.72 | 96499757.73 | 2025 | 729 CONSTRUCTION, INC. (FORMERLY 722 CONSTRUCTION, INC.) | 2845 | 2024 | 2025-02-07 | 05/14/2024 | 169.99 | 0 | 2025-02-06 |  | 1
2023 | Region III | BULACAN | GUIGUINTO (BULACAN) | P00740347LZ | Construction of Flood Mitigation Structure | 120.8779 | 14.8427 | 72374068.34 | 72373409.11 | 2024 | TOPNOTCH CATALYST BUILDERS INC. | 2846 | 2023 | 2024-01-21 | 03/28/2023 | 659.23 | 0 | 2024-01-20 |  | 1
2023 | Region III | BULACAN | CITY OF BALIUAG (BULACAN) | P00725685LZ | Construction of Revetment | 120.8779 | 15.0107 | 96499834.19 | 96499701.59 | 2023 | M.S. RAMOS CONSTRUCTION INC. (FORMERLY: M.S. RAMOS | 2847 | 2023 | 2023-12-09 | 02/13/2023 | 132.6 | 0 | 2023-12-08 |  | 1
2023 | Region III | BULACAN | CITY OF BALIUAG (BULACAN) | P00726461LZ | Construction of Flood Mitigation Structure | 120.8782 | 15.0074 | 96499679.61 | 96498523.97 | 2023 | M3 KONSTRACT CORPORATION (FORMERLY:MARGARITA CONSTRUCTION) | 2848 | 2023 | 2023-12-09 | 02/13/2023 | 1155.64 | 0 | 2023-12-08 |  | 1
2024 | Region III | BULACAN | CITY OF BALIUAG (BULACAN) | P00843309LZ | Construction of Flood Mitigation Structure | 120.8784 | 15.0014 | 77199943.4 | 77199531.57 | 2024 | M3 KONSTRACT CORPORATION (FORMERLY:MARGARITA CONSTRUCTION) | 2849 | 2024 | 2024-10-24 | 02/28/2024 | 411.83 | 0 | 2024-10-23 |  | 1
2022 | Region III | BULACAN | BULACAN (BULACAN) | P00631204LZ | Construction of Slope Protection Structure | 120.8785 | 14.8058 | 35279964.6 | 35278599.12 | 2022 | J. SIMEON CONSTRUCTION | 2850 | 2022 | 2022-07-26 | 01/28/2022 | 1365.48 | 0 | 2022-07-25 |  | 1
2024 | Region III | BULACAN | CITY OF BALIUAG (BULACAN) | P00838371LZ | Construction of Slope Protection Structure | 120.8785 | 14.9996 | 96499972.98 | 96499563.2 | 2024 | M3 KONSTRACT CORPORATION (FORMERLY:MARGARITA CONSTRUCTION) | 2851 | 2024 | 2024-11-01 | 02/07/2024 | 409.78 | 0 | 2024-11-01 | 0
2022 | Region III | BULACAN | GUIGUINTO (BULACAN) | P00621531LZ | Construction of Flood Mitigation Structure | 120.8786 | 14.8476 | 24499916.34 | 24497106.55 | 2022 | NICLEDON CONSTRUCTION | 2852 | 2022 | 2022-12-27 | 04/05/2022 | 2809.79 | 0 | 2022-12-29 | 2
2023 | Region III | BULACAN | CITY OF BALIUAG (BULACAN) | P00740338LZ | Construction of Flood Mitigation Structure | 120.8787 | 15.0014 | 72374734.39 | 72373859.53 | 2023 | WAWAO BUILDERS / DRJY CONSTRUCTION | 2853 | 2023 | 2023-12-22 | 03/28/2023 | 874.86 | 0 | 2023-12-21 |  | 1
2024 | Region III | BULACAN | GUIGUINTO (BULACAN) | P00820820LZ | Construction of Flood Mitigation Structure | 120.8789 | 14.8502 | 28949908.16 | 28949821.9 | 2024 | GREAT PACIFIC BUILDERS AND GEN. CONTRACTOR INC. | 2854 | 2024 | 2024-10-15 | 03/20/2024 | 86.26 | 0 | 2024-10-14 |  | 1
2024 | Region III | BULACAN | PLARIDEL (BULACAN) | P00821269LZ | Construction of Slope Protection Structure | 120.8791 | 14.8986 | 72374950.84 | 72374479.88 | 2024 | TOPNOTCH CATALYST BUILDERS INC. | 2855 | 2024 | 2024-08-07 | 02/07/2024 | 470.96 | 0 | 2024-10-02 | 56
2023 | Region III | BULACAN | CITY OF BALIUAG (BULACAN) | P00740332LZ | Construction of Flood Mitigation Structure | 120.8793 | 15.0061 | 72374734.39 | 72374165.79 | 2023 | YPR GEN. CONTRACTOR AND CONSTRUCTION SUPPLY INC. | 2856 | 2023 | 2023-12-22 | 03/28/2023 | 568.6 | 0 | 2023-12-21 |  | 1
2024 | Region III | BULACAN | CITY OF BALIUAG (BULACAN) | P00838370LZ | Construction of Slope Protection Structure | 120.8793 | 14.9907 | 96499850.14 | 96499605.71 | 2024 | L.R. TIQUI BUILDERS, INC. / M3 KONSTRACT CORPORATION (FORMERLY:MARGARITA CONSTRUCTION) | 2857 | 2024 | 2024-11-02 | 02/07/2024 | 244.43 | 0 | 2024-11-01 |  | 1
2023 | Region III | BULACAN | CITY OF BALIUAG (BULACAN) | P00726901LZ | Construction of Flood Mitigation Structure | 120.8794 | 15.0061 | 77199405.85 | 77198159.93 | 2023 | TRIPLE 8 CONSTRUCTION & SUPPLY, INC. (FORMERLY TRIPLE 8 CONST. & SUPPLY) | 2858 | 2023 | 2023-12-08 | 03/14/2023 | 1245.92 | 0 | 2023-12-07 |  | 1
2022 | Region IV-A | CAVITE | CITY OF GENERAL TRIAS (CAVITE) | P00644740LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.8794 | 14.3787 | 9891250 | 9891250 | 2023 | TRIPLE 8 CONSTRUCTION & SUPPLY, INC. (FORMERLY TRIPLE 8 CONST. & SUPPLY) | 2859 | 2022 | 2023-03-08 | 01/09/2023 | 0 | 0 | 2023-04-07 | 30
2022 | Region III | BULACAN | CITY OF BALIUAG (BULACAN) | P00639467LZ | Construction of Flood Mitigation Structure | 120.8795 | 15.0062 | 48999366.39 | 48999840.49 | 2022 | ST. MATTHEW GEN. CONTRACTOR & DEVELOPMENT CORP. | 2860 | 2022 | 2022-12-07 | 04/05/2022 | 0 | 474.1 | 2023-01-28 | 52
2024 | Region III | BULACAN | CITY OF BALIUAG (BULACAN) | P00843308LZ | Construction of Flood Mitigation Structure | 120.8795 | 14.9894 | 77199945.99 | 77199743.94 | 2024 | M3 KONSTRACT CORPORATION (FORMERLY:MARGARITA CONSTRUCTION) | 2861 | 2024 | 2024-10-24 | 02/28/2024 | 202.05 | 0 | 2024-10-23 |  | 1
2024 | Region III | BULACAN | CITY OF BALIUAG (BULACAN) | P00838365LZ | Construction of Revetment | 120.8795 | 14.9908 | 72374987.18 | 72374906.25 | 2024 | S-ANG CONSTRUCTION & GENERAL TRADING, INC. / C.T. LEONCIO CONSTRUCTION & TRADING | 2862 | 2024 | 2024-11-14 | 03/20/2024 | 80.93 | 0 | 2024-11-13 |  | 1
2023 | Region III | BULACAN | BULACAN (BULACAN) | P00735981LZ | Construction of Flood Mitigation Structure | 120.8795 | 14.8092 | 77199901.56 | 77188463.69 | 2023 | 11-16 CONSTRUCTION | 2863 | 2023 | 2023-12-06 | 02/13/2023 | 11437.87 | 0 | 2023-12-08 | 2
2023 | Region III | BULACAN | CITY OF BALIUAG (BULACAN) | P00726161LZ | Construction of Flood Mitigation Structure | 120.8795 | 15.0061 | 48999447.47 | 48999313.96 | 2023 | MRRM TRADING & CONSTRUCTION / GDL CONSTRUCTION | 2864 | 2023 | 2023-07-20 | 02/06/2023 | 133.51 | 0 | 2023-10-02 | 74
2024 | Region III | BULACAN | GUIGUINTO (BULACAN) | P00839480LZ | Construction of Slope Protection Structure | 120.8796 | 14.8508 | 69299906.7 | 69299988.21 | 2024 | TOPNOTCH CATALYST BUILDERS INC. / BEAM TEAM DEVELOPER SPECIALIST INC. | 2865 | 2024 | 2024-10-14 | 03/20/2024 | 0 | 81.51 | 2024-11-13 | 30
2022 | Region IV-A | CAVITE | CAVITE CITY (CAVITE) | P00620229LZ | Construction of Revetment | 120.8796 | 14.4606 | 51145000 | 48577570.41 | 2023 | R.V. RIETA TRADING & GENERAL CONSTRUCTION / ALMAKAR BUILDERS & METAL WORKS | 2866 | 2022 | 2023-12-09 | 02/28/2022 | 2567429.59 | 0 | 2023-12-08 |  | 1
2024 | Cordillera Administrative Region | MOUNTAIN PROVINCE | BAUKO (MOUNTAIN PROVINCE) | P00821542LZ | Construction of Flood Mitigation Structure | 120.8796 | 17.0074 | 39199997.7 | 39200000 | 2024 | MG SAMIDAN CONSTRUCTION / LOG-AKA CONSTRUCTION | 2867 | 2024 | 2024-08-12 | 02/18/2024 | 0 | 2.3 | 2024-09-22 | 41
2023 | Region IV-A | CAVITE | CITY OF GENERAL TRIAS (CAVITE) | P00744302LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.8797 | 14.3794 | 8899230 | 8899230 | 2023 | JAGONBUILD CONSTRUCTION CORP. (FOR. JAGON BUILDERS | 2868 | 2023 | 2023-05-22 | 03/15/2023 | 0 | 0 | 2023-06-04 | 13
2023 | Region III | BULACAN | BULACAN (BULACAN) | P00735978LZ | Construction of Flood Mitigation Structure | 120.8797 | 14.81 | 77199910.6 | 77198713.48 | 2023 | FERDSTAR BUILDERS INC. | 2869 | 2023 | 2023-10-11 | 02/13/2023 | 1197.12 | 0 | 2023-12-08 | 58
2024 | Region III | BULACAN | BULACAN (BULACAN) | P00844502LZ | Construction of Flood Mitigation Structure | 120.8798 | 14.8101 | 77198999.21 | 77012853.59 | 2024 | IM CONSTRUCTION CORPORATION | 2870 | 2024 | 2024-12-18 | 05/14/2024 | 186145.62 | 0 | 2025-01-07 | 20
2024 | Region III | BULACAN | BULACAN (BULACAN) | P00843314LZ | Construction of Flood Mitigation Structure | 120.8798 | 14.794 | 72374781.59 | 72374225.99 | 2024 | STAR WILLIAM CONSTRUCTION | 2871 | 2024 | 2024-09-23 | 04/18/2024 | 555.6 | 0 | 2024-12-12 | 80
2021 | Region IV-A | CAVITE |  | P00561183LZ | Construction of Drainage Structure | 120.8801 | 14.374 | 3920000 | 3718753.56 | 2022 | FE S. REYES GENERAL CONTRACTOR CORP. | 2872 | 2021 | 2022-08-15 | 03/29/2022 | 201246.44 | 0 | 2022-08-14 |  | 1
2024 | Region III | BULACAN | BULACAN (BULACAN) | P00823364LZ | Construction of Flood Mitigation Structure | 120.8801 | 14.812 | 77199977.4 | 77188821.56 | 2024 | 11-16 CONSTRUCTION | 2873 | 2024 | 2024-11-27 | 04/02/2024 | 11155.84 | 0 | 2024-11-26 |  | 1
2023 | Region III | BULACAN | CITY OF BALIUAG (BULACAN) | P00726468LZ | Construction of Flood Mitigation Structure | 120.8802 | 15.0101 | 96499679.61 | 96497506.9 | 2023 | M3 KONSTRACT CORPORATION (FORMERLY:MARGARITA CONSTRUCTION) | 2874 | 2023 | 2023-12-09 | 02/13/2023 | 2172.71 | 0 | 2023-12-08 |  | 1
2023 | Region III | BULACAN | CITY OF BALIUAG (BULACAN) | P00726903LZ | Construction of Flood Mitigation Structure | 120.8802 | 14.9828 | 77199958.41 | 77199243.03 | 2023 | MICHARIAN BUILDERS AND TRADING | 2875 | 2023 | 2023-12-04 | 03/14/2023 | 715.38 | 0 | 2023-12-07 | 3
2024 | Region III | BULACAN | GUIGUINTO (BULACAN) | P00845983LZ | Construction of Flood Mitigation Structure | 120.8803 | 14.8462 | 29699367.93 | 29699463.05 | 2024 | RJR CALCON CORP. | 2876 | 2024 | 2024-06-25 | 03/01/2024 | 0 | 95.12 | 2024-07-27 | 32
2022 | Region III | BULACAN | PLARIDEL (BULACAN) | P00621076LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.8804 | 14.9011 | 48999497.5 | 48998995.93 | 2023 | TOPNOTCH CATALYST BUILDERS INC. | 2877 | 2022 | 2023-05-13 | 02/18/2022 | 501.57 | 0 | 2023-05-12 |  | 1
2023 | Region III | BULACAN | BULACAN (BULACAN) | P00735977LZ | Construction of Flood Mitigation Structure | 120.8804 | 14.7912 | 77199879.31 | 77199971.28 | 2023 | WAWAO BUILDERS | 2878 | 2023 | 2023-08-16 | 02/13/2023 | 0 | 91.97 | 2023-12-08 | 114
2024 | Region III | BULACAN | BULACAN (BULACAN) | P00843322LZ | Construction of Flood Mitigation Structure | 120.8805 | 14.8132 | 72374824.47 | 72374967.11 | 2024 | WBX CONSTRUCTION, INC (FORMERLY WBX CONSTRUCTION) | 2879 | 2024 | 2024-11-27 | 04/02/2024 | 0 | 142.64 | 2024-11-26 |  | 1
2022 | Region III | BULACAN | CITY OF BALIUAG (BULACAN) | P00640519LZ | Construction of Flood Mitigation Structure | 120.8806 | 14.9797 | 49499297.47 | 49499816.61 | 2023 | STAR WILLIAM CONSTRUCTION | 2880 | 2022 | 2023-01-28 | 04/04/2022 | 0 | 519.14 | 2023-01-27 |  | 1
2023 | Region III | BULACAN | CITY OF BALIUAG (BULACAN) | P00740339LZ | Construction of Flood Mitigation Structure | 120.8806 | 15.0024 | 72374797.38 | 72373832.51 | 2023 | M3 KONSTRACT CORPORATION (FORMERLY:MARGARITA CONSTRUCTION) | 2881 | 2023 | 2023-12-18 | 03/28/2023 | 964.87 | 0 | 2023-12-21 | 3
2022 | Region III | BULACAN | CITY OF BALIUAG (BULACAN) | P00621535LZ | Construction of Flood Mitigation Structure | 120.8807 | 14.9797 | 25479931 | 25479994.08 | 2022 | TOPNOTCH CATALYST BUILDERS INC. | 2882 | 2022 | 2022-08-31 | 04/04/2022 | 0 | 63.08 | 2022-08-30 |  | 1
2023 | Region III | BULACAN | CITY OF BALIUAG (BULACAN) | P00740345LZ | Construction of Flood Mitigation Structure | 120.8807 | 14.9796 | 72374734.39 | 72374590.56 | 2023 | R.D. TALENS CONSTRUCTION AND TRADING / I.F. CLEMENTE CONSTRUCTION CORPORATION | 2883 | 2023 | 2023-10-10 | 04/03/2023 | 143.83 | 0 | 2023-12-27 | 78
2023 | Region III | BULACAN | CITY OF BALIUAG (BULACAN) | P00740337LZ | Construction of Flood Mitigation Structure | 120.8807 | 15.0023 | 72374734.39 | 72372354.56 | 2023 | WAWAO BUILDERS | 2884 | 2023 | 2023-12-19 | 03/28/2023 | 2379.83 | 0 | 2023-12-21 | 2
2023 | Region III | BULACAN | CITY OF BALIUAG (BULACAN) | P00740344LZ | Construction of Flood Mitigation Structure | 120.8807 | 14.9797 | 72374734.39 | 72374585.24 | 2023 | M3 KONSTRACT CORPORATION (FORMERLY:MARGARITA CONSTRUCTION) | 2885 | 2023 | 2023-11-09 | 04/03/2023 | 149.15 | 0 | 2023-12-27 | 48
2023 | Region III | BULACAN | PLARIDEL (BULACAN) | P00726722LZ | Construction of Flood Mitigation Structure | 120.8807 | 14.9012 | 22784118.04 | 22784932.19 | 2023 | S.A. PLEYTO CONSTRUCTION CORPORATION | 2886 | 2023 | 2023-04-13 | 02/06/2023 | 0 | 814.15 | 2023-08-03 | 112
2023 | Region III | BULACAN | BULACAN (BULACAN) | P00735980LZ | Construction of Flood Mitigation Structure | 120.8808 | 14.8145 | 77199695.56 | 77199986.09 | 2023 | WAWAO BUILDERS | 2887 | 2023 | 2023-07-03 | 02/13/2023 | 0 | 290.53 | 2023-12-08 | 158
2023 | Region III | BULACAN | BULACAN (BULACAN) | P00736005LZ | Construction of Revetment | 120.8808 | 14.8145 | 28949732.62 | 28946072.28 | 2023 | STAR WILLIAM CONSTRUCTION | 2888 | 2023 | 2023-05-20 | 02/13/2023 | 3660.34 | 0 | 2023-09-09 | 112
2022 | Region I | PANGASINAN | UMINGAN (PANGASINAN) | P00631093LZ | Construction of Revetment | 120.8808 | 15.925 | 49000000 | 48958019.42 | 2022 | JHI CONSTRUCTION & SUPPLY | 2889 | 2022 | 2022-10-10 | 03/23/2022 | 41980.58 | 0 | 2022-09-29 |  | 11
2023 | Region III | BULACAN | PLARIDEL (BULACAN) | P00727360LZ | Construction of Flood Mitigation Structure | 120.8808 | 14.8991 | 48999985.25 | 48999916.12 | 2023 | FERDSTAR BUILDERS INC. | 2890 | 2023 | 2023-10-30 | 03/07/2023 | 69.13 | 0 | 2023-10-31 | 1
2023 | Region III | BULACAN | CITY OF BALIUAG (BULACAN) | P00740336LZ | Construction of Flood Mitigation Structure | 120.8809 | 14.9847 | 72374988.4 | 72374362.28 | 2023 | ST. MATTHEW GEN. CONTRACTOR & DEVELOPMENT CORP. | 2891 | 2023 | 2023-12-05 | 03/28/2023 | 626.12 | 0 | 2023-12-21 | 16
2023 | Region IV-A | CAVITE | CAVITE CITY (CAVITE) | P00725807LZ | Construction of Revetment | 120.8809 | 14.4616 | 57900000 | 57900000 | 2023 | GRAIA CONSTRUCTION CORPORATION | 2892 | 2023 | 2023-12-04 | 02/19/2023 | 0 | 0 | 2023-12-03 |  | 1
2022 | Region III | BULACAN | CITY OF BALIUAG (BULACAN) | P00640516LZ | Construction of Flood Mitigation Structure | 120.881 | 15.0046 | 49499246.76 | 49499675.98 | 2023 | M3 KONSTRACT CORPORATION (FORMERLY:MARGARITA CONSTRUCTION) | 2893 | 2022 | 2023-01-29 | 04/05/2022 | 0 | 429.22 | 2023-01-28 |  | 1
2024 | Region III | BULACAN | CITY OF BALIUAG (BULACAN) | P00838407LZ | Construction of Slope Protection Structure | 120.8811 | 14.9916 | 96499986.12 | 96499936.68 | 2024 | M3 KONSTRACT CORPORATION (FORMERLY:MARGARITA CONSTRUCTION) | 2894 | 2024 | 2024-09-30 | 02/07/2024 | 49.44 | 0 | 2024-11-01 | 32
2023 | Region III | BULACAN | PLARIDEL (BULACAN) | P00727278LZ | Construction of Flood Mitigation Structure | 120.8813 | 14.8015 | 72374990.81 | 72374749.45 | 2023 | GREAT PACIFIC BUILDERS AND GEN. CONTRACTOR INC. | 2895 | 2023 | 2023-12-08 | 03/14/2023 | 241.36 | 0 | 2023-12-07 |  | 1
2023 | Region III | BULACAN | CITY OF BALIUAG (BULACAN) | P00725762LZ | Construction of Drainage Structure | 120.8813 | 14.9776 | 62048765.16 | 62048663.16 | 2023 | GDL CONSTRUCTION | 2896 | 2023 | 2023-07-20 | 02/13/2023 | 102 | 0 | 2024-02-06 | 201
2023 | Region III | BULACAN | GUIGUINTO (BULACAN) | P00726487LZ | Construction of Flood Mitigation Structure | 120.8815 | 14.8522 | 96499351.52 | 96499860.92 | 2023 | WAWAO BUILDERS | 2897 | 2023 | 2023-08-25 | 02/13/2023 | 0 | 509.4 | 2024-02-06 | 165
2024 | Region III | BULACAN | CITY OF BALIUAG (BULACAN) | P00838372LZ | Construction of Slope Protection Structure | 120.8816 | 15.0002 | 96499955.84 | 96499563.2 | 2024 | YPR GEN. CONTRACTOR AND CONSTRUCTION SUPPLY INC. | 2898 | 2024 | 2024-11-02 | 02/07/2024 | 392.64 | 0 | 2024-11-01 |  | 1
2022 | Region III | BULACAN | PLARIDEL (BULACAN) | P00630941LZ | Construction of Flood Mitigation Structure | 120.8816 | 14.9028 | 62724446.46 | 62715942.26 | 2022 | WAWAO BUILDERS | 2899 | 2022 | 2022-10-28 | 03/07/2022 | 8504.2 | 0 | 2022-10-31 | 3
2023 | Region III | BULACAN | CITY OF BALIUAG (BULACAN) | P00726904LZ | Construction of Flood Mitigation Structure | 120.8817 | 14.981 | 77199958.41 | 77198358.83 | 2023 | TRIPLE 8 CONSTRUCTION & SUPPLY, INC. (FORMERLY TRIPLE 8 CONST. & SUPPLY) | 2900 | 2023 | 2023-12-05 | 03/14/2023 | 1599.58 | 0 | 2023-12-07 | 2
2023 | National Capital Region | NAVOTAS CITY | CITY OF NAVOTAS (METROPOLITAN MANILA) | P00726997LZ | Construction of Flood Mitigation Facility | 120.9463 | 14.6666 | 23492139.8 | 23488443.33 | 2024 | AYANA CONSTRUCTION AND TRADING | 2901 | 2023 | 2024-01-18 | 03/30/2023 | 3696.47 | 0 | 2024-01-17 |  | 1
2021 | National Capital Region | MALABON CITY |  | P00525706LZ | Construction of Dike | 120.9464 | 14.6858 | 29340454.15 | 29400000 | 2022 | ROTAFLEX CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY:ROTA FLEX CONSTRUCTION) | 2902 | 2021 | 2022-10-19 | 03/24/2022 | 0 | 59545.85 | 2022-10-18 |  | 1
2023 | Region I | ILOCOS NORTE | PAGUDPUD (ILOCOS NORTE) | P00725634LZ | Construction of Flood Mitigation Structure | 120.9464 | 18.5506 | 57899669.75 | 57899669.44 | 2023 | JLP CONSTRUCTION & SUPPLY (FORMERLY: JLP CONSTRUCT | 2903 | 2023 | 2023-08-18 | 03/13/2023 | 0.31 | 0 | 2023-12-07 | 111
2022 | National Capital Region | VALENZUELA CITY | CITY OF VALENZUELA (METROPOLITAN MANILA) | P00639409LZ | Construction of Flood Mitigation Structure | 120.9464 | 14.7323 | 48979472.82 | 47382259.09 | 2023 | TOUGHBUILT CONSTRUCTION & TRADING, INC. | 2904 | 2022 | 2023-02-15 | 03/24/2022 | 1597213.73 | 0 | 2023-02-15 | 0
2022 | National Capital Region | VALENZUELA CITY | CITY OF VALENZUELA (METROPOLITAN MANILA) | P00637045LZ | Construction of Flood Mitigation Structure | 120.9465 | 14.7102 | 14681730.66 | 14373152 | 2022 | TOUGHBUILT CONSTRUCTION & TRADING, INC. | 2905 | 2022 | 2022-10-06 | 05/25/2022 | 308578.66 | 0 | 2022-12-19 | 74
2024 | National Capital Region | MALABON CITY | CITY OF MALABON (METROPOLITAN MANILA) | P00820549LZ | Construction of Revetment | 120.9465 | 14.6775 | 45332973.21 | 45334169.87 | 2024 | ROTAFLEX CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY:ROTA FLEX CONSTRUCTION) | 2906 | 2024 | 2024-11-15 | 02/21/2024 | 0 | 1196.66 | 2024-11-15 | 0
2023 | Region I | ILOCOS NORTE | PAGUDPUD (ILOCOS NORTE) | P00725635LZ | Construction of Flood Mitigation Structure | 120.9465 | 18.5509 | 57899449.83 | 57899449.11 | 2023 | RCD GEN. CONTRACTOR & CONSTRUCTION SUPPLY | 2907 | 2023 | 2023-07-24 | 03/13/2023 | 0.72 | 0 | 2023-12-07 | 136
2024 | National Capital Region | MALABON CITY | CITY OF MALABON (METROPOLITAN MANILA) | P00820548LZ | Construction of Revetment | 120.9467 | 14.6764 | 45333664.75 | 45333708.44 | 2024 | ELITE GENERAL CONTRACTOR AND DEVELOPMENT CORP. | 2908 | 2024 | 2024-09-16 | 02/21/2024 | 0 | 43.69 | 2024-11-15 | 60
2024 | National Capital Region | MALABON CITY | CITY OF MALABON (METROPOLITAN MANILA) | P00820547LZ | Construction of Flood Mitigation Structure | 120.9471 | 14.6753 | 48998736.38 | 49000000 | 2024 | JAGONBUILD CONSTRUCTION CORP. (FOR. JAGON BUILDERS | 2909 | 2024 | 2024-08-21 | 02/21/2024 | 0 | 1263.62 | 2024-11-15 | 86
2024 | Region III | NUEVA ECIJA | TALAVERA (NUEVA ECIJA) | P00823434LZ | Construction of Flood Mitigation Structure | 120.9472 | 15.6527 | 19300000 | 19106979.97 | 2024 | BRYAN PAUL P. PACHECO CONST. CORP. | 2910 | 2024 | 2024-07-28 | 03/01/2024 | 193020.03 | 0 | 2024-07-27 |  | 1
2023 | Region II | NUEVA VIZCAYA | SANTA FE (NUEVA VIZCAYA) | P00727114LZ | Construction of Flood Mitigation Structure | 120.9472 | 16.1669 | 43688160 | 42661504.77 | 2023 | M.R. VARGAS CONSTRUCTION CORPORATION (FORMERLY: M.R. VARGAS CONSTRUCTION) | 2911 | 2023 | 2023-11-03 | 05/02/2023 | 1026655.23 | 0 | 2023-11-10 | 7
2023 | Region IV-A | CAVITE | BACOOR CITY (CAVITE) | P00725811LZ | Construction of Revetment | 120.9473 | 14.4241 | 77199945.17 | 77196567.23 | 2023 | ALMAKAR BUILDERS & METAL WORKS | 2912 | 2023 | 2023-12-22 | 02/15/2023 | 3377.94 | 0 | 2023-12-21 |  | 1
2023 | Region III | BULACAN | SANTA MARIA (BULACAN) | P00725746LZ | Construction of Flood Mitigation Structure | 120.9474 | 14.8164 | 86849709.32 | 86848281.05 | 2024 | DAHL CONSTRUCTION CORP. (FORMERLY: DAHL CONSTRUCTION) | 2913 | 2023 | 2024-05-15 | 02/27/2023 | 1428.27 | 0 | 2024-05-14 |  | 1
2024 | Region III | BULACAN | SANTA MARIA (BULACAN) | P00823479LZ | Construction of Flood Mitigation Structure | 120.9474 | 14.8166 | 24124258.49 | 24124554.7 | 2024 | J.G. MENDOZA BUILDERS | 2914 | 2024 | 2024-11-13 | 04/23/2024 | 0 | 296.21 | 2024-11-12 |  | 1
2022 | Region III | BULACAN | SAN RAFAEL (BULACAN) | P00620157LZ | Construction of Flood Mitigation Structure | 120.9476 | 15.0221 | 55004629.32 | 54124555.25 | 2022 | EIRISH BUILDERS & SUPPLY INC. | 2915 | 2022 | 2022-10-05 | 03/07/2022 | 880074.07 | 0 | 2022-10-04 |  | 1
2022 | Region IV-A | CAVITE | CITY OF DASMARIÃ‘AS (CAVITE) | P00620898LZ | Construction of Slope Protection Structure | 120.9476 | 14.3366 | 96499987.1 | 96494841.42 | 2023 | KLDS TRADING & CONSTRUCTION | 2916 | 2022 | 2023-12-01 | 03/02/2022 | 5145.68 | 0 | 2023-12-30 | 29
2024 | National Capital Region | NAVOTAS CITY | CITY OF NAVOTAS (METROPOLITAN MANILA) | P00820552LZ | Construction of Flood Mitigation Facility | 120.9477 | 14.6584 | 29397298.99 | 29398741.8 | 2024 | STRUKTURA TEKNIKA SERVICES CO. | 2917 | 2024 | 2024-11-05 | 02/12/2024 | 0 | 1442.81 | 2024-11-04 |  | 1
2023 | Region IV-A | CAVITE | BACOOR CITY (CAVITE) | P00725814LZ | Construction of Revetment | 120.9477 | 14.4579 | 77199994.42 | 77199978.34 | 2024 | ALMAKAR BUILDERS & METAL WORKS | 2918 | 2023 | 2024-02-10 | 02/15/2023 | 16.08 | 0 | 2024-02-09 |  | 1
2022 | National Capital Region | NAVOTAS CITY | CITY OF NAVOTAS (METROPOLITAN MANILA) | P00631020LZ | Construction of Flood Mitigation Facility | 120.9478 | 14.6522 | 19599649.83 | 19479821.97 | 2022 | AYANA CONSTRUCTION AND TRADING | 2919 | 2022 | 2022-11-10 | 02/14/2022 | 119827.86 | 0 | 2022-11-09 |  | 1
2022 | Region III | BULACAN | BUSTOS (BULACAN) | P00621618LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.9478 | 14.9599 | 48999871.72 | 48999665.01 | 2022 | ALPHA & OMEGA GEN. CONTRACTOR & DEVELOPMENT CORP. | 2920 | 2022 | 2022-10-31 | 04/05/2022 | 206.71 | 0 | 2022-10-30 |  | 1
2021 | Region IV-A | CAVITE |  | P00525631LZ | Construction of Revetment | 120.9479 | 14.4294 | 96499937.25 | 96499914.67 | 2022 | GRAIA CONSTRUCTION CORPORATION | 2921 | 2021 | 2022-09-03 | 10/11/2021 | 22.58 | 0 | 2022-09-02 |  | 1
2022 | National Capital Region | MALABON CITY | CITY OF MALABON (METROPOLITAN MANILA) | P00637757LZ | Construction of Drainage Structure | 120.948 | 14.6661 | 14692274.08 | 14846141.76 | 2023 | ROTAFLEX CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY:ROTA FLEX CONSTRUCTION) | 2922 | 2022 | 2023-05-04 | 03/24/2022 | 0 | 153867.68 | 2023-05-03 |  | 1
2024 | Region III | NUEVA ECIJA | CABANATUAN CITY (NUEVA ECIJA) | P00821256LZ | Construction of Flood Mitigation Structure | 120.948 | 15.5035 | 86849911.76 | 86849907.06 | 2024 | CELSO C. FERRER CONSTRUCTION CORP. | 2923 | 2024 | 2024-07-16 | 02/12/2024 | 4.7 | 0 | 2024-11-18 | 125
2023 | Region III | BULACAN | SANTA MARIA (BULACAN) | P00726163LZ | Construction of Flood Mitigation Structure | 120.948 | 14.8187 | 48999510.17 | 48986913.2 | 2023 | YPR GEN. CONTRACTOR AND CONSTRUCTION SUPPLY INC. | 2924 | 2023 | 2023-09-18 | 02/27/2023 | 12596.97 | 0 | 2024-01-04 | 108
2022 | National Capital Region | VALENZUELA CITY | CITY OF VALENZUELA (METROPOLITAN MANILA) | P00639410LZ | Construction of Flood Mitigation Structure | 120.9481 | 14.7299 | 48980091.57 | 47386189.83 | 2023 | TOUGHBUILT CONSTRUCTION & TRADING, INC. | 2925 | 2022 | 2023-02-15 | 03/24/2022 | 1593901.74 | 0 | 2023-02-15 | 0
2022 | National Capital Region | MALABON CITY | CITY OF MALABON (METROPOLITAN MANILA) | P00640485LZ | Construction of Flood Mitigation Structure | 120.9483 | 14.6733 | 39198044.83 | 39600000 | 2022 | AKN CONSTRUCTION CORPORATION | 2926 | 2022 | 2022-11-28 | 03/24/2022 | 0 | 401955.17 | 2022-11-27 |  | 1
2021 | National Capital Region | NAVOTAS CITY |  | P00561605LZ | Construction of Dike | 120.9483 | 14.6504 | 24745431.3 | 24460268.57 | 2022 | JAGONBUILD CONSTRUCTION CORP. (FOR. JAGON BUILDERS | 2927 | 2021 | 2022-09-06 | 11/11/2021 | 285162.73 | 0 | 2022-09-05 |  | 1
2024 | Region III | BULACAN | SAN ILDEFONSO (BULACAN) | P00823407LZ | Construction of Flood Mitigation Structure | 120.9483 | 15.1182 | 96499225.37 | 96499019.62 | 2025 | 729 CONSTRUCTION, INC. (FORMERLY 722 CONSTRUCTION, INC.) | 2928 | 2024 | 2025-02-07 | 05/06/2024 | 205.75 | 0 | 2025-03-30 | 51
2023 | Region III | BULACAN | SANTA MARIA (BULACAN) | P00725745LZ | Construction of Flood Mitigation Structure | 120.9484 | 14.8071 | 86849868.05 | 86846618.32 | 2024 | M3 KONSTRACT CORPORATION (FORMERLY:MARGARITA CONSTRUCTION) | 2929 | 2023 | 2024-03-31 | 04/24/2023 | 3249.73 | 0 | 2024-03-30 |  | 1
2022 | National Capital Region | NAVOTAS CITY | CITY OF NAVOTAS (METROPOLITAN MANILA) | P00620337LZ | Construction of Flood Mitigation Structure | 120.9487 | 14.6505 | 24499743.7 | 24499589.49 | 2022 | JAGONBUILD CONSTRUCTION CORP. (FOR. JAGON BUILDERS | 2930 | 2022 | 2022-09-23 | 02/28/2022 | 154.21 | 0 | 2022-09-24 | 1
2023 | National Capital Region | VALENZUELA CITY | CITY OF VALENZUELA (METROPOLITAN MANILA) | P00727019LZ | Construction of Flood Mitigation Structure | 120.949 | 14.7139 | 19581377.84 | 19085950.1 | 2023 | NOVA VENTUS CONSTRUCTION INC. | 2931 | 2023 | 2023-08-23 | 03/17/2023 | 495427.74 | 0 | 2023-09-11 | 19
2022 | Region III | BULACAN | CITY OF MEYCAUAYAN (BULACAN) | P00632831LZ | Construction of Flood Mitigation Structure | 120.9492 | 14.746 | 48999431.12 | 39199544.9 | 2022 | TRIPLE 8 CONSTRUCTION & SUPPLY, INC. (FORMERLY TRIPLE 8 CONST. & SUPPLY) | 2932 | 2022 | 2022-07-24 | 02/28/2022 | 9799886.22 | 0 | 2022-07-23 |  | 1
2025 | Region III | NUEVA ECIJA | CABANATUAN CITY (NUEVA ECIJA) | P00921492LZ | Construction of Flood Mitigation Structure | 120.9492 | 15.5001 | 96499925.01 | 95052371.1 | 2025 | CELSO C. FERRER CONSTRUCTION CORP. | 2933 | 2025 | 2025-05-23 | 02/20/2025 | 1447553.91 | 0 | 2026-02-04 | 257
2023 | Region IV-A | CAVITE | BACOOR CITY (CAVITE) | P00725815LZ | Construction of Revetment | 120.9493 | 14.459 | 77199992.9 | 77162485.58 | 2023 | OMNICON BUILDERS | 2934 | 2023 | 2023-10-18 | 02/21/2023 | 37507.32 | 0 | 2023-12-07 | 50
2022 | Region IV-A | BATANGAS | MABINI (BATANGAS) | P00640464LZ | Construction of Flood Mitigation Structure | 120.9493 | 13.7473 | 115800000 | 115798478.8 | 2023 | V.R. PATRON BUILDERS & DEVELOPERS CORP. (PREVIOUSL | 2935 | 2022 | 2023-11-03 | 07/11/2022 | 1521.2 | 0 | 2023-11-02 |  | 1
2022 | Region III | BULACAN | BOCAUE (BULACAN) | P00632816LZ | Construction of Drainage Structure | 120.9494 | 14.8337 | 4949933.95 | 4851085.29 | 2022 | 121 CONSTRUCTION CORPORATION (FORMERLY 121 CONSTUC | 2936 | 2022 | 2022-07-04 | 03/07/2022 | 98848.66 | 0 | 2022-07-03 |  | 1
2022 | Region III | BULACAN | BUSTOS (BULACAN) | P00621534LZ | Construction of Flood Mitigation Structure | 120.9494 | 14.9536 | 48999797.41 | 48999749.14 | 2022 | TRIPLE 8 CONSTRUCTION & SUPPLY, INC. (FORMERLY TRIPLE 8 CONST. & SUPPLY) | 2937 | 2022 | 2022-09-26 | 04/05/2022 | 48.27 | 0 | 2022-10-30 | 34
2021 | Cordillera Administrative Region | ABRA |  | P00561511LZ | Construction of Flood Mitigation Structure | 120.9495 | 17.6639 | 48999985.61 | 48997000 | 2022 | ST. TIMOTHY CONSTRUCTION CORPORATION | 2938 | 2021 | 2022-07-24 | 01/07/2022 | 2985.61 | 0 | 2022-07-23 |  | 1
2022 | National Capital Region | MALABON CITY | CITY OF MALABON (METROPOLITAN MANILA) | P00631012LZ | Construction of Flood Mitigation Facility | 120.9496 | 14.6602 | 19568764.5 | 19599287.13 | 2022 | AL-REM KONSTRUCT INC. | 2939 | 2022 | 2022-12-09 | 02/28/2022 | 0 | 30522.63 | 2023-01-25 | 47
2022 | National Capital Region | MALABON CITY | CITY OF MALABON (METROPOLITAN MANILA) | P00631016LZ | Construction of Drainage Structure | 120.9497 | 14.6619 | 9746639.89 | 9793953.08 | 2023 | AL-REM KONSTRUCT INC. | 2940 | 2022 | 2023-07-03 | 02/14/2022 | 0 | 47313.19 | 2023-07-02 |  | 1
2024 | National Capital Region | MALABON CITY | CITY OF MALABON (METROPOLITAN MANILA) | P00820545LZ | Construction of Flood Mitigation Structure | 120.9498 | 14.6731 | 48947073.05 | 49000000 | 2024 | M.S. RAMOS CONSTRUCTION INC. (FORMERLY: M.S. RAMOS | 2941 | 2024 | 2024-12-06 | 02/12/2024 | 0 | 52926.95 | 2024-12-06 | 0
2024 | Region III | NUEVA ECIJA | CITY OF GAPAN (NUEVA ECIJA) | P00825090LZ | Construction of Flood Mitigation Structure | 120.9498 | 15.3177 | 96499921.45 | 94554741.69 | 2024 | F-DEY CONSTRUCTION AND TRADING / JERRY R. SANTIAGO CONSTRUCTION CORP. (FORMERLY: JERRY SANTIAGO CONSTRUCTION) | 2942 | 2024 | 2024-06-18 | 04/02/2024 | 1945179.76 | 0 | 2025-01-19 | 215
2022 | National Capital Region | VALENZUELA CITY | CITY OF VALENZUELA (METROPOLITAN MANILA) | P00620414LZ | Construction of Flood Mitigation Facility | 120.9498 | 14.7039 | 27496500.92 | 26669657.26 | 2023 | TOUGHBUILT CONSTRUCTION & TRADING, INC. | 2943 | 2022 | 2023-01-03 | 02/08/2022 | 826843.66 | 0 | 2023-01-02 |  | 1
2023 | National Capital Region | NAVOTAS CITY | CITY OF NAVOTAS (METROPOLITAN MANILA) | P00742219LZ | Construction of Flood Mitigation Facility | 120.9499 | 14.6548 | 24743127.4 | 24748789.87 | 2024 | EMICA BUILDERS AND SUPPLY | 2944 | 2023 | 2024-01-12 | 03/27/2023 | 0 | 5662.47 | 2024-01-14 | 2
2024 | Region III | BULACAN | SANTA MARIA (BULACAN) | P00845988LZ | Construction of Drainage Structure | 120.9501 | 14.8187 | 4938824.31 | 4864752.68 | 2024 | FORTUNE RDC ENTERPRISES | 2945 | 2024 | 2024-07-23 | 04/25/2024 | 74071.63 | 0 | 2024-09-11 | 50
2022 | Region III | BULACAN | SAN ILDEFONSO (BULACAN) | P00639343LZ | Construction of Flood Mitigation Structure | 120.9505 | 15.0407 | 96499601.45 | 95051142.43 | 2023 | FLORDES CONSTRUCTION & TRADING CORP. (FORMERLY FLO | 2946 | 2022 | 2023-10-08 | 03/30/2022 | 1448459.02 | 0 | 2023-10-07 |  | 1
2024 | National Capital Region | NAVOTAS CITY | CITY OF NAVOTAS (METROPOLITAN MANILA) | P00820535LZ | Construction of Drainage Structure | 120.9508 | 14.6526 | 29391050.36 | 29399809.82 | 2024 | C.B. TAMPENGCO CONSTRUCTION & SUPPLY | 2947 | 2024 | 2024-09-08 | 02/12/2024 | 0 | 8759.46 | 2024-09-07 |  | 1
2024 | National Capital Region | NAVOTAS CITY | CITY OF NAVOTAS (METROPOLITAN MANILA) | P00820521LZ | Construction of Drainage Structure | 120.9508 | 14.6525 | 11759800.79 | 11759144.81 | 2024 | TRI-DAN-J CONSTRUCTION AND TRADING | 2948 | 2024 | 2024-05-20 | 02/12/2024 | 655.98 | 0 | 2024-06-09 | 20
2023 | Region IV-A | BATANGAS | SAN NICOLAS (BATANGAS) | P00742394LZ | Construction of Slope Protection Structure | 120.9509 | 13.9295 | 29700000 | 29699702 | 2024 | VAN MAKJAY CONSTRUCTION | 2949 | 2023 | 2024-02-01 | 03/21/2023 | 298 | 0 | 2024-01-31 |  | 1
2024 | National Capital Region | MALABON CITY | CITY OF MALABON (METROPOLITAN MANILA) | P00820544LZ | Construction of Flood Mitigation Structure | 120.951 | 14.6726 | 48991675.95 | 49000000 | 2024 | JTC CRUZ CONSTRUCTION CO., INC. | 2950 | 2024 | 2024-12-20 | 02/12/2024 | 0 | 8324.05 | 2024-12-21 | 1
2024 | Region II | NUEVA VIZCAYA | SANTA FE (NUEVA VIZCAYA) | P00820160LZ | Construction of Slope Protection Structure | 120.9511 | 16.1983 | 96500000 | 96499928.41 | 2024 | BRG CONSTRUCTION | 2951 | 2024 | 2024-09-29 | 02/16/2024 | 71.59 | 0 | 2024-12-18 | 80
2022 | Region IV-A | CAVITE | BACOOR CITY (CAVITE) | P00641931LZ | Construction of Flood Mitigation Structure | 120.9512 | 14.4418 | 58799951.08 | 29399135.28 | 2023 | ALMAKAR BUILDERS & METAL WORKS | 2952 | 2022 | 2023-10-07 | 05/04/2022 | 29400815.8 | 0 | 2023-10-06 |  | 1
2023 | Region III | BULACAN | MARILAO (BULACAN) | P00725743LZ | Construction of Flood Mitigation Structure | 120.9513 | 14.7646 | 67548754.34 | 66535523.02 | 2023 | A.J. LAVA BUILDERS CORP. (FORMERLY: A.J. LAVA BUIL | 2953 | 2023 | 2023-08-29 | 02/22/2023 | 1013231.32 | 0 | 2023-08-28 |  | 1
2024 | Region IV-A | CAVITE | BACOOR CITY (CAVITE) | P00820325LZ | Construction of Revetment | 120.9514 | 14.4501 | 96499998.38 | 96499827.17 | 2024 | ALMAKAR BUILDERS & METAL WORKS | 2954 | 2024 | 2024-11-15 | 02/21/2024 | 171.21 | 0 | 2025-01-14 | 60
2022 | Region IV-A | CAVITE | BACOOR CITY (CAVITE) | P00641930LZ | Construction of Flood Mitigation Structure | 120.9514 | 14.4422 | 58799951.08 | 29398828.55 | 2023 | ALMAKAR BUILDERS & METAL WORKS | 2955 | 2022 | 2023-10-07 | 05/04/2022 | 29401122.53 | 0 | 2023-10-06 |  | 1
2022 | Region IV-A | BATANGAS | SAN NICOLAS (BATANGAS) | P00620893LZ | Construction of Flood Mitigation Structure | 120.9515 | 13.9306 | 77200000 | 77198940.97 | 2022 | V.R. PATRON BUILDERS & DEVELOPERS CORP. (PREVIOUSL | 2956 | 2022 | 2022-12-06 | 02/23/2022 | 1059.03 | 0 | 2023-02-19 | 75
2022 | National Capital Region | MALABON CITY | CITY OF MALABON (METROPOLITAN MANILA) | P00637756LZ | Construction of Drainage Structure | 120.9516 | 14.6867 | 9799862.54 | 9900000 | 2022 | GECEL CONSTRUCTION | 2957 | 2022 | 2022-11-18 | 03/24/2022 | 0 | 100137.46 | 2022-11-17 |  | 1
2022 | National Capital Region | MALABON CITY | CITY OF MALABON (METROPOLITAN MANILA) | P00632703LZ | Construction of Flood Mitigation Facility | 120.9517 | 14.6535 | 21554682.3 | 21779964.74 | 2022 | AL-REM KONSTRUCT INC. | 2958 | 2022 | 2022-10-25 | 02/28/2022 | 0 | 225282.44 | 2022-10-24 |  | 1
2024 | Region IV-A | CAVITE | BACOOR CITY (CAVITE) | P00823548LZ | Construction of Revetment | 120.9519 | 14.4487 | 96499973.59 | 96097340.67 | 2025 | GRAIA CONSTRUCTION CORPORATION | 2959 | 2024 | 2025-03-10 | 05/17/2024 | 402632.92 | 0 | 2025-07-09 | 121
2023 | Region II | NUEVA VIZCAYA | SANTA FE (NUEVA VIZCAYA) | P00725662LZ | Construction of Flood Mitigation Structure | 120.9519 | 16.2117 | 96500000 | 96488725.58 | 2023 | AMP 723 CONSTRUCTION CORPORATION (FORMERLY: A.M.P. CONSTRUCTION) / KEVIN PAUL CONSTRUCTION | 2960 | 2023 | 2023-10-15 | 02/10/2023 | 11274.42 | 0 | 2023-10-14 |  | 1
2024 | Region IV-B | OCCIDENTAL MINDORO | SABLAYAN (OCCIDENTAL MINDORO) | P00825124LZ | Construction of Flood Mitigation Structure | 120.952 | 12.6583 | 193000000 | 192997550.6 | 2024 | GOLDEN J'S CONSTRUCTION SERVICES | 2961 | 2024 | 2024-09-05 | 03/02/2024 | 2449.4 | 0 | 2025-02-23 | 171
2023 | Region III | NUEVA ECIJA | CITY OF GAPAN (NUEVA ECIJA) | P00740600LZ | Construction of Drainage Structure | 120.9523 | 15.3127 | 19599956.44 | 19599909.61 | 2023 | R.A. PAHATI CONST. & SUPPLY, INC. | 2962 | 2023 | 2023-07-17 | 03/24/2023 | 46.83 | 0 | 2023-09-09 | 54
2022 | National Capital Region | VALENZUELA CITY | CITY OF VALENZUELA (METROPOLITAN MANILA) | P00620415LZ | Construction of Flood Mitigation Facility | 120.9523 | 14.7063 | 39178967.46 | 37997833.18 | 2022 | TOUGHBUILT CONSTRUCTION & TRADING, INC. | 2963 | 2022 | 2022-12-13 | 02/08/2022 | 1181134.28 | 0 | 2023-01-02 | 20
2023 | Region III | BULACAN | BUSTOS (BULACAN) | P00726716LZ | Construction of Flood Mitigation Structure | 120.9523 | 14.9561 | 48999415.58 | 48992852.15 | 2023 | TRIPLE 8 CONSTRUCTION & SUPPLY, INC. (FORMERLY TRIPLE 8 CONST. & SUPPLY) | 2964 | 2023 | 2023-10-03 | 02/06/2023 | 6563.43 | 0 | 2023-10-02 |  | 1
2022 | Region III | BULACAN | SAN ILDEFONSO (BULACAN) | P00639344LZ | Construction of Flood Mitigation Structure | 120.9524 | 15.0373 | 96499667.16 | 95051207.16 | 2023 | FLORDES CONSTRUCTION & TRADING CORP. (FORMERLY FLO | 2965 | 2022 | 2023-01-07 | 03/30/2022 | 1448460 | 0 | 2023-01-06 |  | 1
2024 | Region III | BULACAN | CITY OF MEYCAUAYAN (BULACAN) | P00825104LZ | Construction of Flood Mitigation Facility | 120.9525 | 14.7513 | 48235603.39 | 48249942.61 | 2025 | ALPHA & OMEGA GEN. CONTRACTOR & DEVELOPMENT CORP. / JB CONSTRUCTION AND SUPPLY INC. (FORMERLY:JB CONSTRUCTION AND SUPPLY) | 2966 | 2024 | 2025-04-11 | 06/05/2024 | 0 | 14339.22 | 2025-04-10 |  | 1
2023 | Region IV-B | OCCIDENTAL MINDORO | CALINTAAN (OCCIDENTAL MINDORO) | P00726765LZ | Construction of Flood Mitigation Structure | 120.9526 | 12.5851 | 45080000 | 45079468.4 | 2023 | R N V CONSTRUCTION | 2967 | 2023 | 2023-06-15 | 02/10/2023 | 531.6 | 0 | 2023-08-16 | 62
2022 | Region IV-A | CAVITE | CITY OF DASMARIÃ‘AS (CAVITE) | P00620897LZ | Construction of Slope Protection Structure | 120.9527 | 14.334 | 96499988.29 | 96498513.53 | 2023 | KLDS TRADING & CONSTRUCTION | 2968 | 2022 | 2023-02-24 | 03/02/2022 | 1474.76 | 0 | 2023-02-23 |  | 1
2023 | Region III | BULACAN | CITY OF MEYCAUAYAN (BULACAN) | P00727364LZ | Rehabilitation / Major Repair of Flood Mitigation Facility | 120.9527 | 14.7513 | 29399433.89 | 29105439.55 | 2023 | FORTUNE RDC ENTERPRISES | 2969 | 2023 | 2023-04-30 | 03/13/2023 | 293994.34 | 0 | 2023-06-16 | 47
2023 | Region IV-B | OCCIDENTAL MINDORO | CALINTAAN (OCCIDENTAL MINDORO) | P00726599LZ | Construction of Flood Mitigation Structure | 120.9528 | 12.5289 | 96500000 | 96424967.48 | 2024 | EIGHT J'S CONSTRUCTION SERVICES | 2970 | 2023 | 2024-01-07 | 05/12/2023 | 75032.52 | 0 | 2024-01-06 |  | 1
2022 | National Capital Region | VALENZUELA CITY | CITY OF VALENZUELA (METROPOLITAN MANILA) | P00620413LZ | Construction of Flood Mitigation Facility | 120.9528 | 14.6989 | 29375016.64 | 28495848.53 | 2023 | TOUGHBUILT CONSTRUCTION & TRADING, INC. | 2971 | 2022 | 2023-01-03 | 02/08/2022 | 879168.11 | 0 | 2023-01-02 |  | 1
2024 | Region IV-A | CAVITE | BACOOR CITY (CAVITE) | P00846058LZ | Construction of Revetment | 120.9532 | 14.4638 | 15839917.35 | 15839774.23 | 2024 | ALMAKAR BUILDERS & METAL WORKS | 2972 | 2024 | 2024-09-13 | 05/15/2024 | 143.12 | 0 | 2024-10-16 | 33
2024 | National Capital Region | MALABON CITY | CITY OF MALABON (METROPOLITAN MANILA) | P00823268LZ | Construction of Flood Mitigation Facility | 120.9533 | 14.6744 | 144668963.5 | 144747339.9 | 2024 | E. F. CHUA CONSTRUCTION, INC. | 2973 | 2024 | 2024-08-31 | 03/08/2024 | 0 | 78376.4 | 2024-09-02 | 2
2024 | National Capital Region | MALABON CITY | CITY OF MALABON (METROPOLITAN MANILA) | P00820037LZ | Construction of Flood Mitigation Structure | 120.9534 | 14.6528 | 96455205.1 | 93551903.43 | 2024 | A.L. SALAZAR CONSTRUCTION, INC. / ROTAFLEX CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY:ROTA FLEX CONSTRUCTION) | 2974 | 2024 | 2024-11-18 | 02/21/2024 | 2903301.67 | 0 | 2025-02-13 | 87
2023 | National Capital Region | MALABON CITY | CITY OF MALABON (METROPOLITAN MANILA) | P00726797LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.9534 | 14.6639 | 144745347.2 | 144750000 | 2024 | L.R. TIQUI BUILDERS, INC. | 2975 | 2023 | 2024-04-05 | 04/19/2023 | 0 | 4652.8 | 2024-04-11 | 6
2022 | Region III | BULACAN | CITY OF MEYCAUAYAN (BULACAN) | P00620164LZ | Construction of Flood Mitigation Structure | 120.9535 | 14.7397 | 95534332.28 | 91703405.56 | 2022 | TRIPLE 8 CONSTRUCTION & SUPPLY, INC. (FORMERLY TRIPLE 8 CONST. & SUPPLY) | 2976 | 2022 | 2022-09-05 | 03/07/2022 | 3830926.72 | 0 | 2022-09-04 |  | 1
2022 | National Capital Region | MALABON CITY | CITY OF MALABON (METROPOLITAN MANILA) | P00620046LZ | Construction of Flood Mitigation Structure | 120.9536 | 14.6704 | 63696605.7 | 62722541.71 | 2023 | MEGAY CONSTRUCTION INC. (FORMERLY: MEGAY CONSTRUCTION) / MGY BUILDERS CORPORATION | 2977 | 2022 | 2023-02-17 | 03/24/2022 | 974063.99 | 0 | 2023-02-15 |  | 2
2021 | National Capital Region | MALABON CITY |  | P00525707LZ | Construction of Dike | 120.9537 | 14.6634 | 41644719.63 | 41649942.02 | 2022 | MEGAY CONSTRUCTION INC. (FORMERLY: MEGAY CONSTRUCTION) | 2978 | 2021 | 2022-10-28 | 03/24/2022 | 0 | 5222.39 | 2022-10-31 | 3
2024 | Cordillera Administrative Region | MOUNTAIN PROVINCE | BONTOC (CAPITAL) (MOUNTAIN PROVINCE) | P00839567LZ | Construction of Flood Mitigation Structure | 120.9541 | 17.151 | 4949999.5 | 4950000 | 2024 | YCHONGLIYAN CONSTRUCTION | 2979 | 2024 | 2024-07-15 | 05/06/2024 | 0 | 0.5 | 2024-07-20 | 5
2023 | Region III | NUEVA ECIJA | CITY OF GAPAN (NUEVA ECIJA) | P00726523LZ | Construction of Flood Mitigation Structure | 120.9543 | 15.3186 | 116311439.5 | 116310433 | 2023 | F-DEY CONSTRUCTION AND TRADING / DGSARM BUILDERS INC. (FORMERLY: D.G. SARMENTA CONSTRUCTION) | 2980 | 2023 | 2023-10-20 | 04/11/2023 | 1006.5 | 0 | 2024-02-03 | 106
2022 | Cordillera Administrative Region | MOUNTAIN PROVINCE | BONTOC (CAPITAL) (MOUNTAIN PROVINCE) | P00632787LZ | Construction of Flood Mitigation Structure | 120.9545 | 17.1504 | 4949999.7 | 4950000 | 2022 | YCHONGLIYAN CONSTRUCTION | 2981 | 2022 | 2022-07-03 | 02/17/2022 | 0 | 0.3 | 2022-07-02 |  | 1
2023 | Region III | NUEVA ECIJA | CITY OF GAPAN (NUEVA ECIJA) | P00727302LZ | Construction of Flood Mitigation Structure | 120.9546 | 15.3181 | 96499911.74 | 96499930.51 | 2023 | R.A. PAHATI CONST. & SUPPLY, INC. | 2982 | 2023 | 2023-09-22 | 03/24/2023 | 0 | 18.77 | 2024-01-10 | 110
2023 | National Capital Region | NAVOTAS CITY | CITY OF NAVOTAS (METROPOLITAN MANILA) | P00726998LZ | Construction of Flood Mitigation Facility | 120.9547 | 14.6503 | 23272624.4 | 23266135.62 | 2023 | WAY MAKER GENERAL CONTRACTOR OPC | 2983 | 2023 | 2023-11-02 | 03/08/2023 | 6488.78 | 0 | 2023-11-01 |  | 1
2023 | Region IV-B | ORIENTAL MINDORO | PUERTO GALERA (ORIENTAL MINDORO) | P00742457LZ | Construction of Drainage Structure | 120.9547 | 13.4994 | 4950000 | 4949871.74 | 2023 | HEAZ CONSTRUCTION | 2984 | 2023 | 2023-07-08 | 03/30/2023 | 128.26 | 0 | 2023-07-07 |  | 1
2022 | Region IV-A | CAVITE | BACOOR CITY (CAVITE) | P00631297LZ | Construction of Flood Mitigation Structure | 120.955 | 14.4497 | 19599972.66 | 9799854.94 | 2023 | OMNICON BUILDERS | 2985 | 2022 | 2023-10-24 | 04/04/2022 | 9800117.72 | 0 | 2023-10-23 |  | 1
2022 | Region III | BULACAN | SANTA MARIA (BULACAN) | P00631224LZ | Construction of Flood Mitigation Structure | 120.955 | 14.7983 | 7838583.29 | 7836269.39 | 2022 | 3AMR CONSTRUCTION SERVICES INC.(FORMERLY: 3AMR CONSTRUCTION SERVICES) | 2986 | 2022 | 2022-11-27 | 06/27/2022 | 2313.9 | 0 | 2022-11-26 |  | 1
2023 | Region III | BULACAN | MARILAO (BULACAN) | P00725744LZ | Construction of Flood Mitigation Structure | 120.955 | 14.768 | 57898878.97 | 57899228.21 | 2023 | A.J. LAVA BUILDERS CORP. (FORMERLY: A.J. LAVA BUIL | 2987 | 2023 | 2023-10-20 | 02/22/2023 | 0 | 349.24 | 2023-10-19 |  | 1
2023 | National Capital Region | VALENZUELA CITY | CITY OF VALENZUELA (METROPOLITAN MANILA) | P00727020LZ | Construction of Flood Mitigation Facility | 120.9552 | 14.709 | 29375181.46 | 28627073.37 | 2024 | NOVA VENTUS CONSTRUCTION INC. | 2988 | 2023 | 2024-06-05 | 03/17/2023 | 748108.09 | 0 | 2024-02-08 |  | 118
2023 | National Capital Region | NAVOTAS CITY | CITY OF NAVOTAS (METROPOLITAN MANILA) | P00726991LZ | Construction of Flood Mitigation Facility | 120.9553 | 14.653 | 23272418.8 | 23274555.73 | 2023 | EARTHWORK BUILDERS, INC. (FORMERLY: EARTHWORK MOVERS) | 2989 | 2023 | 2023-10-10 | 03/08/2023 | 0 | 2136.93 | 2023-10-29 | 19
2023 | National Capital Region | NAVOTAS CITY | CITY OF NAVOTAS (METROPOLITAN MANILA) | P00742216LZ | Construction of Flood Mitigation Facility | 120.9553 | 14.6488 | 19796201.55 | 19799964.89 | 2023 | WAY MAKER GENERAL CONTRACTOR OPC | 2990 | 2023 | 2023-09-22 | 03/27/2023 | 0 | 3763.34 | 2023-09-21 |  | 1
2023 | Region IV-A | CAVITE | TAGAYTAY CITY (CAVITE) | P00726218LZ | Construction of Slope Protection Structure | 120.9553 | 14.1309 | 9799597.75 | 9799430.14 | 2023 | WRC CONSTRUCTION AND GENERAL MERCHANDISE | 2991 | 2023 | 2023-07-24 | 02/17/2023 | 167.61 | 0 | 2023-07-23 |  | 1
2024 | National Capital Region | NAVOTAS CITY | CITY OF NAVOTAS (METROPOLITAN MANILA) | P00845859LZ | Construction of Flood Mitigation Structure | 120.9558 | 14.6393 | 9899720.83 | 9899596.98 | 2024 | JONOR DC CONSTRUCTION | 2992 | 2024 | 2024-08-12 | 02/23/2024 | 123.85 | 0 | 2024-08-19 | 7
2022 | National Capital Region | NAVOTAS CITY | CITY OF NAVOTAS (METROPOLITAN MANILA) | P00620019LZ | Construction of Drainage Structure | 120.956 | 14.6392 | 53891223.95 | 53074618.75 | 2023 | PRIME PACIFIC MARINE & INDUSTRIAL SERVICES CORP. | 2993 | 2022 | 2023-03-15 | 02/21/2022 | 816605.2 | 0 | 2023-03-16 | 1
2022 | National Capital Region | NAVOTAS CITY | CITY OF NAVOTAS (METROPOLITAN MANILA) | P00620339LZ | Construction of Drainage Structure | 120.956 | 14.6392 | 9787727.85 | 9799337.36 | 2022 | C.B. TAMPENGCO CONSTRUCTION & SUPPLY | 2994 | 2022 | 2022-07-08 | 02/14/2022 | 0 | 11609.51 | 2022-07-07 |  | 1
2022 | Region III | BULACAN | SAN MIGUEL (BULACAN) | P00620525LZ | Construction of Flood Mitigation Structure | 120.956 | 15.1331 | 46059664.51 | 45004286 | 2022 | GLOBALCRETE BUILDERS INC. | 2995 | 2022 | 2022-09-11 | 02/28/2022 | 1055378.51 | 0 | 2022-09-10 |  | 1
2022 | Region IV-A | CAVITE | BACOOR CITY (CAVITE) | P00630952LZ | Construction of Revetment | 120.9561 | 14.465 | 77199985.03 | 77199196.47 | 2023 | GRAIA CONSTRUCTION CORPORATION | 2996 | 2022 | 2023-11-20 | 04/07/2022 | 788.56 | 0 | 2024-02-04 | 76
2022 | Region IV-A | CAVITE | CITY OF DASMARIÃ‘AS (CAVITE) | P00620894LZ | Construction of Slope Protection Structure | 120.9562 | 14.3284 | 94569928.24 | 94569844.56 | 2023 | KLDS TRADING & CONSTRUCTION | 2997 | 2022 | 2023-03-10 | 03/02/2022 | 83.68 | 0 | 2023-03-25 | 15
2023 | National Capital Region | NAVOTAS CITY | CITY OF NAVOTAS (METROPOLITAN MANILA) | P00726990LZ | Construction of Flood Mitigation Facility | 120.9562 | 14.6486 | 23269137.14 | 23273276.64 | 2023 | WAY MAKER GENERAL CONTRACTOR OPC | 2998 | 2023 | 2023-12-26 | 03/08/2023 | 0 | 4139.5 | 2023-12-26 | 0
2023 | National Capital Region | NAVOTAS CITY | CITY OF NAVOTAS (METROPOLITAN MANILA) | P00742222LZ | Construction of Flood Mitigation Facility | 120.9563 | 14.6538 | 19793401.5 | 19799982.32 | 2024 | EMICA BUILDERS AND SUPPLY | 2999 | 2023 | 2024-01-25 | 03/27/2023 | 0 | 6580.82 | 2024-01-24 |  | 1
2022 | National Capital Region | MALABON CITY | CITY OF MALABON (METROPOLITAN MANILA) | P00621405LZ | Construction of Flood Mitigation Facility | 120.9564 | 14.655 | 48996047.5 | 48997556.66 | 2023 | ROTAFLEX CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY:ROTA FLEX CONSTRUCTION) / NEWBIG FOUR J CONSTRUCTION INC., (FORMERLY FOUR J | 3000 | 2022 | 2023-03-15 | 03/24/2022 | 0 | 1509.16 | 2023-03-17 | 2
2022 | Region II | CAGAYAN | SANTA PRAXEDES (CAGAYAN) | P00640508LZ | Construction of Slope Protection Structure | 120.9873 | 18.549 | 11880000 | 11880000 | 2022 | JEICCA BUILDERS | 3001 | 2022 | 2022-09-02 | 03/25/2022 | 0 | 0 | 2022-09-01 |  | 1
2022 | Region III | BULACAN | BALAGTAS (BIGAA) (BULACAN) | P00631179LZ | Construction of Flood Mitigation Structure | 120.9873 | 14.8132 | 45079581.87 | 45079869.08 | 2022 | TOPNOTCH CATALYST BUILDERS INC. / BLACK HARDHAT INC. (FORMERLY: JCHARDHAT INC.) | 3002 | 2022 | 2022-12-02 | 02/24/2022 | 0 | 287.21 | 2022-12-19 | 17
2023 | Region II | CAGAYAN | SANTA PRAXEDES (CAGAYAN) | P00736185LZ | Construction of Flood Mitigation Structure | 120.9875 | 18.5731 | 14700000 | 14700000 | 2023 | OCP CONSTRUCTION | 3003 | 2023 | 2023-06-29 | 02/01/2023 | 0 | 0 | 2023-06-28 |  | 1
2022 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00620061LZ | Construction of Flood Mitigation Facility | 120.971 | 14.6171 | 72374819.67 | 69116317.98 | 2023 | LE BRON CONSTRUCTION / AYLAN CONSTRUCTION & TRADING | 3004 | 2022 | 2023-07-28 | 04/01/2022 | 3258501.69 | 0 | 2023-08-21 | 24
2022 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00620067LZ | Construction of Drainage Structure | 120.9875 | 14.5709 | 77200000 | 77169300.35 | 2022 | TRIPLE 8 CONSTRUCTION & SUPPLY, INC. (FORMERLY TRIPLE 8 CONST. & SUPPLY) | 3005 | 2022 | 2022-08-30 | 02/28/2022 | 30699.65 | 0 | 2022-11-13 | 75
2024 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00824613LZ | Construction of Revetment | 120.9878 | 14.5946 | 24499202.34 | 24499058.29 | 2024 | W.J. CONSTRUCTION OPC (FORMERLY: W.J. CONSTRUCTION) | 3006 | 2024 | 2024-06-18 | 02/13/2024 | 144.05 | 0 | 2024-07-31 | 43
2024 | National Capital Region | CALOOCAN CITY | CALOOCAN CITY (METROPOLITAN MANILA) | P00824605LZ | Construction of Drainage Structure | 120.9879 | 14.6442 | 19599830.34 | 19169148.28 | 2024 | DREAMWORX BUILDER & TRADING, INC. | 3007 | 2024 | 2024-09-30 | 02/27/2024 | 430682.06 | 0 | 2024-10-22 | 22
2022 | Region III | NUEVA ECIJA | PEÃ‘ARANDA (NUEVA ECIJA) | P00632836LZ | Construction of Drainage Structure | 121.0045 | 15.3508 | 7919551.33 | 7840925.62 | 2022 | NIVIN DEVELOPMENT CONSTRUCTION CORP. | 3008 | 2022 | 2022-07-19 | 02/14/2022 | 78625.71 | 0 | 2022-07-15 |  | 4
2024 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00823244LZ | Construction of Flood Mitigation Facility | 120.9772 | 14.6082 | 144749532 | 144747306.1 | 2024 | EIGHT J'S CONSTRUCTION SERVICES | 3009 | 2024 | 2024-06-28 | 02/07/2024 | 2225.9 | 0 | 2024-07-28 | 30
2023 | National Capital Region | CALOOCAN CITY | CALOOCAN CITY (METROPOLITAN MANILA) | P00742242LZ | Construction of Drainage Structure | 120.988 | 14.6449 | 9893317.67 | 9666111.95 | 2023 | 5-1 CONSTRUCTION CORPORATION | 3010 | 2023 | 2023-08-28 | 03/17/2023 | 227205.72 | 0 | 2023-08-12 |  | 16
2022 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00620432LZ | Construction of Flood Mitigation Structure | 120.988 | 14.5983 | 48999912.96 | 48999120.68 | 2022 | SUPREME ABF CONST. & CONST. SUPPLY COMPANY INC. | 3011 | 2022 | 2022-10-06 | 02/18/2022 | 792.28 | 0 | 2022-10-05 |  | 1
2024 | National Capital Region | VALENZUELA CITY | CITY OF VALENZUELA (METROPOLITAN MANILA) | P00820585LZ | Construction of Drainage Structure | 120.988 | 14.6928 | 9788963.69 | 9446337.32 | 2024 | ISECURE BUILDER AND CONSTRUCTION SUPPLIES | 3012 | 2024 | 2024-06-03 | 02/14/2024 | 342626.37 | 0 | 2024-06-11 | 8
2022 | National Capital Region | MALABON CITY | CITY OF MALABON (METROPOLITAN MANILA) | P00620013LZ | Construction of Flood Mitigation Structure | 120.9881 | 14.6694 | 92098700 | 90696775.43 | 2023 | A.L. SALAZAR CONSTRUCTION, INC. | 3013 | 2022 | 2023-02-03 | 02/21/2022 | 1401924.57 | 0 | 2023-02-06 | 3
2023 | Region IV-A | CAVITE | BACOOR CITY (CAVITE) | P00742426LZ | Construction of Drainage Structure | 120.9881 | 14.4171 | 3464953.33 | 3457587.29 | 2023 | OMNICON BUILDERS | 3014 | 2023 | 2023-06-30 | 04/24/2023 | 7366.04 | 0 | 2023-07-21 | 21
2023 | Region II | CAGAYAN | SANTA PRAXEDES (CAGAYAN) | P00736186LZ | Construction of Flood Mitigation Structure | 121.0148 | 18.5442 | 14700000 | 14700000 | 2023 | OCP CONSTRUCTION | 3015 | 2023 | 2023-07-24 | 02/01/2023 | 0 | 0 | 2023-06-28 |  | 26
2022 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00620100LZ | Construction of Flood Mitigation Facility | 120.9882 | 14.5943 | 96499921.47 | 96467251.95 | 2023 | AL-AMEN BUILDERS / ST. TIMOTHY CONSTRUCTION CORPORATION | 3016 | 2022 | 2023-08-15 | 02/24/2022 | 32669.52 | 0 | 2023-08-14 |  | 1
2022 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00620426LZ | Construction of Flood Mitigation Structure | 120.9882 | 14.5984 | 41795839.58 | 39892353.69 | 2022 | EL-JAKE BUILDERS | 3017 | 2022 | 2022-10-05 | 02/23/2022 | 1903485.89 | 0 | 2022-10-04 |  | 1
2023 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00725496LZ | Construction of Flood Mitigation Structure | 120.9946 | 14.6003 | 38599963.4 | 38542194.45 | 2023 | NEWBIG FOUR J CONSTRUCTION INC., (FORMERLY FOUR J | 3018 | 2023 | 2023-12-18 | 02/17/2023 | 57768.95 | 0 | 2024-01-31 | 44
2022 | Region IV-A | CAVITE | CITY OF CARMONA (CAVITE) | P00620225LZ | Construction of Revetment | 121.049 | 14.3183 | 96499997.8 | 96486466.78 | 2022 | KLDS TRADING & CONSTRUCTION / OMNICON BUILDERS | 3019 | 2022 | 2022-07-22 | 03/07/2022 | 13531.02 | 0 | 2023-02-13 | 206
2024 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00823239LZ | Construction of Flood Mitigation Facility | 120.971 | 14.6179 | 96498992.55 | 96496919.11 | 2025 | JELSIE CONSTRUCTION & SUPPLY | 3020 | 2024 | 2025-02-18 | 02/07/2024 | 2073.44 | 0 | 2025-03-30 | 40
2024 | Region II | CAGAYAN | SANTA PRAXEDES (CAGAYAN) | P00845936LZ | Construction of Flood Mitigation Structure | 120.9882 | 18.5636 | 4950000 | 4874771.71 | 2024 | OCP CONSTRUCTION | 3021 | 2024 | 2024-07-13 | 04/17/2024 | 75228.29 | 0 | 2024-07-12 |  | 1
2024 | Region III | BULACAN | SANTA MARIA (BULACAN) | P00845782LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.9883 | 14.8405 | 98999423.83 | 98912408.09 | 2025 | NEWBIG FOUR J CONSTRUCTION INC., (FORMERLY FOUR J | 3022 | 2024 | 2025-04-06 | 03/18/2024 | 87015.74 | 0 | 2025-04-05 |  | 1
2023 | National Capital Region | PASAY CITY | PASAY CITY (METROPOLITAN MANILA) | P00726037LZ | Construction of Slope Protection Structure | 120.9883 | 14.5444 | 29399800.22 | 29399474.44 | 2023 | ALE BUILDERS CONSTRUCTION AND DEVELOPMENT CORP. | 3023 | 2023 | 2023-05-08 | 02/16/2023 | 325.78 | 0 | 2023-10-12 | 157
2022 | National Capital Region | PARAÃ‘AQUE CITY | CITY OF PARAÃ‘AQUE (METROPOLITAN MANILA) | P00620077LZ | Construction of Revetment | 120.9885 | 14.484 | 96500000 | 96500000 | 2022 | R.M. NUNEZ CONSTRUCTION CORPORATION(FORMERLY R.M. / AKN CONSTRUCTION CORPORATION | 3024 | 2022 | 2022-12-12 | 02/17/2022 | 0 | 0 | 2023-02-10 | 60
2024 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00823249LZ | Construction of Flood Mitigation Facility | 120.9885 | 14.5941 | 76234855.21 | 76149978.47 | 2024 | JELSIE CONSTRUCTION & SUPPLY | 3025 | 2024 | 2024-06-15 | 02/14/2024 | 84876.74 | 0 | 2024-06-14 |  | 1
2022 | National Capital Region | PARAÃ‘AQUE CITY | CITY OF PARAÃ‘AQUE (METROPOLITAN MANILA) | P00620369LZ | Rehabilitation / Major Repair of Drainage Structure | 120.9886 | 14.4891 | 24500000 | 24491160.45 | 2022 | ALPHA & OMEGA GEN. CONTRACTOR & DEVELOPMENT CORP. | 3026 | 2022 | 2022-12-19 | 02/09/2022 | 8839.55 | 0 | 2022-12-18 |  | 1
2024 | Region III | BULACAN | SANTA MARIA (BULACAN) | P00839582LZ | Construction of Flood Mitigation Structure | 120.9886 | 14.8407 | 49499175.02 | 49496490.33 | 2024 | C & F CONSTRUCTION & DEVELOPMENT CORPORATION | 3027 | 2024 | 2024-10-26 | 02/12/2024 | 2684.69 | 0 | 2024-10-25 |  | 1
2023 | National Capital Region | PARAÃ‘AQUE CITY | CITY OF PARAÃ‘AQUE (METROPOLITAN MANILA) | P00737396LZ | Construction of Drainage Structure | 120.9886 | 14.4892 | 13860000 | 13856409.32 | 2023 | K84 CONSTRUCTION AND DEVELOPMENT CORPORATION | 3028 | 2023 | 2023-09-19 | 03/09/2023 | 3590.68 | 0 | 2023-10-03 | 14
2023 | National Capital Region | PARAÃ‘AQUE CITY | CITY OF PARAÃ‘AQUE (METROPOLITAN MANILA) | P00727011LZ | Construction of Flood Mitigation Structure | 120.9887 | 14.4971 | 39200000 | 39180318 | 2024 | KING EIGHT BUILDERS AND SUPPLY | 3029 | 2023 | 2024-01-18 | 04/17/2023 | 19682 | 0 | 2024-01-21 | 3
2023 | National Capital Region | LAS PIÃ‘AS CITY | CITY OF LAS PIÃ‘AS (METROPOLITAN MANILA) | P00725548LZ | Construction of Flood Mitigation Structure | 120.9887 | 14.4741 | 67549654.17 | 67548419.47 | 2023 | I&E CONSTRUCTION CORPORATION (FORMERLY: I&E CONSTR | 3030 | 2023 | 2023-09-10 | 02/13/2023 | 1234.7 | 0 | 2023-09-09 |  | 1
2022 | Region III | BULACAN | SANTA MARIA (BULACAN) | P00621537LZ | Construction of Flood Mitigation Structure | 120.9888 | 14.8265 | 48999968.79 | 48998090.48 | 2022 | ST. MATTHEW GEN. CONTRACTOR & DEVELOPMENT CORP. | 3031 | 2022 | 2022-10-15 | 03/30/2022 | 1878.31 | 0 | 2022-10-14 |  | 1
2022 | National Capital Region | VALENZUELA CITY | CITY OF VALENZUELA (METROPOLITAN MANILA) | P00620395LZ | Construction of Flood Mitigation Structure | 120.9888 | 14.68 | 19598314.51 | 19029943.69 | 2022 | SONPRO CONSTRUCTION | 3032 | 2022 | 2022-11-17 | 03/24/2022 | 568370.82 | 0 | 2022-11-17 | 0
2018 | Region IV-B | OCCIDENTAL MINDORO |  | P00223240LZ | Construction of Flood Mitigation Structure | 120.9889 | 12.4352 | 54570750 | 52442670.04 | 2023 | FFJJ CONSTRUCTION | 3033 | 2018 | 2023-01-02 | 04/20/2018 | 2128079.96 | 0 | 2018-11-21 |  | 1503
2024 | Region III | BULACAN | SANTA MARIA (BULACAN) | P00839583LZ | Construction of Flood Mitigation Structure | 120.989 | 14.8424 | 49499622.01 | 49495385.93 | 2024 | C & F CONSTRUCTION & DEVELOPMENT CORPORATION | 3034 | 2024 | 2024-12-11 | 02/12/2024 | 4236.08 | 0 | 2024-12-10 |  | 1
2022 | National Capital Region | LAS PIÃ‘AS CITY | CITY OF LAS PIÃ‘AS (METROPOLITAN MANILA) | P00620904LZ | Construction of Flood Mitigation Structure | 120.989 | 14.4829 | 48999947.72 | 48999843.4 | 2022 | I&E CONSTRUCTION CORPORATION (FORMERLY: I&E CONSTR | 3035 | 2022 | 2022-08-07 | 02/09/2022 | 104.32 | 0 | 2022-08-06 |  | 1
2023 | Region III | BULACAN | SANTA MARIA (BULACAN) | P00737466LZ | Construction of Drainage Structure | 120.9892 | 14.8027 | 5935481.14 | 5927984.05 | 2023 | PLL BUILDERS INC. | 3036 | 2023 | 2023-09-17 | 03/22/2023 | 7497.09 | 0 | 2023-09-16 |  | 1
2023 | Region III | NUEVA ECIJA | TALAVERA (NUEVA ECIJA) | P00742337LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.9894 | 15.6748 | 99000000 | 98995000 | 2023 | AMP 723 CONSTRUCTION CORPORATION (FORMERLY: A.M.P. CONSTRUCTION) | 3037 | 2023 | 2023-09-04 | 04/03/2023 | 5000 | 0 | 2023-12-12 | 99
2023 | Region IV-B | OCCIDENTAL MINDORO | RIZAL (OCCIDENTAL MINDORO) | P00726764LZ | Construction of Flood Mitigation Structure | 120.9894 | 12.4366 | 45080000 | 44927793.73 | 2023 | F.A. TORRES CONSTRUCTION / MIGHTY DRAGON BUILDERS INC. | 3038 | 2023 | 2023-05-22 | 02/10/2023 | 152206.27 | 0 | 2023-08-16 | 86
2023 | National Capital Region | PARAÃ‘AQUE CITY | CITY OF PARAÃ‘AQUE (METROPOLITAN MANILA) | P00742110LZ | Construction of Revetment | 120.9895 | 14.5027 | 99000000 | 98997516.14 | 2024 | E.R. RODRIGUEZ CONSTRUCTION CORPORATION (FORMERLY: E.R. RODRIGUEZ CONSTRUCTION) | 3039 | 2023 | 2024-11-18 | 08/14/2023 | 2483.86 | 0 | 2025-01-01 | 44
2024 | National Capital Region | PASAY CITY | PASAY CITY (METROPOLITAN MANILA) | P00839538LZ | Construction of Slope Protection Structure | 120.9895 | 14.5451 | 19799821.65 | 19572165.42 | 2024 | ALE BUILDERS CONSTRUCTION AND DEVELOPMENT CORP. | 3040 | 2024 | 2024-07-15 | 02/20/2024 | 227656.23 | 0 | 2024-08-28 | 44
2023 | National Capital Region | VALENZUELA CITY | CITY OF VALENZUELA (METROPOLITAN MANILA) | P00725563LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.9895 | 14.7009 | 77192219.07 | 75879939.88 | 2024 | CHRIZMARIE BUILDERS AND CONSTRUCTION SUPPLY | 3041 | 2023 | 2024-01-16 | 02/21/2023 | 1312279.19 | 0 | 2024-01-15 |  | 1
2021 | National Capital Region | CALOOCAN CITY |  | P00525799LZ | Construction of Drainage Structure | 120.9897 | 14.6578 | 19599818.99 | 19149003.85 | 2022 | IM CONSTRUCTION CORPORATION | 3042 | 2021 | 2022-09-13 | 02/24/2022 | 450815.14 | 0 | 2022-10-20 | 37
2023 | National Capital Region | PARAÃ‘AQUE CITY | CITY OF PARAÃ‘AQUE (METROPOLITAN MANILA) | P00726815LZ | Construction of Flood Mitigation Structure | 120.9897 | 14.5005 | 57900000 | 57900000 | 2023 | AMETHYST HORIZON BUILDERS AND GEN. CONTRACTOR AND DEVELOPMENT CORP. / K84 CONSTRUCTION AND DEVELOPMENT CORPORATION | 3043 | 2023 | 2023-12-15 | 04/12/2023 | 0 | 0 | 2024-02-19 | 66
2024 | Region III | BULACAN | SANTA MARIA (BULACAN) | P00820824LZ | Construction of Flood Mitigation Structure | 120.9897 | 14.8439 | 48249276.91 | 47520712.83 | 2025 | C & F CONSTRUCTION & DEVELOPMENT CORPORATION | 3044 | 2024 | 2025-02-05 | 04/08/2024 | 728564.08 | 0 | 2025-02-04 |  | 1
2022 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00620094LZ | Construction of Flood Mitigation Facility | 120.9898 | 14.5933 | 67549374.91 | 65691762.9 | 2022 | EIGHT J'S CONSTRUCTION SERVICES | 3045 | 2022 | 2022-11-22 | 04/01/2022 | 1857612.01 | 0 | 2023-04-14 | 143
2022 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00620099LZ | Construction of Flood Mitigation Facility | 120.9898 | 14.5933 | 91669918.39 | 91669837.5 | 2023 | EIGHT J'S CONSTRUCTION SERVICES | 3046 | 2022 | 2023-04-13 | 02/18/2022 | 80.89 | 0 | 2023-04-12 |  | 1
2022 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00620096LZ | Construction of Flood Mitigation Facility | 120.9898 | 14.5933 | 91672699.66 | 89014172 | 2022 | EIGHT J'S CONSTRUCTION SERVICES | 3047 | 2022 | 2022-11-22 | 02/17/2022 | 2658527.66 | 0 | 2023-04-17 | 146
2022 | Region III | BULACAN | SAN MIGUEL (BULACAN) | P00621277LZ | Construction of Flood Mitigation Structure | 120.9898 | 15.2217 | 61490589.09 | 61485086.19 | 2023 | L.R. TIQUI BUILDERS, INC. | 3048 | 2022 | 2023-02-28 | 03/30/2022 | 5502.9 | 0 | 2023-04-22 | 53
2021 | National Capital Region | PARAÃ‘AQUE CITY |  | P00561612LZ | Rehabilitation / Major Repair of Drainage Structure | 120.9899 | 14.4974 | 9900000 | 9900000 | 2022 | M.P.Z. CARREON BUILDERS | 3049 | 2021 | 2022-09-02 | 12/31/2021 | 0 | 0 | 2022-06-27 |  | 67
2024 | National Capital Region | PARAÃ‘AQUE CITY | CITY OF PARAÃ‘AQUE (METROPOLITAN MANILA) | P00843171LZ | Construction of Drainage Structure | 120.9899 | 14.4946 | 4825000 | 4821756.02 | 2024 | K84 CONSTRUCTION AND DEVELOPMENT CORPORATION | 3050 | 2024 | 2024-10-23 | 06/27/2024 | 3243.98 | 0 | 2024-10-23 | 0
2022 | National Capital Region | LAS PIÃ‘AS CITY | CITY OF LAS PIÃ‘AS (METROPOLITAN MANILA) | P00620905LZ | Construction of Flood Mitigation Structure | 120.99 | 14.4526 | 48997127.94 | 48996127.94 | 2023 | I&E CONSTRUCTION CORPORATION (FORMERLY: I&E CONSTR | 3051 | 2022 | 2023-04-08 | 02/09/2022 | 1000 | 0 | 2023-04-07 |  | 1
2023 | National Capital Region | PARAÃ‘AQUE CITY | CITY OF PARAÃ‘AQUE (METROPOLITAN MANILA) | P00726816LZ | Construction of Revetment | 120.9901 | 14.502 | 77200000 | 77199892.17 | 2024 | REND ENTERPRISES & GENERAL CONTRACTOR / MRRM TRADING & CONSTRUCTION | 3052 | 2023 | 2024-09-14 | 07/10/2023 | 107.83 | 0 | 2024-09-13 |  | 1
2021 | National Capital Region | VALENZUELA CITY |  | P00561467LZ | Construction of Flood Mitigation Structure | 120.9902 | 14.7462 | 96465358.98 | 94052821.99 | 2022 | J. SIMEON CONSTRUCTION | 3053 | 2021 | 2022-10-05 | 11/11/2021 | 2412536.99 | 0 | 2022-10-05 | 0
2024 | National Capital Region | CALOOCAN CITY | CALOOCAN CITY (METROPOLITAN MANILA) | P00820063LZ | Construction of Drainage Structure | 120.9902 | 14.6486 | 96495500.04 | 94183044.21 | 2024 | J. SIMEON CONSTRUCTION | 3054 | 2024 | 2024-12-09 | 02/14/2024 | 2312455.83 | 0 | 2024-11-08 |  | 31
2023 | National Capital Region | LAS PIÃ‘AS CITY | CITY OF LAS PIÃ‘AS (METROPOLITAN MANILA) | P00725912LZ | Construction of Flood Mitigation Structure | 120.9904 | 14.4547 | 48999721.32 | 48998566.62 | 2023 | I&E CONSTRUCTION CORPORATION (FORMERLY: I&E CONSTR | 3055 | 2023 | 2023-12-10 | 02/13/2023 | 1154.7 | 0 | 2023-12-09 |  | 1
2022 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00620017LZ | Construction of Drainage Structure | 120.9904 | 14.6224 | 96498802.76 | 96474444.67 | 2023 | RAICON DEVELOPMENT CORPORATION (FORMERLY : RA IGNACIO CONST. CORP.) / ST. MATTHEW GEN. CONTRACTOR & DEVELOPMENT CORP. | 3056 | 2022 | 2023-12-15 | 04/01/2022 | 24358.09 | 0 | 2023-12-30 | 15
2022 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00620068LZ | Construction of Drainage Structure | 120.9904 | 14.5724 | 51225094.97 | 51209204.28 | 2022 | N.M.E. CONSTRUCTION | 3057 | 2022 | 2022-10-04 | 02/28/2022 | 15890.69 | 0 | 2022-10-24 | 20
2024 | National Capital Region | PARAÃ‘AQUE CITY | CITY OF PARAÃ‘AQUE (METROPOLITAN MANILA) | P00845867LZ | Construction of Drainage Structure | 120.9904 | 14.4959 | 4950000 | 4949123.97 | 2024 | K84 CONSTRUCTION AND DEVELOPMENT CORPORATION | 3058 | 2024 | 2024-12-10 | 06/07/2024 | 876.03 | 0 | 2025-01-01 | 22
2022 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00620424LZ | Construction of Flood Mitigation Structure | 120.9906 | 14.5976 | 46883166.09 | 44914073.11 | 2022 | EL-JAKE BUILDERS | 3059 | 2022 | 2022-09-24 | 02/23/2022 | 1969092.98 | 0 | 2022-09-23 |  | 1
2025 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00920012LZ | Construction of Flood Mitigation Facility | 120.9906 | 14.5971 | 96499337.35 | 94675499.87 | 2025 | EIGHT J'S CONSTRUCTION SERVICES / GENECOR CONSTRUCTION SUPPLIES TRADING | 3060 | 2025 | 2025-05-22 | 02/12/2025 | 1823837.48 | 0 | 2025-05-21 |  | 1
2022 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00620002LZ | Construction of Flood Mitigation Structure | 120.9907 | 14.598 | 79273745.93 | 79252428.01 | 2022 | JMK BUILDERS CONSTRUCTION / ALPHA & OMEGA GEN. CONTRACTOR & DEVELOPMENT CORP. | 3061 | 2022 | 2022-10-21 | 02/24/2022 | 21317.92 | 0 | 2022-10-28 | 7
2022 | Region III | BULACAN | SAN MIGUEL (BULACAN) | P00639340LZ | Construction of Flood Mitigation Structure | 120.9907 | 15.2253 | 96499481.76 | 96498941.25 | 2023 | L.R. TIQUI BUILDERS, INC. | 3062 | 2022 | 2023-05-26 | 03/30/2022 | 540.51 | 0 | 2023-06-22 | 27
2024 | Region III | NUEVA ECIJA | LLANERA (NUEVA ECIJA) | P00823446LZ | Construction of Flood Mitigation Structure | 120.991 | 15.6827 | 48250000 | 47877326.45 | 2024 | SPECO BUILDERS INC. (FORMERLY VRF CONSTRUCTION) | 3063 | 2024 | 2024-07-25 | 03/14/2024 | 372673.55 | 0 | 2024-10-08 | 75
2022 | National Capital Region | PARAÃ‘AQUE CITY | CITY OF PARAÃ‘AQUE (METROPOLITAN MANILA) | P00620109LZ | Construction of Revetment | 120.991 | 14.5051 | 96500000 | 96500000 | 2023 | J.H. PAJARA CONSTRUCTION CORPORATION | 3064 | 2022 | 2023-09-23 | 02/17/2022 | 0 | 0 | 2023-09-22 |  | 1
2022 | National Capital Region | PASAY CITY | PASAY CITY (METROPOLITAN MANILA) | P00620088LZ | Rehabilitation / Major Repair of Drainage Structure | 120.9911 | 14.5454 | 64537042.72 | 64455785.31 | 2022 | TRIPLE 8 CONSTRUCTION & SUPPLY, INC. (FORMERLY TRIPLE 8 CONST. & SUPPLY) | 3065 | 2022 | 2022-09-19 | 02/28/2022 | 81257.41 | 0 | 2022-12-23 | 95
2023 | Region IV-B | OCCIDENTAL MINDORO | CALINTAAN (OCCIDENTAL MINDORO) | P00726600LZ | Construction of Flood Mitigation Structure | 120.9911 | 12.5263 | 96500000 | 96496274.13 | 2024 | JELSIE CONSTRUCTION & SUPPLY | 3066 | 2023 | 2024-01-21 | 05/26/2023 | 3725.87 | 0 | 2024-01-20 |  | 1
2024 | Region III | NUEVA ECIJA | LLANERA (NUEVA ECIJA) | P00823448LZ | Construction of Flood Mitigation Structure | 120.9911 | 15.6811 | 48250000 | 47758280.53 | 2024 | SPECO BUILDERS INC. (FORMERLY VRF CONSTRUCTION) | 3067 | 2024 | 2024-07-25 | 03/14/2024 | 491719.47 | 0 | 2024-10-08 | 75
2023 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00725505LZ | Construction of Flood Mitigation Facility | 120.9912 | 14.5996 | 95993331.2 | 93353753.52 | 2023 | EIGHT J'S CONSTRUCTION SERVICES | 3068 | 2023 | 2023-09-18 | 02/16/2023 | 2639577.68 | 0 | 2023-10-06 | 18
2023 | National Capital Region | CALOOCAN CITY | CALOOCAN CITY (METROPOLITAN MANILA) | P00737399LZ | Construction of Drainage Structure | 120.9912 | 14.6438 | 14847267.53 | 14517055.98 | 2023 | NOVA VENTUS CONSTRUCTION INC. | 3069 | 2023 | 2023-11-10 | 03/17/2023 | 330211.55 | 0 | 2023-09-11 |  | 60
2022 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00621410LZ | Construction of Flood Mitigation Structure | 120.9913 | 14.5998 | 48999544.44 | 48781885.7 | 2023 | ALPHA & OMEGA GEN. CONTRACTOR & DEVELOPMENT CORP. | 3070 | 2022 | 2023-05-14 | 05/31/2022 | 217658.74 | 0 | 2023-05-13 |  | 1
2022 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00620098LZ | Construction of Flood Mitigation Facility | 120.9914 | 14.6001 | 91672362.7 | 90964722.8 | 2023 | EIGHT J'S CONSTRUCTION SERVICES | 3071 | 2022 | 2023-04-20 | 02/17/2022 | 707639.9 | 0 | 2023-04-19 |  | 1
2022 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00620095LZ | Construction of Flood Mitigation Facility | 120.9914 | 14.6001 | 91671685.63 | 89288429.57 | 2023 | ST. TIMOTHY CONSTRUCTION CORPORATION / LDC CONSTRUCTION AND SUPPLY, INC. (FORMERLY:LDC CONSTRUCTION AND SUPPLY) | 3072 | 2022 | 2023-05-05 | 02/28/2022 | 2383256.06 | 0 | 2023-05-06 | 1
2023 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00726007LZ | Construction of Flood Mitigation Structure | 120.9915 | 14.6003 | 34784050.9 | 34724638.04 | 2024 | JELSIE CONSTRUCTION & SUPPLY | 3073 | 2023 | 2024-01-13 | 02/17/2023 | 59412.86 | 0 | 2024-01-12 |  | 1
2024 | Region III | NUEVA ECIJA | LLANERA (NUEVA ECIJA) | P00823447LZ | Construction of Flood Mitigation Structure | 120.9915 | 15.686 | 48250000 | 47767457.52 | 2024 | IRC CONSTRUCTION & SUPPLIES / SYMMETRICON BUILDERS CORP. | 3074 | 2024 | 2024-08-31 | 03/15/2024 | 482542.48 | 0 | 2024-10-09 | 39
2022 | National Capital Region | VALENZUELA CITY | CITY OF VALENZUELA (METROPOLITAN MANILA) | P00631033LZ | Construction of Drainage Structure | 120.9917 | 14.717 | 8818109.85 | 8650547.65 | 2022 | TOUGHBUILT CONSTRUCTION & TRADING, INC. | 3075 | 2022 | 2022-08-05 | 02/08/2022 | 167562.2 | 0 | 2022-08-05 | 0
2023 | National Capital Region | PARAÃ‘AQUE CITY | CITY OF PARAÃ‘AQUE (METROPOLITAN MANILA) | P00726817LZ | Construction of Revetment | 120.9917 | 14.5021 | 77200000 | 77194055.8 | 2024 | AMETHYST HORIZON BUILDERS AND GEN. CONTRACTOR AND DEVELOPMENT CORP. / K84 CONSTRUCTION AND DEVELOPMENT CORPORATION | 3076 | 2023 | 2024-09-13 | 07/10/2023 | 5944.2 | 0 | 2024-09-13 | 0
2023 | Region III | NUEVA ECIJA | SAN ANTONIO (NUEVA ECIJA) | P00727298LZ | Construction of Flood Mitigation Structure | 120.9918 | 15.3662 | 96499998.94 | 94475987.07 | 2023 | ITP CONSTRUCTION, INC. | 3077 | 2023 | 2023-07-17 | 03/23/2023 | 2024011.87 | 0 | 2024-01-18 | 185
2024 | Region III | BULACAN | SAN ILDEFONSO (BULACAN) | P00821230LZ | Construction of Flood Mitigation Structure | 120.9919 | 15.0274 | 96498109.54 | 96498717.18 | 2025 | ADSL CONSTRUCTION & TRADING | 3078 | 2024 | 2025-03-01 | 05/06/2024 | 0 | 607.64 | 2025-02-28 |  | 1
2023 | Cordillera Administrative Region | MOUNTAIN PROVINCE | BONTOC (CAPITAL) (MOUNTAIN PROVINCE) | P00726659LZ | Construction of Flood Mitigation Structure | 120.9919 | 17.06 | 29399999.9 | 29400000 | 2023 | KOMICHOV GENERAL CONSTRUCTION | 3079 | 2023 | 2023-11-30 | 08/14/2023 | 0 | 0.1 | 2024-01-17 | 48
2024 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00844683LZ | Construction of Drainage Structure | 120.9921 | 14.607 | 29399646.31 | 28396675.51 | 2024 | V.R. GUEVARRA CONSTRUCTION AND TRADING | 3080 | 2024 | 2024-08-16 | 02/08/2024 | 1002970.8 | 0 | 2024-08-30 | 14
2022 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00620065LZ | Rehabilitation / Major Repair of Drainage Structure | 120.9922 | 14.5966 | 91674489.78 | 88388729.18 | 2023 | ST. TIMOTHY CONSTRUCTION CORPORATION / ELITE GENERAL CONTRACTOR AND DEVELOPMENT CORP. | 3081 | 2022 | 2023-06-15 | 02/23/2022 | 3285760.6 | 0 | 2023-06-14 |  | 1
2022 | National Capital Region | PARAÃ‘AQUE CITY | CITY OF PARAÃ‘AQUE (METROPOLITAN MANILA) | P00620368LZ | Construction of Revetment | 120.9923 | 14.4887 | 49000000 | 48995853.71 | 2022 | SPRING STAR CONSTRUCTION AND SUPPLY | 3082 | 2022 | 2022-10-01 | 02/04/2022 | 4146.29 | 0 | 2022-09-30 |  | 1
2023 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00726008LZ | Construction of Flood Mitigation Structure | 120.9926 | 14.6006 | 34784087.93 | 34233809.58 | 2024 | ST. TIMOTHY CONSTRUCTION CORPORATION / K84 CONSTRUCTION AND DEVELOPMENT CORPORATION | 3083 | 2023 | 2024-08-15 | 02/17/2023 | 550278.35 | 0 | 2024-09-27 | 43
2023 | National Capital Region | LAS PIÃ‘AS CITY | CITY OF LAS PIÃ‘AS (METROPOLITAN MANILA) | P00725914LZ | Construction of Flood Mitigation Structure | 120.9927 | 14.4828 | 48998210.02 | 48994961.38 | 2023 | E. F. CHUA CONSTRUCTION, INC. | 3084 | 2023 | 2023-08-11 | 02/13/2023 | 3248.64 | 0 | 2023-08-10 |  | 1
2020 | National Capital Region | PARAÃ‘AQUE CITY |  | P00421301LZ | Construction of Revetment | 120.9928 | 14.5315 | 98000000 | 96500000 | 2022 | AKN CONSTRUCTION CORPORATION | 3085 | 2020 | 2022-10-24 | 11/25/2020 | 1500000 | 0 | 2022-10-25 | 1
2021 | National Capital Region | PARAÃ‘AQUE CITY |  | P00421301LZ | Construction of Revetment | 120.9928 | 14.5315 | 98000000 | 96500000 | 2022 | AKN CONSTRUCTION CORPORATION | 3086 | 2021 | 2022-10-24 | 11/25/2020 | 1500000 | 0 | 2022-10-25 | 1
2024 | National Capital Region | PARAÃ‘AQUE CITY | CITY OF PARAÃ‘AQUE (METROPOLITAN MANILA) | P00820567LZ | Construction of Revetment | 120.9928 | 14.4898 | 48625580 | 48606719.37 | 2024 | ILFREO CONSTRUCTION CORP. (FORMERLY:ILFREO CONSTRUCTION & TRADING CORP.) | 3087 | 2024 | 2024-09-18 | 02/07/2024 | 18860.63 | 0 | 2024-11-27 | 70
2021 | National Capital Region | CITY OF MANILA |  | P00525828LZ | Construction of Flood Mitigation Structure | 120.9928 | 14.6019 | 48999472.53 | 46793689.84 | 2022 | RAICON DEVELOPMENT CORPORATION (FORMERLY : RA IGNACIO CONST. CORP.) | 3088 | 2021 | 2022-10-20 | 06/28/2021 | 2205782.69 | 0 | 2022-10-26 | 6
2024 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00844682LZ | Construction of Drainage Structure | 120.9928 | 14.6075 | 29399950.39 | 28729795.19 | 2024 | V.R. GUEVARRA CONSTRUCTION AND TRADING | 3089 | 2024 | 2024-10-28 | 02/12/2024 | 670155.2 | 0 | 2024-10-27 |  | 1
2022 | National Capital Region | CALOOCAN CITY | CALOOCAN CITY (METROPOLITAN MANILA) | P00637043LZ | Construction of Drainage Structure | 120.993 | 14.6513 | 7348947.58 | 7193608.46 | 2022 | C.L. MORALES CONSTRUCTION AND TRADING | 3090 | 2022 | 2022-12-07 | 03/24/2022 | 155339.12 | 0 | 2022-09-18 |  | 80
2023 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00726795LZ | Construction of Flood Mitigation Structure | 120.9931 | 14.5707 | 48249544.03 | 48240996.26 | 2024 | ALE BUILDERS CONSTRUCTION AND DEVELOPMENT CORP. | 3091 | 2023 | 2024-04-15 | 04/20/2023 | 8547.77 | 0 | 2024-05-12 | 27
2024 | National Capital Region | CALOOCAN CITY | CALOOCAN CITY (METROPOLITAN MANILA) | P00839527LZ | Rehabilitation / Major Repair of Drainage Structure | 120.9932 | 14.6596 | 4943610.73 | 4869448.78 | 2024 | AVE-MIRA CONSTRUCTION AND TRADING | 3092 | 2024 | 2024-05-13 | 02/14/2024 | 74161.95 | 0 | 2024-05-12 |  | 1
2023 | National Capital Region | PARAÃ‘AQUE CITY | CITY OF PARAÃ‘AQUE (METROPOLITAN MANILA) | P00726818LZ | Construction of Revetment | 120.9933 | 14.5018 | 67550000 | 67543629.01 | 2024 | AARCON BUILDERS | 3093 | 2023 | 2024-12-03 | 07/20/2023 | 6370.99 | 0 | 2024-12-02 |  | 1
2023 | Region IV-A | CAVITE | GEN. MARIANO ALVAREZ (CAVITE) | P00726571LZ | Construction of Revetment | 120.9936 | 14.2856 | 96499951.51 | 96499372.38 | 2024 | PRIME PACIFIC MARINE & INDUSTRIAL SERVICES CORP. | 3094 | 2023 | 2024-10-05 | 04/10/2023 | 579.13 | 0 | 2024-05-02 |  | 156
2024 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00820619LZ | Construction of Drainage Structure | 120.9937 | 14.6104 | 29399964.56 | 29396831.65 | 2024 | RAICON DEVELOPMENT CORPORATION (FORMERLY : RA IGNACIO CONST. CORP.) | 3095 | 2024 | 2024-12-14 | 02/08/2024 | 3132.91 | 0 | 2024-12-13 |  | 1
2023 | National Capital Region | PARAÃ‘AQUE CITY | CITY OF PARAÃ‘AQUE (METROPOLITAN MANILA) | P00737393LZ | Construction of Drainage Structure | 120.9937 | 14.5206 | 5940000 | 5940000 | 2023 | DARCY & ANNA BUILDERS & TRADING | 3096 | 2023 | 2023-07-05 | 02/06/2023 | 0 | 0 | 2023-07-04 |  | 1
2022 | Region III | BULACAN | SAN MIGUEL (BULACAN) | P00639341LZ | Construction of Flood Mitigation Structure | 120.9938 | 15.2271 | 96499438.31 | 96496520.01 | 2023 | L.R. TIQUI BUILDERS, INC. | 3097 | 2022 | 2023-05-26 | 03/30/2022 | 2918.3 | 0 | 2023-06-22 | 27
2024 | National Capital Region | PASAY CITY | PASAY CITY (METROPOLITAN MANILA) | P00820016LZ | Construction of Flood Mitigation Structure | 120.9939 | 14.5461 | 89170822.17 | 89163791.72 | 2024 | AARCON BUILDERS | 3098 | 2024 | 2024-11-15 | 02/20/2024 | 7030.45 | 0 | 2024-11-14 |  | 1
2023 | National Capital Region | PARAÃ‘AQUE CITY | CITY OF PARAÃ‘AQUE (METROPOLITAN MANILA) | P00726819LZ | Construction of Revetment | 120.9941 | 14.5008 | 67550000 | 67549911.44 | 2024 | AARCON BUILDERS | 3099 | 2023 | 2024-11-05 | 09/11/2023 | 88.56 | 0 | 2024-11-04 |  | 1
2022 | National Capital Region | LAS PIÃ‘AS CITY | CITY OF LAS PIÃ‘AS (METROPOLITAN MANILA) | P00637033LZ | Rehabilitation / Major Repair of Drainage Structure | 120.9941 | 14.4182 | 4899999.92 | 4899836.7 | 2022 | FIRST METSTEEL BUILDERS | 3100 | 2022 | 2022-08-12 | 05/27/2022 | 163.22 | 0 | 2022-08-23 | 11
2024 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00820060LZ | Construction of Flood Mitigation Facility | 120.9941 | 14.5811 | 96499885.03 | 96490182.48 | 2024 | EIGHT J'S CONSTRUCTION SERVICES / JIM AND JEM CONSTRUCTION SERVICES | 3101 | 2024 | 2024-09-08 | 03/13/2024 | 9702.55 | 0 | 2024-09-07 |  | 1
2022 | National Capital Region | LAS PIÃ‘AS CITY | CITY OF LAS PIÃ‘AS (METROPOLITAN MANILA) | P00631007LZ | Rehabilitation / Major Repair of Drainage Structure | 120.9941 | 14.4444 | 19599999.97 | 18619999.97 | 2022 | DAVHEZ TRADING & CONSTRUCTION | 3102 | 2022 | 2022-11-22 | 05/27/2022 | 980000 | 0 | 2022-11-21 |  | 1
2022 | National Capital Region | LAS PIÃ‘AS CITY | CITY OF LAS PIÃ‘AS (METROPOLITAN MANILA) | P00620912LZ | Construction of Flood Mitigation Structure | 120.9941 | 14.4523 | 48999978.6 | 48998963.41 | 2022 | ORANI CONSTRUCTION AND SUPPLY CORPORATION (FORMERLY:ORANI BUILDERS & SUPPLY) | 3103 | 2022 | 2022-10-06 | 02/09/2022 | 1015.19 | 0 | 2022-10-05 |  | 1
2025 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00941129LZ | Rehabilitation / Major Repair of Drainage Structure | 120.9942 | 14.6089 | 4949922.56 | 4798989.63 | 2025 | LE BRON CONSTRUCTION | 3104 | 2025 | 2025-04-21 | 02/17/2025 | 150932.93 | 0 | 2025-05-29 | 38
2023 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00740279LZ | Construction of Flood Mitigation Structure | 120.9942 | 14.6132 | 48999612.49 | 47875326.9 | 2024 | SUPREME ABF CONST. & CONST. SUPPLY COMPANY INC. / MANGEN TECHNO-BUILDERS INC. | 3105 | 2023 | 2024-02-20 | 03/28/2023 | 1124285.59 | 0 | 2024-02-19 |  | 1
2022 | National Capital Region | PARAÃ‘AQUE CITY | CITY OF PARAÃ‘AQUE (METROPOLITAN MANILA) | P00620027LZ | Construction of Flood Mitigation Facility | 120.9943 | 14.4775 | 95749230 | 95715093.42 | 2023 | ST. TIMOTHY CONSTRUCTION CORPORATION | 3106 | 2022 | 2023-05-13 | 05/19/2022 | 34136.58 | 0 | 2023-05-12 |  | 1
2024 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00820072LZ | Construction of Retarding Basin | 120.9943 | 14.6137 | 90338911.19 | 88345999.39 | 2024 | SUPREME ABF CONST. & CONST. SUPPLY COMPANY INC. / RJR CALCON CORP. | 3107 | 2024 | 2024-09-10 | 02/08/2024 | 1992911.8 | 0 | 2024-09-27 | 17
2023 | Region III | BULACAN | CITY OF SAN JOSE DEL MONTE (BULACAN) | P00725724LZ | Construction of Flood Mitigation Structure | 121.0371 | 14.8338 | 96499994.92 | 96496572.72 | 2023 | L.R. TIQUI BUILDERS, INC. | 3108 | 2023 | 2023-10-16 | 03/01/2023 | 3422.2 | 0 | 2023-12-28 | 73
2022 | Region IV-A | CAVITE | CITY OF CARMONA (CAVITE) | P00620224LZ | Construction of Revetment | 121.049 | 14.3181 | 86849972.69 | 86833934.73 | 2022 | KLDS TRADING & CONSTRUCTION / OMNICON BUILDERS | 3109 | 2022 | 2022-07-22 | 03/07/2022 | 16037.96 | 0 | 2023-01-14 | 176
2022 | Region III | BULACAN | CITY OF SAN JOSE DEL MONTE (BULACAN) | P00631221LZ | Construction of Flood Mitigation Structure | 121.0372 | 14.8322 | 44099923.15 | 44098986.56 | 2023 | FLORDES CONSTRUCTION & TRADING CORP. (FORMERLY FLO | 3110 | 2022 | 2023-03-19 | 03/31/2022 | 936.59 | 0 | 2023-03-18 |  | 1
2023 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00726775LZ | Construction of Flood Mitigation Structure | 120.971 | 14.6153 | 96499915.79 | 94814590.39 | 2024 | G.F. FABIAN CONSTRUCTION | 3111 | 2023 | 2024-11-15 | 03/14/2023 | 1685325.4 | 0 | 2024-12-04 | 19
2024 | National Capital Region | CALOOCAN CITY | CALOOCAN CITY (METROPOLITAN MANILA) | P00844681LZ | Construction of Drainage Structure | 121.0148 | 14.7349 | 9796941.19 | 9625479.55 | 2024 | SAN IGMEDIO BUILDERS INCORPORATED | 3112 | 2024 | 2024-05-24 | 03/26/2024 | 171461.64 | 0 | 2024-08-21 | 89
2022 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00620059LZ | Construction of Flood Mitigation Structure | 120.9946 | 14.6155 | 96499979.57 | 96494451.74 | 2023 | ST. TIMOTHY CONSTRUCTION CORPORATION | 3113 | 2022 | 2023-02-10 | 04/01/2022 | 5527.83 | 0 | 2023-02-23 | 13
2023 | Region IV-A | CAVITE | BACOOR CITY (CAVITE) | P00742183LZ | Construction of Flood Mitigation Structure | 120.9773 | 14.4187 | 98999935.41 | 98973782.96 | 2024 | GRAIA CONSTRUCTION CORPORATION | 3114 | 2023 | 2024-02-16 | 05/01/2023 | 26152.45 | 0 | 2024-03-24 | 37
2023 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00726777LZ | Construction of Flood Mitigation Facility | 120.9711 | 14.6143 | 72374420.52 | 71687670.79 | 2023 | JELSIE CONSTRUCTION & SUPPLY | 3115 | 2023 | 2023-06-23 | 03/10/2023 | 686749.73 | 0 | 2023-07-21 | 28
2021 | National Capital Region | PARAÃ‘AQUE CITY |  | P00525761LZ | Rehabilitation / Major Repair of Drainage Structure | 121.0046 | 14.4706 | 19600000 | 19593918.94 | 2022 | A.C. RIVERO DEVELOPMENT CORPORATION | 3116 | 2021 | 2022-10-01 | 02/22/2022 | 6081.06 | 0 | 2022-09-30 |  | 1
2023 | National Capital Region | QUEZON CITY | QUEZON CITY (METROPOLITAN MANILA) | P00726012LZ | Construction of Flood Mitigation Structure | 121.0149 | 14.6325 | 19599970.3 | 19000000 | 2023 | M.E. SICAT CONSTRUCTION, INC. (FORMERLY M.E. SICAT | 3117 | 2023 | 2023-07-17 | 02/13/2023 | 599970.3 | 0 | 2023-07-11 |  | 6
2022 | National Capital Region | VALENZUELA CITY | CITY OF VALENZUELA (METROPOLITAN MANILA) | P00637046LZ | Construction of Flood Mitigation Structure | 120.9773 | 14.7132 | 9794679.28 | 9540007.71 | 2022 | TOUGHBUILT CONSTRUCTION & TRADING, INC. | 3118 | 2022 | 2022-11-17 | 03/24/2022 | 254671.57 | 0 | 2022-11-17 | 0
2023 | Region IV-A | LAGUNA | CITY OF BIÃ‘AN (LAGUNA) | P00725825LZ | Construction of Flood Mitigation Structure | 121.0372 | 14.2565 | 96500000 | 96447141.02 | 2024 | M.T. MALIUANAG CONSTRUCTION SERVICES | 3119 | 2023 | 2024-03-15 | 08/09/2023 | 52858.98 | 0 | 2024-06-20 | 97
2024 | Region III | BULACAN | NORZAGARAY (BULACAN) | P00821578LZ | Construction of Flood Mitigation Structure | 121.049 | 14.9048 | 48999499.15 | 48999846.44 | 2024 | ROYAL CROWN MONARCH CONSTRUCTION & SUPPLIES CORP. | 3120 | 2024 | 2024-10-01 | 03/21/2024 | 0 | 347.29 | 2024-10-19 | 18
2023 | Region III | BULACAN | CITY OF MEYCAUAYAN (BULACAN) | P00726725LZ | Construction of Flood Mitigation Structure | 120.9565 | 14.7234 | 48998969.45 | 48996528.42 | 2023 | JB CONSTRUCTION AND SUPPLY INC. (FORMERLY:JB CONSTRUCTION AND SUPPLY) | 3121 | 2023 | 2023-07-11 | 02/22/2023 | 2441.03 | 0 | 2023-08-11 | 31
2024 | National Capital Region | PASAY CITY | PASAY CITY (METROPOLITAN MANILA) | P00820017LZ | Construction of Flood Mitigation Structure | 120.9949 | 14.5465 | 89171676.23 | 89077443.18 | 2024 | JELSIE CONSTRUCTION & SUPPLY | 3122 | 2024 | 2024-10-14 | 02/20/2024 | 94233.05 | 0 | 2024-11-12 | 29
2024 | Region III | NUEVA ECIJA | CABANATUAN CITY (NUEVA ECIJA) | P00845999LZ | Construction of Drainage Structure | 120.9565 | 15.4803 | 4949906.87 | 4873904.4 | 2024 | CELSO C. FERRER CONSTRUCTION CORP. | 3123 | 2024 | 2024-07-26 | 03/20/2024 | 76002.47 | 0 | 2024-07-27 | 1
2021 | National Capital Region | CITY OF MANILA |  | P00525817LZ | Construction of Flood Mitigation Structure | 120.9774 | 14.6356 | 19599263.46 | 19567913.35 | 2022 | 1HB CONSTRUCTION CORP. (FORMERLY: HB CONSTRUCTION) | 3124 | 2021 | 2022-10-21 | 03/29/2022 | 31350.11 | 0 | 2022-09-23 |  | 28
2024 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00820011LZ | Construction of Drainage Structure | 121.015 | 14.5958 | 85550000.31 | 85548671.84 | 2025 | GREAT PACIFIC BUILDERS AND GEN. CONTRACTOR INC. / EVERCORE CONSTRUCTION AND DEVELOPMENT CORP. | 3125 | 2024 | 2025-02-14 | 02/13/2024 | 1328.47 | 0 | 2025-02-13 |  | 1
2021 | National Capital Region | PARAÃ‘AQUE CITY |  | P00525756LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.0373 | 14.4704 | 29400000 | 29397313.67 | 2022 | RNN CONSTRUCTION CORPORATION (FORMERLY RNN CONSTRU | 3126 | 2021 | 2022-10-07 | 03/22/2022 | 2686.33 | 0 | 2022-10-06 |  | 1
2022 | National Capital Region | MAKATI CITY | CITY OF MAKATI (METROPOLITAN MANILA) | P00620389LZ | Rehabilitation / Major Repair of Drainage Structure | 121.0491 | 14.5627 | 17640000 | 17640000 | 2022 | THE STEADFAST BUILDERS | 3127 | 2022 | 2022-07-03 | 02/04/2022 | 0 | 0 | 2022-07-02 |  | 1
2024 | National Capital Region | QUEZON CITY | QUEZON CITY (METROPOLITAN MANILA) | P00824616LZ | Construction of Drainage Structure | 121.0373 | 14.6849 | 19599657.88 | 19598545.53 | 2024 | C.E.M. CONSTRUCTION, INC. | 3128 | 2024 | 2024-06-25 | 02/23/2024 | 1112.35 | 0 | 2024-09-18 | 85
2023 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00726778LZ | Construction of Flood Mitigation Facility | 120.9711 | 14.6143 | 72374399.73 | 70540676.21 | 2023 | JELSIE CONSTRUCTION & SUPPLY | 3129 | 2023 | 2023-08-22 | 03/10/2023 | 1833723.52 | 0 | 2023-08-30 | 8
2022 | Region IV-A | CAVITE | CITY OF DASMARIÃ‘AS (CAVITE) | P00620895LZ | Construction of Slope Protection Structure | 120.9565 | 14.3285 | 94569938.4 | 94569855.64 | 2023 | KLDS TRADING & CONSTRUCTION | 3130 | 2022 | 2023-11-20 | 03/02/2022 | 82.76 | 0 | 2023-11-29 | 9
2024 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00820620LZ | Construction of Drainage Structure | 120.9775 | 14.6313 | 48999335.68 | 48968908.87 | 2025 | AL-AMEN BUILDERS | 3131 | 2024 | 2025-01-18 | 02/07/2024 | 30426.81 | 0 | 2025-01-17 |  | 1
2023 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00726035LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.0047 | 14.582 | 39194521.41 | 38253120.32 | 2023 | ALPHA & OMEGA GEN. CONTRACTOR & DEVELOPMENT CORP. / K84 CONSTRUCTION AND DEVELOPMENT CORPORATION | 3132 | 2023 | 2023-10-24 | 02/27/2023 | 941401.09 | 0 | 2023-10-23 |  | 1
2022 | Region II | NUEVA VIZCAYA | ARITAO (NUEVA VIZCAYA) | P00640511LZ | Construction of Flood Mitigation Structure | 121.0153 | 16.2503 | 34300000 | 34138606.28 | 2022 | AMP 723 CONSTRUCTION CORPORATION (FORMERLY: A.M.P. CONSTRUCTION) | 3133 | 2022 | 2022-11-29 | 03/24/2022 | 161393.72 | 0 | 2022-11-28 |  | 1
2021 | Region IV-A | CAVITE |  | P00526324LZ | Construction of Revetment | 120.9566 | 14.3252 | 53644300.67 | 53637052.73 | 2022 | R2A CONSTRUCTION & TRADING CORPORATION | 3134 | 2021 | 2022-09-20 | 04/22/2021 | 7247.94 | 0 | 2022-10-01 | 11
2023 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00726781LZ | Construction of Flood Mitigation Facility | 120.9711 | 14.6143 | 72374776.28 | 72357606.57 | 2023 | JELSIE CONSTRUCTION & SUPPLY | 3135 | 2023 | 2023-06-23 | 03/10/2023 | 17169.71 | 0 | 2023-07-21 | 28
2024 | National Capital Region | VALENZUELA CITY | CITY OF VALENZUELA (METROPOLITAN MANILA) | P00820595LZ | Construction of Flood Mitigation Structure | 120.9952 | 14.6793 | 14695018.31 | 14401100.63 | 2024 | RWORKMATE CONSTRUCTION | 3136 | 2024 | 2024-09-09 | 02/14/2024 | 293917.68 | 0 | 2024-09-09 | 0
2022 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00620032LZ | Construction of Flood Mitigation Structure | 121.0048 | 14.5986 | 67549240.33 | 64579690.5 | 2023 | TRIPLE 8 CONSTRUCTION & SUPPLY, INC. (FORMERLY TRIPLE 8 CONST. & SUPPLY) | 3137 | 2022 | 2023-06-11 | 02/23/2022 | 2969549.83 | 0 | 2023-06-10 |  | 1
2024 | National Capital Region | QUEZON CITY | QUEZON CITY (METROPOLITAN MANILA) | P00823258LZ | Construction of Flood Mitigation Structure | 121.0153 | 14.6566 | 77199937.29 | 77199937.29 | 2024 | A.J. LAVA BUILDERS CORP. (FORMERLY: A.J. LAVA BUIL | 3138 | 2024 | 2024-12-11 | 03/18/2024 | 0 | 0 | 2025-03-11 | 90
2024 | Region III | BULACAN | ANGAT (BULACAN) | P00821580LZ | Construction of Flood Mitigation Structure | 121.0494 | 14.9197 | 48249925.33 | 48249967.72 | 2024 | ALPHA & OMEGA GEN. CONTRACTOR & DEVELOPMENT CORP. | 3139 | 2024 | 2024-11-07 | 04/08/2024 | 0 | 42.39 | 2024-11-06 |  | 1
2022 | National Capital Region | SAN JUAN CITY | CITY OF SAN JUAN (METROPOLITAN MANILA) | P00621406LZ | Construction of Slope Protection Structure | 121.0374 | 14.6065 | 19599999.95 | 18619991.16 | 2023 | WAWAO BUILDERS | 3140 | 2022 | 2023-01-08 | 03/24/2022 | 980008.79 | 0 | 2022-10-18 |  | 82
2022 | Region IV-A | CAVITE | BACOOR CITY (CAVITE) | P00639377LZ | Construction of Slope Protection Structure | 120.9776 | 14.4271 | 96500000 | 96499256.16 | 2023 | E. F. CHUA CONSTRUCTION, INC. | 3141 | 2022 | 2023-12-15 | 06/14/2022 | 743.84 | 0 | 2023-12-14 |  | 1
2023 | Region IV-A | LAGUNA | CITY OF SAN PEDRO (LAGUNA) | P00725818LZ | Construction of Flood Mitigation Structure | 121.0376 | 14.3429 | 77200000 | 77199993.66 | 2024 | MAR-VEL CONSTRUCTION & SUPPLY | 3142 | 2023 | 2024-03-20 | 03/17/2023 | 6.34 | 0 | 2024-03-19 |  | 1
2022 | National Capital Region | MAKATI CITY | CITY OF MAKATI (METROPOLITAN MANILA) | P00620373LZ | Rehabilitation / Major Repair of Drainage Structure | 121.0496 | 14.5624 | 19600000 | 19600000 | 2022 | THE STEADFAST BUILDERS | 3143 | 2022 | 2022-07-03 | 02/04/2022 | 0 | 0 | 2022-07-02 |  | 1
2023 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00726782LZ | Construction of Flood Mitigation Facility | 120.9711 | 14.6143 | 72374816.16 | 71406713.83 | 2023 | JELSIE CONSTRUCTION & SUPPLY | 3144 | 2023 | 2023-08-22 | 03/10/2023 | 968102.33 | 0 | 2023-08-30 | 8
2022 | National Capital Region | QUEZON CITY | QUEZON CITY (METROPOLITAN MANILA) | P00637761LZ | Rehabilitation / Major Repair of Drainage Structure | 121.0498 | 14.6184 | 7918304.49 | 7902183.52 | 2022 | DIADEMA CONSTRUCTION AND ENTERPRISES INC. (FORMERLY: DIADEMA ENTERPRISES) | 3145 | 2022 | 2022-12-06 | 05/18/2022 | 16120.97 | 0 | 2022-12-21 | 15
2024 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00845872LZ | Construction of Drainage Structure | 120.9777 | 14.6329 | 49499898.64 | 49499821.11 | 2024 | EL-JAKE BUILDERS / MANGEN TECHNO-BUILDERS INC. | 3146 | 2024 | 2024-11-11 | 02/12/2024 | 77.53 | 0 | 2024-11-13 | 2
2021 | National Capital Region | SAN JUAN CITY |  | P00525720LZ | Construction of Flood Mitigation Structure | 121.0377 | 14.6061 | 48999981.62 | 46495969.51 | 2023 | JAGONBUILD CONSTRUCTION CORP. (FOR. JAGON BUILDERS | 3147 | 2021 | 2023-02-13 | 02/24/2022 | 2504012.11 | 0 | 2023-01-29 |  | 15
2022 | National Capital Region | MALABON CITY | CITY OF MALABON (METROPOLITAN MANILA) | P00631019LZ | Construction of Drainage Structure | 120.9566 | 14.6604 | 48999950.85 | 49000000 | 2024 | JAGONBUILD CONSTRUCTION CORP. (FOR. JAGON BUILDERS | 3148 | 2022 | 2024-04-11 | 02/15/2022 | 0 | 49.15 | 2024-09-07 | 149
2021 | National Capital Region | PARAÃ‘AQUE CITY |  | P00525754LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.0154 | 14.4957 | 19600000 | 19594378.86 | 2022 | RNN CONSTRUCTION CORPORATION (FORMERLY RNN CONSTRU | 3149 | 2021 | 2022-09-22 | 03/22/2022 | 5621.14 | 0 | 2022-09-21 |  | 1
2024 | Region III | NUEVA ECIJA | SAN JOSE CITY (NUEVA ECIJA) | P00823444LZ | Construction of Flood Mitigation Structure | 121.0048 | 15.7732 | 48250000 | 47767490.75 | 2024 | WIZARD CONCRETE SOLUTIONS AND CONSTRUCTION CORPORATION (FORMERLY: WIZARD TRADING & CONSTRUCTION) | 3150 | 2024 | 2024-08-01 | 03/13/2024 | 482509.25 | 0 | 2024-10-07 | 67
2022 | National Capital Region | MAKATI CITY | CITY OF MAKATI (METROPOLITAN MANILA) | P00620038LZ | Construction of Revetment | 121.0159 | 14.531 | 87455055 | 85780689.36 | 2022 | E. F. CHUA CONSTRUCTION, INC. | 3151 | 2022 | 2022-11-13 | 02/17/2022 | 1674365.64 | 0 | 2022-11-12 |  | 1
2024 | National Capital Region | VALENZUELA CITY | CITY OF VALENZUELA (METROPOLITAN MANILA) | P00820583LZ | Construction of Drainage Structure | 120.9954 | 14.6933 | 9796791.68 | 9454950.64 | 2024 | SONPRO CONSTRUCTION | 3152 | 2024 | 2024-08-10 | 02/14/2024 | 341841.04 | 0 | 2024-08-10 | 0
2019 | National Capital Region | PARAÃ‘AQUE CITY |  | P00320509LZ | Rehabilitation / Major Repair of Drainage Structure | 121.0377 | 14.4737 | 14700000 | 13106844.5 | 2022 | RIMJ CONSTRUCTION SUPPLIES AND SERVICES (FOR: ROMINA CONSTRUCTION) | 3153 | 2019 | 2022-11-14 | 10/10/2019 | 1593155.5 | 0 | 2022-11-19 | 5
2023 | National Capital Region | PASAY CITY | PASAY CITY (METROPOLITAN MANILA) | P00725512LZ | Construction of Flood Mitigation Structure | 121.0049 | 14.528 | 53074994.96 | 53069305.41 | 2024 | ST. MATTHEW GEN. CONTRACTOR & DEVELOPMENT CORP. / AL-ALAWI CONSTRUCTION | 3154 | 2023 | 2024-02-22 | 02/22/2023 | 5689.55 | 0 | 2024-02-27 | 5
2022 | National Capital Region | NAVOTAS CITY | CITY OF NAVOTAS (METROPOLITAN MANILA) | P00631024LZ | Construction of Flood Mitigation Facility | 120.9571 | 14.6357 | 19599959.06 | 19597223.14 | 2022 | CATTECORYLL CONSTRUCTION & TRADING CORP | 3155 | 2022 | 2022-09-23 | 02/14/2022 | 2735.92 | 0 | 2022-11-09 | 47
2022 | National Capital Region | VALENZUELA CITY | CITY OF VALENZUELA (METROPOLITAN MANILA) | P00620408LZ | Construction of Flood Mitigation Structure | 120.9954 | 14.6959 | 24490415.28 | 23682211.61 | 2022 | TM ABAD CONSTRUCTION CORP. (FOR: TM ABAD CONST.) | 3156 | 2022 | 2022-09-12 | 02/08/2022 | 808203.67 | 0 | 2022-12-03 | 82
2023 | National Capital Region | CALOOCAN CITY | CALOOCAN CITY (METROPOLITAN MANILA) | P00727017LZ | Construction of Drainage Structure | 120.9777 | 14.6382 | 29397260.86 | 28732995.01 | 2023 | MIGHTY CONSTRUCTION & DEVELOPMENT INC. | 3157 | 2023 | 2023-12-27 | 06/19/2023 | 664265.85 | 0 | 2024-02-12 | 47
2024 | National Capital Region | QUEZON CITY | QUEZON CITY (METROPOLITAN MANILA) | P00824620LZ | Construction of Drainage Structure | 121.0378 | 14.6849 | 39199674.26 | 38768477.84 | 2024 | C.E.M. CONSTRUCTION, INC. | 3158 | 2024 | 2024-10-07 | 02/27/2024 | 431196.42 | 0 | 2024-11-21 | 45
2023 | National Capital Region | PARAÃ‘AQUE CITY | CITY OF PARAÃ‘AQUE (METROPOLITAN MANILA) | P00725533LZ | Construction of Flood Mitigation Facility | 121.0159 | 14.4718 | 82025000 | 82023005.37 | 2024 | R.D. TALENS CONSTRUCTION AND TRADING | 3159 | 2023 | 2024-07-04 | 02/22/2023 | 1994.63 | 0 | 2024-07-03 |  | 1
2024 | Region III | BULACAN | SANTA MARIA (BULACAN) | P00838344LZ | Construction of Flood Mitigation Structure | 120.9955 | 14.8791 | 97999967.93 | 96499408.89 | 2024 | L.R. TIQUI BUILDERS, INC. | 3160 | 2024 | 2024-12-04 | 02/14/2024 | 1500559.04 | 0 | 2024-12-03 |  | 1
2022 | Region III | BULACAN | CITY OF MEYCAUAYAN (BULACAN) | P00620160LZ | Construction of Flood Mitigation Structure | 120.9576 | 14.7448 | 95534332.28 | 95512137.72 | 2022 | AZUL BUILDERS | 3161 | 2022 | 2022-09-05 | 03/07/2022 | 22194.56 | 0 | 2022-09-04 |  | 1
2024 | National Capital Region | CALOOCAN CITY | CALOOCAN CITY (METROPOLITAN MANILA) | P00839525LZ | Rehabilitation / Major Repair of Drainage Structure | 121.0051 | 14.6734 | 4949914.68 | 4875644.24 | 2024 | AVE-MIRA CONSTRUCTION AND TRADING | 3162 | 2024 | 2024-09-09 | 02/14/2024 | 74270.44 | 0 | 2024-05-12 |  | 120
2023 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00740281LZ | Construction of Flood Mitigation Structure | 120.9712 | 14.6088 | 96499854.46 | 96445697.36 | 2024 | G.F. FABIAN CONSTRUCTION | 3163 | 2023 | 2024-11-15 | 03/28/2023 | 54157.1 | 0 | 2024-11-27 | 12
2022 | National Capital Region | LAS PIÃ‘AS CITY | CITY OF LAS PIÃ‘AS (METROPOLITAN MANILA) | P00637036LZ | Rehabilitation / Major Repair of Drainage Structure | 120.9712 | 14.4581 | 14699920.46 | 14694920.46 | 2022 | KPSL GENERAL CONTRACTOR INC. | 3164 | 2022 | 2022-11-22 | 05/27/2022 | 5000 | 0 | 2022-11-21 |  | 1
2023 | Region II | NUEVA VIZCAYA | BAMBANG (NUEVA VIZCAYA) | P00727118LZ | Construction of Flood Mitigation Structure | 121.0499 | 16.3626 | 49000000 | 48987038.54 | 2023 | E.T. LATAWAN CONSTRUCTION | 3165 | 2023 | 2023-10-26 | 03/13/2023 | 12961.46 | 0 | 2023-10-27 | 1
2023 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00740511LZ | Rehabilitation / Major Repair of Drainage Structure | 120.9955 | 14.5709 | 48997520.46 | 48361055.97 | 2024 | AMETHYST HORIZON BUILDERS AND GEN. CONTRACTOR AND DEVELOPMENT CORP. | 3166 | 2023 | 2024-06-30 | 05/17/2023 | 636464.49 | 0 | 2024-06-29 |  | 1
2023 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00726776LZ | Construction of Flood Mitigation Facility | 120.9712 | 14.6121 | 96499593.63 | 96495792.9 | 2023 | EIGHT J'S CONSTRUCTION SERVICES | 3167 | 2023 | 2023-06-23 | 03/10/2023 | 3800.73 | 0 | 2023-08-15 | 53
2022 | National Capital Region | MUNTINLUPA CITY | CITY OF MUNTINLUPA (METROPOLITAN MANILA) | P00637754LZ | Construction of Flood Mitigation Structure | 121.0499 | 14.4459 | 49499224.52 | 49174889.46 | 2022 | AKN CONSTRUCTION CORPORATION | 3168 | 2022 | 2022-11-22 | 05/27/2022 | 324335.06 | 0 | 2022-11-21 |  | 1
2022 | National Capital Region | PARAÃ‘AQUE CITY | CITY OF PARAÃ‘AQUE (METROPOLITAN MANILA) | P00631028LZ | Construction of Flood Mitigation Structure | 121.0051 | 14.4764 | 9800000 | 9800000 | 2022 | M.P.Z. CARREON BUILDERS | 3169 | 2022 | 2022-10-25 | 02/09/2022 | 0 | 0 | 2022-10-28 | 3
2024 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00839528LZ | Construction of Drainage Structure | 120.9778 | 14.625 | 4899661.89 | 4898821.31 | 2024 | S.R. LUMANTA CONSTRUCTION & SUPPLY | 3170 | 2024 | 2024-07-09 | 02/07/2024 | 840.58 | 0 | 2024-07-11 | 2
2023 | National Capital Region | QUEZON CITY | QUEZON CITY (METROPOLITAN MANILA) | P00726030LZ | Rehabilitation / Major Repair of Drainage Structure | 121.016 | 14.6194 | 42531684.57 | 42208516.89 | 2023 | FRONT NINE KONSTRUCT (BUILDERS & REALTY DEVELOPMENT) CORPORATION | 3171 | 2023 | 2023-10-30 | 02/17/2023 | 323167.68 | 0 | 2023-10-29 |  | 1
2022 | Region III | BULACAN | SAN RAFAEL (BULACAN) | P00620150LZ | Construction of Flood Mitigation Structure | 120.9576 | 15.033 | 57899710.8 | 54875263.09 | 2022 | EIRISH BUILDERS & SUPPLY INC. | 3172 | 2022 | 2022-10-09 | 03/07/2022 | 3024447.71 | 0 | 2022-10-08 |  | 1
2021 | National Capital Region | PARAÃ‘AQUE CITY |  | P00525755LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.0379 | 14.4706 | 17626280 | 17626280 | 2022 | RNN CONSTRUCTION CORPORATION (FORMERLY RNN CONSTRU | 3173 | 2021 | 2022-09-27 | 03/22/2022 | 0 | 0 | 2022-09-26 |  | 1
2023 | Region II | NUEVA VIZCAYA | KAYAPA (NUEVA VIZCAYA) | P00742309LZ | Construction of Flood Mitigation Structure | 120.978 | 16.3347 | 98084800 | 98041656.51 | 2023 | AMP 723 CONSTRUCTION CORPORATION (FORMERLY: A.M.P. CONSTRUCTION) / KEVIN PAUL CONSTRUCTION | 3174 | 2023 | 2023-11-24 | 03/23/2023 | 43143.49 | 0 | 2023-11-23 |  | 1
2024 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00820654LZ | Construction of Flood Mitigation Structure | 121.0051 | 14.5922 | 29399758.52 | 29399712.44 | 2024 | N.M.E. CONSTRUCTION | 3175 | 2024 | 2024-12-10 | 02/21/2024 | 46.08 | 0 | 2025-01-15 | 36
2023 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00726779LZ | Construction of Flood Mitigation Facility | 120.9712 | 14.6121 | 96499653.7 | 95763985.11 | 2023 | EIGHT J'S CONSTRUCTION SERVICES / JJPR CONSTRUCTION SERVICES | 3176 | 2023 | 2023-06-23 | 03/10/2023 | 735668.59 | 0 | 2023-07-16 | 23
2022 | Region IV-A | CAVITE | CITY OF CARMONA (CAVITE) | P00632880LZ | Construction of Drainage Structure | 121.05 | 14.3099 | 39599727.15 | 9899912.64 | 2022 | TRIPLE 8 CONSTRUCTION & SUPPLY, INC. (FORMERLY TRIPLE 8 CONST. & SUPPLY) | 3177 | 2022 | 2022-08-15 | 02/17/2022 | 29699814.51 | 0 | 2022-08-14 |  | 1
2023 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00726000LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.9956 | 14.6094 | 7839917.67 | 7837953.97 | 2023 | JJPR CONSTRUCTION SERVICES | 3178 | 2023 | 2023-06-16 | 02/17/2023 | 1963.7 | 0 | 2023-06-15 |  | 1
2022 | National Capital Region | LAS PIÃ‘AS CITY | CITY OF LAS PIÃ‘AS (METROPOLITAN MANILA) | P00620907LZ | Construction of Flood Mitigation Structure | 121.0163 | 14.4347 | 48999302.16 | 48993812.8 | 2022 | MRRM TRADING & CONSTRUCTION | 3179 | 2022 | 2022-08-07 | 02/09/2022 | 5489.36 | 0 | 2022-08-06 |  | 1
2023 | National Capital Region | QUEZON CITY | QUEZON CITY (METROPOLITAN MANILA) | P00736170LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.0502 | 14.7257 | 48999920 | 48993565.33 | 2023 | LE BRON CONSTRUCTION | 3180 | 2023 | 2023-12-18 | 03/21/2023 | 6354.67 | 0 | 2024-01-13 | 26
2023 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00726780LZ | Construction of Flood Mitigation Facility | 120.9712 | 14.6121 | 96499482.7 | 94327118.63 | 2023 | EIGHT J'S CONSTRUCTION SERVICES | 3181 | 2023 | 2023-07-25 | 03/10/2023 | 2172364.07 | 0 | 2023-07-31 | 6
2024 | National Capital Region | QUEZON CITY | QUEZON CITY (METROPOLITAN MANILA) | P00824625LZ | Construction of Drainage Structure | 121.0053 | 14.6638 | 19599812.6 | 19395974.55 | 2024 | ROSAND BUILDERS CORPORATION (FORMERLY: ROSAND BUILDERS) | 3182 | 2024 | 2024-11-18 | 04/29/2024 | 203838.05 | 0 | 2024-11-23 | 5
2022 | Region IV-A | CAVITE | SILANG (CAVITE) | P00620879LZ | Construction of Revetment | 120.9782 | 14.2329 | 82922448.2 | 82906844.73 | 2023 | NEWBIG FOUR J CONSTRUCTION INC., (FORMERLY FOUR J | 3183 | 2022 | 2023-01-15 | 03/27/2022 | 15603.47 | 0 | 2023-01-14 |  | 1
2022 | Region IV-A | CAVITE | CITY OF CARMONA (CAVITE) | P00620581LZ | Construction of Revetment | 121.038 | 14.292 | 48999988.19 | 48999129.12 | 2022 | KLDS TRADING & CONSTRUCTION / OMNICON BUILDERS | 3184 | 2022 | 2022-08-07 | 02/09/2022 | 859.07 | 0 | 2022-10-20 | 74
2022 | Region III | BULACAN | CITY OF MEYCAUAYAN (BULACAN) | P00620522LZ | Construction of Flood Mitigation Facility | 120.9577 | 14.7373 | 19607596.69 | 19599471.16 | 2022 | JB CONSTRUCTION AND SUPPLY INC. (FORMERLY:JB CONSTRUCTION AND SUPPLY) | 3185 | 2022 | 2022-08-01 | 02/28/2022 | 8125.53 | 0 | 2022-07-31 |  | 1
2024 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00823236LZ | Construction of Retarding Basin | 120.9714 | 14.6108 | 96499413.2 | 96498773.68 | 2025 | ALPHA & OMEGA GEN. CONTRACTOR & DEVELOPMENT CORP. | 3186 | 2024 | 2025-01-24 | 02/07/2024 | 639.52 | 0 | 2025-01-23 |  | 1
2023 | National Capital Region | PASAY CITY | PASAY CITY (METROPOLITAN MANILA) | P00726036LZ | Rehabilitation / Major Repair of Drainage Structure | 121.0053 | 14.5328 | 24499688.96 | 24070866.51 | 2023 | K84 CONSTRUCTION AND DEVELOPMENT CORPORATION | 3187 | 2023 | 2023-06-06 | 02/23/2023 | 428822.45 | 0 | 2023-07-21 | 45
2022 | National Capital Region | MUNTINLUPA CITY | CITY OF MUNTINLUPA (METROPOLITAN MANILA) | P00640483LZ | Construction of Flood Mitigation Structure | 121.038 | 14.4007 | 48999356.64 | 48994199.14 | 2023 | AARCON BUILDERS | 3188 | 2022 | 2023-01-01 | 04/07/2022 | 5157.5 | 0 | 2022-12-31 |  | 1
2023 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00726798LZ | Construction of Flood Mitigation Structure | 120.9958 | 14.599 | 77199513.96 | 74700405.94 | 2024 | GREAT PACIFIC BUILDERS AND GEN. CONTRACTOR INC. | 3189 | 2023 | 2024-03-31 | 03/09/2023 | 2499108.02 | 0 | 2024-03-30 |  | 1
2023 | Region III | BULACAN | NORZAGARAY (BULACAN) | P00726519LZ | Construction of Flood Mitigation Structure | 121.0503 | 14.9084 | 57899387.58 | 57899987.23 | 2023 | STO. CRISTO CONSTRUCTION & TRADING INC. (FOR: STO. CRISTO CONSTRUCTION & TRADING) | 3190 | 2023 | 2023-10-12 | 02/22/2023 | 0 | 599.65 | 2023-10-11 |  | 1
2024 | National Capital Region | NAVOTAS CITY | CITY OF NAVOTAS (METROPOLITAN MANILA) | P00839517LZ | Construction of Flood Mitigation Facility | 120.9578 | 14.6459 | 9843801.48 | 9899803.02 | 2024 | EARTHWORK BUILDERS, INC. (FORMERLY: EARTHWORK MOVERS) | 3191 | 2024 | 2024-10-08 | 02/21/2024 | 0 | 56001.54 | 2024-10-09 | 1
2022 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00620115LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.9784 | 14.6341 | 53074424.77 | 50683750.77 | 2022 | V.R. GUEVARRA CONSTRUCTION AND TRADING / NEWBIG FOUR J CONSTRUCTION INC., (FORMERLY FOUR J | 3192 | 2022 | 2022-10-19 | 04/01/2022 | 2390674 | 0 | 2022-10-18 |  | 1
2018 | Region IV-B | OCCIDENTAL MINDORO |  | P00223373LZ | Construction of Flood Mitigation Structure | 121.0164 | 12.6322 | 49000000 | 47088811.23 | 2022 | FFJJ CONSTRUCTION | 3193 | 2018 | 2022-11-27 | 04/20/2018 | 1911188.77 | 0 | 2018-11-09 |  | 1479
2024 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00820022LZ | Construction of Revetment | 120.9785 | 14.6342 | 115799352.5 | 113128305.9 | 2024 | DMLC BUILDERS | 3194 | 2024 | 2024-08-13 | 02/14/2024 | 2671046.6 | 0 | 2025-01-16 | 156
2023 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00726801LZ | Construction of Flood Mitigation Facility | 120.9714 | 14.6022 | 72374153.2 | 71910972.99 | 2023 | JELSIE CONSTRUCTION & SUPPLY | 3195 | 2023 | 2023-07-22 | 03/10/2023 | 463180.21 | 0 | 2023-07-21 |  | 1
2022 | National Capital Region | PARAÃ‘AQUE CITY | CITY OF PARAÃ‘AQUE (METROPOLITAN MANILA) | P00631029LZ | Construction of Flood Mitigation Structure | 121.0053 | 14.4763 | 14700000 | 14696791.82 | 2023 | EL KAPITAN CONSTRUCTION SERVICES | 3196 | 2022 | 2023-01-17 | 03/24/2022 | 3208.18 | 0 | 2023-01-16 |  | 1
2021 | National Capital Region | CALOOCAN CITY |  | P00525792LZ | Construction of Flood Mitigation Structure | 121.0381 | 14.7559 | 48977866.71 | 47802379.15 | 2022 | PERSAN CONSTRUCTION, INC. (FORMERLY: PERSAN CONST. | 3197 | 2021 | 2022-12-05 | 03/24/2022 | 1175487.56 | 0 | 2023-02-15 | 72
2024 | Region III | NUEVA ECIJA | CABANATUAN CITY (NUEVA ECIJA) | P00839584LZ | Construction of Drainage Structure | 120.9786 | 15.4856 | 9899964 | 9792146.27 | 2024 | CELSO C. FERRER CONSTRUCTION CORP. | 3198 | 2024 | 2024-11-14 | 05/14/2024 | 107817.73 | 0 | 2024-11-13 |  | 1
2023 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00740286LZ | Construction of Flood Mitigation Facility | 120.9714 | 14.6022 | 72374299.68 | 70385575.94 | 2023 | EIGHT J'S CONSTRUCTION SERVICES | 3199 | 2023 | 2023-07-25 | 03/28/2023 | 1988723.74 | 0 | 2023-08-08 | 14
2023 | National Capital Region | PARAÃ‘AQUE CITY | CITY OF PARAÃ‘AQUE (METROPOLITAN MANILA) | P00737395LZ | Construction of Drainage Structure | 121.0165 | 14.4761 | 5049000 | 5047645.32 | 2023 | G.F. ROVERO MERCHANDISING | 3200 | 2023 | 2023-05-09 | 02/09/2023 | 1354.68 | 0 | 2023-06-07 | 29
2023 | National Capital Region | QUEZON CITY | QUEZON CITY (METROPOLITAN MANILA) | P00736174LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.0382 | 14.7028 | 48999900 | 48990596 | 2023 | MSV CONSTRUCTION AND SUPPLIES | 3201 | 2023 | 2023-08-11 | 02/14/2023 | 9304 | 0 | 2024-01-08 | 150
2022 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00620112LZ | Rehabilitation / Major Repair of Drainage Structure | 120.9787 | 14.6056 | 55680494.59 | 55672291.67 | 2023 | LE BRON CONSTRUCTION | 3202 | 2022 | 2023-03-06 | 02/18/2022 | 8202.92 | 0 | 2023-03-05 |  | 1
2022 | National Capital Region | VALENZUELA CITY | CITY OF VALENZUELA (METROPOLITAN MANILA) | P00621407LZ | Construction of Flood Mitigation Structure | 121.0054 | 14.7085 | 19593693.52 | 19025387.56 | 2022 | SONPRO CONSTRUCTION | 3203 | 2022 | 2022-11-17 | 03/24/2022 | 568305.96 | 0 | 2022-11-17 | 0
2022 | Region III | BULACAN | CITY OF SAN JOSE DEL MONTE (BULACAN) | P00620186LZ | Construction of Slope Protection Structure | 121.0383 | 14.8339 | 94086938.04 | 92676125.88 | 2022 | ALPHA & OMEGA GEN. CONTRACTOR & DEVELOPMENT CORP. / ELITE GENERAL CONTRACTOR AND DEVELOPMENT CORP. | 3204 | 2022 | 2022-12-12 | 03/07/2022 | 1410812.16 | 0 | 2022-12-10 |  | 2
2022 | Cordillera Administrative Region | MOUNTAIN PROVINCE | BONTOC (CAPITAL) (MOUNTAIN PROVINCE) | P00621008LZ | Construction of Flood Mitigation Structure | 120.9787 | 17.0863 | 29399999.7 | 29400000 | 2022 | JBA CONSTRUCTION AND BUILDERS | 3205 | 2022 | 2022-08-12 | 02/17/2022 | 0 | 0.3 | 2022-08-11 |  | 1
2024 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00823252LZ | Construction of Revetment | 120.9788 | 14.6199 | 67549454.35 | 67549086.8 | 2024 | AL-AMEN BUILDERS | 3206 | 2024 | 2024-06-20 | 02/13/2024 | 367.55 | 0 | 2024-08-29 | 70
2023 | Region IV-A | CAVITE | SILANG (CAVITE) | P00742172LZ | Construction of Slope Protection Structure | 120.9789 | 14.2135 | 98999944.23 | 98998997.47 | 2023 | MOTIONTRADE DEVELOPMENT CORPORATION / OMNICON BUILDERS | 3207 | 2023 | 2023-12-02 | 05/22/2023 | 946.76 | 0 | 2024-04-14 | 134
2023 | Region III | BULACAN | CITY OF MEYCAUAYAN (BULACAN) | P00726505LZ | Construction of Flood Mitigation Structure | 120.9789 | 14.7407 | 67549567.63 | 67549932.15 | 2023 | L.R. TIQUI BUILDERS, INC. | 3208 | 2023 | 2023-09-17 | 02/27/2023 | 0 | 364.52 | 2023-09-16 |  | 1
2023 | Region III | BULACAN | CITY OF MEYCAUAYAN (BULACAN) | P00726502LZ | Construction of Flood Mitigation Structure | 120.979 | 14.7407 | 40179117.11 | 39564412.44 | 2023 | N.M.E. CONSTRUCTION | 3209 | 2023 | 2023-08-08 | 02/27/2023 | 614704.67 | 0 | 2023-08-07 |  | 1
2021 | Region IV-A | CAVITE |  | P00525632LZ | Construction of Flood Mitigation Structure | 120.979 | 14.393 | 244145000 | 244114309.5 | 2022 | E. F. CHUA CONSTRUCTION, INC. | 3210 | 2021 | 2022-09-28 | 12/03/2021 | 30690.5 | 0 | 2022-09-27 |  | 1
2022 | Region III | BULACAN | CITY OF MEYCAUAYAN (BULACAN) | P00620188LZ | Construction of Flood Mitigation Structure | 120.9791 | 14.7247 | 95530236.72 | 95510324.84 | 2022 | TRIPLE 8 CONSTRUCTION & SUPPLY, INC. (FORMERLY TRIPLE 8 CONST. & SUPPLY) | 3211 | 2022 | 2022-09-30 | 03/07/2022 | 19911.88 | 0 | 2022-09-29 |  | 1
2021 | National Capital Region | PARAÃ‘AQUE CITY |  | P00525757LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.0165 | 14.4932 | 19600000 | 19599792.93 | 2022 | RNN CONSTRUCTION CORPORATION (FORMERLY RNN CONSTRU | 3212 | 2021 | 2022-09-26 | 03/22/2022 | 207.07 | 0 | 2022-09-25 |  | 1
2023 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00726802LZ | Construction of Flood Mitigation Facility | 120.9714 | 14.6022 | 72374153.2 | 72325692.28 | 2023 | JELSIE CONSTRUCTION & SUPPLY | 3213 | 2023 | 2023-07-22 | 03/10/2023 | 48460.92 | 0 | 2023-07-21 |  | 1
2022 | Region IV-A | CAVITE | BACOOR CITY (CAVITE) | P00639376LZ | Construction of Slope Protection Structure | 120.9791 | 14.4217 | 96499992.5 | 96427547.43 | 2023 | OMNICON BUILDERS | 3214 | 2022 | 2023-02-17 | 04/06/2022 | 72445.07 | 0 | 2023-05-14 | 86
2023 | Region IV-A | CAVITE | BACOOR CITY (CAVITE) | P00742177LZ | Construction of Flood Mitigation Structure | 120.9792 | 14.3927 | 71280000 | 71248261.56 | 2024 | E. F. CHUA CONSTRUCTION, INC. | 3215 | 2023 | 2024-04-11 | 07/17/2023 | 31738.44 | 0 | 2024-04-10 |  | 1
2023 | Region IV-A | CAVITE | SILANG (CAVITE) | P00742171LZ | Construction of Slope Protection Structure | 120.9793 | 14.2162 | 98999942.71 | 98999358.76 | 2024 | JTC CRUZ CONSTRUCTION CO., INC. | 3216 | 2023 | 2024-04-11 | 05/18/2023 | 583.95 | 0 | 2024-05-10 | 29
2023 | Cordillera Administrative Region | MOUNTAIN PROVINCE | BONTOC (CAPITAL) (MOUNTAIN PROVINCE) | P00726414LZ | Construction of Flood Mitigation Structure | 120.9793 | 17.0891 | 77199999.3 | 77200000 | 2024 | A.I.P. CONSTRUCTION / LEWIN VANNE GENERAL ENGINEERING AND CONSTRUCTION | 3217 | 2023 | 2024-02-27 | 07/19/2023 | 0 | 0.7 | 2024-02-26 |  | 1
2025 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00922881LZ | Construction of Flood Mitigation Facility | 120.9793 | 14.5994 | 38599649.79 | 37962740.47 | 2025 | A.M. SALONG CONSTRUCTION | 3218 | 2025 | 2025-04-20 | 03/12/2025 | 636909.32 | 0 | 2025-04-19 |  | 1
2023 | Region IV-B | OCCIDENTAL MINDORO | SAN JOSE (OCCIDENTAL MINDORO) | P00727378LZ | Construction of Flood Mitigation Structure | 120.9793 | 12.4344 | 45080000 | 45077987.54 | 2023 | KEJAMARENIK CONSTRUCTION & CONSTRUCTION SUPPLIES / R.M.A.J. CONSTRUCTION | 3219 | 2023 | 2023-09-20 | 03/20/2023 | 2012.46 | 0 | 2023-10-02 | 12
2024 | National Capital Region | CALOOCAN CITY | CALOOCAN CITY (METROPOLITAN MANILA) | P00838472LZ | Construction of Drainage Structure | 120.9794 | 14.6489 | 24497835.23 | 23958667.09 | 2025 | DMLC BUILDERS | 3220 | 2024 | 2025-03-31 | 05/06/2024 | 539168.14 | 0 | 2024-10-31 |  | 151
2021 | Region IV-A | CAVITE |  | P00525635LZ | Construction of Revetment | 120.9794 | 14.4215 | 48249995.3 | 48227677.8 | 2022 | GRAIA CONSTRUCTION CORPORATION | 3221 | 2021 | 2022-09-11 | 10/11/2021 | 22317.5 | 0 | 2022-09-10 |  | 1
2024 | Region III | NUEVA ECIJA | TALAVERA (NUEVA ECIJA) | P00823469LZ | Construction of Flood Mitigation Structure | 120.9796 | 15.6638 | 28950000 | 28660843.38 | 2024 | RPP 928 CONSTRUCTION CORPORATION | 3222 | 2024 | 2024-08-27 | 03/01/2024 | 289156.62 | 0 | 2024-08-26 |  | 1
2024 | Region III | NUEVA ECIJA | TALAVERA (NUEVA ECIJA) | P00848620LZ | Construction of Flood Mitigation Structure | 120.9796 | 15.6639 | 74250000 | 73507517.6 | 2024 | AMP 723 CONSTRUCTION CORPORATION (FORMERLY: A.M.P. CONSTRUCTION) | 3223 | 2024 | 2024-09-03 | 04/01/2024 | 742482.4 | 0 | 2024-10-26 | 53
2024 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00820089LZ | Construction of Flood Mitigation Facility | 120.9797 | 14.5991 | 140157466.9 | 138756597 | 2024 | JJPR CONSTRUCTION SERVICES | 3224 | 2024 | 2024-04-17 | 02/08/2024 | 1400869.9 | 0 | 2024-06-30 | 74
2023 | Region IV-A | BATANGAS | SAN LUIS (BATANGAS) | P00740398LZ | Construction of Drainage Structure | 120.9797 | 13.845 | 3920000 | 3860000 | 2023 | SUPPLICON BUILDERS | 3225 | 2023 | 2023-06-25 | 04/03/2023 | 60000 | 0 | 2023-06-24 |  | 1
2023 | Region III | BULACAN | SANTA MARIA (BULACAN) | P00742331LZ | Construction of Slope Protection Structure | 120.9798 | 14.8235 | 4945114.06 | 4945644.73 | 2023 | PLL BUILDERS INC. | 3226 | 2023 | 2023-08-09 | 03/30/2023 | 0 | 530.67 | 2023-08-08 |  | 1
2022 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00620433LZ | Construction of Flood Mitigation Structure | 120.9799 | 14.5987 | 48999912.96 | 48999081.39 | 2022 | FLORDES CONSTRUCTION & TRADING CORP. (FORMERLY FLO | 3227 | 2022 | 2022-10-05 | 02/17/2022 | 831.57 | 0 | 2022-10-04 |  | 1
2024 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00823275LZ | Rehabilitation / Major Repair of Flood Mitigation Facility | 120.98 | 14.5978 | 144749606.5 | 144457367.3 | 2024 | EIGHT J'S CONSTRUCTION SERVICES / JMRP CONSTRUCTION SERVICES | 3228 | 2024 | 2024-07-16 | 02/20/2024 | 292239.2 | 0 | 2024-07-17 | 1
2022 | Region IV-A | CAVITE | CITY OF DASMARIÃ‘AS (CAVITE) | P00637081LZ | Construction of Slope Protection Structure | 120.9804 | 14.2906 | 29399994.73 | 29398431.92 | 2023 | KLDS TRADING & CONSTRUCTION | 3229 | 2022 | 2023-01-15 | 04/06/2022 | 1562.81 | 0 | 2023-01-14 |  | 1
2022 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00620423LZ | Construction of Flood Mitigation Structure | 120.9807 | 14.5977 | 48999944.13 | 46917446.49 | 2022 | EIGHT J'S CONSTRUCTION SERVICES | 3230 | 2022 | 2022-10-06 | 02/18/2022 | 2082497.64 | 0 | 2022-10-05 |  | 1
2023 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00725503LZ | Construction of Flood Mitigation Facility | 120.9809 | 14.6335 | 86849891.04 | 86849835.87 | 2023 | EIGHT J'S CONSTRUCTION SERVICES | 3231 | 2023 | 2023-09-14 | 02/17/2023 | 55.17 | 0 | 2023-09-23 | 9
2023 | Region IV-A | CAVITE | SILANG (CAVITE) | P00725765LZ | Construction of Revetment | 120.9809 | 14.2196 | 96499961.13 | 96492780.49 | 2024 | FLORDES CONSTRUCTION & TRADING CORP. (FORMERLY FLO | 3232 | 2023 | 2024-05-17 | 04/24/2023 | 7180.64 | 0 | 2024-05-16 |  | 1
2023 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00727041LZ | Rehabilitation / Major Repair of Flood Mitigation Facility | 120.981 | 14.5885 | 24499419.95 | 24412468.58 | 2023 | JMK BUILDERS CONSTRUCTION | 3233 | 2023 | 2023-12-22 | 04/24/2023 | 86951.37 | 0 | 2024-04-22 | 122
2024 | Region III | BULACAN | SANTA MARIA (BULACAN) | P00820213LZ | Construction of Flood Mitigation Structure | 120.9814 | 14.862 | 85950582.75 | 85943604.24 | 2024 | JB CONSTRUCTION AND SUPPLY INC. (FORMERLY:JB CONSTRUCTION AND SUPPLY) | 3234 | 2024 | 2024-10-21 | 02/26/2024 | 6978.51 | 0 | 2024-11-28 | 38
2023 | Region IV-A | CAVITE | BACOOR CITY (CAVITE) | P00742179LZ | Construction of Flood Mitigation Structure | 120.9816 | 14.3834 | 56430000 | 56428250.88 | 2024 | E. F. CHUA CONSTRUCTION, INC. | 3235 | 2023 | 2024-04-05 | 06/15/2023 | 1749.12 | 0 | 2024-04-04 |  | 1
2022 | National Capital Region | LAS PIÃ‘AS CITY | CITY OF LAS PIÃ‘AS (METROPOLITAN MANILA) | P00637035LZ | Rehabilitation / Major Repair of Drainage Structure | 120.9818 | 14.4806 | 9799996.7 | 9797660.46 | 2022 | QUATRIX CONSTRUCTION AND SUPPLY INC. | 3236 | 2022 | 2022-10-03 | 04/07/2022 | 2336.24 | 0 | 2022-10-02 |  | 1
2023 | Region IV-A | CAVITE | SILANG (CAVITE) | P00725764LZ | Construction of Revetment | 120.9822 | 14.2217 | 96499947.07 | 96493672.63 | 2024 | FLORDES CONSTRUCTION & TRADING CORP. (FORMERLY FLO | 3237 | 2023 | 2024-04-07 | 04/24/2023 | 6274.44 | 0 | 2024-05-16 | 39
2024 | Region III | NUEVA ECIJA | PEÃ‘ARANDA (NUEVA ECIJA) | P00823443LZ | Construction of Flood Mitigation Structure | 120.9825 | 15.3647 | 141840507.3 | 141840512.3 | 2024 | R.A. PAHATI CONST. & SUPPLY, INC. | 3238 | 2024 | 2024-05-28 | 02/12/2024 | 0 | 5 | 2024-12-15 | 201
2020 | Region IV-B | OCCIDENTAL MINDORO |  | P00421959LZ | Construction of Flood Mitigation Structure | 120.9825 | 12.5211 | 34692000 | 34690916.94 | 2023 | HGG BUILDERS & SUPPLY | 3239 | 2020 | 2023-01-02 | 02/24/2020 | 1083.06 | 0 | 2021-02-23 |  | 678
2022 | Region III | BULACAN | SAN MIGUEL (BULACAN) | P00621276LZ | Construction of Flood Mitigation Structure | 120.9826 | 15.2163 | 48999450 | 48248408.12 | 2023 | M3 KONSTRACT CORPORATION (FORMERLY:MARGARITA CONSTRUCTION) | 3240 | 2022 | 2023-02-28 | 03/30/2022 | 751041.88 | 0 | 2023-03-30 | 30
2023 | Region III | BULACAN | SAN MIGUEL (BULACAN) | P00735975LZ | Construction of Flood Mitigation Structure | 120.9826 | 15.1463 | 82024986.86 | 82024947.3 | 2024 | SELPHAR CONSTRUCTION / N.B. AVILA CONSTRUCTION | 3241 | 2023 | 2024-02-26 | 06/05/2023 | 39.56 | 0 | 2024-02-28 | 2
2023 | Region III | BULACAN | SAN MIGUEL (BULACAN) | P00727393LZ | Construction of Flood Mitigation Structure | 120.9826 | 15.1463 | 96499940.3 | 96499303.4 | 2024 | MRRM TRADING & CONSTRUCTION | 3242 | 2023 | 2024-04-04 | 07/10/2023 | 636.9 | 0 | 2024-04-03 |  | 1
2023 | Region III | BULACAN | SAN MIGUEL (BULACAN) | P00727384LZ | Construction of Flood Mitigation Structure | 120.9826 | 15.1463 | 96499920.74 | 96496468.6 | 2024 | FLORDES CONSTRUCTION & TRADING CORP. (FORMERLY FLO | 3243 | 2023 | 2024-04-04 | 07/10/2023 | 3452.14 | 0 | 2024-04-03 |  | 1
2023 | Region III | BULACAN | SAN MIGUEL (BULACAN) | P00727385LZ | Construction of Flood Mitigation Structure | 120.9826 | 15.1463 | 96499938.34 | 96499361.4 | 2024 | GLOBALCRETE BUILDERS INC. | 3244 | 2023 | 2024-04-04 | 07/10/2023 | 576.94 | 0 | 2024-04-03 |  | 1
2023 | Region III | BULACAN | SAN MIGUEL (BULACAN) | P00727397LZ | Construction of Flood Mitigation Structure | 120.9826 | 15.1463 | 86849952.5 | 86848708.72 | 2024 | LE BRON CONSTRUCTION / OLYMPUS MINING AND BUILDERS GROUP PHILS. CORP. (FORMERLY: OLYMPUS BUILDERS AND MINING CORP.) | 3245 | 2023 | 2024-05-23 | 08/28/2023 | 1243.78 | 0 | 2024-05-22 |  | 1
2023 | Region III | BULACAN | SAN MIGUEL (BULACAN) | P00727396LZ | Construction of Flood Mitigation Structure | 120.9826 | 15.1463 | 91674940.51 | 91674157.28 | 2024 | LE BRON CONSTRUCTION / OLYMPUS MINING AND BUILDERS GROUP PHILS. CORP. (FORMERLY: OLYMPUS BUILDERS AND MINING CORP.) | 3246 | 2023 | 2024-05-23 | 08/28/2023 | 783.23 | 0 | 2024-05-22 |  | 1
2024 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00824612LZ | Rehabilitation / Major Repair of Drainage Structure | 120.9828 | 14.6051 | 26459782.87 | 26216676.55 | 2024 | G2XD CONSTRUCTION SERVICES | 3247 | 2024 | 2024-11-21 | 02/12/2024 | 243106.32 | 0 | 2024-11-20 |  | 1
2024 | Region III | BULACAN | SANTA MARIA (BULACAN) | P00820176LZ | Construction of Flood Mitigation Structure | 120.983 | 14.8592 | 88362767.24 | 88355138.92 | 2024 | EIRISH BUILDERS & SUPPLY INC. | 3248 | 2024 | 2024-11-24 | 02/14/2024 | 7628.32 | 0 | 2024-11-23 |  | 1
2023 | Region III | BULACAN | SAN ILDEFONSO (BULACAN) | P00727400LZ | Construction of Flood Mitigation Structure | 120.9831 | 15.027 | 96499982.63 | 96499188.38 | 2024 | GREAT PACIFIC BUILDERS AND GEN. CONTRACTOR INC. | 3249 | 2023 | 2024-04-04 | 07/10/2023 | 794.25 | 0 | 2024-04-03 |  | 1
2024 | Region III | BULACAN | SANTA MARIA (BULACAN) | P00820175LZ | Construction of Flood Mitigation Structure | 120.9833 | 14.8573 | 88363033.02 | 88353631.42 | 2024 | DJB CONSTRUCTION SERVICES | 3250 | 2024 | 2024-11-24 | 02/14/2024 | 9401.6 | 0 | 2024-11-23 |  | 1
2023 | Region IV-B | OCCIDENTAL MINDORO | RIZAL (OCCIDENTAL MINDORO) | P00725865LZ | Construction of Revetment | 120.9834 | 12.5219 | 96499999.21 | 96496890.26 | 2023 | GREAT PACIFIC BUILDERS AND GEN. CONTRACTOR INC. | 3251 | 2023 | 2023-11-10 | 02/11/2023 | 3108.95 | 0 | 2023-11-09 |  | 1
2023 | Region IV-A | CAVITE | SILANG (CAVITE) | P00725763LZ | Construction of Revetment | 120.9835 | 14.2237 | 96499965.62 | 96495469.47 | 2024 | FLORDES CONSTRUCTION & TRADING CORP. (FORMERLY FLO | 3252 | 2023 | 2024-04-07 | 04/24/2023 | 4496.15 | 0 | 2024-05-16 | 39
2023 | Region III | BULACAN | CITY OF MEYCAUAYAN (BULACAN) | P00726503LZ | Construction of Flood Mitigation Structure | 120.9835 | 14.7446 | 40179117.11 | 39564000 | 2023 | AZUL BUILDERS | 3253 | 2023 | 2023-08-22 | 03/13/2023 | 615117.11 | 0 | 2023-08-21 |  | 1
2023 | National Capital Region | CALOOCAN CITY | CALOOCAN CITY (METROPOLITAN MANILA) | P00737398LZ | Construction of Drainage Structure | 120.9836 | 14.6488 | 24742846.22 | 24190409.16 | 2023 | MIGHTY CONSTRUCTION & DEVELOPMENT INC. | 3254 | 2023 | 2023-12-27 | 05/19/2023 | 552437.06 | 0 | 2023-12-13 |  | 14
2024 | Region III | BULACAN | SANTA MARIA (BULACAN) | P00820174LZ | Construction of Flood Mitigation Structure | 120.9836 | 14.8538 | 88362901.29 | 88355337.98 | 2025 | EIRISH BUILDERS & SUPPLY INC. | 3255 | 2024 | 2025-02-22 | 02/14/2024 | 7563.31 | 0 | 2025-02-21 |  | 1
2024 | Region III | BULACAN | SANTA MARIA (BULACAN) | P00823478LZ | Construction of Flood Mitigation Structure | 120.984 | 14.8642 | 61825265.39 | 61825399.21 | 2024 | A.J. LAVA BUILDERS CORP. (FORMERLY: A.J. LAVA BUIL | 3256 | 2024 | 2024-12-18 | 03/18/2024 | 0 | 133.82 | 2024-12-17 |  | 1
2022 | National Capital Region | VALENZUELA CITY | CITY OF VALENZUELA (METROPOLITAN MANILA) | P00620394LZ | Construction of Flood Mitigation Structure | 120.984 | 14.6992 | 14695219.81 | 14239655.66 | 2022 | TM ABAD CONSTRUCTION CORP. (FOR: TM ABAD CONST.) | 3257 | 2022 | 2022-08-30 | 02/08/2022 | 455564.15 | 0 | 2022-09-04 | 5
2022 | National Capital Region | VALENZUELA CITY | CITY OF VALENZUELA (METROPOLITAN MANILA) | P00621409LZ | Construction of Flood Mitigation Structure | 120.9843 | 14.6704 | 19596502.37 | 19028179.35 | 2022 | SONPRO CONSTRUCTION | 3258 | 2022 | 2022-11-17 | 03/24/2022 | 568323.02 | 0 | 2022-11-17 | 0
2022 | National Capital Region | VALENZUELA CITY | CITY OF VALENZUELA (METROPOLITAN MANILA) | P00621408LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.9843 | 14.6704 | 46038732.02 | 44640333.82 | 2023 | TM ABAD CONSTRUCTION CORP. (FOR: TM ABAD CONST.) | 3259 | 2022 | 2023-05-29 | 03/24/2022 | 1398398.2 | 0 | 2023-02-15 |  | 103
2022 | Region IV-A | CAVITE | SILANG (CAVITE) | P00639491LZ | Construction of Drainage Structure | 120.9845 | 14.218 | 19599797.32 | 4899921 | 2022 | TCSC CORP. | 3260 | 2022 | 2022-10-17 | 04/11/2022 | 14699876.32 | 0 | 2022-10-16 |  | 1
2023 | National Capital Region | MALABON CITY | CITY OF MALABON (METROPOLITAN MANILA) | P00742218LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.9846 | 14.6697 | 7916735 | 7916292.51 | 2023 | AL-REM KONSTRUCT INC. | 3261 | 2023 | 2023-07-24 | 03/27/2023 | 442.49 | 0 | 2023-07-23 |  | 1
2022 | National Capital Region | LAS PIÃ‘AS CITY | CITY OF LAS PIÃ‘AS (METROPOLITAN MANILA) | P00637034LZ | Rehabilitation / Major Repair of Drainage Structure | 120.9846 | 14.4846 | 29399999.71 | 29398998.82 | 2023 | OMNICON BUILDERS | 3262 | 2022 | 2023-06-10 | 05/27/2022 | 1000.89 | 0 | 2023-06-09 |  | 1
2023 | Region III | NUEVA ECIJA | CABANATUAN CITY (NUEVA ECIJA) | P00737469LZ | Construction of Flood Mitigation Structure | 120.985 | 15.4736 | 5939960.93 | 5791378.53 | 2023 | CELSO C. FERRER CONSTRUCTION CORP. | 3263 | 2023 | 2023-06-02 | 02/10/2023 | 148582.4 | 0 | 2023-06-02 | 0
2025 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00920054LZ | Construction of Flood Mitigation Facility | 120.985 | 14.6034 | 48249769.2 | 47322508.07 | 2025 | JJPR CONSTRUCTION SERVICES | 3264 | 2025 | 2025-04-02 | 02/12/2025 | 927261.13 | 0 | 2025-04-01 |  | 1
2021 | Cordillera Administrative Region | MOUNTAIN PROVINCE |  | P00526382LZ | Construction of Flood Mitigation Structure | 120.985 | 17.0746 | 48999999.7 | 49000000 | 2022 | ED1SON DEVELOPMENT & CONSTRUCTION INC. / KOMICHOV GENERAL CONSTRUCTION | 3265 | 2021 | 2022-12-15 | 04/11/2022 | 0 | 0.3 | 2022-12-14 |  | 1
2024 | National Capital Region | VALENZUELA CITY | CITY OF VALENZUELA (METROPOLITAN MANILA) | P00820615LZ | Construction of Flood Mitigation Facility | 120.9851 | 14.7046 | 39167656.96 | 38367629.52 | 2024 | TWO DIMENSION CONSTRUCTION | 3266 | 2024 | 2024-11-29 | 02/27/2024 | 800027.44 | 0 | 2025-08-18 | 262
2023 | Region III | BULACAN | SAN MIGUEL (BULACAN) | P00736016LZ | Construction of Flood Mitigation Structure | 120.9851 | 15.2168 | 96499959.06 | 96499956.2 | 2024 | C.T. LEONCIO CONSTRUCTION & TRADING / ALLEYWAY CONSTRUCTION | 3267 | 2023 | 2024-02-29 | 06/05/2023 | 2.86 | 0 | 2024-02-28 |  | 1
2023 | Region III | BULACAN | SAN MIGUEL (BULACAN) | P00736017LZ | Construction of Flood Mitigation Structure | 120.9851 | 15.2168 | 96499994.06 | 96499983.6 | 2024 | ALPHA & OMEGA GEN. CONTRACTOR & DEVELOPMENT CORP. | 3268 | 2023 | 2024-02-29 | 06/05/2023 | 10.46 | 0 | 2024-02-28 |  | 1
2023 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00740290LZ | Construction of Flood Mitigation Facility | 120.9851 | 14.598 | 72374399.73 | 72373998.71 | 2023 | FIAT CONSTRUCTION SERVICES | 3269 | 2023 | 2023-06-23 | 03/28/2023 | 401.02 | 0 | 2023-08-08 | 46
2023 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00726800LZ | Construction of Flood Mitigation Facility | 120.9851 | 14.598 | 72374420.52 | 70586825.43 | 2023 | FIAT CONSTRUCTION SERVICES | 3270 | 2023 | 2023-06-22 | 03/10/2023 | 1787595.09 | 0 | 2023-06-29 | 7
2023 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00726799LZ | Construction of Flood Mitigation Facility | 120.9851 | 14.598 | 72374776.28 | 72374712.09 | 2023 | FIAT CONSTRUCTION SERVICES | 3271 | 2023 | 2023-06-23 | 03/10/2023 | 64.19 | 0 | 2023-06-29 | 6
2022 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00620066LZ | Construction of Drainage Structure | 120.9852 | 14.5698 | 77200000 | 77065181.98 | 2023 | TRIPLE 8 CONSTRUCTION & SUPPLY, INC. (FORMERLY TRIPLE 8 CONST. & SUPPLY) | 3272 | 2022 | 2023-01-13 | 02/28/2022 | 134818.02 | 0 | 2023-01-12 |  | 1
2023 | Region IV-A | CAVITE | SILANG (CAVITE) | P00736024LZ | Construction of Revetment | 120.9853 | 14.2267 | 96499965.55 | 96499962.16 | 2024 | SUPREME ABF CONST. & CONST. SUPPLY COMPANY INC. | 3273 | 2023 | 2024-11-15 | 04/11/2023 | 3.39 | 0 | 2024-08-02 |  | 105
2022 | National Capital Region | VALENZUELA CITY | CITY OF VALENZUELA (METROPOLITAN MANILA) | P00620392LZ | Construction of Flood Mitigation Structure | 120.9854 | 14.6866 | 19596503.01 | 18989004.18 | 2022 | SONPRO CONSTRUCTION | 3274 | 2022 | 2022-11-11 | 03/18/2022 | 607498.83 | 0 | 2022-11-11 | 0
2023 | Region IV-A | CAVITE | SILANG (CAVITE) | P00726570LZ | Construction of Revetment | 120.9854 | 14.2299 | 96499943.8 | 96499032.96 | 2023 | OMNICON BUILDERS | 3275 | 2023 | 2023-11-17 | 02/21/2023 | 910.84 | 0 | 2024-01-15 | 59
2024 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00820087LZ | Construction of Flood Mitigation Facility | 120.9856 | 14.597 | 144749748 | 144717637.9 | 2024 | JIIK CONSTRUCTION SERVICES | 3276 | 2024 | 2024-04-17 | 02/08/2024 | 32110.1 | 0 | 2024-07-05 | 79
2024 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00820088LZ | Construction of Flood Mitigation Facility | 120.9856 | 14.597 | 144749005.8 | 142902794.3 | 2024 | JIIK CONSTRUCTION SERVICES | 3277 | 2024 | 2024-04-17 | 02/12/2024 | 1846211.5 | 0 | 2024-07-09 | 83
2023 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00725997LZ | Construction of Flood Mitigation Structure | 120.9858 | 14.5961 | 34299916.3 | 33678257.09 | 2024 | JELSIE CONSTRUCTION & SUPPLY | 3278 | 2023 | 2024-08-19 | 02/16/2023 | 621659.21 | 0 | 2024-08-25 | 6
2023 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00725495LZ | Construction of Flood Mitigation Structure | 120.9858 | 14.5954 | 48248540.52 | 47375366.03 | 2024 | JELSIE CONSTRUCTION & SUPPLY | 3279 | 2023 | 2024-04-07 | 02/17/2023 | 873174.49 | 0 | 2024-04-06 |  | 1
2023 | Region IV-A | CAVITE | SILANG (CAVITE) | P00742427LZ | Construction of Slope Protection Structure | 120.9859 | 14.2342 | 49499955.68 | 49499413.18 | 2023 | OMNICON BUILDERS | 3280 | 2023 | 2023-12-23 | 05/01/2023 | 542.5 | 0 | 2023-12-22 |  | 1
2024 | National Capital Region | LAS PIÃ‘AS CITY | CITY OF LAS PIÃ‘AS (METROPOLITAN MANILA) | P00821041LZ | Construction of Flood Mitigation Structure | 120.986 | 14.4798 | 96400404.85 | 96395127.6 | 2024 | MRRM TRADING & CONSTRUCTION / KPSL GENERAL CONTRACTOR INC. | 3281 | 2024 | 2024-08-28 | 02/08/2024 | 5277.25 | 0 | 2024-10-03 | 36
2022 | National Capital Region | LAS PIÃ‘AS CITY | CITY OF LAS PIÃ‘AS (METROPOLITAN MANILA) | P00631010LZ | Rehabilitation / Major Repair of Drainage Structure | 120.9864 | 14.4638 | 9799999.82 | 9799014.24 | 2023 | MRJR CONSTRUCTION & TRADING | 3282 | 2022 | 2023-04-16 | 05/27/2022 | 985.58 | 0 | 2023-04-15 |  | 1
2024 | Region III | BULACAN | SANTA MARIA (BULACAN) | P00845783LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.9865 | 14.8432 | 98999835.95 | 98916463.13 | 2025 | NEWBIG FOUR J CONSTRUCTION INC., (FORMERLY FOUR J | 3283 | 2024 | 2025-04-06 | 03/18/2024 | 83372.82 | 0 | 2025-04-05 |  | 1
2022 | National Capital Region | LAS PIÃ‘AS CITY | CITY OF LAS PIÃ‘AS (METROPOLITAN MANILA) | P00620908LZ | Construction of Flood Mitigation Structure | 120.9866 | 14.473 | 48999678.96 | 48997928.47 | 2022 | I&E CONSTRUCTION CORPORATION (FORMERLY: I&E CONSTR | 3284 | 2022 | 2022-10-03 | 04/07/2022 | 1750.49 | 0 | 2022-10-02 |  | 1
2023 | Region II | CAGAYAN | SANTA PRAXEDES (CAGAYAN) | P00742299LZ | Construction of Slope Protection Structure | 120.9867 | 18.5567 | 14850000 | 14542977.58 | 2023 | OCP CONSTRUCTION | 3285 | 2023 | 2023-09-24 | 03/27/2023 | 307022.42 | 0 | 2023-09-23 |  | 1
2022 | Region IV-A | CAVITE | SILANG (CAVITE) | P00639492LZ | Construction of Drainage Structure | 120.9868 | 14.2399 | 19599797.32 | 4899931.63 | 2022 | TCSC CORP. | 3286 | 2022 | 2022-10-17 | 04/11/2022 | 14699865.69 | 0 | 2022-10-16 |  | 1
2025 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00920053LZ | Construction of Flood Mitigation Facility | 120.9869 | 14.6051 | 48249977.78 | 47318052.55 | 2025 | JJPR CONSTRUCTION SERVICES | 3287 | 2025 | 2025-04-02 | 02/12/2025 | 931925.23 | 0 | 2025-04-01 |  | 1
2020 | Region IV-B | OCCIDENTAL MINDORO |  | P00421954LZ | Construction of Flood Mitigation Structure | 120.9869 | 12.4361 | 49000000 | 48999488.98 | 2022 | HGG BUILDERS & SUPPLY | 3288 | 2020 | 2022-11-27 | 02/24/2020 | 511.02 | 0 | 2021-03-13 |  | 624
2022 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00620454LZ | Rehabilitation / Major Repair of Drainage Structure | 120.987 | 14.5939 | 19799898.48 | 19235550.06 | 2022 | JMK BUILDERS CONSTRUCTION | 3289 | 2022 | 2022-08-08 | 06/08/2022 | 564348.42 | 0 | 2023-01-02 | 147
2023 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00737401LZ | Rehabilitation / Major Repair of Drainage Structure | 120.9871 | 14.5939 | 19799999.93 | 19793655.7 | 2023 | JMK BUILDERS CONSTRUCTION | 3290 | 2023 | 2023-08-23 | 02/21/2023 | 6344.23 | 0 | 2023-08-22 |  | 1
2022 | Region II | CAGAYAN | SANTA PRAXEDES (CAGAYAN) | P00621036LZ | Construction of Flood Mitigation Structure | 120.9872 | 18.5664 | 14356020 | 14356020 | 2023 | NCL BUILDERS AND CONSTRUCTION SUPPLY | 3291 | 2022 | 2023-03-10 | 03/29/2022 | 0 | 0 | 2022-11-18 |  | 112
2023 | Region IV-B | OCCIDENTAL MINDORO | CALINTAAN (OCCIDENTAL MINDORO) | P00726766LZ | Construction of Flood Mitigation Structure | 121.0054 | 12.6225 | 45080000 | 44848347.79 | 2023 | F.A. TORRES CONSTRUCTION | 3292 | 2023 | 2023-07-15 | 02/10/2023 | 231652.21 | 0 | 2023-08-16 | 32
2023 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00740291LZ | Construction of Flood Mitigation Facility | 120.9714 | 14.6022 | 72374816.16 | 70920836.76 | 2023 | FIAT CONSTRUCTION SERVICES | 3293 | 2023 | 2023-06-23 | 03/28/2023 | 1453979.4 | 0 | 2023-08-08 | 46
2022 | National Capital Region | QUEZON CITY | QUEZON CITY (METROPOLITAN MANILA) | P00620926LZ | Construction of Flood Mitigation Structure | 121.0166 | 14.6533 | 48019939.82 | 48019939.82 | 2022 | VICTORIA DEVELOPMENT AND VENTURES CORP. (FOR: VICTORIA DEV'T AND CONST. CORP.) | 3294 | 2022 | 2022-11-21 | 02/07/2022 | 0 | 0 | 2022-12-02 | 11
2022 | National Capital Region | QUEZON CITY | QUEZON CITY (METROPOLITAN MANILA) | P00620927LZ | Construction of Flood Mitigation Structure | 121.0166 | 14.6533 | 48019938.26 | 46581350.46 | 2023 | LARSEN-DUTCHER CONSTRACTOR CORPORATION (FORMERLY:LARSEN-DUTCHER CONSTRACTOR) / DREAMWORX BUILDER & TRADING, INC. | 3295 | 2022 | 2023-04-26 | 03/23/2022 | 1438587.8 | 0 | 2023-01-15 |  | 101
2023 | National Capital Region | PARAÃ‘AQUE CITY | CITY OF PARAÃ‘AQUE (METROPOLITAN MANILA) | P00742241LZ | Construction of Drainage Structure | 121.0054 | 14.5107 | 5049000 | 5048995.64 | 2024 | ILFREO CONSTRUCTION CORP. (FORMERLY:ILFREO CONSTRUCTION & TRADING CORP.) | 3296 | 2023 | 2024-03-07 | 08/14/2023 | 4.36 | 0 | 2024-03-06 |  | 1
2022 | National Capital Region | MAKATI CITY | CITY OF MAKATI (METROPOLITAN MANILA) | P00632694LZ | Construction of Drainage Structure | 121.0166 | 14.5752 | 67550000 | 69291965.57 | 2022 | E. F. CHUA CONSTRUCTION, INC. | 3297 | 2022 | 2022-12-13 | 02/17/2022 | 0 | 1741965.57 | 2022-12-12 |  | 1
2023 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00740285LZ | Construction of Flood Mitigation Facility | 120.9714 | 14.6022 | 72373962.3 | 70521409.22 | 2023 | JELSIE CONSTRUCTION & SUPPLY | 3298 | 2023 | 2023-07-25 | 03/28/2023 | 1852553.08 | 0 | 2023-08-08 | 14
2023 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00727026LZ | Construction of Flood Mitigation Structure | 121.0166 | 14.5891 | 39199374.54 | 39158630.18 | 2023 | ST. MATTHEW GEN. CONTRACTOR & DEVELOPMENT CORP. / K84 CONSTRUCTION AND DEVELOPMENT CORPORATION | 3299 | 2023 | 2023-11-08 | 03/01/2023 | 40744.36 | 0 | 2023-11-07 |  | 1
2021 | National Capital Region | PARAÃ‘AQUE CITY |  | P00525758LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.0384 | 14.4706 | 19600000 | 19598319.74 | 2022 | RNN CONSTRUCTION CORPORATION (FORMERLY RNN CONSTRU | 3300 | 2021 | 2022-09-27 | 03/22/2022 | 1680.26 | 0 | 2022-09-26 |  | 1
2023 | Region III | NUEVA ECIJA | LLANERA (NUEVA ECIJA) | P00726171LZ | Construction of Flood Mitigation Structure | 121.0056 | 15.7249 | 49000000 | 48995000 | 2023 | ADROIT EJD CONSTRUCTION CORP. (FORMERLY: ADROIT CONSTRUCTION) / DGSARM BUILDERS INC. (FORMERLY: D.G. SARMENTA CONSTRUCTION) | 3301 | 2023 | 2023-05-16 | 02/13/2023 | 5000 | 0 | 2023-09-09 | 116
2022 | National Capital Region | MAKATI CITY | CITY OF MAKATI (METROPOLITAN MANILA) | P00620020LZ | Construction of Drainage Structure | 121.0166 | 14.5751 | 72375000 | 72364843.39 | 2022 | E. F. CHUA CONSTRUCTION, INC. | 3302 | 2022 | 2022-10-24 | 02/17/2022 | 10156.61 | 0 | 2022-12-12 | 49
2023 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00740283LZ | Construction of Flood Mitigation Facility | 120.9714 | 14.6022 | 72374153.2 | 72291429.13 | 2023 | EIGHT J'S CONSTRUCTION SERVICES | 3303 | 2023 | 2023-07-25 | 03/28/2023 | 82724.07 | 0 | 2023-08-08 | 14
2024 | National Capital Region | PARAÃ‘AQUE CITY | CITY OF PARAÃ‘AQUE (METROPOLITAN MANILA) | P00820570LZ | Construction of Revetment | 121.0056 | 14.4974 | 34300000 | 32931552.36 | 2024 | RNN CONSTRUCTION CORPORATION (FORMERLY RNN CONSTRU / AKN CONSTRUCTION CORPORATION | 3304 | 2024 | 2024-06-06 | 02/08/2024 | 1368447.64 | 0 | 2024-06-05 |  | 1
2024 | Region III | BULACAN | ANGAT (BULACAN) | P00821581LZ | Construction of Flood Mitigation Structure | 121.0167 | 14.9465 | 48249897.83 | 48249073.18 | 2024 | ALPHA & OMEGA GEN. CONTRACTOR & DEVELOPMENT CORP. | 3305 | 2024 | 2024-11-07 | 04/08/2024 | 824.65 | 0 | 2024-11-06 |  | 1
2023 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00740284LZ | Construction of Flood Mitigation Facility | 120.9714 | 14.6022 | 72374315.67 | 70404227.68 | 2023 | EIGHT J'S CONSTRUCTION SERVICES | 3306 | 2023 | 2023-07-25 | 03/28/2023 | 1970087.99 | 0 | 2023-08-08 | 14
2024 | National Capital Region | QUEZON CITY | QUEZON CITY (METROPOLITAN MANILA) | P00844687LZ | Construction of Drainage Structure | 121.0385 | 14.6856 | 9799939.4 | 9799570.63 | 2024 | C.E.M. CONSTRUCTION, INC. | 3307 | 2024 | 2024-06-20 | 02/23/2024 | 368.77 | 0 | 2024-06-20 | 0
2024 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00820659LZ | Construction of Flood Mitigation Structure | 121.0056 | 14.5909 | 39199863.76 | 39197819.94 | 2024 | AMETHYST HORIZON BUILDERS AND GEN. CONTRACTOR AND DEVELOPMENT CORP. | 3308 | 2024 | 2024-07-17 | 02/23/2024 | 2043.82 | 0 | 2024-11-17 | 123
2024 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00845868LZ | Rehabilitation / Major Repair of Drainage Structure | 120.9715 | 14.6068 | 98999294.21 | 98998433.15 | 2024 | EIGHT J'S CONSTRUCTION SERVICES / JMRP CONSTRUCTION SERVICES | 3309 | 2024 | 2024-07-11 | 02/20/2024 | 861.06 | 0 | 2024-10-03 | 84
2022 | National Capital Region | PARAÃ‘AQUE CITY | CITY OF PARAÃ‘AQUE (METROPOLITAN MANILA) | P00640486LZ | Construction of Flood Mitigation Structure | 121.0167 | 14.4761 | 4950000 | 4950000 | 2023 | G.F. ROVERO MERCHANDISING | 3310 | 2022 | 2023-02-06 | 10/10/2022 | 0 | 0 | 2023-02-05 |  | 1
2022 | National Capital Region | QUEZON CITY | QUEZON CITY (METROPOLITAN MANILA) | P00620440LZ | Construction of Flood Mitigation Structure | 121.0385 | 14.666 | 44100000 | 42777000 | 2022 | LARSEN-DUTCHER CONSTRACTOR CORPORATION (FORMERLY:LARSEN-DUTCHER CONSTRACTOR) | 3311 | 2022 | 2022-10-21 | 02/07/2022 | 1323000 | 0 | 2022-12-02 | 42
2022 | National Capital Region | PASAY CITY | PASAY CITY (METROPOLITAN MANILA) | P00620014LZ | Construction of Slope Protection Structure | 121.0058 | 14.5324 | 52323615.95 | 52318093.71 | 2022 | CAANA CONSTRUCTION CORPORATION | 3312 | 2022 | 2022-08-31 | 02/28/2022 | 5522.24 | 0 | 2022-10-24 | 54
2023 | Region IV-A | CAVITE | SILANG (CAVITE) | P00737514LZ | Construction of Drainage Structure | 120.9715 | 14.2152 | 19799810.39 | 4949896.9 | 2023 | ALMAKAR BUILDERS & METAL WORKS | 3313 | 2023 | 2023-08-17 | 02/15/2023 | 14849913.49 | 0 | 2023-09-11 | 25
2022 | Region III | BULACAN | ANGAT (BULACAN) | P00631222LZ | Construction of Flood Mitigation Structure | 121.0169 | 14.9454 | 18619705.64 | 18338920.48 | 2022 | ALPHA & OMEGA GEN. CONTRACTOR & DEVELOPMENT CORP. | 3314 | 2022 | 2022-08-10 | 03/07/2022 | 280785.16 | 0 | 2022-08-09 |  | 1
2023 | National Capital Region | SAN JUAN CITY | CITY OF SAN JUAN (METROPOLITAN MANILA) | P00725970LZ | Construction of Drainage Structure | 121.0387 | 14.6037 | 35279959.91 | 33505657.17 | 2023 | JAGONBUILD CONSTRUCTION CORP. (FOR. JAGON BUILDERS | 3315 | 2023 | 2023-06-18 | 02/06/2023 | 1774302.74 | 0 | 2023-08-03 | 46
2023 | Region IV-B | OCCIDENTAL MINDORO | RIZAL (OCCIDENTAL MINDORO) | P00727377LZ | Construction of Flood Mitigation Structure | 121.017 | 12.4553 | 45080000 | 45079355.23 | 2023 | F.A. TORRES CONSTRUCTION / MIGHTY DRAGON BUILDERS INC. | 3316 | 2023 | 2023-07-17 | 03/10/2023 | 644.77 | 0 | 2023-10-11 | 86
2024 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00820662LZ | Construction of Flood Mitigation Structure | 121.006 | 14.5933 | 24499603.47 | 24492317.29 | 2024 | AMETHYST HORIZON BUILDERS AND GEN. CONTRACTOR AND DEVELOPMENT CORP. | 3317 | 2024 | 2024-04-30 | 02/21/2024 | 7286.18 | 0 | 2024-09-26 | 149
2024 | Region III | BULACAN | SANTA MARIA (BULACAN) | P00844746LZ | Construction of Flood Mitigation Structure | 120.9715 | 14.8167 | 48999987.58 | 48998501.05 | 2024 | R.A. PAHATI CONST. & SUPPLY, INC. | 3318 | 2024 | 2024-07-09 | 03/25/2024 | 1486.53 | 0 | 2024-10-18 | 101
2024 | National Capital Region | CALOOCAN CITY | CALOOCAN CITY (METROPOLITAN MANILA) | P00820597LZ | Construction of Flood Mitigation Structure | 121.039 | 14.7543 | 48975949.56 | 47975930.1 | 2024 | IM CONSTRUCTION CORPORATION | 3319 | 2024 | 2024-05-19 | 02/27/2024 | 1000019.46 | 0 | 2024-09-22 | 126
2023 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00740282LZ | Construction of Flood Mitigation Structure | 120.9715 | 14.6099 | 96499755.21 | 94942061.84 | 2024 | SUPREME ABF CONST. & CONST. SUPPLY COMPANY INC. / MANGEN TECHNO-BUILDERS INC. | 3320 | 2023 | 2024-05-01 | 03/28/2023 | 1557693.37 | 0 | 2024-04-30 |  | 1
2022 | National Capital Region | MAKATI CITY | CITY OF MAKATI (METROPOLITAN MANILA) | P00620037LZ | Construction of Revetment | 121.0172 | 14.5302 | 87815000 | 87811870.7 | 2022 | E. F. CHUA CONSTRUCTION, INC. | 3321 | 2022 | 2022-11-13 | 02/17/2022 | 3129.3 | 0 | 2022-11-12 |  | 1
2023 | Region III | NUEVA ECIJA | SAN JOSE CITY (NUEVA ECIJA) | P00726170LZ | Construction of Flood Mitigation Structure | 121.0176 | 15.8095 | 49000000 | 48999995.55 | 2023 | AMP 723 CONSTRUCTION CORPORATION (FORMERLY: A.M.P. CONSTRUCTION) / IJK MAE CONSTRUCTION INC. | 3322 | 2023 | 2023-09-06 | 02/09/2023 | 4.45 | 0 | 2023-09-05 |  | 1
2024 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00820010LZ | Construction of Drainage Structure | 121.0062 | 14.5989 | 67549628.75 | 67202179.61 | 2024 | G.F. FABIAN CONSTRUCTION | 3323 | 2024 | 2024-12-13 | 02/07/2024 | 347449.14 | 0 | 2024-12-17 | 4
2022 | National Capital Region | MAKATI CITY | CITY OF MAKATI (METROPOLITAN MANILA) | P00620379LZ | Rehabilitation / Major Repair of Drainage Structure | 121.0392 | 14.5628 | 11760000 | 11171751.54 | 2022 | ALEXA TRADING & CONSTRUCTION | 3324 | 2022 | 2022-10-06 | 02/09/2022 | 588248.46 | 0 | 2022-10-05 |  | 1
2023 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00740298LZ | Construction of Flood Mitigation Facility | 120.9715 | 14.6097 | 96499593.7 | 96198358.4 | 2023 | ST. TIMOTHY CONSTRUCTION CORPORATION / D.T. RECIO INCORPORATED | 3325 | 2023 | 2023-06-23 | 03/28/2023 | 301235.3 | 0 | 2023-07-04 | 11
2021 | National Capital Region | QUEZON CITY |  | P00525836LZ | Construction of Slope Protection Structure | 121.018 | 14.635 | 28625800 | 27189705.07 | 2022 | A.L. SALAZAR CONSTRUCTION, INC. | 3326 | 2021 | 2022-12-16 | 03/22/2022 | 1436094.93 | 0 | 2022-12-15 |  | 1
2024 | National Capital Region | CALOOCAN CITY | CALOOCAN CITY (METROPOLITAN MANILA) | P00820598LZ | Construction of Flood Mitigation Structure | 121.0066 | 14.7269 | 48980440.84 | 47951831.23 | 2024 | PERSAN CONSTRUCTION, INC. (FORMERLY: PERSAN CONST. | 3327 | 2024 | 2024-07-22 | 02/27/2024 | 1028609.61 | 0 | 2024-07-24 | 2
2023 | National Capital Region | SAN JUAN CITY | CITY OF SAN JUAN (METROPOLITAN MANILA) | P00725519LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.0392 | 14.5974 | 62724943.96 | 59589301.21 | 2024 | B. BERNARDO CONST., INC. | 3328 | 2023 | 2024-02-11 | 02/13/2023 | 3135642.75 | 0 | 2023-11-23 |  | 80
2023 | Region IV-A | LAGUNA | CITY OF BIÃ‘AN (LAGUNA) | P00725824LZ | Construction of Flood Mitigation Structure | 121.0394 | 14.2705 | 96500000 | 96489102.22 | 2024 | M.T. MALIUANAG CONSTRUCTION SERVICES | 3329 | 2023 | 2024-02-08 | 08/09/2023 | 10897.78 | 0 | 2024-06-20 | 133
2023 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00740295LZ | Construction of Flood Mitigation Facility | 120.9715 | 14.6097 | 96499611.62 | 96411549.07 | 2023 | ST. TIMOTHY CONSTRUCTION CORPORATION / COSMAN BUILDERS | 3330 | 2023 | 2023-06-23 | 03/28/2023 | 88062.55 | 0 | 2023-07-19 | 26
2024 | National Capital Region | PARAÃ‘AQUE CITY | CITY OF PARAÃ‘AQUE (METROPOLITAN MANILA) | P00820571LZ | Construction of Revetment | 121.0181 | 14.4929 | 29400000 | 29394774.79 | 2024 | RNN CONSTRUCTION CORPORATION (FORMERLY RNN CONSTRU | 3331 | 2024 | 2024-05-20 | 02/19/2024 | 5225.21 | 0 | 2024-06-16 | 27
2022 | National Capital Region | LAS PIÃ‘AS CITY | CITY OF LAS PIÃ‘AS (METROPOLITAN MANILA) | P00620910LZ | Construction of Flood Mitigation Structure | 121.007 | 14.4285 | 48999195.3 | 48991818.78 | 2022 | ALPHA & OMEGA GEN. CONTRACTOR & DEVELOPMENT CORP. | 3332 | 2022 | 2022-09-06 | 02/09/2022 | 7376.52 | 0 | 2022-09-05 |  | 1
2023 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00740299LZ | Construction of Flood Mitigation Facility | 120.9715 | 14.6097 | 96499482.71 | 94729146.04 | 2023 | LQG TRADING AND CONSTRUCTION / ST. TIMOTHY CONSTRUCTION CORPORATION | 3333 | 2023 | 2023-07-25 | 03/28/2023 | 1770336.67 | 0 | 2023-07-29 | 4
2022 | National Capital Region | PARAÃ‘AQUE CITY | CITY OF PARAÃ‘AQUE (METROPOLITAN MANILA) | P00621130LZ | Construction of Flood Mitigation Facility | 121.0071 | 14.4697 | 96500000 | 96496182.97 | 2023 | AKN CONSTRUCTION CORPORATION | 3334 | 2022 | 2023-05-17 | 03/24/2022 | 3817.03 | 0 | 2023-05-16 |  | 1
2022 | Region IV-A | LAGUNA | CITY OF SAN PEDRO (LAGUNA) | P00620585LZ | Construction of Revetment | 121.0185 | 14.3388 | 44100000 | 43345890 | 2022 | 11 DIAMOND EAGLE CONSTRUCTION CORPORATION (FORMERLY:11 DIAMOND EAGLE CONSTRUCTION) | 3335 | 2022 | 2022-10-18 | 02/21/2022 | 754110 | 0 | 2022-10-17 |  | 1
2022 | National Capital Region | PARAÃ‘AQUE CITY | CITY OF PARAÃ‘AQUE (METROPOLITAN MANILA) | P00637041LZ | Construction of Flood Mitigation Structure | 121.0188 | 14.4929 | 24500000 | 24499855.4 | 2022 | GMO CONSTRUCTION | 3336 | 2022 | 2022-11-16 | 03/22/2022 | 144.6 | 0 | 2022-11-15 |  | 1
2022 | National Capital Region | PASAY CITY | PASAY CITY (METROPOLITAN MANILA) | P00620110LZ | Construction of Slope Protection Structure | 121.0071 | 14.5318 | 57895380.25 | 57863665.29 | 2022 | ALPHA & OMEGA GEN. CONTRACTOR & DEVELOPMENT CORP. | 3337 | 2022 | 2022-09-07 | 03/02/2022 | 31714.96 | 0 | 2022-10-26 | 49
2024 | Region III | NUEVA ECIJA | GUIMBA (NUEVA ECIJA) | P00823473LZ | Construction of Flood Mitigation Structure | 120.9716 | 15.5907 | 48250000 | 47762663.9 | 2024 | NIÃ‘AS CONSTRUCTION CORP. (FORMERLY: NINA'S CONSTRUCTION AND SUPPLIES) | 3338 | 2024 | 2024-12-23 | 04/29/2024 | 487336.1 | 0 | 2024-12-22 |  | 1
2021 | National Capital Region | MAKATI CITY |  | P00525480LZ | Construction of Flood Mitigation Structure | 121.0188 | 14.5781 | 73500000 | 72368946.37 | 2022 | E. F. CHUA CONSTRUCTION, INC. | 3339 | 2021 | 2022-12-13 | 06/22/2022 | 1131053.63 | 0 | 2022-12-17 | 4
2023 | National Capital Region | PASAY CITY | PASAY CITY (METROPOLITAN MANILA) | P00726038LZ | Construction of Slope Protection Structure | 121.0071 | 14.5318 | 24496286.89 | 23908375.76 | 2023 | ALPHA & OMEGA GEN. CONTRACTOR & DEVELOPMENT CORP. | 3340 | 2023 | 2023-07-20 | 02/21/2023 | 587911.13 | 0 | 2023-07-19 |  | 1
2024 | Region IV-A | LAGUNA | CITY OF BIÃ‘AN (LAGUNA) | P00820891LZ | Construction of Flood Mitigation Structure | 121.0396 | 14.324 | 11760000 | 11709794.19 | 2024 | M.T. MALIUANAG CONSTRUCTION SERVICES | 3341 | 2024 | 2024-06-13 | 02/23/2024 | 50205.81 | 0 | 2024-06-20 | 7
2022 | Region III | NUEVA ECIJA | TALAVERA (NUEVA ECIJA) | P00620537LZ | Construction of Flood Mitigation Structure | 120.972 | 15.6626 | 49000000 | 49000000 | 2022 | AMP 723 CONSTRUCTION CORPORATION (FORMERLY: A.M.P. CONSTRUCTION) | 3342 | 2022 | 2022-09-01 | 02/04/2022 | 0 | 0 | 2022-08-31 |  | 1
2023 | Region III | BULACAN | SAN RAFAEL (BULACAN) | P00726501LZ | Construction of Flood Mitigation Structure | 121.0189 | 14.9612 | 96499956.22 | 96492940.3 | 2024 | GLOBALCRETE BUILDERS INC. | 3343 | 2023 | 2024-10-07 | 06/05/2023 | 7015.92 | 0 | 2024-02-28 |  | 222
2024 | National Capital Region | PASAY CITY | PASAY CITY (METROPOLITAN MANILA) | P00843174LZ | Construction of Flood Mitigation Structure | 121.0191 | 14.5292 | 96499999.03 | 96400267.28 | 2024 | HI-TONE CONSTRUCTION & DEVELOPMENT CORP. (FORMERLY / FS CO BUILDERS AND SUPPLY | 3344 | 2024 | 2024-11-19 | 05/06/2024 | 99731.75 | 0 | 2025-01-29 | 71
2021 | National Capital Region | MAKATI CITY |  | P00561203LZ | Construction of Drainage Structure | 121.0073 | 14.5577 | 69300000 | 69300000 | 2022 | A.L. SALAZAR CONSTRUCTION, INC. | 3345 | 2021 | 2022-11-28 | 04/12/2021 | 0 | 0 | 2022-11-27 |  | 1
2022 | National Capital Region | QUEZON CITY | QUEZON CITY (METROPOLITAN MANILA) | P00620445LZ | Construction of Revetment | 121.0191 | 14.6519 | 19600000 | 19013963 | 2022 | C.E.M. CONSTRUCTION, INC. | 3346 | 2022 | 2022-09-27 | 02/10/2022 | 586037 | 0 | 2022-08-07 |  | 51
2022 | National Capital Region | CALOOCAN CITY | CALOOCAN CITY (METROPOLITAN MANILA) | P00620399LZ | Construction of Flood Mitigation Structure | 121.0396 | 14.7298 | 45067205.88 | 43670120.16 | 2022 | IM CONSTRUCTION CORPORATION | 3347 | 2022 | 2022-11-28 | 02/08/2022 | 1397085.72 | 0 | 2023-01-02 | 35
2022 | Region III | BULACAN | BOCAUE (BULACAN) | P00639351LZ | Construction of Slope Protection Structure | 120.9721 | 14.7987 | 57899561.65 | 57899074.35 | 2023 | 729 CONSTRUCTION, INC. (FORMERLY 722 CONSTRUCTION, INC.) | 3348 | 2022 | 2023-01-27 | 04/04/2022 | 487.3 | 0 | 2023-01-27 | 0
2023 | Region IV-B | OCCIDENTAL MINDORO | CALINTAAN (OCCIDENTAL MINDORO) | P00726596LZ | Construction of Flood Mitigation Structure | 121.0193 | 12.5613 | 49215000 | 49213204.69 | 2023 | JELSIE CONSTRUCTION & SUPPLY | 3349 | 2023 | 2023-07-15 | 02/10/2023 | 1795.31 | 0 | 2023-08-22 | 38
2022 | Region IV-B | OCCIDENTAL MINDORO | CALINTAAN (OCCIDENTAL MINDORO) | P00630955LZ | Construction of Flood Mitigation Structure | 121.0401 | 12.5683 | 130274599.7 | 130274621.5 | 2022 | ST. GERRARD CONSTRUCTION GEN. CONTRACTOR & DEVELOPMENT CORP. (FORMERLY:ST. GERRARD CONSTRUCTION) | 3350 | 2022 | 2022-08-31 | 02/23/2022 | 0 | 21.8 | 2023-01-22 | 144
2022 | National Capital Region | MAKATI CITY | CITY OF MAKATI (METROPOLITAN MANILA) | P00637758LZ | Construction of Revetment | 121.0401 | 14.5672 | 49000000 | 48019963.25 | 2023 | STRONGLANE BUILDERS AND TRADING CORPORATION (FORMERLY: STRONGLANE CONSTRUCTION & TRADING) / RJM CONSTRUCTION AND DEV'T., INC. | 3351 | 2022 | 2023-03-16 | 03/22/2022 | 980036.75 | 0 | 2023-03-15 |  | 1
2023 | National Capital Region | MAKATI CITY | CITY OF MAKATI (METROPOLITAN MANILA) | P00725528LZ | Construction of Revetment | 121.0402 | 14.5667 | 66585000 | 66566424.62 | 2023 | AKN CONSTRUCTION CORPORATION | 3352 | 2023 | 2023-10-19 | 02/15/2023 | 18575.38 | 0 | 2023-10-18 |  | 1
2024 | National Capital Region | MAKATI CITY | CITY OF MAKATI (METROPOLITAN MANILA) | P00820049LZ | Construction of Flood Mitigation Facility | 121.0402 | 14.5675 | 48892690 | 48021877.09 | 2025 | QUATRIX CONSTRUCTION AND SUPPLY INC. | 3353 | 2024 | 2025-02-28 | 07/04/2024 | 870812.91 | 0 | 2025-02-27 |  | 1
2022 | National Capital Region | QUEZON CITY | QUEZON CITY (METROPOLITAN MANILA) | P00631044LZ | Rehabilitation / Major Repair of Drainage Structure | 121.0403 | 14.6578 | 14700000 | 14259000 | 2022 | VERDAX BUILDERS | 3354 | 2022 | 2022-09-11 | 02/14/2022 | 441000 | 0 | 2022-09-10 |  | 1
2023 | National Capital Region | SAN JUAN CITY | CITY OF SAN JUAN (METROPOLITAN MANILA) | P00726789LZ | Construction of Flood Mitigation Structure | 121.0403 | 14.5961 | 46418427.15 | 44096995.9 | 2024 | DARCY & ANNA BUILDERS & TRADING | 3355 | 2023 | 2024-02-12 | 03/22/2023 | 2321431.25 | 0 | 2024-01-23 |  | 20
2022 | National Capital Region | QUEZON CITY | QUEZON CITY (METROPOLITAN MANILA) | P00630925LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.0404 | 14.7169 | 75750125 | 73477621.25 | 2023 | LE BRON CONSTRUCTION | 3356 | 2022 | 2023-02-28 | 02/16/2022 | 2272503.75 | 0 | 2023-02-09 |  | 19
2022 | National Capital Region | CALOOCAN CITY | CALOOCAN CITY (METROPOLITAN MANILA) | P00620402LZ | Construction of Flood Mitigation Structure | 121.0073 | 14.7267 | 29399620.35 | 28752819.36 | 2022 | JAGONBUILD CONSTRUCTION CORP. (FOR. JAGON BUILDERS | 3357 | 2022 | 2022-12-26 | 02/08/2022 | 646800.99 | 0 | 2023-01-02 | 7
2024 | National Capital Region | MAKATI CITY | CITY OF MAKATI (METROPOLITAN MANILA) | P00823262LZ | Construction of Revetment | 121.0408 | 14.5636 | 48893655 | 48889975.99 | 2024 | RNN CONSTRUCTION CORPORATION (FORMERLY RNN CONSTRU / AKN CONSTRUCTION CORPORATION | 3358 | 2024 | 2024-06-20 | 02/20/2024 | 3679.01 | 0 | 2024-11-14 | 147
2024 | National Capital Region | QUEZON CITY | QUEZON CITY (METROPOLITAN MANILA) | P00839537LZ | Rehabilitation / Major Repair of Drainage Structure | 121.041 | 14.6306 | 29699842.38 | 29681398.6 | 2025 | WIZARD CONCRETE SOLUTIONS AND CONSTRUCTION CORPORATION (FORMERLY: WIZARD TRADING & CONSTRUCTION) | 3359 | 2024 | 2025-01-07 | 02/08/2024 | 18443.78 | 0 | 2025-01-06 |  | 1
2023 | National Capital Region | CALOOCAN CITY | CALOOCAN CITY (METROPOLITAN MANILA) | P00725546LZ | Construction of Flood Mitigation Structure | 121.0411 | 14.7709 | 69912555.11 | 68514284.13 | 2023 | AVE-MIRA CONSTRUCTION AND TRADING / ORANI CONSTRUCTION AND SUPPLY CORPORATION (FORMERLY:ORANI BUILDERS & SUPPLY) | 3360 | 2023 | 2023-10-16 | 02/21/2023 | 1398270.98 | 0 | 2024-01-15 | 91
2023 | National Capital Region | MAKATI CITY | CITY OF MAKATI (METROPOLITAN MANILA) | P00725530LZ | Construction of Revetment | 121.0411 | 14.5648 | 58571640 | 58565217.84 | 2023 | RNN CONSTRUCTION CORPORATION (FORMERLY RNN CONSTRU / AKN CONSTRUCTION CORPORATION | 3361 | 2023 | 2023-11-03 | 02/15/2023 | 6422.16 | 0 | 2023-11-02 |  | 1
2023 | Region IV-A | LAGUNA | CITY OF SAN PEDRO (LAGUNA) | P00727165LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.0411 | 14.3571 | 29400000 | 28606212 | 2024 | DATZLAV CONSTRUCTION | 3362 | 2023 | 2024-01-14 | 06/07/2023 | 793788 | 0 | 2024-01-13 |  | 1
2022 | Region III | BULACAN | CITY OF SAN JOSE DEL MONTE (BULACAN) | P00620162LZ | Construction of Flood Mitigation Structure | 121.0412 | 14.7844 | 94176929.31 | 94174761.35 | 2023 | ROYAL CROWN MONARCH CONSTRUCTION & SUPPLIES CORP. | 3363 | 2022 | 2023-03-11 | 03/07/2022 | 2167.96 | 0 | 2023-03-10 |  | 1
2024 | National Capital Region | PARAÃ‘AQUE CITY | CITY OF PARAÃ‘AQUE (METROPOLITAN MANILA) | P00820573LZ | Rehabilitation / Major Repair of Drainage Structure | 121.0412 | 14.5005 | 18655280 | 18655280 | 2025 | THE STEADFAST BUILDERS | 3364 | 2024 | 2025-02-02 | 09/06/2024 | 0 | 0 | 2025-02-01 |  | 1
2023 | National Capital Region | MAKATI CITY | CITY OF MAKATI (METROPOLITAN MANILA) | P00725529LZ | Construction of Revetment | 121.0413 | 14.566 | 66585000 | 66584998.99 | 2023 | AKN CONSTRUCTION CORPORATION | 3365 | 2023 | 2023-10-11 | 02/15/2023 | 1.01 | 0 | 2023-10-18 | 7
2023 | National Capital Region | SAN JUAN CITY | CITY OF SAN JUAN (METROPOLITAN MANILA) | P00726788LZ | Construction of Flood Mitigation Structure | 121.0413 | 14.602 | 96499931.38 | 91675968.42 | 2024 | WAWAO BUILDERS / DRJY CONSTRUCTION | 3366 | 2023 | 2024-03-24 | 03/22/2023 | 4823962.96 | 0 | 2024-01-14 |  | 70
2023 | National Capital Region | CALOOCAN CITY | CALOOCAN CITY (METROPOLITAN MANILA) | P00735955LZ | Construction of Flood Mitigation Structure | 121.0417 | 14.7698 | 81987797.59 | 79754179.55 | 2023 | MRB11 CONSTRUCTION CORPORATION (FORMERLY:MRB CONS | 3367 | 2023 | 2023-12-12 | 02/21/2023 | 2233618.04 | 0 | 2023-12-16 | 4
2022 | National Capital Region | MANDALUYONG CITY | CITY OF MANDALUYONG (METROPOLITAN MANILA) | P00620358LZ | Construction of Drainage Structure | 121.0419 | 14.5817 | 29399660.98 | 27918834.88 | 2023 | 5.J.B.P. PREMIUM CONSTRUCTION CORPORATION | 3368 | 2022 | 2023-01-30 | 02/08/2022 | 1480826.1 | 0 | 2022-12-03 |  | 58
2024 | National Capital Region | CALOOCAN CITY | CALOOCAN CITY (METROPOLITAN MANILA) | P00820041LZ | Construction of Flood Mitigation Structure | 121.042 | 14.769 | 86847956.29 | 85027887.13 | 2024 | AVE-MIRA CONSTRUCTION AND TRADING / ORANI CONSTRUCTION AND SUPPLY CORPORATION (FORMERLY:ORANI BUILDERS & SUPPLY) | 3369 | 2024 | 2024-10-09 | 02/14/2024 | 1820069.16 | 0 | 2024-10-09 | 0
2022 | Region III | BULACAN | CITY OF SAN JOSE DEL MONTE (BULACAN) | P00620166LZ | Construction of Flood Mitigation Structure | 121.0423 | 14.8306 | 94569696.41 | 94554016.97 | 2022 | TRIPLE 8 CONSTRUCTION & SUPPLY, INC. (FORMERLY TRIPLE 8 CONST. & SUPPLY) | 3370 | 2022 | 2022-12-12 | 03/07/2022 | 15679.44 | 0 | 2022-12-11 |  | 1
2022 | Region III | BULACAN | CITY OF SAN JOSE DEL MONTE (BULACAN) | P00620170LZ | Construction of Flood Mitigation Structure | 121.0423 | 14.8302 | 94087086.97 | 94070857.03 | 2022 | TRIPLE 8 CONSTRUCTION & SUPPLY, INC. (FORMERLY TRIPLE 8 CONST. & SUPPLY) | 3371 | 2022 | 2022-12-11 | 03/07/2022 | 16229.94 | 0 | 2022-12-10 |  | 1
2023 | National Capital Region | CALOOCAN CITY | CALOOCAN CITY (METROPOLITAN MANILA) | P00725554LZ | Construction of Flood Mitigation Structure | 121.0424 | 14.7454 | 91667904.39 | 89748679.99 | 2023 | PERSAN CONSTRUCTION, INC. (FORMERLY: PERSAN CONST. | 3372 | 2023 | 2023-12-19 | 02/21/2023 | 1919224.4 | 0 | 2024-01-15 | 27
2022 | Region IV-A | LAGUNA | CITY OF BIÃ‘AN (LAGUNA) | P00639493LZ | Construction of Revetment | 121.0425 | 14.2748 | 34300000 | 34278213.8 | 2023 | DATZLAV CONSTRUCTION | 3373 | 2022 | 2023-02-26 | 07/11/2022 | 21786.2 | 0 | 2023-02-25 |  | 1
2022 | Region IV-A | LAGUNA | CITY OF BIÃ‘AN (LAGUNA) | P00639494LZ | Construction of Revetment | 121.0428 | 14.2762 | 29400000 | 29377630.73 | 2023 | M.T. MALIUANAG CONSTRUCTION SERVICES | 3374 | 2022 | 2023-02-15 | 06/23/2022 | 22369.27 | 0 | 2023-03-09 | 22
2023 | Region IV-A | LAGUNA | CITY OF BIÃ‘AN (LAGUNA) | P00725823LZ | Construction of Flood Mitigation Structure | 121.0428 | 14.2747 | 96500000 | 96496542.37 | 2024 | M.T. MALIUANAG CONSTRUCTION SERVICES | 3375 | 2023 | 2024-03-04 | 08/09/2023 | 3457.63 | 0 | 2024-06-20 | 108
2024 | National Capital Region | QUEZON CITY | QUEZON CITY (METROPOLITAN MANILA) | P00820027LZ | Construction of Flood Mitigation Structure | 121.0429 | 14.7133 | 144749671.4 | 143273224.8 | 2024 | LE BRON CONSTRUCTION | 3376 | 2024 | 2024-11-18 | 03/18/2024 | 1476446.6 | 0 | 2025-03-11 | 113
2023 | National Capital Region | CALOOCAN CITY | CALOOCAN CITY (METROPOLITAN MANILA) | P00736166LZ | Construction of Drainage Structure | 121.043 | 14.7672 | 24499344.34 | 24003340.64 | 2023 | D.C. SANDIL CONSTRUCTION AND REALTY DEVELOPMENT, I | 3377 | 2023 | 2023-12-25 | 03/17/2023 | 496003.7 | 0 | 2023-12-10 |  | 15
2024 | National Capital Region | QUEZON CITY | QUEZON CITY (METROPOLITAN MANILA) | P00820625LZ | Construction of Flood Mitigation Structure | 121.043 | 14.7133 | 48999897.4 | 48416798.62 | 2024 | LE BRON CONSTRUCTION | 3378 | 2024 | 2024-11-18 | 02/06/2024 | 583098.78 | 0 | 2024-11-30 | 12
2024 | Region III | BULACAN | CITY OF SAN JOSE DEL MONTE (BULACAN) | P00844750LZ | Construction of Flood Mitigation Structure | 121.0433 | 14.808 | 19599500.5 | 19303548.04 | 2024 | 1199S CONSTRUCTION | 3379 | 2024 | 2024-10-14 | 04/30/2024 | 295952.46 | 0 | 2024-10-13 |  | 1
2023 | National Capital Region | CALOOCAN CITY | CALOOCAN CITY (METROPOLITAN MANILA) | P00725555LZ | Construction of Flood Mitigation Structure | 121.0434 | 14.7698 | 91667691.68 | 89183418.68 | 2023 | IM CONSTRUCTION CORPORATION | 3380 | 2023 | 2023-11-06 | 02/21/2023 | 2484273 | 0 | 2023-12-16 | 40
2022 | National Capital Region | MAKATI CITY | CITY OF MAKATI (METROPOLITAN MANILA) | P00632713LZ | Rehabilitation / Major Repair of Drainage Structure | 121.0435 | 14.56 | 9800000 | 9815215.1 | 2022 | ALEXA TRADING & CONSTRUCTION | 3381 | 2022 | 2022-09-06 | 02/09/2022 | 0 | 15215.1 | 2022-09-05 |  | 1
2022 | National Capital Region | MAKATI CITY | CITY OF MAKATI (METROPOLITAN MANILA) | P00620385LZ | Rehabilitation / Major Repair of Drainage Structure | 121.0435 | 14.5605 | 4900000 | 4880675.03 | 2022 | RNN CONSTRUCTION CORPORATION (FORMERLY RNN CONSTRU | 3382 | 2022 | 2022-08-18 | 03/22/2022 | 19324.97 | 0 | 2022-08-17 |  | 1
2024 | National Capital Region | TAGUIG CITY | TAGUIG CITY (METROPOLITAN MANILA) | P00821048LZ | Construction of Slope Protection Structure | 121.0436 | 14.5824 | 96499471.03 | 94550181.71 | 2024 | TOUGHBUILT CONSTRUCTION & TRADING, INC. | 3383 | 2024 | 2024-07-22 | 02/13/2024 | 1949289.32 | 0 | 2024-10-08 | 78
2022 | Region III | BULACAN | ANGAT (BULACAN) | P00631223LZ | Construction of Flood Mitigation Structure | 121.0436 | 14.9386 | 44099622.06 | 43434599.76 | 2022 | ALPHA & OMEGA GEN. CONTRACTOR & DEVELOPMENT CORP. | 3384 | 2022 | 2022-09-16 | 03/07/2022 | 665022.3 | 0 | 2022-09-15 |  | 1
2022 | National Capital Region | MAKATI CITY | CITY OF MAKATI (METROPOLITAN MANILA) | P00620387LZ | Rehabilitation / Major Repair of Drainage Structure | 121.0437 | 14.5612 | 24500000 | 24491201.47 | 2022 | ALEXA TRADING & CONSTRUCTION | 3385 | 2022 | 2022-10-18 | 02/15/2022 | 8798.53 | 0 | 2022-10-17 |  | 1
2023 | National Capital Region | CALOOCAN CITY | CALOOCAN CITY (METROPOLITAN MANILA) | P00725544LZ | Construction of Flood Mitigation Structure | 121.0439 | 14.7508 | 86845359.71 | 85195339.66 | 2024 | DARCY & ANNA BUILDERS & TRADING | 3386 | 2023 | 2024-02-08 | 03/17/2023 | 1650020.05 | 0 | 2024-02-08 | 0
2022 | National Capital Region | CALOOCAN CITY | CALOOCAN CITY (METROPOLITAN MANILA) | P00640454LZ | Construction of Flood Mitigation Structure | 121.0441 | 14.7698 | 96477685.35 | 93081552.75 | 2022 | MRB11 CONSTRUCTION CORPORATION (FORMERLY:MRB CONS | 3387 | 2022 | 2022-12-09 | 05/16/2022 | 3396132.6 | 0 | 2023-04-09 | 121
2024 | National Capital Region | PASIG CITY | CITY OF PASIG (METROPOLITAN MANILA) | P00820560LZ | Construction of Slope Protection Structure | 121.0441 | 14.5814 | 48999580.75 | 47992147.31 | 2024 | ELITE GENERAL CONTRACTOR AND DEVELOPMENT CORP. | 3388 | 2024 | 2024-12-26 | 04/01/2024 | 1007433.44 | 0 | 2024-12-25 |  | 1
2024 | National Capital Region | PASIG CITY | CITY OF PASIG (METROPOLITAN MANILA) | P00820561LZ | Construction of Slope Protection Structure | 121.0441 | 14.5811 | 48999807.68 | 47992369.6 | 2024 | ELITE GENERAL CONTRACTOR AND DEVELOPMENT CORP. | 3389 | 2024 | 2024-12-26 | 04/01/2024 | 1007438.08 | 0 | 2024-12-25 |  | 1
2022 | National Capital Region | CALOOCAN CITY | CALOOCAN CITY (METROPOLITAN MANILA) | P00620405LZ | Construction of Flood Mitigation Structure | 121.0443 | 14.7428 | 19598776.96 | 19187780.22 | 2022 | IM CONSTRUCTION CORPORATION | 3390 | 2022 | 2022-08-22 | 02/08/2022 | 410996.74 | 0 | 2022-10-04 | 43
2023 | Region II | NUEVA VIZCAYA | ARITAO (NUEVA VIZCAYA) | P00725663LZ | Construction of Flood Mitigation Structure | 121.0444 | 16.2581 | 96500000 | 96499461.23 | 2023 | AMP 723 CONSTRUCTION CORPORATION (FORMERLY: A.M.P. CONSTRUCTION) / KEVIN PAUL CONSTRUCTION | 3391 | 2023 | 2023-10-15 | 02/10/2023 | 538.77 | 0 | 2023-10-14 |  | 1
2023 | Region II | NUEVA VIZCAYA | ARITAO (NUEVA VIZCAYA) | P00727115LZ | Construction of Flood Mitigation Structure | 121.0447 | 16.2594 | 29125440 | 29123404.28 | 2023 | M.R. VARGAS CONSTRUCTION CORPORATION (FORMERLY: M.R. VARGAS CONSTRUCTION) | 3392 | 2023 | 2023-08-16 | 03/17/2023 | 2035.72 | 0 | 2023-09-10 | 25
2022 | Region IV-A | CAVITE | CITY OF CARMONA (CAVITE) | P00632881LZ | Construction of Drainage Structure | 121.0447 | 14.3049 | 39599727.15 | 7919708.15 | 2022 | TRIPLE 8 CONSTRUCTION & SUPPLY, INC. (FORMERLY TRIPLE 8 CONST. & SUPPLY) | 3393 | 2022 | 2022-08-15 | 02/17/2022 | 31680019 | 0 | 2022-08-14 |  | 1
2021 | National Capital Region | PARAÃ‘AQUE CITY |  | P00525776LZ | Construction of Flood Mitigation Structure | 121.045 | 14.4654 | 19600000 | 18915960 | 2022 | CALCON ENGINEERING | 3394 | 2021 | 2022-09-26 | 03/31/2021 | 684040 | 0 | 2022-09-25 |  | 1
2024 | Region III | BULACAN | NORZAGARAY (BULACAN) | P00839580LZ | Construction of Drainage Structure | 121.0451 | 14.9055 | 4939228.18 | 4865139.76 | 2024 | 1199S CONSTRUCTION | 3395 | 2024 | 2024-10-19 | 05/16/2024 | 74088.42 | 0 | 2024-10-18 |  | 1
2021 | Region IV-A | CAVITE |  | P00525625LZ | Construction of Revetment | 121.0453 | 14.3033 | 77199998.22 | 77199998.22 | 2022 | DMLC BUILDERS | 3396 | 2021 | 2022-10-17 | 03/08/2021 | 0 | 0 | 2022-10-16 |  | 1
2024 | Region IV-A | CAVITE | CITY OF CARMONA (CAVITE) | P00845832LZ | Construction of Revetment | 121.0455 | 14.3035 | 69299989.4 | 69298609.16 | 2025 | OMNICON BUILDERS | 3397 | 2024 | 2025-03-10 | 05/15/2024 | 1380.24 | 0 | 2025-04-16 | 37
2023 | Region IV-A | CAVITE | CITY OF CARMONA (CAVITE) | P00742429LZ | Construction of Slope Protection Structure | 121.0455 | 14.3035 | 89099975.39 | 89092693.05 | 2024 | AARCON BUILDERS | 3398 | 2023 | 2024-05-27 | 06/06/2023 | 7282.34 | 0 | 2024-05-26 |  | 1
2022 | National Capital Region | MUNTINLUPA CITY | CITY OF MUNTINLUPA (METROPOLITAN MANILA) | P00620903LZ | Construction of Flood Mitigation Structure | 121.0456 | 14.388 | 44393323.66 | 42618812.95 | 2022 | ALPHA & OMEGA GEN. CONTRACTOR & DEVELOPMENT CORP. | 3399 | 2022 | 2022-09-03 | 04/07/2022 | 1774510.71 | 0 | 2022-09-02 |  | 1
2021 | National Capital Region | MUNTINLUPA CITY |  | P00561206LZ | Construction of Drainage Structure | 121.0457 | 14.4191 | 9899186.02 | 9893831.88 | 2023 | AARCON BUILDERS | 3400 | 2021 | 2023-03-05 | 01/07/2022 | 5354.14 | 0 | 2023-03-04 |  | 1
2023 | Region III | BULACAN | CITY OF SAN JOSE DEL MONTE (BULACAN) | P00725716LZ | Construction of Flood Mitigation Structure | 121.0458 | 14.8169 | 96499620.51 | 96498963.65 | 2023 | M3 KONSTRACT CORPORATION (FORMERLY:MARGARITA CONSTRUCTION) | 3401 | 2023 | 2023-12-05 | 03/01/2023 | 656.86 | 0 | 2023-12-28 | 23
2023 | National Capital Region | MUNTINLUPA CITY | CITY OF MUNTINLUPA (METROPOLITAN MANILA) | P00725918LZ | Construction of Flood Mitigation Structure | 121.0461 | 14.4263 | 48999732.17 | 48989140.74 | 2023 | L.M.G. CONSTRUCTION INCORPORATED (FORMERLY: LMG CONSTRUCTION) | 3402 | 2023 | 2023-09-10 | 02/13/2023 | 10591.43 | 0 | 2023-09-09 |  | 1
2021 | National Capital Region | QUEZON CITY |  | P00561615LZ | Rehabilitation / Major Repair of Drainage Structure | 121.0462 | 14.6201 | 7919908.35 | 7914730.27 | 2022 | TWO DIMENSION CONSTRUCTION | 3403 | 2021 | 2022-07-07 | 11/10/2021 | 5178.08 | 0 | 2022-07-06 |  | 1
2022 | Region IV-A | LAGUNA | CITY OF BIÃ‘AN (LAGUNA) | P00620223LZ | Construction of Revetment | 121.0463 | 14.2814 | 96500000 | 96498600.2 | 2022 | MAR-VEL CONSTRUCTION & SUPPLY | 3404 | 2022 | 2022-12-05 | 03/09/2022 | 1399.8 | 0 | 2023-02-16 | 73
2022 | National Capital Region | QUEZON CITY | QUEZON CITY (METROPOLITAN MANILA) | P00631042LZ | Construction of Flood Mitigation Structure | 121.0463 | 14.6653 | 14700000 | 14259000 | 2022 | PILASTRO BUILDERS & DEVELOPMENT INC. | 3405 | 2022 | 2022-07-20 | 02/24/2022 | 441000 | 0 | 2022-10-20 | 92
2023 | Region II | NUEVA VIZCAYA | ARITAO (NUEVA VIZCAYA) | P00725666LZ | Construction of Flood Mitigation Structure | 121.0464 | 16.2553 | 48250000 | 48239429.45 | 2023 | AMP 723 CONSTRUCTION CORPORATION (FORMERLY: A.M.P. CONSTRUCTION) | 3406 | 2023 | 2023-08-27 | 02/10/2023 | 10570.55 | 0 | 2023-08-26 |  | 1
2023 | Region IV-A | LAGUNA | CITY OF SANTA ROSA (LAGUNA) | P00737524LZ | Construction of Slope Protection Structure | 121.0466 | 14.2284 | 9900000 | 9899592.24 | 2023 | LE BRON CONSTRUCTION | 3407 | 2023 | 2023-09-22 | 08/09/2023 | 407.76 | 0 | 2024-01-28 | 128
2023 | National Capital Region | QUEZON CITY | QUEZON CITY (METROPOLITAN MANILA) | P00736171LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.0467 | 14.723 | 48999625.86 | 48996288.55 | 2023 | FRAMECON BUILDERS | 3408 | 2023 | 2023-11-24 | 02/14/2023 | 3337.31 | 0 | 2023-12-09 | 15
2023 | National Capital Region | QUEZON CITY | QUEZON CITY (METROPOLITAN MANILA) | P00742248LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.0467 | 14.723 | 49499920.6 | 49499890.92 | 2023 | LE BRON CONSTRUCTION | 3409 | 2023 | 2023-12-18 | 04/05/2023 | 29.68 | 0 | 2024-01-28 | 41
2022 | Region III | BULACAN | CITY OF SAN JOSE DEL MONTE (BULACAN) | P00637027LZ | Construction of Flood Mitigation Structure | 121.047 | 14.7867 | 96499616.33 | 96496179.81 | 2023 | ROYAL CROWN MONARCH CONSTRUCTION & SUPPLIES CORP. | 3410 | 2022 | 2023-03-08 | 03/30/2022 | 3436.52 | 0 | 2023-03-07 |  | 1
2022 | National Capital Region | MAKATI CITY | CITY OF MAKATI (METROPOLITAN MANILA) | P00620388LZ | Rehabilitation / Major Repair of Drainage Structure | 121.0471 | 14.556 | 29400000 | 29400000 | 2022 | QUATRIX CONSTRUCTION AND SUPPLY INC. | 3411 | 2022 | 2022-07-08 | 02/09/2022 | 0 | 0 | 2022-07-07 |  | 1
2022 | National Capital Region | MUNTINLUPA CITY | CITY OF LAS PIÃ‘AS (METROPOLITAN MANILA) | P00632701LZ | Construction of Drainage Structure | 121.0471 | 14.399 | 14699980.22 | 14698980.22 | 2022 | RFSM CONSTRUCTION CORPORATION | 3412 | 2022 | 2022-12-18 | 03/04/2022 | 1000 | 0 | 2022-12-17 |  | 1
2022 | National Capital Region | MUNTINLUPA CITY | CITY OF MUNTINLUPA (METROPOLITAN MANILA) | P00637755LZ | Construction of Drainage Structure | 121.0475 | 14.3989 | 18129068.7 | 18120439.12 | 2023 | KPSL GENERAL CONTRACTOR INC. | 3413 | 2022 | 2023-05-03 | 07/08/2022 | 8629.58 | 0 | 2023-05-02 |  | 1
2021 | Cordillera Administrative Region | APAYAO |  | P00526268LZ | Construction of Flood Mitigation Structure | 121.0476 | 18.2509 | 96500000 | 92692943.8 | 2022 | ASC CONSTRUCTION & CONCRETE PRODUCTS | 3414 | 2021 | 2022-10-03 | 03/18/2021 | 3807056.2 | 0 | 2022-01-25 |  | 251
2023 | National Capital Region | MUNTINLUPA CITY | CITY OF MUNTINLUPA (METROPOLITAN MANILA) | P00725550LZ | Construction of Flood Mitigation Structure | 121.0476 | 14.4272 | 82024778.8 | 81889353.83 | 2023 | TRIPLE 8 CONSTRUCTION & SUPPLY, INC. (FORMERLY TRIPLE 8 CONST. & SUPPLY) / PILASTRO BUILDERS & DEVELOPMENT INC. | 3415 | 2023 | 2023-11-09 | 02/13/2023 | 135424.97 | 0 | 2023-11-08 |  | 1
2023 | National Capital Region | QUEZON CITY | QUEZON CITY (METROPOLITAN MANILA) | P00736172LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.048 | 14.7027 | 29399752.98 | 29399256.06 | 2023 | E.L. TORRES CONSTRUCTION AND TRADING INC. (FORMERLY : E. L. TORRES CONSTRUCTION & TRADING | 3416 | 2023 | 2023-11-24 | 02/14/2023 | 496.92 | 0 | 2023-12-09 | 15
2024 | Region III | BULACAN | NORZAGARAY (BULACAN) | P00821582LZ | Construction of Flood Mitigation Structure | 121.048 | 14.9211 | 48249920.64 | 48249967.43 | 2024 | SYMS CONSTRUCTION TRADING | 3417 | 2024 | 2024-11-04 | 04/08/2024 | 0 | 46.79 | 2024-11-03 |  | 1
2022 | National Capital Region | QUEZON CITY | QUEZON CITY (METROPOLITAN MANILA) | P00631039LZ | Construction of Flood Mitigation Structure | 121.0482 | 14.675 | 19600000 | 19006235 | 2022 | NUEDA BUILDERS CONSTRUCTION & SUPPLY INC. | 3418 | 2022 | 2022-10-05 | 03/22/2022 | 593765 | 0 | 2022-11-15 | 41
2022 | National Capital Region | CALOOCAN CITY | CALOOCAN CITY (METROPOLITAN MANILA) | P00620397LZ | Construction of Flood Mitigation Structure | 121.0483 | 14.7673 | 45065477.4 | 43668317.29 | 2022 | PERSAN CONSTRUCTION, INC. (FORMERLY: PERSAN CONST. | 3419 | 2022 | 2022-08-22 | 02/08/2022 | 1397160.11 | 0 | 2023-01-02 | 133
2023 | Region III | BULACAN | CITY OF SAN JOSE DEL MONTE (BULACAN) | P00725719LZ | Construction of Flood Mitigation Structure | 121.0483 | 14.8152 | 96499224.52 | 96497614.18 | 2023 | M3 KONSTRACT CORPORATION (FORMERLY:MARGARITA CONSTRUCTION) | 3420 | 2023 | 2023-12-05 | 03/01/2023 | 1610.34 | 0 | 2023-12-28 | 23
2023 | Region III | BULACAN | CITY OF SAN JOSE DEL MONTE (BULACAN) | P00725723LZ | Construction of Flood Mitigation Structure | 121.0483 | 14.8434 | 96499786.46 | 96493479.41 | 2024 | FLORDES CONSTRUCTION & TRADING CORP. (FORMERLY FLO | 3421 | 2023 | 2024-02-23 | 04/24/2023 | 6307.05 | 0 | 2024-02-22 |  | 1
2023 | National Capital Region | QUEZON CITY | QUEZON CITY (METROPOLITAN MANILA) | P00726019LZ | Construction of Flood Mitigation Structure | 121.0484 | 14.6791 | 48999999.5 | 48998190.05 | 2023 | A.J. LAVA BUILDERS CORP. (FORMERLY: A.J. LAVA BUIL | 3422 | 2023 | 2023-10-18 | 02/27/2023 | 1809.45 | 0 | 2024-01-21 | 95
2024 | National Capital Region | CALOOCAN CITY | CALOOCAN CITY (METROPOLITAN MANILA) | P00820602LZ | Construction of Flood Mitigation Structure | 121.0487 | 14.7646 | 29399212.6 | 28873493.58 | 2024 | PERSAN CONSTRUCTION, INC. (FORMERLY: PERSAN CONST. | 3423 | 2024 | 2024-05-27 | 02/14/2024 | 525719.02 | 0 | 2024-08-10 | 75
2024 | Region III | BULACAN | CITY OF SAN JOSE DEL MONTE (BULACAN) | P00820230LZ | Construction of Flood Mitigation Structure | 121.0487 | 14.8149 | 96499521.49 | 96495776.49 | 2024 | M3 KONSTRACT CORPORATION (FORMERLY:MARGARITA CONSTRUCTION) | 3424 | 2024 | 2024-11-18 | 02/22/2024 | 3745 | 0 | 2024-12-12 | 24
2024 | National Capital Region | QUEZON CITY | QUEZON CITY (METROPOLITAN MANILA) | P00824615LZ | Construction of Drainage Structure | 121.0074 | 14.6719 | 11759980.38 | 11759532.63 | 2024 | E.I. VILLACORTE CONSTRUCTION | 3425 | 2024 | 2024-06-17 | 02/23/2024 | 447.75 | 0 | 2024-06-20 | 3
2023 | National Capital Region | NAVOTAS CITY | CITY OF NAVOTAS (METROPOLITAN MANILA) | P00726992LZ | Construction of Flood Mitigation Facility | 120.9578 | 14.646 | 23271437.1 | 23274381.97 | 2023 | EARTHWORK BUILDERS, INC. (FORMERLY: EARTHWORK MOVERS) | 3426 | 2023 | 2023-12-27 | 03/08/2023 | 0 | 2944.87 | 2023-12-26 |  | 1
2024 | Region III | BULACAN | NORZAGARAY (BULACAN) | P00823483LZ | Construction of Flood Mitigation Structure | 121.0503 | 14.909 | 43424461.05 | 43424968.82 | 2024 | JB CONSTRUCTION AND SUPPLY INC. (FORMERLY:JB CONSTRUCTION AND SUPPLY) | 3427 | 2024 | 2024-09-29 | 03/11/2024 | 0 | 507.77 | 2024-09-28 |  | 1
2021 | Region IV-A | LAGUNA |  | P00561773LZ | Construction of Revetment | 121.0193 | 14.3529 | 39600000 | 39456327.49 | 2022 | ST. GERRARD CONSTRUCTION GEN. CONTRACTOR & DEVELOPMENT CORP. (FORMERLY:ST. GERRARD CONSTRUCTION) | 3428 | 2021 | 2022-08-09 | 12/07/2021 | 143672.51 | 0 | 2022-08-08 |  | 1
2022 | National Capital Region | MUNTINLUPA CITY | CITY OF MUNTINLUPA (METROPOLITAN MANILA) | P00620914LZ | Construction of Flood Mitigation Structure | 121.0504 | 14.4454 | 9799483.95 | 9794372.22 | 2023 | RNN CONSTRUCTION CORPORATION (FORMERLY RNN CONSTRU | 3429 | 2022 | 2023-07-07 | 02/09/2022 | 5111.73 | 0 | 2023-07-06 |  | 1
2021 | Region IV-A | CAVITE |  | P00561596LZ | Construction of Revetment | 120.9958 | 14.4052 | 98999990.91 | 98990072.01 | 2022 | GRAIA CONSTRUCTION CORPORATION | 3430 | 2021 | 2022-07-22 | 10/11/2021 | 9918.9 | 0 | 2022-07-21 |  | 1
2024 | National Capital Region | PARAÃ‘AQUE CITY | CITY OF PARAÃ‘AQUE (METROPOLITAN MANILA) | P00844676LZ | Construction of Revetment | 121.0251 | 14.4526 | 29400000 | 29365844.46 | 2024 | RNN CONSTRUCTION CORPORATION (FORMERLY RNN CONSTRU | 3431 | 2024 | 2024-08-16 | 05/09/2024 | 34155.54 | 0 | 2024-10-04 | 49
2022 | National Capital Region | LAS PIÃ‘AS CITY | CITY OF LAS PIÃ‘AS (METROPOLITAN MANILA) | P00631008LZ | Rehabilitation / Major Repair of Drainage Structure | 121.0075 | 14.4366 | 9799999.59 | 9309688.71 | 2022 | MRJR CONSTRUCTION & TRADING | 3432 | 2022 | 2022-09-23 | 05/27/2022 | 490310.88 | 0 | 2022-09-22 |  | 1
2022 | National Capital Region | QUEZON CITY | QUEZON CITY (METROPOLITAN MANILA) | P00620449LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.0193 | 14.6185 | 43119992.18 | 43077774.26 | 2022 | M.S. RAMOS CONSTRUCTION INC. (FORMERLY: M.S. RAMOS | 3433 | 2022 | 2022-11-21 | 03/23/2022 | 42217.92 | 0 | 2022-12-01 | 10
2024 | Region III | BULACAN | SANTA MARIA (BULACAN) | P00838343LZ | Construction of Flood Mitigation Structure | 120.9959 | 14.8759 | 97999943.54 | 96499990.88 | 2024 | L.R. TIQUI BUILDERS, INC. | 3434 | 2024 | 2024-12-12 | 02/22/2024 | 1499952.66 | 0 | 2024-12-11 |  | 1
2021 | Region IV-A | BATANGAS |  | P00561749LZ | Construction of Flood Mitigation Structure | 121.0504 | 13.7945 | 2970000 | 2970000 | 2022 | GREENFIELD CONSTRUCTION | 3435 | 2021 | 2022-07-20 | 03/29/2022 | 0 | 0 | 2022-07-19 |  | 1
2023 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00727027LZ | Construction of Flood Mitigation Structure | 121.0193 | 14.5908 | 48999801.63 | 48999399.5 | 2024 | EIGHT J'S CONSTRUCTION SERVICES | 3436 | 2023 | 2024-02-25 | 03/01/2023 | 402.13 | 0 | 2024-02-24 |  | 1
2023 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00737402LZ | Rehabilitation / Major Repair of Drainage Structure | 120.9724 | 14.623 | 4948173.3 | 4947371.32 | 2023 | DENNREY CONSTRUCTION AND TRADING COMPANY | 3437 | 2023 | 2023-06-20 | 03/08/2023 | 801.98 | 0 | 2023-06-19 |  | 1
2023 | Region III | BULACAN | CITY OF MEYCAUAYAN (BULACAN) | P00726726LZ | Construction of Flood Mitigation Structure | 120.9579 | 14.7219 | 48998969.45 | 48997172.39 | 2023 | JB CONSTRUCTION AND SUPPLY INC. (FORMERLY:JB CONSTRUCTION AND SUPPLY) | 3438 | 2023 | 2023-07-11 | 02/22/2023 | 1797.06 | 0 | 2023-08-11 | 31
2023 | Cordillera Administrative Region | IFUGAO | TINOC (IFUGAO) | P00727096LZ | Construction of Flood Mitigation Structure | 120.9725 | 16.6354 | 32505326.94 | 32009050 | 2024 | DJY CONSTRUCTION / BEGAL DESIGN & CONSTRUCTION | 3439 | 2023 | 2024-01-19 | 07/03/2023 | 496276.94 | 0 | 2024-01-18 |  | 1
2024 | Region III | BULACAN | CITY OF SAN JOSE DEL MONTE (BULACAN) | P00820202LZ | Construction of Flood Mitigation Structure | 121.0504 | 14.81 | 96499453.25 | 96495673.58 | 2024 | M3 KONSTRACT CORPORATION (FORMERLY:MARGARITA CONSTRUCTION) | 3440 | 2024 | 2024-11-18 | 02/22/2024 | 3779.67 | 0 | 2024-12-12 | 24
2024 | Region II | NUEVA VIZCAYA | BAMBANG (NUEVA VIZCAYA) | P00820790LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.0252 | 16.3695 | 49000000 | 49000000 | 2024 | V.B. MANUBAY CONSTRUCTION | 3441 | 2024 | 2024-10-03 | 02/16/2024 | 0 | 0 | 2024-10-02 |  | 1
2024 | National Capital Region | PASAY CITY | PASAY CITY (METROPOLITAN MANILA) | P00820018LZ | Construction of Flood Mitigation Structure | 120.9959 | 14.5468 | 89171966.73 | 89071419.94 | 2024 | AMETHYST HORIZON BUILDERS AND GEN. CONTRACTOR AND DEVELOPMENT CORP. | 3442 | 2024 | 2024-10-22 | 02/21/2024 | 100546.79 | 0 | 2024-11-14 | 23
2023 | Region III | NUEVA ECIJA | LLANERA (NUEVA ECIJA) | P00726169LZ | Construction of Flood Mitigation Structure | 121.0077 | 15.7343 | 49000000 | 48016684.03 | 2023 | SPECO BUILDERS INC. (FORMERLY VRF CONSTRUCTION) | 3443 | 2023 | 2023-04-15 | 02/15/2023 | 983315.97 | 0 | 2023-09-11 | 149
2022 | National Capital Region | QUEZON CITY | QUEZON CITY (METROPOLITAN MANILA) | P00620450LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.0194 | 14.6184 | 43119555.59 | 43119548.85 | 2022 | MARCBILT CONSTRUCTION, INC. | 3444 | 2022 | 2022-11-10 | 03/23/2022 | 6.74 | 0 | 2022-12-01 | 21
2023 | Region IV-A | CAVITE | BACOOR CITY (CAVITE) | P00742174LZ | Construction of Flood Mitigation Structure | 121.0079 | 14.3828 | 59400000 | 59390310.24 | 2024 | E. F. CHUA CONSTRUCTION, INC. | 3445 | 2023 | 2024-02-14 | 07/17/2023 | 9689.76 | 0 | 2024-02-25 | 11
2023 | National Capital Region | QUEZON CITY | QUEZON CITY (METROPOLITAN MANILA) | P00742247LZ | Construction of Flood Mitigation Structure | 121.0505 | 14.6737 | 9899998.75 | 9701998.78 | 2023 | REND ENTERPRISES & GENERAL CONTRACTOR | 3446 | 2023 | 2023-07-21 | 03/21/2023 | 197999.97 | 0 | 2023-09-15 | 56
2024 | National Capital Region | PARAÃ‘AQUE CITY | CITY OF PARAÃ‘AQUE (METROPOLITAN MANILA) | P00844677LZ | Construction of Revetment | 121.0252 | 14.4526 | 29400000 | 29399812.65 | 2024 | RNN CONSTRUCTION CORPORATION (FORMERLY RNN CONSTRU | 3447 | 2024 | 2024-08-19 | 03/27/2024 | 187.35 | 0 | 2024-09-17 | 29
2022 | Region IV-A | CAVITE | BACOOR CITY (CAVITE) | P00640460LZ | Construction of Revetment | 120.9582 | 14.4651 | 98999990.55 | 98999347.53 | 2023 | GRAIA CONSTRUCTION CORPORATION | 3448 | 2022 | 2023-12-07 | 04/07/2022 | 643.02 | 0 | 2024-05-15 | 160
2023 | Region II | NUEVA VIZCAYA | ARITAO (NUEVA VIZCAYA) | P00740575LZ | Construction of Flood Mitigation Structure | 121.0253 | 16.2808 | 24271200 | 24269077.07 | 2023 | BIG G BUILDERS | 3449 | 2023 | 2023-09-09 | 03/23/2023 | 2122.93 | 0 | 2023-09-08 |  | 1
2023 | Region IV-A | LAGUNA | CITY OF SAN PEDRO (LAGUNA) | P00742438LZ | Construction of Drainage Structure | 121.0253 | 14.3311 | 4950000 | 4944333.6 | 2023 | JA.VI CONSTRUCTION | 3450 | 2023 | 2023-08-02 | 04/05/2023 | 5666.4 | 0 | 2023-08-01 |  | 1
2022 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00620419LZ | Construction of Flood Mitigation Structure | 120.9725 | 14.6187 | 48999790.29 | 48978202.54 | 2022 | 1HB CONSTRUCTION CORP. (FORMERLY: HB CONSTRUCTION) / DAHL CONSTRUCTION CORP. (FORMERLY: DAHL CONSTRUCTION) | 3451 | 2022 | 2022-09-25 | 02/28/2022 | 21587.75 | 0 | 2022-09-24 |  | 1
2022 | National Capital Region | QUEZON CITY | QUEZON CITY (METROPOLITAN MANILA) | P00637004LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.0194 | 14.6184 | 24124338 | 23180635.76 | 2023 | R2CG BUILDERS INC. (FORMERLY: RRCG 8639 BUILDERS INC.) | 3452 | 2022 | 2023-02-11 | 05/18/2022 | 943702.24 | 0 | 2023-02-10 |  | 1
2023 | National Capital Region | MALABON CITY | CITY OF MALABON (METROPOLITAN MANILA) | P00742226LZ | Construction of Drainage Structure | 120.9582 | 14.6559 | 29696346.9 | 29699974.49 | 2023 | IM CONSTRUCTION CORPORATION | 3453 | 2023 | 2023-12-13 | 03/27/2023 | 0 | 3627.59 | 2023-12-12 |  | 1
2021 | Region II | NUEVA VIZCAYA |  | P00561525LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.0255 | 16.3696 | 49000000 | 49000000 | 2022 | SHANLEY CONSTRUCTION / ALPHA & OMEGA GEN. CONTRACTOR & DEVELOPMENT CORP. | 3454 | 2021 | 2022-12-20 | 01/12/2022 | 0 | 0 | 2023-02-03 | 45
2023 | National Capital Region | CALOOCAN CITY | CALOOCAN CITY (METROPOLITAN MANILA) | P00725978LZ | Construction of Flood Mitigation Structure | 121.0505 | 14.7662 | 29398817.05 | 28901500.48 | 2024 | PERSAN CONSTRUCTION, INC. (FORMERLY: PERSAN CONST. | 3455 | 2023 | 2024-01-09 | 03/17/2023 | 497316.57 | 0 | 2024-01-09 | 0
2024 | National Capital Region | VALENZUELA CITY | CITY OF VALENZUELA (METROPOLITAN MANILA) | P00820582LZ | Construction of Drainage Structure | 120.996 | 14.6891 | 9786277.08 | 9453521.74 | 2024 | GILTOP CIVIL ENGINEERING CONSTRUCTION | 3456 | 2024 | 2024-08-19 | 02/14/2024 | 332755.34 | 0 | 2024-10-09 | 51
2023 | National Capital Region | PASAY CITY | PASAY CITY (METROPOLITAN MANILA) | P00742249LZ | Rehabilitation / Major Repair of Drainage Structure | 121.0079 | 14.5386 | 5939840.7 | 5791218.01 | 2023 | CAANA CONSTRUCTION CORPORATION | 3457 | 2023 | 2023-06-14 | 04/11/2023 | 148622.69 | 0 | 2023-06-23 | 9
2022 | National Capital Region | QUEZON CITY | QUEZON CITY (METROPOLITAN MANILA) | P00620451LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.0196 | 14.6181 | 43119378.09 | 43100448.71 | 2022 | WAWAO BUILDERS | 3458 | 2022 | 2022-11-24 | 03/23/2022 | 18929.38 | 0 | 2022-12-01 | 7
2022 | Region IV-A | CAVITE | SILANG (CAVITE) | P00639490LZ | Construction of Drainage Structure | 120.9582 | 14.24 | 19599797.32 | 4899933.27 | 2022 | TCSC CORP. | 3459 | 2022 | 2022-10-17 | 04/11/2022 | 14699864.05 | 0 | 2022-10-16 |  | 1
2024 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00820090LZ | Construction of Flood Mitigation Facility | 120.9727 | 14.6029 | 144749815.2 | 144723988.9 | 2024 | JJPR CONSTRUCTION SERVICES | 3460 | 2024 | 2024-04-17 | 02/08/2024 | 25826.3 | 0 | 2024-07-05 | 79
2023 | National Capital Region | PARAÃ‘AQUE CITY | CITY OF PARAÃ‘AQUE (METROPOLITAN MANILA) | P00726826LZ | Construction of Flood Mitigation Structure | 121.008 | 14.4695 | 96500000 | 96499846.05 | 2024 | PRECIOUS CONSTRUCTION / KIMCON CONSTRUCTION AND SUPPLY | 3461 | 2023 | 2024-02-20 | 04/27/2023 | 153.95 | 0 | 2024-04-19 | 59
2024 | National Capital Region | PASAY CITY | PASAY CITY (METROPOLITAN MANILA) | P00843177LZ | Rehabilitation / Major Repair of Drainage Structure | 121.0256 | 14.5213 | 96499998.21 | 96393504.48 | 2024 | FS CO BUILDERS AND SUPPLY | 3462 | 2024 | 2024-12-02 | 05/06/2024 | 106493.73 | 0 | 2025-01-29 | 58
2022 | National Capital Region | QUEZON CITY | QUEZON CITY (METROPOLITAN MANILA) | P00637002LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.0196 | 14.6181 | 28949502.01 | 27810536.88 | 2023 | R2CG BUILDERS INC. (FORMERLY: RRCG 8639 BUILDERS INC.) | 3463 | 2022 | 2023-02-11 | 05/18/2022 | 1138965.13 | 0 | 2023-02-10 |  | 1
2024 | Region III | BULACAN | NORZAGARAY (BULACAN) | P00823482LZ | Construction of Flood Mitigation Structure | 121.0506 | 14.9105 | 42525304.62 | 42525565 | 2024 | JB CONSTRUCTION AND SUPPLY INC. (FORMERLY:JB CONSTRUCTION AND SUPPLY) | 3464 | 2024 | 2024-09-28 | 03/11/2024 | 0 | 260.38 | 2024-09-27 |  | 1
2022 | National Capital Region | LAS PIÃ‘AS CITY | CITY OF LAS PIÃ‘AS (METROPOLITAN MANILA) | P00620057LZ | Construction of Slope Protection Structure | 120.9965 | 14.4176 | 67549782.47 | 67449782.47 | 2022 | I&E CONSTRUCTION CORPORATION (FORMERLY: I&E CONSTR | 3465 | 2022 | 2022-09-14 | 02/17/2022 | 100000 | 0 | 2022-09-13 |  | 1
2024 | Region IV-A | LAGUNA | CITY OF SAN PEDRO (LAGUNA) | P00820896LZ | Construction of Flood Mitigation Structure | 121.0506 | 14.3615 | 29400000 | 28719279.7 | 2024 | D.T. RECIO INCORPORATED | 3466 | 2024 | 2024-09-06 | 03/04/2024 | 680720.3 | 0 | 2024-09-19 | 13
2024 | National Capital Region | PASAY CITY | PASAY CITY (METROPOLITAN MANILA) | P00843173LZ | Construction of Flood Mitigation Structure | 121.0198 | 14.5291 | 96499999.79 | 96395644.88 | 2024 | HI-TONE CONSTRUCTION & DEVELOPMENT CORP. (FORMERLY / FS CO BUILDERS AND SUPPLY | 3467 | 2024 | 2024-11-19 | 05/06/2024 | 104354.91 | 0 | 2025-01-29 | 71
2024 | Region III | NUEVA ECIJA | LLANERA (NUEVA ECIJA) | P00823450LZ | Construction of Flood Mitigation Structure | 121.0082 | 15.7451 | 48250000 | 47767474.68 | 2024 | ADROIT EJD CONSTRUCTION CORP. (FORMERLY: ADROIT CONSTRUCTION) | 3468 | 2024 | 2024-09-16 | 03/13/2024 | 482525.32 | 0 | 2024-10-07 | 21
2024 | National Capital Region | CALOOCAN CITY | CALOOCAN CITY (METROPOLITAN MANILA) | P00820600LZ | Construction of Flood Mitigation Structure | 121.0256 | 14.73 | 29399160.51 | 28753954.6 | 2024 | PERSAN CONSTRUCTION, INC. (FORMERLY: PERSAN CONST. | 3469 | 2024 | 2024-06-24 | 02/14/2024 | 645205.91 | 0 | 2024-07-11 | 17
2023 | National Capital Region | NAVOTAS CITY | CITY OF NAVOTAS (METROPOLITAN MANILA) | P00726993LZ | Construction of Flood Mitigation Facility | 120.9582 | 14.6464 | 23268117.35 | 23272181.36 | 2023 | 721 BUILDERS CORPORATION | 3470 | 2023 | 2023-11-02 | 03/08/2023 | 0 | 4064.01 | 2023-11-01 |  | 1
2024 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00823248LZ | Construction of Flood Mitigation Facility | 120.9727 | 14.6029 | 144749982.3 | 144066590.1 | 2024 | JJPR CONSTRUCTION SERVICES | 3471 | 2024 | 2024-06-07 | 02/13/2024 | 683392.2 | 0 | 2024-07-10 | 33
2024 | Region III | NUEVA ECIJA | CABANATUAN CITY (NUEVA ECIJA) | P00843300LZ | Construction of Flood Mitigation Structure | 120.9583 | 15.5219 | 77199905.27 | 75650574.13 | 2024 | FRAMECON BUILDERS | 3472 | 2024 | 2024-09-20 | 03/25/2024 | 1549331.14 | 0 | 2025-01-17 | 119
2023 | Region IV-A | BATANGAS | BATANGAS CITY (CAPITAL) (BATANGAS) | P00726200LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.0506 | 13.7737 | 41795040 | 41795040 | 2023 | TRISTAN TEJADA CONSTRUCTION (FORMERLY: JOMATRIS CO | 3473 | 2023 | 2023-09-16 | 02/10/2023 | 0 | 0 | 2023-09-15 |  | 1
2022 | Cordillera Administrative Region | MOUNTAIN PROVINCE | BONTOC (CAPITAL) (MOUNTAIN PROVINCE) | P00621007LZ | Construction of Flood Mitigation Structure | 121.0084 | 17.047 | 15679999.6 | 15680000 | 2022 | DHEN'Z CONSTRUCTION | 3474 | 2022 | 2022-11-18 | 03/07/2022 | 0 | 0.4 | 2022-09-29 |  | 50
2024 | National Capital Region | PASAY CITY | PASAY CITY (METROPOLITAN MANILA) | P00843178LZ | Rehabilitation / Major Repair of Drainage Structure | 121.0262 | 14.521 | 96499998.29 | 96399674.94 | 2025 | HI-TONE CONSTRUCTION & DEVELOPMENT CORP. (FORMERLY / FS CO BUILDERS AND SUPPLY | 3475 | 2024 | 2025-01-30 | 05/06/2024 | 100323.35 | 0 | 2025-01-29 |  | 1
2024 | National Capital Region | PARAÃ‘AQUE CITY | CITY OF PARAÃ‘AQUE (METROPOLITAN MANILA) | P00820576LZ | Rehabilitation / Major Repair of Drainage Structure | 121.0085 | 14.4686 | 19600000 | 19599817.96 | 2024 | G.F. ROVERO MERCHANDISING | 3476 | 2024 | 2024-06-21 | 02/14/2024 | 182.04 | 0 | 2024-07-21 | 30
2022 | Region III | BULACAN | SAN MIGUEL (BULACAN) | P00639342LZ | Construction of Flood Mitigation Structure | 120.9965 | 15.2281 | 96499526.39 | 96497418.82 | 2023 | L.R. TIQUI BUILDERS, INC. | 3477 | 2022 | 2023-04-18 | 03/30/2022 | 2107.57 | 0 | 2023-06-22 | 65
2022 | National Capital Region | VALENZUELA CITY | CITY OF VALENZUELA (METROPOLITAN MANILA) | P00637044LZ | Construction of Flood Mitigation Structure | 120.9585 | 14.6935 | 8817924.43 | 8553377.26 | 2022 | TOUGHBUILT CONSTRUCTION & TRADING, INC. | 3478 | 2022 | 2022-11-16 | 03/24/2022 | 264547.17 | 0 | 2022-11-17 | 1
2025 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00920010LZ | Construction of Flood Mitigation Facility | 120.9727 | 14.6029 | 96499677.39 | 94714433.36 | 2025 | EIGHT J'S CONSTRUCTION SERVICES / 4 J'S CONSTRUCTION SERVICES | 3479 | 2025 | 2025-05-21 | 02/11/2025 | 1785244.03 | 0 | 2025-05-20 |  | 1
2021 | Region III | BULACAN |  | P00525608LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.0198 | 15.2397 | 67549918.2 | 64847873.01 | 2022 | STO. CRISTO CONSTRUCTION & TRADING INC. (FOR: STO. CRISTO CONSTRUCTION & TRADING) | 3480 | 2021 | 2022-08-31 | 03/24/2021 | 2702045.19 | 0 | 2022-08-30 |  | 1
2022 | National Capital Region | MAKATI CITY | CITY OF MAKATI (METROPOLITAN MANILA) | P00620382LZ | Rehabilitation / Major Repair of Drainage Structure | 121.0507 | 14.5661 | 9800000 | 9728174.56 | 2022 | ALEXA TRADING & CONSTRUCTION | 3481 | 2022 | 2022-08-22 | 02/09/2022 | 71825.44 | 0 | 2022-07-07 |  | 46
2024 | National Capital Region | PARAÃ‘AQUE CITY | CITY OF PARAÃ‘AQUE (METROPOLITAN MANILA) | P00844678LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.0198 | 14.4721 | 14700000 | 14673478.92 | 2024 | AKN CONSTRUCTION CORPORATION | 3482 | 2024 | 2024-12-16 | 09/18/2024 | 26521.08 | 0 | 2024-12-15 |  | 1
2024 | National Capital Region | QUEZON CITY | QUEZON CITY (METROPOLITAN MANILA) | P00839536LZ | Rehabilitation / Major Repair of Drainage Structure | 121.0263 | 14.6212 | 29690699.47 | 29510680.05 | 2024 | 121 CONSTRUCTION CORPORATION (FORMERLY 121 CONSTUC | 3483 | 2024 | 2024-12-13 | 02/08/2024 | 180019.42 | 0 | 2024-12-12 |  | 1
2023 | Region III | BULACAN | MARILAO (BULACAN) | P00742330LZ | Construction of Slope Protection Structure | 120.9728 | 14.772 | 4949959.02 | 4875561.14 | 2023 | FORTUNE RDC ENTERPRISES | 3484 | 2023 | 2023-06-10 | 03/30/2023 | 74397.88 | 0 | 2023-06-09 |  | 1
2024 | National Capital Region | PASAY CITY | PASAY CITY (METROPOLITAN MANILA) | P00820019LZ | Construction of Flood Mitigation Structure | 120.9969 | 14.5472 | 89172016.01 | 89057544.2 | 2024 | ELITE GENERAL CONTRACTOR AND DEVELOPMENT CORP. | 3485 | 2024 | 2024-11-11 | 02/21/2024 | 114471.81 | 0 | 2024-11-15 | 4
2022 | National Capital Region | QUEZON CITY | QUEZON CITY (METROPOLITAN MANILA) | P00631052LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.0509 | 14.7218 | 19600000 | 19012000 | 2023 | E.L. TORRES CONSTRUCTION AND TRADING INC. (FORMERLY : E. L. TORRES CONSTRUCTION & TRADING | 3486 | 2022 | 2023-06-12 | 02/14/2022 | 588000 | 0 | 2023-09-11 | 91
2022 | Region III | NUEVA ECIJA | LLANERA (NUEVA ECIJA) | P00620533LZ | Construction of Flood Mitigation Structure | 121.0085 | 15.7157 | 49000000 | 48996854.09 | 2022 | WIZARD CONCRETE SOLUTIONS AND CONSTRUCTION CORPORATION (FORMERLY: WIZARD TRADING & CONSTRUCTION) / ADROIT EJD CONSTRUCTION CORP. (FORMERLY: ADROIT CONSTRUCTION) | 3487 | 2022 | 2022-08-26 | 02/24/2022 | 3145.91 | 0 | 2022-09-20 | 25
2024 | National Capital Region | QUEZON CITY | QUEZON CITY (METROPOLITAN MANILA) | P00839535LZ | Rehabilitation / Major Repair of Drainage Structure | 121.0263 | 14.6335 | 29699458.46 | 29698539.56 | 2024 | MRB11 CONSTRUCTION CORPORATION (FORMERLY:MRB CONS | 3488 | 2024 | 2024-09-23 | 02/08/2024 | 918.9 | 0 | 2024-10-18 | 25
2024 | Region III | NUEVA ECIJA | PEÃ‘ARANDA (NUEVA ECIJA) | P00825240LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.0198 | 15.3384 | 20579903.08 | 20168228.34 | 2024 | F-DEY CONSTRUCTION AND TRADING | 3489 | 2024 | 2024-04-23 | 02/16/2024 | 411674.74 | 0 | 2024-09-11 | 141
2023 | National Capital Region | CALOOCAN CITY | CALOOCAN CITY (METROPOLITAN MANILA) | P00725979LZ | Construction of Flood Mitigation Structure | 121.051 | 14.7667 | 29398388.94 | 28944405.78 | 2024 | PERSAN CONSTRUCTION, INC. (FORMERLY: PERSAN CONST. | 3490 | 2023 | 2024-01-22 | 04/28/2023 | 453983.16 | 0 | 2024-02-20 | 29
2022 | Region III | NUEVA ECIJA | LLANERA (NUEVA ECIJA) | P00620529LZ | Construction of Flood Mitigation Structure | 120.9969 | 15.6863 | 49000000 | 49000000 | 2022 | IRC CONSTRUCTION & SUPPLIES / SYMMETRICON BUILDERS CORP. | 3491 | 2022 | 2022-09-15 | 02/18/2022 | 0 | 0 | 2022-09-14 |  | 1
2022 | Region III | BULACAN | CITY OF MEYCAUAYAN (BULACAN) | P00620520LZ | Construction of Flood Mitigation Facility | 120.9587 | 14.7353 | 19313572.84 | 19132032.52 | 2022 | GREAT PACIFIC BUILDERS AND GEN. CONTRACTOR INC. | 3492 | 2022 | 2022-10-03 | 02/28/2022 | 181540.32 | 0 | 2022-09-26 |  | 7
2023 | National Capital Region | CALOOCAN CITY | CALOOCAN CITY (METROPOLITAN MANILA) | P00725542LZ | Construction of Flood Mitigation Structure | 121.0086 | 14.7409 | 86845428.47 | 85034813.77 | 2023 | DARCY & ANNA BUILDERS & TRADING | 3493 | 2023 | 2023-12-13 | 04/24/2023 | 1810614.7 | 0 | 2024-03-17 | 95
2024 | National Capital Region | NAVOTAS CITY | CITY OF NAVOTAS (METROPOLITAN MANILA) | P00820538LZ | Construction of Drainage Structure | 120.9589 | 14.6382 | 4898427.16 | 4899439.91 | 2024 | 721 BUILDERS CORPORATION | 3494 | 2024 | 2024-05-30 | 02/12/2024 | 0 | 1012.75 | 2024-06-24 | 25
2024 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00823238LZ | Construction of Flood Mitigation Facility | 120.9728 | 14.6006 | 144749926.7 | 144747913.7 | 2024 | JJPR CONSTRUCTION SERVICES | 3495 | 2024 | 2024-04-17 | 02/08/2024 | 2013 | 0 | 2024-07-05 | 79
2023 | National Capital Region | LAS PIÃ‘AS CITY | CITY OF LAS PIÃ‘AS (METROPOLITAN MANILA) | P00725549LZ | Construction of Flood Mitigation Structure | 120.9969 | 14.4173 | 86849876.37 | 82498128.05 | 2023 | I&E CONSTRUCTION CORPORATION (FORMERLY: I&E CONSTR | 3496 | 2023 | 2023-06-28 | 02/13/2023 | 4351748.32 | 0 | 2023-09-09 | 73
2021 | National Capital Region | CALOOCAN CITY |  | P00525781LZ | Construction of Drainage Structure | 121.0265 | 14.7319 | 4903928.64 | 4821755.94 | 2022 | TM ABAD CONSTRUCTION CORP. (FOR: TM ABAD CONST.) | 3497 | 2021 | 2022-07-01 | 03/24/2022 | 82172.7 | 0 | 2022-07-20 | 19
2022 | National Capital Region | QUEZON CITY | QUEZON CITY (METROPOLITAN MANILA) | P00620452LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.0199 | 14.6744 | 43119831.69 | 42860768.69 | 2023 | LANOY CONSTRUCTION | 3498 | 2022 | 2023-07-23 | 03/23/2022 | 259063 | 0 | 2023-07-22 |  | 1
2022 | National Capital Region | QUEZON CITY | QUEZON CITY (METROPOLITAN MANILA) | P00630926LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.0511 | 14.7397 | 75554850 | 73288204.5 | 2023 | LE BRON CONSTRUCTION | 3499 | 2022 | 2023-02-20 | 02/16/2022 | 2266645.5 | 0 | 2023-02-09 |  | 11
2024 | National Capital Region | VALENZUELA CITY | CITY OF VALENZUELA (METROPOLITAN MANILA) | P00820613LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.9972 | 14.6946 | 14679878.2 | 14386264.93 | 2024 | GILTOP CIVIL ENGINEERING CONSTRUCTION | 3500 | 2024 | 2024-06-12 | 02/14/2024 | 293613.27 | 0 | 2024-06-11 |  | 1
2021 | National Capital Region | CALOOCAN CITY |  | P00525777LZ | Construction of Drainage Structure | 121.0086 | 14.6756 | 4899196.68 | 4786494.27 | 2022 | TM ABAD CONSTRUCTION CORP. (FOR: TM ABAD CONST.) | 3501 | 2021 | 2022-08-15 | 03/24/2022 | 112702.41 | 0 | 2022-07-20 |  | 26
2024 | Region III | BULACAN | CITY OF SAN JOSE DEL MONTE (BULACAN) | P00820825LZ | Construction of Flood Mitigation Structure | 121.0512 | 14.8073 | 48999758.96 | 48994496.09 | 2024 | YPR GEN. CONTRACTOR AND CONSTRUCTION SUPPLY INC. | 3502 | 2024 | 2024-09-08 | 02/12/2024 | 5262.87 | 0 | 2024-09-07 |  | 1
2022 | National Capital Region | NAVOTAS CITY | CITY OF NAVOTAS (METROPOLITAN MANILA) | P00639403LZ | Rehabilitation / Major Repair of Drainage Structure | 120.959 | 14.6508 | 1958453.7 | 1953912.61 | 2022 | EARTHWORK BUILDERS, INC. (FORMERLY: EARTHWORK MOVERS) | 3503 | 2022 | 2022-09-14 | 03/24/2022 | 4541.09 | 0 | 2022-09-13 |  | 1
2023 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00726807LZ | Rehabilitation / Major Repair of Drainage Structure | 120.9972 | 14.6077 | 67549665.2 | 67542628.6 | 2024 | V.R. GUEVARRA CONSTRUCTION AND TRADING / NEWBIG FOUR J CONSTRUCTION INC., (FORMERLY FOUR J | 3504 | 2023 | 2024-06-06 | 03/15/2023 | 7036.6 | 0 | 2024-06-05 |  | 1
2022 | National Capital Region | PARAÃ‘AQUE CITY | CITY OF PARAÃ‘AQUE (METROPOLITAN MANILA) | P00620922LZ | Construction of Flood Mitigation Structure | 121.0268 | 14.4554 | 39200000 | 39200000 | 2022 | AKN CONSTRUCTION CORPORATION | 3505 | 2022 | 2022-08-14 | 03/22/2022 | 0 | 0 | 2022-08-13 |  | 1
2022 | National Capital Region | QUEZON CITY | QUEZON CITY (METROPOLITAN MANILA) | P00637003LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.0199 | 14.6744 | 28949502.01 | 27759373.96 | 2023 | HALREY CONSTRUCTION INC. | 3506 | 2022 | 2023-02-11 | 05/18/2022 | 1190128.05 | 0 | 2023-02-10 |  | 1
2021 | National Capital Region | MAKATI CITY |  | P00561611LZ | Rehabilitation / Major Repair of Drainage Structure | 121.0512 | 14.5624 | 9900000 | 9900000 | 2022 | JAYLOT TRADING & CONSTRUCTION | 3507 | 2021 | 2022-11-05 | 05/24/2022 | 0 | 0 | 2022-11-04 |  | 1
2022 | National Capital Region | LAS PIÃ‘AS CITY | CITY OF LAS PIÃ‘AS (METROPOLITAN MANILA) | P00620911LZ | Construction of Flood Mitigation Structure | 121.0086 | 14.4191 | 48999400.35 | 48990674.66 | 2022 | ST. MATTHEW GEN. CONTRACTOR & DEVELOPMENT CORP. | 3508 | 2022 | 2022-10-29 | 03/04/2022 | 8725.69 | 0 | 2022-10-28 |  | 1
2024 | Region III | NUEVA ECIJA | CABANATUAN CITY (NUEVA ECIJA) | P00843299LZ | Construction of Flood Mitigation Structure | 120.9591 | 15.5343 | 71072170.07 | 71072250 | 2025 | DGSARM BUILDERS INC. (FORMERLY: D.G. SARMENTA CONSTRUCTION) | 3509 | 2024 | 2025-02-07 | 03/20/2024 | 0 | 79.93 | 2025-02-07 | 0
2023 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00726808LZ | Construction of Flood Mitigation Structure | 120.9972 | 14.6052 | 54089213.85 | 54088655.12 | 2024 | TOPNOTCH CATALYST BUILDERS INC. | 3510 | 2023 | 2024-03-18 | 03/15/2023 | 558.73 | 0 | 2024-03-26 | 8
2024 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00823242LZ | Construction of Flood Mitigation Facility | 120.9728 | 14.6006 | 144749875.7 | 144721297.2 | 2024 | JJPR CONSTRUCTION SERVICES | 3511 | 2024 | 2024-04-17 | 02/13/2024 | 28578.5 | 0 | 2024-07-10 | 84
2023 | National Capital Region | TAGUIG CITY | TAGUIG CITY (METROPOLITAN MANILA) | P00742239LZ | Construction of Drainage Structure | 121.0514 | 14.5119 | 14699960.37 | 13963924.69 | 2023 | J.M.L.R. CONSTRUCTION AND SUPPLY | 3512 | 2023 | 2023-11-10 | 05/23/2023 | 736035.68 | 0 | 2023-12-17 | 37
2023 | Region III | BULACAN | NORZAGARAY (BULACAN) | P00726521LZ | Construction of Flood Mitigation Structure | 121.0515 | 14.9075 | 86849257.74 | 86849107 | 2023 | AZUL BUILDERS / JB CONSTRUCTION AND SUPPLY INC. (FORMERLY:JB CONSTRUCTION AND SUPPLY) | 3513 | 2023 | 2023-08-24 | 02/27/2023 | 150.74 | 0 | 2023-12-09 | 107
2024 | National Capital Region | PARAÃ‘AQUE CITY | CITY OF PARAÃ‘AQUE (METROPOLITAN MANILA) | P00820566LZ | Construction of Revetment | 120.9973 | 14.5001 | 49000000 | 48996157.64 | 2025 | REND ENTERPRISES & GENERAL CONTRACTOR | 3514 | 2024 | 2025-01-02 | 02/08/2024 | 3842.36 | 0 | 2025-01-01 |  | 1
2024 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00823254LZ | Construction of Slope Protection Structure | 120.9591 | 14.5849 | 96499859.8 | 96497829.67 | 2024 | CAANA CONSTRUCTION CORPORATION | 3515 | 2024 | 2024-10-07 | 05/27/2024 | 2030.13 | 0 | 2025-01-20 | 105
2024 | National Capital Region | QUEZON CITY | QUEZON CITY (METROPOLITAN MANILA) | P00823273LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.0268 | 14.6254 | 20249468.43 | 20248040.3 | 2024 | MRB11 CONSTRUCTION CORPORATION (FORMERLY:MRB CONS | 3516 | 2024 | 2024-11-25 | 03/26/2024 | 1428.13 | 0 | 2025-01-09 | 45
2023 | National Capital Region | MUNTINLUPA CITY | CITY OF MUNTINLUPA (METROPOLITAN MANILA) | P00725917LZ | Construction of Flood Mitigation Structure | 121.0515 | 14.4456 | 48999835.42 | 48950838.22 | 2023 | RNN CONSTRUCTION CORPORATION (FORMERLY RNN CONSTRU / AKN CONSTRUCTION CORPORATION | 3517 | 2023 | 2023-07-12 | 02/13/2023 | 48997.2 | 0 | 2023-07-11 |  | 1
2022 | National Capital Region | PASAY CITY | PASAY CITY (METROPOLITAN MANILA) | P00620111LZ | Construction of Slope Protection Structure | 121.0087 | 14.531 | 57895380.25 | 57893459.38 | 2022 | AARCON BUILDERS | 3518 | 2022 | 2022-10-25 | 02/28/2022 | 1920.87 | 0 | 2022-10-24 |  | 1
2024 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00823241LZ | Construction of Flood Mitigation Facility | 120.9728 | 14.6006 | 144749637.5 | 144558835.1 | 2024 | JJPR CONSTRUCTION SERVICES | 3519 | 2024 | 2024-04-17 | 02/08/2024 | 190802.4 | 0 | 2024-07-05 | 79
2022 | National Capital Region | QUEZON CITY | QUEZON CITY (METROPOLITAN MANILA) | P00620114LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.0199 | 14.6744 | 77601797.84 | 77323411 | 2023 | MSB VITUG CONSTRUCTION | 3520 | 2022 | 2023-02-17 | 05/24/2022 | 278386.84 | 0 | 2023-02-16 |  | 1
2022 | Region III | BULACAN | SAN MIGUEL (BULACAN) | P00639339LZ | Construction of Flood Mitigation Structure | 121.0268 | 15.2385 | 96499829.13 | 96495644.65 | 2023 | JAGONBUILD CONSTRUCTION CORP. (FOR. JAGON BUILDERS | 3521 | 2022 | 2023-02-16 | 03/30/2022 | 4184.48 | 0 | 2023-03-07 | 19
2022 | National Capital Region | QUEZON CITY | QUEZON CITY (METROPOLITAN MANILA) | P00640487LZ | Construction of Flood Mitigation Structure | 121.0268 | 14.6911 | 29700000 | 28809000 | 2023 | FRAMECON BUILDERS | 3522 | 2022 | 2023-03-14 | 05/19/2022 | 891000 | 0 | 2023-03-13 |  | 1
2021 | National Capital Region | MUNTINLUPA CITY |  | P00525475LZ | Construction of Flood Mitigation Structure | 121.0516 | 14.4288 | 74733984.07 | 74703599.44 | 2022 | E. F. CHUA CONSTRUCTION, INC. | 3523 | 2021 | 2022-12-13 | 04/08/2022 | 30384.63 | 0 | 2022-12-12 |  | 1
2024 | Region III | BULACAN | SANTA MARIA (BULACAN) | P00844747LZ | Construction of Flood Mitigation Structure | 120.9729 | 14.8171 | 48999331.86 | 48998694.98 | 2024 | R.A. PAHATI CONST. & SUPPLY, INC. | 3524 | 2024 | 2024-07-09 | 03/25/2024 | 636.88 | 0 | 2024-10-18 | 101
2022 | National Capital Region | CALOOCAN CITY | CALOOCAN CITY (METROPOLITAN MANILA) | P00637042LZ | Rehabilitation / Major Repair of Drainage Structure | 120.9974 | 14.6536 | 21473676.9 | 21021340.23 | 2022 | C.L. MORALES CONSTRUCTION AND TRADING | 3525 | 2022 | 2022-10-17 | 03/24/2022 | 452336.67 | 0 | 2022-12-17 | 61
2022 | National Capital Region | TAGUIG CITY | TAGUIG CITY (METROPOLITAN MANILA) | P00620086LZ | Construction of Slope Protection Structure | 121.0269 | 14.5326 | 96499494.35 | 91640252.51 | 2023 | PASCAL CONSTRUCTION | 3526 | 2022 | 2023-09-01 | 03/21/2022 | 4859241.84 | 0 | 2023-08-31 |  | 1
2022 | National Capital Region | CALOOCAN CITY | CALOOCAN CITY (METROPOLITAN MANILA) | P00620407LZ | Construction of Flood Mitigation Structure | 121.0517 | 14.7661 | 45068363.51 | 43626337.58 | 2022 | WAWAO BUILDERS | 3527 | 2022 | 2022-12-13 | 02/08/2022 | 1442025.93 | 0 | 2023-01-02 | 20
2023 | National Capital Region | PASAY CITY | PASAY CITY (METROPOLITAN MANILA) | P00726039LZ | Construction of Slope Protection Structure | 121.0087 | 14.531 | 24496286.89 | 23981057.35 | 2023 | AARCON BUILDERS | 3528 | 2023 | 2023-08-19 | 02/20/2023 | 515229.54 | 0 | 2023-07-18 |  | 32
2023 | Region III | BULACAN | BUSTOS (BULACAN) | P00726472LZ | Construction of Flood Mitigation Structure | 120.9592 | 14.9592 | 96499810.58 | 96499989.39 | 2023 | JTC CRUZ CONSTRUCTION CO., INC. | 3529 | 2023 | 2023-07-03 | 02/13/2023 | 0 | 178.81 | 2023-12-08 | 158
2024 | National Capital Region | MAKATI CITY | CITY OF MAKATI (METROPOLITAN MANILA) | P00839521LZ | Rehabilitation / Major Repair of Drainage Structure | 121.0199 | 14.571 | 24750000 | 24746494.54 | 2024 | E. F. CHUA CONSTRUCTION, INC. | 3530 | 2024 | 2024-11-19 | 02/20/2024 | 3505.46 | 0 | 2024-11-18 |  | 1
2021 | National Capital Region | MUNTINLUPA CITY |  | P00525477LZ | Construction of Flood Mitigation Structure | 121.0518 | 14.4383 | 74304910.06 | 74204302.44 | 2022 | E. F. CHUA CONSTRUCTION, INC. | 3531 | 2021 | 2022-12-13 | 04/08/2022 | 100607.62 | 0 | 2022-12-12 |  | 1
2022 | Region III | BULACAN | SANTA MARIA (BULACAN) | P00620190LZ | Construction of Flood Mitigation Structure | 120.9597 | 14.8202 | 95529083.49 | 95533084.87 | 2023 | L.R. TIQUI BUILDERS, INC. | 3532 | 2022 | 2023-04-15 | 03/07/2022 | 0 | 4001.38 | 2023-04-14 |  | 1
2023 | National Capital Region | LAS PIÃ‘AS CITY | CITY OF LAS PIÃ‘AS (METROPOLITAN MANILA) | P00725913LZ | Construction of Flood Mitigation Structure | 120.9732 | 14.4409 | 48996719.42 | 48993363.57 | 2023 | E. F. CHUA CONSTRUCTION, INC. | 3533 | 2023 | 2023-12-19 | 08/22/2023 | 3355.85 | 0 | 2023-12-18 |  | 1
2022 | Region II | CAGAYAN | SANTA PRAXEDES (CAGAYAN) | P00631106LZ | Construction of Flood Mitigation Structure | 120.9975 | 18.5496 | 19600000 | 19600000 | 2022 | HHK CONSTRUCTION | 3534 | 2022 | 2022-12-01 | 03/28/2022 | 0 | 0 | 2022-11-30 |  | 1
2022 | Region III | BULACAN | SAN RAFAEL (BULACAN) | P00620158LZ | Construction of Flood Mitigation Structure | 120.9598 | 15.0277 | 57899715.58 | 50062322.96 | 2022 | EIRISH BUILDERS & SUPPLY INC. | 3535 | 2022 | 2022-10-09 | 03/07/2022 | 7837392.62 | 0 | 2022-10-08 |  | 1
2023 | National Capital Region | LAS PIÃ‘AS CITY | CITY OF LAS PIÃ‘AS (METROPOLITAN MANILA) | P00742213LZ | Construction of Flood Mitigation Structure | 120.9732 | 14.4409 | 48247584.06 | 48247401.06 | 2023 | E. F. CHUA CONSTRUCTION, INC. | 3536 | 2023 | 2023-10-22 | 04/26/2023 | 183 | 0 | 2023-10-21 |  | 1
2023 | National Capital Region | VALENZUELA CITY | CITY OF VALENZUELA (METROPOLITAN MANILA) | P00725994LZ | Construction of Flood Mitigation Structure | 121.0087 | 14.6945 | 48965960.55 | 47937648.46 | 2024 | MRB11 CONSTRUCTION CORPORATION (FORMERLY:MRB CONS | 3537 | 2023 | 2024-01-16 | 02/21/2023 | 1028312.09 | 0 | 2024-01-15 |  | 1
2022 | National Capital Region | QUEZON CITY | QUEZON CITY (METROPOLITAN MANILA) | P00621436LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.027 | 14.6255 | 29399259.72 | 29359033.65 | 2023 | AMETHYST HORIZON BUILDERS AND GEN. CONTRACTOR AND DEVELOPMENT CORP. | 3538 | 2022 | 2023-11-19 | 06/03/2022 | 40226.07 | 0 | 2023-11-18 |  | 1
2024 | Region III | NUEVA ECIJA | GENERAL TINIO (PAPAYA) (NUEVA ECIJA) | P00821239LZ | Construction of Flood Mitigation Structure | 121.0518 | 15.344 | 79657828.73 | 78064126.73 | 2024 | F-DEY CONSTRUCTION AND TRADING / JERRY R. SANTIAGO CONSTRUCTION CORP. (FORMERLY: JERRY SANTIAGO CONSTRUCTION) | 3539 | 2024 | 2024-06-18 | 04/02/2024 | 1593702 | 0 | 2024-12-26 | 191
2022 | Region IV-A | CAVITE | BACOOR CITY (CAVITE) | P00640461LZ | Construction of Revetment | 120.9601 | 14.4662 | 98999998.58 | 98999140.73 | 2023 | GRAIA CONSTRUCTION CORPORATION | 3540 | 2022 | 2023-12-07 | 04/07/2022 | 857.85 | 0 | 2024-08-01 | 238
2023 | National Capital Region | QUEZON CITY | QUEZON CITY (METROPOLITAN MANILA) | P00727040LZ | Rehabilitation / Major Repair of Drainage Structure | 121.0199 | 14.6117 | 19599721.32 | 19597930.63 | 2024 | LIM GENERAL CONTRACTOR CORPORATION | 3541 | 2023 | 2024-08-07 | 03/13/2023 | 1790.69 | 0 | 2024-08-06 |  | 1
2023 | National Capital Region | QUEZON CITY | QUEZON CITY (METROPOLITAN MANILA) | P00727034LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.0199 | 14.6117 | 48999960.85 | 47907420.63 | 2023 | MRB11 CONSTRUCTION CORPORATION (FORMERLY:MRB CONS | 3542 | 2023 | 2023-11-07 | 03/13/2023 | 1092540.22 | 0 | 2023-11-06 |  | 1
2022 | National Capital Region | QUEZON CITY | QUEZON CITY (METROPOLITAN MANILA) | P00631045LZ | Rehabilitation / Major Repair of Drainage Structure | 121.0519 | 14.7168 | 9799221.86 | 9799221.86 | 2022 | TRICHES CONSTRUCTION & TRADING | 3543 | 2022 | 2022-08-10 | 02/14/2022 | 0 | 0 | 2022-08-09 |  | 1
2024 | National Capital Region | CALOOCAN CITY | CALOOCAN CITY (METROPOLITAN MANILA) | P00820599LZ | Construction of Flood Mitigation Structure | 121.0092 | 14.7257 | 48979948.11 | 47926860.63 | 2024 | PERSAN CONSTRUCTION, INC. (FORMERLY: PERSAN CONST. | 3544 | 2024 | 2024-06-10 | 02/27/2024 | 1053087.48 | 0 | 2024-07-24 | 44
2024 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00838476LZ | Rehabilitation / Major Repair of Drainage Structure | 120.9975 | 14.6053 | 29086248.43 | 29086241.46 | 2025 | TOPNOTCH CATALYST BUILDERS INC. | 3545 | 2024 | 2025-02-10 | 02/12/2024 | 6.97 | 0 | 2025-03-05 | 23
2021 | National Capital Region | CITY OF MANILA |  | P00525820LZ | Construction of Flood Mitigation Facility | 120.9601 | 14.6145 | 48999936.11 | 48403077.09 | 2023 | ALPHA & OMEGA GEN. CONTRACTOR & DEVELOPMENT CORP. | 3546 | 2021 | 2023-05-30 | 03/30/2022 | 596859.02 | 0 | 2023-05-29 |  | 1
2022 | National Capital Region | QUEZON CITY | QUEZON CITY (METROPOLITAN MANILA) | P00631050LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.0519 | 14.7113 | 14700000 | 14470000 | 2023 | INDUSTRIAL CONTROLS CORPORATION (ICC) | 3547 | 2022 | 2023-08-12 | 02/14/2022 | 230000 | 0 | 2023-08-11 |  | 1
2023 | Region IV-A | CAVITE | BACOOR CITY (CAVITE) | P00742423LZ | Construction of Flood Mitigation Structure | 121.0093 | 14.3781 | 42570000 | 42568425.04 | 2024 | E. F. CHUA CONSTRUCTION, INC. | 3548 | 2023 | 2024-02-11 | 07/17/2023 | 1574.96 | 0 | 2024-02-10 |  | 1
2023 | National Capital Region | MUNTINLUPA CITY | CITY OF MUNTINLUPA (METROPOLITAN MANILA) | P00725919LZ | Construction of Flood Mitigation Structure | 121.0272 | 14.3773 | 48999999.84 | 48998765.74 | 2024 | A.M. ORETA & CO., INC. | 3549 | 2023 | 2024-03-21 | 02/13/2023 | 1234.1 | 0 | 2024-03-20 |  | 1
2023 | National Capital Region | QUEZON CITY | QUEZON CITY (METROPOLITAN MANILA) | P00727035LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.0199 | 14.6117 | 48999847.45 | 48963617.7 | 2023 | MRB11 CONSTRUCTION CORPORATION (FORMERLY:MRB CONS | 3550 | 2023 | 2023-11-07 | 03/13/2023 | 36229.75 | 0 | 2023-11-06 |  | 1
2024 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00820095LZ | Rehabilitation / Major Repair of Flood Mitigation Facility | 120.9733 | 14.5818 | 96497130.68 | 96492658.53 | 2024 | EIGHT J'S CONSTRUCTION SERVICES | 3551 | 2024 | 2024-08-17 | 02/20/2024 | 4472.15 | 0 | 2024-08-16 |  | 1
2022 | National Capital Region | CALOOCAN CITY | CALOOCAN CITY (METROPOLITAN MANILA) | P00620396LZ | Construction of Flood Mitigation Structure | 121.0094 | 14.7368 | 29395958.2 | 28749240.3 | 2022 | JAGONBUILD CONSTRUCTION CORP. (FOR. JAGON BUILDERS | 3552 | 2022 | 2022-11-14 | 02/08/2022 | 646717.9 | 0 | 2022-12-03 | 19
2022 | Region IV-A | LAGUNA | CITY OF SAN PEDRO (LAGUNA) | P00620221LZ | Construction of Revetment | 121.0273 | 14.3626 | 91675000 | 91641226.89 | 2023 | ALPHA & OMEGA GEN. CONTRACTOR & DEVELOPMENT CORP. / ELITE GENERAL CONTRACTOR AND DEVELOPMENT CORP. | 3553 | 2022 | 2023-03-05 | 02/21/2022 | 33773.11 | 0 | 2023-03-04 |  | 1
2024 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00820096LZ | Rehabilitation / Major Repair of Flood Mitigation Facility | 120.9733 | 14.5818 | 96499274.78 | 96490816.38 | 2024 | EIGHT J'S CONSTRUCTION SERVICES | 3554 | 2024 | 2024-09-17 | 02/21/2024 | 8458.4 | 0 | 2024-09-16 |  | 1
2022 | Region III | BULACAN | SAN ILDEFONSO (BULACAN) | P00639345LZ | Construction of Flood Mitigation Structure | 120.9602 | 15.0284 | 96499878.74 | 95050950.34 | 2023 | KATHA BUILDERS & SUPPLIES INC. | 3555 | 2022 | 2023-06-07 | 03/30/2022 | 1448928.4 | 0 | 2023-06-06 |  | 1
2023 | National Capital Region | QUEZON CITY | QUEZON CITY (METROPOLITAN MANILA) | P00727036LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.0199 | 14.6117 | 48999751.06 | 48963617.7 | 2023 | MRB11 CONSTRUCTION CORPORATION (FORMERLY:MRB CONS | 3556 | 2023 | 2023-11-07 | 03/13/2023 | 36133.36 | 0 | 2023-11-06 |  | 1
2023 | Region III | NUEVA ECIJA | LLANERA (NUEVA ECIJA) | P00726167LZ | Construction of Flood Mitigation Structure | 120.9976 | 15.687 | 23142700 | 23139000 | 2023 | SYMMETRICON BUILDERS CORP. | 3557 | 2023 | 2023-05-04 | 02/21/2023 | 3700 | 0 | 2023-08-18 | 106
2022 | Region IV-A | BATANGAS | CUENCA (BATANGAS) | P00632872LZ | Construction of Drainage Structure | 121.0521 | 13.8816 | 4950000 | 4949178 | 2022 | P-SQUARE CONTRACTING & SERVICES | 3558 | 2022 | 2022-07-02 | 02/08/2022 | 822 | 0 | 2022-07-01 |  | 1
2021 | National Capital Region | PARAÃ‘AQUE CITY |  | P00525764LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.9976 | 14.5168 | 9800000 | 9800000 | 2022 | CALCON ENGINEERING | 3559 | 2021 | 2022-09-19 | 02/22/2022 | 0 | 0 | 2022-09-18 |  | 1
2024 | National Capital Region | PARAÃ‘AQUE CITY | CITY OF PARAÃ‘AQUE (METROPOLITAN MANILA) | P00820575LZ | Rehabilitation / Major Repair of Drainage Structure | 121.0273 | 14.4751 | 29400000 | 29395942.48 | 2024 | GRAC-TA BUILDERS | 3560 | 2024 | 2024-07-22 | 02/08/2024 | 4057.52 | 0 | 2024-08-04 | 13
2023 | Region III | BULACAN | MARILAO (BULACAN) | P00726162LZ | Construction of Flood Mitigation Structure | 120.9734 | 14.7378 | 19598950.18 | 19597861.13 | 2023 | 747 BUILDERS & TRADERS,INC. (FORMERLY:747 BUILDERS & TRADER) | 3561 | 2023 | 2023-12-29 | 02/27/2023 | 1089.05 | 0 | 2023-12-28 |  | 1
2022 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00620431LZ | Construction of Flood Mitigation Facility | 120.9603 | 14.6143 | 24499986.79 | 23470297.9 | 2023 | JELSIE CONSTRUCTION & SUPPLY | 3562 | 2022 | 2023-09-07 | 02/17/2022 | 1029688.89 | 0 | 2023-09-06 |  | 1
2023 | Region IV-A | CAVITE | CITY OF CARMONA (CAVITE) | P00726220LZ | Construction of Revetment | 121.0521 | 14.3078 | 88199984.47 | 44099979.64 | 2023 | AARCON BUILDERS | 3563 | 2023 | 2023-09-18 | 02/16/2023 | 44100004.83 | 0 | 2023-09-27 | 9
2023 | Region IV-A | CAVITE | BACOOR CITY (CAVITE) | P00742176LZ | Construction of Flood Mitigation Structure | 121.0094 | 14.3767 | 79200000 | 79199149.37 | 2024 | E. F. CHUA CONSTRUCTION, INC. | 3564 | 2023 | 2024-04-05 | 07/17/2023 | 850.63 | 0 | 2024-04-04 |  | 1
2022 | National Capital Region | LAS PIÃ‘AS CITY | CITY OF LAS PIÃ‘AS (METROPOLITAN MANILA) | P00631006LZ | Rehabilitation / Major Repair of Drainage Structure | 120.9977 | 14.4629 | 9799920.44 | 9792108.32 | 2022 | MRJR CONSTRUCTION & TRADING | 3565 | 2022 | 2022-10-10 | 06/13/2022 | 7812.12 | 0 | 2022-10-09 |  | 1
2022 | National Capital Region | SAN JUAN CITY | CITY OF SAN JUAN (METROPOLITAN MANILA) | P00621134LZ | Construction of Slope Protection Structure | 121.0275 | 14.6123 | 79349938.81 | 75344255.34 | 2023 | WAWAO BUILDERS | 3566 | 2022 | 2023-03-12 | 03/24/2022 | 4005683.47 | 0 | 2023-01-30 |  | 41
2024 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00820622LZ | Construction of Revetment | 120.9734 | 14.5996 | 11759918.73 | 11489445.53 | 2024 | MANGEN TECHNO-BUILDERS INC. | 3567 | 2024 | 2024-06-15 | 02/12/2024 | 270473.2 | 0 | 2024-06-14 |  | 1
2022 | Region III | BULACAN | SAN MIGUEL (BULACAN) | P00639481LZ | Construction of Flood Mitigation Structure | 120.9977 | 15.2262 | 48999932.94 | 48997970.99 | 2023 | 729 CONSTRUCTION, INC. (FORMERLY 722 CONSTRUCTION, INC.) | 3568 | 2022 | 2023-02-28 | 03/30/2022 | 1961.95 | 0 | 2023-03-30 | 30
2023 | National Capital Region | QUEZON CITY | QUEZON CITY (METROPOLITAN MANILA) | P00727037LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.0199 | 14.6117 | 48999734.05 | 48938414.23 | 2023 | AMETHYST HORIZON BUILDERS AND GEN. CONTRACTOR AND DEVELOPMENT CORP. | 3569 | 2023 | 2023-09-14 | 03/13/2023 | 61319.82 | 0 | 2023-10-07 | 23
2022 | National Capital Region | CALOOCAN CITY | CALOOCAN CITY (METROPOLITAN MANILA) | P00620404LZ | Construction of Flood Mitigation Structure | 121.0275 | 14.7313 | 29397500.73 | 28736038.44 | 2022 | IM CONSTRUCTION CORPORATION | 3570 | 2022 | 2022-12-12 | 02/08/2022 | 661462.29 | 0 | 2023-01-02 | 21
2022 | National Capital Region | MALABON CITY | CITY OF MALABON (METROPOLITAN MANILA) | P00631018LZ | Construction of Drainage Structure | 120.9606 | 14.6706 | 9799986.91 | 9800000 | 2022 | SKYSCRAPERPH CONSTRUCTION CORPORATION | 3571 | 2022 | 2022-08-26 | 02/15/2022 | 0 | 13.09 | 2022-10-11 | 46
2024 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00820658LZ | Construction of Flood Mitigation Structure | 121.0095 | 14.5784 | 39199925.82 | 39172274.95 | 2024 | N.M.E. CONSTRUCTION | 3572 | 2024 | 2024-11-06 | 02/21/2024 | 27650.87 | 0 | 2024-11-05 |  | 1
2024 | Region IV-A | CAVITE | SILANG (CAVITE) | P00839616LZ | Construction of Drainage Structure | 120.9734 | 14.2299 | 9899914.61 | 9899185.43 | 2024 | CMMJ CONSTRUCTION | 3573 | 2024 | 2024-08-22 | 03/28/2024 | 729.18 | 0 | 2024-09-09 | 18
2021 | National Capital Region | CALOOCAN CITY |  | P00525789LZ | Construction of Flood Mitigation Structure | 121.0276 | 14.7664 | 14885113.08 | 14480400.62 | 2022 | IM CONSTRUCTION CORPORATION | 3574 | 2021 | 2022-07-04 | 02/24/2022 | 404712.46 | 0 | 2022-09-20 | 78
2023 | National Capital Region | LAS PIÃ‘AS CITY | CITY OF LAS PIÃ‘AS (METROPOLITAN MANILA) | P00742215LZ | Rehabilitation / Major Repair of Drainage Structure | 120.9736 | 14.4591 | 4899916.84 | 4897852.55 | 2023 | OMNICON BUILDERS | 3575 | 2023 | 2023-07-30 | 04/17/2023 | 2064.29 | 0 | 2023-07-29 |  | 1
2023 | Region IV-A | CAVITE | GEN. MARIANO ALVAREZ (CAVITE) | P00737513LZ | Construction of Drainage Structure | 121.0096 | 14.3069 | 19799810.39 | 4949903.67 | 2023 | ALMAKAR BUILDERS & METAL WORKS | 3576 | 2023 | 2023-08-17 | 02/15/2023 | 14849906.72 | 0 | 2023-09-11 | 25
2023 | Region IV-A | BATANGAS | BAUAN (BATANGAS) | P00740394LZ | Construction of Flood Mitigation Structure | 120.9978 | 13.7821 | 19600000 | 19300000 | 2023 | VICMAR CONSTRUCTION, INC. | 3577 | 2023 | 2023-08-15 | 04/03/2023 | 300000 | 0 | 2023-08-14 |  | 1
2022 | National Capital Region | MALABON CITY | CITY OF MALABON (METROPOLITAN MANILA) | P00631025LZ | Construction of Flood Mitigation Facility | 120.9607 | 14.675 | 19591615.15 | 19599961.42 | 2022 | AL-REM KONSTRUCT INC. | 3578 | 2022 | 2022-08-17 | 02/15/2022 | 0 | 8346.27 | 2022-09-11 | 25
2023 | National Capital Region | QUEZON CITY | QUEZON CITY (METROPOLITAN MANILA) | P00727038LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.0199 | 14.6117 | 48999524.26 | 48948822.01 | 2023 | ELITE GENERAL CONTRACTOR AND DEVELOPMENT CORP. | 3579 | 2023 | 2023-09-14 | 03/13/2023 | 50702.25 | 0 | 2023-10-07 | 23
2023 | National Capital Region | QUEZON CITY | QUEZON CITY (METROPOLITAN MANILA) | P00727039LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.0199 | 14.6117 | 48999620.65 | 48904450.12 | 2023 | A.L. SALAZAR CONSTRUCTION, INC. | 3580 | 2023 | 2023-09-14 | 03/13/2023 | 95170.53 | 0 | 2023-10-07 | 23
2021 | National Capital Region | MUNTINLUPA CITY |  | P00525476LZ | Construction of Flood Mitigation Structure | 121.0522 | 14.4218 | 74304723.04 | 74291808.62 | 2022 | E. F. CHUA CONSTRUCTION, INC. | 3581 | 2021 | 2022-12-13 | 04/08/2022 | 12914.42 | 0 | 2022-12-12 |  | 1
2023 | National Capital Region | PARAÃ‘AQUE CITY | CITY OF PARAÃ‘AQUE (METROPOLITAN MANILA) | P00725540LZ | Construction of Flood Mitigation Facility | 121.0278 | 14.5058 | 91675000 | 91674500.46 | 2024 | EIGHT J'S CONSTRUCTION SERVICES | 3582 | 2023 | 2024-11-04 | 02/15/2023 | 499.54 | 0 | 2024-11-06 | 2
2022 | Region IV-A | LAGUNA | CITY OF SAN PEDRO (LAGUNA) | P00620589LZ | Construction of Flood Mitigation Structure | 121.02 | 14.3441 | 44100000 | 44052051.78 | 2023 | 11 DIAMOND EAGLE CONSTRUCTION CORPORATION (FORMERLY:11 DIAMOND EAGLE CONSTRUCTION) | 3583 | 2022 | 2023-01-12 | 03/21/2022 | 47948.22 | 0 | 2023-01-11 |  | 1
2022 | National Capital Region | MUNTINLUPA CITY | CITY OF MUNTINLUPA (METROPOLITAN MANILA) | P00620762LZ | Construction of Flood Mitigation Structure | 121.0522 | 14.4272 | 91667472.14 | 91567097.47 | 2022 | E. F. CHUA CONSTRUCTION, INC. | 3584 | 2022 | 2022-12-28 | 02/17/2022 | 100374.67 | 0 | 2022-12-27 |  | 1
2023 | Region III | BULACAN | CITY OF MEYCAUAYAN (BULACAN) | P00726504LZ | Construction of Flood Mitigation Facility | 120.9736 | 14.738 | 55965737.26 | 55126251.2 | 2024 | TRIPLE 8 CONSTRUCTION & SUPPLY, INC. (FORMERLY TRIPLE 8 CONST. & SUPPLY) | 3585 | 2023 | 2024-02-17 | 05/18/2023 | 839486.06 | 0 | 2024-02-16 |  | 1
2024 | Region III | NUEVA ECIJA | PEÃ‘ARANDA (NUEVA ECIJA) | P00838527LZ | Construction of Drainage Structure | 120.9978 | 15.3502 | 19599996.35 | 19305542.09 | 2024 | N.C. AGUILAR CONST. & SUPPLY INC. | 3586 | 2024 | 2024-12-29 | 03/25/2024 | 294454.26 | 0 | 2024-12-25 |  | 4
2023 | National Capital Region | PASAY CITY | PASAY CITY (METROPOLITAN MANILA) | P00725510LZ | Construction of Slope Protection Structure | 121.0096 | 14.531 | 62723812.58 | 61218798.82 | 2023 | CAANA CONSTRUCTION CORPORATION | 3587 | 2023 | 2023-09-15 | 02/23/2023 | 1505013.76 | 0 | 2023-10-19 | 34
2024 | National Capital Region | CALOOCAN CITY | CALOOCAN CITY (METROPOLITAN MANILA) | P00824606LZ | Construction of Drainage Structure | 120.9609 | 14.6435 | 39199953.48 | 38296975.74 | 2024 | TOUGHBUILT CONSTRUCTION & TRADING, INC. / NOVA VENTUS CONSTRUCTION INC. | 3588 | 2024 | 2024-10-01 | 02/27/2024 | 902977.74 | 0 | 2024-08-23 |  | 39
2022 | National Capital Region | MAKATI CITY | CITY OF MAKATI (METROPOLITAN MANILA) | P00637040LZ | Construction of Revetment | 121.0098 | 14.5437 | 39200000 | 39200000 | 2022 | STRONGLANE BUILDERS AND TRADING CORPORATION (FORMERLY: STRONGLANE CONSTRUCTION & TRADING) / RJM CONSTRUCTION AND DEV'T., INC. | 3589 | 2022 | 2022-10-24 | 03/22/2022 | 0 | 0 | 2022-11-15 | 22
2022 | National Capital Region | VALENZUELA CITY | CITY OF VALENZUELA (METROPOLITAN MANILA) | P00631034LZ | Rehabilitation / Major Repair of Drainage Structure | 120.9978 | 14.7125 | 4891153.98 | 4793303.64 | 2022 | SONPRO CONSTRUCTION | 3590 | 2022 | 2022-07-18 | 02/08/2022 | 97850.34 | 0 | 2022-06-06 |  | 42
2022 | National Capital Region | MALABON CITY | CITY OF MALABON (METROPOLITAN MANILA) | P00620342LZ | Construction of Flood Mitigation Structure | 120.9736 | 14.6759 | 48998662.83 | 48999339.55 | 2023 | ALPHA & OMEGA GEN. CONTRACTOR & DEVELOPMENT CORP. | 3591 | 2022 | 2023-02-08 | 02/14/2022 | 0 | 676.72 | 2023-02-07 |  | 1
2023 | National Capital Region | CALOOCAN CITY | CALOOCAN CITY (METROPOLITAN MANILA) | P00736165LZ | Construction of Flood Mitigation Structure | 121.02 | 14.7586 | 29397127.94 | 28779766.07 | 2023 | DREAMWORX BUILDER & TRADING, INC. | 3592 | 2023 | 2023-05-22 | 02/21/2023 | 617361.87 | 0 | 2023-12-16 | 208
2022 | Region III | BULACAN | CITY OF SAN JOSE DEL MONTE (BULACAN) | P00631220LZ | Construction of Flood Mitigation Structure | 121.028 | 14.82 | 39199988.09 | 39194488.63 | 2023 | FLORDES CONSTRUCTION & TRADING CORP. (FORMERLY FLO | 3593 | 2022 | 2023-02-14 | 03/30/2022 | 5499.46 | 0 | 2023-02-13 |  | 1
2022 | National Capital Region | NAVOTAS CITY | CITY OF NAVOTAS (METROPOLITAN MANILA) | P00631023LZ | Construction of Flood Mitigation Facility | 120.961 | 14.6366 | 19599868.18 | 19592636.68 | 2022 | CATTECORYLL CONSTRUCTION & TRADING CORP | 3594 | 2022 | 2022-09-23 | 02/15/2022 | 7231.5 | 0 | 2022-11-05 | 43
2023 | National Capital Region | TAGUIG CITY | TAGUIG CITY (METROPOLITAN MANILA) | P00742237LZ | Construction of Drainage Structure | 121.0523 | 14.5444 | 27439309.69 | 26064196.17 | 2024 | WAY MAKER GENERAL CONTRACTOR OPC | 3595 | 2023 | 2024-02-02 | 06/09/2023 | 1375113.52 | 0 | 2024-02-02 | 0
2022 | National Capital Region | QUEZON CITY | QUEZON CITY (METROPOLITAN MANILA) | P00621266LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.02 | 14.617 | 96499498.81 | 92639372.03 | 2023 | 1HB CONSTRUCTION CORP. (FORMERLY: HB CONSTRUCTION) / DAHL CONSTRUCTION CORP. (FORMERLY: DAHL CONSTRUCTION) | 3596 | 2022 | 2023-07-12 | 05/19/2022 | 3860126.78 | 0 | 2023-07-11 |  | 1
2022 | National Capital Region | MANDALUYONG CITY | CITY OF MANDALUYONG (METROPOLITAN MANILA) | P00620364LZ | Construction of Flood Mitigation Structure | 121.0281 | 14.5953 | 45079586.32 | 42808974.2 | 2022 | DAHL CONSTRUCTION CORP. (FORMERLY: DAHL CONSTRUCTION) | 3597 | 2022 | 2022-10-05 | 02/08/2022 | 2270612.12 | 0 | 2022-08-05 |  | 61
2023 | Region III | BULACAN | SANTA MARIA (BULACAN) | P00725759LZ | Construction of Flood Mitigation Structure | 120.9611 | 14.8154 | 86849719.08 | 86843630.91 | 2024 | HALREY CONSTRUCTION INC. | 3598 | 2023 | 2024-04-06 | 02/27/2023 | 6088.17 | 0 | 2024-04-05 |  | 1
2024 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00820656LZ | Construction of Flood Mitigation Structure | 120.998 | 14.5679 | 29399708.96 | 29395548.76 | 2025 | 1129 BUILDERS | 3599 | 2024 | 2025-01-13 | 02/21/2024 | 4160.2 | 0 | 2025-01-12 |  | 1
2022 | National Capital Region | PARAÃ‘AQUE CITY | CITY OF PARAÃ‘AQUE (METROPOLITAN MANILA) | P00620917LZ | Construction of Revetment | 121.0099 | 14.4827 | 29400000 | 27900600 | 2022 | JMK BUILDERS CONSTRUCTION | 3600 | 2022 | 2022-11-17 | 02/04/2022 | 1499400 | 0 | 2022-11-16 |  | 1
2022 | National Capital Region | MALABON CITY | CITY OF MALABON (METROPOLITAN MANILA) | P00620343LZ | Construction of Flood Mitigation Structure | 120.974 | 14.6778 | 48996551.8 | 48999075.67 | 2023 | ST. TIMOTHY CONSTRUCTION CORPORATION | 3601 | 2022 | 2023-02-08 | 02/14/2022 | 0 | 2523.87 | 2023-02-07 |  | 1
2022 | National Capital Region | MAKATI CITY | CITY OF MAKATI (METROPOLITAN MANILA) | P00620028LZ | Construction of Revetment | 120.9981 | 14.5595 | 86850000 | 85286022 | 2023 | SMPE CONSTRUCTION TRADING CORPORATION (FORMERLY: SMPE CONSTRUCTION SUPPLIES TRADING) | 3602 | 2022 | 2023-05-01 | 03/22/2022 | 1563978 | 0 | 2023-04-30 |  | 1
2023 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00742243LZ | Construction of Flood Mitigation Structure | 120.9616 | 14.6294 | 41579763.89 | 41576933.09 | 2023 | JELSIE CONSTRUCTION & SUPPLY | 3603 | 2023 | 2023-09-19 | 03/20/2023 | 2830.8 | 0 | 2023-09-28 | 9
2021 | Region III | BULACAN |  | P00561531LZ | Construction of Flood Mitigation Structure | 121.01 | 15.2386 | 48999868.8 | 47034974.07 | 2023 | FLORDES CONSTRUCTION & TRADING CORP. (FORMERLY FLO | 3604 | 2021 | 2023-06-26 | 03/30/2022 | 1964894.73 | 0 | 2023-07-26 | 30
2022 | National Capital Region | MAKATI CITY | CITY OF MAKATI (METROPOLITAN MANILA) | P00620372LZ | Rehabilitation / Major Repair of Drainage Structure | 121.0523 | 14.5635 | 22540000 | 22540000 | 2022 | QUATRIX CONSTRUCTION AND SUPPLY INC. | 3605 | 2022 | 2022-08-07 | 02/09/2022 | 0 | 0 | 2022-08-06 |  | 1
2023 | Region IV-A | LAGUNA | CITY OF SAN PEDRO (LAGUNA) | P00742436LZ | Construction of Flood Mitigation Structure | 121.0286 | 14.3317 | 29700000 | 29690058.97 | 2023 | BLACK HARDHAT INC. (FORMERLY: JCHARDHAT INC.) | 3606 | 2023 | 2023-12-09 | 05/23/2023 | 9941.03 | 0 | 2023-12-08 |  | 1
2023 | Region IV-A | CAVITE | SILANG (CAVITE) | P00742168LZ | Construction of Revetment | 120.9741 | 14.2122 | 98999944.79 | 98998197.62 | 2023 | SELPHAR CONSTRUCTION / N.B. AVILA CONSTRUCTION | 3607 | 2023 | 2023-11-09 | 05/10/2023 | 1747.17 | 0 | 2024-05-02 | 175
2023 | Region IV-A | BATANGAS | MALVAR (BATANGAS) | P00742391LZ | Construction of Drainage Structure | 121.0201 | 14.0944 | 4950000 | 4949608.5 | 2023 | OIC CONZTRUCT AND SUPPLY CORPORATION(FORMERLY:OIC CONST.) | 3608 | 2023 | 2023-10-18 | 03/23/2023 | 391.5 | 0 | 2023-10-17 |  | 1
2023 | National Capital Region | SAN JUAN CITY | CITY OF SAN JUAN (METROPOLITAN MANILA) | P00737390LZ | Construction of Slope Protection Structure | 121.0286 | 14.6121 | 48999971.04 | 46526297.54 | 2023 | DAHL CONSTRUCTION CORP. (FORMERLY: DAHL CONSTRUCTION) | 3609 | 2023 | 2023-06-18 | 02/06/2023 | 2473673.5 | 0 | 2023-09-17 | 91
2022 | Region III | BULACAN | CITY OF MEYCAUAYAN (BULACAN) | P00620521LZ | Construction of Flood Mitigation Facility | 120.9742 | 14.7384 | 19607596.69 | 19599270.94 | 2022 | ELITE GENERAL CONTRACTOR AND DEVELOPMENT CORP. | 3610 | 2022 | 2022-08-01 | 02/28/2022 | 8325.75 | 0 | 2022-07-31 |  | 1
2024 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00820056LZ | Construction of Flood Mitigation Facility | 120.9616 | 14.6294 | 66002947.02 | 64471193.37 | 2024 | A.M. SALONG CONSTRUCTION | 3611 | 2024 | 2024-04-15 | 02/08/2024 | 1531753.65 | 0 | 2024-04-14 |  | 1
2021 | National Capital Region | PARAÃ‘AQUE CITY |  | P00525762LZ | Rehabilitation / Major Repair of Drainage Structure | 121.0101 | 14.4668 | 9800000 | 9800000 | 2022 | JALENZ CONSTRUCTION & SUPPLY | 3612 | 2021 | 2022-09-03 | 02/22/2022 | 0 | 0 | 2022-09-02 |  | 1
2024 | Region II | CAGAYAN | CLAVERIA (CAGAYAN) | P00845934LZ | Construction of Flood Mitigation Structure | 121.0524 | 18.5539 | 4950000 | 4898635.01 | 2024 | OCP CONSTRUCTION | 3613 | 2024 | 2024-06-13 | 04/04/2024 | 51364.99 | 0 | 2024-06-29 | 16
2021 | National Capital Region | CITY OF MANILA |  | P00525818LZ | Construction of Flood Mitigation Structure | 120.9982 | 14.6019 | 48999662.04 | 46744194.3 | 2022 | FLORDES CONSTRUCTION & TRADING CORP. (FORMERLY FLO | 3614 | 2021 | 2022-08-20 | 03/24/2021 | 2255467.74 | 0 | 2022-08-19 |  | 1
2022 | Region IV-A | CAVITE | BACOOR CITY (CAVITE) | P00640555LZ | Construction of Flood Mitigation Structure | 121.0101 | 14.3749 | 19800000 | 19794810.23 | 2023 | E. F. CHUA CONSTRUCTION, INC. | 3615 | 2022 | 2023-11-06 | 05/11/2023 | 5189.77 | 0 | 2023-12-05 | 29
2023 | Region IV-A | CAVITE | SILANG (CAVITE) | P00725787LZ | Construction of Flood Mitigation Structure | 120.9982 | 14.2982 | 106150000 | 106148617.7 | 2024 | T.E. TRINIDAD CONSTRUCTION / KLDS TRADING & CONSTRUCTION | 3616 | 2023 | 2024-05-21 | 03/27/2023 | 1382.3 | 0 | 2024-05-20 |  | 1
2024 | Region III | BULACAN | SAN MIGUEL (BULACAN) | P00845781LZ | Construction of Flood Mitigation Structure | 121.0524 | 15.1647 | 98999617.56 | 98999298.67 | 2025 | TOPNOTCH CATALYST BUILDERS INC. / ONE FRAME CONSTRUCTION INC. | 3617 | 2024 | 2025-01-13 | 06/20/2024 | 318.89 | 0 | 2025-05-14 | 121
2022 | Region III | BULACAN | CITY OF MEYCAUAYAN (BULACAN) | P00620519LZ | Construction of Flood Mitigation Facility | 120.9617 | 14.7304 | 19314641.23 | 19005606.97 | 2022 | AZUL BUILDERS | 3618 | 2022 | 2022-10-03 | 02/28/2022 | 309034.26 | 0 | 2022-09-20 |  | 13
2022 | Region IV-A | CAVITE | GEN. MARIANO ALVAREZ (CAVITE) | P00632877LZ | Construction of Drainage Structure | 121.0289 | 14.3181 | 39599727.15 | 4949953.47 | 2022 | TRIPLE 8 CONSTRUCTION & SUPPLY, INC. (FORMERLY TRIPLE 8 CONST. & SUPPLY) | 3619 | 2022 | 2022-08-15 | 02/17/2022 | 34649773.68 | 0 | 2022-08-14 |  | 1
2024 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00820012LZ | Construction of Drainage Structure | 121.0201 | 14.5896 | 57899919.16 | 56694104.59 | 2024 | JCA CONSTRUCTION AND CONSTRUCTION SUPPLY | 3620 | 2024 | 2024-12-10 | 02/08/2024 | 1205814.57 | 0 | 2024-12-27 | 17
2024 | Region III | BULACAN | SAN MIGUEL (BULACAN) | P00823420LZ | Construction of Flood Mitigation Structure | 121.0525 | 15.165 | 96499205.99 | 96499350.3 | 2025 | TOPNOTCH CATALYST BUILDERS INC. / ONE FRAME CONSTRUCTION INC. | 3621 | 2024 | 2025-01-13 | 07/15/2024 | 0 | 144.31 | 2025-06-08 | 146
2022 | National Capital Region | VALENZUELA CITY | CITY OF VALENZUELA (METROPOLITAN MANILA) | P00620080LZ | Rehabilitation / Major Repair of Flood Mitigation Facility | 120.9742 | 14.6778 | 136586332.6 | 132215551.9 | 2023 | NEWBIG FOUR J CONSTRUCTION INC., (FORMERLY FOUR J | 3622 | 2022 | 2023-05-06 | 02/11/2022 | 4370780.7 | 0 | 2023-05-05 |  | 1
2024 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00820655LZ | Construction of Flood Mitigation Structure | 121.0202 | 14.5867 | 39199949.64 | 39199611.71 | 2024 | JIIK CONSTRUCTION SERVICES | 3623 | 2024 | 2024-11-05 | 02/20/2024 | 337.93 | 0 | 2024-11-04 |  | 1
2021 | National Capital Region | CALOOCAN CITY |  | P00525782LZ | Construction of Flood Mitigation Structure | 121.0526 | 14.751 | 29385743.67 | 28680080.5 | 2023 | PERSAN CONSTRUCTION, INC. (FORMERLY: PERSAN CONST. | 3624 | 2021 | 2023-03-27 | 03/24/2022 | 705663.17 | 0 | 2022-11-17 |  | 130
2024 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00838335LZ | Construction of Slope Protection Structure | 120.9982 | 14.5881 | 48249020.17 | 48216273.41 | 2024 | AL-AMEN BUILDERS | 3625 | 2024 | 2024-11-12 | 06/13/2024 | 32746.76 | 0 | 2025-02-16 | 96
2022 | Region III | BULACAN | CITY OF BALIUAG (BULACAN) | P00621573LZ | Construction of Spur Dike | 120.9617 | 14.9354 | 96499750.11 | 96499742.98 | 2023 | A.R.L. CONSTRUCTION | 3626 | 2022 | 2023-02-27 | 04/04/2022 | 7.13 | 0 | 2023-02-26 |  | 1
2024 | Region IV-A | LAGUNA | CITY OF SAN PEDRO (LAGUNA) | P00820385LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.029 | 14.3321 | 14700000 | 14473182.52 | 2024 | MICLOVER GENERAL CONSTRUCTION & IRON WORKS | 3627 | 2024 | 2024-08-07 | 02/16/2024 | 226817.48 | 0 | 2024-08-06 |  | 1
2022 | Region IV-A | CAVITE | GEN. MARIANO ALVAREZ (CAVITE) | P00632882LZ | Construction of Drainage Structure | 121.0291 | 14.327 | 39599727.15 | 6929636.01 | 2022 | TRIPLE 8 CONSTRUCTION & SUPPLY, INC. (FORMERLY TRIPLE 8 CONST. & SUPPLY) | 3628 | 2022 | 2022-08-15 | 02/17/2022 | 32670091.14 | 0 | 2022-08-14 |  | 1
2024 | National Capital Region | PARAÃ‘AQUE CITY | CITY OF PARAÃ‘AQUE (METROPOLITAN MANILA) | P00820577LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.0102 | 14.4536 | 29400000 | 29391551.65 | 2024 | RNN CONSTRUCTION CORPORATION (FORMERLY RNN CONSTRU | 3629 | 2024 | 2024-07-22 | 02/15/2024 | 8448.35 | 0 | 2024-08-01 | 10
2023 | National Capital Region | QUEZON CITY | QUEZON CITY (METROPOLITAN MANILA) | P00726031LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.0203 | 14.6127 | 42433952.54 | 41285159.32 | 2023 | LARSEN-DUTCHER CONSTRACTOR CORPORATION (FORMERLY:LARSEN-DUTCHER CONSTRACTOR) | 3630 | 2023 | 2023-09-21 | 02/17/2023 | 1148793.22 | 0 | 2023-10-13 | 22
2022 | Region IV-A | LAGUNA | CITY OF BIÃ‘AN (LAGUNA) | P00620237LZ | Construction of Revetment | 121.0526 | 14.2545 | 96500000 | 96497537.53 | 2022 | MAR-VEL CONSTRUCTION & SUPPLY | 3631 | 2022 | 2022-12-06 | 03/22/2022 | 2462.47 | 0 | 2023-02-10 | 66
2023 | National Capital Region | PARAÃ‘AQUE CITY | CITY OF PARAÃ‘AQUE (METROPOLITAN MANILA) | P00737394LZ | Construction of Drainage Structure | 121.0104 | 14.4699 | 5049000 | 5046783.6 | 2023 | G.F. ROVERO MERCHANDISING | 3632 | 2023 | 2023-07-14 | 02/15/2023 | 2216.4 | 0 | 2023-07-13 |  | 1
2022 | National Capital Region | SAN JUAN CITY | CITY OF SAN JUAN (METROPOLITAN MANILA) | P00632695LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.0294 | 14.5949 | 68599660.55 | 65144336.31 | 2022 | WAWAO BUILDERS | 3633 | 2022 | 2022-09-12 | 03/14/2022 | 3455324.24 | 0 | 2022-10-08 | 26
2022 | National Capital Region | QUEZON CITY | QUEZON CITY (METROPOLITAN MANILA) | P00637005LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.0204 | 14.6146 | 19299714.15 | 18507478.83 | 2023 | ANORE CONSTRUCTION | 3634 | 2022 | 2023-03-14 | 05/19/2022 | 792235.32 | 0 | 2023-03-13 |  | 1
2022 | National Capital Region | CALOOCAN CITY | CALOOCAN CITY (METROPOLITAN MANILA) | P00632717LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.9743 | 14.6359 | 29684232.02 | 28813987.65 | 2022 | IM CONSTRUCTION CORPORATION | 3635 | 2022 | 2022-12-09 | 03/22/2022 | 870244.37 | 0 | 2023-01-14 | 36
2022 | National Capital Region | QUEZON CITY | QUEZON CITY (METROPOLITAN MANILA) | P00621584LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.0204 | 14.6146 | 22539862.31 | 21807952.15 | 2023 | AARCON BUILDERS | 3636 | 2022 | 2023-09-08 | 10/14/2022 | 731910.16 | 0 | 2023-09-07 |  | 1
2023 | National Capital Region | VALENZUELA CITY | CITY OF VALENZUELA (METROPOLITAN MANILA) | P00726809LZ | Rehabilitation / Major Repair of Flood Mitigation Facility | 120.9744 | 14.6774 | 144749391.9 | 141709642.4 | 2024 | TWO DIMENSION CONSTRUCTION | 3637 | 2023 | 2024-04-19 | 04/28/2023 | 3039749.5 | 0 | 2024-04-20 | 1
2023 | National Capital Region | QUEZON CITY | QUEZON CITY (METROPOLITAN MANILA) | P00726032LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.0204 | 14.6133 | 42433971.39 | 41712122.56 | 2023 | ALGIMAR CONSTRUCTION CORPORATION | 3638 | 2023 | 2023-11-13 | 02/17/2023 | 721848.83 | 0 | 2023-11-12 |  | 1
2024 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00838334LZ | Construction of Slope Protection Structure | 120.9983 | 14.5879 | 48249020.17 | 48220023.12 | 2024 | JELSIE CONSTRUCTION & SUPPLY | 3639 | 2024 | 2024-11-12 | 06/13/2024 | 28997.05 | 0 | 2025-02-16 | 96
2022 | National Capital Region | CALOOCAN CITY | CALOOCAN CITY (METROPOLITAN MANILA) | P00632719LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.9744 | 14.6355 | 39582905.85 | 38405318.07 | 2022 | J. SIMEON CONSTRUCTION | 3640 | 2022 | 2022-11-22 | 03/22/2022 | 1177587.78 | 0 | 2023-01-14 | 53
2022 | National Capital Region | MUNTINLUPA CITY | CITY OF MUNTINLUPA (METROPOLITAN MANILA) | P00620761LZ | Construction of Flood Mitigation Structure | 121.0532 | 14.4261 | 92638315.6 | 92634372.43 | 2023 | E. F. CHUA CONSTRUCTION, INC. | 3641 | 2022 | 2023-01-02 | 02/17/2022 | 3943.17 | 0 | 2023-01-01 |  | 1
2022 | National Capital Region | QUEZON CITY | QUEZON CITY (METROPOLITAN MANILA) | P00637000LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.0204 | 14.615 | 28949494.34 | 28931540.41 | 2023 | MSB VITUG CONSTRUCTION | 3642 | 2022 | 2023-08-10 | 05/18/2022 | 17953.93 | 0 | 2023-08-09 |  | 1
2022 | Region IV-A | CAVITE | BACOOR CITY (CAVITE) | P00640465LZ | Construction of Slope Protection Structure | 121.0106 | 14.3763 | 69300000 | 69296494.5 | 2023 | E. F. CHUA CONSTRUCTION, INC. | 3643 | 2022 | 2023-08-16 | 06/28/2022 | 3505.5 | 0 | 2023-08-15 |  | 1
2024 | National Capital Region | QUEZON CITY | QUEZON CITY (METROPOLITAN MANILA) | P00821454LZ | Construction of Revetment | 121.0296 | 14.6631 | 29399608.72 | 28805612.63 | 2024 | OSCORD BUILDERS CORPORATION | 3644 | 2024 | 2024-09-02 | 02/06/2024 | 593996.09 | 0 | 2024-09-01 |  | 1
2023 | National Capital Region | VALENZUELA CITY | CITY OF VALENZUELA (METROPOLITAN MANILA) | P00740504LZ | Construction of Drainage Structure | 120.9745 | 14.6933 | 19595421.06 | 19125110.85 | 2024 | SONPRO CONSTRUCTION | 3645 | 2023 | 2024-04-12 | 06/19/2023 | 470310.21 | 0 | 2024-04-12 | 0
2023 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00726005LZ | Construction of Flood Mitigation Facility | 120.9984 | 14.6024 | 48999803.13 | 48999599.71 | 2023 | JELSIE CONSTRUCTION & SUPPLY | 3646 | 2023 | 2023-07-27 | 02/17/2023 | 203.42 | 0 | 2023-08-20 | 24
2022 | National Capital Region | MUNTINLUPA CITY | CITY OF MUNTINLUPA (METROPOLITAN MANILA) | P00631005LZ | Construction of Flood Mitigation Structure | 121.0532 | 14.4673 | 48999647.28 | 48992948.19 | 2024 | L.M.G. CONSTRUCTION INCORPORATED (FORMERLY: LMG CONSTRUCTION) | 3647 | 2022 | 2024-04-14 | 02/09/2022 | 6699.09 | 0 | 2024-04-11 |  | 3
2021 | Region III | BULACAN |  | P00526006LZ | Construction of Flood Mitigation Structure | 121.0299 | 14.938 | 48999908.86 | 48999950.46 | 2022 | FLORDES CONSTRUCTION & TRADING CORP. (FORMERLY FLO | 3648 | 2021 | 2022-09-09 | 03/08/2021 | 0 | 41.6 | 2022-09-08 |  | 1
2024 | National Capital Region | PARAÃ‘AQUE CITY | CITY OF PARAÃ‘AQUE (METROPOLITAN MANILA) | P00820563LZ | Construction of Revetment | 121.0106 | 14.5 | 34300000 | 34298335.11 | 2024 | RNN CONSTRUCTION CORPORATION (FORMERLY RNN CONSTRU / AKN CONSTRUCTION CORPORATION | 3649 | 2024 | 2024-05-20 | 02/07/2024 | 1664.89 | 0 | 2024-06-04 | 15
2022 | National Capital Region | QUEZON CITY | QUEZON CITY (METROPOLITAN MANILA) | P00621437LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.0204 | 14.615 | 39199401.97 | 39138751.35 | 2023 | ST. MATTHEW GEN. CONTRACTOR & DEVELOPMENT CORP. | 3650 | 2022 | 2023-03-14 | 05/19/2022 | 60650.62 | 0 | 2023-03-13 |  | 1
2022 | National Capital Region | PARAÃ‘AQUE CITY | CITY OF PARAÃ‘AQUE (METROPOLITAN MANILA) | P00621418LZ | Construction of Revetment | 120.9987 | 14.4786 | 49000000 | 46468523.24 | 2022 | SPRING STAR CONSTRUCTION AND SUPPLY | 3651 | 2022 | 2022-11-16 | 03/22/2022 | 2531476.76 | 0 | 2022-11-15 |  | 1
2023 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00737400LZ | Rehabilitation / Major Repair of Drainage Structure | 120.9619 | 14.5986 | 19799884.8 | 19798429.06 | 2024 | JJPR CONSTRUCTION SERVICES | 3652 | 2023 | 2024-09-20 | 02/14/2023 | 1455.74 | 0 | 2024-10-12 | 22
2023 | Cordillera Administrative Region | APAYAO | CALANASAN (BAYAG) (APAYAO) | P00735962LZ | Construction of Flood Mitigation Structure | 120.9745 | 18.3633 | 96500000 | 96500000 | 2024 | TAGEL CORPORATION | 3653 | 2023 | 2024-02-07 | 03/23/2023 | 0 | 0 | 2024-03-25 | 47
2023 | National Capital Region | PARAÃ‘AQUE CITY | CITY OF PARAÃ‘AQUE (METROPOLITAN MANILA) | P00742114LZ | Construction of Revetment | 120.9987 | 14.5224 | 99000000 | 98995281.56 | 2024 | E.R. RODRIGUEZ CONSTRUCTION CORPORATION (FORMERLY: E.R. RODRIGUEZ CONSTRUCTION) | 3654 | 2023 | 2024-04-10 | 04/17/2023 | 4718.44 | 0 | 2024-04-09 |  | 1
2024 | Region III | BULACAN | CITY OF SAN JOSE DEL MONTE (BULACAN) | P00844753LZ | Construction of Slope Protection Structure | 121.0534 | 14.8651 | 48999949.56 | 48260050.31 | 2024 | 1199S CONSTRUCTION / C.T. LEONCIO CONSTRUCTION & TRADING | 3655 | 2024 | 2024-08-12 | 04/30/2024 | 739899.25 | 0 | 2024-10-21 | 70
2022 | National Capital Region | CALOOCAN CITY | CALOOCAN CITY (METROPOLITAN MANILA) | P00620403LZ | Construction of Flood Mitigation Structure | 121.0106 | 14.7347 | 29385289.41 | 28474341.53 | 2022 | JAGONBUILD CONSTRUCTION CORP. (FOR. JAGON BUILDERS | 3656 | 2022 | 2022-11-11 | 02/08/2022 | 910947.88 | 0 | 2022-12-03 | 22
2022 | National Capital Region | LAS PIÃ‘AS CITY | CITY OF LAS PIÃ‘AS (METROPOLITAN MANILA) | P00620336LZ | Rehabilitation / Major Repair of Drainage Structure | 121.0205 | 14.4195 | 48999999.24 | 48998499.24 | 2022 | I&E CONSTRUCTION CORPORATION (FORMERLY: I&E CONSTR | 3657 | 2022 | 2022-11-04 | 02/09/2022 | 1500 | 0 | 2022-11-03 |  | 1
2024 | National Capital Region | PARAÃ‘AQUE CITY | CITY OF PARAÃ‘AQUE (METROPOLITAN MANILA) | P00823259LZ | Construction of Drainage Structure | 121.0299 | 14.4677 | 96500000 | 96500000 | 2024 | RAICON DEVELOPMENT CORPORATION (FORMERLY : RA IGNACIO CONST. CORP.) / P.L.G.L. CONSTRUCTION | 3658 | 2024 | 2024-12-27 | 04/05/2024 | 0 | 0 | 2025-01-28 | 32
2022 | Region IV-A | CAVITE | CITY OF DASMARIÃ‘AS (CAVITE) | P00620878LZ | Construction of Revetment | 120.9635 | 14.3148 | 94305502.49 | 94300703.89 | 2023 | L.R. TIQUI BUILDERS, INC. | 3659 | 2022 | 2023-04-18 | 02/23/2022 | 4798.6 | 0 | 2023-04-17 |  | 1
2022 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00620435LZ | Construction of Flood Mitigation Structure | 120.9988 | 14.6005 | 48998176.84 | 46796995.89 | 2023 | FLORDES CONSTRUCTION & TRADING CORP. (FORMERLY FLO | 3660 | 2022 | 2023-02-26 | 02/16/2022 | 2201180.95 | 0 | 2023-02-25 |  | 1
2024 | Region IV-A | BATANGAS | BATANGAS CITY (CAPITAL) (BATANGAS) | P00823546LZ | Construction of Flood Mitigation Structure | 121.0535 | 13.6715 | 96500000 | 96500000 | 2024 | TRISTAN TEJADA CONSTRUCTION (FORMERLY: JOMATRIS CO | 3661 | 2024 | 2024-12-06 | 05/13/2024 | 0 | 0 | 2025-01-03 | 28
2022 | Region IV-A | CAVITE | BACOOR CITY (CAVITE) | P00639488LZ | Construction of Slope Protection Structure | 121.0107 | 14.3746 | 28950000 | 28946909.86 | 2023 | E. F. CHUA CONSTRUCTION, INC. | 3662 | 2022 | 2023-10-15 | 10/19/2022 | 3090.14 | 0 | 2023-10-14 |  | 1
2023 | Region III | NUEVA ECIJA | CABANATUAN CITY (NUEVA ECIJA) | P00742339LZ | Construction of Drainage Structure | 120.9643 | 15.4931 | 4949925.67 | 4890460.8 | 2023 | CELSO C. FERRER CONSTRUCTION CORP. | 3663 | 2023 | 2023-09-06 | 03/29/2023 | 59464.87 | 0 | 2023-09-05 |  | 1
2022 | National Capital Region | VALENZUELA CITY | CITY OF VALENZUELA (METROPOLITAN MANILA) | P00632715LZ | Construction of Drainage Structure | 120.9747 | 14.6932 | 9758644.67 | 9553691.37 | 2022 | SONPRO CONSTRUCTION | 3664 | 2022 | 2022-10-04 | 02/08/2022 | 204953.3 | 0 | 2022-10-04 | 0
2022 | National Capital Region | QUEZON CITY | QUEZON CITY (METROPOLITAN MANILA) | P00631037LZ | Construction of Flood Mitigation Structure | 121.0206 | 14.6744 | 14700000 | 14260635.6 | 2022 | MSV CONSTRUCTION AND SUPPLIES | 3665 | 2022 | 2022-10-21 | 02/24/2022 | 439364.4 | 0 | 2022-10-20 |  | 1
2022 | Region III | BULACAN | ANGAT (BULACAN) | P00621077LZ | Construction of Flood Mitigation Structure | 121.03 | 14.9181 | 47529768.97 | 46816820.82 | 2022 | MRRM TRADING & CONSTRUCTION / GDL CONSTRUCTION | 3666 | 2022 | 2022-10-14 | 03/30/2022 | 712948.15 | 0 | 2022-10-13 |  | 1
2021 | National Capital Region | CALOOCAN CITY |  | P00525791LZ | Construction of Flood Mitigation Structure | 120.999 | 14.6825 | 9792054.79 | 9548275.07 | 2022 | TOPNOTCH CATALYST BUILDERS INC. | 3667 | 2021 | 2022-08-19 | 03/24/2022 | 243779.72 | 0 | 2022-08-19 | 0
2023 | National Capital Region | QUEZON CITY | QUEZON CITY (METROPOLITAN MANILA) | P00726017LZ | Construction of Flood Mitigation Structure | 121.0301 | 14.7311 | 19599857.14 | 19584084.67 | 2023 | A.T. DUMLAO CONSTRUCTION, INC. FORMERLYANDONI T. D | 3668 | 2023 | 2023-10-09 | 02/13/2023 | 15772.47 | 0 | 2023-10-09 | 0
2024 | National Capital Region | TAGUIG CITY | TAGUIG CITY (METROPOLITAN MANILA) | P00821061LZ | Construction of Slope Protection Structure | 121.0537 | 14.5234 | 135306927.6 | 125754544.8 | 2025 | DAHL CONSTRUCTION CORP. (FORMERLY: DAHL CONSTRUCTION) | 3669 | 2024 | 2025-02-01 | 05/29/2024 | 9552382.8 | 0 | 2025-02-21 | 20
2023 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00726034LZ | Construction of Flood Mitigation Structure | 121.0107 | 14.5808 | 48999300.2 | 47852928.28 | 2024 | N.M.E. CONSTRUCTION | 3670 | 2023 | 2024-03-15 | 02/20/2023 | 1146371.92 | 0 | 2024-03-14 |  | 1
2022 | National Capital Region | MALABON CITY | CITY OF MALABON (METROPOLITAN MANILA) | P00620012LZ | Construction of Flood Mitigation Structure | 120.9643 | 14.6754 | 92101390 | 90686286.95 | 2023 | ALPHA & OMEGA GEN. CONTRACTOR & DEVELOPMENT CORP. / CALCON ENGINEERING | 3671 | 2022 | 2023-04-14 | 02/21/2022 | 1415103.05 | 0 | 2023-04-13 |  | 1
2024 | Region IV-A | BATANGAS | SAN PASCUAL (BATANGAS) | P00823540LZ | Construction of Flood Mitigation Structure | 121.0206 | 13.7879 | 14700000 | 14475000 | 2024 | GREENFIELD CONSTRUCTION | 3672 | 2024 | 2024-05-15 | 02/07/2024 | 225000 | 0 | 2024-06-07 | 23
2020 | National Capital Region | LAS PIÃ‘AS CITY |  | P00449023LZ | Construction of Flood Mitigation Structure | 120.9991 | 14.4294 | 29397952.78 | 29397952.78 | 2022 | ROCKSTEEL CONSTRUCTION AND DEV'T CORPORATION | 3673 | 2020 | 2022-07-07 | 10/16/2020 | 0 | 0 | 2021-07-06 |  | 366
2023 | National Capital Region | CALOOCAN CITY | CALOOCAN CITY (METROPOLITAN MANILA) | P00725543LZ | Construction of Flood Mitigation Structure | 121.0301 | 14.7682 | 86846459.75 | 85283270.22 | 2023 | FRAMECON BUILDERS | 3674 | 2023 | 2023-10-10 | 02/21/2023 | 1563189.53 | 0 | 2024-01-15 | 97
2022 | Cordillera Administrative Region | MOUNTAIN PROVINCE | BONTOC (CAPITAL) (MOUNTAIN PROVINCE) | P00621011LZ | Construction of Flood Mitigation Structure | 121.0108 | 17.0386 | 24499999.2 | 24500000 | 2022 | SADLAN CONSTRUCTION | 3675 | 2022 | 2022-11-18 | 02/17/2022 | 0 | 0.8 | 2022-09-28 |  | 51
2022 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00631035LZ | Rehabilitation / Major Repair of Drainage Structure | 120.9647 | 14.6184 | 48999350 | 47478231.14 | 2022 | ALLEYWAY CONSTRUCTION | 3676 | 2022 | 2022-12-19 | 02/18/2022 | 1521118.86 | 0 | 2022-12-25 | 6
2024 | National Capital Region | TAGUIG CITY | TAGUIG CITY (METROPOLITAN MANILA) | P00821062LZ | Construction of Slope Protection Structure | 121.0537 | 14.5234 | 96499448.22 | 90685600.66 | 2025 | J. SIMEON CONSTRUCTION | 3677 | 2024 | 2025-02-01 | 05/29/2024 | 5813847.56 | 0 | 2025-01-22 |  | 10
2024 | National Capital Region | TAGUIG CITY | TAGUIG CITY (METROPOLITAN MANILA) | P00821060LZ | Construction of Slope Protection Structure | 121.0537 | 14.5234 | 96499553.91 | 88779589.6 | 2025 | RVR3 CONSTRUCTION SUPPLY AND SERVICES | 3678 | 2024 | 2025-02-01 | 06/04/2024 | 7719964.31 | 0 | 2025-02-27 | 26
2024 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00823274LZ | Rehabilitation / Major Repair of Flood Mitigation Facility | 120.9748 | 14.5962 | 144749640.9 | 143198795.2 | 2024 | EIGHT J'S CONSTRUCTION SERVICES / MNJAP CONSTRUCTION SERVICES | 3679 | 2024 | 2024-09-20 | 02/20/2024 | 1550845.7 | 0 | 2024-09-29 | 9
2022 | National Capital Region | PARAÃ‘AQUE CITY | CITY OF PARAÃ‘AQUE (METROPOLITAN MANILA) | P00620924LZ | Construction of Flood Mitigation Structure | 121.0209 | 14.459 | 49000000 | 49000000 | 2022 | ALPHA & OMEGA GEN. CONTRACTOR & DEVELOPMENT CORP. | 3680 | 2022 | 2022-12-26 | 02/04/2022 | 0 | 0 | 2022-12-25 |  | 1
2023 | National Capital Region | QUEZON CITY | QUEZON CITY (METROPOLITAN MANILA) | P00726023LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.0539 | 14.7126 | 48999699 | 47990305.2 | 2023 | MRB11 CONSTRUCTION CORPORATION (FORMERLY:MRB CONS / MANCOL CONSTRUCTION CORPORATION | 3681 | 2023 | 2023-11-27 | 02/13/2023 | 1009393.8 | 0 | 2023-12-08 | 11
2022 | National Capital Region | VALENZUELA CITY | CITY OF VALENZUELA (METROPOLITAN MANILA) | P00632716LZ | Construction of Drainage Structure | 120.9749 | 14.694 | 14838097.44 | 14511642.75 | 2022 | SONPRO CONSTRUCTION | 3682 | 2022 | 2022-12-03 | 02/08/2022 | 326454.69 | 0 | 2022-07-06 |  | 150
2023 | Cordillera Administrative Region | IFUGAO | TINOC (IFUGAO) | P00726856LZ | Construction of Flood Mitigation Structure | 120.9647 | 16.585 | 78902210.58 | 78908050 | 2024 | PAULA MAE BUHONG CONSTRUCTION / DJY CONSTRUCTION | 3683 | 2023 | 2024-01-07 | 04/12/2023 | 0 | 5839.42 | 2024-01-06 |  | 1
2024 | National Capital Region | PARAÃ‘AQUE CITY | CITY OF PARAÃ‘AQUE (METROPOLITAN MANILA) | P00838468LZ | Construction of Revetment | 121.0109 | 14.4558 | 29400000 | 29397318.91 | 2024 | RNN CONSTRUCTION CORPORATION (FORMERLY RNN CONSTRU | 3684 | 2024 | 2024-07-19 | 02/16/2024 | 2681.09 | 0 | 2024-09-30 | 73
2022 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00620434LZ | Construction of Flood Mitigation Structure | 120.9991 | 14.6007 | 48996942.66 | 47470673.29 | 2023 | FLORDES CONSTRUCTION & TRADING CORP. (FORMERLY FLO | 3685 | 2022 | 2023-02-26 | 02/16/2022 | 1526269.37 | 0 | 2023-02-25 |  | 1
2022 | Region III | BULACAN | CITY OF SAN JOSE DEL MONTE (BULACAN) | P00620165LZ | Construction of Flood Mitigation Structure | 121.0302 | 14.7826 | 94569976.6 | 94569849.55 | 2023 | ROYAL CROWN MONARCH CONSTRUCTION & SUPPLIES CORP. | 3686 | 2022 | 2023-02-10 | 03/07/2022 | 127.05 | 0 | 2023-02-09 |  | 1
2023 | Region IV-A | CAVITE | CITY OF CARMONA (CAVITE) | P00726219LZ | Construction of Revetment | 121.0541 | 14.3093 | 88199984.47 | 44099982.24 | 2023 | AARCON BUILDERS | 3687 | 2023 | 2023-09-18 | 02/16/2023 | 44100002.23 | 0 | 2023-09-27 | 9
2022 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00620428LZ | Construction of Flood Mitigation Structure | 120.9649 | 14.6256 | 44690884.57 | 42723595.09 | 2022 | J. SIMEON CONSTRUCTION | 3688 | 2022 | 2022-11-15 | 02/24/2022 | 1967289.48 | 0 | 2022-11-21 | 6
2022 | National Capital Region | PARAÃ‘AQUE CITY | CITY OF PARAÃ‘AQUE (METROPOLITAN MANILA) | P00620921LZ | Construction of Flood Mitigation Structure | 121.0109 | 14.5 | 49000000 | 48996514.9 | 2022 | AKN CONSTRUCTION CORPORATION | 3689 | 2022 | 2022-10-01 | 02/04/2022 | 3485.1 | 0 | 2022-09-30 |  | 1
2022 | National Capital Region | QUEZON CITY | QUEZON CITY (METROPOLITAN MANILA) | P00637001LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.0209 | 14.6148 | 28949335.51 | 28939587.28 | 2023 | FRAMECON BUILDERS | 3690 | 2022 | 2023-10-04 | 05/18/2022 | 9748.23 | 0 | 2023-11-01 | 28
2022 | Region III | BULACAN | ANGAT (BULACAN) | P00621475LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.0303 | 14.9215 | 82024587.1 | 80794218.29 | 2022 | ST. MATTHEW GEN. CONTRACTOR & DEVELOPMENT CORP. | 3691 | 2022 | 2022-12-13 | 03/30/2022 | 1230368.81 | 0 | 2022-12-12 |  | 1
2023 | Region IV-A | LAGUNA | CITY OF SANTA ROSA (LAGUNA) | P00725848LZ | Construction of Flood Mitigation Structure | 121.0541 | 14.2564 | 96500000 | 96498871.76 | 2024 | GREAT PACIFIC BUILDERS AND GEN. CONTRACTOR INC. | 3692 | 2023 | 2024-01-16 | 02/24/2023 | 1128.24 | 0 | 2024-01-15 |  | 1
2023 | Region III | BULACAN | SANTA MARIA (BULACAN) | P00725747LZ | Construction of Dike | 120.9751 | 14.8179 | 86849259.29 | 86849185.16 | 2024 | M3 KONSTRACT CORPORATION (FORMERLY:MARGARITA CONSTRUCTION) | 3693 | 2023 | 2024-03-31 | 04/24/2023 | 74.13 | 0 | 2024-03-30 |  | 1
2022 | National Capital Region | PARAÃ‘AQUE CITY | CITY OF PARAÃ‘AQUE (METROPOLITAN MANILA) | P00637006LZ | Construction of Flood Mitigation Structure | 120.9992 | 14.4962 | 77200000 | 77200000 | 2023 | RAICON DEVELOPMENT CORPORATION (FORMERLY : RA IGNACIO CONST. CORP.) / P.L.G.L. CONSTRUCTION | 3694 | 2022 | 2023-01-17 | 03/24/2022 | 0 | 0 | 2023-01-16 |  | 1
2024 | Cordillera Administrative Region | IFUGAO | TINOC (IFUGAO) | P00820148LZ | Construction of Flood Mitigation Structure | 120.9654 | 16.5938 | 96497181.48 | 96500000 | 2024 | PAULA MAE BUHONG CONSTRUCTION / DJY CONSTRUCTION | 3695 | 2024 | 2024-10-31 | 03/18/2024 | 0 | 2818.52 | 2024-10-30 |  | 1
2022 | Region IV-B | OCCIDENTAL MINDORO | RIZAL (OCCIDENTAL MINDORO) | P00632932LZ | Construction of Flood Mitigation Structure | 121.0109 | 12.5291 | 7920000 | 7794888.79 | 2023 | R.S. TAGALA CONSTRUCTION AND EQUIPMENT RENTALS | 3696 | 2022 | 2023-04-20 | 03/11/2022 | 125111.21 | 0 | 2023-01-26 |  | 84
2022 | Region II | NUEVA VIZCAYA | ARITAO (NUEVA VIZCAYA) | P00640510LZ | Construction of Flood Mitigation Structure | 121.0303 | 16.2874 | 49000000 | 48296850.24 | 2022 | AMP 723 CONSTRUCTION CORPORATION (FORMERLY: A.M.P. CONSTRUCTION) | 3697 | 2022 | 2022-11-15 | 03/24/2022 | 703149.76 | 0 | 2023-01-01 | 47
2022 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00620093LZ | Construction of Flood Mitigation Facility | 120.9751 | 14.6353 | 55729550.05 | 54194662.38 | 2022 | EIGHT J'S CONSTRUCTION SERVICES | 3698 | 2022 | 2022-10-17 | 02/17/2022 | 1534887.67 | 0 | 2022-10-16 |  | 1
2023 | Region IV-A | LAGUNA | CITY OF SANTA ROSA (LAGUNA) | P00725849LZ | Construction of Flood Mitigation Structure | 121.0543 | 14.2529 | 96500000 | 93764149.89 | 2024 | MAR-VEL CONSTRUCTION & SUPPLY | 3699 | 2023 | 2024-03-20 | 02/28/2023 | 2735850.11 | 0 | 2024-03-19 |  | 1
2022 | National Capital Region | QUEZON CITY | QUEZON CITY (METROPOLITAN MANILA) | P00621438LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.0209 | 14.6148 | 39199586.64 | 37595806.22 | 2023 | ANORE CONSTRUCTION | 3700 | 2022 | 2023-04-04 | 05/19/2022 | 1603780.42 | 0 | 2023-04-03 |  | 1
2022 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00620091LZ | Construction of Flood Mitigation Facility | 120.9751 | 14.6353 | 96499080.86 | 96055346.98 | 2022 | ST. TIMOTHY CONSTRUCTION CORPORATION / A.M. SALONG CONSTRUCTION | 3701 | 2022 | 2022-11-16 | 02/23/2022 | 443733.88 | 0 | 2022-11-18 | 2
2023 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00726006LZ | Construction of Flood Mitigation Structure | 120.9993 | 14.5997 | 34784752 | 34782628.8 | 2023 | FLORDES CONSTRUCTION & TRADING CORP. (FORMERLY FLO | 3702 | 2023 | 2023-12-12 | 02/16/2023 | 2123.2 | 0 | 2023-12-11 |  | 1
2022 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00620062LZ | Rehabilitation / Major Repair of Drainage Structure | 120.9655 | 14.6063 | 72374986.27 | 69085265.27 | 2023 | EIGHT J'S CONSTRUCTION SERVICES | 3703 | 2022 | 2023-12-13 | 04/01/2022 | 3289721 | 0 | 2023-12-12 |  | 1
2021 | National Capital Region | QUEZON CITY |  | P00561444LZ | Construction of Flood Mitigation Structure | 121.0109 | 14.6413 | 98000000 | 94973033 | 2022 | PRECIOUS CONSTRUCTION / KING EIGHT BUILDERS AND SUPPLY | 3704 | 2021 | 2022-12-28 | 12/07/2021 | 3026967 | 0 | 2022-11-30 |  | 28
2023 | National Capital Region | CALOOCAN CITY | CALOOCAN CITY (METROPOLITAN MANILA) | P00736167LZ | Construction of Drainage Structure | 121.0304 | 14.7721 | 20575261.35 | 20143168.25 | 2023 | PERSAN CONSTRUCTION, INC. (FORMERLY: PERSAN CONST. | 3705 | 2023 | 2023-11-16 | 02/21/2023 | 432093.1 | 0 | 2023-11-16 | 0
2023 | National Capital Region | CALOOCAN CITY | CALOOCAN CITY (METROPOLITAN MANILA) | P00727015LZ | Construction of Flood Mitigation Structure | 121.0543 | 14.7626 | 24495955.56 | 23952759.89 | 2023 | CALCON ENGINEERING | 3706 | 2023 | 2023-11-27 | 05/19/2023 | 543195.67 | 0 | 2023-11-13 |  | 14
2024 | National Capital Region | PARAÃ‘AQUE CITY | CITY OF PARAÃ‘AQUE (METROPOLITAN MANILA) | P00838467LZ | Construction of Revetment | 120.9993 | 14.4856 | 39200000 | 39200000 | 2024 | TWO DIMENSION CONSTRUCTION | 3707 | 2024 | 2024-12-15 | 02/20/2024 | 0 | 0 | 2024-12-14 |  | 1
2024 | Region IV-A | BATANGAS | SAN PASCUAL (BATANGAS) | P00823536LZ | Construction of Flood Mitigation Structure | 121.021 | 13.7851 | 29400000 | 28950000 | 2024 | N.D.M. SANCHEZ BUILDERS & DEVELOPMENT CORPORATION | 3708 | 2024 | 2024-07-02 | 02/07/2024 | 450000 | 0 | 2024-07-01 |  | 1
2023 | National Capital Region | VALENZUELA CITY | CITY OF VALENZUELA (METROPOLITAN MANILA) | P00725995LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.9758 | 14.6771 | 20229456.94 | 19764178 | 2023 | GLOBALCRETE BUILDERS INC. | 3709 | 2023 | 2023-10-18 | 02/21/2023 | 465278.94 | 0 | 2023-10-17 |  | 1
2021 | National Capital Region | MAKATI CITY |  | P00525749LZ | Construction of Flood Mitigation Structure | 121.0109 | 14.5621 | 39954600 | 37994635.32 | 2022 | E. F. CHUA CONSTRUCTION, INC. | 3710 | 2021 | 2022-08-22 | 04/12/2021 | 1959964.68 | 0 | 2021-10-07 |  | 319
2022 | Region II | NUEVA VIZCAYA | KAYAPA (NUEVA VIZCAYA) | P00620827LZ | Construction of Flood Mitigation Structure | 120.966 | 16.327 | 91675000 | 91506760.15 | 2022 | BRG CONSTRUCTION | 3711 | 2022 | 2022-09-20 | 03/04/2022 | 168239.85 | 0 | 2023-02-02 | 135
2023 | National Capital Region | SAN JUAN CITY | CITY OF SAN JUAN (METROPOLITAN MANILA) | P00726999LZ | Rehabilitation / Major Repair of Drainage Structure | 121.0306 | 14.5959 | 44099966.17 | 41851062.78 | 2024 | KING EIGHT BUILDERS AND SUPPLY / WAWAO BUILDERS | 3712 | 2023 | 2024-09-24 | 03/22/2023 | 2248903.39 | 0 | 2024-02-17 |  | 220
2025 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00920747LZ | Construction of Flood Mitigation Structure | 120.9664 | 14.6264 | 14699517.08 | 14552258.16 | 2025 | XIEH CONSTRUCTION | 3713 | 2025 | 2025-04-21 | 02/11/2025 | 147258.92 | 0 | 2025-06-11 | 51
2022 | National Capital Region | QUEZON CITY | QUEZON CITY (METROPOLITAN MANILA) | P00637760LZ | Rehabilitation / Major Repair of Drainage Structure | 121.0543 | 14.6421 | 13859899.85 | 13854876.21 | 2023 | 5-1 CONSTRUCTION CORPORATION | 3714 | 2022 | 2023-03-17 | 08/16/2022 | 5023.64 | 0 | 2023-04-13 | 27
2022 | National Capital Region | LAS PIÃ‘AS CITY | CITY OF LAS PIÃ‘AS (METROPOLITAN MANILA) | P00637037LZ | Rehabilitation / Major Repair of Drainage Structure | 120.9997 | 14.4232 | 29399056.65 | 29354056.65 | 2022 | I&E CONSTRUCTION CORPORATION (FORMERLY: I&E CONSTR | 3715 | 2022 | 2022-09-03 | 04/07/2022 | 45000 | 0 | 2022-09-02 |  | 1
2024 | Region IV-A | CAVITE | BACOOR CITY (CAVITE) | P00820356LZ | Construction of Revetment | 120.9758 | 14.4154 | 113366253 | 113365255.7 | 2024 | R.K.F. BUILDERS / OMNICON BUILDERS | 3716 | 2024 | 2024-12-03 | 03/08/2024 | 997.3 | 0 | 2025-02-08 | 67
2022 | Region IV-A | CAVITE | SILANG (CAVITE) | P00621296LZ | Construction of Revetment | 120.9758 | 14.2148 | 96499969.55 | 96499745.3 | 2023 | SELPHAR CONSTRUCTION / N.B. AVILA CONSTRUCTION | 3717 | 2022 | 2023-01-31 | 04/13/2022 | 224.25 | 0 | 2023-03-07 | 35
2022 | Region IV-A | CAVITE | SILANG (CAVITE) | P00620862LZ | Construction of Revetment | 120.9758 | 14.2149 | 78164983.08 | 78164480.21 | 2023 | PRIME PACIFIC MARINE & INDUSTRIAL SERVICES CORP. | 3718 | 2022 | 2023-11-06 | 02/23/2022 | 502.87 | 0 | 2023-11-05 |  | 1
2023 | Region III | NUEVA ECIJA | LLANERA (NUEVA ECIJA) | P00726924LZ | Construction of Flood Mitigation Structure | 121.0113 | 15.7478 | 85755690 | 84040574.73 | 2023 | WIZARD CONCRETE SOLUTIONS AND CONSTRUCTION CORPORATION (FORMERLY: WIZARD TRADING & CONSTRUCTION) | 3719 | 2023 | 2023-10-18 | 03/24/2023 | 1715115.27 | 0 | 2023-11-17 | 30
2023 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00725504LZ | Construction of Flood Mitigation Facility | 120.9759 | 14.6058 | 86849820.61 | 84943784.66 | 2023 | AL-AMEN BUILDERS / ST. TIMOTHY CONSTRUCTION CORPORATION | 3720 | 2023 | 2023-07-16 | 02/17/2023 | 1906035.95 | 0 | 2023-07-15 |  | 1
2024 | National Capital Region | PARAÃ‘AQUE CITY | CITY OF PARAÃ‘AQUE (METROPOLITAN MANILA) | P00823260LZ | Construction of Drainage Structure | 121.0306 | 14.4716 | 48250000 | 48250000 | 2024 | JELSIE CONSTRUCTION & SUPPLY | 3721 | 2024 | 2024-12-12 | 07/08/2024 | 0 | 0 | 2025-02-01 | 51
2022 | National Capital Region | CALOOCAN CITY | CALOOCAN CITY (METROPOLITAN MANILA) | P00639411LZ | Construction of Flood Mitigation Structure | 121.0212 | 14.7429 | 39198111.93 | 38155429.67 | 2022 | WAWAO BUILDERS | 3722 | 2022 | 2022-09-15 | 03/24/2022 | 1042682.26 | 0 | 2023-02-15 | 153
2022 | National Capital Region | CALOOCAN CITY | CALOOCAN CITY (METROPOLITAN MANILA) | P00632718LZ | Rehabilitation / Major Repair of Drainage Structure | 120.9665 | 14.6574 | 29394040.47 | 28746683.24 | 2022 | C.L. MORALES CONSTRUCTION AND TRADING | 3723 | 2022 | 2022-09-05 | 02/08/2022 | 647357.23 | 0 | 2022-12-03 | 89
2022 | Region IV-A | LAGUNA | CITY OF SAN PEDRO (LAGUNA) | P00620588LZ | Construction of Flood Mitigation Structure | 121.0544 | 14.3755 | 24500000 | 24468394.71 | 2022 | DATZLAV CONSTRUCTION | 3724 | 2022 | 2022-10-06 | 02/21/2022 | 31605.29 | 0 | 2022-10-05 |  | 1
2024 | Region III | BULACAN | CITY OF MEYCAUAYAN (BULACAN) | P00839581LZ | Construction of Flood Mitigation Structure | 121.0213 | 14.773 | 4949613.15 | 4949040.88 | 2024 | TM ABAD CONSTRUCTION CORP. (FOR: TM ABAD CONST.) | 3725 | 2024 | 2024-04-26 | 02/12/2024 | 572.27 | 0 | 2024-04-25 |  | 1
2023 | National Capital Region | MAKATI CITY | CITY OF MAKATI (METROPOLITAN MANILA) | P00725977LZ | Rehabilitation / Major Repair of Drainage Structure | 121.0113 | 14.574 | 49000000 | 48991852.57 | 2024 | AL-REM KONSTRUCT INC. | 3726 | 2023 | 2024-03-07 | 04/12/2023 | 8147.43 | 0 | 2024-03-06 |  | 1
2022 | National Capital Region | PARAÃ‘AQUE CITY | CITY OF PARAÃ‘AQUE (METROPOLITAN MANILA) | P00620026LZ | Construction of Flood Mitigation Facility | 120.9998 | 14.4799 | 96500000 | 96497599.08 | 2023 | AKN CONSTRUCTION CORPORATION | 3727 | 2022 | 2023-06-16 | 03/24/2022 | 2400.92 | 0 | 2023-06-15 |  | 1
2024 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00823245LZ | Construction of Flood Mitigation Facility | 120.976 | 14.6042 | 144749893.5 | 144748897 | 2024 | EIGHT J'S CONSTRUCTION SERVICES | 3728 | 2024 | 2024-06-20 | 02/07/2024 | 996.5 | 0 | 2024-09-02 | 74
2021 | Region II | NUEVA VIZCAYA |  | P00561680LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.0306 | 16.369 | 29700000 | 29700000 | 2022 | SHANLEY CONSTRUCTION | 3729 | 2021 | 2022-10-12 | 01/12/2022 | 0 | 0 | 2022-10-11 |  | 1
2022 | Region III | BULACAN | SAN RAFAEL (BULACAN) | P00620151LZ | Construction of Flood Mitigation Structure | 120.9667 | 15.0269 | 55004518.97 | 54124446.67 | 2022 | EIRISH BUILDERS & SUPPLY INC. | 3730 | 2022 | 2022-10-05 | 03/07/2022 | 880072.3 | 0 | 2022-10-04 |  | 1
2024 | National Capital Region | PASIG CITY | CITY OF PASIG (METROPOLITAN MANILA) | P00845866LZ | Construction of Drainage Structure | 121.0551 | 14.5667 | 4949974.58 | 4874733.9 | 2024 | ATLANTA CONSTRUCTION COMPANY, INC. | 3731 | 2024 | 2024-08-25 | 04/08/2024 | 75240.68 | 0 | 2024-10-03 | 39
2024 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00823246LZ | Construction of Flood Mitigation Facility | 120.976 | 14.6042 | 72374608.94 | 72374032.61 | 2024 | AL-AMEN BUILDERS | 3732 | 2024 | 2024-06-20 | 02/08/2024 | 576.33 | 0 | 2024-06-22 | 2
2024 | Region IV-A | LAGUNA | CITY OF SAN PEDRO (LAGUNA) | P00839630LZ | Rehabilitation / Major Repair of Drainage Structure | 121.0307 | 14.3356 | 4950000 | 4836385 | 2024 | MICLOVER GENERAL CONSTRUCTION & IRON WORKS | 3733 | 2024 | 2024-08-20 | 02/23/2024 | 113615 | 0 | 2024-08-19 |  | 1
2022 | National Capital Region | VALENZUELA CITY | CITY OF VALENZUELA (METROPOLITAN MANILA) | P00620411LZ | Construction of Flood Mitigation Structure | 121.0113 | 14.6902 | 24498106.74 | 23959118.25 | 2022 | DJB CONSTRUCTION SERVICES | 3734 | 2022 | 2022-07-25 | 02/08/2022 | 538988.49 | 0 | 2022-11-03 | 101
2022 | National Capital Region | LAS PIÃ‘AS CITY | CITY OF LAS PIÃ‘AS (METROPOLITAN MANILA) | P00620913LZ | Construction of Flood Mitigation Structure | 120.9999 | 14.4395 | 48999847.71 | 46574006.57 | 2022 | I&E CONSTRUCTION CORPORATION (FORMERLY: I&E CONSTR | 3735 | 2022 | 2022-08-07 | 02/09/2022 | 2425841.14 | 0 | 2022-08-06 |  | 1
2022 | National Capital Region | CALOOCAN CITY | CALOOCAN CITY (METROPOLITAN MANILA) | P00620418LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.0215 | 14.7351 | 9799126.34 | 9515920.52 | 2022 | DARCY & ANNA BUILDERS & TRADING | 3736 | 2022 | 2022-09-12 | 03/24/2022 | 283205.82 | 0 | 2022-09-18 | 6
2023 | Region IV-A | LAGUNA | CITY OF SAN PEDRO (LAGUNA) | P00725853LZ | Construction of Slope Protection Structure | 121.0216 | 14.3287 | 108080000 | 108079999.1 | 2023 | YPR GEN. CONTRACTOR AND CONSTRUCTION SUPPLY INC. | 3737 | 2023 | 2023-12-10 | 03/31/2023 | 0.9 | 0 | 2023-12-09 |  | 1
2022 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00620438LZ | Rehabilitation / Major Repair of Drainage Structure | 120.9668 | 14.6271 | 48999990.14 | 48995670.99 | 2023 | EIGHT J'S CONSTRUCTION SERVICES | 3738 | 2022 | 2023-04-06 | 03/29/2022 | 4319.15 | 0 | 2023-04-05 |  | 1
2022 | Region III | BULACAN | SAN MIGUEL (BULACAN) | P00639482LZ | Construction of Flood Mitigation Structure | 121 | 15.2261 | 48999753.54 | 48997428.26 | 2022 | 729 CONSTRUCTION, INC. (FORMERLY 722 CONSTRUCTION, INC.) | 3739 | 2022 | 2022-12-01 | 03/30/2022 | 2325.28 | 0 | 2022-12-13 | 12
2023 | Region III | BULACAN | NORZAGARAY (BULACAN) | P00726520LZ | Construction of Flood Mitigation Structure | 121.0552 | 14.9074 | 86849254.29 | 86849882.04 | 2023 | DEVEX INCORPORATED / N.B. AVILA CONSTRUCTION | 3740 | 2023 | 2023-10-23 | 02/27/2023 | 0 | 627.75 | 2023-12-09 | 47
2022 | National Capital Region | PARAÃ‘AQUE CITY | CITY OF PARAÃ‘AQUE (METROPOLITAN MANILA) | P00621478LZ | Construction of Drainage Structure | 121.0113 | 14.465 | 9800000 | 9800000 | 2022 | R.E. ORLINA CONSTRUCTION CORPORATION | 3741 | 2022 | 2022-10-17 | 03/22/2022 | 0 | 0 | 2022-10-16 |  | 1
2022 | National Capital Region | QUEZON CITY | QUEZON CITY (METROPOLITAN MANILA) | P00630924LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.0308 | 14.6967 | 75655950 | 73386271.5 | 2023 | LE BRON CONSTRUCTION | 3742 | 2022 | 2023-04-30 | 03/22/2022 | 2269678.5 | 0 | 2023-03-15 |  | 46
2023 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00727024LZ | Rehabilitation / Major Repair of Drainage Structure | 120.976 | 14.5961 | 24499148.16 | 24485983.22 | 2023 | JIIK CONSTRUCTION SERVICES | 3743 | 2023 | 2023-10-19 | 03/01/2023 | 13164.94 | 0 | 2023-10-18 |  | 1
2024 | National Capital Region | CALOOCAN CITY | CALOOCAN CITY (METROPOLITAN MANILA) | P00839526LZ | Rehabilitation / Major Repair of Drainage Structure | 121 | 14.6632 | 7919901.57 | 7801091.77 | 2024 | TM ABAD CONSTRUCTION CORP. (FOR: TM ABAD CONST.) | 3744 | 2024 | 2024-06-24 | 02/27/2024 | 118809.8 | 0 | 2024-06-24 | 0
2022 | Region IV-B | ORIENTAL MINDORO | SAN TEODORO (ORIENTAL MINDORO) | P00639524LZ | Construction of Flood Mitigation Structure | 121.0217 | 13.4358 | 19600000 | 19364691.43 | 2022 | KARANGYAN BUILDERS & TRADERS | 3745 | 2022 | 2022-12-12 | 04/06/2022 | 235308.57 | 0 | 2022-12-11 |  | 1
2024 | Region III | BULACAN | CITY OF SAN JOSE DEL MONTE (BULACAN) | P00820183LZ | Construction of Dike | 121.0553 | 14.8299 | 96499936.84 | 96496378.66 | 2024 | L.R. TIQUI BUILDERS, INC. | 3746 | 2024 | 2024-12-17 | 02/26/2024 | 3558.18 | 0 | 2024-12-16 |  | 1
2023 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00725999LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.967 | 14.6281 | 21559733.28 | 20983549.7 | 2023 | GOLDEN J'S CONSTRUCTION SERVICES | 3747 | 2023 | 2023-10-20 | 02/17/2023 | 576183.58 | 0 | 2023-10-23 | 3
2023 | Region III | BULACAN | ANGAT (BULACAN) | P00726730LZ | Construction of Flood Mitigation Structure | 121.0309 | 14.9395 | 33174624.32 | 33174759.59 | 2023 | YPR GEN. CONTRACTOR AND CONSTRUCTION SUPPLY INC. | 3748 | 2023 | 2023-08-02 | 02/22/2023 | 0 | 135.27 | 2023-09-02 | 31
2022 | National Capital Region | PARAÃ‘AQUE CITY | CITY OF PARAÃ‘AQUE (METROPOLITAN MANILA) | P00631027LZ | Construction of Flood Mitigation Structure | 121.0115 | 14.4621 | 6860000 | 6860000 | 2022 | STRONGLANE BUILDERS AND TRADING CORPORATION (FORMERLY: STRONGLANE CONSTRUCTION & TRADING) | 3749 | 2022 | 2022-11-05 | 02/09/2022 | 0 | 0 | 2022-11-04 |  | 1
2021 | National Capital Region | CITY OF MANILA |  | P00561157LZ | Rehabilitation / Major Repair of Drainage Structure | 121.0004 | 14.6108 | 48999945.63 | 47284638.82 | 2023 | NEWBIG FOUR J CONSTRUCTION INC., (FORMERLY FOUR J | 3750 | 2021 | 2023-02-24 | 03/30/2022 | 1715306.81 | 0 | 2023-02-23 |  | 1
2021 | Region II | NUEVA VIZCAYA |  | P00561679LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.0217 | 16.3676 | 29700000 | 29700000 | 2022 | SHANLEY CONSTRUCTION | 3751 | 2021 | 2022-09-30 | 01/12/2022 | 0 | 0 | 2022-09-29 |  | 1
2022 | National Capital Region | QUEZON CITY | QUEZON CITY (METROPOLITAN MANILA) | P00620447LZ | Rehabilitation / Major Repair of Drainage Structure | 121.0553 | 14.6351 | 9796132.61 | 9795731.58 | 2022 | DIADEMA CONSTRUCTION AND ENTERPRISES INC. (FORMERLY: DIADEMA ENTERPRISES) | 3752 | 2022 | 2022-07-05 | 02/18/2022 | 401.03 | 0 | 2022-07-04 |  | 1
2024 | National Capital Region | CALOOCAN CITY | CALOOCAN CITY (METROPOLITAN MANILA) | P00824607LZ | Construction of Drainage Structure | 120.9678 | 14.6451 | 39199926.72 | 38259729.8 | 2024 | J. SIMEON CONSTRUCTION / MIGHTY CONSTRUCTION & DEVELOPMENT INC. | 3753 | 2024 | 2024-10-01 | 02/27/2024 | 940196.92 | 0 | 2024-08-23 |  | 39
2023 | Region III | BULACAN | ANGAT (BULACAN) | P00726522LZ | Construction of Flood Mitigation Structure | 121.0311 | 14.9238 | 86849813.45 | 86848966.84 | 2023 | JAGONBUILD CONSTRUCTION CORP. (FOR. JAGON BUILDERS | 3754 | 2023 | 2023-12-10 | 02/27/2023 | 846.61 | 0 | 2023-12-09 |  | 1
2023 | Region IV-A | LAGUNA | CITY OF SANTA ROSA (LAGUNA) | P00725850LZ | Construction of Flood Mitigation Structure | 121.0555 | 14.2502 | 96500000 | 93865181.37 | 2024 | MAR-VEL CONSTRUCTION & SUPPLY | 3755 | 2023 | 2024-03-20 | 02/28/2023 | 2634818.63 | 0 | 2024-03-19 |  | 1
2023 | National Capital Region | CALOOCAN CITY | CALOOCAN CITY (METROPOLITAN MANILA) | P00725541LZ | Construction of Drainage Structure | 121.0005 | 14.6845 | 86849332.6 | 84678409.32 | 2024 | KING EIGHT BUILDERS AND SUPPLY | 3756 | 2023 | 2024-03-21 | 06/19/2023 | 2170923.28 | 0 | 2024-05-12 | 52
2024 | National Capital Region | QUEZON CITY | QUEZON CITY (METROPOLITAN MANILA) | P00820633LZ | Construction of Flood Mitigation Structure | 121.0313 | 14.7039 | 48999937.2 | 48508937.83 | 2024 | AVE-MIRA CONSTRUCTION AND TRADING | 3757 | 2024 | 2024-11-29 | 02/06/2024 | 490999.37 | 0 | 2024-11-30 | 1
2022 | National Capital Region | PARAÃ‘AQUE CITY | CITY OF PARAÃ‘AQUE (METROPOLITAN MANILA) | P00620923LZ | Construction of Flood Mitigation Structure | 121.0117 | 14.4645 | 49000000 | 48997087.44 | 2022 | AKN CONSTRUCTION CORPORATION | 3758 | 2022 | 2022-12-01 | 03/22/2022 | 2912.56 | 0 | 2022-11-30 |  | 1
2023 | National Capital Region | VALENZUELA CITY | CITY OF VALENZUELA (METROPOLITAN MANILA) | P00726803LZ | Construction of Flood Mitigation Structure | 120.968 | 14.7179 | 72374437.5 | 72374958.24 | 2023 | TOUGHBUILT CONSTRUCTION & TRADING, INC. | 3759 | 2023 | 2023-12-18 | 04/20/2023 | 0 | 520.74 | 2024-05-12 | 146
2024 | National Capital Region | CALOOCAN CITY | CALOOCAN CITY (METROPOLITAN MANILA) | P00820594LZ | Construction of Flood Mitigation Structure | 121.0315 | 14.7666 | 48995422.57 | 47818676.13 | 2024 | FRAMECON BUILDERS | 3760 | 2024 | 2024-07-02 | 02/14/2024 | 1176746.44 | 0 | 2024-07-11 | 9
2023 | Region III | BULACAN | CITY OF MEYCAUAYAN (BULACAN) | P00742329LZ | Construction of Slope Protection Structure | 121.0218 | 14.7724 | 4949687.94 | 4875393.12 | 2023 | HALREY CONSTRUCTION INC. | 3761 | 2023 | 2023-07-18 | 03/30/2023 | 74294.82 | 0 | 2023-07-17 |  | 1
2023 | Region II | CAGAYAN | CLAVERIA (CAGAYAN) | P00742298LZ | Construction of Flood Mitigation Structure | 121.0558 | 18.5572 | 9900000 | 9800733.33 | 2023 | DANDEX CONSTRUCTION | 3762 | 2023 | 2023-07-24 | 03/27/2023 | 99266.67 | 0 | 2023-07-23 |  | 1
2024 | National Capital Region | CALOOCAN CITY | CALOOCAN CITY (METROPOLITAN MANILA) | P00839524LZ | Construction of Drainage Structure | 121.0005 | 14.6658 | 4948723.84 | 4874471.73 | 2024 | AVE-MIRA CONSTRUCTION AND TRADING | 3763 | 2024 | 2024-07-08 | 02/14/2024 | 74252.11 | 0 | 2024-06-11 |  | 27
2023 | National Capital Region | PARAÃ‘AQUE CITY | CITY OF PARAÃ‘AQUE (METROPOLITAN MANILA) | P00725534LZ | Construction of Flood Mitigation Facility | 121.0117 | 14.4646 | 82025000 | 82024950.75 | 2024 | VICTORIA DEVELOPMENT AND VENTURES CORP. (FOR: VICTORIA DEV'T AND CONST. CORP.) | 3764 | 2023 | 2024-07-03 | 02/15/2023 | 49.25 | 0 | 2024-07-02 |  | 1
2022 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00621431LZ | Construction of Flood Mitigation Structure | 120.976 | 14.6058 | 48999395.93 | 48999172.37 | 2022 | EIGHT J'S CONSTRUCTION SERVICES / JIIK CONSTRUCTION SERVICES | 3765 | 2022 | 2022-12-12 | 06/13/2022 | 223.56 | 0 | 2023-03-08 | 86
2023 | National Capital Region | CALOOCAN CITY | CALOOCAN CITY (METROPOLITAN MANILA) | P00725558LZ | Construction of Flood Mitigation Structure | 121.0315 | 14.774 | 91670816.45 | 89182996.54 | 2023 | IM CONSTRUCTION CORPORATION | 3766 | 2023 | 2023-12-26 | 02/21/2023 | 2487819.91 | 0 | 2023-12-16 |  | 10
2024 | National Capital Region | CALOOCAN CITY | CALOOCAN CITY (METROPOLITAN MANILA) | P00839523LZ | Construction of Drainage Structure | 120.976 | 14.6489 | 34643636.86 | 33809063.83 | 2024 | TOUGHBUILT CONSTRUCTION & TRADING, INC. / NOVA VENTUS CONSTRUCTION INC. | 3767 | 2024 | 2024-09-30 | 02/27/2024 | 834573.03 | 0 | 2024-08-23 |  | 38
2024 | Region III | BULACAN | SANTA MARIA (BULACAN) | P00845987LZ | Construction of Drainage Structure | 120.9681 | 14.842 | 4936172.86 | 4862221.64 | 2024 | PLL BUILDERS INC. | 3768 | 2024 | 2024-08-16 | 04/25/2024 | 73951.22 | 0 | 2024-09-11 | 26
2024 | National Capital Region | PARAÃ‘AQUE CITY | CITY OF PARAÃ‘AQUE (METROPOLITAN MANILA) | P00820054LZ | Construction of Revetment | 121.0222 | 14.4568 | 92614910 | 92609743.96 | 2024 | RNN CONSTRUCTION CORPORATION (FORMERLY RNN CONSTRU / AKN CONSTRUCTION CORPORATION | 3769 | 2024 | 2024-09-16 | 02/20/2024 | 5166.04 | 0 | 2025-01-21 | 127
2024 | Region IV-A | BATANGAS | BATANGAS CITY (CAPITAL) (BATANGAS) | P00846037LZ | Construction of Drainage Structure | 121.0559 | 13.7532 | 4950000 | 4950000 | 2024 | MARTIN BUILDERS INC. (FOR:MARTIN BUILDERS CONSTRUCTION SERVICES) | 3770 | 2024 | 2024-06-26 | 03/20/2024 | 0 | 0 | 2024-06-25 |  | 1
2024 | National Capital Region | PARAÃ‘AQUE CITY | CITY OF PARAÃ‘AQUE (METROPOLITAN MANILA) | P00820569LZ | Construction of Revetment | 121.0117 | 14.4656 | 14700000 | 14259747.39 | 2024 | EURO CONSTRUCTION AND SUPPLY ( FORMERLY: EURO CONSTRUCTION AND TRADING) | 3771 | 2024 | 2024-11-15 | 07/11/2024 | 440252.61 | 0 | 2024-12-06 | 21
2022 | Region IV-A | CAVITE | GEN. MARIANO ALVAREZ (CAVITE) | P00632885LZ | Construction of Drainage Structure | 121.0006 | 14.2914 | 39599727.15 | 4949901.23 | 2022 | TRIPLE 8 CONSTRUCTION & SUPPLY, INC. (FORMERLY TRIPLE 8 CONST. & SUPPLY) | 3772 | 2022 | 2022-08-15 | 02/17/2022 | 34649825.92 | 0 | 2022-08-14 |  | 1
2023 | Region IV-A | LAGUNA | CITY OF SAN PEDRO (LAGUNA) | P00742435LZ | Rehabilitation / Major Repair of Drainage Structure | 121.0315 | 14.3383 | 4950000 | 4844096 | 2023 | EOZ CONSTRUCTION | 3773 | 2023 | 2023-07-24 | 03/27/2023 | 105904 | 0 | 2023-07-23 |  | 1
2022 | Region IV-A | CAVITE | SILANG (CAVITE) | P00620867LZ | Construction of Revetment | 120.976 | 14.2148 | 78164963.54 | 78162955.77 | 2023 | PRIME PACIFIC MARINE & INDUSTRIAL SERVICES CORP. | 3774 | 2022 | 2023-11-06 | 02/23/2022 | 2007.77 | 0 | 2023-11-05 |  | 1
2023 | National Capital Region | VALENZUELA CITY | CITY OF VALENZUELA (METROPOLITAN MANILA) | P00726804LZ | Construction of Flood Mitigation Structure | 120.9683 | 14.7177 | 96473707.89 | 94316735.57 | 2024 | J. SIMEON CONSTRUCTION / MIGHTY CONSTRUCTION & DEVELOPMENT INC. | 3775 | 2023 | 2024-06-11 | 04/20/2023 | 2156972.32 | 0 | 2024-06-11 | 0
2023 | National Capital Region | CALOOCAN CITY | CALOOCAN CITY (METROPOLITAN MANILA) | P00736168LZ | Construction of Drainage Structure | 121.0561 | 14.7451 | 23519641.64 | 23025730.59 | 2023 | 5-1 CONSTRUCTION CORPORATION | 3776 | 2023 | 2023-06-27 | 02/21/2023 | 493911.05 | 0 | 2023-11-16 | 142
2022 | National Capital Region | QUEZON CITY | QUEZON CITY (METROPOLITAN MANILA) | P00631041LZ | Construction of Flood Mitigation Structure | 121.0117 | 14.6556 | 37085159.99 | 35972605.19 | 2022 | IM CONSTRUCTION CORPORATION | 3777 | 2022 | 2022-12-09 | 02/14/2022 | 1112554.8 | 0 | 2022-12-09 | 0
2022 | National Capital Region | PARAÃ‘AQUE CITY | CITY OF PARAÃ‘AQUE (METROPOLITAN MANILA) | P00620916LZ | Construction of Revetment | 121.0119 | 14.5006 | 49000000 | 49000000 | 2022 | AKN CONSTRUCTION CORPORATION | 3778 | 2022 | 2022-11-16 | 03/22/2022 | 0 | 0 | 2022-11-15 |  | 1
2021 | National Capital Region | PARAÃ‘AQUE CITY |  | P00525759LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.0006 | 14.4853 | 29400000 | 29399703.59 | 2022 | PHILIPPINE CHEMSTEEL INDUSTRIES, INC. | 3779 | 2021 | 2022-10-28 | 03/22/2022 | 296.41 | 0 | 2022-10-27 |  | 1
2023 | National Capital Region | SAN JUAN CITY | CITY OF SAN JUAN (METROPOLITAN MANILA) | P00726787LZ | Rehabilitation / Major Repair of Slope Protection Structure | 121.0316 | 14.5938 | 42335591.2 | 40203391.26 | 2023 | DARCY & ANNA BUILDERS & TRADING | 3780 | 2023 | 2023-09-20 | 03/22/2023 | 2132199.94 | 0 | 2023-10-16 | 26
2022 | Region IV-A | CAVITE | SILANG (CAVITE) | P00639489LZ | Construction of Drainage Structure | 120.9688 | 14.2553 | 19599797.32 | 4899930.04 | 2022 | TCSC CORP. | 3781 | 2022 | 2022-10-17 | 04/11/2022 | 14699867.28 | 0 | 2022-10-16 |  | 1
2023 | Region II | CAGAYAN | CLAVERIA (CAGAYAN) | P00726437LZ | Construction of Flood Mitigation Structure | 121.0223 | 18.5385 | 49000000 | 48250000 | 2024 | SKYLINE CONSTRUCTION, EQUIPMENT AND DEVELOPMENT CORPORATION(FORMERLY: EDDIE G. GUILLEN BUILDERS INC. | 3782 | 2023 | 2024-01-18 | 02/06/2023 | 750000 | 0 | 2023-09-08 |  | 132
2024 | Region II | NUEVA VIZCAYA | BAMBANG (NUEVA VIZCAYA) | P00843258LZ | Construction of Flood Mitigation Structure | 121.0563 | 16.3893 | 89745000 | 89745000 | 2024 | DALCON CONSTRUCTION | 3783 | 2024 | 2024-04-15 | 03/08/2024 | 0 | 0 | 2025-01-12 | 272
2023 | Region III | NUEVA ECIJA | PEÃ‘ARANDA (NUEVA ECIJA) | P00740326LZ | Construction of Flood Mitigation Structure | 121.0119 | 15.7494 | 96499924.12 | 96498568.59 | 2023 | ITP CONSTRUCTION, INC. | 3784 | 2023 | 2023-07-24 | 04/12/2023 | 1355.53 | 0 | 2024-01-29 | 189
2021 | National Capital Region | PASAY CITY |  | P00561226LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.0008 | 14.5373 | 29699590.39 | 28939547.94 | 2022 | E.R. RODRIGUEZ CONSTRUCTION CORPORATION (FORMERLY: E.R. RODRIGUEZ CONSTRUCTION) | 3785 | 2021 | 2022-11-19 | 08/31/2021 | 760042.45 | 0 | 2023-04-06 | 138
2022 | National Capital Region | VALENZUELA CITY | CITY OF VALENZUELA (METROPOLITAN MANILA) | P00620022LZ | Construction of Flood Mitigation Structure | 120.9688 | 14.7233 | 206535800.6 | 199712253.7 | 2023 | E.M. CUERPO, INC. / TOUGHBUILT CONSTRUCTION & TRADING, INC. | 3786 | 2022 | 2023-07-03 | 02/11/2022 | 6823546.9 | 0 | 2023-07-04 | 1
2022 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00621432LZ | Construction of Flood Mitigation Structure | 120.9762 | 14.6062 | 48999789.64 | 48980469.28 | 2023 | J. SIMEON CONSTRUCTION | 3787 | 2022 | 2023-06-02 | 05/20/2022 | 19320.36 | 0 | 2023-06-03 | 1
2022 | National Capital Region | TAGUIG CITY | TAGUIG CITY (METROPOLITAN MANILA) | P00620085LZ | Construction of Slope Protection Structure | 121.0223 | 14.5307 | 62724722.65 | 59566104.23 | 2024 | ST. MATTHEW GEN. CONTRACTOR & DEVELOPMENT CORP. | 3788 | 2022 | 2024-03-01 | 03/21/2022 | 3158618.42 | 0 | 2024-01-27 |  | 34
2022 | National Capital Region | MALABON CITY | CITY OF MALABON (METROPOLITAN MANILA) | P00620045LZ | Construction of Flood Mitigation Structure | 120.9763 | 14.6747 | 68420449.29 | 67516950.32 | 2022 | A.L. SALAZAR CONSTRUCTION, INC. / ROTAFLEX CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY:ROTA FLEX CONSTRUCTION) | 3789 | 2022 | 2022-12-13 | 03/24/2022 | 903498.97 | 0 | 2022-12-17 | 4
2022 | National Capital Region | CALOOCAN CITY | CALOOCAN CITY (METROPOLITAN MANILA) | P00631032LZ | Construction of Flood Mitigation Structure | 121.0563 | 14.7632 | 19595683.3 | 19186271.65 | 2022 | AYLAN CONSTRUCTION & TRADING | 3790 | 2022 | 2022-12-04 | 02/08/2022 | 409411.65 | 0 | 2022-10-04 |  | 61
2021 | National Capital Region | PARAÃ‘AQUE CITY |  | P00525752LZ | Construction of Flood Mitigation Structure | 121.0121 | 14.5008 | 29400000 | 29399024.81 | 2023 | MACSTRENGTH CONSTRUCTION | 3791 | 2021 | 2023-02-17 | 05/24/2022 | 975.19 | 0 | 2023-02-16 |  | 1
2023 | Region IV-A | CAVITE | GEN. MARIANO ALVAREZ (CAVITE) | P00737512LZ | Construction of Drainage Structure | 121.0008 | 14.2917 | 19799810.39 | 4949968.51 | 2023 | ALMAKAR BUILDERS & METAL WORKS | 3792 | 2023 | 2023-08-17 | 02/15/2023 | 14849841.88 | 0 | 2023-09-11 | 25
2024 | National Capital Region | TAGUIG CITY | TAGUIG CITY (METROPOLITAN MANILA) | P00824599LZ | Construction of Slope Protection Structure | 121.0316 | 14.5199 | 14699764.7 | 13964795.22 | 2024 | TUCHAR CONSTRUCTION CORP. (FORMERLY:TUCHAR CONSTRU | 3793 | 2024 | 2024-11-25 | 05/06/2024 | 734969.48 | 0 | 2024-11-23 |  | 2
2023 | Region III | BULACAN | CITY OF MEYCAUAYAN (BULACAN) | P00726506LZ | Construction of Flood Mitigation Structure | 120.9689 | 14.7259 | 68059587.22 | 68372168.96 | 2023 | TRIPLE 8 CONSTRUCTION & SUPPLY, INC. (FORMERLY TRIPLE 8 CONST. & SUPPLY) | 3794 | 2023 | 2023-10-09 | 02/22/2023 | 0 | 312581.74 | 2023-10-08 |  | 1
2024 | Region II | NUEVA VIZCAYA | ARITAO (NUEVA VIZCAYA) | P00820161LZ | Construction of Slope Protection Structure | 121.0225 | 16.2639 | 96500000 | 96499614.17 | 2024 | AMP 723 CONSTRUCTION CORPORATION (FORMERLY: A.M.P. CONSTRUCTION) / RPP 928 CONSTRUCTION CORPORATION | 3795 | 2024 | 2024-09-29 | 02/16/2024 | 385.83 | 0 | 2024-10-21 | 22
2024 | Region IV-A | CAVITE | BACOOR CITY (CAVITE) | P00823549LZ | Construction of Revetment | 120.9764 | 14.3778 | 96499906.44 | 96499777.7 | 2025 | ALMAKAR BUILDERS & METAL WORKS | 3796 | 2024 | 2025-03-10 | 05/17/2024 | 128.74 | 0 | 2025-04-10 | 31
2024 | Region II | NUEVA VIZCAYA | ARITAO (NUEVA VIZCAYA) | P00843261LZ | Construction of Flood Mitigation Structure | 121.0564 | 16.2375 | 132660000 | 129260223.4 | 2024 | INDUSTRIAL CONTROLS CORPORATION (ICC) | 3797 | 2024 | 2024-08-30 | 02/21/2024 | 3399776.6 | 0 | 2025-02-05 | 159
2024 | Region IV-A | BATANGAS | BAUAN (BATANGAS) | P00823541LZ | Construction of Flood Mitigation Structure | 121.0009 | 13.8339 | 24500000 | 24125000 | 2024 | REVERE CONSTRUCTION & SUPPLY CORPORATION (FORMERLY | 3798 | 2024 | 2024-07-29 | 02/07/2024 | 375000 | 0 | 2024-07-28 |  | 1
2021 | National Capital Region | QUEZON CITY |  | P00525838LZ | Construction of Flood Mitigation Structure | 121.0317 | 14.6632 | 49000000 | 47530000 | 2022 | E.L. TORRES CONSTRUCTION AND TRADING INC. (FORMERLY : E. L. TORRES CONSTRUCTION & TRADING | 3799 | 2021 | 2022-12-12 | 02/16/2022 | 1470000 | 0 | 2022-12-11 |  | 1
2023 | Region III | BULACAN | CITY OF MEYCAUAYAN (BULACAN) | P00727308LZ | Construction of Flood Mitigation Structure | 120.9689 | 14.7237 | 48999201.06 | 48249000 | 2023 | ROYAL CROWN MONARCH CONSTRUCTION & SUPPLIES CORP. | 3800 | 2023 | 2023-11-16 | 03/30/2023 | 750201.06 | 0 | 2023-11-15 |  | 1
2022 | Region III | BULACAN | ANGAT (BULACAN) | P00637774LZ | Construction of Slope Protection Structure | 121.0226 | 14.9345 | 4899978.54 | 4949420.32 | 2022 | EDCELCON CONSTRUCTION INC. | 3801 | 2022 | 2022-08-14 | 05/26/2022 | 0 | 49441.78 | 2022-08-13 |  | 1
2024 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00820068LZ | Construction of Retarding Basin | 120.9767 | 14.6352 | 96497993.95 | 96447990.71 | 2024 | JAGONBUILD CONSTRUCTION CORP. (FOR. JAGON BUILDERS | 3802 | 2024 | 2024-10-07 | 02/08/2024 | 50003.24 | 0 | 2024-10-06 |  | 1
2024 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00820657LZ | Construction of Flood Mitigation Structure | 121.0122 | 14.575 | 29395901.32 | 29394984.53 | 2024 | JMK BUILDERS CONSTRUCTION | 3803 | 2024 | 2024-12-05 | 02/20/2024 | 916.79 | 0 | 2024-12-14 | 9
2022 | National Capital Region | TAGUIG CITY | TAGUIG CITY (METROPOLITAN MANILA) | P00631026LZ | Construction of Slope Protection Structure | 121.0564 | 14.4669 | 48999718.68 | 49000000 | 2022 | DAHL CONSTRUCTION CORP. (FORMERLY: DAHL CONSTRUCTION) | 3804 | 2022 | 2022-07-27 | 03/21/2022 | 0 | 281.32 | 2022-11-14 | 110
2024 | National Capital Region | MARIKINA CITY | CITY OF MARIKINA (METROPOLITAN MANILA) | P00821446LZ | Rehabilitation / Major Repair of Drainage Structure | 121.032 | 14.5987 | 29399771.25 | 28797915.84 | 2025 | MRB11 CONSTRUCTION CORPORATION (FORMERLY:MRB CONS | 3805 | 2024 | 2025-01-17 | 04/08/2024 | 601855.41 | 0 | 2025-03-27 | 69
2021 | Cordillera Administrative Region | MOUNTAIN PROVINCE |  | P00526384LZ | Construction of Flood Mitigation Structure | 120.969 | 17.0789 | 35279999.7 | 35280000 | 2022 | AFEW CONSTRUCTION / E.T. LATAWAN CONSTRUCTION | 3806 | 2021 | 2022-09-15 | 04/11/2022 | 0 | 0.3 | 2022-09-14 |  | 1
2022 | Region IV-A | LAGUNA | CITY OF SAN PEDRO (LAGUNA) | P00620242LZ | Construction of Flood Mitigation Structure | 121.023 | 14.3572 | 77200000 | 77199699.39 | 2023 | ALPHA & OMEGA GEN. CONTRACTOR & DEVELOPMENT CORP. / C.S. RAYOS CONSTRUCTION & GENERAL SERVICES, INC. | 3807 | 2022 | 2023-02-20 | 02/21/2022 | 300.61 | 0 | 2023-02-19 |  | 1
2022 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00621433LZ | Construction of Flood Mitigation Structure | 120.9767 | 14.6064 | 48999376.51 | 48973694.24 | 2023 | J. SIMEON CONSTRUCTION | 3808 | 2022 | 2023-03-13 | 05/23/2022 | 25682.27 | 0 | 2023-04-07 | 25
2022 | Region III | NUEVA ECIJA | SAN JOSE CITY (NUEVA ECIJA) | P00620536LZ | Construction of Flood Mitigation Structure | 121.0122 | 15.7573 | 49000000 | 48020044.48 | 2022 | WIZARD CONCRETE SOLUTIONS AND CONSTRUCTION CORPORATION (FORMERLY: WIZARD TRADING & CONSTRUCTION) | 3809 | 2022 | 2022-09-15 | 02/18/2022 | 979955.52 | 0 | 2022-09-14 |  | 1
2024 | National Capital Region | TAGUIG CITY | TAGUIG CITY (METROPOLITAN MANILA) | P00821063LZ | Construction of Slope Protection Structure | 121.0568 | 14.5242 | 96499819.92 | 90709571.71 | 2025 | J. SIMEON CONSTRUCTION | 3810 | 2024 | 2025-02-01 | 05/11/2024 | 5790248.21 | 0 | 2025-01-04 |  | 28
2022 | National Capital Region | QUEZON CITY | QUEZON CITY (METROPOLITAN MANILA) | P00640488LZ | Construction of Flood Mitigation Structure | 121.001 | 14.6572 | 20790000 | 20166300 | 2023 | NUEDA BUILDERS CONSTRUCTION & SUPPLY INC. | 3811 | 2022 | 2023-03-14 | 05/19/2022 | 623700 | 0 | 2023-03-13 |  | 1
2022 | National Capital Region | QUEZON CITY | QUEZON CITY (METROPOLITAN MANILA) | P00632720LZ | Construction of Flood Mitigation Structure | 121.0322 | 14.682 | 39600000 | 38412000 | 2022 | C.E.M. CONSTRUCTION, INC. | 3812 | 2022 | 2022-12-12 | 03/22/2022 | 1188000 | 0 | 2023-03-15 | 93
2023 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00726004LZ | Construction of Flood Mitigation Structure | 120.9768 | 14.6065 | 39199241.47 | 39156110.72 | 2023 | 1HB CONSTRUCTION CORP. (FORMERLY: HB CONSTRUCTION) | 3813 | 2023 | 2023-11-23 | 02/17/2023 | 43130.75 | 0 | 2023-11-22 |  | 1
2024 | Region IV-B | ORIENTAL MINDORO | BACO (ORIENTAL MINDORO) | P00823560LZ | Construction of Flood Mitigation Structure | 121.0231 | 13.3789 | 112700000 | 110974891.8 | 2025 | ARCONIC INC. | 3814 | 2024 | 2025-01-08 | 02/08/2024 | 1725108.2 | 0 | 2025-01-07 |  | 1
2023 | National Capital Region | PASAY CITY | PASAY CITY (METROPOLITAN MANILA) | P00725511LZ | Construction of Flood Mitigation Structure | 121.0123 | 14.5241 | 62724993.26 | 62717241.73 | 2023 | EIGHT J'S CONSTRUCTION SERVICES | 3815 | 2023 | 2023-11-21 | 02/23/2023 | 7751.53 | 0 | 2023-12-05 | 14
2022 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00620429LZ | Construction of Flood Mitigation Structure | 120.9693 | 14.6197 | 24499279.35 | 24491621.21 | 2022 | G.F. FABIAN CONSTRUCTION | 3816 | 2022 | 2022-08-08 | 02/23/2022 | 7658.14 | 0 | 2022-08-20 | 12
2023 | National Capital Region | PASIG CITY | CITY OF PASIG (METROPOLITAN MANILA) | P00725952LZ | Construction of Drainage Structure | 121.0569 | 14.5736 | 5389263.26 | 5119086.15 | 2023 | 816 EMBER CONSTRUCTION CORPORATION | 3817 | 2023 | 2023-08-06 | 02/06/2023 | 270177.11 | 0 | 2023-05-05 |  | 93
2024 | National Capital Region | PASAY CITY | PASAY CITY (METROPOLITAN MANILA) | P00845880LZ | Construction of Drainage Structure | 121.001 | 14.5169 | 4948831.08 | 4809909.62 | 2024 | SLHAV CONSTRUCTION | 3818 | 2024 | 2024-09-11 | 04/11/2024 | 138921.46 | 0 | 2024-09-10 |  | 1
2024 | Region IV-A | CAVITE | SILANG (CAVITE) | P00846057LZ | Construction of Drainage Structure | 121.0011 | 14.2256 | 4949955.4 | 4949659.73 | 2024 | CMMJ CONSTRUCTION | 3819 | 2024 | 2024-11-11 | 05/16/2024 | 295.67 | 0 | 2024-11-10 |  | 1
2024 | National Capital Region | TAGUIG CITY | TAGUIG CITY (METROPOLITAN MANILA) | P00821046LZ | Construction of Slope Protection Structure | 121.0323 | 14.6043 | 96499439.31 | 94521200.8 | 2024 | TOUGHBUILT CONSTRUCTION & TRADING, INC. | 3820 | 2024 | 2024-07-22 | 02/13/2024 | 1978238.51 | 0 | 2024-10-08 | 78
2023 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00740297LZ | Construction of Flood Mitigation Facility | 120.9768 | 14.6003 | 72374173.51 | 70376645.51 | 2023 | EIGHT J'S CONSTRUCTION SERVICES | 3821 | 2023 | 2023-06-22 | 03/28/2023 | 1997528 | 0 | 2023-06-29 | 7
2024 | National Capital Region | PARAÃ‘AQUE CITY | CITY OF PARAÃ‘AQUE (METROPOLITAN MANILA) | P00823261LZ | Construction of Revetment | 121.0123 | 14.4511 | 144750000 | 144749717.8 | 2024 | AKN CONSTRUCTION CORPORATION | 3822 | 2024 | 2024-12-12 | 03/27/2024 | 282.2 | 0 | 2025-04-19 | 128
2022 | Cordillera Administrative Region | ABRA | MALIBCONG (ABRA) | P00632764LZ | Construction of Flood Mitigation Structure | 121.0232 | 17.6128 | 48999950.01 | 49497162.42 | 2022 | ST. TIMOTHY CONSTRUCTION CORPORATION | 3823 | 2022 | 2022-10-27 | 03/01/2022 | 0 | 497212.41 | 2022-10-21 |  | 6
2023 | National Capital Region | PARAÃ‘AQUE CITY | CITY OF PARAÃ‘AQUE (METROPOLITAN MANILA) | P00742111LZ | Construction of Revetment | 121.0013 | 14.4759 | 99000000 | 96129000 | 2024 | E.R. RODRIGUEZ CONSTRUCTION CORPORATION (FORMERLY: E.R. RODRIGUEZ CONSTRUCTION) | 3824 | 2023 | 2024-12-16 | 07/10/2023 | 2871000 | 0 | 2024-12-31 | 15
2022 | National Capital Region | PARAÃ‘AQUE CITY | CITY OF PARAÃ‘AQUE (METROPOLITAN MANILA) | P00639408LZ | Rehabilitation / Major Repair of Drainage Structure | 121.0323 | 14.4841 | 14700000 | 14698821.77 | 2022 | GRAC-TA BUILDERS | 3825 | 2022 | 2022-07-06 | 03/31/2022 | 1178.23 | 0 | 2022-08-26 | 51
2023 | National Capital Region | PARAÃ‘AQUE CITY | CITY OF PARAÃ‘AQUE (METROPOLITAN MANILA) | P00727010LZ | Construction of Revetment | 121.0013 | 14.4759 | 49000000 | 48999627.3 | 2024 | DARCY & ANNA BUILDERS & TRADING | 3826 | 2023 | 2024-04-12 | 04/12/2023 | 372.7 | 0 | 2024-04-11 |  | 1
2023 | Region IV-A | BATANGAS | BAUAN (BATANGAS) | P00740395LZ | Construction of Flood Mitigation Structure | 120.9694 | 13.7763 | 19600000 | 19300000 | 2023 | GREENFIELD CONSTRUCTION | 3827 | 2023 | 2023-08-15 | 04/03/2023 | 300000 | 0 | 2023-08-14 |  | 1
2021 | National Capital Region | QUEZON CITY |  | P00525839LZ | Construction of Flood Mitigation Structure | 121.0123 | 14.6457 | 49000000 | 47530000 | 2023 | E.L. TORRES CONSTRUCTION AND TRADING INC. (FORMERLY : E. L. TORRES CONSTRUCTION & TRADING | 3828 | 2021 | 2023-02-10 | 02/16/2022 | 1470000 | 0 | 2023-02-09 |  | 1
2024 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00845869LZ | Construction of Drainage Structure | 121.0234 | 14.5941 | 98999341.6 | 98959761.62 | 2024 | EIGHT J'S CONSTRUCTION SERVICES / G2XD CONSTRUCTION SERVICES | 3829 | 2024 | 2024-09-20 | 02/20/2024 | 39579.98 | 0 | 2025-01-01 | 103
2024 | Region III | BULACAN | NORZAGARAY (BULACAN) | P00823481LZ | Construction of Flood Mitigation Structure | 121.057 | 14.9082 | 43424897.13 | 43424482.39 | 2024 | JAGONBUILD CONSTRUCTION CORP. (FOR. JAGON BUILDERS | 3830 | 2024 | 2024-10-06 | 03/18/2024 | 414.74 | 0 | 2024-10-05 |  | 1
2023 | Region IV-A | CAVITE | GEN. MARIANO ALVAREZ (CAVITE) | P00737511LZ | Construction of Drainage Structure | 121.0324 | 14.3293 | 19799810.39 | 4949879.02 | 2023 | ALMAKAR BUILDERS & METAL WORKS | 3831 | 2023 | 2023-08-17 | 02/15/2023 | 14849931.37 | 0 | 2023-09-11 | 25
2021 | National Capital Region | CITY OF MANILA |  | P00525827LZ | Construction of Flood Mitigation Structure | 121.0014 | 14.6146 | 48999905.97 | 47155728.25 | 2022 | RAICON DEVELOPMENT CORPORATION (FORMERLY : RA IGNACIO CONST. CORP.) | 3832 | 2021 | 2022-10-27 | 07/15/2021 | 1844177.72 | 0 | 2022-10-26 |  | 1
2023 | Region IV-B | ORIENTAL MINDORO | PUERTO GALERA (ORIENTAL MINDORO) | P00742456LZ | Construction of Drainage Structure | 120.9694 | 13.525 | 4950000 | 4839339.24 | 2023 | SANLAHI GROUP OF BUILDERS INC. | 3833 | 2023 | 2023-09-06 | 03/30/2023 | 110660.76 | 0 | 2023-09-05 |  | 1
2023 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00740293LZ | Construction of Flood Mitigation Facility | 120.9768 | 14.6003 | 72374960.34 | 72216269.62 | 2023 | JELSIE CONSTRUCTION & SUPPLY | 3834 | 2023 | 2023-06-23 | 03/28/2023 | 158690.72 | 0 | 2023-06-29 | 6
2024 | National Capital Region | PASAY CITY | PASAY CITY (METROPOLITAN MANILA) | P00820664LZ | Construction of Slope Protection Structure | 121.0123 | 14.5309 | 49016204.84 | 48982729.87 | 2024 | CAANA CONSTRUCTION CORPORATION | 3835 | 2024 | 2024-06-03 | 02/20/2024 | 33474.97 | 0 | 2024-09-15 | 104
2024 | Region IV-A | LAGUNA | CITY OF BIÃ‘AN (LAGUNA) | P00820884LZ | Construction of Flood Mitigation Structure | 121.057 | 14.2606 | 49000000 | 48997686.53 | 2024 | MAR-VEL CONSTRUCTION & SUPPLY | 3836 | 2024 | 2024-09-29 | 02/12/2024 | 2313.47 | 0 | 2024-09-28 |  | 1
2021 | National Capital Region | CALOOCAN CITY |  | P00525790LZ | Construction of Flood Mitigation Structure | 121.0016 | 14.7342 | 48998204.76 | 47822230.74 | 2022 | PERSAN CONSTRUCTION, INC. (FORMERLY: PERSAN CONST. | 3837 | 2021 | 2022-12-12 | 03/24/2022 | 1175974.02 | 0 | 2023-02-15 | 65
2023 | Region III | BULACAN | SANTA MARIA (BULACAN) | P00742332LZ | Construction of Drainage Structure | 120.9698 | 14.8486 | 4944191.57 | 4941438.89 | 2023 | PLL BUILDERS INC. | 3838 | 2023 | 2023-09-02 | 03/30/2023 | 2752.68 | 0 | 2023-09-01 |  | 1
2023 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00740294LZ | Construction of Flood Mitigation Facility | 120.9768 | 14.6003 | 72374619.81 | 71220223.38 | 2023 | ALPHA & OMEGA GEN. CONTRACTOR & DEVELOPMENT CORP. / A.M. SALONG CONSTRUCTION | 3839 | 2023 | 2023-06-23 | 03/28/2023 | 1154396.43 | 0 | 2023-06-29 | 6
2024 | Region III | BULACAN | ANGAT (BULACAN) | P00821579LZ | Construction of Flood Mitigation Structure | 121.0326 | 14.9335 | 48249312.8 | 48249988.32 | 2024 | ELITE GENERAL CONTRACTOR AND DEVELOPMENT CORP. | 3840 | 2024 | 2024-11-02 | 04/08/2024 | 0 | 675.52 | 2024-11-01 |  | 1
2023 | National Capital Region | PARAÃ‘AQUE CITY | CITY OF PARAÃ‘AQUE (METROPOLITAN MANILA) | P00727012LZ | Construction of Flood Mitigation Facility | 121.0234 | 14.4726 | 19600000 | 19110512.21 | 2024 | JMK BUILDERS CONSTRUCTION | 3841 | 2023 | 2024-04-26 | 05/16/2023 | 489487.79 | 0 | 2024-04-25 |  | 1
2023 | National Capital Region | CALOOCAN CITY | CALOOCAN CITY (METROPOLITAN MANILA) | P00736164LZ | Construction of Flood Mitigation Structure | 121.0123 | 14.6825 | 29398295.98 | 28516336.77 | 2023 | WAWAO BUILDERS | 3842 | 2023 | 2023-12-16 | 02/21/2023 | 881959.21 | 0 | 2023-12-16 | 0
2024 | National Capital Region | VALENZUELA CITY | CITY OF VALENZUELA (METROPOLITAN MANILA) | P00820591LZ | Construction of Flood Mitigation Structure | 121.0018 | 14.7278 | 9796010.08 | 9629462.08 | 2024 | GILTOP CIVIL ENGINEERING CONSTRUCTION | 3843 | 2024 | 2024-07-12 | 02/14/2024 | 166548 | 0 | 2024-07-11 |  | 1
2024 | Region III | BULACAN | CITY OF MEYCAUAYAN (BULACAN) | P00824699LZ | Construction of Flood Mitigation Structure | 120.9698 | 14.7223 | 48999785.66 | 48999993.98 | 2024 | ROYAL CROWN MONARCH CONSTRUCTION & SUPPLIES CORP. | 3844 | 2024 | 2024-09-17 | 03/25/2024 | 0 | 208.32 | 2024-09-16 |  | 1
2023 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00740296LZ | Construction of Flood Mitigation Facility | 120.9768 | 14.6003 | 72374961.18 | 70449787.58 | 2023 | ALPHA & OMEGA GEN. CONTRACTOR & DEVELOPMENT CORP. / GOLDEN J'S CONSTRUCTION SERVICES | 3845 | 2023 | 2023-06-22 | 03/28/2023 | 1925173.6 | 0 | 2023-06-29 | 7
2024 | National Capital Region | QUEZON CITY | QUEZON CITY (METROPOLITAN MANILA) | P00845878LZ | Construction of Flood Mitigation Structure | 121.0334 | 14.6261 | 49499926.25 | 49498395.28 | 2024 | JTC CRUZ CONSTRUCTION CO., INC. | 3846 | 2024 | 2024-12-20 | 03/26/2024 | 1530.97 | 0 | 2024-12-19 |  | 1
2024 | Region IV-A | BATANGAS | TALISAY (BATANGAS) | P00839098LZ | Construction of Drainage Structure | 121.0235 | 14.0949 | 4950000 | 4949056.8 | 2024 | OIC CONZTRUCT AND SUPPLY CORPORATION(FORMERLY:OIC CONST.) | 3847 | 2024 | 2024-06-13 | 02/15/2024 | 943.2 | 0 | 2024-06-12 |  | 1
2024 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00820660LZ | Construction of Flood Mitigation Structure | 121.0124 | 14.5792 | 29399909.09 | 28936681.15 | 2024 | SLHAV CONSTRUCTION | 3848 | 2024 | 2024-06-14 | 03/19/2024 | 463227.94 | 0 | 2025-03-12 | 271
2022 | National Capital Region | TAGUIG CITY | TAGUIG CITY (METROPOLITAN MANILA) | P00620030LZ | Construction of Flood Mitigation Facility | 121.0572 | 14.4668 | 96499593.17 | 96500000 | 2023 | ST. TIMOTHY CONSTRUCTION CORPORATION / TWENTYSIX CONSTRUCTION INC. | 3849 | 2022 | 2023-03-06 | 03/21/2022 | 0 | 406.83 | 2023-04-04 | 29
2022 | Region IV-A | CAVITE | BACOOR CITY (CAVITE) | P00639487LZ | Construction of Slope Protection Structure | 121.002 | 14.3948 | 19300000 | 19298004.01 | 2023 | E. F. CHUA CONSTRUCTION, INC. | 3850 | 2022 | 2023-04-16 | 10/19/2022 | 1995.99 | 0 | 2023-04-15 |  | 1
2022 | National Capital Region | VALENZUELA CITY | CITY OF VALENZUELA (METROPOLITAN MANILA) | P00620029LZ | Construction of Flood Mitigation Facility | 120.9699 | 14.7218 | 241247714.4 | 234010231.7 | 2024 | TOUGHBUILT CONSTRUCTION & TRADING, INC. / AKN CONSTRUCTION CORPORATION | 3851 | 2022 | 2024-02-19 | 02/11/2022 | 7237482.7 | 0 | 2023-10-02 |  | 140
2022 | National Capital Region | LAS PIÃ‘AS CITY | CITY OF LAS PIÃ‘AS (METROPOLITAN MANILA) | P00631009LZ | Rehabilitation / Major Repair of Drainage Structure | 120.9768 | 14.4608 | 19599920.44 | 19594904.1 | 2023 | KPSL GENERAL CONTRACTOR INC. | 3852 | 2022 | 2023-08-22 | 06/13/2022 | 5016.34 | 0 | 2023-08-21 |  | 1
2024 | National Capital Region | TAGUIG CITY | TAGUIG CITY (METROPOLITAN MANILA) | P00821047LZ | Construction of Slope Protection Structure | 121.0334 | 14.5774 | 96499461.64 | 94569472.4 | 2024 | J. SIMEON CONSTRUCTION | 3853 | 2024 | 2024-07-22 | 02/13/2024 | 1929989.24 | 0 | 2024-10-08 | 78
2023 | National Capital Region | MAKATI CITY | CITY OF MAKATI (METROPOLITAN MANILA) | P00725525LZ | Construction of Revetment | 121.0126 | 14.5442 | 73753020 | 73738662.22 | 2024 | TWO DIMENSION CONSTRUCTION | 3854 | 2023 | 2024-01-02 | 03/09/2023 | 14357.78 | 0 | 2024-01-01 |  | 1
2023 | Region IV-A | BATANGAS | BATANGAS CITY (CAPITAL) (BATANGAS) | P00742180LZ | Upgrading of Drainage Structure | 121.0572 | 13.7833 | 99000000 | 99000000 | 2023 | DL ENTERPRISES / MARTIN BUILDERS INC. (FOR:MARTIN BUILDERS CONSTRUCTION SERVICES) | 3855 | 2023 | 2023-11-29 | 04/11/2023 | 0 | 0 | 2024-02-06 | 69
2024 | Region IV-A | BATANGAS | TALISAY (BATANGAS) | P00839607LZ | Construction of Slope Protection Structure | 121.0129 | 14.0924 | 4950000 | 4949278.2 | 2024 | KEASCIA CONSTRUCTION & SUPPLY | 3856 | 2024 | 2024-07-13 | 02/15/2024 | 721.8 | 0 | 2024-07-12 |  | 1
2022 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00620064LZ | Construction of Flood Mitigation Structure | 121.0021 | 14.6032 | 72374894.32 | 72374100.88 | 2022 | EIGHT J'S CONSTRUCTION SERVICES | 3857 | 2022 | 2022-11-18 | 04/01/2022 | 793.44 | 0 | 2023-03-05 | 107
2024 | Region IV-A | CAVITE | BACOOR CITY (CAVITE) | P00846056LZ | Construction of Revetment | 120.9699 | 14.4731 | 15344985.9 | 15344921.42 | 2024 | ALMAKAR BUILDERS & METAL WORKS | 3858 | 2024 | 2024-12-09 | 05/15/2024 | 64.48 | 0 | 2025-01-08 | 30
2024 | National Capital Region | QUEZON CITY | QUEZON CITY (METROPOLITAN MANILA) | P00844688LZ | Construction of Drainage Structure | 121.0336 | 14.6892 | 14699856.72 | 14545505.14 | 2024 | TOUGHBILT CONSTRUCTION & TRADING, INC. | 3859 | 2024 | 2024-07-15 | 04/01/2024 | 154351.58 | 0 | 2024-09-26 | 73
2024 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00820616LZ | Construction of Drainage Structure | 121.0236 | 14.5946 | 9799829.81 | 9703253.01 | 2024 | JMK BUILDERS CONSTRUCTION | 3860 | 2024 | 2024-06-10 | 02/12/2024 | 96576.8 | 0 | 2024-10-13 | 125
2024 | Region IV-A | CAVITE | CITY OF CARMONA (CAVITE) | P00825113LZ | Construction of Revetment | 121.0573 | 14.3235 | 125449966.1 | 125449943.3 | 2024 | OMNICON BUILDERS | 3861 | 2024 | 2024-12-06 | 02/14/2024 | 22.8 | 0 | 2025-03-23 | 107
2024 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00820086LZ | Construction of Flood Mitigation Facility | 120.9769 | 14.6352 | 144749909.1 | 142133628.7 | 2024 | JIIK CONSTRUCTION SERVICES | 3862 | 2024 | 2024-07-06 | 02/08/2024 | 2616280.4 | 0 | 2024-07-05 |  | 1
2023 | National Capital Region | PARAÃ‘AQUE CITY | CITY OF PARAÃ‘AQUE (METROPOLITAN MANILA) | P00742240LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.013 | 14.4491 | 19800000 | 19791672.85 | 2023 | P.L.G.L. CONSTRUCTION | 3863 | 2023 | 2023-10-24 | 05/16/2023 | 8327.15 | 0 | 2024-01-09 | 77
2024 | Region III | BULACAN | SAN ILDEFONSO (BULACAN) | P00845807LZ | Construction of Flood Mitigation Structure | 120.9702 | 15.0227 | 98998746.22 | 98998363.35 | 2025 | TOPNOTCH CATALYST BUILDERS INC. / ONE FRAME CONSTRUCTION INC. | 3864 | 2024 | 2025-01-13 | 05/06/2024 | 382.87 | 0 | 2025-02-28 | 46
2024 | National Capital Region | QUEZON CITY | QUEZON CITY (METROPOLITAN MANILA) | P00820641LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.0336 | 14.7106 | 29399900 | 29399739.03 | 2024 | FRAMECON BUILDERS | 3865 | 2024 | 2024-10-28 | 02/06/2024 | 160.97 | 0 | 2024-10-31 | 3
2022 | National Capital Region | VALENZUELA CITY | CITY OF VALENZUELA (METROPOLITAN MANILA) | P00637047LZ | Construction of Flood Mitigation Facility | 120.9702 | 14.7205 | 24484572.72 | 23689711.72 | 2023 | MIGHTY CONSTRUCTION & DEVELOPMENT INC. | 3866 | 2022 | 2023-02-15 | 03/24/2022 | 794861 | 0 | 2023-02-15 | 0
2024 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00820013LZ | Construction of Drainage Structure | 121.024 | 14.5982 | 67549571.19 | 65235972.08 | 2024 | JCA CONSTRUCTION AND CONSTRUCTION SUPPLY | 3867 | 2024 | 2024-12-10 | 02/14/2024 | 2313599.11 | 0 | 2024-12-09 |  | 1
2022 | Region III | BULACAN | CITY OF SAN JOSE DEL MONTE (BULACAN) | P00637072LZ | Construction of Slope Protection Structure | 121.0575 | 14.8291 | 48999233.8 | 48997036.71 | 2023 | ALPHA & OMEGA GEN. CONTRACTOR & DEVELOPMENT CORP. | 3868 | 2022 | 2023-01-02 | 05/26/2022 | 2197.09 | 0 | 2023-01-04 | 2
2022 | National Capital Region | CALOOCAN CITY | CALOOCAN CITY (METROPOLITAN MANILA) | P00620400LZ | Construction of Flood Mitigation Structure | 121.0133 | 14.6842 | 29399643.45 | 28871376.46 | 2022 | PERSAN CONSTRUCTION, INC. (FORMERLY: PERSAN CONST. | 3869 | 2022 | 2022-12-12 | 02/08/2022 | 528266.99 | 0 | 2022-12-03 |  | 9
2024 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00823247LZ | Construction of Flood Mitigation Facility | 120.9769 | 14.6352 | 144749278.6 | 141715719.7 | 2024 | JIIK CONSTRUCTION SERVICES | 3870 | 2024 | 2024-07-11 | 02/13/2024 | 3033558.9 | 0 | 2024-07-10 |  | 1
2022 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00620063LZ | Construction of Flood Mitigation Facility | 121.0021 | 14.6032 | 72374442.98 | 72374113.53 | 2023 | ALPHA & OMEGA GEN. CONTRACTOR & DEVELOPMENT CORP. / CALCON ENGINEERING | 3871 | 2022 | 2023-08-29 | 04/01/2022 | 329.45 | 0 | 2023-08-28 |  | 1
2022 | Region III | BULACAN | CITY OF SAN JOSE DEL MONTE (BULACAN) | P00620161LZ | Construction of Flood Mitigation Structure | 121.0338 | 14.821 | 94569044.49 | 94569655.86 | 2022 | L.R. TIQUI BUILDERS, INC. | 3872 | 2022 | 2022-11-23 | 03/07/2022 | 0 | 611.37 | 2022-12-11 | 18
2022 | National Capital Region | VALENZUELA CITY | CITY OF VALENZUELA (METROPOLITAN MANILA) | P00620393LZ | Construction of Flood Mitigation Structure | 120.9702 | 14.6975 | 14693446.94 | 14370183.34 | 2022 | STO. CRISTO CONSTRUCTION & TRADING INC. (FOR: STO. CRISTO CONSTRUCTION & TRADING) | 3873 | 2022 | 2022-10-04 | 02/08/2022 | 323263.6 | 0 | 2022-10-04 | 0
2023 | National Capital Region | TAGUIG CITY | TAGUIG CITY (METROPOLITAN MANILA) | P00725521LZ | Construction of Flood Mitigation Facility | 121.0578 | 14.4666 | 91674760.54 | 88875980.92 | 2024 | FRANZCOR TRADING & CONSTRUCTION | 3874 | 2023 | 2024-06-04 | 10/09/2023 | 2798779.62 | 0 | 2024-06-03 |  | 1
2023 | National Capital Region | QUEZON CITY | QUEZON CITY (METROPOLITAN MANILA) | P00742246LZ | Construction of Flood Mitigation Structure | 121.0133 | 14.6495 | 9899999.99 | 9800999.99 | 2024 | IM CONSTRUCTION CORPORATION | 3875 | 2023 | 2024-01-18 | 10/18/2023 | 99000 | 0 | 2024-01-14 |  | 4
2023 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00726793LZ | Construction of Flood Mitigation Structure | 120.9771 | 14.5799 | 96499994.7 | 96495753.94 | 2023 | ST. TIMOTHY CONSTRUCTION CORPORATION / ALRIE CONSTRUCTION SERVICES | 3876 | 2023 | 2023-12-04 | 04/24/2023 | 4240.76 | 0 | 2024-02-16 | 74
2018 | Region IV-B | OCCIDENTAL MINDORO |  | P00223374LZ | Construction of Flood Mitigation Structure | 121.0133 | 12.6311 | 25646600 | 24646157.14 | 2023 | FFJJ CONSTRUCTION | 3877 | 2018 | 2023-03-27 | 04/20/2018 | 1000442.86 | 0 | 2018-10-11 |  | 1628
2022 | National Capital Region | VALENZUELA CITY | CITY OF VALENZUELA (METROPOLITAN MANILA) | P00639412LZ | Construction of Flood Mitigation Facility | 120.9703 | 14.7203 | 13708287.93 | 13274738.88 | 2022 | TOUGHBUILT CONSTRUCTION & TRADING, INC. | 3878 | 2022 | 2022-12-16 | 03/24/2022 | 433549.05 | 0 | 2022-12-17 | 1
2023 | National Capital Region | CALOOCAN CITY | CALOOCAN CITY (METROPOLITAN MANILA) | P00725556LZ | Construction of Flood Mitigation Structure | 121.0338 | 14.7731 | 91669611.62 | 90070431.63 | 2023 | PERSAN CONSTRUCTION, INC. (FORMERLY: PERSAN CONST. | 3879 | 2023 | 2023-11-24 | 03/17/2023 | 1599179.99 | 0 | 2024-02-08 | 76
2023 | National Capital Region | PARAÃ‘AQUE CITY | CITY OF PARAÃ‘AQUE (METROPOLITAN MANILA) | P00725536LZ | Construction of Flood Mitigation Facility | 121.0021 | 14.4944 | 93946803 | 93946610 | 2024 | NEWBIG FOUR J CONSTRUCTION INC., (FORMERLY FOUR J | 3880 | 2023 | 2024-07-15 | 02/14/2023 | 193 | 0 | 2024-07-15 | 0
2022 | National Capital Region | MUNTINLUPA CITY | CITY OF MUNTINLUPA (METROPOLITAN MANILA) | P00620909LZ | Construction of Flood Mitigation Structure | 121.0242 | 14.378 | 48999999.54 | 48994772.98 | 2023 | AARCON BUILDERS | 3881 | 2022 | 2023-09-20 | 03/11/2022 | 5226.56 | 0 | 2023-09-19 |  | 1
2023 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00726794LZ | Construction of Flood Mitigation Structure | 120.9771 | 14.5799 | 96499987.75 | 96495833.14 | 2024 | G.F. FABIAN CONSTRUCTION | 3882 | 2023 | 2024-03-11 | 04/24/2023 | 4154.61 | 0 | 2024-04-16 | 36
2022 | National Capital Region | QUEZON CITY | QUEZON CITY (METROPOLITAN MANILA) | P00632721LZ | Construction of Drainage Structure | 121.0579 | 14.6666 | 19599878.85 | 19012215.8 | 2022 | ENYE CONSTRUCTION & DEVELOPMENT INC. | 3883 | 2022 | 2022-10-24 | 03/22/2022 | 587663.05 | 0 | 2022-10-16 |  | 8
2024 | National Capital Region | PARAÃ‘AQUE CITY | CITY OF PARAÃ‘AQUE (METROPOLITAN MANILA) | P00844675LZ | Construction of Revetment | 121.0134 | 14.4987 | 29400000 | 29155410.96 | 2024 | RNN CONSTRUCTION CORPORATION (FORMERLY RNN CONSTRU | 3884 | 2024 | 2024-10-31 | 07/04/2024 | 244589.04 | 0 | 2024-10-30 |  | 1
2023 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00725508LZ | Construction of Flood Mitigation Structure | 121.0021 | 14.6032 | 90178569.15 | 87814653.82 | 2024 | SUPREME ABF CONST. & CONST. SUPPLY COMPANY INC. / RJR CALCON CORP. | 3885 | 2023 | 2024-02-20 | 02/23/2023 | 2363915.33 | 0 | 2024-04-07 | 47
2023 | Region III | BULACAN | ANGAT (BULACAN) | P00726729LZ | Construction of Flood Mitigation Structure | 121.034 | 14.9313 | 47039419.26 | 47039291.85 | 2023 | STRONGLANE BUILDERS AND TRADING CORPORATION (FORMERLY: STRONGLANE CONSTRUCTION & TRADING) | 3886 | 2023 | 2023-09-19 | 02/22/2023 | 127.41 | 0 | 2023-09-18 |  | 1
2022 | National Capital Region | SAN JUAN CITY | CITY OF SAN JUAN (METROPOLITAN MANILA) | P00620765LZ | Construction of Flood Mitigation Facility | 121.0246 | 14.5983 | 94568883.13 | 89838069.12 | 2023 | R.D. TALENS CONSTRUCTION AND TRADING / NEW EASTPOINT BUILDERS CORP. | 3887 | 2022 | 2023-01-16 | 02/16/2022 | 4730814.01 | 0 | 2022-12-11 |  | 36
2023 | Region IV-A | CAVITE | BACOOR CITY (CAVITE) | P00740645LZ | Construction of Slope Protection Structure | 120.9771 | 14.4341 | 4899985.76 | 4654105.75 | 2023 | R.K.F. BUILDERS | 3888 | 2023 | 2023-07-01 | 04/03/2023 | 245880.01 | 0 | 2023-06-30 |  | 1
2023 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00725507LZ | Construction of Flood Mitigation Facility | 121.0021 | 14.6033 | 90183433.1 | 90183040.8 | 2023 | RAICON DEVELOPMENT CORPORATION (FORMERLY : RA IGNACIO CONST. CORP.) / ST. TIMOTHY CONSTRUCTION CORPORATION | 3889 | 2023 | 2023-06-26 | 02/17/2023 | 392.3 | 0 | 2023-07-07 | 11
2023 | Region III | NUEVA ECIJA | SAN JOSE CITY (NUEVA ECIJA) | P00726166LZ | Construction of Flood Mitigation Structure | 121.0135 | 15.7554 | 49000000 | 48999972.55 | 2023 | AMP 723 CONSTRUCTION CORPORATION (FORMERLY: A.M.P. CONSTRUCTION) / IJK MAE CONSTRUCTION INC. | 3890 | 2023 | 2023-10-27 | 02/09/2023 | 27.45 | 0 | 2023-11-04 | 8
2023 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00725477LZ | Construction of Flood Mitigation Facility | 120.9704 | 14.6079 | 96499495.2 | 93816118.9 | 2023 | EIGHT J'S CONSTRUCTION SERVICES | 3891 | 2023 | 2023-07-25 | 02/16/2023 | 2683376.3 | 0 | 2023-07-24 |  | 1
2022 | National Capital Region | PARAÃ‘AQUE CITY | CITY OF PARAÃ‘AQUE (METROPOLITAN MANILA) | P00620920LZ | Construction of Revetment | 121.0341 | 14.4726 | 49000000 | 48993324.65 | 2023 | RAICON DEVELOPMENT CORPORATION (FORMERLY : RA IGNACIO CONST. CORP.) / P.L.G.L. CONSTRUCTION | 3892 | 2022 | 2023-02-16 | 06/22/2022 | 6675.35 | 0 | 2023-02-15 |  | 1
2023 | National Capital Region | QUEZON CITY | QUEZON CITY (METROPOLITAN MANILA) | P00727029LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.0583 | 14.6287 | 19599546.5 | 19557713.2 | 2024 | E.L. TORRES CONSTRUCTION AND TRADING INC. (FORMERLY : E. L. TORRES CONSTRUCTION & TRADING | 3893 | 2023 | 2024-03-14 | 03/29/2023 | 41833.3 | 0 | 2024-04-05 | 22
2022 | Region IV-A | LAGUNA | CITY OF SAN PEDRO (LAGUNA) | P00620220LZ | Construction of Revetment | 121.0246 | 14.3457 | 91675000 | 88466408.87 | 2023 | ST. MATTHEW GEN. CONTRACTOR & DEVELOPMENT CORP. / ELITE GENERAL CONTRACTOR AND DEVELOPMENT CORP. | 3894 | 2022 | 2023-04-03 | 03/22/2022 | 3208591.13 | 0 | 2023-04-02 |  | 1
2023 | National Capital Region | VALENZUELA CITY | CITY OF VALENZUELA (METROPOLITAN MANILA) | P00725561LZ | Construction of Flood Mitigation Structure | 121.0022 | 14.7057 | 58544305.33 | 57081541.95 | 2023 | DIADEMA CONSTRUCTION AND ENTERPRISES INC. (FORMERLY: DIADEMA ENTERPRISES) | 3895 | 2023 | 2023-07-28 | 02/21/2023 | 1462763.38 | 0 | 2024-01-15 | 171
2022 | National Capital Region | MAKATI CITY | CITY OF MAKATI (METROPOLITAN MANILA) | P00637039LZ | Construction of Revetment | 121.0141 | 14.5529 | 39200000 | 39200000 | 2023 | STRONGLANE BUILDERS AND TRADING CORPORATION (FORMERLY: STRONGLANE CONSTRUCTION & TRADING) | 3896 | 2022 | 2023-05-22 | 03/22/2022 | 0 | 0 | 2023-08-06 | 76
2023 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00726003LZ | Construction of Flood Mitigation Facility | 120.9704 | 14.6079 | 48999790.18 | 48989429.12 | 2023 | JELSIE CONSTRUCTION & SUPPLY | 3897 | 2023 | 2023-06-23 | 02/17/2023 | 10361.06 | 0 | 2023-06-30 | 7
2024 | National Capital Region | CALOOCAN CITY | CALOOCAN CITY (METROPOLITAN MANILA) | P00820045LZ | Construction of Flood Mitigation Structure | 121.0342 | 14.7846 | 91673549.8 | 89565038.74 | 2024 | KING EIGHT BUILDERS AND SUPPLY | 3898 | 2024 | 2024-07-22 | 02/14/2024 | 2108511.06 | 0 | 2024-10-09 | 79
2024 | Region III | BULACAN | NORZAGARAY (BULACAN) | P00823480LZ | Construction of Flood Mitigation Structure | 121.0584 | 14.9088 | 42525451.98 | 42525092.5 | 2024 | DEVEX INCORPORATED | 3899 | 2024 | 2024-10-12 | 03/25/2024 | 359.48 | 0 | 2024-10-11 |  | 1
2022 | Region IV-A | CAVITE | CITY OF DASMARIÃ‘AS (CAVITE) | P00620222LZ | Construction of Revetment | 120.9771 | 14.352 | 96499997.17 | 96494250.28 | 2023 | ALMAKAR BUILDERS & METAL WORKS | 3900 | 2022 | 2023-12-04 | 03/07/2022 | 5746.89 | 0 | 2023-12-24 | 20
2023 | National Capital Region | QUEZON CITY | QUEZON CITY (METROPOLITAN MANILA) | P00726033LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.0249 | 14.6256 | 9799811.8 | 9799232.55 | 2023 | LIM GENERAL CONTRACTOR CORPORATION | 3901 | 2023 | 2023-11-27 | 02/20/2023 | 579.25 | 0 | 2023-11-26 |  | 1
2021 | National Capital Region | CALOOCAN CITY |  | P00525794LZ | Construction of Flood Mitigation Structure | 121.0141 | 14.7341 | 14692196.51 | 14310181.46 | 2022 | IM CONSTRUCTION CORPORATION | 3902 | 2021 | 2022-08-22 | 02/24/2022 | 382015.05 | 0 | 2022-08-21 |  | 1
2023 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00726001LZ | Construction of Flood Mitigation Facility | 120.9704 | 14.6079 | 48999823.74 | 47749362.48 | 2023 | JELSIE CONSTRUCTION & SUPPLY | 3903 | 2023 | 2023-07-25 | 02/17/2023 | 1250461.26 | 0 | 2023-08-04 | 10
2024 | National Capital Region | CALOOCAN CITY | CALOOCAN CITY (METROPOLITAN MANILA) | P00820580LZ | Construction of Drainage Structure | 121.0342 | 14.7846 | 48999682.29 | 47970672.03 | 2024 | WAWAO BUILDERS | 3904 | 2024 | 2024-07-03 | 02/14/2024 | 1029010.26 | 0 | 2025-01-07 | 188
2022 | National Capital Region | CALOOCAN CITY | CALOOCAN CITY (METROPOLITAN MANILA) | P00620024LZ | Construction of Flood Mitigation Structure | 121.0585 | 14.7784 | 66781067.47 | 65374049.41 | 2022 | PERSAN CONSTRUCTION, INC. (FORMERLY: PERSAN CONST. | 3905 | 2022 | 2022-09-19 | 02/11/2022 | 1407018.06 | 0 | 2023-01-05 | 108
2023 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00725506LZ | Construction of Flood Mitigation Structure | 120.9771 | 14.6003 | 95992923.27 | 94716532.95 | 2024 | ST. TIMOTHY CONSTRUCTION CORPORATION / ALLEYWAY CONSTRUCTION | 3906 | 2023 | 2024-08-05 | 02/17/2023 | 1276390.32 | 0 | 2024-08-04 |  | 1
2024 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00820624LZ | Construction of Flood Mitigation Facility | 121.0251 | 14.596 | 48999992.74 | 48891968.68 | 2025 | FLORDES CONSTRUCTION & TRADING CORP. (FORMERLY FLO | 3907 | 2024 | 2025-01-02 | 02/07/2024 | 108024.06 | 0 | 2025-01-01 |  | 1
2023 | Region IV-A | CAVITE | BACOOR CITY (CAVITE) | P00737510LZ | Construction of Slope Protection Structure | 120.9771 | 14.4339 | 4949983.33 | 4703829.86 | 2023 | R.K.F. BUILDERS | 3908 | 2023 | 2023-07-01 | 04/03/2023 | 246153.47 | 0 | 2023-06-30 |  | 1
2023 | National Capital Region | PARAÃ‘AQUE CITY | CITY OF PARAÃ‘AQUE (METROPOLITAN MANILA) | P00727009LZ | Construction of Revetment | 121.0022 | 14.4752 | 49000000 | 48999076.1 | 2024 | EURO CONSTRUCTION AND SUPPLY ( FORMERLY: EURO CONSTRUCTION AND TRADING) | 3909 | 2023 | 2024-03-17 | 05/23/2023 | 923.9 | 0 | 2024-03-16 |  | 1
2024 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00820085LZ | Construction of Flood Mitigation Facility | 120.9704 | 14.6031 | 96499871.93 | 94322661.24 | 2024 | GOLDEN J'S CONSTRUCTION SERVICES | 3910 | 2024 | 2024-07-15 | 02/08/2024 | 2177210.69 | 0 | 2024-07-15 | 0
2023 | National Capital Region | QUEZON CITY | QUEZON CITY (METROPOLITAN MANILA) | P00736173LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.0342 | 14.7105 | 48999699 | 48019705.02 | 2023 | E.L. TORRES CONSTRUCTION AND TRADING INC. (FORMERLY : E. L. TORRES CONSTRUCTION & TRADING | 3911 | 2023 | 2023-12-10 | 02/14/2023 | 979993.98 | 0 | 2023-12-09 |  | 1
2024 | Region III | BULACAN | CITY OF SAN JOSE DEL MONTE (BULACAN) | P00820236LZ | Construction of Flood Mitigation Facility | 121.0586 | 14.8306 | 96499940.27 | 96497855.1 | 2024 | TRIPLE 8 CONSTRUCTION & SUPPLY, INC. (FORMERLY TRIPLE 8 CONST. & SUPPLY) | 3912 | 2024 | 2024-08-09 | 02/22/2024 | 2085.17 | 0 | 2024-12-12 | 125
2022 | National Capital Region | MAKATI CITY | CITY OF MAKATI (METROPOLITAN MANILA) | P00632711LZ | Construction of Revetment | 121.0142 | 14.5521 | 49000000 | 49500000 | 2023 | STRONGLANE BUILDERS AND TRADING CORPORATION (FORMERLY: STRONGLANE CONSTRUCTION & TRADING) | 3913 | 2022 | 2023-05-28 | 03/22/2022 | 0 | 500000 | 2023-05-27 |  | 1
2022 | Region III | BULACAN | SAN MIGUEL (BULACAN) | P00620524LZ | Construction of Flood Mitigation Structure | 120.9772 | 15.1524 | 39199830.15 | 38602322.03 | 2023 | FLORDES CONSTRUCTION & TRADING CORP. (FORMERLY FLO | 3914 | 2022 | 2023-08-13 | 02/28/2022 | 597508.12 | 0 | 2023-08-12 |  | 1
2024 | National Capital Region | PARAÃ‘AQUE CITY | CITY OF PARAÃ‘AQUE (METROPOLITAN MANILA) | P00844674LZ | Rehabilitation / Major Repair of Drainage Structure | 121.0022 | 14.4634 | 14700000 | 14699900.18 | 2024 | G.F. ROVERO MERCHANDISING | 3915 | 2024 | 2024-10-23 | 06/27/2024 | 99.82 | 0 | 2024-10-23 | 0
2024 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00823240LZ | Construction of Flood Mitigation Facility | 120.9704 | 14.6031 | 96499295.44 | 95326327.4 | 2024 | GOLDEN J'S CONSTRUCTION SERVICES | 3916 | 2024 | 2024-07-15 | 02/07/2024 | 1172968.04 | 0 | 2024-08-13 | 29
2024 | Region III | BULACAN | CITY OF SAN JOSE DEL MONTE (BULACAN) | P00820182LZ | Construction of Dike | 121.0343 | 14.8353 | 96499952.4 | 96498309.12 | 2024 | ROYAL CROWN MONARCH CONSTRUCTION & SUPPLIES CORP. | 3917 | 2024 | 2024-11-11 | 02/26/2024 | 1643.28 | 0 | 2024-12-16 | 35
2024 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00823243LZ | Construction of Flood Mitigation Facility | 120.9772 | 14.6082 | 144749997.3 | 144719698.2 | 2024 | EIGHT J'S CONSTRUCTION SERVICES | 3918 | 2024 | 2024-06-20 | 02/16/2024 | 30299.1 | 0 | 2024-07-13 | 23
2022 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00631036LZ | Rehabilitation / Major Repair of Drainage Structure | 121.0022 | 14.604 | 48999989.6 | 48999810.66 | 2022 | EIGHT J'S CONSTRUCTION SERVICES | 3919 | 2022 | 2022-10-17 | 02/23/2022 | 178.94 | 0 | 2022-11-20 | 34
2024 | Region III | BULACAN | CITY OF SAN JOSE DEL MONTE (BULACAN) | P00820267LZ | Construction of Slope Protection Structure | 121.0586 | 14.8306 | 96499740 | 96495510.66 | 2024 | M3 KONSTRACT CORPORATION (FORMERLY:MARGARITA CONSTRUCTION) | 3920 | 2024 | 2024-12-13 | 02/22/2024 | 4229.34 | 0 | 2024-12-12 |  | 1
2024 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00824609LZ | Construction of Flood Mitigation Facility | 120.9704 | 14.618 | 48999956.39 | 48997795.07 | 2024 | JELSIE CONSTRUCTION & SUPPLY | 3921 | 2024 | 2024-06-13 | 02/08/2024 | 2161.32 | 0 | 2024-06-24 | 11
2023 | Region IV-A | BATANGAS | TALISAY (BATANGAS) | P00745444LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.0344 | 14.0941 | 4825000 | 4825000 | 2023 | BCVILLASENOR CONSTRUCTION | 3922 | 2023 | 2023-06-02 | 03/23/2023 | 0 | 0 | 2023-07-19 | 47
2025 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00920745LZ | Construction of Flood Mitigation Facility | 120.9772 | 14.6082 | 48999896.41 | 48015187.82 | 2025 | GOLDEN J'S CONSTRUCTION SERVICES | 3923 | 2025 | 2025-03-12 | 02/14/2025 | 984708.59 | 0 | 2025-04-03 | 22
2024 | Region III | BULACAN | DOÃ‘A REMEDIOS TRINIDAD (BULACAN) | P00844532LZ | Construction of Flood Mitigation Structure | 121.0587 | 15.0044 | 48249412.9 | 48249750.32 | 2025 | FIVE TRAVELLERS CONSTRUCTION INC. | 3924 | 2024 | 2025-02-11 | 06/17/2024 | 0 | 337.42 | 2025-02-10 |  | 1
2024 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00843172LZ | Rehabilitation / Major Repair of Drainage Structure | 120.9705 | 14.6174 | 96499841.66 | 96221240.82 | 2024 | EIGHT J'S CONSTRUCTION SERVICES / MNJAP CONSTRUCTION SERVICES | 3925 | 2024 | 2024-08-19 | 02/20/2024 | 278600.84 | 0 | 2024-10-03 | 45
2022 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00620422LZ | Construction of Flood Mitigation Structure | 120.9772 | 14.6023 | 26007106.48 | 25751991.02 | 2022 | JELSIE CONSTRUCTION & SUPPLY | 3926 | 2022 | 2022-09-26 | 02/23/2022 | 255115.46 | 0 | 2022-09-25 |  | 1
2024 | Region III | BULACAN | CITY OF SAN JOSE DEL MONTE (BULACAN) | P00844749LZ | Construction of Flood Mitigation Structure | 121.0587 | 14.8025 | 48999805.26 | 48257458.19 | 2025 | TRIPLE 8 CONSTRUCTION & SUPPLY, INC. (FORMERLY TRIPLE 8 CONST. & SUPPLY) | 3927 | 2024 | 2025-02-12 | 04/30/2024 | 742347.07 | 0 | 2025-02-17 | 5
2022 | National Capital Region | VALENZUELA CITY | CITY OF VALENZUELA (METROPOLITAN MANILA) | P00621430LZ | Construction of Flood Mitigation Structure | 121.0023 | 14.688 | 19593440.87 | 19005625.23 | 2023 | SONPRO CONSTRUCTION | 3928 | 2022 | 2023-05-08 | 03/24/2022 | 587815.64 | 0 | 2022-11-17 |  | 172
2023 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00740280LZ | Construction of Flood Mitigation Structure | 120.9705 | 14.6081 | 96499854.46 | 96219232.12 | 2024 | G.F. FABIAN CONSTRUCTION | 3929 | 2023 | 2024-07-15 | 03/28/2023 | 280622.34 | 0 | 2024-07-14 |  | 1
2022 | National Capital Region | QUEZON CITY | QUEZON CITY (METROPOLITAN MANILA) | P00640489LZ | Construction of Flood Mitigation Structure | 121.0023 | 14.6413 | 19600000 | 18816000 | 2023 | ALPIZ CONSTRUCTION & DEVELOPMENT CORPORATION | 3930 | 2022 | 2023-01-11 | 05/17/2022 | 784000 | 0 | 2023-01-10 |  | 1
2022 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00620101LZ | Construction of Flood Mitigation Facility | 120.9706 | 14.6181 | 96499763.57 | 96303461.75 | 2023 | EIGHT J'S CONSTRUCTION SERVICES | 3931 | 2022 | 2023-07-25 | 02/23/2022 | 196301.82 | 0 | 2023-07-24 |  | 1
2023 | National Capital Region | QUEZON CITY | QUEZON CITY (METROPOLITAN MANILA) | P00740507LZ | Construction of Flood Mitigation Structure | 121.059 | 14.6884 | 29399999.54 | 29399680.87 | 2023 | WAY MAKER GENERAL CONTRACTOR OPC | 3932 | 2023 | 2023-11-13 | 03/21/2023 | 318.67 | 0 | 2023-12-14 | 31
2024 | National Capital Region | PARAÃ‘AQUE CITY | CITY OF PARAÃ‘AQUE (METROPOLITAN MANILA) | P00848601LZ | Construction of Revetment | 121.0023 | 14.4742 | 79200000 | 79048492.76 | 2025 | E.R. RODRIGUEZ CONSTRUCTION CORPORATION (FORMERLY: E.R. RODRIGUEZ CONSTRUCTION) | 3933 | 2024 | 2025-02-02 | 05/09/2024 | 151507.24 | 0 | 2025-02-01 |  | 1
2022 | Region IV-A | CAVITE | CITY OF CARMONA (CAVITE) | P00632879LZ | Construction of Drainage Structure | 121.059 | 14.3156 | 39599727.15 | 4949610.57 | 2022 | TRIPLE 8 CONSTRUCTION & SUPPLY, INC. (FORMERLY TRIPLE 8 CONST. & SUPPLY) | 3934 | 2022 | 2022-08-15 | 02/17/2022 | 34650116.58 | 0 | 2022-08-14 |  | 1
2022 | National Capital Region | PARAÃ‘AQUE CITY | CITY OF PARAÃ‘AQUE (METROPOLITAN MANILA) | P00620919LZ | Construction of Revetment | 121.0346 | 14.4717 | 49000000 | 48995753.41 | 2023 | AKN CONSTRUCTION CORPORATION | 3935 | 2022 | 2023-05-22 | 06/22/2022 | 4246.59 | 0 | 2023-07-05 | 44
2022 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00620097LZ | Construction of Flood Mitigation Facility | 120.9706 | 14.6181 | 96499960.27 | 93818961.57 | 2022 | EIGHT J'S CONSTRUCTION SERVICES | 3936 | 2022 | 2022-11-17 | 02/18/2022 | 2680998.7 | 0 | 2022-11-24 | 7
2024 | Region III | BULACAN | SAN MIGUEL (BULACAN) | P00844528LZ | Construction of Flood Mitigation Structure | 121.0347 | 15.1594 | 48249521.51 | 48248500.57 | 2025 | C & F CONSTRUCTION & DEVELOPMENT CORPORATION | 3937 | 2024 | 2025-02-25 | 07/01/2024 | 1020.94 | 0 | 2025-02-24 |  | 1
2022 | National Capital Region | CALOOCAN CITY | CALOOCAN CITY (METROPOLITAN MANILA) | P00620401LZ | Construction of Flood Mitigation Structure | 121.0023 | 14.6862 | 45076692.42 | 44130056.18 | 2022 | PERSAN CONSTRUCTION, INC. (FORMERLY: PERSAN CONST. | 3938 | 2022 | 2022-12-12 | 02/08/2022 | 946636.24 | 0 | 2023-01-02 | 21
2023 | Region IV-A | LAGUNA | CITY OF SANTA ROSA (LAGUNA) | P00725846LZ | Construction of Flood Mitigation Structure | 121.0592 | 14.2641 | 96500000 | 96492115.43 | 2023 | GREAT PACIFIC BUILDERS AND GEN. CONTRACTOR INC. | 3939 | 2023 | 2023-12-14 | 02/24/2023 | 7884.57 | 0 | 2024-03-15 | 92
2022 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00620103LZ | Construction of Flood Mitigation Facility | 120.9706 | 14.6181 | 96498810.64 | 93846057.69 | 2022 | EIGHT J'S CONSTRUCTION SERVICES | 3940 | 2022 | 2022-11-17 | 04/01/2022 | 2652752.95 | 0 | 2022-11-16 |  | 1
2024 | National Capital Region | QUEZON CITY | QUEZON CITY (METROPOLITAN MANILA) | P00845879LZ | Construction of Flood Mitigation Structure | 121.0347 | 14.6254 | 49499939.9 | 49498395.28 | 2024 | JTC CRUZ CONSTRUCTION CO., INC. | 3941 | 2024 | 2024-12-20 | 03/26/2024 | 1544.62 | 0 | 2024-12-19 |  | 1
2023 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00725498LZ | Rehabilitation / Major Repair of Flood Control Structure | 120.9706 | 14.6179 | 38597907.41 | 38592779.28 | 2023 | LE BRON CONSTRUCTION | 3942 | 2023 | 2023-09-23 | 02/17/2023 | 5128.13 | 0 | 2023-09-22 |  | 1
2024 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00824614LZ | Construction of Retarding Basin | 121.0024 | 14.6011 | 48999608.47 | 48803086.9 | 2024 | ALPHA & OMEGA GEN. CONTRACTOR & DEVELOPMENT CORP. / MANGEN TECHNO-BUILDERS INC. | 3943 | 2024 | 2024-12-13 | 02/12/2024 | 196521.57 | 0 | 2024-12-20 | 7
2024 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00820070LZ | Construction of Retarding Basin | 120.9706 | 14.6063 | 96499937.49 | 96349103.73 | 2025 | G.F. FABIAN CONSTRUCTION / F316 CONSTRUCTION CORP. | 3944 | 2024 | 2025-03-17 | 02/08/2024 | 150833.76 | 0 | 2025-04-12 | 26
2023 | Region IV-A | LAGUNA | CITY OF SANTA ROSA (LAGUNA) | P00725847LZ | Construction of Flood Mitigation Structure | 121.0592 | 14.2641 | 96500000 | 96499086.72 | 2023 | YPR GEN. CONTRACTOR AND CONSTRUCTION SUPPLY INC. | 3945 | 2023 | 2023-12-08 | 02/24/2023 | 913.28 | 0 | 2024-03-15 | 98
2022 | National Capital Region | QUEZON CITY | QUEZON CITY (METROPOLITAN MANILA) | P00639311LZ | Construction of Flood Mitigation Structure | 121.0348 | 14.7007 | 96500000 | 93605000 | 2023 | PRECIOUS CONSTRUCTION / DARCY & ANNA BUILDERS & TRADING | 3946 | 2022 | 2023-08-07 | 05/19/2022 | 2895000 | 0 | 2023-05-12 |  | 87
2021 | Region II | NUEVA VIZCAYA |  | P00525974LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.0595 | 16.3898 | 29400000 | 24519676.04 | 2022 | J.E.L. CONSTRUCTION & SUPPLY | 3947 | 2021 | 2022-11-18 | 04/05/2022 | 4880323.96 | 0 | 2023-01-25 | 68
2021 | National Capital Region | CITY OF MANILA |  | P00525819LZ | Construction of Flood Mitigation Structure | 121.0024 | 14.6024 | 48999544.34 | 46940474.1 | 2022 | ST. TIMOTHY CONSTRUCTION CORPORATION | 3948 | 2021 | 2022-11-30 | 06/09/2021 | 2059070.24 | 0 | 2022-11-29 |  | 1
2024 | Region III | BULACAN | CITY OF SAN JOSE DEL MONTE (BULACAN) | P00844748LZ | Construction of Flood Mitigation Structure | 121.0595 | 14.812 | 48999939.12 | 48257590.02 | 2025 | TRIPLE 8 CONSTRUCTION & SUPPLY, INC. (FORMERLY TRIPLE 8 CONST. & SUPPLY) | 3949 | 2024 | 2025-02-12 | 04/30/2024 | 742349.1 | 0 | 2025-02-17 | 5
2023 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00725501LZ | Construction of Flood Mitigation Structure | 120.9706 | 14.6064 | 63550014.64 | 63351310.49 | 2024 | ROAD EDGE TRADING & DEVELOPMENT SERVICES | 3950 | 2023 | 2024-10-16 | 02/17/2023 | 198704.15 | 0 | 2024-12-14 | 59
2022 | Region III | BULACAN | CITY OF SAN JOSE DEL MONTE (BULACAN) | P00620163LZ | Construction of Flood Mitigation Structure | 121.0351 | 14.819 | 94569908.29 | 94568676.93 | 2022 | L.R. TIQUI BUILDERS, INC. | 3951 | 2022 | 2022-11-23 | 03/07/2022 | 1231.36 | 0 | 2022-12-11 | 18
2023 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00725502LZ | Construction of Flood Mitigation Structure | 120.9707 | 14.6062 | 63549934.4 | 63260685.8 | 2024 | ROAD EDGE TRADING & DEVELOPMENT SERVICES | 3952 | 2023 | 2024-07-15 | 02/16/2023 | 289248.6 | 0 | 2024-08-15 | 31
2023 | National Capital Region | PARAÃ‘AQUE CITY | CITY OF PARAÃ‘AQUE (METROPOLITAN MANILA) | P00725532LZ | Construction of Flood Mitigation Facility | 121.0024 | 14.4738 | 82990000 | 82982803.05 | 2024 | ST. TIMOTHY CONSTRUCTION CORPORATION | 3953 | 2023 | 2024-04-09 | 02/15/2023 | 7196.95 | 0 | 2024-04-08 |  | 1
2023 | National Capital Region | TAGUIG CITY | TAGUIG CITY (METROPOLITAN MANILA) | P00740502LZ | Construction of Drainage Structure | 121.0595 | 14.4907 | 48999816.21 | 49000000 | 2024 | STO. CRISTO CONSTRUCTION & TRADING INC. (FOR: STO. CRISTO CONSTRUCTION & TRADING) | 3954 | 2023 | 2024-06-03 | 04/27/2023 | 0 | 183.79 | 2024-01-20 |  | 135
2023 | National Capital Region | CALOOCAN CITY | CALOOCAN CITY (METROPOLITAN MANILA) | P00742113LZ | Construction of Flood Mitigation Structure | 121.0352 | 14.773 | 91673593.61 | 89748579.45 | 2023 | PERSAN CONSTRUCTION, INC. (FORMERLY: PERSAN CONST. | 3955 | 2023 | 2023-11-22 | 06/19/2023 | 1925014.16 | 0 | 2024-05-12 | 172
2023 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00725478LZ | Construction of Flood Mitigation Facility | 120.9708 | 14.6061 | 96499808.08 | 96499737.82 | 2023 | EIGHT J'S CONSTRUCTION SERVICES / JIIK CONSTRUCTION SERVICES | 3956 | 2023 | 2023-07-25 | 02/17/2023 | 70.26 | 0 | 2023-08-09 | 15
2023 | Region III | BULACAN | CITY OF SAN JOSE DEL MONTE (BULACAN) | P00725722LZ | Construction of Flood Mitigation Structure | 121.0352 | 14.8354 | 96499815.98 | 96497531.45 | 2023 | TRIPLE 8 CONSTRUCTION & SUPPLY, INC. (FORMERLY TRIPLE 8 CONST. & SUPPLY) | 3957 | 2023 | 2023-12-29 | 03/01/2023 | 2284.53 | 0 | 2023-12-28 |  | 1
2022 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00620436LZ | Construction of Flood Mitigation Structure | 121.0025 | 14.6014 | 29399785.98 | 29316136.16 | 2022 | JMK BUILDERS CONSTRUCTION | 3958 | 2022 | 2022-09-23 | 02/23/2022 | 83649.82 | 0 | 2022-09-26 | 3
2023 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00725479LZ | Construction of Flood Mitigation Facility | 120.9708 | 14.6061 | 96499510.26 | 96452618.46 | 2023 | EIGHT J'S CONSTRUCTION SERVICES | 3959 | 2023 | 2023-07-25 | 02/17/2023 | 46891.8 | 0 | 2023-08-09 | 15
2022 | National Capital Region | MAKATI CITY | CITY OF MAKATI (METROPOLITAN MANILA) | P00620374LZ | Rehabilitation / Major Repair of Drainage Structure | 121.0596 | 14.5415 | 27440000 | 27440000 | 2022 | THE STEADFAST BUILDERS | 3960 | 2022 | 2022-07-03 | 02/04/2022 | 0 | 0 | 2022-07-02 |  | 1
2022 | Region IV-A | LAGUNA | CITY OF SAN PEDRO (LAGUNA) | P00620240LZ | Construction of Revetment | 121.0352 | 14.3431 | 77200000 | 77196457 | 2022 | MAR-VEL CONSTRUCTION & SUPPLY | 3961 | 2022 | 2022-11-15 | 02/21/2022 | 3543 | 0 | 2022-12-04 | 19
2024 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00823250LZ | Construction of Flood Mitigation Facility | 120.9708 | 14.6061 | 96499194.16 | 96362389.26 | 2024 | JELSIE CONSTRUCTION & SUPPLY | 3962 | 2024 | 2024-04-17 | 02/08/2024 | 136804.9 | 0 | 2024-05-16 | 29
2024 | National Capital Region | QUEZON CITY | QUEZON CITY (METROPOLITAN MANILA) | P00838479LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.0354 | 14.7106 | 28468894.2 | 28157584.94 | 2024 | LE BRON CONSTRUCTION | 3963 | 2024 | 2024-09-16 | 02/06/2024 | 311309.26 | 0 | 2024-10-31 | 45
2024 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00823251LZ | Construction of Flood Mitigation Facility | 120.9708 | 14.6061 | 96499153 | 95445184.12 | 2024 | JELSIE CONSTRUCTION & SUPPLY | 3964 | 2024 | 2024-04-17 | 02/08/2024 | 1053968.88 | 0 | 2024-05-16 | 29
2024 | National Capital Region | CALOOCAN CITY | CALOOCAN CITY (METROPOLITAN MANILA) | P00820610LZ | Construction of Drainage Structure | 120.9708 | 14.6384 | 37283853.51 | 35678835.1 | 2025 | TOUGHBUILT CONSTRUCTION & TRADING, INC. | 3965 | 2024 | 2025-01-07 | 02/14/2024 | 1605018.41 | 0 | 2024-08-10 |  | 150
2023 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00725497LZ | Construction of Flood Mitigation Structure | 121.0027 | 14.5981 | 43424387.33 | 43340916.4 | 2024 | NEWBIG FOUR J CONSTRUCTION INC., (FORMERLY FOUR J | 3966 | 2023 | 2024-05-21 | 02/17/2023 | 83470.93 | 0 | 2024-06-14 | 24
2023 | National Capital Region | CALOOCAN CITY | CALOOCAN CITY (METROPOLITAN MANILA) | P00725980LZ | Construction of Flood Mitigation Structure | 121.0598 | 14.7769 | 48999821.53 | 47774811.92 | 2023 | WAWAO BUILDERS | 3967 | 2023 | 2023-12-27 | 02/21/2023 | 1225009.61 | 0
2024 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00820051LZ | Construction of Revetment | 120.9708 | 14.6059 | 67549777.01 | 67305759.15 | 2025 | DOUBLE 12 CONSTRUCTION & SUPPLY | 3968 | 2024 | 2025-01-12 | 02/08/2024 | 244017.86 | 0 | 2025-01-11 |  | 1
2022 | National Capital Region | CALOOCAN CITY | CALOOCAN CITY (METROPOLITAN MANILA) | P00620406LZ | Construction of Flood Mitigation Structure | 121.0354 | 14.7591 | 45064559.78 | 43645007.79 | 2022 | PERSAN CONSTRUCTION, INC. (FORMERLY: PERSAN CONST. | 3969 | 2022 | 2022-09-13 | 02/08/2022 | 1419551.99 | 0 | 2023-01-02 | 111
2021 | Region III | BULACAN |  | P00526012LZ | Construction of Flood Mitigation Structure | 121.0029 | 15.2265 | 24499991.84 | 23519992.2 | 2023 | 729 CONSTRUCTION, INC. (FORMERLY 722 CONSTRUCTION, INC.) | 3970 | 2021 | 2023-12-08 | 03/30/2022 | 979999.64 | 0 | 2023-12-07 |  | 1
2024 | Cordillera Administrative Region | IFUGAO | TINOC (IFUGAO) | P00820152LZ | Construction of Flood Mitigation Structure | 120.9709 | 16.6499 | 96496478.88 | 96500000 | 2024 | DJY CONSTRUCTION | 3971 | 2024 | 2024-12-15 | 03/18/2024 | 0 | 3521.12 | 2024-12-14 |  | 1
2024 | Region IV-A | CAVITE | CITY OF CARMONA (CAVITE) | P00825114LZ | Construction of Revetment | 121.0354 | 14.2994 | 125838870.7 | 125838791.7 | 2025 | OMNICON BUILDERS | 3972 | 2024 | 2025-02-28 | 02/14/2024 | 79 | 0 | 2025-02-27 |  | 1
2022 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00630923LZ | Construction of Drainage Structure | 121.003 | 14.5895 | 54461091.93 | 54455277.96 | 2023 | ST. TIMOTHY CONSTRUCTION CORPORATION | 3973 | 2022 | 2023-12-22 | 04/13/2022 | 5813.97 | 0 | 2024-01-07 | 16
2023 | Region IV-A | LAGUNA | CITY OF BIÃ‘AN (LAGUNA) | P00725827LZ | Construction of Flood Mitigation Structure | 121.0601 | 14.2646 | 96500000 | 93797418 | 2024 | ST. MATTHEW GEN. CONTRACTOR & DEVELOPMENT CORP. | 3974 | 2023 | 2024-03-16 | 02/24/2023 | 2702582 | 0 | 2024-03-15 |  | 1
2024 | National Capital Region | QUEZON CITY | QUEZON CITY (METROPOLITAN MANILA) | P00839534LZ | Rehabilitation / Major Repair of Drainage Structure | 121.0355 | 14.6278 | 29698930.67 | 29697364.69 | 2024 | MANCOL CONSTRUCTION CORPORATION | 3975 | 2024 | 2024-09-23 | 02/08/2024 | 1565.98 | 0 | 2024-09-22 |  | 1
2023 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00725509LZ | Construction of Flood Mitigation Structure | 121.003 | 14.5895 | 57899904.12 | 57660100.17 | 2024 | N.M.E. CONSTRUCTION | 3976 | 2023 | 2024-05-03 | 02/27/2023 | 239803.95 | 0 | 2024-05-02 |  | 1
2023 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00727025LZ | Construction of Flood Mitigation Structure | 121.0035 | 14.598 | 44099986.6 | 44092161.16 | 2023 | G.F. FABIAN CONSTRUCTION | 3977 | 2023 | 2023-09-30 | 03/01/2023 | 7825.44 | 0 | 2023-10-16 | 16
2023 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00742244LZ | Construction of Flood Mitigation Structure | 120.9709 | 14.6171 | 96499826.5 | 95158284.39 | 2024 | JTC CRUZ CONSTRUCTION CO., INC. / NEWBIG FOUR J CONSTRUCTION INC., (FORMERLY FOUR J | 3978 | 2023 | 2024-04-15 | 03/20/2023 | 1341542.11 | 0 | 2024-04-14 |  | 1
2024 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00820057LZ | Construction of Flood Mitigation Facility | 120.9709 | 14.6171 | 65619438.74 | 64212511.86 | 2024 | A.M. SALONG CONSTRUCTION | 3979 | 2024 | 2024-09-26 | 02/08/2024 | 1406926.88 | 0 | 2024-10-06 | 10
2023 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00726002LZ | Construction of Flood Mitigation Facility | 120.971 | 14.6171 | 48999542.28 | 47747381.33 | 2024 | JELSIE CONSTRUCTION & SUPPLY | 3980 | 2023 | 2024-07-16 | 02/16/2023 | 1252160.95 | 0 | 2024-07-15 |  | 1
2022 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00620033LZ | Construction of Flood Mitigation Structure | 120.971 | 14.6171 | 50469124.32 | 48192506.57 | 2023 | ALPHA & OMEGA GEN. CONTRACTOR & DEVELOPMENT CORP. | 3981 | 2022 | 2023-12-13 | 02/23/2022 | 2276617.75 | 0 | 2023-12-30 | 17
2024 | Region II | NUEVA VIZCAYA | ARITAO (NUEVA VIZCAYA) | P00839468LZ | Construction of Slope Protection Structure | 121.0356 | 16.2933 | 57900000 | 57899799.23 | 2025 | AMP 723 CONSTRUCTION CORPORATION (FORMERLY: A.M.P. CONSTRUCTION) | 3982 | 2024 | 2025-02-11 | 06/10/2024 | 200.77 | 0 | 2025-02-10 |  | 1
2022 | Region III | NUEVA ECIJA | SAN JOSE CITY (NUEVA ECIJA) | P00620153LZ | Construction of Flood Mitigation Structure | 121.0036 | 15.7782 | 57900000 | 57899979.93 | 2022 | WIZARD CONCRETE SOLUTIONS AND CONSTRUCTION CORPORATION (FORMERLY: WIZARD TRADING & CONSTRUCTION) | 3983 | 2022 | 2022-10-27 | 03/02/2022 | 20.07 | 0 | 2022-10-26 |  | 1
2022 | National Capital Region | PARAÃ‘AQUE CITY | CITY OF PARAÃ‘AQUE (METROPOLITAN MANILA) | P00620918LZ | Construction of Revetment | 121.0358 | 14.4771 | 49000000 | 48996552.93 | 2023 | RAICON DEVELOPMENT CORPORATION (FORMERLY : RA IGNACIO CONST. CORP.) / P.L.G.L. CONSTRUCTION | 3984 | 2022 | 2023-02-16 | 06/22/2022 | 3447.07 | 0 | 2023-02-15 |  | 1
2024 | National Capital Region | QUEZON CITY | QUEZON CITY (METROPOLITAN MANILA) | P00844689LZ | Construction of Drainage Structure | 121.0358 | 14.68 | 14699939.4 | 14699417.18 | 2024 | REND ENTERPRISES & GENERAL CONTRACTOR | 3985 | 2024 | 2024-09-27 | 04/01/2024 | 522.22 | 0 | 2024-09-26 |  | 1
2024 | Region IV-A | BATANGAS | SAN PASCUAL (BATANGAS) | P00823539LZ | Construction of Flood Mitigation Structure | 121.0361 | 13.7992 | 14700000 | 14475000 | 2024 | GREENFIELD CONSTRUCTION | 3986 | 2024 | 2024-05-15 | 02/07/2024 | 225000 | 0 | 2024-06-07 | 23
2022 | National Capital Region | QUEZON CITY | QUEZON CITY (METROPOLITAN MANILA) | P00639413LZ | Construction of Flood Mitigation Structure | 121.0362 | 14.6729 | 29400000 | 28518000 | 2022 | C.E.M. CONSTRUCTION, INC. | 3987 | 2022 | 2022-12-12 | 05/19/2022 | 882000 | 0 | 2023-03-13 | 91
2023 | Region IV-B | OCCIDENTAL MINDORO | RIZAL (OCCIDENTAL MINDORO) | P00727379LZ | Construction of Flood Mitigation Structure | 121.0363 | 12.467 | 45080000 | 45079770.46 | 2023 | F.A. TORRES CONSTRUCTION / MIGHTY DRAGON BUILDERS INC. | 3988 | 2023 | 2023-07-17 | 03/10/2023 | 229.54 | 0 | 2023-10-02 | 77
2023 | National Capital Region | CALOOCAN CITY | CALOOCAN CITY (METROPOLITAN MANILA) | P00725545LZ | Construction of Flood Mitigation Structure | 121.0366 | 14.7558 | 86844395.44 | 85077965.88 | 2023 | IM CONSTRUCTION CORPORATION | 3989 | 2023 | 2023-11-15 | 02/21/2023 | 1766429.56 | 0 | 2024-01-15 | 61
2024 | National Capital Region | QUEZON CITY | QUEZON CITY (METROPOLITAN MANILA) | P00820632LZ | Construction of Flood Mitigation Structure | 121.0366 | 14.7147 | 48999550.8 | 48458879.03 | 2024 | FRAMECON BUILDERS | 3990 | 2024 | 2024-11-28 | 02/06/2024 | 540671.77 | 0 | 2024-11-30 | 2
2021 | National Capital Region | CALOOCAN CITY |  | P00525778LZ | Construction of Drainage Structure | 121.0039 | 14.68 | 4895657.41 | 4790381.17 | 2022 | IM CONSTRUCTION CORPORATION | 3991 | 2021 | 2022-08-15 | 02/24/2022 | 105276.24 | 0 | 2022-06-22 |  | 54
2023 | National Capital Region | CALOOCAN CITY | CALOOCAN CITY (METROPOLITAN MANILA) | P00725547LZ | Construction of Flood Mitigation Structure | 121.0368 | 14.7725 | 86835047.93 | 85271997.66 | 2023 | E.M. CUERPO, INC. / AYLAN CONSTRUCTION & TRADING | 3992 | 2023 | 2023-12-14 | 02/21/2023 | 1563050.27 | 0 | 2024-01-15 | 32
2022 | Region III | NUEVA ECIJA | SAN JOSE CITY (NUEVA ECIJA) | P00620535LZ | Construction of Flood Mitigation Structure | 121.004 | 15.7458 | 39200000 | 39092350.45 | 2022 | IJK MAE CONSTRUCTION INC. / NIÃ‘AS CONSTRUCTION CORP. (FORMERLY: NINA'S CONSTRUCTION AND SUPPLIES) | 3993 | 2022 | 2022-08-20 | 02/22/2022 | 107649.55 | 0 | 2022-08-19 |  | 1
2022 | Region IV-A | LAGUNA | CITY OF SAN PEDRO (LAGUNA) | P00620586LZ | Construction of Flood Mitigation Structure | 121.0368 | 14.3439 | 27440000 | 27418464.34 | 2022 | FOURTH GENERATION T CONSTRUCTION | 3994 | 2022 | 2022-07-18 | 02/14/2022 | 21535.66 | 0 | 2022-08-29 | 42
2023 | National Capital Region | MAKATI CITY | CITY OF MAKATI (METROPOLITAN MANILA) | P00725975LZ | Rehabilitation / Major Repair of Drainage Structure | 121.004 | 14.5559 | 7350000 | 7129230.51 | 2023 | PETER G. CHUA BUILDERS | 3995 | 2023 | 2023-12-11 | 08/14/2023 | 220769.49 | 0 | 2023-12-10 |  | 1
2023 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00740292LZ | Construction of Flood Mitigation Facility | 121.0042 | 14.6057 | 96499452.36 | 96246850.63 | 2023 | EIGHT J'S CONSTRUCTION SERVICES | 3996 | 2023 | 2023-09-03 | 03/28/2023 | 252601.73 | 0 | 2023-09-02 |  | 1
2022 | National Capital Region | QUEZON CITY | QUEZON CITY (METROPOLITAN MANILA) | P00631038LZ | Construction of Flood Mitigation Structure | 121.0369 | 14.7294 | 9800000 | 9507300.5 | 2022 | C & F CONSTRUCTION & DEVELOPMENT CORPORATION | 3997 | 2022 | 2022-09-27 | 02/24/2022 | 292699.5 | 0 | 2022-08-21 |  | 37
2024 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00820007LZ | Construction of Flood Mitigation Facility | 121.0043 | 14.5797 | 55561317.24 | 55557185.69 | 2024 | G.F. FABIAN CONSTRUCTION | 3998 | 2024 | 2024-06-21 | 02/23/2024 | 4131.55 | 0 | 2024-06-20 |  | 1
2025 | National Capital Region | CITY OF MANILA | CITY OF MANILA (METROPOLITAN MANILA) | P00920131LZ | Construction of Flood Mitigation Facility | 121.0043 | 14.5797 | 138959615 | 137222334.8 | 2025 | ALPHA & OMEGA GEN. CONTRACTOR & DEVELOPMENT CORP. / JCA CONSTRUCTION AND CONSTRUCTION SUPPLY | 3999 | 2025 | 2025-05-06 | 03/03/2025 | 1737280.2 | 0 | 2025-09-27 | 144
2021 | National Capital Region | MUNTINLUPA CITY |  | P00561603LZ | Construction of Flood Mitigation Structure | 121.037 | 14.3678 | 14849352.77 | 14848853.2 | 2022 | R2CG BUILDERS INC. (FORMERLY: RRCG 8639 BUILDERS INC.) | 4000 | 2021 | 2022-07-05 | 01/07/2022 | 499.57 | 0 | 2022-07-04 |  | 1
2022 | National Capital Region | TAGUIG CITY | TAGUIG CITY (METROPOLITAN MANILA) | P00620051LZ | Construction of Slope Protection Structure | 121.0698 | 14.5269 | 96499652.55 | 96500000 | 2022 | DAHL CONSTRUCTION CORP. (FORMERLY: DAHL CONSTRUCTION) | 4001 | 2022 | 2022-10-13 | 02/16/2022 | 0 | 347.45 | 2022-10-12 |  | 1
2024 | Region II | NUEVA VIZCAYA | BAGABAG (NUEVA VIZCAYA) | P00825056LZ | Construction of Flood Mitigation Structure | 121.2574 | 16.5512 | 96500000 | 96500000 | 2024 | V.B. MANUBAY CONSTRUCTION | 4002 | 2024 | 2024-07-22 | 04/02/2024 | 0 | 0 | 2025-02-18 | 211
2021 | Cordillera Administrative Region | KALINGA |  | P00525936LZ | Construction of Flood Mitigation Structure | 121.1613 | 17.3925 | 2940000 | 2862443.94 | 2022 | MATAGOAN KJ BUILDERS AND ENGINEERING SERVICES | 4003 | 2021 | 2022-08-09 | 04/10/2022 | 77556.06 | 0 | 2022-06-27 |  | 43
2023 | Region IV-A | RIZAL | BINANGONAN (RIZAL) | P00742446LZ | Construction of Drainage Structure | 121.2025 | 14.4759 | 4950000 | 4950000 | 2023 | FRANZCOR TRADING & CONSTRUCTION | 4004 | 2023 | 2023-07-20 | 05/10/2023 | 0 | 0 | 2023-08-06 | 17
2023 | Region III | NUEVA ECIJA | GENERAL TINIO (PAPAYA) (NUEVA ECIJA) | P00726532LZ | Construction of Flood Mitigation Structure | 121.0699 | 15.354 | 96499975.07 | 94931876.77 | 2024 | F-DEY CONSTRUCTION AND TRADING / DGSARM BUILDERS INC. (FORMERLY: D.G. SARMENTA CONSTRUCTION) | 4005 | 2023 | 2024-06-16 | 02/23/2023 | 1568098.3 | 0 | 2023-12-12 |  | 187
2022 | National Capital Region | TAGUIG CITY | TAGUIG CITY (METROPOLITAN MANILA) | P00620070LZ | Construction of Slope Protection Structure | 121.07 | 14.5088 | 94569450.51 | 94570000 | 2022 | ALPHA & OMEGA GEN. CONTRACTOR & DEVELOPMENT CORP. / FRANZCOR TRADING & CONSTRUCTION | 4006 | 2022 | 2022-10-13 | 02/16/2022 | 0 | 549.49 | 2022-10-12 |  | 1
2024 | National Capital Region | PASIG CITY | CITY OF PASIG (METROPOLITAN MANILA) | P00825204LZ | Rehabilitation / Major Repair of Drainage Structure | 121.07 | 14.5703 | 8790703.29 | 8601958.42 | 2024 | W. GOMEZ TRADING AND CONSTRUCTION | 4007 | 2024 | 2024-11-03 | 04/08/2024 | 188744.87 | 0 | 2024-11-02 |  | 1
2024 | Region IV-A | BATANGAS | BATANGAS CITY (CAPITAL) (BATANGAS) | P00821322LZ | Construction of Flood Mitigation Structure | 121.0701 | 13.7647 | 86850000 | 86850000 | 2025 | VICMAR CONSTRUCTION, INC. | 4008 | 2024 | 2025-01-25 | 02/07/2024 | 0 | 0 | 2025-01-24 |  | 1
2023 | Region IV-A | BATANGAS | BATANGAS CITY (CAPITAL) (BATANGAS) | P00726202LZ | Construction of Flood Mitigation Structure | 121.0702 | 13.7328 | 39200000 | 39200000 | 2023 | EFREN RAMIREZ CONSTRUCTION AND GENERAL SERVICES CORPORATION | 4009 | 2023 | 2023-10-26 | 02/08/2023 | 0 | 0 | 2023-10-25 |  | 1
2022 | Region IV-A | LAGUNA | CITY OF BIÃ‘AN (LAGUNA) | P00620243LZ | Construction of Flood Mitigation Structure | 121.0703 | 14.2905 | 96500000 | 96353531.2 | 2023 | ST. TIMOTHY CONSTRUCTION CORPORATION / M.T. MALIUANAG CONSTRUCTION SERVICES | 4010 | 2022 | 2023-02-16 | 02/21/2022 | 146468.8 | 0 | 2023-03-13 | 25
2022 | National Capital Region | TAGUIG CITY | TAGUIG CITY (METROPOLITAN MANILA) | P00620069LZ | Construction of Slope Protection Structure | 121.0706 | 14.5099 | 94569211.39 | 89794000.76 | 2022 | HONY TRADING & CONSTRUCTION / B. BERNARDO CONST., INC. | 4011 | 2022 | 2022-09-15 | 02/16/2022 | 4775210.63 | 0 | 2022-10-12 | 27
2023 | National Capital Region | PASIG CITY | CITY OF PASIG (METROPOLITAN MANILA) | P00725955LZ | Construction of Drainage Structure | 121.0831 | 14.6117 | 13719838.92 | 13031103.01 | 2023 | ANDREW LOUIS CONSTRUCTION AND TRADING | 4012 | 2023 | 2023-12-02 | 02/06/2023 | 688735.91 | 0 | 2023-12-01 |  | 1
2023 | Region IV-A | BATANGAS | BATANGAS CITY (CAPITAL) (BATANGAS) | P00742387LZ | Construction of Drainage Structure | 121.0707 | 13.7777 | 9900000 | 9900000 | 2023 | J.A.B. CONSTRUCTION | 4013 | 2023 | 2023-07-06 | 03/21/2023 | 0 | 0 | 2023-07-05 |  | 1
2023 | Region IV-A | BATANGAS | SAN JOSE (BATANGAS) | P00742404LZ | Construction of Drainage Structure | 121.0716 | 13.8837 | 3960000 | 3841200 | 2023 | LUCKY EIGHTY-THREE CONSTRUCTION AND SUPPLY(FOR.VRP | 4014 | 2023 | 2023-12-31 | 09/29/2023 | 118800 | 0 | 2023-11-30 |  | 31
2022 | National Capital Region | CALOOCAN CITY | CALOOCAN CITY (METROPOLITAN MANILA) | P00631031LZ | Construction of Flood Mitigation Structure | 121.0716 | 14.7539 | 19597779.65 | 19205803.61 | 2022 | AYLAN CONSTRUCTION & TRADING | 4015 | 2022 | 2022-10-05 | 02/08/2022 | 391976.04 | 0 | 2022-10-04 |  | 1
2022 | Region III | BULACAN | CITY OF SAN JOSE DEL MONTE (BULACAN) | P00637074LZ | Construction of Flood Mitigation Structure | 121.0719 | 14.7945 | 39199364.55 | 38609812.08 | 2022 | ST. MATTHEW GEN. CONTRACTOR & DEVELOPMENT CORP. | 4016 | 2022 | 2022-10-17 | 05/26/2022 | 589552.47 | 0 | 2022-11-28 | 42
2022 | National Capital Region | TAGUIG CITY | TAGUIG CITY (METROPOLITAN MANILA) | P00620052LZ | Construction of Slope Protection Structure | 121.0721 | 14.5277 | 96499771.95 | 91587933.55 | 2022 | ST. TIMOTHY CONSTRUCTION CORPORATION | 4017 | 2022 | 2022-10-13 | 02/16/2022 | 4911838.4 | 0 | 2022-10-12 |  | 1
2022 | Region III | BULACAN | CITY OF SAN JOSE DEL MONTE (BULACAN) | P00637073LZ | Construction of Drainage Structure | 121.0721 | 14.78 | 29691735 | 29363263.96 | 2023 | FORTUNE RDC ENTERPRISES | 4018 | 2022 | 2023-12-18 | 05/26/2022 | 328471.04 | 0 | 2024-01-08 | 21
2024 | National Capital Region | TAGUIG CITY | PATEROS (METROPOLITAN MANILA) | P00821059LZ | Construction of Slope Protection Structure | 121.0724 | 14.5169 | 72374128.85 | 70926646.27 | 2024 | DAHL CONSTRUCTION CORP. (FORMERLY: DAHL CONSTRUCTION) | 4019 | 2024 | 2024-08-16 | 02/13/2024 | 1447482.58 | 0 | 2024-09-08 | 23
2023 | Region IV-A | BATANGAS | MATAASNAKAHOY (BATANGAS) | P00737495LZ | Rehabilitation / Major Repair of Drainage Structure | 121.1113 | 13.9568 | 4950000 | 4949253 | 2023 | PRIME MOVER'S PHILS. CONSTRUCTION AND SUPPLIES INC. | 4020 | 2023 | 2023-06-02 | 02/03/2023 | 747 | 0 | 2023-06-01 |  | 1
2023 | National Capital Region | MARIKINA CITY | CITY OF MARIKINA (METROPOLITAN MANILA) | P00742230LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.1347 | 14.6582 | 48999621.22 | 46526327.8 | 2024 | 729 CONSTRUCTION, INC. (FORMERLY 722 CONSTRUCTION, INC.) | 4021 | 2023 | 2024-01-18 | 05/24/2023 | 2473293.42 | 0 | 2024-01-17 |  | 1
2024 | National Capital Region | QUEZON CITY | QUEZON CITY (METROPOLITAN MANILA) | P00839530LZ | Construction of Flood Mitigation Structure | 121.0725 | 14.6154 | 19799991.63 | 19206242.7 | 2025 | IM CONSTRUCTION CORPORATION | 4022 | 2024 | 2025-01-22 | 02/08/2024 | 593748.93 | 0 | 2025-01-21 |  | 1
2022 | National Capital Region | PASIG CITY | CITY OF PASIG (METROPOLITAN MANILA) | P00620087LZ | Construction of Revetment | 121.0725 | 14.5598 | 97999911.32 | 93099243.36 | 2023 | E.R. RODRIGUEZ CONSTRUCTION CORPORATION (FORMERLY: E.R. RODRIGUEZ CONSTRUCTION) | 4023 | 2022 | 2023-01-10 | 05/16/2022 | 4900667.96 | 0 | 2023-01-09 |  | 1
2022 | Region IV-A | LAGUNA | CITY OF BIÃ‘AN (LAGUNA) | P00631302LZ | Construction of Flood Mitigation Structure | 121.0726 | 14.2938 | 29400000 | 28769662.5 | 2023 | AARCON BUILDERS | 4024 | 2022 | 2023-07-19 | 03/09/2022 | 630337.5 | 0 | 2023-07-26 | 7
2022 | National Capital Region | PATEROS | TAGUIG CITY (METROPOLITAN MANILA) | P00620016LZ | Construction of Drainage Structure | 121.0726 | 14.5494 | 96499382.34 | 96500000 | 2023 | A.J. LAVA BUILDERS CORP. (FORMERLY: A.J. LAVA BUIL | 4025 | 2022 | 2023-06-21 | 03/21/2022 | 0 | 617.66 | 2023-06-20 |  | 1
2022 | National Capital Region | QUEZON CITY | QUEZON CITY (METROPOLITAN MANILA) | P00637762LZ | Construction of Flood Mitigation Structure | 121.0728 | 14.6156 | 24737643.5 | 24733928.89 | 2023 | SONPRO CONSTRUCTION | 4026 | 2022 | 2023-04-15 | 03/24/2022 | 3714.61 | 0 | 2023-04-14 |  | 1
2022 | Region IV-A | LAGUNA | CITY OF BIÃ‘AN (LAGUNA) | P00620244LZ | Construction of Flood Mitigation Structure | 121.073 | 14.2928 | 96500000 | 96405046.39 | 2023 | ALPHA & OMEGA GEN. CONTRACTOR & DEVELOPMENT CORP. | 4027 | 2022 | 2023-02-16 | 02/21/2022 | 94953.61 | 0 | 2023-03-13 | 25
2023 | Region IV-A | BATANGAS | BATANGAS CITY (CAPITAL) (BATANGAS) | P00726201LZ | Construction of Flood Mitigation Structure | 121.073 | 13.7409 | 39200000 | 39200000 | 2024 | EFREN RAMIREZ CONSTRUCTION AND GENERAL SERVICES CORPORATION | 4028 | 2023 | 2024-06-22 | 02/08/2023 | 0 | 0 | 2024-06-21 |  | 1
2022 | Region IV-A | BATANGAS | BATANGAS CITY (CAPITAL) (BATANGAS) | P00631287LZ | Construction of Flood Mitigation Structure | 121.0731 | 13.7421 | 29400000 | 29400000 | 2022 | RUSMEN BUILDERS & DEVELOPMENT CORPORATION (FORMERL | 4029 | 2022 | 2022-11-28 | 03/30/2022 | 0 | 0 | 2022-11-27 |  | 1
2024 | Region IV-A | BATANGAS | BATANGAS CITY (CAPITAL) (BATANGAS) | P00821323LZ | Construction of Flood Mitigation Structure | 121.0731 | 13.7645 | 86850000 | 86850000 | 2024 | VICMAR CONSTRUCTION, INC. | 4030 | 2024 | 2024-11-14 | 02/07/2024 | 0 | 0 | 2024-11-13 |  | 1
2023 | Region IV-A | BATANGAS | BATANGAS CITY (CAPITAL) (BATANGAS) | P00727369LZ | Construction of Flood Mitigation Structure | 121.0731 | 13.7645 | 34300000 | 34300000 | 2023 | VICMAR CONSTRUCTION, INC. | 4031 | 2023 | 2023-12-05 | 04/05/2023 | 0 | 0 | 2023-12-20 | 15
2022 | National Capital Region | TAGUIG CITY | TAGUIG CITY (METROPOLITAN MANILA) | P00620055LZ | Construction of Slope Protection Structure | 121.0731 | 14.5268 | 96499739.19 | 94190038.78 | 2022 | ST. TIMOTHY CONSTRUCTION CORPORATION | 4032 | 2022 | 2022-11-18 | 03/24/2022 | 2309700.41 | 0 | 2022-11-17 |  | 1
2022 | National Capital Region | PATEROS | TAGUIG CITY (METROPOLITAN MANILA) | P00620359LZ | Construction of Drainage Structure | 121.0732 | 14.5438 | 19599841.24 | 18619388.58 | 2022 | JAYMAR BUILDERS | 4033 | 2022 | 2022-08-06 | 02/08/2022 | 980452.66 | 0 | 2022-08-05 |  | 1
2022 | National Capital Region | TAGUIG CITY | TAGUIG CITY (METROPOLITAN MANILA) | P00620056LZ | Construction of Slope Protection Structure | 121.0734 | 14.5255 | 96499551.09 | 96500000 | 2022 | ALPHA & OMEGA GEN. CONTRACTOR & DEVELOPMENT CORP. | 4034 | 2022 | 2022-11-18 | 03/24/2022 | 0 | 448.91 | 2022-11-17 |  | 1
2023 | Region IV-A | BATANGAS | BATANGAS CITY (CAPITAL) (BATANGAS) | P00726204LZ | Construction of Flood Mitigation Structure | 121.0734 | 13.7378 | 39200000 | 39200000 | 2023 | VICMAR CONSTRUCTION, INC. | 4035 | 2023 | 2023-08-27 | 02/08/2023 | 0 | 0 | 2023-08-26 |  | 1
2023 | National Capital Region | QUEZON CITY | QUEZON CITY (METROPOLITAN MANILA) | P00726024LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.0734 | 14.6126 | 5879910.17 | 5644713.81 | 2023 | 4 DOUBLERS TRADING & CONTRACTOR INC. (FORMERLY: 4 DOUBLERS TRADING AND CONTRACTOR) | 4036 | 2023 | 2023-06-07 | 03/13/2023 | 235196.36 | 0 | 2023-06-06 |  | 1
2024 | Region III | BULACAN | CITY OF SAN JOSE DEL MONTE (BULACAN) | P00820211LZ | Construction of Flood Mitigation Structure | 121.0735 | 14.7726 | 96499701.93 | 96498767.65 | 2024 | ROYAL CROWN MONARCH CONSTRUCTION & SUPPLIES CORP. | 4037 | 2024 | 2024-10-04 | 02/22/2024 | 934.28 | 0 | 2024-12-12 | 69
2022 | National Capital Region | TAGUIG CITY | TAGUIG CITY (METROPOLITAN MANILA) | P00620048LZ | Construction of Flood Mitigation Structure | 121.0735 | 14.5266 | 96499446.79 | 91577975.1 | 2022 | AARCON BUILDERS | 4038 | 2022 | 2022-12-12 | 02/16/2022 | 4921471.69 | 0 | 2022-12-11 |  | 1
2023 | National Capital Region | CALOOCAN CITY | CALOOCAN CITY (METROPOLITAN MANILA) | P00725557LZ | Construction of Flood Mitigation Structure | 121.0735 | 14.7723 | 91666256.9 | 89280149.46 | 2023 | DIADEMA CONSTRUCTION AND ENTERPRISES INC. (FORMERLY: DIADEMA ENTERPRISES) | 4039 | 2023 | 2023-12-25 | 02/21/2023 | 2386107.44 | 0 | 2023-12-16 |  | 9
2022 | National Capital Region | TAGUIG CITY | TAGUIG CITY (METROPOLITAN MANILA) | P00620049LZ | Construction of Flood Mitigation Structure | 121.0737 | 14.5252 | 96499601.39 | 91597421.64 | 2022 | ALPHA & OMEGA GEN. CONTRACTOR & DEVELOPMENT CORP. | 4040 | 2022 | 2022-12-12 | 02/16/2022 | 4902179.75 | 0 | 2022-12-11 |  | 1
2024 | National Capital Region | QUEZON CITY | QUEZON CITY (METROPOLITAN MANILA) | P00820644LZ | Rehabilitation / Major Repair of Drainage Structure | 121.0738 | 14.5966 | 19599381.58 | 19598981.58 | 2024 | MANCOL CONSTRUCTION CORPORATION | 4041 | 2024 | 2024-08-06 | 02/08/2024 | 400 | 0 | 2024-08-05 |  | 1
2023 | National Capital Region | QUEZON CITY | QUEZON CITY (METROPOLITAN MANILA) | P00736169LZ | Construction of Flood Mitigation Structure | 121.0738 | 14.7106 | 48999515.75 | 48019525.44 | 2023 | LE BRON CONSTRUCTION | 4042 | 2023 | 2023-12-20 | 03/07/2023 | 979990.31 | 0 | 2023-12-30 | 10
2023 | National Capital Region | PASIG CITY | CITY OF PASIG (METROPOLITAN MANILA) | P00725969LZ | Rehabilitation / Major Repair of Drainage Structure | 121.0739 | 14.5644 | 11759884.45 | 11154489.46 | 2023 | E.S. JOSEFA CONSTRUCTION | 4043 | 2023 | 2023-06-20 | 02/06/2023 | 605394.99 | 0 | 2023-06-19 |  | 1
2023 | Region IV-A | BATANGAS | BATANGAS CITY (CAPITAL) (BATANGAS) | P00726203LZ | Construction of Flood Mitigation Structure | 121.0739 | 13.7369 | 39200000 | 39200000 | 2023 | VICMAR CONSTRUCTION, INC. | 4044 | 2023 | 2023-08-27 | 02/08/2023 | 0 | 0 | 2023-08-26 |  | 1
2021 | National Capital Region | QUEZON CITY |  | P00525840LZ | Construction of Flood Mitigation Structure | 121.074 | 14.6709 | 48999704.88 | 48985157.08 | 2022 | PERRC INC. (FORMERLY: P.E.R.R.C. CONSTRUCTION & DEVELOPMENT CORPORATION) | 4045 | 2021 | 2022-10-15 | 11/10/2021 | 14547.8 | 0 | 2022-10-14 |  | 1
2023 | National Capital Region | PASIG CITY | CITY OF PASIG (METROPOLITAN MANILA) | P00726631LZ | Construction of Slope Protection Structure | 121.0741 | 14.5668 | 48999977 | 46475997.28 | 2025 | M3 KONSTRACT CORPORATION (FORMERLY:MARGARITA CONSTRUCTION) | 4046 | 2023 | 2025-02-18 | 02/06/2023 | 2523979.72 | 0 | 2025-02-17 |  | 1
2024 | National Capital Region | QUEZON CITY | QUEZON CITY (METROPOLITAN MANILA) | P00820649LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.0742 | 14.6018 | 48999386.53 | 48998985.53 | 2024 | E.L. TORRES CONSTRUCTION AND TRADING INC. (FORMERLY : E. L. TORRES CONSTRUCTION & TRADING | 4047 | 2024 | 2024-12-23 | 02/08/2024 | 401 | 0 | 2024-12-22 |  | 1
2023 | National Capital Region | QUEZON CITY | QUEZON CITY (METROPOLITAN MANILA) | P00727031LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.0742 | 14.6013 | 9799377.16 | 9755779.9 | 2024 | E.L. TORRES CONSTRUCTION AND TRADING INC. (FORMERLY : E. L. TORRES CONSTRUCTION & TRADING | 4048 | 2023 | 2024-01-05 | 03/29/2023 | 43597.26 | 0 | 2024-01-06 | 1
2023 | National Capital Region | PASIG CITY | CITY OF PASIG (METROPOLITAN MANILA) | P00726322LZ | Construction of Slope Protection Structure | 121.0743 | 14.5675 | 97999637.65 | 92869777.58 | 2024 | M3 KONSTRACT CORPORATION (FORMERLY:MARGARITA CONSTRUCTION) | 4049 | 2023 | 2024-06-03 | 03/15/2023 | 5129860.07 | 0 | 2024-07-02 | 29
2024 | National Capital Region | PATEROS | PATEROS (METROPOLITAN MANILA) | P00821052LZ | Construction of Slope Protection Structure | 121.0743 | 14.5433 | 72374844.34 | 70920109.96 | 2024 | HONY TRADING & CONSTRUCTION | 4050 | 2024 | 2024-06-17 | 02/13/2024 | 1454734.38 | 0 | 2024-09-08 | 83
2022 | Region IV-A | BATANGAS | BATANGAS CITY (CAPITAL) (BATANGAS) | P00637787LZ | Construction of Flood Mitigation Structure | 121.0746 | 13.7362 | 39600000 | 39600000 | 2023 | VICMAR CONSTRUCTION, INC. | 4051 | 2022 | 2023-07-04 | 03/30/2022 | 0 | 0 | 2023-07-03 |  | 1
2023 | Region IV-A | BATANGAS | SAN JOSE (BATANGAS) | P00742411LZ | Construction of Drainage Structure | 121.0747 | 13.8437 | 4950000 | 4801500 | 2023 | LUCKY EIGHTY-THREE CONSTRUCTION AND SUPPLY(FOR.VRP | 4052 | 2023 | 2023-10-20 | 05/19/2023 | 148500 | 0 | 2023-08-20 |  | 61
2023 | National Capital Region | QUEZON CITY | QUEZON CITY (METROPOLITAN MANILA) | P00727032LZ | Rehabilitation / Major Repair of Drainage Structure | 121.075 | 14.6175 | 11759509.17 | 11755099.54 | 2024 | 4 DOUBLERS TRADING & CONTRACTOR INC. (FORMERLY: 4 DOUBLERS TRADING AND CONTRACTOR) | 4053 | 2023 | 2024-06-24 | 05/31/2023 | 4409.63 | 0 | 2023-11-01 |  | 236
2024 | National Capital Region | PATEROS | PATEROS (METROPOLITAN MANILA) | P00821055LZ | Construction of Slope Protection Structure | 121.0751 | 14.5435 | 72374544.08 | 70920498.2 | 2024 | ELITE GENERAL CONTRACTOR AND DEVELOPMENT CORP. | 4054 | 2024 | 2024-08-26 | 02/13/2024 | 1454045.88 | 0 | 2024-09-08 | 13
2020 | Region IV-A | LAGUNA |  | P00421352LZ | Construction of Flood Mitigation Facility | 121.0751 | 14.3056 | 106878575 | 103385143.3 | 2022 | R.A. PAHATI CONST. & SUPPLY, INC. | 4055 | 2020 | 2022-12-19 | 11/26/2020 | 3493431.7 | 0 | 2022-12-30 | 11
2021 | Region IV-A | LAGUNA |  | P00421352LZ | Construction of Flood Mitigation Facility | 121.0751 | 14.3056 | 106878575 | 103385143.3 | 2022 | R.A. PAHATI CONST. & SUPPLY, INC. | 4056 | 2021 | 2022-12-19 | 11/26/2020 | 3493431.7 | 0 | 2022-12-30 | 11
2022 | Region IV-A | BATANGAS | BATANGAS CITY (CAPITAL) (BATANGAS) | P00637789LZ | Construction of Slope Protection Structure | 121.0752 | 13.7435 | 4950000 | 4950000 | 2022 | JASMIG CONSTRUCTION CORPORATION (FORMERLY: JASMIG CONSTRUCTION SUPPLY) | 4057 | 2022 | 2022-09-17 | 03/30/2022 | 0 | 0 | 2022-09-16 |  | 1
2024 | National Capital Region | PATEROS | PATEROS (METROPOLITAN MANILA) | P00821057LZ | Construction of Slope Protection Structure | 121.0753 | 14.5439 | 72374921.71 | 70927423.27 | 2024 | ELITE GENERAL CONTRACTOR AND DEVELOPMENT CORP. | 4058 | 2024 | 2024-08-26 | 02/13/2024 | 1447498.44 | 0 | 2024-09-08 | 13
2024 | National Capital Region | PATEROS | PATEROS (METROPOLITAN MANILA) | P00821056LZ | Construction of Slope Protection Structure | 121.0758 | 14.545 | 72374705.15 | 70927211.05 | 2024 | EBUILDERS CONSTRUCTION & DEVELOPMENT CORP. | 4059 | 2024 | 2024-06-25 | 02/13/2024 | 1447494.1 | 0 | 2024-09-08 | 75
2024 | Region III | BULACAN | CITY OF SAN JOSE DEL MONTE (BULACAN) | P00844751LZ | Construction of Flood Mitigation Structure | 121.076 | 14.7969 | 29399636.87 | 29394604.89 | 2024 | TRIPLE 8 CONSTRUCTION & SUPPLY, INC. (FORMERLY TRIPLE 8 CONST. & SUPPLY) | 4060 | 2024 | 2024-09-06 | 04/30/2024 | 5031.98 | 0 | 2024-10-26 | 50
2023 | National Capital Region | QUEZON CITY | QUEZON CITY (METROPOLITAN MANILA) | P00727033LZ | Rehabilitation / Major Repair of Drainage Structure | 121.0763 | 14.6669 | 6859417.44 | 6858041.84 | 2023 | 4 DOUBLERS TRADING & CONTRACTOR INC. (FORMERLY: 4 DOUBLERS TRADING AND CONTRACTOR) | 4061 | 2023 | 2023-12-06 | 04/28/2023 | 1375.6 | 0 | 2023-10-29 |  | 38
2023 | National Capital Region | QUEZON CITY | QUEZON CITY (METROPOLITAN MANILA) | P00726029LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.0764 | 14.6147 | 19599989.18 | 19415450.52 | 2024 | MANCOL CONSTRUCTION CORPORATION | 4062 | 2023 | 2024-01-12 | 02/17/2023 | 184538.66 | 0 | 2024-01-11 |  | 1
2023 | Region IV-A | BATANGAS | SAN JOSE (BATANGAS) | P00742406LZ | Construction of Drainage Structure | 121.0765 | 13.8894 | 3960000 | 3841200 | 2023 | LUCKY EIGHTY-THREE CONSTRUCTION AND SUPPLY(FOR.VRP | 4063 | 2023 | 2023-10-02 | 04/02/2023 | 118800 | 0 | 2023-06-03 |  | 121
2024 | National Capital Region | PATEROS | PATEROS (METROPOLITAN MANILA) | P00821053LZ | Construction of Slope Protection Structure | 121.0766 | 14.5454 | 72374953 | 70927030.3 | 2024 | AMETHYST HORIZON BUILDERS AND GEN. CONTRACTOR AND DEVELOPMENT CORP. | 4064 | 2024 | 2024-06-25 | 02/13/2024 | 1447922.7 | 0 | 2024-09-08 | 75
2023 | National Capital Region | QUEZON CITY | QUEZON CITY (METROPOLITAN MANILA) | P00726016LZ | Construction of Flood Mitigation Structure | 121.0766 | 14.6852 | 48999690.5 | 48509693.6 | 2023 | LEGACY CONSTRUCTION CORPORATION (FORMERLY: LEGACY CONSTRUCTION) | 4065 | 2023 | 2023-12-29 | 03/07/2023 | 489996.9 | 0 | 2023-12-30 | 1
2021 | Region IV-A | LAGUNA |  | P00561779LZ | Construction of Drainage Structure | 121.0767 | 14.3337 | 39600000 | 38012519.5 | 2022 | ST. TIMOTHY CONSTRUCTION CORPORATION | 4066 | 2021 | 2022-07-13 | 02/10/2021 | 1587480.5 | 0 | 2022-07-12 |  | 1
2022 | National Capital Region | TAGUIG CITY | TAGUIG CITY (METROPOLITAN MANILA) | P00620053LZ | Construction of Slope Protection Structure | 121.0771 | 14.5236 | 96499865.17 | 96500000 | 2023 | ST. TIMOTHY CONSTRUCTION CORPORATION | 4067 | 2022 | 2023-01-11 | 03/24/2022 | 0 | 134.83 | 2023-03-05 | 53
2023 | Region II | NUEVA VIZCAYA | BAMBANG (NUEVA VIZCAYA) | P00726143LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.0771 | 16.383 | 49000000 | 46531853.34 | 2023 | J.E.L. CONSTRUCTION & SUPPLY | 4068 | 2023 | 2023-10-21 | 02/15/2023 | 2468146.66 | 0 | 2023-10-20 |  | 1
2023 | Region II | NUEVA VIZCAYA | BAMBANG (NUEVA VIZCAYA) | P00726709LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.0771 | 16.3297 | 39200000 | 39200000 | 2023 | CITRUS COUNTRY CONSTRUCTION | 4069 | 2023 | 2023-09-17 | 02/14/2023 | 0 | 0 | 2023-11-01 | 45
2023 | Region IV-A | BATANGAS | SAN JOSE (BATANGAS) | P00742418LZ | Construction of Slope Protection Structure | 121.0771 | 13.8848 | 2970000 | 2880900 | 2023 | LUCKY EIGHTY-THREE CONSTRUCTION AND SUPPLY(FOR.VRP | 4070 | 2023 | 2023-06-03 | 04/03/2023 | 89100 | 0 | 2023-06-02 |  | 1
2022 | National Capital Region | QUEZON CITY | QUEZON CITY (METROPOLITAN MANILA) | P00620442LZ | Construction of Flood Mitigation Structure | 121.0773 | 14.6974 | 44100000 | 42772590 | 2022 | ST. MATTHEW GEN. CONTRACTOR & DEVELOPMENT CORP. | 4071 | 2022 | 2022-10-21 | 02/07/2022 | 1327410 | 0 | 2022-12-02 | 42
2022 | National Capital Region | TAGUIG CITY | TAGUIG CITY (METROPOLITAN MANILA) | P00620357LZ | Construction of Slope Protection Structure | 121.0775 | 14.5447 | 48999830.59 | 48999982.49 | 2022 | DAHL CONSTRUCTION CORP. (FORMERLY: DAHL CONSTRUCTION) | 4072 | 2022 | 2022-09-22 | 02/08/2022 | 0 | 151.9 | 2022-10-04 | 12
2024 | National Capital Region | QUEZON CITY | QUEZON CITY (METROPOLITAN MANILA) | P00820648LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.0781 | 14.6153 | 9799106.59 | 9790929.75 | 2024 | IM CONSTRUCTION CORPORATION | 4073 | 2024 | 2024-04-22 | 02/08/2024 | 8176.84 | 0 | 2024-06-05 | 44
2021 | Cordillera Administrative Region | APAYAO |  | P00526368LZ | Construction of Flood Mitigation Structure | 121.0783 | 18.5118 | 49000000 | 47521251.3 | 2022 | ASC CONSTRUCTION & CONCRETE PRODUCTS | 4074 | 2021 | 2022-11-24 | 12/01/2021 | 1478748.7 | 0 | 2022-08-16 |  | 100
2023 | Cordillera Administrative Region | APAYAO | CALANASAN (BAYAG) (APAYAO) | P00735961LZ | Construction of Flood Mitigation Structure | 121.0783 | 18.1324 | 96500000 | 96500000 | 2024 | TAGEL CORPORATION / E.C.V. CONSTRUCTION | 4075 | 2023 | 2024-03-11 | 04/05/2023 | 0 | 0 | 2024-03-29 | 18
2023 | Region IV-A | BATANGAS | SAN JOSE (BATANGAS) | P00742409LZ | Construction of Drainage Structure | 121.0785 | 13.8639 | 10890000 | 10563300 | 2023 | LUCKY EIGHTY-THREE CONSTRUCTION AND SUPPLY(FOR.VRP | 4076 | 2023 | 2023-07-27 | 03/30/2023 | 326700 | 0 | 2023-07-26 |  | 1
2024 | National Capital Region | TAGUIG CITY | TAGUIG CITY (METROPOLITAN MANILA) | P00824795LZ | Construction of Slope Protection Structure | 121.0788 | 14.5273 | 96499747.94 | 94568457.67 | 2024 | ZYRE TRADING AND CONSTRUCTION / RVDP CONSTRUCTION | 4077 | 2024 | 2024-10-03 | 04/01/2024 | 1931290.27 | 0 | 2024-11-25 | 53
2022 | National Capital Region | TAGUIG CITY | TAGUIG CITY (METROPOLITAN MANILA) | P00620054LZ | Construction of Slope Protection Structure | 121.079 | 14.5234 | 96499601.39 | 91626371.52 | 2022 | ALPHA & OMEGA GEN. CONTRACTOR & DEVELOPMENT CORP. | 4078 | 2022 | 2022-10-10 | 03/24/2022 | 4873229.87 | 0 | 2022-11-17 | 38
2023 | National Capital Region | QUEZON CITY | QUEZON CITY (METROPOLITAN MANILA) | P00726021LZ | Construction of Flood Mitigation Structure | 121.0793 | 14.6946 | 48999637.4 | 49000000 | 2023 | LEGACY CONSTRUCTION CORPORATION (FORMERLY: LEGACY CONSTRUCTION) | 4079 | 2023 | 2023-12-29 | 03/07/2023 | 0 | 362.6 | 2023-12-30 | 1
2023 | National Capital Region | QUEZON CITY | QUEZON CITY (METROPOLITAN MANILA) | P00726028LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.0795 | 14.6126 | 29399717.27 | 29381895.44 | 2023 | MRB11 CONSTRUCTION CORPORATION (FORMERLY:MRB CONS | 4080 | 2023 | 2023-09-14 | 02/17/2023 | 17821.83 | 0 | 2023-09-13 |  | 1
2022 | Region IV-A | LAGUNA | CITY OF BIÃ‘AN (LAGUNA) | P00640556LZ | Construction of Revetment | 121.08 | 14.3292 | 49500000 | 49472556.72 | 2023 | ALPHA & OMEGA GEN. CONTRACTOR & DEVELOPMENT CORP. | 4081 | 2022 | 2023-08-04 | 07/05/2022 | 27443.28 | 0 | 2023-08-03 |  | 1
2023 | National Capital Region | TAGUIG CITY | TAGUIG CITY (METROPOLITAN MANILA) | P00726820LZ | Construction of Slope Protection Structure | 121.08 | 14.5201 | 96499637.67 | 91578156.14 | 2023 | DAHL CONSTRUCTION CORP. (FORMERLY: DAHL CONSTRUCTION) | 4082 | 2023 | 2023-09-15 | 04/19/2023 | 4921481.53 | 0 | 2023-12-13 | 89
2021 | Cordillera Administrative Region | APAYAO |  | P00561270LZ | Construction of Flood Mitigation Structure | 121.0802 | 18.5357 | 9900000 | 9900000 | 2022 | ASC CONSTRUCTION & CONCRETE PRODUCTS | 4083 | 2021 | 2022-12-15 | 12/01/2021 | 0 | 0 | 2022-07-12 |  | 156
2023 | National Capital Region | CALOOCAN CITY | CALOOCAN CITY (METROPOLITAN MANILA) | P00740300LZ | Construction of Flood Mitigation Structure | 121.0804 | 14.7731 | 96473103.47 | 94021597.95 | 2023 | AMETHYST HORIZON BUILDERS AND GEN. CONTRACTOR AND DEVELOPMENT CORP. | 4084 | 2023 | 2023-12-12 | 04/24/2023 | 2451505.52 | 0 | 2024-02-16 | 66
2024 | Region III | BULACAN | CITY OF SAN JOSE DEL MONTE (BULACAN) | P00820235LZ | Construction of Flood Mitigation Structure | 121.0804 | 14.8375 | 68877359.15 | 68844853.57 | 2024 | FLORDES CONSTRUCTION & TRADING CORP. (FORMERLY FLO | 4085 | 2024 | 2024-12-19 | 02/14/2024 | 32505.58 | 0 | 2024-12-18 |  | 1
2024 | National Capital Region | PASIG CITY | CITY OF PASIG (METROPOLITAN MANILA) | P00824595LZ | Rehabilitation / Major Repair of Drainage Structure | 121.0804 | 14.5641 | 9799886.09 | 9633293.79 | 2024 | DAHL CONSTRUCTION CORP. (FORMERLY: DAHL CONSTRUCTION) | 4086 | 2024 | 2024-07-10 | 04/08/2024 | 166592.3 | 0 | 2024-07-20 | 10
2022 | Region IV-A | LAGUNA | CITY OF BIÃ‘AN (LAGUNA) | P00632898LZ | Construction of Flood Mitigation Structure | 121.0806 | 14.3291 | 49500000 | 49494593.92 | 2022 | MAR-VEL CONSTRUCTION & SUPPLY | 4087 | 2022 | 2022-08-16 | 02/14/2022 | 5406.08 | 0 | 2022-10-01 | 46
2024 | National Capital Region | PASIG CITY | CITY OF PASIG (METROPOLITAN MANILA) | P00823657LZ | Rehabilitation / Major Repair of Drainage Structure | 121.0806 | 14.5824 | 19599815.46 | 19284028.41 | 2024 | GH BELANDRES CONSTRUCTORS INC | 4088 | 2024 | 2024-09-19 | 04/08/2024 | 315787.05 | 0 | 2024-09-18 |  | 1
2023 | National Capital Region | PASIG CITY | CITY OF PASIG (METROPOLITAN MANILA) | P00725941LZ | Rehabilitation / Major Repair of Drainage Structure | 121.0808 | 14.5469 | 7838779.56 | 7442044.02 | 2023 | B. VALENCERINA TRADING & CONSTRUCTION | 4089 | 2023 | 2023-07-20 | 02/06/2023 | 396735.54 | 0 | 2023-07-19 |  | 1
2021 | National Capital Region | CALOOCAN CITY |  | P00525793LZ | Construction of Flood Mitigation Structure | 121.081 | 14.7711 | 19599514.87 | 19148711.92 | 2022 | PERSAN CONSTRUCTION, INC. (FORMERLY: PERSAN CONST. | 4090 | 2021 | 2022-08-16 | 03/24/2022 | 450802.95 | 0 | 2022-11-17 | 93
2024 | National Capital Region | TAGUIG CITY | TAGUIG CITY (METROPOLITAN MANILA) | P00821070LZ | Construction of Slope Protection Structure | 121.081 | 14.5197 | 144749516.3 | 141811101.2 | 2024 | J. SIMEON CONSTRUCTION | 4091 | 2024 | 2024-09-11 | 05/29/2024 | 2938415.1 | 0 | 2025-02-21 | 163
2024 | National Capital Region | TAGUIG CITY | TAGUIG CITY (METROPOLITAN MANILA) | P00821071LZ | Construction of Slope Protection Structure | 121.081 | 14.5197 | 144749474.8 | 141782110.5 | 2024 | J. SIMEON CONSTRUCTION | 4092 | 2024 | 2024-11-15 | 06/04/2024 | 2967364.3 | 0 | 2025-02-27 | 104
2024 | National Capital Region | TAGUIG CITY | TAGUIG CITY (METROPOLITAN MANILA) | P00821072LZ | Construction of Slope Protection Structure | 121.081 | 14.5197 | 144749625 | 141854632.5 | 2024 | J. SIMEON CONSTRUCTION | 4093 | 2024 | 2024-09-11 | 05/29/2024 | 2894992.5 | 0 | 2025-02-21 | 163
2022 | Region IV-A | LAGUNA | CITY OF BIÃ‘AN (LAGUNA) | P00637082LZ | Construction of Flood Mitigation Structure | 121.0811 | 14.3301 | 49000000 | 48994072.94 | 2023 | ALPHA & OMEGA GEN. CONTRACTOR & DEVELOPMENT CORP. | 4094 | 2022 | 2023-08-19 | 07/05/2022 | 5927.06 | 0 | 2023-08-18 |  | 1
2022 | Region II | NUEVA VIZCAYA | BAMBANG (NUEVA VIZCAYA) | P00621072LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.0813 | 16.3956 | 24500000 | 24500000 | 2022 | J.E.L. CONSTRUCTION & SUPPLY | 4095 | 2022 | 2022-11-20 | 02/10/2022 | 0 | 0 | 2022-11-19 |  | 1
2023 | National Capital Region | TAGUIG CITY | TAGUIG CITY (METROPOLITAN MANILA) | P00726821LZ | Construction of Slope Protection Structure | 121.0814 | 14.519 | 96499389.87 | 91674420.38 | 2023 | DAHL CONSTRUCTION CORP. (FORMERLY: DAHL CONSTRUCTION) | 4096 | 2023 | 2023-08-01 | 04/19/2023 | 4824969.49 | 0 | 2023-12-13 | 134
2024 | National Capital Region | QUEZON CITY | QUEZON CITY (METROPOLITAN MANILA) | P00848596LZ | Construction of Revetment | 121.0815 | 14.695 | 54449842.5 | 53796440.8 | 2024 | MRB11 CONSTRUCTION CORPORATION (FORMERLY:MRB CONS | 4097 | 2024 | 2024-12-02 | 03/18/2024 | 653401.7 | 0 | 2025-01-10 | 39
2023 | National Capital Region | TAGUIG CITY | TAGUIG CITY (METROPOLITAN MANILA) | P00726822LZ | Construction of Slope Protection Structure | 121.0819 | 14.5181 | 96499552.85 | 91616675.48 | 2023 | A.J. LAVA BUILDERS CORP. (FORMERLY: A.J. LAVA BUIL | 4098 | 2023 | 2023-08-01 | 04/19/2023 | 4882877.37 | 0 | 2023-12-13 | 134
2022 | Region IV-A | LAGUNA | CITY OF BIÃ‘AN (LAGUNA) | P00631303LZ | Construction of Flood Mitigation Structure | 121.082 | 14.3227 | 29400000 | 28819391 | 2022 | AARCON BUILDERS | 4099 | 2022 | 2022-09-02 | 02/14/2022 | 580609 | 0 | 2022-09-01 |  | 1
2023 | National Capital Region | CALOOCAN CITY | CALOOCAN CITY (METROPOLITAN MANILA) | P00740301LZ | Construction of Flood Mitigation Structure | 121.0821 | 14.7746 | 96478557.39 | 93966981.03 | 2023 | ELITE GENERAL CONTRACTOR AND DEVELOPMENT CORP. | 4100 | 2023 | 2023-12-26 | 04/24/2023 | 2511576.36 | 0 | 2024-02-16 | 52
2022 | National Capital Region | QUEZON CITY | QUEZON CITY (METROPOLITAN MANILA) | P00632722LZ | Construction of Drainage Structure | 121.0823 | 14.6524 | 4949691.14 | 4742519 | 2022 | ANN-GIE BUILDERS | 4101 | 2022 | 2022-09-19 | 02/09/2022 | 207172.14 | 0 | 2022-07-27 |  | 54
2023 | Region IV-B | ORIENTAL MINDORO | NAUJAN (ORIENTAL MINDORO) | P00740429LZ | Construction of Dike | 121.0825 | 13.2707 | 241249991.7 | 241246568.6 | 2023 | SILVERWOLVES CONSTRUCTION CORPORATION | 4102 | 2023 | 2023-10-15 | 04/13/2023 | 3423.1 | 0 | 2024-04-05 | 173
2023 | Region IV-A | BATANGAS | MATAASNAKAHOY (BATANGAS) | P00737496LZ | Construction of Revetment | 121.0827 | 13.972 | 4950000 | 4938291.5 | 2023 | R.B. ABITAL CONSTRUCTION CORP. | 4103 | 2023 | 2023-07-10 | 02/03/2023 | 11708.5 | 0 | 2023-07-16 | 6
2023 | Region IV-A | BATANGAS | MATAASNAKAHOY (BATANGAS) | P00742393LZ | Construction of Revetment | 121.0828 | 13.9708 | 9900000 | 9896963.8 | 2023 | THREE W BUILDERS, INC. | 4104 | 2023 | 2023-10-16 | 03/21/2023 | 3036.2 | 0 | 2023-10-15 |  | 1
2022 | Cordillera Administrative Region | APAYAO | CALANASAN (BAYAG) (APAYAO) | P00620989LZ | Construction of Flood Mitigation Structure | 121.083 | 18.5279 | 49000000 | 49000000 | 2022 | ASC CONSTRUCTION & CONCRETE PRODUCTS | 4105 | 2022 | 2022-12-12 | 02/09/2022 | 0 | 0 | 2023-01-03 | 22
2023 | National Capital Region | PASIG CITY | CITY OF PASIG (METROPOLITAN MANILA) | P00725973LZ | Rehabilitation / Major Repair of Drainage Structure | 121.0831 | 14.6167 | 48999794.64 | 46535105 | 2023 | DAHL CONSTRUCTION CORP. (FORMERLY: DAHL CONSTRUCTION) | 4106 | 2023 | 2023-10-03 | 02/06/2023 | 2464689.64 | 0 | 2023-10-02 |  | 1
2021 | Cordillera Administrative Region | MOUNTAIN PROVINCE |  | P00525919LZ | Construction of Flood Mitigation Structure | 121.3403 | 17.1461 | 19600000 | 19600000 | 2022 | J.M. DAPING CONSTRUCTION SERVICES | 4107 | 2021 | 2022-08-19 | 04/06/2022 | 0 | 0 | 2022-10-06 | 48
2024 | National Capital Region | PASIG CITY | CITY OF PASIG (METROPOLITAN MANILA) | P00821439LZ | Rehabilitation / Major Repair of Slope Protection Structure | 121.0969 | 14.5693 | 48999654.52 | 47524950 | 2024 | DAHL CONSTRUCTION CORP. (FORMERLY: DAHL CONSTRUCTION) | 4108 | 2024 | 2024-08-05 | 02/12/2024 | 1474704.52 | 0 | 2024-08-08 | 3
2023 | Region IV-A | BATANGAS | SAN JOSE (BATANGAS) | P00742408LZ | Construction of Drainage Structure | 121.0602 | 13.8715 | 5940000 | 5761800 | 2023 | LUCKY EIGHTY-THREE CONSTRUCTION AND SUPPLY(FOR.VRP | 4109 | 2023 | 2023-08-24 | 04/27/2023 | 178200 | 0 | 2023-08-23 |  | 1
2022 | National Capital Region | QUEZON CITY | QUEZON CITY (METROPOLITAN MANILA) | P00620444LZ | Construction of Flood Mitigation Structure | 121.0974 | 14.7081 | 44052890.46 | 42731523.6 | 2022 | LARSEN-DUTCHER CONSTRACTOR CORPORATION (FORMERLY:LARSEN-DUTCHER CONSTRACTOR) | 4110 | 2022 | 2022-12-05 | 02/07/2022 | 1321366.86 | 0 | 2022-12-02 |  | 3
2023 | National Capital Region | MAKATI CITY | CITY OF MAKATI (METROPOLITAN MANILA) | P00725531LZ | Construction of Flood Mitigation Facility | 121.0609 | 14.5326 | 62725000 | 61469424.33 | 2024 | KING EIGHT BUILDERS AND SUPPLY | 4111 | 2023 | 2024-03-26 | 07/31/2023 | 1255575.67 | 0 | 2024-03-25 |  | 1
2021 | Region IV-A | RIZAL |  | P00561554LZ | Construction of Flood Mitigation Structure | 121.2574 | 14.538 | 9900000 | 9553249.64 | 2022 | S.B. SORIANO CONSTRUCTION | 4112 | 2021 | 2022-07-01 | 12/23/2021 | 346750.36 | 0 | 2022-06-30 |  | 1
2023 | Cordillera Administrative Region | KALINGA | BALBALAN (KALINGA) | P00742292LZ | Construction of Drainage Structure | 121.1614 | 17.3978 | 4950000 | 4950000 | 2023 | RAD CONSTRUCTION | 4113 | 2023 | 2023-10-28 | 05/29/2023 | 0 | 0 | 2023-10-27 |  | 1
2023 | Cordillera Administrative Region | IFUGAO | AGUINALDO (IFUGAO) | P00725654LZ | Construction of Flood Mitigation Structure | 121.3425 | 16.9758 | 57872873.51 | 57900000 | 2023 | C-BROS CONSTRUCTION / R.S. SEPIAN CONSTRUCTION & TRUCKING | 4114 | 2023 | 2023-11-06 | 06/05/2023 | 0 | 27126.49 | 2023-11-05 |  | 1
2023 | National Capital Region | QUEZON CITY | QUEZON CITY (METROPOLITAN MANILA) | P00726025LZ | Construction of Flood Mitigation Structure | 121.0976 | 14.6685 | 48999989.6 | 48997299.9 | 2023 | IM CONSTRUCTION CORPORATION | 4115 | 2023 | 2023-09-21 | 02/17/2023 | 2689.7 | 0 | 2023-11-22 | 62
2022 | Region IV-A | BATANGAS | LIPA CITY (BATANGAS) | P00640544LZ | Construction of Drainage Structure | 121.2031 | 13.9152 | 6930000 | 6722480.66 | 2022 | KEASCIA CONSTRUCTION & SUPPLY | 4116 | 2022 | 2022-07-19 | 04/04/2022 | 207519.34 | 0 | 2022-07-18 |  | 1
2022 | Region IV-A | RIZAL | MONTALBAN (RIZAL) | P00639378LZ | Construction of Flood Mitigation Structure | 121.1353 | 14.7369 | 96500000 | 96500000 | 2023 | PRECIOUS CONSTRUCTION / MM SENAR CONSTRUCTION AND SUPPLY | 4117 | 2022 | 2023-03-27 | 09/05/2022 | 0 | 0 | 2023-08-14 | 140
2021 | National Capital Region | MAKATI CITY |  | P00525766LZ | Construction of Flood Mitigation Structure | 121.0611 | 14.5325 | 23540000 | 21412893 | 2023 | C.B. TAMPENGCO CONSTRUCTION & SUPPLY | 4118 | 2021 | 2023-01-04 | 03/22/2022 | 2127107 | 0 | 2023-01-03 |  | 1
2023 | Region IV-A | LAGUNA | LOS BAÃ‘OS (LAGUNA) | P00725790LZ | Construction of Flood Mitigation Structure | 121.2579 | 14.1841 | 48250000 | 48231583.13 | 2023 | N.D.M. SANCHEZ BUILDERS & DEVELOPMENT CORPORATION | 4119 | 2023 | 2023-09-26 | 02/08/2023 | 18416.87 | 0 | 2023-09-25 |  | 1
2022 | Region IV-A | BATANGAS | SAN JOSE (BATANGAS) | P00640543LZ | Construction of Drainage Structure | 121.0833 | 13.8667 | 4950000 | 4851000 | 2022 | 830 BUILDERS & DEVELOPERS CORP. | 4120 | 2022 | 2022-07-08 | 04/05/2022 | 99000 | 0 | 2022-07-07 |  | 1
2021 | National Capital Region | MARIKINA CITY |  | P00525744LZ | Construction of Flood Mitigation Structure | 121.1113 | 14.6821 | 57899928.9 | 54988500.69 | 2023 | 11-16 CONSTRUCTION | 4121 | 2021 | 2023-02-09 | 03/17/2022 | 2911428.21 | 0 | 2023-02-08 |  | 1
2022 | National Capital Region | TAGUIG CITY | TAGUIG CITY (METROPOLITAN MANILA) | P00620010LZ | Construction of Slope Protection Structure | 121.0976 | 14.5323 | 94569381.4 | 89844082.13 | 2022 | NEWBIG FOUR J CONSTRUCTION INC., (FORMERLY FOUR J | 4122 | 2022 | 2022-10-13 | 02/16/2022 | 4725299.27 | 0 | 2022-10-12 |  | 1
2023 | Region IV-A | BATANGAS | SAN JOSE (BATANGAS) | P00742399LZ | Construction of Drainage Structure | 121.0977 | 13.8682 | 4950000 | 4802002.04 | 2024 | LLEB CONSTRUCTION AND TRADING | 4123 | 2023 | 2024-01-08 | 06/23/2023 | 147997.96 | 0 | 2023-09-24 |  | 106
2024 | National Capital Region | PASIG CITY | CITY OF PASIG (METROPOLITAN MANILA) | P00824585LZ | Rehabilitation / Major Repair of Drainage Structure | 121.0979 | 14.6197 | 4899523.85 | 4799173.96 | 2024 | TM ABAD CONSTRUCTION CORP. (FOR: TM ABAD CONST.) | 4124 | 2024 | 2024-06-07 | 04/08/2024 | 100349.89 | 0 | 2024-07-05 | 28
2023 | National Capital Region | MARIKINA CITY | CITY OF MARIKINA (METROPOLITAN MANILA) | P00742232LZ | Construction of Drainage Structure | 121.0981 | 14.6603 | 48999750.22 | 46525913.61 | 2023 | 729 CONSTRUCTION, INC. (FORMERLY 722 CONSTRUCTION, INC.) | 4125 | 2023 | 2023-12-19 | 05/24/2023 | 2473836.61 | 0 | 2023-12-18 |  | 1
2024 | National Capital Region | PASIG CITY | CITY OF PASIG (METROPOLITAN MANILA) | P00821438LZ | Rehabilitation / Major Repair of Slope Protection Structure | 121.0984 | 14.5701 | 48999537.17 | 47524455 | 2024 | DAHL CONSTRUCTION CORP. (FORMERLY: DAHL CONSTRUCTION) | 4126 | 2024 | 2024-08-05 | 02/12/2024 | 1475082.17 | 0 | 2024-08-08 | 3
2024 | National Capital Region | TAGUIG CITY | TAGUIG CITY (METROPOLITAN MANILA) | P00821067LZ | Construction of Slope Protection Structure | 121.0985 | 14.6016 | 96499508.64 | 94567799.19 | 2024 | FRANZCOR TRADING & CONSTRUCTION | 4127 | 2024 | 2024-08-16 | 02/13/2024 | 1931709.45 | 0 | 2024-10-08 | 53
2023 | National Capital Region | MARIKINA CITY | CITY OF MARIKINA (METROPOLITAN MANILA) | P00742231LZ | Construction of Drainage Structure | 121.0985 | 14.6615 | 48999750.22 | 46535318.28 | 2024 | 729 CONSTRUCTION, INC. (FORMERLY 722 CONSTRUCTION, INC.) | 4128 | 2023 | 2024-04-14 | 03/27/2023 | 2464431.94 | 0 | 2024-04-13 |  | 1
2024 | Region IV-A | LAGUNA | SAN PABLO CITY (LAGUNA) | P00838450LZ | Construction of Slope Protection Structure | 121.3443 | 14.0605 | 96500000 | 94087224.79 | 2024 | DELPAR CONSTRUCTION & SUPPLIES | 4129 | 2024 | 2024-11-20 | 02/29/2024 | 2412775.21 | 0 | 2024-12-23 | 33
2021 | Cordillera Administrative Region | KALINGA |  | P00525937LZ | Construction of Flood Mitigation Structure | 121.1617 | 17.3832 | 4900000 | 4801517.62 | 2023 | MATAGOAN KJ BUILDERS AND ENGINEERING SERVICES | 4130 | 2021 | 2023-03-31 | 04/10/2022 | 98482.38 | 0 | 2022-07-30 |  | 244
2023 | National Capital Region | MARIKINA CITY | CITY OF MARIKINA (METROPOLITAN MANILA) | P00727230LZ | Construction of Flood Mitigation Facility | 121.0986 | 14.6678 | 97999643.56 | 93035955.95 | 2024 | L.R. TIQUI BUILDERS, INC. | 4131 | 2023 | 2024-02-03 | 06/09/2023 | 4963687.61 | 0 | 2024-02-02 |  | 1
2022 | National Capital Region | MARIKINA CITY | CITY OF MARIKINA (METROPOLITAN MANILA) | P00632710LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.0988 | 14.6506 | 48999627.93 | 46522147.58 | 2023 | L.R. TIQUI BUILDERS, INC. | 4132 | 2022 | 2023-01-14 | 02/08/2022 | 2477480.35 | 0 | 2023-01-13 |  | 1
2022 | National Capital Region | TAGUIG CITY | TAGUIG CITY (METROPOLITAN MANILA) | P00620009LZ | Construction of Slope Protection Structure | 121.0989 | 14.5331 | 94569723.96 | 89841032.41 | 2022 | J.C. UYECIO CONSTRUCTION AND DEVELOPMENT COMPANY / A.J. LAVA BUILDERS CORP. (FORMERLY: A.J. LAVA BUIL | 4133 | 2022 | 2022-10-13 | 02/16/2022 | 4728691.55 | 0 | 2022-10-12 |  | 1
2023 | National Capital Region | PASIG CITY | CITY OF PASIG (METROPOLITAN MANILA) | P00727007LZ | Rehabilitation / Major Repair of Drainage Structure | 121.0989 | 14.552 | 4899697.49 | 4653250 | 2023 | B. VALENCERINA TRADING & CONSTRUCTION | 4134 | 2023 | 2023-08-20 | 05/23/2023 | 246447.49 | 0 | 2023-08-19 |  | 1
2024 | Region IV-B | CAMARINES SUR | SAN JOSE (CAMARINES SUR) | P00820968LZ | Construction of Flood Mitigation Structure | 121.0994 | 12.3528 | 49000000 | 48997765.82 | 2024 | F.A. TORRES CONSTRUCTION / MIGHTY DRAGON BUILDERS INC. | 4135 | 2024 | 2024-05-15 | 02/06/2024 | 2234.18 | 0 | 2024-08-24 | 101
2023 | National Capital Region | PASIG CITY | CITY OF PASIG (METROPOLITAN MANILA) | P00725949LZ | Rehabilitation / Major Repair of Drainage Structure | 121.0994 | 14.6031 | 9799369.38 | 9306350 | 2023 | TUCHAR CONSTRUCTION CORP. (FORMERLY:TUCHAR CONSTRU | 4136 | 2023 | 2023-08-04 | 02/06/2023 | 493019.38 | 0 | 2023-08-03 |  | 1
2023 | National Capital Region | MARIKINA CITY | CITY OF MARIKINA (METROPOLITAN MANILA) | P00726790LZ | Construction of Drainage Structure | 121.0995 | 14.6624 | 49207641.03 | 46727916.11 | 2023 | 729 CONSTRUCTION, INC. (FORMERLY 722 CONSTRUCTION, INC.) | 4137 | 2023 | 2023-12-16 | 03/22/2023 | 2479724.92 | 0 | 2023-12-15 |  | 1
2022 | National Capital Region | TAGUIG CITY | TAGUIG CITY (METROPOLITAN MANILA) | P00620008LZ | Construction of Slope Protection Structure | 121.1 | 14.5338 | 94569862.07 | 89708559.82 | 2022 | J.C. UYECIO CONSTRUCTION AND DEVELOPMENT COMPANY / A.J. LAVA BUILDERS CORP. (FORMERLY: A.J. LAVA BUIL | 4138 | 2022 | 2022-09-01 | 02/16/2022 | 4861302.25 | 0 | 2022-10-12 | 41
2024 | National Capital Region | PASIG CITY | CITY OF PASIG (METROPOLITAN MANILA) | P00824594LZ | Rehabilitation / Major Repair of Drainage Structure | 121.1006 | 14.6032 | 14699667.94 | 14400000 | 2024 | 816 EMBER CONSTRUCTION CORPORATION | 4139 | 2024 | 2024-09-04 | 04/08/2024 | 299667.94 | 0 | 2024-09-03 |  | 1
2023 | Region IV-A | LAGUNA | CITY OF SANTA ROSA (LAGUNA) | P00737522LZ | Rehabilitation / Major Repair of Drainage Structure | 121.1006 | 14.3011 | 4950000 | 4854180 | 2023 | DATZLAV CONSTRUCTION | 4140 | 2023 | 2023-06-29 | 02/08/2023 | 95820 | 0 | 2023-06-28 |  | 1
2023 | National Capital Region | PASIG CITY | CITY OF PASIG (METROPOLITAN MANILA) | P00725944LZ | Rehabilitation / Major Repair of Drainage Structure | 121.1006 | 14.6133 | 5389012.31 | 5118488.9 | 2023 | B. VALENCERINA TRADING & CONSTRUCTION | 4141 | 2023 | 2023-08-04 | 02/06/2023 | 270523.41 | 0 | 2023-08-03 |  | 1
2023 | Region II | CAGAYAN | CLAVERIA (CAGAYAN) | P00740572LZ | Construction of Flood Mitigation Structure | 121.1007 | 18.5765 | 9900000 | 9652511.61 | 2024 | J.B. ALCANTARA BUILDERS | 4142 | 2023 | 2024-01-22 | 03/27/2023 | 247488.39 | 0 | 2023-07-23 |  | 183
2022 | National Capital Region | PASIG CITY | CITY OF PASIG (METROPOLITAN MANILA) | P00621267LZ | Rehabilitation / Major Repair of Slope Protection Structure | 121.1008 | 14.5771 | 72374766.67 | 68727191.24 | 2022 | ST. MATTHEW GEN. CONTRACTOR & DEVELOPMENT CORP. | 4143 | 2022 | 2022-10-04 | 03/24/2022 | 3647575.43 | 0 | 2022-10-18 | 14
2022 | National Capital Region | QUEZON CITY | QUEZON CITY (METROPOLITAN MANILA) | P00621434LZ | Construction of Flood Mitigation Structure | 121.1009 | 14.7079 | 46000226.55 | 44160217.49 | 2023 | TRICHES CONSTRUCTION & TRADING | 4144 | 2022 | 2023-03-12 | 05/17/2022 | 1840009.06 | 0 | 2023-03-11 |  | 1
2024 | National Capital Region | PASIG CITY | CITY OF PASIG (METROPOLITAN MANILA) | P00821450LZ | Rehabilitation / Major Repair of Drainage Structure | 121.101 | 14.6031 | 14699878.61 | 14360000 | 2024 | JCML BUILDERS | 4145 | 2024 | 2024-10-02 | 02/12/2024 | 339878.61 | 0 | 2024-10-01 |  | 1
2023 | National Capital Region | PASIG CITY | CITY OF PASIG (METROPOLITAN MANILA) | P00725954LZ | Construction of Flood Mitigation Structure | 121.1013 | 14.5771 | 3919889.48 | 3726263.38 | 2023 | WAY MAKER GENERAL CONTRACTOR OPC | 4146 | 2023 | 2023-05-07 | 02/06/2023 | 193626.1 | 0 | 2023-05-05 |  | 2
2023 | Region III | NUEVA ECIJA | RIZAL (NUEVA ECIJA) | P00742146LZ | Construction of Flood Mitigation Structure | 121.1013 | 15.7257 | 99000000 | 98996644.29 | 2023 | SPECO BUILDERS INC. (FORMERLY VRF CONSTRUCTION) | 4147 | 2023 | 2023-09-19 | 04/13/2023 | 3355.71 | 0 | 2024-01-06 | 109
2022 | National Capital Region | TAGUIG CITY | TAGUIG CITY (METROPOLITAN MANILA) | P00620007LZ | Construction of Slope Protection Structure | 121.1014 | 14.5349 | 94569850.78 | 89179369.28 | 2022 | J.C. UYECIO CONSTRUCTION AND DEVELOPMENT COMPANY / A.J. LAVA BUILDERS CORP. (FORMERLY: A.J. LAVA BUIL | 4148 | 2022 | 2022-10-13 | 02/16/2022 | 5390481.5 | 0 | 2022-10-12 |  | 1
2022 | National Capital Region | MARIKINA CITY | CITY OF MARIKINA (METROPOLITAN MANILA) | P00639405LZ | Construction of Drainage Structure | 121.1014 | 14.6643 | 48999298.55 | 46531390.29 | 2023 | L.R. TIQUI BUILDERS, INC. | 4149 | 2022 | 2023-04-06 | 03/24/2022 | 2467908.26 | 0 | 2023-04-05 |  | 1
2023 | National Capital Region | PASIG CITY | CITY OF PASIG (METROPOLITAN MANILA) | P00742234LZ | Rehabilitation / Major Repair of Drainage Structure | 121.1015 | 14.541 | 31359513.39 | 29782000 | 2024 | DAHL CONSTRUCTION CORP. (FORMERLY: DAHL CONSTRUCTION) | 4150 | 2023 | 2024-03-26 | 09/05/2023 | 1577513.39 | 0 | 2024-04-30 | 35
2023 | National Capital Region | PASIG CITY | CITY OF PASIG (METROPOLITAN MANILA) | P00725518LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.1016 | 14.5762 | 72374545.58 | 68598212.46 | 2024 | ALPHA & OMEGA GEN. CONTRACTOR & DEVELOPMENT CORP. | 4151 | 2023 | 2024-07-08 | 02/13/2023 | 3776333.12 | 0 | 2023-11-08 |  | 243
2023 | Region IV-B | ORIENTAL MINDORO | NAUJAN (ORIENTAL MINDORO) | P00740428LZ | Construction of Dike | 121.1017 | 13.2865 | 241249996.4 | 241246196.1 | 2023 | SILVERWOLVES CONSTRUCTION CORPORATION | 4152 | 2023 | 2023-10-15 | 04/13/2023 | 3800.3 | 0 | 2024-04-05 | 173
2023 | Region IV-B | ORIENTAL MINDORO | NAUJAN (ORIENTAL MINDORO) | P00740426LZ | Construction of Dike | 121.1017 | 13.2919 | 241250000 | 241246775.7 | 2023 | PHESCO, INCORPORATED | 4153 | 2023 | 2023-10-15 | 04/13/2023 | 3224.3 | 0 | 2024-04-05 | 173
2023 | National Capital Region | PASIG CITY | CITY OF PASIG (METROPOLITAN MANILA) | P00727003LZ | Rehabilitation / Major Repair of Drainage Structure | 121.1019 | 14.6122 | 14699788.83 | 13960450 | 2024 | 816 EMBER CONSTRUCTION CORPORATION | 4154 | 2023 | 2024-02-10 | 06/08/2023 | 739338.83 | 0 | 2024-02-09 |  | 1
2023 | Region IV-B | ORIENTAL MINDORO | BACO (ORIENTAL MINDORO) | P00727185LZ | Rehabilitation / Major Repair of Drainage Structure | 121.1019 | 13.3572 | 9104200 | 9044555.45 | 2023 | CMSEL CONSTRUCTION & DEVELOPER | 4155 | 2023 | 2023-08-15 | 03/30/2023 | 59644.55 | 0 | 2023-08-14 |  | 1
2024 | National Capital Region | PASIG CITY | CITY OF PASIG (METROPOLITAN MANILA) | P00824592LZ | Rehabilitation / Major Repair of Drainage Structure | 121.1019 | 14.6127 | 9799704.94 | 9600000 | 2024 | DAHL CONSTRUCTION CORP. (FORMERLY: DAHL CONSTRUCTION) | 4156 | 2024 | 2024-09-02 | 04/08/2024 | 199704.94 | 0 | 2024-09-01 |  | 1
2024 | National Capital Region | PASIG CITY | CITY OF PASIG (METROPOLITAN MANILA) | P00824598LZ | Rehabilitation / Major Repair of Drainage Structure | 121.102 | 14.5766 | 4899842.29 | 4825413.74 | 2024 | AZUL BUILDERS | 4157 | 2024 | 2024-06-23 | 03/11/2024 | 74428.55 | 0 | 2024-06-07 |  | 16
2024 | National Capital Region | PASIG CITY | CITY OF PASIG (METROPOLITAN MANILA) | P00823266LZ | Rehabilitation / Major Repair of Slope Protection Structure | 121.1021 | 14.5757 | 96499470.57 | 94530649.03 | 2025 | M3 KONSTRACT CORPORATION (FORMERLY:MARGARITA CONSTRUCTION) | 4158 | 2024 | 2025-02-24 | 04/01/2024 | 1968821.54 | 0 | 2025-02-23 |  | 1
2024 | National Capital Region | MARIKINA CITY | CITY OF MARIKINA (METROPOLITAN MANILA) | P00845861LZ | Rehabilitation / Major Repair of Drainage Structure | 121.1021 | 14.6582 | 29699615.72 | 29177719.98 | 2025 | MRB11 CONSTRUCTION CORPORATION (FORMERLY:MRB CONS | 4159 | 2024 | 2025-01-17 | 04/08/2024 | 521895.74 | 0 | 2025-03-02 | 44
2023 | National Capital Region | TAGUIG CITY | TAGUIG CITY (METROPOLITAN MANILA) | P00742108LZ | Construction of Slope Protection Structure | 121.1022 | 14.5348 | 96499766.49 | 91636178.26 | 2024 | DAHL CONSTRUCTION CORP. (FORMERLY: DAHL CONSTRUCTION) | 4160 | 2023 | 2024-01-15 | 09/29/2023 | 4863588.23 | 0 | 2024-05-24 | 130
2024 | Region IV-A | BATANGAS | BATANGAS CITY (CAPITAL) (BATANGAS) | P00820868LZ | Construction of Flood Mitigation Structure | 121.1027 | 13.6251 | 39200000 | 39200000 | 2024 | EFREN RAMIREZ CONSTRUCTION AND GENERAL SERVICES CORPORATION | 4161 | 2024 | 2024-07-17 | 02/07/2024 | 0 | 0 | 2024-07-25 | 8
2023 | National Capital Region | PASIG CITY | CITY OF PASIG (METROPOLITAN MANILA) | P00727005LZ | Rehabilitation / Major Repair of Drainage Structure | 121.1027 | 14.5411 | 5879820.49 | 5584065 | 2023 | ANDREW LOUIS CONSTRUCTION AND TRADING | 4162 | 2023 | 2023-08-20 | 05/23/2023 | 295755.49 | 0 | 2023-08-19 |  | 1
2024 | National Capital Region | PASIG CITY | CITY OF PASIG (METROPOLITAN MANILA) | P00824597LZ | Rehabilitation / Major Repair of Drainage Structure | 121.1028 | 14.5934 | 9799869.07 | 9602277 | 2024 | 729 CONSTRUCTION, INC. (FORMERLY 722 CONSTRUCTION, INC.) | 4163 | 2024 | 2024-10-04 | 04/08/2024 | 197592.07 | 0 | 2024-11-02 | 29
2023 | National Capital Region | PASIG CITY | CITY OF PASIG (METROPOLITAN MANILA) | P00727002LZ | Construction of Drainage Structure | 121.1028 | 14.5941 | 7839304.92 | 7405117.3 | 2023 | CALCON ENGINEERING | 4164 | 2023 | 2023-09-01 | 03/06/2023 | 434187.62 | 0 | 2023-08-31 |  | 1
2023 | Region IV-A | BATANGAS | SAN JOSE (BATANGAS) | P00742416LZ | Rehabilitation / Major Repair of Drainage Structure | 121.1029 | 13.8784 | 4950000 | 4801500 | 2023 | LUCKY EIGHTY-THREE CONSTRUCTION AND SUPPLY(FOR.VRP | 4165 | 2023 | 2023-07-14 | 04/27/2023 | 148500 | 0 | 2023-07-13 |  | 1
2023 | National Capital Region | PASIG CITY | CITY OF PASIG (METROPOLITAN MANILA) | P00725945LZ | Rehabilitation / Major Repair of Drainage Structure | 121.1031 | 14.5939 | 19599635.08 | 18613450 | 2023 | B. BERNARDO CONST., INC. | 4166 | 2023 | 2023-07-05 | 02/06/2023 | 986185.08 | 0 | 2023-07-04 |  | 1
2022 | Region IV-A | BATANGAS | SAN JOSE (BATANGAS) | P00640542LZ | Construction of Drainage Structure | 121.1032 | 13.9237 | 9900000 | 9603000 | 2022 | LUCKY EIGHTY-THREE CONSTRUCTION AND SUPPLY(FOR.VRP | 4167 | 2022 | 2022-08-07 | 04/05/2022 | 297000 | 0 | 2022-08-06 |  | 1
2023 | National Capital Region | TAGUIG CITY | TAGUIG CITY (METROPOLITAN MANILA) | P00742109LZ | Construction of Slope Protection Structure | 121.1032 | 14.5338 | 96499459.73 | 91577987.28 | 2024 | DAHL CONSTRUCTION CORP. (FORMERLY: DAHL CONSTRUCTION) | 4168 | 2023 | 2024-01-15 | 09/29/2023 | 4921472.45 | 0 | 2024-05-24 | 130
2024 | National Capital Region | PASIG CITY | CITY OF PASIG (METROPOLITAN MANILA) | P00845862LZ | Rehabilitation / Major Repair of Drainage Structure | 121.1032 | 14.5459 | 19799647.76 | 19395750 | 2024 | DAHL CONSTRUCTION CORP. (FORMERLY: DAHL CONSTRUCTION) | 4169 | 2024 | 2024-08-07 | 04/08/2024 | 403897.76 | 0 | 2024-10-03 | 57
2022 | Region IV-A | LAGUNA | CITY OF CALAMBA (LAGUNA) | P00640559LZ | Rehabilitation / Major Repair of Drainage Structure | 121.1037 | 14.2018 | 7425000 | 7274006.35 | 2023 | MAGNA RICH TRADING & CONSTRUCTION | 4170 | 2022 | 2023-03-07 | 07/11/2022 | 150993.65 | 0 | 2023-03-06 |  | 1
2023 | Region IV-A | BATANGAS | SAN JOSE (BATANGAS) | P00742415LZ | Rehabilitation / Major Repair of Drainage Structure | 121.1038 | 13.8765 | 4950000 | 4801500 | 2023 | LUCKY EIGHTY-THREE CONSTRUCTION AND SUPPLY(FOR.VRP / LUCKY EIGHTY-THREE CONSTRUCTION AND SUPPLY(FOR.VRP | 4171 | 2023 | 2023-07-14 | 04/27/2023 | 148500 | 0 | 2023-07-13 |  | 1
2023 | Region IV-B | ORIENTAL MINDORO | NAUJAN (ORIENTAL MINDORO) | P00740427LZ | Construction of Dike | 121.1041 | 13.2991 | 241250000 | 241245362.7 | 2023 | MONOLITHIC CONSTRUCTION & CONCRETE PRODUCTS, INC. | 4172 | 2023 | 2023-10-15 | 04/13/2023 | 4637.3 | 0 | 2024-04-05 | 173
2022 | National Capital Region | MARIKINA CITY | CITY OF MARIKINA (METROPOLITAN MANILA) | P00639406LZ | Construction of Drainage Structure | 121.1041 | 14.6651 | 48999803.51 | 46521674.81 | 2022 | STO. CRISTO CONSTRUCTION & TRADING INC. (FOR: STO. CRISTO CONSTRUCTION & TRADING) | 4173 | 2022 | 2022-12-18 | 03/24/2022 | 2478128.7 | 0 | 2022-12-17 |  | 1
2023 | National Capital Region | MARIKINA CITY | CITY OF MARIKINA (METROPOLITAN MANILA) | P00725516LZ | Construction of Flood Mitigation Structure | 121.1043 | 14.6245 | 88003611.07 | 83533778.38 | 2024 | METER KING INC. / JASMIG CONSTRUCTION CORPORATION (FORMERLY: JASMIG CONSTRUCTION SUPPLY) | 4174 | 2023 | 2024-02-03 | 06/09/2023 | 4469832.69 | 0 | 2024-02-02 |  | 1
2024 | Region IV-B | ORIENTAL MINDORO | NAUJAN (ORIENTAL MINDORO) | P00825126LZ | Construction of Flood Mitigation Structure | 121.1047 | 13.2206 | 98000000 | 96499978.46 | 2024 | SILVERWOLVES CONSTRUCTION CORPORATION | 4175 | 2024 | 2024-04-22 | 02/08/2024 | 1500021.54 | 0 | 2025-02-16 | 300
2021 | National Capital Region | MARIKINA CITY |  | P00525717LZ | Construction of Flood Mitigation Structure | 121.1054 | 14.663 | 48999823.99 | 46534811.01 | 2023 | F.P. DE GUZMAN CONSTRUCTION, INC. | 4176 | 2021 | 2023-04-28 | 05/14/2021 | 2465012.98 | 0 | 2023-04-27 |  | 1
2023 | Region IV-A | BATANGAS | SAN JOSE (BATANGAS) | P00742414LZ | Rehabilitation / Major Repair of Drainage Structure | 121.1059 | 13.8792 | 4950000 | 4801500 | 2023 | LUCKY EIGHTY-THREE CONSTRUCTION AND SUPPLY(FOR.VRP | 4177 | 2023 | 2023-08-10 | 05/08/2023 | 148500 | 0 | 2023-08-09 |  | 1
2023 | Region IV-A | BATANGAS | SAN JOSE (BATANGAS) | P00742407LZ | Rehabilitation / Major Repair of Drainage Structure | 121.106 | 13.8787 | 11385000 | 11043450 | 2023 | 830 BUILDERS & DEVELOPERS CORP. | 4178 | 2023 | 2023-08-07 | 04/27/2023 | 341550 | 0 | 2023-09-06 | 30
2023 | Region II | NUEVA VIZCAYA | DUPAX DEL NORTE (NUEVA VIZCAYA) | P00725665LZ | Construction of Flood Mitigation Structure | 121.1061 | 16.3378 | 48250000 | 48249825.26 | 2023 | AMP 723 CONSTRUCTION CORPORATION (FORMERLY: A.M.P. CONSTRUCTION) | 4179 | 2023 | 2023-08-27 | 02/10/2023 | 174.74 | 0 | 2023-08-26 |  | 1
2024 | National Capital Region | PASIG CITY | CITY OF PASIG (METROPOLITAN MANILA) | P00821424LZ | Construction of Drainage Structure | 121.1066 | 14.5471 | 14699465.76 | 14358000 | 2024 | F316 CONSTRUCTION CORP. | 4180 | 2024 | 2024-09-18 | 02/12/2024 | 341465.76 | 0 | 2024-09-17 |  | 1
2022 | Region III | NUEVA ECIJA | RIZAL (NUEVA ECIJA) | P00621619LZ | Construction of Flood Mitigation Structure | 121.1068 | 15.7221 | 49000000 | 48388030.69 | 2022 | SPECO BUILDERS INC. (FORMERLY VRF CONSTRUCTION) | 4181 | 2022 | 2022-09-26 | 04/08/2022 | 611969.31 | 0 | 2022-11-02 | 37
2023 | Region III | NUEVA ECIJA | PANTABANGAN (NUEVA ECIJA) | P00726734LZ | Construction of Flood Mitigation Structure | 121.1069 | 15.722 | 49000000 | 48995000 | 2023 | IRC CONSTRUCTION & SUPPLIES / SYMMETRICON BUILDERS CORP. | 4182 | 2023 | 2023-08-08 | 02/21/2023 | 5000 | 0 | 2023-09-17 | 40
2024 | Region IV-A | RIZAL | SAN MATEO (RIZAL) | P00823552LZ | Construction of Flood Mitigation Structure | 121.1069 | 14.6752 | 49000000 | 48250000 | 2024 | PERSAN CONSTRUCTION, INC. (FORMERLY: PERSAN CONST. | 4183 | 2024 | 2024-07-15 | 04/08/2024 | 750000 | 0 | 2025-01-31 | 200
2022 | Region II | NUEVA VIZCAYA | BAMBANG (NUEVA VIZCAYA) | P00621420LZ | Construction of Flood Mitigation Structure | 121.1069 | 16.405 | 44100000 | 44100000 | 2023 | E.T. LATAWAN CONSTRUCTION | 4184 | 2022 | 2023-01-15 | 05/20/2022 | 0 | 0 | 2023-02-16 | 32
2024 | National Capital Region | PASIG CITY | CITY OF PASIG (METROPOLITAN MANILA) | P00821423LZ | Construction of Drainage Structure | 121.107 | 14.5477 | 14699708.43 | 14355000 | 2024 | F.P. DE GUZMAN CONSTRUCTION, INC. | 4185 | 2024 | 2024-09-18 | 02/12/2024 | 344708.43 | 0 | 2024-09-17 |  | 1
2022 | Region III | NUEVA ECIJA | RIZAL (NUEVA ECIJA) | P00621620LZ | Construction of Flood Mitigation Structure | 121.1071 | 15.7219 | 49000000 | 48020454.15 | 2022 | SPECO BUILDERS INC. (FORMERLY VRF CONSTRUCTION) | 4186 | 2022 | 2022-09-02 | 04/08/2022 | 979545.85 | 0 | 2022-11-02 | 61
2023 | National Capital Region | MARIKINA CITY | CITY OF MARIKINA (METROPOLITAN MANILA) | P00725515LZ | Construction of Drainage Structure | 121.1071 | 14.6348 | 67549059.58 | 56741661.01 | 2024 | ST. GERRARD CONSTRUCTION GEN. CONTRACTOR & DEVELOPMENT CORP. (FORMERLY:ST. GERRARD CONSTRUCTION) | 4187 | 2023 | 2024-03-14 | 02/13/2023 | 10807398.57 | 0 | 2024-04-27 | 44
2022 | National Capital Region | MARIKINA CITY | CITY OF MARIKINA (METROPOLITAN MANILA) | P00632707LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.1072 | 14.6353 | 48999910.66 | 46353618.68 | 2022 | ALPHA & OMEGA GEN. CONTRACTOR & DEVELOPMENT CORP. | 4188 | 2022 | 2022-10-18 | 02/08/2022 | 2646291.98 | 0 | 2022-11-12 | 25
2024 | National Capital Region | PASIG CITY | CITY OF PASIG (METROPOLITAN MANILA) | P00821422LZ | Construction of Drainage Structure | 121.1072 | 14.5483 | 14699775.85 | 14362000 | 2024 | 816 EMBER CONSTRUCTION CORPORATION | 4189 | 2024 | 2024-10-08 | 02/12/2024 | 337775.85 | 0 | 2024-10-07 |  | 1
2023 | National Capital Region | PASIG CITY | CITY OF PASIG (METROPOLITAN MANILA) | P00727004LZ | Construction of Drainage Structure | 121.1073 | 14.5484 | 15679471.34 | 14887658.04 | 2023 | 1HB CONSTRUCTION CORP. (FORMERLY: HB CONSTRUCTION) | 4190 | 2023 | 2023-10-15 | 03/20/2023 | 791813.3 | 0 | 2023-10-14 |  | 1
2023 | National Capital Region | PASIG CITY | CITY OF PASIG (METROPOLITAN MANILA) | P00727006LZ | Rehabilitation / Major Repair of Drainage Structure | 121.1075 | 14.5475 | 14209432.86 | 13491856.5 | 2023 | 816 EMBER CONSTRUCTION CORPORATION | 4191 | 2023 | 2023-10-15 | 03/20/2023 | 717576.36 | 0 | 2023-10-14 |  | 1
2023 | Region II | NUEVA VIZCAYA | BAMBANG (NUEVA VIZCAYA) | P00740574LZ | Construction of Drainage Structure | 121.1076 | 16.3885 | 29400000 | 29400000 | 2024 | BRG CONSTRUCTION | 4192 | 2023 | 2024-03-12 | 05/31/2023 | 0 | 0 | 2024-02-14 |  | 27
2024 | Region III | NUEVA ECIJA | PALAYAN CITY (CAPITAL) (NUEVA ECIJA) | P00821258LZ | Construction of Flood Mitigation Structure | 121.1078 | 15.5981 | 70286667.02 | 68997401.62 | 2024 | SOLFIO P. JACINTO CONSTRUCTION INC. | 4193 | 2024 | 2024-04-30 | 02/13/2024 | 1289265.4 | 0 | 2024-10-23 | 176
2022 | Region II | NUEVA VIZCAYA | BAYOMBONG (CAPITAL) (NUEVA VIZCAYA) | P00621066LZ | Construction of Flood Mitigation Structure | 121.1081 | 16.4423 | 44100000 | 44100000 | 2022 | A.J. LAVA BUILDERS CORP. (FORMERLY: A.J. LAVA BUIL / R.O. BUILDERS & DEVELOPMENT CORPORATION | 4194 | 2022 | 2022-08-23 | 02/07/2022 | 0 | 0 | 2022-11-07 | 76
2023 | National Capital Region | PASIG CITY | CITY OF PASIG (METROPOLITAN MANILA) | P00725946LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.1086 | 14.5876 | 32339673.69 | 26522268.36 | 2023 | ALPHA & OMEGA GEN. CONTRACTOR & DEVELOPMENT CORP. | 4195 | 2023 | 2023-08-04 | 02/06/2023 | 5817405.33 | 0 | 2023-08-03 |  | 1
2021 | National Capital Region | MARIKINA CITY |  | P00525746LZ | Construction of Flood Mitigation Structure | 121.1087 | 14.6775 | 96499544.03 | 91626579.72 | 2022 | ROAD EDGE TRADING & DEVELOPMENT SERVICES | 4196 | 2021 | 2022-12-04 | 02/08/2022 | 4872964.31 | 0 | 2022-12-03 |  | 1
2022 | Region IV-A | RIZAL | CAINTA (RIZAL) | P00639500LZ | Rehabilitation / Major Repair of Drainage Structure | 121.1087 | 14.6047 | 49000000 | 48999996.69 | 2023 | AARCON BUILDERS | 4197 | 2022 | 2023-03-02 | 07/06/2022 | 3.31 | 0 | 2023-03-01 |  | 1
2023 | National Capital Region | PASIG CITY | CITY OF PASIG (METROPOLITAN MANILA) | P00725947LZ | Construction of Flood Mitigation Structure | 121.1087 | 14.5801 | 48999819.12 | 46516087.53 | 2024 | ST. TIMOTHY CONSTRUCTION CORPORATION | 4198 | 2023 | 2024-06-03 | 02/06/2023 | 2483731.59 | 0 | 2024-03-20 |  | 75
2023 | National Capital Region | MARIKINA CITY | CITY OF MARIKINA (METROPOLITAN MANILA) | P00725933LZ | Construction of Drainage Structure | 121.1088 | 14.6373 | 37239416.62 | 35355762.73 | 2023 | YPR GEN. CONTRACTOR AND CONSTRUCTION SUPPLY INC. | 4199 | 2023 | 2023-10-03 | 02/06/2023 | 1883653.89 | 0 | 2023-10-02 |  | 1
2022 | Cordillera Administrative Region | KALINGA | TINGLAYAN (KALINGA) | P00644765LZ | Construction of Slope Protection Structure | 121.109 | 17.2228 | 9630700 | 9620504.08 | 2023 | BANGYAN 3D CONSTRUCTION | 4200 | 2022 | 2023-10-24 | 01/12/2023 | 10195.92 | 0 | 2023-08-08 |  | 77
2022 | Region III | BULACAN | CITY OF SAN JOSE DEL MONTE (BULACAN) | P00637071LZ | Construction of Slope Protection Structure | 121.109 | 14.8201 | 39199406.15 | 39197202.76 | 2022 | C.T. LEONCIO CONSTRUCTION & TRADING | 4201 | 2022 | 2022-11-29 | 05/26/2022 | 2203.39 | 0 | 2022-11-28 |  | 1
2021 | Region IV-A | RIZAL |  | P00525649LZ | Construction of Flood Mitigation Structure | 121.1093 | 14.6014 | 45355000 | 45311851.54 | 2022 | G. ANORE CONSTRUCTION / DOUBLE 12 CONSTRUCTION & SUPPLY | 4202 | 2021 | 2022-12-11 | 04/11/2022 | 43148.46 | 0 | 2022-12-10 |  | 1
2021 | Region II | NUEVA VIZCAYA |  | P00561677LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.1094 | 16.4019 | 29700000 | 29700000 | 2022 | JANN-NORRIS CONSTRUCTION AND SUPPLIES INC. (FORMELY: JANN-NORRIS CONSTRUCTION AND SUPPLIES) | 4203 | 2021 | 2022-08-20 | 01/12/2022 | 0 | 0 | 2022-09-25 | 36
2022 | Region IV-A | RIZAL | CAINTA (RIZAL) | P00620636LZ | Construction of Flood Mitigation Structure | 121.1094 | 14.6035 | 11580000 | 11577576.99 | 2022 | G. ANORE CONSTRUCTION | 4204 | 2022 | 2022-09-28 | 04/11/2022 | 2423.01 | 0 | 2022-09-27 |  | 1
2022 | National Capital Region | QUEZON CITY | QUEZON CITY (METROPOLITAN MANILA) | P00620441LZ | Construction of Flood Mitigation Structure | 121.1096 | 14.6923 | 44100000 | 42768180 | 2022 | E.L. ANOLIN CONSTRUCTION | 4205 | 2022 | 2022-12-12 | 02/07/2022 | 1331820 | 0 | 2022-12-02 |  | 10
2022 | National Capital Region | QUEZON CITY | QUEZON CITY (METROPOLITAN MANILA) | P00620766LZ | Construction of Slope Protection Structure | 121.1096 | 14.6923 | 86850000 | 83373114.19 | 2023 | A.L. SALAZAR CONSTRUCTION, INC. | 4206 | 2022 | 2023-03-06 | 02/16/2022 | 3476885.81 | 0 | 2023-02-09 |  | 25
2022 | National Capital Region | QUEZON CITY | QUEZON CITY (METROPOLITAN MANILA) | P00620928LZ | Construction of Slope Protection Structure | 121.1096 | 14.6923 | 44100000 | 42330218.21 | 2022 | A.L. SALAZAR CONSTRUCTION, INC. | 4207 | 2022 | 2022-11-21 | 02/10/2022 | 1769781.79 | 0 | 2022-12-05 | 14
2022 | National Capital Region | QUEZON CITY | QUEZON CITY (METROPOLITAN MANILA) | P00620767LZ | Construction of Slope Protection Structure | 121.1097 | 14.6923 | 86850000 | 83370218.21 | 2023 | A.L. SALAZAR CONSTRUCTION, INC. | 4208 | 2022 | 2023-04-11 | 03/22/2022 | 3479781.79 | 0 | 2023-03-15 |  | 27
2022 | National Capital Region | MARIKINA CITY | CITY OF MARIKINA (METROPOLITAN MANILA) | P00632709LZ | Rehabilitation / Major Repair of Drainage Structure | 121.1097 | 14.6536 | 29399622.94 | 27920821.91 | 2022 | TUCHAR CONSTRUCTION CORP. (FORMERLY:TUCHAR CONSTRU | 4209 | 2022 | 2022-08-06 | 02/08/2022 | 1478801.03 | 0 | 2022-08-05 |  | 1
2022 | Cordillera Administrative Region | APAYAO | KABUGAO (CAPITAL) (APAYAO) | P00637065LZ | Construction of Flood Mitigation Structure | 121.1097 | 18.0267 | 24499866.44 | 24500000 | 2023 | OMENGAN CONSTRUCTION & DEVELOPMENT CORPORATION | 4210 | 2022 | 2023-04-30 | 05/03/2022 | 0 | 133.56 | 2023-01-07 |  | 113
2021 | Region II | NUEVA VIZCAYA |  | P00526279LZ | Construction of Flood Mitigation Structure | 121.11 | 16.3825 | 125450000 | 117368750.3 | 2022 | J.H. PAJARA CONSTRUCTION CORPORATION | 4211 | 2021 | 2022-12-12 | 01/18/2022 | 8081249.7 | 0 | 2022-12-28 | 16
2023 | National Capital Region | MARIKINA CITY | CITY OF MARIKINA (METROPOLITAN MANILA) | P00725932LZ | Construction of Drainage Structure | 121.1101 | 14.644 | 48999746.68 | 46546399.2 | 2024 | 729 CONSTRUCTION, INC. (FORMERLY 722 CONSTRUCTION, INC.) | 4212 | 2023 | 2024-12-01 | 02/06/2023 | 2453347.48 | 0 | 2024-11-30 |  | 1
2024 | National Capital Region | MARIKINA CITY | CITY OF MARIKINA (METROPOLITAN MANILA) | P00825202LZ | Construction of Slope Protection Structure | 121.1102 | 14.6363 | 48999698.7 | 48001608.49 | 2025 | 729 CONSTRUCTION, INC. (FORMERLY 722 CONSTRUCTION, INC.) | 4213 | 2024 | 2025-03-03 | 04/01/2024 | 998090.21 | 0 | 2025-03-27 | 24
2022 | Region IV-A | LAGUNA | CITY OF SANTA ROSA (LAGUNA) | P00620584LZ | Construction of Revetment | 121.1105 | 14.2661 | 44682120 | 43475714 | 2022 | POWER K CONSTRUCTION SUPPLY & SERVICES / EOZ CONSTRUCTION | 4214 | 2022 | 2022-11-28 | 02/14/2022 | 1206406 | 0 | 2022-11-27 |  | 1
2023 | National Capital Region | MARIKINA CITY | CITY OF MARIKINA (METROPOLITAN MANILA) | P00725934LZ | Construction of Drainage Structure | 121.1107 | 14.6421 | 44099791.69 | 41878276.31 | 2024 | GREAT PACIFIC BUILDERS AND GEN. CONTRACTOR INC. / J.M.L.R. CONSTRUCTION AND SUPPLY | 4215 | 2023 | 2024-03-26 | 02/06/2023 | 2221515.38 | 0 | 2024-03-30 | 4
2023 | National Capital Region | QUEZON CITY | QUEZON CITY (METROPOLITAN MANILA) | P00725513LZ | Construction of Flood Mitigation Structure | 121.1108 | 14.6888 | 96499650 | 96499650 | 2023 | A.L. SALAZAR CONSTRUCTION, INC. | 4216 | 2023 | 2023-12-18 | 02/13/2023 | 0 | 0 | 2024-02-06 | 50
2023 | National Capital Region | QUEZON CITY | QUEZON CITY (METROPOLITAN MANILA) | P00725553LZ | Construction of Flood Mitigation Structure | 121.1109 | 14.6895 | 43559998 | 42762228.48 | 2024 | DIADEMA CONSTRUCTION AND ENTERPRISES INC. (FORMERLY: DIADEMA ENTERPRISES) | 4217 | 2023 | 2024-03-31 | 02/14/2023 | 797769.52 | 0 | 2023-12-09 |  | 113
2021 | National Capital Region | MARIKINA CITY |  | P00525723LZ | Construction of Flood Mitigation Structure | 121.111 | 14.636 | 29399826.31 | 27918676.97 | 2022 | 729 CONSTRUCTION, INC. (FORMERLY 722 CONSTRUCTION, INC.) | 4218 | 2021 | 2022-09-29 | 08/13/2021 | 1481149.34 | 0 | 2022-09-28 |  | 1
2023 | National Capital Region | QUEZON CITY | QUEZON CITY (METROPOLITAN MANILA) | P00725552LZ | Construction of Flood Mitigation Structure | 121.111 | 14.6918 | 96499629.5 | 96499629.5 | 2023 | TRIPLE 8 CONSTRUCTION & SUPPLY, INC. (FORMERLY TRIPLE 8 CONST. & SUPPLY) / PILASTRO BUILDERS & DEVELOPMENT INC. | 4219 | 2023 | 2023-12-19 | 02/27/2023 | 0 | 0 | 2024-02-20 | 63
2024 | National Capital Region | QUEZON CITY | QUEZON CITY (METROPOLITAN MANILA) | P00820023LZ | Construction of Revetment | 121.1111 | 14.6938 | 96499794.5 | 95341600.18 | 2025 | DIADEMA CONSTRUCTION AND ENTERPRISES INC. (FORMERLY: DIADEMA ENTERPRISES) / AF3 CONSTRUCTION CORPORATION | 4220 | 2024 | 2025-03-11 | 03/18/2024 | 1158194.32 | 0 | 2025-03-11 | 0
2023 | National Capital Region | MAKATI CITY | CITY OF MAKATI (METROPOLITAN MANILA) | P00737391LZ | Construction of Flood Mitigation Structure | 121.0611 | 14.5437 | 39600000 | 39599226.64 | 2023 | AARCON BUILDERS | 4221 | 2023 | 2023-10-03 | 02/06/2023 | 773.36 | 0 | 2023-10-02 |  | 1
2021 | National Capital Region | MARIKINA CITY |  | P00525745LZ | Construction of Flood Mitigation Structure | 121.1113 | 14.6821 | 54805730.27 | 51780561.65 | 2023 | 11-16 CONSTRUCTION | 4222 | 2021 | 2023-01-10 | 03/17/2022 | 3025168.62 | 0 | 2023-01-09 |  | 1
2023 | Region IV-A | RIZAL | MONTALBAN (RIZAL) | P00737544LZ | Construction of Flood Mitigation Structure | 121.1355 | 14.752 | 9900000 | 9164395.48 | 2023 | JUNMICMARC CONSTRUCTION | 4223 | 2023 | 2023-10-19 | 05/03/2023 | 735604.52 | 0 | 2023-10-18 |  | 1
2023 | National Capital Region | PASIG CITY | CITY OF PASIG (METROPOLITAN MANILA) | P00725942LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.0838 | 14.5623 | 7349475.04 | 6979271.06 | 2023 | EL KAPITAN CONSTRUCTION SERVICES | 4224 | 2023 | 2023-07-05 | 02/06/2023 | 370203.98 | 0 | 2023-07-04 |  | 1
2022 | Region IV-A | BATANGAS | LOBO (BATANGAS) | P00620863LZ | Construction of Flood Mitigation Structure | 121.2051 | 13.6343 | 79130000 | 79130000 | 2023 | TCSC CORP. / EFREN RAMIREZ CONSTRUCTION AND GENERAL SERVICES CORPORATION | 4225 | 2022 | 2023-11-16 | 02/15/2022 | 0 | 0 | 2023-12-02 | 16
2023 | Region IV-A | BATANGAS | LOBO (BATANGAS) | P00740396LZ | Construction of Flood Mitigation Structure | 121.258 | 13.6053 | 9800000 | 9650000 | 2023 | SUPPLICON BUILDERS | 4226 | 2023 | 2023-09-11 | 04/03/2023 | 150000 | 0 | 2023-09-10 |  | 1
2022 | Region IV-A | RIZAL | JALA-JALA (RIZAL) | P00632918LZ | Construction of Slope Protection Structure | 121.3445 | 14.3189 | 49500000 | 49500000 | 2023 | WAWAO BUILDERS | 4227 | 2022 | 2023-03-17 | 02/15/2022 | 0 | 0 | 2023-03-16 |  | 1
2022 | Region IV-A | RIZAL | ANGONO (RIZAL) | P00620645LZ | Construction of Flood Mitigation Structure | 121.1622 | 14.5337 | 19600000 | 19600000 | 2022 | DJL ROBLES BUILDERS | 4228 | 2022 | 2022-10-07 | 03/28/2022 | 0 | 0 | 2022-10-09 | 2
2023 | Region II | NUEVA VIZCAYA | BAMBANG (NUEVA VIZCAYA) | P00727116LZ | Construction of Flood Mitigation Structure | 121.1115 | 16.4075 | 49000000 | 49000000 | 2023 | BRG CONSTRUCTION | 4229 | 2023 | 2023-11-13 | 03/13/2023 | 0 | 0 | 2023-11-12 |  | 1
2024 | Region II | NUEVA VIZCAYA | BAYOMBONG (CAPITAL) (NUEVA VIZCAYA) | P00825052LZ | Construction of Flood Mitigation Structure | 121.1115 | 16.4446 | 144750000 | 144750000 | 2024 | EGB CONSTRUCTION CORPORATION (FORMERLY: EGB CONSTRUCTION) | 4230 | 2024 | 2024-05-21 | 02/16/2024 | 0 | 0 | 2025-01-24 | 248
2024 | Region II | NUEVA VIZCAYA | BAYOMBONG (CAPITAL) (NUEVA VIZCAYA) | P00825051LZ | Construction of Flood Mitigation Structure | 121.1115 | 16.4444 | 144750000 | 144750000 | 2024 | EGB CONSTRUCTION CORPORATION (FORMERLY: EGB CONSTRUCTION) | 4231 | 2024 | 2024-05-21 | 02/16/2024 | 0 | 0 | 2025-01-24 | 248
2024 | Region IV-A | RIZAL | SAN MATEO (RIZAL) | P00820304LZ | Construction of Flood Mitigation Structure | 121.1116 | 14.6888 | 144750000 | 144750000 | 2024 | AKSUM CONTRACTING CORPORATION | 4232 | 2024 | 2024-07-15 | 03/15/2024 | 0 | 0 | 2025-04-09 | 268
2024 | Region II | NUEVA VIZCAYA | BAMBANG (NUEVA VIZCAYA) | P00825047LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.1117 | 16.4219 | 96500000 | 96500000 | 2024 | DALCON CONSTRUCTION | 4233 | 2024 | 2024-05-15 | 03/08/2024 | 0 | 0 | 2025-01-25 | 255
2021 | National Capital Region | QUEZON CITY |  | P00525501LZ | Construction of Flood Mitigation Structure | 121.1119 | 14.6852 | 85829995 | 82391142.18 | 2023 | A.L. SALAZAR CONSTRUCTION, INC. | 4234 | 2021 | 2023-03-17 | 03/24/2022 | 3438852.82 | 0 | 2023-03-17 | 0
2022 | National Capital Region | QUEZON CITY | QUEZON CITY (METROPOLITAN MANILA) | P00620104LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.1119 | 14.6852 | 72544050 | 72548700 | 2023 | LE BRON CONSTRUCTION | 4235 | 2022 | 2023-01-29 | 02/16/2022 | 0 | 4650 | 2023-02-09 | 11
2024 | National Capital Region | QUEZON CITY | QUEZON CITY (METROPOLITAN MANILA) | P00824630LZ | Construction of Drainage Structure | 121.0612 | 14.6698 | 9799976.1 | 9799974.07 | 2024 | A.J. LAVA BUILDERS CORP. (FORMERLY: A.J. LAVA BUIL | 4236 | 2024 | 2024-05-17 | 02/23/2024 | 2.03 | 0 | 2024-06-20 | 34
2023 | National Capital Region | QUEZON CITY | QUEZON CITY (METROPOLITAN MANILA) | P00726014LZ | Construction of Flood Mitigation Structure | 121.1119 | 14.7028 | 48999850 | 48440881 | 2023 | DIADEMA CONSTRUCTION AND ENTERPRISES INC. (FORMERLY: DIADEMA ENTERPRISES) | 4237 | 2023 | 2023-12-08 | 02/14/2023 | 558969 | 0 | 2023-12-09 | 1
2024 | Region IV-A | RIZAL | SAN MATEO (RIZAL) | P00820305LZ | Construction of Flood Mitigation Structure | 121.112 | 14.6874 | 144750000 | 144750000 | 2024 | AKSUM CONTRACTING CORPORATION | 4238 | 2024 | 2024-06-16 | 03/15/2024 | 0 | 0 | 2025-04-09 | 297
2021 | Region IV-A | RIZAL |  | P00526308LZ | Construction of Flood Mitigation Structure | 121.1124 | 14.6848 | 95918105 | 82028200.85 | 2022 | SUPREME ABF CONST. & CONST. SUPPLY COMPANY INC. | 4239 | 2021 | 2022-12-02 | 03/22/2021 | 13889904.15 | 0 | 2022-12-01 |  | 1
2024 | Region IV-A | BATANGAS | MATAASNAKAHOY (BATANGAS) | P00839605LZ | Rehabilitation / Major Repair of Drainage Structure | 121.1124 | 13.9588 | 9900000 | 9651344 | 2024 | PRIME MOVER'S PHILS. CONSTRUCTION AND SUPPLIES INC. | 4240 | 2024 | 2024-09-28 | 05/02/2024 | 248656 | 0 | 2024-09-27 |  | 1
2023 | Region II | NUEVA VIZCAYA | BAMBANG (NUEVA VIZCAYA) | P00737364LZ | Construction of Flood Mitigation Structure | 121.1127 | 16.4051 | 59400000 | 59400000 | 2023 | M.R. VARGAS CONSTRUCTION CORPORATION (FORMERLY: M.R. VARGAS CONSTRUCTION) | 4241 | 2023 | 2023-10-28 | 02/14/2023 | 0 | 0 | 2023-10-27 |  | 1
2024 | Region IV-A | BATANGAS | MATAASNAKAHOY (BATANGAS) | P00839604LZ | Rehabilitation / Major Repair of Drainage Structure | 121.1127 | 13.9555 | 4950000 | 4825893.43 | 2024 | PRIME MOVER'S PHILS. CONSTRUCTION AND SUPPLIES INC. | 4242 | 2024 | 2024-08-26 | 04/29/2024 | 124106.57 | 0 | 2024-08-25 |  | 1
2024 | Region III | BULACAN | CITY OF SAN JOSE DEL MONTE (BULACAN) | P00820231LZ | Construction of Flood Mitigation Structure | 121.113 | 14.8394 | 68876507.86 | 68871068.05 | 2024 | TRIPLE 8 CONSTRUCTION & SUPPLY, INC. (FORMERLY TRIPLE 8 CONST. & SUPPLY) | 4243 | 2024 | 2024-08-12 | 02/22/2024 | 5439.81 | 0 | 2024-10-25 | 74
2023 | Region IV-A | BATANGAS | SAN JOSE (BATANGAS) | P00737499LZ | Construction of Flood Mitigation Structure | 121.113 | 13.8614 | 5940000 | 5761800 | 2023 | MAC BUILDERS CIVIL ENGINEERING CONSTRUCTION | 4244 | 2023 | 2023-06-07 | 02/08/2023 | 178200 | 0 | 2023-06-06 |  | 1
2021 | Region IV-A | RIZAL |  | P00525647LZ | Construction of Flood Mitigation Structure | 121.1136 | 14.5656 | 43425000 | 40819918.28 | 2022 | C.F. TRINIDAD CONSTRUCTION AND SUPPLIES CORP. (FOR | 4245 | 2021 | 2022-10-02 | 04/06/2022 | 2605081.72 | 0 | 2022-10-01 |  | 1
2023 | Region IV-A | RIZAL | SAN MATEO (RIZAL) | P00726568LZ | Construction of Flood Mitigation Structure | 121.1137 | 14.6865 | 125450000 | 125449994.8 | 2024 | GREAT PACIFIC BUILDERS AND GEN. CONTRACTOR INC. | 4246 | 2023 | 2024-06-01 | 03/10/2023 | 5.2 | 0 | 2024-05-31 |  | 1
2023 | Region IV-A | LAGUNA | CITY OF SANTA ROSA (LAGUNA) | P00737523LZ | Rehabilitation / Major Repair of Drainage Structure | 121.1142 | 14.3078 | 9900000 | 9626996 | 2023 | EOZ CONSTRUCTION | 4247 | 2023 | 2023-10-10 | 03/03/2023 | 273004 | 0 | 2023-10-09 |  | 1
2022 | Region IV-A | RIZAL | CITY OF ANTIPOLO (RIZAL) | P00620261LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.1144 | 14.6142 | 92918885 | 92918782.24 | 2023 | A.J. LAVA BUILDERS CORP. (FORMERLY: A.J. LAVA BUIL / BELL CONSTRUCTION | 4248 | 2022 | 2023-04-24 | 03/07/2022 | 102.76 | 0 | 2023-04-29 | 5
2023 | Region II | NUEVA VIZCAYA | DUPAX DEL NORTE (NUEVA VIZCAYA) | P00726140LZ | Construction of Flood Mitigation Structure | 121.1147 | 16.318 | 49000000 | 48999979.03 | 2023 | R.O. BUILDERS & DEVELOPMENT CORPORATION | 4249 | 2023 | 2023-08-23 | 02/06/2023 | 20.97 | 0 | 2023-08-22 |  | 1
2024 | National Capital Region | MARIKINA CITY | CITY OF MARIKINA (METROPOLITAN MANILA) | P00823233LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.1151 | 14.6738 | 96499973.8 | 94534207.04 | 2024 | L.R. TIQUI BUILDERS, INC. | 4250 | 2024 | 2024-10-21 | 03/14/2024 | 1965766.76 | 0 | 2025-02-19 | 121
2024 | Region IV-A | LAGUNA | CABUYAO CITY (LAGUNA) | P00820365LZ | Construction of Flood Mitigation Structure | 121.1151 | 14.2745 | 87562170 | 85373200 | 2025 | POWER K CONSTRUCTION SUPPLY & SERVICES / EOZ CONSTRUCTION | 4251 | 2024 | 2025-04-02 | 03/01/2024 | 2188970 | 0 | 2025-04-01 |  | 1
2024 | National Capital Region | MARIKINA CITY | CITY OF MARIKINA (METROPOLITAN MANILA) | P00825205LZ | Construction of Slope Protection Structure | 121.1158 | 14.6384 | 40031878.59 | 39216457.66 | 2025 | 729 CONSTRUCTION, INC. (FORMERLY 722 CONSTRUCTION, INC.) | 4252 | 2024 | 2025-02-03 | 04/01/2024 | 815420.93 | 0 | 2025-02-25 | 22
2021 | National Capital Region | MARIKINA CITY |  | P00561473LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.1159 | 14.6383 | 29399531.36 | 27921189.21 | 2022 | 729 CONSTRUCTION, INC. (FORMERLY 722 CONSTRUCTION, INC.) | 4253 | 2021 | 2022-08-24 | 03/01/2021 | 1478342.15 | 0 | 2022-08-23 |  | 1
2021 | National Capital Region | MARIKINA CITY |  | P00525724LZ | Construction of Flood Mitigation Structure | 121.1159 | 14.6383 | 48999683.63 | 46531568.36 | 2023 | L.R. TIQUI BUILDERS, INC. | 4254 | 2021 | 2023-03-01 | 11/03/2021 | 2468115.27 | 0 | 2023-02-28 |  | 1
2022 | National Capital Region | MARIKINA CITY | CITY OF MARIKINA (METROPOLITAN MANILA) | P00639404LZ | Construction of Drainage Structure | 121.1162 | 14.6384 | 48999121.58 | 46531269.11 | 2023 | L.R. TIQUI BUILDERS, INC. | 4255 | 2022 | 2023-05-10 | 07/15/2022 | 2467852.47 | 0 | 2023-05-09 |  | 1
2024 | Region IV-A | RIZAL | CAINTA (RIZAL) | P00820941LZ | Construction of Flood Mitigation Structure | 121.1164 | 14.5684 | 49000000 | 48999965.78 | 2024 | G.F. FABIAN CONSTRUCTION | 4256 | 2024 | 2024-07-26 | 02/14/2024 | 34.22 | 0 | 2024-08-30 | 35
2024 | Region II | NUEVA VIZCAYA | BAYOMBONG (CAPITAL) (NUEVA VIZCAYA) | P00843255LZ | Construction of Flood Mitigation Structure | 121.1165 | 16.4596 | 93605000 | 93605000 | 2024 | DALCON CONSTRUCTION | 4257 | 2024 | 2024-06-30 | 03/08/2024 | 0 | 0 | 2025-01-19 | 203
2022 | Region IV-A | RIZAL | CAINTA (RIZAL) | P00639501LZ | Rehabilitation / Major Repair of Drainage Structure | 121.1166 | 14.5843 | 19600000 | 19592817.96 | 2023 | 5-1 CONSTRUCTION CORPORATION | 4258 | 2022 | 2023-01-22 | 07/27/2022 | 7182.04 | 0 | 2023-01-21 |  | 1
2021 | Region IV-A | RIZAL |  | P00561395LZ | Construction of Drainage Structure | 121.117 | 14.5922 | 24750000 | 24735004.03 | 2022 | J.H.R. ENTERPRISES | 4259 | 2021 | 2022-10-13 | 03/24/2022 | 14995.97 | 0 | 2022-10-18 | 5
2022 | Region IV-A | RIZAL | CAINTA (RIZAL) | P00639505LZ | Rehabilitation / Major Repair of Drainage Structure | 121.1177 | 14.5783 | 9800000 | 9800000 | 2023 | RED TREE CONSTRUCTION | 4260 | 2022 | 2023-04-05 | 07/20/2022 | 0 | 0 | 2023-04-04 |  | 1
2022 | Region IV-A | RIZAL | CAINTA (RIZAL) | P00639503LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.1179 | 14.5686 | 4900000 | 4900000 | 2023 | D.R. ROBLES CONSTRUCTION | 4261 | 2022 | 2023-01-15 | 07/20/2022 | 0 | 0 | 2023-01-14 |  | 1
2023 | Cordillera Administrative Region | KALINGA | TINGLAYAN (KALINGA) | P00726661LZ | Construction of Flood Mitigation Structure | 121.118 | 17.2316 | 9800000 | 9752558.5 | 2023 | JEP CONSTRUCTION | 4262 | 2023 | 2023-11-13 | 02/21/2023 | 47441.5 | 0 | 2023-07-24 |  | 112
2021 | Region IV-A | RIZAL |  | P00561568LZ | Construction of Flood Mitigation Structure | 121.1184 | 14.6857 | 2970000 | 2887852.23 | 2022 | GENUINE BUILDERS | 4263 | 2021 | 2022-12-11 | 09/05/2022 | 82147.77 | 0 | 2022-12-20 | 9
2023 | Region IV-A | BATANGAS | MATAASNAKAHOY (BATANGAS) | P00742392LZ | Construction of Drainage Structure | 121.1186 | 13.9471 | 4950000 | 4949600 | 2023 | PRIME MOVER'S PHILS. CONSTRUCTION AND SUPPLIES INC. | 4264 | 2023 | 2023-09-18 | 03/23/2023 | 400 | 0 | 2023-09-17 |  | 1
2024 | Region II | NUEVA VIZCAYA | BAMBANG (NUEVA VIZCAYA) | P00820788LZ | Construction of Flood Mitigation Structure | 121.1186 | 16.3908 | 19600000 | 19600000 | 2024 | N-J CONSTRUCTION | 4265 | 2024 | 2024-09-05 | 02/21/2024 | 0 | 0 | 2024-09-07 | 2
2024 | Region IV-A | BATANGAS | MATAASNAKAHOY (BATANGAS) | P00846039LZ | Construction of Drainage Structure | 121.1186 | 13.9493 | 4950000 | 4949948 | 2024 | ISHIZAKI CONSTRUCTION & DEVELOPMENT CORPORATION | 4266 | 2024 | 2024-07-09 | 02/15/2024 | 52 | 0 | 2024-07-08 |  | 1
2023 | Region IV-A | RIZAL | SAN MATEO (RIZAL) | P00726569LZ | Construction of Flood Mitigation Structure | 121.1187 | 14.6863 | 106150000 | 106146063.9 | 2024 | GREAT PACIFIC BUILDERS AND GEN. CONTRACTOR INC. | 4267 | 2023 | 2024-05-10 | 03/10/2023 | 3936.1 | 0 | 2024-05-09 |  | 1
2023 | Region IV-A | BATANGAS | LIPA CITY (BATANGAS) | P00727157LZ | Construction of Slope Protection Structure | 121.1191 | 13.9309 | 14700000 | 14700000 | 2023 | TERAVERA CORPORATION | 4268 | 2023 | 2023-11-15 | 03/03/2023 | 0 | 0 | 2023-06-23 |  | 145
2022 | Region IV-B | OCCIDENTAL MINDORO | SAN JOSE (OCCIDENTAL MINDORO) | P00621110LZ | Construction of Flood Mitigation Structure | 121.1192 | 12.4536 | 39200000 | 30889322.14 | 2023 | ALPHA & OMEGA GEN. CONTRACTOR & DEVELOPMENT CORP. | 4269 | 2022 | 2023-06-07 | 04/11/2022 | 8310677.86 | 0 | 2022-12-25 |  | 164
2023 | Region II | NUEVA VIZCAYA | BAYOMBONG (CAPITAL) (NUEVA VIZCAYA) | P00745420LZ | Construction of Flood Mitigation Structure | 121.1194 | 16.4667 | 19500000 | 19300000 | 2023 | J.E.L. CONSTRUCTION & SUPPLY | 4270 | 2023 | 2023-11-30 | 06/28/2023 | 200000 | 0 | 2023-12-04 | 4
2024 | Region II | NUEVA VIZCAYA | BAYOMBONG (CAPITAL) (NUEVA VIZCAYA) | P00825235LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.1197 | 16.4668 | 49000000 | 49000000 | 2024 | V.B. MANUBAY CONSTRUCTION | 4271 | 2024 | 2024-09-02 | 02/16/2024 | 0 | 0 | 2024-10-02 | 30
2020 | Region IV-A | RIZAL |  | P00448737LZ | Construction of Drainage Structure | 121.1198 | 14.698 | 125450000 | 125449561.5 | 2022 | HONEYVILLECONST AND DEVELOPMENT CORPORATION | 4272 | 2020 | 2022-12-19 | 09/10/2020 | 438.5 | 0 | 2022-12-18 |  | 1
2022 | Region IV-A | RIZAL | TAYTAY (RIZAL) | P00620256LZ | Construction of Flood Mitigation Structure | 121.1201 | 14.5534 | 94946350 | 94926276.39 | 2022 | FLORDES CONSTRUCTION & TRADING CORP. (FORMERLY FLO | 4273 | 2022 | 2022-11-15 | 03/28/2022 | 20073.61 | 0 | 2022-11-21 | 6
2023 | Region IV-A | RIZAL | SAN MATEO (RIZAL) | P00736622LZ | Construction of Drainage Structure | 121.1206 | 14.6969 | 49000000 | 49000000 | 2024 | L.S.D. CONSTRUCTION & SUPPLIES | 4274 | 2023 | 2024-05-15 | 09/21/2023 | 0 | 0 | 2024-06-05 | 21
2023 | Region IV-A | RIZAL | SAN MATEO (RIZAL) | P00737540LZ | Construction of Drainage Structure | 121.1207 | 14.6858 | 4950000 | 4950000 | 2023 | JAM KONSTRUCT CONSTRUCTION AND DEVELOPMENT INC. | 4275 | 2023 | 2023-07-01 | 02/20/2023 | 0 | 0 | 2023-06-30 |  | 1
2021 | Cordillera Administrative Region | IFUGAO |  | P00525551LZ | Construction of Flood Mitigation Structure | 121.1208 | 16.7857 | 61566702.65 | 61570860 | 2022 | JANN-NORRIS CONSTRUCTION AND SUPPLIES INC. (FORMELY: JANN-NORRIS CONSTRUCTION AND SUPPLIES) | 4276 | 2021 | 2022-12-26 | 04/05/2022 | 0 | 4157.35 | 2022-12-25 |  | 1
2022 | Region II | NUEVA VIZCAYA | BAMBANG (NUEVA VIZCAYA) | P00621065LZ | Construction of Flood Mitigation Structure | 121.1209 | 16.4244 | 49000000 | 49000000 | 2022 | CITRUS COUNTRY CONSTRUCTION | 4277 | 2022 | 2022-12-18 | 02/10/2022 | 0 | 0 | 2022-12-24 | 6
2022 | Region IV-A | RIZAL | CITY OF ANTIPOLO (RIZAL) | P00620648LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.1209 | 14.6246 | 22050000 | 18433172.71 | 2023 | BELL CONSTRUCTION | 4278 | 2022 | 2023-01-16 | 03/23/2022 | 3616827.29 | 0 | 2023-01-15 |  | 1
2022 | Region II | NUEVA VIZCAYA | BAYOMBONG (CAPITAL) (NUEVA VIZCAYA) | P00641869LZ | Construction of Flood Mitigation Structure | 121.1209 | 16.4682 | 49000000 | 49000000 | 2022 | DALCON CONSTRUCTION | 4279 | 2022 | 2022-11-30 | 03/31/2022 | 0 | 0 | 2023-02-02 | 64
2024 | Region IV-A | RIZAL | SAN MATEO (RIZAL) | P00839651LZ | Construction of Drainage Structure | 121.121 | 14.6771 | 4950000 | 4950000 | 2024 | C.E.M. CONSTRUCTION, INC. | 4280 | 2024 | 2024-05-15 | 02/07/2024 | 0 | 0 | 2024-06-21 | 37
2022 | Cordillera Administrative Region | IFUGAO | LAGAWE (CAPITAL) (IFUGAO) | P00620805LZ | Construction of Flood Mitigation Structure | 121.1211 | 16.785 | 111608777.2 | 75007552.68 | 2023 | DJY CONSTRUCTION | 4281 | 2022 | 2023-10-11 | 10/14/2022 | 36601224.52 | 0 | 2023-10-10 |  | 1
2021 | National Capital Region | MARIKINA CITY |  | P00525478LZ | Construction of Flood Mitigation Structure | 121.1215 | 14.637 | 78399438.55 | 74449237.08 | 2023 | L.R. TIQUI BUILDERS, INC. | 4282 | 2021 | 2023-03-12 | 11/02/2021 | 3950201.47 | 0 | 2023-03-11 |  | 1
2018 | Region IV-B | OCCIDENTAL MINDORO |  | P00223238LZ | Construction of Flood Mitigation Structure | 121.1217 | 12.5866 | 96500000 | 92738982.46 | 2023 | FFJJ CONSTRUCTION | 4283 | 2018 | 2023-02-27 | 04/20/2018 | 3761017.54 | 0 | 2019-02-03 |  | 1485
2023 | Region IV-A | LAGUNA | CITY OF CALAMBA (LAGUNA) | P00726224LZ | Construction of Flood Mitigation Structure | 121.122 | 14.21 | 44100000 | 42953760 | 2023 | PASCAL CONSTRUCTION | 4284 | 2023 | 2023-12-06 | 02/28/2023 | 1146240 | 0 | 2023-12-05 |  | 1
2022 | Region IV-A | RIZAL | CAINTA (RIZAL) | P00637799LZ | Rehabilitation / Major Repair of Drainage Structure | 121.1224 | 14.5921 | 9800000 | 9899885.24 | 2023 | ULTIMOS CONSTRUCTION CORP. | 4285 | 2022 | 2023-05-29 | 07/04/2022 | 0 | 99885.24 | 2023-05-28 |  | 1
2022 | Region II | NUEVA VIZCAYA | BAYOMBONG (CAPITAL) (NUEVA VIZCAYA) | P00621069LZ | Construction of Flood Mitigation Structure | 121.1229 | 16.4332 | 44100000 | 44100000 | 2022 | BRG CONSTRUCTION | 4286 | 2022 | 2022-12-16 | 02/10/2022 | 0 | 0 | 2022-12-23 | 7
2023 | Region II | NUEVA VIZCAYA | BAYOMBONG (CAPITAL) (NUEVA VIZCAYA) | P00726710LZ | Construction of Flood Mitigation Structure | 121.1231 | 16.4714 | 9800000 | 9800000 | 2023 | TRIPLE P CONSTRUCTION | 4287 | 2023 | 2023-05-15 | 02/15/2023 | 0 | 0 | 2023-07-01 | 47
2023 | Region II | NUEVA VIZCAYA | BAYOMBONG (CAPITAL) (NUEVA VIZCAYA) | P00727117LZ | Construction of Flood Mitigation Structure | 121.1231 | 16.4714 | 49000000 | 49000000 | 2023 | DALCON CONSTRUCTION | 4288 | 2023 | 2023-04-23 | 03/08/2023 | 0 | 0 | 2023-12-15 | 236
2023 | Region IV-A | RIZAL | SAN MATEO (RIZAL) | P00737539LZ | Rehabilitation / Major Repair of Drainage Structure | 121.1234 | 14.6978 | 9900000 | 4750931.77 | 2023 | T. REYES CONSTRUCTION | 4289 | 2023 | 2023-08-21 | 04/13/2023 | 5149068.23 | 0 | 2023-09-24 | 34
2023 | Region IV-A | RIZAL | TAYTAY (RIZAL) | P00726575LZ | Construction of Flood Mitigation Structure | 121.1238 | 14.5466 | 106150000 | 106149488 | 2024 | YPR GEN. CONTRACTOR AND CONSTRUCTION SUPPLY INC. | 4290 | 2023 | 2024-04-15 | 03/31/2023 | 512 | 0 | 2024-04-14 |  | 1
2023 | Region IV-A | RIZAL | SAN MATEO (RIZAL) | P00737537LZ | Construction of Drainage Structure | 121.124 | 14.7013 | 4950000 | 4950000 | 2023 | PISTOL CONSTRUCTION AND SUPPLY | 4291 | 2023 | 2023-05-20 | 02/10/2023 | 0 | 0 | 2023-05-19 |  | 1
2024 | Region IV-B | ORIENTAL MINDORO | CITY OF CALAPAN (CAPITAL) (ORIENTAL MINDORO) | P00846101LZ | Construction of Flood Mitigation Structure | 121.1244 | 13.3575 | 19800000 | 19800000 | 2024 | ARCONIC INC. | 4292 | 2024 | 2024-09-10 | 02/22/2024 | 0 | 0 | 2024-09-23 | 13
2023 | Region IV-A | BATANGAS | SAN JOSE (BATANGAS) | P00742413LZ | Construction of Slope Protection Structure | 121.1245 | 13.8811 | 4950000 | 4801500 | 2023 | LUCKY EIGHTY-THREE CONSTRUCTION AND SUPPLY(FOR.VRP | 4293 | 2023 | 2023-09-26 | 04/27/2023 | 148500 | 0 | 2023-07-27 |  | 61
2023 | National Capital Region | MARIKINA CITY | CITY OF MARIKINA (METROPOLITAN MANILA) | P00727000LZ | Construction of Slope Protection Structure | 121.1248 | 14.6681 | 44099424.14 | 41879376.78 | 2023 | 729 CONSTRUCTION, INC. (FORMERLY 722 CONSTRUCTION, INC.) | 4294 | 2023 | 2023-10-20 | 05/24/2023 | 2220047.36 | 0 | 2023-10-19 |  | 1
2021 | Region IV-A | RIZAL |  | P00561569LZ | Construction of Flood Mitigation Structure | 121.1259 | 14.6928 | 9900000 | 9900000 | 2022 | L. EUSEBIO ACE DEVELOPMENT CORPORATION | 4295 | 2021 | 2022-12-19 | 09/05/2022 | 0 | 0 | 2023-01-10 | 22
2023 | Region II | NUEVA VIZCAYA | BAMBANG (NUEVA VIZCAYA) | P00726141LZ | Construction of Flood Mitigation Structure | 121.1261 | 16.407 | 49000000 | 49000000 | 2023 | BRG CONSTRUCTION | 4296 | 2023 | 2023-10-03 | 02/15/2023 | 0 | 0 | 2023-10-02 |  | 1
2024 | Region IV-A | RIZAL | TAYTAY (RIZAL) | P00820960LZ | Construction of Flood Mitigation Structure | 121.1264 | 14.5595 | 19600000 | 19599554.7 | 2024 | C.F. TRINIDAD CONSTRUCTION AND SUPPLIES CORP. (FOR | 4297 | 2024 | 2024-07-04 | 02/21/2024 | 445.3 | 0 | 2024-07-03 |  | 1
2024 | Region II | NUEVA VIZCAYA | BAYOMBONG (CAPITAL) (NUEVA VIZCAYA) | P00821191LZ | Construction of Flood Mitigation Structure | 121.1269 | 16.4738 | 96500000 | 96500000 | 2024 | V.B. MANUBAY CONSTRUCTION | 4298 | 2024 | 2024-12-15 | 02/16/2024 | 0 | 0 | 2025-01-01 | 17
2023 | Region IV-A | RIZAL | SAN MATEO (RIZAL) | P00737541LZ | Construction of Flood Mitigation Structure | 121.127 | 14.6828 | 4950000 | 4950000 | 2023 | C.E.M. CONSTRUCTION, INC. | 4299 | 2023 | 2023-03-27 | 02/10/2023 | 0 | 0 | 2023-04-24 | 28
2021 | Region IV-A | RIZAL |  | P00561571LZ | Construction of Flood Mitigation Structure | 121.127 | 14.6958 | 4950000 | 4818684.46 | 2022 | C.E.M. CONSTRUCTION, INC. | 4300 | 2021 | 2022-11-14 | 09/05/2022 | 131315.54 | 0 | 2022-12-19 | 35
2022 | Region IV-A | LAGUNA | CABUYAO CITY (LAGUNA) | P00620583LZ | Construction of Revetment | 121.1271 | 14.2894 | 47470220 | 46037061.26 | 2022 | ST. TIMOTHY CONSTRUCTION CORPORATION | 4301 | 2022 | 2022-08-20 | 02/14/2022 | 1433158.74 | 0 | 2022-09-28 | 39
2022 | Region IV-A | RIZAL | CAINTA (RIZAL) | P00637802LZ | Rehabilitation / Major Repair of Drainage Structure | 121.1274 | 14.5791 | 9900000 | 9010591.78 | 2023 | G.F. FABIAN CONSTRUCTION | 4302 | 2022 | 2023-01-29 | 06/14/2022 | 889408.22 | 0 | 2023-01-08 |  | 21
2024 | Region III | NUEVA ECIJA | PALAYAN CITY (CAPITAL) (NUEVA ECIJA) | P00821257LZ | Construction of Flood Mitigation Structure | 121.1275 | 15.5947 | 86849972.01 | 85114741.23 | 2024 | JERRY R. SANTIAGO CONSTRUCTION CORP. (FORMERLY: JERRY SANTIAGO CONSTRUCTION) | 4303 | 2024 | 2024-05-13 | 02/13/2024 | 1735230.78 | 0 | 2024-11-16 | 187
2024 | Region IV-B | ORIENTAL MINDORO | CITY OF CALAPAN (CAPITAL) (ORIENTAL MINDORO) | P00824748LZ | Construction of Flood Mitigation Structure | 121.1275 | 13.38 | 18146700 | 17963395.16 | 2024 | TWENTY SIXTEEN CONSTRUCTION AND GENERAL MERCHANDISE | 4304 | 2024 | 2024-10-25 | 02/08/2024 | 183304.84 | 0 | 2024-11-02 | 8
2022 | Region IV-A | BATANGAS | BATANGAS CITY (CAPITAL) (BATANGAS) | P00620558LZ | Construction of Flood Mitigation Structure | 121.1287 | 13.6339 | 19600000 | 19600000 | 2022 | EFREN RAMIREZ CONSTRUCTION AND GENERAL SERVICES CORPORATION / M.J. APIN BUILDERS | 4305 | 2022 | 2022-07-18 | 01/28/2022 | 0 | 0 | 2022-07-17 |  | 1
2023 | Region IV-A | BATANGAS | CITY OF TANAUAN (BATANGAS) | P00725771LZ | Construction of Flood Mitigation Structure | 121.1291 | 14.1057 | 96500000 | 96499118.98 | 2024 | LOUREL DEVELOPMENT CORPORATION (FORMERLY :LOUREL D / THREE W BUILDERS, INC. | 4306 | 2023 | 2024-08-21 | 03/09/2023 | 881.02 | 0 | 2024-08-20 |  | 1
2022 | Region IV-A | RIZAL | TAYTAY (RIZAL) | P00620219LZ | Construction of Flood Mitigation Structure | 121.1304 | 14.5359 | 102290000 | 102289850 | 2023 | ST. TIMOTHY CONSTRUCTION CORPORATION | 4307 | 2022 | 2023-11-30 | 03/23/2022 | 150 | 0 | 2023-11-29 |  | 1
2022 | Region IV-A | RIZAL | CITY OF ANTIPOLO (RIZAL) | P00620632LZ | Construction of Flood Mitigation Structure | 121.1313 | 14.638 | 14700000 | 14699078.69 | 2022 | T. REYES CONSTRUCTION | 4308 | 2022 | 2022-07-21 | 02/22/2022 | 921.31 | 0 | 2022-08-19 | 29
2022 | National Capital Region | MARIKINA CITY | CITY OF MARIKINA (METROPOLITAN MANILA) | P00620078LZ | Construction of Flood Mitigation Structure | 121.1314 | 14.6641 | 96499982.71 | 91630467.22 | 2022 | L.R. TIQUI BUILDERS, INC. | 4309 | 2022 | 2022-12-12 | 03/18/2022 | 4869515.49 | 0 | 2022-12-11 |  | 1
2023 | National Capital Region | MARIKINA CITY | CITY OF MARIKINA (METROPOLITAN MANILA) | P00742229LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.1316 | 14.6638 | 48999922.13 | 46525054.49 | 2024 | M3 KONSTRACT CORPORATION (FORMERLY:MARGARITA CONSTRUCTION) | 4310 | 2023 | 2024-03-06 | 07/11/2023 | 2474867.64 | 0 | 2024-03-05 |  | 1
2024 | National Capital Region | TAGUIG CITY | PATEROS (METROPOLITAN MANILA) | P00821058LZ | Construction of Slope Protection Structure | 121.1318 | 14.6573 | 72374571.93 | 70890893.2 | 2024 | B. BERNARDO CONST., INC. | 4311 | 2024 | 2024-09-09 | 02/13/2024 | 1483678.73 | 0 | 2024-09-08 |  | 1
2022 | Cordillera Administrative Region | IFUGAO | LAGAWE (CAPITAL) (IFUGAO) | P00621003LZ | Construction of Flood Mitigation Structure | 121.1319 | 16.8047 | 111608777.2 | 36551362.81 | 2023 | DJY CONSTRUCTION | 4312 | 2022 | 2023-10-11 | 10/14/2022 | 75057414.39 | 0 | 2023-10-10 |  | 1
2024 | Region II | NUEVA VIZCAYA | BAMBANG (NUEVA VIZCAYA) | P00825234LZ | Construction of Flood Mitigation Structure | 121.1321 | 16.3876 | 49000000 | 49000000 | 2024 | CITRUS COUNTRY CONSTRUCTION | 4313 | 2024 | 2024-12-17 | 05/16/2024 | 0 | 0 | 2024-12-27 | 10
2023 | Region IV-A | BATANGAS | BATANGAS CITY (CAPITAL) (BATANGAS) | P00742388LZ | Construction of Flood Mitigation Structure | 121.1324 | 13.6847 | 8910000 | 8910000 | 2023 | VICMAR CONSTRUCTION, INC. | 4314 | 2023 | 2023-08-17 | 03/21/2023 | 0 | 0 | 2023-08-16 |  | 1
2023 | Region IV-B | ORIENTAL MINDORO | NAUJAN (ORIENTAL MINDORO) | P00726953LZ | Construction of Dike | 121.1325 | 13.2681 | 289499999.8 | 289497725.2 | 2023 | SUNWEST, INC. (FORMERLY: SUNWEST CONSTRUCTION & DEVELOPMENT CORPORATION) / MACROPRIME BUILDERS CORPORATION (FORMERLY: MORANTE BUILDERS & SUPPLY) | 4315 | 2023 | 2023-12-15 | 03/29/2023 | 2274.6 | 0 | 2024-04-14 | 121
2023 | Region IV-B | ORIENTAL MINDORO | NAUJAN (ORIENTAL MINDORO) | P00726954LZ | Construction of Dike | 121.1327 | 13.2679 | 289499999.8 | 289497858.2 | 2023 | SUNWEST, INC. (FORMERLY: SUNWEST CONSTRUCTION & DEVELOPMENT CORPORATION) / FGO CONSTRUCTION | 4316 | 2023 | 2023-12-15 | 03/29/2023 | 2141.6 | 0 | 2024-04-14 | 121
2022 | National Capital Region | MARIKINA CITY | CITY OF MARIKINA (METROPOLITAN MANILA) | P00620079LZ | Construction of Flood Mitigation Structure | 121.1329 | 14.6618 | 96499982.71 | 91620467.22 | 2022 | L.R. TIQUI BUILDERS, INC. | 4317 | 2022 | 2022-12-11 | 03/17/2022 | 4879515.49 | 0 | 2022-12-10 |  | 1
2022 | Cordillera Administrative Region | APAYAO | KABUGAO (CAPITAL) (APAYAO) | P00637064LZ | Construction of Flood Mitigation Structure | 121.1331 | 18.0149 | 24499413.08 | 24500000 | 2023 | OMENGAN CONSTRUCTION & DEVELOPMENT CORPORATION | 4318 | 2022 | 2023-03-28 | 04/04/2022 | 0 | 586.92 | 2022-11-09 |  | 139
2023 | Cordillera Administrative Region | APAYAO | KABUGAO (CAPITAL) (APAYAO) | P00726098LZ | Construction of Revetment | 121.1331 | 18.0149 | 49000000 | 49000000 | 2023 | PBO CONSTRUCTION COMPANY / R.S. SEPIAN CONSTRUCTION & TRUCKING | 4319 | 2023 | 2023-11-22 | 04/06/2023 | 0 | 0 | 2023-11-21 |  | 1
2022 | Region IV-A | LAGUNA | CABUYAO CITY (LAGUNA) | P00620590LZ | Construction of Revetment | 121.1336 | 14.2674 | 47168380 | 47153622.93 | 2022 | AARCON BUILDERS | 4320 | 2022 | 2022-11-28 | 02/14/2022 | 14757.07 | 0 | 2022-11-27 |  | 1
2024 | Region IV-A | RIZAL | SAN MATEO (RIZAL) | P00820298LZ | Construction of Flood Mitigation Structure | 121.1337 | 14.6531 | 144394880 | 144394880 | 2024 | DOUBLE 12 CONSTRUCTION & SUPPLY | 4321 | 2024 | 2024-07-15 | 02/07/2024 | 0 | 0 | 2025-03-01 | 229
2022 | Region IV-A | RIZAL | TAYTAY (RIZAL) | P00620255LZ | Construction of Flood Mitigation Structure | 121.1341 | 14.5366 | 57900000 | 57898640.09 | 2022 | C.F. TRINIDAD CONSTRUCTION AND SUPPLIES CORP. (FOR | 4322 | 2022 | 2022-10-03 | 03/08/2022 | 1359.91 | 0 | 2022-10-02 |  | 1
2024 | Region IV-A | RIZAL | TAYTAY (RIZAL) | P00820935LZ | Construction of Flood Mitigation Structure | 121.1341 | 14.5367 | 29400000 | 29399971.73 | 2024 | E.L. ANOLIN CONSTRUCTION | 4323 | 2024 | 2024-05-28 | 02/20/2024 | 28.27 | 0 | 2024-06-17 | 20
2022 | Region IV-A | RIZAL | TAYTAY (RIZAL) | P00620646LZ | Construction of Flood Mitigation Structure | 121.1342 | 14.5365 | 19600000 | 19599936.38 | 2022 | D.R. ROBLES CONSTRUCTION | 4324 | 2022 | 2022-08-24 | 03/28/2022 | 63.62 | 0 | 2022-08-23 |  | 1
2024 | Region IV-A | LAGUNA | CABUYAO CITY (LAGUNA) | P00839620LZ | Construction of Drainage Structure | 121.1346 | 14.2449 | 4950000 | 4949552 | 2024 | MAR-VEL CONSTRUCTION & SUPPLY | 4325 | 2024 | 2024-07-22 | 02/12/2024 | 448 | 0 | 2024-07-24 | 2
2023 | Cordillera Administrative Region | KALINGA | LUBUAGAN (KALINGA) | P00726104LZ | Construction of Flood Mitigation Structure | 121.1346 | 17.3503 | 9800000 | 9794194.36 | 2023 | HKBT CONSTRUCTION | 4326 | 2023 | 2023-10-06 | 03/13/2023 | 5805.64 | 0 | 2023-10-06 | 0
2023 | Region IV-A | LAGUNA | CITY OF BIÃ‘AN (LAGUNA) | P00740393LZ | Construction of Slope Protection Structure | 121.084 | 14.3564 | 96500000 | 96499005.06 | 2024 | M.T. MALIUANAG CONSTRUCTION SERVICES | 4327 | 2023 | 2024-04-22 | 07/25/2023 | 994.94 | 0 | 2024-05-18 | 26
2023 | Region IV-A | RIZAL | MONTALBAN (RIZAL) | P00725841LZ | Construction of Flood Mitigation Structure | 121.1356 | 14.7369 | 48250000 | 48249216.48 | 2023 | EL-JAKE BUILDERS | 4328 | 2023 | 2023-10-10 | 02/20/2023 | 783.52 | 0 | 2023-10-09 |  | 1
2024 | Region IV-B | ORIENTAL MINDORO | NAUJAN (ORIENTAL MINDORO) | P00838538LZ | Construction of Flood Mitigation Structure | 121.2584 | 13.2746 | 48249999.99 | 48246558.99 | 2024 | MLR SOLID CONSTRUCTION AND DEVELOPMENT CORPORATION | 4329 | 2024 | 2024-07-02 | 03/02/2024 | 3441 | 0 | 2024-07-02 | 0
2024 | Region II | NUEVA VIZCAYA | BAGABAG (NUEVA VIZCAYA) | P00843256LZ | Construction of Flood Mitigation Structure | 121.2586 | 16.5709 | 91675000 | 91675000 | 2024 | DALCON CONSTRUCTION | 4330 | 2024 | 2024-07-24 | 03/08/2024 | 0 | 0 | 2025-01-18 | 178
2022 | Region IV-A | BATANGAS | LIPA CITY (BATANGAS) | P00637792LZ | Construction of Flood Mitigation Structure | 121.1357 | 13.8897 | 9900000 | 9603000 | 2022 | KENSAL RISE CONSTRUCTION | 4331 | 2022 | 2022-08-05 | 04/04/2022 | 297000 | 0 | 2022-08-04 |  | 1
2022 | Region IV-A | RIZAL | ANGONO (RIZAL) | P00620643LZ | Construction of Flood Mitigation Structure | 121.1625 | 14.535 | 19600000 | 19599984.21 | 2022 | A.J. LAVA BUILDERS CORP. (FORMERLY: A.J. LAVA BUIL | 4332 | 2022 | 2022-10-26 | 03/01/2022 | 15.79 | 0 | 2022-07-27 |  | 91
2024 | Region IV-B | ORIENTAL MINDORO | NAUJAN (ORIENTAL MINDORO) | P00838539LZ | Construction of Flood Mitigation Structure | 121.259 | 13.2645 | 48249999.99 | 48247759.16 | 2024 | MLR SOLID CONSTRUCTION AND DEVELOPMENT CORPORATION | 4333 | 2024 | 2024-07-02 | 03/02/2024 | 2240.83 | 0 | 2024-07-02 | 0
2023 | Region IV-A | RIZAL | CITY OF ANTIPOLO (RIZAL) | P00727174LZ | Construction of Flood Mitigation Structure | 121.2053 | 14.5905 | 19600000 | 19600000 | 2023 | TOP KMC CONSTRUCTION AND SUPPLY CORP. | 4334 | 2023 | 2023-08-23 | 03/27/2023 | 0 | 0 | 2023-08-22 |  | 1
2022 | Region IV-A | RIZAL | CITY OF ANTIPOLO (RIZAL) | P00620633LZ | Construction of Flood Mitigation Structure | 121.1361 | 14.6424 | 14700000 | 14699456.57 | 2022 | A.J. LAVA BUILDERS CORP. (FORMERLY: A.J. LAVA BUIL | 4335 | 2022 | 2022-10-20 | 02/23/2022 | 543.43 | 0 | 2022-10-19 |  | 1
2023 | Region IV-A | LAGUNA | CITY OF CALAMBA (LAGUNA) | P00726230LZ | Construction of Revetment | 121.1651 | 14.2157 | 44100000 | 44094608.57 | 2023 | BHENLLABIEN BUILDERS CORPORATION (FORMERLY: BHENLLABIEN BUILDERS CONSTRUCTION) | 4336 | 2023 | 2023-07-20 | 02/08/2023 | 5391.43 | 0 | 2023-09-16 | 58
2023 | Region IV-A | RIZAL | MONTALBAN (RIZAL) | P00740391LZ | Construction of Flood Mitigation Structure | 121.1655 | 14.776 | 193000000 | 192977502.4 | 2024 | ST. GERRARD CONSTRUCTION GEN. CONTRACTOR & DEVELOPMENT CORP. (FORMERLY:ST. GERRARD CONSTRUCTION) | 4337 | 2023 | 2024-06-04 | 08/10/2023 | 22497.6 | 0 | 2024-06-03 |  | 1
2022 | Region IV-A | BATANGAS | LIPA CITY (BATANGAS) | P00640552LZ | Rehabilitation / Major Repair of Drainage Structure | 121.2055 | 13.972 | 9900000 | 9603459 | 2022 | ALBANO CONSTRUCTION AND TRADING | 4338 | 2022 | 2022-08-05 | 04/04/2022 | 296541 | 0 | 2022-08-04 |  | 1
2023 | Region IV-A | RIZAL | MONTALBAN (RIZAL) | P00726256LZ | Construction of Flood Mitigation Structure | 121.1362 | 14.7198 | 49000000 | 39346719.3 | 2023 | A.J. LAVA BUILDERS CORP. (FORMERLY: A.J. LAVA BUIL | 4339 | 2023 | 2023-09-11 | 02/20/2023 | 9653280.7 | 0 | 2023-11-13 | 63
2022 | National Capital Region | MAKATI CITY | CITY OF MAKATI (METROPOLITAN MANILA) | P00620375LZ | Rehabilitation / Major Repair of Drainage Structure | 121.0613 | 14.5429 | 3920000 | 3723510.28 | 2022 | ALEXA TRADING & CONSTRUCTION | 4340 | 2022 | 2022-12-01 | 02/04/2022 | 196489.72 | 0 | 2022-11-30 |  | 1
2021 | Region IV-A | RIZAL |  | P00561570LZ | Construction of Flood Mitigation Structure | 121.3447 | 14.5792 | 1979963.98 | 1930317.07 | 2022 | GKB BUILDERS | 4341 | 2021 | 2022-12-14 | 09/05/2022 | 49646.91 | 0 | 2022-12-13 |  | 1
2022 | National Capital Region | PASIG CITY | CITY OF PASIG (METROPOLITAN MANILA) | P00620006LZ | Construction of Slope Protection Structure | 121.0841 | 14.5872 | 93099467.03 | 88395424.56 | 2023 | L.R. TIQUI BUILDERS, INC. | 4342 | 2022 | 2023-10-17 | 02/16/2022 | 4704042.47 | 0 | 2023-10-16 |  | 1
2022 | Region IV-A | LAGUNA | LOS BAÃ‘OS (LAGUNA) | P00620239LZ | Construction of Revetment | 121.2592 | 14.1871 | 86850000 | 86849261.05 | 2023 | ALPHA & OMEGA GEN. CONTRACTOR & DEVELOPMENT CORP. | 4343 | 2022 | 2023-04-22 | 02/21/2022 | 738.95 | 0 | 2023-04-21 |  | 1
2023 | Region II | NUEVA VIZCAYA | DUPAX DEL NORTE (NUEVA VIZCAYA) | P00725677LZ | Construction of Flood Mitigation Structure | 121.1655 | 16.3003 | 96500000 | 96472643.42 | 2023 | BRG CONSTRUCTION | 4344 | 2023 | 2023-09-30 | 02/10/2023 | 27356.58 | 0 | 2023-10-14 | 14
2023 | Cordillera Administrative Region | KALINGA | LUBUAGAN (KALINGA) | P00726664LZ | Construction of Flood Mitigation Structure | 121.2057 | 17.3669 | 16660000 | 16609960.78 | 2024 | HKBT CONSTRUCTION | 4345 | 2023 | 2024-02-15 | 02/21/2023 | 50039.22 | 0 | 2024-01-05 |  | 41
2024 | Region III | BULACAN | CITY OF SAN JOSE DEL MONTE (BULACAN) | P00820232LZ | Construction of Flood Mitigation Structure | 121.0617 | 14.7795 | 96499803.98 | 96498249.74 | 2024 | ROYAL CROWN MONARCH CONSTRUCTION & SUPPLIES CORP. | 4346 | 2024 | 2024-12-05 | 02/14/2024 | 1554.24 | 0 | 2024-12-04 |  | 1
2024 | Region IV-B | ORIENTAL MINDORO | NAUJAN (ORIENTAL MINDORO) | P00825248LZ | Construction of Flood Mitigation Structure | 121.1369 | 13.2311 | 49000000 | 48999973.92 | 2024 | RICH ADS CONSTRUCTION CORP. (FORMERLY RICH ADS CON / REVERE CONSTRUCTION & SUPPLY CORPORATION (FORMERLY | 4347 | 2024 | 2024-05-14 | 02/22/2024 | 26.08 | 0 | 2024-11-07 | 177
2022 | National Capital Region | QUEZON CITY | QUEZON CITY (METROPOLITAN MANILA) | P00620443LZ | Construction of Flood Mitigation Structure | 121.0845 | 14.6845 | 44100000 | 44100000 | 2023 | TUCHAR CONSTRUCTION CORP. (FORMERLY:TUCHAR CONSTRU | 4348 | 2022 | 2023-01-03 | 02/07/2022 | 0 | 0 | 2023-01-01 |  | 2
2022 | Region IV-A | RIZAL | JALA-JALA (RIZAL) | P00632919LZ | Construction of Slope Protection Structure | 121.3486 | 14.3256 | 29700000 | 29700000 | 2022 | KING EIGHT BUILDERS AND SUPPLY | 4349 | 2022 | 2022-08-12 | 02/15/2022 | 0 | 0 | 2022-08-28 | 16
2023 | Region IV-A | LAGUNA | LOS BAÃ‘OS (LAGUNA) | P00725821LZ | Construction of Revetment | 121.2595 | 14.1874 | 72375000 | 72352314.41 | 2024 | BHENLLABIEN BUILDERS CORPORATION (FORMERLY: BHENLLABIEN BUILDERS CONSTRUCTION) | 4350 | 2023 | 2024-01-12 | 02/08/2023 | 22685.59 | 0 | 2024-01-11 |  | 1
2023 | Cordillera Administrative Region | KALINGA | LUBUAGAN (KALINGA) | P00726103LZ | Construction of Flood Mitigation Structure | 121.1656 | 17.3278 | 4900000 | 4894091.75 | 2023 | SONBLESSED CONSTRUCTION AND SUPPLY | 4351 | 2023 | 2023-10-29 | 04/17/2023 | 5908.25 | 0 | 2023-08-05 |  | 85
2023 | National Capital Region | MAKATI CITY | CITY OF MAKATI (METROPOLITAN MANILA) | P00725976LZ | Construction of Drainage Structure | 121.0617 | 14.5411 | 5880000 | 5880000 | 2023 | LIZVIL CONSTRUCTION & SUPPLY | 4352 | 2023 | 2023-05-23 | 02/15/2023 | 0 | 0 | 2023-07-13 | 51
2023 | Region IV-A | LAGUNA | CITY OF CALAMBA (LAGUNA) | P00725799LZ | Construction of Flood Mitigation Structure | 121.1372 | 14.2125 | 48250000 | 47041826.24 | 2023 | JUSTBILT BUILDERS | 4353 | 2023 | 2023-10-16 | 02/28/2023 | 1208173.76 | 0 | 2023-10-15 |  | 1
2022 | Region IV-A | LAGUNA | BAY (LAGUNA) | P00631300LZ | Construction of Flood Mitigation Structure | 121.2603 | 14.1904 | 19600000 | 19599339.02 | 2023 | 11 DIAMOND EAGLE CONSTRUCTION CORPORATION (FORMERLY:11 DIAMOND EAGLE CONSTRUCTION) | 4354 | 2022 | 2023-12-11 | 01/09/2023 | 660.98 | 0 | 2024-01-11 | 31
2024 | Cordillera Administrative Region | MOUNTAIN PROVINCE | PARACELIS (MOUNTAIN PROVINCE) | P00821549LZ | Construction of Flood Mitigation Structure | 121.3497 | 17.2086 | 39200000 | 39200000 | 2025 | ED1SON DEVELOPMENT & CONSTRUCTION INC. / J.M. DAPING CONSTRUCTION SERVICES | 4355 | 2024 | 2025-03-02 | 02/15/2024 | 0 | 0 | 2025-03-01 |  | 1
2022 | Cordillera Administrative Region | KALINGA | LUBUAGAN (KALINGA) | P00621019LZ | Construction of Flood Mitigation Structure | 121.1656 | 17.3281 | 4900000 | 4605589.49 | 2022 | ROCKWELL BUILDERS | 4356 | 2022 | 2022-09-12 | 03/02/2022 | 294410.51 | 0 | 2022-05-21 |  | 114
2025 | Region IV-B | ORIENTAL MINDORO | CITY OF CALAPAN (CAPITAL) (ORIENTAL MINDORO) | P00921803LZ | Construction of Flood Mitigation Structure | 121.2058 | 13.3197 | 19600000 | 19299949.9 | 2025 | CEFF TRADING & ENGINEERING SERVICES | 4357 | 2025 | 2025-05-27 | 03/13/2025 | 300050.1 | 0 | 2025-10-13 | 139
2024 | Region IV-A | LAGUNA | CITY OF BIÃ‘AN (LAGUNA) | P00824725LZ | Construction of Flood Mitigation Structure | 121.0846 | 14.2863 | 29400000 | 29268232.7 | 2024 | MAR-VEL CONSTRUCTION & SUPPLY | 4358 | 2024 | 2024-11-18 | 03/15/2024 | 131767.3 | 0 | 2024-11-29 | 11
2022 | Region IV-A | CAVITE | CITY OF CARMONA (CAVITE) | P00644780LZ | Construction of Revetment | 121.0619 | 14.3089 | 9649964.16 | 9649872.27 | 2023 | OMNICON BUILDERS | 4359 | 2022 | 2023-06-14 | 02/21/2023 | 91.89 | 0 | 2023-06-13 |  | 1
2022 | Region IV-A | LAGUNA | CITY OF CALAMBA (LAGUNA) | P00640560LZ | Rehabilitation / Major Repair of Drainage Structure | 121.1373 | 14.174 | 7425000 | 7408126.25 | 2023 | FOURTH GENERATION T CONSTRUCTION | 4360 | 2022 | 2023-02-05 | 07/11/2022 | 16873.75 | 0 | 2023-02-04 |  | 1
2022 | Region IV-A | LAGUNA | LOS BAÃ‘OS (LAGUNA) | P00639380LZ | Construction of Flood Mitigation Structure | 121.2606 | 14.166 | 144750000 | 144748520.5 | 2023 | 515 LIFE CONSTRUCTION CORP. / V.R. PATRON BUILDERS & DEVELOPERS CORP. (PREVIOUSL | 4361 | 2022 | 2023-06-07 | 06/13/2022 | 1479.5 | 0 | 2023-06-06 |  | 1
2021 | Cordillera Administrative Region | KALINGA |  | P00525929LZ | Construction of Flood Mitigation Structure | 121.166 | 17.3869 | 2940000 | 2895749.57 | 2022 | MATAGOAN KJ BUILDERS AND ENGINEERING SERVICES | 4362 | 2021 | 2022-08-06 | 04/10/2022 | 44250.43 | 0 | 2022-08-05 |  | 1
2023 | Cordillera Administrative Region | APAYAO | KABUGAO (CAPITAL) (APAYAO) | P00726654LZ | Construction of Revetment | 121.2063 | 17.9821 | 49000000 | 49000000 | 2023 | TAGEL CORPORATION / E.C.V. CONSTRUCTION | 4363 | 2023 | 2023-09-08 | 02/19/2023 | 0 | 0 | 2023-12-20 | 103
2024 | Region IV-A | LAGUNA | CITY OF SANTA ROSA (LAGUNA) | P00820893LZ | Construction of Flood Mitigation Structure | 121.0847 | 14.2859 | 49000000 | 47946089.1 | 2024 | 11 DIAMOND EAGLE CONSTRUCTION CORPORATION (FORMERLY:11 DIAMOND EAGLE CONSTRUCTION) | 4364 | 2024 | 2024-10-13 | 02/26/2024 | 1053910.9 | 0 | 2024-10-12 |  | 1
2023 | Region IV-B | ORIENTAL MINDORO | CITY OF CALAPAN (CAPITAL) (ORIENTAL MINDORO) | P00727188LZ | Construction of Flood Mitigation Structure | 121.2069 | 13.3183 | 38600000 | 38599996.6 | 2023 | E.S.L. BUILDERS & PARTS SUPPLY | 4365 | 2023 | 2023-09-18 | 03/29/2023 | 3.4 | 0 | 2023-10-04 | 16
2022 | Region IV-A | BATANGAS | CITY OF SANTO TOMAS (BATANGAS) | P00632869LZ | Construction of Drainage Structure | 121.1377 | 14.1291 | 4950000 | 4948062.6 | 2022 | KEASCIA CONSTRUCTION & SUPPLY | 4366 | 2022 | 2022-08-02 | 02/04/2022 | 1937.4 | 0 | 2022-08-01 |  | 1
2023 | National Capital Region | TAGUIG CITY | TAGUIG CITY (METROPOLITAN MANILA) | P00742236LZ | Rehabilitation / Major Repair of Drainage Structure | 121.0619 | 14.5035 | 9799659.05 | 9309670.78 | 2023 | RGDG CONSTRUCTION | 4367 | 2023 | 2023-12-04 | 06/08/2023 | 489988.27 | 0 | 2023-12-03 |  | 1
2024 | Region II | NUEVA VIZCAYA | QUEZON (NUEVA VIZCAYA) | P00823344LZ | Construction of Flood Mitigation Structure | 121.2612 | 16.5027 | 96500000 | 96500000 | 2024 | ROAD EDGE TRADING & DEVELOPMENT SERVICES | 4368 | 2024 | 2024-08-22 | 04/02/2024 | 0 | 0 | 2025-02-15 | 177
2023 | Region II | NUEVA VIZCAYA | BAYOMBONG (CAPITAL) (NUEVA VIZCAYA) | P00726708LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.166 | 16.4806 | 47326160 | 47326160 | 2023 | ERIC VAN P. SESBRENO CONSTRUCTION / V.B. GINES CONSTRUCTION | 4369 | 2023 | 2023-09-17 | 02/13/2023 | 0 | 0 | 2023-10-16 | 29
2021 | National Capital Region | PASIG CITY |  | P00561148LZ | Construction of Flood Mitigation Structure | 121.085 | 14.609 | 7839606.24 | 7445274.05 | 2022 | DAHL CONSTRUCTION CORP. (FORMERLY: DAHL CONSTRUCTION) | 4370 | 2021 | 2022-10-26 | 02/24/2022 | 394332.19 | 0 | 2022-11-02 | 7
2024 | Region IV-B | ORIENTAL MINDORO | CITY OF CALAPAN (CAPITAL) (ORIENTAL MINDORO) | P00821604LZ | Construction of Flood Mitigation Structure | 121.2078 | 13.3175 | 29400000 | 29399981.95 | 2024 | E.S.L. BUILDERS & PARTS SUPPLY | 4371 | 2024 | 2024-04-15 | 02/08/2024 | 18.05 | 0 | 2024-10-05 | 173
2022 | Region IV-A | RIZAL | CITY OF ANTIPOLO (RIZAL) | P00620257LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.1384 | 14.6071 | 93122500 | 93122063.22 | 2023 | A.J. LAVA BUILDERS CORP. (FORMERLY: A.J. LAVA BUIL / BELL CONSTRUCTION | 4372 | 2022 | 2023-03-26 | 03/02/2022 | 436.78 | 0 | 2023-03-25 |  | 1
2023 | National Capital Region | TAGUIG CITY | TAGUIG CITY (METROPOLITAN MANILA) | P00740503LZ | Construction of Drainage Structure | 121.062 | 14.505 | 48999969.67 | 46549971.18 | 2024 | ROTAFLEX CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY:ROTA FLEX CONSTRUCTION) | 4373 | 2023 | 2024-02-26 | 06/05/2023 | 2449998.49 | 0 | 2024-02-28 | 2
2022 | Region IV-A | RIZAL | CITY OF ANTIPOLO (RIZAL) | P00620649LZ | Rehabilitation / Major Repair of Slope Protection Structure | 121.2613 | 14.6256 | 49000000 | 48999785.01 | 2023 | ST. TIMOTHY CONSTRUCTION CORPORATION | 4374 | 2022 | 2023-03-12 | 02/16/2022 | 214.99 | 0 | 2023-03-11 |  | 1
2023 | National Capital Region | TAGUIG CITY | TAGUIG CITY (METROPOLITAN MANILA) | P00725520LZ | Construction of Slope Protection Structure | 121.062 | 14.505 | 91674552.46 | 87090824.84 | 2023 | FRANZCOR TRADING & CONSTRUCTION | 4375 | 2023 | 2023-11-15 | 05/05/2023 | 4583727.62 | 0 | 2023-12-29 | 44
2022 | Region IV-A | LAGUNA | SAN PABLO CITY (LAGUNA) | P00620591LZ | Construction of Slope Protection Structure | 121.3498 | 14.0763 | 43120000 | 43120000 | 2023 | MORTAR MASTERS & CONCRETE BUILDERS | 4376 | 2022 | 2023-03-24 | 01/28/2022 | 0 | 0 | 2023-03-23 |  | 1
2024 | Region II | NUEVA VIZCAYA | BAYOMBONG (CAPITAL) (NUEVA VIZCAYA) | P00825236LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.166 | 16.4806 | 49000000 | 49000000 | 2024 | DALCON CONSTRUCTION | 4377 | 2024 | 2024-05-15 | 02/13/2024 | 0 | 0 | 2024-09-29 | 137
2023 | Cordillera Administrative Region | APAYAO | KABUGAO (CAPITAL) (APAYAO) | P00726653LZ | Construction of Revetment | 121.2078 | 17.9837 | 49000000 | 49000000 | 2023 | CMG JR. BUILDERS / PRIME MASTER CONST. AND DEV'T. CORP. | 4378 | 2023 | 2023-12-07 | 04/06/2023 | 0 | 0 | 2024-02-17 | 72
2022 | Region IV-A | RIZAL | MONTALBAN (RIZAL) | P00639375LZ | Construction of Flood Mitigation Structure | 121.1386 | 14.7364 | 96500000 | 94464205.36 | 2023 | KAEL CONSTRUCTION AND SUPPLY | 4379 | 2022 | 2023-03-27 | 10/12/2022 | 2035794.64 | 0 | 2023-09-20 | 177
2022 | Cordillera Administrative Region | MOUNTAIN PROVINCE | NATONIN (MOUNTAIN PROVINCE) | P00620483LZ | Construction of Drainage Structure | 121.2614 | 17.0967 | 34300000 | 34300000 | 2023 | MG SAMIDAN CONSTRUCTION | 4380 | 2022 | 2023-04-13 | 05/26/2022 | 0 | 0 | 2023-02-28 |  | 44
2023 | National Capital Region | CALOOCAN CITY | CALOOCAN CITY (METROPOLITAN MANILA) | P00727013LZ | Construction of Flood Mitigation Structure | 121.0622 | 14.7621 | 48989301.01 | 47813558.33 | 2023 | JAGONBUILD CONSTRUCTION CORP. (FOR. JAGON BUILDERS | 4381 | 2023 | 2023-12-27 | 06/07/2023 | 1175742.68 | 0 | 2024-01-01 | 5
2024 | National Capital Region | PASIG CITY | CITY OF PASIG (METROPOLITAN MANILA) | P00824591LZ | Rehabilitation / Major Repair of Drainage Structure | 121.0853 | 14.5591 | 19599818.2 | 19198671.1 | 2024 | EDELSONS BUILDERS INC. | 4382 | 2024 | 2024-11-16 | 04/08/2024 | 401147.1 | 0 | 2024-11-15 |  | 1
2023 | Region IV-A | LAGUNA | LOS BAÃ‘OS (LAGUNA) | P00725788LZ | Construction of Flood Mitigation Structure | 121.2616 | 14.1714 | 154400000 | 154399847.9 | 2024 | D.L CERVANTES CONSTRUCTION CORPORATION (FORMERLY: / TRIPLE EAGLE CONSTRUCTION AND TRADING | 4383 | 2023 | 2024-06-22 | 03/31/2023 | 152.1 | 0 | 2024-06-21 |  | 1
2023 | National Capital Region | CALOOCAN CITY | CALOOCAN CITY (METROPOLITAN MANILA) | P00727014LZ | Construction of Flood Mitigation Structure | 121.0622 | 14.7621 | 48994208.21 | 47842662.41 | 2023 | IM CONSTRUCTION CORPORATION | 4384 | 2023 | 2023-11-06 | 06/07/2023 | 1151545.8 | 0 | 2024-01-01 | 56
2023 | Region IV-A | BATANGAS | SAN JUAN (BATANGAS) | P00727371LZ | Construction of Flood Mitigation Structure | 121.3507 | 13.8271 | 49000000 | 49000000 | 2023 | LOUREL DEVELOPMENT CORPORATION (FORMERLY :LOUREL D | 4385 | 2023 | 2023-09-18 | 03/11/2023 | 0 | 0 | 2023-10-01 | 13
2022 | Region IV-B | ORIENTAL MINDORO | NAUJAN (ORIENTAL MINDORO) | P00621112LZ | Construction of Flood Mitigation Structure | 121.1661 | 13.1336 | 49000000 | 48999957.5 | 2022 | ALBERTO UY CONSTRUCTION & DEVELOPMENT | 4386 | 2022 | 2022-12-09 | 05/23/2022 | 42.5 | 0 | 2023-01-03 | 25
2022 | Region IV-A | BATANGAS | LOBO (BATANGAS) | P00631285LZ | Construction of Flood Mitigation Structure | 121.2086 | 13.6394 | 49000000 | 49000000 | 2023 | TCSC CORP. / EFREN RAMIREZ CONSTRUCTION AND GENERAL SERVICES CORPORATION | 4387 | 2022 | 2023-01-02 | 01/28/2022 | 0 | 0 | 2023-01-01 |  | 1
2022 | Region IV-A | RIZAL | TAYTAY (RIZAL) | P00620639LZ | Construction of Slope Protection Structure | 121.1391 | 14.5337 | 29400000 | 27343115.77 | 2022 | C.F. TRINIDAD CONSTRUCTION AND SUPPLIES CORP. (FOR | 4388 | 2022 | 2022-09-26 | 04/06/2022 | 2056884.23 | 0 | 2022-10-31 | 35
2024 | Region II | NUEVA VIZCAYA | QUEZON (NUEVA VIZCAYA) | P00823343LZ | Construction of Flood Mitigation Structure | 121.2619 | 16.5033 | 96500000 | 96500000 | 2024 | V.B. MANUBAY CONSTRUCTION | 4389 | 2024 | 2024-07-15 | 03/25/2024 | 0 | 0 | 2025-02-10 | 210
2022 | Region IV-A | BATANGAS | SAN JUAN (BATANGAS) | P00621093LZ | Construction of Flood Mitigation Structure | 121.3511 | 13.827 | 28420000 | 27569128 | 2022 | FIVE TRAVELLERS CONSTRUCTION INC. | 4390 | 2022 | 2022-08-07 | 02/10/2022 | 850872 | 0 | 2022-08-06 |  | 1
2023 | Region IV-A | LAGUNA | CITY OF CALAMBA (LAGUNA) | P00725819LZ | Construction of Flood Mitigation Structure | 121.167 | 14.2256 | 86850000 | 84765670 | 2024 | MSV CONSTRUCTION AND SUPPLIES | 4391 | 2023 | 2024-02-08 | 02/08/2023 | 2084330 | 0 | 2024-02-07 |  | 1
2023 | Region III | BULACAN | CITY OF SAN JOSE DEL MONTE (BULACAN) | P00725718LZ | Construction of Flood Mitigation Structure | 121.0624 | 14.8315 | 96499232.45 | 96497180.56 | 2023 | TRIPLE 8 CONSTRUCTION & SUPPLY, INC. (FORMERLY TRIPLE 8 CONST. & SUPPLY) | 4392 | 2023 | 2023-12-29 | 03/01/2023 | 2051.89 | 0 | 2023-12-28 |  | 1
2023 | Region II | NUEVA VIZCAYA | BAMBANG (NUEVA VIZCAYA) | P00726142LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.0859 | 16.3964 | 49000000 | 49000000 | 2023 | J.E.L. CONSTRUCTION & SUPPLY | 4393 | 2023 | 2023-08-20 | 02/15/2023 | 0 | 0 | 2023-10-20 | 61
2024 | Region IV-A | RIZAL | BINANGONAN (RIZAL) | P00839647LZ | Construction of Slope Protection Structure | 121.21 | 14.4781 | 4950000 | 4949917.86 | 2024 | FRANZCOR TRADING & CONSTRUCTION | 4394 | 2024 | 2024-03-25 | 03/04/2024 | 82.14 | 0 | 2024-04-14 | 20
2023 | Region IV-A | LAGUNA | LOS BAÃ‘OS (LAGUNA) | P00736028LZ | Construction of Flood Mitigation Structure | 121.2639 | 14.1734 | 96500000 | 96499864.97 | 2024 | 11 DIAMOND EAGLE CONSTRUCTION CORPORATION (FORMERLY:11 DIAMOND EAGLE CONSTRUCTION) | 4395 | 2023 | 2024-01-05 | 04/11/2023 | 135.03 | 0 | 2024-01-04 |  | 1
2024 | Region III | NUEVA ECIJA | BONGABON (NUEVA ECIJA) | P00846000LZ | Construction of Flood Mitigation Structure | 121.1392 | 15.6003 | 5879917.65 | 5791723.38 | 2024 | JERRY R. SANTIAGO CONSTRUCTION CORP. (FORMERLY: JERRY SANTIAGO CONSTRUCTION) | 4396 | 2024 | 2024-10-15 | 06/04/2024 | 88194.27 | 0 | 2024-10-15 | 0
2024 | Region IV-B | ORIENTAL MINDORO | GLORIA (ORIENTAL MINDORO) | P00825249LZ | Construction of Flood Mitigation Structure | 121.3516 | 12.3822 | 49000000 | 48997248.42 | 2024 | LUMEL GLENN CONSTRUCTION | 4397 | 2024 | 2024-12-04 | 03/04/2024 | 2751.58 | 0 | 2024-12-03 |  | 1
2023 | Region III | BULACAN | CITY OF SAN JOSE DEL MONTE (BULACAN) | P00725717LZ | Construction of Flood Mitigation Structure | 121.0624 | 14.7757 | 96499459.47 | 96498078.58 | 2024 | ROYAL CROWN MONARCH CONSTRUCTION & SUPPLIES CORP. | 4398 | 2023 | 2024-01-18 | 03/01/2023 | 1380.89 | 0 | 2024-02-26 | 39
2019 | National Capital Region | MARIKINA CITY |  | P00320013LZ | Construction of Drainage Structure | 121.0863 | 14.6324 | 94953904.49 | 94907798.15 | 2022 | C.S.L. CONSTRUCTION CORPORATION / ST. TIMOTHY CONSTRUCTION CORPORATION | 4399 | 2019 | 2022-11-25 | 11/21/2019 | 46106.34 | 0 | 2022-11-24 |  | 1
2022 | National Capital Region | TAGUIG CITY | TAGUIG CITY (METROPOLITAN MANILA) | P00620021LZ | Construction of Drainage Structure | 121.0625 | 14.505 | 72374547.54 | 70930048.4 | 2024 | NEWBIG FOUR J CONSTRUCTION INC., (FORMERLY FOUR J | 4400 | 2022 | 2024-01-12 | 03/21/2022 | 1444499.14 | 0 | 2023-10-13 |  | 91
2023 | Region IV-A | RIZAL | BINANGONAN (RIZAL) | P00737531LZ | Construction of Flood Mitigation Structure | 121.211 | 14.4202 | 9900000 | 9899996.75 | 2023 | E.L. ANOLIN CONSTRUCTION | 4401 | 2023 | 2023-08-16 | 03/20/2023 | 3.25 | 0 | 2023-08-15 |  | 1
2023 | Region IV-A | RIZAL | SAN MATEO (RIZAL) | P00737535LZ | Construction of Flood Mitigation Structure | 121.1399 | 14.71 | 4950000 | 4950000 | 2023 | 22 PRIME CONSTRUCTION AND REALTY DEVELOPMENT INC. | 4402 | 2023 | 2023-10-01 | 05/10/2023 | 0 | 0 | 2023-09-30 |  | 1
2023 | Region III | NUEVA ECIJA | BONGABON (NUEVA ECIJA) | P00726172LZ | Construction of Flood Mitigation Structure | 121.2642 | 15.6447 | 48999974.43 | 48990841.52 | 2023 | CELSO C. FERRER CONSTRUCTION CORP. | 4403 | 2023 | 2023-10-27 | 02/10/2023 | 9132.91 | 0 | 2023-11-04 | 8
2023 | Region IV-A | RIZAL | CITY OF ANTIPOLO (RIZAL) | P00726249LZ | Construction of Flood Mitigation Structure | 121.1671 | 14.6153 | 29400000 | 29400000 | 2024 | STREAMLINE BUILDERS CORPORATION | 4404 | 2023 | 2024-01-04 | 04/10/2023 | 0 | 0 | 2024-01-03 |  | 1
2022 | Region IV-A | LAGUNA | CITY OF BIÃ‘AN (LAGUNA) | P00621463LZ | Construction of Flood Mitigation Structure | 121.0863 | 14.3424 | 49000000 | 48930644.27 | 2023 | ALPHA & OMEGA GEN. CONTRACTOR & DEVELOPMENT CORP. | 4405 | 2022 | 2023-12-23 | 08/08/2022 | 69355.73 | 0 | 2024-05-24 | 153
2024 | Region IV-B | ORIENTAL MINDORO | BULALACAO (SAN PEDRO) (ORIENTAL MINDORO) | P00844781LZ | Construction of Flood Mitigation Structure | 121.3516 | 12.3822 | 29400000 | 29397112.52 | 2024 | D.M. MALIWANAG BUILDERS AND ENTERPRISES | 4406 | 2024 | 2024-09-19 | 04/03/2024 | 2887.48 | 0 | 2024-10-25 | 36
2024 | Region III | BULACAN | CITY OF SAN JOSE DEL MONTE (BULACAN) | P00844754LZ | Construction of Slope Protection Structure | 121.0625 | 14.8497 | 48999992.68 | 48989112.33 | 2024 | ROYAL CROWN MONARCH CONSTRUCTION & SUPPLIES CORP. | 4407 | 2024 | 2024-12-17 | 04/30/2024 | 10880.35 | 0 | 2024-12-28 | 11
2024 | Region II | NUEVA VIZCAYA | BAGABAG (NUEVA VIZCAYA) | P00821178LZ | Construction of Flood Mitigation Structure | 121.2648 | 16.5901 | 144750000 | 144750000 | 2025 | EGB CONSTRUCTION CORPORATION (FORMERLY: EGB CONSTRUCTION) | 4408 | 2024 | 2025-04-11 | 02/16/2024 | 0 | 0 | 2025-04-10 |  | 1
2021 | Region IV-A | RIZAL |  | P00561800LZ | Construction of Flood Mitigation Structure | 121.1403 | 14.755 | 35640000 | 29700000 | 2022 | DOUBLE 12 CONSTRUCTION & SUPPLY | 4409 | 2021 | 2022-12-15 | 09/05/2022 | 5940000 | 0 | 2023-03-02 | 77
2023 | Region IV-A | BATANGAS | CITY OF SANTO TOMAS (BATANGAS) | P00726205LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.1673 | 14.0949 | 29400000 | 29398381.6 | 2023 | VAN MAKJAY CONSTRUCTION | 4410 | 2023 | 2023-10-11 | 03/10/2023 | 1618.4 | 0 | 2023-12-03 | 53
2024 | Region IV-A | LAGUNA | CITY OF CALAMBA (LAGUNA) | P00846067LZ | Construction of Drainage Structure | 121.1405 | 14.2006 | 4950000 | 4836150 | 2024 | DATZLAV CONSTRUCTION | 4411 | 2024 | 2024-08-18 | 03/22/2024 | 113850 | 0 | 2024-08-17 |  | 1
2023 | Region IV-B | ORIENTAL MINDORO | BULALACAO (SAN PEDRO) (ORIENTAL MINDORO) | P00740430LZ | Construction of Flood Mitigation Structure | 121.352 | 12.3842 | 202649905.8 | 202647244.3 | 2023 | AMETHYST HORIZON BUILDERS AND GEN. CONTRACTOR AND DEVELOPMENT CORP. | 4412 | 2023 | 2023-12-10 | 04/13/2023 | 2661.5 | 0 | 2024-04-05 | 117
2023 | National Capital Region | PASIG CITY | CITY OF PASIG (METROPOLITAN MANILA) | P00725965LZ | Rehabilitation / Major Repair of Drainage Structure | 121.0864 | 14.5614 | 6859264.48 | 6514929.4 | 2023 | ANDREW LOUIS CONSTRUCTION AND TRADING | 4413 | 2023 | 2023-05-06 | 02/06/2023 | 344335.08 | 0 | 2023-05-05 |  | 1
2023 | Region III | BULACAN | CITY OF SAN JOSE DEL MONTE (BULACAN) | P00725720LZ | Construction of Flood Mitigation Structure | 121.0625 | 14.7756 | 96499928.13 | 96498410.9 | 2024 | ROYAL CROWN MONARCH CONSTRUCTION & SUPPLIES CORP. | 4414 | 2023 | 2024-02-27 | 03/01/2023 | 1517.23 | 0 | 2024-02-26 |  | 1
2023 | Region IV-A | RIZAL | MORONG (RIZAL) | P00742448LZ | Construction of Slope Protection Structure | 121.2121 | 14.5122 | 4950000 | 4950000 | 2023 | GKB BUILDERS | 4415 | 2023 | 2023-08-12 | 05/11/2023 | 0 | 0 | 2023-08-26 | 14
2024 | Region II | NUEVA VIZCAYA | BAGABAG (NUEVA VIZCAYA) | P00821183LZ | Construction of Flood Mitigation Structure | 121.2649 | 16.5902 | 144750000 | 144750000 | 2025 | EGB CONSTRUCTION CORPORATION (FORMERLY: EGB CONSTRUCTION) | 4416 | 2024 | 2025-04-10 | 02/21/2024 | 0 | 0 | 2025-04-09 |  | 1
2023 | Region IV-B | ORIENTAL MINDORO | CITY OF CALAPAN (CAPITAL) (ORIENTAL MINDORO) | P00742455LZ | Construction of Drainage Structure | 121.1675 | 13.4003 | 4950000 | 4948415.62 | 2023 | E.S.L. BUILDERS & PARTS SUPPLY | 4417 | 2023 | 2023-06-26 | 03/28/2023 | 1584.38 | 0 | 2023-08-08 | 43
2022 | Region IV-A | BATANGAS | LIPA CITY (BATANGAS) | P00640545LZ | Construction of Drainage Structure | 121.1405 | 13.9298 | 24750000 | 24007500 | 2022 | KENSAL RISE CONSTRUCTION | 4418 | 2022 | 2022-10-10 | 04/04/2022 | 742500 | 0 | 2022-10-09 |  | 1
2022 | Cordillera Administrative Region | APAYAO | CALANASAN (BAYAG) (APAYAO) | P00620990LZ | Construction of Flood Mitigation Structure | 121.0864 | 18.5372 | 49000000 | 47169843.01 | 2023 | ASC CONSTRUCTION & CONCRETE PRODUCTS | 4419 | 2022 | 2023-11-15 | 08/09/2022 | 1830156.99 | 0 | 2023-04-24 |  | 205
2022 | Region III | BULACAN | CITY OF SAN JOSE DEL MONTE (BULACAN) | P00637028LZ | Construction of Flood Mitigation Structure | 121.0626 | 14.8522 | 96499638.45 | 95051178.88 | 2023 | TRIPLE 8 CONSTRUCTION & SUPPLY, INC. (FORMERLY TRIPLE 8 CONST. & SUPPLY) | 4420 | 2022 | 2023-04-25 | 05/26/2022 | 1448459.57 | 0 | 2023-04-24 |  | 1
2024 | Region II | NUEVA VIZCAYA | SOLANO (NUEVA VIZCAYA) | P00821180LZ | Construction of Flood Mitigation Structure | 121.2124 | 16.5023 | 144750000 | 144750000 | 2024 | EGB CONSTRUCTION CORPORATION (FORMERLY: EGB CONSTRUCTION) | 4421 | 2024 | 2024-05-21 | 02/16/2024 | 0 | 0 | 2025-01-24 | 248
2022 | Region IV-A | LAGUNA | LOS BAÃ‘OS (LAGUNA) | P00620238LZ | Construction of Revetment | 121.2652 | 14.1797 | 86850000 | 86813738.33 | 2022 | BHENLLABIEN BUILDERS CORPORATION (FORMERLY: BHENLLABIEN BUILDERS CONSTRUCTION) | 4422 | 2022 | 2022-11-18 | 04/04/2022 | 36261.67 | 0 | 2023-02-02 | 76
2022 | Region IV-A | LAGUNA | CITY OF BIÃ‘AN (LAGUNA) | P00621462LZ | Construction of Flood Mitigation Structure | 121.0865 | 14.3459 | 49000000 | 48994674.47 | 2023 | STRUKTURA TEKNIKA SERVICES CO. / ST. MATTHEW GEN. CONTRACTOR & DEVELOPMENT CORP. | 4423 | 2022 | 2023-12-23 | 08/22/2022 | 5325.53 | 0 | 2024-06-07 | 167
2023 | Region II | CAGAYAN | PAMPLONA (CAGAYAN) | P00740573LZ | Construction of Flood Mitigation Structure | 121.3539 | 18.4963 | 19600000 | 19600000 | 2024 | OLIVA DESIGN AND CONSTRUCTION | 4424 | 2023 | 2024-01-31 | 04/27/2023 | 0 | 0 | 2023-11-19 |  | 73
2023 | Region IV-A | BATANGAS | IBAAN (BATANGAS) | P00742397LZ | Construction of Drainage Structure | 121.1675 | 13.8216 | 4950000 | 4801678.25 | 2023 | MAC BUILDERS CIVIL ENGINEERING CONSTRUCTION | 4425 | 2023 | 2023-07-07 | 04/02/2023 | 148321.75 | 0 | 2023-07-29 | 22
2022 | Region IV-A | RIZAL | MONTALBAN (RIZAL) | P00621102LZ | Construction of Flood Mitigation Structure | 121.1406 | 14.7364 | 49000000 | 48509990.21 | 2022 | STO. CRISTO CONSTRUCTION & TRADING INC. (FOR: STO. CRISTO CONSTRUCTION & TRADING) | 4426 | 2022 | 2022-11-07 | 02/16/2022 | 490009.79 | 0 | 2022-11-27 | 20
2023 | Region III | BULACAN | CITY OF SAN JOSE DEL MONTE (BULACAN) | P00725721LZ | Construction of Flood Mitigation Structure | 121.0626 | 14.829 | 96499375.83 | 96497264.42 | 2023 | TRIPLE 8 CONSTRUCTION & SUPPLY, INC. (FORMERLY TRIPLE 8 CONST. & SUPPLY) | 4427 | 2023 | 2023-12-29 | 03/01/2023 | 2111.41 | 0 | 2023-12-28 |  | 1
2024 | Region IV-A | RIZAL | TERESA (RIZAL) | P00820317LZ | Construction of Flood Mitigation Structure | 121.2131 | 14.5719 | 91675000 | 91675000 | 2025 | A.M. ORETA & CO., INC. | 4428 | 2024 | 2025-02-11 | 05/09/2024 | 0 | 0 | 2025-03-14 | 31
2024 | Region II | NUEVA VIZCAYA | BAGABAG (NUEVA VIZCAYA) | P00821181LZ | Construction of Flood Mitigation Structure | 121.2653 | 16.6375 | 144750000 | 144750000 | 2024 | EGB CONSTRUCTION CORPORATION (FORMERLY: EGB CONSTRUCTION) | 4429 | 2024 | 2024-05-21 | 02/16/2024 | 0 | 0 | 2025-02-14 | 269
2023 | National Capital Region | PASIG CITY | CITY OF PASIG (METROPOLITAN MANILA) | P00725964LZ | Rehabilitation / Major Repair of Drainage Structure | 121.0867 | 14.5572 | 8329756.25 | 7910500 | 2023 | JAGONBUILD CONSTRUCTION CORP. (FOR. JAGON BUILDERS | 4430 | 2023 | 2023-07-05 | 02/06/2023 | 419256.25 | 0 | 2023-07-04 |  | 1
2023 | Region IV-A | BATANGAS | SAN JUAN (BATANGAS) | P00742402LZ | Construction of Slope Protection Structure | 121.3583 | 13.658 | 7920000 | 7682785 | 2023 | MEGAJES CONSTRUCTION CORP. | 4431 | 2023 | 2023-07-03 | 03/30/2023 | 237215 | 0 | 2023-06-11 |  | 22
2021 | Cordillera Administrative Region | KALINGA |  | P00525938LZ | Construction of Drainage Structure | 121.1678 | 17.4931 | 1960000 | 1905025.19 | 2023 | BHM CONSTRUCTION | 4432 | 2021 | 2023-08-22 | 03/24/2022 | 54974.81 | 0 | 2022-08-05 |  | 382
2023 | Region IV-A | BATANGAS | BATANGAS CITY (CAPITAL) (BATANGAS) | P00742389LZ | Construction of Flood Mitigation Structure | 121.1406 | 13.6472 | 49500000 | 49500000 | 2023 | EFREN RAMIREZ CONSTRUCTION AND GENERAL SERVICES CORPORATION | 4433 | 2023 | 2023-11-21 | 04/20/2023 | 0 | 0 | 2023-11-20 |  | 1
2023 | National Capital Region | QUEZON CITY | QUEZON CITY (METROPOLITAN MANILA) | P00726026LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.0626 | 14.6293 | 8961988.88 | 8631549 | 2024 | ZALI CONSTRUCTION, INC. | 4434 | 2023 | 2024-06-24 | 02/15/2023 | 330439.88 | 0 | 2023-07-24 |  | 336
2023 | National Capital Region | MARIKINA CITY | CITY OF MARIKINA (METROPOLITAN MANILA) | P00742238LZ | Rehabilitation / Major Repair of Drainage Structure | 121.0868 | 14.6292 | 29397904.21 | 27933956.18 | 2024 | BELL CONSTRUCTION | 4435 | 2023 | 2024-01-03 | 05/04/2023 | 1463948.03 | 0 | 2024-01-02 |  | 1
2023 | Region IV-A | RIZAL | BINANGONAN (RIZAL) | P00737532LZ | Construction of Flood Mitigation Structure | 121.2133 | 14.4288 | 9900000 | 9899996.95 | 2024 | JEBRON BUILDERS DEVELOPMENT CORPORATION | 4436 | 2023 | 2024-02-26 | 03/27/2023 | 3.05 | 0 | 2024-03-19 | 22
2021 | Region IV-A | RIZAL |  | P00526134LZ | Construction of Flood Mitigation Structure | 121.1679 | 14.4992 | 19600000 | 19599999.07 | 2022 | DOUBLE 12 CONSTRUCTION & SUPPLY | 4437 | 2021 | 2022-09-19 | 03/24/2022 | 0.93 | 0 | 2022-08-19 |  | 31
2021 | Region II | NUEVA VIZCAYA |  | P00561682LZ | Construction of Flood Mitigation Structure | 121.0873 | 16.3393 | 24750000 | 24750000 | 2022 | M.R. VARGAS CONSTRUCTION CORPORATION (FORMERLY: M.R. VARGAS CONSTRUCTION) | 4438 | 2021 | 2022-09-15 | 01/27/2022 | 0 | 0 | 2022-10-06 | 21
2021 | Region IV-A | RIZAL |  | P00561558LZ | Construction of Flood Mitigation Structure | 121.1407 | 14.7259 | 30591000 | 29702033.61 | 2022 | ST. TIMOTHY CONSTRUCTION CORPORATION | 4439 | 2021 | 2022-08-18 | 12/20/2021 | 888966.39 | 0 | 2022-08-17 |  | 1
2024 | Region II | NUEVA VIZCAYA | BAGABAG (NUEVA VIZCAYA) | P00843254LZ | Construction of Flood Mitigation Structure | 121.2665 | 16.5849 | 89745000 | 89745000 | 2024 | DALCON CONSTRUCTION | 4440 | 2024 | 2024-07-24 | 03/08/2024 | 0 | 0 | 2025-01-26 | 186
2023 | National Capital Region | QUEZON CITY | QUEZON CITY (METROPOLITAN MANILA) | P00727028LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.0627 | 14.6275 | 4899360.63 | 4851553.48 | 2023 | E.L. TORRES CONSTRUCTION AND TRADING INC. (FORMERLY : E. L. TORRES CONSTRUCTION & TRADING | 4441 | 2023 | 2023-11-30 | 03/29/2023 | 47807.15 | 0 | 2023-12-07 | 7
2024 | Region IV-A | BATANGAS | LIPA CITY (BATANGAS) | P00846045LZ | Construction of Drainage Structure | 121.2145 | 13.9143 | 4950000 | 4800175.78 | 2024 | MEL JEAN CONSTRUCTION CORPORATION | 4442 | 2024 | 2024-10-01 | 05/31/2024 | 149824.22 | 0 | 2024-09-01 |  | 30
2023 | Region IV-A | LAGUNA | CITY OF CALAMBA (LAGUNA) | P00726225LZ | Construction of Flood Mitigation Structure | 121.1688 | 14.2333 | 43531600 | 42200389 | 2023 | PASCAL CONSTRUCTION | 4443 | 2023 | 2023-09-17 | 02/08/2023 | 1331211 | 0 | 2023-09-16 |  | 1
2023 | National Capital Region | PASIG CITY | CITY OF PASIG (METROPOLITAN MANILA) | P00725953LZ | Rehabilitation / Major Repair of Drainage Structure | 121.0874 | 14.5569 | 39199344.7 | 37224156.95 | 2023 | DAHL CONSTRUCTION CORP. (FORMERLY: DAHL CONSTRUCTION) | 4444 | 2023 | 2023-10-03 | 02/06/2023 | 1975187.75 | 0 | 2023-10-02 |  | 1
2021 | Region IV-A | RIZAL |  | P00561573LZ | Construction of Flood Mitigation Structure | 121.3587 | 14.6608 | 1979910.41 | 1929947.64 | 2022 | JG NORA BUILDERS | 4445 | 2021 | 2022-12-14 | 09/05/2022 | 49962.77 | 0 | 2022-12-13 |  | 1
2022 | Cordillera Administrative Region | APAYAO | CONNER (APAYAO) | P00620472LZ | Construction of Flood Mitigation Structure | 121.2678 | 17.8239 | 15678924.68 | 15680000 | 2022 | BAHRAMLEY CONSTRUCTION | 4446 | 2022 | 2022-12-22 | 03/01/2022 | 0 | 1075.32 | 2022-12-24 | 2
2024 | Region IV-B | ORIENTAL MINDORO | CITY OF CALAPAN (CAPITAL) (ORIENTAL MINDORO) | P00845838LZ | Construction of Flood Mitigation Structure | 121.1414 | 13.4047 | 67550000 | 67549998.51 | 2025 | ARCONIC INC. | 4447 | 2024 | 2025-02-24 | 02/22/2024 | 1.49 | 0 | 2025-03-05 | 9
2023 | Region IV-B | OCCIDENTAL MINDORO | CALINTAAN (OCCIDENTAL MINDORO) | P00726597LZ | Construction of Flood Mitigation Structure | 121.0629 | 12.6188 | 49215000 | 49212877.23 | 2023 | GREAT PACIFIC BUILDERS AND GEN. CONTRACTOR INC. / MICKU ROBIN CONSTRUCTION | 4448 | 2023 | 2023-10-22 | 02/10/2023 | 2122.77 | 0 | 2023-10-21 |  | 1
2022 | Region IV-A | RIZAL | TERESA (RIZAL) | P00620215LZ | Construction of Flood Mitigation Structure | 121.2156 | 14.5556 | 77200000 | 77200000 | 2023 | HONY TRADING & CONSTRUCTION / JOAN AND JOHN CONSTRUCTION AND TRADING | 4449 | 2022 | 2023-09-06 | 03/07/2022 | 0 | 0 | 2023-09-05 |  | 1
2023 | Cordillera Administrative Region | IFUGAO | KIANGAN (IFUGAO) | P00742288LZ | Construction of Flood Mitigation Structure | 121.0875 | 16.7702 | 4945128.34 | 4865109.77 | 2024 | MSMV CONSTRUCTION AND SUPPLY | 4450 | 2023 | 2024-11-10 | 08/09/2023 | 80018.57 | 0 | 2023-11-27 |  | 349
2023 | Region IV-A | BATANGAS | SAN JUAN (BATANGAS) | P00742401LZ | Construction of Drainage Structure | 121.3595 | 13.8352 | 4950000 | 4801978.98 | 2023 | JSAM CONSTRUCTION | 4451 | 2023 | 2023-10-04 | 03/30/2023 | 148021.02 | 0 | 2023-07-26 |  | 70
2022 | Cordillera Administrative Region | APAYAO | CONNER (APAYAO) | P00620988LZ | Construction of Flood Mitigation Structure | 121.2678 | 17.8239 | 23519997.48 | 22928490.31 | 2022 | PRIME MASTER CONST. AND DEV'T. CORP. | 4452 | 2022 | 2022-11-02 | 02/09/2022 | 591507.17 | 0 | 2022-11-01 |  | 1
2022 | Region IV-A | BATANGAS | LOBO (BATANGAS) | P00620864LZ | Construction of Flood Mitigation Structure | 121.2159 | 13.6498 | 78469940 | 78469940 | 2023 | TCSC CORP. / EFREN RAMIREZ CONSTRUCTION AND GENERAL SERVICES CORPORATION | 4453 | 2022 | 2023-04-02 | 02/15/2022 | 0 | 0 | 2023-04-01 |  | 1
2024 | National Capital Region | TAGUIG CITY | TAGUIG CITY (METROPOLITAN MANILA) | P00821077LZ | Construction of Slope Protection Structure | 121.063 | 14.4902 | 96499547.45 | 94559906.54 | 2024 | TOPNOTCH CATALYST BUILDERS INC. / BEAM TEAM DEVELOPER SPECIALIST INC. | 4454 | 2024 | 2024-10-09 | 02/13/2024 | 1939640.91 | 0 | 2024-10-08 |  | 1
2021 | Region IV-A | RIZAL |  | P00561804LZ | Construction of Flood Mitigation Structure | 121.1416 | 14.7522 | 35640000 | 5940000 | 2022 | DOUBLE 12 CONSTRUCTION & SUPPLY | 4455 | 2021 | 2022-12-15 | 09/05/2022 | 29700000 | 0 | 2023-03-02 | 77
2023 | Region IV-A | BATANGAS | SAN JUAN (BATANGAS) | P00727156LZ | Construction of Flood Mitigation Structure | 121.3622 | 13.8295 | 39200000 | 39200000 | 2023 | FIVE TRAVELLERS CONSTRUCTION INC. | 4456 | 2023 | 2023-10-02 | 03/03/2023 | 0 | 0 | 2023-10-01 |  | 1
2022 | Region II | CAGAYAN | CLAVERIA (CAGAYAN) | P00621528LZ | Construction of Flood Mitigation Structure | 121.0876 | 18.5776 | 14700000 | 14700000 | 2022 | J.B. ALCANTARA BUILDERS | 4457 | 2022 | 2022-11-04 | 03/28/2022 | 0 | 0 | 2022-11-03 |  | 1
2023 | Region IV-A | BATANGAS | LOBO (BATANGAS) | P00742390LZ | Construction of Slope Protection Structure | 121.2678 | 13.6048 | 9900000 | 9900000 | 2023 | TCSC CORP. | 4458 | 2023 | 2023-06-21 | 03/21/2023 | 0 | 0 | 2023-06-23 | 2
2023 | Region IV-A | RIZAL | TERESA (RIZAL) | P00725832LZ | Construction of Flood Mitigation Structure | 121.216 | 14.573 | 67550000 | 67550000 | 2023 | HONY TRADING & CONSTRUCTION | 4459 | 2023 | 2023-11-16 | 02/10/2023 | 0 | 0 | 2023-11-15 |  | 1
2024 | Region IV-B | ORIENTAL MINDORO | CITY OF CALAPAN (CAPITAL) (ORIENTAL MINDORO) | P00823584LZ | Construction of Flood Mitigation Structure | 121.1689 | 13.4147 | 24125000 | 24124947.7 | 2024 | MARCING CONSTRUCTION SERVICES | 4460 | 2024 | 2024-12-16 | 05/20/2024 | 52.3 | 0 | 2024-12-26 | 10
2023 | Region IV-A | BATANGAS | BATANGAS CITY (CAPITAL) (BATANGAS) | P00726750LZ | Construction of Flood Mitigation Structure | 121.0632 | 13.748 | 49000000 | 49000000 | 2023 | VICMAR CONSTRUCTION, INC. | 4461 | 2023 | 2023-11-06 | 04/05/2023 | 0 | 0 | 2023-11-05 |  | 1
2024 | Cordillera Administrative Region | KALINGA | TINGLAYAN (KALINGA) | P00821563LZ | Construction of Flood Mitigation Structure | 121.1422 | 17.2594 | 8820000 | 8815139.84 | 2024 | MA BUYAGAN CONSTRUCTION SERVICES | 4462 | 2024 | 2024-08-22 | 03/14/2024 | 4860.16 | 0 | 2024-10-13 | 52
2021 | Region IV-A | RIZAL |  | P00561548LZ | Construction of Flood Mitigation Structure | 121.2681 | 14.5247 | 7920000 | 7642498.81 | 2022 | L. EUSEBIO ACE DEVELOPMENT CORPORATION | 4463 | 2021 | 2022-10-17 | 12/16/2021 | 277501.19 | 0 | 2022-10-24 | 7
2022 | Region IV-A | RIZAL | BINANGONAN (RIZAL) | P00620637LZ | Construction of Slope Protection Structure | 121.169 | 14.5005 | 47040000 | 47039965.76 | 2022 | DOUBLE 12 CONSTRUCTION & SUPPLY | 4464 | 2022 | 2022-09-20 | 02/23/2022 | 34.24 | 0 | 2022-09-19 |  | 1
2022 | Region IV-B | ORIENTAL MINDORO | BONGABONG (ORIENTAL MINDORO) | P00632940LZ | Construction of Slope Protection Structure | 121.3656 | 12.6914 | 6929851.07 | 6666333.87 | 2022 | ORIENT STAR CONSTRUCTION, INC. (FORMERLY: ORIENT S | 4465 | 2022 | 2022-12-07 | 02/21/2022 | 263517.2 | 0 | 2022-12-06 |  | 1
2023 | Cordillera Administrative Region | APAYAO | CONNER (APAYAO) | P00740313LZ | Construction of Flood Mitigation Structure | 121.2683 | 17.8197 | 115793907.8 | 115800000 | 2024 | JOMARCANN GENERAL CONSTRUCTION / RODEKOM GENERAL CONSTRUCTION AND ENTERPRISE | 4466 | 2023 | 2024-02-29 | 04/12/2023 | 0 | 6092.2 | 2024-02-28 |  | 1
2022 | Region IV-A | RIZAL | TERESA (RIZAL) | P00620651LZ | Construction of Flood Mitigation Structure | 121.2161 | 14.5728 | 49000000 | 49000000 | 2022 | DOUBLE 12 CONSTRUCTION & SUPPLY | 4467 | 2022 | 2022-10-29 | 02/15/2022 | 0 | 0 | 2022-10-28 |  | 1
2022 | Region II | NUEVA VIZCAYA | BAMBANG (NUEVA VIZCAYA) | P00621419LZ | Construction of Flood Mitigation Structure | 121.0881 | 16.3547 | 49000000 | 49000000 | 2022 | BRG CONSTRUCTION | 4468 | 2022 | 2022-12-18 | 04/04/2022 | 0 | 0 | 2023-01-11 | 24
2021 | Region IV-A | RIZAL |  | P00526133LZ | Construction of Flood Mitigation Structure | 121.169 | 14.5005 | 19600000 | 19599997.48 | 2022 | G. ANORE CONSTRUCTION | 4469 | 2021 | 2022-08-20 | 03/24/2022 | 2.52 | 0 | 2022-08-19 |  | 1
2021 | Region IV-A | BATANGAS |  | P00561181LZ | Construction of Slope Protection Structure | 121.1425 | 13.793 | 33320000 | 32320400 | 2022 | JASMIG CONSTRUCTION CORPORATION (FORMERLY: JASMIG CONSTRUCTION SUPPLY) | 4470 | 2021 | 2022-07-01 | 11/11/2021 | 999600 | 0 | 2022-06-30 |  | 1
2022 | Region IV-A | BATANGAS | BATANGAS CITY (CAPITAL) (BATANGAS) | P00620213LZ | Construction of Flood Mitigation Structure | 121.0632 | 13.7463 | 96500000 | 96500000 | 2022 | VICMAR CONSTRUCTION, INC. | 4471 | 2022 | 2022-12-07 | 02/15/2022 | 0 | 0 | 2023-01-09 | 33
2023 | Cordillera Administrative Region | KALINGA | CITY OF TABUK (CAPITAL) (KALINGA) | P00726657LZ | Construction of Flood Mitigation Structure | 121.3703 | 17.4008 | 48977851.32 | 48970460.61 | 2023 | JTM CONSTRUCTION / GARVIS CONSTRUCTION CORPORATION | 4472 | 2023 | 2023-07-28 | 02/20/2023 | 7390.71 | 0 | 2023-08-31 | 34
2022 | Cordillera Administrative Region | APAYAO | CONNER (APAYAO) | P00620136LZ | Construction of Flood Mitigation Structure | 121.2686 | 17.8183 | 51761907.66 | 51762600 | 2023 | ASC CONSTRUCTION & CONCRETE PRODUCTS | 4473 | 2022 | 2023-05-30 | 04/04/2022 | 0 | 692.34 | 2023-06-14 | 15
2022 | Region IV-A | BATANGAS | SAN JOSE (BATANGAS) | P00640547LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.0885 | 13.9062 | 3960000 | 3841200 | 2022 | 830 BUILDERS & DEVELOPERS CORP. | 4474 | 2022 | 2022-07-02 | 04/04/2022 | 118800 | 0 | 2022-07-01 |  | 1
2023 | Region IV-B | ORIENTAL MINDORO | NAUJAN (ORIENTAL MINDORO) | P00736029LZ | Construction of Dike | 121.1698 | 13.1628 | 217125000 | 217120601.7 | 2023 | NEWBIG FOUR J CONSTRUCTION INC., (FORMERLY FOUR J | 4475 | 2023 | 2023-12-10 | 02/11/2023 | 4398.3 | 0 | 2024-02-04 | 56
2022 | Cordillera Administrative Region | KALINGA | TINGLAYAN (KALINGA) | P00621014LZ | Construction of Flood Mitigation Structure | 121.1425 | 17.2586 | 9800000 | 8598099.86 | 2022 | FEREST DWAYNE CONSTRUCTION | 4476 | 2022 | 2022-10-20 | 03/02/2022 | 1201900.14 | 0 | 2022-10-19 |  | 1
2023 | Region IV-B | ORIENTAL MINDORO | NAUJAN (ORIENTAL MINDORO) | P00736031LZ | Construction of Dike | 121.1701 | 13.1697 | 221950000 | 221948493.4 | 2023 | SUNWEST, INC. (FORMERLY: SUNWEST CONSTRUCTION & DEVELOPMENT CORPORATION) / FGO CONSTRUCTION | 4477 | 2023 | 2023-12-15 | 02/11/2023 | 1506.6 | 0 | 2024-02-28 | 75
2022 | National Capital Region | MAKATI CITY | CITY OF MAKATI (METROPOLITAN MANILA) | P00632712LZ | Rehabilitation / Major Repair of Drainage Structure | 121.0632 | 14.5603 | 13720000 | 13860000 | 2022 | QUATRIX CONSTRUCTION AND SUPPLY INC. | 4478 | 2022 | 2022-07-20 | 02/09/2022 | 0 | 140000 | 2022-07-22 | 2
2023 | Region IV-B | ORIENTAL MINDORO | SOCORRO (ORIENTAL MINDORO) | P00727189LZ | Construction of Drainage Structure | 121.3708 | 13.1231 | 38600000 | 30791170.25 | 2023 | LUMEL GLENN CONSTRUCTION | 4479 | 2023 | 2023-10-01 | 03/07/2023 | 7808829.75 | 0 | 2023-11-05 | 35
2023 | Region IV-A | BATANGAS | SAN JOSE (BATANGAS) | P00742412LZ | Rehabilitation / Major Repair of Drainage Structure | 121.0886 | 13.8903 | 5940000 | 5761800 | 2023 | LUCKY EIGHTY-THREE CONSTRUCTION AND SUPPLY(FOR.VRP | 4480 | 2023 | 2023-09-16 | 05/08/2023 | 178200 | 0 | 2023-08-15 |  | 32
2024 | Region IV-A | RIZAL | TERESA (RIZAL) | P00820963LZ | Construction of Flood Mitigation Structure | 121.2164 | 14.5483 | 48444340 | 48444340 | 2024 | PERSAN CONSTRUCTION, INC. (FORMERLY: PERSAN CONST. | 4481 | 2024 | 2024-10-18 | 02/07/2024 | 0 | 0 | 2024-10-17 |  | 1
2023 | Cordillera Administrative Region | APAYAO | CONNER (APAYAO) | P00726398LZ | Construction of Revetment | 121.2686 | 17.8186 | 72375000 | 72375000 | 2023 | ASC CONSTRUCTION & CONCRETE PRODUCTS | 4482 | 2023 | 2023-12-14 | 02/12/2023 | 0 | 0 | 2024-01-29 | 46
2021 | Region IV-A | RIZAL |  | P00526131LZ | Construction of Flood Mitigation Structure | 121.1429 | 14.6037 | 14700000 | 13966470 | 2022 | LTDL BUILDERS | 4483 | 2021 | 2022-07-27 | 02/28/2022 | 733530 | 0 | 2022-07-26 |  | 1
2023 | Region IV-B | ORIENTAL MINDORO | NAUJAN (ORIENTAL MINDORO) | P00736030LZ | Construction of Dike | 121.1703 | 13.1643 | 217124999.8 | 217121051.4 | 2024 | NEWBIG FOUR J CONSTRUCTION INC., (FORMERLY FOUR J | 4484 | 2023 | 2024-02-05 | 02/11/2023 | 3948.4 | 0 | 2024-02-04 |  | 1
2022 | Region III | AURORA | DINGALAN (AURORA) | P00640456LZ | Construction of Flood Mitigation Structure | 121.3714 | 15.3264 | 118800000 | 118800000 | 2023 | MORNING STEEL CONSTRUCTION / CHRISTIAN IAN CONSTRUCTION CORPORATION | 4485 | 2022 | 2023-05-18 | 07/25/2022 | 0 | 0 | 2023-07-28 | 71
2024 | National Capital Region | PASIG CITY | CITY OF PASIG (METROPOLITAN MANILA) | P00824584LZ | Rehabilitation / Major Repair of Drainage Structure | 121.0886 | 14.6202 | 11759946.87 | 11557707.21 | 2025 | WBX CONSTRUCTION, INC (FORMERLY WBX CONSTRUCTION) | 4486 | 2024 | 2025-02-15 | 10/04/2024 | 202239.66 | 0 | 2025-03-01 | 14
2023 | Region IV-A | RIZAL | TERESA (RIZAL) | P00737533LZ | Construction of Flood Mitigation Structure | 121.2167 | 14.5435 | 4950000 | 4950000 | 2023 | GKB BUILDERS | 4487 | 2023 | 2023-04-15 | 02/20/2023 | 0 | 0 | 2023-06-07 | 53
2023 | Region II | CAGAYAN | CLAVERIA (CAGAYAN) | P00727267LZ | Construction of Flood Mitigation Structure | 121.0888 | 18.6113 | 77200000 | 77200000 | 2024 | SKYLINE CONSTRUCTION, EQUIPMENT AND DEVELOPMENT CORPORATION(FORMERLY: EDDIE G. GUILLEN BUILDERS INC. | 4488 | 2023 | 2024-04-06 | 04/12/2023 | 0 | 0 | 2024-04-05 |  | 1
2023 | Cordillera Administrative Region | KALINGA | LUBUAGAN (KALINGA) | P00726102LZ | Construction of Flood Mitigation Structure | 121.1431 | 17.357 | 7840000 | 7834904.25 | 2024 | SONBLESSED CONSTRUCTION AND SUPPLY | 4489 | 2023 | 2024-04-15 | 04/17/2023 | 5095.75 | 0 | 2023-11-10 |  | 157
2022 | Region IV-A | BATANGAS | PADRE GARCIA (BATANGAS) | P00637791LZ | Construction of Flood Mitigation Structure | 121.2696 | 13.878 | 4950000 | 4801460 | 2022 | DARCY & ANNA BUILDERS & TRADING | 4490 | 2022 | 2022-07-02 | 04/04/2022 | 148540 | 0 | 2022-07-01 |  | 1
2023 | Region IV-A | RIZAL | BINANGONAN (RIZAL) | P00725839LZ | Construction of Flood Mitigation Structure | 121.1704 | 14.5009 | 106150000 | 106149946.5 | 2024 | YPR GEN. CONTRACTOR AND CONSTRUCTION SUPPLY INC. | 4491 | 2023 | 2024-02-04 | 04/11/2023 | 53.5 | 0 | 2024-02-03 |  | 1
2022 | Region IV-A | BATANGAS | BATANGAS CITY (CAPITAL) (BATANGAS) | P00620212LZ | Construction of Flood Mitigation Structure | 121.0633 | 13.7492 | 96500000 | 96500000 | 2022 | VICMAR CONSTRUCTION, INC. | 4492 | 2022 | 2022-12-07 | 02/15/2022 | 0 | 0 | 2023-01-09 | 33
2023 | Region IV-A | RIZAL | BINANGONAN (RIZAL) | P00737530LZ | Construction of Flood Mitigation Structure | 121.2168 | 14.3506 | 9900000 | 9899988.55 | 2023 | FLAG CONSTRUCTION CORPORATION(FOR. FLAG CONSTRUCTI | 4493 | 2023 | 2023-07-17 | 03/20/2023 | 11.45 | 0 | 2023-07-16 |  | 1
2024 | Region II | NUEVA VIZCAYA | BAMBANG (NUEVA VIZCAYA) | P00821192LZ | Construction of Flood Mitigation Structure | 121.0889 | 16.3758 | 96500000 | 96500000 | 2024 | V.B. MANUBAY CONSTRUCTION | 4494 | 2024 | 2024-03-27 | 02/16/2024 | 0 | 0 | 2025-01-01 | 280
2024 | Cordillera Administrative Region | MOUNTAIN PROVINCE | PARACELIS (MOUNTAIN PROVINCE) | P00821545LZ | Construction of Flood Mitigation Structure | 121.3724 | 17.239 | 19600000 | 19600000 | 2024 | JTM CONSTRUCTION | 4495 | 2024 | 2024-10-02 | 02/15/2024 | 0 | 0 | 2024-07-23 |  | 71
2023 | Region IV-A | BATANGAS | LIPA CITY (BATANGAS) | P00737498LZ | Construction of Flood Mitigation Structure | 121.1432 | 13.9418 | 4950000 | 4800269.23 | 2023 | ABLB CONSTRUCTION SERVICES | 4496 | 2023 | 2023-06-07 | 02/08/2023 | 149730.77 | 0 | 2023-06-06 |  | 1
2023 | Region II | NUEVA VIZCAYA | BAGABAG (NUEVA VIZCAYA) | P00742127LZ | Construction of Flood Mitigation Structure | 121.2699 | 16.5867 | 69300000 | 69300000 | 2023 | EGB CONSTRUCTION CORPORATION (FORMERLY: EGB CONSTRUCTION) | 4497 | 2023 | 2023-10-15 | 04/12/2023 | 0 | 0 | 2024-03-08 | 145
2023 | Region IV-B | ORIENTAL MINDORO | NAUJAN (ORIENTAL MINDORO) | P00736034LZ | Construction of Dike | 121.1716 | 13.1777 | 217124995.5 | 217122876.4 | 2023 | SUNWEST, INC. (FORMERLY: SUNWEST CONSTRUCTION & DEVELOPMENT CORPORATION) | 4498 | 2023 | 2023-12-15 | 02/11/2023 | 2119.1 | 0 | 2024-02-28 | 75
2024 | National Capital Region | TAGUIG CITY | TAGUIG CITY (METROPOLITAN MANILA) | P00821065LZ | Construction of Slope Protection Structure | 121.0634 | 14.4907 | 96499469.9 | 94568185.19 | 2024 | DAHL CONSTRUCTION CORP. (FORMERLY: DAHL CONSTRUCTION) | 4499 | 2024 | 2024-09-23 | 02/13/2024 | 1931284.71 | 0 | 2024-10-08 | 15
2023 | Cordillera Administrative Region | MOUNTAIN PROVINCE | PARACELIS (MOUNTAIN PROVINCE) | P00725656LZ | Construction of Flood Mitigation Structure | 121.3738 | 17.231 | 62725000 | 62725000 | 2023 | A.I.P. CONSTRUCTION | 4500 | 2023 | 2023-08-15 | 06/08/2023 | 0 | 0 | 2023-12-29 | 136
2024 | Cordillera Administrative Region | MOUNTAIN PROVINCE | PARACELIS (MOUNTAIN PROVINCE) | P00821120LZ | Construction of Flood Mitigation Structure | 121.3742 | 17.2423 | 52744005 | 52744005 | 2024 | ED1SON DEVELOPMENT & CONSTRUCTION INC. / FLEURDELIS CONSTRUCTION AND SUPPLY | 4501 | 2024 | 2024-09-05 | 02/19/2024 | 0 | 0 | 2024-09-04 |  | 1
2023 | National Capital Region | SAN JUAN CITY | CITY OF SAN JUAN (METROPOLITAN MANILA) | P00737363LZ | Construction of Flood Mitigation Facility | 121.0891 | 14.5885 | 67549650.43 | 65573723.02 | 2024 | R.D. TALENS CONSTRUCTION AND TRADING / NEW EASTPOINT BUILDERS CORP. | 4502 | 2023 | 2024-04-21 | 02/13/2023 | 1975927.41 | 0 | 2023-08-10 |  | 255
2022 | Region IV-A | BATANGAS | LOBO (BATANGAS) | P00631282LZ | Construction of Flood Mitigation Structure | 121.2175 | 13.6518 | 49000000 | 49000000 | 2023 | TCSC CORP. / EFREN RAMIREZ CONSTRUCTION AND GENERAL SERVICES CORPORATION | 4503 | 2022 | 2023-08-31 | 01/28/2022 | 0 | 0 | 2023-08-30 |  | 1
2022 | Region IV-A | RIZAL | CITY OF ANTIPOLO (RIZAL) | P00620623LZ | Construction of Flood Mitigation Structure | 121.1719 | 14.5917 | 27440000 | 27439523.75 | 2022 | BELL CONSTRUCTION | 4504 | 2022 | 2022-09-13 | 02/16/2022 | 476.25 | 0 | 2022-09-12 |  | 1
2024 | National Capital Region | TAGUIG CITY | TAGUIG CITY (METROPOLITAN MANILA) | P00821076LZ | Construction of Slope Protection Structure | 121.0634 | 14.4916 | 96499770.03 | 94569774.62 | 2024 | TOPNOTCH CATALYST BUILDERS INC. / BEAM TEAM DEVELOPER SPECIALIST INC. | 4505 | 2024 | 2024-10-07 | 02/13/2024 | 1929995.41 | 0 | 2024-10-08 | 1
2024 | Region IV-A | RIZAL | BARAS (RIZAL) | P00820312LZ | Construction of Flood Mitigation Structure | 121.2704 | 14.5278 | 91675000 | 91675000 | 2024 | HONY TRADING & CONSTRUCTION | 4506 | 2024 | 2024-10-19 | 02/07/2024 | 0 | 0 | 2025-02-17 | 121
2021 | Region IV-A | RIZAL |  | P00561396LZ | Construction of Drainage Structure | 121.1722 | 14.5011 | 19800000 | 19799998.38 | 2022 | J.H.R. ENTERPRISES | 4507 | 2021 | 2022-08-20 | 03/24/2022 | 1.62 | 0 | 2022-08-19 |  | 1
2023 | Region IV-A | BATANGAS | SAN JOSE (BATANGAS) | P00742410LZ | Construction of Slope Protection Structure | 121.0893 | 13.9255 | 9900000 | 9603000 | 2023 | 830 BUILDERS & DEVELOPERS CORP. | 4508 | 2023 | 2023-11-09 | 08/03/2023 | 297000 | 0 | 2023-12-11 | 32
2022 | Region IV-B | ORIENTAL MINDORO | BONGABONG (ORIENTAL MINDORO) | P00620676LZ | Construction of Flood Mitigation Structure | 121.375 | 12.7006 | 14004987.82 | 13984346.37 | 2022 | KING'S BUILDERS & DEVELOPMENT CORPORATION | 4509 | 2022 | 2022-12-06 | 06/03/2022 | 20641.45 | 0 | 2022-11-28 |  | 8
2023 | Region IV-A | RIZAL | CITY OF ANTIPOLO (RIZAL) | P00742445LZ | Construction of Flood Mitigation Structure | 121.1432 | 14.6058 | 19800000 | 19800000 | 2023 | STREAMLINE BUILDERS CORPORATION | 4510 | 2023 | 2023-12-05 | 05/10/2023 | 0 | 0 | 2023-12-04 |  | 1
2022 | National Capital Region | MAKATI CITY | CITY OF MAKATI (METROPOLITAN MANILA) | P00620378LZ | Rehabilitation / Major Repair of Drainage Structure | 121.0634 | 14.5509 | 10780000 | 10240935.96 | 2022 | ALEXA TRADING & CONSTRUCTION | 4511 | 2022 | 2022-10-01 | 02/04/2022 | 539064.04 | 0 | 2022-09-30 |  | 1
2022 | Region IV-A | LAGUNA | LOS BAÃ‘OS (LAGUNA) | P00632900LZ | Rehabilitation / Major Repair of Drainage Structure | 121.218 | 14.1778 | 5940000 | 5814445.94 | 2022 | A.I.A. CONSTRUCTION | 4512 | 2022 | 2022-07-09 | 03/09/2022 | 125554.06 | 0 | 2022-07-08 |  | 1
2023 | Region IV-A | LAGUNA | BAY (LAGUNA) | P00725792LZ | Construction of Flood Mitigation Structure | 121.2714 | 14.1489 | 48250000 | 48233455 | 2023 | MAR-VEL CONSTRUCTION & SUPPLY | 4513 | 2023 | 2023-10-12 | 02/24/2023 | 16545 | 0 | 2023-10-11 |  | 1
2022 | Region IV-A | QUEZON | PITOGO (QUEZON) | P00621472LZ | Construction of Slope Protection Structure | 121.0893 | 13.7808 | 14699799.99 | 14700000 | 2022 | M.C. LAYGO BUILDERS | 4514 | 2022 | 2022-10-31 | 04/05/2022 | 0 | 200.01 | 2022-10-30 |  | 1
2022 | Cordillera Administrative Region | APAYAO | PUDTOL (APAYAO) | P00620802LZ | Construction of Flood Mitigation Structure | 121.3765 | 18.2066 | 82025000 | 79576285.45 | 2023 | ASC CONSTRUCTION & CONCRETE PRODUCTS / ISNAG BUILDERS & DEV'T. CORPORATION | 4515 | 2022 | 2023-07-31 | 03/31/2022 | 2448714.55 | 0 | 2023-01-23 |  | 189
2024 | Region IV-A | RIZAL | BINANGONAN (RIZAL) | P00820932LZ | Construction of Flood Mitigation Structure | 121.218 | 14.339 | 9800000 | 9799977.16 | 2024 | MAK-JAMS CONSTRUCTION | 4516 | 2024 | 2024-05-29 | 02/19/2024 | 22.84 | 0 | 2024-06-11 | 13
2023 | Region IV-A | BATANGAS | PADRE GARCIA (BATANGAS) | P00742398LZ | Construction of Slope Protection Structure | 121.2715 | 13.8724 | 5940000 | 5761800 | 2023 | KENSAL RISE CONSTRUCTION | 4517 | 2023 | 2023-06-15 | 03/30/2023 | 178200 | 0 | 2023-07-26 | 41
2023 | Region IV-B | ORIENTAL MINDORO | NAUJAN (ORIENTAL MINDORO) | P00736032LZ | Construction of Dike | 121.1724 | 13.1821 | 212300000 | 212299613.5 | 2023 | MACROPRIME BUILDERS CORPORATION (FORMERLY: MORANTE BUILDERS & SUPPLY) / SUNWEST, INC. (FORMERLY: SUNWEST CONSTRUCTION & DEVELOPMENT CORPORATION) | 4518 | 2023 | 2023-12-15 | 02/11/2023 | 386.5 | 0 | 2024-02-28 | 75
2023 | Region II | CAGAYAN | CLAVERIA (CAGAYAN) | P00726434LZ | Construction of Flood Mitigation Structure | 121.0894 | 18.5711 | 49000000 | 48250000 | 2023 | SKYLINE CONSTRUCTION, EQUIPMENT AND DEVELOPMENT CORPORATION(FORMERLY: EDDIE G. GUILLEN BUILDERS INC. | 4519 | 2023 | 2023-08-18 | 02/06/2023 | 750000 | 0 | 2023-08-17 |  | 1
2024 | Region II | NUEVA VIZCAYA | BAYOMBONG (CAPITAL) (NUEVA VIZCAYA) | P00825048LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.1436 | 16.4736 | 96500000 | 96500000 | 2024 | DALCON CONSTRUCTION | 4520 | 2024 | 2024-07-16 | 03/27/2024 | 0 | 0 | 2025-02-13 | 212
2022 | National Capital Region | QUEZON CITY | QUEZON CITY (METROPOLITAN MANILA) | P00631051LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.0635 | 14.7111 | 14700000 | 14259000 | 2022 | E.L. TORRES CONSTRUCTION AND TRADING INC. (FORMERLY : E. L. TORRES CONSTRUCTION & TRADING | 4521 | 2022 | 2022-11-06 | 02/14/2022 | 441000 | 0 | 2022-10-10 |  | 27
2024 | Region IV-B | ORIENTAL MINDORO | BONGABONG (ORIENTAL MINDORO) | P00825131LZ | Construction of Flood Mitigation Structure | 121.3775 | 12.6886 | 96500000 | 96496493.95 | 2025 | CAMBERWELL CONSTRUCTION AND SUPPLIES | 4522 | 2024 | 2025-02-10 | 03/11/2024 | 3506.05 | 0 | 2025-02-17 | 7
2022 | Region IV-A | RIZAL | BINANGONAN (RIZAL) | P00637800LZ | Construction of Flood Mitigation Structure | 121.2184 | 14.3552 | 9900000 | 9899971.09 | 2022 | MAK-JAMS CONSTRUCTION | 4523 | 2022 | 2022-10-03 | 06/06/2022 | 28.91 | 0 | 2022-10-02 |  | 1
2023 | Region IV-A | RIZAL | SAN MATEO (RIZAL) | P00737536LZ | Rehabilitation / Major Repair of Drainage Structure | 121.1437 | 14.7081 | 4950000 | 4950000 | 2023 | 22 PRIME CONSTRUCTION AND REALTY DEVELOPMENT INC. | 4524 | 2023 | 2023-09-23 | 04/11/2023 | 0 | 0 | 2023-09-22 |  | 1
2022 | Cordillera Administrative Region | APAYAO | LUNA (APAYAO) | P00620810LZ | Construction of Flood Mitigation Structure | 121.2719 | 18.3432 | 82025000 | 79564241.95 | 2023 | ASC CONSTRUCTION & CONCRETE PRODUCTS | 4525 | 2022 | 2023-10-09 | 03/31/2022 | 2460758.05 | 0 | 2023-01-23 |  | 259
2022 | Region IV-A | RIZAL | BINANGONAN (RIZAL) | P00639496LZ | Construction of Flood Mitigation Structure | 121.2186 | 14.3559 | 9800000 | 9799983.23 | 2022 | DUKHEA CONSTRUCTION | 4526 | 2022 | 2022-10-24 | 07/27/2022 | 16.77 | 0 | 2022-11-22 | 29
2021 | Region IV-A | LAGUNA |  | P00526091LZ | Construction of Revetment | 121.1727 | 14.2174 | 29400000 | 28372642.6 | 2022 | M.T. MALIUANAG CONSTRUCTION SERVICES | 4527 | 2021 | 2022-07-20 | 03/30/2022 | 1027357.4 | 0 | 2022-10-15 | 87
2021 | National Capital Region | MAKATI CITY |  | P00561155LZ | Rehabilitation / Major Repair of Drainage Structure | 121.0635 | 14.5504 | 14700000 | 13963308.5 | 2022 | JP ESPIRITU CONSTRUCTION SERVICES AND SUPPLY | 4528 | 2021 | 2022-09-20 | 05/24/2022 | 736691.5 | 0 | 2022-09-19 |  | 1
2023 | Region IV-B | ORIENTAL MINDORO | BULALACAO (SAN PEDRO) (ORIENTAL MINDORO) | P00736624LZ | Construction of Flood Mitigation Structure | 121.382 | 12.2969 | 48999974.87 | 47701895.21 | 2023 | LUMEL GLENN CONSTRUCTION | 4529 | 2023 | 2023-11-16 | 02/10/2023 | 1298079.66 | 0 | 2023-11-15 |  | 1
2023 | National Capital Region | PASIG CITY | CITY OF PASIG (METROPOLITAN MANILA) | P00725962LZ | Rehabilitation / Major Repair of Drainage Structure | 121.0896 | 14.5606 | 29399573.02 | 27947309.47 | 2023 | WAY MAKER GENERAL CONTRACTOR OPC | 4530 | 2023 | 2023-10-09 | 02/06/2023 | 1452263.55 | 0 | 2023-11-16 | 38
2022 | Cordillera Administrative Region | IFUGAO | LAMUT (IFUGAO) | P00621502LZ | Construction of Flood Mitigation Structure | 121.1728 | 16.72 | 12544591.72 | 12494941.19 | 2023 | LBJ CONSTRUCTION | 4531 | 2022 | 2023-04-22 | 08/09/2022 | 49650.53 | 0 | 2023-04-21 |  | 1
2024 | Region II | NUEVA VIZCAYA | BAGABAG (NUEVA VIZCAYA) | P00823341LZ | Construction of Flood Mitigation Structure | 121.2188 | 16.444 | 96500000 | 96500000 | 2024 | EGB CONSTRUCTION CORPORATION (FORMERLY: EGB CONSTRUCTION) | 4532 | 2024 | 2024-07-22 | 04/02/2024 | 0 | 0 | 2025-02-15 | 208
2024 | Region III | BULACAN | CITY OF SAN JOSE DEL MONTE (BULACAN) | P00844755LZ | Construction of Slope Protection Structure | 121.0636 | 14.8526 | 48999607.56 | 48990160.74 | 2025 | ROYAL CROWN MONARCH CONSTRUCTION & SUPPLIES CORP. | 4533 | 2024 | 2025-01-20 | 04/30/2024 | 9446.82 | 0 | 2025-01-19 |  | 1
2023 | Cordillera Administrative Region | APAYAO | LUNA (APAYAO) | P00742287LZ | Construction of Flood Mitigation Structure | 121.2722 | 18.3474 | 14700000 | 14243240.81 | 2024 | ASC CONSTRUCTION & CONCRETE PRODUCTS | 4534 | 2023 | 2024-02-27 | 05/30/2023 | 456759.19 | 0 | 2024-01-18 |  | 40
2022 | Cordillera Administrative Region | KALINGA | TINGLAYAN (KALINGA) | P00621017LZ | Construction of Flood Mitigation Structure | 121.1437 | 17.2591 | 9800000 | 9788631.81 | 2022 | YUNAKIM CONSTRUCTION | 4535 | 2022 | 2022-10-25 | 04/10/2022 | 11368.19 | 0 | 2022-09-01 |  | 54
2023 | National Capital Region | TAGUIG CITY | TAGUIG CITY (METROPOLITAN MANILA) | P00726825LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.0897 | 14.5269 | 86849594.79 | 82507105.55 | 2023 | TOPNOTCH CATALYST BUILDERS INC. / BLACK HARDHAT INC. (FORMERLY: JCHARDHAT INC.) | 4536 | 2023 | 2023-10-20 | 03/22/2023 | 4342489.24 | 0 | 2023-11-15 | 26
2023 | Cordillera Administrative Region | APAYAO | PUDTOL (APAYAO) | P00726399LZ | Construction of Flood Mitigation Structure | 121.3843 | 18.2259 | 96500000 | 96481880.32 | 2024 | TAGEL CORPORATION | 4537 | 2023 | 2024-04-03 | 05/05/2023 | 18119.68 | 0 | 2024-05-15 | 42
2022 | Region II | NUEVA VIZCAYA | BAYOMBONG (CAPITAL) (NUEVA VIZCAYA) | P00621070LZ | Construction of Flood Mitigation Structure | 121.1443 | 16.4702 | 40826800 | 40826800 | 2022 | ERIC VAN P. SESBRENO CONSTRUCTION / V.B. GINES CONSTRUCTION | 4538 | 2022 | 2022-12-16 | 02/20/2022 | 0 | 0 | 2022-12-22 | 6
2024 | National Capital Region | PASIG CITY | CITY OF PASIG (METROPOLITAN MANILA) | P00824596LZ | Rehabilitation / Major Repair of Drainage Structure | 121.0898 | 14.597 | 9799798.13 | 9601233.69 | 2024 | IM CONSTRUCTION CORPORATION | 4539 | 2024 | 2024-11-06 | 04/08/2024 | 198564.44 | 0 | 2024-12-02 | 26
2022 | Region IV-A | BATANGAS | LIPA CITY (BATANGAS) | P00640549LZ | Rehabilitation / Major Repair of Drainage Structure | 121.1729 | 13.9098 | 4950000 | 4801470.13 | 2022 | ABLB CONSTRUCTION SERVICES | 4540 | 2022 | 2022-07-07 | 04/04/2022 | 148529.87 | 0 | 2022-07-06 |  | 1
2022 | Region IV-A | RIZAL | BINANGONAN (RIZAL) | P00639499LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.2189 | 14.356 | 9800000 | 9799973.61 | 2022 | FLAG CONSTRUCTION CORPORATION(FOR. FLAG CONSTRUCTI | 4541 | 2022 | 2022-12-22 | 07/04/2022 | 26.39 | 0 | 2022-12-29 | 7
2023 | National Capital Region | QUEZON CITY | QUEZON CITY (METROPOLITAN MANILA) | P00727030LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.0637 | 14.6327 | 14699422.01 | 14653311.8 | 2024 | E.L. TORRES CONSTRUCTION AND TRADING INC. (FORMERLY : E. L. TORRES CONSTRUCTION & TRADING | 4542 | 2023 | 2024-03-07 | 03/29/2023 | 46110.21 | 0 | 2024-03-06 |  | 1
2022 | National Capital Region | PATEROS | TAGUIG CITY (METROPOLITAN MANILA) | P00621524LZ | Construction of Flood Mitigation Structure | 121.0638 | 14.5353 | 48999295.32 | 49000000 | 2022 | TOPNOTCH CATALYST BUILDERS INC. | 4543 | 2022 | 2022-09-19 | 03/24/2022 | 0 | 704.68 | 2022-09-18 |  | 1
2022 | Region II | NUEVA VIZCAYA | BAMBANG (NUEVA VIZCAYA) | P00621067LZ | Construction of Flood Mitigation Structure | 121.1443 | 16.3913 | 49000000 | 49000000 | 2022 | BRG CONSTRUCTION | 4544 | 2022 | 2022-10-09 | 02/10/2022 | 0 | 0 | 2022-12-25 | 77
2022 | Region IV-A | RIZAL | CITY OF ANTIPOLO (RIZAL) | P00620641LZ | Construction of Slope Protection Structure | 121.2726 | 14.6601 | 49000000 | 48946916.5 | 2022 | ALPHA & OMEGA GEN. CONTRACTOR & DEVELOPMENT CORP. | 4545 | 2022 | 2022-10-25 | 03/01/2022 | 53083.5 | 0 | 2022-10-25 | 0
2023 | National Capital Region | PASIG CITY | CITY OF PASIG (METROPOLITAN MANILA) | P00725943LZ | Rehabilitation / Major Repair of Drainage Structure | 121.0899 | 14.5694 | 4649690.93 | 4416000 | 2023 | 1HB CONSTRUCTION CORP. (FORMERLY: HB CONSTRUCTION) | 4546 | 2023 | 2023-03-07 | 02/06/2023 | 233690.93 | 0 | 2023-03-06 |  | 1
2023 | Region IV-A | LAGUNA | CITY OF BIÃ‘AN (LAGUNA) | P00725826LZ | Construction of Flood Mitigation Structure | 121.0638 | 14.2688 | 96500000 | 96498518.01 | 2024 | MAR-VEL CONSTRUCTION & SUPPLY | 4547 | 2023 | 2024-02-02 | 02/24/2023 | 1481.99 | 0 | 2024-02-01 |  | 1
2022 | Cordillera Administrative Region | KALINGA | LUBUAGAN (KALINGA) | P00620489LZ | Construction of Flood Mitigation Structure | 121.1733 | 17.3469 | 9800000 | 8405370.83 | 2023 | MATAGOAN KJ BUILDERS AND ENGINEERING SERVICES | 4548 | 2022 | 2023-08-22 | 03/02/2022 | 1394629.17 | 0 | 2022-09-24 |  | 332
2024 | Region IV-B | ORIENTAL MINDORO | CITY OF CALAPAN (CAPITAL) (ORIENTAL MINDORO) | P00821605LZ | Construction of Flood Mitigation Structure | 121.2208 | 13.3147 | 49000000 | 48999995.96 | 2024 | ETVR TRADING & CONSTRUCTION | 4549 | 2024 | 2024-05-22 | 02/08/2024 | 4.04 | 0 | 2024-10-24 | 155
2024 | Cordillera Administrative Region | MOUNTAIN PROVINCE | BARLIG (MOUNTAIN PROVINCE) | P00823328LZ | Construction of Flood Mitigation Structure | 121.1447 | 17.0839 | 96500000 | 96500000 | 2024 | E.T. LATAWAN CONSTRUCTION | 4550 | 2024 | 2024-08-12 | 02/26/2024 | 0 | 0 | 2024-11-01 | 81
2022 | Region IV-A | RIZAL | CITY OF ANTIPOLO (RIZAL) | P00620254LZ | Construction of Slope Protection Structure | 121.2727 | 14.6601 | 91675000 | 91521089.25 | 2023 | MARCBILT CONSTRUCTION, INC. / DJSEVILLA CONSOLIDATED BUILDERS CORPORATION (FORMER:TOP-BEST ENGINEERING WORKS & SUPPLIES) | 4551 | 2022 | 2023-04-30 | 03/07/2022 | 153910.75 | 0 | 2023-04-29 |  | 1
2023 | National Capital Region | TAGUIG CITY | TAGUIG CITY (METROPOLITAN MANILA) | P00742235LZ | Rehabilitation / Major Repair of Drainage Structure | 121.0638 | 14.5083 | 29399883.49 | 27924104.19 | 2024 | JAYMAR BUILDERS | 4552 | 2023 | 2024-03-14 | 06/08/2023 | 1475779.3 | 0 | 2024-01-02 |  | 72
2022 | National Capital Region | MARIKINA CITY | CITY OF MARIKINA (METROPOLITAN MANILA) | P00632708LZ | Rehabilitation / Major Repair of Drainage Structure | 121.0899 | 14.6497 | 19599189.82 | 18607744.39 | 2023 | STAR WILLIAM CONSTRUCTION | 4553 | 2022 | 2023-04-17 | 02/08/2022 | 991445.43 | 0 | 2023-04-16 |  | 1
2022 | Cordillera Administrative Region | KALINGA | CITY OF TABUK (CAPITAL) (KALINGA) | P00632785LZ | Construction of Flood Mitigation Structure | 121.3858 | 17.3906 | 4939337 | 4811362.67 | 2022 | BAGWIS CONSTRUCTION | 4554 | 2022 | 2022-07-15 | 04/08/2022 | 127974.33 | 0 | 2022-08-04 | 20
2023 | Region IV-B | ORIENTAL MINDORO | NAUJAN (ORIENTAL MINDORO) | P00736033LZ | Construction of Dike | 121.1738 | 13.1892 | 217124999.5 | 217122749.3 | 2023 | SUNWEST, INC. (FORMERLY: SUNWEST CONSTRUCTION & DEVELOPMENT CORPORATION) | 4555 | 2023 | 2023-12-15 | 02/11/2023 | 2250.2 | 0 | 2024-02-28 | 75
2023 | Region IV-B | ORIENTAL MINDORO | NAUJAN (ORIENTAL MINDORO) | P00736035LZ | Construction of Dike | 121.1738 | 13.2089 | 217125000 | 217123234.3 | 2023 | SUNWEST, INC. (FORMERLY: SUNWEST CONSTRUCTION & DEVELOPMENT CORPORATION) | 4556 | 2023 | 2023-12-15 | 02/11/2023 | 1765.7 | 0 | 2024-02-28 | 75
2022 | Region IV-A | BATANGAS | CITY OF TANAUAN (BATANGAS) | P00632873LZ | Rehabilitation / Major Repair of Drainage Structure | 121.145 | 14.0819 | 8910000 | 4823615.6 | 2022 | JERIS CONSTRUCTION AND SUPPLY | 4557 | 2022 | 2022-10-01 | 02/04/2022 | 4086384.4 | 0 | 2022-09-30 |  | 1
2024 | Region IV-A | LAGUNA | BAY (LAGUNA) | P00820374LZ | Construction of Flood Mitigation Structure | 121.2741 | 14.1736 | 96500000 | 93564706 | 2025 | BHENLLABIEN BUILDERS CORPORATION (FORMERLY: BHENLLABIEN BUILDERS CONSTRUCTION) | 4558 | 2024 | 2025-01-21 | 03/01/2024 | 2935294 | 0 | 2025-01-20 |  | 1
2024 | National Capital Region | CALOOCAN CITY | CALOOCAN CITY (METROPOLITAN MANILA) | P00844680LZ | Construction of Flood Mitigation Structure | 121.0642 | 14.7658 | 29388151.14 | 28800369.3 | 2024 | DIADEMA CONSTRUCTION AND ENTERPRISES INC. (FORMERLY: DIADEMA ENTERPRISES) | 4559 | 2024 | 2024-11-17 | 03/26/2024 | 587781.84 | 0 | 2024-09-20 |  | 58
2023 | Region IV-A | RIZAL | BINANGONAN (RIZAL) | P00740652LZ | Construction of Flood Mitigation Structure | 121.2213 | 14.3996 | 9800000 | 9799998.77 | 2023 | FLAG CONSTRUCTION CORPORATION(FOR. FLAG CONSTRUCTI | 4560 | 2023 | 2023-09-22 | 03/29/2023 | 1.23 | 0 | 2023-09-23 | 1
2023 | Region IV-A | RIZAL | BINANGONAN (RIZAL) | P00740653LZ | Construction of Flood Mitigation Structure | 121.2214 | 14.3933 | 4900000 | 4899993.44 | 2023 | MAK-JAMS CONSTRUCTION | 4561 | 2023 | 2023-05-27 | 03/29/2023 | 6.56 | 0 | 2023-05-26 |  | 1
2021 | Region IV-A | RIZAL |  | P00561562LZ | Construction of Flood Mitigation Structure | 121.2219 | 14.4457 | 4950000 | 4801495.3 | 2022 | PEARLCAST CONSTRUCTION & TRADING | 4562 | 2021 | 2022-09-19 | 09/05/2022 | 148504.7 | 0 | 2023-01-31 | 134
2022 | Region IV-A | RIZAL | BINANGONAN (RIZAL) | P00639497LZ | Construction of Slope Protection Structure | 121.222 | 14.3862 | 4900000 | 4899788.04 | 2022 | R.S. MESA CONSTRUCTION CORPORATION | 4563 | 2022 | 2022-12-09 | 07/13/2022 | 211.96 | 0 | 2022-12-08 |  | 1
2022 | Region IV-A | RIZAL | ANGONO (RIZAL) | P00632910LZ | Construction of Flood Mitigation Structure | 121.1451 | 14.5169 | 49500000 | 42347638.77 | 2022 | J.H.R. ENTERPRISES | 4564 | 2022 | 2022-12-19 | 02/23/2022 | 7152361.23 | 0 | 2022-12-18 |  | 1
2021 | National Capital Region | PASIG CITY |  | P00561213LZ | Rehabilitation / Major Repair of Drainage Structure | 121.09 | 14.56 | 14699777.54 | 13960378.73 | 2022 | 1HB CONSTRUCTION CORP. (FORMERLY: HB CONSTRUCTION) | 4565 | 2021 | 2022-07-31 | 01/11/2022 | 739398.81 | 0 | 2022-07-30 |  | 1
2023 | Region IV-B | ORIENTAL MINDORO | CITY OF CALAPAN (CAPITAL) (ORIENTAL MINDORO) | P00727186LZ | Construction of Drainage Structure | 121.2222 | 13.315 | 38600000 | 38599985.72 | 2023 | ETVR TRADING & CONSTRUCTION | 4566 | 2023 | 2023-07-18 | 03/24/2023 | 14.28 | 0 | 2023-09-29 | 73
2022 | Region IV-A | LAGUNA | LOS BAÃ‘OS (LAGUNA) | P00632895LZ | Construction of Drainage Structure | 121.2742 | 14.1887 | 5940000 | 5939211.58 | 2022 | A.I.A. CONSTRUCTION | 4567 | 2022 | 2022-07-06 | 03/09/2022 | 788.42 | 0 | 2022-07-05 |  | 1
2021 | Region IV-A | RIZAL |  | P00561563LZ | Construction of Flood Mitigation Structure | 121.1453 | 14.753 | 9900000 | 9900000 | 2022 | L. EUSEBIO ACE DEVELOPMENT CORPORATION | 4568 | 2021 | 2022-12-11 | 09/05/2022 | 0 | 0 | 2023-01-12 | 32
2021 | National Capital Region | PASIG CITY |  | P00561474LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.09 | 14.554 | 9799569.58 | 9304693.59 | 2022 | E.R. RODRIGUEZ CONSTRUCTION CORPORATION (FORMERLY: E.R. RODRIGUEZ CONSTRUCTION) | 4569 | 2021 | 2022-07-23 | 02/24/2022 | 494875.99 | 0 | 2022-07-22 |  | 1
2023 | Region II | CAGAYAN | RIZAL (CAGAYAN) | P00727345LZ | Construction of Flood Mitigation Structure | 121.3872 | 17.8423 | 19600000 | 19255698.77 | 2024 | JAMPAT BUILDERS | 4570 | 2023 | 2024-06-06 | 02/23/2023 | 344301.23 | 0 | 2023-09-30 |  | 250
2023 | Region IV-B | ORIENTAL MINDORO | NAUJAN (ORIENTAL MINDORO) | P00740434LZ | Construction of Dike | 121.1738 | 13.2124 | 212299993.4 | 212138142.9 | 2023 | SUNWEST, INC. (FORMERLY: SUNWEST CONSTRUCTION & DEVELOPMENT CORPORATION) / PROTOSTAR CONSTRUCTION | 4571 | 2023 | 2023-12-15 | 04/13/2023 | 161850.5 | 0 | 2024-04-29 | 136
2023 | Region IV-A | RIZAL | CITY OF ANTIPOLO (RIZAL) | P00726239LZ | Construction of Flood Mitigation Structure | 121.2747 | 14.6587 | 19600000 | 19599812.56 | 2023 | H FRANCISCO CONSTRUCTION AND SUPPLY | 4572 | 2023 | 2023-09-24 | 03/29/2023 | 187.44 | 0 | 2023-09-23 |  | 1
2023 | Region IV-A | RIZAL | CITY OF ANTIPOLO (RIZAL) | P00726237LZ | Construction of Flood Mitigation Structure | 121.1454 | 14.6409 | 49000000 | 48999987.97 | 2023 | YPR GEN. CONTRACTOR AND CONSTRUCTION SUPPLY INC. / TOP KMC CONSTRUCTION AND SUPPLY CORP. | 4573 | 2023 | 2023-07-20 | 02/16/2023 | 12.03 | 0 | 2023-12-21 | 154
2022 | Region IV-A | RIZAL | MONTALBAN (RIZAL) | P00620214LZ | Construction of Flood Mitigation Structure | 121.1456 | 14.7428 | 96500000 | 96500000 | 2023 | ALPHA & OMEGA GEN. CONTRACTOR & DEVELOPMENT CORP. / JOAN AND JOHN CONSTRUCTION AND TRADING | 4574 | 2022 | 2023-05-16 | 04/04/2022 | 0 | 0 | 2023-05-15 |  | 1
2024 | Region IV-A | RIZAL | BARAS (RIZAL) | P00844777LZ | Construction of Drainage Structure | 121.2753 | 14.5219 | 49000000 | 49000000 | 2024 | MEGA M BUILDERS CORPORATION (FORMERLY: MEGA M BUILDERS) | 4575 | 2024 | 2024-12-10 | 03/25/2024 | 0 | 0 | 2024-12-22 | 12
2021 | Region IV-A | RIZAL |  | P00525648LZ | Construction of Flood Mitigation Structure | 121.1458 | 14.5173 | 46320000 | 42573262.64 | 2022 | EL-JAKE BUILDERS / C.F. TRINIDAD CONSTRUCTION AND SUPPLIES CORP. (FOR | 4576 | 2021 | 2022-10-02 | 04/06/2022 | 3746737.36 | 0 | 2022-10-01 |  | 1
2022 | Region IV-A | LAGUNA | BAY (LAGUNA) | P00631301LZ | Construction of Flood Mitigation Structure | 121.2769 | 14.1939 | 19600000 | 19597737.55 | 2023 | 11 DIAMOND EAGLE CONSTRUCTION CORPORATION (FORMERLY:11 DIAMOND EAGLE CONSTRUCTION) | 4577 | 2022 | 2023-12-11 | 01/09/2023 | 2262.45 | 0 | 2024-01-11 | 31
2023 | Cordillera Administrative Region | KALINGA | TINGLAYAN (KALINGA) | P00726662LZ | Construction of Flood Mitigation Structure | 121.1461 | 17.2603 | 9800000 | 9798721.6 | 2023 | FEREST DWAYNE CONSTRUCTION | 4578 | 2023 | 2023-12-15 | 04/14/2023 | 1278.4 | 0 | 2023-10-09 |  | 67
2023 | Region II | NUEVA VIZCAYA | ARITAO (NUEVA VIZCAYA) | P00725664LZ | Construction of Flood Mitigation Structure | 121.0644 | 16.3114 | 96500000 | 96499860.98 | 2023 | AMP 723 CONSTRUCTION CORPORATION (FORMERLY: A.M.P. CONSTRUCTION) | 4579 | 2023 | 2023-10-15 | 02/10/2023 | 139.02 | 0 | 2023-10-14 |  | 1
2024 | Region IV-A | RIZAL | TERESA (RIZAL) | P00846095LZ | Construction of Flood Mitigation Structure | 121.2222 | 14.5788 | 96500000 | 96500000 | 2024 | ELITE GENERAL CONTRACTOR AND DEVELOPMENT CORP. | 4580 | 2024 | 2024-10-21 | 04/18/2024 | 0 | 0 | 2025-04-11 | 172
2024 | Cordillera Administrative Region | KALINGA | BALBALAN (KALINGA) | P00820767LZ | Construction of Flood Mitigation Structure | 121.2773 | 17.6012 | 5390000 | 5309149.1 | 2024 | BHM CONSTRUCTION | 4581 | 2024 | 2024-06-07 | 02/15/2024 | 80850.9 | 0 | 2024-06-24 | 17
2022 | Region IV-A | LAGUNA | CITY OF CALAMBA (LAGUNA) | P00640558LZ | Rehabilitation / Major Repair of Drainage Structure | 121.1462 | 14.1671 | 7425000 | 7260777 | 2023 | FOURTH GENERATION T CONSTRUCTION | 4582 | 2022 | 2023-04-24 | 07/11/2022 | 164223 | 0 | 2023-01-05 |  | 109
2023 | National Capital Region | CALOOCAN CITY | CALOOCAN CITY (METROPOLITAN MANILA) | P00727016LZ | Construction of Flood Mitigation Structure | 121.0648 | 14.7686 | 24491368.45 | 23947575.3 | 2023 | AVECS CORPORATION | 4583 | 2023 | 2023-12-25 | 05/19/2023 | 543793.15 | 0 | 2023-11-13 |  | 42
2024 | Region III | AURORA | DINGALAN (AURORA) | P00838514LZ | Construction of Flood Mitigation Structure | 121.3878 | 15.3781 | 28950000 | 28950000 | 2024 | DALCON CONSTRUCTION | 4584 | 2024 | 2024-09-20 | 04/30/2024 | 0 | 0 | 2024-10-02 | 12
2024 | Region IV-B | ORIENTAL MINDORO | NAUJAN (ORIENTAL MINDORO) | P00825127LZ | Construction of Flood Mitigation Structure | 121.1739 | 13.2436 | 98000000 | 96499897 | 2024 | SILVERWOLVES CONSTRUCTION CORPORATION | 4585 | 2024 | 2024-03-26 | 02/08/2024 | 1500103 | 0 | 2025-02-16 | 327
2024 | National Capital Region | TAGUIG CITY | TAGUIG CITY (METROPOLITAN MANILA) | P00821083LZ | Construction of Slope Protection Structure | 121.0901 | 14.5333 | 77199789.57 | 75532335.57 | 2024 | ZYRE TRADING AND CONSTRUCTION / RVDP CONSTRUCTION | 4586 | 2024 | 2024-10-28 | 06/04/2024 | 1667454 | 0 | 2025-01-28 | 92
2021 | Region IV-A | BATANGAS |  | P00525615LZ | Construction of Drainage Structure | 121.2233 | 13.8589 | 61347945 | 59514213 | 2022 | IKM BUILDERS AND CONSTRUCTION SUPPLY CORPORATION (FORMERLY: IKM BUILDERS & CONSTRUCTION SUPPLY) / T. SOLOMON CONSTRUCTION AND DEVELOPMENT CORPORATIO | 4587 | 2021 | 2022-08-05 | 11/09/2021 | 1833732 | 0 | 2022-08-04 |  | 1
2024 | Region III | NUEVA ECIJA | GABALDON (BITULOK & SABANI) (NUEVA ECIJA) | P00821223LZ | Construction of Flood Mitigation Structure | 121.2787 | 15.5025 | 86849993.44 | 85112899.88 | 2024 | FRAMECON BUILDERS | 4588 | 2024 | 2024-05-23 | 02/16/2024 | 1737093.56 | 0 | 2024-11-19 | 180
2023 | Region IV-A | BATANGAS | LIPA CITY (BATANGAS) | P00742417LZ | Construction of Drainage Structure | 121.1462 | 13.9495 | 9900000 | 9602811.85 | 2024 | TERAVERA CORPORATION | 4589 | 2023 | 2024-04-26 | 05/19/2023 | 297188.15 | 0 | 2023-09-19 |  | 220
2024 | National Capital Region | TAGUIG CITY | TAGUIG CITY (METROPOLITAN MANILA) | P00821082LZ | Construction of Slope Protection Structure | 121.0904 | 14.5332 | 96499978.57 | 94550679 | 2024 | HALREY CONSTRUCTION INC. | 4590 | 2024 | 2024-09-11 | 02/13/2024 | 1949299.57 | 0 | 2024-10-08 | 27
2021 | Region IV-B | ORIENTAL MINDORO |  | P00561469LZ | Construction of Drainage Structure | 121.1742 | 13.4139 | 96500000 | 94086578.05 | 2023 | A.L. SALAZAR CONSTRUCTION, INC. / ROTAFLEX CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY:ROTA FLEX CONSTRUCTION) | 4591 | 2021 | 2023-06-10 | 04/10/2022 | 2413421.95 | 0 | 2023-05-09 |  | 32
2024 | Region IV-B | ORIENTAL MINDORO | CITY OF CALAPAN (CAPITAL) (ORIENTAL MINDORO) | P00821602LZ | Construction of Flood Mitigation Structure | 121.2253 | 13.3858 | 49000000 | 48996963.79 | 2024 | MARTINEZ ENTERPRISES / FRAMECON BUILDERS | 4592 | 2024 | 2024-05-20 | 02/08/2024 | 3036.21 | 0 | 2024-10-24 | 157
2024 | National Capital Region | CALOOCAN CITY | CALOOCAN CITY (METROPOLITAN MANILA) | P00838474LZ | Construction of Flood Mitigation Structure | 121.0649 | 14.7616 | 48996694.37 | 47851161.52 | 2024 | DIADEMA CONSTRUCTION AND ENTERPRISES INC. (FORMERLY: DIADEMA ENTERPRISES) | 4593 | 2024 | 2024-11-18 | 03/26/2024 | 1145532.85 | 0 | 2024-10-20 |  | 29
2023 | Region II | CAGAYAN | RIZAL (CAGAYAN) | P00727346LZ | Construction of Flood Mitigation Structure | 121.3883 | 17.8419 | 19600000 | 19600000 | 2023 | FLAVIE CIVIL ENGINEERING CONSTRUCTION | 4594 | 2023 | 2023-10-11 | 03/08/2023 | 0 | 0 | 2023-10-13 | 2
2023 | Cordillera Administrative Region | APAYAO | CONNER (APAYAO) | P00726655LZ | Construction of Revetment | 121.2823 | 17.7998 | 24500000 | 24500000 | 2023 | GKA ENGINEERING AND CONSTRUCTION | 4595 | 2023 | 2023-06-22 | 02/12/2023 | 0 | 0 | 2023-08-22 | 61
2021 | Region IV-A | RIZAL |  | P00561799LZ | Construction of Flood Mitigation Structure | 121.147 | 14.721 | 29700000 | 29032498.29 | 2022 | LEGACY CONSTRUCTION CORPORATION (FORMERLY: LEGACY CONSTRUCTION) | 4596 | 2021 | 2022-12-09 | 09/05/2022 | 667501.71 | 0 | 2023-02-28 | 81
2021 | Region IV-B | ORIENTAL MINDORO |  | P00526332LZ | Construction of Flood Mitigation Structure | 121.1742 | 13.4139 | 67550000 | 65861028.99 | 2023 | A.L. SALAZAR CONSTRUCTION, INC. / ROTAFLEX CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY:ROTA FLEX CONSTRUCTION) | 4597 | 2021 | 2023-04-06 | 03/22/2022 | 1688971.01 | 0 | 2023-04-05 |  | 1
2023 | Region IV-B | ORIENTAL MINDORO | CITY OF CALAPAN (CAPITAL) (ORIENTAL MINDORO) | P00727182LZ | Construction of Drainage Structure | 121.2253 | 13.3872 | 33775000 | 33770105.07 | 2023 | MARTINEZ ENTERPRISES / FRAMECON BUILDERS | 4598 | 2023 | 2023-09-05 | 03/29/2023 | 4894.93 | 0 | 2023-09-18 | 13
2024 | Region IV-B | ORIENTAL MINDORO | GLORIA (ORIENTAL MINDORO) | P00821612LZ | Construction of Flood Mitigation Structure | 121.3884 | 12.9616 | 29400000 | 28822592.66 | 2024 | LUMEL GLENN CONSTRUCTION | 4599 | 2024 | 2024-09-09 | 02/07/2024 | 577407.34 | 0 | 2024-09-08 |  | 1
2023 | Region III | NUEVA ECIJA | RIZAL (NUEVA ECIJA) | P00742145LZ | Construction of Flood Mitigation Structure | 121.0905 | 15.698 | 99000000 | 98993408.99 | 2023 | SPECO BUILDERS INC. (FORMERLY VRF CONSTRUCTION) | 4600 | 2023 | 2023-09-05 | 04/13/2023 | 6591.01 | 0 | 2024-01-06 | 123
2023 | Region III | NUEVA ECIJA | GABALDON (BITULOK & SABANI) (NUEVA ECIJA) | P00725727LZ | Construction of Flood Mitigation Structure | 121.2826 | 15.514 | 77199958.44 | 77199989.01 | 2023 | FRAMECON BUILDERS | 4601 | 2023 | 2023-07-18 | 02/21/2023 | 0 | 30.57 | 2023-12-13 | 148
2021 | Region IV-B | ORIENTAL MINDORO |  | P00561399LZ | Construction of Flood Mitigation Structure | 121.1742 | 13.4133 | 7920000 | 7698096.56 | 2022 | ROTAFLEX CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY:ROTA FLEX CONSTRUCTION) | 4602 | 2021 | 2022-08-22 | 03/10/2022 | 221903.44 | 0 | 2022-08-21 |  | 1
2022 | Region IV-A | RIZAL | MONTALBAN (RIZAL) | P00631314LZ | Rehabilitation / Major Repair of Slope Protection Structure | 121.1471 | 14.7363 | 19600000 | 19600000 | 2022 | PERSAN CONSTRUCTION, INC. (FORMERLY: PERSAN CONST. | 4603 | 2022 | 2022-08-22 | 02/16/2022 | 0 | 0 | 2022-10-13 | 52
2024 | Region IV-A | RIZAL | CITY OF ANTIPOLO (RIZAL) | P00820939LZ | Construction of Flood Mitigation Structure | 121.2259 | 14.6627 | 49000000 | 48998726 | 2024 | 1C4M BUILDERS INC. | 4604 | 2024 | 2024-07-29 | 02/12/2024 | 1274 | 0 | 2024-10-07 | 70
2022 | National Capital Region | MAKATI CITY | CITY OF MAKATI (METROPOLITAN MANILA) | P00620371LZ | Rehabilitation / Major Repair of Drainage Structure | 121.0649 | 14.5545 | 5390000 | 5390000 | 2022 | C.B. TAMPENGCO CONSTRUCTION & SUPPLY | 4605 | 2022 | 2022-10-05 | 02/04/2022 | 0 | 0 | 2022-10-04 |  | 1
2022 | Region IV-A | LAGUNA | CITY OF BIÃ‘AN (LAGUNA) | P00620241LZ | Construction of Flood Mitigation Structure | 121.0905 | 14.3555 | 93530695 | 93431009.87 | 2022 | ST. MATTHEW GEN. CONTRACTOR & DEVELOPMENT CORP. | 4606 | 2022 | 2022-11-16 | 04/04/2022 | 99685.13 | 0 | 2023-02-17 | 93
2022 | Region III | AURORA | DINGALAN (AURORA) | P00631147LZ | Construction of Flood Mitigation Structure | 121.391 | 15.3821 | 14700000 | 14700000 | 2022 | DALCON CONSTRUCTION | 4607 | 2022 | 2022-08-22 | 03/14/2022 | 0 | 0 | 2022-08-21 |  | 1
2022 | Cordillera Administrative Region | KALINGA | LUBUAGAN (KALINGA) | P00644766LZ | Construction of Slope Protection Structure | 121.1471 | 17.3754 | 3312626.46 | 3195154.18 | 2023 | BANGYAN 3D CONSTRUCTION | 4608 | 2022 | 2023-10-25 | 01/12/2023 | 117472.28 | 0 | 2023-04-06 |  | 202
2023 | Region IV-B | ORIENTAL MINDORO | CITY OF CALAPAN (CAPITAL) (ORIENTAL MINDORO) | P00742460LZ | Construction of Drainage Structure | 121.1742 | 13.4003 | 4950000 | 4949602.2 | 2023 | MADSAM ENTERPRISES | 4609 | 2023 | 2023-09-02 | 03/28/2023 | 397.8 | 0 | 2023-09-01 |  | 1
2022 | Region IV-A | RIZAL | CITY OF ANTIPOLO (RIZAL) | P00620640LZ | Construction of Slope Protection Structure | 121.2843 | 14.6459 | 9800000 | 9799467.61 | 2022 | QUATRIX CONSTRUCTION AND SUPPLY INC. | 4610 | 2022 | 2022-08-14 | 02/16/2022 | 532.39 | 0 | 2022-08-13 |  | 1
2021 | Cordillera Administrative Region | KALINGA |  | P00525931LZ | Construction of Flood Mitigation Structure | 121.2272 | 17.3925 | 2940000 | 2702958.75 | 2022 | SONBLESSED CONSTRUCTION AND SUPPLY | 4611 | 2021 | 2022-08-10 | 04/10/2022 | 237041.25 | 0 | 2022-06-21 |  | 50
2023 | Region IV-A | LAGUNA | CITY OF SANTA ROSA (LAGUNA) | P00740387LZ | Construction of Flood Mitigation Structure | 121.0907 | 14.2553 | 96500000 | 96408436.09 | 2024 | WAWAO BUILDERS | 4612 | 2023 | 2024-02-08 | 04/14/2023 | 91563.91 | 0 | 2024-03-04 | 25
2022 | Region IV-A | BATANGAS | LIPA CITY (BATANGAS) | P00640548LZ | Rehabilitation / Major Repair of Drainage Structure | 121.1473 | 13.8697 | 13860000 | 13443880 | 2022 | RUSMEN BUILDERS & DEVELOPMENT CORPORATION (FORMERL | 4613 | 2022 | 2022-08-29 | 04/04/2022 | 416120 | 0 | 2022-08-28 |  | 1
2022 | Region IV-A | BATANGAS | LOBO (BATANGAS) | P00631284LZ | Construction of Flood Mitigation Structure | 121.2853 | 13.6753 | 49000000 | 49000000 | 2022 | N.D.M. SANCHEZ BUILDERS & DEVELOPMENT CORPORATION / EFREN RAMIREZ CONSTRUCTION AND GENERAL SERVICES CORPORATION | 4614 | 2022 | 2022-10-09 | 03/02/2022 | 0 | 0 | 2022-10-08 |  | 1
2024 | Region II | NUEVA VIZCAYA | BAMBANG (NUEVA VIZCAYA) | P00824690LZ | Construction of Flood Mitigation Structure | 121.0649 | 16.3919 | 49000000 | 49000000 | 2024 | DALCON CONSTRUCTION | 4615 | 2024 | 2024-03-27 | 02/13/2024 | 0 | 0 | 2024-09-28 | 185
2024 | Region IV-B | ORIENTAL MINDORO | CITY OF CALAPAN (CAPITAL) (ORIENTAL MINDORO) | P00821610LZ | Construction of Flood Mitigation Structure | 121.2276 | 13.3983 | 29400000 | 29399989.24 | 2024 | MAMA'S BOY CONSTRUCTION | 4616 | 2024 | 2024-06-25 | 02/08/2024 | 10.76 | 0 | 2024-10-05 | 102
2022 | Region IV-B | ORIENTAL MINDORO | CITY OF CALAPAN (CAPITAL) (ORIENTAL MINDORO) | P00639520LZ | Construction of Flood Mitigation Structure | 121.1744 | 13.4139 | 98000000 | 96626806.12 | 2023 | ANORE CONSTRUCTION | 4617 | 2022 | 2023-06-21 | 07/21/2022 | 1373193.88 | 0 | 2023-06-20 |  | 1
2023 | National Capital Region | TAGUIG CITY | TAGUIG CITY (METROPOLITAN MANILA) | P00726824LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.0907 | 14.5277 | 86849386 | 82472176.94 | 2023 | TOPNOTCH CATALYST BUILDERS INC. / BLACK HARDHAT INC. (FORMERLY: JCHARDHAT INC.) | 4618 | 2023 | 2023-10-20 | 03/22/2023 | 4377209.06 | 0 | 2023-11-15 | 26
2024 | Region IV-A | LAGUNA | RIZAL (LAGUNA) | P00839634LZ | Construction of Flood Mitigation Structure | 121.3925 | 14.1106 | 1980000 | 1938554 | 2024 | BHENLLABIEN BUILDERS CORPORATION (FORMERLY: BHENLLABIEN BUILDERS CONSTRUCTION) | 4619 | 2024 | 2024-06-09 | 04/11/2024 | 41446 | 0 | 2024-06-08 |  | 1
2022 | Region IV-A | BATANGAS | LIPA CITY (BATANGAS) | P00640550LZ | Rehabilitation / Major Repair of Drainage Structure | 121.1473 | 13.8696 | 9900000 | 9603000 | 2022 | KENSAL RISE CONSTRUCTION | 4620 | 2022 | 2022-08-05 | 04/04/2022 | 297000 | 0 | 2022-08-04 |  | 1
2021 | Region IV-B | ORIENTAL MINDORO |  | P00561405LZ | Construction of Flood Mitigation Structure | 121.2869 | 12.3511 | 9799477.02 | 9899953.64 | 2022 | ANDREM CONSTRUCTION SERVICE | 4621 | 2021 | 2022-09-23 | 04/07/2022 | 0 | 100476.62 | 2022-09-22 |  | 1
2024 | National Capital Region | PASIG CITY | CITY OF PASIG (METROPOLITAN MANILA) | P00824587LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.0909 | 14.5762 | 16659775.01 | 16320409.49 | 2024 | TOPNOTCH CATALYST BUILDERS INC. | 4622 | 2024 | 2024-11-03 | 04/08/2024 | 339365.52 | 0 | 2024-11-02 |  | 1
2021 | Cordillera Administrative Region | KALINGA |  | P00525933LZ | Construction of Drainage Structure | 121.1749 | 17.3997 | 1960000 | 1960000 | 2022 | JBC BUILDERS | 4623 | 2021 | 2022-08-22 | 04/10/2022 | 0 | 0 | 2022-07-13 |  | 40
2024 | Region II | NUEVA VIZCAYA | BAMBANG (NUEVA VIZCAYA) | P00843253LZ | Construction of Flood Mitigation Structure | 121.0913 | 16.3982 | 91675000 | 91675000 | 2024 | DALCON CONSTRUCTION | 4624 | 2024 | 2024-05-15 | 03/08/2024 | 0 | 0 | 2025-01-16 | 246
2025 | Region IV-B | ORIENTAL MINDORO | CITY OF CALAPAN (CAPITAL) (ORIENTAL MINDORO) | P00921195LZ | Construction of Flood Mitigation Structure | 121.2278 | 13.3272 | 49000000 | 48999976.56 | 2025 | MINDALIFI CONSTRUCTION AND SUPPLY | 4625 | 2025 | 2025-04-14 | 02/12/2025 | 23.44 | 0 | 2025-11-10 | 210
2024 | Region III | AURORA | DINGALAN (AURORA) | P00838524LZ | Construction of Flood Mitigation Structure | 121.3925 | 15.3934 | 16887500 | 16887500 | 2024 | DALCON CONSTRUCTION | 4626 | 2024 | 2024-09-20 | 04/30/2024 | 0 | 0 | 2024-09-19 |  | 1
2023 | Region IV-A | LAGUNA | BAY (LAGUNA) | P00725822LZ | Construction of Revetment | 121.287 | 14.1867 | 72375000 | 72369586.56 | 2024 | ST. MATTHEW GEN. CONTRACTOR & DEVELOPMENT CORP. / FOURTH GENERATION T CONSTRUCTION | 4627 | 2023 | 2024-03-27 | 02/23/2023 | 5413.44 | 0 | 2024-03-26 |  | 1
2023 | National Capital Region | MAKATI CITY | CITY OF MAKATI (METROPOLITAN MANILA) | P00737392LZ | Rehabilitation / Major Repair of Drainage Structure | 121.065 | 14.546 | 29700000 | 29700000 | 2023 | THE STEADFAST BUILDERS | 4628 | 2023 | 2023-07-14 | 02/15/2023 | 0 | 0 | 2023-07-13 |  | 1
2023 | Region IV-A | LAGUNA | CITY OF CALAMBA (LAGUNA) | P00737519LZ | Rehabilitation / Major Repair of Drainage Structure | 121.175 | 14.1809 | 6930000 | 6748121.34 | 2023 | EOZ CONSTRUCTION | 4629 | 2023 | 2023-08-14 | 03/27/2023 | 181878.66 | 0 | 2023-08-13 |  | 1
2021 | Cordillera Administrative Region | MOUNTAIN PROVINCE |  | P00525554LZ | Construction of Flood Mitigation Structure | 121.3939 | 17.1878 | 84270555 | 84270555 | 2023 | MG SAMIDAN CONSTRUCTION / R.S. SEPIAN CONSTRUCTION & TRUCKING | 4630 | 2021 | 2023-01-11 | 04/07/2022 | 0 | 0 | 2023-01-10 |  | 1
2022 | Region IV-A | RIZAL | CITY OF ANTIPOLO (RIZAL) | P00620634LZ | Construction of Flood Mitigation Structure | 121.288 | 14.6269 | 29400000 | 29398503.21 | 2023 | 1C4M BUILDERS INC. | 4631 | 2022 | 2023-07-22 | 02/28/2022 | 1496.79 | 0 | 2023-07-21 |  | 1
2024 | Cordillera Administrative Region | IFUGAO | ALFONSO LISTA (POTIA) (IFUGAO) | P00821143LZ | Construction of Flood Mitigation Structure | 121.2279 | 16.7531 | 96492879.47 | 96500000 | 2025 | DJY CONSTRUCTION | 4632 | 2024 | 2025-03-05 | 03/18/2024 | 0 | 7120.53 | 2025-03-04 |  | 1
2022 | National Capital Region | PATEROS | TAGUIG CITY (METROPOLITAN MANILA) | P00620004LZ | Construction of Slope Protection Structure | 121.065 | 14.5352 | 72374642.72 | 68755910.58 | 2022 | TUCHAR CONSTRUCTION CORP. (FORMERLY:TUCHAR CONSTRU | 4633 | 2022 | 2022-09-30 | 03/24/2022 | 3618732.14 | 0 | 2022-10-18 | 18
2023 | Region IV-A | RIZAL | MONTALBAN (RIZAL) | P00727368LZ | Construction of Flood Mitigation Structure | 121.1474 | 14.7212 | 49000000 | 41638341.17 | 2023 | TUCHAR CONSTRUCTION CORP. (FORMERLY:TUCHAR CONSTRU | 4634 | 2023 | 2023-09-25 | 06/07/2023 | 7361658.83 | 0 | 2024-02-07 | 135
2023 | Region IV-A | LAGUNA | CITY OF CALAMBA (LAGUNA) | P00725820LZ | Construction of Revetment | 121.1756 | 14.2268 | 96500000 | 93989732.06 | 2023 | MSV CONSTRUCTION AND SUPPLIES | 4635 | 2023 | 2023-12-31 | 02/08/2023 | 2510267.94 | 0 | 2023-12-30 |  | 1
2023 | Region IV-A | RIZAL | CITY OF ANTIPOLO (RIZAL) | P00726240LZ | Construction of Flood Mitigation Structure | 121.2896 | 14.6211 | 49000000 | 48990287.77 | 2023 | BICOL GOLDROCK CONSTRUCTION CORPORATION | 4636 | 2023 | 2023-12-20 | 04/05/2023 | 9712.23 | 0 | 2024-02-27 | 69
2024 | Cordillera Administrative Region | IFUGAO | LAMUT (IFUGAO) | P00821534LZ | Construction of Flood Mitigation Structure | 121.2279 | 16.7531 | 48246600.07 | 48250000 | 2024 | DJY CONSTRUCTION | 4637 | 2024 | 2024-12-01 | 03/18/2024 | 0 | 3399.93 | 2024-11-30 |  | 1
2024 | Cordillera Administrative Region | IFUGAO | MAYOYAO (IFUGAO) | P00824841LZ | Construction of Flood Mitigation Structure | 121.394 | 16.8572 | 67520258.68 | 67550000 | 2024 | JLY CONSTRUCTION / R.S. SEPIAN CONSTRUCTION & TRUCKING | 4638 | 2024 | 2024-08-27 | 02/20/2024 | 0 | 29741.32 | 2024-10-09 | 43
2022 | Region II | CAGAYAN | CLAVERIA (CAGAYAN) | P00621527LZ | Construction of Flood Mitigation Structure | 121.0915 | 18.5626 | 19600000 | 19600000 | 2022 | SKYLINE CONSTRUCTION, EQUIPMENT AND DEVELOPMENT CORPORATION(FORMERLY: EDDIE G. GUILLEN BUILDERS INC. | 4639 | 2022 | 2022-12-11 | 03/28/2022 | 0 | 0 | 2022-12-08 |  | 3
2023 | Region II | CAGAYAN | CLAVERIA (CAGAYAN) | P00726116LZ | Construction of Flood Mitigation Structure | 121.1475 | 18.6155 | 19600000 | 19600000 | 2024 | MILESTONE 888 CONSTRUCTION INC. | 4640 | 2023 | 2024-02-16 | 02/03/2023 | 0 | 0 | 2023-09-06 |  | 163
2023 | Region IV-A | LAGUNA | CITY OF CALAMBA (LAGUNA) | P00726227LZ | Construction of Revetment | 121.176 | 14.2278 | 49000000 | 47780973.8 | 2023 | PASCAL CONSTRUCTION | 4641 | 2023 | 2023-11-22 | 02/08/2023 | 1219026.2 | 0 | 2023-11-21 |  | 1
2023 | Region IV-B | ORIENTAL MINDORO | VICTORIA (ORIENTAL MINDORO) | P00727184LZ | Construction of Drainage Structure | 121.2903 | 13.1268 | 4604040 | 4604034.99 | 2023 | JCL86 BUILDERS INC. | 4642 | 2023 | 2023-06-27 | 03/30/2023 | 5.01 | 0 | 2023-06-28 | 1
2023 | Region IV-A | RIZAL | CITY OF ANTIPOLO (RIZAL) | P00726245LZ | Construction of Flood Mitigation Structure | 121.2285 | 14.6577 | 49000000 | 48999997.09 | 2023 | BELL CONSTRUCTION | 4643 | 2023 | 2023-09-24 | 03/21/2023 | 2.91 | 0 | 2023-11-14 | 51
2024 | National Capital Region | TAGUIG CITY | TAGUIG CITY (METROPOLITAN MANILA) | P00821075LZ | Construction of Slope Protection Structure | 121.065 | 14.4974 | 96499479.08 | 94569489.5 | 2024 | TOUGHBUILT CONSTRUCTION & TRADING, INC. | 4644 | 2024 | 2024-09-11 | 02/13/2024 | 1929989.58 | 0 | 2024-10-08 | 27
2023 | National Capital Region | MARIKINA CITY | CITY OF MARIKINA (METROPOLITAN MANILA) | P00742233LZ | Rehabilitation / Major Repair of Drainage Structure | 121.0915 | 14.649 | 16579997.38 | 15747899 | 2024 | BELL CONSTRUCTION | 4645 | 2023 | 2024-01-03 | 06/08/2023 | 832098.38 | 0 | 2024-01-02 |  | 1
2023 | Region IV-B | ORIENTAL MINDORO | PINAMALAYAN (ORIENTAL MINDORO) | P00742464LZ | Construction of Drainage Structure | 121.3953 | 12.9989 | 4949948.96 | 4892177.49 | 2023 | LUMEL GLENN CONSTRUCTION | 4646 | 2023 | 2023-06-26 | 03/24/2023 | 57771.47 | 0 | 2023-06-25 |  | 1
2021 | Cordillera Administrative Region | KALINGA |  | P00525940LZ | Construction of Drainage Structure | 121.1477 | 17.2642 | 2940000 | 2886474.56 | 2022 | SALTAN RIVER CORPORATION | 4647 | 2021 | 2022-10-24 | 03/24/2022 | 53525.44 | 0 | 2022-07-01 |  | 115
2023 | Region IV-A | LAGUNA | BAY (LAGUNA) | P00725795LZ | Construction of Flood Mitigation Structure | 121.2908 | 14.1911 | 48250000 | 47042828.71 | 2024 | JTC CRUZ CONSTRUCTION CO., INC. | 4648 | 2023 | 2024-12-31 | 02/28/2023 | 1207171.29 | 0 | 2024-12-30 |  | 1
2022 | Cordillera Administrative Region | IFUGAO | LAMUT (IFUGAO) | P00621004LZ | Construction of Flood Mitigation Structure | 121.1764 | 16.6483 | 38109134.61 | 38105039.76 | 2023 | DJY CONSTRUCTION | 4649 | 2022 | 2023-07-13 | 08/09/2022 | 4094.85 | 0 | 2023-07-12 |  | 1
2023 | Region II | CAGAYAN | CLAVERIA (CAGAYAN) | P00742296LZ | Construction of Flood Mitigation Structure | 121.2286 | 18.5658 | 4950000 | 4900020.07 | 2023 | DANDEX CONSTRUCTION | 4650 | 2023 | 2023-07-14 | 04/14/2023 | 49979.93 | 0 | 2023-07-13 |  | 1
2024 | Region IV-A | BATANGAS | MATAASNAKAHOY (BATANGAS) | P00846040LZ | Construction of Flood Mitigation Structure | 121.0917 | 14.0041 | 4950000 | 4948945.76 | 2024 | ISHIZAKI CONSTRUCTION & DEVELOPMENT CORPORATION | 4651 | 2024 | 2024-07-10 | 02/15/2024 | 1054.24 | 0 | 2024-07-12 | 2
2022 | Region IV-A | BATANGAS | SAN JUAN (BATANGAS) | P00630951LZ | Construction of Revetment | 121.396 | 13.8458 | 72375000 | 70198191.76 | 2022 | ST. TIMOTHY CONSTRUCTION CORPORATION | 4652 | 2022 | 2022-10-31 | 02/25/2022 | 2176808.24 | 0 | 2022-10-30 |  | 1
2023 | Region IV-A | RIZAL | MONTALBAN (RIZAL) | P00726257LZ | Construction of Flood Mitigation Structure | 121.1478 | 14.7371 | 49000000 | 40554378.68 | 2023 | ST. TIMOTHY CONSTRUCTION CORPORATION | 4653 | 2023 | 2023-09-25 | 05/08/2023 | 8445621.32 | 0 | 2024-01-31 | 128
2023 | Region IV-A | RIZAL | CITY OF ANTIPOLO (RIZAL) | P00726247LZ | Construction of Flood Mitigation Structure | 121.2291 | 14.6604 | 49000000 | 48999994.47 | 2023 | BELL CONSTRUCTION | 4654 | 2023 | 2023-12-22 | 03/21/2023 | 5.53 | 0 | 2024-01-13 | 22
2022 | Region IV-A | LAGUNA | BAY (LAGUNA) | P00631299LZ | Construction of Flood Mitigation Structure | 121.2913 | 14.1977 | 19600000 | 19596179.97 | 2023 | 11 DIAMOND EAGLE CONSTRUCTION CORPORATION (FORMERLY:11 DIAMOND EAGLE CONSTRUCTION) | 4655 | 2022 | 2023-11-28 | 01/09/2023 | 3820.03 | 0 | 2024-01-11 | 44
2021 | National Capital Region | MAKATI CITY |  | P00561152LZ | Construction of Flood Mitigation Structure | 121.0652 | 14.5548 | 34300000 | 33648374.93 | 2022 | AARCON BUILDERS | 4656 | 2021 | 2022-08-22 | 03/01/2021 | 651625.07 | 0 | 2021-09-25 |  | 331
2023 | Region IV-A | BATANGAS | SAN JUAN (BATANGAS) | P00726928LZ | Construction of Flood Mitigation Structure | 121.3974 | 13.8455 | 96500000 | 96500000 | 2024 | POWER K CONSTRUCTION SUPPLY & SERVICES | 4657 | 2023 | 2024-01-21 | 04/05/2023 | 0 | 0 | 2024-01-20 |  | 1
2023 | National Capital Region | TAGUIG CITY | TAGUIG CITY (METROPOLITAN MANILA) | P00726823LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.0919 | 14.5285 | 86849579.53 | 82463675.76 | 2023 | TOPNOTCH CATALYST BUILDERS INC. / BLACK HARDHAT INC. (FORMERLY: JCHARDHAT INC.) | 4658 | 2023 | 2023-10-20 | 03/22/2023 | 4385903.77 | 0 | 2023-11-15 | 26
2024 | Region IV-B | ORIENTAL MINDORO | NAUJAN (ORIENTAL MINDORO) | P00823572LZ | Construction of Flood Mitigation Structure | 121.1765 | 13.239 | 289500000 | 289496391.8 | 2024 | ALPHA & OMEGA GEN. CONTRACTOR & DEVELOPMENT CORP. | 4659 | 2024 | 2024-07-15 | 03/09/2024 | 3608.2 | 0 | 2025-03-02 | 230
2024 | Region IV-A | BATANGAS | CITY OF TANAUAN (BATANGAS) | P00839110LZ | Rehabilitation / Major Repair of Drainage Structure | 121.1479 | 14.0904 | 4950000 | 4948737 | 2024 | JERIS CONSTRUCTION AND SUPPLY | 4660 | 2024 | 2024-06-17 | 02/19/2024 | 1263 | 0 | 2024-06-16 |  | 1
2022 | Region IV-A | LAGUNA | LOS BAÃ‘OS (LAGUNA) | P00620245LZ | Construction of Flood Mitigation Structure | 121.2294 | 14.1871 | 86850000 | 86847262.08 | 2023 | 11 DIAMOND EAGLE CONSTRUCTION CORPORATION (FORMERLY:11 DIAMOND EAGLE CONSTRUCTION) | 4661 | 2022 | 2023-01-08 | 03/09/2022 | 2737.92 | 0 | 2023-01-07 |  | 1
2022 | Region III | BULACAN | CITY OF SAN JOSE DEL MONTE (BULACAN) | P00637017LZ | Construction of Slope Protection Structure | 121.0653 | 14.7979 | 96499596.86 | 96471127.99 | 2023 | ST. MATTHEW GEN. CONTRACTOR & DEVELOPMENT CORP. | 4662 | 2022 | 2023-05-18 | 05/26/2022 | 28468.87 | 0 | 2023-06-25 | 38
2023 | Region IV-A | BATANGAS | SAN JUAN (BATANGAS) | P00742185LZ | Construction of Slope Protection Structure | 121.3978 | 13.845 | 99000000 | 96030000 | 2024 | STRUKTURA TEKNIKA SERVICES CO. / E.M. CUERPO, INC. | 4663 | 2023 | 2024-09-10 | 05/15/2023 | 2970000 | 0 | 2024-02-29 |  | 194
2024 | National Capital Region | TAGUIG CITY | TAGUIG CITY (METROPOLITAN MANILA) | P00821436LZ | Construction of Slope Protection Structure | 121.0922 | 14.5309 | 9799733.66 | 9603743.18 | 2024 | B. VALENCERINA TRADING & CONSTRUCTION | 4664 | 2024 | 2024-05-07 | 04/08/2024 | 195990.48 | 0 | 2024-05-06 |  | 1
2024 | Cordillera Administrative Region | IFUGAO | ALFONSO LISTA (POTIA) (IFUGAO) | P00821539LZ | Construction of Flood Mitigation Structure | 121.178 | 16.9284 | 19596856.89 | 19600000 | 2024 | MA CONSTRUCTION | 4665 | 2024 | 2024-08-18 | 02/21/2024 | 0 | 3143.11 | 2024-08-17 |  | 1
2022 | Cordillera Administrative Region | APAYAO | KABUGAO (CAPITAL) (APAYAO) | P00620987LZ | Construction of Flood Mitigation Structure | 121.148 | 18.0265 | 23871900.8 | 23872800 | 2022 | TAGEL CORPORATION | 4666 | 2022 | 2022-11-28 | 04/04/2022 | 0 | 899.2 | 2022-12-29 | 31
2021 | Region IV-B | ORIENTAL MINDORO |  | P00526453LZ | Construction of Flood Mitigation Structure | 121.2308 | 13.3714 | 38220000 | 38200927.2 | 2022 | ORANI CONSTRUCTION AND SUPPLY CORPORATION (FORMERLY:ORANI BUILDERS & SUPPLY) | 4667 | 2021 | 2022-12-14 | 03/07/2022 | 19072.8 | 0 | 2022-12-16 | 2
2021 | National Capital Region | MAKATI CITY |  | P00525765LZ | Construction of Flood Mitigation Structure | 121.0654 | 14.5479 | 21560000 | 20481342.58 | 2023 | C.B. TAMPENGCO CONSTRUCTION & SUPPLY | 4668 | 2021 | 2023-01-08 | 03/22/2022 | 1078657.42 | 0 | 2023-01-07 |  | 1
2024 | Region IV-A | RIZAL | TANAY (RIZAL) | P00846093LZ | Construction of Drainage Structure | 121.2925 | 14.5032 | 4950000 | 4950000 | 2024 | OLIVER AQUINO CONSTRUCTION | 4669 | 2024 | 2024-08-02 | 04/23/2024 | 0 | 0 | 2024-08-01 |  | 1
2024 | National Capital Region | TAGUIG CITY | TAGUIG CITY (METROPOLITAN MANILA) | P00821074LZ | Construction of Slope Protection Structure | 121.0655 | 14.4988 | 96499567.44 | 94569576.09 | 2024 | TOUGHBUILT CONSTRUCTION & TRADING, INC. | 4670 | 2024 | 2024-09-11 | 02/13/2024 | 1929991.35 | 0 | 2024-10-08 | 27
2023 | National Capital Region | MARIKINA CITY | CITY OF MARIKINA (METROPOLITAN MANILA) | P00727228LZ | Construction of Flood Mitigation Facility | 121.0922 | 14.6525 | 97943176.43 | 92990387.76 | 2024 | L.R. TIQUI BUILDERS, INC. / M3 KONSTRACT CORPORATION (FORMERLY:MARGARITA CONSTRUCTION) | 4671 | 2023 | 2024-02-09 | 06/30/2023 | 4952788.67 | 0 | 2024-02-08 |  | 1
2021 | Cordillera Administrative Region | KALINGA |  | P00525941LZ | Construction of Flood Mitigation Structure | 121.1784 | 17.3518 | 9800000 | 9211999.11 | 2022 | SONBLESSED CONSTRUCTION AND SUPPLY | 4672 | 2021 | 2022-10-15 | 04/10/2022 | 588000.89 | 0 | 2022-11-29 | 45
2021 | Region IV-B | ORIENTAL MINDORO |  | P00561192LZ | Construction of Drainage Structure | 121.3986 | 13.0014 | 7840000 | 7590509.36 | 2022 | ANSAVILLA CONSTRUCTION AND DEVELOPMENT CORPORATION | 4673 | 2021 | 2022-09-18 | 04/07/2022 | 249490.64 | 0 | 2022-09-17 |  | 1
2021 | Region IV-A | RIZAL |  | P00561559LZ | Construction of Flood Mitigation Structure | 121.1481 | 14.7206 | 16434000 | 15965017.3 | 2022 | JORENZ BUILDERS DEVELOPMENT CORP. | 4674 | 2021 | 2022-11-14 | 12/16/2021 | 468982.7 | 0 | 2022-12-10 | 26
2021 | Cordillera Administrative Region | KALINGA |  | P00526387LZ | Construction of Flood Mitigation Structure | 121.1481 | 17.2639 | 4900000 | 3977831.03 | 2022 | FEREST DWAYNE CONSTRUCTION | 4675 | 2021 | 2022-12-25 | 04/10/2022 | 922168.97 | 0 | 2022-11-27 |  | 28
2022 | Region II | CAGAYAN | CLAVERIA (CAGAYAN) | P00621039LZ | Construction of Flood Mitigation Structure | 121.1483 | 18.6149 | 29400000 | 29400000 | 2022 | SKYLINE CONSTRUCTION, EQUIPMENT AND DEVELOPMENT CORPORATION(FORMERLY: EDDIE G. GUILLEN BUILDERS INC. | 4676 | 2022 | 2022-12-17 | 03/29/2022 | 0 | 0 | 2022-12-16 |  | 1
2023 | Region III | NUEVA ECIJA | RIZAL (NUEVA ECIJA) | P00726168LZ | Construction of Flood Mitigation Structure | 121.1485 | 15.6952 | 49000000 | 48994904.22 | 2023 | IRC CONSTRUCTION & SUPPLIES / SYMMETRICON BUILDERS CORP. | 4677 | 2023 | 2023-06-09 | 02/21/2023 | 5095.78 | 0 | 2023-09-17 | 100
2023 | Region IV-A | LAGUNA | BAY (LAGUNA) | P00725794LZ | Construction of Flood Mitigation Structure | 121.2927 | 14.193 | 48250000 | 47042947.37 | 2024 | JTC CRUZ CONSTRUCTION CO., INC. | 4678 | 2023 | 2024-03-21 | 02/28/2023 | 1207052.63 | 0 | 2024-03-15 |  | 6
2022 | Cordillera Administrative Region | KALINGA | BALBALAN (KALINGA) | P00620488LZ | Construction of Flood Mitigation Structure | 121.0657 | 17.4859 | 14700000 | 14326756.83 | 2023 | BHM CONSTRUCTION | 4679 | 2022 | 2023-05-29 | 02/21/2022 | 373243.17 | 0 | 2022-10-21 |  | 220
2023 | Region IV-A | RIZAL | CITY OF ANTIPOLO (RIZAL) | P00726238LZ | Construction of Flood Mitigation Structure | 121.1485 | 14.6376 | 49000000 | 49000000 | 2023 | YPR GEN. CONTRACTOR AND CONSTRUCTION SUPPLY INC. / TOP KMC CONSTRUCTION AND SUPPLY CORP. | 4680 | 2023 | 2023-07-31 | 02/16/2023 | 0 | 0 | 2023-11-11 | 103
2022 | Region IV-A | RIZAL | MORONG (RIZAL) | P00620650LZ | Construction of Flood Mitigation Structure | 121.2308 | 14.5147 | 49000000 | 49000000 | 2022 | DOUBLE 12 CONSTRUCTION & SUPPLY | 4681 | 2022 | 2022-07-15 | 02/15/2022 | 0 | 0 | 2022-09-28 | 75
2023 | Region IV-A | RIZAL | MONTALBAN (RIZAL) | P00726927LZ | Construction of Flood Mitigation Structure | 121.1489 | 14.7464 | 96500000 | 78557807.92 | 2024 | PERSAN CONSTRUCTION, INC. (FORMERLY: PERSAN CONST. | 4682 | 2023 | 2024-05-27 | 05/10/2023 | 17942192.08 | 0 | 2024-06-03 | 7
2024 | National Capital Region | TAGUIG CITY | TAGUIG CITY (METROPOLITAN MANILA) | P00821073LZ | Construction of Slope Protection Structure | 121.0659 | 14.5001 | 96499443.41 | 94550154.65 | 2024 | TOUGHBUILT CONSTRUCTION & TRADING, INC. | 4683 | 2024 | 2024-09-11 | 02/13/2024 | 1949288.76 | 0 | 2024-10-08 | 27
2023 | Region II | CAGAYAN | SANCHEZ-MIRA (CAGAYAN) | P00726114LZ | Construction of Flood Mitigation Structure | 121.2308 | 18.5553 | 49000000 | 49000000 | 2023 | TJMT CONSTRUCTION / RAMIKE CONSTRUCTION | 4684 | 2023 | 2023-10-02 | 02/01/2023 | 0 | 0 | 2023-10-01 |  | 1
2023 | Region IV-A | BATANGAS | LIPA CITY (BATANGAS) | P00737500LZ | Construction of Drainage Structure | 121.1808 | 13.9655 | 4950000 | 4800901.5 | 2023 | MAC BUILDERS CIVIL ENGINEERING CONSTRUCTION | 4685 | 2023 | 2023-05-18 | 02/13/2023 | 149098.5 | 0 | 2023-05-17 |  | 1
2022 | Cordillera Administrative Region | MOUNTAIN PROVINCE | PARACELIS (MOUNTAIN PROVINCE) | P00620141LZ | Construction of Flood Mitigation Structure | 121.3997 | 17.2556 | 81060000 | 81060000 | 2023 | MG SAMIDAN CONSTRUCTION / R.S. SEPIAN CONSTRUCTION & TRUCKING | 4686 | 2022 | 2023-01-29 | 02/24/2022 | 0 | 0 | 2023-01-28 |  | 1
2021 | Region IV-A | LAGUNA |  | P00561544LZ | Construction of Flood Mitigation Structure | 121.2933 | 14.037 | 29400000 | 29400000 | 2022 | T. SOLOMON CONSTRUCTION AND DEVELOPMENT CORPORATIO | 4687 | 2021 | 2022-09-15 | 02/18/2022 | 0 | 0 | 2022-09-14 |  | 1
2023 | Region II | CAGAYAN | CLAVERIA (CAGAYAN) | P00726438LZ | Construction of Flood Mitigation Structure | 121.0924 | 18.5517 | 83950800 | 83950800 | 2024 | SKYLINE CONSTRUCTION, EQUIPMENT AND DEVELOPMENT CORPORATION(FORMERLY: EDDIE G. GUILLEN BUILDERS INC. | 4688 | 2023 | 2024-07-12 | 02/06/2023 | 0 | 0 | 2023-11-25 |  | 230
2024 | Region III | NUEVA ECIJA | RIZAL (NUEVA ECIJA) | P00823445LZ | Construction of Flood Mitigation Structure | 121.1498 | 15.6964 | 48250000 | 47767448.6 | 2024 | IRC CONSTRUCTION & SUPPLIES / SYMMETRICON BUILDERS CORP. | 4689 | 2024 | 2024-08-31 | 03/15/2024 | 482551.4 | 0 | 2024-10-09 | 39
2023 | Region IV-B | ORIENTAL MINDORO | VICTORIA (ORIENTAL MINDORO) | P00742458LZ | Construction of Flood Mitigation Structure | 121.2953 | 13.1653 | 4950000 | 4949993.18 | 2023 | MARTINEZ ENTERPRISES | 4690 | 2023 | 2023-04-19 | 03/28/2023 | 6.82 | 0 | 2023-05-23 | 34
2022 | Region IV-A | RIZAL | CITY OF ANTIPOLO (RIZAL) | P00620217LZ | Construction of Flood Mitigation Structure | 121.2316 | 14.6589 | 55033950 | 55033758.16 | 2022 | ST. TIMOTHY CONSTRUCTION CORPORATION | 4691 | 2022 | 2022-10-27 | 03/02/2022 | 191.84 | 0 | 2022-10-26 |  | 1
2024 | National Capital Region | MARIKINA CITY | CITY OF MARIKINA (METROPOLITAN MANILA) | P00824794LZ | Construction of Flood Mitigation Structure | 121.0924 | 14.6404 | 67549147.08 | 66132277.62 | 2024 | BELL CONSTRUCTION | 4692 | 2024 | 2024-12-13 | 04/04/2024 | 1416869.46 | 0 | 2025-02-05 | 54
2022 | National Capital Region | PATEROS | TAGUIG CITY (METROPOLITAN MANILA) | P00620003LZ | Construction of Slope Protection Structure | 121.0661 | 14.5353 | 72374394.92 | 68719487.97 | 2022 | HONY TRADING & CONSTRUCTION | 4693 | 2022 | 2022-09-30 | 03/24/2022 | 3654906.95 | 0 | 2022-10-18 | 18
2023 | Cordillera Administrative Region | APAYAO | LUNA (APAYAO) | P00726400LZ | Construction of Flood Mitigation Structure | 121.4017 | 18.2671 | 96500000 | 96493463.88 | 2024 | ISNAG BUILDERS & DEV'T. CORPORATION / TAGEL CORPORATION | 4694 | 2023 | 2024-03-20 | 05/05/2023 | 6536.12 | 0 | 2024-05-05 | 46
2023 | Region IV-A | RIZAL | CITY OF ANTIPOLO (RIZAL) | P00726253LZ | Construction of Flood Mitigation Structure | 121.1812 | 14.5902 | 31360000 | 31359995 | 2023 | LTDL BUILDERS | 4695 | 2023 | 2023-11-13 | 02/20/2023 | 5 | 0 | 2023-11-12 |  | 1
2024 | Region IV-A | BATANGAS | CITY OF SANTO TOMAS (BATANGAS) | P00823556LZ | Construction of Flood Mitigation Structure | 121.1499 | 14.0908 | 96500000 | 96499092.75 | 2024 | MAR-VEL CONSTRUCTION & SUPPLY | 4696 | 2024 | 2024-11-08 | 03/25/2024 | 907.25 | 0 | 2025-01-17 | 70
2024 | Region II | NUEVA VIZCAYA | KASIBU (NUEVA VIZCAYA) | P00820787LZ | Construction of Flood Mitigation Structure | 121.2967 | 16.3192 | 37567320 | 37553841.26 | 2024 | BRG CONSTRUCTION | 4697 | 2024 | 2024-08-14 | 02/08/2024 | 13478.74 | 0 | 2024-08-13 |  | 1
2021 | Region IV-B | ORIENTAL MINDORO |  | P00526458LZ | Construction of Flood Mitigation Structure | 121.4022 | 12.8672 | 19599570.67 | 19599916.63 | 2022 | GREEN ISLAND ENTERPRISES | 4698 | 2021 | 2022-08-12 | 04/08/2022 | 0 | 345.96 | 2022-10-13 | 62
2021 | National Capital Region | QUEZON CITY |  | P00561443LZ | Construction of Flood Mitigation Structure | 121.0665 | 14.726 | 98000000 | 94973033 | 2022 | PRECIOUS CONSTRUCTION / DARCY & ANNA BUILDERS & TRADING | 4699 | 2021 | 2022-12-01 | 12/07/2021 | 3026967 | 0 | 2022-11-30 |  | 1
2023 | Region IV-A | BATANGAS | LOBO (BATANGAS) | P00726548LZ | Construction of Flood Mitigation Structure | 121.2322 | 13.661 | 96500000 | 96500000 | 2023 | EFREN RAMIREZ CONSTRUCTION AND GENERAL SERVICES CORPORATION / EGB CONSTRUCTION CORPORATION (FORMERLY: EGB CONSTRUCTION) | 4700 | 2023 | 2023-12-15 | 02/10/2023 | 0 | 0 | 2023-12-14 |  | 1
2022 | Region IV-A | RIZAL | CITY OF ANTIPOLO (RIZAL) | P00620627LZ | Construction of Flood Mitigation Structure | 121.1816 | 14.5996 | 9800000 | 9454403.7 | 2022 | 1C4M BUILDERS INC. | 4701 | 2022 | 2022-08-20 | 02/22/2022 | 345596.3 | 0 | 2022-08-19 |  | 1
2024 | Region IV-B | NORTHERN SAMAR | VICTORIA (NORTHERN SAMAR) | P00824749LZ | Construction of Flood Mitigation Structure | 121.2975 | 13.1914 | 3217500 | 3184912.74 | 2024 | KINGSROAD CONSTRUCTION | 4702 | 2024 | 2024-06-06 | 02/08/2024 | 32587.26 | 0 | 2024-06-05 |  | 1
2022 | Region IV-A | RIZAL | ANGONO (RIZAL) | P00632909LZ | Construction of Flood Mitigation Structure | 121.1501 | 14.5241 | 9900000 | 9900000 | 2022 | DJL ROBLES BUILDERS | 4703 | 2022 | 2022-10-05 | 03/28/2022 | 0 | 0 | 2022-10-07 | 2
2024 | Region IV-B | ORIENTAL MINDORO | PINAMALAYAN (ORIENTAL MINDORO) | P00821366LZ | Construction of Flood Mitigation Structure | 121.4022 | 13.0067 | 67550000 | 67547027.84 | 2025 | LUMEL GLENN CONSTRUCTION | 4704 | 2024 | 2025-01-31 | 02/15/2024 | 2972.16 | 0 | 2025-01-30 |  | 1
2024 | National Capital Region | MARIKINA CITY | CITY OF MARIKINA (METROPOLITAN MANILA) | P00838333LZ | Construction of Flood Mitigation Structure | 121.0926 | 14.6531 | 96499466.53 | 94530664.34 | 2025 | M3 KONSTRACT CORPORATION (FORMERLY:MARGARITA CONSTRUCTION) | 4705 | 2024 | 2025-02-13 | 04/01/2024 | 1968802.19 | 0 | 2025-02-12 |  | 1
2021 | National Capital Region | QUEZON CITY |  | P00561158LZ | Rehabilitation / Major Repair of Drainage Structure | 121.0665 | 14.726 | 29399750 | 28417758 | 2022 | C & F CONSTRUCTION & DEVELOPMENT CORPORATION | 4706 | 2021 | 2022-10-31 | 02/16/2022 | 981992 | 0 | 2022-10-12 |  | 19
2024 | Region II | CAGAYAN | SANCHEZ-MIRA (CAGAYAN) | P00823333LZ | Construction of Flood Mitigation Structure | 121.2324 | 18.5555 | 48250000 | 48248286.07 | 2024 | OCP CONSTRUCTION | 4707 | 2024 | 2024-09-06 | 04/05/2024 | 1713.93 | 0 | 2024-10-12 | 36
2023 | Region IV-A | BATANGAS | ROSARIO (BATANGAS) | P00742400LZ | Construction of Drainage Structure | 121.2996 | 13.7351 | 4950000 | 4801500 | 2023 | MAC BUILDERS CIVIL ENGINEERING CONSTRUCTION | 4708 | 2023 | 2023-08-28 | 03/30/2023 | 148500 | 0 | 2023-07-26 |  | 33
2022 | Cordillera Administrative Region | KALINGA | LUBUAGAN (KALINGA) | P00620487LZ | Construction of Flood Mitigation Structure | 121.1503 | 17.3549 | 4900000 | 4467751.53 | 2022 | SONBLESSED CONSTRUCTION AND SUPPLY | 4709 | 2022 | 2022-09-23 | 04/06/2022 | 432248.47 | 0 | 2022-06-12 |  | 103
2024 | Region IV-A | BATANGAS | SAN JUAN (BATANGAS) | P00820320LZ | Construction of Flood Mitigation Structure | 121.4023 | 13.8133 | 77200000 | 77200000 | 2024 | HAWK KEY CONSTRUCTION AND GENERAL MERCHANDISE CORPORATION / YPR GEN. CONTRACTOR AND CONSTRUCTION SUPPLY INC. | 4710 | 2024 | 2024-09-13 | 02/19/2024 | 0 | 0 | 2024-10-24 | 41
2022 | National Capital Region | QUEZON CITY | QUEZON CITY (METROPOLITAN MANILA) | P00631048LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.0665 | 14.726 | 19600000 | 19600000 | 2022 | CG GENERAL CONSTRUCTION & DEVELOPMENT CORPORATION | 4711 | 2022 | 2022-10-10 | 02/14/2022 | 0 | 0 | 2022-12-09 | 60
2022 | Region IV-A | LAGUNA | LOS BAÃ‘OS (LAGUNA) | P00620246LZ | Construction of Flood Mitigation Structure | 121.2327 | 14.1807 | 86850000 | 86847784.09 | 2022 | 11 DIAMOND EAGLE CONSTRUCTION CORPORATION (FORMERLY:11 DIAMOND EAGLE CONSTRUCTION) | 4712 | 2022 | 2022-12-23 | 02/21/2022 | 2215.91 | 0 | 2022-12-22 |  | 1
2023 | Region IV-A | LAGUNA | CITY OF CALAMBA (LAGUNA) | P00726228LZ | Construction of Revetment | 121.1816 | 14.2235 | 44100000 | 42953626 | 2023 | E.R. VENZON CONSTRUCTION | 4713 | 2023 | 2023-11-29 | 02/21/2023 | 1146374 | 0 | 2023-11-28 |  | 1
2023 | Region IV-A | RIZAL | MONTALBAN (RIZAL) | P00737542LZ | Construction of Flood Mitigation Structure | 121.1503 | 14.7374 | 24750000 | 20056331.71 | 2024 | EL-JAKE BUILDERS | 4714 | 2023 | 2024-03-15 | 07/18/2023 | 4693668.29 | 0 | 2024-03-14 |  | 1
2023 | Cordillera Administrative Region | BENGUET | BAGUIO CITY (BENGUET) | P00736180LZ | Construction of Slope Protection Structure | 121.2998 | 16.9943 | 19557230.5 | 19600000 | 2023 | JLY CONSTRUCTION | 4715 | 2023 | 2023-09-20 | 05/08/2023 | 0 | 42769.5 | 2024-01-04 | 106
2023 | Region IV-A | LAGUNA | SANTA CRUZ (CAPITAL) (LAGUNA) | P00742431LZ | Construction of Drainage Structure | 121.4032 | 14.2844 | 4950000 | 4909938.35 | 2023 | DATZLAV CONSTRUCTION | 4716 | 2023 | 2023-08-04 | 05/04/2023 | 40061.65 | 0 | 2023-08-30 | 26
2024 | National Capital Region | MARIKINA CITY | CITY OF MARIKINA (METROPOLITAN MANILA) | P00823234LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.0926 | 14.6531 | 96499459.32 | 94376471.21 | 2024 | L.R. TIQUI BUILDERS, INC. | 4717 | 2024 | 2024-09-16 | 03/22/2024 | 2122988.11 | 0 | 2024-09-16 | 0
2023 | Region IV-A | BATANGAS | BATANGAS CITY (CAPITAL) (BATANGAS) | P00737491LZ | Construction of Drainage Structure | 121.0666 | 13.7646 | 4950000 | 4950000 | 2023 | BERTO LUCCI BUILDERS & SUPPLY | 4718 | 2023 | 2023-04-26 | 02/08/2023 | 0 | 0 | 2023-04-25 |  | 1
2022 | Region IV-B | ORIENTAL MINDORO | NAUJAN (ORIENTAL MINDORO) | P00621113LZ | Construction of Flood Mitigation Structure | 121.2333 | 13.2314 | 49000000 | 48096753.28 | 2023 | ETVR TRADING & CONSTRUCTION | 4719 | 2022 | 2023-03-27 | 07/14/2022 | 903246.72 | 0 | 2023-04-02 | 6
2024 | Region IV-B | ORIENTAL MINDORO | NAUJAN (ORIENTAL MINDORO) | P00820422LZ | Construction of Flood Mitigation Structure | 121.1818 | 13.2488 | 193000000 | 192996270.3 | 2024 | ELITE GENERAL CONTRACTOR AND DEVELOPMENT CORP. | 4720 | 2024 | 2024-08-15 | 03/09/2024 | 3729.7 | 0 | 2025-03-02 | 199
2024 | Region III | NUEVA ECIJA | GABALDON (BITULOK & SABANI) (NUEVA ECIJA) | P00821586LZ | Construction of Flood Mitigation Structure | 121.3015 | 15.4698 | 48999939.83 | 48019833.25 | 2024 | R.A. PAHATI CONST. & SUPPLY, INC. | 4721 | 2024 | 2024-05-24 | 02/12/2024 | 980106.58 | 0 | 2024-09-07 | 106
2023 | National Capital Region | TAGUIG CITY | TAGUIG CITY (METROPOLITAN MANILA) | P00725522LZ | Construction of Slope Protection Structure | 121.0666 | 14.5013 | 75520650.16 | 71706857.32 | 2023 | 11-16 CONSTRUCTION / HAWK KEY CONSTRUCTION AND GENERAL MERCHANDISE CORPORATION | 4722 | 2023 | 2023-08-15 | 03/15/2023 | 3813792.84 | 0 | 2023-10-09 | 55
2021 | Region IV-B | ORIENTAL MINDORO |  | P00526454LZ | Construction of Flood Mitigation Structure | 121.2333 | 13.2314 | 29400000 | 29399930.62 | 2022 | SIXTEEN ENTERPRISES-CALAPAN BRANCH | 4723 | 2021 | 2022-09-30 | 03/07/2022 | 69.38 | 0 | 2022-09-30 | 0
2023 | Region IV-A | BATANGAS | ROSARIO (BATANGAS) | P00726207LZ | Construction of Flood Mitigation Structure | 121.1822 | 13.8391 | 29400000 | 29400000 | 2023 | TONIJON CONSTRUCTION AND DEVELOPMENT INC. (FORMERLY: TONIJON CONSTRUCTION) | 4724 | 2023 | 2023-08-29 | 02/08/2023 | 0 | 0 | 2023-06-30 |  | 60
2024 | National Capital Region | MARIKINA CITY | CITY OF MARIKINA (METROPOLITAN MANILA) | P00825203LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.0926 | 14.6531 | 9799969.95 | 9550193 | 2024 | 729 CONSTRUCTION, INC. (FORMERLY 722 CONSTRUCTION, INC.) | 4725 | 2024 | 2024-05-07 | 04/08/2024 | 249776.95 | 0 | 2024-05-06 |  | 1
2022 | Region III | NUEVA ECIJA | BONGABON (NUEVA ECIJA) | P00620192LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.1511 | 15.6516 | 82024956.02 | 82025000 | 2022 | JERRY R. SANTIAGO CONSTRUCTION CORP. (FORMERLY: JERRY SANTIAGO CONSTRUCTION) | 4726 | 2022 | 2022-07-29 | 02/24/2022 | 0 | 43.98 | 2022-10-20 | 83
2024 | Region III | AURORA | DINGALAN (AURORA) | P00838523LZ | Construction of Flood Mitigation Structure | 121.4038 | 15.385 | 31850000 | 31362500 | 2024 | DALCON CONSTRUCTION | 4727 | 2024 | 2024-11-11 | 04/30/2024 | 487500 | 0 | 2024-11-10 |  | 1
2023 | Region II | NUEVA VIZCAYA | QUEZON (NUEVA VIZCAYA) | P00727120LZ | Construction of Flood Mitigation Structure | 121.2335 | 16.5111 | 49000000 | 49000000 | 2023 | R.O. BUILDERS & DEVELOPMENT CORPORATION | 4728 | 2023 | 2023-10-21 | 03/03/2023 | 0 | 0 | 2023-10-20 |  | 1
2023 | Region III | NUEVA ECIJA | GABALDON (BITULOK & SABANI) (NUEVA ECIJA) | P00725726LZ | Construction of Flood Mitigation Structure | 121.3017 | 15.471 | 90227416.41 | 88397389.39 | 2023 | R.A. PAHATI CONST. & SUPPLY, INC. | 4729 | 2023 | 2023-05-24 | 02/16/2023 | 1830027.02 | 0 | 2023-10-27 | 156
2022 | National Capital Region | TAGUIG CITY | TAGUIG CITY (METROPOLITAN MANILA) | P00620047LZ | Construction of Flood Mitigation Structure | 121.0667 | 14.5338 | 96499365.4 | 96500000 | 2022 | TOPNOTCH CATALYST BUILDERS INC. | 4730 | 2022 | 2022-07-27 | 02/16/2022 | 0 | 634.6 | 2022-10-12 | 77
2023 | Region IV-B | ORIENTAL MINDORO | CITY OF CALAPAN (CAPITAL) (ORIENTAL MINDORO) | P00727187LZ | Construction of Flood Mitigation Structure | 121.2336 | 13.3509 | 38600000 | 38594287.32 | 2023 | RELY CONSTRUCTION & SUPPLY INC.(FORMERLY: RELY CONSTRUCTION AND SUPPLY) | 4731 | 2023 | 2023-07-26 | 03/29/2023 | 5712.68 | 0 | 2023-10-04 | 70
2023 | Region IV-A | RIZAL | CITY OF ANTIPOLO (RIZAL) | P00726241LZ | Construction of Flood Mitigation Structure | 121.3018 | 14.693 | 49000000 | 48999253.95 | 2023 | BELL CONSTRUCTION | 4732 | 2023 | 2023-12-08 | 03/14/2023 | 746.05 | 0 | 2023-12-07 |  | 1
2024 | Region IV-A | BATANGAS | LIPA CITY (BATANGAS) | P00844772LZ | Construction of Drainage Structure | 121.1828 | 13.878 | 6370000 | 6178418.88 | 2024 | ALBANO CONSTRUCTION AND TRADING | 4733 | 2024 | 2024-08-10 | 04/05/2024 | 191581.12 | 0 | 2024-07-17 |  | 24
2023 | Region IV-A | LAGUNA | CITY OF SANTA ROSA (LAGUNA) | P00740386LZ | Construction of Flood Mitigation Structure | 121.0926 | 14.2569 | 96500000 | 96427776.33 | 2023 | LE BRON CONSTRUCTION | 4734 | 2023 | 2023-12-12 | 04/14/2023 | 72223.67 | 0 | 2024-03-04 | 83
2022 | Region II | NUEVA VIZCAYA | BAYOMBONG (CAPITAL) (NUEVA VIZCAYA) | P00621481LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.1518 | 16.474 | 28950000 | 28950000 | 2022 | G.M. PAJARILLAGA CONSTRUCTION & SUPPLY | 4735 | 2022 | 2022-09-30 | 04/05/2022 | 0 | 0 | 2022-11-14 | 45
2024 | Region IV-A | LAGUNA | LILIW (LAGUNA) | P00820907LZ | Construction of Flood Mitigation Structure | 121.4057 | 14.2032 | 19600000 | 19599999.52 | 2025 | L.P.O. ENTERPRISES | 4736 | 2024 | 2025-01-10 | 07/15/2024 | 0.48 | 0 | 2025-01-09 |  | 1
2024 | Region III | BULACAN | CITY OF SAN JOSE DEL MONTE (BULACAN) | P00820184LZ | Construction of Dike | 121.0668 | 14.83 | 96499675.66 | 96498484.3 | 2024 | ROYAL CROWN MONARCH CONSTRUCTION & SUPPLIES CORP. | 4737 | 2024 | 2024-10-04 | 02/26/2024 | 1191.36 | 0 | 2024-12-16 | 73
2024 | Region IV-B | ORIENTAL MINDORO | CITY OF CALAPAN (CAPITAL) (ORIENTAL MINDORO) | P00821603LZ | Construction of Flood Mitigation Structure | 121.2344 | 13.3528 | 49000000 | 48999817.77 | 2024 | MINDALIFI CONSTRUCTION AND SUPPLY | 4738 | 2024 | 2024-05-08 | 02/08/2024 | 182.23 | 0 | 2024-10-24 | 169
2022 | Region IV-A | RIZAL | CITY OF ANTIPOLO (RIZAL) | P00620621LZ | Construction of Slope Protection Structure | 121.3045 | 14.6921 | 14700000 | 14052374.28 | 2022 | A.J. LAVA BUILDERS CORP. (FORMERLY: A.J. LAVA BUIL | 4739 | 2022 | 2022-09-13 | 02/16/2022 | 647625.72 | 0 | 2022-09-12 |  | 1
2022 | Region IV-B | ORIENTAL MINDORO | CITY OF CALAPAN (CAPITAL) (ORIENTAL MINDORO) | P00639526LZ | Construction of Drainage Structure | 121.1836 | 13.4139 | 43120000 | 43119999.53 | 2023 | FRAMECON BUILDERS | 4740 | 2022 | 2023-03-08 | 07/14/2022 | 0.47 | 0 | 2023-03-07 |  | 1
2021 | Region IV-B | ORIENTAL MINDORO |  | P00561581LZ | Construction of Flood Mitigation Structure | 121.4061 | 12.4436 | 19798667.11 | 19599928.35 | 2022 | D.M. MALIWANAG BUILDERS AND ENTERPRISES | 4741 | 2021 | 2022-11-23 | 04/08/2022 | 198738.76 | 0 | 2022-11-22 |  | 1
2023 | Region IV-A | BATANGAS | CITY OF SANTO TOMAS (BATANGAS) | P00725767LZ | Construction of Flood Mitigation Structure | 121.1527 | 14.0876 | 96500000 | 96499879 | 2024 | LOUREL DEVELOPMENT CORPORATION (FORMERLY :LOUREL D | 4742 | 2023 | 2024-05-09 | 03/17/2023 | 121 | 0 | 2024-05-08 |  | 1
2023 | Cordillera Administrative Region | APAYAO | LUNA (APAYAO) | P00735964LZ | Construction of Flood Mitigation Structure | 121.4064 | 18.2705 | 96500000 | 96500000 | 2024 | ASC CONSTRUCTION & CONCRETE PRODUCTS | 4743 | 2023 | 2024-07-10 | 04/25/2023 | 0 | 0 | 2024-05-13 |  | 58
2022 | National Capital Region | PASIG CITY | CITY OF PASIG (METROPOLITAN MANILA) | P00620366LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.0927 | 14.5903 | 48999676.09 | 46499760 | 2022 | MSB VITUG CONSTRUCTION | 4744 | 2022 | 2022-10-12 | 03/17/2022 | 2499916.09 | 0 | 2022-10-11 |  | 1
2024 | Region III | BULACAN | CITY OF SAN JOSE DEL MONTE (BULACAN) | P00844752LZ | Construction of Slope Protection Structure | 121.0671 | 14.846 | 48999165.16 | 48994885.36 | 2024 | FLORDES CONSTRUCTION & TRADING CORP. (FORMERLY FLO | 4745 | 2024 | 2024-11-04 | 04/30/2024 | 4279.8 | 0 | 2024-11-19 | 15
2024 | Region IV-B | ORIENTAL MINDORO | NAUJAN (ORIENTAL MINDORO) | P00821607LZ | Construction of Flood Mitigation Structure | 121.2347 | 13.2333 | 49000000 | 48999940.58 | 2024 | CEFF TRADING & ENGINEERING SERVICES | 4746 | 2024 | 2024-05-27 | 02/08/2024 | 59.42 | 0 | 2024-09-28 | 124
2022 | Region IV-A | RIZAL | PILILLA (RIZAL) | P00620210LZ | Construction of Flood Mitigation Structure | 121.305 | 14.4925 | 96500000 | 96500000 | 2022 | DOUBLE 12 CONSTRUCTION & SUPPLY | 4747 | 2022 | 2022-12-02 | 03/07/2022 | 0 | 0 | 2023-01-05 | 34
2022 | Region IV-A | LAGUNA | CITY OF CALAMBA (LAGUNA) | P00620890LZ | Construction of Flood Mitigation Structure | 121.184 | 14.2298 | 83187825 | 80693065.75 | 2023 | ST. GERRARD CONSTRUCTION GEN. CONTRACTOR & DEVELOPMENT CORP. (FORMERLY:ST. GERRARD CONSTRUCTION) | 4748 | 2022 | 2023-02-15 | 02/21/2022 | 2494759.25 | 0 | 2023-02-14 |  | 1
2024 | Cordillera Administrative Region | KALINGA | TINGLAYAN (KALINGA) | P00821557LZ | Construction of Flood Mitigation Structure | 121.1536 | 17.2694 | 11760000 | 11747921.15 | 2025 | MA BUYAGAN CONSTRUCTION SERVICES | 4749 | 2024 | 2025-02-24 | 04/04/2024 | 12078.85 | 0 | 2025-03-03 | 7
2023 | National Capital Region | TAGUIG CITY | TAGUIG CITY (METROPOLITAN MANILA) | P00725523LZ | Construction of Slope Protection Structure | 121.0671 | 14.5027 | 75520379.96 | 71744360.96 | 2023 | 11-16 CONSTRUCTION / HAWK KEY CONSTRUCTION AND GENERAL MERCHANDISE CORPORATION | 4750 | 2023 | 2023-08-15 | 03/15/2023 | 3776019 | 0 | 2023-10-09 | 55
2023 | National Capital Region | PASIG CITY | CITY OF PASIG (METROPOLITAN MANILA) | P00725950LZ | Construction of Drainage Structure | 121.0928 | 14.5497 | 9799986.28 | 9308598.82 | 2023 | B. VALENCERINA TRADING & CONSTRUCTION | 4751 | 2023 | 2023-07-10 | 02/06/2023 | 491387.46 | 0 | 2023-07-19 | 9
2023 | Region IV-B | ORIENTAL MINDORO | PINAMALAYAN (ORIENTAL MINDORO) | P00726771LZ | Construction of Flood Mitigation Structure | 121.4064 | 13.0242 | 48999994.72 | 48997251.2 | 2023 | ALBERTO UY CONSTRUCTION & DEVELOPMENT | 4752 | 2023 | 2023-12-15 | 02/15/2023 | 2743.52 | 0 | 2023-12-30 | 15
2021 | Region IV-A | RIZAL |  | P00561551LZ | Construction of Flood Mitigation Structure | 121.3053 | 14.4917 | 9900000 | 8173647.31 | 2022 | JCML BUILDERS | 4753 | 2021 | 2022-07-23 | 12/24/2021 | 1726352.69 | 0 | 2022-07-22 |  | 1
2023 | Region IV-B | ORIENTAL MINDORO | CITY OF CALAPAN (CAPITAL) (ORIENTAL MINDORO) | P00727191LZ | Construction of Drainage Structure | 121.2353 | 13.3861 | 33775000 | 33774891.8 | 2023 | E E CONSTRUCTION | 4754 | 2023 | 2023-09-20 | 03/07/2023 | 108.2 | 0 | 2023-09-19 |  | 1
2022 | Region IV-A | LAGUNA | CITY OF CALAMBA (LAGUNA) | P00621098LZ | Construction of Flood Mitigation Structure | 121.1844 | 14.2286 | 39200000 | 39196546.74 | 2022 | R.D. SADSAD CONSTRUCTION & TRADING | 4755 | 2022 | 2022-07-11 | 02/14/2022 | 3453.26 | 0 | 2022-09-16 | 67
2022 | Region IV-A | RIZAL | MONTALBAN (RIZAL) | P00630946LZ | Construction of Flood Mitigation Structure | 121.1542 | 14.7608 | 65620000 | 65620000 | 2022 | ALPHA & OMEGA GEN. CONTRACTOR & DEVELOPMENT CORP. | 4756 | 2022 | 2022-08-22 | 03/07/2022 | 0 | 0 | 2022-12-12 | 112
2021 | National Capital Region | CALOOCAN CITY |  | P00525796LZ | Construction of Flood Mitigation Structure | 121.0671 | 14.7581 | 29398246.97 | 28663271.48 | 2022 | PERSAN CONSTRUCTION, INC. (FORMERLY: PERSAN CONST. | 4757 | 2021 | 2022-11-14 | 03/24/2022 | 734975.49 | 0 | 2022-11-17 | 3
2022 | National Capital Region | TAGUIG CITY | TAGUIG CITY (METROPOLITAN MANILA) | P00620072LZ | Construction of Slope Protection Structure | 121.0928 | 14.529 | 94569981.84 | 89727299.48 | 2022 | HONY TRADING & CONSTRUCTION | 4758 | 2022 | 2022-09-07 | 02/16/2022 | 4842682.36 | 0 | 2022-10-12 | 35
2021 | Region IV-A | RIZAL |  | P00561572LZ | Construction of Flood Mitigation Structure | 121.3063 | 14.4879 | 4950000 | 4776540.5 | 2022 | ANROL CONSTRUCTION | 4759 | 2021 | 2022-12-16 | 09/05/2022 | 173459.5 | 0 | 2023-02-06 | 52
2023 | Region IV-B | ORIENTAL MINDORO | CITY OF CALAPAN (CAPITAL) (ORIENTAL MINDORO) | P00727190LZ | Construction of Drainage Structure | 121.2356 | 13.3483 | 33775000 | 33774992.74 | 2023 | SIXTEEN ENTERPRISES-CALAPAN BRANCH | 4760 | 2023 | 2023-10-22 | 03/29/2023 | 7.26 | 0 | 2023-10-21 |  | 1
2021 | Region IV-A | RIZAL |  | P00561565LZ | Construction of Flood Mitigation Structure | 121.1847 | 14.7618 | 29700000 | 28655605.84 | 2022 | GREAT PACIFIC BUILDERS AND GEN. CONTRACTOR INC. | 4761 | 2021 | 2022-12-18 | 09/05/2022 | 1044394.16 | 0 | 2023-03-07 | 79
2023 | Region IV-A | LAGUNA | CITY OF CALAMBA (LAGUNA) | P00737518LZ | Rehabilitation / Major Repair of Drainage Structure | 121.1545 | 14.2115 | 12870000 | 12817753.43 | 2023 | PASCAL CONSTRUCTION | 4762 | 2023 | 2023-09-30 | 02/24/2023 | 52246.57 | 0 | 2023-09-29 |  | 1
2023 | Cordillera Administrative Region | KALINGA | PINUKPUK (KALINGA) | P00736182LZ | Construction of Flood Mitigation Structure | 121.307 | 17.6074 | 48976965.5 | 48921766.56 | 2024 | JTM CONSTRUCTION | 4763 | 2023 | 2024-01-25 | 02/20/2023 | 55198.94 | 0 | 2024-02-02 | 8
2023 | Region IV-B | ORIENTAL MINDORO | BONGABONG (ORIENTAL MINDORO) | P00742466LZ | Construction of Flood Mitigation Structure | 121.4083 | 12.6741 | 4949956.3 | 4949055.62 | 2023 | D.M. ALMERO ENTERPRISES | 4764 | 2023 | 2023-06-23 | 03/24/2023 | 900.68 | 0 | 2023-07-05 | 12
2023 | National Capital Region | MARIKINA CITY | CITY OF MARIKINA (METROPOLITAN MANILA) | P00727231LZ | Construction of Flood Mitigation Facility | 121.0932 | 14.6529 | 97999570.03 | 93089846.79 | 2024 | M3 KONSTRACT CORPORATION (FORMERLY:MARGARITA CONSTRUCTION) | 4765 | 2023 | 2024-03-09 | 09/25/2023 | 4909723.24 | 0 | 2024-06-19 | 102
2022 | National Capital Region | PATEROS | TAGUIG CITY (METROPOLITAN MANILA) | P00620015LZ | Construction of Drainage Structure | 121.0672 | 14.5408 | 72374706.3 | 68719494.97 | 2022 | HONY TRADING & CONSTRUCTION | 4766 | 2022 | 2022-09-13 | 02/16/2022 | 3655211.33 | 0 | 2022-09-12 |  | 1
2024 | Region IV-B | ORIENTAL MINDORO | CITY OF CALAPAN (CAPITAL) (ORIENTAL MINDORO) | P00821609LZ | Construction of Flood Mitigation Structure | 121.2356 | 13.3861 | 19600000 | 19599848.4 | 2024 | JARO BUILDERS & CONSTRUCTION SUPPLY | 4767 | 2024 | 2024-04-22 | 02/08/2024 | 151.6 | 0 | 2024-09-09 | 140
2023 | Region IV-A | RIZAL | CITY OF ANTIPOLO (RIZAL) | P00737529LZ | Construction of Flood Mitigation Structure | 121.1849 | 14.5979 | 9900000 | 9899999.99 | 2024 | TOP KMC CONSTRUCTION AND SUPPLY CORP. | 4768 | 2023 | 2024-04-25 | 03/09/2023 | 0.01 | 0 | 2024-04-24 |  | 1
2021 | Cordillera Administrative Region | KALINGA |  | P00525925LZ | Construction of Flood Mitigation Structure | 121.1546 | 17.387 | 19939080 | 19939080 | 2023 | BLESSING BUILDERS AND CONSTRUCTION SUPPLY | 4769 | 2021 | 2023-01-23 | 04/10/2022 | 0 | 0 | 2022-10-02 |  | 113
2022 | Region III | AURORA | DINGALAN (AURORA) | P00630934LZ | Construction of Flood Mitigation Facility | 121.4083 | 15.2132 | 91283210 | 91283210 | 2022 | DALCON CONSTRUCTION / EGB CONSTRUCTION CORPORATION (FORMERLY: EGB CONSTRUCTION) | 4770 | 2022 | 2022-11-22 | 02/28/2022 | 0 | 0 | 2022-12-04 | 12
2023 | National Capital Region | QUEZON CITY | QUEZON CITY (METROPOLITAN MANILA) | P00726015LZ | Construction of Flood Mitigation Structure | 121.0932 | 14.6914 | 48999685 | 48509688.15 | 2023 | DIADEMA CONSTRUCTION AND ENTERPRISES INC. (FORMERLY: DIADEMA ENTERPRISES) / A. DELA CRUZ BUILDERS INC. | 4771 | 2023 | 2023-12-22 | 02/27/2023 | 489996.85 | 0 | 2023-12-22 | 0
2022 | National Capital Region | MAKATI CITY | CITY OF MAKATI (METROPOLITAN MANILA) | P00620367LZ | Construction of Revetment | 121.0674 | 14.5496 | 37548700 | 37548700 | 2022 | TWO DIMENSION CONSTRUCTION / RJM CONSTRUCTION AND DEV'T., INC. | 4772 | 2022 | 2022-08-01 | 02/04/2022 | 0 | 0 | 2022-07-31 |  | 1
2024 | Region IV-B | ORIENTAL MINDORO | CITY OF CALAPAN (CAPITAL) (ORIENTAL MINDORO) | P00821608LZ | Construction of Flood Mitigation Structure | 121.2367 | 13.3472 | 49000000 | 48999745.31 | 2024 | E E CONSTRUCTION | 4773 | 2024 | 2024-06-24 | 02/08/2024 | 254.69 | 0 | 2024-10-24 | 122
2023 | Region III | NUEVA ECIJA | BONGABON (NUEVA ECIJA) | P00725728LZ | Construction of Flood Mitigation Structure | 121.1851 | 15.6624 | 90227423.45 | 88777708.23 | 2023 | CELSO C. FERRER CONSTRUCTION CORP. | 4774 | 2023 | 2023-12-13 | 04/17/2023 | 1449715.22 | 0 | 2023-12-26 | 13
2021 | Cordillera Administrative Region | APAYAO |  | P00526270LZ | Construction of Flood Mitigation Structure | 121.3089 | 17.8003 | 82914680 | 80309010.27 | 2023 | ASC CONSTRUCTION & CONCRETE PRODUCTS | 4775 | 2021 | 2023-04-14 | 12/22/2021 | 2605669.73 | 0 | 2022-12-20 |  | 115
2022 | Region III | NUEVA ECIJA | BONGABON (NUEVA ECIJA) | P00620193LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.1547 | 15.654 | 82024995.54 | 82025000 | 2022 | FRAMECON BUILDERS | 4776 | 2022 | 2022-12-29 | 03/02/2022 | 0 | 4.46 | 2022-12-31 | 2
2022 | Region IV-B | ORIENTAL MINDORO | MANSALAY (ORIENTAL MINDORO) | P00630954LZ | Construction of Flood Mitigation Structure | 121.4084 | 12.4813 | 144750000 | 144740430.5 | 2023 | D.M. MALIWANAG BUILDERS AND ENTERPRISES / MONOLITHIC CONSTRUCTION & CONCRETE PRODUCTS, INC. | 4777 | 2022 | 2023-04-30 | 03/24/2022 | 9569.5 | 0 | 2023-04-29 |  | 1
2024 | Cordillera Administrative Region | KALINGA | PASIL (KALINGA) | P00845931LZ | Construction of Flood Mitigation Structure | 121.0675 | 17.3443 | 6930000 | 6926724.62 | 2024 | RAD CONSTRUCTION | 4778 | 2024 | 2024-10-04 | 06/13/2024 | 3275.38 | 0 | 2024-10-09 | 5
2024 | Region IV-A | RIZAL | CITY OF ANTIPOLO (RIZAL) | P00820943LZ | Construction of Flood Mitigation Structure | 121.2369 | 14.6731 | 49000000 | 48744682.77 | 2024 | 1C4M BUILDERS INC. | 4779 | 2024 | 2024-10-21 | 02/14/2024 | 255317.23 | 0 | 2024-10-24 | 3
2024 | Region IV-B | ORIENTAL MINDORO | NAUJAN (ORIENTAL MINDORO) | P00839489LZ | Construction of Flood Mitigation Structure | 121.1853 | 13.2511 | 247500000 | 247495045 | 2024 | RAYMAN BUILDERS INC., | 4780 | 2024 | 2024-08-15 | 03/09/2024 | 4955 | 0 | 2025-03-02 | 199
2024 | Region IV-B | ORIENTAL MINDORO | NAUJAN (ORIENTAL MINDORO) | P00820393LZ | Construction of Flood Mitigation Structure | 121.3095 | 13.335 | 202650000 | 202645832.5 | 2024 | ST. TIMOTHY CONSTRUCTION CORPORATION | 4781 | 2024 | 2024-08-15 | 03/02/2024 | 4167.5 | 0 | 2025-02-23 | 192
2022 | Region IV-A | RIZAL | MONTALBAN (RIZAL) | P00637803LZ | Construction of Flood Mitigation Structure | 121.1548 | 14.7378 | 19800000 | 19800000 | 2023 | EL-JAKE BUILDERS | 4782 | 2022 | 2023-05-11 | 03/29/2022 | 0 | 0 | 2023-05-10 |  | 1
2023 | Region IV-A | RIZAL | PILILLA (RIZAL) | P00725833LZ | Construction of Flood Mitigation Structure | 121.3124 | 14.4971 | 67550000 | 67550000 | 2023 | AARCON BUILDERS | 4783 | 2023 | 2023-08-22 | 02/10/2023 | 0 | 0 | 2023-11-15 | 85
2022 | Region III | AURORA | DINGALAN (AURORA) | P00637067LZ | Construction of Flood Mitigation Structure | 121.4087 | 15.3814 | 49000000 | 49000000 | 2023 | DALCON CONSTRUCTION / EGB CONSTRUCTION CORPORATION (FORMERLY: EGB CONSTRUCTION) | 4784 | 2022 | 2023-02-24 | 06/21/2022 | 0 | 0 | 2023-03-30 | 34
2022 | Region III | BULACAN | CITY OF SAN JOSE DEL MONTE (BULACAN) | P00637016LZ | Construction of Slope Protection Structure | 121.0675 | 14.8072 | 96499037.84 | 96455909 | 2023 | ROYAL CROWN MONARCH CONSTRUCTION & SUPPLIES CORP. | 4785 | 2022 | 2023-07-03 | 05/26/2022 | 43128.84 | 0 | 2023-07-02 |  | 1
2024 | Region IV-A | LAGUNA | CITY OF SANTA ROSA (LAGUNA) | P00824726LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.0933 | 14.2968 | 49000000 | 48999622.78 | 2024 | MAR-VEL CONSTRUCTION & SUPPLY | 4786 | 2024 | 2024-11-02 | 02/16/2024 | 377.22 | 0 | 2024-11-01 |  | 1
2022 | Region IV-A | RIZAL | ANGONO (RIZAL) | P00639498LZ | Construction of Slope Protection Structure | 121.1856 | 14.5432 | 9800000 | 9308628 | 2022 | D.R. ROBLES CONSTRUCTION | 4787 | 2022 | 2022-08-30 | 06/29/2022 | 491372 | 0 | 2022-09-25 | 26
2022 | Region IV-A | BATANGAS | LOBO (BATANGAS) | P00631286LZ | Construction of Flood Mitigation Structure | 121.2372 | 13.6489 | 49000000 | 49000000 | 2023 | TCSC CORP. / EFREN RAMIREZ CONSTRUCTION AND GENERAL SERVICES CORPORATION | 4788 | 2022 | 2023-01-02 | 01/28/2022 | 0 | 0 | 2023-01-01 |  | 1
2022 | Region IV-A | RIZAL | MONTALBAN (RIZAL) | P00630947LZ | Construction of Flood Mitigation Structure | 121.1549 | 14.7623 | 65620000 | 65620000 | 2022 | ALPHA & OMEGA GEN. CONTRACTOR & DEVELOPMENT CORP. | 4789 | 2022 | 2022-08-22 | 03/07/2022 | 0 | 0 | 2022-12-12 | 112
2022 | Region IV-A | BATANGAS | LOBO (BATANGAS) | P00620208LZ | Construction of Flood Mitigation Structure | 121.3142 | 13.6222 | 86850000 | 86850000 | 2022 | TCSC CORP. | 4790 | 2022 | 2022-08-25 | 02/21/2022 | 0 | 0 | 2022-08-24 |  | 1
2022 | Region IV-A | LAGUNA | SANTA CRUZ (CAPITAL) (LAGUNA) | P00644534LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.409 | 14.2877 | 24125000 | 23395522.14 | 2023 | ISOBEL CONCRETE CONSTRUCTOR CORPORATION | 4791 | 2022 | 2023-08-18 | 11/22/2022 | 729477.86 | 0 | 2023-08-17 |  | 1
2024 | Region II | NUEVA VIZCAYA | BAMBANG (NUEVA VIZCAYA) | P00843259LZ | Construction of Flood Mitigation Structure | 121.0676 | 16.3929 | 89745000 | 89745000 | 2024 | DALCON CONSTRUCTION | 4792 | 2024 | 2024-05-31 | 03/08/2024 | 0 | 0 | 2025-01-12 | 226
2021 | Cordillera Administrative Region | KALINGA |  | P00526386LZ | Construction of Flood Mitigation Structure | 121.1884 | 17.3368 | 4900000 | 4519926.68 | 2022 | ROCKWELL BUILDERS | 4793 | 2021 | 2022-11-16 | 04/10/2022 | 380073.32 | 0 | 2022-08-13 |  | 95
2022 | Region IV-A | BATANGAS | CITY OF SANTO TOMAS (BATANGAS) | P00620868LZ | Construction of Flood Mitigation Structure | 121.155 | 14.0849 | 77200000 | 77199364.24 | 2022 | N.D.M. SANCHEZ BUILDERS & DEVELOPMENT CORPORATION | 4794 | 2022 | 2022-11-14 | 02/23/2022 | 635.76 | 0 | 2023-01-17 | 64
2021 | Region II | NUEVA VIZCAYA |  | P00561681LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.2374 | 16.5342 | 29700000 | 29700000 | 2022 | SHANLEY CONSTRUCTION | 4795 | 2021 | 2022-11-13 | 01/12/2022 | 0 | 0 | 2022-11-12 |  | 1
2024 | Region IV-A | LAGUNA | SAN PABLO CITY (LAGUNA) | P00839633LZ | Construction of Flood Mitigation Structure | 121.3155 | 14.0396 | 4950000 | 4949518.07 | 2024 | BHENLLABIEN BUILDERS CORPORATION (FORMERLY: BHENLLABIEN BUILDERS CONSTRUCTION) | 4796 | 2024 | 2024-11-06 | 08/09/2024 | 481.93 | 0 | 2024-11-05 |  | 1
2022 | National Capital Region | QUEZON CITY | QUEZON CITY (METROPOLITAN MANILA) | P00632723LZ | Rehabilitation / Major Repair of Drainage Structure | 121.0676 | 14.6316 | 4949633.23 | 4741678.03 | 2022 | RWORKMATE CONSTRUCTION | 4797 | 2022 | 2022-09-28 | 02/09/2022 | 207955.2 | 0 | 2022-09-27 |  | 1
2024 | Cordillera Administrative Region | MOUNTAIN PROVINCE | PARACELIS (MOUNTAIN PROVINCE) | P00821547LZ | Construction of Flood Mitigation Structure | 121.4095 | 17.1698 | 19600000 | 19600000 | 2024 | J.M. DAPING CONSTRUCTION SERVICES | 4798 | 2024 | 2024-09-16 | 02/15/2024 | 0 | 0 | 2024-06-25 |  | 83
2022 | Region III | BULACAN | CITY OF SAN JOSE DEL MONTE (BULACAN) | P00637070LZ | Construction of Slope Protection Structure | 121.0933 | 14.8134 | 39199928.23 | 38611537.31 | 2022 | E.L. ANOLIN CONSTRUCTION | 4799 | 2022 | 2022-12-21 | 05/26/2022 | 588390.92 | 0 | 2022-12-23 | 2
2024 | Region IV-B | ORIENTAL MINDORO | NAUJAN (ORIENTAL MINDORO) | P00839490LZ | Construction of Flood Mitigation Structure | 121.1887 | 13.2534 | 247500000 | 247496440.5 | 2024 | RAYMAN BUILDERS INC., | 4800 | 2024 | 2024-08-15 | 03/09/2024 | 3559.5 | 0 | 2025-03-02 | 199
2023 | Region IV-A | RIZAL | CITY OF ANTIPOLO (RIZAL) | P00726236LZ | Construction of Flood Mitigation Structure | 121.2375 | 14.6693 | 49000000 | 48999164.58 | 2023 | 1C4M BUILDERS INC. / GREAT PACIFIC BUILDERS AND GEN. CONTRACTOR INC. | 4801 | 2023 | 2023-08-25 | 02/16/2023 | 835.42 | 0 | 2023-11-11 | 78
2021 | Cordillera Administrative Region | APAYAO |  | P00526367LZ | Construction of Flood Mitigation Structure | 121.3158 | 17.8 | 39199819.73 | 38292917.46 | 2022 | ASC CONSTRUCTION & CONCRETE PRODUCTS | 4802 | 2021 | 2022-09-24 | 12/02/2021 | 906902.27 | 0 | 2022-07-11 |  | 75
2024 | Region IV-B | ORIENTAL MINDORO | BULALACAO (SAN PEDRO) (ORIENTAL MINDORO) | P00821611LZ | Construction of Flood Mitigation Structure | 121.3171 | 12.3675 | 29400000 | 29396724.81 | 2024 | MADSAM ENTERPRISES | 4803 | 2024 | 2024-08-04 | 02/02/2024 | 3275.19 | 0 | 2024-08-03 |  | 1
2023 | Region IV-A | BATANGAS | CITY OF TANAUAN (BATANGAS) | P00726551LZ | Construction of Flood Mitigation Structure | 121.1553 | 14.0838 | 96500000 | 96499284.5 | 2023 | NDA BUILDERS AND DEVELOPERS / REVERE CONSTRUCTION & SUPPLY CORPORATION (FORMERLY | 4804 | 2023 | 2023-09-14 | 03/17/2023 | 715.5 | 0 | 2024-02-08 | 147
2023 | Region II | CAGAYAN | SANCHEZ-MIRA (CAGAYAN) | P00725669LZ | Construction of Flood Mitigation Structure | 121.2384 | 18.5568 | 96500000 | 96500000 | 2023 | TJMT CONSTRUCTION / JEICCA BUILDERS | 4805 | 2023 | 2023-09-19 | 02/06/2023 | 0 | 0 | 2023-10-09 | 20
2023 | National Capital Region | TAGUIG CITY | TAGUIG CITY (METROPOLITAN MANILA) | P00725524LZ | Construction of Slope Protection Structure | 121.0676 | 14.5038 | 75463814.5 | 71675531.01 | 2023 | ZYRE TRADING AND CONSTRUCTION / DAHL CONSTRUCTION CORP. (FORMERLY: DAHL CONSTRUCTION) | 4806 | 2023 | 2023-08-01 | 03/15/2023 | 3788283.49 | 0 | 2023-10-09 | 69
2023 | National Capital Region | PASIG CITY | CITY OF PASIG (METROPOLITAN MANILA) | P00725937LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.0935 | 14.5552 | 15679504.33 | 14881389.09 | 2023 | WAY MAKER GENERAL CONTRACTOR OPC | 4807 | 2023 | 2023-05-06 | 02/06/2023 | 798115.24 | 0 | 2023-05-05 |  | 1
2023 | Region IV-A | BATANGAS | ROSARIO (BATANGAS) | P00726206LZ | Construction of Flood Mitigation Structure | 121.32 | 13.8354 | 29400000 | 29400000 | 2023 | TONIJON CONSTRUCTION AND DEVELOPMENT INC. (FORMERLY: TONIJON CONSTRUCTION) | 4808 | 2023 | 2023-08-29 | 02/08/2023 | 0 | 0 | 2023-06-30 |  | 60
2022 | Region IV-B | ORIENTAL MINDORO | PINAMALAYAN (ORIENTAL MINDORO) | P00621123LZ | Construction of Flood Mitigation Structure | 121.41 | 13.0361 | 48999227.91 | 48999413.41 | 2022 | E E CONSTRUCTION / SIXTEEN ENTERPRISES-CALAPAN BRANCH | 4809 | 2022 | 2022-12-27 | 06/03/2022 | 0 | 185.5 | 2023-02-21 | 56
2023 | Region IV-A | BATANGAS | CITY OF SANTO TOMAS (BATANGAS) | P00742396LZ | Construction of Flood Mitigation Structure | 121.1553 | 14.0838 | 96500000 | 98999979 | 2023 | MAR-VEL CONSTRUCTION & SUPPLY | 4810 | 2023 | 2023-12-05 | 03/17/2023 | 0 | 2499979 | 2024-02-08 | 65
2024 | Region IV-B | DAVAO DEL SUR | MAGSAYSAY (DAVAO DEL SUR) | P00824740LZ | Construction of Flood Mitigation Structure | 121.1887 | 12.3798 | 39200000 | 39192528.61 | 2024 | F.A. TORRES CONSTRUCTION / BLACER CONSTRUCTION CORP. | 4811 | 2024 | 2024-08-15 | 03/06/2024 | 7471.39 | 0 | 2024-09-15 | 31
2021 | Region II | NUEVA VIZCAYA |  | P00561678LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.2385 | 16.5364 | 29700000 | 29700000 | 2022 | SHANLEY CONSTRUCTION | 4812 | 2021 | 2022-11-20 | 01/12/2022 | 0 | 0 | 2022-11-19 |  | 1
2023 | Region II | NUEVA VIZCAYA | BAMBANG (NUEVA VIZCAYA) | P00742117LZ | Construction of Flood Mitigation Structure | 121.0936 | 16.3636 | 59400000 | 59400000 | 2023 | DALCON CONSTRUCTION | 4813 | 2023 | 2023-08-24 | 04/12/2023 | 0 | 0 | 2024-02-01 | 161
2024 | Region IV-A | LAGUNA | SAN PABLO CITY (LAGUNA) | P00846074LZ | Construction of Drainage Structure | 121.3204 | 14.0624 | 4950000 | 4811400 | 2024 | DANRICH BUILDERS CORPORATION | 4814 | 2024 | 2024-11-12 | 06/11/2024 | 138600 | 0 | 2024-11-11 |  | 1
2022 | Region IV-A | RIZAL | MONTALBAN (RIZAL) | P00637804LZ | Construction of Flood Mitigation Structure | 121.1557 | 14.7377 | 19800000 | 19800000 | 2023 | EL-JAKE BUILDERS | 4815 | 2022 | 2023-05-11 | 03/29/2022 | 0 | 0 | 2023-05-10 |  | 1
2022 | Region IV-B | ORIENTAL MINDORO | CITY OF CALAPAN (CAPITAL) (ORIENTAL MINDORO) | P00639521LZ | Construction of Flood Mitigation Structure | 121.1894 | 13.3108 | 39200000 | 38392547.71 | 2022 | LUMEL GLENN CONSTRUCTION | 4816 | 2022 | 2022-10-24 | 05/26/2022 | 807452.29 | 0 | 2022-12-01 | 38
2023 | Region IV-A | RIZAL | CITY OF ANTIPOLO (RIZAL) | P00726246LZ | Construction of Flood Mitigation Structure | 121.2388 | 14.6693 | 29400000 | 29399996.27 | 2023 | TOP KMC CONSTRUCTION AND SUPPLY CORP. | 4817 | 2023 | 2023-11-02 | 03/08/2023 | 3.73 | 0 | 2023-11-01 |  | 1
2024 | National Capital Region | CALOOCAN CITY | CALOOCAN CITY (METROPOLITAN MANILA) | P00820003LZ | Construction of Flood Mitigation Structure | 121.0677 | 14.7577 | 86837659.61 | 84662805.54 | 2024 | IM CONSTRUCTION CORPORATION | 4818 | 2024 | 2024-10-01 | 02/14/2024 | 2174854.07 | 0 | 2024-12-08 | 68
2022 | National Capital Region | QUEZON CITY | QUEZON CITY (METROPOLITAN MANILA) | P00621411LZ | Construction of Flood Mitigation Structure | 121.0936 | 14.6677 | 29399954.26 | 28341399.95 | 2023 | E.L. TORRES CONSTRUCTION AND TRADING INC. (FORMERLY : E. L. TORRES CONSTRUCTION & TRADING | 4819 | 2022 | 2023-05-22 | 03/24/2022 | 1058554.31 | 0 | 2023-06-11 | 20
2023 | Cordillera Administrative Region | APAYAO | SANTA MARCELA (APAYAO) | P00726402LZ | Construction of Flood Mitigation Structure | 121.4137 | 18.3096 | 96500000 | 96483381.66 | 2023 | ASC CONSTRUCTION & CONCRETE PRODUCTS | 4820 | 2023 | 2023-12-15 | 04/05/2023 | 16618.34 | 0 | 2024-04-11 | 118
2024 | Cordillera Administrative Region | MOUNTAIN PROVINCE | NATONIN (MOUNTAIN PROVINCE) | P00821147LZ | Construction of Drainage Structure | 121.3207 | 17.1534 | 24162880 | 23793040 | 2024 | A.P.O. GENERAL CONSTRUCTION | 4821 | 2024 | 2024-12-09 | 05/02/2024 | 369840 | 0 | 2024-12-16 | 7
2022 | Region IV-A | RIZAL | MONTALBAN (RIZAL) | P00630948LZ | Construction of Flood Mitigation Structure | 121.156 | 14.764 | 65620000 | 65620000 | 2022 | ST. TIMOTHY CONSTRUCTION CORPORATION | 4822 | 2022 | 2022-08-22 | 03/07/2022 | 0 | 0 | 2022-12-12 | 112
2023 | Region IV-B | ORIENTAL MINDORO | NAUJAN (ORIENTAL MINDORO) | P00727183LZ | Construction of Drainage Structure | 121.1894 | 13.2797 | 33775000 | 33774999.58 | 2023 | FRAMECON BUILDERS | 4823 | 2023 | 2023-08-25 | 03/07/2023 | 0.42 | 0 | 2023-08-27 | 2
2024 | National Capital Region | CALOOCAN CITY | CALOOCAN CITY (METROPOLITAN MANILA) | P00820004LZ | Construction of Flood Mitigation Structure | 121.0677 | 14.7577 | 86847008.51 | 84637889.92 | 2024 | JAGONBUILD CONSTRUCTION CORP. (FOR. JAGON BUILDERS | 4824 | 2024 | 2024-10-01 | 02/14/2024 | 2209118.59 | 0 | 2024-12-08 | 68
2023 | Region II | CAGAYAN | CLAVERIA (CAGAYAN) | P00727268LZ | Construction of Flood Mitigation Structure | 121.0936 | 18.5407 | 49000000 | 48250000 | 2024 | SKYLINE CONSTRUCTION, EQUIPMENT AND DEVELOPMENT CORPORATION(FORMERLY: EDDIE G. GUILLEN BUILDERS INC. | 4825 | 2023 | 2024-01-20 | 03/20/2023 | 750000 | 0 | 2023-10-20 |  | 92
2021 | Cordillera Administrative Region | MOUNTAIN PROVINCE |  | P00525917LZ | Construction of Flood Mitigation Structure | 121.3211 | 17.1512 | 19600000 | 19500000 | 2022 | JFO CONSTRUCTION | 4826 | 2021 | 2022-08-27 | 04/06/2022 | 100000 | 0 | 2022-08-26 |  | 1
2024 | Region IV-A | BATANGAS | CITY OF SANTO TOMAS (BATANGAS) | P00821329LZ | Construction of Flood Mitigation Structure | 121.156 | 14.0826 | 87610420 | 87610008 | 2024 | NDA BUILDERS AND DEVELOPERS | 4827 | 2024 | 2024-09-10 | 03/25/2024 | 412 | 0 | 2025-01-17 | 129
2022 | Region IV-A | RIZAL | CITY OF ANTIPOLO (RIZAL) | P00620629LZ | Construction of Flood Mitigation Structure | 121.2406 | 14.6686 | 29400000 | 29399964.95 | 2022 | 1C4M BUILDERS INC. | 4828 | 2022 | 2022-08-26 | 03/01/2022 | 35.05 | 0 | 2022-08-26 | 0
2021 | National Capital Region | PATEROS |  | P00525721LZ | Construction of Flood Mitigation Structure | 121.068 | 14.5435 | 31782211.14 | 30193100.58 | 2022 | TUCHAR CONSTRUCTION CORP. (FORMERLY:TUCHAR CONSTRU | 4829 | 2021 | 2022-10-19 | 07/28/2021 | 1589110.56 | 0 | 2022-10-18 |  | 1
2024 | Region IV-B | ORIENTAL MINDORO | NAUJAN (ORIENTAL MINDORO) | P00825128LZ | Construction of Flood Mitigation Structure | 121.1894 | 13.2797 | 98000000 | 96500000 | 2024 | SILVERWOLVES CONSTRUCTION CORPORATION | 4830 | 2024 | 2024-05-08 | 02/08/2024 | 1500000 | 0 | 2025-02-16 | 284
2023 | National Capital Region | QUEZON CITY | QUEZON CITY (METROPOLITAN MANILA) | P00726018LZ | Construction of Flood Mitigation Structure | 121.0938 | 14.7053 | 48999671.46 | 48019682.16 | 2023 | C & F CONSTRUCTION & DEVELOPMENT CORPORATION | 4831 | 2023 | 2023-12-09 | 02/13/2023 | 979989.3 | 0 | 2023-12-08 |  | 1
2022 | Region IV-A | BATANGAS | SAN JUAN (BATANGAS) | P00620563LZ | Construction of Slope Protection Structure | 121.4143 | 13.817 | 49000000 | 47532070 | 2022 | M.G. SALAZAR CONSTRUCTION CORP. (FOR. M.G. SALAZAR | 4832 | 2022 | 2022-10-16 | 03/25/2022 | 1467930 | 0 | 2022-10-15 |  | 1
2024 | Region IV-B | ORIENTAL MINDORO | BULALACAO (SAN PEDRO) (ORIENTAL MINDORO) | P00839658LZ | Construction of Drainage Structure | 121.322 | 12.2967 | 4950000 | 4947019.45 | 2024 | SOSEP BUILDERS | 4833 | 2024 | 2024-05-16 | 02/02/2024 | 2980.55 | 0 | 2024-05-15 |  | 1
2024 | Region IV-A | BATANGAS | CITY OF TANAUAN (BATANGAS) | P00821330LZ | Construction of Flood Mitigation Structure | 121.156 | 14.0826 | 86850000 | 86849850.8 | 2024 | NDA BUILDERS AND DEVELOPERS | 4834 | 2024 | 2024-09-10 | 03/25/2024 | 149.2 | 0 | 2025-01-17 | 129
2022 | Region IV-A | RIZAL | CITY OF ANTIPOLO (RIZAL) | P00620216LZ | Construction of Flood Mitigation Structure | 121.2406 | 14.6687 | 55033950 | 55033609.54 | 2022 | ALPHA & OMEGA GEN. CONTRACTOR & DEVELOPMENT CORP. | 4835 | 2022 | 2022-11-27 | 03/03/2022 | 340.46 | 0 | 2022-11-26 |  | 1
2021 | Region IV-A | RIZAL |  | P00561564LZ | Construction of Flood Mitigation Structure | 121.1897 | 14.763 | 29700000 | 29700000 | 2022 | L. EUSEBIO ACE DEVELOPMENT CORPORATION | 4836 | 2021 | 2022-12-05 | 09/05/2022 | 0 | 0 | 2023-02-28 | 85
2022 | Region IV-A | LAGUNA | SANTA CRUZ (CAPITAL) (LAGUNA) | P00644533LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.4144 | 14.2803 | 24125000 | 23812512.45 | 2023 | ISOBEL CONCRETE CONSTRUCTOR CORPORATION | 4837 | 2022 | 2023-08-18 | 11/22/2022 | 312487.55 | 0 | 2023-08-17 |  | 1
2022 | National Capital Region | MARIKINA CITY | CITY OF MARIKINA (METROPOLITAN MANILA) | P00639312LZ | [11 empty] | 0 | 0
2023 | Region IV-A | RIZAL | PILILLA (RIZAL) | P00742447LZ | Construction of Drainage Structure | 121.3231 | 14.4676 | 4950000 | 4950000 | 2023 | GKB BUILDERS | 4839 | 2023 | 2023-08-12 | 05/08/2023 | 0 | 0 | 2023-08-11 |  | 1
2024 | Region IV-A | LAGUNA | CITY OF SAN PEDRO (LAGUNA) | P00820382LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.0681 | 14.3529 | 96500000 | 94087500 | 2025 | AMETHYST HORIZON BUILDERS AND GEN. CONTRACTOR AND DEVELOPMENT CORP. | 4840 | 2024 | 2025-01-17 | 02/26/2024 | 2412500 | 0 | 2025-01-16 |  | 1
2022 | Cordillera Administrative Region | KALINGA | TINGLAYAN (KALINGA) | P00644764LZ | Construction of Slope Protection Structure | 121.1562 | 17.3144 | 11551050 | 11540507.97 | 2023 | BANGYAN 3D CONSTRUCTION | 4841 | 2022 | 2023-10-24 | 01/12/2023 | 10542.03 | 0 | 2023-07-09 |  | 107
2023 | Region IV-A | RIZAL | CITY OF ANTIPOLO (RIZAL) | P00726235LZ | Construction of Flood Mitigation Structure | 121.2416 | 14.667 | 49000000 | 48999996.22 | 2023 | 1C4M BUILDERS INC. / GREAT PACIFIC BUILDERS AND GEN. CONTRACTOR INC. | 4842 | 2023 | 2023-09-21 | 02/16/2023 | 3.78 | 0 | 2024-01-20 | 121
2024 | Region IV-A | LAGUNA | SAN PABLO CITY (LAGUNA) | P00820380LZ | Construction of Flood Mitigation Structure | 121.3247 | 14.0807 | 96500000 | 96487650.86 | 2024 | BHENLLABIEN BUILDERS CORPORATION (FORMERLY: BHENLLABIEN BUILDERS CONSTRUCTION) | 4843 | 2024 | 2024-12-24 | 02/29/2024 | 12349.14 | 0 | 2024-12-23 |  | 1
2022 | Cordillera Administrative Region | APAYAO | CALANASAN (BAYAG) (APAYAO) | P00640502LZ | Construction of Flood Mitigation Structure | 121.1899 | 18.4289 | 6930000 | 6827260.01 | 2023 | E.C.V. CONSTRUCTION | 4844 | 2022 | 2023-09-15 | 03/25/2022 | 102739.99 | 0 | 2022-10-19 |  | 331
2024 | Region IV-A | RIZAL | TANAY (RIZAL) | P00839652LZ | Construction of Flood Mitigation Structure | 121.4154 | 14.627 | 19800000 | 19800000 | 2024 | D.C. SANDIL CONSTRUCTION AND REALTY DEVELOPMENT, I | 4845 | 2024 | 2024-11-14 | 02/07/2024 | 0 | 0 | 2024-11-13 |  | 1
2024 | National Capital Region | PASIG CITY | CITY OF PASIG (METROPOLITAN MANILA) | P00824588LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.0939 | 14.5773 | 4899450.13 | 4797841.91 | 2024 | B. VALENCERINA TRADING & CONSTRUCTION | 4846 | 2024 | 2024-06-24 | 03/27/2024 | 101608.22 | 0 | 2024-06-23 |  | 1
2021 | Region IV-A | RIZAL |  | P00561560LZ | Construction of Flood Mitigation Structure | 121.3293 | 14.482 | 9900000 | 9900000 | 2022 | S.B. SORIANO CONSTRUCTION | 4847 | 2021 | 2022-12-03 | 09/05/2022 | 0 | 0 | 2023-02-02 | 61
2023 | Cordillera Administrative Region | APAYAO | CALANASAN (BAYAG) (APAYAO) | P00735965LZ | Construction of Flood Mitigation Structure | 121.1899 | 18.4291 | 96500000 | 93386847.09 | 2024 | TAGEL CORPORATION / AQUILA CONSTRUCTION CO. | 4848 | 2023 | 2024-03-15 | 06/22/2023 | 3113152.91 | 0 | 2024-06-05 | 82
2023 | Cordillera Administrative Region | APAYAO | SANTA MARCELA (APAYAO) | P00726401LZ | Construction of Flood Mitigation Structure | 121.4159 | 18.2767 | 86850000 | 83452531.58 | 2023 | ASC CONSTRUCTION & CONCRETE PRODUCTS | 4849 | 2023 | 2023-12-15 | 04/14/2023 | 3397468.42 | 0 | 2024-02-06 | 53
2023 | Region IV-A | BATANGAS | SAN JOSE (BATANGAS) | P00742403LZ | Construction of Drainage Structure | 121.0681 | 13.8949 | 3960000 | 3841200 | 2023 | LUCKY EIGHTY-THREE CONSTRUCTION AND SUPPLY(FOR.VRP | 4850 | 2023 | 2023-07-12 | 04/27/2023 | 118800 | 0 | 2023-07-11 |  | 1
2022 | Region IV-A | RIZAL | MONTALBAN (RIZAL) | P00637805LZ | Construction of Flood Mitigation Structure | 121.1567 | 14.7375 | 19800000 | 19800000 | 2023 | EL-JAKE BUILDERS | 4851 | 2022 | 2023-05-11 | 03/29/2022 | 0 | 0 | 2023-05-10 |  | 1
2022 | Region IV-A | RIZAL | CITY OF ANTIPOLO (RIZAL) | P00620631LZ | Construction of Flood Mitigation Structure | 121.2435 | 14.6457 | 49000000 | 48828460.71 | 2023 | ALPHA & OMEGA GEN. CONTRACTOR & DEVELOPMENT CORP. | 4852 | 2022 | 2023-03-24 | 02/22/2022 | 171539.29 | 0 | 2023-05-16 | 53
2022 | Region IV-A | RIZAL | MONTALBAN (RIZAL) | P00630949LZ | Construction of Flood Mitigation Structure | 121.1568 | 14.7659 | 65620000 | 65620000 | 2022 | ST. TIMOTHY CONSTRUCTION CORPORATION | 4853 | 2022 | 2022-08-22 | 03/15/2022 | 0 | 0 | 2022-12-20 | 120
2022 | Region IV-A | BATANGAS | LOBO (BATANGAS) | P00631283LZ | Construction of Flood Mitigation Structure | 121.2447 | 13.6229 | 49000000 | 49000000 | 2022 | TCSC CORP. / EFREN RAMIREZ CONSTRUCTION AND GENERAL SERVICES CORPORATION | 4854 | 2022 | 2022-07-14 | 01/28/2022 | 0 | 0 | 2022-07-13 |  | 1
2023 | National Capital Region | PASIG CITY | CITY OF PASIG (METROPOLITAN MANILA) | P00725959LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.0941 | 14.5577 | 4409768.31 | 4192131.3 | 2023 | WAY MAKER GENERAL CONTRACTOR OPC | 4855 | 2023 | 2023-07-05 | 02/06/2023 | 217637.01 | 0 | 2023-07-04 |  | 1
2022 | Region IV-A | LAGUNA | NAGCARLAN (LAGUNA) | P00620593LZ | Construction of Slope Protection Structure | 121.4162 | 14.1315 | 43120000 | 43120000 | 2023 | MORTAR MASTERS & CONCRETE BUILDERS | 4856 | 2022 | 2023-03-18 | 02/25/2022 | 0 | 0 | 2023-03-17 |  | 1
2023 | Region II | NUEVA VIZCAYA | BAYOMBONG (CAPITAL) (NUEVA VIZCAYA) | P00727119LZ | Construction of Flood Mitigation Structure | 121.1899 | 16.4872 | 49000000 | 49000000 | 2023 | R.O. BUILDERS & DEVELOPMENT CORPORATION | 4857 | 2023 | 2023-09-17 | 03/03/2023 | 0 | 0 | 2023-10-01 | 14
2022 | Region IV-B | ORIENTAL MINDORO | BONGABONG (ORIENTAL MINDORO) | P00639531LZ | Construction of Flood Mitigation Structure | 121.3317 | 12.6819 | 48999151.38 | 48999964.46 | 2023 | IGWT-JAV CONSTRUCTION & DEVELOPMENT CORPORATION / EGB CONSTRUCTION CORPORATION (FORMERLY: EGB CONSTRUCTION) | 4858 | 2022 | 2023-07-19 | 04/13/2022 | 0 | 813.08 | 2023-07-18 |  | 1
2021 | Region IV-A | LAGUNA |  | P00561545LZ | Construction of Flood Mitigation Structure | 121.3321 | 14.068 | 29400000 | 29400000 | 2022 | WERR CORPORATION INTERNATIONAL / PRIME GIGABUILD CONSTRUCTION CORP. (FORMERLY: RON DANIELL CONSTRUCTION CORPORATION) | 4859 | 2021 | 2022-12-14 | 02/18/2022 | 0 | 0 | 2022-12-13 |  | 1
2022 | Region IV-B | ORIENTAL MINDORO | SAN TEODORO (ORIENTAL MINDORO) | P00620266LZ | Construction of Flood Mitigation Structure | 121.3357 | 13.0802 | 144748654.4 | 144749612.6 | 2023 | NEWBIG FOUR J CONSTRUCTION INC., (FORMERLY FOUR J | 4860 | 2022 | 2023-04-09 | 02/23/2022 | 0 | 958.2 | 2023-04-08 |  | 1
2022 | Region IV-B | ORIENTAL MINDORO | SAN TEODORO (ORIENTAL MINDORO) | P00620267LZ | Construction of Flood Mitigation Structure | 121.3357 | 13.0802 | 144748654.3 | 144748796.8 | 2023 | PRIME PACIFIC MARINE & INDUSTRIAL SERVICES CORP. | 4861 | 2022 | 2023-04-25 | 03/22/2022 | 0 | 142.5 | 2023-04-24 |  | 1
2024 | Region IV-B | ORIENTAL MINDORO | NAUJAN (ORIENTAL MINDORO) | P00839491LZ | Construction of Flood Mitigation Structure | 121.1572 | 13.1691 | 247500000 | 247497396.4 | 2024 | ST. TIMOTHY CONSTRUCTION CORPORATION | 4862 | 2024 | 2024-07-04 | 03/02/2024 | 2603.6 | 0 | 2025-02-23 | 234
2022 | National Capital Region | TAGUIG CITY | TAGUIG CITY (METROPOLITAN MANILA) | P00620050LZ | Construction of Flood Mitigation Structure | 121.0682 | 14.5268 | 96499578.82 | 91674599.88 | 2022 | DAHL CONSTRUCTION CORP. (FORMERLY: DAHL CONSTRUCTION) | 4863 | 2022 | 2022-10-13 | 02/16/2022 | 4824978.94 | 0 | 2022-10-12 |  | 1
2022 | Region IV-B | ORIENTAL MINDORO | SAN TEODORO (ORIENTAL MINDORO) | P00620268LZ | Construction of Flood Mitigation Structure | 121.3357 | 13.0802 | 96499875.45 | 96490896.94 | 2022 | ROAD EDGE TRADING & DEVELOPMENT SERVICES | 4864 | 2022 | 2022-11-18 | 03/22/2022 | 8978.51 | 0 | 2022-11-17 |  | 1
2022 | Region IV-A | RIZAL | CITY OF ANTIPOLO (RIZAL) | P00620624LZ | Construction of Flood Mitigation Structure | 121.2451 | 14.6439 | 49000000 | 48999611.62 | 2022 | ALPHA & OMEGA GEN. CONTRACTOR & DEVELOPMENT CORP. | 4865 | 2022 | 2022-10-13 | 02/16/2022 | 388.38 | 0 | 2022-10-12 |  | 1
2024 | Region IV-B | ORIENTAL MINDORO | BONGABONG (ORIENTAL MINDORO) | P00825123LZ | Construction of Flood Mitigation Structure | 121.1572 | 13.1691 | 193000000 | 192997844.4 | 2024 | STX ENTERPRISES | 4866 | 2024 | 2024-11-07 | 03/23/2024 | 2155.6 | 0 | 2025-03-16 | 129
2024 | Region IV-B | ORIENTAL MINDORO | BANSUD (ORIENTAL MINDORO) | P00821355LZ | Construction of Flood Mitigation Structure | 121.4164 | 12.8611 | 67550000 | 67547177.24 | 2024 | ALBERTO UY CONSTRUCTION & DEVELOPMENT | 4867 | 2024 | 2024-12-29 | 02/15/2024 | 2822.76 | 0 | 2024-12-28 |  | 1
2023 | National Capital Region | PASIG CITY | CITY OF PASIG (METROPOLITAN MANILA) | P00727001LZ | Rehabilitation / Major Repair of Drainage Structure | 121.0682 | 14.562 | 3919512.03 | 3702257.74 | 2023 | W. GOMEZ TRADING AND CONSTRUCTION | 4868 | 2023 | 2023-08-20 | 03/24/2023 | 217254.29 | 0 | 2023-08-19 |  | 1
2022 | National Capital Region | TAGUIG CITY | TAGUIG CITY (METROPOLITAN MANILA) | P00620071LZ | Construction of Slope Protection Structure | 121.0941 | 14.5298 | 94569742.72 | 89793537.38 | 2022 | ALPHA & OMEGA GEN. CONTRACTOR & DEVELOPMENT CORP. / EBUILDERS CONSTRUCTION & DEVELOPMENT CORP. | 4869 | 2022 | 2022-10-13 | 02/16/2022 | 4776205.34 | 0 | 2022-10-12 |  | 1
2023 | Region II | CAGAYAN | PAMPLONA (CAGAYAN) | P00727344LZ | Construction of Flood Mitigation Structure | 121.3361 | 18.4583 | 40180000 | 40180000 | 2023 | GVDPM CONSTRUCTION CORP. (FORMERLY: ZM CONSTRUCTIO | 4870 | 2023 | 2023-10-09 | 03/07/2023 | 0 | 0 | 2023-10-08 |  | 1
2022 | Region IV-A | RIZAL | BINANGONAN (RIZAL) | P00637801LZ | Construction of Slope Protection Structure | 121.1902 | 14.5417 | 9900000 | 9402844.07 | 2023 | D.R. ROBLES CONSTRUCTION | 4871 | 2022 | 2023-01-19 | 07/04/2022 | 497155.93 | 0 | 2023-01-18 |  | 1
2024 | Region IV-A | RIZAL | MORONG (RIZAL) | P00839653LZ | Construction of Flood Mitigation Structure | 121.2452 | 14.5158 | 14850000 | 14850000 | 2024 | GKB BUILDERS | 4872 | 2024 | 2024-08-10 | 02/07/2024 | 0 | 0 | 2024-08-09 |  | 1
2024 | Cordillera Administrative Region | KALINGA | TINGLAYAN (KALINGA) | P00824677LZ | Construction of Flood Mitigation Structure | 121.1583 | 17.2848 | 1960000 | 1949979.46 | 2024 | JEP CONSTRUCTION | 4873 | 2024 | 2024-08-22 | 04/29/2024 | 10020.54 | 0 | 2024-09-16 | 25
2022 | Cordillera Administrative Region | KALINGA | PASIL (KALINGA) | P00621015LZ | Construction of Flood Mitigation Structure | 121.1908 | 17.408 | 14700000 | 14589077.57 | 2022 | BANGYAN 3D CONSTRUCTION | 4874 | 2022 | 2022-09-15 | 02/21/2022 | 110922.43 | 0 | 2022-11-27 | 73
2022 | Cordillera Administrative Region | KALINGA | PINUKPUK (KALINGA) | P00620806LZ | Construction of Flood Mitigation Structure | 121.3374 | 17.5567 | 77187735.33 | 77200000 | 2023 | BHM CONSTRUCTION | 4875 | 2022 | 2023-04-13 | 03/21/2022 | 0 | 12264.67 | 2023-02-04 |  | 68
2021 | Region IV-A | BATANGAS |  | P00526305LZ | Construction of Flood Mitigation Structure | 121.0683 | 13.7625 | 144750000 | 144749597.3 | 2023 | PHESCO, INCORPORATED | 4876 | 2021 | 2023-03-03 | 06/21/2021 | 402.7 | 0 | 2023-03-02 |  | 1
2023 | Region IV-A | LAGUNA | CITY OF SANTA ROSA (LAGUNA) | P00740647LZ | Construction of Flood Mitigation Structure | 121.0943 | 14.2975 | 49000000 | 47724810.65 | 2024 | RVR3 CONSTRUCTION SUPPLY AND SERVICES / ORA ET LABORA CONSTRUCTION INC | 4877 | 2023 | 2024-04-12 | 06/27/2023 | 1275189.35 | 0 | 2024-04-11 |  | 1
2023 | Region II | CAGAYAN | ABULUG (CAGAYAN) | P00727270LZ | Construction of Flood Mitigation Structure | 121.4165 | 18.3345 | 67550000 | 67550000 | 2023 | CMG JR. BUILDERS / J.G. YACAS CONSTRUCTION, SUPPLY AND EQUIPMENT RENTAL | 4878 | 2023 | 2023-08-22 | 03/20/2023 | 0 | 0 | 2023-10-17 | 56
2023 | Cordillera Administrative Region | KALINGA | CITY OF TABUK (CAPITAL) (KALINGA) | P00742290LZ | Construction of Drainage Structure | 121.2458 | 17.2548 | 6923941.35 | 6918940.57 | 2023 | BIGA CONSTRUCTION | 4879 | 2023 | 2023-11-15 | 07/05/2023 | 5000.78 | 0 | 2023-09-21 |  | 55
2024 | Region IV-B | ORIENTAL MINDORO | NAUJAN (ORIENTAL MINDORO) | P00839492LZ | Construction of Flood Mitigation Structure | 121.1584 | 13.1649 | 247500000 | 247496511.7 | 2024 | ELITE GENERAL CONTRACTOR AND DEVELOPMENT CORP. | 4880 | 2024 | 2024-07-04 | 03/02/2024 | 3488.3 | 0 | 2025-02-23 | 234
2024 | Region IV-B | ORIENTAL MINDORO | NAUJAN (ORIENTAL MINDORO) | P00823574LZ | Construction of Flood Mitigation Structure | 121.1916 | 13.262 | 241250000 | 241246360.9 | 2024 | GREAT PACIFIC BUILDERS AND GEN. CONTRACTOR INC. | 4881 | 2024 | 2024-07-15 | 03/09/2024 | 3639.1 | 0 | 2025-03-02 | 230
2024 | National Capital Region | PATEROS | PATEROS (METROPOLITAN MANILA) | P00845865LZ | Construction of Slope Protection Structure | 121.0684 | 14.5443 | 49499955.34 | 48485215.11 | 2024 | ZYRE TRADING AND CONSTRUCTION | 4882 | 2024 | 2024-11-15 | 04/01/2024 | 1014740.23 | 0 | 2024-11-28 | 13
2022 | Region II | CAGAYAN | PAMPLONA (CAGAYAN) | P00621038LZ | Construction of Flood Mitigation Structure | 121.3375 | 18.4585 | 49000000 | 49000000 | 2022 | SKYLINE CONSTRUCTION, EQUIPMENT AND DEVELOPMENT CORPORATION(FORMERLY: EDDIE G. GUILLEN BUILDERS INC. | 4883 | 2022 | 2022-10-11 | 03/29/2022 | 0 | 0 | 2022-11-08 | 28
2022 | Region IV-A | BATANGAS | SAN JUAN (BATANGAS) | P00621476LZ | Construction of Flood Mitigation Structure | 121.4168 | 13.8149 | 144750000 | 144749317.9 | 2023 | NEWBIG FOUR J CONSTRUCTION INC., (FORMERLY FOUR J / JASMIG CONSTRUCTION CORPORATION (FORMERLY: JASMIG CONSTRUCTION SUPPLY) | 4884 | 2022 | 2023-08-23 | 04/05/2022 | 682.1 | 0 | 2023-08-22 |  | 1
2024 | National Capital Region | PASIG CITY | CITY OF PASIG (METROPOLITAN MANILA) | P00824593LZ | Rehabilitation / Major Repair of Drainage Structure | 121.0943 | 14.5615 | 14699274.33 | 14398406.78 | 2024 | E.L. ANOLIN CONSTRUCTION | 4885 | 2024 | 2024-09-27 | 04/08/2024 | 300867.55 | 0 | 2024-10-03 | 6
2022 | Region IV-A | RIZAL | MONTALBAN (RIZAL) | P00630950LZ | Construction of Flood Mitigation Structure | 121.1592 | 14.7671 | 65620000 | 65620000 | 2022 | ST. TIMOTHY CONSTRUCTION CORPORATION | 4886 | 2022 | 2022-10-03 | 03/15/2022 | 0 | 0 | 2022-12-20 | 78
2023 | Cordillera Administrative Region | KALINGA | LUBUAGAN (KALINGA) | P00726663LZ | Construction of Flood Mitigation Structure | 121.1925 | 17.3418 | 4900000 | 4893851.15 | 2023 | HKBT CONSTRUCTION | 4887 | 2023 | 2023-11-05 | 06/19/2023 | 6148.85 | 0 | 2023-09-07 |  | 59
2024 | National Capital Region | PATEROS | PATEROS (METROPOLITAN MANILA) | P00825200LZ | Construction of Drainage Structure | 121.0684 | 14.5517 | 6859666.21 | 6653876.22 | 2025 | B. VALENCERINA TRADING & CONSTRUCTION | 4888 | 2024 | 2025-02-01 | 04/08/2024 | 205789.99 | 0 | 2024-07-05 |  | 211
2023 | Region IV-A | LAGUNA | CALAUAN (LAGUNA) | P00726932LZ | Construction of Flood Mitigation Structure | 121.3377 | 14.1864 | 91675000 | 91656824.01 | 2024 | ST. MATTHEW GEN. CONTRACTOR & DEVELOPMENT CORP. | 4889 | 2023 | 2024-01-22 | 04/14/2023 | 18175.99 | 0 | 2024-02-06 | 15
2023 | Region IV-A | LAGUNA | LILIW (LAGUNA) | P00726933LZ | Construction of Flood Mitigation Structure | 121.4174 | 14.1443 | 91675000 | 91409355.92 | 2023 | MEGA M BUILDERS CORPORATION (FORMERLY: MEGA M BUILDERS) / THREE W BUILDERS, INC. | 4890 | 2023 | 2023-12-13 | 04/11/2023 | 265644.08 | 0 | 2024-03-04 | 82
2022 | Region IV-A | RIZAL | CITY OF ANTIPOLO (RIZAL) | P00620622LZ | Construction of Slope Protection Structure | 121.2458 | 14.673 | 49000000 | 48999991.59 | 2023 | ALPHA & OMEGA GEN. CONTRACTOR & DEVELOPMENT CORP. | 4891 | 2022 | 2023-12-18 | 02/16/2022 | 8.41 | 0 | 2024-01-14 | 27
2022 | Cordillera Administrative Region | KALINGA | CITY OF TABUK (CAPITAL) (KALINGA) | P00621005LZ | Construction of Flood Mitigation Structure | 121.3383 | 17.5999 | 40479866 | 40254513.26 | 2022 | CELESTINO CONSTRUCTION DEVELOPMENT CORPORATION (FORMERLY: JJA CONSTRUCTION & SUPPLY) | 4892 | 2022 | 2022-07-14 | 02/15/2022 | 225352.74 | 0 | 2022-07-13 |  | 1
2023 | Region IV-A | BATANGAS | LIPA CITY (BATANGAS) | P00726208LZ | Construction of Revetment | 121.1594 | 13.9575 | 49000000 | 49000000 | 2023 | THREE W BUILDERS, INC. | 4893 | 2023 | 2023-10-02 | 02/08/2023 | 0 | 0 | 2023-07-20 |  | 74
2023 | Region IV-B | ORIENTAL MINDORO | BONGABONG (ORIENTAL MINDORO) | P00736057LZ | Construction of Dike | 121.3387 | 12.343 | 217124999.6 | 217123081.7 | 2023 | G.C.I. CONSTRUCTION AND DEV'T. CORP. / ACIER & BETON CONSTRUCTION | 4894 | 2023 | 2023-12-15 | 02/11/2023 | 1917.9 | 0 | 2024-03-05 | 81
2022 | Region IV-A | LAGUNA | CITY OF SAN PEDRO (LAGUNA) | P00632897LZ | Construction of Flood Mitigation Structure | 121.0685 | 14.3542 | 4950000 | 4843901.6 | 2022 | AYANA CONSTRUCTION AND TRADING | 4895 | 2022 | 2022-08-01 | 04/04/2022 | 106098.4 | 0 | 2022-07-31 |  | 1
2022 | Region IV-B | ORIENTAL MINDORO | GLORIA (ORIENTAL MINDORO) | P00639523LZ | Construction of Flood Mitigation Structure | 121.4186 | 12.9244 | 48999224.56 | 47764451.36 | 2023 | LUMEL GLENN CONSTRUCTION | 4896 | 2022 | 2023-05-18 | 08/12/2022 | 1234773.2 | 0 | 2023-05-17 |  | 1
2021 | Cordillera Administrative Region | KALINGA |  | P00525939LZ | Construction of Flood Mitigation Structure | 121.1927 | 17.5021 | 2940000 | 2816343.9 | 2022 | SALTAN RIVER CORPORATION | 4897 | 2021 | 2022-10-24 | 03/24/2022 | 123656.1 | 0 | 2022-08-29 |  | 56
2022 | Cordillera Administrative Region | KALINGA | PINUKPUK (KALINGA) | P00632786LZ | Construction of Flood Mitigation Structure | 121.246 | 16.6979 | 4948999 | 4839336.32 | 2022 | MATAGOAN KJ BUILDERS AND ENGINEERING SERVICES | 4898 | 2022 | 2022-10-05 | 03/31/2022 | 109662.68 | 0 | 2022-07-27 |  | 70
2021 | Region IV-A | RIZAL |  | P00526132LZ | Construction of Flood Mitigation Structure | 121.1595 | 14.5318 | 39200000 | 37231649.95 | 2022 | A.J. LAVA BUILDERS CORP. (FORMERLY: A.J. LAVA BUIL | 4899 | 2021 | 2022-11-18 | 03/24/2022 | 1968350.05 | 0 | 2022-11-17 |  | 1
2023 | National Capital Region | PASIG CITY | CITY OF PASIG (METROPOLITAN MANILA) | P00725967LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.0944 | 14.5612 | 6859424.07 | 6514476.35 | 2023 | E.S. JOSEFA CONSTRUCTION | 4900 | 2023 | 2023-09-05 | 02/06/2023 | 344947.72 | 0 | 2023-09-04 |  | 1
2024 | Region IV-B | ORIENTAL MINDORO | BULALACAO (SAN PEDRO) (ORIENTAL MINDORO) | P00825130LZ | Construction of Flood Mitigation Structure | 121.3397 | 12.3424 | 96500000 | 96497149.49 | 2025 | ANORE CONSTRUCTION | 4901 | 2024 | 2025-01-07 | 04/01/2024 | 2850.51 | 0 | 2025-01-06 |  | 1
2024 | Cordillera Administrative Region | KALINGA | PASIL (KALINGA) | P00820766LZ | Construction of Flood Mitigation Structure | 121.1929 | 17.4086 | 4900000 | 4894642.74 | 2024 | W.V. CONSTRUCTION | 4902 | 2024 | 2024-11-26 | 04/04/2024 | 5357.26 | 0 | 2024-10-11 |  | 46
2023 | Region IV-A | RIZAL | MONTALBAN (RIZAL) | P00726926LZ | Construction of Flood Mitigation Structure | 121.1599 | 14.768 | 96500000 | 80705888.18 | 2024 | PERSAN CONSTRUCTION, INC. (FORMERLY: PERSAN CONST. | 4903 | 2023 | 2024-04-15 | 05/29/2023 | 15794111.82 | 0 | 2024-08-21 | 128
2024 | Region IV-A | RIZAL | MORONG (RIZAL) | P00846092LZ | Construction of Flood Mitigation Structure | 121.246 | 14.5168 | 4950000 | 4950000 | 2024 | BSKP CONSTRUCTION | 4904 | 2024 | 2024-10-14 | 03/14/2024 | 0 | 0 | 2024-10-13 |  | 1
2024 | Cordillera Administrative Region | IFUGAO | KIANGAN (IFUGAO) | P00820742LZ | Construction of Flood Mitigation Structure | 121.0945 | 16.8105 | 32666663.82 | 32239996.96 | 2024 | DJY CONSTRUCTION / SOUTHLAND CONSTRUCTION AND SUPPLIES | 4905 | 2024 | 2024-10-24 | 02/13/2024 | 426666.86 | 0 | 2024-10-23 |  | 1
2022 | Cordillera Administrative Region | APAYAO | SANTA MARCELA (APAYAO) | P00620807LZ | Construction of Flood Mitigation Structure | 121.419 | 18.2736 | 77200000 | 77189689.42 | 2023 | ASC CONSTRUCTION & CONCRETE PRODUCTS | 4906 | 2022 | 2023-03-20 | 03/31/2022 | 10310.58 | 0 | 2023-02-17 |  | 31
2024 | National Capital Region | PATEROS | PATEROS (METROPOLITAN MANILA) | P00821430LZ | Construction of Slope Protection Structure | 121.0686 | 14.5409 | 48999972.86 | 47990581.97 | 2024 | TUCHAR CONSTRUCTION CORP. (FORMERLY:TUCHAR CONSTRU | 4907 | 2024 | 2024-08-09 | 02/12/2024 | 1009390.89 | 0 | 2024-08-08 |  | 1
2021 | Cordillera Administrative Region | KALINGA |  | P00525934LZ | Construction of Drainage Structure | 121.1599 | 17.3903 | 1960000 | 1888990.97 | 2022 | RAD CONSTRUCTION | 4908 | 2021 | 2022-09-09 | 04/10/2022 | 71009.03 | 0 | 2022-06-07 |  | 94
2023 | Region IV-A | RIZAL | CITY OF ANTIPOLO (RIZAL) | P00727172LZ | Construction of Flood Mitigation Structure | 121.2486 | 14.7046 | 49000000 | 48996559.72 | 2023 | M.G. LUALHATI CONSTRUCTION CORP. | 4909 | 2023 | 2023-11-30 | 03/21/2023 | 3440.28 | 0 | 2023-12-14 | 14
2022 | Region II | CAGAYAN | ABULUG (CAGAYAN) | P00621040LZ | Construction of Flood Mitigation Structure | 121.4196 | 18.3799 | 49000000 | 49000000 | 2023 | JEICCA BUILDERS / W.D. NAVARRO CONSTRUCTION CO. | 4910 | 2022 | 2023-01-08 | 03/29/2022 | 0 | 0 | 2023-01-07 |  | 1
2023 | National Capital Region | MARIKINA CITY | CITY OF MARIKINA (METROPOLITAN MANILA) | P00727232LZ | Construction of Flood Mitigation Facility | 121.0946 | 14.6535 | 97999638.62 | 93041802.1 | 2024 | M3 KONSTRACT CORPORATION (FORMERLY:MARGARITA CONSTRUCTION) | 4911 | 2023 | 2024-03-04 | 09/25/2023 | 4957836.52 | 0 | 2024-06-19 | 107
2022 | Region IV-A | RIZAL | BINANGONAN (RIZAL) | P00632908LZ | Construction of Drainage Structure | 121.193 | 14.4671 | 5940000 | 5312342.23 | 2022 | L.L. MARRON CONSTRUCTION & TRADING | 4912 | 2022 | 2022-07-27 | 03/07/2022 | 627657.77 | 0 | 2022-07-26 |  | 1
2024 | Region III | BULACAN | CITY OF SAN JOSE DEL MONTE (BULACAN) | P00820212LZ | Construction of Flood Mitigation Structure | 121.0686 | 14.8322 | 96499644.28 | 96496502.12 | 2024 | TRIPLE 8 CONSTRUCTION & SUPPLY, INC. (FORMERLY TRIPLE 8 CONST. & SUPPLY) | 4913 | 2024 | 2024-11-21 | 02/14/2024 | 3142.16 | 0 | 2024-12-04 | 13
2021 | Region IV-A | RIZAL |  | P00526135LZ | Construction of Flood Mitigation Structure | 121.1965 | 14.4773 | 15680000 | 15679904.51 | 2022 | GLJ CONSTRUCTION | 4914 | 2021 | 2022-11-18 | 03/24/2022 | 95.49 | 0 | 2022-11-17 |  | 1
2024 | Region IV-A | BATANGAS | BATANGAS CITY (CAPITAL) (BATANGAS) | P00820870LZ | Construction of Flood Mitigation Structure | 121.1601 | 13.643 | 39200000 | 39200000 | 2024 | EFREN RAMIREZ CONSTRUCTION AND GENERAL SERVICES CORPORATION | 4915 | 2024 | 2024-07-26 | 02/07/2024 | 0 | 0 | 2024-07-25 |  | 1
2024 | Cordillera Administrative Region | MOUNTAIN PROVINCE | NATONIN (MOUNTAIN PROVINCE) | P00844736LZ | Construction of Drainage Structure | 121.2502 | 17.0989 | 4900000 | 4900000 | 2024 | CNL CONSTRUCTION | 4916 | 2024 | 2024-08-27 | 07/29/2024 | 0 | 0 | 2024-10-24 | 58
2022 | Region II | CAGAYAN | ABULUG (CAGAYAN) | P00631110LZ | Construction of Flood Mitigation Structure | 121.42 | 18.3799 | 26460000 | 26460000 | 2022 | JEICCA BUILDERS | 4917 | 2022 | 2022-08-28 | 02/11/2022 | 0 | 0 | 2022-08-24 |  | 4
2024 | National Capital Region | PATEROS | PATEROS (METROPOLITAN MANILA) | P00821431LZ | Construction of Slope Protection Structure | 121.0686 | 14.5409 | 48999793.04 | 48005142.75 | 2024 | ELITE GENERAL CONTRACTOR AND DEVELOPMENT CORP. | 4918 | 2024 | 2024-08-09 | 02/12/2024 | 994650.29 | 0 | 2024-08-08 |  | 1
2021 | Region IV-A | RIZAL |  | P00561566LZ | Construction of Flood Mitigation Structure | 121.1975 | 14.7681 | 19800000 | 19007200.25 | 2022 | B. BERNARDO CONST., INC. | 4919 | 2021 | 2022-12-15 | 09/05/2022 | 792799.75 | 0 | 2023-02-22 | 69
2024 | Cordillera Administrative Region | KALINGA | PASIL (KALINGA) | P00824678LZ | Construction of Flood Mitigation Structure | 121.1603 | 17.3869 | 2450000 | 2445325.03 | 2024 | ABMJ CONSTRUCTION AND AGGREGATES | 4920 | 2024 | 2024-07-31 | 04/18/2024 | 4674.97 | 0 | 2024-06-15 |  | 46
2023 | National Capital Region | PASIG CITY | CITY OF PASIG (METROPOLITAN MANILA) | P00725938LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.0947 | 14.5744 | 4899483.08 | 4645985.37 | 2023 | EL KAPITAN CONSTRUCTION SERVICES | 4921 | 2023 | 2023-07-05 | 02/06/2023 | 253497.71 | 0 | 2023-07-04 |  | 1
2024 | Cordillera Administrative Region | KALINGA | LUBUAGAN (KALINGA) | P00821561LZ | Construction of Flood Mitigation Structure | 121.1975 | 17.3655 | 19600000 | 19592654.05 | 2024 | BANGYAN 3D CONSTRUCTION | 4922 | 2024 | 2024-07-21 | 02/15/2024 | 7345.95 | 0 | 2024-10-04 | 75
2023 | Region IV-A | RIZAL | MORONG (RIZAL) | P00725834LZ | Construction of Flood Mitigation Structure | 121.2511 | 14.5056 | 67550000 | 67550000 | 2023 | ALPHA & OMEGA GEN. CONTRACTOR & DEVELOPMENT CORP. | 4923 | 2023 | 2023-08-15 | 02/10/2023 | 0 | 0 | 2023-11-21 | 98
2023 | Region IV-A | LAGUNA | CITY OF SAN PEDRO (LAGUNA) | P00727164LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.0687 | 14.3542 | 29400000 | 28948328 | 2023 | JA.VI CONSTRUCTION | 4924 | 2023 | 2023-12-09 | 05/23/2023 | 451672 | 0 | 2023-12-08 |  | 1
2021 | Cordillera Administrative Region | APAYAO |  | P00526369LZ | Construction of Flood Mitigation Structure | 121.4202 | 18.2702 | 47423180 | 45942583.67 | 2022 | ASC CONSTRUCTION & CONCRETE PRODUCTS | 4925 | 2021 | 2022-11-28 | 12/01/2021 | 1480596.33 | 0 | 2022-08-06 |  | 114
2024 | Region IV-A | BATANGAS | MALVAR (BATANGAS) | P00839109LZ | Rehabilitation / Major Repair of Drainage Structure | 121.1607 | 14.0358 | 4950000 | 4949344.6 | 2024 | NDA BUILDERS AND DEVELOPERS | 4926 | 2024 | 2024-06-13 | 02/15/2024 | 655.4 | 0 | 2024-06-12 |  | 1
2024 | National Capital Region | PASIG CITY | CITY OF PASIG (METROPOLITAN MANILA) | P00824589LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.0947 | 14.5744 | 4899988.51 | 4802163.28 | 2024 | DAHL CONSTRUCTION CORP. (FORMERLY: DAHL CONSTRUCTION) | 4927 | 2024 | 2024-08-20 | 05/23/2024 | 97825.23 | 0 | 2024-08-19 |  | 1
2021 | Region IV-B | ORIENTAL MINDORO |  | P00526452LZ | Construction of Flood Mitigation Structure | 121.1981 | 13.3178 | 39200000 | 39199962.18 | 2022 | ROCKSTEEL CONSTRUCTION AND DEV'T CORPORATION / ORANI CONSTRUCTION AND SUPPLY CORPORATION (FORMERLY:ORANI BUILDERS & SUPPLY) | 4928 | 2021 | 2022-12-19 | 03/08/2022 | 37.82 | 0 | 2022-12-18 |  | 1
2024 | Region III | BULACAN | DOÃ‘A REMEDIOS TRINIDAD (BULACAN) | P00845795LZ | Construction of Flood Mitigation Structure | 121.0687 | 14.9847 | 98999592.46 | 98999634.82 | 2025 | TOPNOTCH CATALYST BUILDERS INC. / ONE FRAME CONSTRUCTION INC. | 4929 | 2024 | 2025-01-13 | 06/19/2024 | 0 | 42.36 | 2025-05-13 | 120
2023 | Region IV-A | RIZAL | MONTALBAN (RIZAL) | P00742449LZ | Construction of Slope Protection Structure | 121.1983 | 14.7912 | 29700000 | 29700000 | 2023 | SOLID PILE CONSTRUCTION | 4930 | 2023 | 2023-10-24 | 07/10/2023 | 0 | 0 | 2024-01-19 | 87
2023 | Region IV-A | LAGUNA | LOS BAÃ‘OS (LAGUNA) | P00725791LZ | Construction of Flood Mitigation Structure | 121.2519 | 14.1748 | 48250000 | 48244616 | 2023 | 11 DIAMOND EAGLE CONSTRUCTION CORPORATION (FORMERLY:11 DIAMOND EAGLE CONSTRUCTION) | 4931 | 2023 | 2023-06-20 | 02/08/2023 | 5384 | 0 | 2023-09-25 | 97
2023 | Region II | CAGAYAN | CLAVERIA (CAGAYAN) | P00726436LZ | Construction of Flood Mitigation Structure | 121.0689 | 18.5612 | 49000000 | 48250000 | 2024 | SKYLINE CONSTRUCTION, EQUIPMENT AND DEVELOPMENT CORPORATION(FORMERLY: EDDIE G. GUILLEN BUILDERS INC. | 4932 | 2023 | 2024-03-22 | 02/06/2023 | 750000 | 0 | 2023-08-17 |  | 218
2023 | National Capital Region | PASIG CITY | CITY OF PASIG (METROPOLITAN MANILA) | P00725940LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.0948 | 14.5544 | 8819129.39 | 8377306.06 | 2023 | AARCON BUILDERS | 4933 | 2023 | 2023-06-05 | 02/06/2023 | 441823.33 | 0 | 2023-06-04 |  | 1
2022 | Region IV-A | LAGUNA | SANTA CRUZ (CAPITAL) (LAGUNA) | P00620889LZ | Construction of Flood Mitigation Structure | 121.4203 | 14.27 | 85885000 | 78406729.84 | 2023 | JTC CRUZ CONSTRUCTION CO., INC. | 4934 | 2022 | 2023-01-17 | 02/19/2022 | 7478270.16 | 0 | 2023-01-16 |  | 1
2023 | Cordillera Administrative Region | KALINGA | LUBUAGAN (KALINGA) | P00726660LZ | Construction of Flood Mitigation Structure | 121.1985 | 17.3635 | 34300000 | 34288345.49 | 2024 | BANGYAN 3D CONSTRUCTION | 4935 | 2023 | 2024-02-26 | 03/13/2023 | 11654.51 | 0 | 2024-02-08 |  | 18
2024 | Region II | NUEVA VIZCAYA | BAGABAG (NUEVA VIZCAYA) | P00843257LZ | Construction of Flood Mitigation Structure | 121.2527 | 16.5539 | 89745000 | 89745000 | 2024 | DALCON CONSTRUCTION | 4936 | 2024 | 2024-07-24 | 03/08/2024 | 0 | 0 | 2025-01-18 | 178
2024 | Region III | BULACAN | DOÃ‘A REMEDIOS TRINIDAD (BULACAN) | P00845794LZ | Construction of Flood Mitigation Structure | 121.0691 | 14.9863 | 98999282.16 | 98999239.11 | 2025 | TOPNOTCH CATALYST BUILDERS INC. / ONE FRAME CONSTRUCTION INC. | 4937 | 2024 | 2025-01-13 | 06/19/2024 | 43.05 | 0 | 2025-05-13 | 120
2024 | National Capital Region | PASIG CITY | CITY OF PASIG (METROPOLITAN MANILA) | P00820558LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.0949 | 14.5851 | 48999995.17 | 47414348.6 | 2024 | 11-16 CONSTRUCTION | 4938 | 2024 | 2024-10-07 | 04/01/2024 | 1585646.57 | 0 | 2024-10-06 |  | 1
2022 | Cordillera Administrative Region | KALINGA | CITY OF TABUK (CAPITAL) (KALINGA) | P00620808LZ | Construction of Dike | 121.4205 | 17.4233 | 57849803.74 | 57562739 | 2023 | JTM CONSTRUCTION / EGB CONSTRUCTION CORPORATION (FORMERLY: EGB CONSTRUCTION) | 4939 | 2022 | 2023-08-01 | 03/21/2022 | 287064.74 | 0 | 2023-01-29 |  | 184
2022 | Cordillera Administrative Region | KALINGA | LUBUAGAN (KALINGA) | P00621020LZ | Construction of Flood Mitigation Structure | 121.1989 | 17.3628 | 29400000 | 29400000 | 2023 | BANGYAN 3D CONSTRUCTION | 4940 | 2022 | 2023-04-25 | 02/21/2022 | 0 | 0 | 2023-03-25 |  | 31
2022 | Cordillera Administrative Region | KALINGA | BALBALAN (KALINGA) | P00620485LZ | Construction of Flood Mitigation Structure | 121.2527 | 17.481 | 14700000 | 14311781.71 | 2022 | BHM CONSTRUCTION | 4941 | 2022 | 2022-11-30 | 02/21/2022 | 388218.29 | 0 | 2022-09-01 |  | 90
2024 | Region IV-B | SURIGAO DEL NORTE | SOCORRO (SURIGAO DEL NORTE) | P00823567LZ | Construction of Flood Mitigation Structure | 121.4219 | 13.0492 | 63700000 | 62724802.09 | 2024 | SIXTEEN ENTERPRISES-CALAPAN BRANCH / E.S.L. BUILDERS & PARTS SUPPLY | 4942 | 2024 | 2024-06-20 | 02/08/2024 | 975197.91 | 0 | 2024-12-02 | 165
2023 | Region IV-A | LAGUNA | CITY OF SANTA ROSA (LAGUNA) | P00740646LZ | Construction of Flood Mitigation Structure | 121.0952 | 14.3 | 49000000 | 47724808.83 | 2024 | RVR3 CONSTRUCTION SUPPLY AND SERVICES / ORA ET LABORA CONSTRUCTION INC | 4943 | 2023 | 2024-04-12 | 06/27/2023 | 1275191.17 | 0 | 2024-04-11 |  | 1
2023 | Region IV-A | BATANGAS | BATANGAS CITY (CAPITAL) (BATANGAS) | P00726751LZ | Construction of Flood Mitigation Structure | 121.0691 | 13.7621 | 49000000 | 49000000 | 2023 | VICMAR CONSTRUCTION, INC. | 4944 | 2023 | 2023-11-04 | 02/08/2023 | 0 | 0 | 2023-11-03 |  | 1
2024 | Region IV-A | RIZAL | BINANGONAN (RIZAL) | P00820933LZ | Construction of Flood Mitigation Structure | 121.1991 | 14.4768 | 15680000 | 15679986.09 | 2024 | HONY TRADING & CONSTRUCTION | 4945 | 2024 | 2024-04-26 | 02/13/2024 | 13.91 | 0 | 2024-06-30 | 65
2023 | Region II | CAGAYAN | ABULUG (CAGAYAN) | P00727272LZ | Construction of Flood Mitigation Structure | 121.422 | 18.3848 | 67550000 | 67506525.33 | 2023 | JC PALOMO CONSTRUCTION & CONSTRUCTION SUPPLY / C.T. LEONCIO CONSTRUCTION & TRADING | 4946 | 2023 | 2023-12-02 | 03/20/2023 | 43474.67 | 0 | 2023-12-01 |  | 1
2021 | National Capital Region | MARIKINA CITY |  | P00525747LZ | Construction of Flood Mitigation Structure | 121.0952 | 14.6536 | 48204029.72 | 45548215.67 | 2022 | ROAD EDGE TRADING & DEVELOPMENT SERVICES | 4947 | 2021 | 2022-10-05 | 02/08/2022 | 2655814.05 | 0 | 2022-10-04 |  | 1
2021 | Region IV-A | BATANGAS |  | P00526304LZ | Construction of Flood Mitigation Structure | 121.0691 | 13.7621 | 144750000 | 143862842 | 2023 | PHESCO, INCORPORATED | 4948 | 2021 | 2023-03-05 | 07/21/2021 | 887158 | 0 | 2023-03-04 |  | 1
2021 | Cordillera Administrative Region | KALINGA |  | P00525930LZ | Construction of Flood Mitigation Structure | 121.2 | 17.3927 | 4900000 | 4858998.43 | 2022 | JBC BUILDERS | 4949 | 2021 | 2022-11-08 | 04/10/2022 | 41001.57 | 0 | 2022-08-17 |  | 83
2022 | National Capital Region | PATEROS | TAGUIG CITY (METROPOLITAN MANILA) | P00620362LZ | Construction of Flood Mitigation Structure | 121.0693 | 14.5456 | 48999945.04 | 46525447.81 | 2022 | TUCHAR CONSTRUCTION CORP. (FORMERLY:TUCHAR CONSTRU | 4950 | 2022 | 2022-08-06 | 02/08/2022 | 2474497.23 | 0 | 2022-08-05 |  | 1
2024 | Region II | NUEVA VIZCAYA | BAGABAG (NUEVA VIZCAYA) | P00823342LZ | Construction of Flood Mitigation Structure | 121.253 | 16.6489 | 96500000 | 96500000 | 2024 | V.B. MANUBAY CONSTRUCTION | 4951 | 2024 | 2024-09-01 | 04/02/2024 | 0 | 0 | 2025-02-25 | 177
2023 | Region IV-A | LAGUNA | CITY OF SANTA ROSA (LAGUNA) | P00740385LZ | Construction of Flood Mitigation Structure | 121.0952 | 14.2585 | 96500000 | 96427413.15 | 2023 | LE BRON CONSTRUCTION | 4952 | 2023 | 2023-12-12 | 04/14/2023 | 72586.85 | 0 | 2024-03-04 | 83
2024 | Region II | CAGAYAN | ABULUG (CAGAYAN) | P00825224LZ | Construction of Flood Mitigation Facility | 121.4236 | 18.3887 | 49000000 | 48958625.47 | 2024 | JLL PULSAR CONSTRUCTION CORPORATION (FORMERLY: PULSAR CONSTRUCTION) | 4953 | 2024 | 2024-08-19 | 04/17/2024 | 41374.53 | 0 | 2024-10-24 | 66
2022 | Cordillera Administrative Region | KALINGA | PASIL (KALINGA) | P00620484LZ | Construction of Flood Mitigation Structure | 121.2001 | 17.3928 | 9800000 | 9525442.35 | 2022 | BHM CONSTRUCTION | 4954 | 2022 | 2022-12-28 | 02/27/2022 | 274557.65 | 0 | 2022-11-08 |  | 50
2022 | National Capital Region | PATEROS | TAGUIG CITY (METROPOLITAN MANILA) | P00620361LZ | Construction of Flood Mitigation Structure | 121.0693 | 14.5457 | 48999880.29 | 46549886.27 | 2022 | HONY TRADING & CONSTRUCTION | 4955 | 2022 | 2022-08-06 | 02/08/2022 | 2449994.02 | 0 | 2022-08-05 |  | 1
2023 | Region IV-A | LAGUNA | LOS BAÃ‘OS (LAGUNA) | P00742437LZ | Construction of Flood Mitigation Structure | 121.2531 | 14.1735 | 99000000 | 98995447 | 2024 | MAR-VEL CONSTRUCTION & SUPPLY | 4956 | 2023 | 2024-03-05 | 04/14/2023 | 4553 | 0 | 2024-03-04 |  | 1
2022 | Cordillera Administrative Region | KALINGA | BALBALAN (KALINGA) | P00620140LZ | Construction of Flood Mitigation Structure | 121.2001 | 17.3928 | 90497700 | 88694393.45 | 2023 | BHM CONSTRUCTION / FIAT CONSTRUCTION SERVICES | 4957 | 2022 | 2023-08-15 | 03/29/2022 | 1803306.55 | 0 | 2023-05-21 |  | 86
2024 | National Capital Region | QUEZON CITY | QUEZON CITY (METROPOLITAN MANILA) | P00820036LZ | Construction of Flood Mitigation Structure | 121.0956 | 14.6662 | 84919921.29 | 84919418.15 | 2024 | MRB11 CONSTRUCTION CORPORATION (FORMERLY:MRB CONS | 4958 | 2024 | 2024-12-13 | 02/15/2024 | 503.14 | 0 | 2025-01-26 | 44
2022 | Region IV-B | ORIENTAL MINDORO | MANSALAY (ORIENTAL MINDORO) | P00632939LZ | Construction of Flood Mitigation Structure | 121.4236 | 12.5219 | 10889469.35 | 10573646.88 | 2022 | D.M. MALIWANAG BUILDERS AND ENTERPRISES | 4959 | 2022 | 2022-09-09 | 04/13/2022 | 315822.47 | 0 | 2022-09-08 |  | 1
2023 | Region II | NUEVA VIZCAYA | BAMBANG (NUEVA VIZCAYA) | P00726144LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.0693 | 16.3765 | 49000000 | 49000000 | 2023 | J.E.L. CONSTRUCTION & SUPPLY | 4960 | 2023 | 2023-10-21 | 02/15/2023 | 0 | 0 | 2023-10-20 |  | 1
2021 | Cordillera Administrative Region | KALINGA |  | P00525935LZ | Construction of Flood Mitigation Structure | 121.2004 | 17.3938 | 9800000 | 9506591.63 | 2022 | BHM CONSTRUCTION | 4961 | 2021 | 2022-12-16 | 03/24/2022 | 293408.37 | 0 | 2022-12-04 |  | 12
2021 | Cordillera Administrative Region | KALINGA |  | P00525942LZ | Construction of Flood Mitigation Structure | 121.2533 | 17.4816 | 9800000 | 9563952.77 | 2022 | BHM CONSTRUCTION | 4962 | 2021 | 2022-11-30 | 03/24/2022 | 236047.23 | 0 | 2022-10-13 |  | 48
2023 | National Capital Region | PASIG CITY | CITY OF PASIG (METROPOLITAN MANILA) | P00725936LZ | Construction of Flood Mitigation Structure | 121.0958 | 14.5847 | 4899756.42 | 4649672.91 | 2023 | 816 EMBER CONSTRUCTION CORPORATION | 4963 | 2023 | 2023-07-20 | 02/06/2023 | 250083.51 | 0 | 2023-05-05 |  | 76
2024 | National Capital Region | PATEROS | PATEROS (METROPOLITAN MANILA) | P00821428LZ | Construction of Slope Protection Structure | 121.0694 | 14.5461 | 48999690.81 | 48000133.62 | 2024 | ZYRE TRADING AND CONSTRUCTION | 4964 | 2024 | 2024-08-09 | 02/12/2024 | 999557.19 | 0 | 2024-08-08 |  | 1
2024 | Region IV-B | ORIENTAL MINDORO | NAUJAN (ORIENTAL MINDORO) | P00825135LZ | Construction of Flood Mitigation Structure | 121.2008 | 13.2128 | 98000000 | 96499892.6 | 2024 | SILVERWOLVES CONSTRUCTION CORPORATION | 4965 | 2024 | 2024-04-19 | 02/08/2024 | 1500107.4 | 0 | 2025-02-16 | 303
2023 | Region IV-A | LAGUNA | LOS BAÃ‘OS (LAGUNA) | P00737521LZ | Construction of Drainage Structure | 121.2533 | 14.1886 | 6930000 | 6878007.25 | 2023 | JA.VI CONSTRUCTION | 4966 | 2023 | 2023-09-06 | 02/24/2023 | 51992.75 | 0 | 2023-09-05 |  | 1
2024 | National Capital Region | PASIG CITY | CITY OF PASIG (METROPOLITAN MANILA) | P00820076LZ | Construction of Slope Protection Structure | 121.0958 | 14.554 | 96499363.58 | 94280000 | 2024 | 11-16 CONSTRUCTION | 4967 | 2024 | 2024-12-01 | 02/13/2024 | 2219363.58 | 0 | 2024-11-30 |  | 1
2024 | Region IV-B | ORIENTAL MINDORO | NAUJAN (ORIENTAL MINDORO) | P00846100LZ | Construction of Flood Mitigation Structure | 121.2567 | 13.2714 | 19800000 | 19799901.48 | 2024 | SILVERWOLVES CONSTRUCTION CORPORATION | 4968 | 2024 | 2024-05-21 | 02/27/2024 | 98.52 | 0 | 2024-09-22 | 124
2024 | Region IV-A | LAGUNA | CITY OF SAN PEDRO (LAGUNA) | P00839622LZ | Construction of Drainage Structure | 121.0694 | 14.3479 | 4950000 | 4864617 | 2024 | MICLOVER GENERAL CONSTRUCTION & IRON WORKS | 4969 | 2024 | 2024-09-09 | 02/16/2024 | 85383 | 0 | 2024-09-11 | 2
2021 | Cordillera Administrative Region | KALINGA |  | P00525928LZ | Construction of Flood Mitigation Structure | 121.2017 | 17.4429 | 4900000 | 4828417.94 | 2022 | SALTAN RIVER CORPORATION | 4970 | 2021 | 2022-08-10 | 03/24/2022 | 71582.06 | 0 | 2022-08-09 |  | 1
2024 | National Capital Region | PATEROS | PATEROS (METROPOLITAN MANILA) | P00821429LZ | Construction of Slope Protection Structure | 121.0694 | 14.5465 | 48999736.94 | 47995260.28 | 2024 | ZYRE TRADING AND CONSTRUCTION | 4971 | 2024 | 2024-10-08 | 02/12/2024 | 1004476.66 | 0 | 2024-10-07 |  | 1
2023 | National Capital Region | MARIKINA CITY | CITY OF MARIKINA (METROPOLITAN MANILA) | P00727229LZ | Construction of Flood Mitigation Facility | 121.096 | 14.6594 | 97999668.18 | 93057109.56 | 2024 | L.R. TIQUI BUILDERS, INC. / 729 CONSTRUCTION, INC. (FORMERLY 722 CONSTRUCTION, INC.) | 4972 | 2023 | 2024-02-24 | 06/30/2023 | 4942558.62 | 0 | 2024-02-23 |  | 1
2022 | National Capital Region | PATEROS | TAGUIG CITY (METROPOLITAN MANILA) | P00620360LZ | Construction of Drainage Structure | 121.0696 | 14.5514 | 19599743.94 | 19600000 | 2022 | HONY TRADING & CONSTRUCTION | 4973 | 2022 | 2022-07-02 | 02/08/2022 | 0 | 256.06 | 2022-06-06 |  | 26
2022 | Region IV-A | BATANGAS | SAN JUAN (BATANGAS) | P00620884LZ | Construction of Revetment | 121.4238 | 13.8339 | 96500000 | 96500000 | 2022 | V.R. PATRON BUILDERS & DEVELOPERS CORP. (PREVIOUSL | 4974 | 2022 | 2022-12-11 | 02/23/2022 | 0 | 0 | 2022-12-10 |  | 1
2024 | Region IV-A | BATANGAS | LOBO (BATANGAS) | P00846034LZ | Construction of Flood Mitigation Structure | 121.2573 | 13.6075 | 14850000 | 14850000 | 2024 | MATRICS CONSTRUCTION | 4975 | 2024 | 2024-08-02 | 04/02/2024 | 0 | 0 | 2024-08-01 |  | 1
2023 | Region IV-A | BATANGAS | BATANGAS CITY (CAPITAL) (BATANGAS) | P00727370LZ | Construction of Flood Mitigation Structure | 121.0698 | 13.7631 | 31430560 | 31430560 | 2023 | VICMAR CONSTRUCTION, INC. | 4976 | 2023 | 2023-11-15 | 03/03/2023 | 0 | 0 | 2023-11-14 |  | 1
2021 | Region II | CAGAYAN |  | P00526280LZ | Construction of Flood Mitigation Structure | 121.4242 | 18.4197 | 96500000 | 96500000 | 2023 | EGB CONSTRUCTION CORPORATION (FORMERLY: EGB CONSTRUCTION) | 4977 | 2021 | 2023-01-12 | 12/06/2021 | 0 | 0 | 2022-12-11 |  | 32
2023 | Region II | NUEVA VIZCAYA | DUPAX DEL SUR (NUEVA VIZCAYA) | P00725676LZ | Construction of Flood Mitigation Structure | 121.0961 | 16.2903 | 96500000 | 96490357.25 | 2023 | BRG CONSTRUCTION | 4978 | 2023 | 2023-10-13 | 02/27/2023 | 9642.75 | 0 | 2023-10-31 | 18
2024 | National Capital Region | MARIKINA CITY | CITY OF MARIKINA (METROPOLITAN MANILA) | P00823235LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.0961 | 14.6582 | 96499954.82 | 94547887.26 | 2024 | L.R. TIQUI BUILDERS, INC. | 4979 | 2024 | 2024-09-02 | 04/01/2024 | 1952067.56 | 0 | 2024-09-26 | 24
2023 | Region IV-A | BATANGAS | SAN JOSE (BATANGAS) | P00742405LZ | Construction of Drainage Structure | 121.0963 | 13.8508 | 2970000 | 2880900 | 2023 | LUCKY EIGHTY-THREE CONSTRUCTION AND SUPPLY(FOR.VRP | 4980 | 2023 | 2023-06-29 | 04/27/2023 | 89100 | 0 | 2023-06-28 |  | 1
2024 | National Capital Region | PASIG CITY | CITY OF PASIG (METROPOLITAN MANILA) | P00820559LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.0965 | 14.5826 | 48999824.54 | 47414632.39 | 2024 | 11-16 CONSTRUCTION | 4981 | 2024 | 2024-10-07 | 04/01/2024 | 1585192.15 | 0 | 2024-10-06 |  | 1
2023 | National Capital Region | PASIG CITY | CITY OF PASIG (METROPOLITAN MANILA) | P00725961LZ | Rehabilitation / Major Repair of Drainage Structure | 121.0966 | 14.5582 | 14209791.94 | 13497696 | 2023 | JAGONBUILD CONSTRUCTION CORP. (FOR. JAGON BUILDERS | 4982 | 2023 | 2023-08-04 | 02/06/2023 | 712095.94 | 0 | 2023-08-03 |  | 1
2022 | National Capital Region | MARIKINA CITY | CITY OF MARIKINA (METROPOLITAN MANILA) | P00639407LZ | Construction of Drainage Structure | 121.0966 | 14.6567 | 48999975.37 | 46525618.35 | 2023 | STAR WILLIAM CONSTRUCTION / W. GOMEZ TRADING AND CONSTRUCTION | 4983 | 2022 | 2023-02-16 | 03/24/2022 | 2474357.02 | 0 | 2023-02-15 |  | 1
2023 | Region IV-A | BATANGAS | SAN JUAN (BATANGAS) | P00726929LZ | Construction of Flood Mitigation Structure | 121.4243 | 13.8357 | 96500000 | 96500000 | 2024 | POWER K CONSTRUCTION SUPPLY & SERVICES | 4984 | 2023 | 2024-02-01 | 05/08/2023 | 0 | 0 | 2024-02-22 | 21
2021 | Region II | CAGAYAN |  | P00525950LZ | Construction of Flood Mitigation Structure | 121.4244 | 18.4214 | 49000000 | 49000000 | 2022 | EGB CONSTRUCTION CORPORATION (FORMERLY: EGB CONSTRUCTION) | 4985 | 2021 | 2022-09-09 | 11/26/2021 | 0 | 0 | 2022-09-08 |  | 1
2022 | Region IV-A | LAGUNA | PAGSANJAN (LAGUNA) | P00621295LZ | Construction of Flood Mitigation Structure | 121.4247 | 14.2569 | 96500000 | 93604490.24 | 2023 | JTC CRUZ CONSTRUCTION CO., INC. | 4986 | 2022 | 2023-06-07 | 09/09/2022 | 2895509.76 | 0 | 2023-08-24 | 78
2022 | Region IV-B | ORIENTAL MINDORO | PINAMALAYAN (ORIENTAL MINDORO) | P00621124LZ | Construction of Flood Mitigation Structure | 121.425 | 13.0492 | 48999772.24 | 48999992.34 | 2023 | L.N. SALVADOR CONSTRUCTION CORP. (FOR: L.N. SALVADOR CONSTRUCTION) | 4987 | 2022 | 2023-03-20 | 06/06/2022 | 0 | 220.1 | 2023-03-19 |  | 1
2023 | Region IV-A | BATANGAS | SAN JUAN (BATANGAS) | P00727311LZ | Construction of Flood Mitigation Structure | 121.425 | 13.8123 | 96500000 | 93605000 | 2024 | 11-16 CONSTRUCTION / HAWK KEY CONSTRUCTION AND GENERAL MERCHANDISE CORPORATION | 4988 | 2023 | 2024-02-19 | 05/04/2023 | 2895000 | 0 | 2024-02-18 |  | 1
2024 | Region IV-A | LAGUNA | SANTA CRUZ (CAPITAL) (LAGUNA) | P00820361LZ | Construction of Flood Mitigation Structure | 121.4256 | 14.2594 | 77889010 | 77888626.76 | 2024 | PROTECH CONSTRUCTION & DEVELOPMENT CORP. (FORMERLY / JOBEL ENTERPRISES | 4989 | 2024 | 2024-07-05 | 02/23/2024 | 383.24 | 0 | 2025-01-04 | 183
2022 | Region II | CAGAYAN | ABULUG (CAGAYAN) | P00620821LZ | Construction of Flood Mitigation Structure | 121.426 | 18.4254 | 96500000 | 96500000 | 2023 | EGB CONSTRUCTION CORPORATION (FORMERLY: EGB CONSTRUCTION) | 4990 | 2022 | 2023-06-09 | 03/29/2022 | 0 | 0 | 2023-06-08 |  | 1
2022 | Region IV-A | LAGUNA | PAGSANJAN (LAGUNA) | P00620888LZ | Construction of Flood Mitigation Structure | 121.4261 | 14.2608 | 85885000 | 83309816.57 | 2022 | DMLC BUILDERS | 4991 | 2022 | 2022-12-09 | 02/19/2022 | 2575183.43 | 0 | 2023-01-16 | 38
2022 | Region II | CAGAYAN | ABULUG (CAGAYAN) | P00621529LZ | Construction of Flood Mitigation Structure | 121.4264 | 18.4145 | 49000000 | 49000000 | 2022 | EGB CONSTRUCTION CORPORATION (FORMERLY: EGB CONSTRUCTION) | 4992 | 2022 | 2022-09-30 | 03/24/2022 | 0 | 0 | 2022-11-04 | 35
2022 | Region IV-A | QUEZON | CANDELARIA (QUEZON) | P00631310LZ | Construction of Slope Protection Structure | 121.4264 | 13.9214 | 39200000 | 39200000 | 2022 | I.A . BOSQUE CONSTRUCTION CORPORATION | 4993 | 2022 | 2022-12-20 | 02/24/2022 | 0 | 0 | 2022-12-19 |  | 1
2022 | Region IV-A | QUEZON | CANDELARIA (QUEZON) | P00620253LZ | Construction of Slope Protection Structure | 121.4266 | 13.9178 | 77200000 | 77199999.9 | 2023 | RAPID FOREMOST CONST. CO. | 4994 | 2022 | 2023-02-14 | 02/24/2022 | 0.1 | 0 | 2023-02-17 | 3
2023 | Region IV-A | LAGUNA | SANTA CRUZ (CAPITAL) (LAGUNA) | P00745984LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.4268 | 14.2621 | 19184200 | 18607381.02 | 2024 | TRIPLE EAGLE CONSTRUCTION AND TRADING | 4995 | 2023 | 2024-06-19 | 11/23/2023 | 576818.98 | 0 | 2024-06-18 |  | 1
2024 | Region III | AURORA | SAN LUIS (AURORA) | P00845950LZ | Construction of Flood Mitigation Structure | 121.4271 | 15.6646 | 49500000 | 49500000 | 2025 | GERRA CONSTRUCTION INCORPORATED (FORMERLY: GERRA CONSTRUCTION) | 4996 | 2024 | 2025-03-17 | 05/30/2024 | 0 | 0 | 2025-03-16 |  | 1
2022 | Region IV-A | BATANGAS | SAN JUAN (BATANGAS) | P00620883LZ | Construction of Revetment | 121.4272 | 13.813 | 96500000 | 93605000 | 2022 | V.R. PATRON BUILDERS & DEVELOPERS CORP. (PREVIOUSL | 4997 | 2022 | 2022-12-11 | 02/23/2022 | 2895000 | 0 | 2022-12-10 |  | 1
2024 | Region II | NUEVA VIZCAYA | DUPAX DEL SUR (NUEVA VIZCAYA) | P00820159LZ | Construction of Slope Protection Structure | 121.0967 | 16.2828 | 96500000 | 96492915.54 | 2024 | BRG CONSTRUCTION | 4998 | 2024 | 2024-09-16 | 02/16/2024 | 7084.46 | 0 | 2024-10-21 | 35
2021 | Cordillera Administrative Region | APAYAO |  | P00561652LZ | Construction of Flood Mitigation Structure | 121.0968 | 18.5272 | 4950000 | 4950000 | 2022 | ALEPHNORTH PEAK CONSTRUCTION AND DEVELOPMENT CO. | 4999 | 2021 | 2022-09-23 | 12/01/2021 | 0 | 0 | 2022-06-24 |  | 91
2022 | National Capital Region | PASIG CITY | CITY OF PASIG (METROPOLITAN MANILA) | P00620005LZ | Rehabilitation / Major Repair of Slope Protection Structure | 121.0968 | 14.5828 | 78399961.78 | 74455738.6 | 2022 | ST. TIMOTHY CONSTRUCTION CORPORATION / AMETHYST HORIZON BUILDERS AND GEN. CONTRACTOR AND DEVELOPMENT CORP. | 5000 | 2022 | 2022-11-02 | 02/16/2022 | 3944223.18 | 0 | 2022-11-01 |  | 1
2022 | Region III | AURORA | SAN LUIS (AURORA) | P00620495LZ | Construction of Flood Mitigation Structure | 121.4935 | 15.7289 | 48249356.52 | 48249356.62 | 2023 | R.D. TALENS CONSTRUCTION AND TRADING | 5001 | 2022 | 2023-09-25 | 08/15/2022 | 0 | 0.1 | 2023-09-24 |  | 1
2022 | Region II | ISABELA | SAN MARIANO (ISABELA) | P00621062LZ | Construction of Flood Mitigation Structure | 122.1067 | 16.8738 | 39199997.04 | 39112266.88 | 2022 | CAMBERWELL CONSTRUCTION AND SUPPLIES / EGB CONSTRUCTION CORPORATION (FORMERLY: EGB CONSTRUCTION) | 5002 | 2022 | 2022-11-18 | 02/14/2022 | 87730.16 | 0 | 2022-11-17 |  | 1
2022 | Region III | AURORA | SAN LUIS (AURORA) | P00631162LZ | Construction of Flood Mitigation Structure | 121.4951 | 15.752 | 49000000 | 49000000 | 2022 | ALEXI LOUISSE CONSTRUCTION & GENERAL MERCHANDISE | 5003 | 2022 | 2022-10-19 | 02/11/2022 | 0 | 0 | 2022-12-20 | 62
2023 | Region IX | ZAMBOANGA DEL SUR | ZAMBOANGA CITY (ZAMBOANGA DEL SUR) | P00732476MN | Construction of Drainage Structure | 122.1092 | 6.9095 | 9800000 | 9897612.75 | 2023 | MI CONSTRUCTION | 5004 | 2023 | 2023-10-20 | 03/23/2023 | 0 | 97612.75 | 2023-11-20 | 31
2023 | Region IV-B | ROMBLON | SAN AGUSTIN (ROMBLON) | P00727194LZ | Construction of Flood Mitigation Structure | 122.1097 | 12.4744 | 48999999.62 | 48992911.21 | 2023 | EMQ DESIGN & CONSTRUCTION | 5005 | 2023 | 2023-09-18 | 03/27/2023 | 7088.41 | 0 | 2023-11-19 | 62
2022 | Region III | AURORA | SAN LUIS (AURORA) | P00631145LZ | Construction of Drainage Structure | 121.502 | 15.7157 | 2940000 | 2820253.94 | 2022 | RADIANCE TRADERS & BUILDERS | 5006 | 2022 | 2022-07-08 | 03/18/2022 | 119746.06 | 0 | 2022-05-01 |  | 68
2024 | Region II | CAGAYAN | TUGUEGARAO CITY (CAPITAL) (CAGAYAN) | P00825227LZ | Construction of Flood Mitigation Structure | 121.7403 | 17.6289 | 34300000 | 34300000 | 2024 | D.J.D. CONSTRUCTION INC. (FORMERLY: D. J. D. CONSTRUCTION) | 5007 | 2024 | 2024-08-16 | 05/24/2024 | 0 | 0 | 2024-10-27 | 72
2023 | Region IX | ZAMBOANGA DEL SUR | ZAMBOANGA CITY (ZAMBOANGA DEL SUR) | P00732473MN | Construction of Flood Mitigation Structure | 121.9469 | 6.9681 | 9800000 | 9768821.29 | 2023 | MCGABRIEL CONSTRUCTION | 5008 | 2023 | 2023-10-18 | 03/23/2023 | 31178.71 | 0 | 2023-10-17 |  | 1
2024 | Region IV-B | ROMBLON | ODIONGAN (ROMBLON) | P00823569LZ | Construction of Flood Mitigation Structure | 122.0161 | 12.4138 | 135099999.1 | 135100000 | 2024 | SUNWEST, INC. (FORMERLY: SUNWEST CONSTRUCTION & DEVELOPMENT CORPORATION) | 5009 | 2024 | 2024-09-23 | 03/13/2024 | 0 | 0.9 | 2025-03-03 | 161
2022 | Region II | CAGAYAN | ABULUG (CAGAYAN) | P00621034LZ | Construction of Flood Mitigation Structure | 121.4273 | 18.395 | 49000000 | 49000000 | 2022 | C.T. LEONCIO CONSTRUCTION & TRADING | 5010 | 2022 | 2022-12-07 | 02/14/2022 | 0 | 0 | 2022-12-06 |  | 1
2022 | Region II | CAGAYAN | PEÃ‘ABLANCA (CAGAYAN) | P00621499LZ | Construction of Flood Mitigation Structure | 121.8036 | 17.6714 | 24125000 | 24125000 | 2022 | CREST92 CONSTRUCTION & DEVELOPMENT CORPORATION (FORMERLY: CREST CONSTRUCTION) | 5011 | 2022 | 2022-11-13 | 03/28/2022 | 0 | 0 | 2022-11-12 |  | 1
2022 | Region IV-A | QUEZON | PITOGO (QUEZON) | P00639495LZ | Construction of Flood Mitigation Structure | 122.1118 | 13.8353 | 48999734.61 | 49000000 | 2022 | RAPID FOREMOST CONST. CO. | 5012 | 2022 | 2022-09-20 | 04/04/2022 | 0 | 265.39 | 2022-10-29 | 39
2022 | Region II | CAGAYAN | PEÃ‘ABLANCA (CAGAYAN) | P00621413LZ | Construction of Flood Mitigation Structure | 121.8044 | 17.6749 | 77200000 | 77200000 | 2023 | MEGAY CONSTRUCTION INC. (FORMERLY: MEGAY CONSTRUCTION) / TJMT CONSTRUCTION | 5013 | 2022 | 2023-04-04 | 03/28/2022 | 0 | 0 | 2023-04-10 | 6
2024 | Region IV-B | ORIENTAL MINDORO | BONGABONG (ORIENTAL MINDORO) | P00821356LZ | Construction of Flood Mitigation Structure | 121.5026 | 12.688 | 67550000 | 67547158.37 | 2024 | LUMEL GLENN CONSTRUCTION | 5014 | 2024 | 2024-10-16 | 02/15/2024 | 2841.63 | 0 | 2024-11-21 | 36
2024 | Region II | ISABELA | SAN AGUSTIN (ISABELA) | P00825050LZ | Construction of Flood Mitigation Structure | 121.7406 | 16.4548 | 115800000 | 115800000 | 2024 | V.B. MANUBAY CONSTRUCTION | 5015 | 2024 | 2024-10-07 | 03/12/2024 | 0 | 0 | 2025-01-02 | 87
2022 | Region II | ISABELA | ROXAS (ISABELA) | P00631119LZ | Construction of Flood Mitigation Structure | 121.6044 | 17.1313 | 42140000 | 41655583.57 | 2022 | RRC CO. INC. (FORMERLY: R R C CONSTRUCTION) | 5016 | 2022 | 2022-08-21 | 03/16/2022 | 484416.43 | 0 | 2022-10-17 | 57
2022 | Region II | ISABELA | QUIRINO (ISABELA) | P00631116LZ | Construction of Flood Mitigation Structure | 121.6679 | 17.1274 | 42140000 | 41506893.72 | 2023 | DANYSONS CONSTRUCTION AND DEVELOPMENT CORPORATION (FORMERLY: DANYSONS CONSTRUCTION) | 5017 | 2022 | 2023-02-13 | 02/28/2022 | 633106.28 | 0 | 2022-12-05 |  | 70
2023 | Region II | BATANES | MAHATAO (BATANES) | P00737441LZ | Construction of Flood Mitigation Structure | 121.9477 | 20.4219 | 4941344 | 4935202.64 | 2023 | DEKM CONSTRUCTION | 5018 | 2023 | 2023-07-17 | 03/23/2023 | 6141.36 | 0 | 2023-08-06 | 20
2023 | Region IV-B | ROMBLON | ODIONGAN (ROMBLON) | P00726276LZ | Construction of Flood Mitigation Structure | 122.0172 | 12.3519 | 48999999.09 | 48997359.66 | 2023 | ROLCO CONSTRUCTION & DEVELOPMENT CORPORATION ( FOR | 5019 | 2023 | 2023-11-06 | 02/21/2023 | 2639.43 | 0 | 2023-11-28 | 22
2021 | Region II | ISABELA |  | P00561450LZ | Construction of Flood Mitigation Structure | 121.8054 | 16.8238 | 96499997.66 | 95051116.94 | 2022 | JANN-NORRIS CONSTRUCTION AND SUPPLIES INC. (FORMELY: JANN-NORRIS CONSTRUCTION AND SUPPLIES) / JOHN-JANN CONST. AND SUPPLIES CORP. | 5020 | 2021 | 2022-12-06 | 11/29/2021 | 1448880.72 | 0 | 2022-12-22 | 16
2024 | Region II | CAGAYAN | IGUIG (CAGAYAN) | P00821150LZ | Construction of Flood Mitigation Structure | 121.7428 | 17.7042 | 34257500 | 34254387.95 | 2024 | MEGAY CONSTRUCTION INC. (FORMERLY: MEGAY CONSTRUCTION) | 5021 | 2024 | 2024-10-21 | 06/03/2024 | 3112.05 | 0 | 2024-12-09 | 49
2023 | Region IV-B | ORIENTAL MINDORO | BONGABONG (ORIENTAL MINDORO) | P00736056LZ | Construction of Dike | 121.5042 | 12.7161 | 217124999.9 | 217122960.1 | 2023 | SUNWEST, INC. (FORMERLY: SUNWEST CONSTRUCTION & DEVELOPMENT CORPORATION) | 5022 | 2023 | 2023-12-15 | 02/11/2023 | 2039.8 | 0 | 2024-03-05 | 81
2024 | Region IX | ZAMBOANGA DEL SUR | ZAMBOANGA CITY (ZAMBOANGA DEL SUR) | P00833572MN | Construction of Drainage Structure | 121.9479 | 6.9579 | 4502295.03 | 4132146.97 | 2024 | CITYWEST BUILDERS AND SUPPLY | 5023 | 2024 | 2024-07-17 | 02/12/2024 | 370148.06 | 0 | 2024-07-16 |  | 1
2022 | Region II | ISABELA | ECHAGUE (ISABELA) | P00639333LZ | Construction of Flood Mitigation Structure | 121.6704 | 16.5845 | 96500000 | 96500000 | 2023 | MA TESORO CONSTRUCTION / EGB CONSTRUCTION CORPORATION (FORMERLY: EGB CONSTRUCTION) | 5024 | 2022 | 2023-01-06 | 04/01/2022 | 0 | 0 | 2023-01-09 | 3
2023 | Region IV-A | QUEZON | LUCENA CITY (CAPITAL) (QUEZON) | P00740384LZ | Construction of Flood Mitigation Structure | 121.6059 | 13.8975 | 96500000 | 96499986.66 | 2024 | WAYCON BUILDERS AND CONSTRUCTION SUPPLY CORP. (FOR:WAYCON BUILDERS & CONSTRUCTION SUPPLY) / ROMHEAD S.J. BUILDERS AND DEVELOPMENT INCORPORATED. | 5025 | 2023 | 2024-08-15 | 05/24/2023 | 13.34 | 0 | 2024-08-14 |  | 1
2024 | Region II | ISABELA | SAN MARIANO (ISABELA) | P00825054LZ | Construction of Flood Mitigation Structure | 122.0179 | 16.9587 | 72374995.63 | 71892884.4 | 2024 | JAY ARCIE CONSTRUCTION AND SUPPLY | 5026 | 2024 | 2024-07-19 | 04/05/2024 | 482111.23 | 0 | 2024-11-29 | 133
2021 | Region II | ISABELA |  | P00561452LZ | Construction of Flood Mitigation Structure | 121.8054 | 16.8238 | 96499998.6 | 95049181.1 | 2022 | JANN-NORRIS CONSTRUCTION AND SUPPLIES INC. (FORMELY: JANN-NORRIS CONSTRUCTION AND SUPPLIES) / INFINITUM 888 CONSTRUCTION AND DEVELOPMENT CORPORATION | 5027 | 2021 | 2022-12-06 | 11/29/2021 | 1450817.5 | 0 | 2022-12-22 | 16
2023 | Region IX | ZAMBOANGA DEL NORTE | SIRAWAI (ZAMBOANGA DEL NORTE) | P00721362MN | Construction of Flood Mitigation Structure | 122.1132 | 7.5234 | 39200000 | 39200000 | 2023 | LONG ISLAND BUILDERS & CONSTRUCTION | 5028 | 2023 | 2023-09-23 | 02/18/2023 | 0 | 0 | 2023-09-22 |  | 1
2024 | Region II | ISABELA | ANGADANAN (ISABELA) | P00824868LZ | Construction of Flood Mitigation Structure | 121.7435 | 16.745 | 77199995.53 | 77159066.51 | 2024 | INFINITUM 888 CONSTRUCTION AND DEVELOPMENT CORPORATION | 5029 | 2024 | 2024-10-17 | 05/09/2024 | 40929.02 | 0 | 2025-02-18 | 124
2023 | Region IV-B | ORIENTAL MINDORO | BONGABONG (ORIENTAL MINDORO) | P00736055LZ | Construction of Dike | 121.5048 | 12.7156 | 217124999.9 | 217123307 | 2023 | SUNWEST, INC. (FORMERLY: SUNWEST CONSTRUCTION & DEVELOPMENT CORPORATION) | 5030 | 2023 | 2023-12-15 | 02/11/2023 | 1692.9 | 0 | 2024-03-05 | 81
2024 | Region II | ISABELA | JONES (ISABELA) | P00843220LZ | Construction of Flood Mitigation Structure | 121.6718 | 16.5213 | 96500000 | 96452294.94 | 2024 | V.B. MANUBAY CONSTRUCTION | 5031 | 2024 | 2024-12-31 | 06/03/2024 | 47705.06 | 0 | 2025-03-30 | 89
2023 | Region II | CAGAYAN | LASAM (CAGAYAN) | P00742297LZ | Construction of Flood Mitigation Structure | 121.6075 | 18.0697 | 49500000 | 48904555.85 | 2024 | JLL PULSAR CONSTRUCTION CORPORATION (FORMERLY: PULSAR CONSTRUCTION) | 5032 | 2023 | 2024-01-17 | 03/27/2023 | 595444.15 | 0 | 2023-10-05 |  | 104
2023 | Region III | AURORA | CASIGURAN (AURORA) | P00740581LZ | Construction of Flood Mitigation Structure | 122.1137 | 16.2714 | 39200000 | 39200000 | 2023 | DALCON CONSTRUCTION / EGB CONSTRUCTION CORPORATION (FORMERLY: EGB CONSTRUCTION) | 5033 | 2023 | 2023-11-20 | 06/20/2023 | 0 | 0 | 2024-01-11 | 52
2021 | Region II | ISABELA |  | P00526278LZ | Construction of Flood Mitigation Structure | 121.8058 | 17.3925 | 75144928 | 74882404 | 2022 | DRAGON TWELVE BUILDERS & CONSTRUCTION SUPPLY / EGB CONSTRUCTION CORPORATION (FORMERLY: EGB CONSTRUCTION) | 5034 | 2021 | 2022-09-15 | 08/02/2021 | 262524 | 0 | 2022-09-17 | 2
2022 | Region IV-B | ROMBLON | ODIONGAN (ROMBLON) | P00631320LZ | Construction of Flood Mitigation Structure | 122.0186 | 12.4742 | 42139999.5 | 42098832.22 | 2022 | SUNWEST, INC. (FORMERLY: SUNWEST CONSTRUCTION & DEVELOPMENT CORPORATION) | 5035 | 2022 | 2022-09-21 | 02/23/2022 | 41167.28 | 0 | 2022-09-20 |  | 1
2023 | Region II | BATANES | IVANA (BATANES) | P00726109LZ | Construction of Flood Mitigation Structure | 121.948 | 20.4231 | 29362020 | 29362020 | 2024 | MJMARI BUILDERS AND DEVELOPMENT CORPORATION (FORMERLY: MJMARI BUILDERS AND ENTERPRISES) | 5036 | 2023 | 2024-03-15 | 03/06/2023 | 0 | 0 | 2024-04-14 | 30
2022 | Region III | AURORA | DIPACULAO (AURORA) | P00631157LZ | Construction of Flood Mitigation Structure | 121.5052 | 15.8475 | 14700000 | 14700000 | 2022 | MORNING STEEL CONSTRUCTION | 5037 | 2022 | 2022-07-17 | 02/11/2022 | 0 | 0 | 2022-07-16 |  | 1
2024 | Region IV-A | QUEZON | GENERAL NAKAR (QUEZON) | P00820287LZ | Construction of Flood Mitigation Structure | 121.6076 | 14.7412 | 51467310 | 51467062.5 | 2024 | DQT BUILDERS CORPORATION (FORMERLY DQT BUILDERS) | 5038 | 2024 | 2024-09-08 | 02/19/2024 | 247.5 | 0 | 2024-09-07 |  | 1
2022 | Region IV-A | QUEZON | LUCENA CITY (CAPITAL) (QUEZON) | P00620870LZ | Construction of Flood Mitigation Structure | 121.6077 | 13.9212 | 96500000 | 96499996.87 | 2023 | RAPID FOREMOST CONST. CO. / JAICA CONST. CORP | 5039 | 2022 | 2023-04-19 | 02/24/2022 | 3.13 | 0 | 2023-04-18 |  | 1
2023 | Region II | ISABELA | CITY OF SANTIAGO (ISABELA) | P00727110LZ | Construction of Flood Mitigation Structure | 121.6086 | 16.6846 | 49000000 | 48999075.93 | 2023 | NTL BUILDERS AND DEVELOPER | 5040 | 2023 | 2023-08-16 | 03/16/2023 | 924.07 | 0 | 2023-11-27 | 103
2021 | Region IV-A | QUEZON |  | P00526110LZ | Construction of Flood Mitigation Structure | 121.61 | 13.9403 | 39200000 | 39200000 | 2022 | RAPID FOREMOST CONST. CO. / WYDERWAYS BUILDERS AND SUPPLIES | 5041 | 2021 | 2022-12-07 | 01/12/2022 | 0 | 0 | 2022-12-06 |  | 1
2021 | Region IV-A | QUEZON |  | P00526109LZ | Construction of Flood Mitigation Structure | 121.61 | 13.9238 | 39200000 | 39199999.98 | 2022 | RAPID FOREMOST CONST. CO. | 5042 | 2021 | 2022-11-07 | 01/12/2022 | 0.02 | 0 | 2022-11-06 |  | 1
2022 | Region IV-A | QUEZON | LUCENA CITY (CAPITAL) (QUEZON) | P00620599LZ | Construction of Flood Mitigation Structure | 121.611 | 13.9168 | 49000000 | 49000000 | 2023 | RAPID FOREMOST CONST. CO. | 5043 | 2022 | 2023-03-15 | 05/20/2022 | 0 | 0 | 2023-03-14 |  | 1
2022 | Region IV-A | QUEZON | LUCENA CITY (CAPITAL) (QUEZON) | P00620598LZ | Construction of Flood Mitigation Structure | 121.6114 | 13.9171 | 49000000 | 49000000 | 2022 | RAPID FOREMOST CONST. CO. / JAICA CONST. CORP | 5044 | 2022 | 2022-10-21 | 02/24/2022 | 0 | 0 | 2022-10-20 |  | 1
2023 | Region II | ISABELA | ROXAS (ISABELA) | P00726424LZ | Construction of Flood Mitigation Structure | 121.6116 | 17.1322 | 48250000 | 48246100.19 | 2023 | SIFFU ROCKS CONSTRUCTION / C.R. DOMINGO CONSTRUCTION AND POWER DEVELOPMENT, INC. (FOR. C.R. DOMINGO CONSTRUCTION, INC.) | 5045 | 2023 | 2023-10-02 | 02/27/2023 | 3899.81 | 0 | 2023-10-24 | 22
2024 | Region III | AURORA | DIPACULAO (AURORA) | P00844535LZ | Construction of Drainage Structure | 121.6719 | 16.0121 | 24125000 | 23638253.17 | 2024 | VANMARVIL CONSTRUCTION | 5046 | 2024 | 2024-12-15 | 04/30/2024 | 486746.83 | 0 | 2024-11-14 |  | 31
2024 | Region II | ISABELA | SAN AGUSTIN (ISABELA) | P00821160LZ | Construction of Flood Mitigation Structure | 121.7441 | 16.4022 | 62725000 | 62722599.34 | 2024 | NTL BUILDERS AND DEVELOPER | 5047 | 2024 | 2024-06-18 | 03/01/2024 | 2400.66 | 0 | 2024-10-26 | 130
2023 | Region II | ISABELA | MALLIG (ISABELA) | P00742304LZ | Construction of Flood Mitigation Structure | 121.612 | 17.1757 | 49179460 | 49092711.12 | 2024 | MAR-DEB CONSTRUCTION & DEVELOPMENT CORP. (FORMERLY: MAR-DEB CONSTRUCTION & DEVELOPMENT) | 5048 | 2023 | 2024-01-05 | 04/11/2023 | 86748.88 | 0 | 2024-01-04 |  | 1
2022 | Region IV-A | QUEZON | LUCENA CITY (CAPITAL) (QUEZON) | P00620600LZ | Construction of Flood Mitigation Structure | 121.6134 | 13.9164 | 49000000 | 49000000 | 2023 | RAPID FOREMOST CONST. CO. | 5049 | 2022 | 2023-07-11 | 05/25/2022 | 0 | 0 | 2023-07-17 | 6
2023 | Region IV-A | QUEZON | LUCENA CITY (CAPITAL) (QUEZON) | P00740379LZ | Construction of Flood Mitigation Structure | 121.6143 | 13.9165 | 96500000 | 96499997.82 | 2024 | RAPID FOREMOST CONST. CO. / JELCON-CONSTRUCTION AND TRADING CORPORATION | 5050 | 2023 | 2024-04-19 | 05/30/2023 | 2.18 | 0 | 2024-04-22 | 3
2023 | Region IV-A | QUEZON | LUCENA CITY (CAPITAL) (QUEZON) | P00740380LZ | Construction of Flood Mitigation Structure | 121.6163 | 13.9175 | 96500000 | 96499987.48 | 2024 | RAPID FOREMOST CONST. CO. | 5051 | 2023 | 2024-05-24 | 05/31/2023 | 12.52 | 0 | 2024-05-23 |  | 1
2022 | Region IV-A | QUEZON | LUCENA CITY (CAPITAL) (QUEZON) | P00620596LZ | Construction of Flood Mitigation Structure | 121.6167 | 13.9498 | 24500000 | 24500000 | 2023 | JAICA CONST. CORP | 5052 | 2022 | 2023-11-13 | 03/24/2022 | 0 | 0 | 2024-03-21 | 129
2024 | Region II | CAGAYAN | SANTO NIÃ‘O (FAIRE) (CAGAYAN) | P00821190LZ | Construction of Flood Mitigation Facility | 121.6172 | 17.9608 | 49000000 | 48237059.31 | 2024 | TJMT CONSTRUCTION / VHT CAGAYAN BUILDERS CORPORATION | 5053 | 2024 | 2024-08-05 | 02/07/2024 | 762940.69 | 0 | 2024-08-15 | 10
2024 | Region IV-A | QUEZON | LUCENA CITY (CAPITAL) (QUEZON) | P00823502LZ | Construction of Flood Mitigation Structure | 121.6182 | 13.9422 | 96500000 | 96500000 | 2025 | UNIVERSAL DE LEON CONSTRUCTION AND AGGREGATES | 5054 | 2024 | 2025-03-24 | 04/29/2024 | 0 | 0 | 2025-03-23 |  | 1
2023 | Region II | ISABELA | ROXAS (ISABELA) | P00726441LZ | Construction of Flood Mitigation Structure | 121.619 | 17.1295 | 72375000 | 72374954.49 | 2024 | MAR-DEB CONSTRUCTION & DEVELOPMENT CORP. (FORMERLY: MAR-DEB CONSTRUCTION & DEVELOPMENT) | 5055 | 2023 | 2024-01-15 | 02/27/2023 | 45.51 | 0 | 2024-01-25 | 10
2022 | Region IV-A | QUEZON | LUCENA CITY (CAPITAL) (QUEZON) | P00632906LZ | Construction of Flood Mitigation Structure | 121.6192 | 13.931 | 4950000 | 4950000 | 2022 | JAICA CONST. CORP | 5056 | 2022 | 2022-07-15 | 03/24/2022 | 0 | 0 | 2022-07-20 | 5
2024 | Region II | ISABELA | ROXAS (ISABELA) | P00821217LZ | Construction of Slope Protection Structure | 121.6193 | 17.1369 | 96500000 | 96488772.99 | 2024 | JWU CONSTRUCTION AND SUPPLY | 5057 | 2024 | 2024-04-16 | 03/04/2024 | 11227.01 | 0 | 2025-03-08 | 326
2022 | Region IV-A | QUEZON | LUCENA CITY (CAPITAL) (QUEZON) | P00631306LZ | Construction of Slope Protection Structure | 121.6196 | 13.9313 | 49000000 | 49000000 | 2023 | I.A . BOSQUE CONSTRUCTION CORPORATION | 5058 | 2022 | 2023-07-12 | 02/24/2022 | 0 | 0 | 2023-08-03 | 22
2021 | Region IV-A | QUEZON |  | P00526444LZ | Construction of Slope Protection Structure | 121.62 | 13.9283 | 49000000 | 49000000 | 2022 | RAPID FOREMOST CONST. CO. | 5059 | 2021 | 2022-10-08 | 01/12/2022 | 0 | 0 | 2022-10-07 |  | 1
2023 | Region II | ISABELA | AURORA (ISABELA) | P00735971LZ | Construction of Flood Mitigation Structure | 121.6217 | 16.9663 | 48250000 | 48233662.14 | 2023 | RRC CO. INC. (FORMERLY: R R C CONSTRUCTION) | 5060 | 2023 | 2023-07-17 | 02/27/2023 | 16337.86 | 0 | 2023-11-23 | 129
2024 | Region II | QUIRINO | AGLIPAY (QUIRINO) | P00825238LZ | Construction of Flood Mitigation Structure | 121.622 | 16.4733 | 34300000 | 34247245.44 | 2024 | A.P.D. CONSTRUCTION, INC. (FORMERLY: APD CONSTRUCTION) | 5061 | 2024 | 2024-09-15 | 04/24/2024 | 52754.56 | 0 | 2024-11-26 | 72
2024 | Region II | ISABELA | ROXAS (ISABELA) | P00824888LZ | Construction of Flood Mitigation Structure | 121.6225 | 17.1386 | 96500000 | 96165781.02 | 2024 | RRC CO. INC. (FORMERLY: R R C CONSTRUCTION) | 5062 | 2024 | 2024-07-29 | 03/18/2024 | 334218.98 | 0 | 2025-03-25 | 239
2023 | Region II | ISABELA | ROXAS (ISABELA) | P00725682LZ | Construction of Slope Protection Structure | 121.6235 | 17.139 | 190750000 | 190598720.8 | 2024 | A. DE GUIA CONSTRUCTION AND DEVELOPMENT CORPORATION (FORMERLY: A. DE GUIA CONSTRUCTION) | 5063 | 2023 | 2024-02-15 | 05/30/2023 | 151279.2 | 0 | 2024-05-15 | 90
2022 | Region IV-A | QUEZON | GENERAL NAKAR (QUEZON) | P00621477LZ | Construction of Flood Mitigation Structure | 121.6245 | 14.7545 | 67550000 | 67379438.9 | 2022 | I&E CONSTRUCTION CORPORATION (FORMERLY: I&E CONSTR | 5064 | 2022 | 2022-09-29 | 03/28/2022 | 170561.1 | 0 | 2022-12-10 | 72
2022 | Region II | CAGAYAN | LASAM (CAGAYAN) | P00631108LZ | Construction of Flood Mitigation Structure | 121.6255 | 18.0932 | 43120000 | 43120000 | 2022 | OCP CONSTRUCTION | 5065 | 2022 | 2022-11-26 | 02/02/2022 | 0 | 0 | 2022-11-26 | 0
2022 | Region III | AURORA | DIPACULAO (AURORA) | P00631151LZ | Construction of Flood Mitigation Structure | 121.6262 | 15.9668 | 9800000 | 9800000 | 2022 | ALEXI LOUISSE CONSTRUCTION & GENERAL MERCHANDISE | 5066 | 2022 | 2022-10-05 | 04/04/2022 | 0 | 0 | 2022-10-04 |  | 1
2022 | Region IV-A | QUEZON | INFANTA (QUEZON) | P00621580LZ | Construction of Flood Mitigation Structure | 121.6265 | 14.7505 | 96500000 | 96499996.64 | 2022 | PHESCO, INCORPORATED | 5067 | 2022 | 2022-10-20 | 03/28/2022 | 3.36 | 0 | 2023-01-28 | 100
2022 | Region II | ISABELA | MALLIG (ISABELA) | P00621160LZ | Construction of Flood Mitigation Structure | 121.6287 | 17.1911 | 96500000 | 96467970.82 | 2023 | RRC CO. INC. (FORMERLY: R R C CONSTRUCTION) | 5068 | 2022 | 2023-05-24 | 06/08/2022 | 32029.18 | 0 | 2023-05-23 |  | 1
2022 | Region IV-A | QUEZON | INFANTA (QUEZON) | P00621579LZ | Construction of Flood Mitigation Structure | 121.6291 | 14.7513 | 96500000 | 96499799.98 | 2022 | PHESCO, INCORPORATED | 5069 | 2022 | 2022-10-20 | 05/17/2022 | 200.02 | 0 | 2023-03-19 | 150
2023 | Region II | ISABELA | SAN MANUEL (ISABELA) | P00742305LZ | Construction of Drainage Structure | 121.6302 | 17.0244 | 9900000 | 9885543.3 | 2024 | 619 BUILDERS CONSTRUCTION CORPORATION | 5070 | 2023 | 2024-01-21 | 05/03/2023 | 14456.7 | 0 | 2023-12-07 |  | 45
2024 | Region II | QUIRINO | AGLIPAY (QUIRINO) | P00825237LZ | Construction of Flood Mitigation Structure | 121.6306 | 16.4685 | 34300000 | 33265659.77 | 2024 | A.P.D. CONSTRUCTION, INC. (FORMERLY: APD CONSTRUCTION) | 5071 | 2024 | 2024-07-30 | 04/24/2024 | 1034340.23 | 0 | 2024-11-26 | 119
2022 | Region II | CAGAYAN | APARRI (CAGAYAN) | P00621023LZ | Construction of Flood Mitigation Structure | 121.6315 | 18.3567 | 19600000 | 19600000 | 2023 | E. GUADIZ CONSTRUCTION | 5072 | 2022 | 2023-10-03 | 02/02/2022 | 0 | 0 | 2022-11-13 |  | 324
2023 | Region IV-A | QUEZON | INFANTA (QUEZON) | P00726591LZ | Construction of Flood Mitigation Structure | 121.6325 | 14.7524 | 96500000 | 91934349.67 | 2023 | DJB CONSTRUCTION SERVICES | 5073 | 2023 | 2023-11-14 | 03/14/2023 | 4565650.33 | 0 | 2024-01-06 | 53
2022 | Region II | ISABELA | ECHAGUE (ISABELA) | P00637013LZ | Construction of Flood Mitigation Structure | 121.6329 | 16.695 | 96500000 | 96494743.04 | 2023 | MA TESORO CONSTRUCTION / EGB CONSTRUCTION CORPORATION (FORMERLY: EGB CONSTRUCTION) | 5074 | 2022 | 2023-02-27 | 04/01/2022 | 5256.96 | 0 | 2023-02-16 |  | 11
2022 | Region IV-A | QUEZON | LUCENA CITY (CAPITAL) (QUEZON) | P00631307LZ | Construction of Slope Protection Structure | 121.6331 | 13.96 | 9800000 | 9800000 | 2022 | WAYCON BUILDERS AND CONSTRUCTION SUPPLY CORP. (FOR:WAYCON BUILDERS & CONSTRUCTION SUPPLY) | 5075 | 2022 | 2022-08-17 | 02/24/2022 | 0 | 0 | 2022-08-16 |  | 1
2023 | Region IV-A | QUEZON | INFANTA (QUEZON) | P00727318LZ | Construction of Flood Mitigation Structure | 121.6338 | 14.7532 | 96500000 | 91287809.4 | 2023 | DJB CONSTRUCTION SERVICES | 5076 | 2023 | 2023-11-14 | 04/04/2023 | 5212190.6 | 0 | 2024-01-27 | 74
2022 | Region II | ISABELA | SAN MANUEL (ISABELA) | P00639336LZ | Rehabilitation / Major Repair of Drainage Structure | 121.6345 | 17.022 | 69074700 | 69023570.25 | 2023 | 619 BUILDERS CONSTRUCTION CORPORATION / C.R. DOMINGO CONSTRUCTION AND POWER DEVELOPMENT, INC. (FOR. C.R. DOMINGO CONSTRUCTION, INC.) | 5077 | 2022 | 2023-04-11 | 06/09/2022 | 51129.75 | 0 | 2023-04-10 |  | 1
2024 | Region IV-A | QUEZON | LUCENA CITY (CAPITAL) (QUEZON) | P00839639LZ | Construction of Flood Mitigation Structure | 121.6346 | 13.9436 | 4950000 | 4950000 | 2024 | JAICA CONST. CORP | 5078 | 2024 | 2024-04-12 | 02/13/2024 | 0 | 0 | 2024-07-10 | 89
2022 | Region II | ISABELA | ROXAS (ISABELA) | P00621156LZ | Construction of Flood Mitigation Structure | 121.6348 | 17.127 | 96500000 | 96499886.84 | 2023 | SIFFU ROCKS CONSTRUCTION / C.R. DOMINGO CONSTRUCTION AND POWER DEVELOPMENT, INC. (FOR. C.R. DOMINGO CONSTRUCTION, INC.) | 5079 | 2022 | 2023-04-18 | 06/08/2022 | 113.16 | 0 | 2023-03-24 |  | 25
2023 | Region IV-A | QUEZON | INFANTA (QUEZON) | P00727317LZ | Construction of Flood Mitigation Structure | 121.635 | 14.7545 | 77200000 | 77002093.09 | 2023 | 11 DIAMOND EAGLE CONSTRUCTION CORPORATION (FORMERLY:11 DIAMOND EAGLE CONSTRUCTION) | 5080 | 2023 | 2023-12-09 | 04/17/2023 | 197906.91 | 0 | 2024-01-25 | 47
2023 | Region IV-A | QUEZON | INFANTA (QUEZON) | P00726947LZ | Construction of Flood Mitigation Structure | 121.635 | 14.7545 | 67550000 | 67548647.45 | 2024 | JUNTEREAL INDUSTRIAL AND DEVELOPMENT CORPORATION | 5081 | 2023 | 2024-05-17 | 08/07/2023 | 1352.55 | 0 | 2024-05-16 |  | 1
2023 | Region IV-A | QUEZON | INFANTA (QUEZON) | P00726937LZ | Construction of Flood Mitigation Structure | 121.6356 | 14.7563 | 193000000 | 192997900.4 | 2024 | SILVERWOLVES CONSTRUCTION CORPORATION | 5082 | 2023 | 2024-04-09 | 06/15/2023 | 2099.6 | 0 | 2024-04-08 |  | 1
2023 | Region IV-A | QUEZON | INFANTA (QUEZON) | P00726936LZ | Construction of Flood Mitigation Structure | 121.6361 | 14.7598 | 193000000 | 192997440.9 | 2024 | SILVERWOLVES CONSTRUCTION CORPORATION | 5083 | 2023 | 2024-04-09 | 06/15/2023 | 2559.1 | 0 | 2024-04-08 |  | 1
2024 | Region II | ISABELA | ROXAS (ISABELA) | P00825232LZ | Construction of Slope Protection Structure | 121.6378 | 17.1291 | 49000000 | 48968530.26 | 2024 | RR BUILDERS / EGB CONSTRUCTION CORPORATION (FORMERLY: EGB CONSTRUCTION) | 5084 | 2024 | 2024-09-01 | 04/15/2024 | 31469.74 | 0 | 2024-12-26 | 116
2023 | Region IV-A | QUEZON | GENERAL NAKAR (QUEZON) | P00727316LZ | Construction of Flood Mitigation Structure | 121.6394 | 14.766 | 96500000 | 96499720.67 | 2024 | I&E CONSTRUCTION CORPORATION (FORMERLY: I&E CONSTR / MOTIONTRADE DEVELOPMENT CORPORATION | 5085 | 2023 | 2024-01-11 | 04/17/2023 | 279.33 | 0 | 2024-01-10 |  | 1
2023 | Region II | ISABELA | AURORA (ISABELA) | P00735970LZ | Construction of Flood Mitigation Structure | 121.6396 | 16.9766 | 47929460 | 47929443.39 | 2023 | ANORE CONSTRUCTION | 5086 | 2023 | 2023-07-26 | 03/13/2023 | 16.61 | 0 | 2023-12-07 | 134
2023 | Region IV-A | QUEZON | LUCENA CITY (CAPITAL) (QUEZON) | P00740649LZ | Construction of Flood Mitigation Structure | 121.6422 | 13.9074 | 19600000 | 19599995.57 | 2023 | I.A . BOSQUE CONSTRUCTION CORPORATION | 5087 | 2023 | 2023-10-10 | 05/09/2023 | 4.43 | 0 | 2024-03-02 | 144
2022 | Region II | ISABELA | SAN ISIDRO (ISABELA) | P00620145LZ | Construction of Flood Mitigation Structure | 121.6422 | 16.7388 | 76703990 | 76703990 | 2022 | V.B. MANUBAY CONSTRUCTION | 5088 | 2022 | 2022-11-10 | 04/13/2022 | 0 | 0 | 2022-12-22 | 42
2022 | Region II | ISABELA | MALLIG (ISABELA) | P00621159LZ | Construction of Flood Mitigation Structure | 121.6425 | 17.1711 | 96500000 | 96448972.94 | 2022 | JWU CONSTRUCTION AND SUPPLY / MAR-DEB CONSTRUCTION & DEVELOPMENT CORP. (FORMERLY: MAR-DEB CONSTRUCTION & DEVELOPMENT) | 5089 | 2022 | 2022-12-14 | 06/08/2022 | 51027.06 | 0 | 2023-03-24 | 100
2023 | Region II | CAGAYAN | GATTARAN (CAGAYAN) | P00726672LZ | Construction of Flood Mitigation Structure | 121.643 | 18.0658 | 39200000 | 39190000 | 2024 | TJMT CONSTRUCTION | 5090 | 2023 | 2024-04-29 | 02/22/2023 | 10000 | 0 | 2023-10-04 |  | 208
2024 | Region II | QUIRINO | AGLIPAY (QUIRINO) | P00820791LZ | Construction of Flood Mitigation Structure | 121.6431 | 16.4432 | 19600000 | 19594188.04 | 2024 | A.P.D. CONSTRUCTION, INC. (FORMERLY: APD CONSTRUCTION) | 5091 | 2024 | 2024-09-11 | 02/16/2024 | 5811.96 | 0 | 2024-09-10 |  | 1
2022 | Region II | ISABELA | ROXAS (ISABELA) | P00621157LZ | Construction of Flood Mitigation Structure | 121.6432 | 17.1271 | 96500000 | 96495711.51 | 2023 | A. DE GUIA CONSTRUCTION AND DEVELOPMENT CORPORATION (FORMERLY: A. DE GUIA CONSTRUCTION) | 5092 | 2022 | 2023-04-17 | 06/08/2022 | 4288.49 | 0 | 2023-05-28 | 41
2022 | Region II | CAGAYAN | GATTARAN (CAGAYAN) | P00621024LZ | Construction of Flood Mitigation Structure | 121.6439 | 18.0673 | 24500000 | 24499913.26 | 2023 | TJMT CONSTRUCTION | 5093 | 2022 | 2023-06-11 | 02/02/2022 | 86.74 | 0 | 2022-12-20 |  | 173
2020 | Region II | CAGAYAN |  | P00448930LZ | Construction of Flood Mitigation Structure | 121.6441 | 18.3509 | 34300000 | 33259747.11 | 2022 | PERRC INC. (FORMERLY: P.E.R.R.C. CONSTRUCTION & DEVELOPMENT CORPORATION) | 5094 | 2020 | 2022-08-04 | 11/18/2020 | 1040252.89 | 0 | 2021-08-07 |  | 362
2021 | Region II | CAGAYAN |  | P00448930LZ | Construction of Flood Mitigation Structure | 121.6441 | 18.3509 | 34300000 | 33259747.11 | 2022 | PERRC INC. (FORMERLY: P.E.R.R.C. CONSTRUCTION & DEVELOPMENT CORPORATION) | 5095 | 2021 | 2022-08-04 | 11/18/2020 | 1040252.89 | 0 | 2021-08-07 |  | 362
2022 | Region II | CAGAYAN | GATTARAN (CAGAYAN) | P00621025LZ | Construction of Flood Mitigation Structure | 121.6444 | 18.0682 | 24500000 | 24499889.95 | 2023 | TJMT CONSTRUCTION | 5096 | 2022 | 2023-05-28 | 02/02/2022 | 110.05 | 0 | 2023-04-04 |  | 54
2022 | Region II | CAGAYAN | GATTARAN (CAGAYAN) | P00621030LZ | Construction of Flood Mitigation Structure | 121.6449 | 18.0691 | 49000000 | 48999684.98 | 2023 | CMG JR. BUILDERS / W.D. NAVARRO CONSTRUCTION CO. | 5097 | 2022 | 2023-06-11 | 03/01/2022 | 315.02 | 0 | 2023-03-13 |  | 90
2023 | Region II | ISABELA | ROXAS (ISABELA) | P00726440LZ | Construction of Flood Mitigation Structure | 121.645 | 17.1272 | 71894190 | 72374776.2 | 2023 | DANYSONS CONSTRUCTION AND DEVELOPMENT CORPORATION (FORMERLY: DANYSONS CONSTRUCTION) | 5098 | 2023 | 2023-10-02 | 04/20/2023 | 0 | 480586.2 | 2023-12-11 | 70
2020 | Region II | CAGAYAN |  | P00448928LZ | Construction of Flood Mitigation Structure | 121.6453 | 18.3502 | 34300000 | 33211358.78 | 2022 | PERRC INC. (FORMERLY: P.E.R.R.C. CONSTRUCTION & DEVELOPMENT CORPORATION) | 5099 | 2020 | 2022-07-10 | 11/18/2020 | 1088641.22 | 0 | 2021-08-07 |  | 337
2021 | Region II | CAGAYAN |  | P00448928LZ | Construction of Flood Mitigation Structure | 121.6453 | 18.3502 | 34300000 | 33211358.78 | 2022 | PERRC INC. (FORMERLY: P.E.R.R.C. CONSTRUCTION & DEVELOPMENT CORPORATION) | 5100 | 2021 | 2022-07-10 | 11/18/2020 | 1088641.22 | 0 | 2021-08-07 |  | 337
2023 | Region II | CAGAYAN | GATTARAN (CAGAYAN) | P00726666LZ | Construction of Flood Mitigation Structure | 121.6454 | 18.0717 | 49000000 | 48980000 | 2023 | TJMT CONSTRUCTION | 5101 | 2023 | 2023-11-26 | 02/21/2023 | 20000 | 0 | 2023-11-09 |  | 17
2022 | Region II | CAGAYAN | APARRI (CAGAYAN) | P00621029LZ | Construction of Flood Mitigation Structure | 121.6469 | 18.3489 | 19600000 | 19404000 | 2023 | PERRC INC. (FORMERLY: P.E.R.R.C. CONSTRUCTION & DEVELOPMENT CORPORATION) | 5102 | 2022 | 2023-03-13 | 03/22/2022 | 196000 | 0 | 2022-11-16 |  | 117
2022 | Region II | ISABELA | SAN ISIDRO (ISABELA) | P00639329LZ | Construction of Flood Mitigation Structure | 121.6484 | 16.773 | 96500000 | 96500000 | 2022 | MA TESORO CONSTRUCTION / EGB CONSTRUCTION CORPORATION (FORMERLY: EGB CONSTRUCTION) | 5103 | 2022 | 2022-11-25 | 04/01/2022 | 0 | 0 | 2022-11-28 | 3
2024 | Region II | CAGAYAN | SOLANA (CAGAYAN) | P00845938LZ | Construction of Drainage Structure | 121.6484 | 17.6783 | 4950000 | 4929544.47 | 2025 | 4MD JSL CONSTRUCTION INC. (FORMERLY: JUST SAFE LEADING (JSL) INNOVATIVE CREATION CORPORATION) | 5104 | 2024 | 2025-02-03 | 09/30/2024 | 20455.53 | 0 | 2025-02-05 | 2
2023 | Region II | ISABELA | CABATUAN (ISABELA) | P00725661LZ | Construction of Flood Mitigation Structure | 121.6486 | 16.9553 | 71894189.85 | 71061011.85 | 2023 | D.A. CADELIÃ‘A CONSTRUCTION / GACUTAN CONSTRUCTION INC. (FORMERLY: GACUTAN CONSTRUCTION) | 5105 | 2023 | 2023-06-20 | 04/11/2023 | 833178 | 0 | 2024-01-07 | 201
2024 | Region II | ISABELA | CABATUAN (ISABELA) | P00820164LZ | Construction of Revetment | 121.6487 | 16.9553 | 77199999.54 | 77154847.16 | 2024 | JWU CONSTRUCTION AND SUPPLY | 5106 | 2024 | 2024-06-20 | 04/11/2024 | 45152.38 | 0 | 2025-01-22 | 216
2024 | Region II | CAGAYAN | GATTARAN (CAGAYAN) | P00824681LZ | Construction of Flood Mitigation Structure | 121.6503 | 18.0808 | 49000000 | 48985000 | 2024 | TJMT CONSTRUCTION | 5107 | 2024 | 2024-07-15 | 02/22/2024 | 15000 | 0 | 2024-11-06 | 114
2023 | Region II | CAGAYAN | GATTARAN (CAGAYAN) | P00726669LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.6506 | 18.0817 | 22540000 | 22530000 | 2024 | TJMT CONSTRUCTION | 5108 | 2023 | 2024-01-28 | 02/27/2023 | 10000 | 0 | 2023-10-09 |  | 111
2024 | Region III | AURORA | DIPACULAO (AURORA) | P00838513LZ | Construction of Flood Mitigation Structure | 121.6516 | 15.9883 | 48250000 | 48250000 | 2024 | ALEXI LOUISSE CONSTRUCTION & GENERAL MERCHANDISE | 5109 | 2024 | 2024-10-21 | 04/30/2024 | 0 | 0 | 2024-12-13 | 53
2022 | Region II | CAGAYAN | LAL-LO (CAGAYAN) | P00639334LZ | Construction of Drainage Structure | 121.6517 | 18.1675 | 49000000 | 47764380.24 | 2024 | JLL PULSAR CONSTRUCTION CORPORATION (FORMERLY: PULSAR CONSTRUCTION) | 5110 | 2022 | 2024-05-12 | 04/01/2022 | 1235619.76 | 0 | 2023-05-27 |  | 351
2022 | Region II | CAGAYAN | LAL-LO (CAGAYAN) | P00639335LZ | Construction of Drainage Structure | 121.6522 | 18.1693 | 49000000 | 47764065.48 | 2024 | JIRK CONSTRUCTION / JLL PULSAR CONSTRUCTION CORPORATION (FORMERLY: PULSAR CONSTRUCTION) | 5111 | 2022 | 2024-05-12 | 04/01/2022 | 1235934.52 | 0 | 2023-05-27 |  | 351
2022 | Region II | ISABELA | ECHAGUE (ISABELA) | P00639332LZ | Construction of Flood Mitigation Structure | 121.6543 | 16.6895 | 96500000 | 96497912.21 | 2023 | MA TESORO CONSTRUCTION / EGB CONSTRUCTION CORPORATION (FORMERLY: EGB CONSTRUCTION) | 5112 | 2022 | 2023-03-16 | 04/01/2022 | 2087.79 | 0 | 2023-03-15 |  | 1
2023 | Region II | CAGAYAN | GATTARAN (CAGAYAN) | P00726665LZ | Construction of Flood Mitigation Structure | 121.6551 | 18.0935 | 49000000 | 48985067.24 | 2023 | TJMT CONSTRUCTION | 5113 | 2023 | 2023-06-25 | 02/21/2023 | 14932.76 | 0 | 2023-11-09 | 137
2023 | Region II | CAGAYAN | APARRI (CAGAYAN) | P00726433LZ | Construction of Flood Mitigation Structure | 121.6553 | 18.307 | 86850000 | 86600000 | 2024 | TJMT CONSTRUCTION | 5114 | 2023 | 2024-05-06 | 04/02/2023 | 250000 | 0 | 2024-03-17 |  | 50
2023 | Region II | CAGAYAN | LAL-LO (CAGAYAN) | P00726675LZ | Construction of Revetment | 121.6556 | 18.1544 | 49000000 | 49000000 | 2024 | CMG JR. BUILDERS | 5115 | 2023 | 2024-01-28 | 02/14/2023 | 0 | 0 | 2023-11-02 |  | 87
2021 | Region II | CAGAYAN |  | P00526281LZ | Construction of Flood Mitigation Structure | 121.6576 | 18.0957 | 94500000 | 93970895.47 | 2022 | CMG JR. BUILDERS / W.D. NAVARRO CONSTRUCTION CO. | 5116 | 2021 | 2022-08-20 | 10/25/2021 | 529104.53 | 0 | 2022-09-06 | 17
2024 | Region II | CAGAYAN | GATTARAN (CAGAYAN) | P00821186LZ | Construction of Flood Mitigation Structure | 121.6581 | 18.0983 | 96500000 | 96490000 | 2024 | TJMT CONSTRUCTION | 5117 | 2024 | 2024-09-02 | 02/22/2024 | 10000 | 0 | 2025-03-01 | 180
2023 | Region II | CAGAYAN | LAL-LO (CAGAYAN) | P00726674LZ | Construction of Revetment | 121.6584 | 18.182 | 49000000 | 49000000 | 2024 | CMG JR. BUILDERS | 5118 | 2023 | 2024-09-29 | 02/14/2023 | 0 | 0 | 2024-01-01 |  | 272
2022 | Region II | CAGAYAN | LAL-LO (CAGAYAN) | P00631105LZ | Construction of Revetment | 121.6589 | 18.183 | 29400000 | 28518000 | 2023 | JIRK CONSTRUCTION | 5119 | 2022 | 2023-06-01 | 08/03/2022 | 882000 | 0 | 2023-04-12 |  | 50
2022 | Region II | CAGAYAN | LAL-LO (CAGAYAN) | P00640506LZ | Construction of Flood Mitigation Structure | 121.6589 | 18.1831 | 49500000 | 49398023.35 | 2023 | MEGAY CONSTRUCTION INC. (FORMERLY: MEGAY CONSTRUCTION) | 5120 | 2022 | 2023-05-28 | 04/01/2022 | 101976.65 | 0 | 2023-01-07 |  | 141
2022 | Region II | CAGAYAN | CAMALANIUGAN (CAGAYAN) | P00630932LZ | Construction of Flood Mitigation Structure | 121.6597 | 18.2984 | 141750000 | 141079466.5 | 2023 | GVDPM CONSTRUCTION CORP. (FORMERLY: ZM CONSTRUCTIO | 5121 | 2022 | 2023-06-24 | 04/08/2022 | 670533.5 | 0 | 2023-06-10 |  | 14
2024 | Region II | CAGAYAN | GATTARAN (CAGAYAN) | P00821187LZ | Construction of Flood Mitigation Structure | 121.66 | 18.1005 | 96500000 | 96488000 | 2024 | TJMT CONSTRUCTION | 5122 | 2024 | 2024-08-19 | 02/22/2024 | 12000 | 0 | 2025-03-01 | 194
2023 | Region II | CAGAYAN | LAL-LO (CAGAYAN) | P00726673LZ | Construction of Flood Mitigation Structure | 121.6608 | 18.1989 | 29400000 | 29389792.97 | 2023 | JIRK CONSTRUCTION | 5123 | 2023 | 2023-12-11 | 02/22/2023 | 10207.03 | 0 | 2023-10-12 |  | 60
2022 | Region II | CAGAYAN | LAL-LO (CAGAYAN) | P00640504LZ | Construction of Flood Mitigation Structure | 121.6611 | 18.1992 | 49500000 | 49398048.36 | 2023 | JLL PULSAR CONSTRUCTION CORPORATION (FORMERLY: PULSAR CONSTRUCTION) | 5124 | 2022 | 2023-05-28 | 04/01/2022 | 101951.64 | 0 | 2023-01-07 |  | 141
2022 | Region II | CAGAYAN | LAL-LO (CAGAYAN) | P00640505LZ | Construction of Flood Mitigation Structure | 121.6617 | 18.1958 | 49500000 | 49399244.41 | 2023 | MEGAY CONSTRUCTION INC. (FORMERLY: MEGAY CONSTRUCTION) | 5125 | 2022 | 2023-05-28 | 04/01/2022 | 100755.59 | 0 | 2023-03-08 |  | 81
2024 | Region II | CAGAYAN | GATTARAN (CAGAYAN) | P00821188LZ | Construction of Flood Mitigation Structure | 121.6618 | 18.1025 | 96500000 | 96490000 | 2025 | TJMT CONSTRUCTION | 5126 | 2024 | 2025-01-24 | 02/22/2024 | 10000 | 0 | 2025-03-01 | 36
2024 | Region II | ISABELA | ROXAS (ISABELA) | P00824877LZ | Construction of Flood Mitigation Structure | 121.6619 | 17.1551 | 96500000 | 96497828.67 | 2025 | JWU CONSTRUCTION AND SUPPLY | 5127 | 2024 | 2025-02-10 | 05/13/2024 | 2171.33 | 0 | 2025-04-15 | 64
2023 | Region II | ISABELA | QUIRINO (ISABELA) | P00726422LZ | Construction of Flood Mitigation Structure | 121.6621 | 17.1211 | 48250000 | 48232335.87 | 2023 | RRC CO. INC. (FORMERLY: R R C CONSTRUCTION) | 5128 | 2023 | 2023-07-24 | 02/27/2023 | 17664.13 | 0 | 2023-10-03 | 71
2024 | Region II | CAGAYAN | GATTARAN (CAGAYAN) | P00821189LZ | Construction of Flood Mitigation Structure | 121.6641 | 18.1044 | 96500000 | 96490000 | 2024 | TJMT CONSTRUCTION | 5129 | 2024 | 2024-12-02 | 02/22/2024 | 10000 | 0 | 2025-03-01 | 89
2024 | Region II | ISABELA | ECHAGUE (ISABELA) | P00845945LZ | Construction of Flood Mitigation Structure | 121.6643 | 16.6941 | 49500000 | 49490000 | 2024 | JWU CONSTRUCTION AND SUPPLY | 5130 | 2024 | 2024-07-18 | 05/10/2024 | 10000 | 0 | 2025-01-02 | 168
2024 | Region II | ISABELA | JONES (ISABELA) | P00843267LZ | Construction of Flood Mitigation Structure | 121.6647 | 16.5734 | 96500000 | 96500000 | 2024 | DALCON CONSTRUCTION | 5131 | 2024 | 2024-10-10 | 06/03/2024 | 0 | 0 | 2025-06-08 | 241
2024 | Region II | ISABELA | JONES (ISABELA) | P00843277LZ | Construction of Flood Mitigation Structure | 121.6649 | 16.5731 | 96500000 | 96487840 | 2024 | JWU CONSTRUCTION AND SUPPLY | 5132 | 2024 | 2024-11-12 | 06/06/2024 | 12160 | 0 | 2025-06-11 | 211
2024 | Region III | AURORA | DIPACULAO (AURORA) | P00838517LZ | Construction of Flood Mitigation Structure | 121.6655 | 16.008 | 48250000 | 47338372.71 | 2025 | ALEXI LOUISSE CONSTRUCTION & GENERAL MERCHANDISE | 5133 | 2024 | 2025-05-08 | 04/30/2024 | 911627.29 | 0 | 2024-11-06 |  | 183
2023 | Region II | ISABELA | JONES (ISABELA) | P00726874LZ | Construction of Flood Mitigation Structure | 121.6664 | 16.5743 | 96500000 | 96465021.4 | 2023 | ROAD EDGE TRADING & DEVELOPMENT SERVICES | 5134 | 2023 | 2023-09-15 | 06/01/2023 | 34978.6 | 0 | 2024-03-23 | 190
2022 | Region II | ISABELA | ECHAGUE (ISABELA) | P00631137LZ | Construction of Flood Mitigation Structure | 121.6677 | 16.694 | 45080000 | 45080000 | 2022 | MA TESORO CONSTRUCTION / EGB CONSTRUCTION CORPORATION (FORMERLY: EGB CONSTRUCTION) | 5135 | 2022 | 2022-08-08 | 02/16/2022 | 0 | 0 | 2022-08-11 | 3
2022 | Region II | ISABELA | ECHAGUE (ISABELA) | P00621617LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.6677 | 16.694 | 19600000 | 19600000 | 2022 | C.R. DOMINGO CONSTRUCTION AND POWER DEVELOPMENT, INC. (FOR. C.R. DOMINGO CONSTRUCTION, INC.) | 5136 | 2022 | 2022-09-01 | 04/13/2022 | 0 | 0 | 2022-09-29 | 28
2022 | Region II | BATANES | MAHATAO (BATANES) | P00632792LZ | Construction of Flood Mitigation Structure | 121.9489 | 20.4145 | 4950000 | 4925027.42 | 2022 | MOJR CONSTRUCTION AND DEVELOPMENT CORPORATION | 5137 | 2022 | 2022-08-05 | 02/17/2022 | 24972.58 | 0 | 2022-07-06 |  | 30
2022 | Region II | ISABELA | SAN MARIANO (ISABELA) | P00621060LZ | Construction of Flood Mitigation Structure | 122.0196 | 16.9821 | 19599997.65 | 19294339.84 | 2022 | YZK BUILDERS | 5138 | 2022 | 2022-07-12 | 03/28/2022 | 305657.81 | 0 | 2022-09-28 | 78
2022 | Region II | CAGAYAN | PEÃ‘ABLANCA (CAGAYAN) | P00621412LZ | Construction of Flood Mitigation Structure | 121.8061 | 17.6584 | 77200000 | 77200000 | 2023 | JC PALOMO CONSTRUCTION & CONSTRUCTION SUPPLY / C.T. LEONCIO CONSTRUCTION & TRADING | 5139 | 2022 | 2023-11-27 | 03/28/2022 | 0 | 0 | 2023-03-19 |  | 253
2023 | Region VI | ILOILO | OTON (ILOILO) | P00733297VS | Construction of Flood Mitigation Structure | 122.1144 | 10.5927 | 29400000 | 29399309.86 | 2024 | ASIA STRUCTURAL DEVELOPER CORPORATION | 5140 | 2023 | 2024-05-10 | 03/29/2023 | 690.14 | 0 | 2024-03-18 |  | 53
2022 | Region IV-B | ROMBLON | FERROL (ROMBLON) | P00631317LZ | Construction of Slope Protection Structure | 121.9489 | 12.3003 | 42139999.5 | 42058853.51 | 2022 | SUNWEST, INC. (FORMERLY: SUNWEST CONSTRUCTION & DEVELOPMENT CORPORATION) | 5141 | 2022 | 2022-09-21 | 02/23/2022 | 81145.99 | 0 | 2022-09-20 |  | 1
2024 | Region IV-B | ROMBLON | ODIONGAN (ROMBLON) | P00844782LZ | Construction of Flood Mitigation Structure | 122.0203 | 12.436 | 48999999.95 | 48997740.27 | 2024 | SUNWEST, INC. (FORMERLY: SUNWEST CONSTRUCTION & DEVELOPMENT CORPORATION) | 5142 | 2024 | 2024-11-25 | 04/08/2024 | 2259.68 | 0 | 2024-12-01 | 6
2021 | Region II | ISABELA |  | P00526277LZ | Construction of Flood Mitigation Structure | 121.8067 | 17.3902 | 75829275 | 75587196.78 | 2022 | DRAGON TWELVE BUILDERS & CONSTRUCTION SUPPLY / EGB CONSTRUCTION CORPORATION (FORMERLY: EGB CONSTRUCTION) | 5143 | 2021 | 2022-11-04 | 08/02/2021 | 242078.22 | 0 | 2022-11-08 | 4
2023 | Region II | ISABELA | CITY OF SANTIAGO (ISABELA) | P00727111LZ | Construction of Flood Mitigation Structure | 121.5081 | 16.7191 | 49000000 | 48997907.91 | 2023 | NTL BUILDERS AND DEVELOPER | 5144 | 2023 | 2023-09-28 | 04/05/2023 | 2092.09 | 0 | 2023-12-17 | 80
2023 | Region II | ISABELA | SAN MARIANO (ISABELA) | P00726444LZ | Construction of Flood Mitigation Structure | 122.0212 | 16.9257 | 96499994.5 | 96399710.65 | 2024 | RRC CO. INC. (FORMERLY: R R C CONSTRUCTION) | 5145 | 2023 | 2024-02-19 | 05/17/2023 | 100283.85 | 0 | 2024-04-01 | 42
2022 | Region II | BATANES | MAHATAO (BATANES) | P00632793LZ | Construction of Flood Mitigation Structure | 121.9491 | 20.4161 | 4924000 | 4900000 | 2022 | MOJR CONSTRUCTION AND DEVELOPMENT CORPORATION | 5146 | 2022 | 2022-09-25 | 03/23/2022 | 24000 | 0 | 2022-08-09 |  | 47
2023 | Region II | ISABELA | QUIRINO (ISABELA) | P00726420LZ | Construction of Flood Mitigation Structure | 121.8068 | 17.155 | 48250000 | 48231388.59 | 2023 | DANYSONS CONSTRUCTION AND DEVELOPMENT CORPORATION (FORMERLY: DANYSONS CONSTRUCTION) | 5147 | 2023 | 2023-07-10 | 02/27/2023 | 18611.41 | 0 | 2023-09-23 | 75
2022 | Region II | ISABELA | JONES (ISABELA) | P00639463LZ | Construction of Flood Mitigation Structure | 121.672 | 16.5212 | 49000000 | 49000000 | 2022 | C.R. DOMINGO CONSTRUCTION AND POWER DEVELOPMENT, INC. (FOR. C.R. DOMINGO CONSTRUCTION, INC.) | 5148 | 2022 | 2022-10-07 | 04/07/2022 | 0 | 0 | 2022-11-27 | 51
2024 | Region II | ISABELA | SAN AGUSTIN (ISABELA) | P00823345LZ | Construction of Flood Mitigation Structure | 121.7445 | 16.4316 | 96500000 | 96398940 | 2024 | V.B. MANUBAY CONSTRUCTION | 5149 | 2024 | 2024-10-21 | 06/03/2024 | 101060 | 0 | 2025-03-31 | 161
2021 | Cordillera Administrative Region | MOUNTAIN PROVINCE |  | P00525920LZ | Construction of Flood Mitigation Structure | 121.5086 | 17.2817 | 19600000 | 19339539.28 | 2022 | UPLAND CONSTRUCTION AND ENGINEERING SERVICES | 5150 | 2021 | 2022-09-26 | 04/03/2022 | 260460.72 | 0 | 2022-10-08 | 12
2024 | Region VI | ILOILO | SAN JOAQUIN (ILOILO) | P00821048VS | Construction of Flood Mitigation Structure | 122.1165 | 10.5826 | 29400000 | 29096770.92 | 2024 | JORDON CONSTRUCTION AND SUPPLY | 5151 | 2024 | 2024-10-05 | 02/29/2024 | 303229.08 | 0 | 2024-09-12 |  | 23
2022 | Region IV-B | MARINDUQUE | BUENAVISTA (MARINDUQUE) | P00639511LZ | Construction of Flood Mitigation Structure | 121.9506 | 13.2709 | 9798000 | 9596042.28 | 2022 | ANNCORP BUILDERS, INC. | 5152 | 2022 | 2022-11-07 | 03/30/2022 | 201957.72 | 0 | 2022-10-07 |  | 31
2022 | Region IV-B | ROMBLON | ODIONGAN (ROMBLON) | P00620670LZ | Construction of Flood Mitigation Structure | 122.0228 | 12.4731 | 48999999.5 | 48239485.81 | 2022 | ROLCO CONSTRUCTION & DEVELOPMENT CORPORATION ( FOR | 5153 | 2022 | 2022-09-20 | 02/24/2022 | 760513.69 | 0 | 2022-09-27 | 7
2024 | Region II | CAGAYAN | GATTARAN (CAGAYAN) | P00824680LZ | Construction of Flood Mitigation Structure | 121.7453 | 18.0436 | 49000000 | 49000000 | 2024 | TJMT CONSTRUCTION | 5154 | 2024 | 2024-11-07 | 02/22/2024 | 0 | 0 | 2024-11-06 |  | 1
2021 | Region IX | ZAMBOANGA DEL SUR |  | P00522042MN | Construction of Flood Mitigation Structure | 121.9506 | 7.0159 | 104347826.1 | 89083475.33 | 2022 | ALTOS CONSTRUCTION / GRACE CONSTRUCTION CORPORATION | 5155 | 2021 | 2022-08-02 | 02/22/2021 | 15264350.77 | 0 | 2022-08-01 |  | 1
2023 | Region III | AURORA | BALER (CAPITAL) (AURORA) | P00737446LZ | Construction of Drainage Structure | 121.5087 | 15.747 | 19800000 | 19800000 | 2023 | VANMARVIL CONSTRUCTION | 5156 | 2023 | 2023-08-07 | 02/13/2023 | 0 | 0 | 2023-08-06 |  | 1
2024 | Region II | ISABELA | JONES (ISABELA) | P00843264LZ | Construction of Flood Mitigation Structure | 121.6724 | 16.5206 | 96500000 | 96489542.98 | 2024 | JWU CONSTRUCTION AND SUPPLY | 5157 | 2024 | 2024-12-04 | 06/06/2024 | 10457.02 | 0 | 2025-03-30 | 116
2024 | Region IV-B | SURIGAO DEL SUR | SAN AGUSTIN (SURIGAO DEL SUR) | P00823571LZ | Construction of Flood Mitigation Structure | 122.1175 | 12.6197 | 96499999.6 | 96500000 | 2024 | SUNWEST, INC. (FORMERLY: SUNWEST CONSTRUCTION & DEVELOPMENT CORPORATION) | 5158 | 2024 | 2024-11-15 | 03/13/2024 | 0 | 0.4 | 2025-02-14 | 91
2024 | Region II | ISABELA | QUIRINO (ISABELA) | P00824890LZ | Construction of Flood Mitigation Structure | 121.8069 | 17.1542 | 96500000 | 96400096.41 | 2024 | A. DE GUIA CONSTRUCTION AND DEVELOPMENT CORPORATION (FORMERLY: A. DE GUIA CONSTRUCTION) | 5159 | 2024 | 2024-09-23 | 03/18/2024 | 99903.59 | 0 | 2025-02-18 | 148
2022 | Region IV-B | ROMBLON | ODIONGAN (ROMBLON) | P00621493LZ | Construction of Flood Mitigation Structure | 122.0236 | 12.4086 | 24499999.56 | 24499568.19 | 2022 | ATHENA CONSTRUCTION AND DEVELOPMENT | 5160 | 2022 | 2022-09-15 | 04/11/2022 | 431.37 | 0 | 2022-10-29 | 44
2023 | Region II | BATANES | MAHATAO (BATANES) | P00726106LZ | Construction of Flood Mitigation Structure | 121.952 | 20.4099 | 29366024 | 29260381.63 | 2024 | MOJR CONSTRUCTION AND DEVELOPMENT CORPORATION | 5161 | 2023 | 2024-03-11 | 02/17/2023 | 105642.37 | 0 | 2024-04-02 | 22
2023 | Region II | ISABELA | SAN AGUSTIN (ISABELA) | P00726863LZ | Construction of Flood Mitigation Structure | 121.7463 | 16.4572 | 96500000 | 96490419.85 | 2023 | V.B. MANUBAY CONSTRUCTION | 5162 | 2023 | 2023-10-16 | 06/15/2023 | 9580.15 | 0 | 2024-04-06 | 173
2024 | Region II | ISABELA | TUMAUINI (ISABELA) | P00824688LZ | Construction of Drainage Structure | 121.808 | 17.2784 | 4900000 | 4894751.6 | 2024 | ARVEA'S CONSTRUCTION | 5163 | 2024 | 2024-10-05 | 06/20/2024 | 5248.4 | 0 | 2024-10-04 |  | 1
2023 | Region II | ISABELA | SAN AGUSTIN (ISABELA) | P00726866LZ | Construction of Flood Mitigation Structure | 121.7468 | 16.4675 | 96500000 | 96500000 | 2023 | GACUTAN CONSTRUCTION INC. (FORMERLY: GACUTAN CONSTRUCTION) | 5164 | 2023 | 2023-11-18 | 06/01/2023 | 0 | 0 | 2024-03-23 | 126
2022 | Region IV-A | QUEZON | SARIAYA (QUEZON) | P00621425LZ | Construction of Slope Protection Structure | 121.5094 | 13.968 | 96500000 | 96500000 | 2023 | WAYCON BUILDERS AND CONSTRUCTION SUPPLY CORP. (FOR:WAYCON BUILDERS & CONSTRUCTION SUPPLY) / ROMHEAD S.J. BUILDERS AND DEVELOPMENT INCORPORATED. | 5165 | 2022 | 2023-06-07 | 06/13/2022 | 0 | 0 | 2023-06-06 |  | 1
2022 | Region II | ISABELA | SAN MARIANO (ISABELA) | P00621063LZ | Construction of Flood Mitigation Structure | 122.0237 | 16.9498 | 39199998.39 | 38606304.15 | 2022 | YZK BUILDERS | 5166 | 2022 | 2022-11-07 | 02/14/2022 | 593694.24 | 0 | 2022-11-06 |  | 1
2024 | Region II | ISABELA | ILAGAN CITY (CAPITAL) (ISABELA) | P00821193LZ | Construction of Flood Mitigation Structure | 121.8647 | 17.134 | 139925000 | 139905285.6 | 2024 | DRAGON TWELVE BUILDERS & CONSTRUCTION SUPPLY | 5167 | 2024 | 2024-07-22 | 02/05/2024 | 19714.4 | 0 | 2025-01-24 | 186
2023 | Region IV-B | ROMBLON | SAN AGUSTIN (ROMBLON) | P00727195LZ | Construction of Flood Mitigation Structure | 122.1178 | 12.6197 | 48999999.6 | 48993645.35 | 2023 | EMQ DESIGN & CONSTRUCTION | 5168 | 2023 | 2023-07-27 | 03/27/2023 | 6354.25 | 0 | 2023-11-19 | 115
2024 | Region II | BATANES | UYUGAN (BATANES) | P00820776LZ | Construction of Flood Mitigation Structure | 121.9523 | 20.3571 | 9800000 | 9698205.04 | 2024 | MJMARI BUILDERS AND DEVELOPMENT CORPORATION (FORMERLY: MJMARI BUILDERS AND ENTERPRISES) | 5169 | 2024 | 2024-06-25 | 04/25/2024 | 101794.96 | 0 | 2024-10-30 | 127
2024 | Region IV-B | ROMBLON | SAN AGUSTIN (ROMBLON) | P00844548LZ | Construction of Flood Mitigation Structure | 122.1181 | 12.6203 | 48249999.93 | 48247354.86 | 2024 | ROLCO CONSTRUCTION & DEVELOPMENT CORPORATION ( FOR / SIM CONSTRUCTION, TRADING AND SERVICES | 5170 | 2024 | 2024-08-19 | 03/20/2024 | 2645.07 | 0 | 2024-11-12 | 85
2023 | Region II | ISABELA | TUMAUINI (ISABELA) | P00726882LZ | Construction of Revetment | 121.8081 | 17.2657 | 108882000 | 108668817.1 | 2024 | ARVEA'S CONSTRUCTION / EGB CONSTRUCTION CORPORATION (FORMERLY: EGB CONSTRUCTION) | 5171 | 2023 | 2024-04-02 | 05/25/2023 | 213182.9 | 0 | 2024-03-01 |  | 32
2023 | Region II | ISABELA | SAN AGUSTIN (ISABELA) | P00726867LZ | Construction of Flood Mitigation Structure | 121.748 | 16.4734 | 96500000 | 96500000 | 2023 | COLBY CONSTRUCTION | 5172 | 2023 | 2023-11-18 | 06/01/2023 | 0 | 0 | 2024-03-23 | 126
2023 | Region II | ISABELA | SANTA MARIA (ISABELA) | P00726683LZ | Construction of Flood Mitigation Structure | 121.7488 | 17.4538 | 49000000 | 48990135.04 | 2023 | EGB CONSTRUCTION CORPORATION (FORMERLY: EGB CONSTRUCTION) | 5173 | 2023 | 2023-10-23 | 05/19/2023 | 9864.96 | 0 | 2024-01-17 | 86
2024 | Cordillera Administrative Region | MOUNTAIN PROVINCE | PARACELIS (MOUNTAIN PROVINCE) | P00821548LZ | Construction of Flood Mitigation Structure | 121.5099 | 17.1423 | 39200000 | 39200000 | 2024 | UPLAND CONSTRUCTION AND ENGINEERING SERVICES / GAWIS CONSTRUCTION SERVICES | 5174 | 2024 | 2024-07-22 | 02/15/2024 | 0 | 0 | 2024-08-31 | 40
2022 | Region IV-B | ROMBLON | SAN ANDRES (ROMBLON) | P00620675LZ | Construction of Flood Mitigation Structure | 122.0247 | 12.5192 | 29399999.47 | 29399566.76 | 2022 | ROLCO CONSTRUCTION & DEVELOPMENT CORPORATION ( FOR / SCATR CONSTRUCTION | 5175 | 2022 | 2022-10-26 | 02/28/2022 | 432.71 | 0 | 2022-10-25 |  | 1
2024 | Region II | ISABELA | ILAGAN CITY (CAPITAL) (ISABELA) | P00820781LZ | Construction of Flood Mitigation Structure | 121.9547 | 17.1909 | 9800000 | 9794710 | 2024 | DRAGON TWELVE BUILDERS & CONSTRUCTION SUPPLY | 5176 | 2024 | 2024-08-15 | 06/11/2024 | 5290 | 0 | 2024-10-12 | 58
2023 | Region II | ISABELA | QUIRINO (ISABELA) | P00726418LZ | Construction of Flood Mitigation Structure | 121.6724 | 17.1201 | 47929460 | 48217377.67 | 2023 | A. DE GUIA CONSTRUCTION AND DEVELOPMENT CORPORATION (FORMERLY: A. DE GUIA CONSTRUCTION) | 5177 | 2023 | 2023-10-17 | 03/13/2023 | 0 | 287917.67 | 2023-10-07 |  | 10
2024 | Region VI | ILOILO | SAN JOAQUIN (ILOILO) | P00820156VS | Construction of Flood Mitigation Structure | 122.1182 | 10.6169 | 5880000 | 5844865.02 | 2024 | DEACONS TEMPLE CONSTRUCTION & SUPPLY | 5178 | 2024 | 2024-04-27 | 02/08/2024 | 35134.98 | 0 | 2024-04-26 |  | 1
2022 | Region II | ISABELA | REINA MERCEDES (ISABELA) | P00631121LZ | Construction of Flood Mitigation Structure | 121.8095 | 16.9804 | 44099997.83 | 43460547.86 | 2023 | MAR-DEB CONSTRUCTION & DEVELOPMENT CORP. (FORMERLY: MAR-DEB CONSTRUCTION & DEVELOPMENT) | 5179 | 2022 | 2023-03-05 | 02/14/2022 | 639449.97 | 0 | 2023-03-14 | 9
2023 | Region II | ISABELA | SANTA MARIA (ISABELA) | P00725678LZ | Construction of Slope Protection Structure | 121.7488 | 17.4538 | 190000000 | 189900000 | 2024 | EGB CONSTRUCTION CORPORATION (FORMERLY: EGB CONSTRUCTION) | 5180 | 2023 | 2024-02-29 | 05/30/2023 | 100000 | 0 | 2024-05-15 | 76
2022 | Region IV-B | MARINDUQUE | MOGPOG (MARINDUQUE) | P00632921LZ | Construction of Flood Mitigation Structure | 121.8648 | 13.5506 | 9898000 | 9898841.47 | 2022 | K CONSTRUCTION & DEVELOPERS CORPORATION | 5181 | 2022 | 2022-09-14 | 02/16/2022 | 0 | 841.47 | 2022-09-13 |  | 1
2022 | Region III | AURORA | MARIA AURORA (AURORA) | P00631149LZ | Construction of Flood Mitigation Structure | 121.5105 | 15.7949 | 19600000 | 19600000 | 2023 | CONRADO B. BAUTISTA CONST. & SUPPLY CORP. (FORMERL | 5182 | 2022 | 2023-02-19 | 02/18/2022 | 0 | 0 | 2023-02-18 |  | 1
2022 | Region IV-B | MARINDUQUE | BUENAVISTA (MARINDUQUE) | P00639515LZ | Construction of Flood Mitigation Structure | 121.9558 | 13.241 | 22538000 | 21976855.62 | 2023 | KURDZ CONSTRUCTION | 5183 | 2022 | 2023-04-10 | 06/27/2022 | 561144.38 | 0 | 2023-04-09 |  | 1
2023 | Region IV-B | ROMBLON | SAN ANDRES (ROMBLON) | P00725879LZ | Construction of Flood Mitigation Structure | 122.0253 | 12.525 | 94087499.48 | 94085449.7 | 2023 | MRRM TRADING & CONSTRUCTION / KPSL GENERAL CONTRACTOR INC. | 5184 | 2023 | 2023-09-13 | 03/09/2023 | 2049.78 | 0 | 2024-02-05 | 145
2023 | Region IV-B | MARINDUQUE | SANTA CRUZ (MARINDUQUE) | P00740421LZ | Construction of Revetment | 122.1182 | 13.4653 | 241249999.4 | 241247074.9 | 2024 | HGG BUILDERS & SUPPLY | 5185 | 2023 | 2024-05-14 | 04/13/2023 | 2924.5 | 0 | 2024-05-13 |  | 1
2024 | Region II | ISABELA | SAN AGUSTIN (ISABELA) | P00843270LZ | Construction of Flood Mitigation Structure | 121.7491 | 16.4863 | 96500000 | 96477720 | 2024 | JWU CONSTRUCTION AND SUPPLY | 5186 | 2024 | 2024-08-01 | 05/20/2024 | 22280 | 0 | 2025-05-25 | 297
2023 | Region II | ISABELA | CITY OF CAUAYAN (ISABELA) | P00742125LZ | Construction of Flood Mitigation Structure | 121.8648 | 16.9034 | 74250000 | 74228232.76 | 2023 | JWU CONSTRUCTION AND SUPPLY | 5187 | 2023 | 2023-08-30 | 05/30/2023 | 21767.24 | 0 | 2024-02-14 | 168
2022 | Region IV-A | QUEZON | SARIAYA (QUEZON) | P00621424LZ | Construction of Slope Protection Structure | 121.5105 | 13.9656 | 96500000 | 96500000 | 2023 | I.A . BOSQUE CONSTRUCTION CORPORATION | 5188 | 2022 | 2023-06-05 | 06/13/2022 | 0 | 0 | 2023-06-06 | 1
2024 | Region II | ISABELA | CABATUAN (ISABELA) | P00823334LZ | Construction of Flood Mitigation Structure | 121.6756 | 16.9769 | 96499995.43 | 96489843.46 | 2024 | JWU CONSTRUCTION AND SUPPLY | 5189 | 2024 | 2024-08-08 | 06/07/2024 | 10151.97 | 0 | 2025-04-25 | 260
2022 | Region II | ISABELA | BENITO SOLIVEN (ISABELA) | P00631129LZ | Construction of Flood Mitigation Structure | 121.9569 | 17.0157 | 39199998.96 | 38376540.84 | 2023 | ROAD EDGE TRADING & DEVELOPMENT SERVICES / MAV CONSTRUCTION SUPPLY AND POWER DEVELOPMENT | 5190 | 2022 | 2023-01-07 | 02/14/2022 | 823458.12 | 0 | 2023-01-06 |  | 1
2024 | Region II | ISABELA | JONES (ISABELA) | P00843288LZ | Construction of Flood Mitigation Structure | 121.676 | 16.5419 | 96500000 | 96499634.76 | 2024 | DALCON CONSTRUCTION | 5191 | 2024 | 2024-10-15 | 06/04/2024 | 365.24 | 0 | 2025-07-19 | 277
2022 | Region IV-A | QUEZON | SARIAYA (QUEZON) | P00621423LZ | Construction of Slope Protection Structure | 121.5107 | 13.9628 | 96500000 | 96500000 | 2023 | I.A . BOSQUE CONSTRUCTION CORPORATION | 5192 | 2022 | 2023-03-15 | 06/13/2022 | 0 | 0 | 2023-04-07 | 23
2023 | Region IV-B | ROMBLON | SAN AGUSTIN (ROMBLON) | P00727192LZ | Construction of Flood Mitigation Structure | 122.1192 | 12.5578 | 48999999.31 | 49000000 | 2023 | LEGACY CONSTRUCTION CORPORATION (FORMERLY: LEGACY CONSTRUCTION) | 5193 | 2023 | 2023-12-07 | 04/18/2023 | 0 | 0.69 | 2023-12-11 | 4
2024 | Region IV-B | ROMBLON | SAN ANDRES (ROMBLON) | P00823577LZ | Construction of Flood Mitigation Structure | 122.0254 | 12.525 | 289500000 | 289492750.9 | 2024 | YPR GEN. CONTRACTOR AND CONSTRUCTION SUPPLY INC. | 5194 | 2024 | 2024-08-10 | 03/02/2024 | 7249.1 | 0 | 2025-02-23 | 197
2022 | Region II | ISABELA | ANGADANAN (ISABELA) | P00621058LZ | Construction of Flood Mitigation Structure | 121.8095 | 16.8372 | 34299997.93 | 34292686.14 | 2023 | JANN-NORRIS CONSTRUCTION AND SUPPLIES INC. (FORMELY: JANN-NORRIS CONSTRUCTION AND SUPPLIES) / INFINITUM 888 CONSTRUCTION AND DEVELOPMENT CORPORATION | 5195 | 2022 | 2023-02-16 | 02/14/2022 | 7311.79 | 0 | 2023-02-15 |  | 1
2022 | Region II | ISABELA | ANGADANAN (ISABELA) | P00631124LZ | Construction of Flood Mitigation Structure | 121.7492 | 16.7614 | 42139998.29 | 42002289.88 | 2023 | DANYSONS CONSTRUCTION AND DEVELOPMENT CORPORATION (FORMERLY: DANYSONS CONSTRUCTION) | 5196 | 2022 | 2023-01-10 | 02/14/2022 | 137708.41 | 0 | 2023-01-18 | 8
2023 | Region IV-B | MARINDUQUE | BOAC (CAPITAL) (MARINDUQUE) | P00727176LZ | Construction of Flood Mitigation Structure | 121.8655 | 13.4411 | 48998000 | 47927960.67 | 2023 | AMETHYST HORIZON BUILDERS AND GEN. CONTRACTOR AND DEVELOPMENT CORP. | 5197 | 2023 | 2023-08-25 | 03/28/2023 | 1070039.33 | 0 | 2023-10-11 | 47
2023 | Region II | ISABELA | ILAGAN CITY (CAPITAL) (ISABELA) | P00742303LZ | Construction of Flood Mitigation Structure | 121.957 | 17.0672 | 29700000 | 29689017 | 2023 | DRAGON TWELVE BUILDERS & CONSTRUCTION SUPPLY | 5198 | 2023 | 2023-11-24 | 06/28/2023 | 10983 | 0 | 2024-02-04 | 72
2022 | Region IV-A | QUEZON | SARIAYA (QUEZON) | P00621465LZ | Construction of Slope Protection Structure | 121.5107 | 13.9669 | 49000000 | 49000000 | 2023 | RAPID FOREMOST CONST. CO. | 5199 | 2022 | 2023-03-14 | 05/19/2022 | 0 | 0 | 2023-03-13 |  | 1
2024 | Region IV-B | SURIGAO DEL SUR | SAN AGUSTIN (SURIGAO DEL SUR) | P00823559LZ | Construction of Flood Mitigation Structure | 122.1193 | 12.5701 | 96499999.95 | 96497695.6 | 2024 | SUNWEST, INC. (FORMERLY: SUNWEST CONSTRUCTION & DEVELOPMENT CORPORATION) | 5200 | 2024 | 2024-09-23 | 04/08/2024 | 2304.35 | 0 | 2025-03-12 | 170
2022 | Region IV-B | ROMBLON | ODIONGAN (ROMBLON) | P00620671LZ | Construction of Flood Mitigation Structure | 122.0256 | 12.4528 | 48999999.5 | 48250000 | 2022 | ROLCO CONSTRUCTION & DEVELOPMENT CORPORATION ( FOR | 5201 | 2022 | 2022-12-12 | 02/24/2022 | 749999.5 | 0 | 2022-11-26 |  | 16
2024 | Region IV-B | SURIGAO DEL SUR | SAN AGUSTIN (SURIGAO DEL SUR) | P00823570LZ | Construction of Flood Mitigation Structure | 122.1197 | 12.6122 | 96499999.08 | 96500000 | 2024 | SUNWEST, INC. (FORMERLY: SUNWEST CONSTRUCTION & DEVELOPMENT CORPORATION) | 5202 | 2024 | 2024-12-13 | 03/13/2024 | 0 | 0.92 | 2025-02-14 | 63
2023 | Region II | ISABELA | ANGADANAN (ISABELA) | P00726706LZ | Construction of Flood Mitigation Structure | 121.8097 | 16.8356 | 19599998.06 | 19499998.06 | 2023 | ED1SON DEVELOPMENT & CONSTRUCTION INC. / BDA JR CONSTRUCTION / INFINITI CONSTRUCTION AND DEVELOPMENT CORPORATION | 5203 | 2023 | 2023-08-25 | 02/28/2023 | 100000 | 0 | 2023-09-03 | 9
2022 | Region IV-A | QUEZON | ATIMONAN (QUEZON) | P00621503LZ | Construction of Flood Mitigation Structure | 121.8663 | 14.0012 | 9800000 | 9800000 | 2022 | MURIELEVEN BUILDERS AND CONSTRUCTION SUPPLY CORP. | 5204 | 2022 | 2022-08-30 | 03/24/2022 | 0 | 0 | 2022-08-29 |  | 1
2024 | Region II | ISABELA | BENITO SOLIVEN (ISABELA) | P00824883LZ | Construction of Flood Mitigation Structure | 121.9581 | 17.0133 | 96499991.68 | 96489915.19 | 2024 | JWU CONSTRUCTION AND SUPPLY | 5205 | 2024 | 2024-10-15 | 07/23/2024 | 10076.49 | 0 | 2025-04-19 | 186
2022 | Region IV-A | QUEZON | SARIAYA (QUEZON) | P00631309LZ | Construction of Slope Protection Structure | 121.5108 | 13.9578 | 29400000 | 29400000 | 2022 | I.A . BOSQUE CONSTRUCTION CORPORATION | 5206 | 2022 | 2022-12-02 | 02/22/2022 | 0 | 0 | 2022-12-02 | 0
2023 | Region IX | BASILAN | CITY OF ISABELA (CAPITAL) (CITY OF ISABELA) | P00733981MN | Construction of Flood Mitigation Structure | 122.0283 | 6.7194 | 66320590 | 66305107.01 | 2024 | RCDG CONSTRUCTION CORPORATION / MMP CONSTRUCTION AND SUPPLIES | 5207 | 2023 | 2024-04-03 | 05/26/2023 | 15482.99 | 0 | 2024-03-24 |  | 10
2023 | Region II | CAGAYAN | CAMALANIUGAN (CAGAYAN) | P00726670LZ | Construction of Flood Mitigation Structure | 121.6767 | 18.27 | 49000000 | 48969979.62 | 2024 | TJMT CONSTRUCTION / PRIME MASTER CONST. AND DEV'T. CORP. | 5208 | 2023 | 2024-07-29 | 02/27/2023 | 30020.38 | 0 | 2023-11-15 |  | 257
2024 | Region IV-B | SURIGAO DEL SUR | SAN AGUSTIN (SURIGAO DEL SUR) | P00823599LZ | Construction of Flood Mitigation Structure | 122.1207 | 12.5689 | 91674999.95 | 91672837.61 | 2024 | SUNWEST, INC. (FORMERLY: SUNWEST CONSTRUCTION & DEVELOPMENT CORPORATION) | 5209 | 2024 | 2024-09-23 | 04/15/2024 | 2162.34 | 0 | 2025-03-09 | 167
2022 | Region II | CAGAYAN | ENRILE (CAGAYAN) | P00620828LZ | Construction of Flood Mitigation Structure | 121.75 | 17.56 | 92157500 | 92157500 | 2024 | M.E. SICAT CONSTRUCTION, INC. (FORMERLY M.E. SICAT | 5210 | 2022 | 2024-02-25 | 03/28/2022 | 0 | 0 | 2023-02-02 |  | 388
2021 | Region II | ISABELA |  | P00525962LZ | Construction of Flood Mitigation Structure | 121.8101 | 16.979 | 47039932.22 | 45784255.14 | 2022 | MAR-DEB CONSTRUCTION & DEVELOPMENT CORP. (FORMERLY: MAR-DEB CONSTRUCTION & DEVELOPMENT) | 5211 | 2021 | 2022-12-13 | 01/19/2022 | 1255677.08 | 0 | 2022-12-12 |  | 1
2023 | Region IV-B | MARINDUQUE | MOGPOG (MARINDUQUE) | P00727180LZ | Construction of Flood Mitigation Structure | 121.8669 | 13.4775 | 48998000 | 47926470.47 | 2023 | ELITE GENERAL CONTRACTOR AND DEVELOPMENT CORP. | 5212 | 2023 | 2023-10-12 | 03/28/2023 | 1071529.53 | 0 | 2023-10-11 |  | 1
2024 | Region IX | ZAMBOANGA DEL SUR | ZAMBOANGA CITY (ZAMBOANGA DEL SUR) | P00833577MN | Construction of Drainage Structure | 121.9582 | 6.9543 | 4900000 | 4574902.04 | 2024 | RME CONSTRUCTION AND ENTERPRISES | 5213 | 2024 | 2024-07-22 | 02/12/2024 | 325097.96 | 0 | 2024-08-07 | 16
2022 | Region IV-A | QUEZON | SARIAYA (QUEZON) | P00631308LZ | Construction of Slope Protection Structure | 121.5109 | 13.9621 | 49000000 | 49000000 | 2022 | WAYCON BUILDERS AND CONSTRUCTION SUPPLY CORP. (FOR:WAYCON BUILDERS & CONSTRUCTION SUPPLY) | 5214 | 2022 | 2022-12-20 | 02/24/2022 | 0 | 0 | 2022-12-19 |  | 1
2023 | Region II | CAGAYAN | CAMALANIUGAN (CAGAYAN) | P00726671LZ | Construction of Flood Mitigation Structure | 121.6772 | 18.2696 | 49000000 | 48975000 | 2024 | TJMT CONSTRUCTION | 5215 | 2023 | 2024-07-29 | 02/27/2023 | 25000 | 0
2024 | Region II | ISABELA | TUMAUINI (ISABELA) | P00824689LZ | Construction of Drainage Structure | 121.8105 | 17.2721 | 4900000 | 4894223.2 | 2024 | ARVEA'S CONSTRUCTION | 5216 | 2024 | 2024-10-07 | 06/24/2024 | 5776.8 | 0 | 2024-10-07 | 0
2023 | Region IV-B | ROMBLON | ODIONGAN (ROMBLON) | P00726274LZ | Construction of Flood Mitigation Structure | 122.0283 | 12.4494 | 48999999.65 | 48992420.13 | 2023 | R N V CONSTRUCTION | 5217 | 2023 | 2023-09-04 | 02/21/2023 | 7579.52 | 0 | 2023-10-16 | 42
2022 | Region II | ISABELA | SAN AGUSTIN (ISABELA) | P00639338LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.7503 | 16.4596 | 67550000 | 67549684.87 | 2022 | GACUTAN CONSTRUCTION INC. (FORMERLY: GACUTAN CONSTRUCTION) | 5218 | 2022 | 2022-08-18 | 04/01/2022 | 315.13 | 0 | 2022-12-07 | 111
2023 | Region III | AURORA | DINALUNGAN (AURORA) | P00737448LZ | Construction of Flood Mitigation Structure | 121.9583 | 16.1358 | 49500000 | 49500000 | 2024 | THREE W BUILDERS, INC. | 5219 | 2023 | 2024-04-22 | 05/16/2023 | 0 | 0 | 2024-01-06 |  | 107
2022 | Region IV-A | QUEZON | SARIAYA (QUEZON) | P00621421LZ | Construction of Slope Protection Structure | 121.5112 | 13.9619 | 96500000 | 96500000 | 2023 | RAPID FOREMOST CONST. CO. / JAICA CONST. CORP | 5220 | 2022 | 2023-05-22 | 06/13/2022 | 0 | 0 | 2023-06-06 | 15
2022 | Region II | ISABELA | ILAGAN CITY (CAPITAL) (ISABELA) | P00621045LZ | Construction of Flood Mitigation Structure | 121.8669 | 17.1926 | 44100000 | 44057567.8 | 2022 | DRAGON TWELVE BUILDERS & CONSTRUCTION SUPPLY | 5221 | 2022 | 2022-09-02 | 05/18/2022 | 42432.2 | 0 | 2023-02-08 | 159
2022 | Region IV-A | QUEZON | SARIAYA (QUEZON) | P00621427LZ | Construction of Slope Protection Structure | 121.5114 | 13.9575 | 96500000 | 96500000 | 2023 | WAYCON BUILDERS AND CONSTRUCTION SUPPLY CORP. (FOR:WAYCON BUILDERS & CONSTRUCTION SUPPLY) | 5222 | 2022 | 2023-05-22 | 06/13/2022 | 0 | 0 | 2023-06-06 | 15
2024 | Region II | ISABELA | CITY OF CAUAYAN (ISABELA) | P00821157LZ | Construction of Flood Mitigation Structure | 121.8107 | 16.8411 | 70830035 | 70830035 | 2024 | MA TESORO CONSTRUCTION | 5223 | 2024 | 2024-11-12 | 03/13/2024 | 0 | 0 | 2025-01-02 | 51
2022 | Region IV-B | MARINDUQUE | SANTA CRUZ (MARINDUQUE) | P00632923LZ | Construction of Flood Mitigation Structure | 122.0284 | 13.5 | 9898000 | 9898092.96 | 2022 | RPE CONSTRUCTION | 5224 | 2022 | 2022-09-13 | 02/16/2022 | 0 | 92.96 | 2022-09-13 | 0
2021 | Region IV-B | ROMBLON |  | P00525650LZ | Construction of Flood Mitigation Structure | 122.1222 | 12.6169 | 57899999.5 | 57900000 | 2022 | SUNWEST, INC. (FORMERLY: SUNWEST CONSTRUCTION & DEVELOPMENT CORPORATION) | 5225 | 2021 | 2022-08-08 | 11/25/2021 | 0 | 0.5 | 2022-08-30 | 22
2021 | Region II | ISABELA |  | P00525965LZ | Construction of Flood Mitigation Structure | 121.6784 | 16.6934 | 46393200 | 46393200 | 2022 | JC PALOMO CONSTRUCTION & CONSTRUCTION SUPPLY | 5226 | 2021 | 2022-09-30 | 03/09/2022 | 0 | 0 | 2022-09-29 |  | 1
2024 | Region II | ISABELA | QUIRINO (ISABELA) | P00824881LZ | Construction of Flood Mitigation Structure | 121.7504 | 17.1778 | 96500000 | 96499999.38 | 2024 | DANYSONS CONSTRUCTION AND DEVELOPMENT CORPORATION (FORMERLY: DANYSONS CONSTRUCTION) | 5227 | 2024 | 2024-07-31 | 04/15/2024 | 0.62 | 0 | 2025-04-14 | 257
2023 | Region II | ISABELA | BENITO SOLIVEN (ISABELA) | P00725659LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.9584 | 17.016 | 43136510.53 | 43115610.44 | 2023 | ROAD EDGE TRADING & DEVELOPMENT SERVICES | 5228 | 2023 | 2023-09-21 | 04/28/2023 | 20900.09 | 0 | 2023-11-22 | 62
2022 | Region IV-A | QUEZON | SARIAYA (QUEZON) | P00621468LZ | Construction of Slope Protection Structure | 121.5124 | 13.9557 | 49000000 | 49000000 | 2023 | JEMAK CONSTRUCTION & SUPPLY / FREPA BUILDER AND CONSTRUCTION SUPPLY | 5229 | 2022 | 2023-02-10 | 05/19/2022 | 0 | 0 | 2023-02-11 | 1
2022 | Region II | ISABELA | ILAGAN CITY (CAPITAL) (ISABELA) | P00621050LZ | Construction of Flood Mitigation Structure | 121.8678 | 17.1497 | 39417560 | 39386293.7 | 2022 | DRAGON TWELVE BUILDERS & CONSTRUCTION SUPPLY | 5230 | 2022 | 2022-12-06 | 05/18/2022 | 31266.3 | 0 | 2023-02-12 | 68
2024 | Region II | ISABELA | SAN MARIANO (ISABELA) | P00825055LZ | Construction of Flood Mitigation Structure | 122.0285 | 16.936 | 72374994.67 | 71919676.47 | 2024 | JAY ARCIE CONSTRUCTION AND SUPPLY | 5231 | 2024 | 2024-10-07 | 05/02/2024 | 455318.2 | 0 | 2024-12-31 | 85
2023 | Region II | ISABELA | CITY OF CAUAYAN (ISABELA) | P00726132LZ | Construction of Flood Mitigation Structure | 121.8107 | 16.8413 | 29400000 | 29396371.76 | 2023 | JWU CONSTRUCTION AND SUPPLY | 5232 | 2023 | 2023-08-22 | 02/23/2023 | 3628.24 | 0 | 2023-10-06 | 45
2023 | Region II | ISABELA | ROXAS (ISABELA) | P00726442LZ | Construction of Flood Mitigation Structure | 121.681 | 17.109 | 67550000 | 67529995.5 | 2023 | JWU CONSTRUCTION AND SUPPLY | 5233 | 2023 | 2023-07-02 | 02/27/2023 | 20004.5 | 0 | 2023-11-17 | 138
2023 | Region II | ISABELA | SAN AGUSTIN (ISABELA) | P00726862LZ | Construction of Flood Mitigation Structure | 121.7518 | 16.4556 | 96500000 | 96424760.83 | 2023 | V.B. MANUBAY CONSTRUCTION | 5234 | 2023 | 2023-10-16 | 06/01/2023 | 75239.17 | 0 | 2024-03-23 | 159
2021 | Region VI | ANTIQUE |  | P00549972VS | Construction of Flood Mitigation Structure | 121.9584 | 10.8072 | 19600000 | 18829429.38 | 2022 | F. GURREA CONSTRUCTION, INCORPORATED | 5235 | 2021 | 2022-12-23 | 09/20/2021 | 770570.62 | 0 | 2022-12-22 |  | 1
2022 | Region IV-A | QUEZON | ATIMONAN (QUEZON) | P00620610LZ | Construction of Flood Mitigation Structure | 121.8686 | 14.0025 | 19600000 | 19600000 | 2022 | MURIELEVEN BUILDERS AND CONSTRUCTION SUPPLY CORP. | 5236 | 2022 | 2022-09-24 | 02/16/2022 | 0 | 0 | 2022-11-22 | 59
2022 | Region IV-A | QUEZON | SARIAYA (QUEZON) | P00621428LZ | Construction of Slope Protection Structure | 121.5125 | 13.9551 | 96500000 | 96500000 | 2023 | WAYCON BUILDERS AND CONSTRUCTION SUPPLY CORP. (FOR:WAYCON BUILDERS & CONSTRUCTION SUPPLY) | 5237 | 2022 | 2023-05-08 | 06/13/2022 | 0 | 0 | 2023-05-07 |  | 1
2021 | Region II | ISABELA |  | P00525963LZ | Construction of Flood Mitigation Structure | 122.0286 | 16.9394 | 46651907.93 | 45208376.78 | 2022 | JC PALOMO CONSTRUCTION & CONSTRUCTION SUPPLY | 5238 | 2021 | 2022-07-28 | 01/19/2022 | 1443531.15 | 0 | 2022-07-27 |  | 1
2022 | Region II | ISABELA | CITY OF CAUAYAN (ISABELA) | P00637015LZ | Construction of Flood Mitigation Structure | 121.8107 | 16.9228 | 96500000 | 96500000 | 2023 | MA TESORO CONSTRUCTION / EGB CONSTRUCTION CORPORATION (FORMERLY: EGB CONSTRUCTION) | 5239 | 2022 | 2023-05-17 | 04/13/2022 | 0 | 0 | 2023-07-06 | 50
2023 | Region IV-B | ROMBLON | SAN AGUSTIN (ROMBLON) | P00742463LZ | Construction of Flood Mitigation Structure | 122.1228 | 12.6136 | 98999999.78 | 99000000 | 2024 | SUNWEST, INC. (FORMERLY: SUNWEST CONSTRUCTION & DEVELOPMENT CORPORATION) | 5240 | 2023 | 2024-02-29 | 05/18/2023 | 0 | 0.22 | 2024-04-20 | 51
2023 | Region II | CAGAYAN | CAMALANIUGAN (CAGAYAN) | P00726881LZ | Construction of Flood Mitigation Structure | 121.6811 | 18.245 | 114732000 | 114611496 | 2023 | GVDPM CONSTRUCTION CORP. (FORMERLY: ZM CONSTRUCTIO | 5241 | 2023 | 2023-11-20 | 05/08/2023 | 120504 | 0 | 2024-01-23 | 64
2023 | Region III | AURORA | DIPACULAO (AURORA) | P00727284LZ | Construction of Flood Mitigation Structure | 121.752 | 16.0757 | 192999760.8 | 192999742.2 | 2024 | R.D. TALENS CONSTRUCTION AND TRADING | 5242 | 2023 | 2024-03-31 | 06/20/2023 | 18.6 | 0 | 2024-07-17 | 108
2022 | Region II | ISABELA | JONES (ISABELA) | P00639465LZ | Construction of Flood Mitigation Structure | 121.8701 | 16.5091 | 34300000 | 34299272.21 | 2022 | MAR-DEB CONSTRUCTION & DEVELOPMENT CORP. (FORMERLY: MAR-DEB CONSTRUCTION & DEVELOPMENT) | 5243 | 2022 | 2022-08-22 | 04/08/2022 | 727.79 | 0 | 2022-11-02 | 72
2022 | Region IV-A | QUEZON | SARIAYA (QUEZON) | P00621467LZ | Construction of Slope Protection Structure | 121.5128 | 13.9543 | 49000000 | 49000000 | 2023 | I.A . BOSQUE CONSTRUCTION CORPORATION | 5244 | 2022 | 2023-04-13 | 05/19/2022 | 0 | 0 | 2023-04-12 |  | 1
2023 | Region IV-B | MARINDUQUE | SANTA CRUZ (MARINDUQUE) | P00742450LZ | Construction of Flood Mitigation Structure | 122.0291 | 13.4721 | 4948000 | 4947211.87 | 2023 | DD ROSAL CONSTRUCTION | 5245 | 2023 | 2023-06-15 | 03/28/2023 | 788.13 | 0 | 2023-06-15 | 0
2024 | Region IV-B | SURIGAO DEL SUR | SAN AGUSTIN (SURIGAO DEL SUR) | P00825132LZ | Construction of Flood Mitigation Structure | 122.1228 | 12.5317 | 96499999.62 | 96500000 | 2024 | SUNWEST, INC. (FORMERLY: SUNWEST CONSTRUCTION & DEVELOPMENT CORPORATION) | 5246 | 2024 | 2024-11-15 | 03/13/2024 | 0 | 0.38 | 2025-02-14 | 91
2023 | Region II | ISABELA | CITY OF CAUAYAN (ISABELA) | P00742122LZ | Construction of Flood Mitigation Structure | 121.8111 | 16.9365 | 74250000 | 74229724.81 | 2023 | JWU CONSTRUCTION AND SUPPLY | 5247 | 2023 | 2023-10-06 | 05/26/2023 | 20275.19 | 0 | 2024-03-28 | 174
2024 | Region II | ISABELA | JONES (ISABELA) | P00843248LZ | Construction of Flood Mitigation Structure | 121.6825 | 16.5566 | 96500000 | 96500000 | 2024 | EGB CONSTRUCTION CORPORATION (FORMERLY: EGB CONSTRUCTION) | 5248 | 2024 | 2024-12-07 | 05/24/2024 | 0 | 0 | 2025-03-20 | 103
2022 | Region II | ISABELA | ANGADANAN (ISABELA) | P00631125LZ | Construction of Flood Mitigation Structure | 121.752 | 16.7656 | 42139997.53 | 42113172.13 | 2022 | DANYSONS CONSTRUCTION AND DEVELOPMENT CORPORATION (FORMERLY: DANYSONS CONSTRUCTION) | 5249 | 2022 | 2022-10-13 | 02/14/2022 | 26825.4 | 0 | 2022-10-22 | 9
2024 | Region II | ISABELA | BENITO SOLIVEN (ISABELA) | P00821210LZ | Construction of Flood Mitigation Structure | 121.9585 | 17.0189 | 62724997.84 | 62714599.71 | 2024 | ROAD EDGE TRADING & DEVELOPMENT SERVICES | 5250 | 2024 | 2024-07-22 | 03/27/2024 | 10398.13 | 0 | 2024-11-11 | 112
2023 | Region II | BATANES | SABTANG (BATANES) | P00727343LZ | Construction of Flood Mitigation Structure | 121.8703 | 20.3382 | 24491344 | 21238973.04 | 2023 | J.F. GABOTERO, INC. | 5251 | 2023 | 2023-12-10 | 03/13/2023 | 3252370.96 | 0 | 2024-03-08 | 89
2022 | Region IV-A | QUEZON | SARIAYA (QUEZON) | P00621469LZ | Construction of Slope Protection Structure | 121.5129 | 13.9532 | 49000000 | 49000000 | 2023 | WAYCON BUILDERS AND CONSTRUCTION SUPPLY CORP. (FOR:WAYCON BUILDERS & CONSTRUCTION SUPPLY) / ROMHEAD S.J. BUILDERS AND DEVELOPMENT INCORPORATED. | 5252 | 2022 | 2023-04-03 | 05/19/2022 | 0 | 0 | 2023-04-02 |  | 1
2022 | Region IV-B | MARINDUQUE | SANTA CRUZ (MARINDUQUE) | P00639507LZ | Construction of Flood Mitigation Structure | 122.0295 | 13.4829 | 9798000 | 9799552.49 | 2022 | RPE CONSTRUCTION | 5253 | 2022 | 2022-10-04 | 03/30/2022 | 0 | 1552.49 | 2022-10-04 | 0
2021 | Region II | ISABELA |  | P00525953LZ | Construction of Flood Mitigation Structure | 121.8116 | 17.3723 | 19600000 | 19305970 | 2022 | DRAGON TWELVE BUILDERS & CONSTRUCTION SUPPLY | 5254 | 2021 | 2022-08-15 | 01/12/2022 | 294030 | 0 | 2022-08-20 | 5
2024 | Region II | ISABELA | SAN AGUSTIN (ISABELA) | P00843269LZ | Construction of Flood Mitigation Structure | 121.7528 | 16.5151 | 96500000 | 96500000 | 2024 | DALCON CONSTRUCTION | 5255 | 2024 | 2024-10-10 | 06/03/2024 | 0 | 0 | 2025-08-22 | 316
2024 | Region II | QUIRINO | MADDELA (QUIRINO) | P00825239LZ | Construction of Flood Mitigation Structure | 121.6827 | 16.3219 | 34300000 | 34295321.46 | 2024 | A.P.D. CONSTRUCTION, INC. (FORMERLY: APD CONSTRUCTION) | 5256 | 2024 | 2024-10-31 | 04/26/2024 | 4678.54 | 0 | 2024-11-28 | 28
2022 | Region II | BATANES | UYUGAN (BATANES) | P00640503LZ | Construction of Flood Mitigation Structure | 121.9588 | 20.3661 | 4950000 | 4938605.84 | 2023 | R.L. PACANA'S CONSTRUCTION & DEVELOPMENT | 5257 | 2022 | 2023-01-01 | 06/06/2022 | 11394.16 | 0 | 2022-10-27 |  | 66
2023 | Region II | ISABELA | SAN AGUSTIN (ISABELA) | P00726870LZ | Construction of Flood Mitigation Structure | 121.7534 | 16.4868 | 96500000 | 96500000 | 2023 | GACUTAN CONSTRUCTION INC. (FORMERLY: GACUTAN CONSTRUCTION) | 5258 | 2023 | 2023-08-17 | 06/01/2023 | 0 | 0 | 2024-03-23 | 219
2022 | Region II | CAGAYAN | CAMALANIUGAN (CAGAYAN) | P00630933LZ | Construction of Flood Mitigation Structure | 121.6835 | 18.2494 | 144250000 | 143859986.3 | 2022 | GVDPM CONSTRUCTION CORP. (FORMERLY: ZM CONSTRUCTIO | 5259 | 2022 | 2022-09-30 | 03/08/2022 | 390013.7 | 0 | 2022-12-31 | 92
2022 | Region III | AURORA | SAN LUIS (AURORA) | P00631155LZ | Construction of Flood Mitigation Structure | 121.5145 | 15.706 | 29400000 | 29400000 | 2022 | R.N.G.M. CONSTRUCTION CORPORATION (FORMERLY: R.N.G.M. CONSTRUCTION) | 5260 | 2022 | 2022-07-16 | 02/18/2022 | 0 | 0 | 2022-07-15 |  | 1
2022 | Region IV-B | MARINDUQUE | GASAN (MARINDUQUE) | P00621622LZ | Construction of Flood Mitigation Structure | 121.8706 | 13.3513 | 19300000 | 19299804.74 | 2023 | SAN SEBASTIAN CONSTRUCTION | 5261 | 2022 | 2023-03-09 | 09/02/2022 | 195.26 | 0 | 2023-03-27 | 18
2022 | Region II | ISABELA | REINA MERCEDES (ISABELA) | P00620819LZ | Construction of Flood Mitigation Structure | 121.8118 | 16.9801 | 96499997.23 | 95052496.94 | 2023 | CAMBERWELL CONSTRUCTION AND SUPPLIES / EGB CONSTRUCTION CORPORATION (FORMERLY: EGB CONSTRUCTION) | 5262 | 2022 | 2023-01-29 | 03/28/2022 | 1447500.29 | 0 | 2023-02-15 | 17
2024 | Region IV-B | QUEZON | SAN ANDRES (QUEZON) | P00844783LZ | Construction of Flood Mitigation Structure | 122.0319 | 12.5283 | 48999999.7 | 48997458.75 | 2024 | ROLCO CONSTRUCTION & DEVELOPMENT CORPORATION ( FOR | 5263 | 2024 | 2024-08-23 | 05/13/2024 | 2540.95 | 0 | 2025-01-05 | 135
2024 | Region III | AURORA | CASIGURAN (AURORA) | P00838521LZ | Construction of Flood Mitigation Structure | 122.1251 | 16.2715 | 48250000 | 48250000 | 2024 | ALEXI LOUISSE CONSTRUCTION & GENERAL MERCHANDISE | 5264 | 2024 | 2024-12-19 | 05/07/2024 | 0 | 0 | 2024-12-24 | 5
2023 | Region II | BATANES | MAHATAO (BATANES) | P00726110LZ | Construction of Flood Mitigation Structure | 121.9592 | 20.3921 | 28844120 | 28820720.71 | 2024 | J.I. ESPINO CONSTRUCTION | 5265 | 2023 | 2024-03-18 | 04/18/2023 | 23399.29 | 0 | 2024-03-26 | 8
2024 | Region III | AURORA | DIPACULAO (AURORA) | P00838510LZ | Construction of Flood Mitigation Structure | 121.7535 | 16.074 | 48250000 | 48250000 | 2024 | ALEXI LOUISSE CONSTRUCTION & GENERAL MERCHANDISE | 5266 | 2024 | 2024-12-17 | 04/30/2024 | 0 | 0 | 2025-01-06 | 20
2021 | Region II | ISABELA |  | P00525954LZ | Construction of Flood Mitigation Structure | 121.7535 | 17.4272 | 29400000 | 28958048.1 | 2022 | DRAGON TWELVE BUILDERS & CONSTRUCTION SUPPLY | 5267 | 2021 | 2022-08-14 | 01/12/2022 | 441951.9 | 0 | 2022-09-09 | 26
2023 | Region II | ISABELA | ANGADANAN (ISABELA) | P00726703LZ | Construction of Flood Mitigation Structure | 121.7538 | 16.7662 | 14699996.09 | 14479105.16 | 2023 | INFINITUM 888 CONSTRUCTION AND DEVELOPMENT CORPORATION | 5268 | 2023 | 2023-07-10 | 03/20/2023 | 220890.93 | 0 | 2023-08-11 | 32
2024 | Region II | ISABELA | JONES (ISABELA) | P00843284LZ | Construction of Flood Mitigation Structure | 121.7548 | 16.5262 | 72375000 | 72374258.98 | 2024 | DALCON CONSTRUCTION | 5269 | 2024 | 2024-10-15 | 06/03/2024 | 741.02 | 0 | 2025-06-12 | 240
2024 | Region II | ISABELA | QUIRINO (ISABELA) | P00820168LZ | Construction of Flood Mitigation Structure | 121.7562 | 17.7619 | 89385055 | 89380485.8 | 2024 | DANYSONS CONSTRUCTION AND DEVELOPMENT CORPORATION (FORMERLY: DANYSONS CONSTRUCTION) | 5270 | 2024 | 2024-07-08 | 02/12/2024 | 4569.2 | 0 | 2025-02-02 | 209
2022 | Region II | ISABELA | SANTO TOMAS (ISABELA) | P00621053LZ | Construction of Flood Mitigation Structure | 121.7563 | 17.365 | 49000000 | 48969896 | 2023 | DRAGON TWELVE BUILDERS & CONSTRUCTION SUPPLY | 5271 | 2022 | 2023-01-17 | 05/18/2022 | 30104 | 0 | 2023-02-11 | 25
2022 | Region II | ISABELA | ANGADANAN (ISABELA) | P00631127LZ | Construction of Flood Mitigation Structure | 121.757 | 16.7532 | 42139997.94 | 41507114.34 | 2022 | A. DE GUIA CONSTRUCTION AND DEVELOPMENT CORPORATION (FORMERLY: A. DE GUIA CONSTRUCTION) | 5272 | 2022 | 2022-07-08 | 02/14/2022 | 632883.6 | 0 | 2022-10-17 | 101
2021 | Region II | ISABELA |  | P00525959LZ | Construction of Flood Mitigation Structure | 121.7575 | 16.7524 | 29399957.1 | 28957991.85 | 2022 | A. DE GUIA CONSTRUCTION AND DEVELOPMENT CORPORATION (FORMERLY: A. DE GUIA CONSTRUCTION) | 5273 | 2021 | 2022-08-18 | 03/28/2022 | 441965.25 | 0 | 2022-08-17 |  | 1
2024 | Region II | ISABELA | SANTA MARIA (ISABELA) | P00821216LZ | Construction of Flood Mitigation Structure | 121.7575 | 17.4592 | 144750000 | 144734339.4 | 2024 | DRAGON TWELVE BUILDERS & CONSTRUCTION SUPPLY | 5274 | 2024 | 2024-10-18 | 04/29/2024 | 15660.6 | 0 | 2025-04-16 | 180
2022 | Region II | ISABELA | SANTO TOMAS (ISABELA) | P00621055LZ | Construction of Flood Mitigation Structure | 121.7579 | 17.3677 | 49000000 | 48970329.5 | 2023 | DRAGON TWELVE BUILDERS & CONSTRUCTION SUPPLY | 5275 | 2022 | 2023-03-15 | 05/18/2022 | 29670.5 | 0 | 2023-04-05 | 21
2023 | Region II | ISABELA | SANTO TOMAS (ISABELA) | P00727103LZ | Construction of Flood Mitigation Structure | 121.7594 | 17.4192 | 49000000 | 48974905.5 | 2023 | DRAGON TWELVE BUILDERS & CONSTRUCTION SUPPLY | 5276 | 2023 | 2023-12-04 | 07/27/2023 | 25094.5 | 0 | 2024-03-30 | 117
2023 | Region II | ISABELA | SAN AGUSTIN (ISABELA) | P00726871LZ | Construction of Flood Mitigation Structure | 121.7596 | 16.491 | 96500000 | 96500000 | 2023 | GACUTAN CONSTRUCTION INC. (FORMERLY: GACUTAN CONSTRUCTION) | 5277 | 2023 | 2023-08-17 | 06/01/2023 | 0 | 0 | 2024-03-23 | 219
2023 | Region II | ISABELA | ANGADANAN (ISABELA) | P00726707LZ | Construction of Flood Mitigation Structure | 121.7605 | 16.7502 | 19599996.95 | 19306310.58 | 2023 | INFINITUM 888 CONSTRUCTION AND DEVELOPMENT CORPORATION | 5278 | 2023 | 2023-06-30 | 03/20/2023 | 293686.37 | 0 | 2023-09-23 | 85
2024 | Region II | ISABELA | SANTO TOMAS (ISABELA) | P00821201LZ | Construction of Flood Mitigation Structure | 121.7609 | 17.3716 | 139925000 | 139912304.5 | 2024 | DRAGON TWELVE BUILDERS & CONSTRUCTION SUPPLY | 5279 | 2024 | 2024-07-22 | 02/05/2024 | 12695.5 | 0 | 2025-01-24 | 186
2023 | Region II | ISABELA | ANGADANAN (ISABELA) | P00727263LZ | Construction of Flood Mitigation Structure | 121.7614 | 16.75 | 95858914.53 | 95827936.6 | 2023 | MAV CONSTRUCTION SUPPLY AND POWER DEVELOPMENT / C.R. DOMINGO CONSTRUCTION AND POWER DEVELOPMENT, INC. (FOR. C.R. DOMINGO CONSTRUCTION, INC.) | 5280 | 2023 | 2023-08-18 | 04/11/2023 | 30977.93 | 0 | 2024-02-28 | 194
2023 | Region II | ISABELA | ANGADANAN (ISABELA) | P00727262LZ | Construction of Flood Mitigation Structure | 121.7626 | 16.7794 | 95858907.7 | 95858906.48 | 2023 | MAV CONSTRUCTION SUPPLY AND POWER DEVELOPMENT / C.R. DOMINGO CONSTRUCTION AND POWER DEVELOPMENT, INC. (FOR. C.R. DOMINGO CONSTRUCTION, INC.) | 5281 | 2023 | 2023-11-06 | 03/15/2023 | 1.22 | 0 | 2024-02-01 | 87
2022 | Region II | ISABELA | SANTO TOMAS (ISABELA) | P00621054LZ | Construction of Flood Mitigation Structure | 121.7627 | 17.3733 | 49000000 | 48970580.36 | 2023 | DRAGON TWELVE BUILDERS & CONSTRUCTION SUPPLY | 5282 | 2022 | 2023-04-06 | 05/18/2022 | 29419.64 | 0 | 2023-04-05 |  | 1
2024 | Region II | ISABELA | JONES (ISABELA) | P00843247LZ | Construction of Flood Mitigation Structure | 121.7639 | 16.5128 | 96500000 | 96500000 | 2024 | DALCON CONSTRUCTION | 5283 | 2024 | 2024-10-04 | 06/13/2024 | 0 | 0 | 2025-04-03 | 181
2024 | Region II | ISABELA | ANGADANAN (ISABELA) | P00824865LZ | Construction of Flood Mitigation Structure | 121.7652 | 16.7503 | 77199986.46 | 77157107.5 | 2025 | INFINITI CONSTRUCTION AND DEVELOPMENT CORPORATION | 5284 | 2024 | 2025-03-06 | 07/23/2024 | 42878.96 | 0 | 2025-05-08 | 63
2023 | Region II | ISABELA | SANTO TOMAS (ISABELA) | P00726685LZ | Construction of Flood Mitigation Structure | 121.766 | 17.3753 | 49000000 | 48988899.5 | 2023 | DRAGON TWELVE BUILDERS & CONSTRUCTION SUPPLY | 5285 | 2023 | 2023-11-17 | 03/02/2023 | 11100.5 | 0 | 2023-12-08 | 21
2024 | Region II | ISABELA | JONES (ISABELA) | P00843246LZ | Construction of Flood Mitigation Structure | 121.7674 | 16.5164 | 96500000 | 96500000 | 2024 | DALCON CONSTRUCTION | 5286 | 2024 | 2024-10-11 | 05/16/2024 | 0 | 0 | 2025-03-06 | 146
2024 | Region II | ISABELA | TUMAUINI (ISABELA) | P00845940LZ | Construction of Flood Mitigation Structure | 121.7675 | 17.3433 | 19800000 | 19789477.17 | 2024 | ARVEA'S CONSTRUCTION | 5287 | 2024 | 2024-09-09 | 06/11/2024 | 10522.83 | 0 | 2024-12-08 | 90
2023 | Region II | ISABELA | TUMAUINI (ISABELA) | P00727105LZ | Construction of Flood Mitigation Structure | 121.7685 | 17.3424 | 29400000 | 29394655.71 | 2023 | DRAGON TWELVE BUILDERS & CONSTRUCTION SUPPLY | 5288 | 2023 | 2023-06-15 | 03/28/2023 | 5344.29 | 0 | 2023-11-20 | 158
2023 | Region II | ISABELA | ANGADANAN (ISABELA) | P00726880LZ | Construction of Flood Mitigation Structure | 121.7686 | 16.8139 | 71894187.41 | 71021820.85 | 2023 | D.A. CADELIÃ‘A CONSTRUCTION / GACUTAN CONSTRUCTION INC. (FORMERLY: GACUTAN CONSTRUCTION) | 5289 | 2023 | 2023-08-25 | 03/15/2023 | 872366.56 | 0 | 2023-12-10 | 107
2023 | Region II | ISABELA | JONES (ISABELA) | P00740314LZ | Construction of Flood Mitigation Structure | 121.7688 | 16.5162 | 96500000 | 96500000 | 2023 | V.B. MANUBAY CONSTRUCTION | 5290 | 2023 | 2023-12-20 | 04/17/2023 | 0 | 0 | 2024-02-07 | 49
2021 | Region II | ISABELA |  | P00561165LZ | Construction of Flood Mitigation Structure | 121.769 | 17.0119 | 48999999.35 | 48705999.35 | 2022 | EGB CONSTRUCTION CORPORATION (FORMERLY: EGB CONSTRUCTION) | 5291 | 2021 | 2022-11-26 | 12/17/2021 | 294000 | 0 | 2022-11-25 |  | 1
2022 | Region III | AURORA | DIPACULAO (AURORA) | P00631152LZ | Construction of Flood Mitigation Structure | 121.7698 | 16.076 | 9800000 | 9501082.94 | 2023 | ALEXI LOUISSE CONSTRUCTION & GENERAL MERCHANDISE | 5292 | 2022 | 2023-02-21 | 06/03/2022 | 298917.06 | 0 | 2022-09-26 |  | 148
2023 | Region II | ISABELA | CITY OF CAUAYAN (ISABELA) | P00727108LZ | Construction of Flood Mitigation Structure | 121.7705 | 16.9441 | 48916000 | 48915964.67 | 2024 | DALCON CONSTRUCTION | 5293 | 2023 | 2024-09-23 | 09/04/2023 | 35.33 | 0 | 2024-09-13 |  | 10
2023 | Region II | CAGAYAN | PEÃ‘ABLANCA (CAGAYAN) | P00726119LZ | Construction of Flood Mitigation Structure | 121.7717 | 17.6295 | 29400000 | 29400000 | 2023 | JC PALOMO CONSTRUCTION & CONSTRUCTION SUPPLY | 5294 | 2023 | 2023-11-06 | 02/09/2023 | 0 | 0 | 2023-12-01 | 25
2023 | Region II | ISABELA | ANGADANAN (ISABELA) | P00726704LZ | Construction of Flood Mitigation Structure | 121.7728 | 16.8047 | 24499978.82 | 24132730.03 | 2023 | INFINITUM 888 CONSTRUCTION AND DEVELOPMENT CORPORATION | 5295 | 2023 | 2023-08-18 | 03/20/2023 | 367248.79 | 0 | 2023-09-30 | 43
2024 | Region II | ISABELA | ANGADANAN (ISABELA) | P00825233LZ | Construction of Flood Mitigation Structure | 121.7728 | 16.8047 | 48999996.67 | 48754901.14 | 2024 | INFINITI CONSTRUCTION AND DEVELOPMENT CORPORATION | 5296 | 2024 | 2024-07-15 | 04/01/2024 | 245095.53 | 0 | 2024-11-10 | 118
2024 | Region II | ISABELA | ANGADANAN (ISABELA) | P00821170LZ | Construction of Revetment | 121.7734 | 16.804 | 96499995.62 | 96479423.61 | 2024 | JWU CONSTRUCTION AND SUPPLY | 5297 | 2024 | 2024-12-17 | 06/17/2024 | 20572.01 | 0 | 2025-05-09 | 143
2024 | Region II | ISABELA | REINA MERCEDES (ISABELA) | P00821203LZ | Construction of Flood Mitigation Structure | 121.7752 | 17.0104 | 144749997.9 | 144457257.8 | 2024 | A. DE GUIA CONSTRUCTION AND DEVELOPMENT CORPORATION (FORMERLY: A. DE GUIA CONSTRUCTION) | 5298 | 2024 | 2024-09-09 | 03/12/2024 | 292740.1 | 0 | 2025-02-21 | 165
2023 | Region II | ISABELA | CITY OF CAUAYAN (ISABELA) | P00727107LZ | Construction of Flood Mitigation Structure | 121.7768 | 16.9305 | 48916000 | 48914436.85 | 2024 | DALCON CONSTRUCTION | 5299 | 2023 | 2024-08-17 | 09/04/2023 | 1563.15 | 0 | 2024-08-16 |  | 1
2024 | Region II | ISABELA | CABAGAN (ISABELA) | P00821196LZ | Construction of Flood Mitigation Structure | 121.7771 | 17.4189 | 139925000 | 139904118.4 | 2024 | DRAGON TWELVE BUILDERS & CONSTRUCTION SUPPLY | 5300 | 2024 | 2024-08-28 | 04/23/2024 | 20881.6 | 0 | 2025-04-09 | 224
2023 | Region II | ISABELA | SAN AGUSTIN (ISABELA) | P00726869LZ | Construction of Flood Mitigation Structure | 121.7772 | 16.4426 | 96500000 | 96500000 | 2023 | V.B. MANUBAY CONSTRUCTION | 5301 | 2023 | 2023-12-13 | 06/15/2023 | 0 | 0 | 2024-04-06 | 115
2022 | Region II | ISABELA | TUMAUINI (ISABELA) | P00620491LZ | Construction of Flood Mitigation Structure | 121.7776 | 17.3375 | 29400000 | 29299999.82 | 2022 | EGB CONSTRUCTION CORPORATION (FORMERLY: EGB CONSTRUCTION) | 5302 | 2022 | 2022-09-09 | 02/15/2022 | 100000.18 | 0 | 2022-10-02 | 23
2023 | Region II | ISABELA | CITY OF CAUAYAN (ISABELA) | P00742121LZ | Construction of Flood Mitigation Structure | 121.7791 | 16.9375 | 74250000 | 74229011.56 | 2024 | JWU CONSTRUCTION AND SUPPLY | 5303 | 2023 | 2024-03-05 | 05/25/2023 | 20988.44 | 0 | 2024-03-27 | 22
2021 | Region II | ISABELA |  | P00561163LZ | Construction of Drainage Structure | 121.7803 | 17.4236 | 4900000 | 4654926.2 | 2022 | DRAGON TWELVE BUILDERS & CONSTRUCTION SUPPLY | 5304 | 2021 | 2022-07-14 | 01/12/2022 | 245073.8 | 0 | 2022-07-13 |  | 1
2022 | Region II | ISABELA | CITY OF CAUAYAN (ISABELA) | P00631133LZ | Construction of Flood Mitigation Structure | 121.7812 | 16.9489 | 44100000 | 44100000 | 2022 | MA TESORO CONSTRUCTION / EGB CONSTRUCTION CORPORATION (FORMERLY: EGB CONSTRUCTION) | 5305 | 2022 | 2022-08-22 | 02/17/2022 | 0 | 0 | 2022-10-06 | 45
2022 | Region III | AURORA | DIPACULAO (AURORA) | P00631150LZ | Construction of Flood Mitigation Structure | 121.7818 | 16.132 | 9800000 | 9800000 | 2022 | A.R. CASTILLO CONSTRUCTION ENTERPRISES | 5306 | 2022 | 2022-07-22 | 03/07/2022 | 0 | 0 | 2022-07-21 |  | 1
2024 | Region II | ISABELA | CITY OF CAUAYAN (ISABELA) | P00821173LZ | Construction of Flood Mitigation Structure | 121.782 | 16.9516 | 70829070 | 70829070 | 2024 | MA TESORO CONSTRUCTION | 5307 | 2024 | 2024-11-12 | 03/13/2024 | 0 | 0 | 2024-11-27 | 15
2024 | Region II | ISABELA | REINA MERCEDES (ISABELA) | P00821204LZ | Construction of Flood Mitigation Structure | 121.7822 | 17.0093 | 144749998.4 | 144724873.4 | 2024 | ROAD EDGE TRADING & DEVELOPMENT SERVICES | 5308 | 2024 | 2024-07-30 | 03/27/2024 | 25125 | 0 | 2025-03-08 | 221
2023 | Region II | ISABELA | REINA MERCEDES (ISABELA) | P00742308LZ | Construction of Drainage Structure | 121.7822 | 16.9854 | 19799993.38 | 19794310.96 | 2024 | DRAGON TWELVE BUILDERS & CONSTRUCTION SUPPLY | 5309 | 2023 | 2024-01-18 | 08/09/2023 | 5682.42 | 0 | 2024-01-17 |  | 1
2023 | Region II | ISABELA | CITY OF CAUAYAN (ISABELA) | P00726131LZ | Construction of Flood Mitigation Structure | 121.783 | 16.9509 | 29400000 | 29399982.46 | 2023 | EGB CONSTRUCTION CORPORATION (FORMERLY: EGB CONSTRUCTION) | 5310 | 2023 | 2023-08-12 | 02/23/2023 | 17.54 | 0 | 2023-08-13 | 1
2023 | Region II | CAGAYAN | GATTARAN (CAGAYAN) | P00726877LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.7831 | 18.0522 | 72375000 | 72350000 | 2024 | TJMT CONSTRUCTION | 5311 | 2023 | 2024-01-29 | 06/08/2023 | 25000 | 0 | 2024-04-21 | 83
2022 | Region II | ISABELA | CITY OF CAUAYAN (ISABELA) | P00640509LZ | Construction of Flood Mitigation Structure | 121.7832 | 16.9509 | 14850000 | 14834053.16 | 2022 | JWU CONSTRUCTION AND SUPPLY | 5312 | 2022 | 2022-09-27 | 04/01/2022 | 15946.84 | 0 | 2022-09-26 |  | 1
2024 | Region II | ISABELA | JONES (ISABELA) | P00843274LZ | Construction of Flood Mitigation Structure | 121.7856 | 16.5331 | 96500000 | 96500000 | 2025 | V.B. MANUBAY CONSTRUCTION | 5313 | 2024 | 2025-02-07 | 05/20/2024 | 0 | 0 | 2025-03-13 | 34
2021 | Region II | ISABELA |  | P00561669LZ | Construction of Drainage Structure | 121.7863 | 17.4212 | 9900000 | 9404811.4 | 2022 | DRAGON TWELVE BUILDERS & CONSTRUCTION SUPPLY | 5314 | 2021 | 2022-08-18 | 01/12/2022 | 495188.6 | 0 | 2022-08-17 |  | 1
2023 | Region II | ISABELA | CITY OF CAUAYAN (ISABELA) | P00742120LZ | Construction of Flood Mitigation Structure | 121.7868 | 16.9687 | 74250000 | 74228619.09 | 2023 | JWU CONSTRUCTION AND SUPPLY | 5315 | 2023 | 2023-12-11 | 05/30/2023 | 21380.91 | 0 | 2024-02-14 | 65
2022 | Region II | CAGAYAN | PEÃ‘ABLANCA (CAGAYAN) | P00621415LZ | Construction of Flood Mitigation Structure | 121.7871 | 17.6196 | 91675000 | 91675000 | 2022 | EGB CONSTRUCTION CORPORATION (FORMERLY: EGB CONSTRUCTION) | 5316 | 2022 | 2022-12-09 | 03/28/2022 | 0 | 0 | 2023-03-21 | 102
2023 | Region II | CAGAYAN | PEÃ‘ABLANCA (CAGAYAN) | P00727099LZ | Construction of Flood Mitigation Structure | 121.7871 | 17.6195 | 49000000 | 48800733.64 | 2023 | MEGAY CONSTRUCTION INC. (FORMERLY: MEGAY CONSTRUCTION) / VHT CAGAYAN BUILDERS CORPORATION | 5317 | 2023 | 2023-10-31 | 03/28/2023 | 199266.36 | 0 | 2023-11-23 | 23
2022 | Region II | ISABELA | CITY OF CAUAYAN (ISABELA) | P00637014LZ | Construction of Flood Mitigation Structure | 121.7873 | 16.9712 | 96500000 | 96498540.53 | 2023 | MA TESORO CONSTRUCTION / EGB CONSTRUCTION CORPORATION (FORMERLY: EGB CONSTRUCTION) | 5318 | 2022 | 2023-06-09 | 04/13/2022 | 1459.47 | 0 | 2023-06-08 |  | 1
2023 | Region II | ISABELA | JONES (ISABELA) | P00726875LZ | Construction of Flood Mitigation Structure | 121.7879 | 16.5339 | 96500000 | 96500000 | 2023 | V.B. MANUBAY CONSTRUCTION | 5319 | 2023 | 2023-08-17 | 05/30/2023 | 0 | 0 | 2024-03-21 | 217
2022 | Region II | ISABELA | CITY OF CAUAYAN (ISABELA) | P00639330LZ | Construction of Flood Mitigation Structure | 121.7879 | 16.9497 | 96500000 | 96500000 | 2023 | MA TESORO CONSTRUCTION / EGB CONSTRUCTION CORPORATION (FORMERLY: EGB CONSTRUCTION) | 5320 | 2022 | 2023-03-09 | 04/13/2022 | 0 | 0 | 2023-03-31 | 22
2024 | Region II | ISABELA | REINA MERCEDES (ISABELA) | P00824875LZ | Construction of Flood Mitigation Structure | 121.791 | 17.0126 | 144749997.4 | 144744790 | 2024 | ROAD EDGE TRADING & DEVELOPMENT SERVICES / MAV CONSTRUCTION SUPPLY AND POWER DEVELOPMENT | 5321 | 2024 | 2024-10-08 | 03/27/2024 | 5207.4 | 0 | 2025-03-02 | 145
2023 | Region II | ISABELA | SAN AGUSTIN (ISABELA) | P00726868LZ | Construction of Flood Mitigation Structure | 121.7913 | 16.4269 | 96500000 | 96499591.31 | 2023 | V.B. MANUBAY CONSTRUCTION | 5322 | 2023 | 2023-10-02 | 06/01/2023 | 408.69 | 0 | 2024-04-26 | 207
2022 | Region II | ISABELA | CITY OF CAUAYAN (ISABELA) | P00631134LZ | Construction of Flood Mitigation Structure | 121.7914 | 16.9491 | 45080000 | 45080000 | 2022 | DANYSONS CONSTRUCTION AND DEVELOPMENT CORPORATION (FORMERLY: DANYSONS CONSTRUCTION) / JWU CONSTRUCTION AND SUPPLY | 5323 | 2022 | 2022-07-22 | 02/17/2022 | 0 | 0 | 2022-09-24 | 64
2023 | Region II | ISABELA | QUIRINO (ISABELA) | P00726419LZ | Construction of Flood Mitigation Structure | 121.7918 | 17.1459 | 47929460 | 48249880.15 | 2023 | MAR-DEB CONSTRUCTION & DEVELOPMENT CORP. (FORMERLY: MAR-DEB CONSTRUCTION & DEVELOPMENT) | 5324 | 2023 | 2023-12-12 | 03/20/2023 | 0 | 320420.15 | 2023-12-13 | 1
2024 | Region II | ISABELA | REINA MERCEDES (ISABELA) | P00821198LZ | Construction of Revetment | 121.7922 | 16.9745 | 144749996.4 | 144689532.5 | 2024 | ROAD EDGE TRADING & DEVELOPMENT SERVICES / HIGH ROAD CONSTRUCTION SERVICES | 5325 | 2024 | 2024-07-15 | 03/27/2024 | 60463.9 | 0 | 2025-03-09 | 237
2024 | Region II | CAGAYAN | BAGGAO (CAGAYAN) | P00823336LZ | Construction of Flood Mitigation Structure | 121.7931 | 17.9044 | 48250000 | 48239325.19 | 2024 | TJMT CONSTRUCTION | 5326 | 2024 | 2024-12-02 | 02/22/2024 | 10674.81 | 0 | 2024-11-06 |  | 26
2022 | Region II | ISABELA | SAN AGUSTIN (ISABELA) | P00631136LZ | Construction of Flood Mitigation Structure | 121.7933 | 16.5338 | 44100000 | 44099748.06 | 2022 | MA TESORO CONSTRUCTION / EGB CONSTRUCTION CORPORATION (FORMERLY: EGB CONSTRUCTION) | 5327 | 2022 | 2022-09-26 | 04/01/2022 | 251.94 | 0 | 2022-09-25 |  | 1
2023 | Region II | ISABELA | REINA MERCEDES (ISABELA) | P00726430LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.7938 | 16.9755 | 43136440.76 | 43116440.23 | 2023 | ROAD EDGE TRADING & DEVELOPMENT SERVICES | 5328 | 2023 | 2023-06-07 | 03/15/2023 | 20000.53 | 0 | 2023-10-21 | 136
2023 | Region II | CAGAYAN | GATTARAN (CAGAYAN) | P00726878LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.7942 | 18.0519 | 72375000 | 72355000 | 2024 | TJMT CONSTRUCTION / TIKA CONSTRUCTION INC. | 5329 | 2023 | 2024-02-16 | 06/08/2023 | 20000 | 0 | 2024-04-21 | 65
2023 | Region II | ISABELA | REINA MERCEDES (ISABELA) | P00726690LZ | Construction of Flood Mitigation Structure | 121.7955 | 16.9764 | 44099998.63 | 43439626.45 | 2023 | A. DE GUIA CONSTRUCTION AND DEVELOPMENT CORPORATION (FORMERLY: A. DE GUIA CONSTRUCTION) | 5330 | 2023 | 2023-04-30 | 03/08/2023 | 660372.18 | 0 | 2023-10-15 | 168
2022 | Region II | ISABELA | SANTO TOMAS (ISABELA) | P00621056LZ | Construction of Flood Mitigation Structure | 121.7964 | 17.3819 | 44100000 | 44072412.5 | 2023 | DRAGON TWELVE BUILDERS & CONSTRUCTION SUPPLY | 5331 | 2022 | 2023-02-05 | 05/18/2022 | 27587.5 | 0 | 2023-02-04 |  | 1
2023 | Region II | CAGAYAN | GATTARAN (CAGAYAN) | P00726879LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.7965 | 18.0529 | 72375000 | 72353000 | 2024 | TJMT CONSTRUCTION | 5332 | 2023 | 2024-04-22 | 06/08/2023 | 22000 | 0 | 2024-04-21 |  | 1
2022 | Region IV-A | QUEZON | ATIMONAN (QUEZON) | P00637083LZ | Construction of Slope Protection Structure | 121.7965 | 14.0083 | 49000000 | 49000000 | 2023 | R.A. MENDIOLA CONSTRUCTION & DEVELOPER / DZEE BUILDERS AND CONSTRUCTION SUPPLY | 5333 | 2022 | 2023-03-15 | 05/20/2022 | 0 | 0 | 2023-03-14 |  | 1
2024 | Region II | ISABELA | REINA MERCEDES (ISABELA) | P00821208LZ | Construction of Flood Mitigation Structure | 121.7979 | 17.0252 | 96499996.07 | 96398901.52 | 2024 | DANYSONS CONSTRUCTION AND DEVELOPMENT CORPORATION (FORMERLY: DANYSONS CONSTRUCTION) | 5334 | 2024 | 2024-06-17 | 03/12/2024 | 101094.55 | 0 | 2025-01-27 | 224
2024 | Region II | ISABELA | REINA MERCEDES (ISABELA) | P00845943LZ | Construction of Revetment | 121.7979 | 17.0254 | 49499999.06 | 49475237.33 | 2024 | MAR-DEB CONSTRUCTION & DEVELOPMENT CORP. (FORMERLY: MAR-DEB CONSTRUCTION & DEVELOPMENT) | 5335 | 2024 | 2024-07-01 | 03/18/2024 | 24761.73 | 0 | 2024-10-29 | 120
2023 | Region II | ISABELA | ANGADANAN (ISABELA) | P00726705LZ | Construction of Flood Mitigation Structure | 121.7981 | 16.8091 | 29207672.46 | 29062893.26 | 2023 | ED1SON DEVELOPMENT & CONSTRUCTION INC. / BDA JR CONSTRUCTION / INFINITI CONSTRUCTION AND DEVELOPMENT CORPORATION | 5336 | 2023 | 2023-09-04 | 02/28/2023 | 144779.2 | 0 | 2023-09-17 | 13
2024 | Region II | ISABELA | GAMU (ISABELA) | P00821165LZ | Construction of Revetment | 121.7987 | 17.0302 | 96499980.52 | 96451855.56 | 2025 | CAMBERWELL CONSTRUCTION AND SUPPLIES | 5337 | 2024 | 2025-03-14 | 09/13/2024 | 48124.96 | 0 | 2025-08-04 | 143
2023 | Region II | ISABELA | SANTO TOMAS (ISABELA) | P00726684LZ | Construction of Flood Mitigation Structure | 121.7988 | 17.3833 | 49000000 | 48993926.88 | 2023 | DRAGON TWELVE BUILDERS & CONSTRUCTION SUPPLY | 5338 | 2023 | 2023-08-19 | 03/02/2023 | 6073.12 | 0 | 2023-12-08 | 111
2022 | Region II | ISABELA | REINA MERCEDES (ISABELA) | P00620820LZ | Construction of Flood Mitigation Structure | 121.7994 | 16.9796 | 96499998.25 | 95057153.07 | 2023 | A. DE GUIA CONSTRUCTION AND DEVELOPMENT CORPORATION (FORMERLY: A. DE GUIA CONSTRUCTION) | 5339 | 2022 | 2023-02-16 | 03/28/2022 | 1442845.18 | 0 | 2023-02-15 |  | 1
2022 | Region II | ISABELA | JONES (ISABELA) | P00639331LZ | Construction of Flood Mitigation Structure | 121.7996 | 16.5347 | 96500000 | 96500000 | 2022 | MA TESORO CONSTRUCTION / EGB CONSTRUCTION CORPORATION (FORMERLY: EGB CONSTRUCTION) | 5340 | 2022 | 2022-11-21 | 04/01/2022 | 0 | 0 | 2023-01-09 | 49
2023 | Region IV-A | QUEZON | PAGBILAO (QUEZON) | P00740651LZ | Construction of Flood Mitigation Structure | 121.8022 | 13.9824 | 12250000 | 12250000 | 2024 | DZEE BUILDERS AND CONSTRUCTION SUPPLY | 5341 | 2023 | 2024-02-10 | 05/08/2023 | 0 | 0 | 2024-02-09 |  | 1
2023 | Region II | ISABELA | ANGADANAN (ISABELA) | P00727261LZ | Construction of Flood Mitigation Structure | 121.8025 | 16.8183 | 95858916.02 | 95828517.81 | 2023 | MAV CONSTRUCTION SUPPLY AND POWER DEVELOPMENT / C.R. DOMINGO CONSTRUCTION AND POWER DEVELOPMENT, INC. (FOR. C.R. DOMINGO CONSTRUCTION, INC.) | 5342 | 2023 | 2023-11-07 | 04/25/2023 | 30398.21 | 0 | 2024-03-13 | 127
2023 | Region IV-A | QUEZON | PADRE BURGOS (QUEZON) | P00740650LZ | Construction of Flood Mitigation Structure | 121.8036 | 13.9722 | 12249981.54 | 12250000 | 2023 | TONWAY BUILDERS AND SUPPLY | 5343 | 2023 | 2023-07-24 | 05/03/2023 | 0 | 18.46 | 2023-08-29 | 36
2022 | Region II | CAGAYAN | BALLESTEROS (CAGAYAN) | P00631109LZ | Construction of Flood Mitigation Structure | 121.5179 | 18.4138 | 49000000 | 49000000 | 2022 | JEICCA BUILDERS / W.D. NAVARRO CONSTRUCTION CO. | 5344 | 2022 | 2022-12-03 | 02/22/2022 | 0 | 0 | 2022-12-02 |  | 1
2024 | Region II | ISABELA | QUIRINO (ISABELA) | P00823339LZ | Construction of Flood Mitigation Structure | 121.6835 | 17.1564 | 96500000 | 96490180.17 | 2024 | A COLOMA CONSTRUCTION / JWU CONSTRUCTION AND SUPPLY | 5345 | 2024 | 2024-10-02 | 03/18/2024 | 9819.83 | 0 | 2025-02-18 | 139
2022 | Region VI | ANTIQUE | SAN JOSE (CAPITAL) (ANTIQUE) | P00620249VS | Construction of Flood Mitigation Structure | 121.9609 | 10.8067 | 52110000 | 8256078.6 | 2023 | F & J GENERAL CONSTRUCTION AND SUPPLY CORPORATION | 5346 | 2022 | 2023-04-22 | 02/18/2022 | 43853921.4 | 0 | 2022-12-19 |  | 124
2022 | Region IV-B | ROMBLON | ODIONGAN (ROMBLON) | P00630957LZ | Construction of Flood Mitigation Structure | 122.0326 | 12.3473 | 53074982.21 | 53074432.75 | 2022 | LEGACY CONSTRUCTION CORPORATION (FORMERLY: LEGACY CONSTRUCTION) | 5347 | 2022 | 2022-12-26 | 05/24/2022 | 549.46 | 0 | 2022-12-25 |  | 1
2024 | Region IV-B | MARINDUQUE | GASAN (MARINDUQUE) | P00846096LZ | Construction of Flood Mitigation Structure | 121.8707 | 13.3082 | 4948000 | 4948075.66 | 2024 | JEDIDIAH CONSTRUCTION | 5348 | 2024 | 2024-04-12 | 01/30/2024 | 0 | 75.66 | 2024-04-11 |  | 1
2024 | Region II | ISABELA | ALICIA (ISABELA) | P00821213LZ | Construction of Revetment | 121.684 | 16.7753 | 96499996.49 | 96441752.68 | 2024 | JWU CONSTRUCTION AND SUPPLY | 5349 | 2024 | 2024-10-25 | 06/24/2024 | 58243.81 | 0 | 2025-05-12 | 199
2022 | Region VI | ANTIQUE | SAN REMIGIO (ANTIQUE) | P00620298VS | Construction of Revetment | 122.1251 | 10.8736 | 49000000 | 49000000 | 2023 | SUNWEST, INC. (FORMERLY: SUNWEST CONSTRUCTION & DEVELOPMENT CORPORATION) | 5350 | 2022 | 2023-02-25 | 02/07/2022 | 0 | 0 | 2023-01-28 |  | 28
2023 | Region IV-A | QUEZON | PADRE BURGOS (QUEZON) | P00736026LZ | Construction of Flood Mitigation Structure | 121.8156 | 13.9112 | 96499903.46 | 96500000 | 2023 | ALPHA & OMEGA GEN. CONTRACTOR & DEVELOPMENT CORP. | 5351 | 2023 | 2023-12-11 | 03/01/2023 | 0 | 96.54 | 2023-12-22 | 11
2024 | Region II | CAGAYAN | BALLESTEROS (CAGAYAN) | P00825053LZ | Construction of Flood Mitigation Facility | 121.5183 | 18.4071 | 49000000 | 48234966.56 | 2024 | JEICCA BUILDERS | 5352 | 2024 | 2024-04-20 | 02/07/2024 | 765033.44 | 0 | 2024-08-11 | 113
2024 | Region II | ISABELA | ROXAS (ISABELA) | P00824887LZ | Construction of Flood Mitigation Structure | 121.6855 | 17.1092 | 96500000 | 96480164.87 | 2025 | RRC CO. INC. (FORMERLY: R R C CONSTRUCTION) | 5353 | 2024 | 2025-05-13 | 05/13/2024 | 19835.13 | 0 | 2025-05-12 |  | 1
2022 | Region IV-B | ROMBLON | ODIONGAN (ROMBLON) | P00620672LZ | Construction of Flood Mitigation Structure | 122.0326 | 12.3473 | 48249750.25 | 48231860.27 | 2022 | ASHLEYKA CONSTRUCTION AND SUPPLIES | 5354 | 2022 | 2022-12-16 | 05/24/2022 | 17889.98 | 0 | 2022-12-15 |  | 1
2023 | Region IV-B | MARINDUQUE | GASAN (MARINDUQUE) | P00737548LZ | Construction of Flood Mitigation Structure | 121.8708 | 13.3082 | 4948000 | 4948142.9 | 2023 | JEDIDIAH CONSTRUCTION | 5355 | 2023 | 2023-04-21 | 01/31/2023 | 0 | 142.9 | 2023-04-20 |  | 1
2024 | Region II | ISABELA | RAMON (ISABELA) | P00820782LZ | Construction of Flood Mitigation Structure | 121.5202 | 16.831 | 3429985 | 3424520.75 | 2024 | MAV CONSTRUCTION SUPPLY AND POWER DEVELOPMENT | 5356 | 2024 | 2024-05-08 | 03/27/2024 | 5464.25 | 0 | 2024-05-07 |  | 1
2023 | Region II | CAGAYAN | PEÃ‘ABLANCA (CAGAYAN) | P00727351LZ | Construction of Flood Mitigation Structure | 121.8157 | 17.7079 | 29400000 | 29400000 | 2023 | QUASAR CONSTRUCTION AND SUPPLY | 5357 | 2023 | 2023-10-19 | 03/21/2023 | 0 | 0 | 2023-10-18 |  | 1
2024 | Region II | BATANES | UYUGAN (BATANES) | P00820774LZ | Construction of Flood Mitigation Structure | 121.961 | 20.3667 | 9800000 | 9749525.43 | 2024 | MJMARI BUILDERS AND DEVELOPMENT CORPORATION (FORMERLY: MJMARI BUILDERS AND ENTERPRISES) | 5358 | 2024 | 2024-11-20 | 06/10/2024 | 50474.57 | 0 | 2024-12-15 | 25
2021 | Region VI | ANTIQUE |  | P00521581VS | Construction of Revetment | 122.1252 | 10.8735 | 49000000 | 48507211.59 | 2022 | SUNWEST, INC. (FORMERLY: SUNWEST CONSTRUCTION & DEVELOPMENT CORPORATION) | 5359 | 2021 | 2022-09-19 | 06/21/2021 | 492788.41 | 0 | 2022-04-15 |  | 157
2022 | Region II | BATANES | UYUGAN (BATANES) | P00632790LZ | Construction of Flood Mitigation Structure | 121.964 | 20.3679 | 4900000 | 4894683.33 | 2022 | REMAR CONSTRUCTION | 5360 | 2022 | 2022-11-06 | 02/28/2022 | 5316.67 | 0 | 2022-07-18 |  | 111
2023 | Region II | ISABELA | ILAGAN CITY (CAPITAL) (ISABELA) | P00726447LZ | Construction of Flood Mitigation Structure | 121.8722 | 17.1539 | 96200000 | 96169397.8 | 2023 | DRAGON TWELVE BUILDERS & CONSTRUCTION SUPPLY | 5361 | 2023 | 2023-09-19 | 03/02/2023 | 30602.2 | 0 | 2023-11-23 | 65
2022 | Region IV-B | ROMBLON | SAN ANDRES (ROMBLON) | P00621492LZ | Construction of Flood Mitigation Structure | 122.0328 | 12.5319 | 24499999.28 | 24500000 | 2022 | ATHENA CONSTRUCTION AND DEVELOPMENT | 5362 | 2022 | 2022-12-15 | 06/20/2022 | 0 | 0.72 | 2023-01-07 | 23
2023 | Region III | AURORA | SAN LUIS (AURORA) | P00740577LZ | Construction of Drainage Structure | 121.5212 | 15.7196 | 2940000 | 2852860.02 | 2023 | RADIANCE TRADERS & BUILDERS | 5363 | 2023 | 2023-07-30 | 05/16/2023 | 87139.98 | 0 | 2023-07-28 |  | 2
2023 | Region IV-B | MARINDUQUE | SANTA CRUZ (MARINDUQUE) | P00740420LZ | Construction of Revetment | 122.1276 | 13.4513 | 241249999.6 | 241247258.7 | 2024 | HGG BUILDERS & SUPPLY | 5364 | 2023 | 2024-05-06 | 04/13/2023 | 2740.9 | 0 | 2024-05-05 |  | 1
2023 | Region II | ISABELA | REINA MERCEDES (ISABELA) | P00726428LZ | Construction of Flood Mitigation Structure | 121.817 | 16.9783 | 52722403.1 | 52702403.1 | 2023 | ROAD EDGE TRADING & DEVELOPMENT SERVICES | 5365 | 2023 | 2023-07-05 | 03/15/2023 | 20000 | 0 | 2023-11-03 | 121
2023 | Region II | BATANES | BASCO (CAPITAL) (BATANES) | P00737438LZ | Construction of Flood Mitigation Structure | 121.9647 | 20.4558 | 5899148 | 5899148 | 2023 | R.L. PACANA'S CONSTRUCTION & DEVELOPMENT | 5366 | 2023 | 2023-09-23 | 02/15/2023 | 0 | 0 | 2023-08-26 |  | 28
2023 | Region II | CAGAYAN | CAMALANIUGAN (CAGAYAN) | P00726667LZ | Construction of Flood Mitigation Structure | 121.6858 | 18.2544 | 35280000 | 35264241.7 | 2024 | APS CONSTRUCTION | 5367 | 2023 | 2024-07-29 | 04/02/2023 | 15758.3 | 0 | 2023-12-03 |  | 239
2024 | Region IV-B | ROMBLON | ODIONGAN (ROMBLON) | P00823566LZ | Construction of Flood Mitigation Structure | 122.0342 | 12.3994 | 125449999.2 | 125450000 | 2024 | SUNWEST, INC. (FORMERLY: SUNWEST CONSTRUCTION & DEVELOPMENT CORPORATION) | 5368 | 2024 | 2024-11-15 | 03/13/2024 | 0 | 0.8 | 2025-02-27 | 104
2020 | Region II | BATANES |  | P00421687LZ | Construction of Flood Mitigation Structure | 121.9657 | 20.4487 | 27428233.68 | 27153948.61 | 2022 | MJMARI BUILDERS AND DEVELOPMENT CORPORATION (FORMERLY: MJMARI BUILDERS AND ENTERPRISES) | 5369 | 2020 | 2022-10-31 | 03/11/2020 | 274285.07 | 0 | 2021-02-11 |  | 627
2022 | Region III | AURORA | SAN LUIS (AURORA) | P00620497LZ | Construction of Flood Mitigation Structure | 121.5217 | 15.7629 | 48245843.28 | 48146608.28 | 2023 | IM CONSTRUCTION CORPORATION | 5370 | 2022 | 2023-05-08 | 08/15/2022 | 99235 | 0 | 2023-05-07 |  | 1
2022 | Region IV-B | MARINDUQUE | GASAN (MARINDUQUE) | P00639510LZ | Construction of Flood Mitigation Structure | 121.8723 | 13.3071 | 5878000 | 5877868.15 | 2022 | T.N.G. CONSTRUCTION CORPORATION | 5371 | 2022 | 2022-09-04 | 03/30/2022 | 131.85 | 0 | 2022-09-03 |  | 1
2023 | Region II | CAGAYAN | CAMALANIUGAN (CAGAYAN) | P00726668LZ | Construction of Flood Mitigation Structure | 121.6861 | 18.2553 | 35280000 | 35255302.94 | 2023 | APS CONSTRUCTION | 5372 | 2023 | 2023-12-01 | 04/05/2023 | 24697.06 | 0 | 2023-12-06 | 5
2022 | Region VI | NEGROS OCCIDENTAL | SILAY CITY (NEGROS OCCIDENTAL) | P00620003VS | Construction of Flood Mitigation Structure | 122.0369 | 10.8131 | 87082562.53 | 87080562 | 2022 | JAIME B. CHING ENTERPRISES / ESJ AND SONS CONSTRUCTION & CONSTRUCTION SUPPLY, INC. (FORM.:ALFIE'S CONST. &CONST. SUPPLY, INC.) | 5373 | 2022 | 2022-12-13 | 02/22/2022 | 2000.53 | 0 | 2022-12-12 |  | 1
2023 | Region IX | ZAMBOANGA DEL SUR | ZAMBOANGA CITY (ZAMBOANGA DEL SUR) | P00721591MN | Construction of Flood Mitigation Structure | 121.9658 | 6.9758 | 29400000 | 26485720.03 | 2023 | UNITEC BUILDER, INCORPORATED | 5374 | 2023 | 2023-12-13 | 06/30/2023 | 2914279.97 | 0 | 2024-01-30 | 48
2024 | Region II | ISABELA | JONES (ISABELA) | P00843228LZ | Construction of Flood Mitigation Structure | 121.818 | 16.5356 | 96500000 | 96499766.88 | 2024 | DALCON CONSTRUCTION | 5375 | 2024 | 2024-10-15 | 06/03/2024 | 233.12 | 0 | 2025-08-06 | 295
2023 | Region II | ISABELA | JONES (ISABELA) | P00726872LZ | Construction of Flood Mitigation Structure | 121.8729 | 16.5095 | 96500000 | 96499800.46 | 2023 | V.B. MANUBAY CONSTRUCTION | 5376 | 2023 | 2023-08-14 | 06/01/2023 | 199.54 | 0 | 2024-03-23 | 222
2024 | Region II | ISABELA | JONES (ISABELA) | P00843249LZ | Construction of Flood Mitigation Structure | 121.6868 | 16.5595 | 96500000 | 96500000 | 2024 | EGB CONSTRUCTION CORPORATION (FORMERLY: EGB CONSTRUCTION) | 5377 | 2024 | 2024-12-07 | 05/20/2024 | 0 | 0 | 2025-03-16 | 99
2023 | Region III | AURORA | CASIGURAN (AURORA) | P00740576LZ | Construction of Flood Mitigation Structure | 122.1301 | 16.2831 | 49000000 | 49000000 | 2024 | GERRA CONSTRUCTION INCORPORATED (FORMERLY: GERRA CONSTRUCTION) | 5378 | 2023 | 2024-02-21 | 03/28/2023 | 0 | 0 | 2024-03-14 | 22
2023 | Region II | ISABELA | SAN MARIANO (ISABELA) | P00726700LZ | Construction of Flood Mitigation Structure | 122.038 | 16.8577 | 43811511.9 | 43371200.6 | 2023 | CAMBERWELL CONSTRUCTION AND SUPPLIES | 5379 | 2023 | 2023-11-21 | 04/11/2023 | 440311.3 | 0 | 2023-11-20 |  | 1
2024 | Region IV-B | MARINDUQUE | BOAC (CAPITAL) (MARINDUQUE) | P00820390LZ | Construction of Flood Mitigation Structure | 121.8731 | 13.4324 | 67548000 | 67544604.27 | 2024 | G.T.J. CONSTRUCTION / R.R. ENCABO CONSTRUCTORS INCORPORATED (FORMERLY RR | 5380 | 2024 | 2024-10-23 | 02/19/2024 | 3395.73 | 0 | 2024-11-19 | 27
2023 | Region II | ISABELA | ALICIA (ISABELA) | P00726702LZ | Construction of Flood Mitigation Structure | 121.6871 | 16.7692 | 19471769.94 | 19461769.94 | 2023 | JWU CONSTRUCTION AND SUPPLY | 5381 | 2023 | 2023-06-01 | 03/15/2023 | 10000 | 0 | 2023-09-15 | 106
2021 | Region II | BATANES |  | P00525946LZ | Construction of Flood Mitigation Structure | 121.9676 | 20.4516 | 29400000 | 24931200 | 2022 | ST. TIMOTHY CONSTRUCTION CORPORATION | 5382 | 2021 | 2022-07-31 | 02/24/2021 | 4468800 | 0 | 2022-02-04 |  | 177
2022 | Cordillera Administrative Region | MOUNTAIN PROVINCE | PARACELIS (MOUNTAIN PROVINCE) | P00621526LZ | Construction of Flood Mitigation Structure | 121.5219 | 17.1244 | 9800000 | 9800000 | 2022 | UPLAND CONSTRUCTION AND ENGINEERING SERVICES | 5383 | 2022 | 2022-10-30 | 06/16/2022 | 0 | 0 | 2022-10-29 |  | 1
2023 | Region II | ISABELA | CITY OF CAUAYAN (ISABELA) | P00742123LZ | Construction of Flood Mitigation Structure | 121.8197 | 16.9225 | 74250000 | 74228662.29 | 2023 | JWU CONSTRUCTION AND SUPPLY | 5384 | 2023 | 2023-08-30 | 05/30/2023 | 21337.71 | 0 | 2024-04-01 | 215
2023 | Region IV-B | ROMBLON | ALCANTARA (ROMBLON) | P00726952LZ | Construction of Flood Mitigation Structure | 122.1305 | 12.5669 | 289500000 | 289497468.8 | 2023 | LEGACY CONSTRUCTION CORPORATION (FORMERLY: LEGACY CONSTRUCTION) | 5385 | 2023 | 2023-12-10 | 03/29/2023 | 2531.2 | 0 | 2024-03-21 | 102
2022 | Cordillera Administrative Region | MOUNTAIN PROVINCE | PARACELIS (MOUNTAIN PROVINCE) | P00620137LZ | Construction of Flood Mitigation Structure | 121.5228 | 17.1197 | 69960570 | 69960570 | 2023 | ED1SON DEVELOPMENT & CONSTRUCTION INC. / GAWIS CONSTRUCTION SERVICES | 5386 | 2022 | 2023-01-19 | 02/24/2022 | 0 | 0 | 2023-01-18 |  | 1
2022 | Region II | ISABELA | CABAGAN (ISABELA) | P00632799LZ | Construction of Flood Mitigation Structure | 121.8205 | 17.3678 | 14849954.58 | 14799954.57 | 2022 | EGB CONSTRUCTION CORPORATION (FORMERLY: EGB CONSTRUCTION) | 5387 | 2022 | 2022-08-27 | 02/15/2022 | 50000.01 | 0 | 2022-08-26 |  | 1
2023 | Region VI | ANTIQUE | SIBALOM (ANTIQUE) | P00721730VS | Construction of Flood Mitigation Structure | 122.0388 | 10.8108 | 91675000 | 91675000 | 2024 | F. GURREA CONSTRUCTION, INCORPORATED | 5388 | 2023 | 2024-05-03 | 02/09/2023 | 0 | 0 | 2024-04-20 |  | 13
2024 | Region II | ISABELA | ALICIA (ISABELA) | P00821214LZ | Construction of Revetment | 121.6872 | 16.7738 | 96499996.15 | 96442247.44 | 2024 | JWU CONSTRUCTION AND SUPPLY / ALGO CONSTRUCTION AND POWER DEVELOPMENT, INC. | 5389 | 2024 | 2024-10-25 | 07/15/2024 | 57748.71 | 0 | 2025-06-02 | 220
2022 | Region II | BATANES | SABTANG (BATANES) | P00632789LZ | Construction of Slope Protection Structure | 121.8739 | 20.3328 | 5940000 | 4978478.33 | 2022 | BHM CONSTRUCTION | 5390 | 2022 | 2022-12-04 | 03/21/2022 | 961521.67 | 0 | 2022-10-30 |  | 35
2023 | Region VI | ANTIQUE | BARBAZA (ANTIQUE) | P00733295VS | Construction of Flood Mitigation Structure | 122.041 | 11.1984 | 14850000 | 14700000 | 2023 | TIBIAO-ANTIQUE N.K. ENTERPRISE, INC. | 5391 | 2023 | 2023-08-25 | 03/30/2023 | 150000 | 0 | 2023-09-13 | 19
2022 | Region II | BATANES | BASCO (CAPITAL) (BATANES) | P00632788LZ | Construction of Flood Mitigation Structure | 121.9679 | 20.4464 | 4950000 | 4947421.64 | 2022 | R.L. PACANA'S CONSTRUCTION & DEVELOPMENT | 5392 | 2022 | 2022-12-04 | 03/21/2022 | 2578.36 | 0 | 2022-08-07 |  | 119
2024 | Region IV-B | ORIENTAL MINDORO | ROXAS (ORIENTAL MINDORO) | P00825251LZ | Construction of Flood Mitigation Structure | 121.5234 | 12.5986 | 49000000 | 48997656.29 | 2024 | LUMEL GLENN CONSTRUCTION | 5393 | 2024 | 2024-12-21 | 03/07/2024 | 2343.71 | 0 | 2024-12-20 |  | 1
2022 | Region IV-B | MARINDUQUE | MOGPOG (MARINDUQUE) | P00639518LZ | Construction of Flood Mitigation Structure | 121.8752 | 13.4738 | 29398000 | 24729962.75 | 2023 | JEDIDIAH CONSTRUCTION | 5394 | 2022 | 2023-02-10 | 03/30/2022 | 4668037.25 | 0 | 2023-02-09 |  | 1
2024 | Region VI | ANTIQUE | SIBALOM (ANTIQUE) | P00820387VS | Construction of Flood Mitigation Structure | 122.041 | 10.8038 | 19600000 | 19600000 | 2024 | SENTINA CONSTRUCTION AND SUPPLY | 5395 | 2024 | 2024-10-28 | 02/07/2024 | 0 | 0 | 2024-08-23 |  | 66
2023 | Region VI | ANTIQUE | SAN JOSE (CAPITAL) (ANTIQUE) | P00721729VS | Construction of Flood Mitigation Structure | 121.9681 | 10.8069 | 86850000 | 57900000 | 2024 | F. GURREA CONSTRUCTION, INCORPORATED | 5396 | 2023 | 2024-02-28 | 02/09/2023 | 28950000 | 0 | 2024-02-27 |  | 1
2023 | Region IV-A | QUEZON | PADRE BURGOS (QUEZON) | P00736027LZ | Construction of Flood Mitigation Structure | 121.8215 | 13.905 | 96499903.53 | 96500000 | 2023 | BOMEL CONSTRUCTION / MAR-VEL CONSTRUCTION & SUPPLY | 5397 | 2023 | 2023-12-11 | 03/06/2023 | 0 | 96.47 | 2023-12-10 |  | 1
2022 | Region VI | ANTIQUE | VALDERRAMA (ANTIQUE) | P00620078VS | Construction of Flood Mitigation Structure | 122.1316 | 11.0112 | 49000000 | 49000000 | 2022 | IBC INTERNATIONAL BUILDERS CORPORATION | 5398 | 2022 | 2022-08-26 | 02/07/2022 | 0 | 0 | 2022-08-30 | 4
2024 | Region II | ISABELA | JONES (ISABELA) | P00843250LZ | Construction of Flood Mitigation Structure | 121.6891 | 16.5638 | 96500000 | 96500000 | 2024 | EGB CONSTRUCTION CORPORATION (FORMERLY: EGB CONSTRUCTION) | 5399 | 2024 | 2024-08-22 | 06/13/2024 | 0 | 0 | 2025-04-09 | 230
2024 | Region II | BATANES | UYUGAN (BATANES) | P00820773LZ | Construction of Flood Mitigation Structure | 121.9687 | 20.3834 | 37632000 | 37632000 | 2024 | MJMARI BUILDERS AND DEVELOPMENT CORPORATION (FORMERLY: MJMARI BUILDERS AND ENTERPRISES) | 5400 | 2024 | 2024-12-11 | 03/11/2024 | 0 | 0 | 2025-03-07 | 86
2024 | Region VI | ANTIQUE | SAN REMIGIO (ANTIQUE) | P00820276VS | Construction of Flood Mitigation Structure | 122.1322 | 10.8899 | 82025000 | 82025000 | 2024 | A.D. PENDON CONSTRUCTION & SUPPLY, INC. (FORMERLY: ADP CONSTRUCTION & SUPPLY) | 5401 | 2024 | 2024-09-24 | 02/23/2024 | 0 | 0 | 2024-12-29 | 96
2023 | Region III | AURORA | BALER (CAPITAL) (AURORA) | P00737445LZ | Construction of Flood Mitigation Structure | 121.5246 | 15.7564 | 14700000 | 14700000 | 2023 | MORNING STEEL CONSTRUCTION | 5402 | 2023 | 2023-06-22 | 02/13/2023 | 0 | 0 | 2023-06-21 |  | 1
2023 | Region IV-B | MARINDUQUE | BOAC (CAPITAL) (MARINDUQUE) | P00727175LZ | Construction of Flood Mitigation Structure | 121.8762 | 13.4326 | 48998000 | 48018673.52 | 2023 | AMETHYST HORIZON BUILDERS AND GEN. CONTRACTOR AND DEVELOPMENT CORP. | 5403 | 2023 | 2023-06-26 | 03/28/2023 | 979326.48 | 0 | 2023-10-11 | 107
2022 | Region IV-B | MARINDUQUE | TORRIJOS (MARINDUQUE) | P00637808LZ | Construction of Flood Mitigation Structure | 122.0432 | 13.269 | 47517999.99 | 47519311.81 | 2023 | G.T.J. CONSTRUCTION | 5404 | 2022 | 2023-05-30 | 03/30/2022 | 0 | 1311.82 | 2023-04-01 |  | 59
2022 | Region II | ISABELA | CITY OF SANTIAGO (ISABELA) | P00621448LZ | Construction of Flood Mitigation Structure | 121.5255 | 16.694 | 49000000 | 49000000 | 2022 | V.B. MANUBAY CONSTRUCTION | 5405 | 2022 | 2022-10-26 | 04/07/2022 | 0 | 0 | 2022-10-25 |  | 1
2022 | Region II | CAGAYAN | GATTARAN (CAGAYAN) | P00632797LZ | Construction of Slope Protection Structure | 121.8227 | 18.023 | 4950000 | 4875750 | 2023 | TJMT CONSTRUCTION | 5406 | 2022 | 2023-05-28 | 10/10/2022 | 74250 | 0 | 2023-04-18 |  | 40
2022 | Region VI | ANTIQUE | BARBAZA (ANTIQUE) | P00631710VS | Construction of Flood Mitigation Structure | 122.0439 | 11.1985 | 9800000 | 9800000 | 2022 | GATEWAY 21-25 CONSTRUCTION CORP. (FORMERLY E.D. DE | 5407 | 2022 | 2022-08-23 | 03/24/2022 | 0 | 0 | 2022-08-22 |  | 1
2022 | Region III | AURORA | DIPACULAO (AURORA) | P00631158LZ | Construction of Flood Mitigation Structure | 121.5259 | 15.878 | 19600000 | 19600000 | 2022 | ALEXI LOUISSE CONSTRUCTION & GENERAL MERCHANDISE | 5408 | 2022 | 2022-12-12 | 03/01/2022 | 0 | 0 | 2022-12-20 | 8
2023 | Region II | ISABELA | JONES (ISABELA) | P00740318LZ | Construction of Flood Mitigation Structure | 121.6893 | 16.5416 | 96500000 | 96489771.32 | 2023 | ROAD EDGE TRADING & DEVELOPMENT SERVICES | 5409 | 2023 | 2023-08-15 | 04/17/2023 | 10228.68 | 0 | 2024-02-07 | 176
2023 | Region III | AURORA | CASIGURAN (AURORA) | P00725760LZ | Construction of Flood Mitigation Structure | 122.1326 | 16.2824 | 289499825.2 | 289499825.2 | 2024 | DALCON CONSTRUCTION / EGB CONSTRUCTION CORPORATION (FORMERLY: EGB CONSTRUCTION) | 5410 | 2023 | 2024-02-21 | 02/27/2023 | 0 | 0 | 2024-02-20 |  | 1
2024 | Region IV-B | MARINDUQUE | BOAC (CAPITAL) (MARINDUQUE) | P00820389LZ | Construction of Flood Mitigation Structure | 121.8783 | 13.4311 | 87813000 | 87809976.28 | 2024 | MRRM TRADING & CONSTRUCTION | 5411 | 2024 | 2024-08-05 | 03/13/2024 | 3023.72 | 0 | 2024-12-14 | 131
2023 | Region IV-B | MARINDUQUE | MOGPOG (MARINDUQUE) | P00727179LZ | Construction of Flood Mitigation Structure | 121.8812 | 13.477 | 48998000 | 48018034.7 | 2023 | DQT BUILDERS CORPORATION (FORMERLY DQT BUILDERS) | 5412 | 2023 | 2023-12-11 | 03/28/2023 | 979965.3 | 0 | 2023-12-10 |  | 1
2024 | Region VI | ANTIQUE | BARBAZA (ANTIQUE) | P00834991VS | Construction of Flood Mitigation Structure | 122.0442 | 11.1983 | 49500000 | 49500000 | 2024 | MINDANAO ROCK | 5413 | 2024 | 2024-10-23 | 03/08/2024 | 0 | 0 | 2024-11-05 | 13
2024 | Region IV-B | MARINDUQUE | MOGPOG (MARINDUQUE) | P00820964LZ | Construction of Flood Mitigation Structure | 121.8822 | 13.477 | 9798000 | 9602077.29 | 2024 | T.N.G. CONSTRUCTION CORPORATION | 5414 | 2024 | 2024-07-05 | 01/30/2024 | 195922.71 | 0 | 2024-04-28 |  | 68
2023 | Region II | ISABELA | ILAGAN CITY (CAPITAL) (ISABELA) | P00726446LZ | Construction of Flood Mitigation Structure | 121.969 | 17.0554 | 96200000 | 96174122 | 2023 | DRAGON TWELVE BUILDERS & CONSTRUCTION SUPPLY | 5415 | 2023 | 2023-10-25 | 03/02/2023 | 25878 | 0 | 2023-11-23 | 29
2023 | Region II | CAGAYAN | BAGGAO (CAGAYAN) | P00726113LZ | Construction of Revetment | 121.8229 | 17.9125 | 49000000 | 48990000 | 2023 | TJMT CONSTRUCTION / VHT CAGAYAN BUILDERS CORPORATION | 5416 | 2023 | 2023-06-15 | 02/27/2023 | 10000 | 0 | 2023-11-15 | 153
2022 | Region VI | ANTIQUE | TIBIAO (ANTIQUE) | P00633212VS | Construction of Slope Protection Structure | 122.0449 | 11.2729 | 4950000 | 4950000 | 2022 | GATEWAY 21-25 CONSTRUCTION CORP. (FORMERLY E.D. DE | 5417 | 2022 | 2022-07-11 | 03/24/2022 | 0 | 0 | 2022-07-10 |  | 1
2024 | Region II | ISABELA | JONES (ISABELA) | P00843227LZ | Construction of Flood Mitigation Structure | 121.8242 | 16.5376 | 96500000 | 96499503.07 | 2024 | DALCON CONSTRUCTION | 5418 | 2024 | 2024-10-15 | 06/03/2024 | 496.93 | 0 | 2025-08-06 | 295
2022 | Region IV-B | MARINDUQUE | MOGPOG (MARINDUQUE) | P00641900LZ | Construction of Flood Mitigation Structure | 121.8827 | 13.5011 | 10888000 | 9813540.74 | 2022 | JEDIDIAH CONSTRUCTION | 5419 | 2022 | 2022-10-13 | 03/30/2022 | 1074459.26 | 0 | 2022-10-12 |  | 1
2021 | Region IX | ZAMBOANGA DEL SUR |  | P00522033MN | Construction of Flood Mitigation Structure | 121.9697 | 6.9809 | 60793971.23 | 57867414.58 | 2022 | TEDDIE CONSTRUCTION DEVELOPMENT, INC. | 5420 | 2021 | 2022-12-22 | 03/26/2021 | 2926556.65 | 0 | 2022-12-21 |  | 1
2022 | Region III | AURORA | DIPACULAO (AURORA) | P00631156LZ | Construction of Flood Mitigation Structure | 121.5301 | 15.835 | 34300000 | 34300000 | 2023 | ALEXI LOUISSE CONSTRUCTION & GENERAL MERCHANDISE | 5421 | 2022 | 2023-06-12 | 03/14/2022 | 0 | 0 | 2023-06-11 |  | 1
2024 | Region II | ISABELA | JONES (ISABELA) | P00843223LZ | Construction of Flood Mitigation Structure | 121.6893 | 16.5702 | 96500000 | 96500000 | 2024 | EGB CONSTRUCTION CORPORATION (FORMERLY: EGB CONSTRUCTION) | 5422 | 2024 | 2024-11-11 | 06/19/2024 | 0 | 0 | 2025-04-15 | 155
2022 | Region II | CAGAYAN | BAGGAO (CAGAYAN) | P00621022LZ | Construction of Flood Mitigation Structure | 121.8841 | 17.9331 | 49000000 | 48989897.82 | 2022 | MEGAY CONSTRUCTION INC. (FORMERLY: MEGAY CONSTRUCTION) | 5423 | 2022 | 2022-10-27 | 02/02/2022 | 10102.18 | 0 | 2022-11-16 | 20
2024 | Region IX | BASILAN | CITY OF ISABELA (CAPITAL) (CITY OF ISABELA) | P00821187MN | Construction of Flood Mitigation Structure | 121.9699 | 6.7047 | 96500000 | 96481614.48 | 2024 | RCDG CONSTRUCTION CORPORATION / MMP CONSTRUCTION AND SUPPLIES | 5424 | 2024 | 2024-12-17 | 06/13/2024 | 18385.52 | 0 | 2025-04-18 | 122
2022 | Region II | BATANES | BASCO (CAPITAL) (BATANES) | P00632795LZ | Construction of Flood Mitigation Structure | 121.9701 | 20.4412 | 9835000 | 9824370.18 | 2022 | R.L. PACANA'S CONSTRUCTION & DEVELOPMENT | 5425 | 2022 | 2022-12-18 | 03/31/2022 | 10629.82 | 0 | 2022-10-01 |  | 78
2022 | Region VI | AKLAN | IBAJAY (AKLAN) | P00630627VS | Construction of Flood Mitigation Structure | 122.1326 | 11.8258 | 19800000 | 19799567.39 | 2023 | ALCEL CONSTRUCTION | 5426 | 2022 | 2023-02-13 | 02/18/2022 | 432.61 | 0 | 2022-12-05 |  | 70
2023 | Region II | ISABELA | ILAGAN CITY (CAPITAL) (ISABELA) | P00726687LZ | Construction of Flood Mitigation Structure | 121.9717 | 17.0514 | 49000000 | 48993521.45 | 2023 | DRAGON TWELVE BUILDERS & CONSTRUCTION SUPPLY | 5427 | 2023 | 2023-06-15 | 03/02/2023 | 6478.55 | 0 | 2023-12-08 | 176
2023 | Region IV-B | MARINDUQUE | BOAC (CAPITAL) (MARINDUQUE) | P00742451LZ | Construction of Flood Mitigation Structure | 121.8844 | 13.4294 | 24748000 | 24515665.5 | 2023 | G.T.J. CONSTRUCTION | 5428 | 2023 | 2023-12-01 | 03/28/2023 | 232334.5 | 0 | 2023-12-02 | 1
2022 | Region IV-A | QUEZON | QUEZON (QUEZON) | P00620619LZ | Construction of Flood Mitigation Structure | 122.1335 | 14.0783 | 5390000 | 5281353.03 | 2022 | RAM BUILDERS | 5429 | 2022 | 2022-07-04 | 03/24/2022 | 108646.97 | 0 | 2022-08-19 | 46
2024 | Cordillera Administrative Region | IFUGAO | MAYOYAO (IFUGAO) | P00823323LZ | Construction of Flood Mitigation Structure | 121.5309 | 16.8571 | 53661879.92 | 53675230 | 2024 | DJY CONSTRUCTION | 5430 | 2024 | 2024-08-20 | 02/23/2024 | 0 | 13350.08 | 2024-08-19 |  | 1
2021 | Region II | ISABELA |  | P00525966LZ | Construction of Flood Mitigation Structure | 121.6901 | 16.7297 | 31211040 | 31210839.89 | 2022 | V.B. MANUBAY CONSTRUCTION | 5431 | 2021 | 2022-09-30 | 03/09/2022 | 200.11 | 0 | 2022-10-14 | 14
2023 | Region IV-B | MARINDUQUE | BOAC (CAPITAL) (MARINDUQUE) | P00727177LZ | Construction of Flood Mitigation Structure | 121.8255 | 13.4516 | 48998000 | 48019649.71 | 2023 | ELITE GENERAL CONTRACTOR AND DEVELOPMENT CORP. | 5432 | 2023 | 2023-06-26 | 03/28/2023 | 978350.29 | 0 | 2023-10-11 | 107
2023 | Region IV-B | ROMBLON | SAN ANDRES (ROMBLON) | P00727196LZ | Construction of Flood Mitigation Structure | 122.0472 | 12.5206 | 48999999.71 | 48993380.67 | 2023 | ROLCO CONSTRUCTION & DEVELOPMENT CORPORATION ( FOR / TABLAS MEGA CONSTRUCTION | 5433 | 2023 | 2023-12-04 | 06/13/2023 | 6619.04 | 0 | 2024-02-05 | 63
2022 | Region IV-B | ROMBLON | SAN AGUSTIN (ROMBLON) | P00637086LZ | Construction of Flood Mitigation Structure | 122.1336 | 12.5661 | 24499999.5 | 24481966.53 | 2023 | ULTIMATE BUILDER'S & CONST. SUPPLY | 5434 | 2022 | 2023-05-11 | 04/06/2022 | 18032.97 | 0 | 2023-05-10 |  | 1
2022 | Region II | ISABELA | BENITO SOLIVEN (ISABELA) | P00632800LZ | Construction of Flood Mitigation Structure | 121.9738 | 16.9586 | 4949995.64 | 4949770.78 | 2022 | YZK BUILDERS | 5435 | 2022 | 2022-08-19 | 02/14/2022 | 224.86 | 0 | 2022-08-18 |  | 1
2024 | Region II | CAGAYAN | BAGGAO (CAGAYAN) | P00823338LZ | Construction of Flood Mitigation Structure | 121.8844 | 17.9328 | 48250000 | 48240000 | 2024 | TJMT CONSTRUCTION | 5436 | 2024 | 2024-12-02 | 03/28/2024 | 10000 | 0 | 2024-12-11 | 9
2023 | Region II | ISABELA | QUIRINO (ISABELA) | P00726416LZ | Construction of Flood Mitigation Structure | 121.6904 | 17.1144 | 47929460 | 47563150.1 | 2023 | MAR-DEB CONSTRUCTION & DEVELOPMENT CORP. (FORMERLY: MAR-DEB CONSTRUCTION & DEVELOPMENT) | 5437 | 2023 | 2023-07-31 | 03/13/2023 | 366309.9 | 0 | 2023-10-07 | 68
2023 | Region II | CAGAYAN | ENRILE (CAGAYAN) | P00742301LZ | Construction of Flood Mitigation Structure | 121.693 | 17.5522 | 9900000 | 9788290.17 | 2023 | DOUBLE J1908 CONSTRUCTION | 5438 | 2023 | 2023-12-20 | 04/05/2023 | 111709.83 | 0 | 2023-10-30 |  | 51
2021 | Region IX | ZAMBOANGA DEL SUR |  | P00522144MN | Construction of Flood Mitigation Structure | 122.0478 | 6.9383 | 4900000 | 4875209.31 | 2022 | LL CONSTRUCTION | 5439 | 2021 | 2022-07-04 | 10/28/2021 | 24790.69 | 0 | 2022-03-29 |  | 97
2022 | Cordillera Administrative Region | IFUGAO | ALFONSO LISTA (POTIA) (IFUGAO) | P00637066LZ | Construction of Flood Mitigation Structure | 121.5311 | 16.8612 | 49000000 | 49000000 | 2022 | C-BROS CONSTRUCTION / EGB CONSTRUCTION CORPORATION (FORMERLY: EGB CONSTRUCTION) | 5440 | 2022 | 2022-12-29 | 04/07/2022 | 0 | 0 | 2023-01-08 | 10
2022 | Region II | CAGAYAN | BAGGAO (CAGAYAN) | P00621028LZ | Construction of Flood Mitigation Structure | 121.8256 | 17.9116 | 49000000 | 48984996.36 | 2022 | MEGAY CONSTRUCTION INC. (FORMERLY: MEGAY CONSTRUCTION) | 5441 | 2022 | 2022-09-26 | 02/02/2022 | 15003.64 | 0 | 2022-11-10 | 45
2023 | Region II | ISABELA | QUIRINO (ISABELA) | P00726421LZ | Construction of Flood Mitigation Structure | 121.6939 | 17.1136 | 48250000 | 47864304.56 | 2023 | MAR-DEB CONSTRUCTION & DEVELOPMENT CORP. (FORMERLY: MAR-DEB CONSTRUCTION & DEVELOPMENT) | 5442 | 2023 | 2023-11-23 | 02/27/2023 | 385695.44 | 0 | 2023-11-22 |  | 1
2023 | Region VI | ILOILO | SAN JOAQUIN (ILOILO) | P00721928VS | Construction of Flood Mitigation Structure | 122.1343 | 10.5857 | 24500000 | 24266621.31 | 2024 | A.D. PENDON CONSTRUCTION & SUPPLY, INC. (FORMERLY: ADP CONSTRUCTION & SUPPLY) | 5443 | 2023 | 2024-03-02 | 03/15/2023 | 233378.69 | 0 | 2023-11-01 |  | 122
2022 | Region IV-A | QUEZON | UNISAN (QUEZON) | P00620602LZ | Construction of Flood Mitigation Structure | 121.9744 | 13.841 | 27439935.51 | 27440000 | 2022 | I.A . BOSQUE CONSTRUCTION CORPORATION | 5444 | 2022 | 2022-11-05 | 02/09/2022 | 0 | 64.49 | 2022-11-04 |  | 1
2024 | Region IV-A | QUEZON | GUMACA (QUEZON) | P00820911LZ | Construction of Flood Mitigation Structure | 122.0479 | 13.944 | 19600000 | 19600000 | 2024 | R.T.Y. CONSTRUCTION | 5445 | 2024 | 2024-07-10 | 03/12/2024 | 0 | 0 | 2024-11-05 | 118
2024 | Region II | CAGAYAN | BAGGAO (CAGAYAN) | P00824679LZ | Construction of Flood Mitigation Structure | 121.8853 | 17.9564 | 44100000 | 44095000 | 2024 | TJMT CONSTRUCTION | 5446 | 2024 | 2024-05-28 | 02/11/2024 | 5000 | 0 | 2024-09-19 | 114
2023 | Cordillera Administrative Region | MOUNTAIN PROVINCE | PARACELIS (MOUNTAIN PROVINCE) | P00725658LZ | Construction of Flood Mitigation Structure | 121.5318 | 17.1191 | 62725000 | 62725000 | 2023 | BALINTUGAN CONSTRUCTION | 5447 | 2023 | 2023-09-24 | 06/08/2023 | 0 | 0 | 2024-01-04 | 102
2022 | Region IV-B | MARINDUQUE | BOAC (CAPITAL) (MARINDUQUE) | P00639516LZ | Construction of Flood Mitigation Structure | 121.8271 | 13.4505 | 19598000 | 19598862.07 | 2022 | JBERNARDO CONSTRUCTION AND SUPPLY | 5448 | 2022 | 2022-09-05 | 03/30/2022 | 0 | 862.07 | 2022-09-22 | 17
2024 | Region II | ISABELA | QUIRINO (ISABELA) | P00824891LZ | Construction of Flood Mitigation Structure | 121.6952 | 17.1121 | 96500000 | 96474480.71 | 2024 | JWU CONSTRUCTION AND SUPPLY | 5449 | 2024 | 2024-08-14 | 04/15/2024 | 25519.29 | 0 | 2025-04-12 | 241
2022 | Region IV-B | ROMBLON | ODIONGAN (ROMBLON) | P00631319LZ | Construction of Flood Mitigation Structure | 121.9756 | 12.3953 | 42139999.5 | 41886289.12 | 2022 | SUNWEST, INC. (FORMERLY: SUNWEST CONSTRUCTION & DEVELOPMENT CORPORATION) | 5450 | 2022 | 2022-08-01 | 02/23/2022 | 253710.38 | 0 | 2022-09-20 | 50
2022 | Region VI | ANTIQUE | TIBIAO (ANTIQUE) | P00620297VS | Construction of Flood Mitigation Structure | 122.0487 | 11.3019 | 33775000 | 29685504.72 | 2022 | TIBIAO-ANTIQUE N.K. ENTERPRISE, INC. | 5451 | 2022 | 2022-08-19 | 02/21/2022 | 4089495.28 | 0 | 2022-09-25 | 37
2022 | Region II | CAGAYAN | BAGGAO (CAGAYAN) | P00621021LZ | Construction of Flood Mitigation Structure | 121.8858 | 17.9253 | 29400000 | 29385000 | 2022 | APS CONSTRUCTION | 5452 | 2022 | 2022-08-10 | 02/02/2022 | 15000 | 0 | 2022-10-19 | 70
2020 | Region VI | ANTIQUE |  | P00420351VS | Construction of Revetment | 122.05 | 11.011 | 115800000 | 115799648 | 2022 | IBC INTERNATIONAL BUILDERS CORPORATION | 5453 | 2020 | 2022-08-01 | 11/23/2020 | 352 | 0 | 2022-07-31 |  | 1
2024 | Region II | CAGAYAN | BALLESTEROS (CAGAYAN) | P00824683LZ | Construction of Flood Mitigation Structure | 121.532 | 18.4062 | 49000000 | 48406589.72 | 2024 | JEICCA BUILDERS | 5454 | 2024 | 2024-05-28 | 02/07/2024 | 593410.28 | 0 | 2024-08-11 | 75
2024 | Region IV-A | QUEZON | UNISAN (QUEZON) | P00846087LZ | Construction of Flood Mitigation Structure | 121.9767 | 13.8363 | 48999958.83 | 49500000 | 2024 | YPR GEN. CONTRACTOR AND CONSTRUCTION SUPPLY INC. | 5455 | 2024 | 2024-11-19 | 05/09/2024 | 0 | 500041.17 | 2025-01-02 | 44
2024 | Region II | ISABELA | JONES (ISABELA) | P00848610LZ | Construction of Flood Mitigation Structure | 121.8272 | 16.5381 | 89100000 | 88986939.82 | 2024 | GACUTAN CONSTRUCTION INC. (FORMERLY: GACUTAN CONSTRUCTION) | 5456 | 2024 | 2024-10-25 | 06/06/2024 | 113060.18 | 0 | 2025-03-19 | 145
2023 | Region VI | ILOILO | SAN JOAQUIN (ILOILO) | P00721927VS | Construction of Flood Mitigation Structure | 122.1357 | 10.5856 | 29400000 | 29112116.85 | 2024 | A.D. PENDON CONSTRUCTION & SUPPLY, INC. (FORMERLY: ADP CONSTRUCTION & SUPPLY) | 5457 | 2023 | 2024-02-29 | 03/15/2023 | 287883.15 | 0 | 2023-10-31 |  | 121
2024 | Region II | ISABELA | QUIRINO (ISABELA) | P00824879LZ | Construction of Flood Mitigation Structure | 121.6952 | 17.1103 | 96500000 | 96470259.43 | 2024 | JWU CONSTRUCTION AND SUPPLY / ALGO CONSTRUCTION AND POWER DEVELOPMENT, INC. | 5458 | 2024 | 2024-08-14 | 04/15/2024 | 29740.57 | 0 | 2025-03-18 | 216
2024 | Region IV-B | MARINDUQUE | BOAC (CAPITAL) (MARINDUQUE) | P00820388LZ | Construction of Flood Mitigation Structure | 121.8859 | 13.4261 | 87813000 | 87810398 | 2024 | SQUARE CUBE CONSTRUCTION(FORMERLY SQUARE CUBE TRAD | 5459 | 2024 | 2024-08-20 | 03/15/2024 | 2602 | 0 | 2024-12-17 | 119
2021 | Region VI | ANTIQUE |  | P00420351VS | Construction of Revetment | 122.05 | 11.011 | 115800000 | 115799648 | 2022 | IBC INTERNATIONAL BUILDERS CORPORATION | 5460 | 2021 | 2022-08-01 | 11/23/2020 | 352 | 0 | 2022-07-31 |  | 1
2023 | Region II | CAGAYAN | BALLESTEROS (CAGAYAN) | P00725670LZ | Construction of Flood Mitigation Structure | 121.5346 | 18.4049 | 96500000 | 96500000 | 2023 | TJMT CONSTRUCTION / JEICCA BUILDERS | 5461 | 2023 | 2023-06-13 | 02/06/2023 | 0 | 0 | 2023-10-08 | 117
2022 | Region IV-B | MARINDUQUE | BOAC (CAPITAL) (MARINDUQUE) | P00632924LZ | Construction of Flood Mitigation Structure | 121.8274 | 13.4266 | 5938000 | 5818384.17 | 2022 | TRIPLE JOHNES Q. CONSTRUCTION | 5462 | 2022 | 2022-10-15 | 02/16/2022 | 119615.83 | 0 | 2022-07-11 |  | 96
2023 | Region VI | AKLAN | IBAJAY (AKLAN) | P00721924VS | Construction of Revetment | 122.1382 | 11.8096 | 49000000 | 48999995.52 | 2023 | GREAT PACIFIC BUILDERS AND GEN. CONTRACTOR INC. / C.S. GARCIA CONSTRUCTION CORPORATION (FORMERLY: C.S. GARCIA CONSTRUCTION) | 5463 | 2023 | 2023-10-17 | 03/17/2023 | 4.48 | 0 | 2023-11-07 | 21
2024 | Region II | ISABELA | ALICIA (ISABELA) | P00821212LZ | Construction of Revetment | 121.6955 | 16.7675 | 96499996.27 | 96489406.74 | 2024 | JWU CONSTRUCTION AND SUPPLY | 5464 | 2024 | 2024-08-05 | 06/24/2024 | 10589.53 | 0 | 2025-05-16 | 284
2022 | Region II | CAGAYAN | BAGGAO (CAGAYAN) | P00621032LZ | Construction of Flood Mitigation Structure | 121.8874 | 17.9562 | 14700000 | 14259000 | 2023 | APS CONSTRUCTION | 5465 | 2022 | 2023-05-28 | 02/02/2022 | 441000 | 0 | 2022-08-15 |  | 286
2021 | Region II | ISABELA |  | P00525566LZ | Construction of Flood Mitigation Structure | 121.5347 | 16.6929 | 96500000 | 96500000 | 2022 | ROAD EDGE TRADING & DEVELOPMENT SERVICES | 5466 | 2021 | 2022-09-30 | 12/07/2021 | 0 | 0 | 2022-10-01 | 1
2022 | Region IV-A | QUEZON | UNISAN (QUEZON) | P00620601LZ | Construction of Flood Mitigation Structure | 121.9772 | 13.8356 | 44245961.62 | 44246020 | 2023 | WAYCON BUILDERS AND CONSTRUCTION SUPPLY CORP. (FOR:WAYCON BUILDERS & CONSTRUCTION SUPPLY) | 5467 | 2022 | 2023-01-01 | 02/10/2022 | 0 | 58.38 | 2022-12-31 |  | 1
2022 | Region VI | ANTIQUE | LAUA-AN (ANTIQUE) | P00620001VS | Construction of Flood Mitigation Structure | 122.0518 | 11.0749 | 50180000 | 34571918.59 | 2022 | SUNWEST, INC. (FORMERLY: SUNWEST CONSTRUCTION & DEVELOPMENT CORPORATION) | 5468 | 2022 | 2022-10-14 | 02/18/2022 | 15608081.41 | 0 | 2022-10-18 | 4
2023 | Region IX | ZAMBOANGA DEL NORTE | SIOCON (ZAMBOANGA DEL NORTE) | P00721657MN | Construction of Flood Mitigation Structure | 122.1417 | 7.7133 | 44100000 | 44100000 | 2024 | R.B. MORALLO CONSTRUCTION | 5469 | 2023 | 2024-01-15 | 05/15/2023 | 0 | 0 | 2024-01-19 | 4
2022 | Region IV-A | QUEZON | PADRE BURGOS (QUEZON) | P00631312LZ | Construction of Flood Mitigation Structure | 121.8276 | 13.9478 | 19599729.78 | 19600000 | 2022 | RAPID FOREMOST CONST. CO. / WYDERWAYS BUILDERS AND SUPPLIES | 5470 | 2022 | 2022-07-25 | 02/09/2022 | 0 | 270.22 | 2022-09-25 | 62
2022 | Region II | QUIRINO | MADDELA (QUIRINO) | P00621073LZ | Construction of Flood Mitigation Structure | 121.6971 | 16.352 | 49000000 | 48995706.5 | 2022 | A.P.D. CONSTRUCTION, INC. (FORMERLY: APD CONSTRUCTION) | 5471 | 2022 | 2022-11-18 | 04/01/2022 | 4293.5 | 0 | 2023-01-22 | 65
2022 | Region II | CAGAYAN | BAGGAO (CAGAYAN) | P00621031LZ | Construction of Flood Mitigation Structure | 121.8875 | 17.9554 | 24500000 | 24500000 | 2022 | TJMT CONSTRUCTION | 5472 | 2022 | 2022-10-24 | 03/30/2022 | 0 | 0 | 2022-12-31 | 68
2021 | Region IV-B | ROMBLON |  | P00561446LZ | Construction of Flood Mitigation Structure | 121.5347 | 13.075 | 135098806 | 86823658.97 | 2022 | LEGACY CONSTRUCTION CORPORATION (FORMERLY: LEGACY CONSTRUCTION) | 5473 | 2021 | 2022-12-22 | 03/24/2022 | 48275147.03 | 0 | 2022-12-21 |  | 1
2022 | Region IV-B | ROMBLON | ODIONGAN (ROMBLON) | P00639383LZ | Construction of Flood Mitigation Structure | 121.9809 | 12.3863 | 106149973.3 | 106147622.3 | 2023 | LEGACY CONSTRUCTION CORPORATION (FORMERLY: LEGACY CONSTRUCTION) | 5474 | 2022 | 2023-06-07 | 05/24/2022 | 2351 | 0 | 2023-06-06 |  | 1
2022 | Region VI | ANTIQUE | LAUA-AN (ANTIQUE) | P00630197VS | Rehabilitation / Major Repair of Flood Control Structure | 122.0518 | 11.0749 | 39200000 | 39200000 | 2022 | F & J GENERAL CONSTRUCTION AND SUPPLY CORPORATION | 5475 | 2022 | 2022-12-05 | 02/07/2022 | 0 | 0 | 2022-10-18 |  | 48
2024 | Region IV-B | MARINDUQUE | MOGPOG (MARINDUQUE) | P00821362LZ | Construction of Flood Mitigation Structure | 121.8878 | 13.4755 | 96498000 | 96495098.79 | 2025 | SUNWEST, INC. (FORMERLY: SUNWEST CONSTRUCTION & DEVELOPMENT CORPORATION) | 5476 | 2024 | 2025-05-01 | 02/19/2024 | 2901.21 | 0 | 2025-04-30 |  | 1
2022 | Region II | CAGAYAN | SANTA ANA (CAGAYAN) | P00631104LZ | Construction of Drainage Structure | 122.1424 | 18.4574 | 42135100 | 42115100 | 2023 | MEGAY CONSTRUCTION INC. (FORMERLY: MEGAY CONSTRUCTION) / TJMT CONSTRUCTION | 5477 | 2022 | 2023-05-08 | 04/01/2022 | 20000 | 0 | 2023-03-09 |  | 60
2021 | Region III | AURORA |  | P00526393LZ | Construction of Flood Mitigation Structure | 121.5352 | 15.7646 | 49000000 | 49000000 | 2022 | IRC CONSTRUCTION & SUPPLIES | 5478 | 2021 | 2022-08-31 | 07/12/2021 | 0 | 0 | 2022-08-08 |  | 23
2023 | Region II | ISABELA | TUMAUINI (ISABELA) | P00726125LZ | Construction of Flood Mitigation Structure | 121.888 | 17.3323 | 19600000 | 19594522.13 | 2023 | DRAGON TWELVE BUILDERS & CONSTRUCTION SUPPLY | 5479 | 2023 | 2023-05-22 | 03/02/2023 | 5477.87 | 0 | 2023-10-11 | 142
2022 | Region II | CAGAYAN | TUGUEGARAO CITY (CAPITAL) (CAGAYAN) | P00621242LZ | Construction of Flood Mitigation Structure | 121.6972 | 17.6258 | 24125000 | 24125000 | 2023 | JTM CONSTRUCTION | 5480 | 2022 | 2023-07-03 | 03/28/2022 | 0 | 0 | 2023-06-16 |  | 17
2023 | Region IV-B | MARINDUQUE | SANTA CRUZ (MARINDUQUE) | P00740437LZ | Construction of Revetment | 122.0537 | 13.476 | 192999999.7 | 192998641 | 2023 | HGG BUILDERS & SUPPLY | 5481 | 2023 | 2023-12-20 | 04/13/2023 | 1358.7 | 0 | 2024-08-06 | 230
2024 | Region VI | ANTIQUE | PATNONGON (ANTIQUE) | P00834990VS | Construction of Flood Mitigation Structure | 121.9814 | 10.9148 | 14850000 | 14812420.01 | 2024 | TIBIAO-ANTIQUE N.K. ENTERPRISE, INC. | 5482 | 2024 | 2024-08-27 | 03/06/2024 | 37579.99 | 0 | 2024-08-29 | 2
2023 | Region IX | ZAMBOANGA DEL NORTE | SIRAWAI (ZAMBOANGA DEL NORTE) | P00721363MN | Construction of Flood Mitigation Structure | 122.1482 | 7.5954 | 39200000 | 39200000 | 2023 | LONG ISLAND BUILDERS & CONSTRUCTION | 5483 | 2023 | 2023-10-06 | 02/18/2023 | 0 | 0 | 2023-10-05 |  | 1
2022 | Region III | AURORA | BALER (CAPITAL) (AURORA) | P00620498LZ | Construction of Flood Mitigation Structure | 121.5363 | 15.765 | 48249095.57 | 48218372.02 | 2023 | IM CONSTRUCTION CORPORATION | 5484 | 2022 | 2023-08-08 | 08/15/2022 | 30723.55 | 0 | 2023-08-07 |  | 1
2022 | Region II | ISABELA | REINA MERCEDES (ISABELA) | P00632801LZ | Construction of Drainage Structure | 121.8284 | 16.9846 | 4949987.53 | 4879992.14 | 2022 | DANYSONS CONSTRUCTION AND DEVELOPMENT CORPORATION (FORMERLY: DANYSONS CONSTRUCTION) | 5485 | 2022 | 2022-08-08 | 02/14/2022 | 69995.39 | 0 | 2022-09-03 | 26
2023 | Region II | CAGAYAN | BAGGAO (CAGAYAN) | P00726111LZ | Construction of Flood Mitigation Structure | 121.8881 | 17.9553 | 49000000 | 48979917.36 | 2023 | DECA CONSTRUCTION / TJMT CONSTRUCTION | 5486 | 2023 | 2023-06-13 | 02/14/2023 | 20082.64 | 0 | 2023-11-02 | 142
2024 | Region II | ISABELA | ALICIA (ISABELA) | P00821211LZ | Construction of Revetment | 121.6974 | 16.7693 | 96499993.83 | 96489676.01 | 2024 | JWU CONSTRUCTION AND SUPPLY | 5487 | 2024 | 2024-08-05 | 06/24/2024 | 10317.82 | 0 | 2025-05-16 | 284
2023 | Region II | ISABELA | SAN MARIANO (ISABELA) | P00742307LZ | Construction of Flood Mitigation Structure | 122.0542 | 16.9731 | 4949989.76 | 4900708 | 2023 | CAMBERWELL CONSTRUCTION AND SUPPLIES | 5488 | 2023 | 2023-07-10 | 04/25/2023 | 49281.76 | 0 | 2023-07-27 | 17
2023 | Region IX | ZAMBOANGA DEL SUR | ZAMBOANGA CITY (ZAMBOANGA DEL SUR) | P00732472MN | Construction of Flood Mitigation Structure | 122.0547 | 6.9275 | 4900000 | 4850980.27 | 2023 | LONG ISLAND BUILDERS & CONSTRUCTION | 5489 | 2023 | 2023-09-13 | 03/23/2023 | 49019.73 | 0 | 2023-09-12 |  | 1
2023 | Region IX | ZAMBOANGA DEL SUR | ZAMBOANGA CITY (ZAMBOANGA DEL SUR) | P00732470MN | Construction of Drainage Structure | 122.0592 | 6.9147 | 4829317.26 | 4826250.44 | 2023 | MEGABALTZ CONSTRUCTION | 5490 | 2023 | 2023-08-17 | 03/23/2023 | 3066.82 | 0 | 2023-09-23 | 37
2024 | Region II | ISABELA | SAN MARIANO (ISABELA) | P00821566LZ | Construction of Flood Mitigation Structure | 122.0594 | 16.976 | 48999997.81 | 48965415.32 | 2024 | CAMBERWELL CONSTRUCTION AND SUPPLIES | 5491 | 2024 | 2024-05-06 | 03/18/2024 | 34582.49 | 0 | 2024-10-19 | 166
2022 | Region VI | ANTIQUE | LAUA-AN (ANTIQUE) | P00630186VS | Rehabilitation / Major Repair of Flood Control Structure | 122.0605 | 11.1159 | 125450000 | 125450000 | 2023 | F. GURREA CONSTRUCTION, INCORPORATED | 5492 | 2022 | 2023-08-16 | 02/21/2022 | 0 | 0 | 2023-06-27 |  | 50
2022 | Region VI | ANTIQUE | BUGASONG (ANTIQUE) | P00620077VS | Construction of Flood Mitigation Structure | 122.0647 | 11.0059 | 49000000 | 49000000 | 2022 | F & J GENERAL CONSTRUCTION AND SUPPLY CORPORATION | 5493 | 2022 | 2022-12-12 | 02/07/2022 | 0 | 0 | 2022-10-29 |  | 44
2023 | Region VI | ILOILO | SAN JOAQUIN (ILOILO) | P00733715VS | Construction of Flood Mitigation Structure | 122.0648 | 10.5226 | 9900000 | 9879364.55 | 2023 | DEACONS TEMPLE CONSTRUCTION & SUPPLY | 5494 | 2023 | 2023-12-02 | 05/30/2023 | 20635.45 | 0 | 2023-10-18 |  | 45
2023 | Region IV-B | ROMBLON | CALATRAVA (ROMBLON) | P00726277LZ | Construction of Flood Mitigation Structure | 122.0658 | 12.6178 | 48999999.54 | 48997970.32 | 2023 | R.G. FLORENTINO CONST. & TRADING INC. | 5495 | 2023 | 2023-08-15 | 02/22/2023 | 2029.22 | 0 | 2023-10-17 | 63
2024 | Region IV-B | DAVAO DEL SUR | SANTA CRUZ (DAVAO DEL SUR) | P00821363LZ | Construction of Flood Mitigation Structure | 122.0677 | 13.4548 | 96498000 | 96495228.29 | 2025 | SUNWEST, INC. (FORMERLY: SUNWEST CONSTRUCTION & DEVELOPMENT CORPORATION) | 5496 | 2024 | 2025-04-20 | 02/19/2024 | 2771.71 | 0 | 2025-04-19 |  | 1
2022 | Region IV-B | MARINDUQUE | SANTA CRUZ (MARINDUQUE) | P00620902LZ | Construction of Flood Mitigation Structure | 122.0685 | 13.4559 | 84879400 | 84891244.45 | 2023 | SARGASSO CONSTRUCTION & DEVELOPMENT CORP. | 5497 | 2022 | 2023-08-24 | 02/23/2022 | 0 | 11844.45 | 2023-08-24 | 0
2022 | Region VI | ILOILO | SAN JOAQUIN (ILOILO) | P00620428VS | Construction of Flood Mitigation Structure | 122.07 | 10.5725 | 4900000 | 4879197.7 | 2022 | CHAMPION BUILDERS AND SUPPLY | 5498 | 2022 | 2022-10-17 | 05/23/2022 | 20802.3 | 0 | 2022-10-16 |  | 1
2022 | Region IV-B | MARINDUQUE | TORRIJOS (MARINDUQUE) | P00637806LZ | Construction of Flood Mitigation Structure | 122.0703 | 13.3149 | 19798000 | 19797898.73 | 2022 | G.T.J. CONSTRUCTION | 5499 | 2022 | 2022-10-30 | 03/30/2022 | 101.27 | 0 | 2022-10-29 |  | 1
2021 | Region II | ISABELA |  | P00561673LZ | Construction of Flood Mitigation Structure | 122.0724 | 16.9532 | 29699995.31 | 29697068.51 | 2022 | YZK BUILDERS | 5500 | 2021 | 2022-07-25 | 01/19/2022 | 2926.8 | 0 | 2022-07-28 | 3
2023 | Region IV-B | ROMBLON | ALCANTARA (ROMBLON) | P00727193LZ | Construction of Flood Mitigation Structure | 122.0739 | 12.3017 | 48999999.67 | 48993745.79 | 2023 | ULTIMATE BUILDER'S & CONST. SUPPLY | 5501 | 2023 | 2023-09-26 | 03/24/2023 | 6253.88 | 0 | 2023-11-16 | 51
2022 | Region IV-B | ROMBLON | ALCANTARA (ROMBLON) | P00621489LZ | Construction of Flood Mitigation Structure | 122.0739 | 12.3011 | 24499999.5 | 24361307.16 | 2022 | ULTIMATE BUILDER'S & CONST. SUPPLY | 5502 | 2022 | 2022-10-10 | 04/06/2022 | 138692.34 | 0 | 2022-10-24 | 14
2022 | Region VI | ANTIQUE | CULASI (ANTIQUE) | P00620295VS | Construction of Flood Mitigation Structure | 122.0748 | 11.4127 | 34300000 | 34300000 | 2022 | TIBIAO-ANTIQUE N.K. ENTERPRISE, INC. | 5503 | 2022 | 2022-08-01 | 02/07/2022 | 0 | 0 | 2022-08-27 | 26
2023 | Region IX | ZAMBOANGA DEL NORTE | SIBUCO (ZAMBOANGA DEL NORTE) | P00721361MN | Construction of Flood Mitigation Structure | 122.0753 | 7.4618 | 44100000 | 44100000 | 2023 | LONG ISLAND BUILDERS & CONSTRUCTION | 5504 | 2023 | 2023-07-10 | 02/18/2023 | 0 | 0 | 2023-10-01 | 83
2023 | Region II | ISABELA | SAN MARIANO (ISABELA) | P00726694LZ | Construction of Flood Mitigation Structure | 122.0756 | 16.956 | 48999999.29 | 48265637.8 | 2023 | YZK BUILDERS | 5505 | 2023 | 2023-06-05 | 03/08/2023 | 734361.49 | 0 | 2023-10-11 | 128
2024 | Region VI | ANTIQUE | SAN REMIGIO (ANTIQUE) | P00820150VS | Construction of Flood Mitigation Structure | 122.0758 | 10.8324 | 49000000 | 49000000 | 2024 | F & J GENERAL CONSTRUCTION AND SUPPLY CORPORATION | 5506 | 2024 | 2024-09-03 | 02/07/2024 | 0 | 0 | 2024-10-05 | 32
2022 | Region VI | ILOILO | BAROTAC NUEVO (ILOILO) | P00620247VS | Construction of Flood Mitigation Structure | 122.0763 | 10.9186 | 19600000 | 19011837.7 | 2022 | STRONGLANE BUILDERS AND TRADING CORPORATION (FORMERLY: STRONGLANE CONSTRUCTION & TRADING) | 5507 | 2022 | 2022-08-24 | 03/11/2022 | 588162.3 | 0 | 2022-08-23 |  | 1
2023 | Region IX | ZAMBOANGA DEL SUR | ZAMBOANGA CITY (ZAMBOANGA DEL SUR) | P00732471MN | Construction of Flood Mitigation Structure | 122.0764 | 6.9386 | 10890000 | 10884616.96 | 2023 | RME CONSTRUCTION AND ENTERPRISES | 5508 | 2023 | 2023-09-25 | 05/05/2023 | 5383.04 | 0 | 2023-11-04 | 40
2024 | Region IX | ZAMBOANGA DEL SUR | ZAMBOANGA CITY (ZAMBOANGA DEL SUR) | P00835858MN | Construction of Flood Mitigation Structure | 122.0765 | 6.9367 | 17640000 | 17633690.21 | 2024 | RME CONSTRUCTION AND ENTERPRISES | 5509 | 2024 | 2024-10-21 | 03/22/2024 | 6309.79 | 0 | 2024-11-08 | 18
2024 | Region III | AURORA | CASIGURAN (AURORA) | P00845956LZ | Construction of Flood Mitigation Structure | 122.0766 | 16.2479 | 49500000 | 49500000 | 2025 | ALEXI LOUISSE CONSTRUCTION & GENERAL MERCHANDISE / BAMM BUSINESS VENTURES INC. | 5510 | 2024 | 2025-02-02 | 04/15/2024 | 0 | 0 | 2025-02-01 |  | 1
2018 | Region IX | ZAMBOANGA DEL SUR |  | P00223199MN | Construction of Flood Mitigation Structure | 122.079 | 6.9214 | 202409605.5 | 198360500 | 2023 | SUNWEST, INC. (FORMERLY: SUNWEST CONSTRUCTION & DEVELOPMENT CORPORATION) / BENDIMIL CONSTRUCTION & DEVELOPMENT CORP. | 5511 | 2018 | 2023-11-19 | 10/11/2018 | 4049105.5 | 0 | 2023-11-18 |  | 1
2022 | Region IV-B | MARINDUQUE | TORRIJOS (MARINDUQUE) | P00637807LZ | Construction of Flood Mitigation Structure | 122.0817 | 13.328 | 14847999.99 | 14563237.53 | 2022 | TRIPLE JOHNES Q. CONSTRUCTION | 5512 | 2022 | 2022-12-02 | 03/30/2022 | 284762.46 | 0 | 2022-12-02 | 0
2022 | Region IV-B | ROMBLON | SANTA MARIA (IMELDA) (ROMBLON) | P00620263LZ | Construction of Flood Mitigation Structure | 122.0819 | 12.3775 | 96017499.33 | 96013026.19 | 2023 | LEGACY CONSTRUCTION CORPORATION (FORMERLY: LEGACY CONSTRUCTION) | 5513 | 2022 | 2023-03-29 | 06/03/2022 | 4473.14 | 0 | 2023-05-06 | 38
2022 | Region VI | ANTIQUE | BUGASONG (ANTIQUE) | P00620076VS | Construction of Flood Mitigation Structure | 122.0821 | 11.0001 | 49000000 | 49000000 | 2023 | F & J GENERAL CONSTRUCTION AND SUPPLY CORPORATION | 5514 | 2022 | 2023-11-21 | 03/24/2022 | 0 | 0 | 2023-03-02 |  | 264
2022 | Region VI | ANTIQUE | LAUA-AN (ANTIQUE) | P00630196VS | Construction of Flood Mitigation Structure | 122.0865 | 11.0739 | 49000000 | 44467535.89 | 2022 | TIBIAO-ANTIQUE N.K. ENTERPRISE, INC. | 5515 | 2022 | 2022-09-12 | 02/07/2022 | 4532464.11 | 0 | 2022-09-16 | 4
2023 | Region IV-B | MARINDUQUE | TORRIJOS (MARINDUQUE) | P00736050LZ | Construction of Revetment | 122.0878 | 13.3175 | 192999999.1 | 192997379.6 | 2023 | HGG BUILDERS & SUPPLY | 5516 | 2023 | 2023-12-15 | 02/11/2023 | 2619.5 | 0 | 2024-02-04 | 51
2024 | Region IV-B | MARINDUQUE | TORRIJOS (MARINDUQUE) | P00839654LZ | Construction of Flood Mitigation Structure | 122.0878 | 13.3239 | 6928000 | 6927884.53 | 2024 | SAMARAH CONSTRUCTION AND SUPPLY | 5517 | 2024 | 2024-07-05 | 01/30/2024 | 115.47 | 0 | 2024-04-25 |  | 71
2024 | Region IV-B | MARINDUQUE | BOAC (CAPITAL) (MARINDUQUE) | P00846097LZ | Construction of Flood Mitigation Structure | 122.0878 | 13.3239 | 4948000 | 4947817.66 | 2024 | JEDIDIAH CONSTRUCTION | 5518 | 2024 | 2024-04-12 | 01/30/2024 | 182.34 | 0 | 2024-04-11 |  | 1
2023 | Region IV-B | MARINDUQUE | TORRIJOS (MARINDUQUE) | P00740418LZ | Construction of Revetment | 122.0905 | 13.3233 | 241249999.6 | 241246840.5 | 2023 | HGG BUILDERS & SUPPLY | 5519 | 2023 | 2023-12-15 | 04/13/2023 | 3159.1 | 0 | 2024-04-05 | 112
2023 | Region IX | ZAMBOANGA DEL SUR | ZAMBOANGA CITY (ZAMBOANGA DEL SUR) | P00732474MN | Construction of Drainage Structure | 122.0905 | 6.9196 | 9800000 | 9899967.65 | 2023 | HMI ENTERPRISES | 5520 | 2023 | 2023-11-24 | 04/24/2023 | 0 | 99967.65 | 2024-02-28 | 96
2022 | Region IX | ZAMBOANGA DEL SUR | ZAMBOANGA CITY (ZAMBOANGA DEL SUR) | P00620260MN | Construction of Flood Mitigation Structure | 122.0917 | 6.9244 | 19517852.63 | 19595510.37 | 2023 | AEJ HARDWARE CONSTRUCTION & ENTERPRISES | 5521 | 2022 | 2023-03-17 | 03/23/2022 | 0 | 77657.74 | 2023-03-16 |  | 1
2024 | Region IV-A | QUEZON | GUMACA (QUEZON) | P00820291LZ | Construction of Flood Mitigation Structure | 122.0927 | 13.9166 | 67550000 | 67550000 | 2024 | ADAD ENGINEERING SERVICES & SUPPLY | 5522 | 2024 | 2024-07-10 | 03/13/2024 | 0 | 0 | 2025-01-05 | 179
2022 | Region VI | AKLAN | NABAS (AKLAN) | P00620008VS | Construction of Revetment | 122.0928 | 11.8207 | 54839020 | 53743402.6 | 2023 | ALPHA & OMEGA GEN. CONTRACTOR & DEVELOPMENT CORP. | 5523 | 2022 | 2023-05-02 | 02/21/2022 | 1095617.4 | 0 | 2022-12-24 |  | 129
2024 | Region VI | ANTIQUE | SEBASTE (ANTIQUE) | P00820152VS | Construction of Slope Protection Structure | 122.093 | 11.5893 | 49000000 | 45570000 | 2024 | TIBIAO-ANTIQUE N.K. ENTERPRISE, INC. | 5524 | 2024 | 2024-11-05 | 02/07/2024 | 3430000 | 0 | 2024-10-05 |  | 31
2023 | Region IV-A | QUEZON | GUMACA (QUEZON) | P00727169LZ | Construction of Flood Mitigation Structure | 122.0931 | 13.9187 | 44100000 | 44100000 | 2023 | ADAD ENGINEERING SERVICES & SUPPLY | 5525 | 2023 | 2023-09-13 | 03/09/2023 | 0 | 0 | 2023-12-02 | 80
2022 | Region IV-A | QUEZON | GUMACA (QUEZON) | P00620209LZ | Construction of Flood Mitigation Structure | 122.0932 | 13.9187 | 92839755 | 92839755 | 2022 | ADAD ENGINEERING SERVICES & SUPPLY / R.T.Y. CONSTRUCTION | 5526 | 2022 | 2022-09-19 | 03/02/2022 | 0 | 0 | 2022-11-25 | 67
2022 | Region IV-A | QUEZON | GUMACA (QUEZON) | P00620608LZ | Construction of Flood Mitigation Structure | 122.0932 | 13.9187 | 19600000 | 19600000 | 2022 | ADAD ENGINEERING SERVICES & SUPPLY | 5527 | 2022 | 2022-07-11 | 02/16/2022 | 0 | 0 | 2022-08-13 | 33
2023 | Region IV-A | QUEZON | GUMACA (QUEZON) | P00726939LZ | Construction of Flood Mitigation Structure | 122.0935 | 13.92 | 82025000 | 82025000 | 2023 | R.T.Y. CONSTRUCTION | 5528 | 2023 | 2023-09-13 | 03/24/2023 | 0 | 0 | 2023-12-17 | 95
2022 | Region IX | ZAMBOANGA DEL SUR | ZAMBOANGA CITY (ZAMBOANGA DEL SUR) | P00631079MN | Construction of Drainage Structure | 122.0941 | 6.9433 | 4736646.36 | 4948757.89 | 2023 | SHERKAD CONSTRUCTION | 5529 | 2022 | 2023-01-22 | 03/24/2022 | 0 | 212111.53 | 2023-01-21 |  | 1
2022 | Region IX | ZAMBOANGA DEL SUR | ZAMBOANGA CITY (ZAMBOANGA DEL SUR) | P00631077MN | Construction of Drainage Structure | 122.0942 | 6.9319 | 4457665.7 | 4801870.31 | 2022 | TERRAINSHAPER CONSTRUCTION AND ENTERPRISES | 5530 | 2022 | 2022-10-19 | 03/23/2022 | 0 | 344204.61 | 2022-10-18 |  | 1
2022 | Region IV-B | ROMBLON | BANTON (ROMBLON) | P00631316LZ | Construction of Slope Protection Structure | 122.0958 | 12.9428 | 36259999.04 | 36258916.06 | 2022 | SUNWEST, INC. (FORMERLY: SUNWEST CONSTRUCTION & DEVELOPMENT CORPORATION) | 5531 | 2022 | 2022-10-25 | 03/10/2022 | 1082.98 | 0 | 2022-10-15 |  | 10
2024 | Region VI | ANTIQUE | SAN REMIGIO (ANTIQUE) | P00820149VS | Construction of Flood Mitigation Structure | 122.0966 | 10.8479 | 29400000 | 29400000 | 2024 | GATEWAY 21-25 CONSTRUCTION CORP. (FORMERLY E.D. DE | 5532 | 2024 | 2024-07-15 | 02/07/2024 | 0 | 0 | 2024-09-07 | 54
2022 | Region III | AURORA | DILASAG (AURORA) | P00631161LZ | Construction of Flood Mitigation Structure | 122.0968 | 16.316 | 49000000 | 49000000 | 2023 | ZF CONSTRUCTION | 5533 | 2022 | 2023-07-13 | 03/14/2022 | 0 | 0 | 2023-07-12 |  | 1
2024 | Region VI | ANTIQUE | SEBASTE (ANTIQUE) | P00820151VS | Construction of Slope Protection Structure | 122.0969 | 11.6226 | 49000000 | 45570000 | 2025 | TIBIAO-ANTIQUE N.K. ENTERPRISE, INC. | 5534 | 2024 | 2025-01-05 | 02/07/2024 | 3430000 | 0 | 2024-10-10 |  | 87
2022 | Region IV-A | QUEZON | PITOGO (QUEZON) | P00631311LZ | Construction of Flood Mitigation Structure | 122.0993 | 13.8176 | 9799946.19 | 9800000 | 2022 | MRRM TRADING & CONSTRUCTION | 5535 | 2022 | 2022-07-25 | 02/10/2022 | 0 | 53.81 | 2022-08-07 | 13
2022 | Region IV-B | ROMBLON | SAN AGUSTIN (ROMBLON) | P00621490LZ | Construction of Flood Mitigation Structure | 122.0994 | 12.465 | 24499999.5 | 24499249.85 | 2022 | EMQ DESIGN & CONSTRUCTION | 5536 | 2022 | 2022-10-10 | 04/12/2022 | 749.65 | 0 | 2022-10-30 | 20
2024 | Region IV-B | SURIGAO DEL SUR | SAN AGUSTIN (SURIGAO DEL SUR) | P00823491LZ | Construction of Flood Mitigation Structure | 122.1 | 12.465 | 48249999.54 | 48249972.86 | 2024 | EMQ DESIGN & CONSTRUCTION | 5537 | 2024 | 2024-09-20 | 04/12/2024 | 26.68 | 0 | 2024-12-05 | 76
2023 | Region IV-B | MARINDUQUE | TORRIJOS (MARINDUQUE) | P00740419LZ | Construction of Revetment | 122.1005 | 13.3265 | 241249999.8 | 241247022.1 | 2023 | HGG BUILDERS & SUPPLY | 5538 | 2023 | 2023-12-15 | 04/13/2023 | 2977.7 | 0 | 2024-04-05 | 112
2022 | Region IX | ZAMBOANGA DEL SUR | ZAMBOANGA CITY (ZAMBOANGA DEL SUR) | P00631080MN | Construction of Flood Mitigation Structure | 122.1032 | 6.9701 | 4948347.03 | 4937068.47 | 2023 | AYESHIA GENERAL TRADING CONSTRUCTION AND MAINTENANCE | 5539 | 2022 | 2023-02-02 | 03/24/2022 | 11278.56 | 0 | 2023-02-01 |  | 1
2024 | Region IV-B | SURIGAO DEL SUR | SAN AGUSTIN (SURIGAO DEL SUR) | P00845835LZ | Construction of Flood Mitigation Structure | 122.1044 | 12.4861 | 98999999.93 | 99000000 | 2024 | SUNWEST, INC. (FORMERLY: SUNWEST CONSTRUCTION & DEVELOPMENT CORPORATION) | 5540 | 2024 | 2024-11-15 | 03/13/2024 | 0 | 0.07 | 2025-02-14 | 91
2022 | Region IV-A | QUEZON | PITOGO (QUEZON) | P00639381LZ | Construction of Flood Mitigation Structure | 122.1051 | 13.833 | 96499945.79 | 76235189.93 | 2023 | ST. GERRARD CONSTRUCTION GEN. CONTRACTOR & DEVELOPMENT CORP. (FORMERLY:ST. GERRARD CONSTRUCTION) | 5541 | 2022 | 2023-05-26 | 06/02/2022 | 20264755.86 | 0 | 2023-05-26 | 0
2022 | Region IV-B | ROMBLON | SAN AGUSTIN (ROMBLON) | P00639385LZ | Construction of Slope Protection Structure | 122.1053 | 12.4636 | 93604999.5 | 93605000 | 2023 | SUNWEST, INC. (FORMERLY: SUNWEST CONSTRUCTION & DEVELOPMENT CORPORATION) | 5542 | 2022 | 2023-06-17 | 07/18/2022 | 0 | 0.5 | 2023-08-15 | 59
2024 | Region IV-B | SURIGAO DEL SUR | SAN AGUSTIN (SURIGAO DEL SUR) | P00823581LZ | Construction of Flood Mitigation Structure | 122.1064 | 12.4635 | 139924999.4 | 139925000 | 2024 | SUNWEST, INC. (FORMERLY: SUNWEST CONSTRUCTION & DEVELOPMENT CORPORATION) | 5543 | 2024 | 2024-11-15 | 04/15/2024 | 0 | 0.6 | 2025-04-08 | 144
2022 | Region VI | ANTIQUE | HAMTIC (ANTIQUE) | P00630195VS | Construction of Flood Mitigation Structure | 121.9819 | 10.6987 | 28950000 | 28945395.97 | 2023 | IBC INTERNATIONAL BUILDERS CORPORATION | 5544 | 2022 | 2023-02-11 | 02/21/2022 | 4604.03 | 0 | 2023-02-10 |  | 1
2022 | Region II | CAGAYAN | ABULUG (CAGAYAN) | P00639461LZ | Construction of Flood Mitigation Structure | 121.4273 | 18.395 | 44100000 | 44100000 | 2022 | E.V. INTERIOR CONSTRUCTION | 5545 | 2022 | 2022-09-30 | 03/29/2022 | 0 | 0 | 2022-11-03 | 34
2024 | Region IV-B | MARINDUQUE | BOAC (CAPITAL) (MARINDUQUE) | P00821601LZ | Construction of Flood Mitigation Structure | 121.8287 | 13.388 | 48998000 | 48995870 | 2024 | SQUARE CUBE CONSTRUCTION(FORMERLY SQUARE CUBE TRAD | 5546 | 2024 | 2024-08-20 | 03/15/2024 | 2130 | 0 | 2024-09-28 | 39
2023 | Region IV-B | MARINDUQUE | BOAC (CAPITAL) (MARINDUQUE) | P00742452LZ | Construction of Flood Mitigation Structure | 121.8883 | 13.413 | 9898000 | 9897013.25 | 2023 | G.T.J. CONSTRUCTION | 5547 | 2023 | 2023-08-04 | 03/28/2023 | 986.75 | 0 | 2023-08-06 | 2
2024 | Region II | ISABELA | JONES (ISABELA) | P00843239LZ | Construction of Flood Mitigation Structure | 121.6974 | 16.545 | 96500000 | 96500000 | 2024 | V.B. MANUBAY CONSTRUCTION / VBM CONSTRUCTION CORP. | 5548 | 2024 | 2024-12-07 | 06/17/2024 | 0 | 0 | 2025-06-22 | 197
2022 | Region VI | AKLAN | IBAJAY (AKLAN) | P00632028VS | Construction of Flood Mitigation Structure | 122.1487 | 11.8095 | 14850000 | 14845000.06 | 2023 | EC BUILDERS | 5549 | 2022 | 2023-02-13 | 03/24/2022 | 4999.94 | 0 | 2022-09-27 |  | 139
2023 | Region IX | ZAMBOANGA DEL SUR | ZAMBOANGA CITY (ZAMBOANGA DEL SUR) | P00721356MN | Construction of Flood Mitigation Structure | 121.9833 | 6.9549 | 39200000 | 39189522.49 | 2023 | BENRAM CONSTRUCTION / ALLROCK CONSTRUCTION | 5550 | 2023 | 2023-10-23 | 04/21/2023 | 10477.51 | 0 | 2023-12-27 | 65
2024 | Region II | ISABELA | QUIRINO (ISABELA) | P00821565LZ | Construction of Flood Mitigation Structure | 121.6976 | 17.1343 | 49000000 | 48996742.35 | 2024 | JWU CONSTRUCTION AND SUPPLY | 5551 | 2024 | 2024-06-24 | 02/12/2024 | 3257.65 | 0 | 2024-09-24 | 92
2022 | Region III | AURORA | DINALUNGAN (AURORA) | P00631167LZ | Construction of Flood Mitigation Structure | 121.8884 | 16.1267 | 14700000 | 13966665.04 | 2022 | ZF CONSTRUCTION | 5552 | 2022 | 2022-10-30 | 03/14/2022 | 733334.96 | 0 | 2022-07-09 |  | 113
2022 | Region II | CAGAYAN | ABULUG (CAGAYAN) | P00621037LZ | Construction of Flood Mitigation Structure | 121.4279 | 18.3401 | 49000000 | 49000000 | 2023 | JC PALOMO CONSTRUCTION & CONSTRUCTION SUPPLY / C.T. LEONCIO CONSTRUCTION & TRADING | 5553 | 2022 | 2023-01-09 | 02/14/2022 | 0 | 0 | 2022-12-08 |  | 32
2021 | Region III | AURORA |  | P00561684LZ | Construction of Flood Mitigation Structure | 121.5373 | 15.5784 | 14850000 | 14850000 | 2022 | RADIANCE TRADERS & BUILDERS | 5554 | 2021 | 2022-12-12 | 01/11/2022 | 0 | 0 | 2022-05-19 |  | 207
2022 | Region VI | AKLAN | IBAJAY (AKLAN) | P00620271VS | Construction of Revetment | 122.1597 | 11.8068 | 86850000 | 86849994.7 | 2023 | SOLID MERCHANDISING / ALPHA & OMEGA GEN. CONTRACTOR & DEVELOPMENT CORP. | 5555 | 2022 | 2023-02-15 | 02/18/2022 | 5.3 | 0 | 2023-02-23 | 8
2023 | Region II | ISABELA | REINA MERCEDES (ISABELA) | P00726689LZ | Construction of Flood Mitigation Structure | 121.8288 | 16.9833 | 43776312.05 | 43457710.95 | 2023 | DANYSONS CONSTRUCTION AND DEVELOPMENT CORPORATION (FORMERLY: DANYSONS CONSTRUCTION) | 5556 | 2023 | 2023-06-08 | 03/08/2023 | 318601.1 | 0 | 2023-10-15 | 129
2021 | Region IV-B | ROMBLON |  | P00561577LZ | Construction of Flood Mitigation Structure | 121.9839 | 12.4053 | 48999999.5 | 49000000 | 2022 | ROLCO CONSTRUCTION & DEVELOPMENT CORPORATION ( FOR | 5557 | 2021 | 2022-10-03 | 08/06/2021 | 0 | 0.5 | 2022-06-13 |  | 112
2022 | Region III | AURORA | SAN LUIS (AURORA) | P00631159LZ | Construction of Flood Mitigation Structure | 121.539 | 15.7418 | 29400000 | 27929140.36 | 2023 | RADIANCE TRADERS & BUILDERS | 5558 | 2022 | 2023-02-01 | 03/01/2022 | 1470859.64 | 0 | 2022-09-01 |  | 153
2023 | Region VI | AKLAN | IBAJAY (AKLAN) | P00721726VS | Construction of Revetment | 122.1618 | 11.8104 | 86850000 | 86849991.39 | 2023 | MONOLITHIC CONSTRUCTION & CONCRETE PRODUCTS, INC. | 5559 | 2023 | 2023-11-20 | 02/23/2023 | 8.61 | 0 | 2023-12-04 | 14
2024 | Region II | CAGAYAN | ABULUG (CAGAYAN) | P00825223LZ | Construction of Flood Mitigation Facility | 121.428 | 18.3404 | 24500000 | 24500000 | 2024 | J.G. YACAS CONSTRUCTION, SUPPLY AND EQUIPMENT RENTAL | 5560 | 2024 | 2024-05-15 | 03/04/2024 | 0 | 0 | 2024-08-10 | 87
2021 | Region II | ISABELA |  | P00561453LZ | Construction of Flood Mitigation Structure | 121.6978 | 16.8 | 96499993.86 | 96427479.98 | 2022 | A. DE GUIA CONSTRUCTION AND DEVELOPMENT CORPORATION (FORMERLY: A. DE GUIA CONSTRUCTION) | 5561 | 2021 | 2022-09-15 | 11/23/2021 | 72513.88 | 0 | 2022-10-17 | 32
2022 | Region VI | AKLAN | BURUANGA (AKLAN) | P00620009VS | Construction of Revetment | 121.8885 | 11.8557 | 88200000 | 84299108.79 | 2023 | F. GURREA CONSTRUCTION, INCORPORATED | 5562 | 2022 | 2023-08-07 | 03/15/2022 | 3900891.21 | 0 | 2023-03-22 |  | 138
2023 | Region II | QUIRINO | MADDELA (QUIRINO) | P00726145LZ | Construction of Flood Mitigation Structure | 121.6979 | 16.3541 | 48534200 | 48531824.06 | 2023 | 3K ROCK ENGINEERING | 5563 | 2023 | 2023-07-31 | 02/07/2023 | 2375.94 | 0 | 2023-10-26 | 87
2023 | Region VI | ANTIQUE | SIBALOM (ANTIQUE) | P00721727VS | Construction of Flood Mitigation Structure | 121.9841 | 10.8066 | 48250000 | 33762056.5 | 2023 | TIBIAO-ANTIQUE N.K. ENTERPRISE, INC. | 5564 | 2023 | 2023-12-09 | 04/11/2023 | 14487943.5 | 0 | 2023-12-19 | 10
2024 | Region II | ISABELA | ALICIA (ISABELA) | P00821205LZ | Construction of Revetment | 121.698 | 16.7686 | 96499995.75 | 96489605.42 | 2024 | JWU CONSTRUCTION AND SUPPLY | 5565 | 2024 | 2024-09-27 | 06/24/2024 | 10390.33 | 0 | 2025-05-12 | 227
2022 | Region III | AURORA | BALER (CAPITAL) (AURORA) | P00631146LZ | Construction of Drainage Structure | 121.5409 | 15.8051 | 29400000 | 27911584.27 | 2023 | CONRADO B. BAUTISTA CONST. & SUPPLY CORP. (FORMERL | 5566 | 2022 | 2023-08-22 | 06/21/2022 | 1488415.73 | 0 | 2022-12-08 |  | 257
2022 | Region IV-A | QUEZON | GENERAL LUNA (QUEZON) | P00639379LZ | Construction of Flood Mitigation Structure | 122.1649 | 13.6986 | 96499893.43 | 96500000 | 2023 | RAPID FOREMOST CONST. CO. / ECOSENSE CONSTRUCTION | 5567 | 2022 | 2023-12-15 | 05/26/2022 | 0 | 106.57 | 2023-12-28 | 13
2024 | Region IV-A | QUEZON | PADRE BURGOS (QUEZON) | P00844775LZ | Construction of Flood Mitigation Structure | 121.8923 | 13.9055 | 48999851 | 49000000 | 2024 | ADAD ENGINEERING SERVICES & SUPPLY / LAICAN ENTERPRISES INC. | 5568 | 2024 | 2024-09-19 | 04/11/2024 | 0 | 149 | 2024-12-05 | 77
2022 | Region II | ISABELA | TUMAUINI (ISABELA) | P00641868LZ | Construction of Flood Mitigation Structure | 121.829 | 17.2428 | 48020000 | 47542133.85 | 2022 | ARVEA'S CONSTRUCTION / EGB CONSTRUCTION CORPORATION (FORMERLY: EGB CONSTRUCTION) | 5569 | 2022 | 2022-12-15 | 04/07/2022 | 477866.15 | 0 | 2022-12-30 | 15
2023 | Region II | CAGAYAN | ABULUG (CAGAYAN) | P00727098LZ | Construction of Flood Mitigation Structure | 121.428 | 18.3964 | 29400000 | 29389157.37 | 2023 | FLAVIE CIVIL ENGINEERING CONSTRUCTION | 5570 | 2023 | 2023-09-09 | 03/21/2023 | 10842.63 | 0 | 2023-09-08 |  | 1
2024 | Region II | CAGAYAN | GONZAGA (CAGAYAN) | P00825221LZ | Construction of Flood Mitigation Structure | 121.9864 | 18.2492 | 29400000 | 29379960.22 | 2024 | APS CONSTRUCTION | 5571 | 2024 | 2024-12-13 | 03/28/2024 | 20039.78 | 0 | 2024-12-12 |  | 1
2021 | Region II | ISABELA |  | P00525564LZ | Construction of Flood Mitigation Structure | 121.5409 | 16.6942 | 94570000 | 94570000 | 2022 | ROAD EDGE TRADING & DEVELOPMENT SERVICES | 5572 | 2021 | 2022-08-27 | 12/07/2021 | 0 | 0 | 2022-08-26 |  | 1
2023 | Region II | ISABELA | REINA MERCEDES (ISABELA) | P00727354LZ | Construction of Flood Mitigation Structure | 121.8294 | 16.9836 | 48679441.65 | 48659288.9 | 2023 | ROAD EDGE TRADING & DEVELOPMENT SERVICES | 5573 | 2023 | 2023-10-20 | 03/15/2023 | 20152.75 | 0 | 2023-10-26 | 6
2022 | Region II | ISABELA | ILAGAN CITY (CAPITAL) (ISABELA) | P00621048LZ | Construction of Flood Mitigation Structure | 121.8926 | 17.1394 | 43948080 | 43898080 | 2023 | EGB CONSTRUCTION CORPORATION (FORMERLY: EGB CONSTRUCTION) | 5574 | 2022 | 2023-01-23 | 05/18/2022 | 50000 | 0 | 2023-02-04 | 12
2024 | Region IV-A | QUEZON | GENERAL LUNA (QUEZON) | P00823513LZ | Construction of Flood Mitigation Structure | 122.165 | 13.6988 | 77199976.74 | 77200000 | 2025 | WAWAO BUILDERS | 5575 | 2024 | 2025-02-11 | 06/05/2024 | 0 | 23.26 | 2025-04-17 | 65
2022 | Region IV-B | ORIENTAL MINDORO | MANSALAY (ORIENTAL MINDORO) | P00640567LZ | Construction of Flood Mitigation Structure | 121.4286 | 12.4853 | 24750000 | 24749532.4 | 2023 | D.M. MALIWANAG BUILDERS AND ENTERPRISES | 5576 | 2022 | 2023-03-13 | 07/20/2022 | 467.6 | 0 | 2023-03-17 | 4
2024 | Region II | ISABELA | ALICIA (ISABELA) | P00821568LZ | Construction of Revetment | 121.6981 | 16.7695 | 38576995.68 | 38566585.69 | 2024 | JWU CONSTRUCTION AND SUPPLY | 5577 | 2024 | 2024-10-25 | 08/29/2024 | 10409.99 | 0 | 2025-03-24 | 150
2020 | Region VI | ANTIQUE |  | P00420350VS | Construction of Revetment | 121.988 | 10.808 | 115800000 | 115798223.4 | 2022 | IBC INTERNATIONAL BUILDERS CORPORATION | 5578 | 2020 | 2022-12-12 | 11/23/2020 | 1776.6 | 0 | 2023-01-24 | 43
2022 | Region III | AURORA | BALER (CAPITAL) (AURORA) | P00631163LZ | Construction of Flood Mitigation Structure | 121.5416 | 15.7698 | 49000000 | 49000000 | 2022 | GERRA CONSTRUCTION INCORPORATED (FORMERLY: GERRA CONSTRUCTION) / JOHN DEE B. BUSTAMANTE CONSTRUCTION | 5579 | 2022 | 2022-08-22 | 03/01/2022 | 0 | 0 | 2022-11-29 | 99
2022 | Region II | ISABELA | ILAGAN CITY (CAPITAL) (ISABELA) | P00621052LZ | Construction of Flood Mitigation Structure | 121.8932 | 17.1478 | 48834576 | 48780682.5 | 2022 | DRAGON TWELVE BUILDERS & CONSTRUCTION SUPPLY | 5580 | 2022 | 2022-11-21 | 04/07/2022 | 53893.5 | 0 | 2022-12-25 | 34
2023 | Region II | ISABELA | REINA MERCEDES (ISABELA) | P00742119LZ | Construction of Flood Mitigation Structure | 121.8294 | 16.9935 | 98999997.13 | 98999519.74 | 2024 | MAR-DEB CONSTRUCTION & DEVELOPMENT CORP. (FORMERLY: MAR-DEB CONSTRUCTION & DEVELOPMENT) | 5581 | 2023 | 2024-05-08 | 04/25/2023 | 477.39 | 0 | 2024-05-13 | 5
2022 | Region II | ISABELA | QUIRINO (ISABELA) | P00621158LZ | Construction of Flood Mitigation Structure | 121.6993 | 17.1377 | 96500000 | 96499222.24 | 2023 | MAR-DEB CONSTRUCTION & DEVELOPMENT CORP. (FORMERLY: MAR-DEB CONSTRUCTION & DEVELOPMENT) | 5582 | 2022 | 2023-05-30 | 06/06/2022 | 777.76 | 0 | 2023-06-18 | 19
2021 | Region VI | ANTIQUE |  | P00420350VS | Construction of Revetment | 121.988 | 10.808 | 115800000 | 115798223.4 | 2022 | IBC INTERNATIONAL BUILDERS CORPORATION | 5583 | 2021 | 2022-12-12 | 11/23/2020 | 1776.6 | 0 | 2023-01-24 | 43
2023 | Region IV-B | ORIENTAL MINDORO | MANSALAY (ORIENTAL MINDORO) | P00742465LZ | Construction of Flood Mitigation Structure | 121.4286 | 12.5322 | 9900000 | 9897188.49 | 2023 | D.M. MALIWANAG BUILDERS AND ENTERPRISES | 5584 | 2023 | 2023-05-22 | 03/24/2023 | 2811.51 | 0 | 2023-08-14 | 84
2023 | Region II | ISABELA | ILAGAN CITY (CAPITAL) (ISABELA) | P00726445LZ | Construction of Flood Mitigation Structure | 121.8934 | 17.1373 | 96200000 | 96180049.98 | 2023 | EGB CONSTRUCTION CORPORATION (FORMERLY: EGB CONSTRUCTION) | 5585 | 2023 | 2023-12-18 | 04/17/2023 | 19950.02 | 0 | 2024-04-06 | 110
2022 | Cordillera Administrative Region | IFUGAO | ALFONSO LISTA (POTIA) (IFUGAO) | P00621479LZ | Construction of Flood Mitigation Structure | 121.5421 | 16.8909 | 49000000 | 49000000 | 2022 | MA CONSTRUCTION / R.S. SEPIAN CONSTRUCTION & TRUCKING | 5586 | 2022 | 2022-12-07 | 04/07/2022 | 0 | 0 | 2022-12-15 | 8
2022 | Region II | ISABELA | TUMAUINI (ISABELA) | P00620492LZ | Construction of Flood Mitigation Structure | 121.8294 | 17.244 | 24500000 | 24255871.63 | 2022 | DRAGON TWELVE BUILDERS & CONSTRUCTION SUPPLY | 5587 | 2022 | 2022-11-25 | 04/07/2022 | 244128.37 | 0 | 2022-11-24 |  | 1
2021 | Region VI | AKLAN |  | P00521767VS | Construction of Revetment | 122.1654 | 11.7581 | 19600000 | 19400000 | 2022 | FIRST MAKEEN CONSTRUCTION | 5588 | 2021 | 2022-11-02 | 10/08/2021 | 200000 | 0 | 2022-03-02 |  | 245
2024 | Region II | ISABELA | BURGOS (ISABELA) | P00824885LZ | Construction of Flood Mitigation Structure | 121.6994 | 17.111 | 96500000 | 96457919.01 | 2024 | RR BUILDERS / EGB CONSTRUCTION CORPORATION (FORMERLY: EGB CONSTRUCTION) | 5589 | 2024 | 2024-09-01 | 05/13/2024 | 42080.99 | 0 | 2025-04-15 | 226
2024 | Region II | CAGAYAN | GONZAGA (CAGAYAN) | P00824682LZ | Construction of Flood Mitigation Structure | 121.9881 | 18.2556 | 29400000 | 29394988.25 | 2024 | APS CONSTRUCTION | 5590 | 2024 | 2024-08-18 | 04/07/2024 | 5011.75 | 0 | 2024-11-22 | 96
2022 | Region II | CAGAYAN | ABULUG (CAGAYAN) | P00621042LZ | Construction of Flood Mitigation Structure | 121.4287 | 18.4412 | 49000000 | 49000000 | 2022 | JLL PULSAR CONSTRUCTION CORPORATION (FORMERLY: PULSAR CONSTRUCTION) | 5591 | 2022 | 2022-11-30 | 02/07/2022 | 0 | 0 | 2022-11-29 |  | 1
2024 | Region III | AURORA | BALER (CAPITAL) (AURORA) | P00823437LZ | Construction of Flood Mitigation Structure | 121.5422 | 15.7726 | 144750000 | 144750000 | 2024 | DALCON CONSTRUCTION / EGB CONSTRUCTION CORPORATION (FORMERLY: EGB CONSTRUCTION) | 5592 | 2024 | 2024-07-22 | 03/07/2024 | 0 | 0 | 2024-12-23 | 154
2024 | Region IV-A | QUEZON | PATNANUNGAN (QUEZON) | P00846081LZ | Construction of Flood Mitigation Structure | 122.1668 | 14.7809 | 4950000 | 4943557.73 | 2024 | N.T. SOTELO CONSTRUCTION AND SUPPLY CORPORATION | 5593 | 2024 | 2024-10-01 | 07/31/2024 | 6442.27 | 0 | 2024-09-30 |  | 1
2023 | Region II | ISABELA | REINA MERCEDES (ISABELA) | P00742118LZ | Construction of Flood Mitigation Structure | 121.83 | 16.9981 | 98999997.93 | 98997072.72 | 2024 | MAR-DEB CONSTRUCTION & DEVELOPMENT CORP. (FORMERLY: MAR-DEB CONSTRUCTION & DEVELOPMENT) | 5594 | 2023 | 2024-05-08 | 04/25/2023 | 2925.21 | 0 | 2024-05-13 | 5
2023 | Region IV-B | ROMBLON | ALCANTARA (ROMBLON) | P00726951LZ | Construction of Flood Mitigation Structure | 121.99 | 12.3765 | 193000000 | 192991021.8 | 2023 | LEGACY CONSTRUCTION CORPORATION (FORMERLY: LEGACY CONSTRUCTION) | 5595 | 2023 | 2023-12-10 | 03/29/2023 | 8978.2 | 0 | 2024-03-21 | 102
2023 | Region IV-A | QUEZON | SARIAYA (QUEZON) | P00727168LZ | Construction of Flood Mitigation Structure | 121.5427 | 13.9479 | 49000000 | 49000000 | 2024 | I.A . BOSQUE CONSTRUCTION CORPORATION | 5596 | 2023 | 2024-02-28 | 03/14/2023 | 0 | 0 | 2024-04-05 | 37
2024 | Region VI | AKLAN | IBAJAY (AKLAN) | P00820026VS | Construction of Revetment | 122.1672 | 11.8144 | 130315530 | 128763569 | 2024 | ALMANA CONSTRUCTION AND DEV'T CORPORATION | 5597 | 2024 | 2024-09-16 | 03/07/2024 | 1551961 | 0 | 2025-04-14 | 210
2022 | Region IV-B | MARINDUQUE | MOGPOG (MARINDUQUE) | P00639517LZ | Construction of Flood Mitigation Structure | 121.8941 | 13.5414 | 9798000 | 9788709.37 | 2023 | K CONSTRUCTION & DEVELOPERS CORPORATION | 5598 | 2022 | 2023-09-05 | 03/30/2022 | 9290.63 | 0 | 2022-08-07 |  | 394
2023 | Region II | ISABELA | NAGUILIAN (ISABELA) | P00726698LZ | Construction of Flood Mitigation Structure | 121.8324 | 17.0072 | 44099985.06 | 44080822 | 2023 | RRC CO. INC. (FORMERLY: R R C CONSTRUCTION) | 5599 | 2023 | 2023-09-27 | 03/14/2023 | 19163.06 | 0 | 2023-10-21 | 24
2022 | Region II | CAGAYAN | ABULUG (CAGAYAN) | P00639462LZ | Construction of Flood Mitigation Structure | 121.4287 | 18.4412 | 53075000 | 52592402.45 | 2023 | MEGAY CONSTRUCTION INC. (FORMERLY: MEGAY CONSTRUCTION) | 5600 | 2022 | 2023-08-04 | 03/29/2022 | 482597.55 | 0 | 2023-01-21 |  | 195
2022 | Region II | QUIRINO | MADDELA (QUIRINO) | P00621074LZ | Construction of Flood Mitigation Structure | 121.6994 | 16.3486 | 49000000 | 48997887.83 | 2022 | A.P.D. CONSTRUCTION, INC. (FORMERLY: APD CONSTRUCTION) | 5601 | 2022 | 2022-11-09 | 04/01/2022 | 2112.17 | 0 | 2023-01-22 | 74
2022 | Region IV-B | ROMBLON | LOOC (ROMBLON) | P00630956LZ | Construction of Flood Mitigation Structure | 121.9902 | 12.2598 | 115799875.6 | 115776410 | 2022 | LEGACY CONSTRUCTION CORPORATION (FORMERLY: LEGACY CONSTRUCTION) | 5602 | 2022 | 2022-12-01 | 02/23/2022 | 23465.6 | 0 | 2022-12-30 | 29
2024 | Cordillera Administrative Region | IFUGAO | ALFONSO LISTA (POTIA) (IFUGAO) | P00823322LZ | Construction of Flood Mitigation Structure | 121.5429 | 16.8774 | 78342073.18 | 78358000 | 2024 | DJY CONSTRUCTION | 5603 | 2024 | 2024-09-25 | 02/23/2024 | 0 | 15926.82 | 2024-09-24 |  | 1
2024 | Region VI | AKLAN | IBAJAY (AKLAN) | P00820028VS | Construction of Revetment | 122.1683 | 11.8184 | 121348750 | 121348746.1 | 2024 | IBC INTERNATIONAL BUILDERS CORPORATION | 5604 | 2024 | 2024-08-19 | 02/06/2024 | 3.9 | 0 | 2024-12-06 | 109
2024 | Region II | ISABELA | ILAGAN CITY (CAPITAL) (ISABELA) | P00844740LZ | Construction of Flood Mitigation Structure | 121.8967 | 17.1503 | 49000000 | 48994560 | 2024 | DRAGON TWELVE BUILDERS & CONSTRUCTION SUPPLY | 5605 | 2024 | 2024-09-15 | 06/24/2024 | 5440 | 0 | 2025-02-12 | 150
2024 | Region VI | AKLAN | IBAJAY (AKLAN) | P00820027VS | Construction of Revetment | 122.1706 | 11.7827 | 96500000 | 95335880.55 | 2024 | ALMANA CONSTRUCTION AND DEV'T CORPORATION | 5606 | 2024 | 2024-09-16 | 03/07/2024 | 1164119.45 | 0 | 2025-02-23 | 160
2022 | Region II | ISABELA | NAGUILIAN (ISABELA) | P00631123LZ | Construction of Flood Mitigation Structure | 121.8324 | 16.9736 | 43831597.17 | 44084315.86 | 2023 | ARCINUE COMM'L CORPORATION | 5607 | 2022 | 2023-03-16 | 02/14/2022 | 0 | 252718.69 | 2023-03-15 |  | 1
2024 | Region IV-B | ROMBLON | ODIONGAN (ROMBLON) | P00825133LZ | Construction of Flood Mitigation Structure | 121.9903 | 12.3714 | 96499999.47 | 96500000 | 2024 | SUNWEST, INC. (FORMERLY: SUNWEST CONSTRUCTION & DEVELOPMENT CORPORATION) | 5608 | 2024 | 2024-12-13 | 03/13/2024 | 0 | 0.53 | 2025-02-14 | 63
2023 | Region II | ISABELA | JONES (ISABELA) | P00740317LZ | Construction of Flood Mitigation Structure | 121.7012 | 16.5457 | 96500000 | 96499900.26 | 2023 | EGB CONSTRUCTION CORPORATION (FORMERLY: EGB CONSTRUCTION) | 5609 | 2023 | 2023-12-07 | 04/17/2023 | 99.74 | 0 | 2024-02-07 | 62
2023 | Region III | AURORA | BALER (CAPITAL) (AURORA) | P00740578LZ | Construction of Drainage Structure | 121.5433 | 15.7969 | 29400000 | 29400000 | 2024 | CONRADO B. BAUTISTA CONST. & SUPPLY CORP. (FORMERL | 5610 | 2023 | 2024-05-16 | 04/13/2023 | 0 | 0 | 2024-01-24 |  | 113
2022 | Cordillera Administrative Region | KALINGA | CITY OF TABUK (CAPITAL) (KALINGA) | P00621496LZ | Construction of Dike | 121.429 | 17.4233 | 57857801.11 | 57568444.07 | 2023 | OMENGAN CONSTRUCTION & DEVELOPMENT CORPORATION | 5611 | 2022 | 2023-03-29 | 04/08/2022 | 289357.04 | 0 | 2023-01-17 |  | 71
2022 | Region II | ISABELA | ILAGAN CITY (CAPITAL) (ISABELA) | P00621046LZ | Construction of Flood Mitigation Structure | 121.8972 | 17.1662 | 44100000 | 44050000 | 2023 | EGB CONSTRUCTION CORPORATION (FORMERLY: EGB CONSTRUCTION) | 5612 | 2022 | 2023-02-19 | 03/29/2022 | 50000 | 0 | 2023-02-18 |  | 1
2021 | Cordillera Administrative Region | KALINGA |  | P00526265LZ | Construction of Flood Mitigation Structure | 121.4294 | 17.4176 | 77197516.75 | 76424709.06 | 2023 | OMENGAN CONSTRUCTION & DEVELOPMENT CORPORATION | 5613 | 2021 | 2023-02-28 | 04/08/2022 | 772807.69 | 0 | 2023-01-04 |  | 55
2022 | Region IV-A | QUEZON | GENERAL LUNA (QUEZON) | P00621470LZ | Construction of Drainage Structure | 122.1736 | 13.6923 | 29399907.64 | 29400000 | 2023 | WYDERWAYS BUILDERS AND SUPPLIES | 5614 | 2022 | 2023-04-22 | 04/05/2022 | 0 | 92.36 | 2023-04-21 |  | 1
2023 | Region II | ISABELA | NAGUILIAN (ISABELA) | P00726427LZ | Construction of Flood Mitigation Structure | 121.8333 | 16.9698 | 52722400.25 | 52833696.23 | 2023 | ROAD EDGE TRADING & DEVELOPMENT SERVICES | 5615 | 2023 | 2023-11-04 | 03/15/2023 | 0 | 111295.98 | 2023-11-03 |  | 1
2023 | Region IV-B | MARINDUQUE | BOAC (CAPITAL) (MARINDUQUE) | P00726950LZ | Construction of Flood Mitigation Structure | 121.8976 | 13.4204 | 77198000 | 77167301.33 | 2023 | DQT BUILDERS CORPORATION (FORMERLY DQT BUILDERS) | 5616 | 2023 | 2023-12-04 | 03/22/2023 | 30698.67 | 0 | 2024-01-14 | 41
2024 | Region III | AURORA | DIPACULAO (AURORA) | P00844534LZ | Construction of Drainage Structure | 121.5442 | 15.8624 | 4900000 | 4798860.49 | 2024 | GVDPM CONSTRUCTION CORP. (FORMERLY: ZM CONSTRUCTIO | 5617 | 2024 | 2024-12-16 | 07/05/2024 | 101139.51 | 0 | 2024-08-28 |  | 110
2023 | Region IV-B | ORIENTAL MINDORO | MANSALAY (ORIENTAL MINDORO) | P00727200LZ | Construction of Flood Mitigation Structure | 121.4297 | 12.5822 | 48999968.93 | 48997147.81 | 2024 | LUMEL GLENN CONSTRUCTION | 5618 | 2023 | 2024-01-18 | 03/15/2023 | 2821.12 | 0 | 2024-01-17 |  | 1
2024 | Region IV-B | ROMBLON | ODIONGAN (ROMBLON) | P00825134LZ | Construction of Flood Mitigation Structure | 121.9903 | 12.3714 | 139924999.4 | 139925000 | 2024 | SUNWEST, INC. (FORMERLY: SUNWEST CONSTRUCTION & DEVELOPMENT CORPORATION) | 5619 | 2024 | 2024-12-13 | 03/13/2024 | 0 | 0.6 | 2025-03-06 | 83
2022 | Region III | AURORA | DIPACULAO (AURORA) | P00631154LZ | Construction of Flood Mitigation Structure | 121.5457 | 15.8596 | 19600000 | 19600000 | 2022 | R.N.G.M. CONSTRUCTION CORPORATION (FORMERLY: R.N.G.M. CONSTRUCTION) | 5620 | 2022 | 2022-12-15 | 03/07/2022 | 0 | 0 | 2022-12-26 | 11
2021 | Region II | ISABELA |  | P00561454LZ | Construction of Flood Mitigation Structure | 121.7014 | 16.7683 | 96499986.74 | 96490653.68 | 2022 | C.R. DOMINGO CONSTRUCTION AND POWER DEVELOPMENT, INC. (FOR. C.R. DOMINGO CONSTRUCTION, INC.) | 5621 | 2021 | 2022-09-02 | 11/23/2021 | 9333.06 | 0 | 2022-10-17 | 45
2022 | Region III | AURORA | DILASAG (AURORA) | P00631160LZ | Construction of Flood Mitigation Structure | 122.1781 | 16.3056 | 9800000 | 9800000 | 2022 | BAMM BUSINESS VENTURES INC. | 5622 | 2022 | 2022-09-14 | 04/04/2022 | 0 | 0 | 2022-09-13 |  | 1
2024 | Region II | ISABELA | NAGUILIAN (ISABELA) | P00821164LZ | Construction of Revetment | 121.8337 | 16.9745 | 96499996.77 | 96489408.59 | 2024 | JWU CONSTRUCTION AND SUPPLY | 5623 | 2024 | 2024-08-05 | 04/03/2024 | 10588.18 | 0 | 2025-02-19 | 198
2023 | Region IV-B | MARINDUQUE | GASAN (MARINDUQUE) | P00737547LZ | Construction of Flood Mitigation Structure | 121.8991 | 13.2785 | 5937999.99 | 5938368.63 | 2023 | G.T.J. CONSTRUCTION | 5624 | 2023 | 2023-06-24 | 01/31/2023 | 0 | 368.64 | 2023-06-23 |  | 1
2022 | Region II | ISABELA | ALICIA (ISABELA) | P00631128LZ | Construction of Flood Mitigation Structure | 121.7022 | 16.7658 | 42139998.88 | 41495256.89 | 2023 | MAR-DEB CONSTRUCTION & DEVELOPMENT CORP. (FORMERLY: MAR-DEB CONSTRUCTION & DEVELOPMENT) | 5625 | 2022 | 2023-02-16 | 05/31/2022 | 644741.99 | 0 | 2023-02-15 |  | 1
2022 | Region II | CAGAYAN | BUGUEY (CAGAYAN) | P00640507LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.8339 | 18.2903 | 24750000 | 19019000 | 2023 | RPF CONSTRUCTION | 5626 | 2022 | 2023-02-06 | 04/01/2022 | 5731000 | 0 | 2022-12-03 |  | 65
2024 | Region IV-A | QUEZON | QUEZON (QUEZON) | P00820922LZ | Construction of Flood Mitigation Structure | 122.1801 | 14.0039 | 4900000 | 4826779.06 | 2024 | RAM BUILDERS | 5627 | 2024 | 2024-04-15 | 02/14/2024 | 73220.94 | 0 | 2024-07-11 | 87
2023 | Region III | AURORA | DIPACULAO (AURORA) | P00727282LZ | Construction of Flood Mitigation Structure | 121.5463 | 15.8616 | 192999972.3 | 192999941.8 | 2024 | PERSAN CONSTRUCTION, INC. (FORMERLY: PERSAN CONST. / 4VC BUILDERS & DEVELOPMENT CORP. | 5628 | 2023 | 2024-03-31 | 06/26/2023 | 30.5 | 0 | 2024-08-27 | 149
2022 | Region II | CAGAYAN | ABULUG (CAGAYAN) | P00631107LZ | Construction of Flood Mitigation Structure | 121.43 | 18.3425 | 43120000 | 43120000 | 2023 | JC PALOMO CONSTRUCTION & CONSTRUCTION SUPPLY / C.T. LEONCIO CONSTRUCTION & TRADING | 5629 | 2022 | 2023-02-10 | 02/14/2022 | 0 | 0 | 2023-01-10 |  | 31
2024 | Region IV-A | QUEZON | ALABAT (QUEZON) | P00820915LZ | Construction of Flood Mitigation Structure | 121.9908 | 14.1219 | 4900000 | 4837404.35 | 2024 | RAM BUILDERS | 5630 | 2024 | 2024-08-08 | 03/12/2024 | 62595.65 | 0 | 2024-08-07 |  | 1
2023 | Cordillera Administrative Region | KALINGA | CITY OF TABUK (CAPITAL) (KALINGA) | P00726412LZ | Construction of Flood Mitigation Structure | 121.4322 | 17.4439 | 144745196.1 | 144750000 | 2024 | JTM CONSTRUCTION / EGB CONSTRUCTION CORPORATION (FORMERLY: EGB CONSTRUCTION) | 5631 | 2023 | 2024-06-21 | 04/12/2023 | 0 | 4803.9 | 2024-04-10 |  | 72
2022 | Region IV-B | MARINDUQUE | BOAC (CAPITAL) (MARINDUQUE) | P00639513LZ | Construction of Flood Mitigation Structure | 121.8992 | 13.4218 | 19598000 | 19568537.1 | 2022 | ZUIDEN BUILDERS INC. | 5632 | 2022 | 2022-10-30 | 03/30/2022 | 29462.9 | 0 | 2022-10-29 |  | 1
2024 | Region IV-A | BATANGAS | SAN JUAN (BATANGAS) | P00820875LZ | Construction of Flood Mitigation Structure | 121.4322 | 13.8101 | 9800000 | 9506486 | 2024 | MEGAJES CONSTRUCTION CORP. | 5633 | 2024 | 2024-07-03 | 04/05/2024 | 293514 | 0 | 2024-07-02 |  | 1
2022 | Region IV-A | QUEZON | QUEZON (QUEZON) | P00640562LZ | Construction of Flood Mitigation Structure | 122.1809 | 14.0044 | 49000000 | 49000000 | 2022 | RAM BUILDERS | 5634 | 2022 | 2022-11-16 | 03/24/2022 | 0 | 0 | 2022-12-17 | 31
2022 | Region II | CAGAYAN | BUGUEY (CAGAYAN) | P00621033LZ | Construction of Flood Mitigation Structure | 121.8339 | 18.2903 | 49000000 | 47530000 | 2023 | AGAFER CONSTRUCTION AND TRADING CORPORATION (FOR: AGAFER CONSTRUCTION AND TRADING) | 5635 | 2022 | 2023-02-06 | 04/01/2022 | 1470000 | 0 | 2023-01-07 |  | 30
2022 | Region III | AURORA | DIPACULAO (AURORA) | P00631143LZ | Construction of Flood Mitigation Structure | 121.548 | 15.8749 | 4900000 | 4900000 | 2022 | ULIRAN CONSTRUCTION SERVICES | 5636 | 2022 | 2022-11-10 | 03/18/2022 | 0 | 0 | 2022-06-26 |  | 137
2022 | Region IV-B | ROMBLON | ODIONGAN (ROMBLON) | P00620264LZ | Construction of Flood Mitigation Structure | 121.9908 | 12.4228 | 96499999.5 | 96485036.56 | 2023 | ROLCO CONSTRUCTION & DEVELOPMENT CORPORATION ( FOR | 5637 | 2022 | 2023-06-26 | 03/29/2022 | 14962.94 | 0 | 2023-05-25 |  | 32
2024 | Cordillera Administrative Region | MOUNTAIN PROVINCE | PARACELIS (MOUNTAIN PROVINCE) | P00821546LZ | Construction of Flood Mitigation Structure | 121.552 | 17.1994 | 39200000 | 39200000 | 2024 | UPLAND CONSTRUCTION AND ENGINEERING SERVICES | 5638 | 2024 | 2024-07-18 | 02/15/2024 | 0 | 0 | 2024-09-16 | 60
2022 | Region II | ISABELA | ECHAGUE (ISABELA) | P00621449LZ | Construction of Flood Mitigation Structure | 121.7055 | 16.6936 | 49000000 | 49000000 | 2022 | V.B. MANUBAY CONSTRUCTION | 5639 | 2022 | 2022-11-10 | 04/12/2022 | 0 | 0 | 2022-12-02 | 22
2024 | Region II | ISABELA | SAN MARIANO (ISABELA) | P00821167LZ | Construction of Revetment | 121.8346 | 17.0137 | 96499998.74 | 96449595.32 | 2024 | CAMBERWELL CONSTRUCTION AND SUPPLIES | 5640 | 2024 | 2024-06-25 | 03/12/2024 | 50403.42 | 0 | 2025-02-02 | 222
2022 | Region IV-A | QUEZON | QUEZON (QUEZON) | P00621498LZ | Construction of Flood Mitigation Structure | 122.1874 | 14.0059 | 24010000 | 24010000 | 2022 | RAM BUILDERS | 5641 | 2022 | 2022-09-12 | 03/24/2022 | 0 | 0 | 2022-10-18 | 36
2024 | Region VI | ANTIQUE | HAMTIC (ANTIQUE) | P00834988VS | Construction of Flood Mitigation Structure | 121.9959 | 10.6359 | 4950000 | 4928055.67 | 2024 | HMM BUILDERS AND CONSTRUCTION SUPPLY | 5642 | 2024 | 2024-05-09 | 03/06/2024 | 21944.33 | 0 | 2024-05-08 |  | 1
2022 | Region II | ISABELA | CITY OF SANTIAGO (ISABELA) | P00639327LZ | Construction of Flood Mitigation Structure | 121.5525 | 16.6747 | 96500000 | 96499615.93 | 2023 | MA TESORO CONSTRUCTION / EGB CONSTRUCTION CORPORATION (FORMERLY: EGB CONSTRUCTION) | 5643 | 2022 | 2023-01-10 | 04/01/2022 | 384.07 | 0 | 2023-01-09 |  | 1
2023 | Region II | ISABELA | ANGADANAN (ISABELA) | P00727266LZ | Construction of Flood Mitigation Structure | 121.707 | 16.7476 | 95858914.67 | 95855332.27 | 2023 | MAV CONSTRUCTION SUPPLY AND POWER DEVELOPMENT / C.R. DOMINGO CONSTRUCTION AND POWER DEVELOPMENT, INC. (FOR. C.R. DOMINGO CONSTRUCTION, INC.) | 5644 | 2023 | 2023-08-18 | 03/15/2023 | 3582.4 | 0 | 2024-02-01 | 167
2024 | Region IV-B | MARINDUQUE | BOAC (CAPITAL) (MARINDUQUE) | P00820965LZ | Construction of Flood Mitigation Structure | 121.8348 | 13.4505 | 19598000 | 18214714.08 | 2024 | JEDIDIAH CONSTRUCTION | 5645 | 2024 | 2024-04-24 | 01/30/2024 | 1383285.92 | 0 | 2024-07-09 | 76
2022 | Region II | CAGAYAN | ABULUG (CAGAYAN) | P00621035LZ | Construction of Flood Mitigation Structure | 121.4323 | 18.412 | 49000000 | 49000000 | 2023 | AGAFER CONSTRUCTION AND TRADING CORPORATION (FOR: AGAFER CONSTRUCTION AND TRADING) | 5646 | 2022 | 2023-03-09 | 03/29/2022 | 0 | 0 | 2023-03-08 |  | 1
2022 | Region III | AURORA | DILASAG (AURORA) | P00631165LZ | Construction of Flood Mitigation Structure | 122.2006 | 16.4363 | 19600000 | 19600000 | 2022 | DALCON CONSTRUCTION | 5647 | 2022 | 2022-07-14 | 02/28/2022 | 0 | 0 | 2022-07-25 | 11
2023 | Region VI | ILOILO | MIAGAO (ILOILO) | P00731617VS | Construction of Flood Mitigation Structure | 122.2022 | 10.7061 | 96500000 | 96353234.03 | 2024 | A.D. PENDON CONSTRUCTION & SUPPLY, INC. (FORMERLY: ADP CONSTRUCTION & SUPPLY) | 5648 | 2023 | 2024-11-19 | 03/23/2023 | 146765.97 | 0 | 2024-11-18 |  | 1
2024 | Region VI | ILOILO | MIAGAO (ILOILO) | P00821051VS | Construction of Flood Mitigation Structure | 122.2028 | 10.6877 | 14700000 | 14677241.97 | 2024 | CONTE BUILDERS & CONSTRUCTION SUPPLY | 5649 | 2024 | 2024-09-26 | 02/27/2024 | 22758.03 | 0 | 2024-09-25 |  | 1
2022 | Region IV-B | MARINDUQUE | BOAC (CAPITAL) (MARINDUQUE) | P00620900LZ | Construction of Flood Mitigation Structure | 121.8995 | 13.4125 | 86848000 | 86848881.33 | 2023 | MONOLITHIC CONSTRUCTION & CONCRETE PRODUCTS, INC. | 5650 | 2022 | 2023-04-26 | 02/23/2022 | 0 | 881.33 | 2023-04-26 | 0
2024 | Region II | ISABELA | NAGUILIAN (ISABELA) | P00821166LZ | Construction of Revetment | 121.8354 | 17.018 | 96499996.12 | 96393939.68 | 2024 | DANYSONS CONSTRUCTION AND DEVELOPMENT CORPORATION (FORMERLY: DANYSONS CONSTRUCTION) | 5651 | 2024 | 2024-06-10 | 03/12/2024 | 106056.44 | 0 | 2025-01-27 | 231
2022 | Region II | ISABELA | CITY OF SANTIAGO (ISABELA) | P00639328LZ | Construction of Flood Mitigation Structure | 121.5537 | 16.6754 | 96500000 | 96499653.77 | 2023 | MA TESORO CONSTRUCTION / EGB CONSTRUCTION CORPORATION (FORMERLY: EGB CONSTRUCTION) | 5652 | 2022 | 2023-03-15 | 04/13/2022 | 346.23 | 0 | 2023-04-20 | 36
2024 | Region VI | ILOILO | MIAGAO (ILOILO) | P00821050VS | Construction of Flood Mitigation Structure | 122.2136 | 10.6392 | 4900000 | 4856848.48 | 2025 | J'14 CONSTRUCTION & SUPPLY | 5653 | 2024 | 2025-01-15 | 05/13/2024 | 43151.52 | 0 | 2024-11-05 |  | 71
2022 | Region IV-B | MARINDUQUE | BOAC (CAPITAL) (MARINDUQUE) | P00639514LZ | Construction of Flood Mitigation Structure | 121.9009 | 13.4148 | 30378000 | 30378967.2 | 2023 | G.T.J. CONSTRUCTION | 5654 | 2022 | 2023-03-26 | 03/30/2022 | 0 | 967.2 | 2023-03-25 |  | 1
2024 | Region IV-B | ROMBLON | ODIONGAN (ROMBLON) | P00844549LZ | Construction of Flood Mitigation Structure | 121.9972 | 12.4228 | 19299999.53 | 19300000 | 2024 | ATHENA CONSTRUCTION AND DEVELOPMENT | 5655 | 2024 | 2024-10-14 | 04/08/2024 | 0 | 0.47 | 2024-10-19 | 5
2022 | Region IV-B | ORIENTAL MINDORO | BONGABONG (ORIENTAL MINDORO) | P00621122LZ | Construction of Flood Mitigation Structure | 121.4331 | 12.6664 | 48999036.16 | 48999954.43 | 2023 | SIXTEEN ENTERPRISES-CALAPAN BRANCH | 5656 | 2022 | 2023-01-07 | 04/13/2022 | 0 | 918.27 | 2023-01-06 |  | 1
2022 | Region II | ISABELA | QUIRINO (ISABELA) | P00637770LZ | Construction of Flood Mitigation Structure | 121.7085 | 17.1164 | 20790000 | 20789987.48 | 2022 | DANYSONS CONSTRUCTION AND DEVELOPMENT CORPORATION (FORMERLY: DANYSONS CONSTRUCTION) | 5657 | 2022 | 2022-11-06 | 04/04/2022 | 12.52 | 0 | 2022-11-05 |  | 1
2022 | Region II | ISABELA | DIVILACAN (ISABELA) | P00631115LZ | Construction of Flood Mitigation Structure | 122.2283 | 17.3344 | 4900000 | 4890000 | 2022 | EGB CONSTRUCTION CORPORATION (FORMERLY: EGB CONSTRUCTION) | 5658 | 2022 | 2022-07-22 | 04/07/2022 | 10000 | 0 | 2022-07-21 |  | 1
2024 | Cordillera Administrative Region | MOUNTAIN PROVINCE | PARACELIS (MOUNTAIN PROVINCE) | P00823330LZ | Construction of Flood Mitigation Structure | 121.5539 | 17.2011 | 96500000 | 96500000 | 2024 | UPLAND CONSTRUCTION AND ENGINEERING SERVICES | 5659 | 2024 | 2024-10-27 | 02/26/2024 | 0 | 0 | 2024-11-01 | 5
2023 | Region IV-B | ROMBLON | ODIONGAN (ROMBLON) | P00726279LZ | Construction of Flood Mitigation Structure | 121.9975 | 12.4228 | 48999999.61 | 48994906.26 | 2023 | R.G. FLORENTINO CONST. & TRADING INC. | 5660 | 2023 | 2023-08-16 | 02/22/2023 | 5093.35 | 0 | 2023-10-17 | 62
2022 | Region II | CAGAYAN | TUGUEGARAO CITY (CAPITAL) (CAGAYAN) | P00621243LZ | Construction of Flood Mitigation Structure | 121.7087 | 17.6037 | 9650000 | 9650000 | 2022 | DOUBLE J1908 CONSTRUCTION | 5661 | 2022 | 2022-11-29 | 03/28/2022 | 0 | 0 | 2022-11-28 |  | 1
2023 | Region IV-A | BATANGAS | SAN JUAN (BATANGAS) | P00727312LZ | Construction of Flood Mitigation Structure | 121.4333 | 13.8112 | 96500000 | 96500000 | 2024 | N.D.M. SANCHEZ BUILDERS & DEVELOPMENT CORPORATION | 5662 | 2023 | 2024-09-02 | 05/04/2023 | 0 | 0 | 2024-02-18 |  | 197
2022 | Region II | ISABELA | ILAGAN CITY (CAPITAL) (ISABELA) | P00621049LZ | Construction of Flood Mitigation Structure | 121.9017 | 17.1645 | 44100000 | 44072939.6 | 2022 | DRAGON TWELVE BUILDERS & CONSTRUCTION SUPPLY | 5663 | 2022 | 2022-10-13 | 05/18/2022 | 27060.4 | 0 | 2023-02-04 | 114
2024 | Region VI | ILOILO | GUIMBAL (ILOILO) | P00832626VS | Construction of Flood Mitigation Structure | 122.2291 | 10.6917 | 19800000 | 19280582.34 | 2024 | SKF BUILDERS AND SUPPLIES CORP. | 5664 | 2024 | 2024-09-05 | 04/08/2024 | 519417.66 | 0 | 2024-09-04 |  | 1
2023 | Region II | CAGAYAN | BUGUEY (CAGAYAN) | P00742294LZ | Construction of Flood Mitigation Structure | 121.8364 | 18.2894 | 4950000 | 4940000 | 2023 | RPF CONSTRUCTION | 5665 | 2023 | 2023-06-09 | 04/05/2023 | 10000 | 0 | 2023-06-13 | 4
2023 | Region IV-A | QUEZON | LUCBAN (QUEZON) | P00737526LZ | Construction of Flood Mitigation Structure | 121.5548 | 14.1143 | 4950000 | 4949935.98 | 2023 | LUCBAN BUILDERS AND CONSTRUCTION SUPPLY INCORPORAT | 5666 | 2023 | 2023-10-19 | 06/02/2023 | 64.02 | 0 | 2023-11-19 | 31
2024 | Region IV-B | ROMBLON | ODIONGAN (ROMBLON) | P00823588LZ | Construction of Flood Mitigation Structure | 121.9986 | 12.4222 | 96499999.8 | 96497999.88 | 2024 | SCATR CONSTRUCTION | 5667 | 2024 | 2024-11-25 | 03/19/2024 | 1999.92 | 0 | 2025-02-20 | 87
2022 | Region II | ISABELA | QUIRINO (ISABELA) | P00621057LZ | Construction of Flood Mitigation Structure | 121.709 | 17.117 | 39200000 | 39199987.54 | 2022 | DANYSONS CONSTRUCTION AND DEVELOPMENT CORPORATION (FORMERLY: DANYSONS CONSTRUCTION) | 5668 | 2022 | 2022-11-18 | 02/28/2022 | 12.46 | 0 | 2022-11-25 | 7
2023 | Region IV-A | LAGUNA | LILIW (LAGUNA) | P00726934LZ | Construction of Flood Mitigation Structure | 121.434 | 14.13 | 86850000 | 86840064.43 | 2024 | AMETHYST HORIZON BUILDERS AND GEN. CONTRACTOR AND DEVELOPMENT CORP. | 5669 | 2023 | 2024-02-04 | 04/11/2023 | 9935.57 | 0 | 2024-02-03 |  | 1
2023 | Region IV-A | QUEZON | SARIAYA (QUEZON) | P00740383LZ | Construction of Flood Mitigation Structure | 121.555 | 13.9477 | 96500000 | 96500000 | 2024 | WAYCON BUILDERS AND CONSTRUCTION SUPPLY CORP. (FOR:WAYCON BUILDERS & CONSTRUCTION SUPPLY) | 5670 | 2023 | 2024-04-26 | 06/02/2023 | 0 | 0 | 2024-04-27 | 1
2023 | Region IV-B | MARINDUQUE | BOAC (CAPITAL) (MARINDUQUE) | P00726258LZ | Construction of Flood Mitigation Structure | 121.9036 | 13.4373 | 47037999.99 | 37243853.46 | 2023 | APRIL ROSE ENT. & BUILDERS | 5671 | 2023 | 2023-08-09 | 01/31/2023 | 9794146.53 | 0 | 2023-08-08 |  | 1
2023 | Region IV-B | ROMBLON | ODIONGAN (ROMBLON) | P00726275LZ | Construction of Flood Mitigation Structure | 121.9986 | 12.4222 | 48999999.7 | 48997559.85 | 2023 | ROLCO CONSTRUCTION & DEVELOPMENT CORPORATION ( FOR | 5672 | 2023 | 2023-12-04 | 02/21/2023 | 2439.85 | 0 | 2023-12-04 | 0
2023 | Region IV-A | BATANGAS | SAN JUAN (BATANGAS) | P00726542LZ | Construction of Revetment | 121.4351 | 13.8288 | 96500000 | 96500000 | 2023 | V.R. PATRON BUILDERS & DEVELOPERS CORP. (PREVIOUSL | 5673 | 2023 | 2023-09-20 | 02/13/2023 | 0 | 0 | 2023-11-30 | 71
2024 | Region II | ISABELA | BURGOS (ISABELA) | P00820170LZ | Construction of Flood Mitigation Structure | 121.7095 | 17.1058 | 89384090 | 89344393.48 | 2024 | MAR-DEB CONSTRUCTION & DEVELOPMENT CORP. (FORMERLY: MAR-DEB CONSTRUCTION & DEVELOPMENT) | 5674 | 2024 | 2024-12-02 | 02/12/2024 | 39696.52 | 0 | 2025-02-02 | 62
2024 | Region III | AURORA | BALER (CAPITAL) (AURORA) | P00821221LZ | Construction of Flood Mitigation Structure | 121.5556 | 15.782 | 146679656.5 | 146679617.4 | 2024 | PERSAN CONSTRUCTION, INC. (FORMERLY: PERSAN CONST. / 4VC BUILDERS & DEVELOPMENT CORP. | 5675 | 2024 | 2024-12-31 | 05/06/2024 | 39.1 | 0 | 2025-04-29 | 119
2023 | Region II | CAGAYAN | BUGUEY (CAGAYAN) | P00742293LZ | Construction of Flood Mitigation Structure | 121.8369 | 18.2894 | 19800000 | 19754081.38 | 2024 | REYROSE CONSTRUCTION | 5676 | 2023 | 2024-07-29 | 04/04/2023 | 45918.62 | 0 | 2023-11-08 |  | 264
2021 | Region IX | ZAMBOANGA DEL SUR |  | P00522141MN | Construction of Flood Mitigation Structure | 121.904 | 7.1332 | 46060000 | 39544872.43 | 2022 | JAMARI CONSTRUCTION (FORMERLY FRAE CONSTRUCTION) | 5677 | 2021 | 2022-08-25 | 06/15/2021 | 6515127.57 | 0 | 2022-09-26 | 32
2023 | Region VI | ILOILO | MIAGAO (ILOILO) | P00733298VS | Construction of Flood Mitigation Structure | 122.2361 | 10.6497 | 49000000 | 48489591.89 | 2024 | PANAY EAST COAST CONSTRUCTION & SUPPLY | 5678 | 2023 | 2024-03-01 | 03/31/2023 | 510408.11 | 0 | 2024-02-03 |  | 27
2023 | Region IV-B | MARINDUQUE | BUENAVISTA (MARINDUQUE) | P00736049LZ | Construction of Revetment | 121.9997 | 13.2033 | 192999999.1 | 192997859.2 | 2023 | HGG BUILDERS & SUPPLY | 5679 | 2023 | 2023-12-15 | 02/11/2023 | 2139.9 | 0 | 2024-02-04 | 51
2022 | Cordillera Administrative Region | IFUGAO | AGUINALDO (IFUGAO) | P00620482LZ | Construction of Flood Mitigation Structure | 121.4354 | 16.9294 | 76237286.54 | 20914465.8 | 2023 | DJY CONSTRUCTION / RODEKOM GENERAL CONSTRUCTION AND ENTERPRISE | 5680 | 2022 | 2023-03-05 | 05/23/2022 | 55322820.74 | 0 | 2023-03-04 |  | 1
2023 | Region IV-B | ORIENTAL MINDORO | ROXAS (ORIENTAL MINDORO) | P00736623LZ | Construction of Flood Mitigation Structure | 121.5558 | 12.6147 | 48999993.45 | 48995230.55 | 2023 | L.N. SALVADOR CONSTRUCTION CORP. (FOR: L.N. SALVADOR CONSTRUCTION) | 5681 | 2023 | 2023-12-15 | 02/17/2023 | 4762.9 | 0 | 2024-01-01 | 17
2023 | Region II | ISABELA | TUMAUINI (ISABELA) | P00725672LZ | Construction of Revetment | 121.8376 | 17.2528 | 109187000 | 109085393.8 | 2024 | EGB CONSTRUCTION CORPORATION (FORMERLY: EGB CONSTRUCTION) | 5682 | 2023 | 2024-08-23 | 05/25/2023 | 101606.2 | 0 | 2024-08-24 | 1
2021 | Region IX | ZAMBOANGA DEL SUR |  | P00522041MN | Construction of Flood Mitigation Structure | 121.9042 | 7.1231 | 77200000 | 75410486.7 | 2022 | RCDG CONSTRUCTION CORPORATION | 5683 | 2021 | 2022-07-29 | 07/05/2021 | 1789513.3 | 0 | 2022-07-30 | 1
2023 | Region II | ISABELA | SAN MARIANO (ISABELA) | P00726696LZ | Construction of Flood Mitigation Structure | 122.0019 | 16.7585 | 48679424.61 | 48668725.8 | 2023 | YZK BUILDERS | 5684 | 2023 | 2023-09-15 | 03/15/2023 | 10698.81 | 0 | 2023-10-16 | 31
2022 | Region II | CAGAYAN | IGUIG (CAGAYAN) | P00620815LZ | Construction of Flood Mitigation Structure | 121.7097 | 17.7711 | 77200000 | 77200000 | 2023 | MEGAY CONSTRUCTION INC. (FORMERLY: MEGAY CONSTRUCTION) | 5685 | 2022 | 2023-12-31 | 03/28/2022 | 0 | 0 | 2023-04-18 |  | 257
2023 | Region IV-B | ORIENTAL MINDORO | MANSALAY (ORIENTAL MINDORO) | P00727320LZ | Construction of Revetment | 121.4356 | 12.6294 | 82024995.07 | 82022284.76 | 2023 | LUMEL GLENN CONSTRUCTION | 5686 | 2023 | 2023-12-15 | 03/24/2023 | 2710.31 | 0 | 2024-02-20 | 67
2023 | Region II | BATANES | SABTANG (BATANES) | P00737440LZ | Construction of Flood Mitigation Structure | 121.8387 | 20.3266 | 9891344 | 7397729.67 | 2024 | JERIS CONSTRUCTION AND SUPPLY | 5687 | 2023 | 2024-11-13 | 04/04/2023 | 2493614.33 | 0 | 2024-04-02 |  | 225
2022 | Region VI | ILOILO | MIAGAO (ILOILO) | P00630199VS | Construction of Slope Protection Structure | 122.2379 | 10.6375 | 49000000 | 48999199.58 | 2023 | IBC INTERNATIONAL BUILDERS CORPORATION | 5688 | 2022 | 2023-04-10 | 02/10/2022 | 800.42 | 0 | 2023-04-09 |  | 1
2022 | Region IV-B | MARINDUQUE | MOGPOG (MARINDUQUE) | P00632925LZ | Construction of Flood Mitigation Structure | 121.9045 | 13.4823 | 4948000 | 4848665 | 2022 | SAMARAH CONSTRUCTION AND SUPPLY | 5689 | 2022 | 2022-07-06 | 02/16/2022 | 99335 | 0 | 2022-07-05 |  | 1
2022 | Region II | CAGAYAN | ENRILE (CAGAYAN) | P00620831LZ | Construction of Flood Mitigation Structure | 121.71 | 17.57 | 92157500 | 92157500 | 2023 | M.E. SICAT CONSTRUCTION, INC. (FORMERLY M.E. SICAT | 5690 | 2022 | 2023-12-19 | 03/28/2022 | 0 | 0 | 2023-01-07 |  | 346
2023 | Region IX | ZAMBOANGA DEL SUR | ZAMBOANGA CITY (ZAMBOANGA DEL SUR) | P00721593MN | Construction of Flood Mitigation Structure | 122.0045 | 6.9439 | 19600000 | 19550054.94 | 2023 | HENSO CONSTRUCTION INC. | 5691 | 2023 | 2023-08-22 | 03/16/2023 | 49945.06 | 0 | 2023-09-20 | 29
2022 | Region II | CAGAYAN | ABULUG (CAGAYAN) | P00621041LZ | Construction of Flood Mitigation Structure | 121.4358 | 18.3622 | 49000000 | 48128215 | 2023 | MEGAY CONSTRUCTION INC. (FORMERLY: MEGAY CONSTRUCTION) | 5692 | 2022 | 2023-02-28 | 02/23/2022 | 871785 | 0 | 2022-12-08 |  | 82
2023 | Region III | AURORA | BALER (CAPITAL) (AURORA) | P00727283LZ | Construction of Flood Mitigation Structure | 121.5563 | 15.7857 | 192999672.3 | 192999618.7 | 2024 | PERSAN CONSTRUCTION, INC. (FORMERLY: PERSAN CONST. / 4VC BUILDERS & DEVELOPMENT CORP. | 5693 | 2023 | 2024-03-31 | 07/06/2023 | 53.6 | 0 | 2024-09-05 | 158
2023 | Region VI | ILOILO | MIAGAO (ILOILO) | P00721649VS | Construction of Flood Mitigation Structure | 122.2394 | 10.6369 | 49000000 | 48484748.19 | 2024 | A.D. PENDON CONSTRUCTION & SUPPLY, INC. (FORMERLY: ADP CONSTRUCTION & SUPPLY) | 5694 | 2023 | 2024-02-27 | 04/05/2023 | 515251.81 | 0 | 2024-02-08 |  | 19
2023 | Region III | AURORA | BALER (CAPITAL) (AURORA) | P00737444LZ | Construction of Drainage Structure | 121.5565 | 15.7685 | 9900000 | 9900000 | 2023 | FORTHRIGHT CONSTRUCTION | 5695 | 2023 | 2023-09-25 | 04/27/2023 | 0 | 0 | 2023-09-24 |  | 1
2022 | Region II | CAGAYAN | SOLANA (CAGAYAN) | P00621500LZ | Construction of Flood Mitigation Structure | 121.7126 | 17.6749 | 19300000 | 19001115.52 | 2023 | RPF CONSTRUCTION | 5696 | 2022 | 2023-03-13 | 03/28/2022 | 298884.48 | 0 | 2023-03-12 |  | 1
2023 | Region IV-B | MARINDUQUE | MOGPOG (MARINDUQUE) | P00737545LZ | Construction of Flood Mitigation Structure | 121.906 | 13.4808 | 9898000 | 9700039.98 | 2023 | KURDZ CONSTRUCTION | 5697 | 2023 | 2023-05-10 | 01/31/2023 | 197960.02 | 0 | 2023-05-09 |  | 1
2022 | Region IV-A | LAGUNA | LILIW (LAGUNA) | P00620592LZ | Construction of Slope Protection Structure | 121.4365 | 14.134 | 43120000 | 43120000 | 2023 | MORTAR MASTERS & CONCRETE BUILDERS | 5698 | 2022 | 2023-08-16 | 01/28/2022 | 0 | 0 | 2023-08-15 |  | 1
2024 | Region IV-A | QUEZON | POLILLO (QUEZON) | P00846080LZ | Construction of Flood Mitigation Structure | 122.0049 | 14.6707 | 4950000 | 4949850.67 | 2024 | C. VILLASEÃ‘OR JR. CONSTRUCTION | 5699 | 2024 | 2024-08-10 | 05/28/2024 | 149.33 | 0 | 2024-08-09 |  | 1
2021 | Region II | ISABELA |  | P00525967LZ | Construction of Flood Mitigation Structure | 122.2398 | 16.5074 | 42140000 | 42140000 | 2022 | DANYSONS CONSTRUCTION AND DEVELOPMENT CORPORATION (FORMERLY: DANYSONS CONSTRUCTION) | 5700 | 2021 | 2022-08-01 | 01/10/2022 | 0 | 0 | 2022-08-13 | 12
2023 | Cordillera Administrative Region | MOUNTAIN PROVINCE | PARACELIS (MOUNTAIN PROVINCE) | P00725657LZ | Construction of Flood Mitigation Structure | 121.5566 | 17.1983 | 67550000 | 67550000 | 2023 | UPLAND CONSTRUCTION AND ENGINEERING SERVICES | 5701 | 2023 | 2023-10-17 | 02/01/2023 | 0 | 0 | 2023-10-20 | 3
2022 | Region II | BATANES | SABTANG (BATANES) | P00632791LZ | Construction of Flood Mitigation Structure | 121.8388 | 20.3262 | 9900000 | 8338455.58 | 2022 | CVAP CONSTRUCTION | 5702 | 2022 | 2022-12-31 | 03/23/2022 | 1561544.42 | 0 | 2022-11-30 |  | 31
2024 | Region II | ISABELA | QUIRINO (ISABELA) | P00824892LZ | Construction of Flood Mitigation Structure | 121.7133 | 17.1005 | 96500000 | 96483409.58 | 2024 | JWU CONSTRUCTION AND SUPPLY | 5703 | 2024 | 2024-05-06 | 04/15/2024 | 16590.42 | 0 | 2025-03-18 | 316
2024 | Region IV-B | MARINDUQUE | BOAC (CAPITAL) (MARINDUQUE) | P00820403LZ | Construction of Flood Mitigation Structure | 121.9072 | 13.4069 | 88629390 | 88629520.01 | 2024 | DQT BUILDERS CORPORATION (FORMERLY DQT BUILDERS) / G.T.J. CONSTRUCTION | 5704 | 2024 | 2024-11-23 | 02/19/2024 | 0 | 130.01 | 2024-11-22 |  | 1
2023 | Region IV-A | BATANGAS | SAN JUAN (BATANGAS) | P00726543LZ | Construction of Revetment | 121.4374 | 13.8108 | 96500000 | 96500000 | 2023 | THREE W BUILDERS, INC. | 5705 | 2023 | 2023-09-18 | 02/13/2023 | 0 | 0 | 2023-11-30 | 73
2022 | Region VI | ILOILO | MIAGAO (ILOILO) | P00620429VS | Construction of Flood Mitigation Structure | 122.2399 | 10.6386 | 14700000 | 14664114.09 | 2022 | ABRIGHT BUILDERS CORPORATION | 5706 | 2022 | 2022-12-03 | 03/29/2022 | 35885.91 | 0 | 2022-12-02 |  | 1
2024 | Region III | AURORA | BALER (CAPITAL) (AURORA) | P00823461LZ | Construction of Flood Mitigation Structure | 121.559 | 15.7491 | 96500000 | 96500000 | 2024 | MORNING STEEL CONSTRUCTION / ALEXI LOUISSE CONSTRUCTION & GENERAL MERCHANDISE | 5707 | 2024 | 2024-12-14 | 02/05/2024 | 0 | 0 | 2024-12-13 |  | 1
2023 | Region IV-A | BATANGAS | SAN JUAN (BATANGAS) | P00726552LZ | Construction of Revetment | 121.4374 | 13.811 | 76235000 | 76235000 | 2023 | VICMAR CONSTRUCTION, INC. / FRANDEL CONSTRUCTION AND DEVELOPMENT CORP. | 5708 | 2023 | 2023-10-26 | 02/13/2023 | 0 | 0 | 2023-10-25 |  | 1
2022 | Region II | ISABELA | QUIRINO (ISABELA) | P00631120LZ | Construction of Flood Mitigation Structure | 121.7139 | 17.1098 | 42140000 | 41507408.17 | 2022 | DANYSONS CONSTRUCTION AND DEVELOPMENT CORPORATION (FORMERLY: DANYSONS CONSTRUCTION) | 5709 | 2022 | 2022-12-13 | 03/14/2022 | 632591.83 | 0 | 2022-12-14 | 1
2023 | Region II | ISABELA | JONES (ISABELA) | P00736189LZ | Construction of Flood Mitigation Structure | 121.908 | 16.5893 | 49000000 | 48998504.16 | 2023 | DANYSONS CONSTRUCTION AND DEVELOPMENT CORPORATION (FORMERLY: DANYSONS CONSTRUCTION) | 5710 | 2023 | 2023-12-02 | 02/22/2023 | 1495.84 | 0 | 2023-12-03 | 1
2022 | Region IV-A | QUEZON | PLARIDEL (QUEZON) | P00620609LZ | Construction of Flood Mitigation Structure | 122.0053 | 13.9413 | 9800000 | 9800000 | 2022 | JEMAK CONSTRUCTION & SUPPLY | 5711 | 2022 | 2022-07-14 | 02/15/2022 | 0 | 0 | 2022-07-13 |  | 1
2023 | Region VI | AKLAN | TANGALAN (AKLAN) | P00733713VS | Repair/Maintenance of Flood Control Structures | 122.242 | 11.7613 | 9900000 | 9898994.31 | 2024 | G.F. ROVERO MERCHANDISING | 5712 | 2023 | 2024-02-07 | 05/22/2023 | 1005.69 | 0 | 2024-02-11 | 4
2023 | Region IV-B | MARINDUQUE | MOGPOG (MARINDUQUE) | P00736046LZ | Construction of Revetment | 121.839 | 13.4862 | 192999999 | 192995358.3 | 2024 | MAG KONSTRUCTION & SUPPLY INC. / MONOLITHIC CONSTRUCTION & CONCRETE PRODUCTS, INC. | 5713 | 2023 | 2024-04-25 | 02/11/2023 | 4640.7 | 0 | 2024-04-24 |  | 1
2022 | Cordillera Administrative Region | IFUGAO | ALFONSO LISTA (POTIA) (IFUGAO) | P00620139LZ | Construction of Flood Mitigation Structure | 121.5608 | 16.9444 | 65778152.24 | 65780190 | 2023 | DJY CONSTRUCTION | 5714 | 2022 | 2023-07-21 | 08/09/2022 | 0 | 2037.76 | 2023-07-20 |  | 1
2024 | Region II | CAGAYAN | ABULUG (CAGAYAN) | P00821220LZ | Rehabilitation / Major Repair of Flood Mitigation Facility | 121.4375 | 18.4078 | 72375000 | 72370157.8 | 2024 | CMG JR. BUILDERS / J. AURELLANO CONSTRUCTION | 5715 | 2024 | 2024-08-09 | 02/02/2024 | 4842.2 | 0 | 2024-09-04 | 26
2021 | Region II | ISABELA |  | P00525958LZ | Construction of Flood Mitigation Structure | 121.7156 | 16.7339 | 29399980.73 | 29399986.97 | 2022 | ADVANCED FOUNDATION CONSTRUCTION SYSTEMS CORP. / INFINITUM 888 CONSTRUCTION AND DEVELOPMENT CORPORATION | 5716 | 2021 | 2022-11-03 | 04/13/2022 | 0 | 6.24 | 2022-11-29 | 26
2023 | Region IX | ZAMBOANGA DEL SUR | ZAMBOANGA CITY (ZAMBOANGA DEL SUR) | P00734016MN | Construction of Flood Mitigation Structure | 121.9081 | 7.1011 | 29400000 | 29349867.01 | 2023 | MOTHER'S ROLE CONSTRUCTION | 5717 | 2023 | 2023-08-25 | 04/24/2023 | 50132.99 | 0 | 2023-12-27 | 124
2022 | Region VI | ILOILO | IGBARAS (ILOILO) | P00620086VS | Construction of Flood Mitigation Structure | 122.2426 | 10.7409 | 4900000 | 4886195.03 | 2022 | VEONG CONSTRUCTION & SUPPLY | 5718 | 2022 | 2022-12-19 | 08/04/2022 | 13804.97 | 0 | 2022-12-04 |  | 15
2023 | Region II | ISABELA | GAMU (ISABELA) | P00726697LZ | Construction of Flood Mitigation Structure | 121.8397 | 17.07 | 44099947.03 | 43438480.05 | 2023 | A. DE GUIA CONSTRUCTION AND DEVELOPMENT CORPORATION (FORMERLY: A. DE GUIA CONSTRUCTION) | 5719 | 2023 | 2023-06-07 | 03/08/2023 | 661466.98 | 0 | 2023-10-15 | 130
2023 | Region II | ISABELA | ANGADANAN (ISABELA) | P00727264LZ | Construction of Flood Mitigation Structure | 121.7167 | 16.733 | 95858908.16 | 95847472.62 | 2023 | MAV CONSTRUCTION SUPPLY AND POWER DEVELOPMENT / C.R. DOMINGO CONSTRUCTION AND POWER DEVELOPMENT, INC. (FOR. C.R. DOMINGO CONSTRUCTION, INC.) | 5720 | 2023 | 2023-08-18 | 03/15/2023 | 11435.54 | 0 | 2024-02-01 | 167
2023 | Region III | AURORA | BALER (CAPITAL) (AURORA) | P00737443LZ | Construction of Drainage Structure | 121.5623 | 15.7597 | 6930000 | 6930000 | 2023 | RADIANCE TRADERS & BUILDERS | 5721 | 2023 | 2023-12-18 | 06/13/2023 | 0 | 0 | 2023-09-12 |  | 97
2023 | Cordillera Administrative Region | KALINGA | CITY OF TABUK (CAPITAL) (KALINGA) | P00736181LZ | Construction of Flood Mitigation Structure | 121.4378 | 17.4601 | 29126922.2 | 29100540.73 | 2023 | QUIÃ‘ONES CONSTRUCTION | 5722 | 2023 | 2023-06-20 | 02/20/2023 | 26381.47 | 0 | 2023-07-18 | 28
2023 | Region II | BATANES | SABTANG (BATANES) | P00726105LZ | Construction of Flood Mitigation Structure | 121.8401 | 20.3336 | 9791344 | 9761069.11 | 2023 | J.F. GABOTERO, INC. | 5723 | 2023 | 2023-06-15 | 02/15/2023 | 30274.89 | 0 | 2023-12-22 | 190
2023 | Region VI | ILOILO | MIAGAO (ILOILO) | P00733296VS | Construction of Flood Mitigation Structure | 122.2467 | 10.6362 | 49000000 | 48456649.66 | 2024 | A.D. PENDON CONSTRUCTION & SUPPLY, INC. (FORMERLY: ADP CONSTRUCTION & SUPPLY) | 5724 | 2023 | 2024-03-08 | 03/29/2023 | 543350.34 | 0 | 2024-02-01 |  | 36
2023 | Region IV-B | MARINDUQUE | MOGPOG (MARINDUQUE) | P00727178LZ | Construction of Flood Mitigation Structure | 121.9081 | 13.4792 | 48998000 | 48998898.55 | 2024 | R.S. TAGALA CONSTRUCTION AND EQUIPMENT RENTALS / SIXTEEN ENTERPRISES-CALAPAN BRANCH | 5725 | 2023 | 2024-03-13 | 03/28/2023 | 0 | 898.55 | 2024-02-12 |  | 30
2022 | Region II | ISABELA | QUIRINO (ISABELA) | P00621564LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.7167 | 17.1109 | 67550000 | 67549855.42 | 2023 | DANYSONS CONSTRUCTION AND DEVELOPMENT CORPORATION (FORMERLY: DANYSONS CONSTRUCTION) | 5726 | 2022 | 2023-03-15 | 06/06/2022 | 144.58 | 0 | 2023-03-19 | 4
2024 | Region III | AURORA | BALER (CAPITAL) (AURORA) | P00820800LZ | Construction of Flood Mitigation Structure | 121.5623 | 15.7485 | 49000000 | 49000000 | 2024 | MORNING STEEL CONSTRUCTION | 5727 | 2024 | 2024-11-24 | 03/05/2024 | 0 | 0 | 2024-11-23 |  | 1
2024 | Region IV-B | ROMBLON | ODIONGAN (ROMBLON) | P00823585LZ | Construction of Flood Mitigation Structure | 122.0061 | 12.405 | 96499999.45 | 96484539.95 | 2025 | SCATR CONSTRUCTION | 5728 | 2024 | 2025-02-21 | 03/19/2024 | 15459.5 | 0 | 2025-02-20 |  | 1
2021 | Region II | CAGAYAN |  | P00525952LZ | Construction of Flood Mitigation Structure | 121.4378 | 18.4066 | 49000000 | 49000000 | 2022 | ASC CONSTRUCTION & CONCRETE PRODUCTS | 5729 | 2021 | 2022-07-11 | 11/26/2021 | 0 | 0 | 2022-07-10 |  | 1
2022 | Region IV-B | MARINDUQUE | BOAC (CAPITAL) (MARINDUQUE) | P00632926LZ | Construction of Drainage Structure | 121.8405 | 13.4491 | 14848000 | 14792987.32 | 2023 | YURUSA CONSTRUCTION & DEVELOPMENT CORP. | 5730 | 2022 | 2023-08-04 | 03/01/2022 | 55012.68 | 0 | 2022-09-23 |  | 315
2023 | Region II | ISABELA | QUIRINO (ISABELA) | P00726423LZ | Construction of Flood Mitigation Structure | 121.7167 | 17.1109 | 48250000 | 48248898.3 | 2023 | RRC CO. INC. (FORMERLY: R R C CONSTRUCTION) | 5731 | 2023 | 2023-09-24 | 02/27/2023 | 1101.7 | 0 | 2023-09-23 |  | 1
2023 | Region II | CAGAYAN | ABULUG (CAGAYAN) | P00727269LZ | Construction of Flood Mitigation Structure | 121.4381 | 18.4049 | 67550000 | 67550000 | 2023 | TJMT CONSTRUCTION | 5732 | 2023 | 2023-08-22 | 03/20/2023 | 0 | 0 | 2023-10-17 | 56
2023 | Region II | ISABELA | ILAGAN CITY (CAPITAL) (ISABELA) | P00726123LZ | Construction of Flood Mitigation Structure | 121.9106 | 17.2193 | 49000000 | 48994848.5 | 2023 | DRAGON TWELVE BUILDERS & CONSTRUCTION SUPPLY | 5733 | 2023 | 2023-11-08 | 03/02/2023 | 5151.5 | 0 | 2023-12-08 | 30
2024 | Region II | ISABELA | CITY OF SANTIAGO (ISABELA) | P00845944LZ | Construction of Slope Protection Structure | 121.5635 | 16.6579 | 4950000 | 4939562.86 | 2024 | CASAN CONSTRUCTION AND TRADING | 5734 | 2024 | 2024-09-14 | 06/19/2024 | 10437.14 | 0 | 2024-10-02 | 18
2022 | Region IX | ZAMBOANGA DEL SUR | ZAMBOANGA CITY (ZAMBOANGA DEL SUR) | P00630565MN | Construction of Slope Protection Structure | 122.0069 | 6.9371 | 19600000 | 19599660.32 | 2022 | TEDDIE CONSTRUCTION DEVELOPMENT, INC. | 5735 | 2022 | 2022-12-21 | 03/23/2022 | 339.68 | 0 | 2023-01-02 | 12
2022 | Region IV-A | QUEZON | LOPEZ (QUEZON) | P00620607LZ | Construction of Flood Mitigation Structure | 122.2561 | 13.8901 | 19600000 | 19600000 | 2022 | MURIELEVEN BUILDERS AND CONSTRUCTION SUPPLY CORP. | 5736 | 2022 | 2022-11-09 | 02/16/2022 | 0 | 0 | 2022-11-08 |  | 1
2023 | Region II | ISABELA | NAGUILIAN (ISABELA) | P00726692LZ | Construction of Flood Mitigation Structure | 121.8409 | 17.0367 | 44099994.23 | 43783286.72 | 2023 | YZK BUILDERS | 5737 | 2023 | 2023-06-16 | 03/14/2023 | 316707.51 | 0 | 2023-10-22 | 128
2021 | Region II | ISABELA |  | P00525565LZ | Construction of Flood Mitigation Structure | 121.5664 | 16.6787 | 96500000 | 96500000 | 2022 | ROAD EDGE TRADING & DEVELOPMENT SERVICES | 5738 | 2021 | 2022-09-27 | 12/07/2021 | 0 | 0 | 2022-09-27 | 0
2023 | Region IV-A | QUEZON | AGDANGAN (QUEZON) | P00742442LZ | Construction of Flood Mitigation Structure | 121.9113 | 13.8701 | 24499634.5 | 24750000 | 2023 | R.A. MENDIOLA CONSTRUCTION & DEVELOPER | 5739 | 2023 | 2023-08-15 | 03/30/2023 | 0 | 250365.5 | 2023-10-24 | 70
2022 | Region IV-B | ORIENTAL MINDORO | BONGABONG (ORIENTAL MINDORO) | P00632937LZ | Construction of Flood Mitigation Structure | 121.4403 | 12.6681 | 17324395.64 | 17324354.24 | 2022 | E E CONSTRUCTION | 5740 | 2022 | 2022-07-26 | 02/16/2022 | 41.4 | 0 | 2022-08-08 | 13
2023 | Region II | ISABELA | SAN MARIANO (ISABELA) | P00726701LZ | Construction of Flood Mitigation Structure | 122.0078 | 16.9149 | 48679457.26 | 48184997.98 | 2023 | CAMBERWELL CONSTRUCTION AND SUPPLIES | 5741 | 2023 | 2023-11-10 | 04/04/2023 | 494459.28 | 0 | 2023-11-02 |  | 8
2023 | Region IV-A | QUEZON | LOPEZ (QUEZON) | P00726232LZ | Construction of Flood Mitigation Structure | 122.2574 | 13.8812 | 49000000 | 49000000 | 2024 | R.A. MENDIOLA CONSTRUCTION & DEVELOPER | 5742 | 2023 | 2024-01-14 | 02/08/2023 | 0 | 0 | 2024-02-03 | 20
2022 | Region II | ISABELA | GAMU (ISABELA) | P00631122LZ | Construction of Flood Mitigation Structure | 121.8416 | 17.068 | 44099998.29 | 43172489.53 | 2022 | ROAD EDGE TRADING & DEVELOPMENT SERVICES | 5743 | 2022 | 2022-11-08 | 03/28/2022 | 927508.76 | 0 | 2022-11-07 |  | 1
2023 | Region II | CAGAYAN | LASAM (CAGAYAN) | P00742300LZ | Construction of Flood Mitigation Structure | 121.567 | 18.0576 | 4950000 | 4800079.75 | 2023 | HHK CONSTRUCTION | 5744 | 2023 | 2023-06-17 | 03/27/2023 | 149920.25 | 0 | 2023-06-16 |  | 1
2023 | Region IV-A | QUEZON | AGDANGAN (QUEZON) | P00742169LZ | Construction of Flood Mitigation Structure | 121.9119 | 13.8757 | 96499426.07 | 99000000 | 2023 | AMETHYST HORIZON BUILDERS AND GEN. CONTRACTOR AND DEVELOPMENT CORP. | 5745 | 2023 | 2023-12-06 | 04/11/2023 | 0 | 2500573.93 | 2024-07-02 | 209
2022 | Region IX | ZAMBOANGA DEL SUR | ZAMBOANGA CITY (ZAMBOANGA DEL SUR) | P00631082MN | Construction of Flood Mitigation Structure | 121.9129 | 7.0307 | 39195927.69 | 39549988.07 | 2022 | LONG ISLAND BUILDERS & CONSTRUCTION | 5746 | 2022 | 2022-10-17 | 03/23/2022 | 0 | 354060.38 | 2022-10-16 |  | 1
2024 | Region II | ISABELA | ANGADANAN (ISABELA) | P00824867LZ | Construction of Flood Mitigation Structure | 121.7188 | 16.7308 | 77199975.42 | 77164336.44 | 2025 | INFINITUM 888 CONSTRUCTION AND DEVELOPMENT CORPORATION / ALGO CONSTRUCTION AND POWER DEVELOPMENT, INC. | 5747 | 2024 | 2025-02-28 | 07/17/2024 | 35638.98 | 0 | 2025-05-02 | 63
2023 | Region II | ISABELA | SAN MARIANO (ISABELA) | P00726699LZ | Construction of Flood Mitigation Structure | 122.0086 | 16.9715 | 48999987.13 | 48504957.56 | 2023 | CAMBERWELL CONSTRUCTION AND SUPPLIES | 5748 | 2023 | 2023-09-18 | 04/25/2023 | 495029.57 | 0 | 2023-11-26 | 69
2023 | Region IV-B | MARINDUQUE | BOAC (CAPITAL) (MARINDUQUE) | P00742453LZ | Construction of Flood Mitigation Structure | 121.8418 | 13.4826 | 19798000 | 18550221.21 | 2023 | JEDIDIAH CONSTRUCTION | 5749 | 2023 | 2023-09-19 | 03/28/2023 | 1247778.79 | 0 | 2023-09-18 |  | 1
2022 | Region VI | AKLAN | TANGALAN (AKLAN) | P00620075VS | Construction of Revetment | 122.2578 | 11.7734 | 49000000 | 48999981.58 | 2023 | ALPHA & OMEGA GEN. CONTRACTOR & DEVELOPMENT CORP. | 5750 | 2022 | 2023-11-20 | 02/18/2022 | 18.42 | 0 | 2023-04-10 |  | 224
2024 | Region II | ISABELA | ROXAS (ISABELA) | P00820171LZ | Construction of Flood Mitigation Structure | 121.5685 | 17.1366 | 89384090 | 89383813.47 | 2024 | JWU CONSTRUCTION AND SUPPLY | 5751 | 2024 | 2024-04-06 | 02/12/2024 | 276.53 | 0 | 2025-02-02 | 302
2023 | Region II | ISABELA | JONES (ISABELA) | P00727112LZ | Construction of Flood Mitigation Structure | 121.719 | 16.5322 | 49000000 | 48997541.39 | 2023 | GACUTAN CONSTRUCTION INC. (FORMERLY: GACUTAN CONSTRUCTION) | 5752 | 2023 | 2023-08-17 | 04/11/2023 | 2458.61 | 0 | 2023-12-07 | 112
2022 | Region IV-B | ORIENTAL MINDORO | MANSALAY (ORIENTAL MINDORO) | P00632938LZ | Construction of Flood Mitigation Structure | 121.4403 | 12.5433 | 4949844.51 | 4949872.82 | 2022 | J.A. BUILDERS AND SUPPLY | 5753 | 2022 | 2022-09-11 | 04/11/2022 | 0 | 28.31 | 2022-09-10 |  | 1
2024 | Region II | BATANES | SABTANG (BATANES) | P00820777LZ | Construction of Flood Mitigation Structure | 121.8423 | 20.301 | 9800000 | 9779993.66 | 2024 | J.F. GABOTERO, INC. | 5754 | 2024 | 2024-05-28 | 03/11/2024 | 20006.34 | 0 | 2025-01-18 | 235
2022 | Region II | BATANES | SABTANG (BATANES) | P00632796LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.9141 | 20.3676 | 6930000 | 5973946.32 | 2022 | CVAP CONSTRUCTION | 5755 | 2022 | 2022-11-09 | 03/23/2022 | 956053.68 | 0 | 2022-11-27 | 18
2024 | Region IV-B | ROMBLON | LOOC (ROMBLON) | P00823597LZ | Construction of Flood Mitigation Structure | 122.0088 | 12.2933 | 91674999.95 | 91674999.76 | 2024 | SUNWEST, INC. (FORMERLY: SUNWEST CONSTRUCTION & DEVELOPMENT CORPORATION) | 5756 | 2024 | 2024-09-23 | 04/08/2024 | 0.19 | 0 | 2025-03-02 | 160
2022 | Region VI | AKLAN | TANGALAN (AKLAN) | P00620010VS | Construction of Revetment | 122.2605 | 11.7713 | 86850000 | 86849991.48 | 2023 | ST. TIMOTHY CONSTRUCTION CORPORATION | 5757 | 2022 | 2023-01-25 | 02/18/2022 | 8.52 | 0 | 2023-01-25 | 0
2023 | Region II | ISABELA | NAGUILIAN (ISABELA) | P00726429LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.843 | 17.0372 | 43136512.02 | 43116512.02 | 2023 | ROAD EDGE TRADING & DEVELOPMENT SERVICES | 5758 | 2023 | 2023-07-20 | 03/15/2023 | 20000 | 0 | 2023-10-19 | 91
2023 | Region II | CAGAYAN | SANTO NIÃ‘O (FAIRE) (CAGAYAN) | P00727271LZ | Construction of Flood Mitigation Structure | 121.5699 | 17.8582 | 49215000 | 48229745.38 | 2024 | AGAFER CONSTRUCTION AND TRADING CORPORATION (FOR: AGAFER CONSTRUCTION AND TRADING) | 5759 | 2023 | 2024-02-06 | 03/20/2023 | 985254.62 | 0 | 2023-11-26 |  | 72
2023 | Region II | ISABELA | JONES (ISABELA) | P00740316LZ | Construction of Flood Mitigation Structure | 121.7191 | 16.5486 | 96500000 | 96499663.2 | 2023 | MAR-DEB CONSTRUCTION & DEVELOPMENT CORP. (FORMERLY: MAR-DEB CONSTRUCTION & DEVELOPMENT) | 5760 | 2023 | 2023-09-04 | 04/17/2023 | 336.8 | 0 | 2024-02-06 | 155
2023 | Region III | AURORA | MARIA AURORA (AURORA) | P00737442LZ | Construction of Drainage Structure | 121.4404 | 15.7733 | 5940000 | 5763972.54 | 2023 | VANMARVIL CONSTRUCTION | 5761 | 2023 | 2023-10-23 | 04/27/2023 | 176027.46 | 0 | 2023-05-30 |  | 146
2023 | Region II | ISABELA | GAMU (ISABELA) | P00726691LZ | Construction of Flood Mitigation Structure | 121.8437 | 17.0643 | 44099995.81 | 43437238 | 2023 | DANYSONS CONSTRUCTION AND DEVELOPMENT CORPORATION (FORMERLY: DANYSONS CONSTRUCTION) | 5762 | 2023 | 2023-06-05 | 03/08/2023 | 662757.81 | 0 | 2023-10-15 | 132
2022 | Region II | CAGAYAN | TUGUEGARAO CITY (CAPITAL) (CAGAYAN) | P00621044LZ | Construction of Flood Mitigation Structure | 121.7194 | 17.6254 | 15680000 | 15680000 | 2023 | DEKM CONSTRUCTION | 5763 | 2022 | 2023-06-15 | 03/28/2022 | 0 | 0 | 2023-06-08 |  | 7
2024 | Region II | ISABELA | DINAPIGUE (ISABELA) | P00843181LZ | Construction of Flood Mitigation Structure | 122.2621 | 16.5332 | 96500000 | 96500000 | 2025 | DALCON CONSTRUCTION | 5764 | 2024 | 2025-02-15 | 09/24/2024 | 0 | 0 | 2025-12-09 | 297
2022 | Region II | ISABELA | ILAGAN CITY (CAPITAL) (ISABELA) | P00621051LZ | Construction of Flood Mitigation Structure | 121.9162 | 17.1158 | 48999706.95 | 48949706.95 | 2022 | EGB CONSTRUCTION CORPORATION (FORMERLY: EGB CONSTRUCTION) | 5765 | 2022 | 2022-11-09 | 02/24/2022 | 50000 | 0 | 2022-11-09 | 0
2023 | Region II | ISABELA | SAN MARIANO (ISABELA) | P00726443LZ | Construction of Flood Mitigation Structure | 122.0089 | 16.981 | 96499992.77 | 96301840.45 | 2024 | RRC CO. INC. (FORMERLY: R R C CONSTRUCTION) | 5766 | 2023 | 2024-04-22 | 06/08/2023 | 198152.32 | 0 | 2024-04-25 | 3
2022 | Region IV-B | ORIENTAL MINDORO | POLA (ORIENTAL MINDORO) | P00639525LZ | Construction of Flood Mitigation Structure | 121.4406 | 13.14 | 7840000 | 7839977.45 | 2022 | MARC JILL CONSTRUCTION | 5767 | 2022 | 2022-10-14 | 07/14/2022 | 22.55 | 0 | 2022-10-13 |  | 1
2023 | Region II | ISABELA | JONES (ISABELA) | P00740315LZ | Construction of Flood Mitigation Structure | 121.7198 | 16.5512 | 96500000 | 96500000 | 2023 | MAR-DEB CONSTRUCTION & DEVELOPMENT CORP. (FORMERLY: MAR-DEB CONSTRUCTION & DEVELOPMENT) | 5768 | 2023 | 2023-09-08 | 05/12/2023 | 0 | 0 | 2024-03-03 | 177
2022 | Region II | ISABELA | CITY OF SANTIAGO (ISABELA) | P00620823LZ | Construction of Flood Mitigation Structure | 121.57 | 16.6892 | 70445000 | 70445000 | 2022 | MAR-DEB CONSTRUCTION & DEVELOPMENT CORP. (FORMERLY: MAR-DEB CONSTRUCTION & DEVELOPMENT) | 5769 | 2022 | 2022-07-18 | 02/17/2022 | 0 | 0 | 2022-10-13 | 87
2023 | Region IX | ZAMBOANGA DEL SUR | ZAMBOANGA CITY (ZAMBOANGA DEL SUR) | P00721358MN | Construction of Flood Mitigation Structure | 121.9186 | 7.0283 | 41160000 | 41109966.96 | 2023 | JM2K CONSTRUCTION | 5770 | 2023 | 2023-10-25 | 02/16/2023 | 50033.04 | 0 | 2024-02-09 | 107
2022 | Region IV-B | ROMBLON | SAN ANDRES (ROMBLON) | P00620669LZ | Construction of Flood Mitigation Structure | 122.0089 | 12.54 | 29399999.47 | 29400000 | 2022 | ROLCO CONSTRUCTION & DEVELOPMENT CORPORATION ( FOR / SCATR CONSTRUCTION | 5771 | 2022 | 2022-12-01 | 02/28/2022 | 0 | 0.53 | 2022-11-30 |  | 1
2022 | Region IV-A | QUEZON | LOPEZ (QUEZON) | P00620614LZ | Construction of Flood Mitigation Structure | 122.2643 | 13.8806 | 29400000 | 29400000 | 2023 | MURIELEVEN BUILDERS AND CONSTRUCTION SUPPLY CORP. | 5772 | 2022 | 2023-01-16 | 03/24/2022 | 0 | 0 | 2023-02-10 | 25
2024 | Region II | ISABELA | SAN AGUSTIN (ISABELA) | P00843230LZ | Construction of Flood Mitigation Structure | 121.8442 | 16.452 | 96500000 | 96400000 | 2024 | GACUTAN CONSTRUCTION INC. (FORMERLY: GACUTAN CONSTRUCTION) | 5773 | 2024 | 2024-08-10 | 02/15/2024 | 100000 | 0
2023 | Region IV-A | QUEZON | LOPEZ (QUEZON) | P00726234LZ | Construction of Flood Mitigation Structure | 122.2655 | 13.879 | 49000000 | 49000000 | 2023 | R.A. MENDIOLA CONSTRUCTION & DEVELOPER | 5774 | 2023 | 2023-12-30 | 02/08/2023 | 0 | 0 | 2023-12-29 |  | 1
2024 | Region II | ISABELA | ILAGAN CITY (CAPITAL) (ISABELA) | P00821202LZ | Construction of Flood Mitigation Structure | 121.92 | 17.121 | 139925000 | 139912867.3 | 2024 | DRAGON TWELVE BUILDERS & CONSTRUCTION SUPPLY | 5775 | 2024 | 2024-09-20 | 02/05/2024 | 12132.7 | 0 | 2025-01-24 | 126
2022 | Region III | AURORA | BALER (CAPITAL) (AURORA) | P00631166LZ | Construction of Flood Mitigation Structure | 121.5712 | 15.7575 | 49000000 | 49000000 | 2022 | R.N.G.M. CONSTRUCTION CORPORATION (FORMERLY: R.N.G.M. CONSTRUCTION) | 5776 | 2022 | 2022-12-16 | 02/11/2022 | 0 | 0 | 2022-12-24 | 8
2022 | Region II | CAGAYAN | TUGUEGARAO CITY (CAPITAL) (CAGAYAN) | P00620822LZ | Construction of Flood Mitigation Structure | 121.72 | 17.63 | 57900000 | 57900000 | 2023 | RPF CONSTRUCTION | 5777 | 2022 | 2023-06-20 | 03/28/2022 | 0 | 0 | 2023-05-21 |  | 30
2022 | Cordillera Administrative Region | IFUGAO | AGUINALDO (IFUGAO) | P00620481LZ | Construction of Flood Mitigation Structure | 121.4413 | 16.9309 | 76237286.54 | 31817660 | 2023 | DJY CONSTRUCTION / RODEKOM GENERAL CONSTRUCTION AND ENTERPRISE | 5778 | 2022 | 2023-03-05 | 05/23/2022 | 44419626.54 | 0 | 2023-03-04 |  | 1
2024 | Region II | ISABELA | DINAPIGUE (ISABELA) | P00843287LZ | Construction of Flood Mitigation Structure | 122.2665 | 16.5324 | 96500000 | 96500000 | 2024 | DALCON CONSTRUCTION | 5779 | 2024 | 2024-12-07 | 06/19/2024 | 0 | 0 | 2025-04-16 | 130
2022 | Region II | CAGAYAN | TUGUEGARAO CITY (CAPITAL) (CAGAYAN) | P00621043LZ | Construction of Flood Mitigation Structure | 121.7212 | 17.6235 | 17287200 | 17287200 | 2023 | MEGAY CONSTRUCTION INC. (FORMERLY: MEGAY CONSTRUCTION) | 5780 | 2022 | 2023-03-22 | 03/23/2022 | 0 | 0 | 2023-03-21 |  | 1
2024 | Region IV-B | ROMBLON | LOOC (ROMBLON) | P00823598LZ | Construction of Flood Mitigation Structure | 122.0089 | 12.2933 | 91674999.95 | 91672764.45 | 2024 | SUNWEST, INC. (FORMERLY: SUNWEST CONSTRUCTION & DEVELOPMENT CORPORATION) | 5781 | 2024 | 2024-09-23 | 04/08/2024 | 2235.5 | 0 | 2025-03-02 | 160
2022 | Region II | CAGAYAN | TUGUEGARAO CITY (CAPITAL) (CAGAYAN) | P00621244LZ | Construction of Flood Mitigation Structure | 121.7212 | 17.6235 | 19300000 | 19300000 | 2023 | JTM CONSTRUCTION | 5782 | 2022 | 2023-06-26 | 03/28/2022 | 0 | 0 | 2023-06-29 | 3
2024 | Region IV-A | LAGUNA | PAGSANJAN (LAGUNA) | P00844542LZ | Construction of Flood Mitigation Structure | 121.4464 | 14.2661 | 96500000 | 96499165.86 | 2024 | PROTECH CONSTRUCTION & DEVELOPMENT CORP. (FORMERLY | 5783 | 2024 | 2024-10-04 | 03/15/2024 | 834.14 | 0 | 2025-02-27 | 146
2024 | Region VI | ILOILO | IGBARAS (ILOILO) | P00821047VS | Construction of Flood Mitigation Structure | 122.2669 | 10.7187 | 14700000 | 14596493.95 | 2024 | GALENO CONSTRUCTION, INC. | 5784 | 2024 | 2024-08-12 | 03/20/2024 | 103506.05 | 0 | 2024-08-11 |  | 1
2022 | Region IX | ZAMBOANGA DEL SUR | ZAMBOANGA CITY (ZAMBOANGA DEL SUR) | P00620110MN | Construction of Flood Mitigation Structure | 121.9203 | 7.0011 | 24499642.36 | 19071820.96 | 2022 | YN BUILDERS AND SUPPLY | 5785 | 2022 | 2022-11-28 | 02/28/2022 | 5427821.4 | 0 | 2022-11-27 |  | 1
2022 | Region II | ISABELA | ROXAS (ISABELA) | P00621480LZ | Construction of Flood Mitigation Structure | 121.5734 | 17.1401 | 49000000 | 48996572.12 | 2023 | ROAD EDGE TRADING & DEVELOPMENT SERVICES | 5786 | 2022 | 2023-04-04 | 04/04/2022 | 3427.88 | 0 | 2023-04-03 |  | 1
2023 | Region IX | ZAMBOANGA DEL SUR | ZAMBOANGA CITY (ZAMBOANGA DEL SUR) | P00721354MN | Construction of Flood Mitigation Structure | 121.9203 | 7.0342 | 29285877.45 | 29218092.67 | 2023 | WENKON CONSTRUCTION SERVICES | 5787 | 2023 | 2023-11-15 | 02/16/2023 | 67784.78 | 0 | 2023-12-22 | 37
2023 | Region II | ISABELA | GAMU (ISABELA) | P00726431LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.8442 | 17.0625 | 43136507.81 | 43116483.57 | 2023 | ROAD EDGE TRADING & DEVELOPMENT SERVICES | 5788 | 2023 | 2023-06-07 | 03/15/2023 | 20024.24 | 0 | 2023-10-21 | 136
2022 | Region II | BATANES | IVANA (BATANES) | P00632794LZ | Construction of Flood Mitigation Structure | 121.9209 | 20.378 | 4794000 | 4770046.3 | 2022 | REMAR CONSTRUCTION | 5789 | 2022 | 2022-09-25 | 03/14/2022 | 23953.7 | 0 | 2022-07-21 |  | 66
2024 | Region II | ISABELA | AURORA (ISABELA) | P00845942LZ | Construction of Flood Mitigation Structure | 121.5755 | 16.9497 | 4950000 | 4902860.34 | 2024 | R.E.A. CONSTRUCTION | 5790 | 2024 | 2024-06-02 | 04/15/2024 | 47139.66 | 0 | 2024-09-23 | 113
2021 | Region IX | ZAMBOANGA DEL SUR |  | P00522142MN | Construction of Flood Mitigation Structure | 121.9211 | 6.9979 | 49000000 | 41992237.57 | 2022 | MCGABRIEL CONSTRUCTION / AQUATERRA KONSTRUKT INC. | 5791 | 2021 | 2022-09-13 | 06/15/2021 | 7007762.43 | 0 | 2022-09-12 |  | 1
2024 | Region II | ISABELA | SAN AGUSTIN (ISABELA) | P00843229LZ | Construction of Flood Mitigation Structure | 121.8444 | 16.4447 | 96500000 | 96500000 | 2024 | DALCON CONSTRUCTION | 5792 | 2024 | 2024-11-12 | 06/03/2024 | 0 | 0 | 2025-03-24 | 132
2023 | Region IX | ZAMBOANGA DEL SUR | ZAMBOANGA CITY (ZAMBOANGA DEL SUR) | P00732469MN | Construction of Drainage Structure | 122.009 | 6.9296 | 4900000 | 4879296.3 | 2023 | RME CONSTRUCTION AND ENTERPRISES | 5793 | 2023 | 2023-08-24 | 03/23/2023 | 20703.7 | 0 | 2023-09-23 | 30
2023 | Region II | ISABELA | DINAPIGUE (ISABELA) | P00736609LZ | Construction of Flood Mitigation Structure | 122.268 | 16.571 | 49000000 | 49000000 | 2023 | ALPHA & OMEGA GEN. CONTRACTOR & DEVELOPMENT CORP. | 5794 | 2023 | 2023-09-18 | 02/17/2023 | 0 | 0 | 2023-09-27 | 9
2021 | Region II | ISABELA |  | P00561455LZ | Construction of Flood Mitigation Structure | 121.5762 | 16.9139 | 96499999.82 | 96497593.3 | 2022 | C.R. DOMINGO CONSTRUCTION AND POWER DEVELOPMENT, INC. (FOR. C.R. DOMINGO CONSTRUCTION, INC.) | 5795 | 2021 | 2022-10-10 | 11/23/2021 | 2406.52 | 0 | 2022-10-17 | 7
2023 | Region IV-A | LAGUNA | FAMY (LAGUNA) | P00742432LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.4482 | 14.4504 | 98010000 | 98009253.72 | 2024 | DMLC BUILDERS | 5796 | 2023 | 2024-03-08 | 03/25/2023 | 746.28 | 0 | 2024-03-07 |  | 1
2022 | Region II | ISABELA | QUIRINO (ISABELA) | P00621155LZ | Construction of Flood Mitigation Structure | 121.7213 | 17.1062 | 96500000 | 96311346.48 | 2023 | ANORE CONSTRUCTION / RR BUILDERS | 5797 | 2022 | 2023-04-17 | 06/08/2022 | 188653.52 | 0 | 2023-05-23 | 36
2022 | Region IV-B | ROMBLON | ROMBLON (CAPITAL) (ROMBLON) | P00621488LZ | Construction of Flood Mitigation Structure | 122.2686 | 12.55 | 24499999.5 | 24499640.14 | 2022 | MT. GUITING-GUITING CONSTRUCTION | 5798 | 2022 | 2022-10-19 | 04/11/2022 | 359.36 | 0 | 2022-10-29 | 10
2023 | Region II | ISABELA | ILAGAN CITY (CAPITAL) (ISABELA) | P00726455LZ | Construction of Flood Mitigation Structure | 121.9242 | 17.1217 | 96200000 | 96177084 | 2023 | DRAGON TWELVE BUILDERS & CONSTRUCTION SUPPLY | 5799 | 2023 | 2023-08-10 | 03/02/2023 | 22916 | 0 | 2023-11-23 | 105
2025 | Region IV-B | ORIENTAL MINDORO | NAUJAN (ORIENTAL MINDORO) | P00921190LZ | Construction of Drainage Structure | 122.0092 | 12.1542 | 14700000 | 14699999.28 | 2025 | CEFF TRADING & ENGINEERING SERVICES / JUWAWI CORPORATION | 5800 | 2025 | 2025-05-26 | 02/18/2025 | 0.72 | 0 | 2025-06-26 | 31
2024 | Region II | CAGAYAN | AMULUNG (CAGAYAN) | P00825229LZ | Construction of Flood Mitigation Structure | 121.7222 | 17.8344 | 19600000 | 19600000 | 2024 | VHT CAGAYAN BUILDERS CORPORATION | 5801 | 2024 | 2024-07-30 | 05/15/2024 | 0 | 0 | 2024-09-21 | 53
2022 | Cordillera Administrative Region | KALINGA | PINUKPUK (KALINGA) | P00621006LZ | Construction of Flood Mitigation Structure | 121.5762 | 17.3498 | 48983118.75 | 48449186.44 | 2023 | JTM CONSTRUCTION / EGB CONSTRUCTION CORPORATION (FORMERLY: EGB CONSTRUCTION) | 5802 | 2022 | 2023-01-05 | 02/15/2022 | 533932.31 | 0 | 2022-10-13 |  | 84
2022 | Region IV-A | LAGUNA | LILIW (LAGUNA) | P00620594LZ | Construction of Slope Protection Structure | 121.4482 | 14.1351 | 43028860 | 43028860 | 2023 | MORTAR MASTERS & CONCRETE BUILDERS | 5803 | 2022 | 2023-08-24 | 01/28/2022 | 0 | 0 | 2023-09-04 | 11
2024 | Region II | ISABELA | DINAPIGUE (ISABELA) | P00843234LZ | Construction of Flood Mitigation Structure | 122.2686 | 16.5685 | 96500000 | 96297431.08 | 2025 | GACUTAN CONSTRUCTION INC. (FORMERLY: GACUTAN CONSTRUCTION) | 5804 | 2024 | 2025-02-03 | 08/14/2024 | 202568.92 | 0 | 2025-10-29 | 268
2024 | Region II | ISABELA | GAMU (ISABELA) | P00824872LZ | Construction of Flood Mitigation Structure | 121.8446 | 17.061 | 144749997.6 | 144724100 | 2024 | ROAD EDGE TRADING & DEVELOPMENT SERVICES / HIGH ROAD CONSTRUCTION SERVICES | 5805 | 2024 | 2024-07-25 | 03/27/2024 | 25897.6 | 0 | 2025-03-08 | 226
2024 | Region IV-A | QUEZON | PEREZ (QUEZON) | P00820919LZ | Construction of Flood Mitigation Structure | 121.9245 | 14.1974 | 4900000 | 4899985.77 | 2024 | MURIELEVEN BUILDERS AND CONSTRUCTION SUPPLY CORP. | 5806 | 2024 | 2024-08-08 | 03/12/2024 | 14.23 | 0 | 2024-08-07 |  | 1
2024 | Region IV-B | ROMBLON | ODIONGAN (ROMBLON) | P00823587LZ | Construction of Flood Mitigation Structure | 122.0092 | 12.4503 | 109372134.5 | 109372135 | 2024 | SCATR CONSTRUCTION | 5807 | 2024 | 2024-09-18 | 03/19/2024 | 0 | 0.5 | 2025-02-26 | 161
2024 | Region IV-A | QUEZON | PEREZ (QUEZON) | P00820924LZ | Construction of Flood Mitigation Structure | 121.9248 | 14.2223 | 4900000 | 4826371.91 | 2024 | RAM BUILDERS | 5808 | 2024 | 2024-08-08 | 03/12/2024 | 73628.09 | 0 | 2024-08-07 |  | 1
2024 | Region IV-A | LAGUNA | FAMY (LAGUNA) | P00844543LZ | Construction of Flood Mitigation Structure | 121.4487 | 14.4475 | 96500000 | 96499996.4 | 2024 | POWER K CONSTRUCTION SUPPLY & SERVICES | 5809 | 2024 | 2024-11-12 | 03/01/2024 | 3.6 | 0 | 2025-02-13 | 93
2024 | Region II | ISABELA | JONES (ISABELA) | P00843251LZ | Construction of Flood Mitigation Structure | 121.7222 | 16.5571 | 72375000 | 72375000 | 2024 | CASAN CONSTRUCTION AND TRADING | 5810 | 2024 | 2024-08-20 | 05/28/2024 | 0 | 0 | 2025-02-15 | 179
2022 | Region II | ISABELA | CITY OF SANTIAGO (ISABELA) | P00620825LZ | Construction of Flood Mitigation Structure | 121.5765 | 16.6863 | 71186120 | 71185884.17 | 2022 | V.B. MANUBAY CONSTRUCTION | 5811 | 2022 | 2022-07-25 | 02/17/2022 | 235.83 | 0 | 2022-10-14 | 81
2024 | Region II | ISABELA | NAGUILIAN (ISABELA) | P00821567LZ | Construction of Revetment | 121.8451 | 17.0337 | 48999987.96 | 48941780.88 | 2024 | A. DE GUIA CONSTRUCTION AND DEVELOPMENT CORPORATION (FORMERLY: A. DE GUIA CONSTRUCTION) | 5812 | 2024 | 2024-06-07 | 02/20/2024 | 58207.08 | 0 | 2024-10-01 | 116
2024 | Region VI | ILOILO | IGBARAS (ILOILO) | P00832628VS | Construction of Flood Mitigation Structure | 122.2694 | 10.7166 | 19800000 | 19749811.34 | 2024 | RINEL CONSTRUCTION SERVICES | 5813 | 2024 | 2024-09-25 | 04/11/2024 | 50188.66 | 0 | 2024-09-30 | 5
2022 | Region IX | ZAMBOANGA DEL SUR | ZAMBOANGA CITY (ZAMBOANGA DEL SUR) | P00620109MN | Construction of Flood Mitigation Structure | 122.0094 | 6.9293 | 39581710 | 39253426.63 | 2022 | BENRAM CONSTRUCTION | 5814 | 2022 | 2022-12-12 | 02/23/2022 | 328283.37 | 0 | 2022-12-26 | 14
2024 | Region IV-A | QUEZON | PEREZ (QUEZON) | P00820912LZ | Construction of Flood Mitigation Structure | 121.9258 | 14.1912 | 9800000 | 9797696.23 | 2024 | RAM BUILDERS | 5815 | 2024 | 2024-11-30 | 03/12/2024 | 2303.77 | 0 | 2024-11-29 |  | 1
2021 | Region IV-B | OCCIDENTAL MINDORO |  | P00561143LZ | Construction of Flood Mitigation Structure | 122.0094 | 12.2433 | 19299999.5 | 19300000 | 2022 | SUNWEST, INC. (FORMERLY: SUNWEST CONSTRUCTION & DEVELOPMENT CORPORATION) | 5816 | 2021 | 2022-07-07 | 01/13/2022 | 0 | 0.5 | 2022-08-05 | 29
2022 | Region II | CAGAYAN | AMULUNG (CAGAYAN) | P00620811LZ | Construction of Flood Mitigation Structure | 121.7233 | 17.8255 | 77200000 | 77200000 | 2022 | E.V. INTERIOR CONSTRUCTION | 5817 | 2022 | 2022-12-13 | 03/28/2022 | 0 | 0 | 2022-12-12 |  | 1
2022 | Region IV-A | LAGUNA | FAMY (LAGUNA) | P00621293LZ | Construction of Flood Mitigation Structure | 121.4494 | 14.4486 | 96500000 | 96499444.57 | 2023 | NEWBIG FOUR J CONSTRUCTION INC., (FORMERLY FOUR J | 5818 | 2022 | 2023-11-06 | 09/09/2022 | 555.43 | 0 | 2023-11-05 |  | 1
2022 | Region II | ISABELA | ROXAS (ISABELA) | P00631117LZ | Construction of Flood Mitigation Structure | 121.5771 | 17.1416 | 42140000 | 41674688.35 | 2023 | MAR-DEB CONSTRUCTION & DEVELOPMENT CORP. (FORMERLY: MAR-DEB CONSTRUCTION & DEVELOPMENT) | 5819 | 2022 | 2023-01-03 | 04/04/2022 | 465311.65 | 0 | 2023-01-05 | 2
2023 | Region II | ISABELA | DINAPIGUE (ISABELA) | P00736611LZ | Construction of Flood Mitigation Structure | 122.2696 | 16.5635 | 49000000 | 48996784.15 | 2023 | ST. TIMOTHY CONSTRUCTION CORPORATION / JAY ARCIE CONSTRUCTION AND SUPPLY | 5820 | 2023 | 2023-06-15 | 02/17/2023 | 3215.85 | 0 | 2023-09-27 | 104
2023 | Region II | ISABELA | JONES (ISABELA) | P00726876LZ | Construction of Flood Mitigation Structure | 121.8451 | 16.5383 | 96500000 | 96500000 | 2023 | V.B. MANUBAY CONSTRUCTION | 5821 | 2023 | 2023-09-18 | 05/30/2023 | 0 | 0 | 2024-03-21 | 185
2023 | Region II | BATANES | BASCO (CAPITAL) (BATANES) | P00727342LZ | Construction of Flood Mitigation Structure | 121.9262 | 20.35 | 24142500 | 24112288.35 | 2023 | J.F. GABOTERO, INC. | 5822 | 2023 | 2023-09-15 | 03/13/2023 | 30211.65 | 0 | 2024-01-24 | 131
2023 | Region VI | ANTIQUE | PATNONGON (ANTIQUE) | P00721974VS | Construction of Flood Mitigation Structure | 122.0095 | 10.9067 | 43425000 | 43425000 | 2024 | F & J GENERAL CONSTRUCTION AND SUPPLY CORPORATION | 5823 | 2023 | 2024-01-30 | 03/30/2023 | 0 | 0 | 2023-12-20 |  | 41
2024 | Region II | ISABELA | MALLIG (ISABELA) | P00845941LZ | Construction of Flood Mitigation Structure | 121.5776 | 17.177 | 49500000 | 49475272.59 | 2025 | MAR-DEB CONSTRUCTION & DEVELOPMENT CORP. (FORMERLY: MAR-DEB CONSTRUCTION & DEVELOPMENT) | 5824 | 2024 | 2025-03-06 | 04/15/2024 | 24727.41 | 0 | 2025-03-06 | 0
2022 | Region II | CAGAYAN | SOLANA (CAGAYAN) | P00621414LZ | Construction of Flood Mitigation Structure | 121.7233 | 17.6813 | 93002840 | 93002840 | 2023 | ASC CONSTRUCTION & CONCRETE PRODUCTS | 5825 | 2022 | 2023-04-17 | 03/28/2022 | 0 | 0 | 2023-06-14 | 58
2023 | Region II | ISABELA | JONES (ISABELA) | P00736188LZ | Construction of Flood Mitigation Structure | 121.9264 | 16.603 | 49000000 | 48998838.57 | 2023 | DANYSONS CONSTRUCTION AND DEVELOPMENT CORPORATION (FORMERLY: DANYSONS CONSTRUCTION) | 5826 | 2023 | 2023-11-27 | 02/17/2023 | 1161.43 | 0 | 2023-11-28 | 1
2022 | Region II | ISABELA | CITY OF SANTIAGO (ISABELA) | P00620826LZ | Construction of Flood Mitigation Structure | 121.5799 | 16.6859 | 69480000 | 69479741.6 | 2022 | V.B. MANUBAY CONSTRUCTION | 5827 | 2022 | 2022-10-05 | 02/17/2022 | 258.4 | 0 | 2022-10-12 | 7
2023 | Region IV-B | MARINDUQUE | GASAN (MARINDUQUE) | P00740417LZ | Construction of Flood Mitigation Structure | 121.8461 | 13.3281 | 241249999.9 | 241248643.7 | 2023 | HGG BUILDERS & SUPPLY | 5828 | 2023 | 2023-12-15 | 04/13/2023 | 1356.2 | 0 | 2024-04-05 | 112
2022 | Region VI | ANTIQUE | SIBALOM (ANTIQUE) | P00620248VS | Construction of Flood Mitigation Structure | 122.0095 | 10.7993 | 52941830 | 1693418.13 | 2022 | TIBIAO-ANTIQUE N.K. ENTERPRISE, INC. | 5829 | 2022 | 2022-09-26 | 02/18/2022 | 51248411.87 | 0 | 2022-10-02 | 6
2023 | Region II | ISABELA | DINAPIGUE (ISABELA) | P00736610LZ | Construction of Flood Mitigation Structure | 122.2697 | 16.5302 | 49000000 | 49000000 | 2023 | ST. TIMOTHY CONSTRUCTION CORPORATION | 5830 | 2023 | 2023-09-18 | 02/17/2023 | 0 | 0 | 2023-09-27 | 9
2023 | Region II | CAGAYAN | SOLANA (CAGAYAN) | P00727100LZ | Construction of Flood Mitigation Structure | 121.7241 | 17.6818 | 29400000 | 29400000 | 2023 | ASC CONSTRUCTION & CONCRETE PRODUCTS | 5831 | 2023 | 2023-07-17 | 03/16/2023 | 0 | 0 | 2023-08-15 | 29
2022 | Region II | ISABELA | TUMAUINI (ISABELA) | P00620494LZ | Construction of Flood Mitigation Structure | 121.9275 | 17.2717 | 39200000 | 39156940 | 2022 | DRAGON TWELVE BUILDERS & CONSTRUCTION SUPPLY | 5832 | 2022 | 2022-09-20 | 04/07/2022 | 43060 | 0 | 2022-12-15 | 86
2024 | Region IV-A | LAGUNA | LUMBAN (LAGUNA) | P00820359LZ | Construction of Flood Mitigation Structure | 121.4497 | 14.319 | 77889010 | 77887135 | 2024 | PROTECH CONSTRUCTION & DEVELOPMENT CORP. (FORMERLY / JOBEL ENTERPRISES | 5833 | 2024 | 2024-07-18 | 02/23/2024 | 1875 | 0 | 2025-01-04 | 170
2023 | Region II | ISABELA | ROXAS (ISABELA) | P00726425LZ | Construction of Flood Mitigation Structure | 121.5806 | 17.1382 | 48250000 | 48246114.85 | 2023 | SIFFU ROCKS CONSTRUCTION / C.R. DOMINGO CONSTRUCTION AND POWER DEVELOPMENT, INC. (FOR. C.R. DOMINGO CONSTRUCTION, INC.) | 5834 | 2023 | 2023-08-24 | 02/27/2023 | 3885.15 | 0 | 2023-12-15 | 113
2024 | Region II | ISABELA | SAN GUILLERMO (ISABELA) | P00843260LZ | Construction of Flood Mitigation Structure | 121.8466 | 16.7064 | 87815000 | 87802963.92 | 2024 | JWU CONSTRUCTION AND SUPPLY | 5835 | 2024 | 2024-11-30 | 07/05/2024 | 12036.08 | 0 | 2025-09-23 | 297
2022 | Region IV-B | ROMBLON | ROMBLON (CAPITAL) (ROMBLON) | P00637087LZ | Construction of Flood Mitigation Structure | 122.2714 | 12.4961 | 24499999.5 | 24497433.72 | 2022 | EMQ DESIGN & CONSTRUCTION | 5836 | 2022 | 2022-10-12 | 04/12/2022 | 2565.78 | 0 | 2022-10-30 | 18
2022 | Region II | ISABELA | ECHAGUE (ISABELA) | P00639337LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.7242 | 16.7082 | 67550000 | 67550000 | 2022 | ROAD EDGE TRADING & DEVELOPMENT SERVICES | 5837 | 2022 | 2022-12-15 | 04/13/2022 | 0 | 0 | 2023-01-11 | 27
2024 | Region VI | AKLAN | MALAY (AKLAN) | P00820146VS | Construction of Flood Mitigation Structure | 121.9285 | 11.8964 | 19926340 | 19917934.53 | 2024 | J.C. TAMAYO ENTERPRISES | 5838 | 2024 | 2024-06-10 | 02/06/2024 | 8405.47 | 0 | 2024-07-18 | 38
2023 | Region IV-A | LAGUNA | LUMBAN (LAGUNA) | P00742433LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.4506 | 14.3162 | 96525000 | 95071125.53 | 2024 | JTC CRUZ CONSTRUCTION CO., INC. | 5839 | 2023 | 2024-03-08 | 03/25/2023 | 1453874.47 | 0 | 2024-03-07 |  | 1
2022 | Region II | ISABELA | CITY OF SANTIAGO (ISABELA) | P00621473LZ | Construction of Flood Mitigation Structure | 121.5852 | 16.6862 | 72375000 | 72374738.52 | 2022 | V.B. MANUBAY CONSTRUCTION | 5840 | 2022 | 2022-12-09 | 04/12/2022 | 261.48 | 0 | 2023-01-20 | 42
2022 | Region IV-B | ROMBLON | ODIONGAN (ROMBLON) | P00621491LZ | Construction of Flood Mitigation Structure | 122.01 | 12.4225 | 24499999.5 | 24499247.05 | 2022 | R N V CONSTRUCTION | 5841 | 2022 | 2022-12-06 | 04/12/2022 | 752.45 | 0 | 2022-12-05 |  | 1
2023 | Region II | ISABELA | DINAPIGUE (ISABELA) | P00740319LZ | Construction of Flood Mitigation Structure | 122.2717 | 16.5732 | 96500000 | 96500000 | 2023 | V.B. MANUBAY CONSTRUCTION | 5842 | 2023 | 2023-12-08 | 07/07/2023 | 0 | 0 | 2024-05-06 | 150
2022 | Region II | CAGAYAN | BAGGAO (CAGAYAN) | P00621026LZ | Construction of Flood Mitigation Structure | 121.9287 | 17.8388 | 19600000 | 12771183.6 | 2024 | ARCI CONSTRUCTION | 5843 | 2022 | 2024-09-30 | 02/02/2022 | 6828816.4 | 0 | 2022-09-29 |  | 732
2024 | Region II | ISABELA | GAMU (ISABELA) | P00824873LZ | Construction of Flood Mitigation Structure | 121.8485 | 17.0527 | 144749998.7 | 144724653.2 | 2024 | ROAD EDGE TRADING & DEVELOPMENT SERVICES / HIGH ROAD CONSTRUCTION SERVICES | 5844 | 2024 | 2024-08-23 | 03/27/2024 | 25345.5 | 0 | 2025-03-08 | 197
2021 | Region II | CAGAYAN |  | P00525557LZ | Construction of Flood Mitigation Structure | 121.7247 | 17.6273 | 59729640 | 59132762.6 | 2023 | RPF CONSTRUCTION / EGB CONSTRUCTION CORPORATION (FORMERLY: EGB CONSTRUCTION) | 5845 | 2021 | 2023-03-31 | 11/22/2021 | 596877.4 | 0 | 2022-05-29 |  | 306
2023 | Region IV-A | LAGUNA | LUMBAN (LAGUNA) | P00742434LZ | Rehabilitation / Major Repair of Flood Control Structure | 121.451 | 14.3153 | 89100000 | 89099964.33 | 2024 | JTC CRUZ CONSTRUCTION CO., INC. | 5846 | 2023 | 2024-02-22 | 03/25/2023 | 35.67 | 0 | 2024-02-21 |  | 1
2023 | Region II | CAGAYAN | SANTO NIÃ‘O (FAIRE) (CAGAYAN) | P00727347LZ | Construction of Flood Mitigation Structure | 121.5904 | 17.9284 | 24500000 | 24105830.87 | 2023 | JDL5 CONSTRUCTION CORPORATION (FORMERLY: DEOJ CONSTRUCTION) | 5847 | 2023 | 2023-11-03 | 03/21/2023 | 394169.13 | 0 | 2023-09-03 |  | 61
2022 | Region VI | ILOILO | GUIMBAL (ILOILO) | P00620083VS | Construction of Flood Mitigation Structure | 122.2792 | 10.6603 | 4900000 | 4851128.23 | 2022 | GOLDEN ROADRUNNER INTERNATIONAL CORP. | 5848 | 2022 | 2022-08-16 | 02/16/2022 | 48871.77 | 0 | 2022-05-13 |  | 95
2024 | Region IV-B | GUIMARAS | BUENAVISTA (GUIMARAS) | P00821364LZ | Construction of Flood Mitigation Structure | 121.9288 | 13.2665 | 96498000 | 96495777.91 | 2025 | SUNWEST, INC. (FORMERLY: SUNWEST CONSTRUCTION & DEVELOPMENT CORPORATION) | 5849 | 2024 | 2025-03-24 | 02/19/2024 | 2222.09 | 0 | 2025-03-29 | 5
2023 | Region IV-B | ROMBLON | ODIONGAN (ROMBLON) | P00727197LZ | Construction of Flood Mitigation Structure | 122.01 | 12.4236 | 48999999.52 | 48993414.82 | 2023 | R N V CONSTRUCTION | 5850 | 2023 | 2023-09-13 | 03/24/2023 | 6584.7 | 0 | 2023-11-16 | 64
2022 | Region II | ISABELA | SAN MATEO (ISABELA) | P00621059LZ | Construction of Flood Mitigation Structure | 121.5925 | 16.903 | 29399999.28 | 28953495.34 | 2022 | D.A. CADELIÃ‘A CONSTRUCTION / GACUTAN CONSTRUCTION INC. (FORMERLY: GACUTAN CONSTRUCTION) | 5851 | 2022 | 2022-10-14 | 03/28/2022 | 446503.94 | 0 | 2022-10-13 |  | 1
2023 | Region IV-A | LAGUNA | LUMBAN (LAGUNA) | P00726565LZ | Construction of Flood Mitigation Structure | 121.4522 | 14.3132 | 96500000 | 96499790.33 | 2023 | JTC CRUZ CONSTRUCTION CO., INC. | 5852 | 2023 | 2023-12-15 | 02/11/2023 | 209.67 | 0 | 2024-01-26 | 42
2022 | Region II | CAGAYAN | IGUIG (CAGAYAN) | P00620813LZ | Construction of Flood Mitigation Structure | 121.7254 | 17.7641 | 77200000 | 76374847.58 | 2024 | VIKING CONSTRUCTION & SUPPLIES | 5853 | 2022 | 2024-03-27 | 03/28/2022 | 825152.42 | 0 | 2023-03-31 |  | 362
2022 | Region IV-B | MARINDUQUE | GASAN (MARINDUQUE) | P00639512LZ | Construction of Flood Mitigation Structure | 121.8489 | 13.364 | 9797999.99 | 9700095.72 | 2022 | JEDIDIAH CONSTRUCTION | 5854 | 2022 | 2022-10-08 | 03/30/2022 | 97904.27 | 0 | 2022-10-07 |  | 1
2024 | Region II | CAGAYAN | BAGGAO (CAGAYAN) | P00823335LZ | Construction of Flood Mitigation Structure | 121.9289 | 17.8386 | 48250000 | 48233879.64 | 2024 | TJMT CONSTRUCTION | 5855 | 2024 | 2024-07-15 | 02/16/2024 | 16120.36 | 0 | 2024-10-31 | 108
2022 | Region II | ISABELA | SAN MANUEL (ISABELA) | P00620144LZ | Construction of Flood Mitigation Structure | 121.5934 | 17.0332 | 73867855 | 73830813.63 | 2023 | DANYSONS CONSTRUCTION AND DEVELOPMENT CORPORATION (FORMERLY: DANYSONS CONSTRUCTION) / JWU CONSTRUCTION AND SUPPLY | 5856 | 2022 | 2023-03-21 | 04/04/2022 | 37041.37 | 0 | 2023-03-14 |  | 7
2024 | Region II | ISABELA | JONES (ISABELA) | P00843243LZ | Construction of Flood Mitigation Structure | 121.7256 | 16.5722 | 96500000 | 96484520 | 2024 | JWU CONSTRUCTION AND SUPPLY | 5857 | 2024 | 2024-12-04 | 06/10/2024 | 15480 | 0 | 2025-06-15 | 193
2024 | Region IV-A | LAGUNA | PAGSANJAN (LAGUNA) | P00823376LZ | Construction of Flood Mitigation Structure | 121.4526 | 14.272 | 96500000 | 93594921.19 | 2025 | 11-16 CONSTRUCTION | 5858 | 2024 | 2025-02-28 | 03/15/2024 | 2905078.81 | 0 | 2025-02-27 |  | 1
2022 | Region IV-B | MARINDUQUE | BOAC (CAPITAL) (MARINDUQUE) | P00620899LZ | Construction of Flood Mitigation Structure | 121.8501 | 13.4429 | 86848000 | 86543354.23 | 2022 | R.T.Y. CONSTRUCTION | 5859 | 2022 | 2022-12-21 | 03/30/2022 | 304645.77 | 0 | 2023-01-25 | 35
2022 | Region VI | ILOILO | IGBARAS (ILOILO) | P00632997VS | Construction of Flood Mitigation Structure | 122.281 | 10.7223 | 29400000 | 29106048.36 | 2023 | TOPMOST DEVELOPMENT & MKTG. CORP. | 5860 | 2022 | 2023-02-13 | 06/01/2022 | 293951.64 | 0 | 2023-01-11 |  | 33
2023 | Region II | CAGAYAN | BAGGAO (CAGAYAN) | P00726112LZ | Construction of Revetment | 121.9289 | 17.8386 | 49000000 | 48999760.64 | 2023 | CMG JR. BUILDERS | 5861 | 2023 | 2023-07-23 | 02/14/2023 | 239.36 | 0 | 2023-11-02 | 102
2024 | Region IV-A | QUEZON | ALABAT (QUEZON) | P00820916LZ | Construction of Flood Mitigation Structure | 122.01 | 14.1115 | 4900000 | 4827143.98 | 2024 | RAM BUILDERS | 5862 | 2024 | 2024-08-08 | 03/12/2024 | 72856.02 | 0 | 2024-08-07 |  | 1
2021 | Region II | CAGAYAN |  | P00561665LZ | Construction of Flood Mitigation Structure | 121.5948 | 17.9272 | 4950000 | 4848606.56 | 2022 | JLL PULSAR CONSTRUCTION CORPORATION (FORMERLY: PULSAR CONSTRUCTION) | 5863 | 2021 | 2022-12-02 | 03/24/2021 | 101393.44 | 0 | 2021-06-23 |  | 527
2023 | Region IV-A | LAGUNA | LUMBAN (LAGUNA) | P00726566LZ | Construction of Flood Mitigation Structure | 121.4528 | 14.3122 | 96500000 | 93567192.5 | 2023 | PROTECH CONSTRUCTION & DEVELOPMENT CORP. (FORMERLY / JOBEL ENTERPRISES | 5864 | 2023 | 2023-08-22 | 02/11/2023 | 2932807.5 | 0 | 2024-01-26 | 157
2024 | Region II | CAGAYAN | AMULUNG (CAGAYAN) | P00824861LZ | Construction of Flood Mitigation Structure | 121.7257 | 17.8215 | 67550000 | 67550000 | 2024 | MEGAY CONSTRUCTION INC. (FORMERLY: MEGAY CONSTRUCTION) / VHT CAGAYAN BUILDERS CORPORATION | 5865 | 2024 | 2024-11-30 | 05/09/2024 | 0 | 0 | 2024-12-10 | 10
2022 | Region IV-A | QUEZON | CALAUAG (QUEZON) | P00621101LZ | Construction of Flood Mitigation Structure | 122.2877 | 13.9224 | 9800000 | 9800000 | 2022 | ARDA CONSTRUCTION AND SUPPLY | 5866 | 2022 | 2022-09-27 | 03/16/2022 | 0 | 0 | 2022-09-26 |  | 1
2024 | Region II | ISABELA | ILAGAN CITY (CAPITAL) (ISABELA) | P00824870LZ | Construction of Flood Mitigation Structure | 121.8504 | 17.1044 | 96500000 | 96492518.4 | 2024 | DRAGON TWELVE BUILDERS & CONSTRUCTION SUPPLY | 5867 | 2024 | 2024-10-15 | 05/29/2024 | 7481.6 | 0 | 2025-05-17 | 214
2023 | Region IV-B | MARINDUQUE | BUENAVISTA (MARINDUQUE) | P00725868LZ | Construction of Flood Mitigation Structure | 121.929 | 13.2609 | 72373000 | 72367731.57 | 2023 | J.D. LEGASPI CONSTRUCTION / ZUIDEN BUILDERS INC. | 5868 | 2023 | 2023-11-28 | 02/24/2023 | 5268.43 | 0 | 2023-12-02 | 4
2024 | Region IV-A | QUEZON | ALABAT (QUEZON) | P00820909LZ | Construction of Flood Mitigation Structure | 122.0107 | 14.096 | 19600000 | 19599888.56 | 2024 | RAM BUILDERS | 5869 | 2024 | 2024-11-06 | 03/12/2024 | 111.44 | 0 | 2024-11-05 |  | 1
2022 | Region IV-A | QUEZON | LUCENA CITY (CAPITAL) (QUEZON) | P00637798LZ | Construction of Flood Mitigation Structure | 121.5953 | 13.9669 | 4950000 | 4950000 | 2022 | WAYCON BUILDERS AND CONSTRUCTION SUPPLY CORP. (FOR:WAYCON BUILDERS & CONSTRUCTION SUPPLY) | 5870 | 2022 | 2022-10-16 | 05/20/2022 | 0 | 0 | 2022-10-15 |  | 1
2024 | Region II | ISABELA | JONES (ISABELA) | P00843225LZ | Construction of Flood Mitigation Structure | 121.8514 | 16.5362 | 96500000 | 96399715.44 | 2024 | GACUTAN CONSTRUCTION INC. (FORMERLY: GACUTAN CONSTRUCTION) | 5871 | 2024 | 2024-11-16 | 05/21/2024 | 100284.56 | 0 | 2025-03-14 | 118
2022 | Region IV-B | MARINDUQUE | BUENAVISTA (MARINDUQUE) | P00621429LZ | Construction of Flood Mitigation Structure | 121.9306 | 13.2641 | 96498000 | 96497681.88 | 2023 | SUNWEST, INC. (FORMERLY: SUNWEST CONSTRUCTION & DEVELOPMENT CORPORATION) | 5872 | 2022 | 2023-08-02 | 03/30/2022 | 318.12 | 0 | 2023-08-02 | 0
2022 | Region IV-B | ORIENTAL MINDORO | MANSALAY (ORIENTAL MINDORO) | P00632941LZ | Construction of Drainage Structure | 121.4544 | 12.5781 | 9899922.98 | 9899907.62 | 2022 | AIDFELART CONST. CORP. | 5873 | 2022 | 2022-08-14 | 02/21/2022 | 15.36 | 0 | 2022-08-13 |  | 1
2023 | Region II | CAGAYAN | TUGUEGARAO CITY (CAPITAL) (CAGAYAN) | P00726121LZ | Construction of Flood Mitigation Structure | 121.7258 | 17.6244 | 49000000 | 49000000 | 2024 | RPF CONSTRUCTION | 5874 | 2023 | 2024-02-05 | 02/09/2023 | 0 | 0 | 2024-02-07 | 2
2022 | Region IV-B | MARINDUQUE | BOAC (CAPITAL) (MARINDUQUE) | P00620269LZ | Construction of Flood Mitigation Structure | 121.8517 | 13.4375 | 86848000 | 86848824.12 | 2022 | R.T.Y. CONSTRUCTION | 5875 | 2022 | 2022-11-28 | 03/30/2022 | 0 | 824.12 | 2023-01-25 | 58
2021 | Region VI | AKLAN |  | P00521758VS | Construction of Revetment | 122.2892 | 11.4029 | 60325860 | 59402499.64 | 2022 | PATRILA BUILDERS, INC. | 5876 | 2021 | 2022-07-27 | 10/15/2021 | 923360.36 | 0 | 2022-11-24 | 120
2021 | Region IX | BASILAN |  | P00522047MN | Construction of Revetment | 121.9338 | 6.6191 | 144557364.9 | 144207784.9 | 2022 | RCDG CONSTRUCTION CORPORATION / HHH DEVELOPER AND CONSTRUCTION | 5877 | 2021 | 2022-09-15 | 06/25/2021 | 349580 | 0 | 2022-09-14 |  | 1
2023 | Region II | ISABELA | ILAGAN CITY (CAPITAL) (ISABELA) | P00726688LZ | Construction of Flood Mitigation Structure | 122.0113 | 17.0778 | 49000000 | 48994145.8 | 2023 | DRAGON TWELVE BUILDERS & CONSTRUCTION SUPPLY | 5878 | 2023 | 2023-06-15 | 03/02/2023 | 5854.2 | 0 | 2023-11-24 | 162
2022 | Region II | ISABELA | SAN MATEO (ISABELA) | P00631126LZ | Construction of Flood Mitigation Structure | 121.5956 | 16.9319 | 42139998.39 | 41512797.12 | 2023 | D.A. CADELIÃ‘A CONSTRUCTION / GACUTAN CONSTRUCTION INC. (FORMERLY: GACUTAN CONSTRUCTION) | 5879 | 2022 | 2023-03-28 | 05/31/2022 | 627201.27 | 0 | 2023-03-27 |  | 1
2023 | Region IV-A | QUEZON | ALABAT (QUEZON) | P00727170LZ | Construction of Flood Mitigation Structure | 122.0114 | 14.0963 | 24500000 | 24496456.69 | 2023 | RAM BUILDERS | 5880 | 2023 | 2023-10-09 | 03/09/2023 | 3543.31 | 0 | 2023-11-02 | 24
2024 | Cordillera Administrative Region | IFUGAO | AGUINALDO (IFUGAO) | P00820744LZ | Construction of Flood Mitigation Structure | 121.4545 | 16.9293 | 96479015.97 | 98000000 | 2024 | MA CONSTRUCTION / R.S. SEPIAN CONSTRUCTION & TRUCKING | 5881 | 2024 | 2024-05-27 | 02/16/2024 | 0 | 1520984.03 | 2024-10-14 | 140
2021 | Region II | CAGAYAN |  | P00526392LZ | Construction of Flood Mitigation Structure | 121.7261 | 17.625 | 14700000 | 14258479.57 | 2023 | RPF CONSTRUCTION | 5882 | 2021 | 2023-03-19 | 11/11/2021 | 441520.43 | 0 | 2022-04-18 |  | 335
2022 | Region II | ISABELA | JONES (ISABELA) | P00631135LZ | Construction of Flood Mitigation Structure | 121.8527 | 16.5373 | 44100000 | 44099988.47 | 2022 | MA TESORO CONSTRUCTION / EGB CONSTRUCTION CORPORATION (FORMERLY: EGB CONSTRUCTION) | 5883 | 2022 | 2022-09-22 | 04/07/2022 | 11.53 | 0 | 2022-10-31 | 39
2023 | Region VI | ILOILO | GUIMBAL (ILOILO) | P00721646VS | Construction of Flood Mitigation Structure | 122.2898 | 10.6952 | 29400000 | 29091213.14 | 2023 | ABRIGHT BUILDERS CORPORATION | 5884 | 2023 | 2023-12-19 | 03/16/2023 | 308786.86 | 0 | 2024-01-03 | 15
2022 | Region IX | ZAMBOANGA DEL SUR | ZAMBOANGA CITY (ZAMBOANGA DEL SUR) | P00631081MN | Construction of Flood Mitigation Structure | 121.9356 | 7.0036 | 49000000 | 49482639.74 | 2023 | JM2K CONSTRUCTION | 5885 | 2022 | 2023-03-25 | 03/21/2022 | 0 | 482639.74 | 2023-03-24 |  | 1
2023 | Region II | ISABELA | SAN MARIANO (ISABELA) | P00726695LZ | Construction of Flood Mitigation Structure | 122.0116 | 16.995 | 46266891.44 | 46256541.75 | 2023 | YZK BUILDERS | 5886 | 2023 | 2023-08-22 | 04/11/2023 | 10349.69 | 0 | 2023-11-07 | 77
2023 | Region II | CAGAYAN | TUGUEGARAO CITY (CAPITAL) (CAGAYAN) | P00726120LZ | Construction of Drainage Structure | 121.7261 | 17.605 | 49000000 | 49000000 | 2024 | MEGAY CONSTRUCTION INC. (FORMERLY: MEGAY CONSTRUCTION) | 5887 | 2023 | 2024-02-19 | 02/09/2023 | 0 | 0 | 2024-02-22 | 3
2024 | Region IV-A | LAGUNA | SINILOAN (LAGUNA) | P00844545LZ | Construction of Flood Mitigation Structure | 121.4558 | 14.43 | 96500000 | 96499568.47 | 2025 | POWER K CONSTRUCTION SUPPLY & SERVICES | 5888 | 2024 | 2025-03-07 | 03/22/2024 | 431.53 | 0 | 2025-03-06 |  | 1
2024 | Region II | BATANES | UYUGAN (BATANES) | P00820778LZ | Construction of Flood Mitigation Structure | 121.9376 | 20.3534 | 9800000 | 9784961.17 | 2024 | J.F. GABOTERO, INC. | 5889 | 2024 | 2024-08-26 | 03/04/2024 | 15038.83 | 0 | 2024-09-08 | 13
2024 | Region II | ISABELA | AURORA (ISABELA) | P00824894LZ | Construction of Slope Protection Structure | 121.6014 | 16.9529 | 144750000 | 144740047.4 | 2025 | JWU CONSTRUCTION AND SUPPLY | 5890 | 2024 | 2025-03-21 | 07/17/2024 | 9952.6 | 0 | 2025-08-08 | 140
2023 | Region IV-A | QUEZON | LOPEZ (QUEZON) | P00727314LZ | Construction of Flood Mitigation Structure | 122.2916 | 13.9148 | 87815000 | 87815000 | 2024 | WAYCON BUILDERS AND CONSTRUCTION SUPPLY CORP. (FOR:WAYCON BUILDERS & CONSTRUCTION SUPPLY) | 5891 | 2023 | 2024-02-16 | 03/24/2023 | 0 | 0 | 2024-02-15 |  | 1
2023 | Region II | ISABELA | ILAGAN CITY (CAPITAL) (ISABELA) | P00726676LZ | Construction of Flood Mitigation Structure | 121.8528 | 17.1016 | 49000000 | 48975104.35 | 2023 | EGB CONSTRUCTION CORPORATION (FORMERLY: EGB CONSTRUCTION) | 5892 | 2023 | 2023-11-24 | 04/17/2023 | 24895.65 | 0 | 2024-01-23 | 60
2024 | Region IV-B | ROMBLON | ODIONGAN (ROMBLON) | P00823586LZ | Construction of Flood Mitigation Structure | 122.0119 | 12.4742 | 96499999.43 | 96497440.82 | 2024 | SCATR CONSTRUCTION | 5893 | 2024 | 2024-09-17 | 03/19/2024 | 2558.61 | 0 | 2025-02-20 | 156
2022 | Region IV-A | LAGUNA | LUMBAN (LAGUNA) | P00620886LZ | Construction of Flood Mitigation Structure | 121.4561 | 14.3075 | 86149410 | 83514566.55 | 2022 | JUSTBILT BUILDERS | 5894 | 2022 | 2022-11-14 | 02/19/2022 | 2634843.45 | 0 | 2023-01-16 | 63
2023 | Region IV-A | QUEZON | LUCENA CITY (CAPITAL) (QUEZON) | P00726567LZ | Construction of Flood Mitigation Structure | 121.6032 | 13.9631 | 57900000 | 57899998.23 | 2024 | RAPID FOREMOST CONST. CO. | 5895 | 2023 | 2024-08-14 | 02/22/2023 | 1.77 | 0 | 2024-08-16 | 2
2022 | Region II | ISABELA | ECHAGUE (ISABELA) | P00631132LZ | Construction of Flood Mitigation Structure | 121.7271 | 16.7142 | 45080000 | 45077651.65 | 2022 | MA TESORO CONSTRUCTION / EGB CONSTRUCTION CORPORATION (FORMERLY: EGB CONSTRUCTION) | 5896 | 2022 | 2022-07-31 | 02/16/2022 | 2348.35 | 0 | 2022-08-11 | 11
2024 | Region II | ISABELA | ILAGAN CITY (CAPITAL) (ISABELA) | P00821194LZ | Construction of Flood Mitigation Structure | 121.8537 | 17.1056 | 139925000 | 139905104.4 | 2024 | EGB CONSTRUCTION CORPORATION (FORMERLY: EGB CONSTRUCTION) | 5897 | 2024 | 2024-12-15 | 02/14/2024 | 19895.6 | 0 | 2025-02-05 | 52
2022 | Region IV-A | QUEZON | CALAUAG (QUEZON) | P00620618LZ | Construction of Flood Mitigation Structure | 122.2921 | 13.9604 | 9800000 | 9800000 | 2022 | TG SURCON BUILDERS INC. | 5898 | 2022 | 2022-07-14 | 02/15/2022 | 0 | 0 | 2022-07-13 |  | 1
2022 | Region II | ISABELA | SAN MARIANO (ISABELA) | P00621061LZ | Construction of Flood Mitigation Structure | 122.0122 | 16.9562 | 29399995.92 | 28958609.7 | 2022 | YZK BUILDERS | 5899 | 2022 | 2022-10-09 | 03/28/2022 | 441386.22 | 0 | 2022-10-08 |  | 1
2022 | Region IV-A | LAGUNA | SANTA CRUZ (CAPITAL) (LAGUNA) | P00620887LZ | Construction of Flood Mitigation Structure | 121.4561 | 14.3058 | 85885000 | 85884929.73 | 2022 | JTC CRUZ CONSTRUCTION CO., INC. | 5900 | 2022 | 2022-11-14 | 02/19/2022 | 70.27 | 0 | 2023-01-16 | 63
2023 | Region II | BATANES | UYUGAN (BATANES) | P00737439LZ | Construction of Flood Mitigation Structure | 121.9376 | 20.3506 | 4874464 | 4095167.51 | 2023 | SWIFT DEVELOPMENT AND SUPPLIES CORP. | 5901 | 2023 | 2023-09-20 | 02/21/2023 | 779296.49 | 0 | 2023-08-28 |  | 23
2023 | Region II | ISABELA | SAN MARIANO (ISABELA) | P00726693LZ | Construction of Flood Mitigation Structure | 122.0127 | 16.9851 | 43811506.43 | 43801383.68 | 2023 | YZK BUILDERS | 5902 | 2023 | 2023-08-15 | 04/11/2023 | 10122.75 | 0 | 2023-10-04 | 50
2021 | Region II | CAGAYAN |  | P00526391LZ | Construction of Flood Mitigation Structure | 121.7284 | 17.6179 | 49000000 | 41495798.75 | 2022 | ASC CONSTRUCTION & CONCRETE PRODUCTS | 5903 | 2021 | 2022-12-13 | 11/11/2021 | 7504201.25 | 0 | 2022-11-01 |  | 42
2024 | Region IV-A | QUEZON | CALAUAG (QUEZON) | P00820927LZ | Construction of Flood Mitigation Structure | 122.2929 | 13.9604 | 4900000 | 4833252.63 | 2024 | MURIELEVEN BUILDERS AND CONSTRUCTION SUPPLY CORP. | 5904 | 2024 | 2024-07-12 | 02/14/2024 | 66747.37 | 0 | 2024-07-11 |  | 1
2024 | Region II | BATANES | UYUGAN (BATANES) | P00820768LZ | Construction of Flood Mitigation Structure | 121.938 | 20.349 | 9800000 | 9780073.63 | 2024 | J.F. GABOTERO, INC. | 5905 | 2024 | 2024-07-26 | 03/26/2024 | 19926.37 | 0 | 2024-09-30 | 66
2023 | Region II | ISABELA | SAN MARIANO (ISABELA) | P00742306LZ | Construction of Flood Mitigation Structure | 122.0131 | 16.9861 | 4949989.92 | 4900426.44 | 2023 | CAMBERWELL CONSTRUCTION AND SUPPLIES | 5906 | 2023 | 2023-11-19 | 05/17/2023 | 49563.48 | 0 | 2023-11-18 |  | 1
2024 | Region IV-B | MARINDUQUE | BOAC (CAPITAL) (MARINDUQUE) | P00820405LZ | Construction of Flood Mitigation Structure | 121.8566 | 13.4338 | 67548000 | 67545243 | 2024 | DQT BUILDERS CORPORATION (FORMERLY DQT BUILDERS) | 5907 | 2024 | 2024-10-28 | 02/19/2024 | 2757 | 0 | 2024-10-27 |  | 1
2023 | Region IV-B | ROMBLON | SAN ANDRES (ROMBLON) | P00726278LZ | Construction of Flood Mitigation Structure | 122.0136 | 12.5419 | 48999999.5 | 48996131.97 | 2023 | ROLCO CONSTRUCTION & DEVELOPMENT CORPORATION ( FOR | 5908 | 2023 | 2023-08-21 | 02/21/2023 | 3867.53 | 0 | 2023-10-16 | 56
2024 | Region II | ISABELA | ANGADANAN (ISABELA) | P00824862LZ | Construction of Flood Mitigation Structure | 121.7285 | 16.7173 | 77199985.11 | 77163172.6 | 2025 | INFINITUM 888 CONSTRUCTION AND DEVELOPMENT CORPORATION / ALGO CONSTRUCTION AND POWER DEVELOPMENT, INC. | 5909 | 2024 | 2025-03-25 | 07/17/2024 | 36812.51 | 0 | 2025-05-02 | 38
2022 | Region IV-A | LAGUNA | PAGSANJAN (LAGUNA) | P00620885LZ | Construction of Flood Mitigation Structure | 121.4575 | 14.2736 | 85885000 | 83249659.5 | 2023 | PROTECH CONSTRUCTION & DEVELOPMENT CORP. (FORMERLY / JOBEL ENTERPRISES | 5910 | 2022 | 2023-06-05 | 02/19/2022 | 2635340.5 | 0 | 2023-06-04 |  | 1
2024 | Region II | CAGAYAN | BAGGAO (CAGAYAN) | P00823337LZ | Construction of Flood Mitigation Structure | 121.8578 | 17.8947 | 48250000 | 48244212.26 | 2024 | TJMT CONSTRUCTION | 5911 | 2024 | 2024-07-01 | 03/07/2024 | 5787.74 | 0 | 2024-11-20 | 142
2024 | Region IV-B | ROMBLON | ODIONGAN (ROMBLON) | P00823582LZ | Construction of Flood Mitigation Structure | 122.0139 | 12.4164 | 139924999.6 | 139925000 | 2024 | SUNWEST, INC. (FORMERLY: SUNWEST CONSTRUCTION & DEVELOPMENT CORPORATION) | 5912 | 2024 | 2024-09-23 | 03/13/2024 | 0 | 0.4 | 2025-03-06 | 164
2023 | Region IV-A | QUEZON | LOPEZ (QUEZON) | P00727373LZ | Construction of Flood Mitigation Structure | 122.2931 | 13.915 | 44100000 | 44100000 | 2023 | WAYCON BUILDERS AND CONSTRUCTION SUPPLY CORP. (FOR:WAYCON BUILDERS & CONSTRUCTION SUPPLY) | 5913 | 2023 | 2023-12-03 | 03/09/2023 | 0 | 0 | 2023-12-02 |  | 1
2023 | Region II | BATANES | UYUGAN (BATANES) | P00726107LZ | Construction of Flood Mitigation Structure | 121.938 | 20.3539 | 9738048 | 9738048 | 2023 | REMAR CONSTRUCTION | 5914 | 2023 | 2023-08-21 | 02/17/2023 | 0 | 0 | 2023-09-20 | 30
2024 | Region II | ISABELA | ANGADANAN (ISABELA) | P00821168LZ | Construction of Revetment | 121.7289 | 16.7714 | 96499995.31 | 96479997.58 | 2024 | JWU CONSTRUCTION AND SUPPLY / HIGH ROAD CONSTRUCTION SERVICES | 5915 | 2024 | 2024-08-06 | 06/19/2024 | 19997.73 | 0 | 2025-05-06 | 273
2021 | Region IV-A | LAGUNA |  | P00526321LZ | Construction of Flood Mitigation Structure | 121.458 | 14.3029 | 96500474.32 | 93605396.83 | 2022 | JUSTBILT BUILDERS | 5916 | 2021 | 2022-08-29 | 04/05/2021 | 2895077.49 | 0 | 2022-08-28 |  | 1
2024 | Region II | ISABELA | JONES (ISABELA) | P00843252LZ | Construction of Flood Mitigation Structure | 121.8583 | 16.4993 | 96500000 | 96500000 | 2024 | DALCON CONSTRUCTION | 5917 | 2024 | 2024-10-10 | 06/03/2024 | 0 | 0 | 2025-06-08 | 241
2024 | Region IV-B | ROMBLON | ODIONGAN (ROMBLON) | P00821365LZ | Construction of Flood Mitigation Structure | 122.0142 | 12.4158 | 139924999.8 | 139925000 | 2024 | SUNWEST, INC. (FORMERLY: SUNWEST CONSTRUCTION & DEVELOPMENT CORPORATION) | 5918 | 2024 | 2024-09-23 | 03/13/2024 | 0 | 0.2 | 2025-03-06 | 164
2023 | Region IV-A | QUEZON | LOPEZ (QUEZON) | P00727315LZ | Construction of Flood Mitigation Structure | 122.2935 | 13.9164 | 86850000 | 86850000 | 2023 | WAYCON BUILDERS AND CONSTRUCTION SUPPLY CORP. (FOR:WAYCON BUILDERS & CONSTRUCTION SUPPLY) | 5919 | 2023 | 2023-12-18 | 03/24/2023 | 0 | 0 | 2023-12-17 |  | 1
2023 | Region II | BATANES | UYUGAN (BATANES) | P00726108LZ | Construction of Flood Mitigation Structure | 121.9381 | 20.3529 | 2904804 | 2897777.75 | 2023 | REMAR CONSTRUCTION | 5920 | 2023 | 2023-05-06 | 02/17/2023 | 7026.25 | 0 | 2023-05-05 |  | 1
2021 | Region IV-B | ORIENTAL MINDORO |  | P00526459LZ | Construction of Flood Mitigation Structure | 121.4581 | 12.8547 | 19599804.46 | 19599958.93 | 2022 | KING'S BUILDERS & DEVELOPMENT CORPORATION | 5921 | 2021 | 2022-10-17 | 04/08/2022 | 0 | 154.47 | 2022-10-16 |  | 1
2022 | Region IV-B | ROMBLON | CONCEPCION (ROMBLON) | P00640564LZ | Construction of Flood Mitigation Structure | 121.7316 | 12.9161 | 19799999.5 | 19799697.37 | 2023 | SIM CONSTRUCTION, TRADING AND SERVICES | 5922 | 2022 | 2023-05-06 | 07/21/2022 | 302.13 | 0 | 2023-05-05 |  | 1
2023 | Region VI | ANTIQUE | SIBALOM (ANTIQUE) | P00721728VS | Construction of Flood Mitigation Structure | 122.0149 | 10.797 | 67550000 | 67550000 | 2023 | A.D. PENDON CONSTRUCTION & SUPPLY, INC. (FORMERLY: ADP CONSTRUCTION & SUPPLY) | 5923 | 2023 | 2023-08-25 | 02/09/2023 | 0 | 0 | 2023-11-15 | 82
2023 | Region VI | AKLAN | MALAY (AKLAN) | P00721623VS | Rehabilitation / Major Repair of Flood Control Structure | 122.2959 | 11.7142 | 29400000 | 29392615.8 | 2023 | EDISON C BUILDERS & CONSTRUCTION SUPPLY | 5924 | 2023 | 2023-11-20 | 04/03/2023 | 7384.2 | 0 | 2023-10-23 |  | 28
2022 | Region IV-B | MARINDUQUE | MOGPOG (MARINDUQUE) | P00632928LZ | Construction of Flood Mitigation Structure | 121.86 | 13.4772 | 9898000 | 9905612.11 | 2022 | T.N.G. CONSTRUCTION CORPORATION | 5925 | 2022 | 2022-07-16 | 02/16/2022 | 0 | 7612.11 | 2022-07-15 |  | 1
2023 | Region IX | ZAMBOANGA DEL SUR | ZAMBOANGA CITY (ZAMBOANGA DEL SUR) | P00734014MN | Construction of Flood Mitigation Structure | 121.9381 | 6.9711 | 29400000 | 29399535.35 | 2023 | DANSBURG MACRO-BUILDERS INC. | 5926 | 2023 | 2023-12-12 | 07/31/2023 | 464.65 | 0 | 2023-12-11 |  | 1
2022 | Region IV-B | ROMBLON | CONCEPCION (ROMBLON) | P00640565LZ | Construction of Flood Mitigation Structure | 121.7316 | 12.9161 | 19799999.5 | 19503220.7 | 2023 | SIM CONSTRUCTION, TRADING AND SERVICES | 5927 | 2022 | 2023-05-06 | 07/21/2022 | 296778.8 | 0 | 2023-05-05 |  | 1
2024 | Region IV-B | ROMBLON | ODIONGAN (ROMBLON) | P00823583LZ | Construction of Flood Mitigation Structure | 122.0158 | 12.4142 | 139924999.5 | 139925000 | 2024 | SUNWEST, INC. (FORMERLY: SUNWEST CONSTRUCTION & DEVELOPMENT CORPORATION) | 5928 | 2024 | 2024-09-23 | 03/13/2024 | 0 | 0.5 | 2025-03-06 | 164
2023 | Region VI | AKLAN | MALINAO (AKLAN) | P00733714VS | Construction of Revetment | 122.3021 | 11.6519 | 9900000 | 9899987.28 | 2023 | SOLID MERCHANDISING | 5929 | 2023 | 2023-09-15 | 05/04/2023 | 12.72 | 0 | 2023-10-04 | 19
2022 | Region III | AURORA | DINALUNGAN (AURORA) | P00631164LZ | Construction of Flood Mitigation Structure | 121.8603 | 16.1156 | 14700000 | 13961777.38 | 2022 | ZF CONSTRUCTION | 5930 | 2022 | 2022-10-23 | 03/01/2022 | 738222.62 | 0 | 2022-06-24 |  | 121
2023 | Region II | CAGAYAN | GONZAGA (CAGAYAN) | P00742295LZ | Construction of Flood Mitigation Structure | 121.94 | 18.2461 | 4950000 | 4940000 | 2023 | APS CONSTRUCTION | 5931 | 2023 | 2023-07-03 | 04/05/2023 | 10000 | 0 | 2023-06-13 |  | 20
2022 | Region IV-B | ROMBLON | CONCEPCION (ROMBLON) | P00640566LZ | Construction of Flood Mitigation Structure | 121.7316 | 12.9161 | 19799999.5 | 19785666.38 | 2023 | SIM CONSTRUCTION, TRADING AND SERVICES | 5932 | 2022 | 2023-08-23 | 07/21/2022 | 14333.12 | 0 | 2023-07-24 |  | 30
2022 | Region IV-A | LAGUNA | PAGSANJAN (LAGUNA) | P00621294LZ | Construction of Flood Mitigation Structure | 121.4581 | 14.2769 | 96500000 | 93605267.39 | 2023 | DMLC BUILDERS | 5933 | 2022 | 2023-08-25 | 09/09/2022 | 2894732.61 | 0 | 2023-08-24 |  | 1
2023 | Region VI | AKLAN | MALINAO (AKLAN) | P00733712VS | Construction of Revetment | 122.3022 | 11.6457 | 49500000 | 49499996.53 | 2024 | TOPMOST DEVELOPMENT & MKTG. CORP. | 5934 | 2023 | 2024-04-17 | 04/26/2023 | 3.47 | 0 | 2024-04-23 | 6
2021 | Region II | BATANES |  | P00525943LZ | Construction of Flood Mitigation Structure | 121.9405 | 20.3491 | 36750000 | 31164000 | 2022 | ST. TIMOTHY CONSTRUCTION CORPORATION | 5935 | 2021 | 2022-11-01 | 02/24/2021 | 5586000 | 0 | 2022-02-18 |  | 256
2024 | Region II | CAGAYAN | IGUIG (CAGAYAN) | P00845937LZ | Rehabilitation / Major Repair of Drainage Structure | 121.7359 | 17.7518 | 2475000 | 2475000 | 2024 | 4MD JSL CONSTRUCTION INC. (FORMERLY: JUST SAFE LEADING (JSL) INNOVATIVE CREATION CORPORATION) | 5936 | 2024 | 2024-12-09 | 08/15/2024 | 0 | 0 | 2025-01-31 | 53
2022 | Region IV-B | ORIENTAL MINDORO | BANSUD (ORIENTAL MINDORO) | P00621116LZ | Construction of Flood Mitigation Structure | 121.4581 | 12.8544 | 48999689.3 | 48999734.76 | 2023 | LUMEL GLENN CONSTRUCTION | 5937 | 2022 | 2023-04-05 | 06/03/2022 | 0 | 45.46 | 2023-04-04 |  | 1
2023 | Region VI | ILOILO | GUIMBAL (ILOILO) | P00731678VS | Construction of Flood Mitigation Structure | 122.3022 | 10.6786 | 49000000 | 48485657.34 | 2023 | PANAY EAST COAST CONSTRUCTION & SUPPLY | 5938 | 2023 | 2023-10-23 | 03/24/2023 | 514342.66 | 0 | 2023-10-22 |  | 1
2022 | Region IX | ZAMBOANGA DEL SUR | ZAMBOANGA CITY (ZAMBOANGA DEL SUR) | P00620107MN | Construction of Flood Mitigation Structure | 121.9418 | 6.9624 | 39104996.18 | 33723565.84 | 2022 | JAYKRIS ENTERPRISES & CONSTRUCTION (FORMERLY: JAYKRIS ENTERPRISES) | 5939 | 2022 | 2022-12-23 | 02/24/2022 | 5381430.34 | 0 | 2023-01-09 | 17
2023 | Cordillera Administrative Region | KALINGA | CITY OF TABUK (CAPITAL) (KALINGA) | P00742291LZ | Construction of Flood Mitigation Structure | 121.4585 | 17.5209 | 4948513.52 | 4941699.76 | 2023 | ZERO ONE CONSTRUCTION AND SUPPLY | 5940 | 2023 | 2023-08-30 | 06/20/2023 | 6813.76 | 0 | 2023-08-30 | 0
2022 | Region II | ISABELA | CABAGAN (ISABELA) | P00632798LZ | Construction of Flood Mitigation Structure | 121.7365 | 17.4111 | 14849986.5 | 14799986.51 | 2022 | EGB CONSTRUCTION CORPORATION (FORMERLY: EGB CONSTRUCTION) | 5941 | 2022 | 2022-08-27 | 02/15/2022 | 49999.99 | 0 | 2022-08-26 |  | 1
2023 | Region VI | AKLAN | BANGA (AKLAN) | P00721984VS | Construction of Flood Mitigation Structure | 122.3043 | 11.6078 | 49000000 | 48999545.82 | 2023 | A.D. PENDON CONSTRUCTION & SUPPLY, INC. (FORMERLY: ADP CONSTRUCTION & SUPPLY) | 5942 | 2023 | 2023-10-16 | 05/04/2023 | 454.18 | 0 | 2024-01-04 | 80
2023 | Region IV-B | MARINDUQUE | MOGPOG (MARINDUQUE) | P00726949LZ | Construction of Flood Mitigation Structure | 121.8605 | 13.4899 | 77198000 | 77198380.79 | 2024 | J.D. LEGASPI CONSTRUCTION / ZUIDEN BUILDERS INC. | 5943 | 2023 | 2024-02-02 | 03/22/2023 | 0 | 380.79 | 2024-02-01 |  | 1
2022 | Region II | ISABELA | ILAGAN CITY (CAPITAL) (ISABELA) | P00621047LZ | Construction of Flood Mitigation Structure | 121.9446 | 17.1071 | 44100000 | 44050000 | 2023 | EGB CONSTRUCTION CORPORATION (FORMERLY: EGB CONSTRUCTION) | 5944 | 2022 | 2023-02-05 | 05/18/2022 | 50000 | 0 | 2023-02-04 |  | 1
2023 | Region IV-A | LAGUNA | PAGSANJAN (LAGUNA) | P00740388LZ | Construction of Flood Mitigation Structure | 121.4596 | 14.2698 | 91675000 | 90687783.34 | 2023 | PROTECH CONSTRUCTION & DEVELOPMENT CORP. (FORMERLY / JOBEL ENTERPRISES | 5945 | 2023 | 2023-11-07 | 04/14/2023 | 987216.66 | 0 | 2024-03-20 | 134
2023 | Region II | CAGAYAN | TUGUEGARAO CITY (CAPITAL) (CAGAYAN) | P00742302LZ | Construction of Flood Mitigation Structure | 121.7372 | 17.6415 | 4950000 | 4925536.59 | 2023 | 4MD JSL CONSTRUCTION INC. (FORMERLY: JUST SAFE LEADING (JSL) INNOVATIVE CREATION CORPORATION) | 5946 | 2023 | 2023-11-15 | 04/05/2023 | 24463.41 | 0 | 2023-11-16 | 1
2023 | Region VI | ILOILO | GUIMBAL (ILOILO) | P00731680VS | Construction of Flood Mitigation Structure | 122.3044 | 10.6844 | 49000000 | 48479090.03 | 2024 | PANAY EAST COAST CONSTRUCTION & SUPPLY | 5947 | 2023 | 2024-04-03 | 03/23/2023 | 520909.97 | 0 | 2024-01-26 |  | 68
2024 | Region II | ISABELA | JONES (ISABELA) | P00843237LZ | Construction of Flood Mitigation Structure | 121.7384 | 16.5622 | 96500000 | 96475000 | 2024 | JWU CONSTRUCTION AND SUPPLY | 5948 | 2024 | 2024-11-12 | 06/13/2024 | 25000 | 0 | 2025-06-18 | 218
2022 | Region IV-B | MARINDUQUE | BUENAVISTA (MARINDUQUE) | P00639508LZ | Construction of Flood Mitigation Structure | 121.945 | 13.252 | 14698000 | 14698930.12 | 2022 | JEFF ENTERPRISES | 5949 | 2022 | 2022-11-20 | 03/30/2022 | 0 | 930.12 | 2022-11-19 |  | 1
2023 | Region II | ISABELA | JONES (ISABELA) | P00726139LZ | Construction of Flood Mitigation Structure | 121.861 | 16.5258 | 29400000 | 29399861.97 | 2023 | CASAN CONSTRUCTION AND TRADING | 5950 | 2023 | 2023-04-26 | 02/28/2023 | 138.03 | 0 | 2023-09-18 | 145
2023 | Region II | ISABELA | ANGADANAN (ISABELA) | P00727265LZ | Construction of Flood Mitigation Structure | 121.7395 | 16.7475 | 95858913.52 | 94704698.46 | 2023 | INFINITUM 888 CONSTRUCTION AND DEVELOPMENT CORPORATION / C.R. DOMINGO CONSTRUCTION AND POWER DEVELOPMENT, INC. (FOR. C.R. DOMINGO CONSTRUCTION, INC.) | 5951 | 2023 | 2023-11-06 | 03/15/2023 | 1154215.06 | 0 | 2024-02-01 | 87
2023 | Region IV-A | LAGUNA | LUMBAN (LAGUNA) | P00726221LZ | Construction of Flood Mitigation Structure | 121.4603 | 14.2892 | 49000000 | 48999662.4 | 2023 | JUSTBILT BUILDERS | 5952 | 2023 | 2023-07-06 | 02/09/2023 | 337.6 | 0 | 2023-11-02 | 119
2023 | Region II | ISABELA | QUIRINO (ISABELA) | P00726417LZ | Construction of Flood Mitigation Structure | 121.7396 | 17.1147 | 48250000 | 48248853.2 | 2023 | ANORE CONSTRUCTION | 5953 | 2023 | 2023-08-06 | 02/27/2023 | 1146.8 | 0 | 2023-09-23 | 48
2023 | Region II | ISABELA | CORDON (ISABELA) | P00736191LZ | Construction of Flood Mitigation Structure | 121.4615 | 16.7311 | 49000000 | 48999666.52 | 2024 | DANYSONS CONSTRUCTION AND DEVELOPMENT CORPORATION (FORMERLY: DANYSONS CONSTRUCTION) | 5954 | 2023 | 2024-05-13 | 02/22/2023 | 333.48 | 0 | 2023-12-13 |  | 152
2023 | Region II | ISABELA | JONES (ISABELA) | P00726138LZ | Construction of Flood Mitigation Structure | 121.8622 | 16.5311 | 29400000 | 29399253.02 | 2023 | CASAN CONSTRUCTION AND TRADING | 5955 | 2023 | 2023-06-15 | 02/20/2023 | 746.98 | 0 | 2023-09-10 | 87
2023 | Region II | ISABELA | CORDON (ISABELA) | P00736190LZ | Construction of Flood Mitigation Structure | 121.4616 | 16.7311 | 49000000 | 48999858.51 | 2024 | DANYSONS CONSTRUCTION AND DEVELOPMENT CORPORATION (FORMERLY: DANYSONS CONSTRUCTION) | 5956 | 2023 | 2024-05-14 | 02/22/2023 | 141.49 | 0 | 2023-12-16 |  | 150
2023 | Region IV-A | LAGUNA | PAGSANJAN (LAGUNA) | P00740389LZ | Construction of Flood Mitigation Structure | 121.4621 | 14.267 | 91675000 | 88893886 | 2024 | PROTECH CONSTRUCTION & DEVELOPMENT CORP. (FORMERLY | 5957 | 2023 | 2024-02-21 | 04/14/2023 | 2781114 | 0 | 2024-03-27 | 35
2022 | Region II | ISABELA | JONES (ISABELA) | P00639464LZ | Construction of Flood Mitigation Structure | 121.8622 | 16.531 | 34300000 | 34300000 | 2022 | MAR-DEB CONSTRUCTION & DEVELOPMENT CORP. (FORMERLY: MAR-DEB CONSTRUCTION & DEVELOPMENT) | 5958 | 2022 | 2022-11-23 | 06/28/2022 | 0 | 0 | 2023-01-22 | 60
2024 | Region IV-B | ORIENTAL MINDORO | BANSUD (ORIENTAL MINDORO) | P00825250LZ | Construction of Flood Mitigation Structure | 121.4622 | 12.8551 | 49000000 | 48997595.16 | 2024 | IGWT-JAV CONSTRUCTION & DEVELOPMENT CORPORATION | 5959 | 2024 | 2024-09-26 | 03/11/2024 | 2404.84 | 0 | 2024-09-25 |  | 1
2023 | Region II | ISABELA | JONES (ISABELA) | P00726873LZ | Construction of Flood Mitigation Structure | 121.8627 | 16.504 | 96500000 | 96499762.04 | 2023 | V.B. MANUBAY CONSTRUCTION | 5960 | 2023 | 2023-08-14 | 06/01/2023 | 237.96 | 0 | 2024-03-23 | 222
2023 | Region IV-A | LAGUNA | LUMBAN (LAGUNA) | P00726222LZ | Construction of Flood Mitigation Structure | 121.4631 | 14.286 | 49000000 | 48999768.02 | 2023 | PROTECH CONSTRUCTION & DEVELOPMENT CORP. (FORMERLY | 5961 | 2023 | 2023-08-09 | 02/09/2023 | 231.98 | 0 | 2023-11-02 | 85
2023 | Region IV-B | MARINDUQUE | MOGPOG (MARINDUQUE) | P00737546LZ | Construction of Flood Mitigation Structure | 121.8631 | 13.4926 | 4947999.99 | 4849037.42 | 2023 | KEJAMARENIK CONSTRUCTION & CONSTRUCTION SUPPLIES | 5962 | 2023 | 2023-04-20 | 01/31/2023 | 98962.57 | 0 | 2023-04-20 | 0
2023 | Region III | AURORA | MARIA AURORA (AURORA) | P00740579LZ | Construction of Flood Mitigation Structure | 121.4631 | 15.8622 | 29400000 | 29400000 | 2023 | DALCON CONSTRUCTION | 5963 | 2023 | 2023-06-26 | 03/28/2023 | 0 | 0 | 2023-08-24 | 59
2021 | Region IV-B | MARINDUQUE |  | P00526330LZ | Construction of Flood Mitigation Structure | 121.8633 | 13.4391 | 96498000 | 96502061.41 | 2022 | SUNWEST, INC. (FORMERLY: SUNWEST CONSTRUCTION & DEVELOPMENT CORPORATION) | 5964 | 2021 | 2022-09-16 | 03/26/2021 | 0 | 4061.41 | 2022-09-16 | 0
2023 | Region II | CAGAYAN | PIAT (CAGAYAN) | P00727349LZ | Construction of Flood Mitigation Structure | 121.4644 | 17.8256 | 29400000 | 29400000 | 2023 | DEKM CONSTRUCTION / DECERIE'S CONSTRUCTION | 5965 | 2023 | 2023-11-24 | 02/23/2023 | 0 | 0 | 2023-10-12 |  | 43
2022 | Region IV-B | ORIENTAL MINDORO | ROXAS (ORIENTAL MINDORO) | P00621118LZ | Construction of Flood Mitigation Structure | 121.4658 | 12.6075 | 48999355.56 | 48999910.68 | 2022 | ALBERTO UY CONSTRUCTION & DEVELOPMENT | 5966 | 2022 | 2022-12-16 | 04/11/2022 | 0 | 555.12 | 2022-12-15 |  | 1
2022 | Region IV-B | MARINDUQUE | MOGPOG (MARINDUQUE) | P00639509LZ | Construction of Flood Mitigation Structure | 121.8642 | 13.4788 | 39198000 | 38862577.77 | 2023 | SARGASSO CONSTRUCTION & DEVELOPMENT CORP. | 5967 | 2022 | 2023-03-27 | 03/30/2022 | 335422.23 | 0 | 2023-04-10 | 14
2023 | Region III | AURORA | MARIA AURORA (AURORA) | P00740580LZ | Construction of Flood Mitigation Structure | 121.4665 | 15.8148 | 29400000 | 29400000 | 2023 | DALCON CONSTRUCTION | 5968 | 2023 | 2023-07-25 | 03/28/2023 | 0 | 0 | 2023-08-26 | 32
2024 | Region II | CAGAYAN | LASAM (CAGAYAN) | P00823332LZ | Construction of Flood Mitigation Structure | 121.4689 | 18.0264 | 19600000 | 19266187.98 | 2024 | FLAVIE CIVIL ENGINEERING CONSTRUCTION | 5969 | 2024 | 2024-07-12 | 02/08/2024 | 333812.02 | 0 | 2024-07-11 |  | 1
2022 | Region IV-B | ORIENTAL MINDORO | BONGABONG (ORIENTAL MINDORO) | P00639533LZ | Construction of Flood Mitigation Structure | 121.4692 | 12.7589 | 48999976.68 | 48999912.4 | 2023 | ALBERTO UY CONSTRUCTION & DEVELOPMENT | 5970 | 2022 | 2023-02-14 | 04/11/2022 | 64.28 | 0 | 2023-02-13 |  | 1
2023 | Region II | CAGAYAN | LASAM (CAGAYAN) | P00726117LZ | Construction of Flood Mitigation Structure | 121.4693 | 18.0273 | 23428860 | 22758838 | 2023 | FLAVIE CIVIL ENGINEERING CONSTRUCTION | 5971 | 2023 | 2023-07-15 | 02/02/2023 | 670022 | 0 | 2023-07-14 |  | 1
2023 | Region IV-A | LAGUNA | PANGIL (LAGUNA) | P00725817LZ | Construction of Flood Mitigation Structure | 121.4712 | 14.4051 | 74723810 | 72606074.11 | 2024 | DMLC BUILDERS | 5972 | 2023 | 2024-02-19 | 02/09/2023 | 2117735.89 | 0 | 2024-02-16 |  | 3
2024 | Region IV-B | ORIENTAL MINDORO | GLORIA (ORIENTAL MINDORO) | P00821354LZ | Construction of Flood Mitigation Structure | 121.4714 | 12.9436 | 67550000 | 67547131.91 | 2024 | ALBERTO UY CONSTRUCTION & DEVELOPMENT / BANAYAD CONSTRUCTION SERVICES | 5973 | 2024 | 2024-09-20 | 02/15/2024 | 2868.09 | 0 | 2024-09-30 | 10
2023 | Region II | ISABELA | CORDON (ISABELA) | P00736607LZ | Construction of Flood Mitigation Structure | 121.472 | 16.6842 | 49000000 | 48999983.08 | 2023 | DANYSONS CONSTRUCTION AND DEVELOPMENT CORPORATION (FORMERLY: DANYSONS CONSTRUCTION) | 5974 | 2023 | 2023-12-11 | 02/17/2023 | 16.92 | 0 | 2023-12-10 |  | 1
2024 | Region II | CAGAYAN | PIAT (CAGAYAN) | P00845935LZ | Construction of Flood Mitigation Structure | 121.4731 | 17.7949 | 9900000 | 9701811.56 | 2024 | DEKM CONSTRUCTION | 5975 | 2024 | 2024-12-29 | 04/04/2024 | 198188.44 | 0 | 2024-07-19 |  | 163
2022 | Region III | AURORA | MARIA AURORA (AURORA) | P00631144LZ | Construction of Drainage Structure | 121.4741 | 15.7673 | 39200000 | 39200000 | 2022 | MORNING STEEL CONSTRUCTION | 5976 | 2022 | 2022-11-16 | 03/01/2022 | 0 | 0 | 2022-11-15 |  | 1
2022 | Region IV-B | ORIENTAL MINDORO | GLORIA (ORIENTAL MINDORO) | P00639532LZ | Construction of Flood Mitigation Structure | 121.4744 | 12.9444 | 19599699.81 | 19599783.18 | 2022 | EGB CONSTRUCTION CORPORATION (FORMERLY: EGB CONSTRUCTION) | 5977 | 2022 | 2022-12-19 | 04/13/2022 | 0 | 83.37 | 2022-12-18 |  | 1
2024 | Region II | ISABELA | CORDON (ISABELA) | P00843283LZ | Construction of Flood Mitigation Structure | 121.4745 | 16.6837 | 96500000 | 96500000 | 2024 | GACUTAN CONSTRUCTION INC. (FORMERLY: GACUTAN CONSTRUCTION) | 5978 | 2024 | 2024-11-11 | 06/24/2024 | 0 | 0 | 2025-04-28 | 168
2024 | Cordillera Administrative Region | KALINGA | CITY OF TABUK (CAPITAL) (KALINGA) | P00824672LZ | Construction of Flood Mitigation Structure | 121.4757 | 17.5563 | 9800000 | 9793424.9 | 2024 | ZERO ONE CONSTRUCTION AND SUPPLY | 5979 | 2024 | 2024-07-25 | 06/11/2024 | 6575.1 | 0 | 2024-10-07 | 74
2023 | Region II | ISABELA | CORDON (ISABELA) | P00736608LZ | Construction of Flood Mitigation Structure | 121.4762 | 16.7239 | 49000000 | 48999988.6 | 2023 | DANYSONS CONSTRUCTION AND DEVELOPMENT CORPORATION (FORMERLY: DANYSONS CONSTRUCTION) | 5980 | 2023 | 2023-10-31 | 02/22/2023 | 11.4 | 0 | 2023-11-15 | 15
2022 | Region IV-B | ORIENTAL MINDORO | ROXAS (ORIENTAL MINDORO) | P00621117LZ | Construction of Flood Mitigation Structure | 121.4767 | 12.5875 | 48999150.02 | 48999931.65 | 2022 | LUMEL GLENN CONSTRUCTION | 5981 | 2022 | 2022-12-18 | 04/13/2022 | 0 | 781.63 | 2022-12-17 |  | 1
2024 | Region II | ISABELA | CORDON (ISABELA) | P00820784LZ | Construction of Flood Mitigation Structure | 121.477 | 16.7233 | 9800000 | 9636008.66 | 2024 | FNS BUILDERS & ENTERPRISE | 5982 | 2024 | 2024-08-10 | 07/01/2024 | 163991.34 | 0 | 2024-10-31 | 82
2024 | Region II | ISABELA | SAN AGUSTIN (ISABELA) | P00820786LZ | Construction of Flood Mitigation Structure | 121.4774 | 16.7226 | 42147840 | 42147840 | 2024 | NTL BUILDERS AND DEVELOPER | 5983 | 2024 | 2024-05-17 | 02/07/2024 | 0 | 0 | 2024-09-09 | 115
2022 | Region IV-B | ORIENTAL MINDORO | BONGABONG (ORIENTAL MINDORO) | P00621121LZ | Construction of Flood Mitigation Structure | 121.4783 | 12.6739 | 48999243.91 | 48999950.04 | 2023 | TWENTY SIXTEEN CONSTRUCTION AND GENERAL MERCHANDISE / LUMEL GLENN CONSTRUCTION | 5984 | 2022 | 2023-01-17 | 04/13/2022 | 0 | 706.13 | 2023-01-16 |  | 1
2022 | Cordillera Administrative Region | MOUNTAIN PROVINCE | PARACELIS (MOUNTAIN PROVINCE) | P00620138LZ | Construction of Flood Mitigation Structure | 121.4788 | 17.1249 | 57900000 | 57900000 | 2022 | MG SAMIDAN CONSTRUCTION / A.P.O. GENERAL CONSTRUCTION | 5985 | 2022 | 2022-11-23 | 02/24/2022 | 0 | 0 | 2023-01-29 | 67
2024 | Region III | AURORA | SAN LUIS (AURORA) | P00824692LZ | Construction of Flood Mitigation Structure | 121.4798 | 15.7172 | 49000000 | 49000000 | 2024 | DALCON CONSTRUCTION | 5986 | 2024 | 2024-08-22 | 05/07/2024 | 0 | 0 | 2024-10-19 | 58
2022 | Region IV-B | ORIENTAL MINDORO | MANSALAY (ORIENTAL MINDORO) | P00621120LZ | Construction of Flood Mitigation Structure | 121.4806 | 12.5606 | 49000000 | 47597494.09 | 2023 | ALBERTO UY CONSTRUCTION & DEVELOPMENT | 5987 | 2022 | 2023-08-21 | 07/20/2022 | 1402505.91 | 0 | 2023-08-20 |  | 1
2023 | Cordillera Administrative Region | IFUGAO | ALFONSO LISTA (POTIA) (IFUGAO) | P00725655LZ | Construction of Flood Mitigation Structure | 121.4806 | 16.9312 | 86849025.68 | 86850000 | 2024 | DJY CONSTRUCTION | 5988 | 2023 | 2024-01-31 | 05/07/2023 | 0 | 974.32 | 2024-01-30 |  | 1
2023 | Region II | CAGAYAN | SANTO NIÃ‘O (FAIRE) (CAGAYAN) | P00727348LZ | Construction of Flood Mitigation Structure | 121.4816 | 17.8501 | 29400000 | 28665000 | 2023 | TJMT CONSTRUCTION / VHT CAGAYAN BUILDERS CORPORATION | 5989 | 2023 | 2023-09-09 | 03/21/2023 | 735000 | 0 | 2023-09-08 |  | 1
2023 | Region IV-B | ORIENTAL MINDORO | BONGABONG (ORIENTAL MINDORO) | P00727199LZ | Construction of Flood Mitigation Structure | 121.4817 | 12.6714 | 49000000 | 48999818.34 | 2023 | LUMEL GLENN CONSTRUCTION | 5990 | 2023 | 2023-10-25 | 03/20/2023 | 181.66 | 0 | 2023-10-24 |  | 1
2021 | Region IV-B | ORIENTAL MINDORO |  | P00561580LZ | Construction of Flood Mitigation Structure | 121.4817 | 12.7592 | 29399220.03 | 29399927.83 | 2022 | NORTHERN BUILDERS | 5991 | 2021 | 2022-10-24 | 04/08/2022 | 0 | 707.8 | 2022-10-30 | 6
2021 | Region IV-B | ORIENTAL MINDORO |  | P00526460LZ | Construction of Flood Mitigation Structure | 121.4825 | 12.5817 | 19599121.99 | 19599948.04 | 2022 | D.M. MALIWANAG BUILDERS AND ENTERPRISES | 5992 | 2021 | 2022-10-14 | 04/08/2022 | 0 | 826.05 | 2022-10-13 |  | 1
2023 | Region IV-B | ORIENTAL MINDORO | MANSALAY (ORIENTAL MINDORO) | P00726594LZ | Construction of Revetment | 121.4839 | 12.5814 | 82024998.49 | 82022349.1 | 2023 | LUMEL GLENN CONSTRUCTION | 5993 | 2023 | 2023-12-18 | 02/17/2023 | 2649.39 | 0 | 2023-12-17 |  | 1
2022 | Cordillera Administrative Region | IFUGAO | ALFONSO LISTA (POTIA) (IFUGAO) | P00620480LZ | Construction of Flood Mitigation Structure | 121.4842 | 16.9311 | 76237286.54 | 24010000 | 2023 | DJY CONSTRUCTION / RODEKOM GENERAL CONSTRUCTION AND ENTERPRISE | 5994 | 2022 | 2023-03-05 | 05/23/2022 | 52227286.54 | 0 | 2023-03-04 |  | 1
2023 | Region IV-B | ORIENTAL MINDORO | MANSALAY (ORIENTAL MINDORO) | P00725863LZ | Construction of Revetment | 121.4864 | 12.5542 | 77199988.11 | 77197292.65 | 2024 | ROAD EDGE TRADING & DEVELOPMENT SERVICES | 5995 | 2023 | 2024-02-06 | 02/17/2023 | 2695.46 | 0 | 2024-02-05 |  | 1
2022 | Region IV-B | ORIENTAL MINDORO | MANSALAY (ORIENTAL MINDORO) | P00621119LZ | Construction of Flood Mitigation Structure | 121.4864 | 12.5714 | 48999404.78 | 48996447 | 2023 | LUMEL GLENN CONSTRUCTION | 5996 | 2022 | 2023-03-09 | 06/03/2022 | 2957.78 | 0 | 2023-03-08 |  | 1
2023 | Region II | CAGAYAN | BALLESTEROS (CAGAYAN) | P00740571LZ | Construction of Flood Mitigation Structure | 121.488 | 18.3078 | 9800000 | 9800000 | 2023 | J.G. YACAS CONSTRUCTION, SUPPLY AND EQUIPMENT RENTAL | 5997 | 2023 | 2023-08-18 | 04/28/2023 | 0 | 0 | 2023-08-17 |  | 1
2024 | Region IV-B | ORIENTAL MINDORO | MANSALAY (ORIENTAL MINDORO) | P00825252LZ | Construction of Flood Mitigation Structure | 121.4883 | 12.553 | 49000000 | 48996871.4 | 2024 | CAMBERWELL CONSTRUCTION AND SUPPLIES | 5998 | 2024 | 2024-12-16 | 03/04/2024 | 3128.6 | 0 | 2024-12-16 | 0
2023 | Region IV-B | OCCIDENTAL MINDORO | SANTA CRUZ (OCCIDENTAL MINDORO) | P00725867LZ | Construction of Revetment | 121.4905 | 12.7495 | 96499999.33 | 96496887.97 | 2023 | ST. MATTHEW GEN. CONTRACTOR & DEVELOPMENT CORP. | 5999 | 2023 | 2023-12-10 | 02/11/2023 | 3111.36 | 0 | 2024-01-02 | 23
2022 | Region III | AURORA | MARIA AURORA (AURORA) | P00620496LZ | Construction of Flood Mitigation Structure | 121.4925 | 15.7524 | 48248290 | 48248213.19 | 2023 | R.D. TALENS CONSTRUCTION AND TRADING | 6000 | 2022 | 2023-04-06 | 08/15/2022 | 76.81 | 0 | 2023-04-05 |  | 1
2023 | Region VI | NEGROS OCCIDENTAL | PULUPANDAN (NEGROS OCCIDENTAL) | P00733734VS | Construction of Flood Mitigation Structure | 122.8113 | 10.5269 | 49499999.57 | 49499990 | 2023 | JAIME B. CHING ENTERPRISES | 6001 | 2023 | 2023-12-24 | 04/11/2023 | 9.57 | 0 | 2023-10-22 |  | 63
2022 | Region VI | NEGROS OCCIDENTAL | VALLADOLID (NEGROS OCCIDENTAL) | P00633222VS | Construction of Slope Protection Structure | 122.8207 | 10.4778 | 48999995.95 | 48999974.49 | 2022 | JAIME B. CHING ENTERPRISES | 6002 | 2022 | 2022-10-18 | 03/31/2022 | 21.46 | 0 | 2022-10-17 |  | 1
2024 | Region VI | NEGROS OCCIDENTAL | VALLADOLID (NEGROS OCCIDENTAL) | P00820017VS | Construction of Flood Mitigation Structure | 122.8211 | 10.4786 | 70637027.15 | 70173447.67 | 2024 | R.A. CONSTRUCTION DEVELOPMENT CORPORATION (FORMERLY: R.A. CONSTRUCTION & GENERAL MERCHANDISE) | 6003 | 2024 | 2024-10-14 | 03/05/2024 | 463579.48 | 0 | 2024-11-15 | 32
2023 | Region VI | CAPIZ | PANAY (CAPIZ) | P00721735VS | Construction of Flood Mitigation Structure | 122.8218 | 11.4931 | 88201000 | 88200838.4 | 2024 | MEGAGOLD CONSTRUCTION AND DEVELOPMENT, OPC / MONOLITHIC CONSTRUCTION & CONCRETE PRODUCTS, INC. | 6004 | 2023 | 2024-03-21 | 03/08/2023 | 161.6 | 0 | 2024-03-20 |  | 1
2022 | Region VII | NEGROS ORIENTAL | CITY OF BAYAWAN (TULONG) (NEGROS ORIENTAL) | P00620313VS | Rehabilitation / Major Repair of Flood Control Structure | 122.8231 | 9.4 | 39200000 | 39200000 | 2023 | LEGACY CONSTRUCTION CORPORATION (FORMERLY: LEGACY CONSTRUCTION) | 6005 | 2022 | 2023-02-28 | 02/17/2022 | 0 | 0 | 2023-02-27 |  | 1
2022 | Region V | CAMARINES NORTE | LABO (CAMARINES NORTE) | P00631388LZ | Construction of Flood Mitigation Structure | 122.8232 | 14.1423 | 23519677.48 | 23519677.48 | 2023 | BRENTMIN ROOFING ENTERPRISE | 6006 | 2022 | 2023-05-04 | 03/31/2022 | 0 | 0 | 2023-05-03 |  | 1
2023 | Region VI | NEGROS OCCIDENTAL | BACOLOD CITY (CAPITAL) (NEGROS OCCIDENTAL) | P00721629VS | Construction of Drainage Structure | 122.954 | 10.6642 | 19600000 | 19296606.08 | 2023 | GOLDSTAR MARKETING & CONSTRUCTION SERVICES, INC. | 6007 | 2023 | 2023-08-28 | 02/08/2023 | 303393.92 | 0 | 2023-08-28 | 0
2023 | Region VI | ILOILO | ALIMODIAN (ILOILO) | P00721748VS | Construction of Flood Mitigation Structure | 122.4347 | 10.8184 | 96500000 | 96499391.23 | 2024 | A.D. PENDON CONSTRUCTION & SUPPLY, INC. (FORMERLY: ADP CONSTRUCTION & SUPPLY) | 6008 | 2023 | 2024-02-17 | 02/10/2023 | 608.77 | 0 | 2024-02-16 |  | 1
2022 | Region VII | NEGROS ORIENTAL | CITY OF BAYAWAN (TULONG) (NEGROS ORIENTAL) | P00620310VS | Rehabilitation / Major Repair of Flood Control Structure | 122.8233 | 9.3997 | 42525140 | 42525140 | 2023 | LEGACY CONSTRUCTION CORPORATION (FORMERLY: LEGACY CONSTRUCTION) | 6009 | 2022 | 2023-03-23 | 02/17/2022 | 0 | 0 | 2023-03-22 |  | 1
2022 | Region VII | NEGROS ORIENTAL | CITY OF BAYAWAN (TULONG) (NEGROS ORIENTAL) | P00620311VS | Rehabilitation / Major Repair of Flood Control Structure | 122.8233 | 9.3997 | 38778600 | 38778600 | 2023 | LEGACY CONSTRUCTION CORPORATION (FORMERLY: LEGACY CONSTRUCTION) | 6010 | 2022 | 2023-03-23 | 02/17/2022 | 0 | 0 | 2023-03-22 |  | 1
2022 | Region VII | NEGROS ORIENTAL | CITY OF BAYAWAN (TULONG) (NEGROS ORIENTAL) | P00620312VS | Rehabilitation / Major Repair of Flood Control Structure | 122.8233 | 9.4 | 42826000 | 42826000 | 2023 | LEGACY CONSTRUCTION CORPORATION (FORMERLY: LEGACY CONSTRUCTION) | 6011 | 2022 | 2023-02-14 | 02/17/2022 | 0 | 0 | 2023-02-13 |  | 1
2022 | Region VI | CAPIZ | PANAY (CAPIZ) | P00620264VS | Construction of Flood Mitigation Structure | 122.8241 | 11.4892 | 62725000 | 62724975.2 | 2022 | MRRM TRADING & CONSTRUCTION / SALMEGA BUILDERS | 6012 | 2022 | 2022-11-15 | 02/28/2022 | 24.8 | 0 | 2022-12-23 | 38
2022 | Region VI | CAPIZ | MA-AYON (CAPIZ) | P00620265VS | Construction of Flood Mitigation Structure | 122.8247 | 11.3754 | 57900000 | 57899349.35 | 2023 | A.D. PENDON CONSTRUCTION & SUPPLY, INC. (FORMERLY: ADP CONSTRUCTION & SUPPLY) | 6013 | 2022 | 2023-09-10 | 03/27/2022 | 650.65 | 0 | 2023-03-03 |  | 191
2023 | Region V | CAMARINES NORTE | LABO (CAMARINES NORTE) | P00736150LZ | Construction of Flood Mitigation Structure | 122.8282 | 14.1454 | 57899877.77 | 57899877.77 | 2023 | C.B. GARAY PHILWIDE BUILDERS | 6014 | 2023 | 2023-12-31 | 04/05/2023 | 0 | 0 | 2023-12-30 |  | 1
2022 | Region VI | CAPIZ | PONTEVEDRA (CAPIZ) | P00620263VS | Construction of Flood Mitigation Structure | 122.8283 | 11.4842 | 62725000 | 62724396.82 | 2023 | ST. TIMOTHY CONSTRUCTION CORPORATION | 6015 | 2022 | 2023-12-21 | 02/28/2022 | 603.18 | 0 | 2024-02-02 | 43
2024 | Region VI | NEGROS OCCIDENTAL | CITY OF KABANKALAN (NEGROS OCCIDENTAL) | P00820291VS | Construction of Flood Mitigation Structure | 122.8293 | 9.9564 | 110098780 | 110098780 | 2024 | JAIME B. CHING ENTERPRISES | 6016 | 2024 | 2024-09-23 | 02/22/2024 | 0 | 0 | 2024-10-14 | 21
2023 | Region V | CAMARINES NORTE | LABO (CAMARINES NORTE) | P00736126LZ | Construction of Flood Mitigation Structure | 122.8296 | 14.1161 | 96499853.8 | 77004263.34 | 2024 | PARTIDO CONSTRUCTION & SUPPLY | 6017 | 2023 | 2024-01-05 | 04/05/2023 | 19495590.46 | 0 | 2024-01-04 |  | 1
2023 | Region V | CAMARINES NORTE | LABO (CAMARINES NORTE) | P00736127LZ | Construction of Flood Mitigation Structure | 122.8297 | 14.1486 | 96499492.62 | 95553202.05 | 2024 | EUS CONSTRUCTION | 6018 | 2023 | 2024-07-26 | 07/27/2023 | 946290.57 | 0 | 2024-07-25 |  | 1
2022 | Region V | CAMARINES NORTE | LABO (CAMARINES NORTE) | P00631397LZ | Construction of Flood Mitigation Structure | 122.8304 | 14.1494 | 19599469.25 | 19014625.6 | 2023 | EUS CONSTRUCTION | 6019 | 2022 | 2023-02-14 | 03/22/2022 | 584843.65 | 0 | 2023-02-13 |  | 1
2023 | Region V | CAMARINES NORTE | LABO (CAMARINES NORTE) | P00737562LZ | Construction of Flood Mitigation Structure | 122.8308 | 14.1181 | 49499290.12 | 48969976.29 | 2024 | C.B. GARAY PHILWIDE BUILDERS | 6020 | 2023 | 2024-03-24 | 04/05/2023 | 529313.83 | 0 | 2024-03-23 |  | 1
2022 | Region V | CAMARINES NORTE | LABO (CAMARINES NORTE) | P00620698LZ | Construction of Flood Mitigation Structure | 122.8314 | 14.1508 | 48999850.41 | 48999850.41 | 2023 | BRENTMIN ROOFING ENTERPRISE | 6021 | 2022 | 2023-03-30 | 03/31/2022 | 0 | 0 | 2023-03-29 |  | 1
2022 | Region VI | NEGROS OCCIDENTAL | BAGO CITY (NEGROS OCCIDENTAL) | P00620307VS | Construction of Flood Mitigation Structure | 122.832 | 10.5329 | 48999994.27 | 48999243.3 | 2022 | JAIME B. CHING ENTERPRISES | 6022 | 2022 | 2022-09-03 | 02/10/2022 | 750.97 | 0 | 2022-09-02 |  | 1
2022 | Region V | CAMARINES NORTE | LABO (CAMARINES NORTE) | P00631389LZ | Construction of Flood Mitigation Structure | 122.8327 | 14.1521 | 34299370 | 33270844.9 | 2023 | BRENTMIN ROOFING ENTERPRISE | 6023 | 2022 | 2023-03-03 | 03/21/2022 | 1028525.1 | 0 | 2023-03-02 |  | 1
2022 | Region V | CAMARINES NORTE | LABO (CAMARINES NORTE) | P00631390LZ | Construction of Flood Mitigation Structure | 122.8332 | 14.1507 | 34299455.1 | 34299455.1 | 2023 | EUS CONSTRUCTION | 6024 | 2022 | 2023-05-04 | 03/21/2022 | 0 | 0 | 2023-05-03 |  | 1
2022 | Region V | CAMARINES NORTE | LABO (CAMARINES NORTE) | P00631392LZ | Construction of Flood Mitigation Structure | 122.8341 | 14.1497 | 24499786.26 | 23747366.08 | 2023 | EUS CONSTRUCTION | 6025 | 2022 | 2023-06-02 | 03/23/2022 | 752420.18 | 0 | 2023-06-01 |  | 1
2023 | Region VI | NEGROS OCCIDENTAL | BAGO CITY (NEGROS OCCIDENTAL) | P00721745VS | Construction of Flood Mitigation Structure | 122.8344 | 10.5267 | 80094995.15 | 80094986.22 | 2024 | JAIME B. CHING ENTERPRISES | 6026 | 2023 | 2024-02-11 | 04/11/2023 | 8.93 | 0 | 2024-01-29 |  | 13
2023 | Region V | CAMARINES NORTE | LABO (CAMARINES NORTE) | P00736626LZ | Construction of Flood Mitigation Structure | 122.8344 | 14.1247 | 48999703.48 | 48999703.48 | 2024 | C.B. GARAY PHILWIDE BUILDERS | 6027 | 2023 | 2024-05-13 | 05/03/2023 | 0 | 0 | 2024-05-12 |  | 1
2021 | Region V | CAMARINES NORTE |  | P00561470LZ | Construction of Flood Mitigation Structure | 122.835 | 14.1491 | 96499331.17 | 96499331.17 | 2022 | EUS CONSTRUCTION | 6028 | 2021 | 2022-09-02 | 12/01/2021 | 0 | 0 | 2022-09-01 |  | 1
2022 | Region V | CAMARINES NORTE | LABO (CAMARINES NORTE) | P00631393LZ | Construction of Flood Mitigation Structure | 122.8355 | 14.1446 | 24499765.86 | 24499765.86 | 2022 | EUS CONSTRUCTION | 6029 | 2022 | 2022-10-22 | 03/11/2022 | 0 | 0 | 2022-10-21 |  | 1
2023 | Region V | CAMARINES NORTE | LABO (CAMARINES NORTE) | P00736130LZ | Construction of Flood Mitigation Structure | 122.8358 | 14.1268 | 48999537.51 | 48250000 | 2024 | C.B. GARAY PHILWIDE BUILDERS | 6030 | 2023 | 2024-05-08 | 04/05/2023 | 749537.51 | 0 | 2024-05-07 |  | 1
2022 | Region VI | AKLAN | BANGA (AKLAN) | P00620293VS | Rehabilitation / Major Repair of Flood Control Structure | 122.3048 | 11.5652 | 19600000 | 19177758.11 | 2023 | G.F. ROVERO MERCHANDISING | 6031 | 2022 | 2023-04-17 | 02/18/2022 | 422241.89 | 0 | 2022-09-01 |  | 228
2022 | Region V | CAMARINES NORTE | LABO (CAMARINES NORTE) | P00631411LZ | Construction of Flood Mitigation Structure | 122.8365 | 14.1403 | 48999753.44 | 48997951.93 | 2022 | BRENTMIN ROOFING ENTERPRISE | 6032 | 2022 | 2022-11-25 | 03/17/2022 | 1801.51 | 0 | 2022-11-24 |  | 1
2022 | Region V | CAMARINES NORTE | LABO (CAMARINES NORTE) | P00631394LZ | Construction of Flood Mitigation Structure | 122.8368 | 14.1418 | 34299611.43 | 33270352.17 | 2023 | BRENTMIN ROOFING ENTERPRISE | 6033 | 2022 | 2023-03-03 | 03/21/2022 | 1029259.26 | 0 | 2023-03-02 |  | 1
2022 | Region VI | NEGROS OCCIDENTAL | CITY OF KABANKALAN (NEGROS OCCIDENTAL) | P00630209VS | Construction of Flood Mitigation Structure | 122.8376 | 9.9681 | 49000000 | 49000000 | 2022 | JAIME B. CHING ENTERPRISES | 6034 | 2022 | 2022-10-25 | 02/17/2022 | 0 | 0 | 2022-12-09 | 45
2023 | Region VI | NEGROS OCCIDENTAL | CITY OF KABANKALAN (NEGROS OCCIDENTAL) | P00721743VS | Construction of Flood Mitigation Structure | 122.8396 | 9.9738 | 89262500 | 89262500 | 2023 | JAIME B. CHING ENTERPRISES | 6035 | 2023 | 2023-08-22 | 02/20/2023 | 0 | 0 | 2023-10-30 | 69
2022 | Region VI | NEGROS OCCIDENTAL | BAGO CITY (NEGROS OCCIDENTAL) | P00630211VS | Construction of Flood Mitigation Structure | 122.8402 | 10.5405 | 48999991.34 | 48656985.15 | 2022 | SILVER DRAGON CONSTRUCTION & LUMBER & GLASS SUPPLY INC. | 6036 | 2022 | 2022-11-02 | 03/31/2022 | 343006.19 | 0 | 2022-11-01 |  | 1
2022 | Region VI | NEGROS OCCIDENTAL | BAGO CITY (NEGROS OCCIDENTAL) | P00633223VS | Construction of Flood Mitigation Structure | 122.8417 | 10.544 | 48999991.7 | 48563891.77 | 2023 | SILVER DRAGON CONSTRUCTION & LUMBER & GLASS SUPPLY INC. | 6037 | 2022 | 2023-02-13 | 03/31/2022 | 436099.93 | 0 | 2023-02-12 |  | 1
2024 | Region VI | NEGROS OCCIDENTAL | CITY OF KABANKALAN (NEGROS OCCIDENTAL) | P00820290VS | Construction of Flood Mitigation Structure | 122.8427 | 9.9706 | 125450000 | 125450000 | 2024 | JAIME B. CHING ENTERPRISES | 6038 | 2024 | 2024-10-22 | 02/22/2024 | 0 | 0 | 2024-11-13 | 22
2023 | Region V | CAMARINES SUR | PASACAO (CAMARINES SUR) | P00726972LZ | Construction of Flood Mitigation Structure | 123.0099 | 13.5188 | 139925000 | 139925000 | 2024 | SUNWEST, INC. (FORMERLY: SUNWEST CONSTRUCTION & DEVELOPMENT CORPORATION) | 6039 | 2023 | 2024-02-21 | 04/17/2023 | 0 | 0 | 2024-04-12 | 51
2023 | Region V | CAMARINES SUR | GAINZA (CAMARINES SUR) | P00742205LZ | Construction of Flood Mitigation Structure | 123.1306 | 13.615 | 74250000 | 74250000 | 2023 | LEGACY CONSTRUCTION CORPORATION (FORMERLY: LEGACY CONSTRUCTION) | 6040 | 2023 | 2023-11-21 | 04/18/2023 | 0 | 0 | 2024-02-23 | 94
2023 | Region V | CAMARINES SUR | SIPOCOT (CAMARINES SUR) | P00740490LZ | Construction of Flood Mitigation Structure | 122.9053 | 13.8354 | 82024119.28 | 82024118.17 | 2023 | BICOL GOLDROCK CONSTRUCTION CORPORATION | 6041 | 2023 | 2023-12-05 | 04/19/2023 | 1.11 | 0 | 2023-12-05 | 0
2022 | Region VII | CEBU | MALABUYOC (CEBU) | P00633012VS | Construction of Flood Mitigation Structure | 123.3244 | 9.6317 | 48999955.8 | 48999955.8 | 2022 | QM BUILDERS | 6042 | 2022 | 2022-10-25 | 03/23/2022 | 0 | 0 | 2022-10-24 |  | 1
2024 | Region VI | NEGROS OCCIDENTAL | BINALBAGAN (NEGROS OCCIDENTAL) | P00820270VS | Construction of Slope Protection Structure | 122.8437 | 10.2114 | 88258900 | 88258900 | 2024 | LEGACY CONSTRUCTION CORPORATION (FORMERLY: LEGACY CONSTRUCTION) | 6043 | 2024 | 2024-10-22 | 02/14/2024 | 0 | 0 | 2024-12-03 | 42
2023 | Region VII | NEGROS ORIENTAL | SANTA CATALINA (NEGROS ORIENTAL) | P00721848VS | Construction of Flood Mitigation Structure | 122.845 | 9.3503 | 44100000 | 44100000 | 2023 | H.L.J CONSTRUCTION & ENTERPRISES | 6044 | 2023 | 2023-10-03 | 02/28/2023 | 0 | 0 | 2023-10-02 |  | 1
2022 | Region VI | NEGROS OCCIDENTAL | CITY OF HIMAMAYLAN (NEGROS OCCIDENTAL) | P00620305VS | Construction of Slope Protection Structure | 122.8474 | 10.0518 | 33775000 | 33774997.7 | 2022 | JAIME B. CHING ENTERPRISES | 6045 | 2022 | 2022-11-01 | 03/02/2022 | 2.3 | 0 | 2022-10-31 |  | 1
2022 | Region VI | NEGROS OCCIDENTAL | CITY OF HIMAMAYLAN (NEGROS OCCIDENTAL) | P00630644VS | Construction of Slope Protection Structure | 122.8476 | 10.0497 | 49000000 | 49000000 | 2022 | LEGACY CONSTRUCTION CORPORATION (FORMERLY: LEGACY CONSTRUCTION) | 6046 | 2022 | 2022-12-12 | 02/17/2022 | 0 | 0 | 2022-11-14 |  | 28
2023 | Region V | CAMARINES NORTE | SAN LORENZO RUIZ (IMELDA) (CAMARINES NORTE) | P00737375LZ | Construction of Flood Mitigation Structure | 122.8501 | 14.0141 | 6929992.33 | 6715990.86 | 2023 | 128 DRAGON CONSTRUCTION AND SUPPLIES | 6047 | 2023 | 2023-11-24 | 07/07/2023 | 214001.47 | 0 | 2023-11-23 |  | 1
2022 | Region V | CAMARINES NORTE | SAN LORENZO RUIZ (IMELDA) (CAMARINES NORTE) | P00620304LZ | Construction of Slope Protection Structure | 122.8504 | 14.0133 | 86849987.78 | 86849987.78 | 2023 | EUS CONSTRUCTION / 128 DRAGON CONSTRUCTION AND SUPPLIES | 6048 | 2022 | 2023-12-26 | 07/14/2022 | 0 | 0 | 2023-12-25 |  | 1
2022 | Region VI | ILOILO | BAROTAC VIEJO (ILOILO) | P00620005VS | Construction of Flood Mitigation Structure | 122.8509 | 11.023 | 96500000 | 96500000 | 2023 | WOODLAND CONSTRUCTION & SUPPLY, INC. / SUPREME ABF CONST. & CONST. SUPPLY COMPANY INC. | 6049 | 2022 | 2023-07-04 | 03/25/2022 | 0 | 0 | 2023-06-08 |  | 26
2024 | Region VI | ILOILO | BAROTAC VIEJO (ILOILO) | P00820166VS | Construction of Flood Mitigation Structure | 122.8514 | 11.0235 | 44100000 | 44100000 | 2025 | PANAY EAST COAST CONSTRUCTION & SUPPLY | 6050 | 2024 | 2025-03-10 | 01/30/2024 | 0 | 0 | 2025-03-09 |  | 1
2024 | Region VI | ILOILO | BAROTAC VIEJO (ILOILO) | P00820169VS | Construction of Flood Mitigation Structure | 122.8518 | 11.0231 | 29400000 | 29400000 | 2024 | SBF CONSTRUCTION & DEVELOPMENT CORPORATION | 6051 | 2024 | 2024-12-21 | 03/19/2024 | 0 | 0 | 2024-12-20 |  | 1
2022 | Region VI | ILOILO | BAROTAC VIEJO (ILOILO) | P00620004VS | Construction of Flood Mitigation Structure | 122.8519 | 11.023 | 96500000 | 96500000 | 2023 | MRZA CONSTRUCTION CORPORATION / ROPRIM CONSTRUCTION CORPORATION (FORMERLY ROPRIM CONSTRUCTION) | 6052 | 2022 | 2023-10-09 | 03/25/2022 | 0 | 0 | 2023-10-20 | 11
2021 | Region VI | ILOILO |  | P00521539VS | Construction of Flood Mitigation Structure | 122.8522 | 11.0277 | 77200000 | 77200000 | 2022 | F. GURREA CONSTRUCTION, INCORPORATED | 6053 | 2021 | 2022-09-28 | 05/24/2021 | 0 | 0 | 2022-04-30 |  | 151
2023 | Region VI | NEGROS OCCIDENTAL | SAN ENRIQUE (NEGROS OCCIDENTAL) | P00721935VS | Construction of Flood Mitigation Structure | 122.8522 | 10.4094 | 29399998.33 | 29047198.6 | 2023 | SILVER DRAGON CONSTRUCTION & LUMBER & GLASS SUPPLY INC. | 6054 | 2023 | 2023-11-15 | 04/11/2023 | 352799.73 | 0 | 2023-11-14 |  | 1
2023 | Region VI | ILOILO | BAROTAC VIEJO (ILOILO) | P00721467VS | Construction of Flood Mitigation Structure | 122.8532 | 11.0216 | 86464000 | 86464000 | 2024 | F. GURREA CONSTRUCTION, INCORPORATED | 6055 | 2023 | 2024-05-20 | 02/17/2023 | 0 | 0 | 2024-05-19 |  | 1
2024 | Region VI | ILOILO | BAROTAC VIEJO (ILOILO) | P00820167VS | Construction of Flood Mitigation Structure | 122.8538 | 11.0216 | 44100000 | 44100000 | 2024 | TOPMOST DEVELOPMENT & MKTG. CORP. | 6056 | 2024 | 2024-11-10 | 01/30/2024 | 0 | 0 | 2024-11-09 |  | 1
2024 | Region V | CAMARINES NORTE | PARACALE (CAMARINES NORTE) | P00839668LZ | Construction of Drainage Structure | 122.8549 | 14.2352 | 4949995.1 | 4949995.1 | 2024 | JAEJR ELECTRICAL, CONSTRUCTION & SUPPLY | 6057 | 2024 | 2024-09-16 | 04/05/2024 | 0 | 0 | 2024-09-15 |  | 1
2023 | Region V | CAMARINES NORTE | LABO (CAMARINES NORTE) | P00736149LZ | Construction of Flood Mitigation Structure | 122.8566 | 14.167 | 57899576.25 | 57332639.72 | 2024 | EUS CONSTRUCTION | 6058 | 2023 | 2024-05-12 | 05/03/2023 | 566936.53 | 0 | 2024-05-11 |  | 1
2023 | Region VI | ILOILO | BAROTAC VIEJO (ILOILO) | P00721468VS | Construction of Flood Mitigation Structure | 122.857 | 11.0209 | 86464000 | 86464000 | 2024 | F. GURREA CONSTRUCTION, INCORPORATED | 6059 | 2023 | 2024-05-20 | 02/17/2023 | 0 | 0 | 2024-05-19 |  | 1
2022 | Region V | CAMARINES NORTE | LABO (CAMARINES NORTE) | P00631395LZ | Construction of Flood Mitigation Structure | 122.8577 | 14.1674 | 34299914.41 | 33271379.32 | 2023 | BRENTMIN ROOFING ENTERPRISE | 6060 | 2022 | 2023-01-08 | 03/23/2022 | 1028535.09 | 0 | 2023-01-07 |  | 1
2024 | Region IX | ZAMBOANGA DEL NORTE | SALUG (ZAMBOANGA DEL NORTE) | P00820391MN | Construction of Flood Mitigation Structure | 122.8579 | 8.1396 | 44100000 | 44100000 | 2024 | LONG ISLAND BUILDERS & CONSTRUCTION | 6061 | 2024 | 2024-08-12 | 02/07/2024 | 0 | 0 | 2024-12-10 | 120
2022 | Region VI | NEGROS OCCIDENTAL | SAN ENRIQUE (NEGROS OCCIDENTAL) | P00620109VS | Construction of Flood Mitigation Structure | 122.8589 | 10.4025 | 48999996.56 | 48960615.25 | 2023 | A.C. RIVERO DEVELOPMENT CORPORATION | 6062 | 2022 | 2023-01-02 | 02/10/2022 | 39381.31 | 0 | 2022-10-07 |  | 87
2024 | Region IX | ZAMBOANGA DEL NORTE | LEON T. POSTIGO (ZAMBOANGA DEL NORTE) | P00820004MN | Construction of Flood Mitigation Structure | 122.8596 | 8.1406 | 96500000 | 96500000 | 2025 | F.A. TORRES CONSTRUCTION / R.B. MORALLO CONSTRUCTION | 6063 | 2024 | 2025-01-22 | 03/24/2024 | 0 | 0 | 2025-02-17 | 26
2022 | Region VI | ILOILO | BAROTAC VIEJO (ILOILO) | P00633217VS | Construction of Flood Mitigation Structure | 122.8631 | 11.0249 | 49500000 | 49500000 | 2023 | 1 BEATUS BUILDERS CORP. / A.D. PENDON CONSTRUCTION & SUPPLY, INC. (FORMERLY: ADP CONSTRUCTION & SUPPLY) | 6064 | 2022 | 2023-04-17 | 03/24/2022 | 0 | 0 | 2022-11-29 |  | 139
2024 | Region VI | NEGROS OCCIDENTAL | PONTEVEDRA (NEGROS OCCIDENTAL) | P00820309VS | Construction of Flood Mitigation Structure | 122.8633 | 10.3753 | 96499998.56 | 96400918.4 | 2025 | R.A. CONSTRUCTION DEVELOPMENT CORPORATION (FORMERLY: R.A. CONSTRUCTION & GENERAL MERCHANDISE) / ONE TERRA BUILDERS AND CONSTRUCTION SUPPLY | 6065 | 2024 | 2025-02-23 | 03/11/2024 | 99080.16 | 0 | 2025-02-22 |  | 1
2022 | Region VI | NEGROS OCCIDENTAL | PONTEVEDRA (NEGROS OCCIDENTAL) | P00620110VS | Construction of Flood Mitigation Structure | 122.8652 | 10.3775 | 48999995.34 | 48925761.61 | 2022 | JAIME B. CHING ENTERPRISES | 6066 | 2022 | 2022-10-08 | 02/10/2022 | 74233.73 | 0 | 2022-10-07 |  | 1
2022 | Region VI | NEGROS OCCIDENTAL | VALLADOLID (NEGROS OCCIDENTAL) | P00633219VS | Construction of Slope Protection Structure | 122.866 | 10.4435 | 48999990.8 | 48784339.51 | 2022 | SILVER DRAGON CONSTRUCTION & LUMBER & GLASS SUPPLY INC. | 6067 | 2022 | 2022-09-27 | 03/31/2022 | 215651.29 | 0 | 2022-09-26 |  | 1
2023 | Region VI | NEGROS OCCIDENTAL | PULUPANDAN (NEGROS OCCIDENTAL) | P00733692VS | Construction of Flood Mitigation Structure | 122.8664 | 10.4433 | 98999990.35 | 98999701.5 | 2024 | FOUR SG ENTERPRISES / WILKINSON CONSTRUCTION | 6068 | 2023 | 2024-04-19 | 04/26/2023 | 288.85 | 0 | 2024-04-18 |  | 1
2022 | Region V | CAMARINES NORTE | LABO (CAMARINES NORTE) | P00620318LZ | Construction of Flood Mitigation Structure | 122.8665 | 14.1751 | 133128651.8 | 133128606.1 | 2023 | HGG BUILDERS & SUPPLY | 6069 | 2022 | 2023-06-01 | 03/24/2022 | 45.7 | 0 | 2023-05-31 |  | 1
2023 | Region V | CAMARINES NORTE | LABO (CAMARINES NORTE) | P00736151LZ | Construction of Flood Mitigation Structure | 122.8671 | 14.1788 | 57899410.67 | 57279912.51 | 2024 | EUS CONSTRUCTION | 6070 | 2023 | 2024-05-01 | 05/03/2023 | 619498.16 | 0 | 2024-04-30 |  | 1
2024 | Region V | CAMARINES SUR | LUPI (CAMARINES SUR) | P00823605LZ | Construction of Flood Mitigation Structure | 122.8675 | 13.7715 | 96499676.3 | 96494270.23 | 2024 | RAPIDWORKZ CONSTRUCTION & SUPPLY / STEVEN CONSTRUCTION & SUPPLY | 6071 | 2024 | 2024-06-04 | 03/25/2024 | 5406.07 | 0 | 2025-03-16 | 285
2024 | Region V | CAMARINES SUR | LUPI (CAMARINES SUR) | P00823621LZ | Construction of Flood Mitigation Structure | 122.8675 | 13.7717 | 96499359.27 | 94386023.3 | 2024 | G.C.I. CONSTRUCTION AND DEV'T. CORP. | 6072 | 2024 | 2024-09-18 | 03/27/2024 | 2113335.97 | 0 | 2025-03-18 | 181
2024 | Region V | CAMARINES SUR | LUPI (CAMARINES SUR) | P00823604LZ | Construction of Flood Mitigation Structure | 122.8675 | 13.7712 | 96499370.81 | 96494439.77 | 2024 | RAPIDWORKZ CONSTRUCTION & SUPPLY / STEVEN CONSTRUCTION & SUPPLY | 6073 | 2024 | 2024-06-04 | 03/25/2024 | 4931.04 | 0 | 2025-03-16 | 285
2022 | Region V | CAMARINES SUR | LIBMANAN (CAMARINES SUR) | P00620713LZ | Construction of Dike | 122.8681 | 13.6023 | 49000000 | 47972884 | 2022 | CPR CONSTRUCTION AND SUPPLY, INC. (FORMERLY: CPR CONSTRUCTION AND SUPPLY) / 417 LP CONSTRUCTION CORPORATION | 6074 | 2022 | 2022-09-16 | 02/24/2022 | 1027116 | 0 | 2022-09-15 |  | 1
2024 | Region V | CAMARINES SUR | LUPI (CAMARINES SUR) | P00823620LZ | Construction of Flood Mitigation Structure | 122.8683 | 13.7712 | 96499767.64 | 94450662 | 2024 | BICOL GOLDROCK CONSTRUCTION CORPORATION | 6075 | 2024 | 2024-08-14 | 03/27/2024 | 2049105.64 | 0 | 2025-03-18 | 216
2023 | Region V | CAMARINES NORTE | SAN VICENTE (CAMARINES NORTE) | P00737374LZ | Construction of Flood Mitigation Structure | 122.8698 | 14.1062 | 6929998.18 | 6708694.75 | 2023 | 128 DRAGON CONSTRUCTION AND SUPPLIES | 6076 | 2023 | 2023-09-25 | 07/07/2023 | 221303.43 | 0 | 2023-09-24 |  | 1
2023 | Region VII | NEGROS ORIENTAL | SANTA CATALINA (NEGROS ORIENTAL) | P00721690VS | Rehabilitation / Major Repair of Flood Control Structure | 122.87 | 9.3236 | 5314540 | 5314540 | 2023 | MIGHTY HOK SUMMIT CONSTRUCTION & DEVELOPMENT CORP. | 6077 | 2023 | 2023-06-02 | 02/15/2023 | 0 | 0 | 2023-06-01 |  | 1
2022 | Region V | CAMARINES NORTE | VINZONS (CAMARINES NORTE) | P00631406LZ | Construction of Flood Mitigation Structure | 122.8704 | 14.199 | 42139800.68 | 40876698.39 | 2022 | BRENTMIN ROOFING ENTERPRISE | 6078 | 2022 | 2022-11-23 | 03/23/2022 | 1263102.29 | 0 | 2022-11-22 |  | 1
2022 | Region VII | NEGROS ORIENTAL | SANTA CATALINA (NEGROS ORIENTAL) | P00633022VS | Construction of Flood Mitigation Structure | 122.8711 | 9.3267 | 49000000 | 49000000 | 2022 | PHILSOUTH BUILDERS INC (FORMERLY:PHILSOUTH BUILDERS) | 6079 | 2022 | 2022-11-01 | 04/07/2022 | 0 | 0 | 2022-10-31 |  | 1
2023 | Region VII | NEGROS ORIENTAL | SANTA CATALINA (NEGROS ORIENTAL) | P00721689VS | Rehabilitation / Major Repair of Flood Control Structure | 122.8711 | 9.3228 | 9069900 | 9069900 | 2023 | MIGHTY HOK SUMMIT CONSTRUCTION & DEVELOPMENT CORP. | 6080 | 2023 | 2023-07-14 | 02/15/2023 | 0 | 0 | 2023-07-13 |  | 1
2023 | Region V | CAMARINES NORTE | SAN VICENTE (CAMARINES NORTE) | P00736153LZ | Construction of Drainage Structure | 122.8714 | 14.1062 | 28949922 | 27996855.81 | 2024 | INFINITUM FORTUNE | 6081 | 2023 | 2024-04-16 | 09/22/2023 | 953066.19 | 0 | 2024-04-15 |  | 1
2022 | Region V | CAMARINES SUR | LIBMANAN (CAMARINES SUR) | P00620714LZ | Construction of Dike | 122.8725 | 13.5984 | 49000000 | 47914650 | 2022 | BICOL GOLDROCK CONSTRUCTION CORPORATION | 6082 | 2022 | 2022-09-20 | 02/28/2022 | 1085350 | 0 | 2022-09-19 |  | 1
2022 | Region VII | NEGROS ORIENTAL | SANTA CATALINA (NEGROS ORIENTAL) | P00620320VS | Rehabilitation / Major Repair of Flood Control Structure | 122.8731 | 9.3281 | 47804400 | 47804400 | 2022 | PHILSOUTH BUILDERS INC (FORMERLY:PHILSOUTH BUILDERS) | 6083 | 2022 | 2022-10-13 | 03/07/2022 | 0 | 0 | 2022-10-12 |  | 1
2022 | Region IX | ZAMBOANGA SIBUGAY | SIAY (ZAMBOANGA SIBUGAY) | P00620204MN | Construction of Flood Mitigation Structure | 122.8741 | 7.6573 | 76932940 | 76103499.33 | 2023 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R | 6084 | 2022 | 2023-07-13 | 02/23/2022 | 829440.67 | 0 | 2023-03-09 |  | 126
2022 | Region VI | NEGROS OCCIDENTAL | BAGO CITY (NEGROS OCCIDENTAL) | P00630210VS | Construction of Flood Mitigation Structure | 122.8786 | 10.5614 | 48999995.25 | 48568433.55 | 2022 | SILVER DRAGON CONSTRUCTION & LUMBER & GLASS SUPPLY INC. | 6085 | 2022 | 2022-12-07 | 02/10/2022 | 431561.7 | 0 | 2022-12-06 |  | 1
2022 | Region VI | NEGROS OCCIDENTAL | BAGO CITY (NEGROS OCCIDENTAL) | P00633221VS | Construction of Slope Protection Structure | 122.8789 | 10.5614 | 48999999.32 | 48794199.32 | 2022 | SILVER DRAGON CONSTRUCTION & LUMBER & GLASS SUPPLY INC. | 6086 | 2022 | 2022-12-20 | 03/31/2022 | 205800 | 0 | 2023-01-24 | 35
2022 | Region VI | NEGROS OCCIDENTAL | SAN ENRIQUE (NEGROS OCCIDENTAL) | P00633220VS | Construction of Slope Protection Structure | 122.8792 | 10.415 | 48999991.5 | 48642285.17 | 2022 | SILVER DRAGON CONSTRUCTION & LUMBER & GLASS SUPPLY INC. | 6087 | 2022 | 2022-12-19 | 03/31/2022 | 357706.33 | 0 | 2022-11-19 |  | 30
2023 | Region VI | NEGROS OCCIDENTAL | BINALBAGAN (NEGROS OCCIDENTAL) | P00721502VS | Construction of Slope Protection Structure | 122.8801 | 10.2091 | 79130000 | 79130000 | 2024 | KENNETH CONSTRUCTION AND GENERAL MERCHANDISE | 6088 | 2023 | 2024-02-23 | 02/15/2023 | 0 | 0 | 2024-03-04 | 10
2022 | Region VI | NEGROS OCCIDENTAL | BINALBAGAN (NEGROS OCCIDENTAL) | P00620108VS | Construction of Slope Protection Structure | 122.8826 | 10.2102 | 49000000 | 49000000 | 2022 | LEGACY CONSTRUCTION CORPORATION (FORMERLY: LEGACY CONSTRUCTION) | 6089 | 2022 | 2022-12-13 | 02/14/2022 | 0 | 0 | 2022-12-12 |  | 1
2023 | Region VI | NEGROS OCCIDENTAL | ISABELA (NEGROS OCCIDENTAL) | P00721870VS | Construction of Slope Protection Structure | 122.8829 | 10.2102 | 79130000 | 79130000 | 2023 | JAIME B. CHING ENTERPRISES | 6090 | 2023 | 2023-09-22 | 03/20/2023 | 0 | 0 | 2023-11-01 | 40
2022 | Region VI | NEGROS OCCIDENTAL | BINALBAGAN (NEGROS OCCIDENTAL) | P00630642VS | Construction of Drainage Structure | 122.8829 | 10.2092 | 9900000 | 9899983.1 | 2022 | LEGACY CONSTRUCTION CORPORATION (FORMERLY: LEGACY CONSTRUCTION) | 6091 | 2022 | 2022-09-13 | 03/28/2022 | 16.9 | 0 | 2022-09-12 |  | 1
2022 | Region V | CAMARINES SUR | PASACAO (CAMARINES SUR) | P00620715LZ | Construction of Dike | 122.8829 | 13.5887 | 49000000 | 48020996 | 2022 | NFH CONSTRUCTION & SUPPLY | 6092 | 2022 | 2022-09-20 | 02/28/2022 | 979004 | 0 | 2022-09-19 |  | 1
2022 | Region VII | NEGROS ORIENTAL | SANTA CATALINA (NEGROS ORIENTAL) | P00620316VS | Rehabilitation / Major Repair of Flood Control Structure | 122.8831 | 9.2244 | 33310200 | 33310200 | 2022 | LEGACY CONSTRUCTION CORPORATION (FORMERLY: LEGACY CONSTRUCTION) | 6093 | 2022 | 2022-12-13 | 03/08/2022 | 0 | 0 | 2022-12-12 |  | 1
2021 | Region VI | NEGROS OCCIDENTAL |  | P00549970VS | Construction of Slope Protection Structure | 122.884 | 10.2112 | 98000000 | 96499989.34 | 2022 | LEGACY CONSTRUCTION CORPORATION (FORMERLY: LEGACY CONSTRUCTION) / KWIKBUILT DEVELOPMENT CORPORATION | 6094 | 2021 | 2022-07-14 | 10/20/2021 | 1500010.66 | 0 | 2022-07-13 |  | 1
2022 | Region V | CAMARINES NORTE | SAN VICENTE (CAMARINES NORTE) | P00631412LZ | Construction of Flood Mitigation Structure | 122.8843 | 14.1119 | 42139998.47 | 42139953.11 | 2022 | BRENTMIN ROOFING ENTERPRISE | 6095 | 2022 | 2022-11-24 | 03/24/2022 | 45.36 | 0 | 2022-11-23 |  | 1
2022 | Region VII | NEGROS ORIENTAL | SANTA CATALINA (NEGROS ORIENTAL) | P00620315VS | Rehabilitation / Major Repair of Flood Control Structure | 122.8844 | 9.2222 | 45927700 | 45927700 | 2022 | LEGACY CONSTRUCTION CORPORATION (FORMERLY: LEGACY CONSTRUCTION) | 6096 | 2022 | 2022-12-27 | 02/17/2022 | 0 | 0 | 2022-12-26 |  | 1
2023 | Region VII | NEGROS ORIENTAL | SANTA CATALINA (NEGROS ORIENTAL) | P00721849VS | Construction of Flood Mitigation Structure | 122.885 | 9.225 | 44100000 | 44100000 | 2023 | HOMEWORLD CONSTRUCTION CORP. (FORMERLY HOMEWORLD E | 6097 | 2023 | 2023-12-27 | 02/28/2023 | 0 | 0 | 2023-11-06 |  | 51
2023 | Region VI | NEGROS OCCIDENTAL | BINALBAGAN (NEGROS OCCIDENTAL) | P00733694VS | Construction of Slope Protection Structure | 122.8856 | 10.2104 | 99000000 | 99000000 | 2023 | LEGACY CONSTRUCTION CORPORATION (FORMERLY: LEGACY CONSTRUCTION) | 6098 | 2023 | 2023-12-18 | 04/12/2023 | 0 | 0 | 2023-12-17 |  | 1
2023 | Region VI | NEGROS OCCIDENTAL | HINIGARAN (NEGROS OCCIDENTAL) | P00733693VS | Construction of Slope Protection Structure | 122.8866 | 10.2104 | 99000000 | 98993348.2 | 2023 | LEGACY CONSTRUCTION CORPORATION (FORMERLY: LEGACY CONSTRUCTION) | 6099 | 2023 | 2023-12-13 | 04/12/2023 | 6651.8 | 0 | 2023-12-12 |  | 1
2022 | Region V | CAMARINES NORTE | SAN LORENZO RUIZ (IMELDA) (CAMARINES NORTE) | P00631401LZ | Construction of Flood Mitigation Structure | 122.8926 | 14.0593 | 42139690.8 | 40884642.31 | 2022 | 128 DRAGON CONSTRUCTION AND SUPPLIES | 6100 | 2022 | 2022-11-21 | 03/21/2022 | 1255048.49 | 0 | 2022-11-20 |  | 1
2022 | Region V | CAMARINES NORTE | SAN LORENZO RUIZ (IMELDA) (CAMARINES NORTE) | P00640467LZ | Construction of Flood Mitigation Structure | 122.8953 | 14.0628 | 98999782.58 | 98999782.58 | 2023 | EUS CONSTRUCTION | 6101 | 2022 | 2023-04-30 | 03/31/2022 | 0 | 0 | 2023-04-29 |  | 1
2022 | Region VII | NEGROS ORIENTAL | SANTA CATALINA (NEGROS ORIENTAL) | P00632034VS | Construction of Flood Mitigation Structure | 122.8989 | 9.1844 | 49000000 | 49500000 | 2023 | PHILSOUTH BUILDERS INC (FORMERLY:PHILSOUTH BUILDERS) | 6102 | 2022 | 2023-01-09 | 04/07/2022 | 0 | 500000 | 2023-01-08 |  | 1
2022 | Region V | CAMARINES NORTE | VINZONS (CAMARINES NORTE) | P00631405LZ | Construction of Flood Mitigation Structure | 122.9028 | 14.1776 | 42139949.97 | 40876171.84 | 2023 | 128 DRAGON CONSTRUCTION AND SUPPLIES | 6103 | 2022 | 2023-03-26 | 03/21/2022 | 1263778.13 | 0 | 2023-03-25 |  | 1
2023 | Region V | CAMARINES NORTE | VINZONS (CAMARINES NORTE) | P00737373LZ | Construction of Flood Mitigation Structure | 122.903 | 14.1751 | 6929996.82 | 6721290.85 | 2023 | 128 DRAGON CONSTRUCTION AND SUPPLIES | 6104 | 2023 | 2023-08-18 | 07/07/2023 | 208705.97 | 0 | 2023-09-19 | 32
2022 | Region V | CAMARINES NORTE | TALISAY (CAMARINES NORTE) | P00632953LZ | Construction of Flood Mitigation Structure | 122.9034 | 14.1287 | 4949304.31 | 4800384.14 | 2022 | 888RV CONSTRUCTION AND SUPPLIES | 6105 | 2022 | 2022-07-25 | 03/21/2022 | 148920.17 | 0 | 2022-07-24 |  | 1
2023 | Region V | CAMARINES NORTE | TALISAY (CAMARINES NORTE) | P00737376LZ | Construction of Flood Mitigation Structure | 122.9036 | 14.1289 | 6929991.41 | 6929991.41 | 2023 | 128 DRAGON CONSTRUCTION AND SUPPLIES | 6106 | 2023 | 2023-09-20 | 07/07/2023 | 0 | 0 | 2023-09-19 |  | 1
2022 | Region V | CAMARINES NORTE | SAN LORENZO RUIZ (IMELDA) (CAMARINES NORTE) | P00640466LZ | Construction of Flood Mitigation Structure | 122.9042 | 13.9415 | 98999968.07 | 98999876.01 | 2022 | EUS CONSTRUCTION / BRENTMIN ROOFING ENTERPRISE | 6107 | 2022 | 2022-08-12 | 03/25/2022 | 92.06 | 0 | 2022-12-24 | 134
2024 | Region IX | ZAMBOANGA SIBUGAY | IPIL (CAPITAL) (ZAMBOANGA SIBUGAY) | P00820243MN | Construction of Flood Mitigation Structure | 122.9543 | 7.7225 | 67550000 | 58599948.87 | 2024 | LONG ISLAND BUILDERS & CONSTRUCTION | 6108 | 2024 | 2024-09-30 | 04/11/2024 | 8950051.13 | 0 | 2024-12-28 | 89
2023 | Region VI | ILOILO | MINA (ILOILO) | P00721932VS | Construction of Flood Mitigation Structure | 122.4357 | 10.9792 | 19600000 | 18619962.5 | 2023 | J.C. ALBASON BUILDERS AND SUPPLY | 6109 | 2023 | 2023-09-20 | 03/06/2023 | 980037.5 | 0 | 2023-08-28 |  | 23
2022 | Region VII | CEBU | MALABUYOC (CEBU) | P00633011VS | Construction of Flood Mitigation Structure | 123.3246 | 9.662 | 48999992.92 | 48999992.92 | 2022 | QM BUILDERS | 6110 | 2022 | 2022-10-25 | 03/23/2022 | 0 | 0 | 2022-10-24 |  | 1
2022 | Region VII | NEGROS ORIENTAL | SANTA CATALINA (NEGROS ORIENTAL) | P00633019VS | Construction of Flood Mitigation Structure | 122.9053 | 9.1672 | 49000000 | 49000000 | 2023 | PHILSOUTH BUILDERS INC (FORMERLY:PHILSOUTH BUILDERS) | 6111 | 2022 | 2023-03-08 | 04/07/2022 | 0 | 0 | 2023-03-07 |  | 1
2022 | Region VII | NEGROS ORIENTAL | CITY OF TANJAY (NEGROS ORIENTAL) | P00642545VS | Rehabilitation / Major Repair of Flood Control Structure | 123.1321 | 9.5074 | 14475000 | 14475000 | 2022 | R.E. SINGSON CONSTRUCTION AND DEVELOPMENT INC. (FORMERLY: R.E. SINGSON CONSTRUCTION) | 6112 | 2022 | 2022-07-22 | 03/24/2022 | 0 | 0 | 2022-07-21 |  | 1
2024 | Region VI | AKLAN | NEW WASHINGTON (AKLAN) | P00821039VS | Rehabilitation / Major Repair of Flood Control Structure | 122.4377 | 11.6481 | 29400000 | 29399990.42 | 2024 | GREENLAND BUILDERS | 6113 | 2024 | 2024-10-10 | 04/05/2024 | 9.58 | 0 | 2024-12-27 | 78
2023 | Region VI | NEGROS OCCIDENTAL | ISABELA (NEGROS OCCIDENTAL) | P00733231VS | Construction of Slope Protection Structure | 123.0101 | 10.2451 | 96500000 | 96500000 | 2024 | LEGACY CONSTRUCTION CORPORATION (FORMERLY: LEGACY CONSTRUCTION) | 6114 | 2023 | 2024-02-11 | 04/12/2023 | 0 | 0 | 2024-02-10 |  | 1
2022 | Region V | CAMARINES NORTE | BASUD (CAMARINES NORTE) | P00630995LZ | Rehabilitation / Major Repair of Flood Control Structure | 122.955 | 14.0559 | 50179228.24 | 50158065.88 | 2022 | ED1SON DEVELOPMENT & CONSTRUCTION INC. / ARIK CONSTRUCTION | 6115 | 2022 | 2022-10-05 | 03/22/2022 | 21162.36 | 0 | 2022-10-04 |  | 1
2023 | Region VII | CEBU | MALABUYOC (CEBU) | P00721521VS | Construction of Revetment | 123.3248 | 9.6509 | 96305224.08 | 96304510.15 | 2023 | SANTECH BUILDERS CORPORATION / GICAR CONSTRUCTION, INC. | 6116 | 2023 | 2023-11-17 | 02/08/2023 | 713.93 | 0 | 2023-12-18 | 31
2022 | Region VI | ILOILO | GUIMBAL (ILOILO) | P00632996VS | Construction of Flood Mitigation Structure | 122.3063 | 10.7322 | 9800000 | 9784658.85 | 2023 | GOOD FORTUNE INTERNATIONAL, INC. | 6117 | 2022 | 2023-02-05 | 05/23/2022 | 15341.15 | 0 | 2022-11-02 |  | 95
2024 | Region VII | NEGROS ORIENTAL | MANJUYOD (NEGROS ORIENTAL) | P00820863VS | Construction of Flood Mitigation Structure | 123.1327 | 9.6742 | 57900000 | 57900000 | 2024 | HOMEWORLD CONSTRUCTION CORP. (FORMERLY HOMEWORLD E | 6118 | 2024 | 2024-12-11 | 03/07/2024 | 0 | 0 | 2024-12-12 | 1
2024 | Region V | CAMARINES SUR | CANAMAN (CAMARINES SUR) | P00839669LZ | Construction of Flood Mitigation Structure | 123.1359 | 13.6205 | 4949941.58 | 4897900 | 2024 | MEGA-ANT BUILDERS AND CONSTRUCTION SUPPLIES | 6119 | 2024 | 2024-04-18 | 02/22/2024 | 52041.58 | 0 | 2024-05-16 | 28
2023 | Region VII | NEGROS ORIENTAL | BINDOY (PAYABON) (NEGROS ORIENTAL) | P00721951VS | Construction of Flood Mitigation Structure | 123.136 | 9.7829 | 29400000 | 29400000 | 2023 | RCODE BUILDERS AND AGGREGATES SUPPLY | 6120 | 2023 | 2023-12-27 | 03/07/2023 | 0 | 0 | 2023-12-30 | 3
2022 | Region VII | NEGROS ORIENTAL | MANJUYOD (NEGROS ORIENTAL) | P00620141VS | Construction of Flood Mitigation Structure | 123.1385 | 9.673 | 29400000 | 29400000 | 2023 | JAIME B. CHING ENTERPRISES | 6121 | 2022 | 2023-07-09 | 02/08/2022 | 0 | 0 | 2022-10-19 |  | 263
2022 | Region V | CAMARINES SUR | CAMALIGAN (CAMARINES SUR) | P00620724LZ | Construction of Flood Mitigation Structure | 123.1393 | 13.6197 | 43419755.29 | 43419755.29 | 2022 | CENTERWAYS CONSTRUCTION AND DEVELOPMENT INC. | 6122 | 2022 | 2022-10-05 | 03/24/2022 | 0 | 0 | 2022-10-04 |  | 1
2022 | Region VII | NEGROS ORIENTAL | AYUNGON (NEGROS ORIENTAL) | P00642566VS | Rehabilitation / Major Repair of Flood Control Structure | 123.1397 | 9.8503 | 2845757.02 | 2845757.02 | 2022 | GRAM CONSTRUCTION AND SUPPLY | 6123 | 2022 | 2022-07-23 | 06/06/2022 | 0 | 0 | 2022-07-22 |  | 1
2024 | Region VII | NEGROS ORIENTAL | BINDOY (PAYABON) (NEGROS ORIENTAL) | P00820205VS | Construction of Flood Mitigation Structure | 123.1408 | 9.7798 | 18963000 | 18800000 | 2024 | RCODE BUILDERS AND AGGREGATES SUPPLY | 6124 | 2024 | 2024-10-13 | 02/07/2024 | 163000 | 0 | 2024-09-06 |  | 37
2023 | Region V | CAMARINES SUR | LUPI (CAMARINES SUR) | P00736095LZ | Construction of Flood Mitigation Structure | 122.9054 | 13.8354 | 82024836.59 | 82024753.5 | 2023 | BICOL GOLDROCK CONSTRUCTION CORPORATION | 6125 | 2023 | 2023-11-17 | 03/31/2023 | 83.09 | 0 | 2023-11-16 |  | 1
2022 | Region VI | CAPIZ | DUMALAG (CAPIZ) | P00620299VS | Construction of Flood Mitigation Structure | 122.6017 | 11.2816 | 42627866.39 | 42627858 | 2023 | IBC INTERNATIONAL BUILDERS CORPORATION | 6126 | 2022 | 2023-11-28 | 02/15/2022 | 8.39 | 0 | 2023-11-27 |  | 1
2023 | Region V | CAMARINES SUR | GAINZA (CAMARINES SUR) | P00727324LZ | Construction of Flood Mitigation Structure | 123.1411 | 13.6189 | 72375000 | 72375000 | 2024 | BICOL GOLDROCK CONSTRUCTION CORPORATION | 6127 | 2023 | 2024-02-08 | 04/05/2023 | 0 | 0 | 2024-02-10 | 2
2022 | Region VII | NEGROS ORIENTAL | BINDOY (PAYABON) (NEGROS ORIENTAL) | P00620021VS | Construction of Flood Mitigation Structure | 123.1426 | 9.7504 | 72375000 | 72375000 | 2022 | ST. TIMOTHY CONSTRUCTION CORPORATION / ELITE GENERAL CONTRACTOR AND DEVELOPMENT CORP. | 6128 | 2022 | 2022-08-11 | 02/24/2022 | 0 | 0 | 2022-12-24 | 135
2024 | Region VII | NEGROS ORIENTAL | BINDOY (PAYABON) (NEGROS ORIENTAL) | P00820198VS | Construction of Flood Mitigation Structure | 123.1427 | 9.7663 | 30506420 | 30506420 | 2024 | MOLROW CONSTRUCTION & SUPPLY | 6129 | 2024 | 2024-12-12 | 03/07/2024 | 0 | 0 | 2024-12-13 | 1
2022 | Region V | CAMARINES SUR | NAGA CITY (CAMARINES SUR) | P00621523LZ | Construction of Flood Mitigation Structure | 123.2409 | 13.6201 | 77081758.13 | 76604250.86 | 2022 | PHILWORKS CONSTRUCTION & SUPPLY | 6130 | 2022 | 2022-10-12 | 04/04/2022 | 477507.27 | 0 | 2022-10-17 | 5
2022 | Region VII | NEGROS ORIENTAL | MANJUYOD (NEGROS ORIENTAL) | P00642565VS | Rehabilitation / Major Repair of Flood Control Structure | 123.1431 | 9.6719 | 39907110.08 | 39907110.08 | 2023 | LEGACY CONSTRUCTION CORPORATION (FORMERLY: LEGACY CONSTRUCTION) / MIGHTY HOK SUMMIT CONSTRUCTION & DEVELOPMENT CORP. | 6131 | 2022 | 2023-01-20 | 06/06/2022 | 0 | 0 | 2023-01-19 |  | 1
2023 | Region VII | NEGROS ORIENTAL | MANJUYOD (NEGROS ORIENTAL) | P00721789VS | Construction of Flood Mitigation Structure | 123.1435 | 9.6728 | 72375000 | 72375000 | 2023 | LEGACY CONSTRUCTION CORPORATION (FORMERLY: LEGACY CONSTRUCTION) / MIGHTY HOK SUMMIT CONSTRUCTION & DEVELOPMENT CORP. | 6132 | 2023 | 2023-12-27 | 02/07/2023 | 0 | 0 | 2024-02-08 | 43
2024 | Region V | CAMARINES SUR | CALABANGA (CAMARINES SUR) | P00820475LZ | Construction of Flood Mitigation Structure | 123.1436 | 13.7158 | 96499807.55 | 96344723.24 | 2024 | CENTERWAYS CONSTRUCTION AND DEVELOPMENT INC. | 6133 | 2024 | 2024-10-11 | 04/08/2024 | 155084.31 | 0 | 2024-12-05 | 55
2023 | Region V | CAMARINES SUR | CANAMAN (CAMARINES SUR) | P00727220LZ | Construction of Flood Mitigation Structure | 123.144 | 13.664 | 48999916.73 | 48463992 | 2023 | STEVEN CONSTRUCTION & SUPPLY | 6134 | 2023 | 2023-12-07 | 06/01/2023 | 535924.73 | 0 | 2024-01-27 | 51
2024 | Region VII | NEGROS ORIENTAL | BINDOY (PAYABON) (NEGROS ORIENTAL) | P00820204VS | Construction of Flood Mitigation Structure | 123.1456 | 9.7614 | 19600000 | 19450000 | 2024 | MAI CONSTRUCTION & SUPPLY | 6135 | 2024 | 2024-07-15 | 02/07/2024 | 150000 | 0 | 2024-08-07 | 23
2023 | Region V | CAMARINES SUR | GAINZA (CAMARINES SUR) | P00742203LZ | Construction of Flood Mitigation Structure | 123.147 | 13.6192 | 74250000 | 74250000 | 2023 | LEGACY CONSTRUCTION CORPORATION (FORMERLY: LEGACY CONSTRUCTION) | 6136 | 2023 | 2023-11-24 | 04/04/2023 | 0 | 0 | 2024-02-09 | 77
2023 | Region VII | NEGROS ORIENTAL | BINDOY (PAYABON) (NEGROS ORIENTAL) | P00721788VS | Construction of Flood Mitigation Structure | 123.15 | 9.7503 | 72375000 | 72375000 | 2024 | JAIME B. CHING ENTERPRISES | 6137 | 2023 | 2024-07-21 | 02/07/2023 | 0 | 0 | 2024-01-27 |  | 176
2024 | Region VII | NEGROS ORIENTAL | CITY OF TANJAY (NEGROS ORIENTAL) | P00821059VS | Construction of Flood Mitigation Structure | 123.1501 | 9.5148 | 39200000 | 39200000 | 2024 | QM BUILDERS | 6138 | 2024 | 2024-12-09 | 05/29/2024 | 0 | 0 | 2024-12-08 |  | 1
2022 | Region V | CAMARINES SUR | GAINZA (CAMARINES SUR) | P00620701LZ | Construction of Dike | 123.1526 | 13.6173 | 49000000 | 48024323 | 2022 | BICOL GOLDROCK CONSTRUCTION CORPORATION | 6139 | 2022 | 2022-09-14 | 02/22/2022 | 975677 | 0 | 2022-09-13 |  | 1
2022 | Region VI | ILOILO | ESTANCIA (ILOILO) | P00642581VS | Construction of Flood Mitigation Structure | 123.1528 | 11.4444 | 19300000 | 19300000 | 2023 | PANAY EAST COAST CONSTRUCTION & SUPPLY | 6140 | 2022 | 2023-04-07 | 05/25/2022 | 0 | 0 | 2023-01-23 |  | 74
2022 | Region VII | NEGROS ORIENTAL | LA LIBERTAD (NEGROS ORIENTAL) | P00620143VS | Construction of Flood Mitigation Structure | 123.1532 | 10.0769 | 19600000 | 19600000 | 2022 | KOUKEN CONSTRUCTION | 6141 | 2022 | 2022-09-25 | 02/08/2022 | 0 | 0 | 2022-09-22 |  | 3
2022 | Region VII | NEGROS ORIENTAL | BINDOY (PAYABON) (NEGROS ORIENTAL) | P00642551VS | Rehabilitation / Major Repair of Flood Control Structure | 123.1567 | 9.7219 | 3930850.34 | 3930850.34 | 2022 | MAI CONSTRUCTION & SUPPLY | 6142 | 2022 | 2022-08-11 | 06/06/2022 | 0 | 0 | 2022-08-10 |  | 1
2022 | Region V | CAMARINES SUR | MILAOR (CAMARINES SUR) | P00620706LZ | Construction of Dike | 123.157 | 13.5854 | 49000000 | 47539836 | 2022 | HI-TONE CONSTRUCTION & DEVELOPMENT CORP. (FORMERLY | 6143 | 2022 | 2022-09-20 | 02/28/2022 | 1460164 | 0 | 2022-09-19 |  | 1
2023 | Region V | CAMARINES SUR | MILAOR (CAMARINES SUR) | P00726630LZ | Construction of Flood Mitigation Structure | 123.1608 | 13.5799 | 144268222.8 | 144268222.8 | 2024 | G.C.I. CONSTRUCTION AND DEV'T. CORP. | 6144 | 2023 | 2024-03-29 | 05/04/2023 | 0 | 0 | 2024-05-02 | 34
2023 | Region V | CAMARINES SUR | CAMALIGAN (CAMARINES SUR) | P00726610LZ | Rehabilitation / Major Repair of Flood Control Structure | 123.1625 | 13.6194 | 67520249.96 | 66753754.22 | 2023 | STEVEN CONSTRUCTION & SUPPLY | 6145 | 2023 | 2023-09-15 | 04/11/2023 | 766495.74 | 0 | 2023-11-18 | 64
2023 | Region IX | ZAMBOANGA DEL NORTE | PRES. MANUEL A. ROXAS (ZAMBOANGA DEL NORTE) | P00732479MN | Construction of Flood Mitigation Structure | 123.1625 | 8.4738 | 4950000 | 4900000.27 | 2024 | D' DREAMER DEVELOPMENT CORPORATION | 6146 | 2023 | 2024-01-29 | 02/14/2023 | 49999.73 | 0 | 2023-04-08 |  | 296
2023 | Region VII | NEGROS ORIENTAL | CITY OF TANJAY (NEGROS ORIENTAL) | P00731624VS | Construction of Flood Mitigation Structure | 123.1647 | 9.5294 | 96500000 | 96500000 | 2024 | D.K. JOCSON CONSTRUCTION | 6147 | 2023 | 2024-03-17 | 02/23/2023 | 0 | 0 | 2024-03-16 |  | 1
2023 | Region V | CAMARINES SUR | GAINZA (CAMARINES SUR) | P00742204LZ | Construction of Flood Mitigation Structure | 123.1651 | 13.6186 | 74250000 | 74250000 | 2023 | LEGACY CONSTRUCTION CORPORATION (FORMERLY: LEGACY CONSTRUCTION) | 6148 | 2023 | 2023-10-13 | 04/04/2023 | 0 | 0 | 2024-02-09 | 119
2023 | Region V | CAMARINES SUR | MILAOR (CAMARINES SUR) | P00740458LZ | Construction of Flood Mitigation Structure | 123.1673 | 13.5759 | 120625000 | 120625000 | 2024 | BICOL GOLDROCK CONSTRUCTION CORPORATION | 6149 | 2023 | 2024-04-12 | 04/17/2023 | 0 | 0 | 2024-04-11 |  | 1
2023 | Region VII | NEGROS ORIENTAL | TAYASAN (NEGROS ORIENTAL) | P00721791VS | Construction of Flood Mitigation Structure | 123.1675 | 9.9214 | 72375000 | 72375000 | 2024 | JAIME B. CHING ENTERPRISES | 6150 | 2023 | 2024-08-25 | 02/07/2023 | 0 | 0 | 2024-06-01 |  | 85
2024 | Region IX | ZAMBOANGA DEL SUR | KUMALARANG (ZAMBOANGA DEL SUR) | P00820396MN | Construction of Flood Mitigation Structure | 123.1681 | 7.7462 | 19600000 | 19579552.34 | 2025 | JZL BUILDERS & ENTERPRISES | 6151 | 2024 | 2025-02-24 | 04/22/2024 | 20447.66 | 0 | 2024-10-20 |  | 127
2023 | Region V | CAMARINES SUR | MILAOR (CAMARINES SUR) | P00740459LZ | Construction of Flood Mitigation Structure | 123.169 | 13.5743 | 120625000 | 120625000 | 2024 | G.C.I. CONSTRUCTION AND DEV'T. CORP. | 6152 | 2023 | 2024-02-22 | 04/17/2023 | 0 | 0 | 2024-04-11 | 49
2022 | Region V | CAMARINES SUR | MAGARAO (CAMARINES SUR) | P00621550LZ | Construction of Flood Mitigation Structure | 123.1723 | 13.6601 | 48112067.46 | 48099080.59 | 2022 | PRECIOUS CONSTRUCTION | 6153 | 2022 | 2022-12-05 | 04/01/2022 | 12986.87 | 0 | 2022-12-16 | 11
2022 | Region VII | NEGROS ORIENTAL | TAYASAN (NEGROS ORIENTAL) | P00632032VS | Construction of Dike | 123.1731 | 9.9214 | 4950000 | 4950000 | 2022 | SAGITTARIUS CONSTRUCTION | 6154 | 2022 | 2022-09-13 | 03/30/2022 | 0 | 0 | 2022-09-12 |  | 1
2021 | Region V | CAMARINES SUR |  | P00561427LZ | Construction of Slope Protection Structure | 123.1737 | 13.66 | 3959979.66 | 3959871.7 | 2022 | MRBAY CONSTRUCTION | 6155 | 2021 | 2022-11-29 | 04/05/2022 | 107.96 | 0 | 2022-09-09 |  | 81
2024 | Region VI | NEGROS OCCIDENTAL | SILAY CITY (NEGROS OCCIDENTAL) | P00832635VS | Construction of Flood Mitigation Structure | 123.1739 | 10.6975 | 4949994.85 | 4949999.85 | 2024 | SL & G CONSTRUCTION | 6156 | 2024 | 2024-05-07 | 02/14/2024 | 0 | 5 | 2024-05-06 |  | 1
2023 | Region V | CAMARINES SUR | MINALABAC (CAMARINES SUR) | P00736100LZ | Construction of Flood Mitigation Structure | 123.1743 | 13.5697 | 96500000 | 96500000 | 2023 | BICOL GOLDROCK CONSTRUCTION CORPORATION | 6157 | 2023 | 2023-12-15 | 02/17/2023 | 0 | 0 | 2024-01-19 | 35
2023 | Region V | CAMARINES SUR | MINALABAC (CAMARINES SUR) | P00740456LZ | Construction of Flood Mitigation Structure | 123.1743 | 13.5697 | 120625000 | 120625000 | 2024 | G.C.I. CONSTRUCTION AND DEV'T. CORP. | 6158 | 2023 | 2024-01-31 | 04/05/2023 | 0 | 0 | 2024-03-30 | 59
2024 | Region VII | NEGROS ORIENTAL | CITY OF GUIHULNGAN (NEGROS ORIENTAL) | P00832657VS | Construction of Flood Mitigation Structure | 123.175 | 10.1218 | 4950000 | 4935000 | 2024 | GRAM CONSTRUCTION AND SUPPLY | 6159 | 2024 | 2024-06-25 | 02/07/2024 | 15000 | 0 | 2024-06-24 |  | 1
2023 | Region V | CAMARINES SUR | MINALABAC (CAMARINES SUR) | P00740457LZ | Construction of Flood Mitigation Structure | 123.1762 | 13.5675 | 120625000 | 120625000 | 2023 | BICOL GOLDROCK CONSTRUCTION CORPORATION | 6160 | 2023 | 2023-10-17 | 04/05/2023 | 0 | 0 | 2024-03-30 | 165
2023 | Region V | CAMARINES SUR | MINALABAC (CAMARINES SUR) | P00736099LZ | Construction of Flood Mitigation Structure | 123.1776 | 13.5663 | 96500000 | 96447416.6 | 2023 | NFH CONSTRUCTION & SUPPLY | 6161 | 2023 | 2023-10-17 | 02/17/2023 | 52583.4 | 0 | 2024-01-19 | 94
2022 | Region VII | NEGROS ORIENTAL | CITY OF TANJAY (NEGROS ORIENTAL) | P00620049VS | Construction of Flood Mitigation Structure | 123.1779 | 9.5071 | 67550000 | 67550000 | 2022 | QM BUILDERS | 6162 | 2022 | 2022-11-09 | 02/18/2022 | 0 | 0 | 2022-11-08 |  | 1
2022 | Region IX | ZAMBOANGA DEL SUR | KUMALARANG (ZAMBOANGA DEL SUR) | P00620010MN | Construction of Flood Mitigation Structure | 123.1786 | 7.7835 | 96900000 | 82330663.39 | 2023 | ESR CONSTRUCTION AND DEVELOPMENT CORPORATION (FORMERLY: ESR CONSTRUCTION & SUPPLIES) | 6163 | 2022 | 2023-07-31 | 03/10/2022 | 14569336.61 | 0 | 2023-07-30 |  | 1
2022 | Region IX | ZAMBOANGA DEL SUR | KUMALARANG (ZAMBOANGA DEL SUR) | P00620210MN | Construction of Flood Mitigation Structure | 123.1786 | 7.7835 | 68008114.32 | 47185394.21 | 2023 | ESR CONSTRUCTION AND DEVELOPMENT CORPORATION (FORMERLY: ESR CONSTRUCTION & SUPPLIES) | 6164 | 2022 | 2023-05-15 | 03/10/2022 | 20822720.11 | 0 | 2023-05-14 |  | 1
2022 | Region V | CAMARINES SUR | MINALABAC (CAMARINES SUR) | P00620707LZ | Construction of Dike | 123.1795 | 13.5646 | 49000000 | 48024732 | 2022 | G.C.I. CONSTRUCTION AND DEV'T. CORP. | 6165 | 2022 | 2022-09-14 | 02/22/2022 | 975268 | 0 | 2022-09-13 |  | 1
2024 | Region V | CAMARINES SUR | NAGA CITY (CAMARINES SUR) | P00846119LZ | Construction of Flood Mitigation Structure | 123.1816 | 13.6137 | 4949958.96 | 4889903.22 | 2024 | BENJOSH CONSTRUCTION SUPPLY | 6166 | 2024 | 2024-10-19 | 06/03/2024 | 60055.74 | 0 | 2024-10-18 |  | 1
2024 | Region VII | NEGROS ORIENTAL | ZAMBOANGUITA (NEGROS ORIENTAL) | P00820213VS | Construction of Flood Mitigation Structure | 123.1834 | 9.1626 | 20778940 | 20778940 | 2024 | NRS BUILDERS AND SUPPLIES | 6167 | 2024 | 2024-10-15 | 04/11/2024 | 0 | 0 | 2024-10-14 |  | 1
2022 | Region IX | ZAMBOANGA DEL NORTE | MANUKAN (ZAMBOANGA DEL NORTE) | P00620112MN | Construction of Flood Mitigation Structure | 123.1844 | 8.5237 | 39808090 | 39408043.22 | 2024 | MONTAÃ‘O CONSTRUCTION & DEVELOPMENT CORPORATION | 6168 | 2022 | 2024-09-30 | 03/31/2022 | 400046.78 | 0 | 2022-10-28 |  | 703
2023 | Region V | CAMARINES SUR | MILAOR (CAMARINES SUR) | P00727323LZ | Construction of Flood Mitigation Structure | 123.1848 | 13.6004 | 72375000 | 72375000 | 2023 | G.C.I. CONSTRUCTION AND DEV'T. CORP. | 6169 | 2023 | 2023-12-15 | 04/17/2023 | 0 | 0 | 2024-02-22 | 69
2023 | Region V | CAMARINES SUR | MILAOR (CAMARINES SUR) | P00737563LZ | Rehabilitation / Major Repair of Flood Control Structure | 123.1853 | 13.5909 | 7425000 | 7425000 | 2024 | SHLA CONSTRUCTION AND SUPPLY | 6170 | 2023 | 2024-02-13 | 10/17/2023 | 0 | 0 | 2024-02-12 |  | 1
2022 | Region V | CAMARINES SUR | MILAOR (CAMARINES SUR) | P00620716LZ | Construction of Revetment | 123.1855 | 13.5801 | 49000000 | 48015300.91 | 2022 | KCS CONSTRUCTION & SUPPLY | 6171 | 2022 | 2022-09-14 | 02/22/2022 | 984699.09 | 0 | 2022-09-13 |  | 1
2023 | Region V | CAMARINES SUR | NAGA CITY (CAMARINES SUR) | P00726609LZ | Rehabilitation / Major Repair of Flood Control Structure | 123.1857 | 13.6106 | 57899890.26 | 57204819.77 | 2023 | STEVEN CONSTRUCTION & SUPPLY | 6172 | 2023 | 2023-12-15 | 04/11/2023 | 695070.49 | 0 | 2023-12-14 |  | 1
2022 | Region V | CAMARINES SUR | NAGA CITY (CAMARINES SUR) | P00621548LZ | Construction of Flood Mitigation Structure | 123.1857 | 13.6132 | 39052317.69 | 39052245.17 | 2022 | CPR CONSTRUCTION AND SUPPLY, INC. (FORMERLY: CPR CONSTRUCTION AND SUPPLY) / 417 LP CONSTRUCTION CORPORATION | 6173 | 2022 | 2022-11-11 | 04/06/2022 | 72.52 | 0 | 2022-11-10 |  | 1
2024 | Region VII | NEGROS ORIENTAL | CANLAON CITY (NEGROS ORIENTAL) | P00820196VS | Construction of Flood Mitigation Structure | 123.1858 | 10.3726 | 2940000 | 2913716.97 | 2024 | REKINA CONSTRUCTION SERVICES | 6174 | 2024 | 2024-11-07 | 03/07/2024 | 26283.03 | 0 | 2024-11-06 |  | 1
2023 | Region VII | NEGROS ORIENTAL | ZAMBOANGUITA (NEGROS ORIENTAL) | P00721955VS | Construction of Drainage Structure | 123.1861 | 9.0964 | 19600000 | 19600000 | 2023 | MG CONSTRUCTION | 6175 | 2023 | 2023-10-07 | 04/05/2023 | 0 | 0 | 2023-10-06 |  | 1
2021 | Region V | CAMARINES SUR |  | P00561420LZ | Construction of Drainage Structure | 123.1879 | 13.6636 | 1569126.32 | 1489100 | 2022 | LAHDETH CONSTRUCTION AND SUPPLY | 6176 | 2021 | 2022-07-01 | 04/05/2022 | 80026.32 | 0 | 2022-06-30 |  | 1
2022 | Region V | CAMARINES SUR | MILAOR (CAMARINES SUR) | P00631001LZ | Rehabilitation / Major Repair of Flood Control Structure | 123.1879 | 13.5799 | 72375000 | 70926749 | 2022 | G.C.I. CONSTRUCTION AND DEV'T. CORP. | 6177 | 2022 | 2022-09-15 | 03/16/2022 | 1448251 | 0 | 2022-11-26 | 72
2024 | Region VII | NEGROS ORIENTAL | ZAMBOANGUITA (NEGROS ORIENTAL) | P00820214VS | Construction of Flood Mitigation Structure | 123.1902 | 9.0979 | 45080000 | 45080000 | 2024 | ELITE GENERAL CONTRACTOR AND DEVELOPMENT CORP. | 6178 | 2024 | 2024-08-12 | 02/20/2024 | 0 | 0 | 2024-10-02 | 51
2022 | Region V | MASBATE | BALUD (MASBATE) | P00620737LZ | Construction of Flood Mitigation Structure | 123.191 | 12.0375 | 24499994.04 | 24500000 | 2022 | LEGACY BSCA CONSTRUCTION AND SUPPLY CORP. | 6179 | 2022 | 2022-07-23 | 02/11/2022 | 0 | 5.96 | 2022-07-22 |  | 1
2022 | Region V | CAMARINES SUR | MINALABAC (CAMARINES SUR) | P00620705LZ | Construction of Dike | 123.1913 | 13.5304 | 49000000 | 48019191 | 2022 | BICOL GOLDROCK CONSTRUCTION CORPORATION | 6180 | 2022 | 2022-09-14 | 02/22/2022 | 980809 | 0 | 2022-09-13 |  | 1
2023 | Region V | CAMARINES SUR | CALABANGA (CAMARINES SUR) | P00737567LZ | Construction of Flood Mitigation Structure | 123.192 | 13.6984 | 4949988.14 | 4899993 | 2023 | MEGA-ANT BUILDERS AND CONSTRUCTION SUPPLIES | 6181 | 2023 | 2023-04-15 | 02/17/2023 | 49995.14 | 0 | 2023-05-01 | 16
2023 | Region VII | NEGROS ORIENTAL | JIMALALUD (NEGROS ORIENTAL) | P00721839VS | Construction of Flood Mitigation Structure | 123.1928 | 9.9711 | 39200000 | 39200000 | 2023 | KOUKEN CONSTRUCTION | 6182 | 2023 | 2023-10-29 | 02/07/2023 | 0 | 0 | 2023-10-28 |  | 1
2022 | Region V | CAMARINES SUR | CALABANGA (CAMARINES SUR) | P00640580LZ | Construction of Flood Mitigation Structure | 123.1931 | 13.6985 | 4949919.99 | 4499725.15 | 2022 | 417 LP CONSTRUCTION CORPORATION | 6183 | 2022 | 2022-09-16 | 04/01/2022 | 450194.84 | 0 | 2022-09-15 |  | 1
2024 | Region V | CAMARINES SUR | CALABANGA (CAMARINES SUR) | P00839670LZ | Construction of Flood Mitigation Structure | 123.1937 | 13.6985 | 4949926.97 | 4896762.41 | 2024 | MEGA-ANT BUILDERS AND CONSTRUCTION SUPPLIES | 6184 | 2024 | 2024-04-15 | 02/22/2024 | 53164.56 | 0 | 2024-05-16 | 31
2022 | Region V | CAMARINES SUR | MINALABAC (CAMARINES SUR) | P00620700LZ | Construction of Dike | 123.1939 | 13.5345 | 49000000 | 48020707.46 | 2022 | HI-TONE CONSTRUCTION & DEVELOPMENT CORP. (FORMERLY | 6185 | 2022 | 2022-09-20 | 02/28/2022 | 979292.54 | 0 | 2022-09-19 |  | 1
2023 | Region V | CAMARINES SUR | MINALABAC (CAMARINES SUR) | P00736098LZ | Construction of Dike | 123.1939 | 13.5598 | 96500000 | 96500000 | 2023 | G.C.I. CONSTRUCTION AND DEV'T. CORP. | 6186 | 2023 | 2023-10-17 | 02/17/2023 | 0 | 0 | 2024-01-19 | 94
2023 | Region V | CAMARINES SUR | MINALABAC (CAMARINES SUR) | P00727322LZ | Construction of Flood Mitigation Structure | 123.194 | 13.5387 | 72375000 | 72227938.37 | 2023 | G.C.I. CONSTRUCTION AND DEV'T. CORP. | 6187 | 2023 | 2023-10-17 | 04/05/2023 | 147061.63 | 0 | 2024-02-10 | 116
2022 | Region V | CAMARINES SUR | MINALABAC (CAMARINES SUR) | P00620702LZ | Construction of Dike | 123.1943 | 13.562 | 49000000 | 47976248.09 | 2022 | HI-TONE CONSTRUCTION & DEVELOPMENT CORP. (FORMERLY | 6188 | 2022 | 2022-09-30 | 03/14/2022 | 1023751.91 | 0 | 2022-10-03 | 3
2024 | Region V | CAMARINES SUR | MINALABAC (CAMARINES SUR) | P00821377LZ | Construction of Flood Mitigation Structure | 123.1947 | 13.5586 | 133170000 | 133169700 | 2024 | G.C.I. CONSTRUCTION AND DEV'T. CORP. | 6189 | 2024 | 2024-10-25 | 02/20/2024 | 300 | 0 | 2025-02-16 | 114
2023 | Region V | CAMARINES SUR | MINALABAC (CAMARINES SUR) | P00727383LZ | Construction of Flood Mitigation Structure | 123.1949 | 13.5611 | 49000000 | 48965337.45 | 2023 | C.T. LEONCIO CONSTRUCTION & TRADING | 6190 | 2023 | 2023-12-18 | 04/05/2023 | 34662.55 | 0 | 2024-01-12 | 25
2023 | Region V | CAMARINES SUR | MINALABAC (CAMARINES SUR) | P00736096LZ | Construction of Dike | 123.195 | 13.5372 | 96500000 | 96500000 | 2024 | HI-TONE CONSTRUCTION & DEVELOPMENT CORP. (FORMERLY | 6191 | 2023 | 2024-02-01 | 03/01/2023 | 0 | 0 | 2024-01-31 |  | 1
2023 | Region V | CAMARINES SUR | CALABANGA (CAMARINES SUR) | P00737566LZ | Construction of Flood Mitigation Structure | 123.1973 | 13.6989 | 4949997.19 | 4900002 | 2023 | MEGA-ANT BUILDERS AND CONSTRUCTION SUPPLIES | 6192 | 2023 | 2023-04-15 | 02/17/2023 | 49995.19 | 0 | 2023-05-01 | 16
2023 | Region V | CAMARINES SUR | MINALABAC (CAMARINES SUR) | P00737564LZ | Rehabilitation / Major Repair of Flood Control Structure | 123.1973 | 13.556 | 49500000 | 49464968 | 2023 | NFH CONSTRUCTION & SUPPLY | 6193 | 2023 | 2023-10-17 | 02/08/2023 | 35032 | 0 | 2023-12-08 | 52
2021 | Region V | CAMARINES SUR |  | P00561424LZ | Construction of Slope Protection Structure | 123.1985 | 13.6991 | 2969481.12 | 2941315.96 | 2022 | J-NAC CONSTRUCTION & SUPPLY | 6194 | 2021 | 2022-08-17 | 04/06/2022 | 28165.16 | 0 | 2022-08-16 |  | 1
2023 | Region VII | NEGROS ORIENTAL | AMLAN (AYUQUITAN) (NEGROS ORIENTAL) | P00721953VS | Rehabilitation / Major Repair of Flood Control Structure | 123.1988 | 9.4709 | 49000000 | 49000000 | 2024 | PHILSOUTH BUILDERS INC (FORMERLY:PHILSOUTH BUILDERS) | 6195 | 2023 | 2024-01-21 | 04/11/2023 | 0 | 0 | 2024-01-20 |  | 1
2023 | Region VII | NEGROS ORIENTAL | LA LIBERTAD (NEGROS ORIENTAL) | P00721905VS | Construction of Flood Mitigation Structure | 123.1992 | 10.0339 | 67550000 | 67550000 | 2023 | JAIME B. CHING ENTERPRISES | 6196 | 2023 | 2023-12-27 | 03/24/2023 | 0 | 0 | 2024-01-22 | 26
2024 | Region V | MASBATE | BALUD (MASBATE) | P00820483LZ | Construction of Flood Mitigation Structure | 123.1993 | 11.9399 | 62724959.88 | 62724959.88 | 2024 | HKP CONSTRUCTION AND SUPPLY / A3 CONSTRUCTION & SUPPLY | 6197 | 2024 | 2024-12-17 | 05/13/2024 | 0 | 0 | 2025-01-17 | 31
2022 | Region VII | NEGROS ORIENTAL | LA LIBERTAD (NEGROS ORIENTAL) | P00620136VS | Construction of Flood Mitigation Structure | 123.1997 | 10.034 | 49000000 | 49000000 | 2022 | JAIME B. CHING ENTERPRISES | 6198 | 2022 | 2022-11-05 | 02/08/2022 | 0 | 0 | 2022-11-04 |  | 1
2022 | Region VI | NEGROS OCCIDENTAL | CADIZ CITY (NEGROS OCCIDENTAL) | P00620304VS | Construction of Flood Mitigation Structure | 123.2003 | 10.9567 | 39091219.17 | 39089218.29 | 2022 | R.A.G. CORONA CONSTRUCTION AND AGGREGATES SUPPLY | 6199 | 2022 | 2022-12-18 | 03/30/2022 | 2000.88 | 0 | 2022-12-17 |  | 1
2024 | Region VI | NEGROS OCCIDENTAL | CADIZ CITY (NEGROS OCCIDENTAL) | P00820007VS | Construction of Flood Mitigation Structure | 123.2008 | 10.9564 | 57899987.32 | 57896911.64 | 2024 | R.A.G. CORONA CONSTRUCTION AND AGGREGATES SUPPLY | 6200 | 2024 | 2024-10-24 | 03/13/2024 | 3075.68 | 0 | 2024-10-23 |  | 1
2022 | Region VI | NEGROS OCCIDENTAL | CADIZ CITY (NEGROS OCCIDENTAL) | P00620303VS | Construction of Flood Mitigation Structure | 123.2008 | 10.9564 | 38111218.31 | 38109219 | 2022 | R.A.G. CORONA CONSTRUCTION AND AGGREGATES SUPPLY | 6201 | 2022 | 2022-12-11 | 03/30/2022 | 1999.31 | 0 | 2022-12-10 |  | 1
2023 | Region V | CAMARINES SUR | MINALABAC (CAMARINES SUR) | P00726602LZ | Construction of Dike | 123.2014 | 13.5276 | 67550000 | 67550000 | 2023 | BICOL GOLDROCK CONSTRUCTION CORPORATION | 6202 | 2023 | 2023-10-05 | 02/22/2023 | 0 | 0 | 2023-12-19 | 75
2023 | Region V | CAMARINES SUR | MINALABAC (CAMARINES SUR) | P00737389LZ | Rehabilitation / Major Repair of Flood Control Structure | 123.2019 | 13.5202 | 69300000 | 69300000 | 2023 | NFH CONSTRUCTION & SUPPLY | 6203 | 2023 | 2023-10-19 | 02/22/2023 | 0 | 0 | 2023-10-18 |  | 1
2022 | Region V | CAMARINES SUR | NAGA CITY (CAMARINES SUR) | P00620292LZ | Construction of Flood Mitigation Structure | 123.2019 | 13.6353 | 52139326.92 | 52139326.92 | 2023 | CENTERWAYS CONSTRUCTION AND DEVELOPMENT INC. | 6204 | 2022 | 2023-02-14 | 04/08/2022 | 0 | 0 | 2023-02-13 |  | 1
2024 | Region V | CAMARINES SUR | NAGA CITY (CAMARINES SUR) | P00846121LZ | Construction of Flood Mitigation Structure | 123.2029 | 13.6175 | 4949938.61 | 4949423.05 | 2024 | AA PAHATI CONSTRUCTION AND SUPPLY | 6205 | 2024 | 2024-07-12 | 05/08/2024 | 515.56 | 0 | 2024-08-23 | 42
2022 | Region V | CAMARINES SUR | MINALABAC (CAMARINES SUR) | P00620703LZ | Construction of Dike | 123.2047 | 13.5026 | 49000000 | 48015655.63 | 2022 | G.C.I. CONSTRUCTION AND DEV'T. CORP. | 6206 | 2022 | 2022-09-14 | 02/22/2022 | 984344.37 | 0 | 2022-09-13 |  | 1
2022 | Region VII | NEGROS ORIENTAL | LA LIBERTAD (NEGROS ORIENTAL) | P00620139VS | Construction of Flood Mitigation Structure | 123.2079 | 10.0527 | 36241380 | 36241380 | 2022 | JAIME B. CHING ENTERPRISES | 6207 | 2022 | 2022-10-06 | 02/08/2022 | 0 | 0 | 2022-10-05 |  | 1
2023 | Region V | CAMARINES SUR | CALABANGA (CAMARINES SUR) | P00737565LZ | Construction of Flood Mitigation Structure | 123.2135 | 13.7078 | 4949196.27 | 4897585.84 | 2023 | MEGA-ANT BUILDERS AND CONSTRUCTION SUPPLIES | 6208 | 2023 | 2023-09-28 | 06/13/2023 | 51610.43 | 0 | 2023-09-29 | 1
2022 | Region V | CAMARINES SUR | CALABANGA (CAMARINES SUR) | P00621549LZ | Construction of Flood Mitigation Structure | 123.2147 | 13.7168 | 48891676.39 | 48888375.42 | 2022 | PEU CONSTRUCTION AND SUPPLY / STEVEN CONSTRUCTION & SUPPLY | 6209 | 2022 | 2022-10-27 | 04/04/2022 | 3300.97 | 0 | 2022-10-26 |  | 1
2022 | Region VII | NEGROS ORIENTAL | VALENCIA (LUZURRIAGA) (NEGROS ORIENTAL) | P00632036VS | Construction of Drainage Structure | 123.221 | 9.2734 | 4950000 | 4950000 | 2022 | MG CONSTRUCTION | 6210 | 2022 | 2022-12-09 | 04/19/2022 | 0 | 0 | 2022-12-08 |  | 1
2023 | Region V | CAMARINES SUR | NAGA CITY (CAMARINES SUR) | P00727221LZ | Construction of Flood Mitigation Structure | 123.2244 | 13.6479 | 48990141.48 | 48464895.49 | 2023 | PHILWORKS CONSTRUCTION & SUPPLY | 6211 | 2023 | 2023-12-19 | 05/08/2023 | 525245.99 | 0 | 2024-01-03 | 15
2022 | Region VII | NEGROS ORIENTAL | VALENCIA (LUZURRIAGA) (NEGROS ORIENTAL) | P00632035VS | Construction of Drainage Structure | 123.2289 | 9.2908 | 4950000 | 4950000 | 2023 | MG CONSTRUCTION | 6212 | 2022 | 2023-01-12 | 04/19/2022 | 0 | 0 | 2022-12-21 |  | 22
2022 | Region VII | NEGROS ORIENTAL | VALENCIA (LUZURRIAGA) (NEGROS ORIENTAL) | P00620314VS | Rehabilitation / Major Repair of Flood Control Structure | 123.2297 | 9.3142 | 37240000 | 37240000 | 2022 | LEGACY CONSTRUCTION CORPORATION (FORMERLY: LEGACY CONSTRUCTION) | 6213 | 2022 | 2022-11-04 | 03/08/2022 | 0 | 0 | 2022-12-30 | 56
2023 | Region V | CAMARINES SUR | BALATAN (CAMARINES SUR) | P00736106LZ | Construction of Flood Mitigation Structure | 123.2333 | 13.3219 | 96489164 | 96489125.4 | 2023 | HI-TONE CONSTRUCTION & DEVELOPMENT CORP. (FORMERLY | 6214 | 2023 | 2023-12-20 | 02/17/2023 | 38.6 | 0 | 2023-12-22 | 2
2024 | Region V | MASBATE | BALUD (MASBATE) | P00820484LZ | Construction of Flood Mitigation Structure | 123.2339 | 11.9642 | 62724959.24 | 62724959.24 | 2025 | NEXT GENERATION CONSTRUCTION AND SUPPLY CORPORATION / 3R3M CONSTRUCTION AND SUPPLY CORPORATION (FORMERLY: 3R3M CONSTRUCTION AND SUPPLY) | 6215 | 2024 | 2025-03-17 | 07/10/2024 | 0 | 0 | 2025-03-16 |  | 1
2023 | Region V | MASBATE | CLAVERIA (MASBATE) | P00726297LZ | Construction of Flood Mitigation Structure | 123.2378 | 12.8994 | 23520000 | 23516730.44 | 2023 | SISBRO CONSTRUCTION CORPORATION (FORMERLY: SISBRO CONSTRUCTION & SUPPLY) | 6216 | 2023 | 2023-07-15 | 04/09/2023 | 3269.56 | 0 | 2023-11-02 | 110
2024 | Region V | MASBATE | CLAVERIA (MASBATE) | P00820434LZ | Construction of Flood Mitigation Structure | 123.2381 | 12.8986 | 96500000 | 96490836.48 | 2024 | A3 CONSTRUCTION & SUPPLY / SJMC CONSTRUCTION SERVICES | 6217 | 2024 | 2024-11-28 | 03/19/2024 | 9163.52 | 0 | 2025-03-02 | 94
2023 | Region V | CAMARINES SUR | BALATAN (CAMARINES SUR) | P00736135LZ | Construction of Flood Mitigation Structure | 123.2382 | 13.3082 | 48221995 | 48221995 | 2023 | BICOL GOLDROCK CONSTRUCTION CORPORATION | 6218 | 2023 | 2023-08-18 | 03/20/2023 | 0 | 0 | 2023-10-12 | 55
2023 | Region IV-B | ROMBLON | MAGDIWANG (ROMBLON) | P00736058LZ | Construction of Flood Mitigation Structure | 122.4389 | 12.4633 | 95534999.99 | 95535000 | 2023 | SUNWEST, INC. (FORMERLY: SUNWEST CONSTRUCTION & DEVELOPMENT CORPORATION) | 6219 | 2023 | 2023-12-06 | 03/29/2023 | 0 | 0.01 | 2024-02-29 | 85
2023 | Region VII | CEBU | MALABUYOC (CEBU) | P00745601VS | Rehabilitation / Major Repair of Flood Control Structure | 123.3248 | 9.6479 | 87599650.26 | 87599384.57 | 2024 | QM BUILDERS | 6220 | 2023 | 2024-05-27 | 08/10/2023 | 265.69 | 0 | 2024-05-26 |  | 1
2022 | Region VI | NEGROS OCCIDENTAL | ENRIQUE B. MAGALONA (SARAVIA) (NEGROS OCCIDENTAL) | P00630179VS | Construction of Flood Mitigation Structure | 122.9559 | 10.8893 | 96499997.03 | 96497991.15 | 2023 | REDSON CONSTRUCTION AND SUPPLIES, INC. (FORMERLY: REDSON CONSTRUCTION AND SUPPLIES) / SUPREME ABF CONST. & CONST. SUPPLY COMPANY INC. | 6221 | 2022 | 2023-04-24 | 02/22/2022 | 2005.88 | 0 | 2023-04-23 |  | 1
2023 | Region VI | ILOILO | GUIMBAL (ILOILO) | P00731679VS | Construction of Flood Mitigation Structure | 122.3072 | 10.6811 | 49000000 | 48485507.81 | 2024 | PANAY EAST COAST CONSTRUCTION & SUPPLY | 6222 | 2023 | 2024-03-13 | 04/11/2023 | 514492.19 | 0 | 2024-01-12 |  | 61
2022 | Region V | CAMARINES SUR | BULA (CAMARINES SUR) | P00621125LZ | Construction of Flood Mitigation Structure | 123.2411 | 13.4686 | 39200000 | 39116647.55 | 2022 | ALRO CONSTRUCTION & DEVELOPMENT CORP. | 6223 | 2022 | 2022-11-25 | 02/22/2022 | 83352.45 | 0 | 2022-11-25 | 0
2023 | Region V | CAMARINES SUR | DEL GALLEGO (CAMARINES SUR) | P00740489LZ | Construction of Flood Mitigation Structure | 122.6036 | 13.9199 | 72374414.82 | 72374410.13 | 2023 | C.T. LEONCIO CONSTRUCTION & TRADING | 6224 | 2023 | 2023-12-12 | 04/19/2023 | 4.69 | 0 | 2023-12-11 |  | 1
2023 | Region VI | ILOILO | GUIMBAL (ILOILO) | P00721650VS | Construction of Flood Mitigation Structure | 122.3074 | 10.662 | 14700000 | 14667784.1 | 2023 | TOPMOST DEVELOPMENT & MKTG. CORP. | 6225 | 2023 | 2023-10-07 | 04/11/2023 | 32215.9 | 0 | 2023-09-21 |  | 16
2023 | Region V | CAMARINES SUR | LUPI (CAMARINES SUR) | P00726291LZ | Construction of Revetment | 122.9079 | 13.7904 | 48999621.56 | 48999620.59 | 2024 | NEWBIG FOUR J CONSTRUCTION INC., (FORMERLY FOUR J | 6226 | 2023 | 2024-02-06 | 05/18/2023 | 0.97 | 0 | 2024-02-05 |  | 1
2024 | Region VI | ILOILO | AJUY (ILOILO) | P00820170VS | Construction of Flood Mitigation Structure | 122.9576 | 11.0978 | 9800000 | 9702998.81 | 2024 | SBF CONSTRUCTION & DEVELOPMENT CORPORATION | 6227 | 2024 | 2024-08-09 | 04/08/2024 | 97001.19 | 0 | 2024-08-08 |  | 1
2023 | Region IV-A | QUEZON | GUINAYANGAN (QUEZON) | P00727171LZ | Construction of Drainage Structure | 122.4418 | 13.9111 | 9800000 | 9800000 | 2023 | DZEE BUILDERS AND CONSTRUCTION SUPPLY | 6228 | 2023 | 2023-09-04 | 03/09/2023 | 0 | 0 | 2023-09-03 |  | 1
2022 | Region V | CAMARINES SUR | BULA (CAMARINES SUR) | P00631429LZ | Construction of Flood Mitigation Structure | 123.2413 | 13.4725 | 49000000 | 48999963.93 | 2022 | RICHMAR CONSTRUCTION | 6229 | 2022 | 2022-08-30 | 02/22/2022 | 36.07 | 0 | 2022-09-08 | 9
2021 | Region V | ALBAY |  | P00561131LZ | Construction of Flood Mitigation Structure | 123.3261 | 13.1942 | 192999778.4 | 192072579.2 | 2022 | SUNWEST, INC. (FORMERLY: SUNWEST CONSTRUCTION & DEVELOPMENT CORPORATION) | 6230 | 2021 | 2022-12-15 | 12/16/2021 | 927199.2 | 0 | 2022-12-26 | 11
2023 | Region V | CAMARINES SUR | DEL GALLEGO (CAMARINES SUR) | P00740488LZ | Construction of Flood Mitigation Structure | 122.6042 | 13.9198 | 72374615.83 | 72374529.7 | 2023 | NFH CONSTRUCTION & SUPPLY / SHLA CONSTRUCTION AND SUPPLY | 6231 | 2023 | 2023-11-10 | 04/19/2023 | 86.13 | 0 | 2023-11-11 | 1
2023 | Region V | CAMARINES SUR | LUPI (CAMARINES SUR) | P00740483LZ | Construction of Flood Mitigation Structure | 122.908 | 13.8212 | 82024705.7 | 82024700.2 | 2023 | HONEYVILLECONST AND DEVELOPMENT CORPORATION | 6232 | 2023 | 2023-12-06 | 04/19/2023 | 5.5 | 0 | 2023-12-05 |  | 1
2023 | Region VI | AKLAN | NEW WASHINGTON (AKLAN) | P00721483VS | Rehabilitation / Major Repair of Flood Control Structure | 122.4434 | 11.6401 | 72375000 | 72374994.45 | 2024 | ST. TIMOTHY CONSTRUCTION CORPORATION / GREENLAND BUILDERS | 6233 | 2023 | 2024-05-20 | 04/13/2023 | 5.55 | 0 | 2024-05-01 |  | 19
2024 | Region VII | CEBU | MALABUYOC (CEBU) | P00834659VS | Construction of Flood Mitigation Structure | 123.3263 | 9.6766 | 39196117.95 | 39196051.67 | 2024 | GREEN WORLD CONSTRUCTION / MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY | 6234 | 2024 | 2024-05-27 | 02/26/2024 | 66.28 | 0 | 2024-09-12 | 108
2021 | Region VI | ILOILO |  | P00549999VS | Construction of Cutoff Channel | 122.3075 | 10.6836 | 19800000 | 19603507.77 | 2022 | GOLDEN ROADRUNNER INTERNATIONAL CORP. | 6235 | 2021 | 2022-08-15 | 01/06/2022 | 196492.23 | 0 | 2022-06-14 |  | 62
2024 | Region IX | ZAMBOANGA SIBUGAY | IPIL (CAPITAL) (ZAMBOANGA SIBUGAY) | P00820218MN | Construction of Flood Mitigation Structure | 122.6063 | 7.765 | 57900000 | 38685192 | 2024 | BARILLO CONSTRUCTION AND ENTERPRISES | 6236 | 2024 | 2024-11-18 | 03/21/2024 | 19214808 | 0 | 2024-11-19 | 1
2023 | Region V | CAMARINES SUR | LUPI (CAMARINES SUR) | P00740481LZ | Construction of Flood Mitigation Structure | 122.9081 | 13.8213 | 82024605.46 | 82024604.89 | 2023 | BICOL GOLDROCK CONSTRUCTION CORPORATION | 6237 | 2023 | 2023-11-30 | 04/19/2023 | 0.57 | 0 | 2023-12-05 | 5
2024 | Region IX | ZAMBOANGA DEL SUR | SAN MIGUEL (ZAMBOANGA DEL SUR) | P00820139MN | Construction of Flood Mitigation Structure | 123.2422 | 7.7233 | 49000000 | 48974384.57 | 2024 | NRMM CONSTRUCTION AND DEV'T CORP. | 6238 | 2024 | 2024-07-16 | 04/08/2024 | 25615.43 | 0 | 2024-11-16 | 123
2024 | Region IX | ZAMBOANGA SIBUGAY | IPIL (CAPITAL) (ZAMBOANGA SIBUGAY) | P00820226MN | Construction of Flood Mitigation Structure | 122.4471 | 7.6307 | 57900000 | 57892201.4 | 2024 | ST. MATTHEW GEN. CONTRACTOR & DEVELOPMENT CORP. | 6239 | 2024 | 2024-09-23 | 03/18/2024 | 7798.6 | 0 | 2024-11-16 | 54
2023 | Region VI | AKLAN | LIBACAO (AKLAN) | P00721990VS | Construction of Flood Mitigation Structure | 122.3079 | 11.4817 | 27440000 | 27419992.88 | 2023 | PATRILA BUILDERS, INC. | 6240 | 2023 | 2023-10-16 | 03/24/2023 | 20007.12 | 0 | 2023-11-24 | 39
2022 | Region V | CAMARINES SUR | TINAMBAC (CAMARINES SUR) | P00631427LZ | Rehabilitation / Major Repair of Flood Control Structure | 123.3264 | 13.8146 | 29400000 | 29400000 | 2023 | SHLA CONSTRUCTION AND SUPPLY | 6241 | 2022 | 2023-07-13 | 02/15/2022 | 0 | 0 | 2023-07-12 |  | 1
2024 | Region IX | ZAMBOANGA SIBUGAY | IPIL (CAPITAL) (ZAMBOANGA SIBUGAY) | P00820220MN | Construction of Flood Mitigation Structure | 122.6082 | 7.7669 | 57900000 | 38685192 | 2024 | BARILLO CONSTRUCTION AND ENTERPRISES | 6242 | 2024 | 2024-11-20 | 03/21/2024 | 19214808 | 0 | 2024-11-19 |  | 1
2024 | Region VII | CEBU | MALABUYOC (CEBU) | P00834668VS | Construction of Flood Mitigation Structure | 123.3279 | 9.6505 | 48996071.74 | 48995671.74 | 2024 | JA ACHACOSO ENTERPRISES & GENERAL SERVICES | 6243 | 2024 | 2024-08-12 | 03/18/2024 | 400 | 0 | 2024-10-21 | 70
2023 | Region VI | NEGROS OCCIDENTAL | BACOLOD CITY (CAPITAL) (NEGROS OCCIDENTAL) | P00721639VS | Construction of Drainage Structure | 122.9578 | 10.6735 | 19600000 | 19600000 | 2023 | BNYU DEVELOPMENT CORPORATION (FORMERLY:BNYU ENTERPRISES & CONSTRUCTION) | 6244 | 2023 | 2023-06-22 | 03/15/2023 | 0 | 0 | 2023-10-02 | 102
2022 | Region V | CAMARINES NORTE | DAET (CAPITAL) (CAMARINES NORTE) | P00621484LZ | Construction of Flood Mitigation Structure | 122.9088 | 14.0904 | 29399945.15 | 29399945.15 | 2022 | 888RV CONSTRUCTION AND SUPPLIES | 6245 | 2022 | 2022-10-18 | 03/31/2022 | 0 | 0 | 2022-10-17 |  | 1
2023 | Region V | CAMARINES SUR | BULA (CAMARINES SUR) | P00736116LZ | Construction of Flood Mitigation Structure | 123.2434 | 13.4719 | 96386222 | 96386086.27 | 2023 | WELEX CONSTRUCTION, INCORPORATED (FORMERLY WELEX C | 6246 | 2023 | 2023-08-25 | 02/17/2023 | 135.73 | 0 | 2023-12-07 | 104
2024 | Region VI | AKLAN | BANGA (AKLAN) | P00820300VS | Construction of Revetment | 122.3082 | 11.5792 | 28950000 | 28949980.16 | 2024 | G.F. ROVERO MERCHANDISING | 6247 | 2024 | 2024-07-19 | 02/06/2024 | 19.84 | 0 | 2024-07-28 | 9
2023 | Region VI | ILOILO | LEGANES (ILOILO) | P00733720VS | Construction of Flood Mitigation Structure | 122.6101 | 10.7919 | 96525000 | 96524109.64 | 2024 | IBC INTERNATIONAL BUILDERS CORPORATION | 6248 | 2023 | 2024-05-24 | 04/04/2023 | 890.36 | 0 | 2024-05-23 |  | 1
2023 | Region V | CAMARINES SUR | PASACAO (CAMARINES SUR) | P00726971LZ | Construction of Flood Mitigation Structure | 123.0117 | 13.5185 | 139925000 | 139925000 | 2024 | SUNWEST, INC. (FORMERLY: SUNWEST CONSTRUCTION & DEVELOPMENT CORPORATION) | 6249 | 2023 | 2024-02-21 | 04/17/2023 | 0 | 0 | 2024-04-12 | 51
2023 | Region V | CAMARINES SUR | NABUA (CAMARINES SUR) | P00736121LZ | Construction of Flood Mitigation Structure | 123.328 | 13.4028 | 96472910 | 96472842.95 | 2023 | STEVEN CONSTRUCTION & SUPPLY | 6250 | 2023 | 2023-09-15 | 02/17/2023 | 67.05 | 0 | 2023-12-07 | 83
2024 | Region IX | ZAMBOANGA SIBUGAY | IPIL (CAPITAL) (ZAMBOANGA SIBUGAY) | P00820225MN | Construction of Flood Mitigation Structure | 122.4496 | 7.6312 | 57900000 | 57749526.89 | 2024 | LAKEWOOD CONSTRUCTION COMPANY | 6251 | 2024 | 2024-11-11 | 03/12/2024 | 150473.11 | 0 | 2024-11-10 |  | 1
2021 | Region VI | NEGROS OCCIDENTAL |  | P00549885VS | Construction of Flood Mitigation Structure | 122.9581 | 10.8731 | 24749853.47 | 24500000 | 2022 | M.K.U. CONSTRUCTION AND SUPPLY | 6252 | 2021 | 2022-07-24 | 09/08/2021 | 249853.47 | 0 | 2022-07-23 |  | 1
2022 | Region VI | CAPIZ | MAMBUSAO (CAPIZ) | P00620278VS | Construction of Flood Mitigation Structure | 122.6101 | 11.4349 | 55969419.75 | 55969403.95 | 2024 | SUPREME ABF CONST. & CONST. SUPPLY COMPANY INC. | 6253 | 2022 | 2024-02-02 | 03/06/2022 | 15.8 | 0 | 2023-11-04 |  | 90
2023 | Region V | CAMARINES NORTE | DAET (CAPITAL) (CAMARINES NORTE) | P00727321LZ | Construction of Flood Mitigation Structure | 122.9118 | 14.0941 | 96499909.87 | 96499909.87 | 2023 | E. GARCIA CONSTRUCTION CORP.(FOR. E. GARCIA CONST | 6254 | 2023 | 2023-12-04 | 07/06/2023 | 0 | 0 | 2024-04-13 | 131
2022 | Region IX | ZAMBOANGA DEL NORTE | PRES. MANUEL A. ROXAS (ZAMBOANGA DEL NORTE) | P00632607MN | Construction of Flood Mitigation Structure | 123.2445 | 8.5145 | 4950000 | 4919990.04 | 2022 | GOLDEN LION CONSTRUCTION | 6255 | 2022 | 2022-11-24 | 03/31/2022 | 30009.96 | 0 | 2022-06-19 |  | 158
2023 | Region VI | AKLAN | BANGA (AKLAN) | P00721986VS | Construction of Flood Mitigation Structure | 122.3087 | 11.4358 | 49000000 | 48999991.8 | 2024 | F. GURREA CONSTRUCTION, INCORPORATED | 6256 | 2023 | 2024-03-25 | 03/17/2023 | 8.2 | 0 | 2024-03-30 | 5
2024 | Region VI | ILOILO | SAN MIGUEL (ILOILO) | P00820171VS | Construction of Flood Mitigation Structure | 122.4511 | 10.7798 | 11760000 | 11759999.77 | 2024 | 1 BEATUS BUILDERS CORP. | 6257 | 2024 | 2024-12-31 | 05/07/2024 | 0.23 | 0 | 2024-12-30 |  | 1
2022 | Region V | ALBAY | LIBON (ALBAY) | P00620308LZ | Construction of Flood Mitigation Structure | 123.3291 | 13.1996 | 48139996.4 | 48139996.4 | 2022 | MAKAPA CORPORATION / PROTERRE CONSTRUCTION | 6258 | 2022 | 2022-12-18 | 03/23/2022 | 0 | 0 | 2022-12-17 |  | 1
2023 | Region VI | ILOILO | AJUY (ILOILO) | P00721494VS | Construction of Flood Mitigation Structure | 123.0122 | 11.1038 | 86464000 | 86452076.5 | 2024 | IBC INTERNATIONAL BUILDERS CORPORATION | 6259 | 2023 | 2024-07-03 | 02/17/2023 | 11923.5 | 0 | 2024-07-02 |  | 1
2023 | Region VI | NEGROS OCCIDENTAL | BACOLOD CITY (CAPITAL) (NEGROS OCCIDENTAL) | P00721637VS | Construction of Drainage Structure | 122.9584 | 10.6682 | 29400000 | 29400000 | 2023 | WILKINSON CONSTRUCTION | 6260 | 2023 | 2023-12-11 | 02/08/2023 | 0 | 0 | 2023-10-12 |  | 60
2023 | Region VI | NEGROS OCCIDENTAL | CADIZ CITY (NEGROS OCCIDENTAL) | P00721659VS | Construction of Flood Mitigation Structure | 123.3292 | 10.9144 | 39199987.76 | 39198000 | 2023 | A.C. RIVERO DEVELOPMENT CORPORATION | 6261 | 2023 | 2023-08-20 | 02/13/2023 | 1987.76 | 0 | 2023-08-19 |  | 1
2023 | Region VI | ILOILO | GUIMBAL (ILOILO) | P00721648VS | Construction of Flood Mitigation Structure | 122.3094 | 10.7158 | 14700000 | 14549734.26 | 2023 | GOOD FORTUNE INTERNATIONAL, INC. | 6262 | 2023 | 2023-06-12 | 02/10/2023 | 150265.74 | 0 | 2023-06-11 |  | 1
2022 | Region IV-A | QUEZON | GUINAYANGAN (QUEZON) | P00620617LZ | Construction of Flood Mitigation Structure | 122.4521 | 13.9041 | 19600000 | 19600000 | 2022 | MURIELEVEN BUILDERS AND CONSTRUCTION SUPPLY CORP. | 6263 | 2022 | 2022-09-23 | 02/16/2022 | 0 | 0 | 2022-09-22 |  | 1
2022 | Region V | CAMARINES SUR | PASACAO (CAMARINES SUR) | P00620710LZ | Construction of Dike | 123.0133 | 13.5172 | 49000000 | 47529798.51 | 2022 | HI-TONE CONSTRUCTION & DEVELOPMENT CORP. (FORMERLY | 6264 | 2022 | 2022-09-15 | 02/28/2022 | 1470201.49 | 0 | 2022-09-19 | 4
2023 | Region IV-B | ROMBLON | SAN FERNANDO (ROMBLON) | P00725880LZ | Construction of Flood Mitigation Structure | 122.6171 | 12.29 | 50662499.78 | 50658133.52 | 2023 | ROLCO CONSTRUCTION & DEVELOPMENT CORPORATION ( FOR | 6265 | 2023 | 2023-08-16 | 02/21/2023 | 4366.26 | 0 | 2023-10-22 | 67
2024 | Region VII | NEGROS ORIENTAL | SIATON (NEGROS ORIENTAL) | P00820211VS | Construction of Flood Mitigation Structure | 122.9118 | 9.1485 | 45080000 | 45080000 | 2024 | YPR GEN. CONTRACTOR AND CONSTRUCTION SUPPLY INC. | 6266 | 2024 | 2024-09-02 | 02/20/2024 | 0 | 0 | 2024-09-10 | 8
2024 | Region IX | ZAMBOANGA SIBUGAY | SIAY (ZAMBOANGA SIBUGAY) | P00820140MN | Construction of Flood Mitigation Structure | 122.9152 | 7.7755 | 13066340 | 10225709.86 | 2025 | EG-VRYLE CONSTRUCTION & ENTERPRISES | 6267 | 2024 | 2025-02-10 | 04/17/2024 | 2840630.14 | 0 | 2024-07-27 |  | 198
2023 | Region V | CAMARINES SUR | LUPI (CAMARINES SUR) | P00736075LZ | Construction of Flood Mitigation Structure | 122.9156 | 13.8937 | 82024565.85 | 82024538 | 2023 | G.C.I. CONSTRUCTION AND DEV'T. CORP. | 6268 | 2023 | 2023-11-17 | 03/31/2023 | 27.85 | 0 | 2023-11-16 |  | 1
2023 | Region V | CAMARINES SUR | LUPI (CAMARINES SUR) | P00736089LZ | Construction of Flood Mitigation Structure | 122.9162 | 13.7965 | 82024756.3 | 82024747.74 | 2023 | MGT BUILDER'S & SUPPLY / R.K.X. ODIAMAR CONSTRUCTION | 6269 | 2023 | 2023-10-23 | 03/31/2023 | 8.56 | 0 | 2023-11-16 | 24
2023 | Region V | CAMARINES SUR | LUPI (CAMARINES SUR) | P00736090LZ | Construction of Flood Mitigation Structure | 122.9163 | 13.7965 | 82024538.02 | 82024518.55 | 2023 | G.C.I. CONSTRUCTION AND DEV'T. CORP. | 6270 | 2023 | 2023-11-16 | 03/31/2023 | 19.47 | 0 | 2023-11-16 | 0
2024 | Region VII | NEGROS ORIENTAL | LA LIBERTAD (NEGROS ORIENTAL) | P00820199VS | Construction of Flood Mitigation Structure | 123.2447 | 10.0528 | 8820000 | 8731537.66 | 2024 | KOUKEN CONSTRUCTION | 6271 | 2024 | 2024-06-24 | 02/07/2024 | 88462.34 | 0 | 2024-06-23 |  | 1
2023 | Region V | CAMARINES SUR | LUPI (CAMARINES SUR) | P00740482LZ | Construction of Flood Mitigation Structure | 122.9165 | 13.7969 | 82024188.27 | 82024184.66 | 2024 | G.C.I. CONSTRUCTION AND DEV'T. CORP. | 6272 | 2023 | 2024-01-05 | 04/19/2023 | 3.61 | 0 | 2024-01-06 | 1
2023 | Region VI | NEGROS OCCIDENTAL | BACOLOD CITY (CAPITAL) (NEGROS OCCIDENTAL) | P00721635VS | Construction of Drainage Structure | 122.9596 | 10.6791 | 19600000 | 19600000 | 2024 | KENNETH CONSTRUCTION AND GENERAL MERCHANDISE | 6273 | 2023 | 2024-05-10 | 02/08/2023 | 0 | 0 | 2023-09-12 |  | 241
2022 | Region V | CAMARINES SUR | MAGARAO (CAMARINES SUR) | P00640581LZ | Construction of Slope Protection Structure | 123.2482 | 13.6659 | 29699785.51 | 28211825 | 2022 | PRECIOUS CONSTRUCTION | 6274 | 2022 | 2022-12-11 | 05/24/2022 | 1487960.51 | 0 | 2022-12-10 |  | 1
2021 | Region VI | AKLAN |  | P00521744VS | Construction of Flood Mitigation Structure | 122.3108 | 11.6422 | 96500000 | 94314902.66 | 2022 | F. GURREA CONSTRUCTION, INCORPORATED | 6275 | 2021 | 2022-08-25 | 07/12/2021 | 2185097.34 | 0 | 2022-04-10 |  | 137
2024 | Region VI | ILOILO | SAN MIGUEL (ILOILO) | P00820266VS | Construction of Flood Mitigation Structure | 122.4525 | 10.7804 | 86850000 | 86849591.61 | 2024 | J E G CONSTRUCTION FIRM CORPORATION / UY CONDEV CORPORATION (FORMERLY:UY CONSTRUCTION & | 6276 | 2024 | 2024-11-27 | 02/14/2024 | 408.39 | 0 | 2025-09-18 | 295
2024 | Region VI | NEGROS OCCIDENTAL | CADIZ CITY (NEGROS OCCIDENTAL) | P00820173VS | Construction of Flood Mitigation Structure | 123.3292 | 10.9144 | 48999992.35 | 48997991.31 | 2024 | A.C. RIVERO DEVELOPMENT CORPORATION | 6277 | 2024 | 2024-08-12 | 02/14/2024 | 2001.04 | 0 | 2024-08-11 |  | 1
2024 | Region VI | ILOILO | AJUY (ILOILO) | P00820168VS | Construction of Flood Mitigation Structure | 123.0138 | 11.1173 | 29400000 | 29399525.91 | 2024 | C'ZARLES CONSTRUCTION & SUPPLY | 6278 | 2024 | 2024-12-10 | 03/19/2024 | 474.09 | 0 | 2024-12-09 |  | 1
2022 | Region VI | ILOILO | AJUY (ILOILO) | P00620094VS | Construction of Flood Mitigation Structure | 123.0141 | 11.1185 | 39200000 | 39703144.12 | 2023 | ACCELERATED METAL TECHNOLOGY & CONSTRUCTION, INC. | 6279 | 2022 | 2023-03-20 | 01/28/2022 | 0 | 503144.12 | 2023-01-03 |  | 76
2021 | Region VI | ILOILO |  | P00521606VS | Construction of Slope Protection Structure | 122.6188 | 11.0481 | 14700000 | 14000000 | 2022 | UBS UNITED BUILDERS AND SUPPLY INC. | 6280 | 2021 | 2022-08-03 | 03/29/2022 | 700000 | 0 | 2022-07-16 |  | 18
2022 | Region V | CAMARINES SUR | BALATAN (CAMARINES SUR) | P00620729LZ | Construction of Flood Mitigation Structure | 123.2489 | 13.329 | 39200000 | 39199942.42 | 2022 | ALRO CONSTRUCTION & DEVELOPMENT CORP. | 6281 | 2022 | 2022-09-15 | 02/22/2022 | 57.58 | 0 | 2022-10-26 | 41
2023 | Region V | CAMARINES SUR | LUPI (CAMARINES SUR) | P00736074LZ | Construction of Flood Mitigation Structure | 122.9178 | 13.9288 | 82024683.97 | 82024679.88 | 2023 | G.C.I. CONSTRUCTION AND DEV'T. CORP. | 6282 | 2023 | 2023-08-23 | 03/31/2023 | 4.09 | 0 | 2023-11-16 | 85
2022 | Region VI | NEGROS OCCIDENTAL | BACOLOD CITY (CAPITAL) (NEGROS OCCIDENTAL) | P00620014VS | Construction of Revetment | 122.9599 | 10.7053 | 58857280 | 58857280 | 2023 | SILVER DRAGON CONSTRUCTION & LUMBER & GLASS SUPPLY INC. | 6283 | 2022 | 2023-05-15 | 03/01/2022 | 0 | 0 | 2023-02-04 |  | 100
2023 | Region VI | ILOILO | AJUY (ILOILO) | P00721493VS | Construction of Flood Mitigation Structure | 123.0146 | 11.1199 | 86464000 | 86464000 | 2024 | C'ZARLES CONSTRUCTION & SUPPLY | 6284 | 2023 | 2024-02-29 | 02/17/2023 | 0 | 0 | 2024-02-28 |  | 1
2022 | Region VI | ILOILO | DUEÃ‘AS (ILOILO) | P00620018VS | Construction of Flood Mitigation Structure | 122.6188 | 11.0482 | 40002620 | 39200433.3 | 2022 | UBS UNITED BUILDERS AND SUPPLY INC. | 6285 | 2022 | 2022-08-23 | 02/10/2022 | 802186.7 | 0 | 2022-07-24 |  | 30
2024 | Region VII | NEGROS ORIENTAL | CITY OF GUIHULNGAN (NEGROS ORIENTAL) | P00820203VS | Construction of Flood Mitigation Structure | 123.25 | 10.0684 | 29400000 | 29400000 | 2024 | KOUKEN CONSTRUCTION | 6286 | 2024 | 2024-09-04 | 02/07/2024 | 0 | 0 | 2024-09-03 |  | 1
2022 | Region IV-A | QUEZON | GUINAYANGAN (QUEZON) | P00620615LZ | Construction of Flood Mitigation Structure | 122.4558 | 13.8942 | 19600000 | 19600000 | 2022 | MURIELEVEN BUILDERS AND CONSTRUCTION SUPPLY CORP. | 6287 | 2022 | 2022-11-21 | 02/15/2022 | 0 | 0 | 2022-11-20 |  | 1
2023 | Region VII | CEBU | MALABUYOC (CEBU) | P00721511VS | Construction of Groundsill | 123.3295 | 9.6877 | 94520123.73 | 3342425.31 | 2024 | QM BUILDERS | 6288 | 2023 | 2024-07-13 | 09/04/2023 | 91177698.42 | 0 | 2024-07-12 |  | 1
2022 | Region VI | NEGROS OCCIDENTAL | CITY OF TALISAY (NEGROS OCCIDENTAL) | P00620098VS | Construction of Flood Mitigation Structure | 122.9608 | 10.7185 | 48999988.02 | 48998000 | 2022 | M.K.U. CONSTRUCTION AND SUPPLY | 6289 | 2022 | 2022-08-07 | 02/08/2022 | 1988.02 | 0 | 2022-08-06 |  | 1
2022 | Region VI | ILOILO | GUIMBAL (ILOILO) | P00620084VS | Construction of Flood Mitigation Structure | 122.3109 | 10.7139 | 9800000 | 9701673.55 | 2022 | GOLDEN ROADRUNNER INTERNATIONAL CORP. | 6290 | 2022 | 2022-08-22 | 03/29/2022 | 98326.45 | 0 | 2022-08-01 |  | 21
2023 | Region V | CAMARINES SUR | PASACAO (CAMARINES SUR) | P00736097LZ | Construction of Dike | 123.0146 | 13.5162 | 96500000 | 96500000 | 2023 | NFH CONSTRUCTION & SUPPLY | 6291 | 2023 | 2023-11-24 | 02/22/2023 | 0 | 0 | 2024-01-24 | 61
2023 | Region VI | ILOILO | DUEÃ‘AS (ILOILO) | P00721655VS | Construction of Flood Mitigation Structure | 122.6191 | 11.0491 | 24500000 | 24427996.21 | 2023 | UBS UNITED BUILDERS AND SUPPLY INC. | 6292 | 2023 | 2023-09-25 | 02/13/2023 | 72003.79 | 0 | 2023-09-20 |  | 5
2024 | Region VI | NEGROS OCCIDENTAL | CITY OF TALISAY (NEGROS OCCIDENTAL) | P00820174VS | Construction of Flood Mitigation Structure | 122.9613 | 10.7185 | 48999999.42 | 48999999.46 | 2024 | M.K.U. CONSTRUCTION AND SUPPLY | 6293 | 2024 | 2024-08-12 | 02/14/2024 | 0 | 0.04 | 2024-08-11 |  | 1
2023 | Region V | CAMARINES SUR | LUPI (CAMARINES SUR) | P00736092LZ | Construction of Flood Mitigation Structure | 122.9178 | 13.9289 | 82024953.97 | 82024888.9 | 2023 | BICOL GOLDROCK CONSTRUCTION CORPORATION | 6294 | 2023 | 2023-06-26 | 03/31/2023 | 65.07 | 0 | 2023-11-16 | 143
2024 | Region VII | NEGROS ORIENTAL | SIBULAN (NEGROS ORIENTAL) | P00820207VS | Construction of Flood Mitigation Structure | 123.2506 | 9.3176 | 19600000 | 19600000 | 2024 | ASHLEYKA CONSTRUCTION AND SUPPLIES | 6295 | 2024 | 2024-08-22 | 04/04/2024 | 0 | 0 | 2024-09-04 | 13
2022 | Region VI | AKLAN | BANGA (AKLAN) | P00620074VS | Construction of Revetment | 122.3114 | 11.5463 | 49000000 | 48999997.71 | 2023 | A.D. PENDON CONSTRUCTION & SUPPLY, INC. (FORMERLY: ADP CONSTRUCTION & SUPPLY) | 6296 | 2022 | 2023-10-25 | 06/03/2022 | 2.29 | 0 | 2023-01-30 |  | 268
2023 | Region VII | CEBU | MALABUYOC (CEBU) | P00721513VS | Construction of Revetment | 123.3301 | 9.6877 | 95533212.98 | 95532668.54 | 2023 | QM BUILDERS | 6297 | 2023 | 2023-12-18 | 02/08/2023 | 544.44 | 0 | 2023-12-17 |  | 1
2023 | Region VI | NEGROS OCCIDENTAL | LA CASTELLANA (NEGROS OCCIDENTAL) | P00732011VS | Construction of Slope Protection Structure | 123.0152 | 10.3312 | 57900000 | 57900000 | 2024 | LEGACY CONSTRUCTION CORPORATION (FORMERLY: LEGACY CONSTRUCTION) | 6298 | 2023 | 2024-01-04 | 04/09/2023 | 0 | 0 | 2024-01-03 |  | 1
2024 | Region IX | ZAMBOANGA SIBUGAY | ROSELLER LIM (ZAMBOANGA SIBUGAY) | P00820890MN | Construction of Flood Mitigation Structure | 122.465 | 7.6513 | 96500000 | 95529501.4 | 2025 | BARILLO CONSTRUCTION AND ENTERPRISES | 6299 | 2024 | 2025-01-27 | 05/08/2024 | 970498.6 | 0 | 2025-02-23 | 27
2022 | Region VI | CAPIZ | DUMALAG (CAPIZ) | P00630181VS | Construction of Flood Mitigation Structure | 122.62 | 11.306 | 53075000 | 53075000 | 2023 | WOODLAND CONSTRUCTION & SUPPLY, INC. | 6300 | 2022 | 2023-05-30 | 03/21/2022 | 0 | 0 | 2023-05-29 |  | 1
2022 | Region V | CAMARINES NORTE | DAET (CAPITAL) (CAMARINES NORTE) | P00621485LZ | Construction of Flood Mitigation Structure | 122.962 | 14.1123 | 29399217.07 | 28511229.65 | 2022 | EUS CONSTRUCTION | 6301 | 2022 | 2022-09-17 | 03/30/2022 | 887987.42 | 0 | 2022-09-16 |  | 1
2024 | Region VI | ANTIQUE | BUGASONG (ANTIQUE) | P00820273VS | Construction of Flood Mitigation Structure | 122.62 | 11.0053 | 82025000 | 82025000 | 2024 | F & J GENERAL CONSTRUCTION AND SUPPLY CORPORATION | 6302 | 2024 | 2024-12-16 | 02/09/2024 | 0 | 0 | 2024-12-15 |  | 1
2023 | Region V | CAMARINES SUR | LUPI (CAMARINES SUR) | P00736094LZ | Construction of Flood Mitigation Structure | 122.918 | 13.8937 | 82024231.78 | 80999846.15 | 2023 | MGT BUILDER'S & SUPPLY / R.K.X. ODIAMAR CONSTRUCTION | 6303 | 2023 | 2023-11-17 | 03/31/2023 | 1024385.63 | 0 | 2023-11-16 |  | 1
2023 | Region VII | NEGROS ORIENTAL | VALENCIA (LUZURRIAGA) (NEGROS ORIENTAL) | P00721847VS | Construction of Flood Mitigation Structure | 123.2511 | 9.3094 | 44100000 | 44100000 | 2023 | LEGACY CONSTRUCTION CORPORATION (FORMERLY: LEGACY CONSTRUCTION) | 6304 | 2023 | 2023-10-08 | 03/01/2023 | 0 | 0 | 2023-10-07 |  | 1
2023 | Region VI | NEGROS OCCIDENTAL | LA CASTELLANA (NEGROS OCCIDENTAL) | P00732021VS | Construction of Slope Protection Structure | 123.0154 | 10.3313 | 49000000 | 49000000 | 2023 | LEGACY CONSTRUCTION CORPORATION (FORMERLY: LEGACY CONSTRUCTION) | 6305 | 2023 | 2023-12-24 | 04/09/2023 | 0 | 0 | 2023-12-23 |  | 1
2022 | Region IV-A | QUEZON | BUENAVISTA (QUEZON) | P00621471LZ | Construction of Flood Mitigation Structure | 122.4668 | 13.7414 | 29399864.62 | 29400000 | 2022 | MRRM TRADING & CONSTRUCTION | 6306 | 2022 | 2022-11-15 | 04/05/2022 | 0 | 135.38 | 2022-12-29 | 44
2024 | Region VI | ILOILO | GUIMBAL (ILOILO) | P00832630VS | Construction of Flood Mitigation Structure | 122.3122 | 10.6572 | 29700000 | 29649524.81 | 2025 | RINEL CONSTRUCTION SERVICES | 6307 | 2024 | 2025-03-03 | 04/29/2024 | 50475.19 | 0 | 2025-05-11 | 69
2024 | Region VI | NEGROS OCCIDENTAL | ENRIQUE B. MAGALONA (SARAVIA) (NEGROS OCCIDENTAL) | P00834637VS | Construction of Flood Mitigation Structure | 122.9625 | 10.8847 | 29399991.35 | 29399993.82 | 2024 | SL & G CONSTRUCTION | 6308 | 2024 | 2024-08-06 | 02/19/2024 | 0 | 2.47 | 2024-08-05 |  | 1
2022 | Region VII | NEGROS ORIENTAL | BASAY (NEGROS ORIENTAL) | P00620321VS | Rehabilitation / Major Repair of Flood Control Structure | 122.6231 | 9.4328 | 45810100 | 45810100 | 2022 | LEGACY CONSTRUCTION CORPORATION (FORMERLY: LEGACY CONSTRUCTION) | 6309 | 2022 | 2022-12-09 | 02/17/2022 | 0 | 0 | 2023-01-22 | 44
2023 | Region VII | CEBU | MALABUYOC (CEBU) | P00721888VS | Construction of Dike | 123.3316 | 9.6887 | 96497670 | 96497659.06 | 2024 | NEWBIG FOUR J CONSTRUCTION INC., (FORMERLY FOUR J | 6310 | 2023 | 2024-01-16 | 03/16/2023 | 10.94 | 0 | 2024-01-15 |  | 1
2022 | Region VII | NEGROS ORIENTAL | SIATON (NEGROS ORIENTAL) | P00620319VS | Rehabilitation / Major Repair of Flood Control Structure | 122.9189 | 9.1325 | 39200000 | 39200000 | 2022 | LEGACY CONSTRUCTION CORPORATION (FORMERLY: LEGACY CONSTRUCTION) / MIGHTY HOK SUMMIT CONSTRUCTION & DEVELOPMENT CORP. | 6311 | 2022 | 2022-09-20 | 02/17/2022 | 0 | 0 | 2022-11-04 | 45
2023 | Region V | CAMARINES SUR | BALATAN (CAMARINES SUR) | P00736105LZ | Rehabilitation / Major Repair of Flood Control Structure | 123.2516 | 13.3303 | 96478328 | 96478328 | 2023 | HI-TONE CONSTRUCTION & DEVELOPMENT CORP. (FORMERLY | 6312 | 2023 | 2023-12-15 | 02/17/2023 | 0 | 0 | 2024-01-01 | 17
2024 | Region VII | NEGROS ORIENTAL | BASAY (NEGROS ORIENTAL) | P00820408VS | Construction of Flood Mitigation Structure | 122.6233 | 9.4319 | 45080000 | 45080000 | 2024 | ELITE GENERAL CONTRACTOR AND DEVELOPMENT CORP. | 6313 | 2024 | 2024-07-31 | 02/20/2024 | 0 | 0 | 2024-09-06 | 37
2023 | Region VI | NEGROS OCCIDENTAL | LA CASTELLANA (NEGROS OCCIDENTAL) | P00744501VS | Rehabilitation / Major Repair of Slope Protection Structure | 123.0154 | 10.3347 | 1158000 | 1154359 | 2023 | ST. RAYMUND CONSTRUCTION, INC. | 6314 | 2023 | 2023-07-09 | 04/12/2023 | 3641 | 0 | 2023-07-02 |  | 7
2022 | Region VI | ILOILO | SAN MIGUEL (ILOILO) | P00620237VS | Construction of Flood Mitigation Structure | 122.4684 | 10.7839 | 96500000 | 96499992.73 | 2023 | F. GURREA CONSTRUCTION, INCORPORATED / GOOD FORTUNE INTERNATIONAL, INC. | 6315 | 2022 | 2023-04-25 | 02/21/2022 | 7.27 | 0 | 2023-06-03 | 39
2023 | Region VII | CEBU | MALABUYOC (CEBU) | P00721889VS | Construction of Dike | 123.3316 | 9.6889 | 96497673.36 | 96497667.23 | 2023 | NEWBIG FOUR J CONSTRUCTION INC., (FORMERLY FOUR J | 6316 | 2023 | 2023-12-07 | 03/16/2023 | 6.13 | 0 | 2024-01-15 | 39
2022 | Region VI | NEGROS OCCIDENTAL | ENRIQUE B. MAGALONA (SARAVIA) (NEGROS OCCIDENTAL) | P00632030VS | Construction of Flood Mitigation Structure | 122.9627 | 10.8849 | 29399974.89 | 29399974 | 2022 | A.C. RIVERO DEVELOPMENT CORPORATION | 6317 | 2022 | 2022-09-28 | 03/30/2022 | 0.89 | 0 | 2022-09-27 |  | 1
2022 | Region VI | NEGROS OCCIDENTAL | LA CARLOTA CITY (NEGROS OCCIDENTAL) | P00632031VS | Construction of Drainage Structure | 122.9194 | 10.4592 | 39199995.37 | 39196031.75 | 2023 | JAIME B. CHING ENTERPRISES | 6318 | 2022 | 2023-06-25 | 03/31/2022 | 3963.62 | 0 | 2023-06-24 |  | 1
2022 | Region VII | NEGROS ORIENTAL | VALENCIA (LUZURRIAGA) (NEGROS ORIENTAL) | P00633021VS | Construction of Flood Mitigation Structure | 123.2517 | 9.3097 | 49000000 | 49000000 | 2023 | PHILSOUTH BUILDERS INC (FORMERLY:PHILSOUTH BUILDERS) | 6319 | 2022 | 2023-02-14 | 04/07/2022 | 0 | 0 | 2022-12-06 |  | 70
2022 | Region V | CAMARINES NORTE | JOSE PANGANIBAN (CAMARINES NORTE) | P00631416LZ | Construction of Flood Mitigation Structure | 122.6263 | 14.2917 | 19599792.89 | 19019199.19 | 2022 | EUS CONSTRUCTION | 6320 | 2022 | 2022-10-21 | 03/17/2022 | 580593.7 | 0 | 2022-10-20 |  | 1
2024 | Region VI | ILOILO | GUIMBAL (ILOILO) | P00832625VS | Construction of Flood Mitigation Structure | 122.3122 | 10.7175 | 49500000 | 49445882.19 | 2024 | IBC INTERNATIONAL BUILDERS CORPORATION | 6321 | 2024 | 2024-11-15 | 04/08/2024 | 54117.81 | 0 | 2024-11-03 |  | 12
2022 | Region V | CAMARINES SUR | LIBMANAN (CAMARINES SUR) | P00620723LZ | Construction of Revetment | 123.0179 | 13.7105 | 49000000 | 48022335 | 2022 | BICOL GOLDROCK CONSTRUCTION CORPORATION | 6322 | 2022 | 2022-08-05 | 02/22/2022 | 977665 | 0 | 2022-09-13 | 39
2022 | Region V | CAMARINES NORTE | JOSE PANGANIBAN (CAMARINES NORTE) | P00631398LZ | Construction of Flood Mitigation Structure | 122.632 | 14.3107 | 19599324.6 | 19259399.53 | 2022 | BRENTMIN ROOFING ENTERPRISE | 6323 | 2022 | 2022-08-29 | 03/24/2022 | 339925.07 | 0 | 2022-08-28 |  | 1
2023 | Region VI | ILOILO | CALINOG (ILOILO) | P00721999VS | Construction of Flood Mitigation Structure | 122.4706 | 11.1504 | 24500000 | 24499986.89 | 2023 | STRONGLANE BUILDERS AND TRADING CORPORATION (FORMERLY: STRONGLANE CONSTRUCTION & TRADING) | 6324 | 2023 | 2023-09-25 | 03/06/2023 | 13.11 | 0 | 2023-09-24 |  | 1
2024 | Region VI | NEGROS OCCIDENTAL | SILAY CITY (NEGROS OCCIDENTAL) | P00832638VS | Construction of Flood Mitigation Structure | 122.9628 | 10.8119 | 10394998.95 | 10392962.4 | 2024 | CANLAON BUILDERS AND DEVELOPMENT CORPORATION | 6325 | 2024 | 2024-05-28 | 02/14/2024 | 2036.55 | 0 | 2024-05-27 |  | 1
2023 | Region V | CAMARINES NORTE | DAET (CAPITAL) (CAMARINES NORTE) | P00726772LZ | Construction of Flood Mitigation Structure | 122.9195 | 14.1023 | 77199973.4 | 77199972.9 | 2023 | EUS CONSTRUCTION | 6326 | 2023 | 2023-12-18 | 06/30/2023 | 0.5 | 0 | 2024-03-05 | 78
2023 | Region V | CAMARINES SUR | BALATAN (CAMARINES SUR) | P00725884LZ | Construction of Flood Mitigation Structure | 123.2523 | 13.3308 | 48244415 | 48244407.6 | 2023 | BICOL GOLDROCK CONSTRUCTION CORPORATION | 6327 | 2023 | 2023-08-25 | 03/20/2023 | 7.4 | 0 | 2023-10-12 | 48
2024 | Region VI | ILOILO | GUIMBAL (ILOILO) | P00821042VS | Construction of Flood Mitigation Structure | 122.3131 | 10.6925 | 29400000 | 29094184.94 | 2024 | GALENO CONSTRUCTION, INC. | 6328 | 2024 | 2024-07-25 | 02/26/2024 | 305815.06 | 0 | 2024-07-24 |  | 1
2023 | Region VII | CEBU | MALABUYOC (CEBU) | P00721890VS | Construction of Dike | 123.3317 | 9.6886 | 96497671.28 | 96497659.53 | 2023 | NEWBIG FOUR J CONSTRUCTION INC., (FORMERLY FOUR J | 6329 | 2023 | 2023-12-07 | 03/16/2023 | 11.75 | 0 | 2024-01-15 | 39
2024 | Region VII | NEGROS ORIENTAL | SIATON (NEGROS ORIENTAL) | P00835016VS | Construction of Flood Mitigation Structure | 123.0184 | 9.0618 | 29700000 | 29700000 | 2024 | MIGHTY HOK SUMMIT CONSTRUCTION & DEVELOPMENT CORP. | 6330 | 2024 | 2024-08-06 | 04/11/2024 | 0 | 0 | 2024-10-16 | 71
2022 | Region VII | NEGROS ORIENTAL | BASAY (NEGROS ORIENTAL) | P00620309VS | Rehabilitation / Major Repair of Flood Control Structure | 122.6375 | 9.408 | 42786800 | 42786800 | 2023 | H.L.J CONSTRUCTION & ENTERPRISES | 6331 | 2022 | 2023-04-28 | 03/08/2022 | 0 | 0 | 2023-04-27 |  | 1
2023 | Region VI | ILOILO | MAASIN (ILOILO) | P00721654VS | Construction of Flood Mitigation Structure | 122.4712 | 10.8839 | 19600000 | 19599435.17 | 2023 | TIB TIMCO INFRA BUILDERS | 6332 | 2023 | 2023-08-25 | 02/13/2023 | 564.83 | 0 | 2023-08-24 |  | 1
2022 | Region V | CAMARINES SUR | LIBMANAN (CAMARINES SUR) | P00631002LZ | Rehabilitation / Major Repair of Flood Control Structure | 123.0196 | 13.7089 | 72375000 | 70925228.67 | 2022 | G.C.I. CONSTRUCTION AND DEV'T. CORP. | 6333 | 2022 | 2022-12-09 | 05/25/2022 | 1449771.33 | 0 | 2023-02-04 | 57
2024 | Region IX | ZAMBOANGA DEL SUR | SAN MIGUEL (ZAMBOANGA DEL SUR) | P00820137MN | Construction of Flood Mitigation Structure | 123.2537 | 7.6277 | 29400000 | 29384767.64 | 2024 | NRMM CONSTRUCTION AND DEV'T CORP. | 6334 | 2024 | 2024-08-15 | 05/02/2024 | 15232.36 | 0 | 2024-11-12 | 89
2022 | Region IX | ZAMBOANGA SIBUGAY | SIAY (ZAMBOANGA SIBUGAY) | P00630570MN | Construction of Flood Mitigation Structure | 122.9214 | 7.7611 | 39200000 | 38699939.44 | 2022 | LONG ISLAND BUILDERS & CONSTRUCTION | 6335 | 2022 | 2022-11-20 | 02/07/2022 | 500060.56 | 0 | 2022-11-19 |  | 1
2023 | Region VII | CEBU | MALABUYOC (CEBU) | P00745598VS | Rehabilitation / Major Repair of Flood Control Structure | 123.3323 | 9.689 | 94316016.53 | 94315929.32 | 2024 | JTC CRUZ CONSTRUCTION CO., INC. / NEWBIG FOUR J CONSTRUCTION INC., (FORMERLY FOUR J | 6336 | 2023 | 2024-06-08 | 08/10/2023 | 87.21 | 0 | 2024-06-07 |  | 1
2022 | Region IV-A | QUEZON | CATANAUAN (QUEZON) | P00620866LZ | Construction of Flood Mitigation Structure | 122.3138 | 13.6053 | 68997392.35 | 68997500 | 2022 | RAPID FOREMOST CONST. CO. / JAICA CONST. CORP | 6337 | 2022 | 2022-11-08 | 02/16/2022 | 0 | 107.65 | 2022-12-11 | 33
2022 | Region VI | ILOILO | POTOTAN (ILOILO) | P00620006VS | Construction of Flood Mitigation Structure | 122.6405 | 10.9445 | 63634030 | 62361253.4 | 2023 | ROPRIM CONSTRUCTION CORPORATION (FORMERLY ROPRIM CONSTRUCTION) | 6338 | 2022 | 2023-11-26 | 02/18/2022 | 1272776.6 | 0 | 2022-09-08 |  | 444
2022 | Region IX | ZAMBOANGA DEL NORTE | LABASON (ZAMBOANGA DEL NORTE) | P00620006MN | Construction of Flood Mitigation Structure | 122.4715 | 8.0559 | 86058217.5 | 86058217.5 | 2022 | MONTAÃ‘O CONSTRUCTION & DEVELOPMENT CORPORATION | 6339 | 2022 | 2022-10-15 | 03/02/2022 | 0 | 0 | 2022-12-16 | 62
2023 | Region IX | ZAMBOANGA SIBUGAY | DIPLAHAN (ZAMBOANGA SIBUGAY) | P00721227MN | Construction of Flood Mitigation Structure | 122.9633 | 7.7921 | 57900000 | 57803416.06 | 2023 | LAKEWOOD CONSTRUCTION COMPANY | 6340 | 2023 | 2023-11-25 | 03/27/2023 | 96583.94 | 0 | 2023-11-24 |  | 1
2024 | Region IX | ZAMBOANGA DEL NORTE | JOSE DALMAN (PONOT) (ZAMBOANGA DEL NORTE) | P00833585MN | Construction of Flood Mitigation Structure | 123.0197 | 8.4508 | 9900000 | 9894959.6 | 2025 | RDT CONSTRUCTION AND GENERAL MERCHANDISE | 6341 | 2024 | 2025-02-23 | 02/14/2024 | 5040.4 | 0 | 2024-06-28 |  | 240
2022 | Region VII | NEGROS ORIENTAL | VALENCIA (LUZURRIAGA) (NEGROS ORIENTAL) | P00633020VS | Construction of Flood Mitigation Structure | 123.255 | 9.3167 | 49000000 | 49000000 | 2022 | PHILSOUTH BUILDERS INC (FORMERLY:PHILSOUTH BUILDERS) | 6342 | 2022 | 2022-11-13 | 04/07/2022 | 0 | 0 | 2022-11-12 |  | 1
2022 | Region IX | ZAMBOANGA SIBUGAY | SIAY (ZAMBOANGA SIBUGAY) | P00630474MN | Construction of Flood Mitigation Structure | 122.9215 | 7.7616 | 98000000 | 96039900.6 | 2022 | LONG ISLAND BUILDERS & CONSTRUCTION | 6343 | 2022 | 2022-12-12 | 02/21/2022 | 1960099.4 | 0 | 2023-01-15 | 34
2023 | Region IV-A | QUEZON | CATANAUAN (QUEZON) | P00726589LZ | Construction of Flood Mitigation Structure | 122.3139 | 13.6054 | 67549901.08 | 67550000 | 2024 | R.A. MENDIOLA CONSTRUCTION & DEVELOPER | 6344 | 2023 | 2024-05-31 | 03/06/2023 | 0 | 98.92 | 2024-06-01 | 1
2023 | Region VII | CEBU | MALABUYOC (CEBU) | P00745599VS | Rehabilitation / Major Repair of Flood Control Structure | 123.3337 | 9.6885 | 95377514.44 | 95377254.06 | 2024 | JUSTBILT BUILDERS / NEWBIG FOUR J CONSTRUCTION INC., (FORMERLY FOUR J | 6345 | 2023 | 2024-06-09 | 08/10/2023 | 260.38 | 0 | 2024-06-08 |  | 1
2023 | Region VI | ILOILO | MAASIN (ILOILO) | P00721933VS | Construction of Flood Mitigation Structure | 122.4716 | 10.883 | 29400000 | 28801449.8 | 2023 | TIB TIMCO INFRA BUILDERS | 6346 | 2023 | 2023-08-20 | 03/17/2023 | 598550.2 | 0 | 2023-09-13 | 24
2023 | Region IX | ZAMBOANGA SIBUGAY | DIPLAHAN (ZAMBOANGA SIBUGAY) | P00721228MN | Construction of Flood Mitigation Structure | 122.9635 | 7.7926 | 57900000 | 57843164.86 | 2023 | LONG ISLAND BUILDERS & CONSTRUCTION | 6347 | 2023 | 2023-11-27 | 03/20/2023 | 56835.14 | 0 | 2023-11-17 |  | 10
2023 | Region V | CAMARINES NORTE | LABO (CAMARINES NORTE) | P00742476LZ | Construction of Flood Mitigation Structure | 122.4731 | 14.1875 | 9899092.81 | 9899092.81 | 2023 | JAEJR ELECTRICAL, CONSTRUCTION & SUPPLY | 6348 | 2023 | 2023-08-25 | 05/03/2023 | 0 | 0 | 2023-08-24 |  | 1
2023 | Region V | CAMARINES SUR | LIBMANAN (CAMARINES SUR) | P00726962LZ | Construction of Flood Mitigation Structure | 123.0207 | 13.7074 | 72375000 | 72352610.15 | 2023 | C.T. LEONCIO CONSTRUCTION & TRADING | 6349 | 2023 | 2023-12-22 | 04/05/2023 | 22389.85 | 0 | 2024-02-10 | 50
2024 | Region VII | NEGROS ORIENTAL | CITY OF GUIHULNGAN (NEGROS ORIENTAL) | P00820202VS | Construction of Flood Mitigation Structure | 123.2554 | 10.0779 | 14700000 | 14700000 | 2024 | KOUKEN CONSTRUCTION | 6350 | 2024 | 2024-08-13 | 02/07/2024 | 0 | 0 | 2024-08-12 |  | 1
2024 | Region IX | ZAMBOANGA DEL SUR | GUIPOS (ZAMBOANGA DEL SUR) | P00820138MN | Construction of Flood Mitigation Structure | 123.334 | 7.7491 | 19600000 | 19362789 | 2025 | ZMS CONST. & DEV. CORP. (FORMERLY:ZMS CONSTRUCTION | 6351 | 2024 | 2025-01-27 | 04/08/2024 | 237211 | 0 | 2024-10-06 |  | 113
2023 | Region V | CAMARINES SUR | LUPI (CAMARINES SUR) | P00736076LZ | Construction of Flood Mitigation Structure | 122.9217 | 13.8927 | 81923121.41 | 81923120.95 | 2023 | NFH CONSTRUCTION & SUPPLY | 6352 | 2023 | 2023-11-17 | 03/31/2023 | 0.46 | 0 | 2023-11-16 |  | 1
2023 | Region VI | AKLAN | BANGA (AKLAN) | P00721983VS | Construction of Flood Mitigation Structure | 122.3141 | 11.6212 | 49000000 | 48999776.62 | 2023 | GREAT PACIFIC BUILDERS AND GEN. CONTRACTOR INC. | 6353 | 2023 | 2023-11-22 | 03/30/2023 | 223.38 | 0 | 2023-11-21 |  | 1
2021 | Region VI | ILOILO |  | P00521769VS | Rehabilitation / Major Repair of Flood Control Structure | 122.6405 | 11.1017 | 13982640 | 13982427.05 | 2023 | STRONGLANE BUILDERS AND TRADING CORPORATION (FORMERLY: STRONGLANE CONSTRUCTION & TRADING) | 6354 | 2021 | 2023-01-01 | 03/29/2022 | 212.95 | 0 | 2022-09-14 |  | 109
2023 | Region IX | ZAMBOANGA SIBUGAY | DIPLAHAN (ZAMBOANGA SIBUGAY) | P00721364MN | Construction of Revetment | 122.9639 | 7.7896 | 49000000 | 48944628.48 | 2023 | L.C. CONSTRUCTION CORPORATION (FOR: L.C. CONSTRUCTION) | 6355 | 2023 | 2023-12-18 | 03/10/2023 | 55371.52 | 0 | 2023-12-21 | 3
2022 | Region IX | ZAMBOANGA DEL NORTE | LABASON (ZAMBOANGA DEL NORTE) | P00620005MN | Construction of Flood Mitigation Structure | 122.4743 | 8.0637 | 86058217.5 | 86057735 | 2022 | EDANNA CONSTRUCTION | 6356 | 2022 | 2022-11-15 | 03/02/2022 | 482.5 | 0 | 2023-01-15 | 61
2024 | Region VII | NEGROS ORIENTAL | SIATON (NEGROS ORIENTAL) | P00820212VS | Construction of Flood Mitigation Structure | 123.0209 | 9.0486 | 44067660 | 44067660 | 2024 | AMETHYST HORIZON BUILDERS AND GEN. CONTRACTOR AND DEVELOPMENT CORP. | 6357 | 2024 | 2024-09-11 | 02/20/2024 | 0 | 0 | 2024-09-10 |  | 1
2022 | Region V | CAMARINES SUR | BATO (CAMARINES SUR) | P00620727LZ | Construction of Flood Mitigation Structure | 123.3354 | 13.3643 | 49000000 | 48999593.39 | 2022 | E.A. SANCHO CONST. INC. (FORM. E.A. SANCHO CONST.) | 6358 | 2022 | 2022-10-25 | 02/22/2022 | 406.61 | 0 | 2022-11-07 | 13
2022 | Region V | CAMARINES NORTE | VINZONS (CAMARINES NORTE) | P00630991LZ | Construction of Flood Mitigation Structure | 122.9218 | 14.2188 | 49214258.35 | 49214258.35 | 2023 | BRENTMIN ROOFING ENTERPRISE | 6359 | 2022 | 2023-01-28 | 03/22/2022 | 0 | 0 | 2023-01-27 |  | 1
2022 | Region VI | AKLAN | MADALAG (AKLAN) | P00620291VS | Construction of Revetment | 122.3141 | 11.5254 | 48250000 | 46648504.47 | 2023 | F & J GENERAL CONSTRUCTION AND SUPPLY CORPORATION | 6360 | 2022 | 2023-05-10 | 06/08/2022 | 1601495.53 | 0 | 2023-01-25 |  | 105
2024 | Region VI | ILOILO | POTOTAN (ILOILO) | P00820160VS | Construction of Flood Mitigation Structure | 122.641 | 10.9425 | 38220000 | 38219688.96 | 2024 | ROPRIM CONSTRUCTION CORPORATION (FORMERLY ROPRIM CONSTRUCTION) | 6361 | 2024 | 2024-12-16 | 02/12/2024 | 311.04 | 0 | 2024-08-03 |  | 135
2024 | Region VI | NEGROS OCCIDENTAL | ENRIQUE B. MAGALONA (SARAVIA) (NEGROS OCCIDENTAL) | P00832637VS | Construction of Flood Mitigation Structure | 122.9658 | 10.8772 | 4949999.69 | 4949999.69 | 2024 | SL & G CONSTRUCTION | 6362 | 2024 | 2024-05-05 | 02/14/2024 | 0 | 0 | 2024-05-04 |  | 1
2022 | Region V | CAMARINES SUR | LIBMANAN (CAMARINES SUR) | P00620720LZ | Construction of Revetment | 123.0209 | 13.6958 | 49000000 | 48012861.68 | 2022 | BICOL GOLDROCK CONSTRUCTION CORPORATION | 6363 | 2022 | 2022-08-17 | 02/22/2022 | 987138.32 | 0 | 2022-09-13 | 27
2022 | Region VI | ILOILO | CABATUAN (ILOILO) | P00630178VS | Construction of Flood Mitigation Structure | 122.4751 | 10.8783 | 101325000 | 101325000 | 2023 | F. GURREA CONSTRUCTION, INCORPORATED | 6364 | 2022 | 2023-08-15 | 02/21/2022 | 0 | 0 | 2023-06-11 |  | 65
2023 | Region VII | NEGROS ORIENTAL | SAN JOSE (NEGROS ORIENTAL) | P00721532VS | Rehabilitation / Major Repair of Flood Control Structure | 123.2583 | 9.388 | 53075000 | 53075000 | 2024 | UY CONDEV CORPORATION (FORMERLY:UY CONSTRUCTION & | 6365 | 2023 | 2024-04-02 | 06/05/2023 | 0 | 0 | 2024-04-01 |  | 1
2023 | Region VI | NEGROS OCCIDENTAL | BACOLOD CITY (CAPITAL) (NEGROS OCCIDENTAL) | P00721641VS | Construction of Flood Mitigation Structure | 122.9219 | 10.6053 | 49000000 | 49000000 | 2023 | A.C. RIVERO DEVELOPMENT CORPORATION | 6366 | 2023 | 2023-12-18 | 02/08/2023 | 0 | 0 | 2023-11-03 |  | 45
2023 | Region VI | AKLAN | MADALAG (AKLAN) | P00721991VS | Construction of Flood Mitigation Structure | 122.3144 | 11.5235 | 49000000 | 48999204.19 | 2023 | F & J GENERAL CONSTRUCTION AND SUPPLY CORPORATION | 6367 | 2023 | 2023-10-23 | 03/17/2023 | 795.81 | 0 | 2023-11-08 | 16
2022 | Region VI | NEGROS OCCIDENTAL | CADIZ CITY (NEGROS OCCIDENTAL) | P00620103VS | Construction of Flood Mitigation Structure | 123.3367 | 10.8957 | 44099996.91 | 40164560 | 2022 | C'ZARLES CONSTRUCTION & SUPPLY / GKMM CONSTRUCTION & SUPPLIES, INC. (FORMERLY: GKMM CONSTRUCTION & SUPPLIES) | 6368 | 2022 | 2022-08-15 | 02/08/2022 | 3935436.91 | 0 | 2022-09-27 | 43
2023 | Region VI | ILOILO | POTOTAN (ILOILO) | P00721652VS | Construction of Flood Mitigation Structure | 122.6411 | 10.9444 | 49000000 | 48998978.3 | 2024 | ROPRIM CONSTRUCTION CORPORATION (FORMERLY ROPRIM CONSTRUCTION) | 6369 | 2023 | 2024-07-07 | 02/13/2023 | 1021.7 | 0 | 2024-01-18 |  | 171
2023 | Region V | CAMARINES NORTE | DAET (CAPITAL) (CAMARINES NORTE) | P00742200LZ | Construction of Flood Mitigation Structure | 122.9669 | 14.1128 | 98999990.3 | 98999990.3 | 2024 | ED1SON DEVELOPMENT & CONSTRUCTION INC. / ARIK CONSTRUCTION | 6370 | 2023 | 2024-11-21 | 12/20/2023 | 0 | 0 | 2024-12-18 | 27
2022 | Region VI | NEGROS OCCIDENTAL | LA CASTELLANA (NEGROS OCCIDENTAL) | P00620405VS | Construction of Slope Protection Structure | 123.0212 | 10.3353 | 96500000 | 96500000 | 2023 | JAIME B. CHING ENTERPRISES | 6371 | 2022 | 2023-02-02 | 05/19/2022 | 0 | 0 | 2023-02-01 |  | 1
2023 | Region VI | ILOILO | OTON (ILOILO) | P00721929VS | Construction of Flood Mitigation Structure | 122.4774 | 10.6882 | 19600000 | 19599092.07 | 2024 | ASIA STRUCTURAL DEVELOPER CORPORATION | 6372 | 2023 | 2024-04-23 | 03/15/2023 | 907.93 | 0 | 2024-02-23 |  | 60
2024 | Region VI | ILOILO | CALINOG (ILOILO) | P00820034VS | Construction of Slope Protection Structure | 122.4797 | 11.163 | 120625000 | 120624908 | 2024 | IBC INTERNATIONAL BUILDERS CORPORATION | 6373 | 2024 | 2024-07-22 | 02/16/2024 | 92 | 0 | 2024-12-28 | 159
2022 | Region V | CAMARINES NORTE | SAN LORENZO RUIZ (IMELDA) (CAMARINES NORTE) | P00632955LZ | Construction of Flood Mitigation Structure | 122.9219 | 13.9511 | 4949310.75 | 4803335.09 | 2022 | 128 DRAGON CONSTRUCTION AND SUPPLIES | 6374 | 2022 | 2022-07-06 | 03/21/2022 | 145975.66 | 0 | 2022-07-05 |  | 1
2024 | Region VII | CEBU | MALABUYOC (CEBU) | P00820858VS | Construction of Flood Mitigation Structure | 123.3377 | 9.6866 | 96496398.18 | 96495998.18 | 2024 | JTC CRUZ CONSTRUCTION CO., INC. | 6375 | 2024 | 2024-09-16 | 03/18/2024 | 400 | 0 | 2025-01-17 | 123
2022 | Region VI | AKLAN | BANGA (AKLAN) | P00620289VS | Construction of Revetment | 122.3145 | 11.6019 | 48250000 | 48249302.2 | 2023 | F & J GENERAL CONSTRUCTION AND SUPPLY CORPORATION | 6376 | 2022 | 2023-11-20 | 06/08/2022 | 697.8 | 0 | 2023-10-05 |  | 46
2024 | Region VII | NEGROS ORIENTAL | CITY OF GUIHULNGAN (NEGROS ORIENTAL) | P00820201VS | Construction of Flood Mitigation Structure | 123.2593 | 10.0858 | 14700000 | 14700000 | 2024 | EJJ CONSTRUCTION AND SUPPLY | 6377 | 2024 | 2024-06-03 | 02/07/2024 | 0 | 0 | 2024-08-04 | 62
2022 | Region VII | NEGROS ORIENTAL | CITY OF GUIHULNGAN (NEGROS ORIENTAL) | P00620142VS | Construction of Flood Mitigation Structure | 123.2594 | 10.0858 | 14700000 | 14700000 | 2022 | ALOJA BUILDERS AND REALTY | 6378 | 2022 | 2022-07-25 | 02/08/2022 | 0 | 0 | 2022-07-24 |  | 1
2022 | Region VI | ILOILO | CITY OF PASSI (ILOILO) | P00620436VS | Construction of Flood Mitigation Structure | 122.6424 | 11.1003 | 19600000 | 19587821.47 | 2023 | STRONGLANE BUILDERS AND TRADING CORPORATION (FORMERLY: STRONGLANE CONSTRUCTION & TRADING) | 6379 | 2022 | 2023-07-03 | 03/29/2022 | 12178.53 | 0 | 2022-09-04 |  | 302
2023 | Region VI | NEGROS OCCIDENTAL | CADIZ CITY (NEGROS OCCIDENTAL) | P00732017VS | Construction of Flood Mitigation Structure | 123.2606 | 10.9439 | 4949962.61 | 4947393 | 2023 | ROCK-WILLIAN CONSTRUCTION AND SUPPLY | 6380 | 2023 | 2023-04-24 | 02/13/2023 | 2569.61 | 0 | 2023-04-30 | 6
2023 | Region VI | ILOILO | CITY OF PASSI (ILOILO) | P00721747VS | Construction of Flood Mitigation Structure | 122.6435 | 11.0771 | 77200000 | 74115163.12 | 2024 | F. GURREA CONSTRUCTION, INCORPORATED | 6381 | 2023 | 2024-10-07 | 02/27/2023 | 3084836.88 | 0 | 2023-11-20 |  | 322
2021 | Region VII | NEGROS ORIENTAL |  | P00549978VS | Construction of Flood Mitigation Structure | 123.2619 | 9.3258 | 49000000 | 49000000 | 2022 | PHILSOUTH BUILDERS INC (FORMERLY:PHILSOUTH BUILDERS) | 6382 | 2021 | 2022-08-20 | 10/15/2021 | 0 | 0 | 2022-08-19 |  | 1
2022 | Region IV-B | ROMBLON | SAN FERNANDO (ROMBLON) | P00641827LZ | Construction of Flood Mitigation Structure | 122.4847 | 12.3914 | 24499999.5 | 24496124.69 | 2022 | MT. GUITING-GUITING CONSTRUCTION | 6383 | 2022 | 2022-08-15 | 04/11/2022 | 3874.81 | 0 | 2022-10-29 | 75
2024 | Region VI | NEGROS OCCIDENTAL | CITY OF TALISAY (NEGROS OCCIDENTAL) | P00834998VS | Construction of Flood Mitigation Structure | 122.9673 | 10.7344 | 4949995.49 | 4947449.14 | 2024 | SL & G CONSTRUCTION | 6384 | 2024 | 2024-06-04 | 03/13/2024 | 2546.35 | 0 | 2024-06-03 |  | 1
2022 | Region VI | NEGROS OCCIDENTAL | LA CASTELLANA (NEGROS OCCIDENTAL) | P00620406VS | Construction of Slope Protection Structure | 123.0213 | 10.3353 | 96500000 | 96500000 | 2023 | JAIME B. CHING ENTERPRISES | 6385 | 2022 | 2023-01-18 | 05/19/2022 | 0 | 0 | 2023-01-18 | 0
2023 | Region VI | ILOILO | TIGBAUAN (ILOILO) | P00733716VS | Construction of Flood Mitigation Structure | 122.3164 | 10.6762 | 4950000 | 4939933.07 | 2023 | ABRIGHT BUILDERS CORPORATION | 6386 | 2023 | 2023-07-09 | 05/04/2023 | 10066.93 | 0 | 2023-07-08 |  | 1
2022 | Region VI | AKLAN | BATAN (AKLAN) | P00620012VS | Construction of Revetment | 122.4855 | 11.5985 | 57900000 | 56814451.8 | 2023 | F. GURREA CONSTRUCTION, INCORPORATED | 6387 | 2022 | 2023-05-08 | 03/15/2022 | 1085548.2 | 0 | 2022-11-22 |  | 167
2023 | Region V | CAMARINES SUR | LIBMANAN (CAMARINES SUR) | P00726963LZ | Construction of Flood Mitigation Structure | 123.0221 | 13.7039 | 72375000 | 72375000 | 2023 | BICOL GOLDROCK CONSTRUCTION CORPORATION | 6388 | 2023 | 2023-11-15 | 04/17/2023 | 0 | 0 | 2024-02-22 | 99
2022 | Region V | CAMARINES NORTE | DAET (CAPITAL) (CAMARINES NORTE) | P00632952LZ | Construction of Flood Mitigation Structure | 122.968 | 14.1013 | 19799782.94 | 19799782.74 | 2022 | 128 DRAGON CONSTRUCTION AND SUPPLIES | 6389 | 2022 | 2022-09-10 | 03/21/2022 | 0.2 | 0 | 2022-09-09 |  | 1
2023 | Region VI | ILOILO | SAN ENRIQUE (ILOILO) | P00733232VS | Construction of Slope Protection Structure | 122.6473 | 11.0972 | 94087500 | 94086501.57 | 2024 | STRONGLANE BUILDERS AND TRADING CORPORATION (FORMERLY: STRONGLANE CONSTRUCTION & TRADING) | 6390 | 2023 | 2024-05-03 | 04/26/2023 | 998.43 | 0 | 2024-05-02 |  | 1
2022 | Region VII | NEGROS ORIENTAL | SIBULAN (NEGROS ORIENTAL) | P00632033VS | Construction of Flood Mitigation Structure | 123.2628 | 9.3789 | 4950000 | 4950000 | 2022 | LEGACY CONSTRUCTION CORPORATION (FORMERLY: LEGACY CONSTRUCTION) | 6391 | 2022 | 2022-10-29 | 07/04/2022 | 0 | 0 | 2022-10-28 |  | 1
2022 | Region VI | NEGROS OCCIDENTAL | SAN CARLOS CITY (NEGROS OCCIDENTAL) | P00620250VS | Construction of Flood Mitigation Structure | 123.3379 | 10.3878 | 33775000 | 33775000 | 2023 | JAIME B. CHING ENTERPRISES | 6392 | 2022 | 2023-02-04 | 03/29/2022 | 0 | 0 | 2023-02-03 |  | 1
2022 | Region VI | AKLAN | ALTAVAS (AKLAN) | P00620072VS | Construction of Revetment | 122.4857 | 11.535 | 48250000 | 48249783.09 | 2023 | TIBIAO-ANTIQUE N.K. ENTERPRISE, INC. | 6393 | 2022 | 2023-08-24 | 05/25/2022 | 216.91 | 0 | 2023-08-23 |  | 1
2023 | Region VI | NEGROS OCCIDENTAL | BACOLOD CITY (CAPITAL) (NEGROS OCCIDENTAL) | P00721489VS | Construction of Revetment | 122.922 | 10.1053 | 96500000 | 96500000 | 2024 | SUPREME ABF CONST. & CONST. SUPPLY COMPANY INC. | 6394 | 2023 | 2024-08-12 | 02/08/2023 | 0 | 0 | 2024-06-24 |  | 49
2024 | Region VII | CEBU | MALABUYOC (CEBU) | P00820859VS | Construction of Flood Mitigation Structure | 123.3385 | 9.6853 | 96496418.22 | 96495968.22 | 2024 | JTC CRUZ CONSTRUCTION CO., INC. | 6395 | 2024 | 2024-10-11 | 03/18/2024 | 450 | 0 | 2025-01-17 | 98
2023 | Region V | CAMARINES SUR | LIBMANAN (CAMARINES SUR) | P00726957LZ | Construction of Flood Mitigation Structure | 123.0225 | 13.6958 | 72375000 | 72334499.77 | 2023 | NFH CONSTRUCTION & SUPPLY | 6396 | 2023 | 2023-12-15 | 04/05/2023 | 40500.23 | 0 | 2024-02-10 | 57
2023 | Region V | CAMARINES NORTE | LABO (CAMARINES NORTE) | P00742209LZ | Construction of Flood Mitigation Structure | 122.4915 | 14.1875 | 98999963.19 | 98999963.19 | 2024 | EUS CONSTRUCTION | 6397 | 2023 | 2024-03-06 | 06/05/2023 | 0 | 0 | 2024-03-05 |  | 1
2023 | Region V | CAMARINES NORTE | DAET (CAPITAL) (CAMARINES NORTE) | P00736122LZ | Construction of Flood Mitigation Structure | 122.9224 | 14.1035 | 96499899.68 | 96499883.32 | 2023 | EUS CONSTRUCTION | 6398 | 2023 | 2023-12-18 | 07/04/2023 | 16.36 | 0 | 2024-04-11 | 115
2022 | Region VII | CEBU | ALEGRIA (CEBU) | P00620455VS | Construction of Flood Mitigation Structure | 123.3386 | 9.7184 | 48999996.9 | 48999996.9 | 2022 | QM BUILDERS | 6399 | 2022 | 2022-12-17 | 03/23/2022 | 0 | 0 | 2022-12-16 |  | 1
2023 | Region VII | NEGROS ORIENTAL | CITY OF GUIHULNGAN (NEGROS ORIENTAL) | P00721840VS | Construction of Flood Mitigation Structure | 123.2629 | 10.1276 | 49000000 | 49000000 | 2023 | JAIME B. CHING ENTERPRISES | 6400 | 2023 | 2023-09-21 | 02/07/2023 | 0 | 0 | 2023-09-20 |  | 1
2022 | Region VI | CAPIZ | DUMALAG (CAPIZ) | P00630183VS | Construction of Flood Mitigation Structure | 122.648 | 11.3162 | 53073080.5 | 53072959.65 | 2024 | PANAY EAST COAST CONSTRUCTION & SUPPLY | 6401 | 2022 | 2024-02-09 | 04/06/2022 | 120.85 | 0 | 2023-12-01 |  | 70
2022 | Region VI | NEGROS OCCIDENTAL | ISABELA (NEGROS OCCIDENTAL) | P00630643VS | Construction of Drainage Structure | 123.0234 | 10.2892 | 19800000 | 19799998.39 | 2022 | LEGACY CONSTRUCTION CORPORATION (FORMERLY: LEGACY CONSTRUCTION) | 6402 | 2022 | 2022-08-15 | 03/28/2022 | 1.61 | 0 | 2022-09-13 | 29
2023 | Region V | CAMARINES SUR | LUPI (CAMARINES SUR) | P00736093LZ | Construction of Flood Mitigation Structure | 122.9228 | 13.9222 | 82024109.98 | 82024108.85 | 2023 | MGT BUILDER'S & SUPPLY / R.K.X. ODIAMAR CONSTRUCTION | 6403 | 2023 | 2023-11-10 | 03/31/2023 | 1.13 | 0 | 2023-11-16 | 6
2023 | Region V | CAMARINES NORTE | SANTA ELENA (CAMARINES NORTE) | P00737558LZ | Construction of Flood Mitigation Structure | 122.3166 | 14.0855 | 4949559.66 | 4885102.75 | 2023 | GREAT WALL ENGINEERING | 6404 | 2023 | 2023-05-22 | 04/05/2023 | 64456.91 | 0 | 2023-05-21 |  | 1
2022 | Region VI | NEGROS OCCIDENTAL | BACOLOD CITY (CAPITAL) (NEGROS OCCIDENTAL) | P00620015VS | Construction of Revetment | 122.9684 | 10.6892 | 69163480 | 69163480 | 2023 | LEGACY CONSTRUCTION CORPORATION (FORMERLY: LEGACY CONSTRUCTION) | 6405 | 2022 | 2023-01-30 | 02/23/2022 | 0 | 0 | 2023-01-07 |  | 23
2022 | Region IV-B | ROMBLON | MAGDIWANG (ROMBLON) | P00620674LZ | Construction of Flood Mitigation Structure | 122.4917 | 12.47 | 47529999.98 | 47529824.24 | 2023 | E.R. DELA CRUZ CONSTRUCTION & SUPPLY | 6406 | 2022 | 2023-04-22 | 03/01/2022 | 175.74 | 0 | 2023-03-15 |  | 38
2022 | Region V | CAMARINES SUR | LIBMANAN (CAMARINES SUR) | P00620708LZ | Construction of Dike | 123.0268 | 13.6841 | 49000000 | 48015893 | 2022 | NFH CONSTRUCTION & SUPPLY | 6407 | 2022 | 2022-10-06 | 03/16/2022 | 984107 | 0 | 2022-10-05 |  | 1
2022 | Region VI | NEGROS OCCIDENTAL | BACOLOD CITY (CAPITAL) (NEGROS OCCIDENTAL) | P00620424VS | Construction of Revetment | 122.9229 | 10.6025 | 49000000 | 49000000 | 2023 | A.C. RIVERO DEVELOPMENT CORPORATION | 6408 | 2022 | 2023-02-26 | 03/25/2022 | 0 | 0 | 2023-01-17 |  | 40
2023 | Region VI | AKLAN | NEW WASHINGTON (AKLAN) | P00721481VS | Rehabilitation / Major Repair of Flood Control Structure | 122.493 | 11.6087 | 72742665 | 72742653.95 | 2024 | ST. TIMOTHY CONSTRUCTION CORPORATION | 6409 | 2023 | 2024-03-02 | 04/13/2023 | 11.05 | 0 | 2024-03-01 |  | 1
2022 | Region VI | CAPIZ | DUMALAG (CAPIZ) | P00620461VS | Construction of Flood Mitigation Structure | 122.6483 | 11.3166 | 44099462.11 | 44099458.65 | 2023 | WOODLAND CONSTRUCTION & SUPPLY, INC. | 6410 | 2022 | 2023-09-22 | 04/06/2022 | 3.46 | 0 | 2023-09-24 | 2
2022 | Region V | CAMARINES SUR | BULA (CAMARINES SUR) | P00631430LZ | Construction of Flood Mitigation Structure | 123.2638 | 13.4586 | 49000000 | 47285080 | 2022 | RAMARPLUS INCORPORATED (FORMERLY RAMAR ENTERPRISES | 6411 | 2022 | 2022-07-28 | 02/22/2022 | 1714920 | 0 | 2022-09-08 | 42
2022 | Region VI | ILOILO | TUBUNGAN (ILOILO) | P00620087VS | Construction of Flood Mitigation Structure | 122.317 | 10.7669 | 9800000 | 9702608.69 | 2022 | A.D. PENDON CONSTRUCTION & SUPPLY, INC. (FORMERLY: ADP CONSTRUCTION & SUPPLY) | 6412 | 2022 | 2022-08-10 | 02/10/2022 | 97391.31 | 0 | 2022-06-30 |  | 41
2023 | Region VI | NEGROS OCCIDENTAL | BACOLOD CITY (CAPITAL) (NEGROS OCCIDENTAL) | P00721926VS | Construction of Revetment | 122.9687 | 10.6558 | 49000000 | 49000000 | 2024 | M.K.U. CONSTRUCTION AND SUPPLY | 6413 | 2023 | 2024-04-03 | 03/03/2023 | 0 | 0 | 2023-10-28 |  | 158
2022 | Region VII | CEBU | ALEGRIA (CEBU) | P00620458VS | Construction of Flood Mitigation Structure | 123.3386 | 9.7178 | 48999923.86 | 48999923.86 | 2022 | QM BUILDERS | 6414 | 2022 | 2022-12-17 | 03/23/2022 | 0 | 0 | 2022-12-16 |  | 1
2023 | Region VI | NEGROS OCCIDENTAL | BINALBAGAN (NEGROS OCCIDENTAL) | P00733691VS | Construction of Slope Protection Structure | 122.9246 | 10.2076 | 99000000 | 99000000 | 2024 | LEGACY CONSTRUCTION CORPORATION (FORMERLY: LEGACY CONSTRUCTION) | 6415 | 2023 | 2024-02-14 | 04/12/2023 | 0 | 0 | 2024-02-13 |  | 1
2024 | Region VII | NEGROS ORIENTAL | SIATON (NEGROS ORIENTAL) | P00820409VS | Rehabilitation / Major Repair of Flood Control Structure | 123.0272 | 9.0917 | 45080000 | 45080000 | 2024 | AMETHYST HORIZON BUILDERS AND GEN. CONTRACTOR AND DEVELOPMENT CORP. | 6416 | 2024 | 2024-07-16 | 02/20/2024 | 0 | 0 | 2024-09-10 | 56
2022 | Region VI | ILOILO | DUMANGAS (ILOILO) | P00620246VS | Construction of Flood Mitigation Structure | 122.6495 | 10.8138 | 19600000 | 19036065.74 | 2022 | TIB TIMCO INFRA BUILDERS | 6417 | 2022 | 2022-08-05 | 02/23/2022 | 563934.26 | 0 | 2022-08-04 |  | 1
2022 | Region VII | CEBU | ALEGRIA (CEBU) | P00620454VS | Construction of Flood Mitigation Structure | 123.3387 | 9.7176 | 48999811.45 | 48999811.45 | 2022 | QM BUILDERS | 6418 | 2022 | 2022-12-17 | 03/23/2022 | 0 | 0 | 2022-12-16 |  | 1
2021 | Region VI | AKLAN |  | P00521794VS | Construction of Flood Mitigation Structure | 122.3177 | 11.6517 | 98000000 | 93520048.17 | 2022 | A.D. PENDON CONSTRUCTION & SUPPLY, INC. (FORMERLY: ADP CONSTRUCTION & SUPPLY) | 6419 | 2021 | 2022-07-13 | 04/15/2021 | 4479951.83 | 0 | 2022-02-23 |  | 140
2023 | Region VII | NEGROS ORIENTAL | SIATON (NEGROS ORIENTAL) | P00721851VS | Construction of Flood Mitigation Structure | 122.925 | 9.12 | 49000000 | 49000000 | 2023 | HOMEWORLD CONSTRUCTION CORP. (FORMERLY HOMEWORLD E | 6420 | 2023 | 2023-12-03 | 03/09/2023 | 0 | 0 | 2023-10-23 |  | 41
2022 | Region V | CAMARINES SUR | BULA (CAMARINES SUR) | P00631431LZ | Construction of Flood Mitigation Structure | 123.2641 | 13.4588 | 49000000 | 47285313.97 | 2022 | RICHMAR CONSTRUCTION | 6421 | 2022 | 2022-07-28 | 02/22/2022 | 1714686.03 | 0 | 2022-09-08 | 42
2023 | Region VII | NEGROS ORIENTAL | SIATON (NEGROS ORIENTAL) | P00721852VS | Rehabilitation / Major Repair of Flood Control Structure | 123.0289 | 9.0925 | 44100000 | 44100000 | 2023 | JANUARY BUILDERS | 6422 | 2023 | 2023-09-05 | 03/06/2023 | 0 | 0 | 2023-11-04 | 60
2024 | Region V | CAMARINES NORTE | BASUD (CAMARINES NORTE) | P00820438LZ | Construction of Flood Mitigation Structure | 122.969 | 14.0582 | 86849994.71 | 86849923.14 | 2024 | 128 DRAGON CONSTRUCTION AND SUPPLIES | 6423 | 2024 | 2024-12-09 | 03/25/2024 | 71.57 | 0 | 2024-12-08 |  | 1
2023 | Region VI | ILOILO | DUMANGAS (ILOILO) | P00721812VS | Construction of Flood Mitigation Structure | 122.6508 | 10.8476 | 19600000 | 19490000 | 2023 | PESOM CONSTRUCTION SERVICES (FORMERLY: PESOM BUILDERS AND CONSTRUCTION SUPPLY) | 6424 | 2023 | 2023-10-02 | 02/13/2023 | 110000 | 0 | 2023-07-25 |  | 69
2022 | Region IV-B | ROMBLON | MAGDIWANG (ROMBLON) | P00620673LZ | Construction of Flood Mitigation Structure | 122.4989 | 12.4778 | 46549999.61 | 45829108.83 | 2022 | R.G. FLORENTINO CONST. & TRADING INC. | 6425 | 2022 | 2022-10-10 | 04/13/2022 | 720890.78 | 0 | 2022-12-04 | 55
2023 | Region VII | CEBU | ALEGRIA (CEBU) | P00721947VS | Construction of Revetment | 123.339 | 9.729 | 48895927.07 | 48895926.27 | 2023 | QM BUILDERS | 6426 | 2023 | 2023-10-11 | 03/06/2023 | 0.8 | 0 | 2023-10-10 |  | 1
2024 | Region VI | NEGROS OCCIDENTAL | BINALBAGAN (NEGROS OCCIDENTAL) | P00820269VS | Construction of Slope Protection Structure | 122.9257 | 10.2023 | 88258900 | 88258900 | 2024 | C'ZARLES CONSTRUCTION & SUPPLY / JVC TOUGH CORE CONSTRUCTION & BUILDERS CORP. | 6427 | 2024 | 2024-08-31 | 02/13/2024 | 0 | 0 | 2024-10-03 | 33
2022 | Region VI | NEGROS OCCIDENTAL | CITY OF TALISAY (NEGROS OCCIDENTAL) | P00630633VS | Construction of Drainage Structure | 122.9694 | 10.7367 | 4949996.82 | 4947860 | 2022 | REDSON CONSTRUCTION AND SUPPLIES, INC. (FORMERLY: REDSON CONSTRUCTION AND SUPPLIES) | 6428 | 2022 | 2022-07-12 | 03/30/2022 | 2136.82 | 0 | 2022-07-11 |  | 1
2022 | Region V | CAMARINES SUR | PILI (CAPITAL) (CAMARINES SUR) | P00632964LZ | Construction of Flood Mitigation Structure | 123.2644 | 13.5775 | 4949999.27 | 4945912.3 | 2022 | DELPAR CONSTRUCTION & SUPPLIES | 6429 | 2022 | 2022-11-16 | 05/26/2022 | 4086.97 | 0 | 2022-11-15 |  | 1
2024 | Region VI | ILOILO | DUMANGAS (ILOILO) | P00820391VS | Construction of Flood Mitigation Structure | 122.6509 | 10.8475 | 49000000 | 48885166.99 | 2024 | MJ BARCELONA CONSTRUCTION AND SUPPLY / STEVEN CONSTRUCTION & SUPPLY | 6430 | 2024 | 2024-08-07 | 02/12/2024 | 114833.01 | 0 | 2024-08-15 | 8
2022 | Region VII | NEGROS ORIENTAL | SIATON (NEGROS ORIENTAL) | P00633023VS | Construction of Flood Mitigation Structure | 122.9258 | 9.12 | 49000000 | 49000000 | 2022 | LEGACY CONSTRUCTION CORPORATION (FORMERLY: LEGACY CONSTRUCTION) / MIGHTY HOK SUMMIT CONSTRUCTION & DEVELOPMENT CORP. | 6431 | 2022 | 2022-11-06 | 04/18/2022 | 0 | 0 | 2022-12-16 | 40
2023 | Region VI | ILOILO | GUIMBAL (ILOILO) | P00733718VS | Construction of Flood Mitigation Structure | 122.318 | 10.657 | 19800000 | 19335253.9 | 2024 | CONTE BUILDERS & CONSTRUCTION SUPPLY | 6432 | 2023 | 2024-01-05 | 05/15/2023 | 464746.1 | 0 | 2023-12-11 |  | 25
2022 | Region IV-B | ROMBLON | SAN FERNANDO (ROMBLON) | P00641899LZ | Construction of Flood Mitigation Structure | 122.5024 | 12.38 | 72374934.61 | 74202417.84 | 2023 | LEGACY CONSTRUCTION CORPORATION (FORMERLY: LEGACY CONSTRUCTION) | 6433 | 2022 | 2023-07-14 | 09/13/2022 | 0 | 1827483.23 | 2023-06-08 |  | 36
2024 | Region VII | CEBU | MALABUYOC (CEBU) | P00835012VS | Construction of Flood Mitigation Structure | 123.339 | 9.6851 | 148495665.1 | 148495065.1 | 2024 | NEWBIG FOUR J CONSTRUCTION INC., (FORMERLY FOUR J | 6434 | 2024 | 2024-08-14 | 03/12/2024 | 600 | 0 | 2025-02-03 | 173
2023 | Region V | CAMARINES SUR | LUPI (CAMARINES SUR) | P00736091LZ | Construction of Flood Mitigation Structure | 122.9262 | 13.7846 | 82024521.89 | 80966304.71 | 2024 | MGT BUILDER'S & SUPPLY / R.K.X. ODIAMAR CONSTRUCTION | 6435 | 2023 | 2024-01-08 | 03/31/2023 | 1058217.18 | 0 | 2024-01-07 |  | 1
2023 | Region IX | ZAMBOANGA SIBUGAY | DIPLAHAN (ZAMBOANGA SIBUGAY) | P00721658MN | Construction of Flood Mitigation Structure | 122.9698 | 7.7476 | 49000000 | 48939769.73 | 2024 | GENETIAN BUILDERS AND ENTERPRISES INCORPORATED (FORMERLY: GENETIAN BUILDERS) | 6436 | 2023 | 2024-02-23 | 03/28/2023 | 60230.27 | 0 | 2024-01-08 |  | 46
2022 | Region VI | NEGROS OCCIDENTAL | LA CASTELLANA (NEGROS OCCIDENTAL) | P00620439VS | Construction of Slope Protection Structure | 123.0307 | 10.3385 | 96500000 | 96499993.8 | 2023 | LEGACY CONSTRUCTION CORPORATION (FORMERLY: LEGACY CONSTRUCTION) | 6437 | 2022 | 2023-04-01 | 05/19/2022 | 6.2 | 0 | 2023-03-31 |  | 1
2022 | Region VII | NEGROS ORIENTAL | CITY OF GUIHULNGAN (NEGROS ORIENTAL) | P00620144VS | Construction of Flood Mitigation Structure | 123.2657 | 10.1009 | 29400000 | 29400000 | 2022 | MIGHTY HOK SUMMIT CONSTRUCTION & DEVELOPMENT CORP. | 6438 | 2022 | 2022-10-17 | 02/08/2022 | 0 | 0 | 2022-10-16 |  | 1
2024 | Region VI | ILOILO | DUMANGAS (ILOILO) | P00834560VS | Construction of Revetment | 122.6538 | 10.8426 | 77200000 | 76431495.76 | 2025 | WOODLAND CONSTRUCTION & SUPPLY, INC. / MRZA CONSTRUCTION CORPORATION | 6439 | 2024 | 2025-02-24 | 03/08/2024 | 768504.24 | 0 | 2024-10-12 |  | 135
2023 | Region VI | ILOILO | GUIMBAL (ILOILO) | P00721866VS | Construction of Flood Mitigation Structure | 122.3181 | 10.7261 | 62725000 | 62081979.88 | 2024 | TOPMOST DEVELOPMENT & MKTG. CORP. | 6440 | 2023 | 2024-04-25 | 05/30/2023 | 643020.12 | 0 | 2024-02-11 |  | 74
2022 | Region VI | NEGROS OCCIDENTAL | CITY OF SIPALAY (NEGROS OCCIDENTAL) | P00620306VS | Construction of Flood Mitigation Structure | 122.5039 | 9.7481 | 34300000 | 33753548.3 | 2022 | JAIME B. CHING ENTERPRISES | 6441 | 2022 | 2022-09-21 | 02/17/2022 | 546451.7 | 0 | 2022-10-26 | 35
2023 | Region V | CAMARINES NORTE | LABO (CAMARINES NORTE) | P00742475LZ | Construction of Flood Mitigation Structure | 122.5077 | 14.184 | 29699257.64 | 29699257.64 | 2024 | EUS CONSTRUCTION | 6442 | 2023 | 2024-03-11 | 08/09/2023 | 0 | 0 | 2024-03-26 | 15
2022 | Region IX | ZAMBOANGA SIBUGAY | IMELDA (ZAMBOANGA SIBUGAY) | P00620208MN | Construction of Flood Mitigation Structure | 122.9262 | 7.6457 | 101325000 | 101324314 | 2023 | ALPHA & OMEGA GEN. CONTRACTOR & DEVELOPMENT CORP. | 6443 | 2022 | 2023-07-04 | 02/22/2022 | 686 | 0 | 2023-07-03 |  | 1
2022 | Region VI | NEGROS OCCIDENTAL | BACOLOD CITY (CAPITAL) (NEGROS OCCIDENTAL) | P00620420VS | Construction of Drainage Structure | 122.97 | 10.7016 | 72949175 | 72949175 | 2024 | WILKINSON CONSTRUCTION | 6444 | 2022 | 2024-06-27 | 03/25/2022 | 0 | 0 | 2022-12-27 |  | 548
2022 | Region VI | NEGROS OCCIDENTAL | LA CASTELLANA (NEGROS OCCIDENTAL) | P00620440VS | Construction of Slope Protection Structure | 123.0308 | 10.3386 | 96500000 | 96499992.77 | 2023 | LEGACY CONSTRUCTION CORPORATION (FORMERLY: LEGACY CONSTRUCTION) | 6445 | 2022 | 2023-03-29 | 05/19/2022 | 7.23 | 0 | 2023-03-28 |  | 1
2023 | Region VII | NEGROS ORIENTAL | DUMAGUETE CITY (CAPITAL) (NEGROS ORIENTAL) | P00733748VS | Construction of Flood Mitigation Structure | 123.2661 | 9.3089 | 29700000 | 29700000 | 2023 | UY CONDEV CORPORATION (FORMERLY:UY CONSTRUCTION & | 6446 | 2023 | 2023-10-06 | 05/05/2023 | 0 | 0 | 2023-11-23 | 48
2023 | Region VI | ILOILO | POTOTAN (ILOILO) | P00721810VS | Construction of Flood Mitigation Structure | 122.6542 | 10.8523 | 49000000 | 48506217.66 | 2024 | WOODLAND CONSTRUCTION & SUPPLY, INC. | 6447 | 2023 | 2024-03-04 | 02/23/2023 | 493782.34 | 0 | 2023-11-08 |  | 117
2023 | Region IV-A | QUEZON | CATANAUAN (QUEZON) | P00726588LZ | Construction of Flood Mitigation Structure | 122.3186 | 13.606 | 67549419.49 | 67550000 | 2024 | R.A. MENDIOLA CONSTRUCTION & DEVELOPER | 6448 | 2023 | 2024-06-02 | 03/06/2023 | 0 | 580.51 | 2024-06-01 |  | 1
2022 | Region VI | AKLAN | BATAN (AKLAN) | P00620287VS | Construction of Dike | 122.5077 | 11.5919 | 48250000 | 40426458.54 | 2023 | TIBIAO-ANTIQUE N.K. ENTERPRISE, INC. | 6449 | 2022 | 2023-05-30 | 03/29/2022 | 7823541.46 | 0 | 2023-07-14 | 45
2021 | Region VI | NEGROS OCCIDENTAL |  | P00521589VS | Construction of Revetment | 122.97 | 10.6514 | 34300000 | 31936464.9 | 2023 | SUPREME ABF CONST. & CONST. SUPPLY COMPANY INC. | 6450 | 2021 | 2023-09-25 | 10/07/2021 | 2363535.1 | 0 | 2022-09-15 |  | 375
2023 | Region VI | NEGROS OCCIDENTAL | LA CARLOTA CITY (NEGROS OCCIDENTAL) | P00721504VS | Construction of Flood Mitigation Structure | 122.9263 | 10.4207 | 81059992.57 | 81058217.84 | 2024 | JAIME B. CHING ENTERPRISES | 6451 | 2023 | 2024-01-29 | 04/11/2023 | 1774.73 | 0 | 2024-01-28 |  | 1
2023 | Region V | CAMARINES SUR | BULA (CAMARINES SUR) | P00736117LZ | Construction of Flood Mitigation Structure | 123.2675 | 13.4586 | 96456652.25 | 96456652.25 | 2023 | RAPIDWORKZ CONSTRUCTION & SUPPLY / STEVEN CONSTRUCTION & SUPPLY | 6452 | 2023 | 2023-07-24 | 02/17/2023 | 0 | 0 | 2023-12-07 | 136
2024 | Region VI | ILOILO | POTOTAN (ILOILO) | P00820393VS | Construction of Flood Mitigation Structure | 122.6542 | 10.8524 | 34300000 | 34169585.46 | 2024 | A.D. PENDON CONSTRUCTION & SUPPLY, INC. (FORMERLY: ADP CONSTRUCTION & SUPPLY) | 6453 | 2024 | 2024-08-11 | 02/12/2024 | 130414.54 | 0 | 2024-08-09 |  | 2
2022 | Region IV-A | QUEZON | CATANAUAN (QUEZON) | P00620861LZ | Construction of Flood Mitigation Structure | 122.3189 | 13.6055 | 68997339.85 | 68997500 | 2023 | RAPID FOREMOST CONST. CO. / JELCON-CONSTRUCTION AND TRADING CORPORATION | 6454 | 2022 | 2023-02-10 | 02/16/2022 | 0 | 160.15 | 2023-02-09 |  | 1
2024 | Region V | CAMARINES SUR | LUPI (CAMARINES SUR) | P00821409LZ | Construction of Flood Mitigation Structure | 122.9266 | 13.7831 | 67549956.03 | 67549956.01 | 2024 | BICOL GOLDROCK CONSTRUCTION CORPORATION | 6455 | 2024 | 2024-06-25 | 02/16/2024 | 0.02 | 0 | 2024-11-03 | 131
2024 | Region VII | CEBU | MALABUYOC (CEBU) | P00834571VS | Construction of Flood Mitigation Structure | 123.339 | 9.6851 | 57895364.01 | 57895064.01 | 2024 | JTC CRUZ CONSTRUCTION CO., INC. | 6456 | 2024 | 2024-08-14 | 04/01/2024 | 300 | 0 | 2024-11-18 | 96
2023 | Region VI | NEGROS OCCIDENTAL | CITY OF TALISAY (NEGROS OCCIDENTAL) | P00732020VS | Construction of Flood Mitigation Structure | 122.9701 | 10.7386 | 5444918.82 | 5443341.3 | 2023 | REDSON CONSTRUCTION AND SUPPLIES, INC. (FORMERLY: REDSON CONSTRUCTION AND SUPPLIES) | 6457 | 2023 | 2023-05-01 | 02/13/2023 | 1577.52 | 0 | 2023-04-30 |  | 1
2023 | Region V | CAMARINES SUR | BULA (CAMARINES SUR) | P00736115LZ | Construction of Flood Mitigation Structure | 123.2681 | 13.4603 | 67539164 | 67539164 | 2023 | MUNTOPAR BUILDERS CORP. | 6458 | 2023 | 2023-08-18 | 02/17/2023 | 0 | 0 | 2023-10-16 | 59
2024 | Region VI | NEGROS OCCIDENTAL | BINALBAGAN (NEGROS OCCIDENTAL) | P00820003VS | Construction of Slope Protection Structure | 122.9268 | 10.2036 | 67550000 | 67549997.3 | 2024 | KENNETH CONSTRUCTION AND GENERAL MERCHANDISE | 6459 | 2024 | 2024-08-09 | 02/13/2024 | 2.7 | 0 | 2024-10-11 | 63
2022 | Region VI | CAPIZ | JAMINDAN (CAPIZ) | P00620301VS | Construction of Flood Mitigation Structure | 122.5117 | 11.4068 | 42630000 | 42629655.34 | 2023 | A.D. PENDON CONSTRUCTION & SUPPLY, INC. (FORMERLY: ADP CONSTRUCTION & SUPPLY) | 6460 | 2022 | 2023-12-22 | 02/15/2022 | 344.66 | 0 | 2023-08-22 |  | 122
2023 | Region VI | NEGROS OCCIDENTAL | ISABELA (NEGROS OCCIDENTAL) | P00733732VS | Construction of Slope Protection Structure | 123.031 | 10.2478 | 49500000 | 49500000 | 2023 | KENNETH CONSTRUCTION AND GENERAL MERCHANDISE | 6461 | 2023 | 2023-12-04 | 03/23/2023 | 0 | 0 | 2023-12-03 |  | 1
2024 | Region VI | ILOILO | SANTA BARBARA (ILOILO) | P00821138VS | Construction of Flood Mitigation Structure | 122.5136 | 10.7788 | 72375000 | 72373092.54 | 2024 | MONOLITHIC CONSTRUCTION & CONCRETE PRODUCTS, INC. | 6462 | 2024 | 2024-12-13 | 03/12/2024 | 1907.46 | 0 | 2024-12-23 | 10
2022 | Region VII | CEBU | ALEGRIA (CEBU) | P00620019VS | Construction of Flood Mitigation Structure | 123.3391 | 9.7279 | 86844519.15 | 86844519.15 | 2022 | QM BUILDERS | 6463 | 2022 | 2022-10-03 | 02/21/2022 | 0 | 0 | 2022-10-02 |  | 1
2024 | Region VI | ILOILO | SAN ENRIQUE (ILOILO) | P00821142VS | Construction of Flood Mitigation Structure | 122.6564 | 11.0685 | 96500000 | 96499845.49 | 2024 | STRONGLANE BUILDERS AND TRADING CORPORATION (FORMERLY: STRONGLANE CONSTRUCTION & TRADING) | 6464 | 2024 | 2024-12-01 | 03/27/2024 | 154.51 | 0 | 2024-10-28 |  | 34
2023 | Region IV-A | QUEZON | CATANAUAN (QUEZON) | P00726587LZ | Construction of Flood Mitigation Structure | 122.3211 | 13.6058 | 77199944.15 | 77200000 | 2024 | R.A. MENDIOLA CONSTRUCTION & DEVELOPER | 6465 | 2023 | 2024-06-02 | 03/06/2023 | 0 | 55.85 | 2024-06-01 |  | 1
2024 | Region VI | NEGROS OCCIDENTAL | CITY OF TALISAY (NEGROS OCCIDENTAL) | P00832639VS | Construction of Flood Mitigation Structure | 122.9701 | 10.7483 | 9899996.76 | 9897916.56 | 2024 | CANLAON BUILDERS AND DEVELOPMENT CORPORATION | 6466 | 2024 | 2024-06-02 | 02/14/2024 | 2080.2 | 0 | 2024-06-01 |  | 1
2023 | Region V | CAMARINES SUR | BULA (CAMARINES SUR) | P00736119LZ | Construction of Flood Mitigation Structure | 123.2681 | 13.4603 | 96478328 | 96478328 | 2023 | HI-TONE CONSTRUCTION & DEVELOPMENT CORP. (FORMERLY | 6467 | 2023 | 2023-12-15 | 02/17/2023 | 0 | 0 | 2024-01-06 | 22
2023 | Region VI | NEGROS OCCIDENTAL | BACOLOD CITY (CAPITAL) (NEGROS OCCIDENTAL) | P00721636VS | Construction of Revetment | 122.9309 | 10.6374 | 39200000 | 39200000 | 2023 | M.K.U. CONSTRUCTION AND SUPPLY | 6468 | 2023 | 2023-10-09 | 02/08/2023 | 0 | 0 | 2023-09-08 |  | 31
2024 | Region VI | NEGROS OCCIDENTAL | ENRIQUE B. MAGALONA (SARAVIA) (NEGROS OCCIDENTAL) | P00834999VS | Construction of Flood Mitigation Structure | 123.0316 | 10.9025 | 49499996.88 | 49497759.51 | 2024 | LEGACY CONSTRUCTION CORPORATION (FORMERLY: LEGACY CONSTRUCTION) | 6469 | 2024 | 2024-10-13 | 03/13/2024 | 2237.37 | 0 | 2024-10-12 |  | 1
2023 | Region VII | NEGROS ORIENTAL | SIATON (NEGROS ORIENTAL) | P00721853VS | Construction of Flood Mitigation Structure | 123.0322 | 9.0544 | 49000000 | 49000000 | 2023 | JANUARY BUILDERS | 6470 | 2023 | 2023-09-22 | 03/06/2023 | 0 | 0 | 2023-10-28 | 36
2022 | Region VI | ILOILO | GUIMBAL (ILOILO) | P00620088VS | Construction of Flood Mitigation Structure | 122.3213 | 10.7321 | 4900000 | 4851531.95 | 2022 | PANAY EAST COAST CONSTRUCTION & SUPPLY | 6471 | 2022 | 2022-07-04 | 02/10/2022 | 48468.05 | 0 | 2022-05-07 |  | 58
2024 | Region IX | ZAMBOANGA DEL SUR | BAYOG (ZAMBOANGA DEL SUR) | P00821214MN | Construction of Flood Mitigation Structure | 123.0326 | 7.8578 | 39200000 | 39200000 | 2024 | BADSBRO CONSTRUCTION AND GENERAL MERCHANDISE | 6472 | 2024 | 2024-12-05 | 05/09/2024 | 0 | 0 | 2024-12-04 |  | 1
2023 | Region VII | CEBU | ALEGRIA (CEBU) | P00721897VS | Construction of Revetment | 123.3396 | 9.7236 | 96015752.6 | 96014645 | 2023 | QM BUILDERS | 6473 | 2023 | 2023-08-14 | 03/23/2023 | 1107.6 | 0 | 2024-01-29 | 168
2023 | Region IV-A | QUEZON | CATANAUAN (QUEZON) | P00742167LZ | Construction of Flood Mitigation Structure | 122.322 | 13.6052 | 72374756.44 | 74250000 | 2024 | LIBRIUS CONSTRUCTION & SUPPLY CORPORATION / JEMAK CONSTRUCTION & SUPPLY | 6474 | 2023 | 2024-06-14 | 09/08/2023 | 0 | 1875243.56 | 2024-06-14 | 0
2024 | Region VII | NEGROS ORIENTAL | SIATON (NEGROS ORIENTAL) | P00820407VS | Construction of Flood Mitigation Structure | 123.0327 | 9.0499 | 48368880 | 48368880 | 2024 | AMETHYST HORIZON BUILDERS AND GEN. CONTRACTOR AND DEVELOPMENT CORP. | 6475 | 2024 | 2024-08-07 | 03/11/2024 | 0 | 0 | 2024-09-30 | 54
2023 | Region VII | NEGROS ORIENTAL | SIBULAN (NEGROS ORIENTAL) | P00721842VS | Rehabilitation / Major Repair of Flood Control Structure | 123.2688 | 9.3365 | 49000000 | 49000000 | 2023 | PHILSOUTH BUILDERS INC (FORMERLY:PHILSOUTH BUILDERS) | 6476 | 2023 | 2023-09-20 | 02/06/2023 | 0 | 0 | 2023-10-13 | 23
2021 | Region V | CAMARINES NORTE |  | P00561417LZ | Construction of Drainage Structure | 122.9319 | 14.1062 | 14849998.78 | 14849998.78 | 2022 | ARIK CONSTRUCTION | 6477 | 2021 | 2022-12-23 | 03/17/2022 | 0 | 0 | 2022-12-22 |  | 1
2022 | Region VI | ILOILO | SANTA BARBARA (ILOILO) | P00620238VS | Construction of Flood Mitigation Structure | 122.5152 | 10.7767 | 91276455 | 91275340.05 | 2023 | F. GURREA CONSTRUCTION, INCORPORATED / GOLDEN ROADRUNNER INTERNATIONAL CORP. | 6478 | 2022 | 2023-04-19 | 02/21/2022 | 1114.95 | 0 | 2023-04-19 | 0
2024 | Region VI | ILOILO | POTOTAN (ILOILO) | P00820396VS | Construction of Flood Mitigation Structure | 122.6576 | 10.8441 | 34300000 | 33958511.47 | 2024 | J.S. LAYSON & CO. , INC. | 6479 | 2024 | 2024-09-01 | 03/08/2024 | 341488.53 | 0 | 2024-08-23 |  | 9
2023 | Region V | CAMARINES SUR | SIPOCOT (CAMARINES SUR) | P00740485LZ | Construction of Flood Mitigation Structure | 122.932 | 13.7819 | 82024908.85 | 82024902.06 | 2024 | HGG BUILDERS & SUPPLY | 6480 | 2023 | 2024-01-02 | 04/19/2023 | 6.79 | 0 | 2024-01-01 |  | 1
2023 | Region V | CAMARINES NORTE | DAET (CAPITAL) (CAMARINES NORTE) | P00737370LZ | Construction of Flood Mitigation Structure | 122.9713 | 14.0963 | 7919998.19 | 7674011.94 | 2023 | 128 DRAGON CONSTRUCTION AND SUPPLIES | 6481 | 2023 | 2023-10-03 | 07/07/2023 | 245986.25 | 0 | 2023-10-02 |  | 1
2023 | Region VII | CEBU | ALEGRIA (CEBU) | P00721948VS | Construction of Revetment | 123.3411 | 9.7432 | 48900215.48 | 48900211.81 | 2023 | QM BUILDERS | 6482 | 2023 | 2023-08-22 | 03/06/2023 | 3.67 | 0 | 2023-10-09 | 48
2021 | Region VII | NEGROS ORIENTAL |  | P00549968VS | Construction of Flood Mitigation Structure | 123.2734 | 9.3568 | 93605000 | 93605000 | 2022 | PHILSOUTH BUILDERS INC (FORMERLY:PHILSOUTH BUILDERS) | 6483 | 2021 | 2022-10-31 | 10/22/2021 | 0 | 0 | 2022-10-31 | 0
2024 | Region VI | ILOILO | DINGLE (ILOILO) | P00834565VS | Construction of Revetment | 122.6592 | 10.966 | 96500000 | 95543504.1 | 2024 | A.D. PENDON CONSTRUCTION & SUPPLY, INC. (FORMERLY: ADP CONSTRUCTION & SUPPLY) | 6484 | 2024 | 2024-12-16 | 03/08/2024 | 956495.9 | 0 | 2024-10-09 |  | 68
2023 | Region V | CAMARINES SUR | LIBMANAN (CAMARINES SUR) | P00726959LZ | Construction of Flood Mitigation Structure | 123.0346 | 13.691 | 72375000 | 72375000 | 2023 | NFH CONSTRUCTION & SUPPLY | 6485 | 2023 | 2023-10-19 | 04/05/2023 | 0 | 0 | 2024-02-10 | 114
2022 | Region VII | NEGROS ORIENTAL | SIBULAN (NEGROS ORIENTAL) | P00620047VS | Construction of Flood Mitigation Structure | 123.2734 | 9.3568 | 67550000 | 67550000 | 2022 | PHILSOUTH BUILDERS INC (FORMERLY:PHILSOUTH BUILDERS) | 6486 | 2022 | 2022-12-14 | 02/18/2022 | 0 | 0 | 2022-12-13 |  | 1
2023 | Region VI | CAPIZ | SIGMA (CAPIZ) | P00721808VS | Construction of Flood Mitigation Structure | 122.6593 | 11.4242 | 47039244.65 | 47033663.89 | 2024 | WOODLAND CONSTRUCTION & SUPPLY, INC. | 6487 | 2023 | 2024-05-30 | 03/13/2023 | 5580.76 | 0 | 2024-04-30 |  | 30
2022 | Region IV-A | QUEZON | CATANAUAN (QUEZON) | P00620860LZ | Construction of Flood Mitigation Structure | 122.3226 | 13.6051 | 68997384.32 | 68997500 | 2022 | RAPID FOREMOST CONST. CO. | 6488 | 2022 | 2022-10-03 | 02/16/2022 | 0 | 115.68 | 2022-12-11 | 69
2024 | Region V | CAMARINES NORTE | BASUD (CAMARINES NORTE) | P00820464LZ | Construction of Flood Mitigation Structure | 122.9322 | 14.0263 | 96499986.42 | 96499986.42 | 2024 | BRENTMIN ROOFING ENTERPRISE | 6489 | 2024 | 2024-10-31 | 03/19/2024 | 0 | 0 | 2024-12-18 | 48
2023 | Region VI | ILOILO | ILOILO CITY (CAPITAL) (ILOILO) | P00733724VS | Construction of Drainage Structure | 122.5159 | 10.6889 | 4950000 | 4945183.08 | 2023 | PAG BUILDERS | 6490 | 2023 | 2023-08-30 | 04/17/2023 | 4816.92 | 0 | 2023-07-27 |  | 34
2023 | Region VI | NEGROS OCCIDENTAL | CITY OF TALISAY (NEGROS OCCIDENTAL) | P00732018VS | Construction of Flood Mitigation Structure | 122.9714 | 10.7468 | 4949996.87 | 4947882 | 2023 | REDSON CONSTRUCTION AND SUPPLIES, INC. (FORMERLY: REDSON CONSTRUCTION AND SUPPLIES) | 6491 | 2023 | 2023-05-01 | 02/13/2023 | 2114.87 | 0 | 2023-04-30 |  | 1
2023 | Region VI | NEGROS OCCIDENTAL | BACOLOD CITY (CAPITAL) (NEGROS OCCIDENTAL) | P00721473VS | Construction of Revetment | 123.0369 | 10.6674 | 91675000 | 91675000 | 2024 | LEGACY CONSTRUCTION CORPORATION (FORMERLY: LEGACY CONSTRUCTION) | 6492 | 2023 | 2024-03-12 | 02/08/2023 | 0 | 0 | 2024-01-08 |  | 64
2023 | Region VII | CEBU | ALEGRIA (CEBU) | P00745604VS | Rehabilitation / Major Repair of Flood Control Structure | 123.3418 | 9.7264 | 94373514.16 | 94373513.88 | 2024 | QM BUILDERS | 6493 | 2023 | 2024-06-08 | 08/10/2023 | 0.28 | 0 | 2024-06-07 |  | 1
2023 | Region VI | NEGROS OCCIDENTAL | SILAY CITY (NEGROS OCCIDENTAL) | P00721738VS | Construction of Flood Mitigation Structure | 122.9715 | 10.8268 | 96499981.33 | 96497998.12 | 2023 | SUPREME ABF CONST. & CONST. SUPPLY COMPANY INC. | 6494 | 2023 | 2023-12-11 | 02/14/2023 | 1983.21 | 0 | 2024-01-16 | 36
2023 | Region VI | ILOILO | MINA (ILOILO) | P00721931VS | Construction of Flood Mitigation Structure | 122.5161 | 10.9594 | 29400000 | 29095198.81 | 2023 | CONTE BUILDERS & CONSTRUCTION SUPPLY | 6495 | 2023 | 2023-09-28 | 03/06/2023 | 304801.19 | 0 | 2023-09-02 |  | 26
2024 | Region IX | ZAMBOANGA DEL SUR | BAYOG (ZAMBOANGA DEL SUR) | P00820244MN | Construction of Flood Mitigation Structure | 123.0377 | 7.8355 | 66467270 | 66467270 | 2024 | BADSBRO CONSTRUCTION AND GENERAL MERCHANDISE | 6496 | 2024 | 2024-11-06 | 03/22/2024 | 0 | 0 | 2024-12-04 | 28
2021 | Region VII | CEBU |  | P00549977VS | Construction of Flood Mitigation Structure | 123.2757 | 10.2758 | 9900000 | 9148241.83 | 2022 | GOLDFIN CONSTRUCTION & DEVELOPMENT CORPORATION (FORMERLY: GOLDFIN CONSTRUCTION) | 6497 | 2021 | 2022-08-02 | 03/29/2022 | 751758.17 | 0 | 2022-08-01 |  | 1
2022 | Region VI | CAPIZ | DUMALAG (CAPIZ) | P00620460VS | Construction of Flood Mitigation Structure | 122.6594 | 11.3092 | 44098402.91 | 44098309.82 | 2023 | PANAY EAST COAST CONSTRUCTION & SUPPLY | 6498 | 2022 | 2023-09-15 | 04/06/2022 | 93.09 | 0 | 2023-08-17 |  | 29
2022 | Region V | CAMARINES NORTE | TALISAY (CAMARINES NORTE) | P00631402LZ | Construction of Flood Mitigation Structure | 122.9323 | 14.1429 | 19599273.46 | 19368185.9 | 2022 | 128 DRAGON CONSTRUCTION AND SUPPLIES | 6499 | 2022 | 2022-08-18 | 03/17/2022 | 231087.56 | 0 | 2022-08-21 | 3
2022 | Region IV-A | QUEZON | CATANAUAN (QUEZON) | P00620857LZ | Construction of Flood Mitigation Structure | 122.3229 | 13.5977 | 68997457.22 | 68997500 | 2023 | RAPID FOREMOST CONST. CO. | 6500 | 2022 | 2023-02-10 | 02/16/2022 | 0 | 42.78 | 2023-02-09 |  | 1
2024 | Region IX | ZAMBOANGA DEL NORTE | LABASON (ZAMBOANGA DEL NORTE) | P00820133MN | Rehabilitation / Major Repair of Flood Control Structure | 122.5167 | 8.0683 | 34300000 | 34300000 | 2024 | LONG ISLAND BUILDERS & CONSTRUCTION | 6501 | 2024 | 2024-08-14 | 02/07/2024 | 0 | 0 | 2024-11-26 | 104
2022 | Region V | CAMARINES NORTE | DAET (CAPITAL) (CAMARINES NORTE) | P00631387LZ | Construction of Flood Mitigation Structure | 122.9327 | 14.1047 | 42139793.86 | 42139793.86 | 2022 | BRENTMIN ROOFING ENTERPRISE | 6502 | 2022 | 2022-11-25 | 03/25/2022 | 0 | 0 | 2022-11-24 |  | 1
2024 | Region VI | NEGROS OCCIDENTAL | SILAY CITY (NEGROS OCCIDENTAL) | P00820282VS | Construction of Flood Mitigation Structure | 122.9715 | 10.8268 | 96499999.97 | 96499999.99 | 2025 | SILVERGRACES CONSTRUCTION AND CONSTRUCTION SUPPLY | 6503 | 2024 | 2025-03-12 | 02/19/2024 | 0 | 0.02 | 2025-03-11 |  | 1
2024 | Region V | CAMARINES SUR | PILI (CAPITAL) (CAMARINES SUR) | P00846118LZ | Construction of Flood Mitigation Structure | 123.2777 | 13.5556 | 4949973.51 | 4889297.34 | 2024 | BENJOSH CONSTRUCTION SUPPLY | 6504 | 2024 | 2024-08-08 | 05/28/2024 | 60676.17 | 0 | 2024-08-20 | 12
2023 | Region IV-A | QUEZON | CATANAUAN (QUEZON) | P00736019LZ | Construction of Flood Mitigation Structure | 122.324 | 13.5886 | 96499959.25 | 96500000 | 2024 | V.R. PATRON BUILDERS & DEVELOPERS CORP. (PREVIOUSL | 6505 | 2023 | 2024-03-05 | 03/14/2023 | 0 | 40.75 | 2024-03-04 |  | 1
2022 | Region VII | CEBU | ALEGRIA (CEBU) | P00620453VS | Construction of Flood Mitigation Structure | 123.3421 | 9.7501 | 48999988.97 | 48999988.97 | 2022 | QM BUILDERS | 6506 | 2022 | 2022-10-25 | 03/23/2022 | 0 | 0 | 2022-10-24 |  | 1
2024 | Region IX | ZAMBOANGA DEL NORTE | LABASON (ZAMBOANGA DEL NORTE) | P00820132MN | Rehabilitation / Major Repair of Flood Control Structure | 122.5167 | 8.0682 | 14700000 | 14700000 | 2024 | DEBRIS ENTERPRISES AND CONSTRUCTION | 6507 | 2024 | 2024-05-26 | 02/07/2024 | 0 | 0 | 2024-09-19 | 116
2022 | Region VI | NEGROS OCCIDENTAL | CITY OF VICTORIAS (NEGROS OCCIDENTAL) | P00620255VS | Construction of Flood Mitigation Structure | 123.0383 | 10.8928 | 91674987.7 | 91672987 | 2023 | REDSON CONSTRUCTION AND SUPPLIES, INC. (FORMERLY: REDSON CONSTRUCTION AND SUPPLIES) | 6508 | 2022 | 2023-01-01 | 02/22/2022 | 2000.7 | 0 | 2022-12-31 |  | 1
2024 | Region VII | NEGROS ORIENTAL | SANTA CATALINA (NEGROS ORIENTAL) | P00820406VS | Construction of Flood Mitigation Structure | 122.9345 | 9.4143 | 45080000 | 45080000 | 2024 | AMETHYST HORIZON BUILDERS AND GEN. CONTRACTOR AND DEVELOPMENT CORP. | 6509 | 2024 | 2024-10-01 | 03/11/2024 | 0 | 0 | 2024-09-30 |  | 1
2024 | Region VI | NEGROS OCCIDENTAL | SILAY CITY (NEGROS OCCIDENTAL) | P00820284VS | Construction of Flood Mitigation Structure | 122.9715 | 10.8268 | 96499993.37 | 96499995.02 | 2024 | SUPREME ABF CONST. & CONST. SUPPLY COMPANY INC. | 6510 | 2024 | 2024-09-25 | 02/19/2024 | 0 | 1.65 | 2025-01-06 | 103
2020 | Region IX | ZAMBOANGA DEL NORTE |  | P00443081MN | Construction of Drainage Structure | 123.28 | 8.5107 | 6930000 | 6913195.24 | 2023 | D' DREAMER DEVELOPMENT CORPORATION | 6511 | 2020 | 2023-03-31 | 11/27/2020 | 16804.76 | 0 | 2021-04-01 |  | 729
2022 | Region VII | CEBU | ALEGRIA (CEBU) | P00620452VS | Construction of Flood Mitigation Structure | 123.3422 | 9.7506 | 48999987.89 | 48999987.89 | 2022 | QM BUILDERS | 6512 | 2022 | 2022-10-25 | 03/23/2022 | 0 | 0 | 2022-10-24 |  | 1
2024 | Region VI | ILOILO | DINGLE (ILOILO) | P00820390VS | Construction of Flood Mitigation Structure | 122.6595 | 10.9695 | 9800000 | 9750012.74 | 2024 | STRONGLANE BUILDERS AND TRADING CORPORATION (FORMERLY: STRONGLANE CONSTRUCTION & TRADING) | 6513 | 2024 | 2024-07-08 | 03/08/2024 | 49987.26 | 0 | 2024-08-20 | 43
2022 | Region IV-A | QUEZON | CATANAUAN (QUEZON) | P00620858LZ | Construction of Flood Mitigation Structure | 122.3249 | 13.5997 | 68514957.9 | 68515000 | 2023 | WAYCON BUILDERS AND CONSTRUCTION SUPPLY CORP. (FOR:WAYCON BUILDERS & CONSTRUCTION SUPPLY) / ROMHEAD S.J. BUILDERS AND DEVELOPMENT INCORPORATED. | 6514 | 2022 | 2023-05-19 | 02/16/2022 | 0 | 42.1 | 2023-05-20 | 1
2022 | Region IV-B | ROMBLON | MAGDIWANG (ROMBLON) | P00631318LZ | Construction of Flood Mitigation Structure | 122.5194 | 12.4853 | 48999906.45 | 24068307.9 | 2023 | ASHLEYKA CONSTRUCTION AND SUPPLIES | 6515 | 2022 | 2023-07-31 | 10/11/2022 | 24931598.55 | 0 | 2023-05-06 |  | 86
2022 | Region VI | NEGROS OCCIDENTAL | CITY OF VICTORIAS (NEGROS OCCIDENTAL) | P00620107VS | Construction of Flood Mitigation Structure | 123.0389 | 10.8928 | 48999980.49 | 48998000 | 2022 | REDSON CONSTRUCTION AND SUPPLIES, INC. (FORMERLY: REDSON CONSTRUCTION AND SUPPLIES) | 6516 | 2022 | 2022-09-23 | 02/08/2022 | 1980.49 | 0 | 2022-09-22 |  | 1
2022 | Region VII | NEGROS ORIENTAL | SIATON (NEGROS ORIENTAL) | P00633018VS | Construction of Flood Mitigation Structure | 122.9353 | 9.0997 | 49000000 | 49000000 | 2022 | H.L.J CONSTRUCTION & ENTERPRISES | 6517 | 2022 | 2022-12-11 | 04/06/2022 | 0 | 0 | 2022-12-10 |  | 1
2021 | Region VI | NEGROS OCCIDENTAL |  | P00521587VS | Construction of Revetment | 122.9715 | 10.6903 | 34300000 | 34300000 | 2022 | A.C. RIVERO DEVELOPMENT CORPORATION | 6518 | 2021 | 2022-07-25 | 10/07/2021 | 0 | 0 | 2022-05-29 |  | 57
2023 | Region V | CAMARINES SUR | BAAO (CAMARINES SUR) | P00736107LZ | Construction of Flood Mitigation Structure | 123.3441 | 13.4347 | 96429566 | 96428308.59 | 2024 | HI-TONE CONSTRUCTION & DEVELOPMENT CORP. (FORMERLY | 6519 | 2023 | 2024-02-06 | 02/17/2023 | 1257.41 | 0 | 2024-02-05 |  | 1
2022 | Region V | CAMARINES SUR | LIBMANAN (CAMARINES SUR) | P00620717LZ | Construction of Revetment | 123.0405 | 13.6885 | 49000000 | 48015655.63 | 2022 | NFH CONSTRUCTION & SUPPLY | 6520 | 2022 | 2022-10-06 | 03/16/2022 | 984344.37 | 0 | 2022-10-05 |  | 1
2023 | Region VI | ILOILO | DUMANGAS (ILOILO) | P00721934VS | Construction of Flood Mitigation Structure | 122.6595 | 10.9695 | 24500000 | 23763658.51 | 2023 | STRONGLANE BUILDERS AND TRADING CORPORATION (FORMERLY: STRONGLANE CONSTRUCTION & TRADING) | 6521 | 2023 | 2023-12-20 | 03/06/2023 | 736341.49 | 0 | 2023-09-20 |  | 91
2023 | Region VII | NEGROS ORIENTAL | SANTA CATALINA (NEGROS ORIENTAL) | P00721956VS | Construction of Flood Mitigation Structure | 122.9361 | 9.4172 | 36260000 | 36260000 | 2023 | LEGACY CONSTRUCTION CORPORATION (FORMERLY: LEGACY CONSTRUCTION) | 6522 | 2023 | 2023-11-01 | 04/05/2023 | 0 | 0 | 2023-10-31 |  | 1
2022 | Region IX | ZAMBOANGA SIBUGAY | DIPLAHAN (ZAMBOANGA SIBUGAY) | P00620197MN | Construction of Flood Mitigation Structure | 122.9727 | 7.7603 | 104500000.4 | 104499773.7 | 2023 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R | 6523 | 2022 | 2023-06-30 | 02/22/2022 | 226.7 | 0 | 2023-06-29 |  | 1
2021 | Region IX | ZAMBOANGA DEL NORTE |  | P00443081MN | Construction of Drainage Structure | 123.28 | 8.5107 | 6930000 | 6913195.24 | 2023 | D' DREAMER DEVELOPMENT CORPORATION | 6524 | 2021 | 2023-03-31 | 11/27/2020 | 16804.76 | 0 | 2021-04-01 |  | 729
2022 | Region IV-B | ROMBLON | MAGDIWANG (ROMBLON) | P00631321LZ | Construction of Flood Mitigation Structure | 122.5194 | 12.4853 | 48999906.45 | 24067723.15 | 2023 | ASHLEYKA CONSTRUCTION AND SUPPLIES | 6525 | 2022 | 2023-07-31 | 10/11/2022 | 24932183.3 | 0 | 2023-05-06 |  | 86
2021 | Region IV-B | ROMBLON |  | P00561579LZ | Construction of Flood Mitigation Structure | 122.5216 | 12.4727 | 48248385.32 | 48184309.17 | 2022 | LEGACY CONSTRUCTION CORPORATION (FORMERLY: LEGACY CONSTRUCTION) | 6526 | 2021 | 2022-12-07 | 03/24/2022 | 64076.15 | 0 | 2022-12-06 |  | 1
2023 | Region VI | NEGROS OCCIDENTAL | CALATRAVA (NEGROS OCCIDENTAL) | P00721873VS | Construction of Flood Mitigation Structure | 123.3452 | 10.6985 | 38599746.44 | 38212514.85 | 2023 | KENNETH CONSTRUCTION AND GENERAL MERCHANDISE | 6527 | 2023 | 2023-10-04 | 04/05/2023 | 387231.59 | 0 | 2023-10-03 |  | 1
2022 | Region IV-A | QUEZON | CATANAUAN (QUEZON) | P00620859LZ | Construction of Flood Mitigation Structure | 122.3249 | 13.6 | 68514978.22 | 54879864.36 | 2023 | ST. GERRARD CONSTRUCTION GEN. CONTRACTOR & DEVELOPMENT CORP. (FORMERLY:ST. GERRARD CONSTRUCTION) | 6528 | 2022 | 2023-02-15 | 02/21/2022 | 13635113.86 | 0 | 2023-02-14 |  | 1
2023 | Region V | CAMARINES SUR | LIBMANAN (CAMARINES SUR) | P00726961LZ | Construction of Flood Mitigation Structure | 123.0406 | 13.6885 | 72375000 | 72375000 | 2023 | BICOL GOLDROCK CONSTRUCTION CORPORATION | 6529 | 2023 | 2023-10-17 | 04/17/2023 | 0 | 0 | 2024-02-22 | 128
2021 | Region VI | ILOILO |  | P00521771VS | Construction of Slope Protection Structure | 122.6596 | 10.9689 | 9800000 | 9309957.28 | 2022 | STRONGLANE BUILDERS AND TRADING CORPORATION (FORMERLY: STRONGLANE CONSTRUCTION & TRADING) | 6530 | 2021 | 2022-10-31 | 03/29/2022 | 490042.72 | 0 | 2022-07-04 |  | 119
2023 | Region VII | NEGROS ORIENTAL | MABINAY (NEGROS ORIENTAL) | P00721844VS | Construction of Flood Mitigation Structure | 122.9371 | 9.7333 | 24500000 | 24500000 | 2023 | MIGHTY HOK SUMMIT CONSTRUCTION & DEVELOPMENT CORP. | 6531 | 2023 | 2023-09-13 | 02/17/2023 | 0 | 0 | 2023-09-12 |  | 1
2023 | Region IX | ZAMBOANGA SIBUGAY | DIPLAHAN (ZAMBOANGA SIBUGAY) | P00721403MN | Construction of Flood Mitigation Structure | 122.9739 | 7.7559 | 48250000 | 48249820.66 | 2024 | DL ENTERPRISES | 6532 | 2023 | 2024-04-17 | 07/21/2023 | 179.34 | 0 | 2024-04-16 |  | 1
2022 | Region VI | ILOILO | ILOILO CITY (CAPITAL) (ILOILO) | P00620011VS | Construction of Revetment | 122.5218 | 10.6959 | 52331467.5 | 52330984.82 | 2023 | WOODLAND CONSTRUCTION & SUPPLY, INC. | 6533 | 2022 | 2023-02-08 | 02/21/2022 | 482.68 | 0 | 2023-02-07 |  | 1
2023 | Region VII | NEGROS ORIENTAL | DAUIN (NEGROS ORIENTAL) | P00721954VS | Construction of Drainage Structure | 123.2811 | 9.2147 | 19600000 | 19600000 | 2023 | MG CONSTRUCTION | 6534 | 2023 | 2023-10-11 | 04/05/2023 | 0 | 0 | 2023-10-10 |  | 1
2024 | Region IV-A | QUEZON | CATANAUAN (QUEZON) | P00821324LZ | Construction of Flood Mitigation Structure | 122.3249 | 13.6025 | 96499932.85 | 96500000 | 2024 | ST. TIMOTHY CONSTRUCTION CORPORATION | 6535 | 2024 | 2024-12-03 | 02/14/2024 | 0 | 67.15 | 2025-01-24 | 52
2022 | Region VII | CEBU | ALEGRIA (CEBU) | P00633229VS | Construction of Flood Mitigation Structure | 123.3455 | 9.7723 | 49499923.49 | 49499923.49 | 2022 | QM BUILDERS | 6536 | 2022 | 2022-10-26 | 03/24/2022 | 0 | 0 | 2022-10-25 |  | 1
2024 | Region VI | ILOILO | POTOTAN (ILOILO) | P00820395VS | Construction of Flood Mitigation Structure | 122.6629 | 10.8935 | 34300000 | 32875340.04 | 2024 | WOODLAND CONSTRUCTION & SUPPLY, INC. | 6537 | 2024 | 2024-12-27 | 02/12/2024 | 1424659.96 | 0 | 2024-08-09 |  | 140
2022 | Region VI | NEGROS OCCIDENTAL | ENRIQUE B. MAGALONA (SARAVIA) (NEGROS OCCIDENTAL) | P00620106VS | Construction of Flood Mitigation Structure | 123.0419 | 10.9072 | 48999980.49 | 48997994 | 2022 | SILVERGRACES CONSTRUCTION AND CONSTRUCTION SUPPLY | 6538 | 2022 | 2022-09-23 | 02/08/2022 | 1986.49 | 0 | 2022-09-22 |  | 1
2023 | Region VI | NEGROS OCCIDENTAL | BACOLOD CITY (CAPITAL) (NEGROS OCCIDENTAL) | P00721625VS | Construction of Drainage Structure | 122.9385 | 10.1045 | 19600000 | 19600000 | 2023 | REDSON CONSTRUCTION AND SUPPLIES, INC. (FORMERLY: REDSON CONSTRUCTION AND SUPPLIES) | 6539 | 2023 | 2023-12-19 | 02/08/2023 | 0 | 0 | 2023-09-27 |  | 83
2023 | Region V | CAMARINES NORTE | BASUD (CAMARINES NORTE) | P00726774LZ | Construction of Flood Mitigation Structure | 122.9739 | 14.0625 | 125147545.1 | 125147336.6 | 2023 | BRENTMIN ROOFING ENTERPRISE | 6540 | 2023 | 2023-09-06 | 03/31/2023 | 208.5 | 0 | 2024-01-17 | 133
2022 | Region IV-A | QUEZON | CATANAUAN (QUEZON) | P00639382LZ | Construction of Flood Mitigation Structure | 122.3252 | 13.5878 | 96499953.91 | 96500000 | 2023 | RAPID FOREMOST CONST. CO. | 6541 | 2022 | 2023-01-21 | 04/04/2022 | 0 | 46.09 | 2023-01-20 |  | 1
2022 | Region VI | NEGROS OCCIDENTAL | SALVADOR BENEDICTO (NEGROS OCCIDENTAL) | P00620259VS | Construction of Flood Mitigation Structure | 123.3457 | 10.6989 | 48249583.32 | 48249938.13 | 2022 | JAIME B. CHING ENTERPRISES | 6542 | 2022 | 2022-09-10 | 03/02/2022 | 0 | 354.81 | 2022-09-09 |  | 1
2023 | Region V | CAMARINES SUR | BULA (CAMARINES SUR) | P00736113LZ | Construction of Flood Mitigation Structure | 123.2815 | 13.4855 | 72320815.32 | 72319240.89 | 2023 | HI-TONE CONSTRUCTION & DEVELOPMENT CORP. (FORMERLY | 6543 | 2023 | 2023-09-22 | 02/17/2023 | 1574.43 | 0 | 2023-10-24 | 32
2024 | Region VI | ILOILO | BAROTAC NUEVO (ILOILO) | P00821139VS | Construction of Flood Mitigation Structure | 122.6657 | 10.9468 | 72375000 | 72274190.79 | 2024 | EARLY RISER CONSTRUCTION / CMG JR. BUILDERS | 6544 | 2024 | 2024-05-27 | 03/08/2024 | 100809.21 | 0 | 2024-10-02 | 128
2022 | Region VI | NEGROS OCCIDENTAL | ENRIQUE B. MAGALONA (SARAVIA) (NEGROS OCCIDENTAL) | P00620254VS | Construction of Flood Mitigation Structure | 123.0419 | 10.8992 | 91674932.84 | 91673000.19 | 2023 | SUPREME ABF CONST. & CONST. SUPPLY COMPANY INC. | 6545 | 2022 | 2023-01-31 | 02/22/2022 | 1932.65 | 0 | 2023-01-30 |  | 1
2023 | Region V | CAMARINES SUR | SIPOCOT (CAMARINES SUR) | P00736082LZ | Construction of Flood Mitigation Structure | 122.9741 | 13.7643 | 82024931.07 | 82024862 | 2023 | BICOL GOLDROCK CONSTRUCTION CORPORATION | 6546 | 2023 | 2023-08-23 | 03/31/2023 | 69.07 | 0 | 2023-11-16 | 85
2022 | Region V | CAMARINES NORTE | DAET (CAPITAL) (CAMARINES NORTE) | P00631384LZ | Construction of Flood Mitigation Structure | 122.9386 | 14.1052 | 29399160.79 | 29399160.79 | 2022 | BRENTMIN ROOFING ENTERPRISE | 6547 | 2022 | 2022-08-29 | 03/11/2022 | 0 | 0 | 2022-08-28 |  | 1
2023 | Region IV-A | QUEZON | CATANAUAN (QUEZON) | P00736018LZ | Construction of Flood Mitigation Structure | 122.3276 | 13.5982 | 96499982.12 | 96500000 | 2023 | R.T.Y. CONSTRUCTION | 6548 | 2023 | 2023-12-06 | 03/06/2023 | 0 | 17.88 | 2024-01-15 | 40
2022 | Region VII | NEGROS ORIENTAL | CITY OF GUIHULNGAN (NEGROS ORIENTAL) | P00620137VS | Construction of Flood Mitigation Structure | 123.2815 | 10.1789 | 14700000 | 14700000 | 2022 | MG CONSTRUCTION | 6549 | 2022 | 2022-09-17 | 02/08/2022 | 0 | 0 | 2022-09-16 |  | 1
2022 | Region VII | CEBU | ALEGRIA (CEBU) | P00620448VS | Construction of Flood Mitigation Structure | 123.3462 | 9.787 | 96499992.71 | 96499992.71 | 2023 | QM BUILDERS | 6550 | 2022 | 2023-01-24 | 03/24/2022 | 0 | 0 | 2023-01-23 |  | 1
2022 | Region VI | AKLAN | BANGA (AKLAN) | P00620270VS | Construction of Revetment | 122.3286 | 11.6482 | 49955155 | 49954779.27 | 2023 | UNITEC BUILDER, INCORPORATED | 6551 | 2022 | 2023-02-10 | 03/17/2022 | 375.73 | 0 | 2023-02-11 | 1
2022 | Region V | CAMARINES NORTE | MERCEDES (CAMARINES NORTE) | P00631408LZ | Construction of Flood Mitigation Structure | 123.0422 | 14.0176 | 42139682.6 | 40874089.92 | 2022 | BRENTMIN ROOFING ENTERPRISE | 6552 | 2022 | 2022-11-14 | 03/17/2022 | 1265592.68 | 0 | 2022-11-16 | 2
2022 | Region V | CAMARINES NORTE | DAET (CAPITAL) (CAMARINES NORTE) | P00632951LZ | Construction of Flood Mitigation Structure | 122.9394 | 14.0993 | 4949927.33 | 4790497.46 | 2022 | 128 DRAGON CONSTRUCTION AND SUPPLIES | 6553 | 2022 | 2022-07-25 | 03/21/2022 | 159429.87 | 0 | 2022-07-24 |  | 1
2022 | Region V | CAMARINES NORTE | BASUD (CAMARINES NORTE) | P00631383LZ | Construction of Flood Mitigation Structure | 122.9743 | 14.0648 | 42139665.94 | 42136788.85 | 2022 | EUS CONSTRUCTION | 6554 | 2022 | 2022-09-12 | 03/11/2022 | 2877.09 | 0 | 2022-09-11 |  | 1
2024 | Region VI | ILOILO | POTOTAN (ILOILO) | P00820294VS | Construction of Flood Mitigation Structure | 122.6691 | 10.9272 | 120625000 | 118369503.2 | 2024 | IBC INTERNATIONAL BUILDERS CORPORATION | 6555 | 2024 | 2024-12-16 | 02/16/2024 | 2255496.8 | 0 | 2024-10-23 |  | 54
2021 | Region IX | ZAMBOANGA DEL NORTE |  | P00522045MN | Construction of Flood Mitigation Structure | 122.5242 | 8.0596 | 100646958.6 | 98946902.71 | 2022 | EDANNA CONSTRUCTION / BNR CONSTRUCTION & DEVELOPMENT CORP. | 6556 | 2021 | 2022-08-15 | 04/20/2021 | 1700055.89 | 0 | 2022-08-14 |  | 1
2024 | Region VII | NEGROS ORIENTAL | CITY OF GUIHULNGAN (NEGROS ORIENTAL) | P00820197VS | Construction of Flood Mitigation Structure | 123.2815 | 10.1789 | 29400000 | 29400000 | 2024 | MIGHTY HOK SUMMIT CONSTRUCTION & DEVELOPMENT CORP. | 6557 | 2024 | 2024-10-27 | 02/07/2024 | 0 | 0 | 2024-10-08 |  | 19
2024 | Region IV-A | QUEZON | CATANAUAN (QUEZON) | P00844776LZ | Construction of Drainage Structure | 122.3298 | 13.5879 | 14699915.51 | 14700000 | 2024 | LAICAN ENTERPRISES INC. | 6558 | 2024 | 2024-10-21 | 05/20/2024 | 0 | 84.49 | 2024-10-29 | 8
2024 | Region VII | NEGROS ORIENTAL | SIATON (NEGROS ORIENTAL) | P00820210VS | Construction of Flood Mitigation Structure | 123.0426 | 9.0616 | 45080000 | 45080000 | 2024 | ELITE GENERAL CONTRACTOR AND DEVELOPMENT CORP. | 6559 | 2024 | 2024-09-11 | 02/20/2024 | 0 | 0 | 2024-09-10 |  | 1
2022 | Region VII | CEBU | ALEGRIA (CEBU) | P00633230VS | Construction of Flood Mitigation Structure | 123.3463 | 9.7872 | 49499921.84 | 49499921.84 | 2022 | QM BUILDERS | 6560 | 2022 | 2022-10-25 | 03/23/2022 | 0 | 0 | 2022-10-24 |  | 1
2021 | Region VI | NEGROS OCCIDENTAL |  | P00549973VS | Construction of Flood Mitigation Structure | 122.9409 | 10.6672 | 8820000 | 8820000 | 2022 | HOMEWORLD CONSTRUCTION CORP. (FORMERLY HOMEWORLD E | 6561 | 2021 | 2022-08-31 | 10/07/2021 | 0 | 0 | 2022-05-05 |  | 118
2023 | Region V | CAMARINES SUR | SIPOCOT (CAMARINES SUR) | P00740486LZ | Construction of Flood Mitigation Structure | 122.9744 | 13.7692 | 82024111.07 | 82024049.2 | 2023 | BICOL GOLDROCK CONSTRUCTION CORPORATION | 6562 | 2023 | 2023-12-22 | 04/19/2023 | 61.87 | 0 | 2023-12-22 | 0
2021 | Region IX | ZAMBOANGA SIBUGAY |  | P00522154MN | Construction of Flood Mitigation Structure | 122.5274 | 7.7133 | 43120000 | 42112247.18 | 2023 | JAYKRIS ENTERPRISES & CONSTRUCTION (FORMERLY: JAYKRIS ENTERPRISES) | 6563 | 2021 | 2023-11-28 | 02/17/2021 | 1007752.82 | 0 | 2021-10-08 |  | 781
2022 | Region VI | CAPIZ | SIGMA (CAPIZ) | P00620273VS | Construction of Flood Mitigation Structure | 122.6697 | 11.4141 | 55968658.91 | 55941243.48 | 2024 | A.D. PENDON CONSTRUCTION & SUPPLY, INC. (FORMERLY: ADP CONSTRUCTION & SUPPLY) | 6564 | 2022 | 2024-02-06 | 03/01/2022 | 27415.43 | 0 | 2023-12-29 |  | 39
2022 | Region VI | NEGROS OCCIDENTAL | BACOLOD CITY (CAPITAL) (NEGROS OCCIDENTAL) | P00620079VS | Construction of Flood Mitigation Structure | 122.9413 | 10.6676 | 8820000 | 8820000 | 2023 | HOMEWORLD CONSTRUCTION CORP. (FORMERLY HOMEWORLD E | 6565 | 2022 | 2023-01-16 | 03/21/2022 | 0 | 0 | 2022-11-26 |  | 51
2022 | Region V | CAMARINES SUR | SIPOCOT (CAMARINES SUR) | P00621518LZ | Construction of Flood Mitigation Structure | 122.9746 | 13.754 | 89101796.39 | 89101796.39 | 2023 | HGG BUILDERS & SUPPLY | 6566 | 2022 | 2023-05-20 | 06/27/2022 | 0 | 0 | 2023-05-19 |  | 1
2022 | Region VI | ILOILO | CALINOG (ILOILO) | P00620245VS | Construction of Flood Mitigation Structure | 122.5282 | 11.1264 | 34300000 | 34299712.36 | 2022 | STRONGLANE BUILDERS AND TRADING CORPORATION (FORMERLY: STRONGLANE CONSTRUCTION & TRADING) | 6567 | 2022 | 2022-07-16 | 02/10/2022 | 287.64 | 0 | 2022-07-23 | 7
2022 | Region V | CAMARINES SUR | BULA (CAMARINES SUR) | P00620323LZ | Construction of Flood Mitigation Structure | 123.2816 | 13.4793 | 97103902.58 | 97103902.58 | 2023 | RAMARPLUS INCORPORATED (FORMERLY RAMAR ENTERPRISES | 6568 | 2022 | 2023-01-30 | 03/24/2022 | 0 | 0 | 2023-01-29 |  | 1
2024 | Region IX | ZAMBOANGA DEL SUR | PITOGO (ZAMBOANGA DEL SUR) | P00821216MN | Construction of Flood Mitigation Structure | 123.3468 | 7.472 | 14700000 | 14679922.81 | 2025 | ZMS CONST. & DEV. CORP. (FORMERLY:ZMS CONSTRUCTION | 6569 | 2024 | 2025-04-29 | 05/09/2024 | 20077.19 | 0 | 2024-10-30 |  | 181
2022 | Region VI | ILOILO | GUIMBAL (ILOILO) | P00620425VS | Construction of Flood Mitigation Structure | 122.3302 | 10.663 | 9800000 | 9790031.39 | 2022 | GOOD FORTUNE INTERNATIONAL, INC. | 6570 | 2022 | 2022-12-15 | 08/05/2022 | 9968.61 | 0 | 2022-12-14 |  | 1
2024 | Region VII | NEGROS ORIENTAL | SIATON (NEGROS ORIENTAL) | P00820209VS | Construction of Flood Mitigation Structure | 123.0427 | 9.0613 | 45080000 | 45080000 | 2024 | AMETHYST HORIZON BUILDERS AND GEN. CONTRACTOR AND DEVELOPMENT CORP. | 6571 | 2024 | 2024-08-12 | 02/20/2024 | 0 | 0 | 2024-09-10 | 29
2023 | Region V | CAMARINES SUR | SIPOCOT (CAMARINES SUR) | P00740484LZ | Construction of Flood Mitigation Structure | 122.9748 | 13.7543 | 72374683.37 | 72374681.42 | 2023 | NFH CONSTRUCTION & SUPPLY / SHLA CONSTRUCTION AND SUPPLY | 6572 | 2023 | 2023-11-10 | 04/19/2023 | 1.95 | 0 | 2023-11-11 | 1
2022 | Region VI | CAPIZ | SIGMA (CAPIZ) | P00620277VS | Construction of Flood Mitigation Structure | 122.6697 | 11.4141 | 62965489.07 | 62965479.53 | 2024 | A.D. PENDON CONSTRUCTION & SUPPLY, INC. (FORMERLY: ADP CONSTRUCTION & SUPPLY) | 6573 | 2022 | 2024-02-20 | 03/01/2022 | 9.54 | 0 | 2024-01-08 |  | 43
2021 | Region V | CAMARINES NORTE |  | P00525660LZ | Construction of Flood Mitigation Structure | 122.942 | 14.1085 | 65583420.66 | 65583420.66 | 2022 | EUS CONSTRUCTION / 128 DRAGON CONSTRUCTION AND SUPPLIES | 6574 | 2021 | 2022-12-15 | 05/20/2022 | 0 | 0 | 2023-01-29 | 45
2023 | Region VI | NEGROS OCCIDENTAL | ENRIQUE B. MAGALONA (SARAVIA) (NEGROS OCCIDENTAL) | P00721739VS | Construction of Flood Mitigation Structure | 123.043 | 10.8792 | 86849975.57 | 86847998 | 2023 | SILVERGRACES CONSTRUCTION AND CONSTRUCTION SUPPLY | 6575 | 2023 | 2023-12-15 | 02/14/2023 | 1977.57 | 0 | 2023-12-14 |  | 1
2023 | Region V | CAMARINES SUR | SIPOCOT (CAMARINES SUR) | P00726606LZ | Construction of Revetment | 122.9749 | 13.7706 | 57899833.65 | 57899831.5 | 2023 | DMLC BUILDERS | 6576 | 2023 | 2023-11-08 | 05/18/2023 | 2.15 | 0 | 2024-02-06 | 90
2021 | Region IV-A | QUEZON |  | P00526112LZ | Construction of Flood Mitigation Structure | 122.3327 | 13.5872 | 39199894.28 | 39200000 | 2022 | R.T.Y. CONSTRUCTION | 6577 | 2021 | 2022-07-05 | 02/12/2021 | 0 | 105.72 | 2022-07-04 |  | 1
2022 | Region VI | ILOILO | ILOILO CITY (CAPITAL) (ILOILO) | P00620444VS | Construction of Drainage Structure | 122.5298 | 10.7241 | 115800000 | 113778192.7 | 2024 | A.D. PENDON CONSTRUCTION & SUPPLY, INC. (FORMERLY: ADP CONSTRUCTION & SUPPLY) | 6578 | 2022 | 2024-03-20 | 03/29/2022 | 2021807.3 | 0 | 2024-03-25 | 5
2024 | Region VII | CEBU | ALEGRIA (CEBU) | P00834664VS | Construction of Flood Mitigation Structure | 123.3471 | 9.7867 | 48995366.78 | 48995002.78 | 2024 | FS CO BUILDERS AND SUPPLY | 6579 | 2024 | 2024-06-20 | 03/18/2024 | 364 | 0 | 2024-10-21 | 123
2023 | Region V | CAMARINES SUR | BULA (CAMARINES SUR) | P00736114LZ | Construction of Flood Mitigation Structure | 123.2819 | 13.4833 | 77086212.17 | 77086212.17 | 2023 | HI-TONE CONSTRUCTION & DEVELOPMENT CORP. (FORMERLY | 6580 | 2023 | 2023-09-25 | 02/16/2023 | 0 | 0 | 2023-11-02 | 38
2023 | Region VI | NEGROS OCCIDENTAL | BACOLOD CITY (CAPITAL) (NEGROS OCCIDENTAL) | P00721486VS | Construction of Flood Mitigation Structure | 122.9426 | 10.6535 | 96500000 | 96500000 | 2024 | LEGACY CONSTRUCTION CORPORATION (FORMERLY: LEGACY CONSTRUCTION) / M.K.U. CONSTRUCTION AND SUPPLY | 6581 | 2023 | 2024-02-15 | 02/08/2023 | 0 | 0 | 2023-12-03 |  | 74
2023 | Region V | CAMARINES SUR | SIPOCOT (CAMARINES SUR) | P00740491LZ | Construction of Flood Mitigation Structure | 122.9752 | 13.7548 | 82024639.56 | 82023729.03 | 2023 | BICOL GOLDROCK CONSTRUCTION CORPORATION | 6582 | 2023 | 2023-12-05 | 04/19/2023 | 910.53 | 0 | 2023-12-05 | 0
2022 | Region V | CAMARINES SUR | NABUA (CAMARINES SUR) | P00620730LZ | Construction of Flood Mitigation Structure | 123.3501 | 13.4278 | 39200000 | 37237616.17 | 2023 | ALRO CONSTRUCTION & DEVELOPMENT CORP. | 6583 | 2022 | 2023-08-10 | 02/22/2022 | 1962383.83 | 0 | 2023-08-09 |  | 1
2023 | Region VI | ILOILO | GUIMBAL (ILOILO) | P00721930VS | Construction of Flood Mitigation Structure | 122.3334 | 10.6679 | 19600000 | 19395767.87 | 2024 | GALENO CONSTRUCTION, INC. | 6584 | 2023 | 2024-03-04 | 09/14/2023 | 204232.13 | 0 | 2024-03-03 |  | 1
2022 | Region IV-A | QUEZON | TAGKAWAYAN (QUEZON) | P00620620LZ | Rehabilitation / Major Repair of Drainage Structure | 122.5327 | 13.9674 | 25284000 | 25284000 | 2022 | RUSLIN CONSTRUCTION | 6585 | 2022 | 2022-11-15 | 02/16/2022 | 0 | 0 | 2022-12-29 | 44
2023 | Region V | CAMARINES SUR | BULA (CAMARINES SUR) | P00736112LZ | Construction of Flood Mitigation Structure | 123.2821 | 13.4871 | 72347907.66 | 72347907.66 | 2023 | HI-TONE CONSTRUCTION & DEVELOPMENT CORP. (FORMERLY | 6586 | 2023 | 2023-09-15 | 02/17/2023 | 0 | 0 | 2023-10-24 | 39
2025 | Region VII | NEGROS ORIENTAL | SANTA CATALINA (NEGROS ORIENTAL) | P00920324VS | Construction of Flood Mitigation Structure | 122.9428 | 9.4211 | 49000000 | 48852510 | 2025 | MIGHTY HOK SUMMIT CONSTRUCTION & DEVELOPMENT CORP. | 6587 | 2025 | 2025-04-22 | 02/19/2025 | 147490 | 0 | 2025-09-15 | 146
2023 | Region VI | CAPIZ | CUARTERO (CAPIZ) | P00721993VS | Construction of Flood Mitigation Structure | 122.6698 | 11.3072 | 72374750.12 | 72374727.18 | 2024 | WOODLAND CONSTRUCTION & SUPPLY, INC. | 6588 | 2023 | 2024-06-15 | 04/17/2023 | 22.94 | 0 | 2024-06-14 |  | 1
2024 | Region VI | NEGROS OCCIDENTAL | ISABELA (NEGROS OCCIDENTAL) | P00820004VS | Construction of Slope Protection Structure | 122.9752 | 10.2317 | 96500000 | 95052445.9 | 2024 | LEGACY CONSTRUCTION CORPORATION (FORMERLY: LEGACY CONSTRUCTION) | 6589 | 2024 | 2024-08-05 | 02/14/2024 | 1447554.1 | 0 | 2024-10-10 | 66
2022 | Region VI | ILOILO | GUIMBAL (ILOILO) | P00620427VS | Construction of Flood Mitigation Structure | 122.3336 | 10.6679 | 9800000 | 9703498.97 | 2023 | GOLDEN ROADRUNNER INTERNATIONAL CORP. | 6590 | 2022 | 2023-01-03 | 03/29/2022 | 96501.03 | 0 | 2022-09-30 |  | 95
2024 | Region VI | NEGROS OCCIDENTAL | ENRIQUE B. MAGALONA (SARAVIA) (NEGROS OCCIDENTAL) | P00820285VS | Construction of Flood Mitigation Structure | 123.043 | 10.8792 | 96499993.25 | 96499993.42 | 2024 | SILVERGRACES CONSTRUCTION AND CONSTRUCTION SUPPLY | 6591 | 2024 | 2024-12-10 | 02/19/2024 | 0 | 0.17 | 2025-01-06 | 27
2022 | Region VI | ILOILO | PAVIA (ILOILO) | P00630203VS | Rehabilitation / Major Repair of Flood Control Structure | 122.5331 | 10.7744 | 33775000 | 33774530.07 | 2023 | IBC INTERNATIONAL BUILDERS CORPORATION | 6592 | 2022 | 2023-01-07 | 04/01/2022 | 469.93 | 0 | 2023-01-06 |  | 1
2022 | Region VI | NEGROS OCCIDENTAL | ISABELA (NEGROS OCCIDENTAL) | P00620438VS | Construction of Slope Protection Structure | 122.943 | 10.2063 | 96500000 | 96500000 | 2023 | LEGACY CONSTRUCTION CORPORATION (FORMERLY: LEGACY CONSTRUCTION) | 6593 | 2022 | 2023-01-17 | 05/19/2022 | 0 | 0 | 2023-01-18 | 1
2023 | Region VI | AKLAN | BANGA (AKLAN) | P00721985VS | Construction of Flood Mitigation Structure | 122.3336 | 11.6532 | 29400000 | 29399938.85 | 2023 | G.F. ROVERO MERCHANDISING | 6594 | 2023 | 2023-08-16 | 05/04/2023 | 61.15 | 0 | 2023-11-13 | 89
2024 | Region VI | NEGROS OCCIDENTAL | SAGAY CITY (NEGROS OCCIDENTAL) | P00832634VS | Construction of Flood Mitigation Structure | 123.3528 | 10.8889 | 4949987.49 | 4947617.3 | 2024 | JAIME B. CHING ENTERPRISES | 6595 | 2024 | 2024-06-04 | 03/13/2024 | 2370.19 | 0 | 2024-06-03 |  | 1
2022 | Region VI | CAPIZ | SIGMA (CAPIZ) | P00620274VS | Construction of Flood Mitigation Structure | 122.6703 | 11.4143 | 55969778.33 | 55969699.01 | 2023 | IBC INTERNATIONAL BUILDERS CORPORATION | 6596 | 2022 | 2023-11-13 | 03/01/2022 | 79.32 | 0 | 2023-11-12 |  | 1
2023 | Region VI | NEGROS OCCIDENTAL | BACOLOD CITY (CAPITAL) (NEGROS OCCIDENTAL) | P00732016VS | Construction of Flood Mitigation Structure | 122.9763 | 10.5914 | 4950000 | 4950000 | 2023 | KENBE CONSTRUCTION & SUPPLY | 6597 | 2023 | 2023-04-25 | 02/08/2023 | 0 | 0 | 2023-06-06 | 42
2023 | Region V | CAMARINES SUR | BULA (CAMARINES SUR) | P00726629LZ | Construction of Flood Mitigation Structure | 123.2824 | 13.4714 | 120971555.2 | 120971555.2 | 2024 | BICOL GOLDROCK CONSTRUCTION CORPORATION | 6598 | 2023 | 2024-04-15 | 04/20/2023 | 0 | 0 | 2024-05-05 | 20
2022 | Region VI | NEGROS OCCIDENTAL | SILAY CITY (NEGROS OCCIDENTAL) | P00620253VS | Construction of Flood Mitigation Structure | 122.9764 | 10.8324 | 90709991.89 | 90707998 | 2023 | SUPREME ABF CONST. & CONST. SUPPLY COMPANY INC. / CBCL CONSTRUCTION & SUPPLY | 6599 | 2022 | 2023-01-21 | 02/22/2022 | 1993.89 | 0 | 2023-01-20 |  | 1
2024 | Region VII | NEGROS ORIENTAL | SIATON (NEGROS ORIENTAL) | P00820208VS | Construction of Flood Mitigation Structure | 123.0431 | 9.0565 | 45080000 | 45080000 | 2024 | YPR GEN. CONTRACTOR AND CONSTRUCTION SUPPLY INC. | 6600 | 2024 | 2024-09-11 | 02/20/2024 | 0 | 0 | 2024-09-10 |  | 1
2024 | Region VI | ILOILO | CALINOG (ILOILO) | P00820388VS | Construction of Flood Mitigation Structure | 122.5335 | 11.1191 | 34300000 | 34299949.95 | 2024 | STRONGLANE BUILDERS AND TRADING CORPORATION (FORMERLY: STRONGLANE CONSTRUCTION & TRADING) | 6601 | 2024 | 2024-06-15 | 02/12/2024 | 50.05 | 0 | 2024-08-29 | 75
2024 | Region V | CAMARINES SUR | LUPI (CAMARINES SUR) | P00844576LZ | Construction of Revetment | 122.943 | 13.8737 | 96499502.24 | 94305463.04 | 2024 | BICOL GOLDROCK CONSTRUCTION CORPORATION | 6602 | 2024 | 2024-06-21 | 03/27/2024 | 2194039.2 | 0 | 2025-03-18 | 270
2022 | Region VI | AKLAN | LEZO (AKLAN) | P00620073VS | Construction of Revetment | 122.3337 | 11.6713 | 49000000 | 48999997.14 | 2022 | S.T. SALCEDO CONSTRUCTION CORP.(FORMERLY: SHAK CONSTRUCTION & SUPPLY) | 6603 | 2022 | 2022-10-19 | 02/04/2022 | 2.86 | 0 | 2022-10-28 | 9
2022 | Region IV-B | ROMBLON | CAJIDIOCAN (ROMBLON) | P00639384LZ | Construction of Flood Mitigation Structure | 122.6736 | 12.3652 | 106149999.9 | 106137741.4 | 2023 | LEGACY CONSTRUCTION CORPORATION (FORMERLY: LEGACY CONSTRUCTION) | 6604 | 2022 | 2023-08-31 | 03/24/2022 | 12258.5 | 0 | 2023-05-31 |  | 92
2023 | Region V | CAMARINES SUR | BULA (CAMARINES SUR) | P00736118LZ | Construction of Flood Mitigation Structure | 123.2827 | 13.474 | 96500000 | 96500000 | 2024 | SUNWEST, INC. (FORMERLY: SUNWEST CONSTRUCTION & DEVELOPMENT CORPORATION) | 6605 | 2023 | 2024-04-09 | 06/20/2023 | 0 | 0 | 2024-04-08 |  | 1
2022 | Region V | CAMARINES NORTE | TALISAY (CAMARINES NORTE) | P00640472LZ | Construction of Flood Mitigation Structure | 122.9768 | 14.1479 | 49499918.87 | 49499918.87 | 2022 | EUS CONSTRUCTION | 6606 | 2022 | 2022-12-09 | 03/31/2022 | 0 | 0 | 2022-12-08 |  | 1
2023 | Region VII | CEBU | MALABUYOC (CEBU) | P00721526VS | Construction of Flood Mitigation Structure | 123.3528 | 9.6455 | 57898243.83 | 57896886 | 2023 | QM BUILDERS / FIRST GRANDEUR BUILDERS | 6607 | 2023 | 2023-08-16 | 02/08/2023 | 1357.83 | 0 | 2023-10-05 | 50
2022 | Region V | CAMARINES SUR | PASACAO (CAMARINES SUR) | P00620712LZ | Construction of Dike | 123.0444 | 13.509 | 49000000 | 48017313 | 2022 | NFH CONSTRUCTION & SUPPLY | 6608 | 2022 | 2022-09-15 | 02/28/2022 | 982687 | 0 | 2022-09-19 | 4
2023 | Region V | CAMARINES NORTE | DAET (CAPITAL) (CAMARINES NORTE) | P00742192LZ | Construction of Flood Mitigation Structure | 122.9768 | 14.1452 | 19799998.09 | 19799998.09 | 2024 | 128 DRAGON CONSTRUCTION AND SUPPLIES | 6609 | 2023 | 2024-02-11 | 09/05/2023 | 0 | 0 | 2024-02-09 |  | 2
2023 | Region VI | ILOILO | CALINOG (ILOILO) | P00721811VS | Construction of Flood Mitigation Structure | 122.5336 | 11.1192 | 24500000 | 24499440.86 | 2023 | EARLY RISER CONSTRUCTION | 6610 | 2023 | 2023-05-22 | 02/13/2023 | 559.14 | 0 | 2023-09-15 | 116
2022 | Region V | CAMARINES NORTE | DAET (CAPITAL) (CAMARINES NORTE) | P00631386LZ | Construction of Flood Mitigation Structure | 122.9435 | 14.115 | 29399162.64 | 29399162.64 | 2022 | BRENTMIN ROOFING ENTERPRISE | 6611 | 2022 | 2022-11-01 | 03/15/2022 | 0 | 0 | 2022-10-31 |  | 1
2021 | Region IV-A | QUEZON |  | P00561185LZ | Construction of Drainage Structure | 122.6755 | 13.3281 | 9899982.47 | 9800000 | 2022 | ADAD ENGINEERING SERVICES & SUPPLY | 6612 | 2021 | 2022-10-26 | 03/31/2022 | 99982.47 | 0 | 2022-10-25 |  | 1
2023 | Region VII | CEBU | MALABUYOC (CEBU) | P00745600VS | Rehabilitation / Major Repair of Flood Control Structure | 123.353 | 9.6482 | 94220799.91 | 94220452.01 | 2024 | QM BUILDERS | 6613 | 2023 | 2024-07-03 | 09/04/2023 | 347.9 | 0 | 2024-07-02 |  | 1
2023 | Region VI | AKLAN | BANGA (AKLAN) | P00721992VS | Rehabilitation / Major Repair of Flood Control Structure | 122.3337 | 11.6533 | 19600000 | 19583672.06 | 2023 | EC BUILDERS | 6614 | 2023 | 2023-08-29 | 03/15/2023 | 16327.94 | 0 | 2023-09-17 | 19
2023 | Region VI | NEGROS OCCIDENTAL | CITY OF VICTORIAS (NEGROS OCCIDENTAL) | P00721740VS | Construction of Flood Mitigation Structure | 123.0457 | 10.8758 | 86849992.44 | 86847719 | 2023 | REDSON CONSTRUCTION AND SUPPLIES, INC. (FORMERLY: REDSON CONSTRUCTION AND SUPPLIES) | 6615 | 2023 | 2023-12-18 | 02/14/2023 | 2273.44 | 0 | 2024-01-04 | 17
2024 | Region V | CAMARINES SUR | SIPOCOT (CAMARINES SUR) | P00845848LZ | Construction of Revetment | 122.9786 | 13.7699 | 98999528.72 | 98999371.67 | 2024 | JUSTBILT BUILDERS | 6616 | 2024 | 2024-12-16 | 05/07/2024 | 157.05 | 0 | 2025-04-28 | 133
2024 | Region IX | ZAMBOANGA DEL NORTE | KATIPUNAN (ZAMBOANGA DEL NORTE) | P00833583MN | Construction of Flood Mitigation Structure | 123.2842 | 8.5136 | 9900000 | 9854928.39 | 2025 | RDT CONSTRUCTION AND GENERAL MERCHANDISE | 6617 | 2024 | 2025-01-26 | 02/21/2024 | 45071.61 | 0 | 2024-07-05 |  | 205
2022 | Region VI | CAPIZ | DUMARAO (CAPIZ) | P00620300VS | Construction of Flood Mitigation Structure | 122.676 | 11.3001 | 42225822.3 | 43225821.07 | 2024 | A.D. PENDON CONSTRUCTION & SUPPLY, INC. (FORMERLY: ADP CONSTRUCTION & SUPPLY) | 6618 | 2022 | 2024-02-08 | 02/21/2022 | 0 | 999998.77 | 2023-10-15 |  | 116
2022 | Region IV-A | QUEZON | TAGKAWAYAN (QUEZON) | P00620606LZ | Construction of Flood Mitigation Structure | 122.5358 | 13.9646 | 19600000 | 19600000 | 2022 | BOMEL CONSTRUCTION | 6619 | 2022 | 2022-09-12 | 02/15/2022 | 0 | 0 | 2022-09-11 |  | 1
2022 | Region V | CAMARINES NORTE | TALISAY (CAMARINES NORTE) | P00620699LZ | Construction of Flood Mitigation Structure | 122.9435 | 14.1435 | 41159560.59 | 41159560.59 | 2022 | BRENTMIN ROOFING ENTERPRISE / N.E.B. CONSTRUCTION AND SUPPLY | 6620 | 2022 | 2022-09-05 | 03/18/2022 | 0 | 0 | 2022-09-17 | 12
2024 | Region VI | AKLAN | BANGA (AKLAN) | P00821160VS | Construction of Revetment | 122.334 | 11.6533 | 28950000 | 28949793.71 | 2024 | PASTRANA CONSTRUCTION & SUPPLIES (FORMERLY: PASTRA | 6621 | 2024 | 2024-06-18 | 02/19/2024 | 206.29 | 0 | 2024-08-07 | 50
2022 | Region V | CAMARINES NORTE | SANTA ELENA (CAMARINES NORTE) | P00631410LZ | Construction of Flood Mitigation Structure | 122.3371 | 14.1569 | 19599294.8 | 19525424.72 | 2022 | EUS CONSTRUCTION | 6622 | 2022 | 2022-08-22 | 03/17/2022 | 73870.08 | 0 | 2022-08-21 |  | 1
2022 | Region VI | NEGROS OCCIDENTAL | SAGAY CITY (NEGROS OCCIDENTAL) | P00620302VS | Construction of Flood Mitigation Structure | 123.3531 | 10.8933 | 48999964.03 | 48997964.88 | 2023 | JAIME B. CHING ENTERPRISES | 6623 | 2022 | 2023-05-11 | 02/08/2022 | 1999.15 | 0 | 2023-05-10 |  | 1
2023 | Region V | CAMARINES SUR | CALABANGA (CAMARINES SUR) | P00742477LZ | Construction of Flood Mitigation Structure | 123.2857 | 13.7588 | 4949993.14 | 4749500 | 2023 | MEGA-ANT BUILDERS AND CONSTRUCTION SUPPLIES | 6624 | 2023 | 2023-08-26 | 06/13/2023 | 200493.14 | 0 | 2023-08-25 |  | 1
2022 | Region V | CAMARINES SUR | SIPOCOT (CAMARINES SUR) | P00632961LZ | Construction of Revetment | 122.9789 | 13.7704 | 29699693.1 | 29699691.66 | 2022 | NFH CONSTRUCTION & SUPPLY | 6625 | 2022 | 2022-11-10 | 03/24/2022 | 1.44 | 0 | 2022-11-09 |  | 1
2024 | Region V | CAMARINES SUR | RAGAY (CAMARINES SUR) | P00844587LZ | Construction of Revetment | 122.6786 | 13.8212 | 96499961.53 | 96495012.79 | 2024 | RAPIDWORKZ CONSTRUCTION & SUPPLY / STEVEN CONSTRUCTION & SUPPLY | 6626 | 2024 | 2024-06-04 | 03/25/2024 | 4948.74 | 0 | 2025-03-16 | 285
2023 | Region VI | NEGROS OCCIDENTAL | BACOLOD CITY (CAPITAL) (NEGROS OCCIDENTAL) | P00721632VS | Construction of Drainage Structure | 122.9442 | 10.6636 | 34300000 | 34300000 | 2023 | A.C. RIVERO DEVELOPMENT CORPORATION | 6627 | 2023 | 2023-11-03 | 03/03/2023 | 0 | 0 | 2023-11-02 |  | 1
2023 | Region VII | CEBU | MALABUYOC (CEBU) | P00721523VS | Construction of Flood Mitigation Structure | 123.3531 | 9.6443 | 96015727.77 | 96015132.75 | 2023 | QUIRANTE CONSTRUCTION CORPORATION (FORMERLY: QUIRANTE CONSTRUCTION) | 6628 | 2023 | 2023-09-26 | 02/08/2023 | 595.02 | 0 | 2023-12-17 | 82
2021 | Region VI | ILOILO |  | P00521547VS | Rehabilitation / Major Repair of Flood Control Structure | 122.537 | 10.7699 | 19300000 | 19300000 | 2023 | S.T. SALCEDO CONSTRUCTION CORP.(FORMERLY: SHAK CONSTRUCTION & SUPPLY) | 6629 | 2021 | 2023-09-16 | 06/23/2022 | 0 | 0 | 2023-09-15 |  | 1
2023 | Region VII | NEGROS ORIENTAL | DUMAGUETE CITY (CAPITAL) (NEGROS ORIENTAL) | P00721846VS | Construction of Flood Mitigation Structure | 123.2859 | 9.3093 | 49000000 | 49000000 | 2023 | ASHLEYKA CONSTRUCTION AND SUPPLIES | 6630 | 2023 | 2023-11-20 | 02/13/2023 | 0 | 0 | 2023-11-19 |  | 1
2023 | Region V | CAMARINES NORTE | SANTA ELENA (CAMARINES NORTE) | P00726288LZ | Construction of Flood Mitigation Structure | 122.3371 | 14.1568 | 17639257.98 | 17639257.98 | 2023 | EUS CONSTRUCTION | 6631 | 2023 | 2023-08-26 | 04/05/2023 | 0 | 0 | 2023-08-25 |  | 1
2024 | Region VI | NEGROS OCCIDENTAL | CITY OF VICTORIAS (NEGROS OCCIDENTAL) | P00820286VS | Construction of Flood Mitigation Structure | 123.0457 | 10.8758 | 96499995.9 | 96499996.75 | 2024 | REDSON CONSTRUCTION AND SUPPLIES, INC. (FORMERLY: REDSON CONSTRUCTION AND SUPPLIES) | 6632 | 2024 | 2024-12-10 | 03/13/2024 | 0 | 0.85 | 2025-01-29 | 50
2022 | Region V | CAMARINES SUR | SIPOCOT (CAMARINES SUR) | P00632962LZ | Construction of Revetment | 122.9796 | 13.7712 | 29699598.45 | 29699598.42 | 2022 | NFH CONSTRUCTION & SUPPLY | 6633 | 2022 | 2022-11-10 | 03/24/2022 | 0.03 | 0 | 2022-11-09 |  | 1
2023 | Region VI | NEGROS OCCIDENTAL | BACOLOD CITY (CAPITAL) (NEGROS OCCIDENTAL) | P00721640VS | Construction of Drainage Structure | 122.9453 | 10.6578 | 11760000 | 11760000 | 2023 | ANCHORVILLE REALTY DEV'T CONSTRUCTION CORP. | 6634 | 2023 | 2023-09-26 | 02/08/2023 | 0 | 0 | 2023-08-06 |  | 51
2022 | Region VI | ILOILO | POTOTAN (ILOILO) | P00620260VS | Construction of Flood Mitigation Structure | 122.6855 | 10.9131 | 44100000 | 43217768.99 | 2023 | A.D. PENDON CONSTRUCTION & SUPPLY, INC. (FORMERLY: ADP CONSTRUCTION & SUPPLY) | 6635 | 2022 | 2023-10-29 | 03/29/2022 | 882231.01 | 0 | 2022-09-09 |  | 415
2023 | Region VII | CEBU | MALABUYOC (CEBU) | P00721908VS | Construction of Flood Mitigation Structure | 123.3532 | 9.6442 | 72373235.28 | 72373204.29 | 2023 | LEGACY CONSTRUCTION CORPORATION (FORMERLY: LEGACY CONSTRUCTION) | 6636 | 2023 | 2023-11-24 | 03/16/2023 | 30.99 | 0 | 2023-12-02 | 8
2023 | Region VI | ILOILO | ILOILO CITY (CAPITAL) (ILOILO) | P00733726VS | Construction of Drainage Structure | 122.5374 | 10.7195 | 4950000 | 4900642.53 | 2024 | OTING CONSTRUCTION AND SUPPLY | 6637 | 2023 | 2024-11-08 | 04/17/2023 | 49357.47 | 0 | 2023-07-30 |  | 467
2022 | Region V | CAMARINES SUR | BULA (CAMARINES SUR) | P00620294LZ | Construction of Flood Mitigation Structure | 123.2864 | 13.4892 | 97281469.34 | 97281469.34 | 2023 | RAMARPLUS INCORPORATED (FORMERLY RAMAR ENTERPRISES | 6638 | 2022 | 2023-03-31 | 03/21/2022 | 0 | 0 | 2023-04-07 | 7
2023 | Region V | CAMARINES NORTE | TALISAY (CAMARINES NORTE) | P00740452LZ | Construction of Flood Mitigation Structure | 122.9453 | 14.1433 | 96499613.82 | 96499613.82 | 2024 | E. GARCIA CONSTRUCTION CORP.(FOR. E. GARCIA CONST | 6639 | 2023 | 2024-02-15 | 08/09/2023 | 0 | 0 | 2024-05-17 | 92
2024 | Region V | CAMARINES SUR | SIPOCOT (CAMARINES SUR) | P00820481LZ | Construction of Flood Mitigation Structure | 123.0474 | 13.8097 | 113974814.6 | 113974811.1 | 2024 | G.C.I. CONSTRUCTION AND DEV'T. CORP. | 6640 | 2024 | 2024-06-24 | 03/01/2024 | 3.5 | 0 | 2025-01-04 | 194
2023 | Region V | CAMARINES SUR | SIPOCOT (CAMARINES SUR) | P00736078LZ | Construction of Flood Mitigation Structure | 122.9455 | 13.7816 | 72374683.76 | 72374568 | 2023 | NFH CONSTRUCTION & SUPPLY / SHLA CONSTRUCTION AND SUPPLY | 6641 | 2023 | 2023-08-23 | 03/31/2023 | 115.76 | 0 | 2023-10-23 | 61
2023 | Region VI | AKLAN | NUMANCIA (AKLAN) | P00721925VS | Construction of Revetment | 122.3375 | 11.7216 | 49000000 | 48999994.12 | 2024 | GREAT PACIFIC BUILDERS AND GEN. CONTRACTOR INC. | 6642 | 2023 | 2024-06-18 | 03/17/2023 | 5.88 | 0 | 2024-07-23 | 35
2022 | Region VII | CEBU | MALABUYOC (CEBU) | P00620446VS | Construction of Flood Mitigation Structure | 123.3535 | 9.6489 | 96499958.77 | 96499958.77 | 2023 | QM BUILDERS | 6643 | 2022 | 2023-01-24 | 03/24/2022 | 0 | 0 | 2023-01-23 |  | 1
2022 | Region VI | NEGROS OCCIDENTAL | MANAPLA (NEGROS OCCIDENTAL) | P00630641VS | Construction of Flood Mitigation Structure | 122.9798 | 11.0757 | 9899996.24 | 8826240 | 2022 | GALFONS BUILDERS & SUPPLY, INC. | 6644 | 2022 | 2022-08-04 | 02/08/2022 | 1073756.24 | 0 | 2022-08-03 |  | 1
2024 | Region IX | ZAMBOANGA DEL NORTE | LEON T. POSTIGO (ZAMBOANGA DEL NORTE) | P00820134MN | Rehabilitation / Major Repair of Flood Control Structure | 122.5403 | 8.0695 | 14700000 | 14700000 | 2024 | ST. JOSEPH CONSTRUCTION & TRADING | 6645 | 2024 | 2024-07-22 | 02/07/2024 | 0 | 0 | 2024-09-19 | 59
2022 | Region VI | NEGROS OCCIDENTAL | BACOLOD CITY (CAPITAL) (NEGROS OCCIDENTAL) | P00620080VS | Construction of Revetment | 122.9457 | 10.6446 | 44113720 | 44113720 | 2022 | SUPREME ABF CONST. & CONST. SUPPLY COMPANY INC. | 6646 | 2022 | 2022-09-18 | 02/08/2022 | 0 | 0 | 2022-09-12 |  | 6
2022 | Region V | CAMARINES SUR | BAAO (CAMARINES SUR) | P00630970LZ | Construction of Flood Mitigation Structure | 123.3535 | 13.4563 | 67550000 | 65185821.9 | 2022 | RICHMAR CONSTRUCTION | 6647 | 2022 | 2022-12-09 | 02/22/2022 | 2364178.1 | 0 | 2022-12-11 | 2
2024 | Region VI | ILOILO | BAROTAC NUEVO (ILOILO) | P00820389VS | Construction of Flood Mitigation Structure | 122.6863 | 10.9093 | 39200000 | 38999560.22 | 2024 | A.D. PENDON CONSTRUCTION & SUPPLY, INC. (FORMERLY: ADP CONSTRUCTION & SUPPLY) | 6648 | 2024 | 2024-07-08 | 02/12/2024 | 200439.78 | 0 | 2024-10-06 | 90
2023 | Region VI | AKLAN | NUMANCIA (AKLAN) | P00733711VS | Construction of Revetment | 122.3392 | 11.7361 | 9900000 | 9891863.68 | 2023 | VILLORENTE TWIN BUILDERS CORPORATION | 6649 | 2023 | 2023-10-20 | 05/11/2023 | 8136.32 | 0 | 2023-10-19 |  | 1
2022 | Region VI | ILOILO | AJUY (ILOILO) | P00620095VS | Construction of Flood Mitigation Structure | 122.9808 | 11.0736 | 96500000 | 96500000 | 2023 | IBC INTERNATIONAL BUILDERS CORPORATION | 6650 | 2022 | 2023-06-25 | 03/25/2022 | 0 | 0 | 2023-06-24 |  | 1
2023 | Region VI | ILOILO | ILOILO CITY (CAPITAL) (ILOILO) | P00733727VS | Construction of Drainage Structure | 122.5414 | 10.6975 | 4950000 | 4939923.08 | 2023 | GOLDEN ROADRUNNER INTERNATIONAL CORP. | 6651 | 2023 | 2023-10-10 | 05/12/2023 | 10076.92 | 0 | 2023-10-09 |  | 1
2021 | Region IX | ZAMBOANGA DEL NORTE |  | P00522035MN | Construction of Flood Mitigation Structure | 123.0497 | 8.4847 | 67550000 | 67418646.51 | 2022 | ESR CONSTRUCTION AND DEVELOPMENT CORPORATION (FORMERLY: ESR CONSTRUCTION & SUPPLIES) | 6652 | 2021 | 2022-11-24 | 03/22/2021 | 131353.49 | 0 | 2022-02-07 |  | 290
2024 | Region V | CAMARINES SUR | BULA (CAMARINES SUR) | P00821392LZ | Construction of Flood Mitigation Structure | 123.287 | 13.444 | 139925000 | 139925000 | 2024 | G.C.I. CONSTRUCTION AND DEV'T. CORP. | 6653 | 2024 | 2024-11-19 | 02/21/2024 | 0 | 0 | 2024-12-27 | 38
2023 | Region VI | ILOILO | GUIMBAL (ILOILO) | P00733717VS | Construction of Flood Mitigation Structure | 122.3443 | 10.6711 | 19600000 | 19563085.49 | 2024 | DEACONS TEMPLE CONSTRUCTION & SUPPLY | 6654 | 2023 | 2024-01-05 | 04/18/2023 | 36914.51 | 0 | 2023-12-02 |  | 34
2023 | Region VI | CAPIZ | DAO (CAPIZ) | P00721723VS | Construction of Flood Mitigation Structure | 122.6865 | 11.3913 | 71409713.25 | 71409709.04 | 2024 | A.D. PENDON CONSTRUCTION & SUPPLY, INC. (FORMERLY: ADP CONSTRUCTION & SUPPLY) | 6655 | 2023 | 2024-06-29 | 03/13/2023 | 4.21 | 0 | 2024-06-21 |  | 8
2023 | Region VI | ILOILO | GUIMBAL (ILOILO) | P00721647VS | Construction of Flood Mitigation Structure | 122.3452 | 10.6711 | 14700000 | 14551344.14 | 2023 | PANAY EAST COAST CONSTRUCTION & SUPPLY | 6656 | 2023 | 2023-08-08 | 02/10/2023 | 148655.86 | 0 | 2023-08-07 |  | 1
2023 | Region VII | CEBU | MALABUYOC (CEBU) | P00721525VS | Construction of Flood Mitigation Structure | 123.3553 | 9.6426 | 57898231.91 | 57898184.98 | 2023 | QM BUILDERS | 6657 | 2023 | 2023-07-21 | 02/08/2023 | 46.93 | 0 | 2023-10-05 | 76
2022 | Region V | CAMARINES NORTE | DAET (CAPITAL) (CAMARINES NORTE) | P00620697LZ | Construction of Flood Mitigation Structure | 122.9812 | 14.1066 | 24499945.05 | 23745445.6 | 2022 | JCO CONSTRUCTION AND SUPPLY | 6658 | 2022 | 2022-09-05 | 03/24/2022 | 754499.45 | 0 | 2022-09-04 |  | 1
2023 | Region VI | ILOILO | PAVIA (ILOILO) | P00721496VS | Rehabilitation / Major Repair of Flood Control Structure | 122.5417 | 10.7687 | 27985000 | 27985000 | 2024 | RMKP CONSTRUCTION INC. (FORMERLY: RMKP CONSTRUCTION) | 6659 | 2023 | 2024-01-27 | 02/16/2023 | 0 | 0 | 2024-01-26 |  | 1
2024 | Region VII | NEGROS ORIENTAL | BAIS CITY (NEGROS ORIENTAL) | P00820402VS | Construction of Flood Mitigation Structure | 123.0504 | 9.596 | 9800000 | 9800000 | 2024 | PHILSOUTH BUILDERS INC (FORMERLY:PHILSOUTH BUILDERS) | 6660 | 2024 | 2024-07-21 | 04/04/2024 | 0 | 0 | 2024-07-20 |  | 1
2023 | Region VI | NEGROS OCCIDENTAL | BACOLOD CITY (CAPITAL) (NEGROS OCCIDENTAL) | P00721487VS | Construction of Revetment | 122.9457 | 10.6447 | 96500000 | 96500000 | 2024 | SUPREME ABF CONST. & CONST. SUPPLY COMPANY INC. / CANLAON BUILDERS AND DEVELOPMENT CORPORATION | 6661 | 2023 | 2024-01-22 | 02/22/2023 | 0 | 0 | 2024-01-03 |  | 19
2023 | Region V | CAMARINES SUR | BULA (CAMARINES SUR) | P00726628LZ | Construction of Flood Mitigation Structure | 123.2872 | 13.4863 | 115659116.9 | 115659116.9 | 2024 | G.C.I. CONSTRUCTION AND DEV'T. CORP. | 6662 | 2023 | 2024-03-31 | 04/03/2023 | 0 | 0 | 2024-04-16 | 16
2023 | Region VII | CEBU | MALABUYOC (CEBU) | P00721683VS | Construction of Flood Mitigation Structure | 123.3553 | 9.6426 | 48998254.45 | 48995336.08 | 2023 | FIRST GRANDEUR BUILDERS | 6663 | 2023 | 2023-08-23 | 02/08/2023 | 2918.37 | 0 | 2023-09-13 | 21
2022 | Region VI | NEGROS OCCIDENTAL | SILAY CITY (NEGROS OCCIDENTAL) | P00634051VS | Construction of Flood Mitigation Structure | 122.9822 | 10.8192 | 43425000 | 43423000.33 | 2023 | IBC INTERNATIONAL BUILDERS CORPORATION | 6664 | 2022 | 2023-06-01 | 05/24/2022 | 1999.67 | 0 | 2023-05-31 |  | 1
2023 | Region V | CAMARINES NORTE | SANTA ELENA (CAMARINES NORTE) | P00737557LZ | Construction of Flood Mitigation Structure | 122.346 | 14.2108 | 9899717.98 | 8169001.17 | 2023 | GREAT WALL ENGINEERING | 6665 | 2023 | 2023-07-31 | 04/05/2023 | 1730716.81 | 0 | 2023-07-30 |  | 1
2022 | Region VI | NEGROS OCCIDENTAL | SILAY CITY (NEGROS OCCIDENTAL) | P00634049VS | Construction of Flood Mitigation Structure | 122.9839 | 10.8213 | 43425000 | 43423000 | 2023 | R.A.G. CORONA CONSTRUCTION AND AGGREGATES SUPPLY | 6666 | 2022 | 2023-03-04 | 05/24/2022 | 2000 | 0 | 2023-03-03 |  | 1
2022 | Region VI | NEGROS OCCIDENTAL | BINALBAGAN (NEGROS OCCIDENTAL) | P00620437VS | Construction of Slope Protection Structure | 122.9458 | 10.2074 | 96500000 | 96498863.82 | 2023 | LEGACY CONSTRUCTION CORPORATION (FORMERLY: LEGACY CONSTRUCTION) | 6667 | 2022 | 2023-01-19 | 05/19/2022 | 1136.18 | 0 | 2023-01-18 |  | 1
2023 | Region VI | ILOILO | ILOILO CITY (CAPITAL) (ILOILO) | P00733731VS | Construction of Drainage Structure | 122.5419 | 10.6891 | 4950000 | 4940475.35 | 2023 | NOE'S BUILDERS | 6668 | 2023 | 2023-10-16 | 07/12/2023 | 9524.65 | 0 | 2023-10-01 |  | 15
2023 | Region VII | NEGROS ORIENTAL | BAIS CITY (NEGROS ORIENTAL) | P00731632VS | Construction of Flood Mitigation Structure | 123.0506 | 9.5942 | 96500000 | 96500000 | 2024 | PHILSOUTH BUILDERS INC (FORMERLY:PHILSOUTH BUILDERS) | 6669 | 2023 | 2024-02-12 | 03/10/2023 | 0 | 0 | 2024-02-11 |  | 1
2022 | Region VI | CAPIZ | DUMARAO (CAPIZ) | P00620275VS | Construction of Flood Mitigation Structure | 122.6889 | 11.2679 | 50372664 | 50372582.3 | 2023 | WOODLAND CONSTRUCTION & SUPPLY, INC. | 6670 | 2022 | 2023-12-04 | 02/28/2022 | 81.7 | 0 | 2023-12-08 | 4
2022 | Region VII | NEGROS ORIENTAL | DUMAGUETE CITY (CAPITAL) (NEGROS ORIENTAL) | P00630662VS | Construction of Drainage Structure | 123.2892 | 9.2776 | 4950000 | 4950000 | 2022 | ASHLEYKA CONSTRUCTION AND SUPPLIES | 6671 | 2022 | 2022-08-01 | 02/11/2022 | 0 | 0 | 2022-07-31 |  | 1
2023 | Region VII | CEBU | MALABUYOC (CEBU) | P00721684VS | Construction of Flood Mitigation Structure | 123.3553 | 9.6426 | 48998238.83 | 48998238.17 | 2023 | GREEN WORLD CONSTRUCTION / MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY | 6672 | 2023 | 2023-07-24 | 02/08/2023 | 0.66 | 0 | 2023-09-13 | 51
2022 | Region VI | NEGROS OCCIDENTAL | SILAY CITY (NEGROS OCCIDENTAL) | P00620099VS | Construction of Flood Mitigation Structure | 122.9847 | 10.7968 | 29399996.92 | 29398000 | 2022 | EMR BUILDERS AND DEVELOPMENT CORPORATION (FORMERLY: EMR BUILDERS) | 6673 | 2022 | 2022-07-17 | 02/08/2022 | 1996.92 | 0 | 2022-07-16 |  | 1
2024 | Region VI | ILOILO | ILOILO CITY (CAPITAL) (ILOILO) | P00834995VS | Construction of Flood Mitigation Structure | 122.542 | 10.6886 | 9900000 | 9899955.26 | 2024 | NOE'S BUILDERS | 6674 | 2024 | 2024-09-13 | 02/19/2024 | 44.74 | 0 | 2024-09-12 |  | 1
2023 | Region VI | NEGROS OCCIDENTAL | CITY OF VICTORIAS (NEGROS OCCIDENTAL) | P00721471VS | Construction of Flood Mitigation Structure | 123.0536 | 10.8939 | 96499996.21 | 96498052.34 | 2024 | R.A.G. CORONA CONSTRUCTION AND AGGREGATES SUPPLY | 6675 | 2023 | 2024-08-07 | 02/14/2023 | 1943.87 | 0 | 2024-08-06 |  | 1
2023 | Region VI | CAPIZ | DAO (CAPIZ) | P00721996VS | Construction of Flood Mitigation Structure | 122.6893 | 11.4034 | 24499169.6 | 24490880.97 | 2024 | MEGAGOLD CONSTRUCTION AND DEVELOPMENT, OPC | 6676 | 2023 | 2024-05-16 | 03/13/2023 | 8288.63 | 0 | 2024-04-29 |  | 17
2022 | Region VI | NEGROS OCCIDENTAL | ISABELA (NEGROS OCCIDENTAL) | P00630180VS | Construction of Slope Protection Structure | 122.9464 | 10.2079 | 96500000 | 96016865.27 | 2023 | LEGACY CONSTRUCTION CORPORATION (FORMERLY: LEGACY CONSTRUCTION) | 6677 | 2022 | 2023-03-09 | 02/18/2022 | 483134.73 | 0 | 2023-03-09 | 0
2023 | Region VI | NEGROS OCCIDENTAL | SAGAY CITY (NEGROS OCCIDENTAL) | P00721737VS | Construction of Flood Mitigation Structure | 123.3556 | 10.8883 | 86849994.23 | 86848000 | 2024 | JAIME B. CHING ENTERPRISES | 6678 | 2023 | 2024-03-14 | 02/14/2023 | 1994.23 | 0 | 2024-03-13 |  | 1
2022 | Region VI | NEGROS OCCIDENTAL | SILAY CITY (NEGROS OCCIDENTAL) | P00634050VS | Construction of Flood Mitigation Structure | 122.9852 | 10.8199 | 43425000 | 43423000 | 2023 | M.K.U. CONSTRUCTION AND SUPPLY | 6679 | 2022 | 2023-03-04 | 05/24/2022 | 2000 | 0 | 2023-03-03 |  | 1
2021 | Region VI | ILOILO |  | P00521615VS | Construction of Drainage Structure | 122.5454 | 10.7183 | 9799121.91 | 8774648.72 | 2022 | VANNIE CONSTRUCTION AND SUPPLY (FORMERLY: VANNIE | 6680 | 2021 | 2022-08-27 | 02/22/2022 | 1024473.19 | 0 | 2022-08-26 |  | 1
2023 | Region IV-A | QUEZON | TAGKAWAYAN (QUEZON) | P00742444LZ | Construction of Slope Protection Structure | 122.5463 | 13.9623 | 10692000 | 10692000 | 2023 | BOMEL CONSTRUCTION | 6681 | 2023 | 2023-10-04 | 04/03/2023 | 0 | 0 | 2023-10-03 |  | 1
2021 | Region VI | AKLAN |  | P00521760VS | Construction of Revetment | 122.3469 | 11.6755 | 96040000 | 92777160.39 | 2023 | MONOLITHIC CONSTRUCTION & CONCRETE PRODUCTS, INC. | 6682 | 2021 | 2023-05-29 | 05/12/2021 | 3262839.61 | 0 | 2022-03-16 |  | 439
2022 | Region VI | ILOILO | BAROTAC NUEVO (ILOILO) | P00620419VS | Construction of Flood Mitigation Structure | 122.696 | 10.8992 | 57900000 | 56741097.53 | 2023 | PANAY EAST COAST CONSTRUCTION & SUPPLY | 6683 | 2022 | 2023-06-07 | 03/29/2022 | 1158902.47 | 0 | 2022-10-13 |  | 237
2022 | Region VI | NEGROS OCCIDENTAL | CITY OF TALISAY (NEGROS OCCIDENTAL) | P00620097VS | Construction of Flood Mitigation Structure | 122.9853 | 10.7172 | 39199990.14 | 39198000 | 2022 | M.K.U. CONSTRUCTION AND SUPPLY | 6684 | 2022 | 2022-07-27 | 02/08/2022 | 1990.14 | 0 | 2022-07-26 |  | 1
2023 | Region VII | NEGROS ORIENTAL | SIBULAN (NEGROS ORIENTAL) | P00732031VS | Construction of Drainage Structure | 123.2898 | 9.3358 | 4950000 | 4946804.4 | 2023 | 8G CONSTRUCTION AND GENERAL SERVICES | 6685 | 2023 | 2023-05-22 | 02/06/2023 | 3195.6 | 0 | 2023-05-21 |  | 1
2022 | Region VI | ILOILO | DUMANGAS (ILOILO) | P00620431VS | Construction of Flood Mitigation Structure | 122.6975 | 10.7878 | 19600000 | 19188407.19 | 2023 | PGO CONSTRUCTION | 6686 | 2022 | 2023-04-03 | 03/29/2022 | 411592.81 | 0 | 2022-09-07 |  | 208
2023 | Region IV-A | QUEZON | TAGKAWAYAN (QUEZON) | P00742443LZ | Construction of Slope Protection Structure | 122.5463 | 13.9623 | 9900000 | 9900000 | 2023 | BOMEL CONSTRUCTION | 6687 | 2023 | 2023-10-06 | 04/03/2023 | 0 | 0 | 2023-10-05 |  | 1
2023 | Region VI | AKLAN | KALIBO (CAPITAL) (AKLAN) | P00721987VS | Construction of Flood Mitigation Structure | 122.3581 | 11.6889 | 49000000 | 48999994.3 | 2023 | S.T. SALCEDO CONSTRUCTION CORP.(FORMERLY: SHAK CONSTRUCTION & SUPPLY) | 6688 | 2023 | 2023-09-22 | 03/03/2023 | 5.7 | 0 | 2023-12-25 | 94
2023 | Region V | CAMARINES SUR | BAAO (CAMARINES SUR) | P00736069LZ | Construction of Flood Mitigation Structure | 123.3561 | 13.4586 | 241249988 | 241249988 | 2024 | SUNWEST, INC. (FORMERLY: SUNWEST CONSTRUCTION & DEVELOPMENT CORPORATION) | 6689 | 2023 | 2024-12-09 | 06/30/2023 | 0 | 0 | 2024-12-25 | 16
2024 | Region VI | ILOILO | DUMANGAS (ILOILO) | P00821052VS | Construction of Flood Mitigation Structure | 122.6976 | 10.7873 | 34300000 | 34239725.52 | 2025 | A.D. PENDON CONSTRUCTION & SUPPLY, INC. (FORMERLY: ADP CONSTRUCTION & SUPPLY) | 6690 | 2024 | 2025-02-24 | 02/12/2024 | 60274.48 | 0 | 2024-08-05 |  | 203
2022 | Region VI | ILOILO | ILOILO CITY (CAPITAL) (ILOILO) | P00620272VS | Construction of Revetment | 122.5491 | 10.8348 | 96499990.6 | 95504856.13 | 2023 | F. GURREA CONSTRUCTION, INCORPORATED | 6691 | 2022 | 2023-04-05 | 02/21/2022 | 995134.47 | 0 | 2023-04-04 |  | 1
2023 | Region V | CAMARINES NORTE | BASUD (CAMARINES NORTE) | P00736132LZ | Construction of Flood Mitigation Structure | 123.0593 | 13.8509 | 48249185.8 | 33586270.84 | 2023 | ALPHA & OMEGA GEN. CONTRACTOR & DEVELOPMENT CORP. | 6692 | 2023 | 2023-12-27 | 07/06/2023 | 14662914.96 | 0 | 2024-02-12 | 47
2022 | Region VI | NEGROS OCCIDENTAL | SAGAY CITY (NEGROS OCCIDENTAL) | P00630206VS | Construction of Flood Mitigation Structure | 123.3569 | 10.8887 | 48250000 | 48250000 | 2022 | A.C. RIVERO DEVELOPMENT CORPORATION | 6693 | 2022 | 2022-10-08 | 02/21/2022 | 0 | 0 | 2022-10-07 |  | 1
2022 | Region VI | AKLAN | KALIBO (CAPITAL) (AKLAN) | P00620290VS | Construction of Revetment | 122.3587 | 11.6948 | 49000000 | 48999996.04 | 2022 | CLIFFORD CONSTRUCTION CORPORATION | 6694 | 2022 | 2022-09-26 | 02/04/2022 | 3.96 | 0 | 2022-11-15 | 50
2022 | Region VI | NEGROS OCCIDENTAL | BACOLOD CITY (CAPITAL) (NEGROS OCCIDENTAL) | P00633213VS | Construction of Drainage Structure | 122.9472 | 10.6753 | 4950000 | 4950000 | 2022 | KENBE CONSTRUCTION & SUPPLY | 6695 | 2022 | 2022-09-28 | 03/25/2022 | 0 | 0 | 2022-10-19 | 21
2022 | Region VI | NEGROS OCCIDENTAL | CITY OF TALISAY (NEGROS OCCIDENTAL) | P00620102VS | Construction of Flood Mitigation Structure | 122.9853 | 10.7172 | 48999992.63 | 48998001.04 | 2022 | LEGACY CONSTRUCTION CORPORATION (FORMERLY: LEGACY CONSTRUCTION) | 6696 | 2022 | 2022-12-02 | 02/08/2022 | 1991.59 | 0 | 2022-12-01 |  | 1
2023 | Region VI | NEGROS OCCIDENTAL | SILAY CITY (NEGROS OCCIDENTAL) | P00721660VS | Construction of Flood Mitigation Structure | 122.9861 | 10.7956 | 25479993.35 | 25478000 | 2023 | XA CONSTRUCTION | 6697 | 2023 | 2023-08-02 | 02/13/2023 | 1993.35 | 0 | 2023-08-01 |  | 1
2024 | Region VI | NEGROS OCCIDENTAL | SILAY CITY (NEGROS OCCIDENTAL) | P00820175VS | Construction of Flood Mitigation Structure | 122.9861 | 10.7956 | 28213216.63 | 28213217.31 | 2024 | XA CONSTRUCTION | 6698 | 2024 | 2024-07-22 | 02/14/2024 | 0 | 0.68 | 2024-07-21 |  | 1
2024 | Region VI | NEGROS OCCIDENTAL | SILAY CITY (NEGROS OCCIDENTAL) | P00820176VS | Construction of Flood Mitigation Structure | 122.9872 | 10.8022 | 28213212.73 | 28213216.9 | 2024 | CANLAON BUILDERS AND DEVELOPMENT CORPORATION | 6699 | 2024 | 2024-06-17 | 02/14/2024 | 0 | 4.17 | 2024-07-21 | 34
2022 | Region VII | NEGROS ORIENTAL | CITY OF GUIHULNGAN (NEGROS ORIENTAL) | P00620138VS | Construction of Flood Mitigation Structure | 123.2929 | 10.1977 | 19600000 | 19600000 | 2022 | MIGHTY HOK SUMMIT CONSTRUCTION & DEVELOPMENT CORP. | 6700 | 2022 | 2022-11-23 | 02/08/2022 | 0 | 0 | 2022-11-22 |  | 1
2022 | Region VI | NEGROS OCCIDENTAL | CITY OF VICTORIAS (NEGROS OCCIDENTAL) | P00633001VS | Construction of Flood Mitigation Structure | 123.0605 | 10.9108 | 9799953.3 | 9798000 | 2022 | R.A.G. CORONA CONSTRUCTION AND AGGREGATES SUPPLY | 6701 | 2022 | 2022-07-15 | 03/30/2022 | 1953.3 | 0 | 2022-07-14 |  | 1
2021 | Region VI | ILOILO |  | P00521605VS | Construction of Flood Mitigation Structure | 122.6976 | 10.7874 | 23520000 | 22602830 | 2023 | ROPRIM CONSTRUCTION CORPORATION (FORMERLY ROPRIM CONSTRUCTION) | 6702 | 2021 | 2023-01-01 | 03/29/2022 | 917170 | 0 | 2022-09-12 |  | 111
2023 | Region V | CAMARINES SUR | SIPOCOT (CAMARINES SUR) | P00740487LZ | Construction of Flood Mitigation Structure | 122.9879 | 13.7419 | 82024895.94 | 82024887 | 2023 | G.C.I. CONSTRUCTION AND DEV'T. CORP. | 6703 | 2023 | 2023-12-06 | 04/19/2023 | 8.94 | 0 | 2023-12-05 |  | 1
2023 | Region VI | GUIMARAS | NUEVA VALENCIA (GUIMARAS) | P00721475VS | Construction of Flood Mitigation Structure | 122.5495 | 10.4166 | 57900000 | 57868773.82 | 2023 | ALPHA & OMEGA GEN. CONTRACTOR & DEVELOPMENT CORP. | 6704 | 2023 | 2023-10-02 | 02/17/2023 | 31226.18 | 0 | 2023-11-17 | 46
2023 | Region VI | AKLAN | KALIBO (CAPITAL) (AKLAN) | P00721988VS | Construction of Flood Mitigation Structure | 122.3587 | 11.6948 | 49000000 | 48999989.53 | 2023 | CLIFFORD CONSTRUCTION CORPORATION | 6705 | 2023 | 2023-10-16 | 04/03/2023 | 10.47 | 0 | 2023-12-08 | 53
2021 | Region IX | ZAMBOANGA DEL NORTE |  | P00522145MN | [11 empty] | 0 | 0
2023 | Region VI | NEGROS OCCIDENTAL | CITY OF VICTORIAS (NEGROS OCCIDENTAL) | P00733300VS | Construction of Flood Mitigation Structure | 123.0628 | 10.9159 | 29399997.54 | 29399997.54 | 2023 | R.A.G. CORONA CONSTRUCTION AND AGGREGATES SUPPLY | 6707 | 2023 | 2023-09-20 | 04/04/2023 | 0 | 0 | 2023-09-19 |  | 1
2024 | Region VII | NEGROS ORIENTAL | CITY OF BAYAWAN (TULONG) (NEGROS ORIENTAL) | P00820405VS | Construction of Flood Mitigation Structure | 122.7133 | 9.3842 | 45080000 | 45080000 | 2024 | ALPHA & OMEGA GEN. CONTRACTOR & DEVELOPMENT CORP. | 6708 | 2024 | 2024-10-24 | 04/11/2024 | 0 | 0 | 2024-10-31 | 7
2022 | Region VI | NEGROS OCCIDENTAL | HINIGARAN (NEGROS OCCIDENTAL) | P00630176VS | Construction of Slope Protection Structure | 122.9476 | 10.2344 | 96500000 | 96499992 | 2022 | A.C. RIVERO DEVELOPMENT CORPORATION | 6709 | 2022 | 2022-09-30 | 02/17/2022 | 8 | 0 | 2022-10-14 | 14
2022 | Region V | CAMARINES SUR | BATO (CAMARINES SUR) | P00620726LZ | Construction of Dike | 123.3571 | 13.3579 | 49000000 | 48999292.44 | 2022 | MEGAY CONSTRUCTION INC. (FORMERLY: MEGAY CONSTRUCTION) | 6710 | 2022 | 2022-08-15 | 02/22/2022 | 707.56 | 0 | 2022-09-08 | 24
2023 | Region VI | GUIMARAS | NUEVA VALENCIA (GUIMARAS) | P00721474VS | Construction of Flood Mitigation Structure | 122.5496 | 10.4166 | 57900000 | 57895645.35 | 2023 | F. GURREA CONSTRUCTION, INCORPORATED | 6711 | 2023 | 2023-10-25 | 02/11/2023 | 4354.65 | 0 | 2023-11-11 | 17
2024 | Region V | CAMARINES SUR | TINAMBAC (CAMARINES SUR) | P00824783LZ | Construction of Flood Mitigation Structure | 123.2933 | 13.9048 | 49000000 | 49000000 | 2024 | SPRING STAR CONSTRUCTION AND SUPPLY | 6712 | 2024 | 2024-11-11 | 03/14/2024 | 0 | 0 | 2024-11-24 | 13
2023 | Region VI | NEGROS OCCIDENTAL | CITY OF VICTORIAS (NEGROS OCCIDENTAL) | P00731613VS | Rehabilitation / Major Repair of Flood Control Structure | 123.0631 | 10.9161 | 86849986.31 | 86847967 | 2023 | LEGACY CONSTRUCTION CORPORATION (FORMERLY: LEGACY CONSTRUCTION) | 6713 | 2023 | 2023-11-24 | 02/14/2023 | 2019.31 | 0 | 2023-11-23 |  | 1
2022 | Region VII | NEGROS ORIENTAL | CITY OF BAYAWAN (TULONG) (NEGROS ORIENTAL) | P00620318VS | Rehabilitation / Major Repair of Flood Control Structure | 122.7136 | 9.3858 | 40709200 | 40709200 | 2023 | LEGACY CONSTRUCTION CORPORATION (FORMERLY: LEGACY CONSTRUCTION) | 6714 | 2022 | 2023-03-18 | 03/15/2022 | 0 | 0 | 2023-03-17 |  | 1
2024 | Region IX | ZAMBOANGA DEL NORTE | POLANCO (ZAMBOANGA DEL NORTE) | P00820003MN | Construction of Flood Mitigation Structure | 123.3579 | 8.5125 | 77584070 | 77584062.83 | 2024 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R | 6715 | 2024 | 2024-10-27 | 03/20/2024 | 7.17 | 0 | 2024-12-15 | 49
2022 | Region VI | NEGROS OCCIDENTAL | CITY OF TALISAY (NEGROS OCCIDENTAL) | P00620101VS | Construction of Flood Mitigation Structure | 122.9903 | 10.7094 | 48999991.11 | 48997999 | 2022 | A.C. RIVERO DEVELOPMENT CORPORATION | 6716 | 2022 | 2022-08-07 | 02/08/2022 | 1992.11 | 0 | 2022-08-06 |  | 1
2022 | Region VI | ILOILO | CALINOG (ILOILO) | P00620435VS | Construction of Flood Mitigation Structure | 122.5501 | 11.1208 | 34300000 | 34299962.78 | 2022 | EARLY RISER CONSTRUCTION / CMG JR. BUILDERS | 6717 | 2022 | 2022-10-30 | 03/29/2022 | 37.22 | 0 | 2022-10-05 |  | 25
2022 | Region VI | NEGROS OCCIDENTAL | BACOLOD CITY (CAPITAL) (NEGROS OCCIDENTAL) | P00620423VS | Construction of Revetment | 122.9477 | 10.677 | 16331700 | 15515114.99 | 2023 | SILVERRIA CONSTRUCTION AND CONSTRUCTION SUPPLY COMPANY, OPC | 6718 | 2022 | 2023-08-28 | 03/25/2022 | 816585.01 | 0 | 2022-08-04 |  | 389
2024 | Region VII | NEGROS ORIENTAL | AYUNGON (NEGROS ORIENTAL) | P00820195VS | Construction of Flood Mitigation Structure | 123.0632 | 9.9054 | 2940000 | 2940000 | 2024 | HIGEL CONSTRUCTION | 6719 | 2024 | 2024-08-16 | 02/07/2024 | 0 | 0 | 2024-08-15 |  | 1
2023 | Region VII | NEGROS ORIENTAL | CITY OF BAYAWAN (TULONG) (NEGROS ORIENTAL) | P00721688VS | Construction of Flood Mitigation Structure | 122.7139 | 9.3861 | 49000000 | 49000000 | 2023 | LEGACY CONSTRUCTION CORPORATION (FORMERLY: LEGACY CONSTRUCTION) | 6720 | 2023 | 2023-12-03 | 03/24/2023 | 0 | 0 | 2023-12-02 |  | 1
2024 | Region VI | AKLAN | KALIBO (CAPITAL) (AKLAN) | P00821159VS | Construction of Revetment | 122.3597 | 11.7057 | 28950000 | 28949995.94 | 2024 | CLIFFORD CONSTRUCTION CORPORATION | 6721 | 2024 | 2024-07-09 | 03/07/2024 | 4.06 | 0 | 2024-09-02 | 55
2022 | Region VI | ILOILO | ILOILO CITY (CAPITAL) (ILOILO) | P00630205VS | Rehabilitation / Major Repair of Flood Control Structure | 122.5542 | 10.7568 | 41012500 | 41650000 | 2023 | IBC INTERNATIONAL BUILDERS CORPORATION | 6722 | 2022 | 2023-08-08 | 08/15/2022 | 0 | 637500 | 2023-08-07 |  | 1
2024 | Region VII | NEGROS ORIENTAL | CITY OF GUIHULNGAN (NEGROS ORIENTAL) | P00820200VS | Construction of Flood Mitigation Structure | 123.294 | 10.1964 | 14700000 | 14624973.33 | 2024 | ALEXANDRIA CONSTRUCTION AND SUPPLY | 6723 | 2024 | 2024-08-05 | 02/07/2024 | 75026.67 | 0 | 2024-08-04 |  | 1
2022 | Region V | CAMARINES SUR | LIBMANAN (CAMARINES SUR) | P00620718LZ | Construction of Revetment | 123.0633 | 13.6914 | 49000000 | 48024732 | 2022 | BICOL GOLDROCK CONSTRUCTION CORPORATION | 6724 | 2022 | 2022-09-20 | 02/28/2022 | 975268 | 0 | 2022-09-19 |  | 1
2022 | Region VI | ILOILO | ILOILO CITY (CAPITAL) (ILOILO) | P00630204VS | Rehabilitation / Major Repair of Flood Control Structure | 122.5544 | 10.7575 | 41012500 | 41650000 | 2023 | IBC INTERNATIONAL BUILDERS CORPORATION | 6725 | 2022 | 2023-08-13 | 08/15/2022 | 0 | 637500 | 2023-08-12 |  | 1
2023 | Region VI | AKLAN | MAKATO (AKLAN) | P00721725VS | Construction of Revetment | 122.3615 | 11.7241 | 86850000 | 86849862.21 | 2024 | GREAT PACIFIC BUILDERS AND GEN. CONTRACTOR INC. | 6726 | 2023 | 2024-02-01 | 02/07/2023 | 137.79 | 0 | 2024-01-31 |  | 1
2022 | Region VII | NEGROS ORIENTAL | CITY OF BAYAWAN (TULONG) (NEGROS ORIENTAL) | P00620317VS | Rehabilitation / Major Repair of Flood Control Structure | 122.715 | 9.3903 | 29782200 | 29782200 | 2023 | LEGACY CONSTRUCTION CORPORATION (FORMERLY: LEGACY CONSTRUCTION) | 6727 | 2022 | 2023-02-22 | 03/21/2022 | 0 | 0 | 2023-02-07 |  | 15
2024 | Region VI | NEGROS OCCIDENTAL | BACOLOD CITY (CAPITAL) (NEGROS OCCIDENTAL) | P00832623VS | Construction of Drainage Structure | 122.9905 | 10.6884 | 6435000 | 6435000 | 2024 | SILVERRIA CONSTRUCTION AND CONSTRUCTION SUPPLY COMPANY, OPC | 6728 | 2024 | 2024-07-21 | 04/03/2024 | 0 | 0 | 2024-07-20 |  | 1
2021 | Region VI | NEGROS OCCIDENTAL |  | P00521583VS | Construction of Revetment | 122.9478 | 10.7036 | 29400000 | 29400000 | 2023 | SILVER DRAGON CONSTRUCTION & LUMBER & GLASS SUPPLY INC. | 6729 | 2021 | 2023-10-30 | 10/07/2021 | 0 | 0 | 2022-06-19 |  | 498
2022 | Region VI | NEGROS OCCIDENTAL | ISABELA (NEGROS OCCIDENTAL) | P00630177VS | Construction of Slope Protection Structure | 122.9481 | 10.2359 | 96500000 | 96496538.43 | 2022 | JAIME B. CHING ENTERPRISES | 6730 | 2022 | 2022-10-21 | 02/23/2022 | 3461.57 | 0 | 2022-10-20 |  | 1
2020 | Region V | CAMARINES SUR |  | P00448880LZ | Rehabilitation / Major Repair of Flood Control Structure | 123.2945 | 13.4456 | 74250000 | 70888755.4 | 2022 | ALRO CONSTRUCTION & DEVELOPMENT CORP. | 6731 | 2020 | 2022-08-16 | 12/07/2020 | 3361244.6 | 0 | 2022-06-27 |  | 50
2022 | Region IX | ZAMBOANGA DEL NORTE | POLANCO (ZAMBOANGA DEL NORTE) | P00620003MN | Construction of Revetment | 123.3589 | 8.5131 | 66100000 | 66096928.66 | 2023 | LEGACY CONSTRUCTION CORPORATION (FORMERLY: LEGACY CONSTRUCTION) | 6732 | 2022 | 2023-05-13 | 02/24/2022 | 3071.34 | 0 | 2023-05-12 |  | 1
2022 | Region V | CAMARINES NORTE | DAET (CAPITAL) (CAMARINES NORTE) | P00620282LZ | Construction of Flood Mitigation Structure | 122.9489 | 14.1144 | 82024458.68 | 82021322.03 | 2022 | WIZARD CONCRETE SOLUTIONS AND CONSTRUCTION CORPORATION (FORMERLY: WIZARD TRADING & CONSTRUCTION) | 6733 | 2022 | 2022-11-22 | 03/16/2022 | 3136.65 | 0 | 2022-11-21 |  | 1
2021 | Region V | CAMARINES SUR |  | P00448880LZ | Rehabilitation / Major Repair of Flood Control Structure | 123.2945 | 13.4456 | 74250000 | 70888755.4 | 2022 | ALRO CONSTRUCTION & DEVELOPMENT CORP. | 6734 | 2021 | 2022-08-16 | 12/07/2020 | 3361244.6 | 0 | 2022-06-27 |  | 50
2024 | Region VI | NEGROS OCCIDENTAL | SAN CARLOS CITY (NEGROS OCCIDENTAL) | P00820012VS | Construction of Flood Mitigation Structure | 123.3594 | 10.4461 | 96500000 | 96500000 | 2024 | WILKINSON CONSTRUCTION | 6735 | 2024 | 2024-10-03 | 03/01/2024 | 0 | 0 | 2025-01-13 | 102
2023 | Region VI | NEGROS OCCIDENTAL | CITY OF VICTORIAS (NEGROS OCCIDENTAL) | P00731614VS | Construction of Flood Mitigation Structure | 123.0646 | 10.9051 | 53074992.48 | 53072822 | 2023 | SUPREME ABF CONST. & CONST. SUPPLY COMPANY INC. | 6736 | 2023 | 2023-10-17 | 02/14/2023 | 2170.48 | 0 | 2023-10-16 |  | 1
2023 | Region VI | ILOILO | ILOILO CITY (CAPITAL) (ILOILO) | P00733723VS | Rehabilitation / Major Repair of Drainage Structure | 122.5545 | 10.7363 | 4950000 | 4929675.72 | 2023 | A.D. PENDON CONSTRUCTION & SUPPLY, INC. (FORMERLY: ADP CONSTRUCTION & SUPPLY) | 6737 | 2023 | 2023-09-21 | 06/08/2023 | 20324.28 | 0 | 2023-09-20 |  | 1
2022 | Region VI | CAPIZ | ROXAS CITY (CAPITAL) (CAPIZ) | P00633215VS | Construction of Drainage Structure | 122.7314 | 11.5874 | 4950000 | 4949423.38 | 2022 | RCDG CONSTRUCTION CORPORATION | 6738 | 2022 | 2022-10-31 | 05/31/2022 | 576.62 | 0 | 2022-12-01 | 31
2024 | Region V | CAMARINES SUR | SIPOCOT (CAMARINES SUR) | P00821006LZ | Construction of Flood Mitigation Structure | 122.9907 | 13.7424 | 9799395.54 | 9680309 | 2024 | BICOL GOLDROCK CONSTRUCTION CORPORATION | 6739 | 2024 | 2024-05-01 | 03/01/2024 | 119086.54 | 0 | 2024-04-30 |  | 1
2024 | Region V | CAMARINES NORTE | BASUD (CAMARINES NORTE) | P00820469LZ | Construction of Flood Mitigation Structure | 122.9489 | 13.9664 | 154399294.6 | 154399262.8 | 2024 | PARTIDO CONSTRUCTION & SUPPLY | 6740 | 2024 | 2024-11-30 | 04/08/2024 | 31.8 | 0 | 2025-02-05 | 67
2022 | Region VII | NEGROS ORIENTAL | DUMAGUETE CITY (CAPITAL) (NEGROS ORIENTAL) | P00630227VS | Construction of Flood Mitigation Structure | 123.2953 | 9.2836 | 49000000 | 49000000 | 2023 | SUPREME MEGA STRUCTURE BUILDERS, INC. / SYNDTITE CONSTRUCTION CORPORATION (FORMERLY: R.C. TAGALA CONSTRUCTION) | 6741 | 2022 | 2023-11-20 | 05/27/2022 | 0 | 0 | 2024-01-04 | 45
2022 | Region VI | AKLAN | KALIBO (CAPITAL) (AKLAN) | P00620292VS | Construction of Revetment | 122.3626 | 11.6968 | 48250000 | 48249999.5 | 2023 | F & J GENERAL CONSTRUCTION AND SUPPLY CORPORATION | 6742 | 2022 | 2023-05-15 | 06/08/2022 | 0.5 | 0 | 2023-06-10 | 26
2023 | Region V | CAMARINES SUR | LIBMANAN (CAMARINES SUR) | P00736129LZ | Construction of Revetment | 123.0649 | 13.6673 | 52232555 | 52205593.07 | 2024 | BICOL GOLDROCK CONSTRUCTION CORPORATION | 6743 | 2023 | 2024-03-15 | 07/03/2023 | 26961.93 | 0 | 2024-03-22 | 7
2023 | Region VII | NEGROS ORIENTAL | MABINAY (NEGROS ORIENTAL) | P00721781VS | Rehabilitation / Major Repair of Flood Control Structure | 122.949 | 9.6881 | 53557500 | 53557500 | 2023 | PHILSOUTH BUILDERS INC (FORMERLY:PHILSOUTH BUILDERS) | 6744 | 2023 | 2023-11-30 | 02/17/2023 | 0 | 0 | 2023-11-02 |  | 28
2023 | Region IX | ZAMBOANGA DEL NORTE | SALUG (ZAMBOANGA DEL NORTE) | P00721212MN | Construction of Flood Mitigation Structure | 122.7511 | 8.1043 | 110975000 | 110974998.9 | 2023 | MONTAÃ‘O CONSTRUCTION & DEVELOPMENT CORPORATION / DOMNPHIL CONSTRUCTION | 6745 | 2023 | 2023-11-22 | 03/20/2023 | 1.1 | 0 | 2023-11-21 |  | 1
2024 | Region VI | NEGROS OCCIDENTAL | CITY OF TALISAY (NEGROS OCCIDENTAL) | P00834559VS | Construction of Flood Mitigation Structure | 122.9913 | 10.7053 | 96499989.11 | 96498004.56 | 2024 | SILVERGRACES CONSTRUCTION AND CONSTRUCTION SUPPLY | 6746 | 2024 | 2024-11-01 | 03/13/2024 | 1984.55 | 0 | 2024-10-31 |  | 1
2022 | Region IX | ZAMBOANGA DEL NORTE | KATIPUNAN (ZAMBOANGA DEL NORTE) | P00620111MN | Construction of Flood Mitigation Structure | 123.2987 | 8.5062 | 39808090 | 39708089.93 | 2024 | MONTAÃ‘O CONSTRUCTION & DEVELOPMENT CORPORATION | 6747 | 2022 | 2024-09-30 | 02/10/2022 | 100000.07 | 0 | 2022-08-07 |  | 785
2023 | Region VI | AKLAN | KALIBO (CAPITAL) (AKLAN) | P00721989VS | Construction of Flood Mitigation Structure | 122.3646 | 11.7181 | 49000000 | 48999993.67 | 2024 | G.F. ROVERO MERCHANDISING | 6748 | 2023 | 2024-01-22 | 04/28/2023 | 6.33 | 0 | 2024-03-29 | 67
2023 | Region V | CAMARINES SUR | BATO (CAMARINES SUR) | P00725902LZ | Construction of Flood Mitigation Structure | 123.3605 | 13.3615 | 121061136.6 | 121061136.6 | 2024 | BICOL GOLDROCK CONSTRUCTION CORPORATION | 6749 | 2023 | 2024-03-31 | 03/27/2023 | 0 | 0 | 2024-04-03 | 3
2022 | Region VI | NEGROS OCCIDENTAL | CITY OF VICTORIAS (NEGROS OCCIDENTAL) | P00630639VS | Construction of Drainage Structure | 123.0664 | 10.9031 | 11780999.11 | 11778985 | 2022 | KENBE CONSTRUCTION & SUPPLY | 6750 | 2022 | 2022-07-17 | 02/08/2022 | 2014.11 | 0 | 2022-07-16 |  | 1
2022 | Region VI | NEGROS OCCIDENTAL | BACOLOD CITY (CAPITAL) (NEGROS OCCIDENTAL) | P00632029VS | Construction of Drainage Structure | 122.9924 | 10.6822 | 16830000 | 16830000 | 2023 | ALTA NEGROS INDUSTRIAL SUPPLY CORPORATION | 6751 | 2022 | 2023-02-27 | 03/25/2022 | 0 | 0 | 2022-10-25 |  | 125
2023 | Region VI | NEGROS OCCIDENTAL | SILAY CITY (NEGROS OCCIDENTAL) | P00732019VS | Construction of Flood Mitigation Structure | 122.949 | 10.8369 | 5939829.15 | 5938000 | 2023 | CANLAON BUILDERS AND DEVELOPMENT CORPORATION | 6752 | 2023 | 2023-05-07 | 02/13/2023 | 1829.15 | 0 | 2023-05-06 |  | 1
2022 | Region VI | ILOILO | ILOILO CITY (CAPITAL) (ILOILO) | P00620017VS | Construction of Slope Protection Structure | 122.5558 | 10.7316 | 50690967.5 | 49840615.93 | 2023 | S.T. SALCEDO CONSTRUCTION CORP.(FORMERLY: SHAK CONSTRUCTION & SUPPLY) | 6753 | 2022 | 2023-11-27 | 04/11/2022 | 850351.57 | 0 | 2023-06-01 |  | 179
2023 | Region IX | ZAMBOANGA DEL NORTE | SALUG (ZAMBOANGA DEL NORTE) | P00721211MN | Construction of Flood Mitigation Structure | 122.7525 | 8.1058 | 110975000 | 110528273.3 | 2023 | GREAT PACIFIC BUILDERS AND GEN. CONTRACTOR INC. | 6754 | 2023 | 2023-11-22 | 03/20/2023 | 446726.7 | 0 | 2023-11-21 |  | 1
2024 | Region V | CAMARINES SUR | SIRUMA (CAMARINES SUR) | P00824782LZ | Construction of Flood Mitigation Structure | 123.299 | 14.0519 | 49000000 | 49000000 | 2024 | BICOL GOLDROCK CONSTRUCTION CORPORATION | 6755 | 2024 | 2024-10-16 | 02/18/2024 | 0 | 0 | 2024-11-03 | 18
2022 | Region VI | NEGROS OCCIDENTAL | SAGAY CITY (NEGROS OCCIDENTAL) | P00620104VS | Construction of Flood Mitigation Structure | 123.3627 | 10.9032 | 44099946.95 | 44097954.14 | 2022 | SUPREME ABF CONST. & CONST. SUPPLY COMPANY INC. | 6756 | 2022 | 2022-11-05 | 02/08/2022 | 1992.81 | 0 | 2022-11-04 |  | 1
2023 | Region V | CAMARINES NORTE | SANTA ELENA (CAMARINES NORTE) | P00737556LZ | Construction of Flood Mitigation Structure | 122.3666 | 14.2369 | 9899549.73 | 9765731.14 | 2023 | GREAT WALL ENGINEERING | 6757 | 2023 | 2023-06-28 | 04/05/2023 | 133818.59 | 0 | 2023-06-27 |  | 1
2023 | Region VI | NEGROS OCCIDENTAL | CITY OF VICTORIAS (NEGROS OCCIDENTAL) | P00733301VS | Construction of Flood Mitigation Structure | 123.0719 | 10.8975 | 9799993.26 | 9799993.26 | 2023 | KENBE CONSTRUCTION & SUPPLY | 6758 | 2023 | 2023-08-19 | 04/04/2023 | 0 | 0 | 2023-08-18 |  | 1
2024 | Region VI | NEGROS OCCIDENTAL | ISABELA (NEGROS OCCIDENTAL) | P00820001VS | Construction of Slope Protection Structure | 122.993 | 10.2274 | 96500000 | 95052356.29 | 2024 | LEGACY CONSTRUCTION CORPORATION (FORMERLY: LEGACY CONSTRUCTION) | 6759 | 2024 | 2024-08-05 | 02/14/2024 | 1447643.71 | 0 | 2024-10-10 | 66
2024 | Region VI | NEGROS OCCIDENTAL | CITY OF VICTORIAS (NEGROS OCCIDENTAL) | P00834639VS | Construction of Flood Mitigation Structure | 123.0761 | 10.9103 | 9899991.56 | 9797929.22 | 2024 | SL & G CONSTRUCTION | 6760 | 2024 | 2024-06-22 | 03/13/2024 | 102062.34 | 0 | 2024-06-21 |  | 1
2022 | Region V | CAMARINES NORTE | TALISAY (CAMARINES NORTE) | P00631403LZ | Construction of Flood Mitigation Structure | 122.9494 | 14.1421 | 42139864.61 | 42139864.61 | 2022 | BRENTMIN ROOFING ENTERPRISE | 6761 | 2022 | 2022-09-16 | 03/15/2022 | 0 | 0 | 2022-09-15 |  | 1
2023 | Region VI | NEGROS OCCIDENTAL | CADIZ CITY (NEGROS OCCIDENTAL) | P00721470VS | Construction of Flood Mitigation Structure | 123.2991 | 10.9628 | 86849997.34 | 86846790 | 2023 | C'ZARLES CONSTRUCTION & SUPPLY / GKMM CONSTRUCTION & SUPPLIES, INC. (FORMERLY: GKMM CONSTRUCTION & SUPPLIES) | 6762 | 2023 | 2023-11-20 | 02/14/2023 | 3207.34 | 0 | 2024-03-08 | 109
2023 | Region VI | ILOILO | ILOILO CITY (CAPITAL) (ILOILO) | P00733730VS | Construction of Drainage Structure | 122.5564 | 10.725 | 9900000 | 9849144.79 | 2023 | ABELARDE BUILDERS AND SUPPLY | 6763 | 2023 | 2023-09-22 | 04/17/2023 | 50855.21 | 0 | 2023-08-29 |  | 24
2021 | Region IX | ZAMBOANGA SIBUGAY |  | P00522029MN | Construction of Flood Mitigation Structure | 122.7531 | 7.8041 | 115719689.6 | 114564540.7 | 2022 | ALPHA & OMEGA GEN. CONTRACTOR & DEVELOPMENT CORP. | 6764 | 2021 | 2022-09-07 | 02/22/2021 | 1155148.9 | 0 | 2022-09-06 |  | 1
2022 | Region IV-A | QUEZON | LOPEZ (QUEZON) | P00621100LZ | Construction of Flood Mitigation Structure | 122.3705 | 13.8243 | 9800000 | 9800000 | 2022 | TG SURCON BUILDERS INC. | 6765 | 2022 | 2022-07-21 | 02/15/2022 | 0 | 0 | 2022-07-20 |  | 1
2023 | Region VII | CEBU | ALEGRIA (CEBU) | P00733279VS | Construction of Flood Mitigation Structure | 123.3656 | 9.7779 | 96493832.09 | 96493771.15 | 2024 | QM BUILDERS | 6766 | 2023 | 2024-01-11 | 05/05/2023 | 60.94 | 0 | 2024-03-05 | 54
2022 | Region VI | NEGROS OCCIDENTAL | CITY OF TALISAY (NEGROS OCCIDENTAL) | P00620408VS | Construction of Flood Mitigation Structure | 122.9933 | 10.7125 | 48999989.07 | 48998000 | 2022 | IGWT-JAV CONSTRUCTION & DEVELOPMENT CORPORATION / EGB CONSTRUCTION CORPORATION (FORMERLY: EGB CONSTRUCTION) | 6767 | 2022 | 2022-11-25 | 03/30/2022 | 1989.07 | 0 | 2022-11-24 |  | 1
2021 | Region VII | NEGROS ORIENTAL |  | P00549969VS | Construction of Flood Mitigation Structure | 123.0765 | 9.4577 | 77200000 | 77200000 | 2022 | UY CONDEV CORPORATION (FORMERLY:UY CONSTRUCTION & | 6768 | 2021 | 2022-12-23 | 10/22/2021 | 0 | 0 | 2022-12-26 | 3
2022 | Region VI | NEGROS OCCIDENTAL | SILAY CITY (NEGROS OCCIDENTAL) | P00620105VS | Construction of Flood Mitigation Structure | 122.9972 | 10.7576 | 48999965.8 | 48997998 | 2022 | SUPREME ABF CONST. & CONST. SUPPLY COMPANY INC. | 6769 | 2022 | 2022-09-16 | 02/08/2022 | 1967.8 | 0 | 2022-09-15 |  | 1
2023 | Region VI | GUIMARAS | NUEVA VALENCIA (GUIMARAS) | P00721868VS | Construction of Flood Mitigation Structure | 122.5601 | 10.4293 | 57900000 | 57899915.92 | 2023 | ALPHA & OMEGA GEN. CONTRACTOR & DEVELOPMENT CORP. / S.T. SALCEDO CONSTRUCTION CORP.(FORMERLY: SHAK CONSTRUCTION & SUPPLY) | 6770 | 2023 | 2023-11-27 | 03/17/2023 | 84.08 | 0 | 2023-12-25 | 28
2023 | Region VII | CEBU | ALEGRIA (CEBU) | P00733280VS | Construction of Flood Mitigation Structure | 123.3656 | 9.7779 | 96493838.37 | 96493822.06 | 2023 | QM BUILDERS | 6771 | 2023 | 2023-09-21 | 05/05/2023 | 16.31 | 0 | 2024-03-05 | 166
2024 | Region V | CAMARINES NORTE | DAET (CAPITAL) (CAMARINES NORTE) | P00845842LZ | Construction of Flood Mitigation Structure | 122.9495 | 14.0931 | 4949985.81 | 4949985.81 | 2024 | 888RV CONSTRUCTION AND SUPPLIES | 6772 | 2024 | 2024-08-05 | 05/31/2024 | 0 | 0 | 2024-08-04 |  | 1
2023 | Region VI | AKLAN | KALIBO (CAPITAL) (AKLAN) | P00721923VS | Construction of Revetment | 122.3713 | 11.719 | 29400000 | 29399989.61 | 2023 | G.F. ROVERO MERCHANDISING | 6773 | 2023 | 2023-11-23 | 05/10/2023 | 10.39 | 0 | 2024-01-04 | 42
2022 | Region VI | NEGROS OCCIDENTAL | CITY OF VICTORIAS (NEGROS OCCIDENTAL) | P00632999VS | Construction of Flood Mitigation Structure | 123.0775 | 10.8958 | 24499930.64 | 24498000 | 2022 | R.A.G. CORONA CONSTRUCTION AND AGGREGATES SUPPLY | 6774 | 2022 | 2022-08-30 | 03/30/2022 | 1930.64 | 0 | 2022-08-29 |  | 1
2024 | Region IX | ZAMBOANGA SIBUGAY | KABASALAN (ZAMBOANGA SIBUGAY) | P00835861MN | Construction of Flood Mitigation Structure | 122.7541 | 7.8091 | 29400000 | 20431934.07 | 2025 | DEBRIS ENTERPRISES AND CONSTRUCTION | 6775 | 2024 | 2025-01-20 | 07/15/2024 | 8968065.93 | 0 | 2025-01-22 | 2
2024 | Region V | CAMARINES SUR | PILI (CAPITAL) (CAMARINES SUR) | P00846122LZ | Construction of Flood Mitigation Structure | 123.3006 | 13.6205 | 9799903.37 | 9693474.21 | 2024 | MEGA-ANT BUILDERS AND CONSTRUCTION SUPPLIES | 6776 | 2024 | 2024-08-08 | 04/05/2024 | 106429.16 | 0 | 2024-11-05 | 89
2023 | Region VI | NEGROS OCCIDENTAL | BACOLOD CITY (CAPITAL) (NEGROS OCCIDENTAL) | P00721628VS | Construction of Drainage Structure | 122.9496 | 10.6622 | 29400000 | 28963474.65 | 2023 | GOLDSTAR MARKETING & CONSTRUCTION SERVICES, INC. | 6777 | 2023 | 2023-08-28 | 02/08/2023 | 436525.35 | 0 | 2023-09-12 | 15
2023 | Region VI | ILOILO | ILOILO CITY (CAPITAL) (ILOILO) | P00721864VS | Construction of Flood Mitigation Structure | 122.5607 | 10.6905 | 96500000 | 96500000 | 2024 | PANAY EAST COAST CONSTRUCTION & SUPPLY / A.D. PENDON CONSTRUCTION & SUPPLY, INC. (FORMERLY: ADP CONSTRUCTION & SUPPLY) | 6778 | 2023 | 2024-12-18 | 08/23/2023 | 0 | 0 | 2024-12-23 | 5
2022 | Region VI | AKLAN | KALIBO (CAPITAL) (AKLAN) | P00620288VS | Construction of Revetment | 122.3718 | 11.7201 | 49000000 | 48999996.13 | 2023 | S.T. SALCEDO CONSTRUCTION CORP.(FORMERLY: SHAK CONSTRUCTION & SUPPLY) | 6779 | 2022 | 2023-02-09 | 02/18/2022 | 3.87 | 0 | 2023-02-10 | 1
2024 | Region VI | NEGROS OCCIDENTAL | CITY OF VICTORIAS (NEGROS OCCIDENTAL) | P00832633VS | Construction of Flood Mitigation Structure | 123.0786 | 10.9061 | 9899998.79 | 9899999.42 | 2024 | CBCL CONSTRUCTION & SUPPLY | 6780 | 2024 | 2024-06-07 | 02/19/2024 | 0 | 0.63 | 2024-06-06 |  | 1
2023 | Region VII | CEBU | BADIAN (CEBU) | P00745596VS | Rehabilitation / Major Repair of Flood Control Structure | 123.368 | 9.8092 | 71745219.27 | 71744573.2 | 2024 | WTG CONSTRUCTION & DEVELOPMENT CORPORATION | 6781 | 2023 | 2024-04-24 | 08/10/2023 | 646.07 | 0 | 2024-04-26 | 2
2022 | Region VI | NEGROS OCCIDENTAL | ISABELA (NEGROS OCCIDENTAL) | P00620242VS | Construction of Slope Protection Structure | 122.9499 | 10.2335 | 96500000 | 96499995.37 | 2023 | R.A. CONSTRUCTION DEVELOPMENT CORPORATION (FORMERLY: R.A. CONSTRUCTION & GENERAL MERCHANDISE) / JAIME B. CHING ENTERPRISES | 6782 | 2022 | 2023-01-21 | 02/17/2022 | 4.63 | 0 | 2023-01-20 |  | 1
2022 | Region VI | NEGROS OCCIDENTAL | CADIZ CITY (NEGROS OCCIDENTAL) | P00630634VS | Construction of Drainage Structure | 123.3021 | 10.9315 | 9899993.28 | 9897858 | 2022 | PJD CONSTRUCTION AND SUPPLY | 6783 | 2022 | 2022-08-01 | 02/08/2022 | 2135.28 | 0 | 2022-07-31 |  | 1
2023 | Region VI | ILOILO | ILOILO CITY (CAPITAL) (ILOILO) | P00733721VS | Construction of Drainage Structure | 122.5618 | 10.7235 | 4950000 | 4934487.18 | 2023 | LUCKY H&K CONSTRUCTION | 6784 | 2023 | 2023-07-31 | 04/17/2023 | 15512.82 | 0 | 2023-07-30 |  | 1
2024 | Region IX | ZAMBOANGA DEL SUR | BAYOG (ZAMBOANGA DEL SUR) | P00820394MN | Construction of Flood Mitigation Structure | 122.9985 | 7.8064 | 49000000 | 49000000 | 2024 | BADSBRO CONSTRUCTION AND GENERAL MERCHANDISE | 6785 | 2024 | 2024-10-31 | 03/22/2024 | 0 | 0 | 2024-10-30 |  | 1
2022 | Region VI | CAPIZ | PANITAN (CAPIZ) | P00620261VS | Construction of Flood Mitigation Structure | 122.7587 | 11.4447 | 62725000 | 62724502.62 | 2022 | A.D. PENDON CONSTRUCTION & SUPPLY, INC. (FORMERLY: ADP CONSTRUCTION & SUPPLY) | 6786 | 2022 | 2022-12-12 | 02/28/2022 | 497.38 | 0 | 2022-12-11 |  | 1
2023 | Region VI | ILOILO | ILOILO CITY (CAPITAL) (ILOILO) | P00721863VS | Construction of Flood Mitigation Structure | 122.5622 | 10.6904 | 96500000 | 96500000 | 2024 | METRO GEAR CONSTRUCTION CORP. / A.D. PENDON CONSTRUCTION & SUPPLY, INC. (FORMERLY: ADP CONSTRUCTION & SUPPLY) | 6787 | 2023 | 2024-11-25 | 08/23/2023 | 0 | 0 | 2024-11-24 |  | 1
2022 | Region VI | ILOILO | TIGBAUAN (ILOILO) | P00633216VS | Construction of Flood Mitigation Structure | 122.374 | 10.6774 | 4950000 | 4940135.94 | 2022 | PANAY EAST COAST CONSTRUCTION & SUPPLY | 6788 | 2022 | 2022-12-05 | 05/23/2022 | 9864.06 | 0 | 2022-10-29 |  | 37
2023 | Region VII | CEBU | ALEGRIA (CEBU) | P00733278VS | Construction of Flood Mitigation Structure | 123.3686 | 9.7733 | 67543921.09 | 67543892.79 | 2023 | QM BUILDERS | 6789 | 2023 | 2023-10-19 | 05/05/2023 | 28.3 | 0 | 2024-01-12 | 85
2022 | Region VI | NEGROS OCCIDENTAL | HINIGARAN (NEGROS OCCIDENTAL) | P00620243VS | Construction of Slope Protection Structure | 122.9502 | 10.2338 | 96500000 | 96499996.46 | 2022 | SUPREME ABF CONST. & CONST. SUPPLY COMPANY INC. | 6790 | 2022 | 2022-12-15 | 02/17/2022 | 3.54 | 0 | 2023-01-02 | 18
2023 | Region IX | ZAMBOANGA SIBUGAY | BUUG (ZAMBOANGA SIBUGAY) | P00721659MN | Construction of Flood Mitigation Structure | 122.9994 | 7.8063 | 49000000 | 48898051.48 | 2024 | JAYKRIS ENTERPRISES & CONSTRUCTION (FORMERLY: JAYKRIS ENTERPRISES) | 6791 | 2023 | 2024-08-30 | 05/15/2023 | 101948.52 | 0 | 2024-02-25 |  | 187
2023 | Region VII | NEGROS ORIENTAL | VALLEHERMOSO (NEGROS ORIENTAL) | P00721790VS | Construction of Flood Mitigation Structure | 123.3075 | 10.3529 | 72375000 | 72375000 | 2023 | LEGACY CONSTRUCTION CORPORATION (FORMERLY: LEGACY CONSTRUCTION) / MIGHTY HOK SUMMIT CONSTRUCTION & DEVELOPMENT CORP. | 6792 | 2023 | 2023-11-07 | 02/07/2023 | 0 | 0 | 2023-11-06 |  | 1
2022 | Region V | CAMARINES NORTE | LABO (CAMARINES NORTE) | P00640470LZ | Construction of Flood Mitigation Structure | 122.761 | 14.1495 | 49499743.8 | 49499743.8 | 2023 | BRENTMIN ROOFING ENTERPRISE | 6793 | 2022 | 2023-05-29 | 03/31/2022 | 0 | 0 | 2023-05-28 |  | 1
2023 | Region VI | ILOILO | ILOILO CITY (CAPITAL) (ILOILO) | P00721862VS | Construction of Flood Mitigation Structure | 122.5635 | 10.6902 | 96500000 | 96500000 | 2024 | TYER ONE CONSTRUCTION CORPORATION / A.D. PENDON CONSTRUCTION & SUPPLY, INC. (FORMERLY: ADP CONSTRUCTION & SUPPLY) | 6794 | 2023 | 2024-11-01 | 08/23/2023 | 0 | 0 | 2024-10-31 |  | 1
2023 | Region VII | CEBU | BADIAN (CEBU) | P00721518VS | Construction of Revetment | 123.369 | 9.8081 | 96305247.77 | 96305245.4 | 2023 | WTG CONSTRUCTION & DEVELOPMENT CORPORATION | 6795 | 2023 | 2023-12-19 | 02/08/2023 | 2.37 | 0 | 2023-12-18 |  | 1
2024 | Region VI | AKLAN | BALETE (AKLAN) | P00820148VS | Construction of Revetment | 122.3749 | 11.5594 | 39200000 | 39199936.73 | 2024 | G.F. ROVERO MERCHANDISING | 6796 | 2024 | 2024-04-24 | 02/06/2024 | 63.27 | 0 | 2024-08-05 | 103
2023 | Region IX | ZAMBOANGA DEL NORTE | SINDANGAN (ZAMBOANGA DEL NORTE) | P00732478MN | Construction of Flood Mitigation Structure | 123.0788 | 8.2161 | 4950000 | 4900002.01 | 2024 | D' DREAMER DEVELOPMENT CORPORATION | 6797 | 2023 | 2024-03-20 | 02/14/2023 | 49997.99 | 0 | 2023-04-08 |  | 347
2023 | Region VI | NEGROS OCCIDENTAL | ISABELA (NEGROS OCCIDENTAL) | P00721503VS | Construction of Slope Protection Structure | 122.9504 | 10.2364 | 78165000 | 78165000 | 2023 | J.F. UY CONSTRUCTION SERVICES / JAIME B. CHING ENTERPRISES | 6798 | 2023 | 2023-11-15 | 04/03/2023 | 0 | 0 | 2023-11-14 |  | 1
2024 | Region VII | CEBU | GINATILAN (CEBU) | P00834585VS | Construction of Flood Mitigation Structure | 123.3103 | 9.5511 | 57896087.6 | 57895587.6 | 2024 | LEGACY CONSTRUCTION CORPORATION (FORMERLY: LEGACY CONSTRUCTION) | 6799 | 2024 | 2024-06-20 | 02/16/2024 | 500 | 0 | 2024-10-04 | 106
2021 | Region IX | ZAMBOANGA SIBUGAY |  | P00550477MN | Construction of Drainage Structure | 122.7616 | 7.7919 | 14850000 | 14816160.07 | 2023 | ALBE CONSTRUCTION & ENTERPRISES | 6800 | 2021 | 2023-01-09 | 04/05/2021 | 33839.93 | 0 | 2022-01-07 |  | 367
2022 | Region VI | ILOILO | SAN JOAQUIN (ILOILO) | P00620090VS | Construction of Flood Mitigation Structure | 122.3758 | 10.6781 | 19600000 | 19403838.46 | 2022 | GOLDEN ROADRUNNER INTERNATIONAL CORP. | 6801 | 2022 | 2022-10-08 | 02/10/2022 | 196161.54 | 0 | 2022-08-22 |  | 47
2023 | Region VI | GUIMARAS | NUEVA VALENCIA (GUIMARAS) | P00721867VS | Construction of Flood Mitigation Structure | 122.5637 | 10.4366 | 57900000 | 57610530.48 | 2023 | ALPHA & OMEGA GEN. CONTRACTOR & DEVELOPMENT CORP. | 6802 | 2023 | 2023-11-27 | 03/17/2023 | 289469.52 | 0 | 2023-12-25 | 28
2023 | Region VII | CEBU | BADIAN (CEBU) | P00721512VS | Construction of Revetment | 123.369 | 9.8081 | 96015750.57 | 96015713.2 | 2023 | WTG CONSTRUCTION & DEVELOPMENT CORPORATION | 6803 | 2023 | 2023-12-18 | 02/08/2023 | 37.37 | 0 | 2023-12-17 |  | 1
2022 | Region VI | NEGROS OCCIDENTAL | CITY OF VICTORIAS (NEGROS OCCIDENTAL) | P00633000VS | Construction of Drainage Structure | 123.079 | 10.9064 | 9799951.95 | 9798000 | 2022 | R.A.G. CORONA CONSTRUCTION AND AGGREGATES SUPPLY | 6804 | 2022 | 2022-07-09 | 03/30/2022 | 1951.95 | 0 | 2022-07-08 |  | 1
2022 | Region V | CAMARINES NORTE | DAET (CAPITAL) (CAMARINES NORTE) | P00632959LZ | Construction of Flood Mitigation Structure | 122.9508 | 14.1011 | 4949365.09 | 4798589.86 | 2022 | 128 DRAGON CONSTRUCTION AND SUPPLIES | 6805 | 2022 | 2022-07-26 | 03/22/2022 | 150775.23 | 0 | 2022-07-25 |  | 1
2022 | Region V | CAMARINES SUR | LIBMANAN (CAMARINES SUR) | P00620721LZ | Construction of Revetment | 122.9997 | 13.6975 | 49000000 | 48018533.15 | 2022 | KCS CONSTRUCTION & SUPPLY | 6806 | 2022 | 2022-09-20 | 02/28/2022 | 981466.85 | 0 | 2022-09-19 |  | 1
2023 | Region VI | NEGROS OCCIDENTAL | BACOLOD CITY (CAPITAL) (NEGROS OCCIDENTAL) | P00721633VS | Construction of Drainage Structure | 122.9512 | 10.6775 | 19600000 | 19600000 | 2023 | HOMEWORLD CONSTRUCTION CORP. (FORMERLY HOMEWORLD E | 6807 | 2023 | 2023-12-27 | 02/08/2023 | 0 | 0 | 2023-12-26 |  | 1
2024 | Region V | CAMARINES SUR | BULA (CAMARINES SUR) | P00821393LZ | Construction of Flood Mitigation Structure | 123.3106 | 13.4236 | 139925000 | 139925000 | 2024 | HI-TONE CONSTRUCTION & DEVELOPMENT CORP. (FORMERLY / KENZAI BUILDERS CORPORATION | 6808 | 2024 | 2024-09-20 | 02/21/2024 | 0 | 0 | 2024-12-27 | 98
2022 | Region V | CAMARINES NORTE | LABO (CAMARINES NORTE) | P00631391LZ | Construction of Flood Mitigation Structure | 122.7618 | 14.1501 | 24499771.08 | 24499771.08 | 2023 | EUS CONSTRUCTION | 6809 | 2022 | 2023-03-11 | 03/17/2022 | 0 | 0 | 2023-03-10 |  | 1
2023 | Region VII | CEBU | BADIAN (CEBU) | P00745597VS | Rehabilitation / Major Repair of Flood Control Structure | 123.3695 | 9.8123 | 81432079.58 | 81431510 | 2024 | WTG CONSTRUCTION & DEVELOPMENT CORPORATION | 6810 | 2023 | 2024-05-12 | 08/10/2023 | 569.58 | 0 | 2024-05-11 |  | 1
2022 | Region VI | ILOILO | TIGBAUAN (ILOILO) | P00620089VS | Construction of Flood Mitigation Structure | 122.3758 | 10.6781 | 9800000 | 9703074.2 | 2022 | PANAY EAST COAST CONSTRUCTION & SUPPLY | 6811 | 2022 | 2022-12-26 | 03/29/2022 | 96925.8 | 0 | 2022-09-09 |  | 108
2024 | Region VI | NEGROS OCCIDENTAL | CITY OF VICTORIAS (NEGROS OCCIDENTAL) | P00834997VS | Construction of Flood Mitigation Structure | 123.081 | 10.9122 | 5444991.75 | 5444992.8 | 2024 | CANLAON BUILDERS AND DEVELOPMENT CORPORATION | 6812 | 2024 | 2024-06-01 | 03/13/2024 | 0 | 1.05 | 2024-05-31 |  | 1
2023 | Region IX | ZAMBOANGA DEL SUR | BAYOG (ZAMBOANGA DEL SUR) | P00721606MN | Construction of Flood Mitigation Structure | 123.001 | 7.8097 | 58800000 | 58493426.41 | 2024 | BADSBRO CONSTRUCTION AND GENERAL MERCHANDISE | 6813 | 2023 | 2024-01-22 | 04/18/2023 | 306573.59 | 0 | 2023-12-14 |  | 39
2022 | Region V | CAMARINES SUR | LIBMANAN (CAMARINES SUR) | P00620722LZ | Construction of Revetment | 123.0016 | 13.6991 | 49000000 | 48015655.63 | 2022 | KCS CONSTRUCTION & SUPPLY | 6814 | 2022 | 2022-09-20 | 02/28/2022 | 984344.37 | 0 | 2022-09-19 |  | 1
2023 | Region V | CAMARINES NORTE | TALISAY (CAMARINES NORTE) | P00740493LZ | Construction of Flood Mitigation Structure | 122.9514 | 14.1449 | 96499924.2 | 96499924.2 | 2024 | EUS CONSTRUCTION / VINHAR CONSTRUCTION & MARKETING (FOR. VINHAR CONST | 6815 | 2023 | 2024-06-28 | 10/06/2023 | 0 | 0 | 2024-07-14 | 16
2024 | Region VI | ILOILO | DUEÃ‘AS (ILOILO) | P00834994VS | Construction of Flood Mitigation Structure | 122.564 | 11.087 | 39600000 | 39492437.76 | 2024 | UBS UNITED BUILDERS AND SUPPLY INC. | 6816 | 2024 | 2024-09-01 | 03/08/2024 | 107562.24 | 0 | 2024-08-31 |  | 1
2023 | Region V | CAMARINES NORTE | LABO (CAMARINES NORTE) | P00736125LZ | Construction of Flood Mitigation Structure | 122.7637 | 14.1527 | 96499775.93 | 95479124.82 | 2024 | EUS CONSTRUCTION | 6817 | 2023 | 2024-07-25 | 07/26/2023 | 1020651.11 | 0 | 2024-07-24 |  | 1
2022 | Region V | CAMARINES NORTE | MERCEDES (CAMARINES NORTE) | P00631409LZ | Construction of Flood Mitigation Structure | 123.002 | 14.1062 | 42139885.61 | 42139885.61 | 2022 | 128 DRAGON CONSTRUCTION AND SUPPLIES | 6818 | 2022 | 2022-09-17 | 03/16/2022 | 0 | 0 | 2022-09-16 |  | 1
2022 | Region V | ALBAY | CITY OF LIGAO (ALBAY) | P00631353LZ | Construction of Flood Mitigation Structure | 123.3114 | 13.0253 | 92956675.49 | 48969287.6 | 2023 | RAMARPLUS INCORPORATED (FORMERLY RAMAR ENTERPRISES | 6819 | 2022 | 2023-03-01 | 03/22/2022 | 43987387.89 | 0 | 2023-02-28 |  | 1
2024 | Region VI | AKLAN | BALETE (AKLAN) | P00820041VS | Rehabilitation / Major Repair of Flood Control Structure | 122.376 | 11.5562 | 49062530 | 49062232.76 | 2024 | G.F. ROVERO MERCHANDISING | 6820 | 2024 | 2024-04-24 | 02/06/2024 | 297.24 | 0 | 2024-08-21 | 119
2023 | Region VII | CEBU | MALABUYOC (CEBU) | P00721520VS | Construction of Revetment | 123.3698 | 9.6529 | 96396402.16 | 96396397.96 | 2023 | ZLREJ TRADING AND CONSTRUCTION CORPORATION / GICAR CONSTRUCTION, INC. | 6821 | 2023 | 2023-11-17 | 02/08/2023 | 4.2 | 0 | 2023-12-18 | 31
2024 | Region VI | NEGROS OCCIDENTAL | MANAPLA (NEGROS OCCIDENTAL) | P00832631VS | Construction of Flood Mitigation Structure | 123.0894 | 10.9351 | 4949991.62 | 4947977.52 | 2024 | LEGACY CONSTRUCTION CORPORATION (FORMERLY: LEGACY CONSTRUCTION) | 6822 | 2024 | 2024-06-02 | 03/13/2024 | 2014.1 | 0 | 2024-06-01 |  | 1
2022 | Region VI | NEGROS OCCIDENTAL | SILAY CITY (NEGROS OCCIDENTAL) | P00630638VS | Construction of Flood Mitigation Structure | 122.9514 | 10.8497 | 10394999.05 | 10392997 | 2022 | CANLAON BUILDERS AND DEVELOPMENT CORPORATION | 6823 | 2022 | 2022-07-22 | 02/08/2022 | 2002.05 | 0 | 2022-07-21 |  | 1
2023 | Region VI | ILOILO | ILOILO CITY (CAPITAL) (ILOILO) | P00721861VS | Construction of Flood Mitigation Structure | 122.565 | 10.6901 | 96500000 | 96500000 | 2024 | A.D. PENDON CONSTRUCTION & SUPPLY, INC. (FORMERLY: ADP CONSTRUCTION & SUPPLY) | 6824 | 2023 | 2024-11-04 | 08/23/2023 | 0 | 0 | 2024-11-03 |  | 1
2024 | Region IX | ZAMBOANGA DEL NORTE | SALUG (ZAMBOANGA DEL NORTE) | P00820131MN | Construction of Flood Mitigation Structure | 122.7642 | 8.0833 | 19600000 | 19600000 | 2024 | MIN CONSTRUCTION | 6825 | 2024 | 2024-07-04 | 02/07/2024 | 0 | 0 | 2024-11-03 | 122
2022 | Region VI | NEGROS OCCIDENTAL | ISABELA (NEGROS OCCIDENTAL) | P00620441VS | Construction of Slope Protection Structure | 123.0031 | 10.2443 | 96500000 | 96500000 | 2023 | LEGACY CONSTRUCTION CORPORATION (FORMERLY: LEGACY CONSTRUCTION) | 6826 | 2022 | 2023-03-28 | 05/19/2022 | 0 | 0 | 2023-03-27 |  | 1
2024 | Region IX | ZAMBOANGA DEL SUR | PITOGO (ZAMBOANGA DEL SUR) | P00821215MN | Construction of Flood Mitigation Structure | 123.3698 | 7.4025 | 14700000 | 14679957.15 | 2025 | ZMS CONST. & DEV. CORP. (FORMERLY:ZMS CONSTRUCTION | 6827 | 2024 | 2025-04-29 | 05/09/2024 | 20042.85 | 0 | 2024-10-30 |  | 181
2022 | Region V | CAMARINES NORTE | MERCEDES (CAMARINES NORTE) | P00631415LZ | Construction of Flood Mitigation Structure | 123.0912 | 13.9178 | 42139475.15 | 42139475.15 | 2022 | BRENTMIN ROOFING ENTERPRISE | 6828 | 2022 | 2022-09-18 | 03/17/2022 | 0 | 0 | 2022-09-17 |  | 1
2022 | Region V | ALBAY | CITY OF LIGAO (ALBAY) | P00631357LZ | Construction of Dike | 123.3705 | 13.0391 | 29337534.11 | 29337534.11 | 2022 | 4DOVE BUILDERS CORPORATION | 6829 | 2022 | 2022-07-15 | 02/17/2022 | 0 | 0 | 2022-08-29 | 45
2023 | Region V | CAMARINES SUR | CANAMAN (CAMARINES SUR) | P00737568LZ | Construction of Flood Mitigation Structure | 123.0923 | 13.6648 | 4949983.15 | 4895533 | 2023 | MEGA-ANT BUILDERS AND CONSTRUCTION SUPPLIES | 6830 | 2023 | 2023-05-15 | 03/22/2023 | 54450.15 | 0 | 2023-07-07 | 53
2022 | Region V | CAMARINES SUR | NABUA (CAMARINES SUR) | P00632971LZ | Rehabilitation / Major Repair of Flood Control Structure | 123.3713 | 13.4068 | 4950000 | 4831050.02 | 2022 | QDC CONSTRUCTION AND SUPPLY | 6831 | 2022 | 2022-09-09 | 03/24/2022 | 118949.98 | 0 | 2022-08-22 |  | 18
2023 | Region V | CAMARINES SUR | BULA (CAMARINES SUR) | P00736120LZ | Construction of Flood Mitigation Structure | 123.3117 | 13.4211 | 96315788 | 96314191.85 | 2023 | HI-TONE CONSTRUCTION & DEVELOPMENT CORP. (FORMERLY | 6832 | 2023 | 2023-12-07 | 02/17/2023 | 1596.15 | 0 | 2023-12-07 | 0
2023 | Region VII | NEGROS ORIENTAL | BAIS CITY (NEGROS ORIENTAL) | P00721841VS | Rehabilitation / Major Repair of Flood Control Structure | 123.0969 | 9.5816 | 49000000 | 49000000 | 2023 | PHILSOUTH BUILDERS INC (FORMERLY:PHILSOUTH BUILDERS) | 6833 | 2023 | 2023-09-07 | 02/13/2023 | 0 | 0 | 2023-10-24 | 47
2023 | Region VI | ILOILO | ILOILO CITY (CAPITAL) (ILOILO) | P00733729VS | Construction of Drainage Structure | 122.5666 | 10.7194 | 4950000 | 4930000 | 2023 | PESOM CONSTRUCTION SERVICES (FORMERLY: PESOM BUILDERS AND CONSTRUCTION SUPPLY) | 6834 | 2023 | 2023-08-27 | 05/12/2023 | 20000 | 0 | 2023-08-16 |  | 11
2022 | Region V | CAMARINES SUR | BAAO (CAMARINES SUR) | P00631435LZ | Construction of Flood Mitigation Structure | 123.3715 | 13.4715 | 29400000 | 29399841.95 | 2022 | SISAM CONSTRUCTION & SUPPLIES | 6835 | 2022 | 2022-12-22 | 05/26/2022 | 158.05 | 0 | 2022-12-21 |  | 1
2022 | Region V | CAMARINES SUR | LIBMANAN (CAMARINES SUR) | P00620719LZ | Construction of Revetment | 123.0032 | 13.7142 | 49000000 | 48015489 | 2022 | NFH CONSTRUCTION & SUPPLY | 6836 | 2022 | 2022-09-20 | 02/28/2022 | 984511 | 0 | 2022-09-19 |  | 1
2024 | Region VI | AKLAN | BALETE (AKLAN) | P00820147VS | Construction of Revetment | 122.377 | 11.557 | 39200000 | 39199794.21 | 2024 | G.F. ROVERO MERCHANDISING | 6837 | 2024 | 2024-04-24 | 02/06/2024 | 205.79 | 0 | 2024-08-12 | 110
2023 | Region VI | NEGROS OCCIDENTAL | BACOLOD CITY (CAPITAL) (NEGROS OCCIDENTAL) | P00721626VS | Construction of Drainage Structure | 122.9518 | 10.6859 | 29400000 | 29400000 | 2023 | HUMMING BIRD CONSTRUCTION & SUPPLY CORPORATION | 6838 | 2023 | 2023-12-20 | 02/08/2023 | 0 | 0 | 2023-10-12 |  | 69
2024 | Region V | CAMARINES NORTE | PARACALE (CAMARINES NORTE) | P00839667LZ | Construction of Flood Mitigation Facility | 122.7644 | 14.2207 | 4949980.94 | 4948973.07 | 2024 | JAEJR ELECTRICAL, CONSTRUCTION & SUPPLY | 6839 | 2024 | 2024-06-08 | 02/16/2024 | 1007.87 | 0 | 2024-06-07 |  | 1
2024 | Region VI | NEGROS OCCIDENTAL | CADIZ CITY (NEGROS OCCIDENTAL) | P00832636VS | Construction of Flood Mitigation Structure | 123.3125 | 10.9554 | 4949990.89 | 4947977.29 | 2024 | HAFF CONSTRUCTION AND SUPPLIES, INC. (FORMERLY: HAFF CONSTRUCTION AND SUPPLIES) | 6840 | 2024 | 2024-06-04 | 03/13/2024 | 2013.6 | 0 | 2024-06-03 |  | 1
2023 | Region V | CAMARINES SUR | PAMPLONA (CAMARINES SUR) | P00726292LZ | Construction of Revetment | 123.0973 | 13.5717 | 49000000 | 48493174.09 | 2023 | BICOL GOLDROCK CONSTRUCTION CORPORATION | 6841 | 2023 | 2023-10-27 | 02/08/2023 | 506825.91 | 0 | 2023-10-29 | 2
2020 | Region VI | ILOILO |  | P00442501VS | Construction of Revetment | 122.568 | 10.705 | 39600000 | 38453540.08 | 2022 | ROPRIM CONSTRUCTION CORPORATION (FORMERLY ROPRIM CONSTRUCTION) | 6842 | 2020 | 2022-08-10 | 11/23/2020 | 1146459.92 | 0 | 2022-08-09 |  | 1
2023 | Region V | CAMARINES SUR | NABUA (CAMARINES SUR) | P00736104LZ | Construction of Flood Mitigation Structure | 123.3724 | 13.4005 | 96402476 | 96402424.49 | 2023 | SUNWEST, INC. (FORMERLY: SUNWEST CONSTRUCTION & DEVELOPMENT CORPORATION) | 6843 | 2023 | 2023-12-22 | 02/17/2023 | 51.51 | 0 | 2023-12-27 | 5
2023 | Region V | CAMARINES SUR | LIBMANAN (CAMARINES SUR) | P00726955LZ | Construction of Flood Mitigation Structure | 123.0036 | 13.6995 | 72375000 | 70928316.1 | 2024 | BICOL GOLDROCK CONSTRUCTION CORPORATION | 6844 | 2023 | 2024-03-26 | 04/05/2023 | 1446683.9 | 0 | 2024-03-31 | 5
2023 | Region IX | ZAMBOANGA SIBUGAY | IMELDA (ZAMBOANGA SIBUGAY) | P00721404MN | Construction of Revetment | 122.9518 | 7.6596 | 96500000 | 96499965.23 | 2024 | BADSBRO CONSTRUCTION AND GENERAL MERCHANDISE | 6845 | 2023 | 2024-01-19 | 05/22/2023 | 34.77 | 0 | 2024-01-18 |  | 1
2024 | Region VI | ILOILO | BANATE (ILOILO) | P00820164VS | Construction of Drainage Structure | 122.7672 | 11.087 | 4900000 | 4899987.47 | 2024 | MZ BUILDERS & CONSTRUCTION SUPPLY | 6846 | 2024 | 2024-07-12 | 03/08/2024 | 12.53 | 0 | 2024-07-11 |  | 1
2022 | Region VII | CEBU | GINATILAN (CEBU) | P00620037VS | Construction of Flood Mitigation Structure | 123.3144 | 9.5718 | 48999896.71 | 48999896.71 | 2022 | FIRST GRANDEUR BUILDERS | 6847 | 2022 | 2022-11-10 | 03/23/2022 | 0 | 0 | 2022-11-09 |  | 1
2023 | Region V | CAMARINES SUR | PAMPLONA (CAMARINES SUR) | P00740681LZ | Construction of Flood Mitigation Structure | 123.0982 | 13.5727 | 49000000 | 48997080.61 | 2024 | HONEYVILLECONST AND DEVELOPMENT CORPORATION | 6848 | 2023 | 2024-01-06 | 04/17/2023 | 2919.39 | 0 | 2024-01-05 |  | 1
2021 | Region VI | ILOILO |  | P00442501VS | Construction of Revetment | 122.568 | 10.705 | 39600000 | 38453540.08 | 2022 | ROPRIM CONSTRUCTION CORPORATION (FORMERLY ROPRIM CONSTRUCTION) | 6849 | 2021 | 2022-08-10 | 11/23/2020 | 1146459.92 | 0 | 2022-08-09 |  | 1
2022 | Region V | ALBAY | LIBON (ALBAY) | P00631362LZ | Construction of Flood Mitigation Structure | 123.3725 | 13.2458 | 98000000 | 49000000 | 2022 | RAMARPLUS INCORPORATED (FORMERLY RAMAR ENTERPRISES | 6850 | 2022 | 2022-12-15 | 03/22/2022 | 49000000 | 0 | 2022-12-30 | 15
2024 | Region V | CAMARINES SUR | LIBMANAN (CAMARINES SUR) | P00825142LZ | Construction of Flood Mitigation Structure | 123.0043 | 13.6997 | 135100000 | 135099448.6 | 2024 | BICOL GOLDROCK CONSTRUCTION CORPORATION | 6851 | 2024 | 2024-09-25 | 04/23/2024 | 551.4 | 0 | 2025-04-20 | 207
2023 | Region V | CAMARINES NORTE | SANTA ELENA (CAMARINES NORTE) | P00727215LZ | Construction of Flood Mitigation Structure | 122.3794 | 14.1084 | 17639628.18 | 17483692.3 | 2023 | EUS CONSTRUCTION | 6852 | 2023 | 2023-08-02 | 04/05/2023 | 155935.88 | 0 | 2023-08-25 | 23
2022 | Region VI | CAPIZ | ROXAS CITY (CAPITAL) (CAPIZ) | P00633214VS | Construction of Drainage Structure | 122.7676 | 11.584 | 4950000 | 4202711.02 | 2022 | KIRSKAT VENTURE | 6853 | 2022 | 2022-10-22 | 04/13/2022 | 747288.98 | 0 | 2022-10-21 |  | 1
2022 | Region V | CAMARINES SUR | SAN FERNANDO (CAMARINES SUR) | P00620709LZ | Construction of Dike | 123.0991 | 13.4816 | 49000000 | 48021720 | 2022 | G.C.I. CONSTRUCTION AND DEV'T. CORP. | 6854 | 2022 | 2022-09-14 | 02/22/2022 | 978280 | 0 | 2022-09-13 |  | 1
2022 | Region VII | NEGROS ORIENTAL | VALLEHERMOSO (NEGROS ORIENTAL) | P00620140VS | Construction of Flood Mitigation Structure | 123.3158 | 10.3257 | 49000000 | 49000000 | 2023 | ST. TIMOTHY CONSTRUCTION CORPORATION / ELITE GENERAL CONTRACTOR AND DEVELOPMENT CORP. | 6855 | 2022 | 2023-06-25 | 02/08/2022 | 0 | 0 | 2022-12-26 |  | 181
2024 | Region VI | NEGROS OCCIDENTAL | BACOLOD CITY (CAPITAL) (NEGROS OCCIDENTAL) | P00820307VS | Construction of Revetment | 122.9521 | 10.641 | 96500000 | 96500000 | 2024 | C'ZARLES CONSTRUCTION & SUPPLY / JVC TOUGH CORE CONSTRUCTION & BUILDERS CORP. | 6856 | 2024 | 2024-10-16 | 02/20/2024 | 0 | 0 | 2024-10-15 |  | 1
2021 | Region VI | ILOILO |  | P00521617VS | Construction of Drainage Structure | 122.5691 | 10.692 | 9799965.93 | 8448396.05 | 2022 | CONTE BUILDERS & CONSTRUCTION SUPPLY | 6857 | 2021 | 2022-08-15 | 02/22/2022 | 1351569.88 | 0 | 2022-09-21 | 37
2022 | Region V | ALBAY | LIBON (ALBAY) | P00631377LZ | Rehabilitation / Major Repair of Flood Control Structure | 123.3728 | 13.2457 | 49000000 | 48997251.57 | 2022 | MAKAPA CORPORATION | 6858 | 2022 | 2022-11-13 | 02/17/2022 | 2748.43 | 0 | 2022-11-12 |  | 1
2024 | Region VI | ILOILO | AJUY (ILOILO) | P00820165VS | Construction of Flood Mitigation Structure | 123.0044 | 11.0889 | 29400000 | 29400000 | 2024 | JEJOR'S CONSTRUCTION CORPORATION | 6859 | 2024 | 2024-12-10 | 03/19/2024 | 0 | 0 | 2024-12-09 |  | 1
2022 | Region V | CAMARINES NORTE | SANTA ELENA (CAMARINES NORTE) | P00631400LZ | Construction of Flood Mitigation Structure | 122.38 | 14.163 | 24499261.95 | 24499261.95 | 2022 | N.E.B. CONSTRUCTION AND SUPPLY | 6860 | 2022 | 2022-08-23 | 03/11/2022 | 0 | 0 | 2022-08-22 |  | 1
2023 | Region V | CAMARINES SUR | LIBMANAN (CAMARINES SUR) | P00726958LZ | Construction of Flood Mitigation Structure | 123.0045 | 13.7152 | 72375000 | 72239845.66 | 2024 | G.C.I. CONSTRUCTION AND DEV'T. CORP. | 6861 | 2023 | 2024-01-31 | 04/05/2023 | 135154.34 | 0 | 2024-02-10 | 10
2024 | Region VII | CEBU | MALABUYOC (CEBU) | P00820070VS | Construction of Flood Mitigation Structure | 123.3739 | 9.6523 | 128180577.7 | 128179667.5 | 2024 | GICAR CONSTRUCTION, INC. | 6862 | 2024 | 2024-06-18 | 02/16/2024 | 910.2 | 0 | 2025-02-18 | 245
2022 | Region VI | CAPIZ | PANITAN (CAPIZ) | P00620262VS | Construction of Flood Mitigation Structure | 122.7725 | 11.4663 | 62725000 | 62724905.03 | 2022 | MRRM TRADING & CONSTRUCTION / SALMEGA BUILDERS | 6863 | 2022 | 2022-11-15 | 02/28/2022 | 94.97 | 0 | 2022-12-11 | 26
2022 | Region VII | NEGROS ORIENTAL | MANJUYOD (NEGROS ORIENTAL) | P00642567VS | Rehabilitation / Major Repair of Flood Control Structure | 123.0997 | 9.6406 | 3273333.2 | 3273333.2 | 2022 | MAI CONSTRUCTION & SUPPLY | 6864 | 2022 | 2022-07-06 | 06/06/2022 | 0 | 0 | 2022-07-07 | 1
2023 | Region VI | NEGROS OCCIDENTAL | BACOLOD CITY (CAPITAL) (NEGROS OCCIDENTAL) | P00721627VS | Construction of Drainage Structure | 122.9522 | 10.6597 | 29400000 | 29400000 | 2023 | TMTC CONSTRUCTION AND SUPPLY CORPORATION | 6865 | 2023 | 2023-10-16 | 02/08/2023 | 0 | 0 | 2023-09-12 |  | 34
2023 | Region VII | CEBU | MALABUYOC (CEBU) | P00721519VS | Construction of Revetment | 123.3744 | 9.6529 | 96207158.11 | 96207155.27 | 2023 | GICAR CONSTRUCTION, INC. | 6866 | 2023 | 2023-11-24 | 02/08/2023 | 2.84 | 0 | 2023-12-18 | 24
2024 | Region VI | NEGROS OCCIDENTAL | BACOLOD CITY (CAPITAL) (NEGROS OCCIDENTAL) | P00820308VS | Construction of Revetment | 123.0045 | 10.6613 | 96500000 | 96500000 | 2024 | C'ZARLES CONSTRUCTION & SUPPLY / JVC TOUGH CORE CONSTRUCTION & BUILDERS CORP. | 6867 | 2024 | 2024-10-16 | 02/20/2024 | 0 | 0 | 2024-10-15 |  | 1
2024 | Region VI | NEGROS OCCIDENTAL | SAGAY CITY (NEGROS OCCIDENTAL) | P00820005VS | Construction of Flood Mitigation Structure | 123.3778 | 10.7951 | 96499988.22 | 96494917.59 | 2024 | SUPREME ABF CONST. & CONST. SUPPLY COMPANY INC. / PGO CONSTRUCTION | 6868 | 2024 | 2024-10-15 | 04/11/2024 | 5070.63 | 0 | 2024-11-29 | 45
2021 | Region VI | ILOILO |  | P00521613VS | Construction of Slope Protection Structure | 122.5704 | 10.7511 | 15587880 | 14132568.92 | 2022 | BOAZ AND JACHIN CONSTRUCTION SUPPLY & SERVICES | 6869 | 2021 | 2022-07-10 | 04/12/2021 | 1455311.08 | 0 | 2022-02-10 |  | 150
2022 | Region VII | CEBU | GINATILAN (CEBU) | P00620038VS | Construction of Flood Mitigation Structure | 123.3181 | 9.5995 | 29394311.68 | 29394310.95 | 2022 | WORLDWIDE BUILDERS | 6870 | 2022 | 2022-08-22 | 02/10/2022 | 0.73 | 0 | 2022-08-17 |  | 5
2023 | Region V | CAMARINES NORTE | PARACALE (CAMARINES NORTE) | P00737560LZ | Construction of Flood Mitigation Structure | 122.7801 | 14.2722 | 9899936.97 | 9813293.71 | 2023 | EUS CONSTRUCTION | 6871 | 2023 | 2023-09-06 | 04/05/2023 | 86643.26 | 0 | 2023-09-05 |  | 1
2022 | Region VI | ANTIQUE | SIBALOM (ANTIQUE) | P00620296VS | Construction of Revetment | 122.3881 | 10.8074 | 49000000 | 49000000 | 2023 | TIBIAO-ANTIQUE N.K. ENTERPRISE, INC. / SENTINA CONSTRUCTION AND SUPPLY | 6872 | 2022 | 2023-04-28 | 02/07/2022 | 0 | 0 | 2023-03-29 |  | 30
2023 | Region V | CAMARINES SUR | LIBMANAN (CAMARINES SUR) | P00726960LZ | Construction of Flood Mitigation Structure | 123.102 | 13.6793 | 72375000 | 72358567.14 | 2024 | BICOL GOLDROCK CONSTRUCTION CORPORATION | 6873 | 2023 | 2024-03-26 | 04/05/2023 | 16432.86 | 0 | 2024-04-08 | 13
2022 | Region VI | NEGROS OCCIDENTAL | ISABELA (NEGROS OCCIDENTAL) | P00620442VS | Construction of Slope Protection Structure | 123.0049 | 10.2446 | 96500000 | 96500000 | 2023 | LEGACY CONSTRUCTION CORPORATION (FORMERLY: LEGACY CONSTRUCTION) | 6874 | 2022 | 2023-03-06 | 05/19/2022 | 0 | 0 | 2023-03-05 |  | 1
2023 | Region V | CAMARINES NORTE | BASUD (CAMARINES NORTE) | P00737371LZ | Construction of Flood Mitigation Structure | 122.9531 | 14.0813 | 6929997.06 | 6929997.06 | 2023 | 128 DRAGON CONSTRUCTION AND SUPPLIES | 6875 | 2023 | 2023-09-15 | 07/07/2023 | 0 | 0 | 2023-10-02 | 17
2022 | Region V | ALBAY | LIBON (ALBAY) | P00631363LZ | Construction of Flood Mitigation Structure | 123.3785 | 13.2551 | 98000000 | 49000000 | 2022 | RAMARPLUS INCORPORATED (FORMERLY RAMAR ENTERPRISES | 6876 | 2022 | 2022-12-15 | 03/22/2022 | 49000000 | 0 | 2022-12-30 | 15
2024 | Region V | CAMARINES SUR | NABUA (CAMARINES SUR) | P00821375LZ | Construction of Flood Mitigation Structure | 123.3191 | 13.418 | 138477500 | 138477500 | 2024 | G.C.I. CONSTRUCTION AND DEV'T. CORP. / MPIRE NINE CONSTRUCTION OPC | 6877 | 2024 | 2024-08-20 | 03/04/2024 | 0 | 0 | 2025-01-08 | 141
2024 | Region VI | ILOILO | TIGBAUAN (ILOILO) | P00834993VS | Construction of Flood Mitigation Structure | 122.3882 | 10.709 | 29700000 | 29669248.58 | 2024 | RINEL CONSTRUCTION SERVICES | 6878 | 2024 | 2024-06-10 | 02/23/2024 | 30751.42 | 0 | 2024-07-21 | 41
2022 | Region VI | NEGROS OCCIDENTAL | ILOG (NEGROS OCCIDENTAL) | P00620266VS | Construction of Flood Mitigation Structure | 122.7867 | 10.025 | 86850000 | 73579995.56 | 2023 | KVC CONSTRUCTION | 6879 | 2022 | 2023-10-20 | 02/21/2022 | 13270004.44 | 0 | 2023-07-14 |  | 98
2023 | Region V | CAMARINES SUR | PAMPLONA (CAMARINES SUR) | P00726604LZ | Construction of Dike | 123.1035 | 13.6255 | 53075000 | 53047839.5 | 2024 | BICOL GOLDROCK CONSTRUCTION CORPORATION | 6880 | 2023 | 2024-01-15 | 03/01/2023 | 27160.5 | 0 | 2024-01-19 | 4
2023 | Region VI | ILOILO | TIGBAUAN (ILOILO) | P00733299VS | Construction of Flood Mitigation Structure | 122.3926 | 10.71 | 14700000 | 14679731.63 | 2023 | GOOD FORTUNE INTERNATIONAL, INC. | 6881 | 2023 | 2023-10-07 | 03/29/2023 | 20268.37 | 0 | 2023-10-07 | 0
2023 | Region VI | NEGROS OCCIDENTAL | ILOG (NEGROS OCCIDENTAL) | P00721744VS | Construction of Flood Mitigation Structure | 122.7874 | 10.036 | 89262500 | 89262500 | 2023 | LEGACY CONSTRUCTION CORPORATION (FORMERLY: LEGACY CONSTRUCTION) / M.K.U. CONSTRUCTION AND SUPPLY | 6882 | 2023 | 2023-08-22 | 02/20/2023 | 0 | 0 | 2023-10-30 | 69
2021 | Region IX | ZAMBOANGA DEL NORTE |  | P00522146MN | Construction of Flood Mitigation Structure | 123.0052 | 8.2248 | 49000000 | 29354536.9 | 2022 | BADSBRO CONSTRUCTION AND GENERAL MERCHANDISE | 6883 | 2021 | 2022-09-22 | 08/31/2021 | 19645463.1 | 0 | 2022-04-11 |  | 164
2023 | Region VI | NEGROS OCCIDENTAL | HINIGARAN (NEGROS OCCIDENTAL) | P00733733VS | Construction of Slope Protection Structure | 122.9536 | 10.2267 | 49500000 | 49500000 | 2023 | LEGACY CONSTRUCTION CORPORATION (FORMERLY: LEGACY CONSTRUCTION) | 6884 | 2023 | 2023-10-05 | 03/23/2023 | 0 | 0 | 2023-10-04 |  | 1
2024 | Region IV-B | CAMARINES SUR | SAN FERNANDO (CAMARINES SUR) | P00820989LZ | Construction of Flood Mitigation Structure | 122.5752 | 12.3178 | 19599999.56 | 19600000 | 2024 | R.G. FLORENTINO CONST. & TRADING INC. | 6885 | 2024 | 2024-11-23 | 03/19/2024 | 0 | 0.44 | 2024-12-02 | 9
2023 | Region VII | CEBU | GINATILAN (CEBU) | P00721546VS | Construction of Flood Mitigation Structure | 123.3206 | 9.5685 | 87813259.66 | 87811664 | 2023 | FIRST GRANDEUR BUILDERS / MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY | 6886 | 2023 | 2023-11-26 | 02/08/2023 | 1595.66 | 0 | 2023-11-25 |  | 1
2022 | Region V | CAMARINES SUR | NABUA (CAMARINES SUR) | P00620274LZ | Construction of Flood Mitigation Structure | 123.3795 | 13.4032 | 93127727.21 | 93127727.21 | 2022 | RAMARPLUS INCORPORATED (FORMERLY RAMAR ENTERPRISES | 6887 | 2022 | 2022-11-30 | 03/21/2022 | 0 | 0 | 2023-01-14 | 45
2023 | Region VI | ILOILO | CONCEPCION (ILOILO) | P00733719VS | Construction of Flood Mitigation Structure | 123.1095 | 11.2164 | 49500000 | 49500000 | 2024 | PANAY EAST COAST CONSTRUCTION & SUPPLY | 6888 | 2023 | 2024-02-08 | 03/28/2023 | 0 | 0 | 2024-02-07 |  | 1
2023 | Region V | CAMARINES NORTE | SANTA ELENA (CAMARINES NORTE) | P00726289LZ | Construction of Flood Mitigation Structure | 122.3933 | 14.2196 | 17639927.68 | 14241069.96 | 2023 | GREAT WALL ENGINEERING | 6889 | 2023 | 2023-08-26 | 04/05/2023 | 3398857.72 | 0 | 2023-08-25 |  | 1
2024 | Region VI | NEGROS OCCIDENTAL | ILOG (NEGROS OCCIDENTAL) | P00820292VS | Construction of Flood Mitigation Structure | 122.7874 | 10.0356 | 110098780 | 110098780 | 2024 | M.K.U. CONSTRUCTION AND SUPPLY | 6890 | 2024 | 2024-05-27 | 02/12/2024 | 0 | 0 | 2024-10-04 | 130
2023 | Region VI | ILOILO | AJUY (ILOILO) | P00721495VS | Construction of Flood Mitigation Structure | 123.007 | 11.0912 | 86464000 | 86464000 | 2024 | F. GURREA CONSTRUCTION, INCORPORATED | 6891 | 2023 | 2024-03-21 | 02/17/2023 | 0 | 0 | 2024-03-20 |  | 1
2023 | Region VI | ILOILO | ILOILO CITY (CAPITAL) (ILOILO) | P00733728VS | Construction of Drainage Structure | 122.5763 | 10.7058 | 4950000 | 4949720 | 2023 | 5'S CONSTRUCTION & SUPPLY | 6892 | 2023 | 2023-07-22 | 04/17/2023 | 280 | 0 | 2023-07-21 |  | 1
2023 | Region VII | CEBU | GINATILAN (CEBU) | P00733259VS | Construction of Flood Mitigation Structure | 123.3206 | 9.5685 | 96495820.17 | 96495338.63 | 2023 | LEGACY CONSTRUCTION CORPORATION (FORMERLY: LEGACY CONSTRUCTION) | 6893 | 2023 | 2023-12-18 | 04/11/2023 | 481.54 | 0 | 2024-02-10 | 54
2023 | Region V | CAMARINES NORTE | SANTA ELENA (CAMARINES NORTE) | P00737559LZ | Construction of Slope Protection Structure | 122.3946 | 14.2195 | 9899456.63 | 9882322.17 | 2023 | JAEJR ELECTRICAL, CONSTRUCTION & SUPPLY | 6894 | 2023 | 2023-06-15 | 04/05/2023 | 17134.46 | 0 | 2023-06-27 | 12
2024 | Region VII | CEBU | MALABUYOC (CEBU) | P00834589VS | Construction of Flood Mitigation Structure | 123.3839 | 9.6656 | 57896859.19 | 57896338.99 | 2024 | ZLREJ TRADING AND CONSTRUCTION CORPORATION | 6895 | 2024 | 2024-08-12 | 03/18/2024 | 520.2 | 0 | 2024-11-04 | 84
2023 | Region VI | NEGROS OCCIDENTAL | BACOLOD CITY (CAPITAL) (NEGROS OCCIDENTAL) | P00721638VS | Construction of Drainage Structure | 122.9536 | 10.6643 | 19600000 | 18617139.31 | 2023 | EMR BUILDERS AND DEVELOPMENT CORPORATION (FORMERLY: EMR BUILDERS) | 6896 | 2023 | 2023-10-23 | 02/08/2023 | 982860.69 | 0 | 2023-08-28 |  | 56
2022 | Region V | CAMARINES NORTE | PARACALE (CAMARINES NORTE) | P00640469LZ | Construction of Flood Mitigation Structure | 122.7875 | 14.2845 | 49999857.99 | 48001721.62 | 2022 | EUS CONSTRUCTION | 6897 | 2022 | 2022-10-10 | 03/31/2022 | 1998136.37 | 0 | 2022-10-09 |  | 1
2023 | Region VII | NEGROS ORIENTAL | PAMPLONA (NEGROS ORIENTAL) | P00721843VS | Rehabilitation / Major Repair of Flood Control Structure | 123.1099 | 9.4723 | 49000000 | 49000000 | 2023 | PHILSOUTH BUILDERS INC (FORMERLY:PHILSOUTH BUILDERS) | 6898 | 2023 | 2023-11-26 | 02/06/2023 | 0 | 0 | 2023-11-25 |  | 1
2022 | Region VI | ILOILO | AJUY (ILOILO) | P00620093VS | Construction of Flood Mitigation Structure | 123.0072 | 11.0921 | 39200000 | 39197764.65 | 2023 | ACCELERATED METAL TECHNOLOGY & CONSTRUCTION, INC. | 6899 | 2022 | 2023-03-20 | 01/28/2022 | 2235.35 | 0 | 2023-01-04 |  | 75
2022 | Region VI | ILOILO | MINA (ILOILO) | P00620430VS | Construction of Flood Mitigation Structure | 122.5765 | 10.9316 | 30323160 | 28679261.91 | 2023 | TIBIAO-ANTIQUE N.K. ENTERPRISE, INC. | 6900 | 2022 | 2023-11-30 | 03/29/2022 | 1643898.09 | 0 | 2022-09-08 |  | 448
2023 | Region VII | CEBU | GINATILAN (CEBU) | P00733273VS | Construction of Flood Mitigation Structure | 123.3206 | 9.5685 | 96493927.94 | 96493891.72 | 2023 | QM BUILDERS | 6901 | 2023 | 2023-12-11 | 04/11/2023 | 36.22 | 0 | 2024-02-18 | 69
2023 | Region V | CAMARINES NORTE | SANTA ELENA (CAMARINES NORTE) | P00727216LZ | Construction of Flood Mitigation Structure | 122.3963 | 14.2201 | 19599626.9 | 19573649.78 | 2023 | JAEJR ELECTRICAL, CONSTRUCTION & SUPPLY | 6902 | 2023 | 2023-09-10 | 04/05/2023 | 25977.12 | 0 | 2023-09-09 |  | 1
2023 | Region VI | NEGROS OCCIDENTAL | BACOLOD CITY (CAPITAL) (NEGROS OCCIDENTAL) | P00721634VS | Construction of Drainage Structure | 122.9539 | 10.6842 | 29400000 | 29400000 | 2024 | HOMEWORLD CONSTRUCTION CORP. (FORMERLY HOMEWORLD E | 6903 | 2023 | 2024-01-11 | 02/08/2023 | 0 | 0 | 2024-01-10 |  | 1
2022 | Region VI | ILOILO | BAROTAC NUEVO (ILOILO) | P00620432VS | Construction of Flood Mitigation Structure | 122.7882 | 10.9001 | 19600000 | 19110082.98 | 2022 | MZ BUILDERS & CONSTRUCTION SUPPLY | 6904 | 2022 | 2022-07-15 | 03/29/2022 | 489917.02 | 0 | 2022-07-24 | 9
2023 | Region VII | NEGROS ORIENTAL | PAMPLONA (NEGROS ORIENTAL) | P00721952VS | Rehabilitation / Major Repair of Flood Control Structure | 123.1099 | 9.4723 | 49000000 | 49000000 | 2023 | PHILSOUTH BUILDERS INC (FORMERLY:PHILSOUTH BUILDERS) | 6905 | 2023 | 2023-10-24 | 04/11/2023 | 0 | 0 | 2023-12-03 | 40
2022 | Region VI | NEGROS OCCIDENTAL | ILOG (NEGROS OCCIDENTAL) | P00620267VS | Construction of Flood Mitigation Structure | 122.7891 | 10.0333 | 57900000 | 57900000 | 2023 | LEGACY CONSTRUCTION CORPORATION (FORMERLY: LEGACY CONSTRUCTION) / M.K.U. CONSTRUCTION AND SUPPLY | 6906 | 2022 | 2023-04-03 | 03/14/2022 | 0 | 0 | 2023-03-11 |  | 23
2023 | Region V | CAMARINES SUR | LIBMANAN (CAMARINES SUR) | P00742191LZ | Construction of Flood Mitigation Structure | 123.0081 | 13.7055 | 52470000 | 52469933.27 | 2023 | C.T. LEONCIO CONSTRUCTION & TRADING | 6907 | 2023 | 2023-12-26 | 04/18/2023 | 66.73 | 0 | 2024-01-01 | 6
2022 | Region VI | ILOILO | MINA (ILOILO) | P00633208VS | Construction of Flood Mitigation Structure | 122.5765 | 10.9316 | 59400000 | 59399635.55 | 2024 | TIBIAO-ANTIQUE N.K. ENTERPRISE, INC. | 6908 | 2022 | 2024-09-01 | 05/23/2022 | 364.45 | 0 | 2023-03-16 |  | 535
2023 | Region VII | CEBU | GINATILAN (CEBU) | P00733274VS | Construction of Flood Mitigation Structure | 123.3206 | 9.5685 | 96493921.75 | 96493883.95 | 2023 | QM BUILDERS | 6909 | 2023 | 2023-12-11 | 04/11/2023 | 37.8 | 0 | 2024-02-18 | 69
2021 | Region VI | ILOILO |  | P00521614VS | Construction of Drainage Structure | 122.5795 | 10.7284 | 9750144.89 | 8075088.61 | 2022 | 5'S CONSTRUCTION & SUPPLY | 6910 | 2021 | 2022-07-08 | 02/22/2022 | 1675056.28 | 0 | 2022-07-07 |  | 1
2023 | Region VI | NEGROS OCCIDENTAL | BACOLOD CITY (CAPITAL) (NEGROS OCCIDENTAL) | P00721630VS | Construction of Drainage Structure | 122.9539 | 10.6657 | 24500000 | 24500000 | 2023 | RISM BUILDERS AND CONSTRUCTION SERVICES, INC. (FORMERLY RISM DESIGNER'S & GEN. MDSE. & ENG'G.) | 6911 | 2023 | 2023-08-26 | 02/08/2023 | 0 | 0 | 2023-09-17 | 22
2022 | Region V | CAMARINES SUR | MAGARAO (CAMARINES SUR) | P00621520LZ | Construction of Flood Mitigation Structure | 123.1105 | 13.6667 | 67323491.64 | 67323312.63 | 2023 | PRECIOUS CONSTRUCTION | 6912 | 2022 | 2023-03-03 | 05/24/2022 | 179.01 | 0 | 2023-03-02 |  | 1
2021 | Region V | CAMARINES SUR |  | P00526342LZ | Construction of Flood Mitigation Structure | 122.7902 | 13.8173 | 54299077.17 | 54298479.89 | 2022 | E. GARCIA CONSTRUCTION CORP.(FOR. E. GARCIA CONST | 6913 | 2021 | 2022-08-05 | 08/10/2021 | 597.28 | 0 | 2022-08-04 |  | 1
2021 | Region V | MASBATE |  | P00561848LZ | Construction of Flood Mitigation Structure | 123.3849 | 12.4932 | 24749955.63 | 24749955.63 | 2022 | VAEMAR CONSTRUCTION AND SUPPLY | 6914 | 2021 | 2022-10-08 | 03/01/2022 | 0 | 0 | 2022-10-07 |  | 1
2023 | Region V | CAMARINES NORTE | SANTA ELENA (CAMARINES NORTE) | P00736124LZ | Construction of Flood Mitigation Structure | 122.3979 | 14.2137 | 96499762.64 | 95553815.6 | 2023 | EUS CONSTRUCTION | 6915 | 2023 | 2023-11-16 | 04/05/2023 | 945947.04 | 0 | 2024-01-04 | 49
2022 | Region VI | NEGROS OCCIDENTAL | ISABELA (NEGROS OCCIDENTAL) | P00620443VS | Construction of Slope Protection Structure | 123.0081 | 10.2455 | 96500000 | 96500000 | 2023 | LEGACY CONSTRUCTION CORPORATION (FORMERLY: LEGACY CONSTRUCTION) | 6916 | 2022 | 2023-03-20 | 05/19/2022 | 0 | 0 | 2023-03-19 |  | 1
2023 | Region VI | NEGROS OCCIDENTAL | BACOLOD CITY (CAPITAL) (NEGROS OCCIDENTAL) | P00721631VS | Construction of Drainage Structure | 122.954 | 10.6667 | 19600000 | 19600000 | 2023 | ROCK-WILLIAN CONSTRUCTION AND SUPPLY | 6917 | 2023 | 2023-09-20 | 03/10/2023 | 0 | 0 | 2023-09-27 | 7
2021 | Region VI | ILOILO |  | P00521609VS | Construction of Slope Protection Structure | 122.5801 | 10.9341 | 29400000 | 29009563.52 | 2022 | STELLAR BUILDERS | 6918 | 2021 | 2022-10-17 | 10/08/2021 | 390436.48 | 0 | 2022-03-04 |  | 227
2022 | Region V | CAMARINES SUR | BAAO (CAMARINES SUR) | P00631434LZ | Construction of Flood Mitigation Structure | 123.3857 | 13.4648 | 49000000 | 47285146.43 | 2022 | SISAM CONSTRUCTION & SUPPLIES | 6919 | 2022 | 2022-10-03 | 03/18/2022 | 1714853.57 | 0 | 2022-10-02 |  | 1
2023 | Region VII | CEBU | GINATILAN (CEBU) | P00733275VS | Construction of Flood Mitigation Structure | 123.3206 | 9.5685 | 96493927.35 | 96493927.25 | 2023 | QM BUILDERS | 6920 | 2023 | 2023-12-11 | 04/11/2023 | 0.1 | 0 | 2024-02-10 | 61
2022 | Region VI | NEGROS OCCIDENTAL | ISABELA (NEGROS OCCIDENTAL) | P00620241VS | Construction of Slope Protection Structure | 123.0082 | 10.2456 | 72733980 | 72730969.68 | 2022 | JAIME B. CHING ENTERPRISES | 6921 | 2022 | 2022-09-28 | 02/17/2022 | 3010.32 | 0 | 2022-09-21 |  | 7
2024 | Region V | CAMARINES NORTE | SANTA ELENA (CAMARINES NORTE) | P00820471LZ | Construction of Flood Mitigation Structure | 122.3996 | 14.2112 | 154399220.3 | 154399195.2 | 2024 | HGG BUILDERS & SUPPLY | 6922 | 2024 | 2024-11-30 | 04/08/2024 | 25.1 | 0 | 2025-02-05 | 67
2022 | Region VI | ILOILO | ILOILO CITY (CAPITAL) (ILOILO) | P00630629VS | Construction of Drainage Structure | 122.5858 | 10.7558 | 4900000 | 4353155.8 | 2023 | BOAZ AND JACHIN CONSTRUCTION SUPPLY & SERVICES | 6923 | 2022 | 2023-11-25 | 02/21/2022 | 546844.2 | 0 | 2022-07-24 |  | 489
2022 | Region V | CAMARINES SUR | CANAMAN (CAMARINES SUR) | P00620326LZ | Rehabilitation / Major Repair of Flood Control Structure | 123.1117 | 13.6691 | 144640011.9 | 144640011.9 | 2023 | CENTERWAYS CONSTRUCTION AND DEVELOPMENT INC. / ASCON CONSTRUCTION AND SUPPLY | 6924 | 2022 | 2023-03-26 | 04/08/2022 | 0 | 0 | 2023-03-25 |  | 1
2023 | Region VII | CEBU | GINATILAN (CEBU) | P00733276VS | Construction of Flood Mitigation Structure | 123.3206 | 9.5685 | 91668879.47 | 91668851.52 | 2023 | QM BUILDERS | 6925 | 2023 | 2023-12-11 | 04/11/2023 | 27.95 | 0 | 2024-02-03 | 54
2023 | Region VI | NEGROS OCCIDENTAL | CITY OF KABANKALAN (NEGROS OCCIDENTAL) | P00721741VS | Construction of Flood Mitigation Structure | 122.7968 | 10.0001 | 89262500 | 89262500 | 2023 | LEGACY CONSTRUCTION CORPORATION (FORMERLY: LEGACY CONSTRUCTION) / M.K.U. CONSTRUCTION AND SUPPLY | 6926 | 2023 | 2023-09-19 | 02/20/2023 | 0 | 0 | 2023-10-30 | 41
2022 | Region V | CAMARINES NORTE | BASUD (CAMARINES NORTE) | P00630976LZ | Construction of Flood Mitigation Structure | 123.0082 | 14.0786 | 96499449.21 | 96499449.21 | 2022 | EUS CONSTRUCTION / BRENTMIN ROOFING ENTERPRISE | 6927 | 2022 | 2022-07-25 | 03/18/2022 | 0 | 0 | 2022-12-17 | 145
2024 | Region VI | AKLAN | NEW WASHINGTON (AKLAN) | P00821040VS | Rehabilitation / Major Repair of Flood Control Structure | 122.4267 | 11.6583 | 29400000 | 29399995.16 | 2024 | GREENLAND BUILDERS | 6928 | 2024 | 2024-08-14 | 04/22/2024 | 4.84 | 0 | 2024-11-01 | 79
2023 | Region V | CAMARINES SUR | NABUA (CAMARINES SUR) | P00727327LZ | Construction of Flood Mitigation Structure | 123.386 | 13.4008 | 77129566 | 77128501.17 | 2024 | BICOL GOLDROCK CONSTRUCTION CORPORATION | 6929 | 2023 | 2024-02-19 | 04/20/2023 | 1064.83 | 0 | 2024-02-18 |  | 1
2022 | Region VII | NEGROS ORIENTAL | BAIS CITY (NEGROS ORIENTAL) | P00620048VS | Construction of Flood Mitigation Structure | 123.1123 | 9.9833 | 67550000 | 67550000 | 2022 | PHILSOUTH BUILDERS INC (FORMERLY:PHILSOUTH BUILDERS) | 6930 | 2022 | 2022-12-07 | 02/18/2022 | 0 | 0 | 2022-12-06 |  | 1
2023 | Region VI | NEGROS OCCIDENTAL | CITY OF KABANKALAN (NEGROS OCCIDENTAL) | P00721742VS | Construction of Flood Mitigation Structure | 122.7975 | 10.0086 | 89262500 | 89262500 | 2023 | JAIME B. CHING ENTERPRISES / ESJ AND SONS CONSTRUCTION & CONSTRUCTION SUPPLY, INC. (FORM.:ALFIE'S CONST. &CONST. SUPPLY, INC.) | 6931 | 2023 | 2023-08-22 | 02/20/2023 | 0 | 0 | 2023-10-30 | 69
2022 | Region VI | NEGROS OCCIDENTAL | ISABELA (NEGROS OCCIDENTAL) | P00630207VS | Construction of Slope Protection Structure | 122.954 | 10.2278 | 44100000 | 44100000 | 2022 | LEGACY CONSTRUCTION CORPORATION (FORMERLY: LEGACY CONSTRUCTION) | 6932 | 2022 | 2022-11-22 | 05/19/2022 | 0 | 0 | 2022-11-23 | 1
2023 | Region VI | ILOILO | ILOILO CITY (CAPITAL) (ILOILO) | P00731612VS | Construction of Slope Protection Structure | 122.4273 | 11.0775 | 142337500 | 142337500 | 2024 | MAC BUILDERS CORP. (FORMERLY: MAC BUILDERS DEVELOPMENT CORPORATION) | 6933 | 2023 | 2024-03-20 | 02/07/2023 | 0 | 0 | 2024-03-19 |  | 1
2023 | Region V | CAMARINES SUR | LIBMANAN (CAMARINES SUR) | P00726956LZ | Construction of Flood Mitigation Structure | 123.0085 | 13.7048 | 72375000 | 72374796.65 | 2024 | BICOL GOLDROCK CONSTRUCTION CORPORATION | 6934 | 2023 | 2024-01-25 | 04/05/2023 | 203.35 | 0 | 2024-02-10 | 16
2023 | Region VI | GUIMARAS | JORDAN (CAPITAL) (GUIMARAS) | P00721643VS | Construction of Flood Mitigation Structure | 122.5878 | 10.6637 | 49000000 | 48921423.56 | 2023 | ALPHA & OMEGA GEN. CONTRACTOR & DEVELOPMENT CORP. | 6935 | 2023 | 2023-10-03 | 02/17/2023 | 78576.44 | 0 | 2023-10-28 | 25
2023 | Region V | MASBATE | AROROY (MASBATE) | P00726300LZ | Construction of Flood Mitigation Structure | 123.386 | 12.4936 | 24499976.73 | 24500000 | 2023 | RED DIAMOND CONSTRUCTION AND SUPPLY CORPORATION (FORMERLY: RED DIAMOND CONSTRUCTION) | 6936 | 2023 | 2023-08-09 | 05/19/2023 | 0 | 23.27 | 2023-11-22 | 105
2022 | Region V | CAMARINES SUR | CANAMAN (CAMARINES SUR) | P00620327LZ | Rehabilitation / Major Repair of Flood Control Structure | 123.1133 | 13.626 | 144514022.5 | 144514022.5 | 2023 | CENTERWAYS CONSTRUCTION AND DEVELOPMENT INC. / CHEEREL CONSTRUCTION & SUPPLY | 6937 | 2022 | 2023-06-25 | 04/08/2022 | 0 | 0 | 2023-06-24 |  | 1
2022 | Region VI | NEGROS OCCIDENTAL | CITY OF SIPALAY (NEGROS OCCIDENTAL) | P00620269VS | Construction of Flood Mitigation Structure | 122.4275 | 9.752 | 52834715 | 52834715 | 2022 | JAIME B. CHING ENTERPRISES | 6938 | 2022 | 2022-11-21 | 03/14/2022 | 0 | 0 | 2023-01-25 | 65
2023 | Region VII | CEBU | GINATILAN (CEBU) | P00733304VS | Construction of Flood Mitigation Structure | 123.3206 | 9.5685 | 48993856.08 | 48993826.58 | 2023 | QM BUILDERS | 6939 | 2023 | 2023-11-13 | 04/11/2023 | 29.5 | 0 | 2023-11-12 |  | 1
2023 | Region VII | CEBU | ALEGRIA (CEBU) | P00745603VS | Rehabilitation / Major Repair of Flood Control Structure | 123.3862 | 9.8506 | 88641817.5 | 88641056.04 | 2023 | ZLREJ TRADING AND CONSTRUCTION CORPORATION / GICAR CONSTRUCTION, INC. | 6940 | 2023 | 2023-12-18 | 08/10/2023 | 761.46 | 0 | 2024-05-27 | 161
2022 | Region V | CAMARINES SUR | SAN FERNANDO (CAMARINES SUR) | P00620711LZ | Construction of Dike | 123.115 | 13.4753 | 49000000 | 48017728 | 2022 | G.C.I. CONSTRUCTION AND DEV'T. CORP. | 6941 | 2022 | 2022-09-14 | 02/22/2022 | 982272 | 0 | 2022-09-13 |  | 1
2022 | Region VI | NEGROS OCCIDENTAL | CITY OF KABANKALAN (NEGROS OCCIDENTAL) | P00620268VS | Construction of Flood Mitigation Structure | 122.798 | 9.9955 | 96500000 | 96500000 | 2023 | LEGACY CONSTRUCTION CORPORATION (FORMERLY: LEGACY CONSTRUCTION) / M.K.U. CONSTRUCTION AND SUPPLY | 6942 | 2022 | 2023-06-05 | 03/14/2022 | 0 | 0 | 2023-04-23 |  | 43
2023 | Region VI | NEGROS OCCIDENTAL | HINIGARAN (NEGROS OCCIDENTAL) | P00733230VS | Construction of Slope Protection Structure | 122.954 | 10.2269 | 96500000 | 96500000 | 2024 | LEGACY CONSTRUCTION CORPORATION (FORMERLY: LEGACY CONSTRUCTION) / BCV CONSTRUCTION | 6943 | 2023 | 2024-02-07 | 06/01/2023 | 0 | 0 | 2024-02-06 |  | 1
2023 | Region V | CAMARINES SUR | LIBMANAN (CAMARINES SUR) | P00736128LZ | Construction of Revetment | 123.0087 | 13.704 | 67550000 | 67461008.26 | 2023 | G.C.I. CONSTRUCTION AND DEV'T. CORP. | 6944 | 2023 | 2023-12-18 | 02/22/2023 | 88991.74 | 0 | 2023-12-19 | 1
2023 | Region VII | CEBU | GINATILAN (CEBU) | P00733260VS | Construction of Flood Mitigation Structure | 123.3206 | 9.5685 | 96493926.94 | 96493919.26 | 2023 | QM BUILDERS | 6945 | 2023 | 2023-09-25 | 04/11/2023 | 7.68 | 0 | 2024-02-18 | 146
2022 | Region IX | ZAMBOANGA DEL SUR | KUMALARANG (ZAMBOANGA DEL SUR) | P00630568MN | Construction of Flood Mitigation Structure | 123.117 | 7.7818 | 49000000 | 31820034.82 | 2023 | GENETIAN BUILDERS AND ENTERPRISES INCORPORATED (FORMERLY: GENETIAN BUILDERS) | 6946 | 2022 | 2023-05-29 | 03/31/2022 | 17179965.18 | 0 | 2022-11-08 |  | 202
2024 | Region VI | NEGROS OCCIDENTAL | SAN CARLOS CITY (NEGROS OCCIDENTAL) | P00820013VS | Construction of Flood Mitigation Structure | 123.3872 | 10.4675 | 77200000 | 77200000 | 2024 | RKVT CONSTRUCTION / WILKINSON CONSTRUCTION | 6947 | 2024 | 2024-12-05 | 04/29/2024 | 0 | 0 | 2025-02-06 | 63
2023 | Region VI | ILOILO | ILOILO CITY (CAPITAL) (ILOILO) | P00731611VS | Construction of Slope Protection Structure | 122.428 | 11.0779 | 142337500 | 142337500 | 2024 | MONOLITHIC CONSTRUCTION & CONCRETE PRODUCTS, INC. | 6948 | 2023 | 2024-03-20 | 02/07/2023 | 0 | 0 | 2024-03-19 |  | 1
2023 | Region VI | GUIMARAS | JORDAN (CAPITAL) (GUIMARAS) | P00721491VS | Construction of Flood Mitigation Structure | 122.5897 | 10.662 | 72375000 | 72374214.1 | 2023 | ST. MATTHEW GEN. CONTRACTOR & DEVELOPMENT CORP. / S.T. SALCEDO CONSTRUCTION CORP.(FORMERLY: SHAK CONSTRUCTION & SUPPLY) | 6949 | 2023 | 2023-10-10 | 02/17/2023 | 785.9 | 0 | 2023-12-16 | 67
2023 | Region V | CAMARINES SUR | CANAMAN (CAMARINES SUR) | P00726611LZ | Rehabilitation / Major Repair of Flood Control Structure | 123.1176 | 13.6202 | 125282575.1 | 123941697.7 | 2023 | 417 LP CONSTRUCTION CORPORATION / STEVEN CONSTRUCTION & SUPPLY | 6950 | 2023 | 2023-12-13 | 05/03/2023 | 1340877.4 | 0 | 2024-02-21 | 70
2024 | Region VI | NEGROS OCCIDENTAL | CITY OF KABANKALAN (NEGROS OCCIDENTAL) | P00820293VS | Construction of Flood Mitigation Structure | 122.7993 | 9.9997 | 125450000 | 125450000 | 2025 | HOMEWORLD CONSTRUCTION CORP. (FORMERLY HOMEWORLD E | 6951 | 2024 | 2025-01-23 | 02/22/2024 | 0 | 0 | 2025-01-22 |  | 1
2022 | Region V | CAMARINES SUR | CANAMAN (CAMARINES SUR) | P00621521LZ | Construction of Flood Mitigation Structure | 123.1184 | 13.6181 | 77199869.2 | 77199308.02 | 2023 | 417 LP CONSTRUCTION CORPORATION / STEVEN CONSTRUCTION & SUPPLY | 6952 | 2022 | 2023-04-11 | 04/01/2022 | 561.18 | 0 | 2023-04-15 | 4
2024 | Region IV-A | QUEZON | SAN NARCISO (QUEZON) | P00820292LZ | Construction of Flood Mitigation Structure | 122.5897 | 13.4728 | 96499982.76 | 96500000 | 2024 | VFL BUILDERS / WAWAO BUILDERS | 6953 | 2024 | 2024-09-19 | 02/14/2024 | 0 | 17.24 | 2024-12-08 | 80
2023 | Region VII | CEBU | GINATILAN (CEBU) | P00733261VS | Construction of Flood Mitigation Structure | 123.3206 | 9.5685 | 96493921.52 | 96493901.55 | 2023 | QM BUILDERS | 6954 | 2023 | 2023-12-11 | 04/11/2023 | 19.97 | 0 | 2024-02-18 | 69
2023 | Region VI | NEGROS OCCIDENTAL | SAN CARLOS CITY (NEGROS OCCIDENTAL) | P00721872VS | Construction of Flood Mitigation Structure | 123.3873 | 10.4951 | 38600000 | 38600000 | 2023 | KENNETH CONSTRUCTION AND GENERAL MERCHANDISE | 6955 | 2023 | 2023-12-02 | 04/05/2023 | 0 | 0 | 2023-12-01 |  | 1
2022 | Region VI | NEGROS OCCIDENTAL | MANAPLA (NEGROS OCCIDENTAL) | P00620096VS | Construction of Flood Mitigation Structure | 123.1228 | 10.9411 | 44099994.25 | 44097985 | 2022 | C'ZARLES CONSTRUCTION & SUPPLY / GKMM CONSTRUCTION & SUPPLIES, INC. (FORMERLY: GKMM CONSTRUCTION & SUPPLIES) | 6956 | 2022 | 2022-08-30 | 02/08/2022 | 2009.25 | 0 | 2022-09-04 | 5
2023 | Region V | CAMARINES NORTE | LABO (CAMARINES NORTE) | P00737561LZ | Construction of Flood Mitigation Structure | 122.7996 | 14.1997 | 4949218.45 | 4300548.63 | 2023 | GOLDEN CONSTRUCTION AND SUPPLY | 6957 | 2023 | 2023-08-09 | 04/05/2023 | 648669.82 | 0 | 2023-08-08 |  | 1
2023 | Region VI | ILOILO | ILOILO CITY (CAPITAL) (ILOILO) | P00731610VS | Construction of Slope Protection Structure | 122.4286 | 11.0782 | 142337500 | 142337500 | 2024 | IBC INTERNATIONAL BUILDERS CORPORATION | 6958 | 2023 | 2024-03-20 | 02/07/2023 | 0 | 0 | 2024-03-19 |  | 1
2022 | Region V | CAMARINES SUR | CALABANGA (CAMARINES SUR) | P00621522LZ | Construction of Flood Mitigation Structure | 123.1245 | 13.7247 | 67549896.9 | 67549873.69 | 2022 | PEU CONSTRUCTION AND SUPPLY / STEVEN CONSTRUCTION & SUPPLY | 6959 | 2022 | 2022-12-05 | 04/06/2022 | 23.21 | 0 | 2023-01-08 | 34
2023 | Region VII | NEGROS ORIENTAL | CITY OF BAYAWAN (TULONG) (NEGROS ORIENTAL) | P00722002VS | Construction of Flood Mitigation Structure | 122.8011 | 9.3692 | 49000000 | 49000000 | 2023 | LEGACY CONSTRUCTION CORPORATION (FORMERLY: LEGACY CONSTRUCTION) / MIGHTY HOK SUMMIT CONSTRUCTION & DEVELOPMENT CORP. | 6960 | 2023 | 2023-12-15 | 04/19/2023 | 0 | 0 | 2024-03-17 | 93
2023 | Region VI | NEGROS OCCIDENTAL | SAN CARLOS CITY (NEGROS OCCIDENTAL) | P00721507VS | Construction of Flood Mitigation Structure | 123.3875 | 10.4675 | 91674990.57 | 91674989.91 | 2023 | KENNETH CONSTRUCTION AND GENERAL MERCHANDISE | 6961 | 2023 | 2023-12-24 | 03/02/2023 | 0.66 | 0 | 2023-12-23 |  | 1
2022 | Region IX | ZAMBOANGA SIBUGAY | IPIL (CAPITAL) (ZAMBOANGA SIBUGAY) | P00620261MN | Construction of Flood Mitigation Structure | 122.5906 | 7.7852 | 39200000 | 39049908.32 | 2022 | LAKEWOOD CONSTRUCTION COMPANY | 6962 | 2022 | 2022-10-17 | 02/23/2022 | 150091.68 | 0 | 2023-02-03 | 109
2023 | Region VII | CEBU | GINATILAN (CEBU) | P00733303VS | Construction of Flood Mitigation Structure | 123.3206 | 9.5685 | 48993836.6 | 48993817.63 | 2023 | QM BUILDERS | 6963 | 2023 | 2023-11-13 | 04/11/2023 | 18.97 | 0 | 2023-11-12 |  | 1
2022 | Region II | ISABELA | PALANAN (ISABELA) | P00621064LZ | Construction of Flood Mitigation Structure | 122.4287 | 17.06 | 47014507.53 | 46307660.7 | 2023 | CAMBERWELL CONSTRUCTION AND SUPPLIES / EGB CONSTRUCTION CORPORATION (FORMERLY: EGB CONSTRUCTION) | 6964 | 2022 | 2023-12-15 | 04/13/2022 | 706846.83 | 0 | 2023-12-14 |  | 1
2023 | Region V | CAMARINES SUR | GAINZA (CAMARINES SUR) | P00742206LZ | Construction of Flood Mitigation Structure | 123.126 | 13.6124 | 74250000 | 74250000 | 2023 | LEGACY CONSTRUCTION CORPORATION (FORMERLY: LEGACY CONSTRUCTION) | 6965 | 2023 | 2023-11-20 | 04/04/2023 | 0 | 0 | 2024-02-09 | 81
2023 | Region VII | NEGROS ORIENTAL | CITY OF BAYAWAN (TULONG) (NEGROS ORIENTAL) | P00721850VS | Construction of Flood Mitigation Structure | 122.8019 | 9.3689 | 49000000 | 49000000 | 2023 | LEGACY CONSTRUCTION CORPORATION (FORMERLY: LEGACY CONSTRUCTION) / MIGHTY HOK SUMMIT CONSTRUCTION & DEVELOPMENT CORP. | 6966 | 2023 | 2023-12-15 | 03/20/2023 | 0 | 0 | 2024-06-05 | 173
2023 | Region VI | GUIMARAS | JORDAN (CAPITAL) (GUIMARAS) | P00721644VS | Construction of Flood Mitigation Facility | 122.5916 | 10.6595 | 49000000 | 48997205.76 | 2023 | S.T. SALCEDO CONSTRUCTION CORP.(FORMERLY: SHAK CONSTRUCTION & SUPPLY) | 6967 | 2023 | 2023-11-27 | 02/11/2023 | 2794.24 | 0 | 2023-11-02 |  | 25
2024 | Region V | CAMARINES SUR | NABUA (CAMARINES SUR) | P00821408LZ | Construction of Flood Mitigation Structure | 123.3207 | 13.4177 | 96500000 | 96500000 | 2024 | BICOL GOLDROCK CONSTRUCTION CORPORATION | 6968 | 2024 | 2024-07-25 | 02/21/2024 | 0 | 0 | 2024-12-10 | 138
2022 | Region II | ISABELA | PALANAN (ISABELA) | P00631131LZ | Construction of Flood Mitigation Structure | 122.4299 | 17.0578 | 39199990.39 | 38415942.07 | 2023 | ROAD EDGE TRADING & DEVELOPMENT SERVICES | 6969 | 2022 | 2023-10-20 | 02/14/2022 | 784048.32 | 0 | 2023-12-14 | 55
2024 | Region VI | NEGROS OCCIDENTAL | MANAPLA (NEGROS OCCIDENTAL) | P00832632VS | Construction of Drainage Structure | 123.127 | 10.9573 | 4949998.46 | 4947989.58 | 2024 | LEGACY CONSTRUCTION CORPORATION (FORMERLY: LEGACY CONSTRUCTION) | 6970 | 2024 | 2024-06-04 | 03/13/2024 | 2008.88 | 0 | 2024-06-03 |  | 1
2023 | Region VII | NEGROS ORIENTAL | CITY OF BAYAWAN (TULONG) (NEGROS ORIENTAL) | P00722003VS | Construction of Flood Mitigation Structure | 122.8019 | 9.3686 | 49000000 | 49000000 | 2024 | PHILSOUTH BUILDERS INC (FORMERLY:PHILSOUTH BUILDERS) | 6971 | 2023 | 2024-03-22 | 03/29/2023 | 0 | 0 | 2024-03-21 |  | 1
2021 | Region VI | ILOILO |  | P00521538VS | Construction of Flood Mitigation Facility | 122.5934 | 10.7948 | 115800000 | 108845699.4 | 2024 | F. GURREA CONSTRUCTION, INCORPORATED | 6972 | 2021 | 2024-06-06 | 03/17/2022 | 6954300.6 | 0 | 2024-04-22 |  | 45
2023 | Region VI | AKLAN | NEW WASHINGTON (AKLAN) | P00721622VS | Rehabilitation / Major Repair of Flood Control Structure | 122.4299 | 11.6551 | 49000000 | 48999990.69 | 2024 | GREENLAND BUILDERS / MONOLITHIC CONSTRUCTION & CONCRETE PRODUCTS, INC. | 6973 | 2023 | 2024-03-18 | 04/03/2023 | 9.31 | 0 | 2024-03-17 |  | 1
2022 | Region VII | CEBU | ALEGRIA (CEBU) | P00633009VS | Construction of Dike | 123.3887 | 9.7497 | 48509993.45 | 48509993.45 | 2022 | ZLREJ TRADING AND CONSTRUCTION CORPORATION / GICAR CONSTRUCTION, INC. | 6974 | 2022 | 2022-10-24 | 03/23/2022 | 0 | 0 | 2022-10-23 |  | 1
2022 | Region V | CAMARINES SUR | CALABANGA (CAMARINES SUR) | P00621519LZ | Construction of Flood Mitigation Structure | 123.1288 | 13.716 | 57880302.79 | 57879793.55 | 2023 | STEVEN CONSTRUCTION & SUPPLY | 6975 | 2022 | 2023-06-01 | 04/01/2022 | 509.24 | 0 | 2023-05-31 |  | 1
2023 | Region VII | CEBU | GINATILAN (CEBU) | P00733258VS | Construction of Flood Mitigation Structure | 123.3208 | 9.5686 | 96495829.19 | 96495413.69 | 2024 | LEGACY CONSTRUCTION CORPORATION (FORMERLY: LEGACY CONSTRUCTION) | 6976 | 2023 | 2024-04-11 | 04/11/2023 | 415.5 | 0 | 2024-04-10 |  | 1
2024 | Region IX | ZAMBOANGA SIBUGAY | KABASALAN (ZAMBOANGA SIBUGAY) | P00820011MN | Rehabilitation / Major Repair of Flood Control Structure | 122.8039 | 7.7824 | 53075000 | 38178711.63 | 2024 | BELVIC ENTERPRISES & CONSTRUCTION / FFJJ CONSTRUCTION | 6977 | 2024 | 2024-09-25 | 04/05/2024 | 14896288.37 | 0 | 2024-11-20 | 56
2022 | Region VI | ILOILO | ALIMODIAN (ILOILO) | P00620239VS | Construction of Flood Mitigation Structure | 122.4314 | 10.8397 | 96500000 | 96477262.26 | 2023 | SUPREME ABF CONST. & CONST. SUPPLY COMPANY INC. | 6978 | 2022 | 2023-03-13 | 02/18/2022 | 22737.74 | 0 | 2023-03-12 |  | 1
2023 | Region V | CAMARINES SUR | NABUA (CAMARINES SUR) | P00726613LZ | Construction of Flood Mitigation Structure | 123.3217 | 13.4171 | 77167492 | 77167401.48 | 2023 | G.C.I. CONSTRUCTION AND DEV'T. CORP. | 6979 | 2023 | 2023-10-27 | 02/16/2023 | 90.52 | 0 | 2023-11-02 | 6
2022 | Region VI | ILOILO | BANATE (ILOILO) | P00620016VS | Construction of Flood Mitigation Structure | 122.8062 | 10.9972 | 86675335 | 84636253.6 | 2023 | F. GURREA CONSTRUCTION, INCORPORATED | 6980 | 2022 | 2023-02-20 | 02/18/2022 | 2039081.4 | 0 | 2022-09-14 |  | 159
2024 | Region VI | ILOILO | ALIMODIAN (ILOILO) | P00820267VS | Construction of Flood Mitigation Structure | 122.4314 | 10.8375 | 66695010 | 66694563.99 | 2024 | WOODLAND CONSTRUCTION & SUPPLY, INC. | 6981 | 2024 | 2024-09-20 | 02/14/2024 | 446.01 | 0 | 2024-10-31 | 41
2022 | Region VII | CEBU | ALEGRIA (CEBU) | P00633010VS | Construction of Dike | 123.3887 | 9.7497 | 48705992.01 | 48705992.01 | 2022 | ZLREJ TRADING AND CONSTRUCTION CORPORATION / GICAR CONSTRUCTION, INC. | 6982 | 2022 | 2022-10-25 | 03/23/2022 | 0 | 0 | 2022-10-24 |  | 1
2024 | Region VI | NEGROS OCCIDENTAL | CADIZ CITY (NEGROS OCCIDENTAL) | P00820172VS | Construction of Flood Mitigation Structure | 123.3222 | 10.9369 | 48999993.48 | 48997432.14 | 2024 | SILVERGRACES CONSTRUCTION AND CONSTRUCTION SUPPLY | 6983 | 2024 | 2024-09-09 | 03/13/2024 | 2561.34 | 0 | 2024-09-08 |  | 1
2024 | Region VII | NEGROS ORIENTAL | CITY OF BAYAWAN (TULONG) (NEGROS ORIENTAL) | P00820404VS | Construction of Flood Mitigation Structure | 122.8101 | 9.3767 | 45080000 | 45080000 | 2024 | ELITE GENERAL CONTRACTOR AND DEVELOPMENT CORP. | 6984 | 2024 | 2024-07-12 | 03/11/2024 | 0 | 0 | 2024-09-30 | 80
2023 | Region VI | ILOILO | ALIMODIAN (ILOILO) | P00721749VS | Construction of Flood Mitigation Structure | 122.4319 | 10.8371 | 96500000 | 96499785.68 | 2024 | A.D. PENDON CONSTRUCTION & SUPPLY, INC. (FORMERLY: ADP CONSTRUCTION & SUPPLY) | 6985 | 2023 | 2024-03-25 | 02/10/2023 | 214.32 | 0 | 2024-10-14 | 203
2023 | Region VII | CEBU | ALEGRIA (CEBU) | P00721875VS | Construction of Dike | 123.3888 | 9.7504 | 96305251.57 | 96305249.03 | 2023 | ZLREJ TRADING AND CONSTRUCTION CORPORATION / GICAR CONSTRUCTION, INC. | 6986 | 2023 | 2023-11-21 | 03/16/2023 | 2.54 | 0 | 2024-01-23 | 63
2023 | Region VII | CEBU | ALEGRIA (CEBU) | P00721878VS | Construction of Dike | 123.3891 | 9.7483 | 96401751.14 | 96401605 | 2023 | NEWBIG FOUR J CONSTRUCTION INC., (FORMERLY FOUR J | 6987 | 2023 | 2023-06-20 | 03/16/2023 | 146.14 | 0 | 2024-01-23 | 217
2023 | Region VI | ILOILO | BANATE (ILOILO) | P00721657VS | Construction of Flood Mitigation Structure | 122.8101 | 10.9978 | 29400000 | 29085839.72 | 2023 | PANAY EAST COAST CONSTRUCTION & SUPPLY | 6988 | 2023 | 2023-11-22 | 02/13/2023 | 314160.28 | 0 | 2023-09-18 |  | 65
2022 | Region VI | ILOILO | ALIMODIAN (ILOILO) | P00620240VS | Construction of Flood Mitigation Structure | 122.4335 | 10.8146 | 96500000 | 96499040.75 | 2022 | A.D. PENDON CONSTRUCTION & SUPPLY, INC. (FORMERLY: ADP CONSTRUCTION & SUPPLY) | 6989 | 2022 | 2022-12-19 | 02/18/2022 | 959.25 | 0 | 2023-04-25 | 127
2022 | Region VI | NEGROS OCCIDENTAL | CADIZ CITY (NEGROS OCCIDENTAL) | P00620100VS | Construction of Flood Mitigation Structure | 123.3222 | 10.9369 | 44099984.87 | 44097764 | 2022 | C'ZARLES CONSTRUCTION & SUPPLY | 6990 | 2022 | 2022-08-14 | 02/08/2022 | 2220.87 | 0 | 2022-08-13 |  | 1
2024 | Region VI | ILOILO | ALIMODIAN (ILOILO) | P00820268VS | Construction of Flood Mitigation Structure | 122.4337 | 10.812 | 86850000 | 86848871.29 | 2024 | A.D. PENDON CONSTRUCTION & SUPPLY, INC. (FORMERLY: ADP CONSTRUCTION & SUPPLY) | 6991 | 2024 | 2024-09-20 | 02/14/2024 | 1128.71 | 0 | 2024-12-09 | 80
2023 | Region VII | CEBU | ALEGRIA (CEBU) | P00721877VS | Construction of Dike | 123.3891 | 9.7483 | 96305254.11 | 96305168.91 | 2023 | CENTERWAYS CONSTRUCTION AND DEVELOPMENT INC. | 6992 | 2023 | 2023-06-20 | 03/16/2023 | 85.2 | 0 | 2024-01-23 | 217
2024 | Region VII | NEGROS ORIENTAL | CITY OF GUIHULNGAN (NEGROS ORIENTAL) | P00834572VS | Construction of Flood Mitigation Structure | 123.3229 | 10.2644 | 57900000 | 57900000 | 2024 | HOMEWORLD CONSTRUCTION CORP. (FORMERLY HOMEWORLD E | 6993 | 2024 | 2024-11-20 | 03/07/2024 | 0 | 0 | 2024-11-19 |  | 1
2023 | Region VI | AKLAN | NEW WASHINGTON (AKLAN) | P00721482VS | Rehabilitation / Major Repair of Flood Control Structure | 122.4338 | 11.6516 | 72375000 | 72374990.05 | 2024 | GREENLAND BUILDERS / MONOLITHIC CONSTRUCTION & CONCRETE PRODUCTS, INC. | 6994 | 2023 | 2024-04-30 | 04/03/2023 | 9.95 | 0 | 2024-04-30 | 0
2023 | Region V | CAMARINES SUR | TINAMBAC (CAMARINES SUR) | P00727217LZ | Rehabilitation / Major Repair of Flood Control Structure | 123.3234 | 13.8195 | 49000000 | 48997981.5 | 2023 | KCS CONSTRUCTION & SUPPLY | 6995 | 2023 | 2023-12-18 | 06/19/2023 | 2018.5 | 0 | 2024-03-30 | 103
2024 | Region VI | ILOILO | ALIMODIAN (ILOILO) | P00834636VS | Construction of Flood Mitigation Structure | 122.4344 | 10.8088 | 97510000 | 97509993.65 | 2024 | IBC INTERNATIONAL BUILDERS CORPORATION | 6996 | 2024 | 2024-12-17 | 03/12/2024 | 6.35 | 0 | 2025-02-25 | 70
2022 | Region V | CAMARINES SUR | NABUA (CAMARINES SUR) | P00630992LZ | Rehabilitation / Major Repair of Flood Control Structure | 123.3234 | 13.4183 | 50662500 | 50661882.68 | 2022 | RICHMAR CONSTRUCTION | 6997 | 2022 | 2022-12-09 | 03/22/2022 | 617.32 | 0 | 2022-12-10 | 1
2024 | Region VII | CEBU | MALABUYOC (CEBU) | P00834666VS | Construction of Flood Mitigation Structure | 123.3234 | 9.6477 | 39196412.06 | 39195962.06 | 2024 | KENNETH CONSTRUCTION AND GENERAL MERCHANDISE | 6998 | 2024 | 2024-09-09 | 02/26/2024 | 450 | 0 | 2024-09-08 |  | 1
2023 | Region VII | CEBU | GINATILAN (CEBU) | P00745595VS | Rehabilitation / Major Repair of Flood Control Structure | 123.3236 | 9.5728 | 93359605.29 | 93358722 | 2024 | QM BUILDERS | 6999 | 2023 | 2024-04-24 | 08/10/2023 | 883.29 | 0 | 2024-06-05 | 42
2023 | Region VII | CEBU | MALABUYOC (CEBU) | P00745602VS | Rehabilitation / Major Repair of Flood Control Structure | 123.3239 | 9.6476 | 45508662.88 | 44812058.15 | 2023 | QM BUILDERS | 7000 | 2023 | 2023-12-18 | 09/04/2023 | 696604.73 | 0 | 2024-03-12 | 85
2023 | Region VI | NEGROS OCCIDENTAL | SAN CARLOS CITY (NEGROS OCCIDENTAL) | P00721506VS | Construction of Flood Mitigation Structure | 123.4323 | 10.5349 | 48250000 | 48250000 | 2024 | KENNETH CONSTRUCTION AND GENERAL MERCHANDISE | 7001 | 2023 | 2024-04-05 | 02/10/2023 | 0 | 0 | 2024-04-04 |  | 1
2024 | Region V | CAMARINES SUR | GOA (CAMARINES SUR) | P00844569LZ | Construction of Flood Mitigation Structure | 123.4331 | 13.7819 | 120625000 | 120625000 | 2025 | SUNWEST, INC. (FORMERLY: SUNWEST CONSTRUCTION & DEVELOPMENT CORPORATION) | 7002 | 2024 | 2025-03-31 | 05/09/2024 | 0 | 0 | 2025-05-07 | 37
2023 | Region VII | CEBU | RONDA (CEBU) | P00733743VS | Construction of Flood Mitigation Structure | 123.4337 | 9.9807 | 96497699.8 | 96496313.54 | 2023 | NEWBIG FOUR J CONSTRUCTION INC., (FORMERLY FOUR J | 7003 | 2023 | 2023-06-21 | 04/11/2023 | 1386.26 | 0 | 2024-02-18 | 242
2023 | Region VII | CEBU | MINGLANILLA (CEBU) | P00721536VS | Construction of Drainage Structure | 123.8004 | 10.2472 | 67550000 | 67550000 | 2024 | ARQ BUILDERS / 647 CONSTRUCTION AND DEVELOPMENT CORPORATION | 7004 | 2023 | 2024-02-12 | 05/23/2023 | 0 | 0 | 2024-02-11 |  | 1
2024 | Region VII | CEBU | LILOAN (CEBU) | P00820052VS | Construction of Flood Mitigation Structure | 124.0055 | 10.4276 | 96500000 | 96474783.85 | 2024 | MC GEOMETRIC PROPORTIONS, INC. / ST. MATTHEW GEN. CONTRACTOR & DEVELOPMENT CORP. | 7005 | 2024 | 2024-12-26 | 02/16/2024 | 25216.15 | 0 | 2024-12-25 |  | 1
2023 | Region VII | BOHOL | TUBIGON (BOHOL) | P00721939VS | Construction of Flood Mitigation Structure | 123.9467 | 9.9388 | 9800000 | 9785651.71 | 2023 | 3N CONSTRUCTION & SUPPLY | 7006 | 2023 | 2023-11-17 | 05/12/2023 | 14348.29 | 0 | 2023-11-16 |  | 1
2023 | Region VII | CEBU | RONDA (CEBU) | P00733250VS | Construction of Flood Mitigation Structure | 123.4337 | 9.9807 | 96207968.1 | 96207226.8 | 2023 | LEGACY CONSTRUCTION CORPORATION (FORMERLY: LEGACY CONSTRUCTION) | 7007 | 2023 | 2023-12-18 | 04/11/2023 | 741.3 | 0 | 2024-02-18 | 62
2024 | Region IX | ZAMBOANGA DEL SUR | MAHAYAG (ZAMBOANGA DEL SUR) | P00821212MN | Construction of Flood Mitigation Structure | 123.4338 | 8.1083 | 39200000 | 39174963.49 | 2024 | MJMARI BUILDERS AND DEVELOPMENT CORPORATION (FORMERLY: MJMARI BUILDERS AND ENTERPRISES) | 7008 | 2024 | 2024-09-20 | 02/19/2024 | 25036.51 | 0 | 2024-09-19 |  | 1
2024 | Region VII | CEBU | DUMANJUG (CEBU) | P00820873VS | Construction of Flood Mitigation Structure | 123.4342 | 10.0597 | 48243868.9 | 48239207.23 | 2024 | QM BUILDERS | 7009 | 2024 | 2024-11-20 | 06/03/2024 | 4661.67 | 0 | 2025-01-06 | 47
2023 | Region V | ALBAY | LIBON (ALBAY) | P00740465LZ | Construction of Flood Mitigation Structure | 123.4342 | 13.3231 | 146555000 | 72304999.43 | 2023 | RAMARPLUS INCORPORATED (FORMERLY RAMAR ENTERPRISES | 7010 | 2023 | 2023-11-30 | 05/15/2023 | 74250000.57 | 0 | 2024-03-08 | 99
2024 | Region V | CAMARINES SUR | GOA (CAMARINES SUR) | P00844570LZ | Construction of Flood Mitigation Structure | 123.4342 | 13.7844 | 120625000 | 120625000 | 2024 | SUNWEST, INC. (FORMERLY: SUNWEST CONSTRUCTION & DEVELOPMENT CORPORATION) | 7011 | 2024 | 2024-12-28 | 05/09/2024 | 0 | 0 | 2025-05-03 | 126
2023 | Region VII | CEBU | RONDA (CEBU) | P00733249VS | Construction of Flood Mitigation Structure | 123.4347 | 9.98 | 96302861.55 | 96302851.43 | 2023 | WORLDWIDE BUILDERS | 7012 | 2023 | 2023-08-23 | 04/11/2023 | 10.12 | 0 | 2024-02-18 | 179
2022 | Region VI | NEGROS OCCIDENTAL | SALVADOR BENEDICTO (NEGROS OCCIDENTAL) | P00620258VS | Construction of Flood Mitigation Structure | 123.4349 | 10.5284 | 48249770.18 | 48249939.29 | 2022 | KENNETH CONSTRUCTION AND GENERAL MERCHANDISE / SUPREME ABF CONST. & CONST. SUPPLY COMPANY INC. | 7013 | 2022 | 2022-09-01 | 02/21/2022 | 0 | 169.11 | 2022-08-31 |  | 1
2023 | Region IX | ZAMBOANGA DEL SUR | LABANGAN (ZAMBOANGA DEL SUR) | P00721494MN | Construction of Flood Mitigation Structure | 123.435 | 7.922 | 19600000 | 19586447.87 | 2024 | GENETIAN BUILDERS AND ENTERPRISES INCORPORATED (FORMERLY: GENETIAN BUILDERS) | 7014 | 2023 | 2024-08-16 | 04/26/2023 | 13552.13 | 0 | 2023-08-15 |  | 367
2024 | Region IX | ZAMBOANGA DEL SUR | LABANGAN (ZAMBOANGA DEL SUR) | P00820392MN | Construction of Flood Mitigation Structure | 123.4358 | 7.9201 | 29400000 | 29382350.72 | 2024 | GENETIAN BUILDERS AND ENTERPRISES INCORPORATED (FORMERLY: GENETIAN BUILDERS) | 7015 | 2024 | 2024-09-05 | 02/19/2024 | 17649.28 | 0 | 2024-09-04 |  | 1
2023 | Region V | ALBAY | LIBON (ALBAY) | P00740466LZ | Construction of Flood Mitigation Structure | 123.4367 | 13.2709 | 146555000 | 72373483.6 | 2023 | RAMARPLUS INCORPORATED (FORMERLY RAMAR ENTERPRISES | 7016 | 2023 | 2023-11-15 | 05/03/2023 | 74181516.4 | 0 | 2024-02-25 | 102
2024 | Region VII | CEBU | RONDA (CEBU) | P00834596VS | Construction of Flood Mitigation Structure | 123.4368 | 9.98 | 57896085.01 | 57895771.96 | 2024 | LEGACY CONSTRUCTION CORPORATION (FORMERLY: LEGACY CONSTRUCTION) | 7017 | 2024 | 2024-05-13 | 03/12/2024 | 313.05 | 0 | 2024-10-29 | 169
2024 | Region VII | CEBU | RONDA (CEBU) | P00834595VS | Construction of Flood Mitigation Structure | 123.4368 | 9.98 | 57896066.39 | 57895766.39 | 2024 | LEGACY CONSTRUCTION CORPORATION (FORMERLY: LEGACY CONSTRUCTION) | 7018 | 2024 | 2024-07-12 | 04/01/2024 | 300 | 0 | 2024-11-18 | 129
2022 | Region VI | NEGROS OCCIDENTAL | SAN CARLOS CITY (NEGROS OCCIDENTAL) | P00620256VS | Construction of Flood Mitigation Structure | 123.4393 | 10.5123 | 33775000 | 33775000 | 2023 | JAIME B. CHING ENTERPRISES | 7019 | 2022 | 2023-08-12 | 03/02/2022 | 0 | 0 | 2023-08-11 |  | 1
2023 | Region VII | CEBU | OSLOB (CEBU) | P00721675VS | Construction of Flood Mitigation Structure | 123.4405 | 9.5341 | 29400000 | 29399995.65 | 2023 | EDANNA CONSTRUCTION | 7020 | 2023 | 2023-05-15 | 02/10/2023 | 4.35 | 0 | 2023-08-25 | 102
2023 | Region V | ALBAY | CITY OF TABACO (ALBAY) | P00727205LZ | Construction of Flood Mitigation Structure | 123.4411 | 13.2136 | 71049999.14 | 29400000 | 2024 | SANRHO BUILDERS, INC.(FOR. SANRHO CONST. AND SUPPL | 7021 | 2023 | 2024-02-14 | 06/26/2023 | 41649999.14 | 0 | 2024-02-13 |  | 1
2022 | Region V | ALBAY | MALILIPOT (ALBAY) | P00631351LZ | Rehabilitation / Major Repair of Flood Control Structure | 123.4414 | 13.1914 | 19599999.96 | 19600000 | 2022 | CAJUGOTAN BUILDERS AND DEVELOPMENT CORP. (FOR: CAJUGOTAN CONSTRUCTION & SUPPLY) | 7022 | 2022 | 2022-07-11 | 03/16/2022 | 0 | 0.04 | 2022-07-13 | 2
2022 | Region V | ALBAY | MALILIPOT (ALBAY) | P00631323LZ | Construction of Drainage Structure | 123.4424 | 13.1956 | 53899992.32 | 4900000 | 2023 | 3DIAMONDS CONSTRUCTION CORPORATION | 7023 | 2022 | 2023-01-29 | 08/05/2022 | 48999992.32 | 0 | 2023-01-28 |  | 1
2022 | Region V | ALBAY | MALILIPOT (ALBAY) | P00631324LZ | Construction of Drainage Structure | 123.4426 | 13.1944 | 53899992.32 | 4900000 | 2023 | 3DIAMONDS CONSTRUCTION CORPORATION | 7024 | 2022 | 2023-01-29 | 08/05/2022 | 48999992.32 | 0 | 2023-01-28 |  | 1
2022 | Region IX | ZAMBOANGA DEL NORTE | DAPITAN CITY (ZAMBOANGA DEL NORTE) | P00620199MN | Construction of Flood Mitigation Structure | 123.4443 | 8.5381 | 94770720 | 93823025.2 | 2023 | LEGACY CONSTRUCTION CORPORATION (FORMERLY: LEGACY CONSTRUCTION) | 7025 | 2022 | 2023-10-03 | 02/24/2022 | 947694.8 | 0 | 2023-10-02 |  | 1
2022 | Region VII | CEBU | DUMANJUG (CEBU) | P00620044VS | Construction of Flood Mitigation Structure | 123.4444 | 10.0539 | 49071869.95 | 48320749 | 2022 | QM BUILDERS | 7026 | 2022 | 2022-09-26 | 02/21/2022 | 751120.95 | 0 | 2022-09-25 |  | 1
2022 | Region V | ALBAY | PIO DURAN (ALBAY) | P00631373LZ | Rehabilitation / Major Repair of Flood Control Structure | 123.4449 | 13.0471 | 92956675.49 | 43987387.89 | 2023 | RAMARPLUS INCORPORATED (FORMERLY RAMAR ENTERPRISES | 7027 | 2022 | 2023-03-01 | 03/22/2022 | 48969287.6 | 0 | 2023-02-28 |  | 1
2022 | Region VII | CEBU | DUMANJUG (CEBU) | P00620457VS | Construction of Flood Mitigation Structure | 123.4459 | 10.0647 | 48999927.85 | 48999927.85 | 2022 | QM BUILDERS | 7028 | 2022 | 2022-11-10 | 03/23/2022 | 0 | 0 | 2022-11-09 |  | 1
2023 | Region VII | CEBU | MOALBOAL (CEBU) | P00733255VS | Construction of Flood Mitigation Structure | 123.4461 | 9.9517 | 96302757.9 | 96302742.83 | 2023 | LEGACY CONSTRUCTION CORPORATION (FORMERLY: LEGACY CONSTRUCTION) | 7029 | 2023 | 2023-12-18 | 04/11/2023 | 15.07 | 0 | 2024-02-18 | 62
2023 | Region VII | CEBU | MOALBOAL (CEBU) | P00733254VS | Construction of Flood Mitigation Structure | 123.4462 | 9.9516 | 96302851.74 | 96302624.08 | 2023 | LEGACY CONSTRUCTION CORPORATION (FORMERLY: LEGACY CONSTRUCTION) | 7030 | 2023 | 2023-12-11 | 04/11/2023 | 227.66 | 0 | 2024-02-18 | 69
2023 | Region VII | CEBU | MOALBOAL (CEBU) | P00733256VS | Construction of Flood Mitigation Structure | 123.4463 | 9.9517 | 96302901.81 | 96302869.75 | 2023 | LEGACY CONSTRUCTION CORPORATION (FORMERLY: LEGACY CONSTRUCTION) | 7031 | 2023 | 2023-12-18 | 04/11/2023 | 32.06 | 0 | 2024-02-18 | 62
2023 | Region VII | CEBU | MOALBOAL (CEBU) | P00733302VS | Construction of Flood Mitigation Structure | 123.4463 | 9.9517 | 48997410.83 | 48996438 | 2023 | QM BUILDERS | 7032 | 2023 | 2023-11-15 | 04/11/2023 | 972.83 | 0 | 2023-11-14 |  | 1
2023 | Region VII | CEBU | MOALBOAL (CEBU) | P00733257VS | Construction of Flood Mitigation Structure | 123.4463 | 9.9516 | 96303005.92 | 96302785.31 | 2023 | LEGACY CONSTRUCTION CORPORATION (FORMERLY: LEGACY CONSTRUCTION) | 7033 | 2023 | 2023-12-11 | 04/11/2023 | 220.61 | 0 | 2024-02-10 | 61
2023 | Region VII | CEBU | MOALBOAL (CEBU) | P00733745VS | Rehabilitation / Major Repair of Flood Control Structure | 123.4463 | 9.9516 | 96497377.37 | 96497149.81 | 2024 | NEWBIG FOUR J CONSTRUCTION INC., (FORMERLY FOUR J | 7034 | 2023 | 2024-04-19 | 04/11/2023 | 227.56 | 0 | 2024-04-18 |  | 1
2022 | Region V | CAMARINES SUR | TIGAON (CAMARINES SUR) | P00620313LZ | Construction of Flood Mitigation Structure | 123.4465 | 13.585 | 82025000 | 82025000 | 2023 | PARTIDO CONSTRUCTION & SUPPLY | 7035 | 2022 | 2023-01-13 | 04/05/2022 | 0 | 0 | 2023-04-26 | 103
2023 | Region V | ALBAY | CITY OF TABACO (ALBAY) | P00727210LZ | Construction of Flood Mitigation Structure | 123.4466 | 13.213 | 71049999.14 | 41650000 | 2024 | SANRHO BUILDERS, INC.(FOR. SANRHO CONST. AND SUPPL | 7036 | 2023 | 2024-02-14 | 06/26/2023 | 29399999.14 | 0 | 2024-02-13 |  | 1
2023 | Region VII | CEBU | DUMANJUG (CEBU) | P00721547VS | Construction of Flood Mitigation Structure | 123.4466 | 10.0541 | 87812215.64 | 87812030.33 | 2023 | QM BUILDERS | 7037 | 2023 | 2023-09-27 | 06/27/2023 | 185.31 | 0 | 2024-04-14 | 200
2023 | Region VII | CEBU | DUMANJUG (CEBU) | P00733244VS | Construction of Flood Mitigation Structure | 123.4468 | 10.0537 | 96205468.74 | 96205338.56 | 2023 | QM BUILDERS | 7038 | 2023 | 2023-11-15 | 04/11/2023 | 130.18 | 0 | 2024-02-18 | 95
2023 | Region VII | CEBU | DUMANJUG (CEBU) | P00721510VS | Construction of Revetment | 123.4468 | 10.0534 | 96014118.04 | 96014116.92 | 2023 | QM BUILDERS | 7039 | 2023 | 2023-11-20 | 02/08/2023 | 1.12 | 0 | 2024-02-15 | 87
2023 | Region VII | CEBU | DUMANJUG (CEBU) | P00721874VS | Construction of Revetment | 123.4469 | 10.053 | 96110620.61 | 96110610.97 | 2024 | QM BUILDERS | 7040 | 2023 | 2024-01-30 | 03/23/2023 | 9.64 | 0 | 2024-03-29 | 59
2022 | Region VII | CEBU | DUMANJUG (CEBU) | P00620042VS | Construction of Flood Mitigation Structure | 123.447 | 10.064 | 48998325.59 | 48998325.59 | 2022 | QM BUILDERS | 7041 | 2022 | 2022-09-26 | 02/10/2022 | 0 | 0 | 2022-09-29 | 3
2024 | Region VII | CEBU | MOALBOAL (CEBU) | P00834661VS | Construction of Flood Mitigation Structure | 123.4489 | 9.9491 | 29395359.15 | 29395164.54 | 2024 | SUDAN CONSTRUCTION AND SUPPLY CORP. | 7042 | 2024 | 2024-04-15 | 02/26/2024 | 194.61 | 0 | 2024-09-12 | 150
2022 | Region V | CAMARINES SUR | LAGONOY (CAMARINES SUR) | P00631421LZ | Construction of Flood Mitigation Structure | 123.4508 | 13.9185 | 49000000 | 49000000 | 2023 | BICOL GOLDROCK CONSTRUCTION CORPORATION | 7043 | 2022 | 2023-08-21 | 03/10/2022 | 0 | 0 | 2023-08-21 | 0
2022 | Region V | MASBATE | MILAGROS (MASBATE) | P00620746LZ | Rehabilitation / Major Repair of Flood Control Structure | 123.4528 | 12.2261 | 25080105.49 | 25080160 | 2022 | GACT ENTERPRISES | 7044 | 2022 | 2022-08-16 | 02/08/2022 | 0 | 54.51 | 2022-08-15 |  | 1
2022 | Region V | ALBAY | BACACAY (ALBAY) | P00631331LZ | Rehabilitation / Major Repair of Flood Control Structure | 123.4535 | 13.1346 | 48999731.93 | 49000000 | 2022 | 3DIAMONDS CONSTRUCTION CORPORATION | 7045 | 2022 | 2022-11-25 | 05/09/2022 | 0 | 268.07 | 2022-11-24 |  | 1
2022 | Region V | ALBAY | BACACAY (ALBAY) | P00631336LZ | Rehabilitation / Major Repair of Flood Control Structure | 123.4538 | 13.1527 | 48999292.7 | 49000000 | 2022 | MAKAPA CORPORATION | 7046 | 2022 | 2022-09-25 | 02/24/2022 | 0 | 707.3 | 2022-09-24 |  | 1
2023 | Region IX | ZAMBOANGA DEL SUR | MAHAYAG (ZAMBOANGA DEL SUR) | P00721599MN | Construction of Flood Mitigation Structure | 123.456 | 8.077 | 53900000 | 53850000 | 2024 | MJMARI BUILDERS AND DEVELOPMENT CORPORATION (FORMERLY: MJMARI BUILDERS AND ENTERPRISES) | 7047 | 2023 | 2024-04-23 | 08/31/2023 | 50000 | 0 | 2024-04-22 |  | 1
2022 | Region V | CAMARINES SUR | TIGAON (CAMARINES SUR) | P00620314LZ | Construction of Flood Mitigation Structure | 123.4569 | 13.5931 | 82025000 | 82025000 | 2023 | PARTIDO CONSTRUCTION & SUPPLY | 7048 | 2022 | 2023-01-18 | 03/17/2022 | 0 | 0 | 2023-01-19 | 1
2023 | Region V | ALBAY | POLANGUI (ALBAY) | P00740467LZ | Construction of Flood Mitigation Structure | 123.4582 | 13.323 | 72375000 | 72375000 | 2023 | RICHMAR CONSTRUCTION | 7049 | 2023 | 2023-09-12 | 04/25/2023 | 0 | 0 | 2024-01-03 | 113
2022 | Region V | CAMARINES SUR | BAAO (CAMARINES SUR) | P00631433LZ | Construction of Flood Mitigation Structure | 123.4596 | 13.4596 | 49000000 | 47282777.73 | 2022 | RAMARPLUS INCORPORATED (FORMERLY RAMAR ENTERPRISES | 7050 | 2022 | 2022-10-25 | 02/22/2022 | 1717222.27 | 0 | 2022-10-24 |  | 1
2023 | Region VII | CEBU | OSLOB (CEBU) | P00721679VS | Construction of Flood Mitigation Structure | 123.4598 | 9.5659 | 14700000 | 14700000 | 2023 | BT CONSTRUCTION AND GENERAL SERVICES | 7051 | 2023 | 2023-09-26 | 03/17/2023 | 0 | 0 | 2023-09-25 |  | 1
2022 | Region V | ALBAY | PIO DURAN (ALBAY) | P00631371LZ | Rehabilitation / Major Repair of Flood Control Structure | 123.4599 | 13.0169 | 19557075.83 | 19557075.83 | 2022 | ELKANKONSTRAK DEVELOPMENT CORPORATION | 7052 | 2022 | 2022-09-29 | 02/17/2022 | 0 | 0 | 2022-09-28 |  | 1
2022 | Region V | ALBAY | CITY OF LIGAO (ALBAY) | P00631382LZ | Rehabilitation / Major Repair of Flood Control Structure | 123.46 | 13.0168 | 19600000 | 19600000 | 2022 | VINMOR CONSTRUCTION AND SUPPLY | 7053 | 2022 | 2022-08-20 | 04/11/2022 | 0 | 0 | 2022-10-06 | 47
2023 | Region IX | ZAMBOANGA DEL SUR | RAMON MAGSAYSAY (LIARGO) (ZAMBOANGA DEL SUR) | P00721605MN | Construction of Flood Mitigation Structure | 123.46 | 8.053 | 53900000 | 53849885.62 | 2023 | NRMM CONSTRUCTION AND DEV'T CORP. | 7054 | 2023 | 2023-12-18 | 04/26/2023 | 50114.38 | 0 | 2023-12-17 |  | 1
2024 | Region IX | ZAMBOANGA DEL SUR | PAGADIAN CITY (CAPITAL) (ZAMBOANGA DEL SUR) | P00821073MN | Construction of Flood Mitigation Structure | 123.4627 | 7.8472 | 29400000 | 29374518.4 | 2024 | ZMS CONST. & DEV. CORP. (FORMERLY:ZMS CONSTRUCTION | 7055 | 2024 | 2024-08-08 | 02/19/2024 | 25481.6 | 0 | 2024-09-04 | 27
2023 | Region VII | CEBU | RONDA (CEBU) | P00733252VS | Construction of Flood Mitigation Structure | 123.4627 | 9.972 | 96304438.09 | 96304156.61 | 2024 | LEGACY CONSTRUCTION CORPORATION (FORMERLY: LEGACY CONSTRUCTION) | 7056 | 2023 | 2024-02-19 | 04/11/2023 | 281.48 | 0 | 2024-02-18 |  | 1
2023 | Region VII | CEBU | RONDA (CEBU) | P00733253VS | Construction of Flood Mitigation Structure | 123.4628 | 9.972 | 96497418.6 | 96497208.87 | 2023 | LEGACY CONSTRUCTION CORPORATION (FORMERLY: LEGACY CONSTRUCTION) | 7057 | 2023 | 2023-12-18 | 04/11/2023 | 209.73 | 0 | 2024-02-18 | 62
2023 | Region IX | ZAMBOANGA DEL SUR | PAGADIAN CITY (CAPITAL) (ZAMBOANGA DEL SUR) | P00721603MN | Construction of Flood Mitigation Structure | 123.463 | 7.847 | 78400000 | 78400000 | 2024 | GENETIAN BUILDERS AND ENTERPRISES INCORPORATED (FORMERLY: GENETIAN BUILDERS) / ZMS CONST. & DEV. CORP. (FORMERLY:ZMS CONSTRUCTION | 7058 | 2023 | 2024-03-08 | 05/29/2023 | 0 | 0 | 2024-03-07 |  | 1
2023 | Region VII | CEBU | RONDA (CEBU) | P00733744VS | Construction of Flood Mitigation Structure | 123.463 | 9.9724 | 96496918.11 | 96496818.2 | 2023 | LEGACY CONSTRUCTION CORPORATION (FORMERLY: LEGACY CONSTRUCTION) | 7059 | 2023 | 2023-12-18 | 04/11/2023 | 99.91 | 0 | 2024-02-18 | 62
2023 | Region VII | CEBU | RONDA (CEBU) | P00733242VS | Construction of Flood Mitigation Structure | 123.463 | 9.9724 | 96207965.7 | 96207944.4 | 2023 | WTG CONSTRUCTION & DEVELOPMENT CORPORATION | 7060 | 2023 | 2023-12-19 | 04/11/2023 | 21.3 | 0 | 2024-02-18 | 61
2022 | Region VII | CEBU | RONDA (CEBU) | P00633003VS | Construction of Revetment | 123.4631 | 9.9728 | 48999980.42 | 48999980.42 | 2022 | WTG CONSTRUCTION & DEVELOPMENT CORPORATION | 7061 | 2022 | 2022-10-25 | 03/23/2022 | 0 | 0 | 2022-10-24 |  | 1
2023 | Region VII | CEBU | RONDA (CEBU) | P00733237VS | Construction of Flood Mitigation Structure | 123.4631 | 9.9728 | 96303649.73 | 96303639.41 | 2024 | WTG CONSTRUCTION & DEVELOPMENT CORPORATION | 7062 | 2023 | 2024-02-19 | 04/11/2023 | 10.32 | 0 | 2024-02-18 |  | 1
2022 | Region VII | CEBU | RONDA (CEBU) | P00633002VS | Construction of Revetment | 123.4631 | 9.9729 | 48999971.56 | 48395100 | 2022 | WTG CONSTRUCTION & DEVELOPMENT CORPORATION | 7063 | 2022 | 2022-10-25 | 03/23/2022 | 604871.56 | 0 | 2022-10-24 |  | 1
2023 | Region VII | CEBU | RONDA (CEBU) | P00733239VS | Construction of Flood Mitigation Structure | 123.4632 | 9.9729 | 96304465.68 | 96304443.13 | 2024 | WTG CONSTRUCTION & DEVELOPMENT CORPORATION | 7064 | 2023 | 2024-02-19 | 04/11/2023 | 22.55 | 0 | 2024-02-18 |  | 1
2023 | Region VII | CEBU | RONDA (CEBU) | P00733241VS | Construction of Flood Mitigation Structure | 123.4637 | 9.9726 | 96400965.21 | 96400924.58 | 2023 | WTG CONSTRUCTION & DEVELOPMENT CORPORATION | 7065 | 2023 | 2023-12-19 | 04/11/2023 | 40.63 | 0 | 2024-02-18 | 61
2022 | Region VI | NEGROS OCCIDENTAL | SALVADOR BENEDICTO (NEGROS OCCIDENTAL) | P00620257VS | Construction of Flood Mitigation Structure | 123.4647 | 10.5616 | 48250000 | 48250000 | 2022 | WILKINSON CONSTRUCTION | 7066 | 2022 | 2022-09-11 | 03/02/2022 | 0 | 0 | 2022-09-10 |  | 1
2024 | Region V | ALBAY | OAS (ALBAY) | P00823607LZ | Construction of Flood Mitigation Structure | 123.465 | 13.2562 | 144750000 | 144750000 | 2025 | RICHMAR CONSTRUCTION | 7067 | 2024 | 2025-02-08 | 04/15/2024 | 0 | 0 | 2025-02-07 |  | 1
2023 | Region V | ALBAY | POLANGUI (ALBAY) | P00740471LZ | Construction of Flood Mitigation Structure | 123.4656 | 13.3622 | 144610000 | 72305000 | 2024 | RAMARPLUS INCORPORATED (FORMERLY RAMAR ENTERPRISES | 7068 | 2023 | 2024-05-08 | 05/15/2023 | 72305000 | 0 | 2024-05-07 |  | 1
2023 | Region VII | CEBU | DUMANJUG (CEBU) | P00721886VS | Construction of Flood Mitigation Structure | 123.4681 | 10.0361 | 96498255.29 | 96498045.79 | 2023 | QM BUILDERS | 7069 | 2023 | 2023-10-11 | 03/23/2023 | 209.5 | 0 | 2024-01-30 | 111
2024 | Region VII | CEBU | DUMANJUG (CEBU) | P00832615VS | Construction of Flood Mitigation Structure | 123.4687 | 10.0372 | 98996961.23 | 98996461.23 | 2024 | QM BUILDERS | 7070 | 2024 | 2024-10-03 | 02/16/2024 | 500 | 0 | 2024-12-17 | 75
2021 | Region V | ALBAY |  | P00526484LZ | Rehabilitation / Major Repair of Flood Control Structure | 123.4715 | 13.2888 | 30380000 | 29316368.64 | 2022 | MAKAPA CORPORATION | 7071 | 2021 | 2022-07-31 | 01/19/2022 | 1063631.36 | 0 | 2022-07-31 | 0
2022 | Region V | ALBAY | POLANGUI (ALBAY) | P00620692LZ | Construction of Flood Mitigation Structure | 123.4717 | 13.286 | 21824600 | 21824598.38 | 2023 | R. RELATO CONSTRUCTION | 7072 | 2022 | 2023-01-06 | 06/06/2022 | 1.62 | 0 | 2023-01-05 |  | 1
2021 | Region VI | NEGROS OCCIDENTAL |  | P00521541VS | Construction of Flood Mitigation Structure | 123.4731 | 10.5709 | 79106840 | 79106840 | 2022 | A.C. RIVERO DEVELOPMENT CORPORATION | 7073 | 2021 | 2022-08-02 | 02/19/2021 | 0 | 0 | 2022-08-01 |  | 1
2022 | Region IX | ZAMBOANGA DEL NORTE | LABASON (ZAMBOANGA DEL NORTE) | P00620004MN | Construction of Flood Mitigation Structure | 123.4734 | 8.0603 | 97294497.96 | 97293841.99 | 2022 | ALPHA & OMEGA GEN. CONTRACTOR & DEVELOPMENT CORP. | 7074 | 2022 | 2022-12-20 | 02/18/2022 | 655.97 | 0 | 2023-04-07 | 108
2022 | Region V | MASBATE | AROROY (MASBATE) | P00620738LZ | Construction of Flood Mitigation Structure | 123.4751 | 12.4853 | 24499969.03 | 24499132.16 | 2022 | JOHNCB CONSTRUCTION & SUPPLIES | 7075 | 2022 | 2022-08-15 | 02/08/2022 | 836.87 | 0 | 2022-08-14 |  | 1
2023 | Region VII | CEBU | DUMANJUG (CEBU) | P00721509VS | Construction of Revetment | 123.4752 | 10.0295 | 96305247.38 | 96302053.8 | 2023 | QM BUILDERS | 7076 | 2023 | 2023-08-23 | 02/08/2023 | 3193.58 | 0 | 2023-12-18 | 117
2023 | Region VII | CEBU | DUMANJUG (CEBU) | P00721887VS | Construction of Flood Mitigation Structure | 123.4752 | 10.0295 | 96498243.99 | 96492809.55 | 2023 | QM BUILDERS | 7077 | 2023 | 2023-08-22 | 03/23/2023 | 5434.44 | 0 | 2024-01-30 | 161
2022 | Region V | ALBAY | OAS (ALBAY) | P00631369LZ | Rehabilitation / Major Repair of Flood Control Structure | 123.4768 | 13.2583 | 19600000 | 19598937.42 | 2022 | ELKANKONSTRAK DEVELOPMENT CORPORATION | 7078 | 2022 | 2022-07-16 | 02/17/2022 | 1062.58 | 0 | 2022-07-15 |  | 1
2023 | Region VII | CEBU | DUMANJUG (CEBU) | P00733236VS | Construction of Flood Mitigation Structure | 123.4785 | 10.0231 | 96496735.66 | 96496733.21 | 2023 | QUIRANTE CONSTRUCTION CORPORATION (FORMERLY: QUIRANTE CONSTRUCTION) | 7079 | 2023 | 2023-12-11 | 04/11/2023 | 2.45 | 0 | 2024-02-10 | 61
2023 | Region VII | CEBU | BOLJOON (CEBU) | P00721941VS | Construction of Flood Mitigation Structure | 123.4787 | 9.6236 | 29400000 | 29399938.4 | 2023 | WYNE ROSE CONSTRUCTION AND SUPPLY CORP. | 7080 | 2023 | 2023-08-15 | 05/04/2023 | 61.6 | 0 | 2023-11-16 | 93
2023 | Region VII | CEBU | DUMANJUG (CEBU) | P00733247VS | Construction of Flood Mitigation Structure | 123.4798 | 10.0223 | 86846017.51 | 86845976.88 | 2024 | QM BUILDERS | 7081 | 2023 | 2024-03-28 | 04/11/2023 | 40.63 | 0 | 2024-03-27 |  | 1
2023 | Region VII | CEBU | DUMANJUG (CEBU) | P00733246VS | Construction of Flood Mitigation Structure | 123.4798 | 10.0223 | 86847453.38 | 86847397.29 | 2023 | QM BUILDERS | 7082 | 2023 | 2023-09-25 | 04/11/2023 | 56.09 | 0 | 2024-01-25 | 122
2023 | Region VII | CEBU | DUMANJUG (CEBU) | P00733248VS | Construction of Flood Mitigation Structure | 123.4798 | 10.0223 | 96496917.46 | 96496912.4 | 2023 | QM BUILDERS | 7083 | 2023 | 2023-12-18 | 04/11/2023 | 5.06 | 0 | 2024-02-18 | 62
2023 | Region VII | CEBU | DUMANJUG (CEBU) | P00733245VS | Construction of Flood Mitigation Structure | 123.4798 | 10.0223 | 96304067.86 | 94860000 | 2023 | QM BUILDERS | 7084 | 2023 | 2023-12-15 | 04/11/2023 | 1444067.86 | 0 | 2024-02-18 | 65
2023 | Region VII | CEBU | DUMANJUG (CEBU) | P00733235VS | Construction of Flood Mitigation Structure | 123.4801 | 10.0225 | 96497705.05 | 96497704.66 | 2023 | QUIRANTE CONSTRUCTION CORPORATION (FORMERLY: QUIRANTE CONSTRUCTION) | 7085 | 2023 | 2023-12-11 | 04/11/2023 | 0.39 | 0 | 2024-02-10 | 61
2024 | Region V | CAMARINES SUR | BUHI (CAMARINES SUR) | P00820425LZ | Construction of Flood Mitigation Structure | 123.4802 | 13.4024 | 139925000 | 139925000 | 2024 | SISBRO CONSTRUCTION CORPORATION (FORMERLY: SISBRO CONSTRUCTION & SUPPLY) | 7086 | 2024 | 2024-11-19 | 02/21/2024 | 0 | 0 | 2025-02-10 | 83
2023 | Region IX | ZAMBOANGA DEL SUR | LABANGAN (ZAMBOANGA DEL SUR) | P00721602MN | Construction of Flood Mitigation Structure | 123.481 | 7.875 | 14700000 | 14684995.71 | 2023 | ZMS CONST. & DEV. CORP. (FORMERLY:ZMS CONSTRUCTION | 7087 | 2023 | 2023-08-14 | 03/13/2023 | 15004.29 | 0 | 2023-08-01 |  | 13
2023 | Region IX | ZAMBOANGA DEL SUR | LABANGAN (ZAMBOANGA DEL SUR) | P00721604MN | Construction of Flood Mitigation Structure | 123.481 | 7.894 | 53900000 | 53851405.11 | 2025 | GENETIAN BUILDERS AND ENTERPRISES INCORPORATED (FORMERLY: GENETIAN BUILDERS) | 7088 | 2023 | 2025-02-06 | 04/26/2023 | 48594.89 | 0 | 2024-02-15 |  | 357
2023 | Region V | CAMARINES SUR | BUHI (CAMARINES SUR) | P00726973LZ | Construction of Flood Mitigation Structure | 123.4819 | 13.4015 | 139824182 | 139819182 | 2024 | HI-TONE CONSTRUCTION & DEVELOPMENT CORP. (FORMERLY | 7089 | 2023 | 2024-07-12 | 03/22/2023 | 5000 | 0 | 2024-07-11 |  | 1
2022 | Region VII | CEBU | DUMANJUG (CEBU) | P00633008VS | Construction of Dike | 123.482 | 10.0211 | 48754979.41 | 48754979.41 | 2022 | WORLDWIDE BUILDERS / QUIRANTE CONSTRUCTION CORPORATION (FORMERLY: QUIRANTE CONSTRUCTION) | 7090 | 2022 | 2022-10-25 | 03/23/2022 | 0 | 0 | 2022-10-24 |  | 1
2022 | Region VII | CEBU | DUMANJUG (CEBU) | P00633007VS | Construction of Dike | 123.482 | 10.0211 | 48264980.74 | 48264980.74 | 2022 | QUIRANTE CONSTRUCTION CORPORATION (FORMERLY: QUIRANTE CONSTRUCTION) | 7091 | 2022 | 2022-10-24 | 03/23/2022 | 0 | 0 | 2022-10-23 |  | 1
2022 | Region V | SORSOGON | DONSOL (SORSOGON) | P00620325LZ | Construction of Flood Mitigation Structure | 123.4837 | 12.9879 | 279839557.3 | 140956866 | 2023 | CENTERWAYS CONSTRUCTION AND DEVELOPMENT INC. | 7092 | 2022 | 2023-12-20 | 07/14/2022 | 138882691.3 | 0 | 2023-12-31 | 11
2023 | Region VII | CEBU | DUMANJUG (CEBU) | P00721946VS | Construction of Dike | 123.4863 | 10.0072 | 48997646.06 | 48997477.13 | 2023 | WORLDWIDE BUILDERS | 7093 | 2023 | 2023-05-16 | 03/06/2023 | 168.93 | 0 | 2023-10-07 | 144
2023 | Region VII | CEBU | DUMANJUG (CEBU) | P00733234VS | Construction of Flood Mitigation Structure | 123.4863 | 10.0072 | 96498258.25 | 96498225.85 | 2023 | WORLDWIDE BUILDERS | 7094 | 2023 | 2023-06-19 | 04/11/2023 | 32.4 | 0 | 2024-02-10 | 236
2022 | Region VII | CEBU | DUMANJUG (CEBU) | P00633006VS | Construction of Dike | 123.4876 | 10.0026 | 48803966.54 | 48803966.54 | 2022 | WORLDWIDE BUILDERS / QUIRANTE CONSTRUCTION CORPORATION (FORMERLY: QUIRANTE CONSTRUCTION) | 7095 | 2022 | 2022-10-25 | 03/23/2022 | 0 | 0 | 2022-10-24 |  | 1
2023 | Region VII | CEBU | DUMANJUG (CEBU) | P00733238VS | Construction of Flood Mitigation Structure | 123.4893 | 10.0533 | 96302820.25 | 96300450.1 | 2023 | QM BUILDERS | 7096 | 2023 | 2023-12-15 | 04/11/2023 | 2370.15 | 0 | 2024-02-18 | 65
2023 | Region VII | CEBU | DUMANJUG (CEBU) | P00733240VS | Construction of Flood Mitigation Structure | 123.4893 | 10.0533 | 95821967.19 | 95821739.57 | 2023 | QM BUILDERS | 7097 | 2023 | 2023-12-15 | 06/13/2023 | 227.62 | 0 | 2024-04-20 | 127
2023 | Region VII | CEBU | DUMANJUG (CEBU) | P00721524VS | Construction of Revetment | 123.4903 | 10.0541 | 96014135.07 | 96011592.91 | 2023 | QM BUILDERS | 7098 | 2023 | 2023-08-22 | 02/08/2023 | 2542.16 | 0 | 2023-12-17 | 117
2022 | Region V | MASBATE | MILAGROS (MASBATE) | P00620745LZ | Rehabilitation / Major Repair of Flood Control Structure | 123.4905 | 12.2341 | 24465683.83 | 24465683.83 | 2022 | 3R3M CONSTRUCTION AND SUPPLY CORPORATION (FORMERLY: 3R3M CONSTRUCTION AND SUPPLY) | 7099 | 2022 | 2022-08-14 | 02/07/2022 | 0 | 0 | 2022-08-13 |  | 1
2023 | Region V | CAMARINES SUR | GOA (CAMARINES SUR) | P00736101LZ | Construction of Flood Mitigation Structure | 123.4908 | 13.6892 | 95536200 | 95536200 | 2024 | G.C.I. CONSTRUCTION AND DEV'T. CORP. | 7100 | 2023 | 2024-04-01 | 02/26/2023 | 0 | 0 | 2024-03-31 |  | 1
2023 | Region V | ALBAY | POLANGUI (ALBAY) | P00740470LZ | Construction of Flood Mitigation Structure | 123.4913 | 13.3631 | 144610000 | 72305000 | 2024 | RAMARPLUS INCORPORATED (FORMERLY RAMAR ENTERPRISES | 7101 | 2023 | 2024-05-08 | 05/15/2023 | 72305000 | 0 | 2024-05-07 |  | 1
2021 | Region V | MASBATE |  | P00561849LZ | Construction of Flood Mitigation Structure | 123.4915 | 12.2348 | 29699956.55 | 29700000 | 2022 | 3R3M CONSTRUCTION AND SUPPLY CORPORATION (FORMERLY: 3R3M CONSTRUCTION AND SUPPLY) | 7102 | 2021 | 2022-08-30 | 02/28/2022 | 0 | 43.45 | 2022-09-10 | 11
2022 | Region V | ALBAY | OAS (ALBAY) | P00631370LZ | Rehabilitation / Major Repair of Flood Control Structure | 123.493 | 13.2725 | 19600000 | 19600000 | 2022 | ELKANKONSTRAK DEVELOPMENT CORPORATION | 7103 | 2022 | 2022-11-10 | 03/10/2022 | 0 | 0 | 2022-11-09 |  | 1
2022 | Region V | CAMARINES SUR | TIGAON (CAMARINES SUR) | P00620316LZ | Construction of Flood Mitigation Structure | 123.4931 | 13.6403 | 82025000 | 82025000 | 2022 | PARTIDO CONSTRUCTION & SUPPLY | 7104 | 2022 | 2022-11-11 | 04/05/2022 | 0 | 0 | 2023-01-28 | 78
2024 | Region X | MISAMIS OCCIDENTAL | TANGUB CITY (MISAMIS OCCIDENTAL) | P00835875MN | Rehabilitation / Major Repair of Flood Control Structure | 123.6964 | 8.092 | 4900000 | 4752999.28 | 2024 | ABIB BUILDERS ENTERPRISE | 7105 | 2024 | 2024-11-24 | 04/08/2024 | 147000.72 | 0 | 2024-07-14 |  | 133
2023 | Region VII | CEBU | MANDAUE CITY (CEBU) | P00721760VS | Construction of Flood Mitigation Structure | 123.9472 | 10.3421 | 96500000 | 96399888 | 2023 | QUIRANTE CONSTRUCTION CORPORATION (FORMERLY: QUIRANTE CONSTRUCTION) | 7106 | 2023 | 2023-11-28 | 05/11/2023 | 100112 | 0 | 2024-04-10 | 134
2023 | Region V | SORSOGON | PILAR (SORSOGON) | P00742485LZ | Rehabilitation / Major Repair of Flood Control Structure | 123.6966 | 12.8711 | 56939964.51 | 4949945.99 | 2023 | CENTERWAYS CONSTRUCTION AND DEVELOPMENT INC. / CHEEREL CONSTRUCTION & SUPPLY | 7107 | 2023 | 2023-11-17 | 03/27/2023 | 51990018.52 | 0 | 2023-11-18 | 1
2023 | Region V | ALBAY | DARAGA (LOCSIN) (ALBAY) | P00740443LZ | Construction of Dike | 123.6969 | 13.1669 | 72373544.13 | 72373476.66 | 2023 | NEXT GENERATION CONSTRUCTION AND SUPPLY CORPORATION | 7108 | 2023 | 2023-09-30 | 04/19/2023 | 67.47 | 0 | 2023-10-23 | 23
2024 | Region X | MISAMIS OCCIDENTAL | TANGUB CITY (MISAMIS OCCIDENTAL) | P00835871MN | Construction of Drainage Structure | 123.6974 | 8.0917 | 4900000 | 4752999.45 | 2024 | WEISENWORK CONSTRUCTION | 7109 | 2024 | 2024-11-24 | 04/08/2024 | 147000.55 | 0 | 2024-07-14 |  | 133
2022 | Region X | MISAMIS OCCIDENTAL | PLARIDEL (MISAMIS OCCIDENTAL) | P00620153MN | Construction of Flood Mitigation Structure | 123.6974 | 8.6294 | 35404460 | 35404455.04 | 2022 | RITCHE-NATHALIE BUILDERS & GENERAL MERCHANDISE | 7110 | 2022 | 2022-09-20 | 03/14/2022 | 4.96 | 0 | 2022-10-08 | 18
2023 | Region V | ALBAY | DARAGA (LOCSIN) (ALBAY) | P00737377LZ | Construction of Dike | 123.6975 | 13.1626 | 67548487.89 | 67548347.27 | 2023 | AJAN JEADA, INC. (FORMERLY: JEADA CONSTRUCTION) | 7111 | 2023 | 2023-09-15 | 02/27/2023 | 140.62 | 0 | 2023-09-19 | 4
2023 | Region V | ALBAY | DARAGA (LOCSIN) (ALBAY) | P00737378LZ | Construction of Dike | 123.6979 | 13.1628 | 57898485.71 | 57898423.68 | 2023 | AJAN JEADA, INC. (FORMERLY: JEADA CONSTRUCTION) | 7112 | 2023 | 2023-08-31 | 02/27/2023 | 62.03 | 0 | 2023-09-03 | 3
2021 | Region V | ALBAY |  | P00526194LZ | Construction of Dike | 123.699 | 13.1688 | 29398331.55 | 29398117.6 | 2022 | ANKOR GAULLE CONSTRUCTION AND SUPPLY CORPORATION | 7113 | 2021 | 2022-07-13 | 03/02/2022 | 213.95 | 0 | 2022-07-12 |  | 1
2022 | Region V | ALBAY | DARAGA (LOCSIN) (ALBAY) | P00621129LZ | Construction of Dike | 123.6991 | 13.1689 | 67548441.49 | 67547845.61 | 2022 | NUMERICAL GATE CONSTRUCTION & SUPPLY CORPORATION | 7114 | 2022 | 2022-09-22 | 03/04/2022 | 595.88 | 0 | 2022-10-11 | 19
2023 | Region V | SORSOGON | CITY OF SORSOGON (CAPITAL) (SORSOGON) | P00742487LZ | Construction of Flood Mitigation Structure | 124.0057 | 12.9732 | 54449963.17 | 9557940.64 | 2024 | CENTERWAYS CONSTRUCTION AND DEVELOPMENT INC. / CHEEREL CONSTRUCTION & SUPPLY | 7115 | 2023 | 2024-03-05 | 07/18/2023 | 44892022.53 | 0 | 2024-03-04 |  | 1
2023 | Region VII | CEBU | MINGLANILLA (CEBU) | P00721671VS | Construction of Drainage Structure | 123.8004 | 10.2472 | 9800000 | 9780000 | 2023 | AR ADLAWAN CONSTRUCTION | 7116 | 2023 | 2023-11-14 | 05/04/2023 | 20000 | 0 | 2023-11-13 |  | 1
2022 | Region V | ALBAY | DARAGA (LOCSIN) (ALBAY) | P00621126LZ | Construction of Dike | 123.6992 | 13.165 | 72373180.75 | 72372651.51 | 2022 | CBC CONSTRUCTION & SUPPLY | 7117 | 2022 | 2022-08-31 | 03/04/2022 | 529.24 | 0 | 2022-10-13 | 43
2021 | Region V | ALBAY |  | P00526193LZ | Construction of Dike | 123.7003 | 13.1702 | 29398402.85 | 29397833 | 2022 | ANKOR GAULLE CONSTRUCTION AND SUPPLY CORPORATION | 7118 | 2021 | 2022-07-13 | 03/02/2022 | 569.85 | 0 | 2022-07-12 |  | 1
2023 | Region V | ALBAY | CITY OF TABACO (ALBAY) | P00727203LZ | Construction of Flood Mitigation Structure | 123.7005 | 13.348 | 75459988.26 | 20580000 | 2023 | CAJUGOTAN BUILDERS AND DEVELOPMENT CORP. (FOR: CAJUGOTAN CONSTRUCTION & SUPPLY) / DSB CONSTRUCTION & SUPPLY, INC. (FORMERLY: DSB CO | 7119 | 2023 | 2023-11-06 | 05/15/2023 | 54879988.26 | 0 | 2023-12-09 | 33
2022 | Region V | ALBAY | DARAGA (LOCSIN) (ALBAY) | P00621546LZ | Construction of Flood Mitigation Structure | 123.7024 | 13.1665 | 48998413.09 | 48998161.04 | 2022 | HI-TONE CONSTRUCTION & DEVELOPMENT CORP. (FORMERLY | 7120 | 2022 | 2022-12-26 | 06/30/2022 | 252.05 | 0 | 2022-12-25 |  | 1
2023 | Region X | MISAMIS OCCIDENTAL | PLARIDEL (MISAMIS OCCIDENTAL) | P00721377MN | Construction of Flood Mitigation Structure | 123.7041 | 8.6275 | 49000000 | 47529998.48 | 2023 | MINDANAO ROCK | 7121 | 2023 | 2023-09-14 | 02/26/2023 | 1470001.52 | 0 | 2023-09-13 |  | 1
2022 | Region X | MISAMIS OCCIDENTAL | PLARIDEL (MISAMIS OCCIDENTAL) | P00620152MN | Construction of Flood Mitigation Structure | 123.7044 | 8.6274 | 35404460 | 35348469.03 | 2022 | RITCHE-NATHALIE BUILDERS & GENERAL MERCHANDISE | 7122 | 2022 | 2022-09-20 | 03/14/2022 | 55990.97 | 0 | 2022-10-08 | 18
2022 | Region X | MISAMIS OCCIDENTAL | PLARIDEL (MISAMIS OCCIDENTAL) | P00620154MN | Construction of Flood Mitigation Structure | 123.7046 | 8.6226 | 29400000 | 28421918.91 | 2023 | SILVER CONSTRUCTION | 7123 | 2022 | 2023-04-30 | 06/05/2022 | 978081.09 | 0 | 2022-12-24 |  | 127
2022 | Region V | ALBAY | DARAGA (LOCSIN) (ALBAY) | P00621127LZ | Construction of Dike | 123.7047 | 13.1611 | 67548450.3 | 67548080.26 | 2022 | NUMERICAL GATE CONSTRUCTION & SUPPLY CORPORATION | 7124 | 2022 | 2022-09-22 | 03/04/2022 | 370.04 | 0 | 2022-10-11 | 19
2022 | Region VII | CEBU | DUMANJUG (CEBU) | P00633232VS | Construction of Revetment | 123.4933 | 10.0533 | 48508341.34 | 48508341.34 | 2022 | QM BUILDERS | 7125 | 2022 | 2022-10-25 | 03/23/2022 | 0 | 0 | 2022-10-24 |  | 1
2023 | Region V | ALBAY | DARAGA (LOCSIN) (ALBAY) | P00740669LZ | Construction of Dike | 123.7058 | 13.0988 | 48676181.97 | 48675979.44 | 2023 | NEXT GENERATION CONSTRUCTION AND SUPPLY CORPORATION | 7126 | 2023 | 2023-10-01 | 04/05/2023 | 202.53 | 0 | 2023-09-30 |  | 1
2023 | Region V | MASBATE | SAN JACINTO (MASBATE) | P00736134LZ | Construction of Flood Mitigation Structure | 123.7061 | 12.5697 | 48249895.41 | 48249895.41 | 2024 | CENTERWAYS CONSTRUCTION AND DEVELOPMENT INC. | 7127 | 2023 | 2024-04-02 | 07/13/2023 | 0 | 0 | 2024-04-01 |  | 1
2023 | Region V | ALBAY | MALILIPOT (ALBAY) | P00740473LZ | Construction of Flood Mitigation Structure | 123.7067 | 13.3261 | 96499978.52 | 96500000 | 2023 | HI-TONE CONSTRUCTION & DEVELOPMENT CORP. (FORMERLY | 7128 | 2023 | 2023-12-26 | 04/12/2023 | 0 | 21.48 | 2024-01-08 | 13
2021 | Region X | MISAMIS OCCIDENTAL |  | P00550543MN | Construction of Flood Mitigation Structure | 123.707 | 8.6237 | 63300000 | 58864693.36 | 2022 | RITCHE-NATHALIE BUILDERS & GENERAL MERCHANDISE | 7129 | 2021 | 2022-12-15 | 12/12/2021 | 4435306.64 | 0 | 2022-09-03 |  | 103
2021 | Region X | MISAMIS OCCIDENTAL |  | P00550438MN | Construction of Drainage Structure | 123.707 | 8.6178 | 59400000 | 57899999.97 | 2022 | MAMSAR CONSTRUCTION AND INDUSTRIAL CORPORATION | 7130 | 2021 | 2022-10-18 | 12/15/2021 | 1500000.03 | 0 | 2022-08-10 |  | 69
2023 | Region V | ALBAY | DARAGA (LOCSIN) (ALBAY) | P00726969LZ | Construction of Dike | 123.7084 | 13.1584 | 72373558.73 | 72373340.99 | 2023 | QDC CONSTRUCTION AND SUPPLY / 3RB CONSTRUCTION & SUPPLY | 7131 | 2023 | 2023-12-18 | 04/17/2023 | 217.74 | 0 | 2023-12-17 |  | 1
2022 | Region V | MASBATE | SAN JACINTO (MASBATE) | P00640480LZ | Rehabilitation / Major Repair of Flood Control Structure | 123.7085 | 12.5697 | 98998436.24 | 98998436.24 | 2023 | CENTERWAYS CONSTRUCTION AND DEVELOPMENT INC. | 7132 | 2022 | 2023-06-08 | 07/28/2022 | 0 | 0 | 2023-06-07 |  | 1
2021 | Region X | MISAMIS OCCIDENTAL |  | P00550571MN | Construction of Drainage Structure | 123.7095 | 8.6214 | 9900000 | 8057107.97 | 2022 | RJLG CONSTRUCTION AND SUPPLIES | 7133 | 2021 | 2022-08-31 | 02/08/2022 | 1842892.03 | 0 | 2022-06-30 |  | 62
2023 | Region V | ALBAY | MALINAO (ALBAY) | P00726622LZ | Construction of Flood Mitigation Structure | 123.7099 | 13.4111 | 144748972.1 | 144748972.1 | 2023 | MAKAPA CORPORATION | 7134 | 2023 | 2023-12-15 | 03/30/2023 | 0 | 0 | 2024-01-23 | 39
2023 | Region V | ALBAY | DARAGA (LOCSIN) (ALBAY) | P00740658LZ | Construction of Dike | 123.71 | 13.158 | 24498553.59 | 24498279.9 | 2023 | AJAN JEADA, INC. (FORMERLY: JEADA CONSTRUCTION) | 7135 | 2023 | 2023-07-28 | 04/17/2023 | 273.69 | 0 | 2023-07-27 |  | 1
2023 | Region VII | CEBU | MADRIDEJOS (CEBU) | P00721544VS | Construction of Flood Mitigation Structure | 123.7114 | 11.2587 | 96500000 | 96499608.51 | 2023 | WTG CONSTRUCTION & DEVELOPMENT CORPORATION / ROVILLA CONSTRUCTION | 7136 | 2023 | 2023-12-14 | 02/20/2023 | 391.49 | 0 | 2024-02-24 | 72
2023 | Region V | ALBAY | DARAGA (LOCSIN) (ALBAY) | P00736142LZ | Construction of Dike | 123.7133 | 13.0795 | 48178611.02 | 48178149.83 | 2023 | RCDS CONSTRUCTION & SUPPLY, INC.(FOR RCDS CONST. | 7137 | 2023 | 2023-12-24 | 07/03/2023 | 461.19 | 0 | 2023-12-23 |  | 1
2023 | Region V | MASBATE | SAN FERNANDO (MASBATE) | P00726294LZ | Construction of Flood Mitigation Structure | 123.7136 | 12.4953 | 23520000 | 23519999.15 | 2024 | KYLA CONSTRUCTION SUPPLY | 7138 | 2023 | 2024-02-02 | 04/09/2023 | 0.85 | 0 | 2024-01-01 |  | 32
2024 | Region VII | CEBU | CITY OF NAGA (CEBU) | P00820854VS | Construction of Flood Mitigation Structure | 123.7137 | 10.2705 | 96500000 | 96390888 | 2024 | QUIRANTE CONSTRUCTION CORPORATION (FORMERLY: QUIRANTE CONSTRUCTION) | 7139 | 2024 | 2024-10-15 | 02/23/2024 | 109112 | 0 | 2024-12-24 | 70
2024 | Region VII | CEBU | CITY OF NAGA (CEBU) | P00820867VS | Construction of Flood Mitigation Structure | 123.7137 | 10.2705 | 96500000 | 96399888 | 2024 | QUIRANTE CONSTRUCTION CORPORATION (FORMERLY: QUIRANTE CONSTRUCTION) | 7140 | 2024 | 2024-09-20 | 02/23/2024 | 100112 | 0 | 2024-12-24 | 95
2023 | Region V | ALBAY | MALINAO (ALBAY) | P00727208LZ | Rehabilitation / Major Repair of Flood Control Structure | 123.7143 | 13.4074 | 118739934.6 | 2940000 | 2024 | DSB CONSTRUCTION & SUPPLY, INC. (FORMERLY: DSB CO | 7141 | 2023 | 2024-03-06 | 05/15/2023 | 115799934.6 | 0 | 2024-03-05 |  | 1
2024 | Region VII | CEBU | BALAMBAN (CEBU) | P00820345VS | Construction of Flood Mitigation Structure | 123.7144 | 10.5176 | 96500000 | 96201348.9 | 2024 | WTG CONSTRUCTION & DEVELOPMENT CORPORATION | 7142 | 2024 | 2024-11-20 | 02/12/2024 | 298651.1 | 0 | 2024-11-19 |  | 1
2024 | Region X | MISAMIS OCCIDENTAL | TANGUB CITY (MISAMIS OCCIDENTAL) | P00835872MN | Construction of Drainage Structure | 123.7144 | 8.0947 | 4900000 | 4752999.34 | 2025 | WEISENWORK CONSTRUCTION | 7143 | 2024 | 2025-01-28 | 06/20/2024 | 147000.66 | 0 | 2024-12-24 |  | 35
2023 | Region VII | CEBU | BALAMBAN (CEBU) | P00721767VS | Construction of Flood Mitigation Structure | 123.7145 | 10.5188 | 67550000 | 67451959 | 2023 | HELM CONSTRUCTION & SUPPLIES | 7144 | 2023 | 2023-10-20 | 02/09/2023 | 98041 | 0 | 2023-10-19 |  | 1
2023 | Region V | ALBAY | DARAGA (LOCSIN) (ALBAY) | P00742472LZ | Construction of Dike | 123.7149 | 13.1584 | 29698522.26 | 29698072.37 | 2023 | JEJAN CONSTRUCTION AND SUPPLY(FOR. JEJAN CONSTRUCT | 7145 | 2023 | 2023-08-17 | 04/10/2023 | 449.89 | 0 | 2023-08-29 | 12
2022 | Region V | ALBAY | DARAGA (LOCSIN) (ALBAY) | P00630978LZ | Construction of Flood Mitigation Structure | 123.7149 | 13.1587 | 57898364.38 | 57898264.38 | 2022 | PROTECH CONSTRUCTION & DEVELOPMENT CORP. (FORMERLY / KRATOS DEVELOPMENT CORP. | 7146 | 2022 | 2022-10-23 | 03/21/2022 | 100 | 0 | 2022-10-22 |  | 1
2023 | Region V | ALBAY | MANITO (ALBAY) | P00726976LZ | Construction of Dike | 123.7152 | 13.1585 | 72373550.87 | 72373461.51 | 2023 | CBC CONSTRUCTION & SUPPLY | 7147 | 2023 | 2023-10-22 | 04/10/2023 | 89.36 | 0 | 2023-10-21 |  | 1
2022 | Region V | SORSOGON | PILAR (SORSOGON) | P00620760LZ | Construction of Flood Mitigation Structure | 123.7157 | 12.0202 | 48999974.96 | 47304633.91 | 2022 | CENTERWAYS CONSTRUCTION AND DEVELOPMENT INC. | 7148 | 2022 | 2022-11-18 | 02/16/2022 | 1695341.05 | 0 | 2022-11-18 | 0
2022 | Region V | MASBATE | SAN FERNANDO (MASBATE) | P00640478LZ | Rehabilitation / Major Repair of Flood Control Structure | 123.7165 | 12.4943 | 98999705.73 | 98999705.73 | 2023 | CENTERWAYS CONSTRUCTION AND DEVELOPMENT INC. | 7149 | 2022 | 2023-11-18 | 08/22/2022 | 0 | 0 | 2023-11-17 |  | 1
2022 | Region V | ALBAY | DARAGA (LOCSIN) (ALBAY) | P00631341LZ | Construction of Drainage Structure | 123.7167 | 13.1497 | 29398368.82 | 29397676.96 | 2022 | JEJAN CONSTRUCTION AND SUPPLY(FOR. JEJAN CONSTRUCT | 7150 | 2022 | 2022-12-04 | 04/06/2022 | 691.86 | 0 | 2022-12-03 |  | 1
2022 | Region V | ALBAY | LEGAZPI CITY (CAPITAL) (ALBAY) | P00630999LZ | Rehabilitation / Major Repair of Flood Control Structure | 123.7173 | 13.1966 | 57898285.51 | 57897955 | 2022 | MAKAPA CORPORATION | 7151 | 2022 | 2022-10-18 | 03/16/2022 | 330.51 | 0 | 2022-10-17 |  | 1
2021 | Region VII | CEBU |  | P00549965VS | Construction of Flood Mitigation Structure | 123.7178 | 10.1746 | 77200000 | 77200000 | 2022 | QUIRANTE CONSTRUCTION CORPORATION (FORMERLY: QUIRANTE CONSTRUCTION) | 7152 | 2021 | 2022-08-01 | 11/03/2021 | 0 | 0 | 2022-07-31 |  | 1
2023 | Region V | ALBAY | CITY OF TABACO (ALBAY) | P00740480LZ | Construction of Flood Mitigation Structure | 123.7182 | 13.3538 | 144749999 | 144750000 | 2023 | SANRHO BUILDERS, INC.(FOR. SANRHO CONST. AND SUPPL | 7153 | 2023 | 2023-11-07 | 04/14/2023 | 0 | 1 | 2023-12-26 | 49
2023 | Region V | ALBAY | CITY OF TABACO (ALBAY) | P00727202LZ | Construction of Flood Mitigation Structure | 123.7182 | 13.3538 | 46059971.1 | 21560000 | 2023 | JORMAND CONSTRUCTION & SUPPLY | 7154 | 2023 | 2023-09-15 | 05/09/2023 | 24499971.1 | 0 | 2023-10-22 | 37
2022 | Region V | ALBAY | DARAGA (LOCSIN) (ALBAY) | P00620273LZ | Construction of Flood Mitigation Structure | 123.7206 | 13.1516 | 96498239.06 | 96497819.97 | 2023 | CENTERWAYS CONSTRUCTION AND DEVELOPMENT INC. | 7155 | 2022 | 2023-02-02 | 04/13/2022 | 419.09 | 0 | 2023-02-01 |  | 1
2024 | Region VII | CEBU | CITY OF NAGA (CEBU) | P00820353VS | Construction of Flood Mitigation Structure | 123.722 | 10.2362 | 120625000 | 120575000 | 2024 | QM BUILDERS / JANUARY BUILDERS | 7156 | 2024 | 2024-08-19 | 02/20/2024 | 50000 | 0 | 2024-12-31 | 134
2021 | Region V | ALBAY |  | P00525682LZ | Construction of Flood Mitigation Structure | 123.7225 | 13.1896 | 115799985.6 | 115800000 | 2022 | MAKAPA CORPORATION | 7157 | 2021 | 2022-09-15 | 08/16/2021 | 0 | 14.4 | 2022-10-13 | 28
2022 | Region V | ALBAY | LEGAZPI CITY (CAPITAL) (ALBAY) | P00620684LZ | Construction of Flood Mitigation Structure | 123.7225 | 13.1883 | 40529505.35 | 39191886.59 | 2022 | MAKAPA CORPORATION | 7158 | 2022 | 2022-12-22 | 03/21/2022 | 1337618.76 | 0 | 2022-12-21 |  | 1
2022 | Region V | ALBAY | DARAGA (LOCSIN) (ALBAY) | P00620679LZ | Construction of Flood Mitigation Structure | 123.7234 | 13.1539 | 29398109.49 | 29339615.74 | 2022 | ALPHARD PRIMECON CONSTRUCTION | 7159 | 2022 | 2022-07-17 | 02/21/2022 | 58493.75 | 0 | 2022-07-16 |  | 1
2023 | Region V | ALBAY | LEGAZPI CITY (CAPITAL) (ALBAY) | P00740659LZ | Construction of Dike | 123.7234 | 13.0364 | 48886193 | 48885924.75 | 2023 | CENTERWAYS CONSTRUCTION AND DEVELOPMENT INC. / CBC CONSTRUCTION & SUPPLY | 7160 | 2023 | 2023-12-06 | 06/19/2023 | 268.25 | 0 | 2023-11-29 |  | 7
2024 | Region VII | CEBU | BALAMBAN (CEBU) | P00820399VS | Rehabilitation / Major Repair of Flood Control Structure | 123.7241 | 10.5282 | 19600000 | 19501488.5 | 2024 | W.GO CONSTRUCTION AND SUPPLY | 7161 | 2024 | 2024-07-12 | 02/02/2024 | 98511.5 | 0 | 2024-07-13 | 1
2023 | Region VII | CEBU | BALAMBAN (CEBU) | P00721820VS | Rehabilitation / Major Repair of Flood Control Structure | 123.7245 | 10.527 | 19600000 | 19403655 | 2023 | WTG CONSTRUCTION & DEVELOPMENT CORPORATION | 7162 | 2023 | 2023-07-28 | 02/02/2023 | 196345 | 0 | 2023-07-28 | 0
2024 | Region VII | CEBU | MADRIDEJOS (CEBU) | P00820073VS | Construction of Flood Mitigation Structure | 123.7245 | 11.295 | 96500000 | 96500000 | 2024 | WTG CONSTRUCTION & DEVELOPMENT CORPORATION / ROVILLA CONSTRUCTION | 7163 | 2024 | 2024-11-21 | 02/13/2024 | 0 | 0 | 2024-11-20 |  | 1
2021 | Region V | ALBAY |  | P00561812LZ | Rehabilitation / Major Repair of Flood Control Structure | 123.7246 | 13.3515 | 21037038.51 | 21037500 | 2022 | CAJUGOTAN BUILDERS AND DEVELOPMENT CORP. (FOR: CAJUGOTAN CONSTRUCTION & SUPPLY) | 7164 | 2021 | 2022-09-10 | 04/11/2022 | 0 | 461.49 | 2022-09-27 | 17
2024 | Region X | MISAMIS OCCIDENTAL | PLARIDEL (MISAMIS OCCIDENTAL) | P00835781MN | Construction of Flood Mitigation Structure | 123.7258 | 8.6034 | 86850000 | 86849960.44 | 2025 | ANIMAS BROS CONSTRUCTION CORPORATION (FORMERLY: ANIMAS BROS CONSTRUCTION) | 7165 | 2024 | 2025-03-28 | 05/16/2024 | 39.56 | 0 | 2025-03-28 | 0
2021 | Region V | ALBAY |  | P00561194LZ | Construction of Flood Mitigation Structure | 123.7259 | 13.3519 | 22769820.13 | 22770000 | 2022 | 8AR CONSTRUCTION AND DEVELOPMENT CORPORATION | 7166 | 2021 | 2022-09-09 | 04/20/2022 | 0 | 179.87 | 2022-09-08 |  | 1
2022 | Region V | ALBAY | LEGAZPI CITY (CAPITAL) (ALBAY) | P00620688LZ | Construction of Flood Mitigation Structure | 123.727 | 13.101 | 47979582.02 | 47979306.09 | 2022 | SISBRO CONSTRUCTION CORPORATION (FORMERLY: SISBRO CONSTRUCTION & SUPPLY) / 3RB CONSTRUCTION & SUPPLY | 7167 | 2022 | 2022-07-12 | 02/21/2022 | 275.93 | 0 | 2022-08-15 | 34
2024 | Region V | MASBATE | SAN FERNANDO (MASBATE) | P00821011LZ | Construction of Flood Mitigation Structure | 123.7286 | 12.4897 | 49000000 | 48999995.07 | 2024 | ALXM CONSTRUCTION & DEV'T. CORP. (FORMERLY:ALXM CONSTRUCTION) | 7168 | 2024 | 2024-08-16 | 03/19/2024 | 4.93 | 0 | 2024-11-18 | 94
2023 | Region VII | CEBU | BALAMBAN (CEBU) | P00721765VS | Construction of Flood Mitigation Structure | 123.7289 | 10.5242 | 67550000 | 67177531 | 2023 | HELM CONSTRUCTION & SUPPLIES | 7169 | 2023 | 2023-10-20 | 02/09/2023 | 372469 | 0 | 2023-10-19 |  | 1
2023 | Region V | MASBATE | SAN FERNANDO (MASBATE) | P00726293LZ | Construction of Flood Mitigation Structure | 123.7292 | 12.4889 | 23520000 | 23519966.83 | 2024 | KYLA CONSTRUCTION SUPPLY | 7170 | 2023 | 2024-01-02 | 04/09/2023 | 33.17 | 0 | 2024-01-01 |  | 1
2022 | Region V | ALBAY | LEGAZPI CITY (CAPITAL) (ALBAY) | P00632948LZ | Construction of Flood Mitigation Structure | 123.7293 | 13.0763 | 49498324.28 | 49479552.03 | 2022 | TWINCARE BUILDERS INC. / 3RB CONSTRUCTION & SUPPLY | 7171 | 2022 | 2022-08-19 | 02/21/2022 | 18772.25 | 0 | 2022-08-18 |  | 1
2024 | Region VII | CEBU | BALAMBAN (CEBU) | P00820344VS | Construction of Flood Mitigation Structure | 123.7294 | 10.5221 | 96500000 | 96315000 | 2024 | HELM CONSTRUCTION & SUPPLIES | 7172 | 2024 | 2024-11-20 | 02/12/2024 | 185000 | 0 | 2024-11-19 |  | 1
2023 | Region VII | CEBU | BALAMBAN (CEBU) | P00721766VS | Construction of Flood Mitigation Structure | 123.7295 | 10.527 | 67550000 | 66947542 | 2023 | WTG CONSTRUCTION & DEVELOPMENT CORPORATION | 7173 | 2023 | 2023-10-20 | 02/09/2023 | 602458 | 0 | 2023-10-19 |  | 1
2023 | Region V | ALBAY | LEGAZPI CITY (CAPITAL) (ALBAY) | P00727213LZ | Construction of Dike | 123.7299 | 13.0754 | 29398956.34 | 29398908.74 | 2023 | ROCA BLANCA CONSTRUCTION | 7174 | 2023 | 2023-06-23 | 05/03/2023 | 47.6 | 0 | 2023-07-30 | 37
2022 | Region V | ALBAY | LEGAZPI CITY (CAPITAL) (ALBAY) | P00620687LZ | Construction of Flood Mitigation Structure | 123.7299 | 13.0956 | 47977981.86 | 47977926.84 | 2022 | HI-TONE CONSTRUCTION & DEVELOPMENT CORP. (FORMERLY | 7175 | 2022 | 2022-08-12 | 02/21/2022 | 55.02 | 0 | 2022-08-11 |  | 1
2022 | Region V | ALBAY | DARAGA (LOCSIN) (ALBAY) | P00640571LZ | Construction of Revetment | 123.7303 | 13.0916 | 34649920.75 | 34649568.31 | 2022 | MUNTOPAR BUILDERS CORP. | 7176 | 2022 | 2022-09-13 | 04/11/2022 | 352.44 | 0 | 2022-09-12 |  | 1
2024 | Region V | ALBAY | MALILIPOT (ALBAY) | P00820993LZ | Construction of Flood Mitigation Structure | 123.731 | 13.3225 | 87449970.17 | 39200000 | 2025 | CAJUGOTAN BUILDERS AND DEVELOPMENT CORP. (FOR: CAJUGOTAN CONSTRUCTION & SUPPLY) / JORMAND CONSTRUCTION & SUPPLY | 7177 | 2024 | 2025-02-07 | 06/24/2024 | 48249970.17 | 0 | 2025-02-06 |  | 1
2022 | Region V | ALBAY | CITY OF TABACO (ALBAY) | P00620310LZ | Construction of Flood Mitigation Structure | 123.731 | 13.3526 | 94569992.05 | 94570000 | 2022 | SANRHO BUILDERS, INC.(FOR. SANRHO CONST. AND SUPPL | 7178 | 2022 | 2022-12-23 | 03/09/2022 | 0 | 7.95 | 2022-12-22 |  | 1
2022 | Region V | ALBAY | LEGAZPI CITY (CAPITAL) (ALBAY) | P00620690LZ | Construction of Flood Mitigation Structure | 123.7313 | 13.1395 | 39198450.26 | 39197847.13 | 2022 | HKP CONSTRUCTION AND SUPPLY / STEVEN CONSTRUCTION & SUPPLY | 7179 | 2022 | 2022-08-02 | 02/21/2022 | 603.13 | 0 | 2022-08-01 |  | 1
2024 | Region V | ALBAY | MALILIPOT (ALBAY) | P00823643LZ | Construction of Flood Mitigation Structure | 123.7317 | 13.3219 | 87449970.17 | 48250000 | 2025 | CAJUGOTAN BUILDERS AND DEVELOPMENT CORP. (FOR: CAJUGOTAN CONSTRUCTION & SUPPLY) / JORMAND CONSTRUCTION & SUPPLY | 7180 | 2024 | 2025-02-07 | 06/24/2024 | 39199970.17 | 0 | 2025-02-06 |  | 1
2022 | Region V | ALBAY | CITY OF TABACO (ALBAY) | P00640568LZ | Rehabilitation / Major Repair of Flood Control Structure | 123.7319 | 13.3545 | 66329638.23 | 16830000 | 2022 | JORMAND CONSTRUCTION & SUPPLY | 7181 | 2022 | 2022-11-11 | 06/23/2022 | 49499638.23 | 0 | 2023-01-03 | 53
2023 | Region V | ALBAY | CITY OF TABACO (ALBAY) | P00727206LZ | Rehabilitation / Major Repair of Drainage Structure | 123.7328 | 13.3603 | 75459988.26 | 4900000 | 2023 | CAJUGOTAN BUILDERS AND DEVELOPMENT CORP. (FOR: CAJUGOTAN CONSTRUCTION & SUPPLY) / DSB CONSTRUCTION & SUPPLY, INC. (FORMERLY: DSB CO | 7182 | 2023 | 2023-11-06 | 05/15/2023 | 70559988.26 | 0 | 2023-12-09 | 33
2023 | Region V | MASBATE | SAN FERNANDO (MASBATE) | P00726296LZ | Construction of Flood Mitigation Structure | 123.7336 | 12.4653 | 23520000 | 23519995.67 | 2023 | JIMWELL BUILDERS AND SUPPLIES CORPORATION (FORMERLY:JIMWELL BUILDERS) | 7183 | 2023 | 2023-08-30 | 04/09/2023 | 4.33 | 0 | 2023-11-02 | 64
2021 | Region V | ALBAY |  | P00525675LZ | Construction of Flood Mitigation Structure | 123.7341 | 13.0742 | 289499999.7 | 144750000 | 2022 | MAKAPA CORPORATION | 7184 | 2021 | 2022-09-21 | 03/19/2021 | 144749999.7 | 0 | 2022-09-20 |  | 1
2024 | Region VII | CEBU | CITY OF NAGA (CEBU) | P00820354VS | Construction of Flood Mitigation Structure | 123.7343 | 10.2182 | 96500000 | 96450000 | 2024 | QM BUILDERS / JANUARY BUILDERS | 7185 | 2024 | 2024-05-10 | 02/20/2024 | 50000 | 0 | 2024-12-21 | 225
2023 | Region V | ALBAY | CITY OF TABACO (ALBAY) | P00737555LZ | Construction of Flood Mitigation Structure | 123.7345 | 13.3654 | 30689724.37 | 5940000 | 2023 | JORMAND CONSTRUCTION & SUPPLY | 7186 | 2023 | 2023-08-31 | 04/27/2023 | 24749724.37 | 0 | 2023-09-23 | 23
2023 | Region VII | CEBU | CITY OF NAGA (CEBU) | P00721819VS | Construction of Flood Mitigation Structure | 123.7353 | 10.2176 | 34300000 | 34290000 | 2023 | JANUARY BUILDERS | 7187 | 2023 | 2023-10-10 | 04/27/2023 | 10000 | 0 | 2023-11-09 | 30
2023 | Region V | ALBAY | MALILIPOT (ALBAY) | P00727204LZ | Construction of Flood Mitigation Structure | 123.7355 | 13.3214 | 75459988.26 | 20580000 | 2023 | CAJUGOTAN BUILDERS AND DEVELOPMENT CORP. (FOR: CAJUGOTAN CONSTRUCTION & SUPPLY) / DSB CONSTRUCTION & SUPPLY, INC. (FORMERLY: DSB CO | 7188 | 2023 | 2023-11-06 | 05/15/2023 | 54879988.26 | 0 | 2023-12-09 | 33
2023 | Region V | ALBAY | CITY OF TABACO (ALBAY) | P00726987LZ | Construction of Flood Mitigation Structure | 123.7362 | 13.3605 | 138149999.5 | 96500000 | 2024 | SANRHO BUILDERS, INC.(FOR. SANRHO CONST. AND SUPPL / 3RB CONSTRUCTION & SUPPLY | 7189 | 2023 | 2024-03-05 | 05/26/2023 | 41649999.5 | 0 | 2024-03-04 |  | 1
2022 | Region V | ALBAY | LEGAZPI CITY (CAPITAL) (ALBAY) | P00620307LZ | Construction of Flood Mitigation Structure | 123.7365 | 13.2169 | 48731844.78 | 47123519.5 | 2023 | MAKAPA CORPORATION | 7190 | 2022 | 2023-01-22 | 03/21/2022 | 1608325.28 | 0 | 2023-01-21 |  | 1
2023 | Region V | ALBAY | CITY OF TABACO (ALBAY) | P00727209LZ | Construction of Flood Mitigation Structure | 123.7365 | 13.3595 | 138149999.5 | 41650000 | 2024 | SANRHO BUILDERS, INC.(FOR. SANRHO CONST. AND SUPPL / 3RB CONSTRUCTION & SUPPLY | 7191 | 2023 | 2024-03-05 | 05/26/2023 | 96499999.5 | 0 | 2024-03-04 |  | 1
2024 | Region V | ALBAY | LEGAZPI CITY (CAPITAL) (ALBAY) | P00844787LZ | Construction of Slope Protection Structure | 123.7372 | 13.1827 | 48998954.51 | 48998722.69 | 2024 | A3 CONSTRUCTION & SUPPLY | 7192 | 2024 | 2024-10-10 | 03/25/2024 | 231.82 | 0 | 2024-10-09 |  | 1
2022 | Region V | ALBAY | CITY OF TABACO (ALBAY) | P00620677LZ | Construction of Flood Mitigation Structure | 123.7376 | 13.3537 | 19600195.19 | 19600000 | 2022 | SANRHO BUILDERS, INC.(FOR. SANRHO CONST. AND SUPPL | 7193 | 2022 | 2022-07-13 | 02/24/2022 | 195.19 | 0 | 2022-07-12 |  | 1
2022 | Region V | ALBAY | CITY OF TABACO (ALBAY) | P00620678LZ | Construction of Flood Mitigation Structure | 123.7377 | 13.3585 | 39199371.85 | 39200000 | 2022 | SANRHO BUILDERS, INC.(FOR. SANRHO CONST. AND SUPPL | 7194 | 2022 | 2022-08-02 | 02/24/2022 | 0 | 628.15 | 2022-08-01 |  | 1
2024 | Region V | ALBAY | LEGAZPI CITY (CAPITAL) (ALBAY) | P00844788LZ | Construction of Flood Mitigation Structure | 123.7378 | 13.1158 | 48998956.32 | 48998837.03 | 2024 | HI-TONE CONSTRUCTION & DEVELOPMENT CORP. (FORMERLY / KNJ CONSTRUCTION AND SUPPLY | 7195 | 2024 | 2024-09-20 | 03/25/2024 | 119.29 | 0 | 2024-09-19 |  | 1
2022 | Region V | ALBAY | CITY OF TABACO (ALBAY) | P00620303LZ | Construction of Flood Mitigation Structure | 123.738 | 13.3563 | 77199999.96 | 77200000 | 2023 | SANRHO BUILDERS, INC.(FOR. SANRHO CONST. AND SUPPL | 7196 | 2022 | 2023-01-03 | 03/09/2022 | 0 | 0.04 | 2023-01-02 |  | 1
2022 | Region V | ALBAY | RAPU-RAPU (ALBAY) | P00639391LZ | Construction of Flood Mitigation Structure | 123.738 | 13.3563 | 96494876.5 | 96494642.76 | 2023 | SUNWEST, INC. (FORMERLY: SUNWEST CONSTRUCTION & DEVELOPMENT CORPORATION) | 7197 | 2022 | 2023-04-12 | 06/20/2022 | 233.74 | 0 | 2023-04-11 |  | 1
2023 | Region V | ALBAY | CITY OF TABACO (ALBAY) | P00740497LZ | Construction of Flood Mitigation Structure | 123.7381 | 13.3527 | 96499772.26 | 96500000 | 2024 | MAKAPA CORPORATION / 8AR CONSTRUCTION AND DEVELOPMENT CORPORATION | 7198 | 2023 | 2024-04-16 | 08/18/2023 | 0 | 227.74 | 2024-04-15 |  | 1
2023 | Region V | ALBAY | LEGAZPI CITY (CAPITAL) (ALBAY) | P00740671LZ | Construction of Dike | 123.7383 | 13.1752 | 48928064.13 | 48927385.73 | 2023 | JEJAN CONSTRUCTION AND SUPPLY(FOR. JEJAN CONSTRUCT / TWINCARE BUILDERS INC. | 7199 | 2023 | 2023-12-15 | 06/19/2023 | 678.4 | 0 | 2023-12-18 | 3
2022 | Region V | ALBAY | MALILIPOT (ALBAY) | P00631334LZ | Rehabilitation / Major Repair of Flood Control Structure | 123.7384 | 13.2874 | 34299996.45 | 24500000 | 2022 | DSB CONSTRUCTION & SUPPLY, INC. (FORMERLY: DSB CO | 7200 | 2022 | 2022-09-30 | 05/30/2022 | 9799996.45 | 0 | 2022-10-31 | 31
2024 | Region V | MASBATE | SAN JACINTO (MASBATE) | P00820504LZ | Construction of Flood Mitigation Structure | 123.7389 | 12.5594 | 63156355 | 63156272.13 | 2025 | A3 CONSTRUCTION & SUPPLY / EJ CANTORIA CONSTRUCTION & SUPPLY | 7201 | 2024 | 2025-03-25 | 04/08/2024 | 82.87 | 0 | 2025-04-10 | 16
2022 | Region X | MISAMIS OCCIDENTAL | JIMENEZ (MISAMIS OCCIDENTAL) | P00631094MN | Construction of Flood Mitigation Structure | 123.7393 | 8.3258 | 4950000 | 4949866.03 | 2023 | RJLG CONSTRUCTION AND SUPPLIES | 7202 | 2022 | 2023-05-31 | 02/17/2022 | 133.97 | 0 | 2022-08-14 |  | 290
2022 | Region V | ALBAY | MALILIPOT (ALBAY) | P00631325LZ | Construction of Flood Mitigation Structure | 123.7393 | 13.2887 | 53899992.32 | 44100000 | 2023 | 3DIAMONDS CONSTRUCTION CORPORATION | 7203 | 2022 | 2023-01-29 | 08/05/2022 | 9799992.32 | 0 | 2023-01-28 |  | 1
2023 | Region V | ALBAY | CITY OF TABACO (ALBAY) | P00740495LZ | Construction of Flood Mitigation Structure | 123.7395 | 13.3503 | 96499997.35 | 96500000 | 2024 | 3RB CONSTRUCTION & SUPPLY | 7204 | 2023 | 2024-02-22 | 05/26/2023 | 0 | 2.65 | 2024-02-21 |  | 1
2023 | Region V | ALBAY | CITY OF TABACO (ALBAY) | P00727201LZ | Construction of Flood Mitigation Structure | 123.74 | 13.3425 | 75459988.26 | 29400000 | 2023 | CAJUGOTAN BUILDERS AND DEVELOPMENT CORP. (FOR: CAJUGOTAN CONSTRUCTION & SUPPLY) / DSB CONSTRUCTION & SUPPLY, INC. (FORMERLY: DSB CO | 7205 | 2023 | 2023-11-06 | 05/15/2023 | 46059988.26 | 0 | 2023-12-09 | 33
2022 | Region V | ALBAY | LEGAZPI CITY (CAPITAL) (ALBAY) | P00620685LZ | Construction of Flood Mitigation Structure | 123.74 | 13.0981 | 40218604.29 | 40192116.94 | 2022 | TWINCARE BUILDERS INC. / JCM AMEG BUILDERS CORPORATION (FORMERLY: AMEG CONSTRUCTION & SUPPLY) | 7206 | 2022 | 2022-08-08 | 02/21/2022 | 26487.35 | 0 | 2022-08-07 |  | 1
2023 | Region VII | CEBU | MADRIDEJOS (CEBU) | P00721545VS | Construction of Flood Mitigation Structure | 123.7404 | 11.299 | 96500000 | 96493655.55 | 2023 | WTG CONSTRUCTION & DEVELOPMENT CORPORATION / ROVILLA CONSTRUCTION | 7207 | 2023 | 2023-12-14 | 02/20/2023 | 6344.45 | 0 | 2023-12-24 | 10
2023 | Region V | ALBAY | CITY OF TABACO (ALBAY) | P00740496LZ | Construction of Flood Mitigation Structure | 123.7405 | 13.3412 | 96499998.97 | 96500000 | 2024 | DSB CONSTRUCTION & SUPPLY, INC. (FORMERLY: DSB CO | 7208 | 2023 | 2024-04-21 | 08/23/2023 | 0 | 1.03 | 2024-04-20 |  | 1
2023 | Region VII | CEBU | MANDAUE CITY (CEBU) | P00733264VS | Construction of Flood Mitigation Structure | 123.9472 | 10.3421 | 96500000 | 96398888 | 2023 | QUIRANTE CONSTRUCTION CORPORATION (FORMERLY: QUIRANTE CONSTRUCTION) | 7209 | 2023 | 2023-11-29 | 05/12/2023 | 101112 | 0 | 2024-04-11 | 134
2024 | Region VII | CEBU | ARGAO (CEBU) | P00820066VS | Construction of Flood Mitigation Structure | 123.6072 | 9.8872 | 64655000 | 64575000 | 2024 | GICAR CONSTRUCTION, INC. | 7210 | 2024 | 2024-12-30 | 03/19/2024 | 80000 | 0 | 2024-12-29 |  | 1
2022 | Region V | SORSOGON | CASTILLA (SORSOGON) | P00640591LZ | Construction of Flood Mitigation Structure | 123.878 | 12.936 | 49499987.41 | 19799984.31 | 2023 | ALNINO CONSTRUCTION & SUPPLY CORPORATION (FORMERLY: AL NINO CONSTRUCTION & SUPPLY) | 7211 | 2022 | 2023-05-05 | 04/04/2022 | 29700003.1 | 0 | 2023-05-06 | 1
2024 | Region VII | CEBU | SOGOD (CEBU) | P00821056VS | Construction of Flood Mitigation Structure | 124.006 | 10.7285 | 49000000 | 48964040.18 | 2024 | VSP STRUCTURE VENTURES CORP. (FORMERLY: VIRLO CONSTRUCTION) | 7212 | 2024 | 2024-10-10 | 03/15/2024 | 35959.82 | 0 | 2024-10-09 |  | 1
2024 | Region VII | CEBU | CATMON (CEBU) | P00820055VS | Construction of Flood Mitigation Structure | 124.0084 | 10.7184 | 72375000 | 72367100.6 | 2024 | VSP STRUCTURE VENTURES CORP. (FORMERLY: VIRLO CONSTRUCTION) | 7213 | 2024 | 2024-11-11 | 02/16/2024 | 7899.4 | 0 | 2024-11-10 |  | 1
2022 | Region V | SORSOGON | CASTILLA (SORSOGON) | P00620759LZ | Construction of Flood Mitigation Structure | 123.8014 | 12.9772 | 39199979.11 | 37586374.39 | 2022 | CENTERWAYS CONSTRUCTION AND DEVELOPMENT INC. | 7214 | 2022 | 2022-10-12 | 03/11/2022 | 1613604.72 | 0 | 2022-10-11 |  | 1
2023 | Region V | SORSOGON | CITY OF SORSOGON (CAPITAL) (SORSOGON) | P00742193LZ | Construction of Flood Mitigation Structure | 123.9476 | 13.1065 | 69299990.63 | 69206320.09 | 2024 | ALPHA RYDER CONSTRUCTION & SUPPLIES | 7215 | 2023 | 2024-01-24 | 04/19/2023 | 93670.54 | 0 | 2024-01-22 |  | 2
2022 | Region V | SORSOGON | IROSIN (SORSOGON) | P00620321LZ | Construction of Flood Mitigation Structure | 124.0091 | 12.7106 | 174378350.7 | 174378350.7 | 2023 | MAKAPA CORPORATION | 7216 | 2022 | 2023-05-31 | 05/12/2022 | 0 | 0 | 2023-06-04 | 4
2022 | Region VII | CEBU | DUMANJUG (CEBU) | P00633231VS | Construction of Revetment | 123.4933 | 10.0533 | 48508289.02 | 48508289.02 | 2022 | QM BUILDERS | 7217 | 2022 | 2022-10-25 | 03/23/2022 | 0 | 0 | 2022-10-24 |  | 1
2023 | Region V | SORSOGON | BULAN (SORSOGON) | P00725895LZ | Construction of Flood Mitigation Structure | 123.8783 | 12.6715 | 96500000 | 96500000 | 2024 | HI-TONE CONSTRUCTION & DEVELOPMENT CORP. (FORMERLY | 7218 | 2023 | 2024-08-18 | 06/08/2023 | 0 | 0 | 2024-08-17 |  | 1
2022 | Region V | ALBAY | GUINOBATAN (ALBAY) | P00640475LZ | Construction of Revetment | 123.612 | 13.1889 | 99000000 | 98999988.18 | 2023 | CENTERWAYS CONSTRUCTION AND DEVELOPMENT INC. / FS CO BUILDERS AND SUPPLY | 7219 | 2022 | 2023-06-20 | 06/13/2022 | 11.82 | 0 | 2023-06-19 |  | 1
2024 | Region VII | CEBU | MINGLANILLA (CEBU) | P00835007VS | Construction of Drainage Structure | 123.8032 | 10.2493 | 4950000 | 4940000 | 2024 | CARCEL CONSTRUCTION AND DEVELOPMENT CORPORATION | 7220 | 2024 | 2024-10-25 | 04/29/2024 | 10000 | 0 | 2024-10-24 |  | 1
2023 | Region VII | CEBU | MANDAUE CITY (CEBU) | P00721831VS | Construction of Flood Mitigation Structure | 123.9485 | 10.3413 | 39200000 | 39150000 | 2023 | ON POINT CONSTRUCTION AND DEVELOPMENT CORPORATION (FORMERLY:ON POINT CONSTRUCTION) | 7221 | 2023 | 2023-10-05 | 05/11/2023 | 50000 | 0 | 2023-12-26 | 82
2022 | Region V | ALBAY | POLANGUI (ALBAY) | P00640473LZ | Construction of Flood Mitigation Structure | 123.494 | 13.27 | 99000000 | 96029543.42 | 2023 | CENTERWAYS CONSTRUCTION AND DEVELOPMENT INC. / FS CO BUILDERS AND SUPPLY | 7222 | 2022 | 2023-06-17 | 07/11/2022 | 2970456.58 | 0 | 2023-06-16 |  | 1
2021 | Region V | MASBATE |  | P00525701LZ | Construction of Flood Mitigation Structure | 123.6122 | 12.6439 | 53075000 | 50425248.21 | 2022 | HI-TONE CONSTRUCTION & DEVELOPMENT CORP. (FORMERLY / L BROS CONSTRUCTION AND SUPPLY INC (FORMERLY: L BROS. CONSTRUCTION & SUPPLY) | 7223 | 2021 | 2022-11-29 | 11/23/2021 | 2649751.79 | 0 | 2022-07-24 |  | 128
2024 | Region VII | CEBU | CATMON (CEBU) | P00820057VS | Construction of Flood Mitigation Structure | 124.011 | 10.6451 | 72375000 | 71630987.97 | 2024 | QUIRANTE CONSTRUCTION CORPORATION (FORMERLY: QUIRANTE CONSTRUCTION) | 7224 | 2024 | 2024-11-11 | 02/16/2024 | 744012.03 | 0 | 2024-11-10 |  | 1
2022 | Region V | SORSOGON | CASTILLA (SORSOGON) | P00640595LZ | Construction of Flood Mitigation Structure | 123.8785 | 12.947 | 49499989.68 | 19799962.19 | 2023 | ALNINO CONSTRUCTION & SUPPLY CORPORATION (FORMERLY: AL NINO CONSTRUCTION & SUPPLY) | 7225 | 2022 | 2023-02-24 | 04/04/2022 | 29700027.49 | 0 | 2023-02-24 | 0
2024 | Region X | LANAO DEL NORTE | TUBOD (CAPITAL) (LANAO DEL NORTE) | P00821087MN | Construction of Flood Mitigation Structure | 123.8053 | 8.0498 | 49000000 | 49000000 | 2024 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R | 7226 | 2024 | 2024-09-24 | 01/23/2024 | 0 | 0 | 2024-12-02 | 69
2022 | Region V | CAMARINES SUR | GOA (CAMARINES SUR) | P00620315LZ | Construction of Flood Mitigation Structure | 123.4954 | 13.6814 | 78168860 | 78168860 | 2023 | PARTIDO CONSTRUCTION & SUPPLY | 7227 | 2022 | 2023-04-13 | 04/05/2022 | 0 | 0 | 2023-04-13 | 0
2023 | Region V | SORSOGON | CITY OF SORSOGON (CAPITAL) (SORSOGON) | P00742484LZ | Construction of Flood Mitigation Structure | 123.9487 | 13.1055 | 49499985.92 | 49493043.02 | 2023 | ALPHA RYDER CONSTRUCTION & SUPPLIES | 7228 | 2023 | 2023-11-17 | 03/27/2023 | 6942.9 | 0 | 2023-11-18 | 1
2022 | Region V | ALBAY | GUINOBATAN (ALBAY) | P00631381LZ | Rehabilitation / Major Repair of Flood Control Structure | 123.6148 | 13.1941 | 97100000 | 39199999.71 | 2023 | 3DIAMONDS CONSTRUCTION CORPORATION | 7229 | 2022 | 2023-07-15 | 04/07/2022 | 57900000.29 | 0 | 2023-07-14 |  | 1
2023 | Region V | SORSOGON | CITY OF SORSOGON (CAPITAL) (SORSOGON) | P00725896LZ | Construction of Drainage Structure | 124.0113 | 12.9757 | 96499986.55 | 96499897.52 | 2024 | CENTERWAYS CONSTRUCTION AND DEVELOPMENT INC. / CHEEREL CONSTRUCTION & SUPPLY | 7230 | 2023 | 2024-06-25 | 08/31/2023 | 89.03 | 0 | 2024-06-24 |  | 1
2023 | Region V | MASBATE | DIMASALANG (MASBATE) | P00726304LZ | Construction of Flood Mitigation Structure | 123.8786 | 12.1762 | 39000160.77 | 38786902.99 | 2023 | NEXT GENERATION CONSTRUCTION AND SUPPLY CORPORATION | 7231 | 2023 | 2023-09-25 | 05/12/2023 | 213257.78 | 0 | 2024-01-12 | 109
2024 | Region X | MISAMIS OCCIDENTAL | SINACABAN (MISAMIS OCCIDENTAL) | P00835870MN | Construction of Drainage Structure | 123.8054 | 8.3087 | 4900000 | 4752999.57 | 2024 | WEISENWORK CONSTRUCTION | 7232 | 2024 | 2024-11-25 | 06/20/2024 | 147000.43 | 0 | 2024-11-24 |  | 1
2023 | Region V | ALBAY | CITY OF TABACO (ALBAY) | P00740499LZ | Construction of Flood Mitigation Structure | 123.7406 | 13.3393 | 118739934.6 | 96500000 | 2024 | DSB CONSTRUCTION & SUPPLY, INC. (FORMERLY: DSB CO | 7233 | 2023 | 2024-03-06 | 05/15/2023 | 22239934.6 | 0 | 2024-03-05 |  | 1
2023 | Region VII | CEBU | CEBU CITY (CAPITAL) (CEBU) | P00732026VS | Construction of Flood Mitigation Structure | 123.8791 | 10.3062 | 4950000 | 4938694.26 | 2024 | BELCONSTRUCT CORPORATION | 7234 | 2023 | 2024-02-17 | 10/17/2023 | 11305.74 | 0 | 2024-02-16 |  | 1
2022 | Region VII | CEBU |  | P00633228VS | Rehabilitation / Major Repair of Drainage Structure | 123.9491 | 10.3328 | 4950000 | 4939949.55 | 2022 | PLD CONSTRUCTION AND DEVELOPMENT INC. (FORMERLY: PLD CONSTRUCTION) | 7235 | 2022 | 2022-07-08 | 03/30/2022 | 10050.45 | 0 | 2022-07-07 |  | 1
2023 | Region V | SORSOGON | IROSIN (SORSOGON) | P00725905LZ | Rehabilitation / Major Repair of Flood Control Structure | 124.014 | 12.7535 | 115800000 | 115793368.5 | 2024 | HI-TONE CONSTRUCTION & DEVELOPMENT CORP. (FORMERLY / CENTERWAYS CONSTRUCTION AND DEVELOPMENT INC. | 7236 | 2023 | 2024-05-17 | 06/08/2023 | 6631.5 | 0 | 2024-05-16 |  | 1
2024 | Region V | ALBAY | TIWI (ALBAY) | P00823641LZ | Construction of Flood Mitigation Structure | 123.6161 | 13.4973 | 62724192.45 | 62725000 | 2024 | 8AR CONSTRUCTION AND DEVELOPMENT CORPORATION | 7237 | 2024 | 2024-11-11 | 04/19/2024 | 0 | 807.55 | 2024-11-10 |  | 1
2022 | Region VII | CEBU | TUBURAN (CEBU) | P00630226VS | Construction of Flood Mitigation Structure | 123.8058 | 10.7214 | 24500000 | 24364998.06 | 2023 | DINAH RBS CONSTRUCTION AND SUPPLY INCORPORATED (FORMERLY: DINAH JANE CONSTRUCTION AND SUPPLY) / JUGA BUILDERS & CONSTRUCTION SUPPLY | 7238 | 2022 | 2023-01-01 | 07/01/2022 | 135001.94 | 0 | 2022-12-31 |  | 1
2022 | Region V | SORSOGON | BULAN (SORSOGON) | P00630973LZ | Construction of Flood Mitigation Structure | 123.8792 | 12.673 | 67549794.35 | 67549794.35 | 2023 | CENTERWAYS CONSTRUCTION AND DEVELOPMENT INC. | 7239 | 2022 | 2023-05-21 | 04/08/2022 | 0 | 0 | 2023-05-20 |  | 1
2022 | Region V | CAMARINES SUR | GOA (CAMARINES SUR) | P00620284LZ | Construction of Flood Mitigation Structure | 123.4954 | 13.7023 | 91648653.09 | 91648653.09 | 2023 | BICOL GOLDROCK CONSTRUCTION CORPORATION | 7240 | 2022 | 2023-04-16 | 03/24/2022 | 0 | 0 | 2023-04-15 |  | 1
2023 | Region X | MISAMIS OCCIDENTAL | TANGUB CITY (MISAMIS OCCIDENTAL) | P00721379MN | Construction of Slope Protection Structure | 123.7407 | 8.0762 | 49000000 | 47530000 | 2024 | MINDANAO ROCK | 7241 | 2023 | 2024-12-22 | 02/10/2023 | 1470000 | 0 | 2023-07-28 |  | 513
2022 | Region VII | CEBU | SAN REMIGIO (CEBU) | P00620118VS | Construction of Flood Mitigation Structure | 123.9492 | 10.9035 | 49000000 | 49000000 | 2022 | DINAH RBS CONSTRUCTION AND SUPPLY INCORPORATED (FORMERLY: DINAH JANE CONSTRUCTION AND SUPPLY) | 7242 | 2022 | 2022-10-30 | 02/18/2022 | 0 | 0 | 2022-10-29 |  | 1
2022 | Region V | SORSOGON | IROSIN (SORSOGON) | P00631479LZ | Rehabilitation / Major Repair of Flood Control Structure | 124.0156 | 12.7044 | 39200000 | 37621089.23 | 2022 | CENTERWAYS CONSTRUCTION AND DEVELOPMENT INC. | 7243 | 2022 | 2022-12-26 | 03/15/2022 | 1578910.77 | 0 | 2023-01-22 | 27
2023 | Region VII | CEBU | SIBONGA (CEBU) | P00721670VS | Construction of Drainage Structure | 123.6164 | 10.0164 | 4900000 | 4850000 | 2023 | 647 CONSTRUCTION AND DEVELOPMENT CORPORATION | 7244 | 2023 | 2023-05-29 | 02/15/2023 | 50000 | 0 | 2023-05-27 |  | 2
2023 | Region V | MASBATE | USON (MASBATE) | P00727225LZ | Construction of Flood Mitigation Structure | 123.8059 | 12.1897 | 31171010.57 | 31162943.24 | 2023 | RED DIAMOND CONSTRUCTION AND SUPPLY CORPORATION (FORMERLY: RED DIAMOND CONSTRUCTION) | 7245 | 2023 | 2023-09-11 | 04/18/2023 | 8067.33 | 0 | 2023-12-05 | 85
2024 | Region V | CAMARINES SUR | TIGAON (CAMARINES SUR) | P00844790LZ | Construction of Flood Mitigation Structure | 123.4958 | 13.6357 | 49000000 | 49000000 | 2024 | ALRO CONSTRUCTION & DEVELOPMENT CORP. | 7246 | 2024 | 2024-12-06 | 02/27/2024 | 0 | 0 | 2024-12-05 |  | 1
2022 | Region V | ALBAY | LEGAZPI CITY (CAPITAL) (ALBAY) | P00639543LZ | Construction of Flood Mitigation Structure | 123.7408 | 13.1122 | 48999805.42 | 48999560.94 | 2022 | WELEX CONSTRUCTION, INCORPORATED (FORMERLY WELEX C | 7247 | 2022 | 2022-09-15 | 04/11/2022 | 244.48 | 0 | 2022-09-30 | 15
2023 | Region VII | CEBU | CONSOLACION (CEBU) | P00721978VS | Construction of Flood Mitigation Structure | 123.9508 | 10.4021 | 96500000 | 96500000 | 2023 | QUIRANTE CONSTRUCTION CORPORATION (FORMERLY: QUIRANTE CONSTRUCTION) / ZLREJ TRADING AND CONSTRUCTION CORPORATION | 7248 | 2023 | 2023-11-28 | 03/21/2023 | 0 | 0 | 2023-12-02 | 4
2023 | Region V | MASBATE | DIMASALANG (MASBATE) | P00727224LZ | Construction of Flood Mitigation Structure | 123.8796 | 12.1764 | 37208477.29 | 37198373.92 | 2024 | GACT ENTERPRISES | 7249 | 2023 | 2024-02-06 | 06/09/2023 | 10103.37 | 0 | 2024-02-05 |  | 1
2022 | Region X | LANAO DEL NORTE | TUBOD (CAPITAL) (LANAO DEL NORTE) | P00620037MN | Construction of Flood Mitigation Structure | 123.8066 | 8.0545 | 96500000 | 93088514.16 | 2023 | KOUZBARY BUILDERS / LANAO BUILDER AND ENTERPRISES | 7250 | 2022 | 2023-11-06 | 03/25/2022 | 3411485.84 | 0 | 2023-01-17 |  | 293
2022 | Region V | SORSOGON | DONSOL (SORSOGON) | P00640593LZ | Construction of Flood Mitigation Structure | 123.6173 | 12.9815 | 49499987.41 | 4949981.04 | 2023 | ALNINO CONSTRUCTION & SUPPLY CORPORATION (FORMERLY: AL NINO CONSTRUCTION & SUPPLY) | 7251 | 2022 | 2023-05-05 | 04/04/2022 | 44550006.37 | 0 | 2023-05-06 | 1
2023 | Region V | MASBATE | BALENO (MASBATE) | P00725888LZ | Construction of Flood Mitigation Structure | 123.4959 | 12.4569 | 51144977.9 | 51145000 | 2023 | SPRING STAR CONSTRUCTION AND SUPPLY | 7252 | 2023 | 2023-07-28 | 04/05/2023 | 0 | 22.1 | 2023-11-17 | 112
2021 | Region V | SORSOGON |  | P00526343LZ | Construction of Flood Mitigation Structure | 124.0158 | 12.7043 | 289499939.2 | 144750000 | 2022 | MAKAPA CORPORATION | 7253 | 2021 | 2022-10-06 | 05/24/2021 | 144749939.2 | 0 | 2022-10-05 |  | 1
2022 | Region V | ALBAY | RAPU-RAPU (ALBAY) | P00632700LZ | Rehabilitation / Major Repair of Flood Control Structure | 123.7411 | 13.3355 | 69294868.52 | 69294242.44 | 2022 | HI-TONE CONSTRUCTION & DEVELOPMENT CORP. (FORMERLY | 7254 | 2022 | 2022-10-26 | 03/16/2022 | 626.08 | 0 | 2022-10-25 |  | 1
2023 | Region VII | CEBU | CONSOLACION (CEBU) | P00722001VS | Construction of Flood Mitigation Structure | 123.951 | 10.4018 | 8073240 | 8067898.81 | 2023 | NEOVENTURES CONSTRUCTION | 7255 | 2023 | 2023-06-27 | 03/08/2023 | 5341.19 | 0 | 2023-06-30 | 3
2022 | Region V | MASBATE | USON (MASBATE) | P00620750LZ | Construction of Revetment | 123.8067 | 12.1895 | 35279548.2 | 35260510.32 | 2022 | SPRING STAR CONSTRUCTION AND SUPPLY | 7256 | 2022 | 2022-09-12 | 02/16/2022 | 19037.88 | 0 | 2022-10-12 | 30
2024 | Region V | ALBAY | TIWI (ALBAY) | P00820991LZ | Construction of Flood Mitigation Structure | 123.6189 | 13.4918 | 39199999.48 | 39200000 | 2024 | JORMAND CONSTRUCTION & SUPPLY | 7257 | 2024 | 2024-07-21 | 02/13/2024 | 0 | 0.52 | 2024-07-20 |  | 1
2021 | Region V | MASBATE |  | P00561437LZ | Construction of Flood Mitigation Structure | 123.4961 | 12.4567 | 9899940.55 | 9900000 | 2022 | EBARAM GENERAL CONSTRUCTION & SUPPLY | 7258 | 2021 | 2022-12-30 | 10/19/2022 | 0 | 59.45 | 2023-01-23 | 24
2022 | Region VII | CEBU | CATMON (CEBU) | P00620028VS | Construction of Flood Mitigation Structure | 124.0163 | 10.6462 | 86850000 | 86774888 | 2022 | QUIRANTE CONSTRUCTION CORPORATION (FORMERLY: QUIRANTE CONSTRUCTION) | 7259 | 2022 | 2022-12-01 | 03/07/2022 | 75112 | 0 | 2022-11-30 |  | 1
2024 | Region V | ALBAY | CITY OF TABACO (ALBAY) | P00823649LZ | Construction of Flood Mitigation Structure | 123.7411 | 13.3336 | 104219999.5 | 104220000 | 2025 | SANRHO BUILDERS, INC.(FOR. SANRHO CONST. AND SUPPL | 7260 | 2024 | 2025-02-26 | 04/17/2024 | 0 | 0.5 | 2024-12-17 |  | 71
2023 | Region VII | CEBU | SIBONGA (CEBU) | P00721542VS | Construction of Flood Mitigation Structure | 123.6201 | 10.0086 | 53075000 | 53060000 | 2023 | JANUARY BUILDERS | 7261 | 2023 | 2023-09-19 | 03/06/2023 | 15000 | 0 | 2023-10-16 | 27
2023 | Region V | SORSOGON | CITY OF SORSOGON (CAPITAL) (SORSOGON) | P00726321LZ | Construction of Flood Mitigation Structure | 123.9526 | 12.968 | 39199987.79 | 38006678.27 | 2023 | STEVEN CONSTRUCTION & SUPPLY | 7262 | 2023 | 2023-09-18 | 02/22/2023 | 1193309.52 | 0 | 2023-09-17 |  | 1
2022 | Region VII | CEBU | TABUELAN (CEBU) | P00620117VS | Construction of Flood Mitigation Structure | 123.8804 | 10.8233 | 49000000 | 49000000 | 2022 | WTG CONSTRUCTION & DEVELOPMENT CORPORATION | 7263 | 2022 | 2022-09-12 | 02/18/2022 | 0 | 0 | 2022-09-11 |  | 1
2023 | Region V | MASBATE | USON (MASBATE) | P00726309LZ | Construction of Flood Mitigation Structure | 123.807 | 12.189 | 29794664.26 | 29786118.31 | 2023 | EJ CANTORIA CONSTRUCTION & SUPPLY | 7264 | 2023 | 2023-09-25 | 04/18/2023 | 8545.95 | 0 | 2023-12-03 | 69
2022 | Region V | SORSOGON | BULAN (SORSOGON) | P00631480LZ | Rehabilitation / Major Repair of Flood Control Structure | 123.8807 | 12.6806 | 43424539.68 | 43424539.68 | 2023 | CENTERWAYS CONSTRUCTION AND DEVELOPMENT INC. | 7265 | 2022 | 2023-04-13 | 04/08/2022 | 0 | 0 | 2023-04-12 |  | 1
2023 | Region V | CAMARINES SUR | TINAMBAC (CAMARINES SUR) | P00726985LZ | Construction of Flood Mitigation Structure | 123.4965 | 13.6801 | 93123700 | 93123700 | 2023 | PARTIDO CONSTRUCTION & SUPPLY | 7266 | 2023 | 2023-12-18 | 03/30/2023 | 0 | 0 | 2024-02-27 | 71
2022 | Region VII | BOHOL | CLARIN (BOHOL) | P00630216VS | Construction of Flood Mitigation Structure | 124.018 | 9.9647 | 19600000 | 13900320 | 2022 | SLP CONSTRUCTION | 7267 | 2022 | 2022-12-25 | 02/08/2022 | 5699680 | 0 | 2022-09-09 |  | 107
2022 | Region V | ALBAY | LEGAZPI CITY (CAPITAL) (ALBAY) | P00639542LZ | Construction of Flood Mitigation Structure | 123.7424 | 13.1896 | 19599998.21 | 19597880.84 | 2022 | RAPIDWORKZ CONSTRUCTION & SUPPLY | 7268 | 2022 | 2022-09-04 | 04/11/2022 | 2117.37 | 0 | 2022-09-01 |  | 3
2021 | Region V | ALBAY |  | P00525691LZ | Construction of Flood Mitigation Structure | 123.6205 | 13.4914 | 120624912.8 | 120624912.8 | 2022 | WEARR ENTERPRISES & DEVELOPMENT CORP. | 7269 | 2021 | 2022-12-08 | 02/15/2022 | 0 | 0 | 2022-12-07 |  | 1
2023 | Region X | LANAO DEL NORTE | MAIGO (LANAO DEL NORTE) | P00721252MN | Construction of Flood Mitigation Structure | 123.9527 | 8.1592 | 53075000 | 53075000 | 2023 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R | 7270 | 2023 | 2023-10-24 | 03/17/2023 | 0 | 0 | 2024-01-04 | 72
2024 | Region V | ALBAY | GUINOBATAN (ALBAY) | P00820491LZ | Construction of Flood Mitigation Structure | 123.6221 | 13.2154 | 102290000 | 102290000 | 2024 | WCS CONSTRUCTION, INC. | 7271 | 2024 | 2024-09-30 | 03/25/2024 | 0 | 0 | 2025-01-02 | 94
2022 | Region X | LANAO DEL NORTE | TUBOD (CAPITAL) (LANAO DEL NORTE) | P00620038MN | Construction of Flood Mitigation Structure | 123.8074 | 8.0559 | 144750000 | 139725176.6 | 2023 | KOUZBARY BUILDERS / LANAO BUILDER AND ENTERPRISES | 7272 | 2022 | 2023-10-03 | 03/25/2022 | 5024823.4 | 0 | 2023-10-02 |  | 1
2024 | Region V | SORSOGON | MATNOG (SORSOGON) | P00839678LZ | Construction of Flood Mitigation Structure | 124.0185 | 12.6397 | 9900000 | 4850574.82 | 2024 | GDBS BUILDERS AND ENTERPRISE | 7273 | 2024 | 2024-04-25 | 02/16/2024 | 5049425.18 | 0 | 2024-04-24 |  | 1
2024 | Region V | CAMARINES SUR | BUHI (CAMARINES SUR) | P00820498LZ | Construction of Flood Mitigation Structure | 123.4975 | 13.422 | 139925000 | 139925000 | 2024 | SUNWEST, INC. (FORMERLY: SUNWEST CONSTRUCTION & DEVELOPMENT CORPORATION) | 7274 | 2024 | 2024-12-16 | 02/21/2024 | 0 | 0 | 2025-03-07 | 81
2021 | Region V | ALBAY |  | P00526197LZ | Construction of Flood Mitigation Structure | 123.743 | 13.1523 | 34298406.91 | 34298212.71 | 2022 | NUMERICAL GATE CONSTRUCTION & SUPPLY CORPORATION | 7275 | 2021 | 2022-08-04 | 03/02/2022 | 194.2 | 0 | 2022-08-03 |  | 1
2024 | Region VII | CEBU | MANDAUE CITY (CEBU) | P00834650VS | Construction of Flood Mitigation Structure | 123.9531 | 10.3306 | 9800000 | 9774508.23 | 2024 | A.S.T BUILDERS | 7276 | 2024 | 2024-07-01 | 02/23/2024 | 25491.77 | 0 | 2024-07-01 | 0
2021 | Region V | MASBATE |  | P00525702LZ | Construction of Flood Mitigation Structure | 123.6224 | 12.569 | 53075000 | 51456790.87 | 2022 | CENTERWAYS CONSTRUCTION AND DEVELOPMENT INC. | 7277 | 2021 | 2022-11-29 | 11/23/2021 | 1618209.13 | 0 | 2022-07-24 |  | 128
2023 | Region VII | CEBU | CEBU CITY (CAPITAL) (CEBU) | P00732023VS | Construction of Flood Mitigation Structure | 123.8813 | 10.3322 | 4950000 | 4940079.39 | 2023 | BELCONSTRUCT CORPORATION | 7278 | 2023 | 2023-12-24 | 08/23/2023 | 9920.61 | 0 | 2023-12-23 |  | 1
2023 | Region VII | CEBU | TUBURAN (CEBU) | P00721825VS | Construction of Flood Mitigation Structure | 123.8083 | 10.6854 | 44100000 | 44015442.55 | 2023 | VEN RAY CONSTRUCTION CORPORATION | 7279 | 2023 | 2023-08-30 | 02/02/2023 | 84557.45 | 0 | 2023-08-29 |  | 1
2023 | Region VII | BOHOL | CLARIN (BOHOL) | P00721664VS | Construction of Flood Mitigation Structure | 124.0186 | 9.9645 | 49000000 | 48999862.87 | 2023 | SLP CONSTRUCTION / YS CONSTRUCTION | 7280 | 2023 | 2023-12-27 | 02/21/2023 | 137.13 | 0 | 2023-12-26 |  | 1
2022 | Region V | MASBATE | SAN JACINTO (MASBATE) | P00640479LZ | Rehabilitation / Major Repair of Flood Control Structure | 123.7431 | 12.5283 | 98999139.6 | 98999139.6 | 2023 | CENTERWAYS CONSTRUCTION AND DEVELOPMENT INC. | 7281 | 2022 | 2023-09-01 | 08/11/2022 | 0 | 0 | 2023-08-31 |  | 1
2023 | Region V | CAMARINES SUR | BUHI (CAMARINES SUR) | P00740492LZ | Construction of Flood Mitigation Structure | 123.4985 | 13.4241 | 81911222 | 81909707.57 | 2024 | HI-TONE CONSTRUCTION & DEVELOPMENT CORP. (FORMERLY | 7282 | 2023 | 2024-03-04 | 04/11/2023 | 1514.43 | 0 | 2024-03-03 |  | 1
2023 | Region X | MISAMIS OCCIDENTAL | TANGUB CITY (MISAMIS OCCIDENTAL) | P00721381MN | Construction of Slope Protection Structure | 123.7434 | 8.0616 | 49000000 | 47530000 | 2023 | MINDANAO ROCK | 7283 | 2023 | 2023-10-30 | 02/24/2023 | 1470000 | 0 | 2023-08-08 |  | 83
2023 | Region V | SORSOGON | MAGALLANES (SORSOGON) | P00742489LZ | Construction of Flood Mitigation Structure | 123.8817 | 12.8411 | 98999982.07 | 49499987.99 | 2024 | STEVEN CONSTRUCTION & SUPPLY | 7284 | 2023 | 2024-02-21 | 04/12/2023 | 49499994.08 | 0 | 2024-02-20 |  | 1
2023 | Region VII | CEBU | CONSOLACION (CEBU) | P00721540VS | Construction of Flood Mitigation Structure | 123.9531 | 10.3702 | 86850000 | 86789658.38 | 2023 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R / XLA CONSTRUCTION | 7285 | 2023 | 2023-10-06 | 02/13/2023 | 60341.62 | 0 | 2023-10-05 |  | 1
2024 | Region VII | CEBU | CITY OF CARCAR (CEBU) | P00820356VS | Construction of Flood Mitigation Structure | 123.631 | 10.0681 | 120625000 | 120625000 | 2025 | QM BUILDERS / AR ADLAWAN CONSTRUCTION | 7286 | 2024 | 2025-01-03 | 02/22/2024 | 0 | 0 | 2025-01-02 |  | 1
2022 | Region VII | CEBU | TUBURAN (CEBU) | P00634053VS | Construction of Flood Mitigation Structure | 123.8088 | 10.7198 | 48618400 | 48049193.6 | 2023 | VEN RAY CONSTRUCTION CORPORATION | 7287 | 2022 | 2023-01-24 | 05/24/2022 | 569206.4 | 0 | 2022-12-25 |  | 30
2022 | Region V | SORSOGON | IROSIN (SORSOGON) | P00631473LZ | Construction of Flood Mitigation Structure | 124.0203 | 12.732 | 58800000 | 28518000 | 2022 | MUNTOPAR BUILDERS CORP. | 7288 | 2022 | 2022-10-13 | 02/15/2022 | 30282000 | 0 | 2022-10-12 |  | 1
2022 | Region V | CAMARINES SUR | LAGONOY (CAMARINES SUR) | P00632969LZ | Construction of Flood Mitigation Structure | 123.4988 | 13.6321 | 10395000 | 10395000 | 2022 | JO20 CONSTRUCTION AND SUPPLY | 7289 | 2022 | 2022-08-01 | 03/17/2022 | 0 | 0 | 2022-07-31 |  | 1
2023 | Region V | ALBAY | LEGAZPI CITY (CAPITAL) (ALBAY) | P00740444LZ | Construction of Dike | 123.7439 | 13.1341 | 72272653.25 | 72271706.58 | 2023 | JEJAN CONSTRUCTION AND SUPPLY(FOR. JEJAN CONSTRUCT / STEVEN CONSTRUCTION & SUPPLY | 7290 | 2023 | 2023-10-31 | 04/19/2023 | 946.67 | 0 | 2023-10-31 | 0
2023 | Region VII | CEBU | MANDAUE CITY (CEBU) | P00721900VS | Construction of Flood Mitigation Structure | 123.9531 | 10.3702 | 57900000 | 57789620.79 | 2023 | PHIL ASIA RESOURCES & DEVELOPMENT CORP. / WTG CONSTRUCTION & DEVELOPMENT CORPORATION | 7291 | 2023 | 2023-11-10 | 05/11/2023 | 110379.21 | 0 | 2023-11-30 | 20
2022 | Region VII | CEBU | TUBURAN (CEBU) | P00620126VS | Construction of Slope Protection Structure | 123.8092 | 10.7213 | 49000000 | 48941933.27 | 2023 | VEN RAY CONSTRUCTION CORPORATION | 7292 | 2022 | 2023-09-01 | 10/11/2022 | 58066.73 | 0 | 2023-07-13 |  | 50
2022 | Region V | SORSOGON | IROSIN (SORSOGON) | P00631475LZ | Construction of Revetment | 124.021 | 12.6956 | 49000000 | 48999998.36 | 2023 | CENTERWAYS CONSTRUCTION AND DEVELOPMENT INC. | 7293 | 2022 | 2023-04-01 | 04/12/2022 | 1.64 | 0 | 2023-03-31 |  | 1
2023 | Region V | ALBAY | CAMALIG (ALBAY) | P00737381LZ | Construction of Dike | 123.6327 | 13.1701 | 67548539.34 | 67548527.29 | 2023 | AJAN JEADA, INC. (FORMERLY: JEADA CONSTRUCTION) | 7294 | 2023 | 2023-09-14 | 02/27/2023 | 12.05 | 0 | 2023-09-13 |  | 1
2022 | Region V | ALBAY | CAMALIG (ALBAY) | P00631345LZ | Construction of Dike | 123.6343 | 13.2017 | 48998323.83 | 48997990.88 | 2022 | SISBRO CONSTRUCTION CORPORATION (FORMERLY: SISBRO CONSTRUCTION & SUPPLY) / 3RB CONSTRUCTION & SUPPLY | 7295 | 2022 | 2022-07-15 | 02/21/2022 | 332.95 | 0 | 2022-08-15 | 31
2024 | Region VII | CEBU | ALEGRIA (CEBU) | P00834597VS | Construction of Flood Mitigation Structure | 123.3891 | 9.7483 | 57896715.2 | 57896315.2 | 2024 | CENTERWAYS CONSTRUCTION AND DEVELOPMENT INC. | 7296 | 2024 | 2024-06-13 | 02/26/2024 | 400 | 0 | 2024-10-14 | 123
2023 | Region VII | CEBU | CEBU CITY (CAPITAL) (CEBU) | P00721687VS | Construction of Flood Mitigation Structure | 123.8821 | 10.3316 | 49000000 | 48900270 | 2024 | HELM CONSTRUCTION & SUPPLIES | 7297 | 2023 | 2024-03-01 | 06/15/2023 | 99730 | 0 | 2024-02-29 |  | 1
2023 | Region V | CAMARINES SUR | TIGAON (CAMARINES SUR) | P00742478LZ | Construction of Flood Mitigation Structure | 123.4998 | 13.635 | 47768100 | 47768100 | 2023 | ALRO CONSTRUCTION & DEVELOPMENT CORP. | 7298 | 2023 | 2023-11-20 | 03/30/2023 | 0 | 0 | 2024-01-23 | 64
2023 | Region V | ALBAY | LEGAZPI CITY (CAPITAL) (ALBAY) | P00740673LZ | Construction of Dike | 123.7447 | 13.1389 | 34279617.23 | 34299587.13 | 2023 | ROLCO CONSTRUCTION & DEVELOPMENT CORPORATION ( FOR | 7299 | 2023 | 2023-09-20 | 04/10/2023 | 0 | 19969.9 | 2023-09-19 |  | 1
2022 | Region X | LANAO DEL NORTE | MAIGO (LANAO DEL NORTE) | P00620044MN | Construction of Slope Protection Structure | 123.9531 | 8.1576 | 67550000 | 67550000 | 2023 | MAMSAR CONSTRUCTION AND INDUSTRIAL CORPORATION | 7300 | 2022 | 2023-01-09 | 03/18/2022 | 0 | 0 | 2023-01-16 | 7
2022 | Region V | SORSOGON | BULAN (SORSOGON) | P00630964LZ | Construction of Flood Mitigation Structure | 123.8823 | 12.7038 | 57900000 | 56163261.31 | 2023 | CENTERWAYS CONSTRUCTION AND DEVELOPMENT INC. | 7301 | 2022 | 2023-03-02 | 05/27/2022 | 1736738.69 | 0 | 2023-03-01 |  | 1
2023 | Region VII | CEBU | CARMEN (CEBU) | P00744362VS | Rehabilitation / Major Repair of Flood Control Structure | 124.0245 | 10.6063 | 4413910 | 4402803.81 | 2023 | POWER MOVE BUILDERS & CONSTRUCTION SUPPLY | 7302 | 2023 | 2023-06-12 | 03/30/2023 | 11106.19 | 0 | 2023-06-11 |  | 1
2022 | Region V | CAMARINES SUR | NABUA (CAMARINES SUR) | P00620275LZ | Construction of Flood Mitigation Structure | 123.3905 | 13.4045 | 97244668.14 | 97244668.14 | 2022 | RAMARPLUS INCORPORATED (FORMERLY RAMAR ENTERPRISES | 7303 | 2022 | 2022-11-30 | 03/21/2022 | 0 | 0 | 2023-01-20 | 51
2022 | Region V | MASBATE | MILAGROS (MASBATE) | P00620741LZ | Rehabilitation / Major Repair of Flood Control Structure | 123.5008 | 12.2313 | 33004435.48 | 33004435.48 | 2022 | SPRING STAR CONSTRUCTION AND SUPPLY | 7304 | 2022 | 2022-08-18 | 02/08/2022 | 0 | 0 | 2022-08-26 | 8
2023 | Region V | ALBAY | LEGAZPI CITY (CAPITAL) (ALBAY) | P00727380LZ | Construction of Dike | 123.7451 | 13.1352 | 24498540.76 | 24497975.66 | 2023 | JEJAN CONSTRUCTION AND SUPPLY(FOR. JEJAN CONSTRUCT | 7305 | 2023 | 2023-07-28 | 04/05/2023 | 565.1 | 0 | 2023-07-27 |  | 1
2023 | Region V | ALBAY | CAMALIG (ALBAY) | P00737382LZ | Construction of Dike | 123.6345 | 13.1703 | 57898534.32 | 57898389.08 | 2023 | AJAN JEADA, INC. (FORMERLY: JEADA CONSTRUCTION) | 7306 | 2023 | 2023-08-31 | 02/27/2023 | 145.24 | 0 | 2023-09-01 | 1
2024 | Region VII | CEBU | CONSOLACION (CEBU) | P00821057VS | Construction of Flood Mitigation Structure | 123.9533 | 10.3701 | 49000000 | 48970000 | 2024 | GONZALODO ENTERPRISES | 7307 | 2024 | 2024-08-22 | 04/19/2024 | 30000 | 0 | 2024-11-14 | 84
2023 | Region VII | CEBU | TUBURAN (CEBU) | P00721823VS | Rehabilitation / Major Repair of Flood Control Structure | 123.811 | 10.6927 | 19600000 | 19540533.8 | 2023 | VEN RAY CONSTRUCTION CORPORATION | 7308 | 2023 | 2023-09-06 | 02/02/2023 | 59466.2 | 0 | 2023-09-05 |  | 1
2023 | Region VII | CEBU | DANAO CITY (CEBU) | P00721770VS | Construction of Flood Mitigation Structure | 124.0247 | 10.5408 | 77200000 | 77077770.77 | 2023 | POWER MOVE BUILDERS & CONSTRUCTION SUPPLY / VSP STRUCTURE VENTURES CORP. (FORMERLY: VIRLO CONSTRUCTION) | 7309 | 2023 | 2023-12-24 | 03/30/2023 | 122229.23 | 0 | 2023-12-23 |  | 1
2023 | Region V | ALBAY | MANITO (ALBAY) | P00726982LZ | Construction of Dike | 123.8833 | 13.1138 | 72316488.3 | 72316233.42 | 2024 | MUNTOPAR BUILDERS CORP. / ALPHARD PRIMECON CONSTRUCTION | 7310 | 2023 | 2024-01-19 | 08/15/2023 | 254.88 | 0 | 2024-01-18 |  | 1
2023 | Region VI | NEGROS OCCIDENTAL | SAN CARLOS CITY (NEGROS OCCIDENTAL) | P00733699VS | Construction of Flood Mitigation Structure | 123.3909 | 10.4649 | 49500000 | 49500000 | 2024 | KENNETH CONSTRUCTION AND GENERAL MERCHANDISE | 7311 | 2023 | 2024-01-12 | 04/27/2023 | 0 | 0 | 2024-01-11 |  | 1
2022 | Region V | MASBATE | SAN JACINTO (MASBATE) | P00640482LZ | Rehabilitation / Major Repair of Slope Protection Structure | 123.6346 | 12.5439 | 98999354.98 | 98999354.98 | 2023 | CENTERWAYS CONSTRUCTION AND DEVELOPMENT INC. | 7312 | 2022 | 2023-12-20 | 07/28/2022 | 0 | 0 | 2023-12-25 | 5
2023 | Region V | CAMARINES SUR | GOA (CAMARINES SUR) | P00736102LZ | Construction of Flood Mitigation Structure | 123.5028 | 13.6762 | 95536200 | 95536200 | 2024 | BICOL GOLDROCK CONSTRUCTION CORPORATION | 7313 | 2023 | 2024-08-27 | 02/26/2023 | 0 | 0 | 2024-08-09 |  | 18
2022 | Region X | MISAMIS OCCIDENTAL | TANGUB CITY (MISAMIS OCCIDENTAL) | P00630586MN | Construction of Slope Protection Structure | 123.7451 | 8.0536 | 14700000 | 13963714.93 | 2023 | GRACE CONSTRUCTION CORPORATION | 7314 | 2022 | 2023-03-20 | 05/23/2022 | 736285.07 | 0 | 2022-11-10 |  | 130
2022 | Region VII | CEBU | CONSOLACION (CEBU) | P00633227VS | Construction of Flood Mitigation Structure | 123.9537 | 10.3974 | 49500000 | 49500000 | 2022 | A.S.T BUILDERS | 7315 | 2022 | 2022-12-12 | 03/30/2022 | 0 | 0 | 2022-12-11 |  | 1
2022 | Region V | SORSOGON | CASIGURAN (SORSOGON) | P00620300LZ | Construction of Flood Mitigation Structure | 124.025 | 12.8846 | 77199986.42 | 77199727.69 | 2022 | M.G. SALAZAR CONSTRUCTION CORP. (FOR. M.G. SALAZAR | 7316 | 2022 | 2022-11-13 | 02/17/2022 | 258.73 | 0 | 2022-11-12 |  | 1
2022 | Region V | ALBAY | CAMALIG (ALBAY) | P00639539LZ | Construction of Flood Mitigation Structure | 123.636 | 13.1792 | 48998392.17 | 48998161.24 | 2022 | INFRA BUILDERS AND SELLERS, PHILIPPINES | 7317 | 2022 | 2022-10-07 | 04/11/2022 | 230.93 | 0 | 2022-10-06 |  | 1
2022 | Region VII | BOHOL | CALAPE (BOHOL) | P00633209VS | Construction of Slope Protection Structure | 123.8839 | 9.8641 | 99000000 | 99000000 | 2023 | CEBU 7H TECHNOCHEM INDUSTRIES, INC. / REBTRADE INTERNATIONAL CORPORATION | 7318 | 2022 | 2023-02-18 | 07/15/2022 | 0 | 0 | 2023-02-17 |  | 1
2022 | Region VII | CEBU | MOALBOAL (CEBU) | P00620451VS | Construction of Flood Mitigation Structure | 123.3914 | 9.9331 | 29399951.87 | 29399951.87 | 2022 | RCDG CONSTRUCTION CORPORATION | 7319 | 2022 | 2022-11-10 | 03/23/2022 | 0 | 0 | 2022-11-09 |  | 1
2024 | Region V | ALBAY | OAS (ALBAY) | P00823647LZ | Construction of Flood Mitigation Structure | 123.5031 | 13.2545 | 57900000 | 57900000 | 2024 | RICHMAR CONSTRUCTION | 7320 | 2024 | 2024-08-21 | 04/15/2024 | 0 | 0 | 2024-12-09 | 110
2023 | Region X | LANAO DEL NORTE | MAIGO (LANAO DEL NORTE) | P00721251MN | Construction of Flood Mitigation Structure | 123.9539 | 8.156 | 57900000 | 57900000 | 2024 | DICON BUILDERS CORP. | 7321 | 2023 | 2024-01-26 | 03/27/2023 | 0 | 0 | 2024-01-27 | 1
2022 | Region V | ALBAY | LEGAZPI CITY (CAPITAL) (ALBAY) | P00620682LZ | Construction of Flood Mitigation Structure | 123.7456 | 13.1187 | 29398439.56 | 29398439.56 | 2022 | BIEN RAICE CONSTRUCTION AND SUPPLY CORPORATION | 7322 | 2022 | 2022-07-07 | 03/02/2022 | 0 | 0 | 2022-07-25 | 18
2022 | Region VII | CEBU | TUBURAN (CEBU) | P00620123VS | Construction of Flood Mitigation Structure | 123.8121 | 10.7144 | 49000000 | 48945957.56 | 2023 | VEN RAY CONSTRUCTION CORPORATION | 7323 | 2022 | 2023-06-23 | 08/02/2022 | 54042.44 | 0 | 2023-05-04 |  | 50
2023 | Region VII | CEBU | CATMON (CEBU) | P00721830VS | Construction of Flood Mitigation Structure | 124.0251 | 10.6485 | 49000000 | 48994888 | 2023 | QUIRANTE CONSTRUCTION CORPORATION (FORMERLY: QUIRANTE CONSTRUCTION) | 7324 | 2023 | 2023-08-27 | 01/30/2023 | 5112 | 0 | 2023-08-26 |  | 1
2024 | Region VII | CEBU | CITY OF CARCAR (CEBU) | P00820190VS | Construction of Flood Mitigation Structure | 123.6361 | 10.0903 | 24137400 | 23913150.01 | 2024 | A.T. DUMLAO CONSTRUCTION, INC. FORMERLYANDONI T. D | 7325 | 2024 | 2024-10-31 | 02/15/2024 | 224249.99 | 0 | 2024-10-30 |  | 1
2022 | Region V | ALBAY | TIWI (ALBAY) | P00637811LZ | Construction of Flood Mitigation Structure | 123.3922 | 13.2822 | 66329638.23 | 19800000 | 2022 | JORMAND CONSTRUCTION & SUPPLY | 7326 | 2022 | 2022-11-11 | 06/23/2022 | 46529638.23 | 0 | 2023-01-03 | 53
2022 | Region V | CAMARINES SUR | GOA (CAMARINES SUR) | P00620725LZ | Construction of Flood Mitigation Structure | 123.5035 | 13.7107 | 48234246.84 | 48234246.84 | 2023 | BICOL GOLDROCK CONSTRUCTION CORPORATION | 7327 | 2022 | 2023-02-26 | 03/22/2022 | 0 | 0 | 2023-02-25 |  | 1
2023 | Region VII | CEBU | CONSOLACION (CEBU) | P00722000VS | Construction of Flood Mitigation Structure | 123.954 | 10.4009 | 49000000 | 48989000 | 2023 | GTM BUILDERS & SUPPLY / ECBJ EASTCOAST CONSTRUCTION | 7328 | 2023 | 2023-09-25 | 04/18/2023 | 11000 | 0 | 2023-09-29 | 4
2023 | Region V | ALBAY | LEGAZPI CITY (CAPITAL) (ALBAY) | P00742473LZ | Construction of Dike | 123.7457 | 13.1221 | 49410664.89 | 49410453.64 | 2023 | ALRO CONSTRUCTION & DEVELOPMENT CORP. | 7329 | 2023 | 2023-09-22 | 04/05/2023 | 211.25 | 0 | 2023-10-02 | 10
2023 | Region VII | CEBU | CONSOLACION (CEBU) | P00721832VS | Construction of Flood Mitigation Structure | 123.9541 | 10.401 | 49000000 | 48900000 | 2023 | ZLREJ TRADING AND CONSTRUCTION CORPORATION / GICAR CONSTRUCTION, INC. | 7330 | 2023 | 2023-09-18 | 03/08/2023 | 100000 | 0 | 2023-09-20 | 2
2024 | Region X | LANAO DEL NORTE | SULTAN NAGA DIMAPORO (KAROMATAN) (LANAO DEL NORTE) | P00821090MN | Construction of Flood Mitigation Structure | 123.8129 | 7.7416 | 48995500 | 48840967.7 | 2024 | MOYA CONSTRUCTION / AL HUSSEIN CONSTRUCTION | 7331 | 2024 | 2024-11-18 | 02/16/2024 | 154532.3 | 0 | 2024-11-19 | 1
2022 | Region V | SORSOGON | CITY OF SORSOGON (CAPITAL) (SORSOGON) | P00632977LZ | Construction of Drainage Structure | 124.0267 | 13.0461 | 58899904.98 | 4947141.49 | 2022 | CENTERWAYS CONSTRUCTION AND DEVELOPMENT INC. | 7332 | 2022 | 2022-09-12 | 03/17/2022 | 53952763.49 | 0 | 2022-09-11 |  | 1
2022 | Region V | ALBAY | MALINAO (ALBAY) | P00631330LZ | Construction of Flood Mitigation Structure | 123.3926 | 13.2031 | 48999749.19 | 49000000 | 2022 | 3DIAMONDS CONSTRUCTION CORPORATION | 7333 | 2022 | 2022-11-30 | 08/10/2022 | 0 | 250.81 | 2023-01-26 | 57
2023 | Region V | SORSOGON | BULAN (SORSOGON) | P00742195LZ | Construction of Flood Mitigation Structure | 123.8841 | 12.7075 | 99000000 | 96031002.69 | 2024 | CENTERWAYS CONSTRUCTION AND DEVELOPMENT INC. | 7334 | 2023 | 2024-03-10 | 05/29/2023 | 2968997.31 | 0 | 2024-03-09 |  | 1
2021 | Region VII | SIQUIJOR |  | P00549964VS | Construction of Flood Mitigation Structure | 123.6384 | 9.1253 | 96500000 | 96499997.28 | 2023 | JASA GD 2000 CONSTRUCTION CORPORATION (FORMERLY:JASA BUILDER'S) | 7335 | 2021 | 2023-01-24 | 01/13/2022 | 2.72 | 0 | 2023-01-23 |  | 1
2023 | Region IX | ZAMBOANGA DEL SUR | MOLAVE (ZAMBOANGA DEL SUR) | P00732480MN | Construction of Drainage Structure | 123.504 | 8.087 | 4950000 | 4939955.66 | 2023 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R | 7336 | 2023 | 2023-09-05 | 02/20/2023 | 10044.34 | 0 | 2023-06-08 |  | 89
2024 | Region V | ALBAY | LEGAZPI CITY (CAPITAL) (ALBAY) | P00846108LZ | Construction of Flood Mitigation Structure | 123.7467 | 13.1188 | 98998957.41 | 98998134.14 | 2024 | AJAN JEADA, INC. (FORMERLY: JEADA CONSTRUCTION) / ALRO CONSTRUCTION & DEVELOPMENT CORP. | 7337 | 2024 | 2024-10-22 | 03/20/2024 | 823.27 | 0 | 2025-02-13 | 114
2023 | Region VII | CEBU | LAPU-LAPU CITY (OPON) (CEBU) | P00721680VS | Construction of Flood Mitigation Structure | 123.9546 | 10.2891 | 29400000 | 29400000 | 2023 | FLORIANE CONSTRUCTION CORPORATION (FORMERLY: FLORIANE CONSTRUCTION & SUPPLY) | 7338 | 2023 | 2023-09-07 | 02/14/2023 | 0 | 0 | 2023-09-07 | 0
2024 | Region VII | CEBU | TUBURAN (CEBU) | P00820192VS | Rehabilitation / Major Repair of Flood Control Structure | 123.8135 | 10.7149 | 19600000 | 19300000 | 2024 | JJ &J CONSTRUCTION & GENERAL SUPPLY | 7339 | 2024 | 2024-07-12 | 02/02/2024 | 300000 | 0 | 2024-07-13 | 1
2022 | Region VII | BOHOL | LOBOC (BOHOL) | P00620116VS | Construction of Flood Mitigation Structure | 124.027 | 9.6441 | 49000000 | 48988729.71 | 2023 | LABB CONSTRUCTION DEVELOPMENT INC. (FORMERLY: LABB CONSTRUCTION) | 7340 | 2022 | 2023-12-09 | 04/12/2022 | 11270.29 | 0 | 2023-12-08 |  | 1
2023 | Region X | LANAO DEL NORTE | SULTAN NAGA DIMAPORO (KAROMATAN) (LANAO DEL NORTE) | P00721613MN | Construction of Revetment | 123.8135 | 7.7413 | 49000000 | 48973571.68 | 2024 | NDP CONSTRUCTION DEVELOPMENT / AL HUSSEIN CONSTRUCTION | 7341 | 2023 | 2024-05-02 | 06/21/2023 | 26428.32 | 0 | 2024-05-01 |  | 1
2022 | Region V | CAMARINES SUR | BAAO (CAMARINES SUR) | P00631004LZ | Rehabilitation / Major Repair of Flood Control Structure | 123.3931 | 13.4526 | 77200000 | 77199975.67 | 2022 | SISAM CONSTRUCTION & SUPPLIES | 7342 | 2022 | 2022-09-19 | 03/23/2022 | 24.33 | 0 | 2022-11-27 | 69
2022 | Region V | MASBATE | CITY OF MASBATE (CAPITAL) (MASBATE) | P00620747LZ | Rehabilitation / Major Repair of Flood Control Structure | 123.6392 | 12.3496 | 33004386.92 | 33004386.92 | 2022 | ARKY CONSTRUCTION AND SUPPLY | 7343 | 2022 | 2022-10-05 | 02/08/2022 | 0 | 0 | 2022-10-04 |  | 1
2022 | Region V | ALBAY | LIBON (ALBAY) | P00630993LZ | Rehabilitation / Major Repair of Flood Control Structure | 123.3935 | 13.2777 | 77200000 | 77200000 | 2023 | WEARR ENTERPRISES & DEVELOPMENT CORP. | 7344 | 2022 | 2023-09-10 | 08/15/2022 | 0 | 0 | 2023-09-07 |  | 3
2023 | Region V | ALBAY | CAMALIG (ALBAY) | P00740440LZ | Construction of Dike | 123.6392 | 13.19 | 72316434.18 | 72316174.75 | 2023 | NEXT GENERATION CONSTRUCTION AND SUPPLY CORPORATION | 7345 | 2023 | 2023-10-07 | 06/19/2023 | 259.43 | 0 | 2023-12-24 | 78
2021 | Region V | CAMARINES SUR |  | P00526232LZ | Construction of Flood Mitigation Structure | 123.5046 | 13.7345 | 49000000 | 49000000 | 2022 | E.A. SANCHO CONST. INC. (FORM. E.A. SANCHO CONST.) | 7346 | 2021 | 2022-11-04 | 11/09/2021 | 0 | 0 | 2022-10-03 |  | 32
2023 | Region VII | BOHOL | CORTES (BOHOL) | P00721936VS | Construction of Drainage Structure | 123.8855 | 9.7248 | 49000000 | 48656422 | 2024 | LABB CONSTRUCTION DEVELOPMENT INC. (FORMERLY: LABB CONSTRUCTION) | 7347 | 2023 | 2024-04-14 | 07/05/2023 | 343578 | 0 | 2024-04-13 |  | 1
2023 | Region X | LANAO DEL NORTE | MAIGO (LANAO DEL NORTE) | P00721253MN | Construction of Flood Mitigation Structure | 123.9548 | 8.1556 | 53075000 | 53075000 | 2023 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R | 7348 | 2023 | 2023-11-20 | 03/27/2023 | 0 | 0 | 2024-01-15 | 56
2022 | Region VII | BOHOL | LOBOC (BOHOL) | P00620115VS | Construction of Flood Mitigation Structure | 124.0274 | 9.6438 | 49000000 | 48998764.5 | 2023 | BOOMETRIX DEVELOPMENT CORP. | 7349 | 2022 | 2023-12-11 | 04/26/2022 | 1235.5 | 0 | 2023-12-22 | 11
2024 | Region X | LANAO DEL NORTE | SAPAD (LANAO DEL NORTE) | P00820154MN | Construction of Flood Mitigation Structure | 123.8145 | 7.8501 | 12233289.01 | 11976633.24 | 2024 | LANAO BUILDER AND ENTERPRISES | 7350 | 2024 | 2024-10-29 | 02/16/2024 | 256655.77 | 0 | 2024-10-28 |  | 1
2022 | Region V | ALBAY | MALINAO (ALBAY) | P00640570LZ | Construction of Flood Mitigation Structure | 123.3955 | 13.2133 | 66329638.23 | 14850000 | 2022 | JORMAND CONSTRUCTION & SUPPLY | 7351 | 2022 | 2022-11-11 | 06/23/2022 | 51479638.23 | 0 | 2023-01-03 | 53
2023 | Region VII | CEBU | ASTURIAS (CEBU) | P00721764VS | Construction of Flood Mitigation Structure | 123.747 | 10.5533 | 77200000 | 77134000 | 2023 | VEN RAY CONSTRUCTION CORPORATION | 7352 | 2023 | 2023-11-28 | 03/02/2023 | 66000 | 0 | 2023-11-27 |  | 1
2023 | Region V | CAMARINES SUR | BUHI (CAMARINES SUR) | P00726975LZ | Construction of Flood Mitigation Structure | 123.5059 | 13.4299 | 139859984 | 139859923.4 | 2024 | HI-TONE CONSTRUCTION & DEVELOPMENT CORP. (FORMERLY | 7353 | 2023 | 2024-03-27 | 03/22/2023 | 60.6 | 0 | 2024-03-26 |  | 1
2022 | Region V | SORSOGON | DONSOL (SORSOGON) | P00620324LZ | Construction of Flood Mitigation Structure | 123.5068 | 12.9663 | 279839557.3 | 131553950 | 2023 | CENTERWAYS CONSTRUCTION AND DEVELOPMENT INC. | 7354 | 2022 | 2023-12-20 | 07/14/2022 | 148285607.3 | 0 | 2023-12-31 | 11
2022 | Region VII | CEBU | CEBU CITY (CAPITAL) (CEBU) | P00633015VS | Construction of Drainage Structure | 123.8858 | 10.359 | 4900000 | 4792519.98 | 2023 | INCEP CONSTRUCTION AND DEVELOPMENT CORP. | 7355 | 2022 | 2023-03-02 | 09/13/2022 | 107480.02 | 0 | 2023-03-01 |  | 1
2023 | Region V | ALBAY | CAMALIG (ALBAY) | P00742196LZ | Construction of Dike | 123.6399 | 13.1936 | 98886253.44 | 98885867.64 | 2023 | CENTERWAYS CONSTRUCTION AND DEVELOPMENT INC. | 7356 | 2023 | 2023-12-20 | 06/30/2023 | 385.8 | 0 | 2024-04-22 | 124
2024 | Region VII | CEBU | CONSOLACION (CEBU) | P00820325VS | Construction of Flood Mitigation Structure | 123.9549 | 10.4068 | 96500000 | 96399888 | 2024 | QUIRANTE CONSTRUCTION CORPORATION (FORMERLY: QUIRANTE CONSTRUCTION) | 7357 | 2024 | 2024-08-09 | 02/16/2024 | 100112 | 0 | 2024-08-10 | 1
2024 | Region X | LANAO DEL NORTE | SULTAN NAGA DIMAPORO (KAROMATAN) (LANAO DEL NORTE) | P00821089MN | Construction of Flood Mitigation Structure | 123.8152 | 7.7422 | 48995500 | 48869498.05 | 2024 | U.M.D. CONSTRUCTION / LANAO BUILDER AND ENTERPRISES | 7358 | 2024 | 2024-09-24 | 02/16/2024 | 126001.95 | 0 | 2024-10-05 | 11
2021 | Region V | ALBAY |  | P00525680LZ | Construction of Flood Mitigation Structure | 123.7476 | 13.2069 | 289499999.7 | 144749999.8 | 2022 | MAKAPA CORPORATION | 7359 | 2021 | 2022-09-21 | 03/19/2021 | 144749999.9 | 0 | 2022-09-20 |  | 1
2022 | Region VII | BOHOL | LOBOC (BOHOL) | P00630220VS | Construction of Flood Mitigation Structure | 124.0283 | 9.6392 | 49000000 | 49000000 | 2023 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY | 7360 | 2022 | 2023-12-15 | 04/01/2022 | 0 | 0 | 2024-01-26 | 42
2024 | Region VII | CEBU | CITY OF TALISAY (CEBU) | P00834981VS | Construction of Flood Mitigation Structure | 123.8164 | 10.3117 | 148500000 | 148500000 | 2025 | QM BUILDERS | 7361 | 2024 | 2025-02-21 | 03/08/2024 | 0 | 0 | 2025-03-17 | 24
2022 | Region V | CAMARINES SUR | BAAO (CAMARINES SUR) | P00630989LZ | Construction of Flood Mitigation Structure | 123.3956 | 13.4552 | 67550000 | 65187109.3 | 2022 | RAMARPLUS INCORPORATED (FORMERLY RAMAR ENTERPRISES | 7362 | 2022 | 2022-12-09 | 03/22/2022 | 2362890.7 | 0 | 2022-12-09 | 0
2023 | Region V | MASBATE | MILAGROS (MASBATE) | P00725889LZ | Construction of Flood Mitigation Structure | 123.507 | 12.2163 | 91674973.36 | 91675000 | 2024 | HKP CONSTRUCTION AND SUPPLY / DSB CONSTRUCTION & SUPPLY, INC. (FORMERLY: DSB CO | 7363 | 2023 | 2024-06-10 | 08/09/2023 | 0 | 26.64 | 2024-06-09 |  | 1
2023 | Region VII | CEBU | MANDAUE CITY (CEBU) | P00721681VS | Construction of Flood Mitigation Structure | 123.9555 | 10.3576 | 49000000 | 48984888 | 2024 | QUIRANTE CONSTRUCTION CORPORATION (FORMERLY: QUIRANTE CONSTRUCTION) | 7364 | 2023 | 2024-01-07 | 05/12/2023 | 15112 | 0 | 2024-01-06 |  | 1
2023 | Region V | ALBAY | CAMALIG (ALBAY) | P00740441LZ | Construction of Dike | 123.6401 | 13.186 | 72268122.02 | 72267813.25 | 2023 | CENTERWAYS CONSTRUCTION AND DEVELOPMENT INC. / FS CO BUILDERS AND SUPPLY | 7365 | 2023 | 2023-11-22 | 05/17/2023 | 308.77 | 0 | 2023-11-21 |  | 1
2023 | Region VII | CEBU | CEBU CITY (CAPITAL) (CEBU) | P00721836VS | Construction of Flood Mitigation Structure | 123.8869 | 10.3015 | 44100000 | 43595644.8 | 2024 | CHARLZ CONSTRUCTION, INC. | 7366 | 2023 | 2024-02-20 | 07/20/2023 | 504355.2 | 0 | 2024-02-19 |  | 1
2023 | Region V | ALBAY | LEGAZPI CITY (CAPITAL) (ALBAY) | P00740675LZ | Construction of Dike | 123.7488 | 13.2122 | 48942370.68 | 48942124.8 | 2023 | ALPHA RYDER CONSTRUCTION & SUPPLIES | 7367 | 2023 | 2023-09-30 | 05/17/2023 | 245.88 | 0 | 2023-11-01 | 32
2022 | Region VII | BOHOL | LOBOC (BOHOL) | P00630219VS | Construction of Flood Mitigation Structure | 124.0307 | 9.6348 | 40180000 | 40179948.69 | 2023 | N.N. YU CONSTRUCTION, INC. (FORMERLY: YU CONSTRUCTION) | 7368 | 2022 | 2023-02-15 | 05/04/2022 | 51.31 | 0 | 2023-02-14 |  | 1
2024 | Region VII | CEBU | CITY OF TALISAY (CEBU) | P00834982VS | Construction of Flood Mitigation Structure | 123.8164 | 10.3117 | 148500000 | 148500000 | 2025 | QM BUILDERS | 7369 | 2024 | 2025-02-21 | 03/08/2024 | 0 | 0 | 2025-03-17 | 24
2023 | Region V | CAMARINES SUR | NABUA (CAMARINES SUR) | P00727326LZ | Construction of Flood Mitigation Structure | 123.3963 | 13.4034 | 77097058 | 77096696.93 | 2023 | BICOL GOLDROCK CONSTRUCTION CORPORATION / ASCON CONSTRUCTION AND SUPPLY | 7370 | 2023 | 2023-08-25 | 03/20/2023 | 361.07 | 0 | 2023-12-04 | 101
2022 | Region V | SORSOGON | CITY OF SORSOGON (CAPITAL) (SORSOGON) | P00620289LZ | Construction of Flood Mitigation Structure | 123.956 | 12.9636 | 77199993.93 | 77165034.11 | 2023 | AARCON BUILDERS | 7371 | 2022 | 2023-05-25 | 02/17/2022 | 34959.82 | 0 | 2023-05-24 |  | 1
2022 | Region V | ALBAY | CAMALIG (ALBAY) | P00631344LZ | Construction of Dike | 123.6404 | 13.196 | 48998316.52 | 48998125.42 | 2022 | SISBRO CONSTRUCTION CORPORATION (FORMERLY: SISBRO CONSTRUCTION & SUPPLY) / 3RB CONSTRUCTION & SUPPLY | 7372 | 2022 | 2022-07-15 | 02/21/2022 | 191.1 | 0 | 2022-08-15 | 31
2022 | Region VII | CEBU | CEBU CITY (CAPITAL) (CEBU) | P00633017VS | Construction of Flood Mitigation Structure | 123.8892 | 10.3855 | 4950000 | 4895000 | 2022 | BELCONSTRUCT CORPORATION | 7373 | 2022 | 2022-09-30 | 05/30/2022 | 55000 | 0 | 2022-09-29 |  | 1
2023 | Region V | MASBATE | USON (MASBATE) | P00726303LZ | Construction of Flood Mitigation Structure | 123.7496 | 12.2445 | 39181452.96 | 39140952.92 | 2024 | GACT ENTERPRISES | 7374 | 2023 | 2024-06-08 | 08/07/2023 | 40500.04 | 0 | 2024-06-07 |  | 1
2024 | Region VII | CEBU | TABOGON (CEBU) | P00835006VS | Construction of Flood Mitigation Structure | 124.0308 | 10.9477 | 49500000 | 49500000 | 2024 | GONZALODO ENTERPRISES | 7375 | 2024 | 2024-12-26 | 08/27/2024 | 0 | 0 | 2025-03-14 | 78
2022 | Region V | SORSOGON | MAGALLANES (SORSOGON) | P00640600LZ | Construction of Flood Mitigation Structure | 123.8188 | 12.8205 | 59399996.63 | 19734064.7 | 2022 | ALNINO CONSTRUCTION & SUPPLY CORPORATION (FORMERLY: AL NINO CONSTRUCTION & SUPPLY) | 7376 | 2022 | 2022-11-11 | 04/04/2022 | 39665931.93 | 0 | 2022-11-12 | 1
2023 | Region VII | CEBU | LAPU-LAPU CITY (OPON) (CEBU) | P00733741VS | Rehabilitation / Major Repair of Drainage Structure | 123.9561 | 10.2901 | 29700000 | 17194575 | 2024 | FLORIANE CONSTRUCTION CORPORATION (FORMERLY: FLORIANE CONSTRUCTION & SUPPLY) | 7377 | 2023 | 2024-07-31 | 05/18/2023 | 12505425 | 0 | 2024-08-04 | 4
2022 | Region VII | CEBU | CEBU CITY (CAPITAL) (CEBU) | P00630656VS | Construction of Drainage Structure | 123.8894 | 10.2997 | 4950000 | 4939702.44 | 2022 | 1ST J.E. ADLAWAN CONSTRUCTION & SUPPLY CORPORATION (FORMERLY: ELEAZAR V. ADLAWAN CONSTRUCTION) | 7378 | 2022 | 2022-07-19 | 03/18/2022 | 10297.56 | 0 | 2022-07-18 |  | 1
2024 | Region VII | CEBU | BADIAN (CEBU) | P00834658VS | Construction of Flood Mitigation Structure | 123.3976 | 9.8715 | 48996720 | 48996484.84 | 2024 | QUIRANTE CONSTRUCTION CORPORATION (FORMERLY: QUIRANTE CONSTRUCTION) | 7379 | 2024 | 2024-10-22 | 03/18/2024 | 235.16 | 0 | 2024-10-21 |  | 1
2023 | Region VII | CEBU | CEBU CITY (CAPITAL) (CEBU) | P00721835VS | Construction of Flood Mitigation Structure | 123.8895 | 10.2975 | 44100000 | 44019255 | 2024 | GOWIL BUILDERS | 7380 | 2023 | 2024-01-15 | 06/14/2023 | 80745 | 0 | 2024-01-14 |  | 1
2024 | Region V | ALBAY | CAMALIG (ALBAY) | P00823628LZ | Construction of Dike | 123.6407 | 13.1414 | 48248953.35 | 48248950.81 | 2024 | MUNTOPAR BUILDERS CORP. | 7381 | 2024 | 2024-11-15 | 04/12/2024 | 2.54 | 0 | 2024-12-22 | 37
2024 | Region V | MASBATE | SAN FERNANDO (MASBATE) | P00821010LZ | Construction of Flood Mitigation Structure | 123.7506 | 12.4897 | 49000000 | 48999764.72 | 2024 | A3 CONSTRUCTION & SUPPLY | 7382 | 2024 | 2024-12-02 | 04/01/2024 | 235.28 | 0 | 2024-12-01 |  | 1
2022 | Region VII | BOHOL | CATIGBIAN (BOHOL) | P00620111VS | Construction of Flood Mitigation Structure | 124.0323 | 9.8625 | 49000000 | 48999390 | 2022 | BNYU DEVELOPMENT CORPORATION (FORMERLY:BNYU ENTERPRISES & CONSTRUCTION) | 7383 | 2022 | 2022-11-15 | 03/24/2022 | 610 | 0 | 2022-11-14 |  | 1
2024 | Region V | CAMARINES SUR | BUHI (CAMARINES SUR) | P00820437LZ | Construction of Flood Mitigation Structure | 123.5082 | 13.4333 | 139925000 | 139925000 | 2024 | SISBRO CONSTRUCTION CORPORATION (FORMERLY: SISBRO CONSTRUCTION & SUPPLY) | 7384 | 2024 | 2024-12-12 | 02/21/2024 | 0 | 0 | 2025-03-04 | 82
2023 | Region VII | CEBU | ALEGRIA (CEBU) | P00721876VS | Construction of Dike | 123.3978 | 9.7504 | 96112254 | 96112225.44 | 2023 | ZLREJ TRADING AND CONSTRUCTION CORPORATION / GICAR CONSTRUCTION, INC. | 7385 | 2023 | 2023-11-21 | 03/16/2023 | 28.56 | 0 | 2024-01-22 | 62
2023 | Region V | ALBAY | CAMALIG (ALBAY) | P00740668LZ | Construction of Dike | 123.6408 | 13.1433 | 48188808.48 | 48186131.52 | 2023 | NEXT GENERATION CONSTRUCTION AND SUPPLY CORPORATION | 7386 | 2023 | 2023-07-15 | 04/05/2023 | 2676.96 | 0 | 2023-09-26 | 73
2022 | Region V | ALBAY | LIBON (ALBAY) | P00631368LZ | Rehabilitation / Major Repair of Flood Control Structure | 123.3983 | 13.2934 | 93100000 | 49000000 | 2022 | RAMARPLUS INCORPORATED (FORMERLY RAMAR ENTERPRISES | 7387 | 2022 | 2022-12-16 | 03/22/2022 | 44100000 | 0 | 2022-12-30 | 14
2022 | Region V | SORSOGON | CITY OF SORSOGON (CAPITAL) (SORSOGON) | P00620293LZ | Construction of Flood Mitigation Structure | 123.9566 | 12.964 | 77199994.18 | 77026450.47 | 2023 | STEVEN CONSTRUCTION & SUPPLY | 7388 | 2022 | 2023-05-25 | 02/17/2022 | 173543.71 | 0 | 2023-05-24 |  | 1
2024 | Region VII | CEBU | CITY OF TALISAY (CEBU) | P00834979VS | Construction of Flood Mitigation Structure | 123.8197 | 10.2833 | 89100000 | 89100000 | 2024 | QM BUILDERS | 7389 | 2024 | 2024-12-19 | 03/04/2024 | 0 | 0 | 2024-12-18 |  | 1
2021 | Region VII | CEBU |  | P00549966VS | Construction of Flood Mitigation Structure | 123.7509 | 10.2062 | 77200000 | 77200000 | 2022 | QUIRANTE CONSTRUCTION CORPORATION (FORMERLY: QUIRANTE CONSTRUCTION) | 7390 | 2021 | 2022-08-01 | 11/03/2021 | 0 | 0 | 2022-07-31 |  | 1
2023 | Region V | MASBATE | MILAGROS (MASBATE) | P00725892LZ | Construction of Flood Mitigation Structure | 123.5084 | 12.2161 | 62724955.75 | 62725000 | 2024 | HKP CONSTRUCTION AND SUPPLY / DSB CONSTRUCTION & SUPPLY, INC. (FORMERLY: DSB CO | 7391 | 2023 | 2024-04-15 | 08/09/2023 | 0 | 44.25 | 2024-04-14 |  | 1
2023 | Region V | SORSOGON | CITY OF SORSOGON (CAPITAL) (SORSOGON) | P00742490LZ | Construction of Flood Mitigation Structure | 124.0356 | 13.0367 | 54449963.17 | 4943439.65 | 2024 | CENTERWAYS CONSTRUCTION AND DEVELOPMENT INC. / CHEEREL CONSTRUCTION & SUPPLY | 7392 | 2023 | 2024-03-05 | 07/18/2023 | 49506523.52 | 0 | 2024-03-04 |  | 1
2022 | Region V | ALBAY | CAMALIG (ALBAY) | P00639535LZ | Construction of Flood Mitigation Structure | 123.6419 | 13.1955 | 48998457.14 | 48999470.75 | 2022 | HI-TONE CONSTRUCTION & DEVELOPMENT CORP. (FORMERLY | 7393 | 2022 | 2022-12-13 | 06/20/2022 | 0 | 1013.61 | 2022-12-12 |  | 1
2022 | Region VII | CEBU | CITY OF CARCAR (CEBU) | P00620020VS | Construction of Flood Mitigation Structure | 123.6449 | 10.1029 | 91675000 | 91674735.35 | 2023 | PRIME GIGABUILD CONSTRUCTION CORP. (FORMERLY: RON DANIELL CONSTRUCTION CORPORATION) | 7394 | 2022 | 2023-01-16 | 03/25/2022 | 264.65 | 0 | 2023-01-15 |  | 1
2023 | Region VII | CEBU | CEBU CITY (CAPITAL) (CEBU) | P00733747VS | Construction of Flood Mitigation Structure | 123.89 | 10.3022 | 4950000 | 4944995.26 | 2024 | MATROSON BUILDERS & ENGINEERING SERVICES | 7395 | 2023 | 2024-02-10 | 10/10/2023 | 5004.74 | 0 | 2024-02-09 |  | 1
2024 | Region VII | CEBU | SAN REMIGIO (CEBU) | P00834644VS | Construction of Flood Mitigation Structure | 123.9566 | 10.9697 | 19600000 | 19600000 | 2024 | ADAMANT DEVELOPMENT CORPORATION | 7396 | 2024 | 2024-12-19 | 07/08/2024 | 0 | 0 | 2024-12-18 |  | 1
2024 | Region VII | CEBU | CITY OF TALISAY (CEBU) | P00834983VS | Construction of Flood Mitigation Structure | 123.8219 | 10.2825 | 138600000 | 138600000 | 2025 | QM BUILDERS | 7397 | 2024 | 2025-01-20 | 03/04/2024 | 0 | 0 | 2025-01-19 |  | 1
2022 | Region V | ALBAY | OAS (ALBAY) | P00631358LZ | Construction of Flood Mitigation Structure | 123.5087 | 13.2504 | 98000000 | 48999187.66 | 2023 | RAMARPLUS INCORPORATED (FORMERLY RAMAR ENTERPRISES | 7398 | 2022 | 2023-03-31 | 08/01/2022 | 49000812.34 | 0 | 2023-05-11 | 41
2022 | Region V | ALBAY | LEGAZPI CITY (CAPITAL) (ALBAY) | P00620302LZ | Construction of Flood Mitigation Structure | 123.7511 | 13.1618 | 67548263.6 | 67548213.38 | 2022 | NEXT GENERATION CONSTRUCTION AND SUPPLY CORPORATION / 3RB CONSTRUCTION & SUPPLY | 7399 | 2022 | 2022-10-09 | 03/04/2022 | 50.22 | 0 | 2022-10-08 |  | 1
2024 | Region VII | CEBU | DAANBANTAYAN (CEBU) | P00820187VS | Construction of Flood Mitigation Structure | 124.0371 | 10.8994 | 29400000 | 29400000 | 2024 | TCP BUILDERS | 7400 | 2024 | 2024-07-11 | 02/13/2024 | 0 | 0 | 2024-07-10 |  | 1
2023 | Region V | MASBATE | SAN FERNANDO (MASBATE) | P00726295LZ | Construction of Flood Mitigation Structure | 123.7514 | 12.49 | 23520000 | 23519985.34 | 2023 | EJ CANTORIA CONSTRUCTION & SUPPLY | 7401 | 2023 | 2023-09-04 | 03/31/2023 | 14.66 | 0 | 2023-10-24 | 50
2023 | Region VII | CEBU | CEBU CITY (CAPITAL) (CEBU) | P00721838VS | Construction of Flood Mitigation Structure | 123.8924 | 10.3356 | 44100000 | 44030000 | 2023 | ARQ BUILDERS / VNCO CONSTRUCTION | 7402 | 2023 | 2023-12-13 | 07/24/2023 | 70000 | 0 | 2024-02-23 | 72
2022 | Region V | ALBAY | CAMALIG (ALBAY) | P00620681LZ | Construction of Flood Mitigation Structure | 123.6453 | 13.2067 | 44098373.46 | 44098134.64 | 2022 | ALRO CONSTRUCTION & DEVELOPMENT CORP. | 7403 | 2022 | 2022-07-25 | 02/21/2022 | 238.82 | 0 | 2022-08-06 | 12
2023 | Region V | CAMARINES SUR | OCAMPO (CAMARINES SUR) | P00726618LZ | Construction of Flood Mitigation Structure | 123.3988 | 13.5659 | 86849990.26 | 85981400 | 2023 | PHILWORKS CONSTRUCTION & SUPPLY | 7404 | 2023 | 2023-12-01 | 02/20/2023 | 868590.26 | 0 | 2023-11-30 |  | 1
2023 | Region VII | CEBU | CITY OF TALISAY (CEBU) | P00721879VS | Construction of Flood Mitigation Structure | 123.8221 | 10.2758 | 96500000 | 96500000 | 2024 | QM BUILDERS | 7405 | 2023 | 2024-03-05 | 05/04/2023 | 0 | 0 | 2024-03-04 |  | 1
2023 | Region V | MASBATE | PALANAS (MASBATE) | P00726308LZ | Construction of Flood Mitigation Structure | 123.9571 | 12.0993 | 22494177.9 | 22491873.94 | 2023 | RED DIAMOND CONSTRUCTION AND SUPPLY CORPORATION (FORMERLY: RED DIAMOND CONSTRUCTION) | 7406 | 2023 | 2023-07-15 | 04/25/2023 | 2303.96 | 0 | 2023-11-26 | 134
2022 | Region V | MASBATE | MILAGROS (MASBATE) | P00620291LZ | Construction of Flood Mitigation Structure | 123.5087 | 12.2159 | 96499963.39 | 96500000 | 2023 | HGG BUILDERS & SUPPLY | 7407 | 2022 | 2023-05-24 | 02/22/2022 | 0 | 36.61 | 2023-05-23 |  | 1
2022 | Region V | SORSOGON | CITY OF SORSOGON (CAPITAL) (SORSOGON) | P00630971LZ | Construction of Flood Mitigation Structure | 124.0377 | 13.0407 | 96499962.61 | 96499953.46 | 2022 | CENTERWAYS CONSTRUCTION AND DEVELOPMENT INC. | 7408 | 2022 | 2022-12-21 | 02/18/2022 | 9.15 | 0 | 2022-12-20 |  | 1
2023 | Region VII | CEBU | ASTURIAS (CEBU) | P00721822VS | Rehabilitation / Major Repair of Flood Control Structure | 123.7514 | 10.6294 | 19600000 | 18546000 | 2023 | VEN RAY CONSTRUCTION CORPORATION | 7409 | 2023 | 2023-10-26 | 05/02/2023 | 1054000 | 0 | 2023-10-25 |  | 1
2022 | Region V | SORSOGON | CITY OF SORSOGON (CAPITAL) (SORSOGON) | P00620272LZ | Construction of Flood Mitigation Structure | 124.0439 | 13.0428 | 96499843.54 | 96493351.5 | 2022 | HI-TONE CONSTRUCTION & DEVELOPMENT CORP. (FORMERLY | 7410 | 2022 | 2022-12-03 | 02/17/2022 | 6492.04 | 0 | 2022-12-02 |  | 1
2024 | Region VII | CEBU | TOLEDO CITY (CEBU) | P00820398VS | Construction of Flood Mitigation Structure | 123.6464 | 10.3929 | 49000000 | 49000000 | 2024 | VEN RAY CONSTRUCTION CORPORATION | 7411 | 2024 | 2024-09-05 | 02/02/2024 | 0 | 0 | 2024-09-04 |  | 1
2022 | Region VII | CEBU | CEBU CITY (CAPITAL) (CEBU) | P00630661VS | Construction of Drainage Structure | 123.8953 | 10.3213 | 4950000 | 4939939.5 | 2023 | M.C. BUYSER CONSTRUCTION & SUPPLY | 7412 | 2022 | 2023-02-13 | 10/05/2022 | 10060.5 | 0 | 2023-02-04 |  | 9
2022 | Region VII | CEBU | LAPU-LAPU CITY (OPON) (CEBU) | P00630647VS | Construction of Flood Mitigation Structure | 123.9571 | 10.3175 | 6930000 | 6930000 | 2022 | MEGA PLUS CONSTRUCTION AND SUPPLY CORP. (FORMERLY: MEGA PLUS CONSTRUCTION) | 7413 | 2022 | 2022-07-27 | 02/15/2022 | 0 | 0 | 2022-07-28 | 1
2023 | Region VII | CEBU | CITY OF TALISAY (CEBU) | P00721880VS | Construction of Flood Mitigation Structure | 123.8221 | 10.2758 | 96500000 | 96500000 | 2024 | QM BUILDERS | 7414 | 2023 | 2024-03-05 | 05/04/2023 | 0 | 0 | 2024-03-04 |  | 1
2022 | Region V | ALBAY | LIBON (ALBAY) | P00631372LZ | Rehabilitation / Major Repair of Flood Control Structure | 123.3988 | 13.2937 | 93100000 | 44100000 | 2022 | RAMARPLUS INCORPORATED (FORMERLY RAMAR ENTERPRISES | 7415 | 2022 | 2022-12-16 | 03/22/2022 | 49000000 | 0 | 2022-12-30 | 14
2022 | Region VII | CEBU | DUMANJUG (CEBU) | P00633233VS | Construction of Drainage Structure | 123.5095 | 10.0245 | 45539979.25 | 45539979.25 | 2022 | QM BUILDERS | 7416 | 2022 | 2022-10-19 | 03/23/2022 | 0 | 0 | 2022-10-18 |  | 1
2021 | Region V | ALBAY |  | P00561196LZ | Construction of Flood Mitigation Structure | 123.7519 | 13.1887 | 39198459.2 | 39197824.08 | 2022 | CBC CONSTRUCTION & SUPPLY | 7417 | 2021 | 2022-08-11 | 03/04/2022 | 635.12 | 0 | 2022-08-10 |  | 1
2022 | Region V | SORSOGON | CITY OF SORSOGON (CAPITAL) (SORSOGON) | P00620271LZ | Construction of Flood Mitigation Structure | 124.0451 | 13.0424 | 96499965.44 | 96472990.61 | 2022 | HI-TONE CONSTRUCTION & DEVELOPMENT CORP. (FORMERLY | 7418 | 2022 | 2022-12-03 | 02/17/2022 | 26974.83 | 0 | 2022-12-02 |  | 1
2024 | Region V | ALBAY | LEGAZPI CITY (CAPITAL) (ALBAY) | P00839666LZ | Construction of Flood Mitigation Structure | 123.7522 | 13.205 | 19798908.64 | 19015682.52 | 2024 | QJ CONSTRUCTION | 7419 | 2024 | 2024-08-05 | 04/23/2024 | 783226.12 | 0 | 2024-08-04 |  | 1
2023 | Region V | ALBAY | OAS (ALBAY) | P00740501LZ | Rehabilitation / Major Repair of Flood Control Structure | 123.5105 | 13.25 | 62655000 | 62655000 | 2023 | CPR CONSTRUCTION AND SUPPLY, INC. (FORMERLY: CPR CONSTRUCTION AND SUPPLY) | 7420 | 2023 | 2023-10-10 | 05/22/2023 | 0 | 0 | 2024-03-23 | 165
2023 | Region VII | CEBU | MANDAUE CITY (CEBU) | P00733263VS | Construction of Flood Mitigation Structure | 123.9571 | 10.3571 | 96500000 | 96399888 | 2024 | QUIRANTE CONSTRUCTION CORPORATION (FORMERLY: QUIRANTE CONSTRUCTION) | 7421 | 2023 | 2024-04-04 | 05/12/2023 | 100112 | 0 | 2024-11-12 | 222
2023 | Region VII | CEBU | CITY OF TALISAY (CEBU) | P00721881VS | Construction of Flood Mitigation Structure | 123.8221 | 10.2758 | 96500000 | 96500000 | 2024 | QM BUILDERS | 7422 | 2023 | 2024-03-05 | 05/04/2023 | 0 | 0 | 2024-03-04 |  | 1
2023 | Region V | ALBAY | LIBON (ALBAY) | P00742202LZ | Construction of Flood Mitigation Structure | 123.3988 | 13.2938 | 146555000 | 74179689.03 | 2023 | RAMARPLUS INCORPORATED (FORMERLY RAMAR ENTERPRISES | 7423 | 2023 | 2023-11-15 | 05/03/2023 | 72375310.97 | 0 | 2024-02-25 | 102
2023 | Region V | SORSOGON | CITY OF SORSOGON (CAPITAL) (SORSOGON) | P00726320LZ | Construction of Flood Mitigation Structure | 123.8978 | 12.9926 | 71669931.81 | 29399984.46 | 2023 | CENTERWAYS CONSTRUCTION AND DEVELOPMENT INC. | 7424 | 2023 | 2023-11-22 | 02/23/2023 | 42269947.35 | 0 | 2023-11-21 |  | 1
2023 | Region V | MASBATE | MILAGROS (MASBATE) | P00725891LZ | Construction of Flood Mitigation Structure | 123.5111 | 12.2157 | 57899968.79 | 57900000 | 2024 | HKP CONSTRUCTION AND SUPPLY / DSB CONSTRUCTION & SUPPLY, INC. (FORMERLY: DSB CO | 7425 | 2023 | 2024-04-06 | 08/09/2023 | 0 | 31.21 | 2024-04-05 |  | 1
2024 | Region VII | CEBU | TOLEDO CITY (CEBU) | P00820358VS | Construction of Flood Mitigation Structure | 123.6491 | 10.3925 | 77200000 | 77200000 | 2024 | JJ &J CONSTRUCTION & GENERAL SUPPLY | 7426 | 2024 | 2024-10-25 | 02/12/2024 | 0 | 0 | 2024-11-08 | 14
2023 | Region VII | CEBU | DAANBANTAYAN (CEBU) | P00721669VS | Construction of Flood Mitigation Structure | 124.0455 | 11.274 | 19600000 | 19600000 | 2023 | TCP BUILDERS | 7427 | 2023 | 2023-07-08 | 02/06/2023 | 0 | 0 | 2023-07-07 |  | 1
2022 | Region V | ALBAY | MALILIPOT (ALBAY) | P00630994LZ | Rehabilitation / Major Repair of Flood Control Structure | 123.7527 | 13.2928 | 95229997.38 | 52110000 | 2023 | RCDS CONSTRUCTION & SUPPLY, INC.(FOR RCDS CONST. | 7428 | 2022 | 2023-04-01 | 08/05/2022 | 43119997.38 | 0 | 2023-03-31 |  | 1
2023 | Region V | SORSOGON | BULAN (SORSOGON) | P00740449LZ | Construction of Flood Mitigation Structure | 123.9574 | 12.6596 | 106149972.9 | 102434887.6 | 2023 | WELEX CONSTRUCTION, INCORPORATED (FORMERLY WELEX C | 7429 | 2023 | 2023-09-30 | 05/25/2023 | 3715085.3 | 0 | 2024-03-05 | 157
2023 | Region VII | CEBU | CITY OF TALISAY (CEBU) | P00721882VS | Construction of Flood Mitigation Structure | 123.8221 | 10.2758 | 96500000 | 96500000 | 2024 | QM BUILDERS | 7430 | 2023 | 2024-03-05 | 05/04/2023 | 0 | 0 | 2024-03-04 |  | 1
2023 | Region V | CAMARINES SUR | OCAMPO (CAMARINES SUR) | P00725907LZ | Construction of Flood Mitigation Structure | 123.3989 | 13.5657 | 57771903.68 | 57194183 | 2023 | PHILWORKS CONSTRUCTION & SUPPLY | 7431 | 2023 | 2023-10-06 | 02/20/2023 | 577720.68 | 0 | 2023-10-05 |  | 1
2022 | Region V | ALBAY | SANTO DOMINGO (LIBOG) (ALBAY) | P00632699LZ | Construction of Flood Mitigation Structure | 123.5113 | 13.1329 | 57899996.25 | 59400000 | 2022 | HI-TONE CONSTRUCTION & DEVELOPMENT CORP. (FORMERLY | 7432 | 2022 | 2022-10-11 | 03/11/2022 | 0 | 1500003.75 | 2022-10-10 |  | 1
2022 | Region VII | CEBU | CEBU CITY (CAPITAL) (CEBU) | P00630654VS | Construction of Flood Mitigation Structure | 123.8984 | 10.4404 | 4950000 | 4934888 | 2022 | TEN TWENTY ALLIED DEVELOPERS | 7433 | 2022 | 2022-09-19 | 05/30/2022 | 15112 | 0 | 2022-09-29 | 10
2023 | Region VII | CEBU | CEBU CITY (CAPITAL) (CEBU) | P00721786VS | Construction of Flood Mitigation Structure | 123.8223 | 10.3605 | 86850000 | 86697376.14 | 2024 | A.S.T BUILDERS / KYLE CONSTRUCTION SERVICES | 7434 | 2023 | 2024-01-24 | 04/19/2023 | 152623.86 | 0 | 2024-01-25 | 1
2023 | Region VII | CEBU | MOALBOAL (CEBU) | P00721949VS | Construction of Drainage Structure | 123.4 | 9.9516 | 26458250.44 | 26458248.92 | 2023 | QM BUILDERS | 7435 | 2023 | 2023-11-24 | 03/06/2023 | 1.52 | 0 | 2023-11-23 |  | 1
2023 | Region V | ALBAY | CAMALIG (ALBAY) | P00726979LZ | Construction of Dike | 123.6497 | 13.1718 | 72373954.3 | 72373363.93 | 2023 | NEXT GENERATION CONSTRUCTION AND SUPPLY CORPORATION | 7436 | 2023 | 2023-11-23 | 05/17/2023 | 590.37 | 0 | 2023-11-22 |  | 1
2022 | Region V | ALBAY | RAPU-RAPU (ALBAY) | P00639387LZ | Construction of Flood Mitigation Structure | 124.0482 | 13.2277 | 86844853.25 | 86844393.96 | 2023 | SUNWEST, INC. (FORMERLY: SUNWEST CONSTRUCTION & DEVELOPMENT CORPORATION) | 7437 | 2022 | 2023-03-02 | 07/12/2022 | 459.29 | 0 | 2023-03-01 |  | 1
2024 | Region VII | CEBU | ASTURIAS (CEBU) | P00820400VS | Rehabilitation / Major Repair of Flood Control Structure | 123.7535 | 10.6289 | 19600000 | 19249374.01 | 2024 | VEN RAY CONSTRUCTION CORPORATION | 7438 | 2024 | 2024-07-12 | 02/02/2024 | 350625.99 | 0 | 2024-07-13 | 1
2022 | Region VII | CEBU | CONSOLACION (CEBU) | P00620025VS | Construction of Flood Mitigation Structure | 123.9587 | 10.3944 | 96500000 | 96500000 | 2022 | BNR CONSTRUCTION & DEVELOPMENT CORP. | 7439 | 2022 | 2022-10-24 | 02/24/2022 | 0 | 0 | 2022-10-23 |  | 1
2024 | Region V | CAMARINES SUR | BUHI (CAMARINES SUR) | P00821406LZ | Construction of Flood Mitigation Structure | 123.5115 | 13.396 | 135100000 | 135100000 | 2024 | G.C.I. CONSTRUCTION AND DEV'T. CORP. | 7440 | 2024 | 2024-09-20 | 02/21/2024 | 0 | 0 | 2025-02-07 | 140
2023 | Region X | MISAMIS OCCIDENTAL | ALORAN (MISAMIS OCCIDENTAL) | P00721378MN | Construction of Flood Mitigation Structure | 123.8226 | 8.4198 | 49000000 | 48999979.13 | 2023 | RITCHE-NATHALIE BUILDERS & GENERAL MERCHANDISE | 7441 | 2023 | 2023-10-31 | 02/27/2023 | 20.87 | 0 | 2023-08-24 |  | 68
2022 | Region VII | CEBU | ALCANTARA (CEBU) | P00633005VS | Construction of Revetment | 123.4007 | 9.9641 | 29399912.37 | 29399912.37 | 2022 | QM BUILDERS | 7442 | 2022 | 2022-09-18 | 03/23/2022 | 0 | 0 | 2022-09-17 |  | 1
2024 | Region V | ALBAY | CAMALIG (ALBAY) | P00821387LZ | Construction of Slope Protection Structure | 123.6509 | 13.1904 | 96498958.63 | 96498182.44 | 2024 | A3 CONSTRUCTION & SUPPLY | 7443 | 2024 | 2024-11-18 | 02/26/2024 | 776.19 | 0 | 2024-12-05 | 17
2024 | Region XII | SULTAN KUDARAT | KALAMANSIG (SULTAN KUDARAT) | P00833601MN | Construction of Flood Mitigation Structure | 124.0489 | 6.555 | 4950000 | 4941664.1 | 2024 | CS CONST. AND SUPPLY INC. (FORMERLY: CS CONSTRUCTION AND SUPPLY) | 7444 | 2024 | 2024-07-08 | 03/25/2024 | 8335.9 | 0 | 2024-06-21 |  | 17
2022 | Region V | ALBAY | LEGAZPI CITY (CAPITAL) (ALBAY) | P00639392LZ | Construction of Flood Mitigation Structure | 123.7542 | 13.204 | 97998410.04 | 96499920.56 | 2023 | INFRA BUILDERS AND SELLERS, PHILIPPINES | 7445 | 2022 | 2023-01-11 | 04/13/2022 | 1498489.48 | 0 | 2023-01-10 |  | 1
2022 | Region VII | CEBU | CONSOLACION (CEBU) | P00620024VS | Construction of Flood Mitigation Structure | 123.9601 | 10.389 | 77200000 | 77200000 | 2022 | QUIRANTE CONSTRUCTION CORPORATION (FORMERLY: QUIRANTE CONSTRUCTION) | 7446 | 2022 | 2022-12-08 | 02/24/2022 | 0 | 0 | 2022-12-07 |  | 1
2022 | Region V | ALBAY | OAS (ALBAY) | P00631361LZ | Construction of Flood Mitigation Structure | 123.5129 | 13.2453 | 98000000 | 48999374.49 | 2023 | RAMARPLUS INCORPORATED (FORMERLY RAMAR ENTERPRISES | 7447 | 2022 | 2023-03-31 | 08/01/2022 | 49000625.51 | 0 | 2023-05-11 | 41
2022 | Region V | ALBAY | CAMALIG (ALBAY) | P00631348LZ | Rehabilitation / Major Repair of Flood Control Structure | 123.6511 | 13.1904 | 24498430.13 | 24498153.5 | 2022 | SISBRO CONSTRUCTION CORPORATION (FORMERLY: SISBRO CONSTRUCTION & SUPPLY) | 7448 | 2022 | 2022-07-14 | 02/21/2022 | 276.63 | 0 | 2022-07-13 |  | 1
2023 | Region VII | CEBU | TUBURAN (CEBU) | P00721826VS | Construction of Flood Mitigation Structure | 123.8234 | 10.7064 | 43120000 | 43015488.45 | 2023 | VEN RAY CONSTRUCTION CORPORATION | 7449 | 2023 | 2023-08-29 | 02/02/2023 | 104511.55 | 0 | 2023-08-28 |  | 1
2022 | Region V | CAMARINES SUR | NABUA (CAMARINES SUR) | P00630988LZ | Construction of Flood Mitigation Structure | 123.4008 | 13.4108 | 67550000 | 67549910.38 | 2022 | RICHMAR CONSTRUCTION | 7450 | 2022 | 2022-10-25 | 03/22/2022 | 89.62 | 0 | 2022-12-29 | 65
2022 | Region VII | CEBU | CEBU CITY (CAPITAL) (CEBU) | P00630657VS | Construction of Drainage Structure | 123.8992 | 10.3009 | 4950000 | 4742460 | 2022 | PLANAC CONSTRUCTION | 7451 | 2022 | 2022-07-18 | 03/17/2022 | 207540 | 0 | 2022-07-17 |  | 1
2022 | Region V | SORSOGON | IROSIN (SORSOGON) | P00630972LZ | Construction of Flood Mitigation Structure | 124.0493 | 12.7036 | 77200000 | 77193935.96 | 2022 | CENTERWAYS CONSTRUCTION AND DEVELOPMENT INC. | 7452 | 2022 | 2022-12-31 | 03/24/2022 | 6064.04 | 0 | 2022-12-30 |  | 1
2023 | Region V | ALBAY | LEGAZPI CITY (CAPITAL) (ALBAY) | P00737386LZ | Construction of Dike | 123.7544 | 13.2085 | 67548497.04 | 67548108.72 | 2023 | INFRA BUILDERS AND SELLERS, PHILIPPINES | 7453 | 2023 | 2023-06-15 | 02/27/2023 | 388.32 | 0 | 2023-09-07 | 84
2022 | Region V | SORSOGON | CITY OF SORSOGON (CAPITAL) (SORSOGON) | P00620758LZ | Construction of Flood Mitigation Structure | 123.9608 | 12.9867 | 36451065.52 | 23118304.01 | 2022 | MUNTOPAR BUILDERS CORP. | 7454 | 2022 | 2022-11-26 | 03/11/2022 | 13332761.51 | 0 | 2022-11-25 |  | 1
2022 | Region V | ALBAY | CAMALIG (ALBAY) | P00620287LZ | Construction of Flood Mitigation Structure | 123.6514 | 13.1988 | 57898316.15 | 57898152.54 | 2022 | MUNTOPAR BUILDERS CORP. | 7455 | 2022 | 2022-09-29 | 03/04/2022 | 163.61 | 0 | 2022-09-28 |  | 1
2022 | Region VII | CEBU | TUBURAN (CEBU) | P00634052VS | Construction of Slope Protection Structure | 123.8249 | 10.7295 | 39200000 | 39146455 | 2023 | VEN RAY CONSTRUCTION CORPORATION | 7456 | 2022 | 2023-12-28 | 07/19/2022 | 53545 | 0 | 2024-03-11 | 74
2024 | Region VII | CEBU | ALCANTARA (CEBU) | P00820058VS | Construction of Flood Mitigation Structure | 123.401 | 9.9641 | 144745352.1 | 144745350.3 | 2024 | QM BUILDERS | 7457 | 2024 | 2024-09-16 | 02/16/2024 | 1.8 | 0 | 2025-01-09 | 115
2023 | Region V | SORSOGON | IROSIN (SORSOGON) | P00740450LZ | Construction of Flood Mitigation Structure | 124.0516 | 12.7027 | 106149680.2 | 106149680.2 | 2023 | WELEX CONSTRUCTION, INCORPORATED (FORMERLY WELEX C | 7458 | 2023 | 2023-08-31 | 05/25/2023 | 0 | 0 | 2024-03-05 | 187
2022 | Region V | SORSOGON | BULAN (SORSOGON) | P00631478LZ | Construction of Revetment | 123.9611 | 12.6847 | 49000000 | 49000000 | 2022 | CENTERWAYS CONSTRUCTION AND DEVELOPMENT INC. | 7459 | 2022 | 2022-11-12 | 03/14/2022 | 0 | 0 | 2022-11-11 |  | 1
2022 | Region V | ALBAY | LEGAZPI CITY (CAPITAL) (ALBAY) | P00639537LZ | Construction of Flood Mitigation Structure | 123.7546 | 13.2041 | 39198403.66 | 39197337.19 | 2022 | ALPHA RYDER CONSTRUCTION & SUPPLIES | 7460 | 2022 | 2022-09-20 | 04/11/2022 | 1066.47 | 0 | 2022-09-19 |  | 1
2022 | Region VII | CEBU | BARILI (CEBU) | P00620125VS | Construction of Flood Mitigation Structure | 123.5136 | 10.1139 | 39200000 | 39198712.68 | 2023 | QM BUILDERS / DOCAST CONSTRUCTION | 7461 | 2022 | 2023-05-04 | 08/24/2022 | 1287.32 | 0 | 2023-05-03 |  | 1
2022 | Region V | ALBAY | MALINAO (ALBAY) | P00631337LZ | Rehabilitation / Major Repair of Flood Control Structure | 123.6529 | 13.3378 | 88199992.73 | 44100000 | 2023 | WEARR ENTERPRISES & DEVELOPMENT CORP. | 7462 | 2022 | 2023-04-21 | 09/05/2022 | 44099992.73 | 0 | 2023-04-20 |  | 1
2022 | Region VII | CEBU | CEBU CITY (CAPITAL) (CEBU) | P00630652VS | Construction of Drainage Structure | 123.9006 | 10.2976 | 4950000 | 4941185.77 | 2022 | NEW GLOBALDEV CORPORATION | 7463 | 2022 | 2022-08-24 | 02/22/2022 | 8814.23 | 0 | 2022-08-23 |  | 1
2024 | Region VII | CEBU | CITY OF TALISAY (CEBU) | P00820320VS | Construction of Flood Mitigation Structure | 123.8252 | 10.2765 | 144750000 | 144750000 | 2025 | QM BUILDERS | 7464 | 2024 | 2025-01-10 | 02/20/2024 | 0 | 0 | 2025-01-09 |  | 1
2023 | Region XII | SULTAN KUDARAT | KALAMANSIG (SULTAN KUDARAT) | P00734414MN | Construction of Flood Mitigation Structure | 124.0523 | 6.5578 | 4950000 | 4950000 | 2023 | COFEJOK CONSTRUCTION AND SUPPLY CORPORATION (FORME | 7465 | 2023 | 2023-08-28 | 03/24/2023 | 0 | 0 | 2023-08-09 |  | 19
2023 | Region V | CAMARINES SUR | NABUA (CAMARINES SUR) | P00742208LZ | Construction of Flood Mitigation Structure | 123.4014 | 13.4088 | 98932788 | 98931423.45 | 2024 | LEGACY CONSTRUCTION CORPORATION (FORMERLY: LEGACY CONSTRUCTION) | 7466 | 2023 | 2024-02-08 | 04/20/2023 | 1364.55 | 0 | 2024-02-07 |  | 1
2023 | Region VII | CEBU | CONSOLACION (CEBU) | P00721944VS | Construction of Flood Mitigation Structure | 123.9612 | 10.3869 | 14700000 | 14650900 | 2023 | KYLE CONSTRUCTION SERVICES | 7467 | 2023 | 2023-05-26 | 03/08/2023 | 49100 | 0 | 2023-08-01 | 67
2023 | Region V | ALBAY | POLANGUI (ALBAY) | P00740468LZ | Construction of Flood Mitigation Structure | 123.5138 | 13.3282 | 144610000 | 72289030 | 2023 | RICHMAR CONSTRUCTION | 7468 | 2023 | 2023-12-15 | 05/25/2023 | 72320970 | 0 | 2024-03-18 | 94
2023 | Region V | ALBAY | CAMALIG (ALBAY) | P00740663LZ | Construction of Drainage Structure | 123.654 | 13.1802 | 48998424.78 | 48998443.23 | 2024 | FS CO BUILDERS AND SUPPLY | 7469 | 2023 | 2024-03-22 | 07/03/2023 | 0 | 18.45 | 2024-06-10 | 80
2024 | Region VII | CEBU | CITY OF TALISAY (CEBU) | P00820322VS | Construction of Flood Mitigation Structure | 123.8252 | 10.2764 | 144750000 | 144750000 | 2025 | QM BUILDERS | 7470 | 2024 | 2025-04-10 | 02/20/2024 | 0 | 0 | 2025-04-09 |  | 1
2022 | Region V | SORSOGON | MATNOG (SORSOGON) | P00620753LZ | Construction of Flood Mitigation Structure | 124.0578 | 12.6082 | 98000000 | 48999228.83 | 2023 | M.G. SALAZAR CONSTRUCTION CORP. (FOR. M.G. SALAZAR | 7471 | 2022 | 2023-03-21 | 02/18/2022 | 49000771.17 | 0 | 2023-03-05 |  | 16
2024 | Region V | CAMARINES SUR | NABUA (CAMARINES SUR) | P00820466LZ | Construction of Flood Mitigation Structure | 123.4014 | 13.4065 | 96500000 | 96500000 | 2024 | HI-TONE CONSTRUCTION & DEVELOPMENT CORP. (FORMERLY | 7472 | 2024 | 2024-12-11 | 02/21/2024 | 0 | 0 | 2024-12-10 |  | 1
2023 | Region V | ALBAY | POLANGUI (ALBAY) | P00740469LZ | Construction of Flood Mitigation Structure | 123.5139 | 13.328 | 144610000 | 72289030 | 2023 | RICHMAR CONSTRUCTION | 7473 | 2023 | 2023-12-15 | 05/25/2023 | 72320970 | 0 | 2024-03-18 | 94
2023 | Region VII | CEBU | MEDELLIN (CEBU) | P00721529VS | Construction of Flood Mitigation Structure | 123.9615 | 11.1255 | 63323300 | 63323300 | 2023 | GONZALODO ENTERPRISES / RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R | 7474 | 2023 | 2023-10-12 | 02/14/2023 | 0 | 0 | 2023-10-11 |  | 1
2022 | Region VII | CEBU | TOLEDO CITY (CEBU) | P00620122VS | Construction of Flood Mitigation Structure | 123.6542 | 10.4043 | 45080000 | 44272101.34 | 2022 | JJ &J CONSTRUCTION & GENERAL SUPPLY / PLD CONSTRUCTION AND DEVELOPMENT INC. (FORMERLY: PLD CONSTRUCTION) | 7475 | 2022 | 2022-12-01 | 04/04/2022 | 807898.66 | 0 | 2022-11-30 |  | 1
2022 | Region V | ALBAY | LEGAZPI CITY (CAPITAL) (ALBAY) | P00632950LZ | Construction of Drainage Structure | 123.7549 | 13.1955 | 48998402.13 | 48998381.6 | 2022 | ALPHA RYDER CONSTRUCTION & SUPPLIES | 7476 | 2022 | 2022-07-31 | 02/21/2022 | 20.53 | 0 | 2022-08-18 | 18
2023 | Region VII | CEBU | TOLEDO CITY (CEBU) | P00721827VS | Construction of Flood Mitigation Structure | 123.6543 | 10.4037 | 49000000 | 48999982.85 | 2023 | JJ &J CONSTRUCTION & GENERAL SUPPLY / PLD CONSTRUCTION AND DEVELOPMENT INC. (FORMERLY: PLD CONSTRUCTION) | 7477 | 2023 | 2023-12-13 | 03/21/2023 | 17.15 | 0 | 2023-12-12 |  | 1
2022 | Region VII | BOHOL | ANTEQUERA (BOHOL) | P00620113VS | Construction of Flood Mitigation Structure | 123.9007 | 9.7545 | 49000000 | 48912420.75 | 2023 | BNYU DEVELOPMENT CORPORATION (FORMERLY:BNYU ENTERPRISES & CONSTRUCTION) | 7478 | 2022 | 2023-09-30 | 09/22/2022 | 87579.25 | 0 | 2023-09-29 |  | 1
2024 | Region VII | CEBU | CITY OF TALISAY (CEBU) | P00820321VS | Construction of Flood Mitigation Structure | 123.8255 | 10.2769 | 144750000 | 144750000 | 2025 | QM BUILDERS | 7479 | 2024 | 2025-01-10 | 02/20/2024 | 0 | 0 | 2025-01-09 |  | 1
2023 | Region XII | SULTAN KUDARAT | KALAMANSIG (SULTAN KUDARAT) | P00721650MN | Construction of Flood Mitigation Structure | 124.0583 | 6.5321 | 96500000 | 96500000 | 2023 | AMP 723 CONSTRUCTION CORPORATION (FORMERLY: A.M.P. CONSTRUCTION) | 7480 | 2023 | 2023-11-17 | 03/27/2023 | 0 | 0 | 2024-05-17 | 182
2023 | Region VII | CEBU | MALABUYOC (CEBU) | P00721522VS | Construction of Revetment | 123.515 | 9.7759 | 96305217.84 | 96305129.41 | 2023 | QUIRANTE CONSTRUCTION CORPORATION (FORMERLY: QUIRANTE CONSTRUCTION) | 7481 | 2023 | 2023-09-26 | 02/08/2023 | 88.43 | 0 | 2023-12-18 | 83
2022 | Region V | ALBAY | MALILIPOT (ALBAY) | P00631322LZ | Construction of Flood Mitigation Structure | 123.7554 | 13.3066 | 44099984.92 | 44100000 | 2022 | WEARR ENTERPRISES & DEVELOPMENT CORP. | 7482 | 2022 | 2022-10-07 | 04/25/2022 | 0 | 15.08 | 2022-10-06 |  | 1
2022 | Region VII | CEBU | CEBU CITY (CAPITAL) (CEBU) | P00630651VS | Construction of Drainage Structure | 123.9019 | 10.3028 | 4950000 | 4930064.61 | 2022 | CMDV CONSTRUCTION | 7483 | 2022 | 2022-07-25 | 03/24/2022 | 19935.39 | 0 | 2022-07-24 |  | 1
2024 | Region VII | CEBU | CONSOLACION (CEBU) | P00820328VS | Construction of Flood Mitigation Structure | 123.9616 | 10.3958 | 135100000 | 135100000 | 2024 | GONZALODO ENTERPRISES / WTG CONSTRUCTION & DEVELOPMENT CORPORATION | 7484 | 2024 | 2024-06-05 | 02/16/2024 | 0 | 0 | 2024-12-29 | 207
2022 | Region V | CAMARINES SUR | IRIGA CITY (CAMARINES SUR) | P00631428LZ | Construction of Flood Mitigation Structure | 123.4015 | 13.4093 | 39200000 | 39189729.5 | 2022 | SISAM CONSTRUCTION & SUPPLIES | 7485 | 2022 | 2022-08-15 | 02/22/2022 | 10270.5 | 0 | 2022-08-27 | 12
2022 | Region V | SORSOGON | MATNOG (SORSOGON) | P00620751LZ | Construction of Flood Mitigation Structure | 124.0589 | 12.6075 | 98000000 | 48999966.52 | 2023 | M.G. SALAZAR CONSTRUCTION CORP. (FOR. M.G. SALAZAR | 7486 | 2022 | 2023-03-21 | 02/18/2022 | 49000033.48 | 0 | 2023-03-05 |  | 16
2022 | Region V | ALBAY | SANTO DOMINGO (LIBOG) (ALBAY) | P00639395LZ | Construction of Slope Protection Structure | 123.7556 | 13.24 | 95534999.73 | 95535000 | 2023 | SUNWEST, INC. (FORMERLY: SUNWEST CONSTRUCTION & DEVELOPMENT CORPORATION) | 7487 | 2022 | 2023-02-10 | 06/23/2022 | 0 | 0.27 | 2023-02-17 | 7
2024 | Region VII | CEBU | CITY OF TALISAY (CEBU) | P00820323VS | Construction of Flood Mitigation Structure | 123.8256 | 10.2767 | 144750000 | 144750000 | 2025 | QM BUILDERS | 7488 | 2024 | 2025-01-10 | 02/20/2024 | 0 | 0 | 2025-01-09 |  | 1
2022 | Region V | ALBAY | BACACAY (ALBAY) | P00639397LZ | Construction of Slope Protection Structure | 123.9023 | 13.2397 | 164048591.3 | 164048591.3 | 2023 | SUNWEST, INC. (FORMERLY: SUNWEST CONSTRUCTION & DEVELOPMENT CORPORATION) | 7489 | 2022 | 2023-07-14 | 07/18/2022 | 0 | 0 | 2023-07-13 |  | 1
2024 | Region VII | CEBU | PINAMUNGAJAN (CEBU) | P00820191VS | Construction of Flood Mitigation Structure | 123.6558 | 10.2724 | 14700000 | 14655082.09 | 2024 | VEN RAY CONSTRUCTION CORPORATION | 7490 | 2024 | 2024-09-06 | 02/02/2024 | 44917.91 | 0 | 2024-09-06 | 0
2022 | Region V | CAMARINES SUR | LAGONOY (CAMARINES SUR) | P00631422LZ | Construction of Flood Mitigation Structure | 123.5164 | 13.9191 | 49000000 | 49000000 | 2023 | E. GARCIA CONSTRUCTION CORP.(FOR. E. GARCIA CONST | 7491 | 2022 | 2023-08-22 | 03/17/2022 | 0 | 0 | 2023-08-22 | 0
2023 | Region V | CAMARINES SUR | IRIGA CITY (CAMARINES SUR) | P00742207LZ | Construction of Flood Mitigation Structure | 123.4016 | 13.4099 | 98966394 | 98956878.59 | 2024 | LEGACY CONSTRUCTION CORPORATION (FORMERLY: LEGACY CONSTRUCTION) | 7492 | 2023 | 2024-02-08 | 04/20/2023 | 9515.41 | 0 | 2024-02-07 |  | 1
2023 | Region V | MASBATE | PLACER (MASBATE) | P00726306LZ | Construction of Flood Mitigation Structure | 123.9625 | 11.9421 | 27366178.4 | 26818854.83 | 2023 | SQUARE N CONSTRUCTION & SUPPLY | 7493 | 2023 | 2023-12-09 | 04/28/2023 | 547323.57 | 0 | 2023-12-08 |  | 1
2023 | Region XII | SULTAN KUDARAT | LEBAK (SULTAN KUDARAT) | P00734415MN | Construction of Flood Mitigation Structure | 124.0599 | 6.6309 | 4950000 | 4356000 | 2023 | JV CONSTECH | 7494 | 2023 | 2023-08-01 | 03/24/2023 | 594000 | 0 | 2023-08-01 | 0
2023 | Region V | MASBATE | SAN FERNANDO (MASBATE) | P00725883LZ | Construction of Flood Mitigation Structure | 123.7558 | 12.4908 | 48249045.25 | 48249045.25 | 2024 | CENTERWAYS CONSTRUCTION AND DEVELOPMENT INC. | 7495 | 2023 | 2024-05-06 | 03/23/2023 | 0 | 0 | 2024-01-31 |  | 96
2024 | Region VII | CEBU | CITY OF TALISAY (CEBU) | P00821145VS | Construction of Flood Mitigation Structure | 123.8258 | 10.2805 | 57900000 | 57900000 | 2024 | QM BUILDERS | 7496 | 2024 | 2024-11-11 | 03/22/2024 | 0 | 0 | 2024-11-10 |  | 1
2022 | Region V | SORSOGON | BULAN (SORSOGON) | P00620334LZ | Rehabilitation / Major Repair of Flood Control Structure | 123.9025 | 12.6675 | 92640000 | 92639979.74 | 2023 | CENTERWAYS CONSTRUCTION AND DEVELOPMENT INC. | 7497 | 2022 | 2023-04-26 | 03/18/2022 | 20.26 | 0 | 2023-04-25 |  | 1
2023 | Region V | SORSOGON | IROSIN (SORSOGON) | P00742480LZ | Construction of Flood Mitigation Structure | 124.0613 | 12.7123 | 99000000 | 98963028.11 | 2023 | RMH CONSTRUCTION & SUPPLY / STEVEN CONSTRUCTION & SUPPLY | 7498 | 2023 | 2023-12-27 | 05/22/2023 | 36971.89 | 0 | 2024-02-08 | 43
2024 | Region V | CAMARINES SUR | SAN JOSE (CAMARINES SUR) | P00820473LZ | Construction of Flood Mitigation Structure | 123.5201 | 13.6875 | 96500000 | 93436357.49 | 2024 | PARTIDO CONSTRUCTION & SUPPLY | 7499 | 2024 | 2024-11-20 | 03/19/2024 | 3063642.51 | 0 | 2024-12-05 | 15
2023 | Region V | SORSOGON | CITY OF SORSOGON (CAPITAL) (SORSOGON) | P00726319LZ | Construction of Flood Mitigation Structure | 123.9034 | 12.9759 | 71669931.81 | 29399976.04 | 2023 | CENTERWAYS CONSTRUCTION AND DEVELOPMENT INC. | 7500 | 2023 | 2023-11-22 | 02/23/2023 | 42269955.77 | 0 | 2023-11-21 |  | 1
2023 | Region X | LANAO DEL SUR | MALABANG (LANAO DEL SUR) | P00721270MN | Construction of Flood Mitigation Structure | 124.0624 | 7.6135 | 48250000 | 47043280.19 | 2023 | M.M.A. ACHIEVER CONSTRUCTION & DEVELOPMENT CORP. | 7501 | 2023 | 2023-10-04 | 02/13/2023 | 1206719.81 | 0 | 2023-10-03 |  | 1
2023 | Region VII | CEBU | MOALBOAL (CEBU) | P00721950VS | Construction of Drainage Structure | 123.4018 | 9.9111 | 26458256 | 26457957.62 | 2024 | QM BUILDERS | 7502 | 2023 | 2024-03-16 | 06/27/2023 | 298.38 | 0 | 2024-03-15 |  | 1
2023 | Region VII | CEBU | MANDAUE CITY (CEBU) | P00721759VS | Construction of Flood Mitigation Structure | 123.9629 | 10.3406 | 96500000 | 96400000 | 2023 | QUIRANTE CONSTRUCTION CORPORATION (FORMERLY: QUIRANTE CONSTRUCTION) / ZLREJ TRADING AND CONSTRUCTION CORPORATION | 7503 | 2023 | 2023-10-05 | 05/12/2023 | 100000 | 0 | 2024-03-12 | 159
2022 | Region VII | CEBU | CITY OF TALISAY (CEBU) | P00620120VS | Construction of Flood Mitigation Structure | 123.8273 | 10.2705 | 49000000 | 49000000 | 2022 | W.GO CONSTRUCTION AND SUPPLY / WTG CONSTRUCTION & DEVELOPMENT CORPORATION | 7504 | 2022 | 2022-09-16 | 02/14/2022 | 0 | 0 | 2022-09-17 | 1
2024 | Region X | MISAMIS OCCIDENTAL | TANGUB CITY (MISAMIS OCCIDENTAL) | P00835874MN | Rehabilitation / Major Repair of Flood Control Structure | 123.7564 | 8.0802 | 4900000 | 4752999.94 | 2025 | ABIB BUILDERS ENTERPRISE | 7505 | 2024 | 2025-03-28 | 06/21/2024 | 147000.06 | 0 | 2024-12-25 |  | 93
2023 | Region V | CAMARINES SUR | SAN JOSE (CAMARINES SUR) | P00727382LZ | Construction of Flood Mitigation Structure | 123.5202 | 13.6828 | 48518113 | 48996903.75 | 2023 | PARTIDO CONSTRUCTION & SUPPLY | 7506 | 2023 | 2023-12-05 | 06/15/2023 | 0 | 478790.75 | 2024-01-16 | 42
2022 | Region VI | NEGROS OCCIDENTAL | SAN CARLOS CITY (NEGROS OCCIDENTAL) | P00620007VS | Construction of Flood Mitigation Structure | 123.402 | 10.48 | 48250000 | 48249993.45 | 2022 | JAIME B. CHING ENTERPRISES | 7507 | 2022 | 2022-10-11 | 03/02/2022 | 6.55 | 0 | 2022-10-10 |  | 1
2022 | Region V | ALBAY | MALINAO (ALBAY) | P00631339LZ | Rehabilitation / Major Repair of Flood Control Structure | 123.6566 | 13.3508 | 47039957.04 | 47040000 | 2023 | WEARR ENTERPRISES & DEVELOPMENT CORP. | 7508 | 2022 | 2023-01-20 | 08/05/2022 | 0 | 42.96 | 2023-01-19 |  | 1
2022 | Region X | LANAO DEL SUR | MALABANG (LANAO DEL SUR) | P00620039MN | Construction of Flood Mitigation Structure | 124.0626 | 7.6102 | 77200000 | 75655911.8 | 2022 | M.M.A. ACHIEVER CONSTRUCTION & DEVELOPMENT CORP. / RENREN TRADING AND CONSTRUCTION SERVICES | 7509 | 2022 | 2022-11-30 | 03/21/2022 | 1544088.2 | 0 | 2022-11-29 |  | 1
2023 | Region V | MASBATE | MILAGROS (MASBATE) | P00725890LZ | Construction of Flood Mitigation Structure | 123.5205 | 12.2144 | 57899970.85 | 57900000 | 2024 | SPRING STAR CONSTRUCTION AND SUPPLY | 7510 | 2023 | 2024-04-06 | 08/09/2023 | 0 | 29.15 | 2024-04-05 |  | 1
2023 | Region V | CAMARINES SUR | OCAMPO (CAMARINES SUR) | P00725906LZ | Construction of Flood Mitigation Structure | 123.4023 | 13.5601 | 57673534.38 | 57067962 | 2023 | CENTERWAYS CONSTRUCTION AND DEVELOPMENT INC. | 7511 | 2023 | 2023-09-20 | 02/20/2023 | 605572.38 | 0 | 2023-09-19 |  | 1
2021 | Region V | ALBAY |  | P00561583LZ | Construction of Flood Mitigation Structure | 123.6573 | 13.342 | 29699985.6 | 9900000 | 2022 | JORMAND CONSTRUCTION & SUPPLY | 7512 | 2021 | 2022-09-15 | 04/19/2022 | 19799985.6 | 0 | 2022-09-14 |  | 1
2022 | Region X | LANAO DEL NORTE | MAIGO (LANAO DEL NORTE) | P00620143MN | Construction of Slope Protection Structure | 123.9633 | 8.1661 | 49000000 | 49000000 | 2022 | LANAO BUILDER AND ENTERPRISES | 7513 | 2022 | 2022-10-12 | 03/18/2022 | 0 | 0 | 2022-10-15 | 3
2024 | Region V | ALBAY | LEGAZPI CITY (CAPITAL) (ALBAY) | P00844582LZ | Construction of Flood Mitigation Structure | 123.7569 | 13.2124 | 96498889.05 | 96498856.25 | 2024 | INFRA BUILDERS AND SELLERS, PHILIPPINES | 7514 | 2024 | 2024-09-22 | 04/12/2024 | 32.8 | 0 | 2025-03-10 | 169
2022 | Region VII | CEBU | CITY OF TALISAY (CEBU) | P00632991VS | Construction of Flood Mitigation Structure | 123.8286 | 10.2686 | 135100000 | 135100000 | 2022 | QUIRANTE CONSTRUCTION CORPORATION (FORMERLY: QUIRANTE CONSTRUCTION) | 7515 | 2022 | 2022-12-15 | 04/18/2022 | 0 | 0 | 2023-05-15 | 151
2022 | Region VII | CEBU | TUBURAN (CEBU) | P00630224VS | Construction of Flood Mitigation Structure | 123.832 | 10.6359 | 49000000 | 48985440.67 | 2023 | VEN RAY CONSTRUCTION CORPORATION | 7516 | 2022 | 2023-03-03 | 06/02/2022 | 14559.33 | 0 | 2023-03-02 |  | 1
2023 | Region VII | CEBU | CEBU CITY (CAPITAL) (CEBU) | P00721778VS | Construction of Flood Mitigation Structure | 123.9034 | 10.3041 | 57200000 | 57124194.51 | 2023 | VSP STRUCTURE VENTURES CORP. (FORMERLY: VIRLO CONSTRUCTION) | 7517 | 2023 | 2023-11-20 | 03/20/2023 | 75805.49 | 0 | 2023-11-19 |  | 1
2023 | Region VII | CEBU | LAPU-LAPU CITY (OPON) (CEBU) | P00733740VS | Construction of Flood Mitigation Structure | 124.0627 | 10.2635 | 17820000 | 17752004 | 2023 | FLORIANE CONSTRUCTION CORPORATION (FORMERLY: FLORIANE CONSTRUCTION & SUPPLY) | 7518 | 2023 | 2023-09-21 | 05/11/2023 | 67996 | 0 | 2023-10-19 | 28
2023 | Region V | CAMARINES SUR | SAN JOSE (CAMARINES SUR) | P00740682LZ | Construction of Flood Mitigation Structure | 123.5208 | 13.6768 | 48518100 | 48518100 | 2023 | ALRO CONSTRUCTION & DEVELOPMENT CORP. | 7519 | 2023 | 2023-11-17 | 03/30/2023 | 0 | 0 | 2023-11-19 | 2
2023 | Region V | CAMARINES SUR | OCAMPO (CAMARINES SUR) | P00726984LZ | Construction of Flood Mitigation Structure | 123.4025 | 13.5602 | 57821156.98 | 57228490 | 2023 | CENTERWAYS CONSTRUCTION AND DEVELOPMENT INC. | 7520 | 2023 | 2023-10-20 | 03/22/2023 | 592666.98 | 0 | 2023-10-19 |  | 1
2022 | Region VII | CEBU | MEDELLIN (CEBU) | P00620041VS | Construction of Flood Mitigation Structure | 123.9638 | 11.1256 | 57735950 | 57735950 | 2022 | GONZALODO ENTERPRISES / RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R | 7521 | 2022 | 2022-11-14 | 03/06/2022 | 0 | 0 | 2022-11-13 |  | 1
2024 | Region VII | CEBU | SAN REMIGIO (CEBU) | P00820185VS | Construction of Flood Mitigation Structure | 123.9037 | 10.9264 | 29400000 | 29400000 | 2024 | WTG CONSTRUCTION & DEVELOPMENT CORPORATION | 7522 | 2024 | 2024-07-11 | 02/13/2024 | 0 | 0 | 2024-07-10 |  | 1
2022 | Region V | ALBAY | MALILIPOT (ALBAY) | P00631327LZ | Construction of Flood Mitigation Structure | 123.7569 | 13.3005 | 44099919.19 | 44100000 | 2023 | RCDS CONSTRUCTION & SUPPLY, INC.(FOR RCDS CONST. | 7523 | 2022 | 2023-01-06 | 07/25/2022 | 0 | 80.81 | 2023-01-05 |  | 1
2023 | Region VII | CEBU | CITY OF TALISAY (CEBU) | P00721762VS | Construction of Flood Mitigation Structure | 123.8344 | 10.246 | 96500000 | 96484888 | 2023 | QUIRANTE CONSTRUCTION CORPORATION (FORMERLY: QUIRANTE CONSTRUCTION) | 7524 | 2023 | 2023-09-11 | 03/06/2023 | 15112 | 0 | 2024-01-05 | 116
2021 | Region VII | BOHOL |  | P00521779VS | Construction of Flood Mitigation Structure | 124.0687 | 10.0288 | 40158440 | 38703951.53 | 2022 | BNYU DEVELOPMENT CORPORATION (FORMERLY:BNYU ENTERPRISES & CONSTRUCTION) | 7525 | 2021 | 2022-11-30 | 04/15/2021 | 1454488.47 | 0 | 2021-12-25 |  | 340
2022 | Region V | MASBATE | MILAGROS (MASBATE) | P00620280LZ | Construction of Flood Mitigation Structure | 123.5212 | 12.2143 | 96499953.61 | 96500000 | 2023 | HGG BUILDERS & SUPPLY | 7526 | 2022 | 2023-07-30 | 03/30/2022 | 0 | 46.39 | 2023-07-29 |  | 1
2022 | Region VII | CEBU | ALCANTARA (CEBU) | P00620447VS | Construction of Flood Mitigation Structure | 123.4027 | 9.9697 | 96499953.35 | 96499953.35 | 2022 | QM BUILDERS | 7527 | 2022 | 2022-12-16 | 03/24/2022 | 0 | 0 | 2023-01-23 | 38
2022 | Region V | ALBAY | MALINAO (ALBAY) | P00630997LZ | Rehabilitation / Major Repair of Flood Control Structure | 123.6577 | 13.3459 | 48249198.58 | 48250000 | 2022 | MAKAPA CORPORATION | 7528 | 2022 | 2022-09-04 | 03/18/2022 | 0 | 801.42 | 2022-09-03 |  | 1
2022 | Region V | SORSOGON | IROSIN (SORSOGON) | P00620333LZ | Rehabilitation / Major Repair of Flood Control Structure | 123.9638 | 12.7297 | 96500000 | 95380291.78 | 2023 | STEVEN CONSTRUCTION & SUPPLY | 7529 | 2022 | 2023-04-16 | 02/15/2022 | 1119708.22 | 0 | 2023-04-15 |  | 1
2022 | Region V | MASBATE | SAN FERNANDO (MASBATE) | P00631462LZ | Construction of Flood Mitigation Structure | 123.7572 | 12.4919 | 49000000 | 46549610.06 | 2022 | SISBRO CONSTRUCTION CORPORATION (FORMERLY: SISBRO CONSTRUCTION & SUPPLY) / 3RB CONSTRUCTION & SUPPLY | 7530 | 2022 | 2022-07-25 | 03/10/2022 | 2450389.94 | 0 | 2022-11-11 | 109
2022 | Region VII | CEBU | CITY OF TALISAY (CEBU) | P00620030VS | Construction of Flood Mitigation Structure | 123.8345 | 10.246 | 96500000 | 96500000 | 2022 | QUIRANTE CONSTRUCTION CORPORATION (FORMERLY: QUIRANTE CONSTRUCTION) | 7531 | 2022 | 2022-12-19 | 02/16/2022 | 0 | 0 | 2022-12-18 |  | 1
2023 | Region V | ALBAY | MALINAO (ALBAY) | P00740656LZ | Construction of Flood Mitigation Structure | 123.4039 | 13.22 | 95059998.36 | 47040000 | 2023 | STEVEN CONSTRUCTION & SUPPLY | 7532 | 2023 | 2023-10-27 | 05/09/2023 | 48019998.36 | 0 | 2024-01-01 | 66
2022 | Region V | MASBATE | MILAGROS (MASBATE) | P00620295LZ | Construction of Flood Mitigation Structure | 123.6578 | 12.3386 | 96499920.1 | 96500000 | 2023 | YAKAL CONSTRUCTION | 7533 | 2022 | 2023-04-27 | 02/16/2022 | 0 | 79.9 | 2023-04-26 |  | 1
2022 | Region VII | CEBU | CEBU CITY (CAPITAL) (CEBU) | P00620433VS | Construction of Flood Mitigation Structure | 123.9038 | 10.3018 | 49000000 | 49000000 | 2022 | WTG CONSTRUCTION & DEVELOPMENT CORPORATION | 7534 | 2022 | 2022-12-24 | 03/24/2022 | 0 | 0 | 2022-12-23 |  | 1
2023 | Region V | SORSOGON | MATNOG (SORSOGON) | P00726318LZ | Construction of Flood Mitigation Structure | 124.0746 | 12.5409 | 68600000 | 28317826.74 | 2023 | AREMAR CONSTRUCTION CORPORATION | 7535 | 2023 | 2023-11-22 | 05/15/2023 | 40282173.26 | 0 | 2023-12-27 | 35
2022 | Region V | SORSOGON | IROSIN (SORSOGON) | P00631474LZ | Construction of Flood Mitigation Structure | 123.9644 | 12.73 | 49000000 | 47363531.26 | 2022 | STEVEN CONSTRUCTION & SUPPLY | 7536 | 2022 | 2022-09-02 | 02/14/2022 | 1636468.74 | 0 | 2022-09-01 |  | 1
2023 | Region V | MASBATE | SAN FERNANDO (MASBATE) | P00725882LZ | Construction of Flood Mitigation Structure | 123.7574 | 12.4899 | 48249363.78 | 48249363.78 | 2024 | CENTERWAYS CONSTRUCTION AND DEVELOPMENT INC. | 7537 | 2023 | 2024-02-02 | 03/24/2023 | 0 | 0 | 2024-02-01 |  | 1
2022 | Region V | CAMARINES SUR | SAGÃ‘AY (CAMARINES SUR) | P00631423LZ | Construction of Flood Mitigation Structure | 123.5222 | 13.5989 | 29400000 | 29400000 | 2022 | STEVEN CONSTRUCTION & SUPPLY | 7538 | 2022 | 2022-10-07 | 03/10/2022 | 0 | 0 | 2022-10-09 | 2
2023 | Region VII | CEBU | ALCANTARA (CEBU) | P00721945VS | Construction of Revetment | 123.4047 | 9.9619 | 48606241.83 | 48605990.17 | 2023 | QM BUILDERS | 7539 | 2023 | 2023-08-17 | 03/06/2023 | 251.66 | 0 | 2023-10-09 | 53
2024 | Region VII | BOHOL | TUBIGON (BOHOL) | P00820044VS | Construction of Flood Mitigation Structure | 123.9657 | 9.951 | 70022330 | 69866876.96 | 2024 | BNYU DEVELOPMENT CORPORATION (FORMERLY:BNYU ENTERPRISES & CONSTRUCTION) | 7540 | 2024 | 2024-11-05 | 04/11/2024 | 155453.04 | 0 | 2024-12-18 | 43
2022 | Region V | SORSOGON | CITY OF SORSOGON (CAPITAL) (SORSOGON) | P00631485LZ | Rehabilitation / Major Repair of Flood Control Structure | 123.9039 | 12.9785 | 58899904.98 | 19597043.51 | 2022 | CENTERWAYS CONSTRUCTION AND DEVELOPMENT INC. | 7541 | 2022 | 2022-09-12 | 03/17/2022 | 39302861.47 | 0 | 2022-09-11 |  | 1
2022 | Region V | ALBAY | MALINAO (ALBAY) | P00631338LZ | Rehabilitation / Major Repair of Flood Control Structure | 123.6586 | 13.3403 | 88199992.73 | 44100000 | 2023 | WEARR ENTERPRISES & DEVELOPMENT CORP. | 7542 | 2022 | 2023-04-21 | 09/05/2022 | 44099992.73 | 0 | 2023-04-20 |  | 1
2023 | Region X | LANAO DEL SUR | PUALAS (LANAO DEL SUR) | P00735054MN | Construction of Flood Mitigation Structure | 124.0809 | 7.8116 | 49500000 | 48763650.33 | 2024 | AL HUSSEIN CONSTRUCTION | 7543 | 2023 | 2024-03-14 | 05/29/2023 | 736349.67 | 0 | 2023-10-17 |  | 149
2024 | Region VII | CEBU | ASTURIAS (CEBU) | P00820346VS | Construction of Flood Mitigation Structure | 123.7584 | 10.6296 | 96500000 | 96341651.25 | 2024 | VEN RAY CONSTRUCTION CORPORATION | 7544 | 2024 | 2024-11-20 | 02/12/2024 | 158348.75 | 0 | 2024-11-19 |  | 1
2022 | Region X | LANAO DEL NORTE | TUBOD (CAPITAL) (LANAO DEL NORTE) | P00634134MN | Construction of Slope Protection Structure | 123.8346 | 8.052 | 14850000 | 8696543.7 | 2022 | INSTA BUILDERS & SUPPLIES CORP | 7545 | 2022 | 2022-08-20 | 03/24/2022 | 6153456.3 | 0 | 2022-08-19 |  | 1
2023 | Region V | CAMARINES SUR | BUHI (CAMARINES SUR) | P00736111LZ | Construction of Flood Mitigation Structure | 123.5224 | 13.4197 | 77155504 | 77155504 | 2024 | SUNWEST, INC. (FORMERLY: SUNWEST CONSTRUCTION & DEVELOPMENT CORPORATION) | 7546 | 2023 | 2024-01-02 | 02/16/2023 | 0 | 0 | 2024-01-01 |  | 1
2023 | Region V | CAMARINES SUR | PILI (CAPITAL) (CAMARINES SUR) | P00726964LZ | Construction of Revetment | 123.4053 | 13.5583 | 96204617.75 | 95114888.2 | 2024 | ELKANKONSTRAK DEVELOPMENT CORPORATION | 7547 | 2023 | 2024-02-18 | 05/09/2023 | 1089729.55 | 0 | 2024-02-17 |  | 1
2022 | Region VII | BOHOL | MARIBOJOC (BOHOL) | P00620112VS | Construction of Flood Mitigation Structure | 123.9039 | 9.7483 | 42347760 | 42347760 | 2023 | HERBERT MALMIS GENERAL MERCHANDISING & CONTRACTOR | 7548 | 2022 | 2023-03-07 | 06/14/2022 | 0 | 0 | 2023-03-06 |  | 1
2022 | Region V | SORSOGON | MATNOG (SORSOGON) | P00630968LZ | Construction of Flood Mitigation Structure | 124.0826 | 12.5814 | 67550000 | 65526866.97 | 2023 | CENTERWAYS CONSTRUCTION AND DEVELOPMENT INC. | 7549 | 2022 | 2023-05-09 | 05/27/2022 | 2023133.03 | 0 | 2023-05-08 |  | 1
2022 | Region V | ALBAY | MALILIPOT (ALBAY) | P00630959LZ | Construction of Flood Mitigation Structure | 123.7586 | 13.3187 | 57899994.48 | 57900000 | 2022 | 3DIAMONDS CONSTRUCTION CORPORATION | 7550 | 2022 | 2022-10-26 | 04/25/2022 | 0 | 5.52 | 2022-10-25 |  | 1
2023 | Region V | CAMARINES SUR | OCAMPO (CAMARINES SUR) | P00727219LZ | Construction of Flood Mitigation Structure | 123.4053 | 13.5583 | 48999995.42 | 48463641.53 | 2024 | FP5 CONSTRUCTION & DEVELOPMENT CORPORATION (FORMERLY: JS & V ENTERPRISES GENERAL CONTRACTOR, INC.) / PHILWORKS CONSTRUCTION & SUPPLY | 7551 | 2023 | 2024-07-04 | 05/26/2023 | 536353.89 | 0 | 2024-07-03 |  | 1
2022 | Region VII | CEBU | TUBURAN (CEBU) | P00634037VS | Construction of Flood Mitigation Structure | 123.8365 | 10.7038 | 49000000 | 48696738.3 | 2023 | VEN RAY CONSTRUCTION CORPORATION | 7552 | 2022 | 2023-11-03 | 06/29/2022 | 303261.7 | 0 | 2023-06-12 |  | 144
2024 | Region VII | CEBU | CONSOLACION (CEBU) | P00834655VS | Construction of Flood Mitigation Structure | 123.9677 | 10.3691 | 49000000 | 48970000 | 2024 | GONZALODO ENTERPRISES | 7553 | 2024 | 2024-06-19 | 03/15/2024 | 30000 | 0 | 2024-10-10 | 113
2022 | Region VII | BOHOL | MARIBOJOC (BOHOL) | P00620114VS | Construction of Flood Mitigation Structure | 123.9039 | 9.7444 | 29400000 | 29400000 | 2023 | D' 5J CONSTRUCTION & SUPPLY | 7554 | 2022 | 2023-02-17 | 05/25/2022 | 0 | 0 | 2023-02-16 |  | 1
2023 | Region VII | CEBU | TOLEDO CITY (CEBU) | P00733738VS | Construction of Flood Mitigation Structure | 123.6594 | 10.4094 | 4950000 | 4938269 | 2023 | YBK CONSTRUCTION | 7555 | 2023 | 2023-09-15 | 07/03/2023 | 11731 | 0 | 2023-09-14 |  | 1
2023 | Region V | SORSOGON | MATNOG (SORSOGON) | P00742482LZ | Construction of Flood Mitigation Structure | 124.0836 | 12.5474 | 4950000 | 4753294.14 | 2023 | KYLA CONSTRUCTION SUPPLY | 7556 | 2023 | 2023-07-19 | 05/15/2023 | 196705.86 | 0 | 2023-07-18 |  | 1
2023 | Region V | ALBAY | POLANGUI (ALBAY) | P00740678LZ | Construction of Flood Mitigation Structure | 123.5224 | 13.3405 | 97860000 | 48930000 | 2023 | RICHMAR CONSTRUCTION | 7557 | 2023 | 2023-12-27 | 06/01/2023 | 48930000 | 0 | 2024-03-10 | 74
2023 | Region V | SORSOGON | CASTILLA (SORSOGON) | P00727227LZ | Construction of Flood Mitigation Structure | 123.7592 | 12.8614 | 56939964.51 | 19599999.83 | 2023 | CENTERWAYS CONSTRUCTION AND DEVELOPMENT INC. / CHEEREL CONSTRUCTION & SUPPLY | 7558 | 2023 | 2023-11-17 | 03/27/2023 | 37339964.68 | 0 | 2023-11-18 | 1
2022 | Region VII | CEBU | TUBURAN (CEBU) | P00634036VS | Construction of Flood Mitigation Structure | 123.8368 | 10.7039 | 49000000 | 48998099.5 | 2023 | HELM CONSTRUCTION & SUPPLIES | 7559 | 2022 | 2023-06-01 | 06/02/2022 | 1900.5 | 0 | 2023-05-31 |  | 1
2023 | Region V | SORSOGON | CITY OF SORSOGON (CAPITAL) (SORSOGON) | P00725897LZ | Construction of Flood Mitigation Structure | 123.9677 | 13.0915 | 96499985.49 | 93086138.67 | 2024 | CENTERWAYS CONSTRUCTION AND DEVELOPMENT INC. / CHEEREL CONSTRUCTION & SUPPLY | 7560 | 2023 | 2024-03-22 | 05/12/2023 | 3413846.82 | 0 | 2024-03-21 |  | 1
2023 | Region V | ALBAY | MANITO (ALBAY) | P00740477LZ | Construction of Dike | 123.9048 | 13.098 | 72197651.67 | 72197542.53 | 2023 | HI-TONE CONSTRUCTION & DEVELOPMENT CORP. (FORMERLY | 7561 | 2023 | 2023-11-12 | 05/17/2023 | 109.14 | 0 | 2023-11-11 |  | 1
2022 | Region VII | CEBU | MEDELLIN (CEBU) | P00620022VS | Construction of Flood Mitigation Structure | 123.9678 | 11.1485 | 57900000 | 57900000 | 2022 | GONZALODO ENTERPRISES | 7562 | 2022 | 2022-12-14 | 02/21/2022 | 0 | 0 | 2022-12-13 |  | 1
2023 | Region XII | SULTAN KUDARAT | KALAMANSIG (SULTAN KUDARAT) | P00721317MN | Construction of Flood Mitigation Structure | 124.0848 | 6.5503 | 96500000 | 96499839.71 | 2023 | MUST ENTERPRISES / ALBANOR CONSTRUCTION | 7563 | 2023 | 2023-11-17 | 02/23/2023 | 160.29 | 0 | 2023-12-02 | 15
2022 | Region V | MASBATE | AROROY (MASBATE) | P00620743LZ | Rehabilitation / Major Repair of Flood Control Structure | 123.4072 | 12.3993 | 34192148.92 | 34188561.03 | 2022 | A3 CONSTRUCTION & SUPPLY | 7564 | 2022 | 2022-09-15 | 02/11/2022 | 3587.89 | 0 | 2022-10-02 | 17
2023 | Region V | ALBAY | CITY OF LIGAO (ALBAY) | P00726627LZ | Construction of Flood Mitigation Structure | 123.5245 | 13.2348 | 125406649 | 125406649 | 2023 | MAKAPA CORPORATION | 7565 | 2023 | 2023-11-16 | 03/30/2023 | 0 | 0 | 2024-01-16 | 61
2022 | Region V | MASBATE | SAN FERNANDO (MASBATE) | P00631461LZ | Construction of Flood Mitigation Structure | 123.7603 | 12.4889 | 49000000 | 46549010.81 | 2022 | SISBRO CONSTRUCTION CORPORATION (FORMERLY: SISBRO CONSTRUCTION & SUPPLY) / 3RB CONSTRUCTION & SUPPLY | 7566 | 2022 | 2022-08-09 | 03/10/2022 | 2450989.19 | 0 | 2022-11-11 | 94
2023 | Region V | SORSOGON | MAGALLANES (SORSOGON) | P00742486LZ | Construction of Flood Mitigation Structure | 123.837 | 12.8231 | 56939964.51 | 4949998.43 | 2023 | CENTERWAYS CONSTRUCTION AND DEVELOPMENT INC. / CHEEREL CONSTRUCTION & SUPPLY | 7567 | 2023 | 2023-11-17 | 03/27/2023 | 51989966.08 | 0 | 2023-11-18 | 1
2023 | Region V | CAMARINES SUR | SAN JOSE (CAMARINES SUR) | P00740445LZ | Construction of Flood Mitigation Structure | 123.5252 | 13.5939 | 66875340 | 66875340 | 2024 | ALRO CONSTRUCTION & DEVELOPMENT CORP. | 7568 | 2023 | 2024-03-05 | 05/15/2023 | 0 | 0 | 2024-03-05 | 0
2023 | Region VII | CEBU | CEBU CITY (CAPITAL) (CEBU) | P00732027VS | Construction of Flood Mitigation Structure | 123.9054 | 10.3046 | 4950000 | 4935000 | 2024 | CELJEM CONSTRUCTION & DEVELOPMENT CORP. | 7569 | 2023 | 2024-02-22 | 08/23/2023 | 15000 | 0 | 2024-02-21 |  | 1
2023 | Region V | ALBAY | MALINAO (ALBAY) | P00727328LZ | Construction of Flood Mitigation Structure | 123.6608 | 13.3539 | 101324236 | 101324139.6 | 2024 | MAKAPA CORPORATION | 7570 | 2023 | 2024-02-27 | 03/30/2023 | 96.4 | 0 | 2024-02-26 |  | 1
2024 | Region VII | BOHOL | TUBIGON (BOHOL) | P00832221VS | Construction of Flood Mitigation Structure | 123.9682 | 9.9459 | 144750000 | 144312978.9 | 2025 | SILVERWOLVES CONSTRUCTION CORPORATION | 7571 | 2024 | 2025-02-22 | 04/11/2024 | 437021.1 | 0 | 2025-02-21 |  | 1
2023 | Region V | SORSOGON | MATNOG (SORSOGON) | P00742481LZ | Construction of Flood Mitigation Structure | 124.0849 | 12.5859 | 11880000 | 11523308.3 | 2023 | CARMIG CONSTRUCTION & SUPPLY | 7572 | 2023 | 2023-10-06 | 06/09/2023 | 356691.7 | 0 | 2023-10-05 |  | 1
2024 | Region V | ALBAY | LIBON (ALBAY) | P00823602LZ | Construction of Flood Mitigation Structure | 123.4078 | 13.3191 | 144750000 | 144750000 | 2025 | RAMARPLUS INCORPORATED (FORMERLY RAMAR ENTERPRISES | 7573 | 2024 | 2025-04-05 | 06/10/2024 | 0 | 0 | 2025-04-04 |  | 1
2022 | Region V | SORSOGON | GUBAT (SORSOGON) | P00620755LZ | Construction of Flood Mitigation Structure | 124.0863 | 12.8725 | 98000000 | 47205646.64 | 2022 | C.T. LEONCIO CONSTRUCTION & TRADING | 7574 | 2022 | 2022-10-14 | 02/14/2022 | 50794353.36 | 0 | 2022-10-13 |  | 1
2023 | Region VII | CEBU | TOLEDO CITY (CEBU) | P00721821VS | Rehabilitation / Major Repair of Flood Control Structure | 123.6612 | 10.3831 | 19600000 | 19599992.8 | 2023 | JJ &J CONSTRUCTION & GENERAL SUPPLY | 7575 | 2023 | 2023-09-28 | 03/02/2023 | 7.2 | 0 | 2023-09-27 |  | 1
2021 | Region V | ALBAY |  | P00561193LZ | Construction of Flood Mitigation Structure | 123.8376 | 13.2645 | 24619763.98 | 11880000 | 2022 | DSB CONSTRUCTION & SUPPLY, INC. (FORMERLY: DSB CO | 7576 | 2021 | 2022-09-17 | 04/26/2022 | 12739763.98 | 0 | 2022-09-16 |  | 1
2024 | Region VII | CEBU | CITY OF NAGA (CEBU) | P00821150VS | Construction of Flood Mitigation Structure | 123.7604 | 10.262 | 54364240 | 54163972.77 | 2024 | LCTING CONSTRUCTION AND DEVELOPMENT CORPORATION (FORMERLY: L.C. TING CONSTRUCTION) | 7577 | 2024 | 2024-10-07 | 02/23/2024 | 200267.23 | 0 | 2024-10-06 |  | 1
2023 | Region V | ALBAY | POLANGUI (ALBAY) | P00740679LZ | Construction of Flood Mitigation Structure | 123.5254 | 13.3223 | 97860000 | 48930000 | 2023 | RICHMAR CONSTRUCTION | 7578 | 2023 | 2023-12-27 | 06/01/2023 | 48930000 | 0 | 2024-03-10 | 74
2024 | Region X | MISAMIS OCCIDENTAL | JIMENEZ (MISAMIS OCCIDENTAL) | P00820155MN | Construction of Flood Mitigation Structure | 123.8377 | 8.3282 | 9800000 | 9799878.8 | 2024 | SGM CONSTRUCTION | 7579 | 2024 | 2024-11-04 | 03/07/2024 | 121.2 | 0 | 2024-06-12 |  | 145
2022 | Region VII | CEBU | CEBU CITY (CAPITAL) (CEBU) | P00630659VS | Construction of Drainage Structure | 123.9055 | 10.3036 | 4950000 | 4929981.5 | 2022 | KAUIE BUILDERS & SUPPLIES INC. (FORMERLY: KAUIE BUILDERS AND CONSTRUCTION SUPPLIES) | 7580 | 2022 | 2022-07-18 | 03/17/2022 | 20018.5 | 0 | 2022-07-17 |  | 1
2023 | Region V | SORSOGON | JUBAN (SORSOGON) | P00740685LZ | Construction of Flood Mitigation Structure | 123.9684 | 12.8248 | 24500000 | 23765326.79 | 2023 | FULLEROS BOTOX BUILDERS AND DESIGN | 7581 | 2023 | 2023-08-31 | 04/17/2023 | 734673.21 | 0 | 2023-10-20 | 50
2022 | Region VII | CEBU | RONDA (CEBU) | P00620040VS | Construction of Flood Mitigation Structure | 123.4084 | 10.0017 | 48992790.68 | 48992790.68 | 2022 | WORLDWIDE BUILDERS / QUIRANTE CONSTRUCTION CORPORATION (FORMERLY: QUIRANTE CONSTRUCTION) | 7582 | 2022 | 2022-09-30 | 02/10/2022 | 0 | 0 | 2022-09-29 |  | 1
2022 | Region V | SORSOGON | GUBAT (SORSOGON) | P00632973LZ | Construction of Flood Mitigation Structure | 124.0865 | 12.8725 | 49500000 | 29067904.86 | 2022 | RMH CONSTRUCTION & SUPPLY / STEVEN CONSTRUCTION & SUPPLY | 7583 | 2022 | 2022-09-03 | 02/14/2022 | 20432095.14 | 0 | 2022-09-02 |  | 1
2022 | Region V | ALBAY | MALILIPOT (ALBAY) | P00631333LZ | Rehabilitation / Major Repair of Flood Control Structure | 123.7613 | 13.3099 | 95229997.38 | 43120000 | 2023 | RCDS CONSTRUCTION & SUPPLY, INC.(FOR RCDS CONST. | 7584 | 2022 | 2023-04-01 | 08/05/2022 | 52109997.38 | 0 | 2023-03-31 |  | 1
2022 | Region V | ALBAY | MALINAO (ALBAY) | P00620332LZ | Rehabilitation / Major Repair of Flood Control Structure | 123.6613 | 13.3537 | 101324983 | 101325000 | 2023 | MAKAPA CORPORATION | 7585 | 2022 | 2023-02-10 | 03/21/2022 | 0 | 17 | 2023-02-09 |  | 1
2023 | Region VII | CEBU | CITY OF TALISAY (CEBU) | P00732022VS | Construction of Flood Mitigation Structure | 123.839 | 10.2666 | 4950000 | 4940000 | 2023 | PLANAC CONSTRUCTION | 7586 | 2023 | 2023-05-26 | 02/15/2023 | 10000 | 0 | 2023-05-27 | 1
2023 | Region XII | SULTAN KUDARAT | KALAMANSIG (SULTAN KUDARAT) | P00721318MN | Construction of Flood Mitigation Structure | 124.0909 | 6.5456 | 96500000 | 71120500.88 | 2023 | MUST ENTERPRISES / ALBANOR CONSTRUCTION | 7587 | 2023 | 2023-12-07 | 03/08/2023 | 25379499.12 | 0 | 2024-03-02 | 86
2022 | Region VII | CEBU | CEBU CITY (CAPITAL) (CEBU) | P00620033VS | Construction of Flood Mitigation Structure | 123.906 | 10.2977 | 96500000 | 96500000 | 2023 | UKC BUILDERS, INC. / ON POINT CONSTRUCTION AND DEVELOPMENT CORPORATION (FORMERLY:ON POINT CONSTRUCTION) | 7588 | 2022 | 2023-02-23 | 03/10/2022 | 0 | 0 | 2023-03-09 | 14
2023 | Region V | SORSOGON | JUBAN (SORSOGON) | P00740686LZ | Construction of Flood Mitigation Structure | 123.9684 | 12.8247 | 19600000 | 19027799.48 | 2023 | FULLEROS BOTOX BUILDERS AND DESIGN | 7589 | 2023 | 2023-08-31 | 04/17/2023 | 572200.52 | 0 | 2023-10-13 | 43
2022 | Region V | CAMARINES SUR | SAGÃ‘AY (CAMARINES SUR) | P00631424LZ | Construction of Flood Mitigation Structure | 123.5271 | 13.6018 | 29400000 | 29400000 | 2022 | IA FERRER CONSTRUCTION & SUPPLY | 7590 | 2022 | 2022-11-21 | 04/11/2022 | 0 | 0 | 2022-11-20 |  | 1
2022 | Region V | CAMARINES SUR | IRIGA CITY (CAMARINES SUR) | P00640582LZ | Construction of Flood Mitigation Structure | 123.4088 | 13.4138 | 49500000 | 48109727.57 | 2022 | STEVEN CONSTRUCTION & SUPPLY | 7591 | 2022 | 2022-12-27 | 04/12/2022 | 1390272.43 | 0 | 2022-12-26 |  | 1
2022 | Region X | MISAMIS OCCIDENTAL | CLARIN (MISAMIS OCCIDENTAL) | P00620156MN | Construction of Drainage Structure | 123.8429 | 8.266 | 39200000 | 37239055.24 | 2024 | GRACE CONSTRUCTION CORPORATION | 7592 | 2022 | 2024-03-24 | 04/04/2022 | 1960944.76 | 0 | 2023-01-31 |  | 418
2023 | Region V | CATANDUANES | SAN ANDRES (CALOLBON) (CATANDUANES) | P00740683LZ | Construction of Flood Mitigation Structure | 124.0912 | 13.6329 | 48999999.48 | 48232154.04 | 2024 | NQA CONSTRUCTION & SUPPLY | 7593 | 2023 | 2024-02-06 | 07/28/2023 | 767845.44 | 0 | 2024-02-09 | 3
2023 | Region VII | CEBU | COMPOSTELA (CEBU) | P00744360VS | Rehabilitation / Major Repair of Flood Control Structure | 123.9695 | 10.4502 | 31061420 | 31005336.24 | 2023 | VSP STRUCTURE VENTURES CORP. (FORMERLY: VIRLO CONSTRUCTION) | 7594 | 2023 | 2023-08-26 | 03/30/2023 | 56083.76 | 0 | 2023-08-25 |  | 1
2023 | Region V | ALBAY | SANTO DOMINGO (LIBOG) (ALBAY) | P00742467LZ | Construction of Flood Mitigation Structure | 123.7633 | 13.2147 | 98999999.4 | 99000000 | 2023 | HI-TONE CONSTRUCTION & DEVELOPMENT CORP. (FORMERLY | 7595 | 2023 | 2023-10-26 | 04/12/2023 | 0 | 0.6 | 2023-12-09 | 44
2022 | Region VII | CEBU | ALCANTARA (CEBU) | P00633004VS | Construction of Revetment | 123.4105 | 10.0028 | 48999991.18 | 48999991.18 | 2022 | QM BUILDERS / FIRST GRANDEUR BUILDERS | 7596 | 2022 | 2022-10-27 | 03/23/2022 | 0 | 0 | 2022-10-26 |  | 1
2022 | Region X | MISAMIS OCCIDENTAL | TUDELA (MISAMIS OCCIDENTAL) | P00620160MN | Construction of Slope Protection Structure | 123.8429 | 8.266 | 49000000 | 47530000 | 2024 | MINDANAO ROCK | 7597 | 2022 | 2024-02-18 | 03/29/2022 | 1470000 | 0 | 2022-09-21 |  | 515
2024 | Region V | ALBAY | POLANGUI (ALBAY) | P00844565LZ | Construction of Flood Mitigation Structure | 123.5281 | 13.3467 | 144750000 | 144749802.6 | 2025 | RICHMAR CONSTRUCTION | 7598 | 2024 | 2025-01-15 | 05/13/2024 | 197.4 | 0 | 2025-03-07 | 51
2022 | Region VII | CEBU | CEBU CITY (CAPITAL) (CEBU) | P00620134VS | Construction of Flood Mitigation Structure | 123.9061 | 10.3986 | 49000000 | 49000000 | 2022 | GONZALODO ENTERPRISES | 7599 | 2022 | 2022-11-22 | 02/22/2022 | 0 | 0 | 2022-11-23 | 1
2023 | Region VII | CEBU | MALABUYOC (CEBU) | P00731619VS | Construction of Flood Mitigation Structure | 123.4114 | 9.9987 | 95723452.13 | 95722592.49 | 2023 | LEGACY CONSTRUCTION CORPORATION (FORMERLY: LEGACY CONSTRUCTION) | 7600 | 2023 | 2023-12-18 | 02/08/2023 | 859.64 | 0 | 2023-12-17 |  | 1
2023 | Region V | MASBATE | MOBO (MASBATE) | P00726299LZ | Construction of Flood Mitigation Structure | 123.6615 | 12.3214 | 48999989.53 | 49000000 | 2023 | A3 CONSTRUCTION & SUPPLY / EJ CANTORIA CONSTRUCTION & SUPPLY | 7601 | 2023 | 2023-11-19 | 04/11/2023 | 0 | 10.47 | 2023-11-18 |  | 1
2021 | Region X | MISAMIS OCCIDENTAL |  | P00522176MN | Construction of Flood Mitigation Structure | 123.8442 | 8.1422 | 49000000 | 46550000.28 | 2022 | MINDANAO ROCK | 7602 | 2021 | 2022-07-25 | 10/08/2021 | 2449999.72 | 0 | 2022-06-01 |  | 54
2023 | Region VII | CEBU | CEBU CITY (CAPITAL) (CEBU) | P00732028VS | Construction of Flood Mitigation Structure | 123.9076 | 10.3029 | 4950000 | 4932965.79 | 2023 | NEW GLOBALDEV CORPORATION | 7603 | 2023 | 2023-12-24 | 08/23/2023 | 17034.21 | 0 | 2023-12-23 |  | 1
2021 | Region VII | CEBU |  | P00550018VS | Construction of Drainage Structure | 123.5282 | 9.9857 | 29700000 | 26345090.31 | 2022 | O.Q. CONSTRUCTION AND SUPPLY | 7604 | 2021 | 2022-09-23 | 10/20/2021 | 3354909.69 | 0 | 2022-10-03 | 10
2023 | Region V | SORSOGON | MATNOG (SORSOGON) | P00737578LZ | Construction of Flood Mitigation Structure | 124.0928 | 12.5338 | 54450000 | 9800997.16 | 2023 | ALHADRAX CONSTRUCTION AND SUPPLY | 7605 | 2023 | 2023-10-29 | 05/02/2023 | 44649002.84 | 0 | 2023-10-28 |  | 1
2023 | Region VII | CEBU | COMPOSTELA (CEBU) | P00721829VS | Construction of Flood Mitigation Structure | 123.9701 | 10.4499 | 49000000 | 48949066.04 | 2023 | VSP STRUCTURE VENTURES CORP. (FORMERLY: VIRLO CONSTRUCTION) | 7606 | 2023 | 2023-07-10 | 01/30/2023 | 50933.96 | 0 | 2023-08-26 | 47
2023 | Region VII | CEBU | MALABUYOC (CEBU) | P00731618VS | Construction of Flood Mitigation Structure | 123.4114 | 9.9987 | 95533076.14 | 95531364.4 | 2023 | LEGACY CONSTRUCTION CORPORATION (FORMERLY: LEGACY CONSTRUCTION) | 7607 | 2023 | 2023-12-18 | 02/08/2023 | 1711.74 | 0 | 2023-12-17 |  | 1
2022 | Region VII | CEBU | CEBU CITY (CAPITAL) (CEBU) | P00630658VS | Construction of Drainage Structure | 123.9078 | 10.295 | 4950000 | 4900186.98 | 2022 | CEBU HAYDTER CONSTRUCTION | 7608 | 2022 | 2022-07-18 | 03/17/2022 | 49813.02 | 0 | 2022-07-17 |  | 1
2022 | Region X | MISAMIS OCCIDENTAL | TUDELA (MISAMIS OCCIDENTAL) | P00620043MN | Construction of Flood Mitigation Structure | 123.8443 | 8.2436 | 30900380 | 29355361 | 2023 | MINDANAO ROCK | 7609 | 2022 | 2023-07-24 | 05/23/2022 | 1545019 | 0 | 2022-12-25 |  | 211
2024 | Region VII | CEBU | TOLEDO CITY (CEBU) | P00820343VS | Construction of Flood Mitigation Structure | 123.6618 | 10.382 | 77200000 | 77200000 | 2024 | VEN RAY CONSTRUCTION CORPORATION | 7610 | 2024 | 2024-11-15 | 02/20/2024 | 0 | 0 | 2024-11-16 | 1
2022 | Region V | MASBATE | SAN FERNANDO (MASBATE) | P00631465LZ | Construction of Flood Mitigation Structure | 123.7638 | 12.4873 | 34300000 | 32584624.86 | 2022 | A3 CONSTRUCTION & SUPPLY / SISBRO CONSTRUCTION CORPORATION (FORMERLY: SISBRO CONSTRUCTION & SUPPLY) | 7611 | 2022 | 2022-11-27 | 03/17/2022 | 1715375.14 | 0 | 2022-10-27 |  | 31
2023 | Region V | MASBATE | MILAGROS (MASBATE) | P00726302LZ | Construction of Flood Mitigation Structure | 123.5295 | 12.2536 | 48999976.66 | 49000000 | 2023 | NEXT GENERATION CONSTRUCTION AND SUPPLY CORPORATION | 7612 | 2023 | 2023-06-26 | 02/02/2023 | 0 | 23.34 | 2023-09-11 | 77
2022 | Region V | CATANDUANES | SAN ANDRES (CALOLBON) (CATANDUANES) | P00640585LZ | Construction of Flood Mitigation Structure | 124.0955 | 13.5986 | 29399999.13 | 29398756.61 | 2022 | AL-JON CONSTRUCTION DEVELOPMENT, INC. (FORMERLY: ALJON CONSTRUCTION & SUPPLY) | 7613 | 2022 | 2022-11-24 | 04/12/2022 | 1242.52 | 0 | 2022-11-23 |  | 1
2023 | Region VII | CEBU | RONDA (CEBU) | P00721516VS | Construction of Revetment | 123.4114 | 9.9987 | 96401741.73 | 96401741.64 | 2023 | FIRST GRANDEUR BUILDERS / MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY | 7614 | 2023 | 2023-12-19 | 02/08/2023 | 0.09 | 0 | 2023-12-18 |  | 1
2022 | Region VII | CEBU | TABOGON (CEBU) | P00620029VS | Construction of Flood Mitigation Structure | 123.9704 | 10.9269 | 72375000 | 72375000 | 2022 | PRIME GIGABUILD CONSTRUCTION CORP. (FORMERLY: RON DANIELL CONSTRUCTION CORPORATION) | 7615 | 2022 | 2022-11-21 | 02/21/2022 | 0 | 0 | 2022-11-20 |  | 1
2022 | Region V | ALBAY | SANTO DOMINGO (LIBOG) (ALBAY) | P00639396LZ | Construction of Slope Protection Structure | 123.8455 | 13.2258 | 94569452.7 | 94570000 | 2023 | HI-TONE CONSTRUCTION & DEVELOPMENT CORP. (FORMERLY / KENZAI BUILDERS CORPORATION | 7616 | 2022 | 2023-01-29 | 08/03/2022 | 0 | 547.3 | 2023-01-28 |  | 1
2022 | Region V | ALBAY | CAMALIG (ALBAY) | P00640468LZ | Construction of Flood Mitigation Structure | 123.662 | 13.1878 | 97998363.27 | 97998183.09 | 2023 | KENZAI BUILDERS CORPORATION / JCM AMEG BUILDERS CORPORATION (FORMERLY: AMEG CONSTRUCTION & SUPPLY) | 7617 | 2022 | 2023-01-30 | 04/13/2022 | 180.18 | 0 | 2023-01-29 |  | 1
2023 | Region VII | CEBU | ASTURIAS (CEBU) | P00721768VS | Construction of Flood Mitigation Structure | 123.7644 | 10.6227 | 77200000 | 77199933.95 | 2023 | WTG CONSTRUCTION & DEVELOPMENT CORPORATION | 7618 | 2023 | 2023-11-28 | 03/02/2023 | 66.05 | 0 | 2023-11-27 |  | 1
2022 | Region VII | CEBU | CEBU CITY (CAPITAL) (CEBU) | P00633016VS | Construction of Flood Mitigation Structure | 123.9082 | 10.3045 | 4900000 | 4889970 | 2022 | PLANAC CONSTRUCTION | 7619 | 2022 | 2022-12-22 | 09/13/2022 | 10030 | 0 | 2022-12-21 |  | 1
2023 | Region V | ALBAY | SANTO DOMINGO (LIBOG) (ALBAY) | P00740460LZ | Construction of Flood Mitigation Structure | 123.7649 | 13.2262 | 192998274.8 | 192998274.8 | 2024 | TR CONSTRUCTION CORPORATION (FOR: TR CONSTRUCTION) | 7620 | 2023 | 2024-03-31 | 05/29/2023 | 0 | 0 | 2024-04-10 | 10
2022 | Region V | ALBAY | CAMALIG (ALBAY) | P00639536LZ | Construction of Flood Mitigation Structure | 123.6623 | 13.1885 | 48998376.35 | 48998250.84 | 2022 | HI-TONE CONSTRUCTION & DEVELOPMENT CORP. (FORMERLY | 7621 | 2022 | 2022-11-23 | 04/11/2022 | 125.51 | 0 | 2022-11-22 |  | 1
2022 | Region VII | CEBU | DALAGUETE (CEBU) | P00620127VS | Construction of Flood Mitigation Structure | 123.5298 | 9.763 | 49000000 | 49000000 | 2022 | QUIRANTE CONSTRUCTION CORPORATION (FORMERLY: QUIRANTE CONSTRUCTION) | 7622 | 2022 | 2022-10-14 | 02/09/2022 | 0 | 0 | 2022-10-20 | 6
2022 | Region V | CATANDUANES | SAN ANDRES (CALOLBON) (CATANDUANES) | P00631453LZ | Construction of Flood Mitigation Structure | 124.0973 | 13.5962 | 48998759.21 | 48998742.08 | 2022 | AL-JON CONSTRUCTION DEVELOPMENT, INC. (FORMERLY: ALJON CONSTRUCTION & SUPPLY) | 7623 | 2022 | 2022-11-21 | 03/02/2022 | 17.13 | 0 | 2022-11-20 |  | 1
2023 | Region VII | CEBU | MALABUYOC (CEBU) | P00733272VS | Construction of Groundsill | 123.4114 | 9.9987 | 57898226.98 | 57898214.56 | 2023 | QM BUILDERS | 7624 | 2023 | 2023-12-07 | 04/11/2023 | 12.42 | 0 | 2023-12-06 |  | 1
2023 | Region VII | CEBU | MANDAUE CITY (CEBU) | P00721774VS | Construction of Flood Mitigation Structure | 123.9709 | 10.3439 | 96500000 | 96399888 | 2023 | QUIRANTE CONSTRUCTION CORPORATION (FORMERLY: QUIRANTE CONSTRUCTION) | 7625 | 2023 | 2023-12-12 | 05/12/2023 | 100112 | 0 | 2024-03-12 | 91
2024 | Region X | MISAMIS OCCIDENTAL | TUDELA (MISAMIS OCCIDENTAL) | P00820156MN | Construction of Flood Mitigation Structure | 123.8457 | 8.2499 | 12250000 | 11882500.74 | 2024 | ABIB BUILDERS ENTERPRISE | 7626 | 2024 | 2024-10-20 | 03/01/2024 | 367499.26 | 0 | 2024-07-07 |  | 105
2021 | Region VII | CEBU |  | P00549967VS | Construction of Flood Mitigation Structure | 123.6629 | 10.1074 | 77200000 | 77200000 | 2022 | WERR CORPORATION INTERNATIONAL / PRIME GIGABUILD CONSTRUCTION CORP. (FORMERLY: RON DANIELL CONSTRUCTION CORPORATION) | 7627 | 2021 | 2022-08-31 | 11/03/2021 | 0 | 0 | 2022-08-30 |  | 1
2023 | Region VII | CEBU | CEBU CITY (CAPITAL) (CEBU) | P00721685VS | Construction of Flood Mitigation Structure | 123.9083 | 10.302 | 44100000 | 43978839.53 | 2023 | FLUSSKREBS CONSTRUCTORS | 7628 | 2023 | 2023-09-21 | 03/29/2023 | 121160.47 | 0 | 2023-10-29 | 38
2022 | Region V | MASBATE | SAN FERNANDO (MASBATE) | P00631463LZ | Construction of Flood Mitigation Structure | 123.7655 | 12.4897 | 34300000 | 34299948.51 | 2022 | A3 CONSTRUCTION & SUPPLY / SISBRO CONSTRUCTION CORPORATION (FORMERLY: SISBRO CONSTRUCTION & SUPPLY) | 7629 | 2022 | 2022-09-05 | 03/17/2022 | 51.49 | 0 | 2022-10-27 | 52
2022 | Region V | ALBAY | CITY OF LIGAO (ALBAY) | P00631356LZ | Construction of Dike | 123.5307 | 13.2279 | 39200000 | 39100891.04 | 2023 | 3DIAMONDS CONSTRUCTION CORPORATION | 7630 | 2022 | 2023-02-25 | 08/15/2022 | 99108.96 | 0 | 2023-02-24 |  | 1
2022 | Region VII | BOHOL | SAGBAYAN (BORJA) (BOHOL) | P00630212VS | Construction of Flood Mitigation Structure | 124.1011 | 9.9194 | 49000000 | 47530000 | 2023 | B. VICENCIO BUILDERS (BVB), INC. (FORMERLY:B. VICENCIO CONSTRUCTION) / ZLREJ TRADING AND CONSTRUCTION CORPORATION | 7631 | 2022 | 2023-08-01 | 03/28/2022 | 1470000 | 0 | 2023-02-19 |  | 163
2023 | Region VII | CEBU | MALABUYOC (CEBU) | P00733262VS | Construction of Flood Mitigation Structure | 123.4114 | 9.9987 | 96493378.77 | 96493356.5 | 2024 | QM BUILDERS | 7632 | 2023 | 2024-01-11 | 05/05/2023 | 22.27 | 0 | 2024-03-05 | 54
2023 | Region VII | CEBU | MALABUYOC (CEBU) | P00733277VS | Construction of Flood Mitigation Structure | 123.4114 | 9.9987 | 96493910.79 | 96493351.85 | 2023 | QM BUILDERS | 7633 | 2023 | 2023-09-26 | 05/05/2023 | 558.94 | 0 | 2024-03-05 | 161
2021 | Region X | MISAMIS OCCIDENTAL |  | P00522302MN | Construction of Flood Mitigation Structure | 123.8463 | 8.3335 | 45355000 | 35108440.26 | 2023 | C'ZARLES CONSTRUCTION & SUPPLY | 7634 | 2021 | 2023-04-24 | 07/23/2021 | 10246559.74 | 0 | 2023-04-23 |  | 1
2023 | Region V | ALBAY | CAMALIG (ALBAY) | P00742197LZ | Construction of Dike | 123.663 | 13.1946 | 98928597.11 | 98928190.55 | 2024 | CENTERWAYS CONSTRUCTION AND DEVELOPMENT INC. / FS CO BUILDERS AND SUPPLY | 7635 | 2023 | 2024-02-13 | 07/03/2023 | 406.56 | 0 | 2024-05-06 | 83
2023 | Region VII | CEBU | CEBU CITY (CAPITAL) (CEBU) | P00732029VS | Construction of Flood Mitigation Structure | 123.9087 | 10.398 | 4950000 | 4933978.32 | 2024 | ST. BERNARDINE CONSTRUCTION & ENTERPRISES (FOR. ST | 7636 | 2023 | 2024-01-21 | 08/23/2023 | 16021.68 | 0 | 2024-01-20 |  | 1
2023 | Region V | MASBATE | USON (MASBATE) | P00726305LZ | Construction of Flood Mitigation Structure | 123.7678 | 12.2148 | 39068761.93 | 38730805.32 | 2023 | RED DIAMOND CONSTRUCTION AND SUPPLY CORPORATION (FORMERLY: RED DIAMOND CONSTRUCTION) | 7637 | 2023 | 2023-12-22 | 04/18/2023 | 337956.61 | 0 | 2024-02-17 | 57
2024 | Region IX | ZAMBOANGA DEL SUR | TAMBULIG (ZAMBOANGA DEL SUR) | P00820393MN | Construction of Flood Mitigation Structure | 123.5323 | 8.0259 | 29400000 | 29374937.82 | 2024 | GENETIAN BUILDERS AND ENTERPRISES INCORPORATED (FORMERLY: GENETIAN BUILDERS) | 7638 | 2024 | 2024-09-05 | 02/19/2024 | 25062.18 | 0 | 2024-09-04 |  | 1
2022 | Region V | SORSOGON | GUBAT (SORSOGON) | P00632975LZ | Construction of Flood Mitigation Structure | 124.1018 | 12.9086 | 49500000 | 18940659.69 | 2022 | RMH CONSTRUCTION & SUPPLY / STEVEN CONSTRUCTION & SUPPLY | 7639 | 2022 | 2022-09-03 | 02/14/2022 | 30559340.31 | 0 | 2022-09-02 |  | 1
2024 | Region VII | CEBU | RONDA (CEBU) | P00834660VS | Construction of Flood Mitigation Structure | 123.4123 | 10.0027 | 39196417.46 | 39196415.8 | 2024 | FIRST GRANDEUR BUILDERS | 7640 | 2024 | 2024-09-05 | 04/01/2024 | 1.66 | 0 | 2024-10-17 | 42
2022 | Region VII | CEBU | BADIAN (CEBU) | P00620456VS | Construction of Slope Protection Structure | 123.4129 | 9.8398 | 48996091.75 | 48996091.75 | 2023 | QM BUILDERS | 7641 | 2022 | 2023-01-29 | 03/23/2022 | 0 | 0 | 2023-01-28 |  | 1
2022 | Region VII | CEBU | CITY OF TALISAY (CEBU) | P00633225VS | Construction of Flood Mitigation Structure | 123.8466 | 10.2403 | 49500000 | 49500000 | 2022 | QUIRANTE CONSTRUCTION CORPORATION (FORMERLY: QUIRANTE CONSTRUCTION) | 7642 | 2022 | 2022-12-21 | 04/13/2022 | 0 | 0 | 2022-12-20 |  | 1
2022 | Region VII | CEBU | CEBU CITY (CAPITAL) (CEBU) | P00630653VS | Construction of Drainage Structure | 123.9087 | 10.3239 | 4950000 | 4935395.43 | 2022 | 1ST J.E. ADLAWAN CONSTRUCTION & SUPPLY CORPORATION (FORMERLY: ELEAZAR V. ADLAWAN CONSTRUCTION) | 7643 | 2022 | 2022-07-25 | 03/24/2022 | 14604.57 | 0 | 2022-07-24 |  | 1
2024 | Region V | ALBAY | CAMALIG (ALBAY) | P00844568LZ | Construction of Flood Mitigation Structure | 123.6642 | 13.1823 | 96498905.59 | 96498671.05 | 2024 | A3 CONSTRUCTION & SUPPLY | 7644 | 2024 | 2024-11-15 | 04/08/2024 | 234.54 | 0 | 2025-03-04 | 109
2023 | Region V | MASBATE | SAN FERNANDO (MASBATE) | P00736133LZ | Construction of Flood Mitigation Structure | 123.7681 | 12.4788 | 48249895.17 | 48249895.17 | 2023 | CENTERWAYS CONSTRUCTION AND DEVELOPMENT INC. | 7645 | 2023 | 2023-12-22 | 03/24/2023 | 0 | 0 | 2023-10-06 |  | 77
2022 | Region VII | BOHOL | BILAR (BOHOL) | P00630218VS | Construction of Drainage Structure | 124.1019 | 9.7037 | 32340000 | 32337988.76 | 2022 | ZLREJ TRADING AND CONSTRUCTION CORPORATION / AQUATERRA KONSTRUKT INC. | 7646 | 2022 | 2022-12-15 | 03/23/2022 | 2011.24 | 0 | 2022-12-14 |  | 1
2022 | Region V | SORSOGON | GUBAT (SORSOGON) | P00630967LZ | Construction of Flood Mitigation Structure | 124.1033 | 12.9347 | 67550000 | 67550000 | 2023 | MUNTOPAR BUILDERS CORP. | 7647 | 2022 | 2023-03-29 | 03/18/2022 | 0 | 0 | 2023-03-28 |  | 1
2022 | Region V | SORSOGON | GUBAT (SORSOGON) | P00630966LZ | Construction of Flood Mitigation Structure | 124.1034 | 12.9348 | 67550000 | 67550000 | 2023 | MUNTOPAR BUILDERS CORP. | 7648 | 2022 | 2023-01-29 | 03/18/2022 | 0 | 0 | 2023-02-06 | 8
2023 | Region VII | CEBU | DALAGUETE (CEBU) | P00733739VS | Construction of Drainage Structure | 123.5332 | 9.7556 | 4950000 | 4938888.88 | 2023 | BT CONSTRUCTION AND GENERAL SERVICES | 7649 | 2023 | 2023-05-07 | 04/03/2023 | 11111.12 | 0 | 2023-05-06 |  | 1
2025 | Region VII | CEBU | MANDAUE CITY (CEBU) | P00920070VS | Construction of Flood Mitigation Structure | 123.9711 | 10.3434 | 72375000 | 72325000 | 2025 | ON POINT CONSTRUCTION AND DEVELOPMENT CORPORATION (FORMERLY:ON POINT CONSTRUCTION) | 7650 | 2025 | 2025-04-28 | 02/21/2025 | 50000 | 0 | 2025-11-01 | 187
2022 | Region VII | BOHOL | INABANGA (BOHOL) | P00630215VS | Construction of Flood Mitigation Structure | 124.1042 | 10.0324 | 49000000 | 47292350 | 2023 | B. VICENCIO BUILDERS (BVB), INC. (FORMERLY:B. VICENCIO CONSTRUCTION) / ZLREJ TRADING AND CONSTRUCTION CORPORATION | 7651 | 2022 | 2023-10-31 | 01/31/2022 | 1707650 | 0 | 2022-12-30 |  | 305
2023 | Region VII | CEBU | RONDA (CEBU) | P00721977VS | Construction of Flood Mitigation Structure | 123.4138 | 10.0033 | 86848251.07 | 86848237.27 | 2023 | QM BUILDERS / FIRST GRANDEUR BUILDERS | 7652 | 2023 | 2023-11-20 | 03/16/2023 | 13.8 | 0 | 2024-01-01 | 42
2024 | Region X | LANAO DEL NORTE | BAROY (LANAO DEL NORTE) | P00820153MN | Construction of Flood Mitigation Structure | 123.8485 | 7.9645 | 12250000 | 12250000 | 2024 | PRIME HAUS BUILDERS & ENTERPRISES | 7653 | 2024 | 2024-07-24 | 01/23/2024 | 0 | 0 | 2024-08-22 | 29
2022 | Region V | ALBAY | CAMALIG (ALBAY) | P00639544LZ | Construction of Flood Mitigation Structure | 123.6643 | 13.1262 | 48999919.64 | 48999516.44 | 2022 | A3 CONSTRUCTION & SUPPLY / FIRST OMB CONSTRUCTION AND DEVELOPMENT CORP. | 7654 | 2022 | 2022-09-30 | 04/11/2022 | 403.2 | 0 | 2022-09-30 | 0
2023 | Region V | ALBAY | SANTO DOMINGO (LIBOG) (ALBAY) | P00740461LZ | Construction of Flood Mitigation Structure | 123.7685 | 13.2245 | 192998182 | 192998182 | 2023 | TR CONSTRUCTION CORPORATION (FOR: TR CONSTRUCTION) | 7655 | 2023 | 2023-12-31 | 05/04/2023 | 0 | 0 | 2024-04-13 | 104
2023 | Region VII | BOHOL | ALBURQUERQUE (BOHOL) | P00721938VS | Construction of Flood Mitigation Structure | 123.972 | 9.6058 | 17640000 | 17490000 | 2024 | HERBERT MALMIS GENERAL MERCHANDISING & CONTRACTOR | 7656 | 2023 | 2024-01-07 | 05/11/2023 | 150000 | 0 | 2024-01-06 |  | 1
2022 | Region VII | CEBU | CEBU CITY (CAPITAL) (CEBU) | P00630660VS | Construction of Drainage Structure | 123.9088 | 10.2972 | 4950000 | 4935105.1 | 2022 | 1ST J.E. ADLAWAN CONSTRUCTION & SUPPLY CORPORATION (FORMERLY: ELEAZAR V. ADLAWAN CONSTRUCTION) | 7657 | 2022 | 2022-07-25 | 03/24/2022 | 14894.9 | 0 | 2022-07-24 |  | 1
2024 | Region V | SORSOGON | CITY OF SORSOGON (CAPITAL) (SORSOGON) | P00846128LZ | Construction of Flood Mitigation Structure | 124.1059 | 13.0371 | 79199947.93 | 19799980.32 | 2024 | AREMAR CONSTRUCTION CORPORATION | 7658 | 2024 | 2024-12-11 | 05/17/2024 | 59399967.61 | 0 | 2024-12-10 |  | 1
2022 | Region V | ALBAY | CITY OF LIGAO (ALBAY) | P00630977LZ | Construction of Groundsill | 123.5335 | 13.249 | 67550000 | 67550000 | 2022 | HI-TONE CONSTRUCTION & DEVELOPMENT CORP. (FORMERLY | 7659 | 2022 | 2022-12-01 | 03/14/2022 | 0 | 0 | 2023-01-21 | 51
2024 | Region VII | CEBU | MOALBOAL (CEBU) | P00834662VS | Construction of Flood Mitigation Structure | 123.4146 | 10.0074 | 29395323.91 | 29394904.7 | 2024 | SUDAN CONSTRUCTION AND SUPPLY CORP. | 7660 | 2024 | 2024-04-15 | 02/26/2024 | 419.21 | 0 | 2024-09-12 | 150
2022 | Region V | SORSOGON | CASTILLA (SORSOGON) | P00640477LZ | Construction of Revetment | 123.8489 | 12.9795 | 98999981.21 | 98999981.03 | 2023 | CENTERWAYS CONSTRUCTION AND DEVELOPMENT INC. | 7661 | 2022 | 2023-06-22 | 06/21/2022 | 0.18 | 0 | 2023-06-21 |  | 1
2023 | Region VII | CEBU | TUBURAN (CEBU) | P00721674VS | Construction of Drainage Structure | 123.8496 | 10.787 | 10780000 | 10779791.4 | 2023 | JIAN ARMEL RICHARD CHRISTERSON (JARC) CONSTRUCTION & MARINE SERVICES CORPORATION (FORMERLY:J.A.R.C. | 7662 | 2023 | 2023-10-09 | 05/25/2023 | 208.6 | 0 | 2023-10-08 |  | 1
2023 | Region VII | CEBU | CEBU CITY (CAPITAL) (CEBU) | P00733746VS | Construction of Flood Mitigation Structure | 123.9091 | 10.3196 | 4950000 | 4940000 | 2024 | PLANAC CONSTRUCTION | 7663 | 2023 | 2024-05-13 | 11/09/2023 | 10000 | 0 | 2024-05-12 |  | 1
2023 | Region V | ALBAY | SANTO DOMINGO (LIBOG) (ALBAY) | P00740475LZ | Construction of Flood Mitigation Structure | 123.7688 | 13.2538 | 96499955.68 | 96500000 | 2023 | HI-TONE CONSTRUCTION & DEVELOPMENT CORP. (FORMERLY | 7664 | 2023 | 2023-09-20 | 04/17/2023 | 0 | 44.32 | 2023-12-14 | 85
2023 | Region VII | CEBU | CITY OF BOGO (CEBU) | P00721535VS | Construction of Flood Mitigation Structure | 123.9725 | 11.0622 | 89745000 | 89745000 | 2023 | GONZALODO ENTERPRISES / RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R | 7665 | 2023 | 2023-12-07 | 02/14/2023 | 0 | 0 | 2023-12-06 |  | 1
2022 | Region VII | CEBU | DALAGUETE (CEBU) | P00620130VS | Construction of Slope Protection Structure | 123.5341 | 9.7837 | 49000000 | 49000000 | 2022 | QUIRANTE CONSTRUCTION CORPORATION (FORMERLY: QUIRANTE CONSTRUCTION) | 7666 | 2022 | 2022-10-21 | 02/09/2022 | 0 | 0 | 2022-10-20 |  | 1
2023 | Region V | SORSOGON | CITY OF SORSOGON (CAPITAL) (SORSOGON) | P00737581LZ | Construction of Flood Mitigation Structure | 124.1065 | 13.0408 | 71669931.81 | 7919978.36 | 2023 | CENTERWAYS CONSTRUCTION AND DEVELOPMENT INC. | 7667 | 2023 | 2023-11-22 | 02/23/2023 | 63749953.45 | 0 | 2023-11-21 |  | 1
2024 | Region VII | CEBU | MOALBOAL (CEBU) | P00834594VS | Construction of Flood Mitigation Structure | 123.4146 | 10.0074 | 57895284.24 | 57894463.74 | 2024 | ZLREJ TRADING AND CONSTRUCTION CORPORATION | 7668 | 2024 | 2024-09-24 | 03/12/2024 | 820.5 | 0 | 2024-12-28 | 95
2023 | Region V | SORSOGON | CITY OF SORSOGON (CAPITAL) (SORSOGON) | P00742492LZ | Construction of Flood Mitigation Structure | 123.9094 | 12.9776 | 54449963.17 | 9546698.83 | 2024 | CENTERWAYS CONSTRUCTION AND DEVELOPMENT INC. / CHEEREL CONSTRUCTION & SUPPLY | 7669 | 2023 | 2024-03-05 | 07/18/2023 | 44903264.34 | 0 | 2024-03-04 |  | 1
2023 | Region VII | CEBU | TOLEDO CITY (CEBU) | P00721673VS | Construction of Flood Mitigation Structure | 123.6654 | 10.4121 | 49000000 | 48938244.75 | 2024 | VEN RAY CONSTRUCTION CORPORATION | 7670 | 2023 | 2024-05-24 | 10/19/2023 | 61755.25 | 0 | 2024-05-24 | 0
2022 | Region VII | CEBU | TUBURAN (CEBU) | P00620121VS | Construction of Drainage Structure | 123.85 | 10.7872 | 7603820 | 7603479.13 | 2023 | JUGA BUILDERS & CONSTRUCTION SUPPLY | 7671 | 2022 | 2023-04-14 | 09/08/2022 | 340.87 | 0 | 2023-04-13 |  | 1
2023 | Region V | ALBAY | SANTO DOMINGO (LIBOG) (ALBAY) | P00740455LZ | Rehabilitation / Major Repair of Flood Control Structure | 123.7697 | 13.231 | 72374999.99 | 72375000 | 2023 | A3 CONSTRUCTION & SUPPLY | 7672 | 2023 | 2023-11-22 | 06/01/2023 | 0 | 0.01 | 2023-12-23 | 31
2023 | Region V | SORSOGON | CITY OF SORSOGON (CAPITAL) (SORSOGON) | P00725894LZ | Construction of Flood Mitigation Structure | 124.1065 | 13.0575 | 48249921.98 | 48247328.32 | 2023 | C.T. LEONCIO CONSTRUCTION & TRADING | 7673 | 2023 | 2023-11-28 | 02/23/2023 | 2593.66 | 0 | 2023-11-27 |  | 1
2022 | Region X | LANAO DEL NORTE | MAIGO (LANAO DEL NORTE) | P00620144MN | Construction of Slope Protection Structure | 123.9731 | 8.1694 | 49000000 | 49000000 | 2022 | LANAO BUILDER AND ENTERPRISES | 7674 | 2022 | 2022-12-15 | 03/18/2022 | 0 | 0 | 2022-12-14 |  | 1
2024 | Region V | MASBATE | CITY OF MASBATE (CAPITAL) (MASBATE) | P00820442LZ | Construction of Flood Mitigation Structure | 123.5389 | 12.2686 | 96499956.77 | 96499956.99 | 2024 | C.L. CARANDANG ENTERPRISES / A3 CONSTRUCTION & SUPPLY | 7675 | 2024 | 2024-09-26 | 02/21/2024 | 0 | 0.22 | 2024-12-31 | 96
2024 | Region VII | CEBU | ALEGRIA (CEBU) | P00834663VS | Construction of Flood Mitigation Structure | 123.4146 | 10.0074 | 48996112.34 | 48995812.34 | 2024 | LEGACY CONSTRUCTION CORPORATION (FORMERLY: LEGACY CONSTRUCTION) | 7676 | 2024 | 2024-05-21 | 03/12/2024 | 300 | 0 | 2024-10-15 | 147
2024 | Region VII | CEBU | SAN REMIGIO (CEBU) | P00820188VS | Construction of Flood Mitigation Structure | 123.9103 | 10.9326 | 29400000 | 29400000 | 2024 | DINAH RBS CONSTRUCTION AND SUPPLY INCORPORATED (FORMERLY: DINAH JANE CONSTRUCTION AND SUPPLY) | 7677 | 2024 | 2024-08-05 | 02/13/2024 | 0 | 0 | 2024-08-04 |  | 1
2022 | Region VII | CEBU | CITY OF TALISAY (CEBU) | P00633224VS | Construction of Flood Mitigation Structure | 123.8517 | 10.2456 | 9900000 | 9900000 | 2022 | QUIRANTE CONSTRUCTION CORPORATION (FORMERLY: QUIRANTE CONSTRUCTION) | 7678 | 2022 | 2022-08-30 | 04/13/2022 | 0 | 0 | 2022-08-29 |  | 1
2022 | Region VII | CEBU | BARILI (CEBU) | P00630192VS | Construction of Slope Protection Structure | 123.5389 | 10.1219 | 96500000 | 96277080.22 | 2022 | VEN RAY CONSTRUCTION CORPORATION | 7679 | 2022 | 2022-12-28 | 03/01/2022 | 222919.78 | 0 | 2022-12-31 | 3
2022 | Region V | SORSOGON | GUBAT (SORSOGON) | P00631476LZ | Construction of Revetment | 124.1139 | 12.9449 | 58800000 | 28517999.41 | 2022 | MUNTOPAR BUILDERS CORP. | 7680 | 2022 | 2022-09-04 | 02/15/2022 | 30282000.59 | 0 | 2022-09-03 |  | 1
2022 | Region VII | CEBU | CONSOLACION (CEBU) | P00620043VS | Construction of Flood Mitigation Structure | 123.9751 | 10.3668 | 115800000 | 115799830.6 | 2023 | MORTAR MASTERS & CONCRETE BUILDERS / VSP STRUCTURE VENTURES CORP. (FORMERLY: VIRLO CONSTRUCTION) | 7681 | 2022 | 2023-04-20 | 04/08/2022 | 169.4 | 0 | 2023-04-19 |  | 1
2024 | Region VII | BOHOL | CALAPE (BOHOL) | P00834640VS | Construction of Flood Mitigation Structure | 123.9104 | 9.9167 | 19600000 | 19532000 | 2024 | BNYU DEVELOPMENT CORPORATION (FORMERLY:BNYU ENTERPRISES & CONSTRUCTION) | 7682 | 2024 | 2024-09-10 | 04/12/2024 | 68000 | 0 | 2024-10-07 | 27
2023 | Region V | ALBAY | LIBON (ALBAY) | P00742201LZ | Rehabilitation / Major Repair of Flood Control Structure | 123.4169 | 13.2882 | 146555000 | 74249999.5 | 2023 | RAMARPLUS INCORPORATED (FORMERLY RAMAR ENTERPRISES | 7683 | 2023 | 2023-11-30 | 05/15/2023 | 72305000.5 | 0 | 2024-03-08 | 99
2024 | Region VII | CEBU | TOLEDO CITY (CEBU) | P00820397VS | Construction of Flood Mitigation Structure | 123.6658 | 10.3543 | 49000000 | 48857807.52 | 2024 | VEN RAY CONSTRUCTION CORPORATION | 7684 | 2024 | 2024-10-17 | 02/02/2024 | 142192.48 | 0 | 2024-10-16 |  | 1
2023 | Region VII | BOHOL | TAGBILARAN CITY (CAPITAL) (BOHOL) | P00721904VS | Construction of Drainage Structure | 123.8555 | 9.6649 | 72231631.04 | 72150000 | 2024 | LABB CONSTRUCTION DEVELOPMENT INC. (FORMERLY: LABB CONSTRUCTION) | 7685 | 2023 | 2024-06-23 | 11/10/2023 | 81631.04 | 0 | 2024-06-22 |  | 1
2024 | Region V | ALBAY | SANTO DOMINGO (LIBOG) (ALBAY) | P00825137LZ | Construction of Flood Mitigation Structure | 123.77 | 13.2219 | 173699800.5 | 173699690 | 2024 | TR CONSTRUCTION CORPORATION (FOR: TR CONSTRUCTION) | 7686 | 2024 | 2024-12-31 | 05/03/2024 | 110.5 | 0 | 2025-03-09 | 68
2022 | Region V | SORSOGON | SANTA MAGDALENA (SORSOGON) | P00620752LZ | Construction of Flood Mitigation Structure | 124.1145 | 12.6552 | 49000000 | 47415662.39 | 2022 | STEVEN CONSTRUCTION & SUPPLY | 7687 | 2022 | 2022-08-01 | 02/14/2022 | 1584337.61 | 0 | 2022-07-31 |  | 1
2022 | Region V | MASBATE | CITY OF MASBATE (CAPITAL) (MASBATE) | P00620739LZ | Rehabilitation / Major Repair of Flood Control Structure | 123.5389 | 12.2681 | 20334927.38 | 20334927.38 | 2022 | HKP CONSTRUCTION AND SUPPLY | 7688 | 2022 | 2022-08-09 | 02/07/2022 | 0 | 0 | 2022-08-08 |  | 1
2023 | Region V | ALBAY | CAMALIG (ALBAY) | P00737380LZ | Construction of Dike | 123.6666 | 13.1285 | 57728398.82 | 57728167.3 | 2023 | INFRA BUILDERS AND SELLERS, PHILIPPINES | 7689 | 2023 | 2023-09-02 | 02/27/2023 | 231.52 | 0 | 2023-09-01 |  | 1
2024 | Region VII | CEBU | CARMEN (CEBU) | P00834574VS | Construction of Flood Mitigation Structure | 123.977 | 10.606 | 67550000 | 67549987 | 2024 | VSP STRUCTURE VENTURES CORP. (FORMERLY: VIRLO CONSTRUCTION) | 7690 | 2024 | 2024-12-31 | 06/13/2024 | 13 | 0 | 2024-12-30 |  | 1
2023 | Region V | SORSOGON | BULAN (SORSOGON) | P00737576LZ | Construction of Flood Mitigation Structure | 123.9117 | 12.6389 | 54450000 | 9603008.42 | 2023 | ALHADRAX CONSTRUCTION AND SUPPLY | 7691 | 2023 | 2023-10-29 | 05/02/2023 | 44846991.58 | 0 | 2023-10-28 |  | 1
2022 | Region IX | ZAMBOANGA DEL NORTE | DAPITAN CITY (ZAMBOANGA DEL NORTE) | P00634127MN | Construction of Slope Protection Structure | 123.4174 | 8.6509 | 14850000 | 14847933.19 | 2023 | WESTMIN ENTERPRISES & CONSTRUCTION SERVICES | 7692 | 2022 | 2023-02-01 | 03/24/2022 | 2066.81 | 0 | 2023-01-31 |  | 1
2023 | Region X | MISAMIS OCCIDENTAL | CLARIN (MISAMIS OCCIDENTAL) | P00721614MN | Rehabilitation / Major Repair of Slope Protection Structure | 123.8559 | 8.2039 | 49000000 | 47530000 | 2023 | MINDANAO ROCK | 7693 | 2023 | 2023-12-11 | 02/10/2023 | 1470000 | 0 | 2023-07-25 |  | 139
2022 | Region V | ALBAY | SANTO DOMINGO (LIBOG) (ALBAY) | P00620311LZ | Construction of Flood Mitigation Structure | 123.7704 | 13.254 | 138413784.2 | 138413784.2 | 2022 | HI-TONE CONSTRUCTION & DEVELOPMENT CORP. (FORMERLY | 7694 | 2022 | 2022-12-15 | 03/28/2022 | 0 | 0 | 2023-01-12 | 28
2022 | Region V | SORSOGON | GUBAT (SORSOGON) | P00620754LZ | Construction of Flood Mitigation Structure | 124.1147 | 12.9094 | 98000000 | 49000000 | 2022 | C.T. LEONCIO CONSTRUCTION & TRADING | 7695 | 2022 | 2022-10-14 | 02/14/2022 | 49000000 | 0 | 2022-10-13 |  | 1
2022 | Region V | CAMARINES SUR | DEL GALLEGO (CAMARINES SUR) | P00620317LZ | Construction of Flood Mitigation Structure | 123.7704 | 13.254 | 89290069.17 | 89290069.17 | 2023 | E. GARCIA CONSTRUCTION CORP.(FOR. E. GARCIA CONST | 7696 | 2022 | 2023-06-15 | 06/20/2022 | 0 | 0 | 2023-06-16 | 1
2023 | Region IX | ZAMBOANGA DEL SUR | TAMBULIG (ZAMBOANGA DEL SUR) | P00721601MN | Construction of Flood Mitigation Structure | 123.539 | 8.069 | 9800000 | 9779316.2 | 2024 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R | 7697 | 2023 | 2024-03-12 | 05/25/2023 | 20683.8 | 0 | 2024-03-11 |  | 1
2023 | Region VII | CEBU | CEBU CITY (CAPITAL) (CEBU) | P00721833VS | Construction of Flood Mitigation Structure | 123.9163 | 10.3969 | 9800000 | 9784118 | 2023 | GOWIL BUILDERS | 7698 | 2023 | 2023-07-20 | 03/20/2023 | 15882 | 0 | 2023-07-19 |  | 1
2022 | Region V | SORSOGON | CITY OF SORSOGON (CAPITAL) (SORSOGON) | P00639393LZ | Construction of Flood Mitigation Structure | 123.9776 | 13.0939 | 57899973.2 | 55874133.4 | 2022 | ALPHA RYDER CONSTRUCTION & SUPPLIES | 7699 | 2022 | 2022-10-18 | 04/06/2022 | 2025839.8 | 0 | 2022-10-17 |  | 1
2023 | Region VII | CEBU | TOLEDO CITY (CEBU) | P00721824VS | Construction of Flood Mitigation Structure | 123.6672 | 10.3516 | 49000000 | 48994486.8 | 2024 | JJ &J CONSTRUCTION & GENERAL SUPPLY | 7700 | 2023 | 2024-03-01 | 06/01/2023 | 5513.2 | 0 | 2024-03-02 | 1
2023 | Region VII | CEBU | CEBU CITY (CAPITAL) (CEBU) | P00721784VS | Construction of Flood Mitigation Structure | 123.856 | 10.3069 | 96500000 | 96396340.74 | 2024 | BNR CONSTRUCTION & DEVELOPMENT CORP. | 7701 | 2023 | 2024-03-05 | 05/23/2023 | 103659.26 | 0 | 2024-03-04 |  | 1
2024 | Region VII | CEBU | RONDA (CEBU) | P00834667VS | Construction of Flood Mitigation Structure | 123.4182 | 10.0045 | 48996358.28 | 48996321.52 | 2024 | RDY BUILDERS CONSTRUCTION AND GENERAL MERCHANDISE / MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY | 7702 | 2024 | 2024-05-20 | 03/18/2024 | 36.76 | 0 | 2024-10-21 | 154
2022 | Region V | SORSOGON | CITY OF SORSOGON (CAPITAL) (SORSOGON) | P00620756LZ | Construction of Flood Mitigation Structure | 124.1171 | 13.0672 | 36451065.52 | 12421484.87 | 2022 | MUNTOPAR BUILDERS CORP. | 7703 | 2022 | 2022-11-26 | 03/11/2022 | 24029580.65 | 0 | 2022-11-25 |  | 1
2023 | Region X | LANAO DEL NORTE | LALA (LANAO DEL NORTE) | P00721422MN | Construction of Flood Mitigation Structure | 123.7706 | 7.9165 | 110800000 | 108491280.9 | 2024 | LANAO BUILDER AND ENTERPRISES | 7704 | 2023 | 2024-07-04 | 02/13/2023 | 2308719.1 | 0 | 2024-07-03 |  | 1
2023 | Region VII | BOHOL | BUENAVISTA (BOHOL) | P00721940VS | Construction of Flood Mitigation Structure | 124.1172 | 10.0442 | 39200000 | 39100000 | 2024 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R | 7705 | 2023 | 2024-11-26 | 05/04/2023 | 100000 | 0 | 2023-11-19 |  | 373
2022 | Region V | ALBAY | CITY OF LIGAO (ALBAY) | P00620691LZ | Construction of Flood Mitigation Structure | 123.542 | 13.2537 | 29400000 | 29400000 | 2022 | NGS CONSTRUCTION SUPPLY | 7706 | 2022 | 2022-10-15 | 04/04/2022 | 0 | 0 | 2022-10-14 |  | 1
2024 | Region VII | BOHOL | TUBIGON (BOHOL) | P00820178VS | Construction of Flood Mitigation Structure | 123.917 | 9.9316 | 4900000 | 4890000 | 2024 | NENIAL CONSTRUCTION | 7707 | 2024 | 2024-07-18 | 04/11/2024 | 10000 | 0 | 2024-07-17 |  | 1
2023 | Region V | ALBAY | POLANGUI (ALBAY) | P00726626LZ | Construction of Flood Mitigation Structure | 123.4185 | 13.3255 | 125336435.3 | 125336435 | 2023 | MAKAPA CORPORATION | 7708 | 2023 | 2023-12-19 | 04/20/2023 | 0.3 | 0 | 2024-04-13 | 116
2021 | Region V | ALBAY |  | P00526196LZ | Construction of Flood Mitigation Structure | 123.7707 | 13.0401 | 29398367.15 | 29398110.84 | 2022 | ANKOR GAULLE CONSTRUCTION AND SUPPLY CORPORATION | 7709 | 2021 | 2022-07-12 | 03/02/2022 | 256.31 | 0 | 2022-07-23 | 11
2022 | Region VII | BOHOL | BUENAVISTA (BOHOL) | P00630188VS | Construction of Flood Mitigation Structure | 124.1215 | 10.051 | 66585000 | 66585000 | 2023 | CEBU 7H TECHNOCHEM INDUSTRIES, INC. / PLD CONSTRUCTION AND DEVELOPMENT INC. (FORMERLY: PLD CONSTRUCTION) | 7710 | 2022 | 2023-10-30 | 08/11/2022 | 0 | 0 | 2023-09-30 |  | 30
2023 | Region V | SORSOGON | CITY OF SORSOGON (CAPITAL) (SORSOGON) | P00742483LZ | Construction of Flood Mitigation Structure | 123.9786 | 13.093 | 52469973.68 | 51124338.4 | 2023 | ALPHA RYDER CONSTRUCTION & SUPPLIES | 7711 | 2023 | 2023-11-08 | 03/27/2023 | 1345635.28 | 0 | 2023-11-07 |  | 1
2022 | Region V | CAMARINES SUR | LAGONOY (CAMARINES SUR) | P00631419LZ | Construction of Flood Mitigation Structure | 123.5429 | 13.9319 | 49000000 | 49000000 | 2023 | E. GARCIA CONSTRUCTION CORP.(FOR. E. GARCIA CONST | 7712 | 2022 | 2023-11-21 | 03/10/2022 | 0 | 0 | 2023-10-11 |  | 41
2024 | Region V | ALBAY | LIBON (ALBAY) | P00821003LZ | Construction of Flood Mitigation Structure | 123.4186 | 13.3255 | 9800000 | 9800000 | 2024 | SISBRO CONSTRUCTION CORPORATION (FORMERLY: SISBRO CONSTRUCTION & SUPPLY) | 7713 | 2024 | 2024-07-02 | 03/18/2024 | 0 | 0 | 2024-07-14 | 12
2022 | Region V | SORSOGON | CASTILLA (SORSOGON) | P00630987LZ | Construction of Flood Mitigation Structure | 123.857 | 12.9727 | 67549984.7 | 67548745.83 | 2023 | CENTERWAYS CONSTRUCTION AND DEVELOPMENT INC. | 7714 | 2022 | 2023-02-13 | 04/06/2022 | 1238.87 | 0 | 2023-02-12 |  | 1
2023 | Region V | MASBATE | CAWAYAN (MASBATE) | P00726307LZ | Construction of Flood Mitigation Structure | 123.7712 | 11.9275 | 23509608.55 | 23506539.35 | 2023 | JOHNCB CONSTRUCTION & SUPPLIES | 7715 | 2023 | 2023-08-29 | 02/13/2023 | 3069.2 | 0 | 2023-09-18 | 20
2024 | Region X | MISAMIS OCCIDENTAL | TANGUB CITY (MISAMIS OCCIDENTAL) | P00835873MN | Construction of Drainage Structure | 123.669 | 8.1029 | 4900000 | 4752999.28 | 2024 | WEISENWORK CONSTRUCTION | 7716 | 2024 | 2024-09-24 | 06/21/2024 | 147000.72 | 0 | 2024-09-26 | 2
2024 | Region VII | CEBU | CITY OF BOGO (CEBU) | P00820186VS | Construction of Flood Mitigation Structure | 123.9812 | 10.999 | 29400000 | 29400000 | 2024 | DINAH RBS CONSTRUCTION AND SUPPLY INCORPORATED (FORMERLY: DINAH JANE CONSTRUCTION AND SUPPLY) | 7717 | 2024 | 2024-08-05 | 02/13/2024 | 0 | 0 | 2024-08-04 |  | 1
2022 | Region V | SORSOGON | BARCELONA (SORSOGON) | P00640587LZ | Construction of Flood Mitigation Structure | 124.1271 | 12.8604 | 15840000 | 15523200 | 2022 | ALHADRAX CONSTRUCTION AND SUPPLY | 7718 | 2022 | 2022-11-16 | 06/21/2022 | 316800 | 0 | 2022-11-15 |  | 1
2022 | Region V | ALBAY | POLANGUI (ALBAY) | P00620296LZ | Construction of Flood Mitigation Structure | 123.419 | 13.3258 | 192707498.1 | 192707498.1 | 2023 | RAMARPLUS INCORPORATED (FORMERLY RAMAR ENTERPRISES | 7719 | 2022 | 2023-01-24 | 03/21/2022 | 0 | 0 | 2023-01-23 |  | 1
2022 | Region V | MASBATE | DIMASALANG (MASBATE) | P00631471LZ | Construction of Slope Protection Structure | 123.8576 | 12.1944 | 48999921.4 | 48985300.98 | 2023 | SPRING STAR CONSTRUCTION AND SUPPLY | 7720 | 2022 | 2023-01-04 | 02/16/2022 | 14620.42 | 0 | 2023-01-03 |  | 1
2021 | Region X | LANAO DEL NORTE |  | P00522342MN | Construction of Flood Mitigation Structure | 123.7715 | 7.9169 | 34687500 | 32884498.68 | 2022 | LANAO BUILDER AND ENTERPRISES | 7721 | 2021 | 2022-12-16 | 04/13/2022 | 1803001.32 | 0 | 2023-01-12 | 27
2022 | Region V | SORSOGON | PILAR (SORSOGON) | P00639549LZ | Construction of Flood Mitigation Structure | 123.6713 | 12.9199 | 58799990.39 | 19599587.99 | 2023 | MUNTOPAR BUILDERS CORP. | 7722 | 2022 | 2023-06-01 | 04/04/2022 | 39200402.4 | 0 | 2023-05-31 |  | 1
2022 | Region VII | CEBU | CEBU CITY (CAPITAL) (CEBU) | P00620132VS | Construction of Flood Mitigation Structure | 123.9191 | 10.3892 | 27504680 | 26592415.28 | 2023 | SBD BUILDERS | 7723 | 2022 | 2023-05-19 | 02/22/2022 | 912264.72 | 0 | 2022-12-02 |  | 168
2022 | Region V | ALBAY | CITY OF LIGAO (ALBAY) | P00620306LZ | Construction of Flood Mitigation Structure | 123.5446 | 13.2524 | 106149935.7 | 106149935.7 | 2023 | G.C.I. CONSTRUCTION AND DEV'T. CORP. | 7724 | 2022 | 2023-07-13 | 07/25/2022 | 0 | 0 | 2023-07-12 |  | 1
2022 | Region V | SORSOGON | MATNOG (SORSOGON) | P00640590LZ | Construction of Flood Mitigation Structure | 123.9821 | 12.5548 | 19800000 | 18245676.54 | 2023 | MAGDA CONSTRUCTION AND SUPPLY INC. | 7725 | 2022 | 2023-08-02 | 06/24/2022 | 1554323.46 | 0 | 2023-08-18 | 16
2022 | Region X | LANAO DEL SUR | BALABAGAN (LANAO DEL SUR) | P00634128MN | Construction of Flood Mitigation Structure | 124.1271 | 7.5133 | 6930000 | 6860609.84 | 2022 | TESAR BUILDERS | 7726 | 2022 | 2022-10-26 | 06/29/2022 | 69390.16 | 0 | 2022-10-25 |  | 1
2022 | Region IX | ZAMBOANGA DEL SUR | PAGADIAN CITY (CAPITAL) (ZAMBOANGA DEL SUR) | P00630566MN | Construction of Flood Mitigation Structure | 123.4197 | 7.8258 | 19600000 | 15639498.93 | 2022 | L.C. CONSTRUCTION CORPORATION (FOR: L.C. CONSTRUCTION) | 7727 | 2022 | 2022-12-16 | 02/16/2022 | 3960501.07 | 0 | 2022-09-05 |  | 102
2022 | Region V | SORSOGON | CASTILLA (SORSOGON) | P00640592LZ | Construction of Flood Mitigation Structure | 123.8577 | 12.9168 | 49499987.41 | 24749997.68 | 2023 | ALNINO CONSTRUCTION & SUPPLY CORPORATION (FORMERLY: AL NINO CONSTRUCTION & SUPPLY) | 7728 | 2022 | 2023-05-05 | 04/04/2022 | 24749989.73 | 0 | 2023-05-06 | 1
2023 | Region V | ALBAY | MALINAO (ALBAY) | P00740655LZ | Construction of Flood Mitigation Structure | 123.675 | 13.3787 | 95059998.36 | 48020000 | 2023 | STEVEN CONSTRUCTION & SUPPLY | 7729 | 2023 | 2023-10-27 | 05/09/2023 | 47039998.36 | 0 | 2024-01-01 | 66
2024 | Region V | CAMARINES SUR | SAN JOSE (CAMARINES SUR) | P00820472LZ | Construction of Flood Mitigation Structure | 123.5454 | 13.677 | 96500000 | 96500000 | 2025 | ALRO CONSTRUCTION & DEVELOPMENT CORP. | 7730 | 2024 | 2025-02-10 | 02/28/2024 | 0 | 0 | 2025-03-03 | 21
2023 | Region VII | BOHOL | BALILIHAN (BOHOL) | P00721663VS | Construction of Flood Mitigation Structure | 123.9869 | 9.7667 | 4900000 | 4885000 | 2023 | HUSAIN CONSTRUCTION AND SUPPLY CO. | 7731 | 2023 | 2023-04-25 | 02/16/2023 | 15000 | 0 | 2023-04-24 |  | 1
2023 | Region X | LANAO DEL SUR | POONA BAYABAO (GATA) (LANAO DEL SUR) | P00721664MN | Construction of Flood Mitigation Structure | 124.128 | 7.5077 | 28950000 | 28658991.24 | 2023 | M.M.A. ACHIEVER CONSTRUCTION & DEVELOPMENT CORP. | 7732 | 2023 | 2023-08-31 | 04/11/2023 | 291008.76 | 0 | 2023-08-30 |  | 1
2022 | Region VII | CEBU | RONDA (CEBU) | P00620045VS | Construction of Flood Mitigation Structure | 123.4201 | 10.0306 | 29398308.21 | 29398308.21 | 2022 | DT&C CONSTRUCTION | 7733 | 2022 | 2022-08-18 | 02/10/2022 | 0 | 0 | 2022-08-17 |  | 1
2024 | Region X | MISAMIS OCCIDENTAL | LOPEZ JAENA (MISAMIS OCCIDENTAL) | P00821222MN | Construction of Flood Mitigation Structure | 123.7721 | 8.5501 | 37240000 | 37239990.16 | 2025 | MINDANAO ROCK | 7734 | 2024 | 2025-03-21 | 03/11/2024 | 9.84 | 0 | 2025-02-02 |  | 47
2022 | Region V | SORSOGON | MAGALLANES (SORSOGON) | P00620286LZ | Construction of Flood Mitigation Structure | 123.8599 | 12.7919 | 57899981.64 | 57892326.39 | 2023 | CENTERWAYS CONSTRUCTION AND DEVELOPMENT INC. | 7735 | 2022 | 2023-03-10 | 03/21/2022 | 7655.25 | 0 | 2023-03-09 |  | 1
2022 | Region V | SORSOGON | PILAR (SORSOGON) | P00639548LZ | Construction of Flood Mitigation Structure | 123.6764 | 12.9267 | 58799990.39 | 39199962.76 | 2023 | MUNTOPAR BUILDERS CORP. | 7736 | 2022 | 2023-06-01 | 04/04/2022 | 19600027.63 | 0 | 2023-05-31 |  | 1
2024 | Region VII | CEBU | CEBU CITY (CAPITAL) (CEBU) | P00820334VS | Construction of Flood Mitigation Structure | 123.9203 | 10.3909 | 144750000 | 144594682.6 | 2024 | FLUSSKREBS CONSTRUCTORS / BNR CONSTRUCTION & DEVELOPMENT CORP. | 7737 | 2024 | 2024-11-28 | 03/07/2024 | 155317.4 | 0 | 2024-12-18 | 20
2022 | Region V | ALBAY | OAS (ALBAY) | P00631354LZ | Construction of Flood Mitigation Structure | 123.5495 | 13.2898 | 19600000 | 19600000 | 2023 | ELKANKONSTRAK DEVELOPMENT CORPORATION | 7738 | 2022 | 2023-01-06 | 07/11/2022 | 0 | 0 | 2023-01-05 |  | 1
2023 | Region VI | NEGROS OCCIDENTAL | SAN CARLOS CITY (NEGROS OCCIDENTAL) | P00733700VS | Construction of Flood Mitigation Structure | 123.4212 | 10.4817 | 19799844 | 19800000 | 2023 | KENNETH CONSTRUCTION AND GENERAL MERCHANDISE | 7739 | 2023 | 2023-10-29 | 04/27/2023 | 0 | 156 | 2023-10-28 |  | 1
2023 | Region VII | CEBU | CITY OF BOGO (CEBU) | P00721534VS | Construction of Flood Mitigation Structure | 123.9869 | 11.052 | 67550000 | 67550000 | 2023 | GONZALODO ENTERPRISES / RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R | 7740 | 2023 | 2023-10-27 | 02/14/2023 | 0 | 0 | 2023-10-26 |  | 1
2023 | Region X | LANAO DEL NORTE | LALA (LANAO DEL NORTE) | P00721495MN | Construction of Flood Mitigation Structure | 123.7721 | 7.9195 | 48995500 | 48448879.15 | 2024 | LANAO BUILDER AND ENTERPRISES | 7741 | 2023 | 2024-02-22 | 08/10/2023 | 546620.85 | 0 | 2024-04-05 | 43
2023 | Region X | MISAMIS OCCIDENTAL | CLARIN (MISAMIS OCCIDENTAL) | P00721257MN | Rehabilitation / Major Repair of Slope Protection Structure | 123.86 | 8.1906 | 49000000 | 47529999.47 | 2023 | MINDANAO ROCK | 7742 | 2023 | 2023-12-11 | 02/20/2023 | 1470000.53 | 0 | 2023-11-21 |  | 20
2023 | Region V | ALBAY | DARAGA (LOCSIN) (ALBAY) | P00727212LZ | Construction of Dike | 123.6768 | 13.1372 | 48809911.73 | 48809805.94 | 2023 | VERZONTAL INFRASTRUCTURE CORPORATION (FORMERLY: VERZONTAL BUILDERS, INC.) | 7743 | 2023 | 2023-09-17 | 03/21/2023 | 105.79 | 0 | 2023-09-16 |  | 1
2022 | Region VII | BOHOL | ANTEQUERA (BOHOL) | P00620308VS | Construction of Flood Mitigation Structure | 123.9204 | 9.743 | 49000000 | 47914729.53 | 2022 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R / HERBERT MALMIS GENERAL MERCHANDISING & CONTRACTOR | 7744 | 2022 | 2022-11-15 | 02/23/2022 | 1085270.47 | 0 | 2022-11-14 |  | 1
2024 | Region V | ALBAY | OAS (ALBAY) | P00824784LZ | Construction of Flood Mitigation Structure | 123.5527 | 13.6757 | 51940000 | 51940000 | 2024 | SPRING STAR CONSTRUCTION AND SUPPLY | 7745 | 2024 | 2024-12-12 | 04/02/2024 | 0 | 0 | 2024-12-26 | 14
2021 | Region V | CATANDUANES |  | P00561199LZ | Construction of Flood Mitigation Structure | 124.1307 | 13.9833 | 29398758.79 | 29397518.79 | 2022 | JASMIN CONSTRUCTION | 7746 | 2021 | 2022-12-31 | 09/06/2022 | 1240 | 0 | 2023-02-16 | 47
2024 | Region VII | CEBU | RONDA (CEBU) | P00834586VS | Construction of Flood Mitigation Structure | 123.4215 | 10.0064 | 57896963.4 | 57896463.4 | 2024 | CENTERWAYS CONSTRUCTION AND DEVELOPMENT INC. | 7747 | 2024 | 2024-06-13 | 02/16/2024 | 500 | 0 | 2024-10-04 | 113
2023 | Region VII | CEBU | CEBU CITY (CAPITAL) (CEBU) | P00732024VS | Construction of Flood Mitigation Structure | 123.86 | 10.2709 | 9900000 | 9884041.44 | 2024 | BELCONSTRUCT CORPORATION | 7748 | 2023 | 2024-02-07 | 08/17/2023 | 15958.56 | 0 | 2024-02-06 |  | 1
2023 | Region VII | CEBU | CEBU CITY (CAPITAL) (CEBU) | P00721837VS | Construction of Flood Mitigation Structure | 123.9205 | 10.3915 | 44100000 | 43999790.93 | 2023 | FLUSSKREBS CONSTRUCTORS | 7749 | 2023 | 2023-12-19 | 03/20/2023 | 100209.07 | 0 | 2023-12-16 |  | 3
2021 | Region VII | CEBU |  | P00550016VS | Construction of Flood Mitigation Structure | 123.6769 | 10.3383 | 14850000 | 14849542.74 | 2022 | O.Q. CONSTRUCTION AND SUPPLY | 7750 | 2021 | 2022-09-09 | 01/11/2022 | 457.26 | 0 | 2022-08-06 |  | 34
2022 | Region V | SORSOGON | CITY OF SORSOGON (CAPITAL) (SORSOGON) | P00630962LZ | Construction of Slope Protection Structure | 123.9872 | 12.9842 | 67549981.59 | 67547282.86 | 2022 | CENTERWAYS CONSTRUCTION AND DEVELOPMENT INC. | 7751 | 2022 | 2022-12-27 | 02/17/2022 | 2698.73 | 0 | 2022-12-26 |  | 1
2022 | Region V | CAMARINES SUR | LAGONOY (CAMARINES SUR) | P00639546LZ | Construction of Flood Mitigation Structure | 123.553 | 13.884 | 49000000 | 49000000 | 2023 | E.A. SANCHO CONST. INC. (FORM. E.A. SANCHO CONST.) | 7752 | 2022 | 2023-06-12 | 05/25/2022 | 0 | 0 | 2023-06-11 |  | 1
2021 | Region V | CATANDUANES |  | P00561433LZ | Construction of Flood Mitigation Structure | 124.1307 | 13.985 | 9898760 | 9898760 | 2022 | A.V. LAYNES TRADING AND CONSTRUCTION | 7753 | 2021 | 2022-07-01 | 01/18/2022 | 0 | 0 | 2022-06-30 |  | 1
2023 | Region VII | CEBU | RONDA (CEBU) | P00721893VS | Construction of Dike | 123.4215 | 10.0012 | 96497669.07 | 96497499.84 | 2023 | JCM AMEG BUILDERS CORPORATION (FORMERLY: AMEG CONSTRUCTION & SUPPLY) | 7754 | 2023 | 2023-07-10 | 03/16/2023 | 169.23 | 0 | 2024-01-15 | 189
2022 | Region X | LANAO DEL NORTE | LALA (LANAO DEL NORTE) | P00620212MN | Construction of Flood Mitigation Structure | 123.7725 | 7.9192 | 102983835 | 99375933.66 | 2023 | KOUZBARY BUILDERS / LANAO BUILDER AND ENTERPRISES | 7755 | 2022 | 2023-01-14 | 03/21/2022 | 3607901.34 | 0 | 2023-01-13 |  | 1
2021 | Region V | ALBAY |  | P00561195LZ | Construction of Flood Mitigation Structure | 123.6781 | 13.3823 | 29699985.6 | 19800000 | 2022 | JORMAND CONSTRUCTION & SUPPLY | 7756 | 2021 | 2022-09-15 | 04/19/2022 | 9899985.6 | 0 | 2022-09-14 |  | 1
2024 | Region VII | CEBU | CITY OF BOGO (CEBU) | P00834643VS | Construction of Flood Mitigation Structure | 123.9872 | 11.055 | 49000000 | 49000000 | 2025 | QM BUILDERS / ADAMANT DEVELOPMENT CORPORATION | 7757 | 2024 | 2025-02-09 | 07/24/2024 | 0 | 0 | 2025-02-08 |  | 1
2024 | Region VII | CEBU | CEBU CITY (CAPITAL) (CEBU) | P00820332VS | Construction of Flood Mitigation Structure | 123.9206 | 10.3799 | 144750000 | 144598801.2 | 2024 | A.S.T BUILDERS / BNR CONSTRUCTION & DEVELOPMENT CORP. | 7758 | 2024 | 2024-11-19 | 03/07/2024 | 151198.8 | 0 | 2024-12-18 | 29
2022 | Region VII | SIQUIJOR | SIQUIJOR (CAPITAL) (SIQUIJOR) | P00630228VS | Construction of Slope Protection Structure | 123.5535 | 9.1452 | 19600000 | 19600000 | 2022 | HELM CONSTRUCTION & SUPPLIES / W.GO CONSTRUCTION AND SUPPLY | 7759 | 2022 | 2022-09-09 | 02/10/2022 | 0 | 0 | 2022-09-10 | 1
2022 | Region V | CATANDUANES | CARAMORAN (CATANDUANES) | P00631454LZ | Construction of Flood Mitigation Structure | 124.1307 | 13.9863 | 9798760 | 9798760 | 2022 | NIDA BUILDER'S & SUPPLIES | 7760 | 2022 | 2022-07-16 | 03/02/2022 | 0 | 0 | 2022-07-24 | 8
2024 | Region V | MASBATE | DIMASALANG (MASBATE) | P00821016LZ | Construction of Flood Mitigation Structure | 123.8609 | 12.189 | 48956486.55 | 48942303.93 | 2024 | 3R3M CONSTRUCTION AND SUPPLY CORPORATION (FORMERLY: 3R3M CONSTRUCTION AND SUPPLY) | 7761 | 2024 | 2024-09-11 | 02/15/2024 | 14182.62 | 0 | 2024-09-10 |  | 1
2022 | Region V | CAMARINES SUR | IRIGA CITY (CAMARINES SUR) | P00620329LZ | Rehabilitation / Major Repair of Flood Control Structure | 123.4223 | 13.4876 | 77200000 | 77199986.09 | 2022 | CENTERWAYS CONSTRUCTION AND DEVELOPMENT INC. | 7762 | 2022 | 2022-10-14 | 03/21/2022 | 13.91 | 0 | 2022-11-25 | 42
2022 | Region X | LANAO DEL NORTE | KOLAMBUGAN (LANAO DEL NORTE) | P00620148MN | Construction of Slope Protection Structure | 123.9211 | 8.1278 | 49000000 | 49000000 | 2022 | LANAO BUILDER AND ENTERPRISES | 7763 | 2022 | 2022-12-10 | 03/18/2022 | 0 | 0 | 2022-12-14 | 4
2023 | Region VII | CEBU | CITY OF BOGO (CEBU) | P00733737VS | Construction of Flood Mitigation Structure | 123.9881 | 11.0073 | 4950000 | 4950000 | 2023 | Z & G CONSTRUCTION SERVICES | 7764 | 2023 | 2023-06-10 | 04/11/2023 | 0 | 0 | 2023-06-09 |  | 1
2024 | Region VII | CEBU | MANDAUE CITY (CEBU) | P00834575VS | Construction of Flood Mitigation Structure | 123.9213 | 10.3386 | 67550000 | 67450000 | 2025 | ZLREJ TRADING AND CONSTRUCTION CORPORATION | 7765 | 2024 | 2025-03-20 | 09/11/2024 | 100000 | 0 | 2025-03-30 | 10
2024 | Region V | ALBAY | MALINAO (ALBAY) | P00823644LZ | Construction of Flood Mitigation Structure | 123.6783 | 13.4044 | 48249999.1 | 48250000 | 2024 | OMEGA CONTRACTING AND DEVELOPMENT CORP. / STEVEN CONSTRUCTION & SUPPLY | 7766 | 2024 | 2024-08-28 | 04/16/2024 | 0 | 0.9 | 2024-09-06 | 9
2023 | Region V | MASBATE | CITY OF MASBATE (CAPITAL) (MASBATE) | P00726301LZ | Construction of Flood Mitigation Structure | 123.5583 | 12.2701 | 48999950.6 | 49000000 | 2023 | RED DIAMOND CONSTRUCTION AND SUPPLY CORPORATION (FORMERLY: RED DIAMOND CONSTRUCTION) | 7767 | 2023 | 2023-05-16 | 02/01/2023 | 0 | 49.4 | 2023-09-10 | 117
2022 | Region V | ALBAY | BACACAY (ALBAY) | P00631340LZ | Rehabilitation / Major Repair of Flood Control Structure | 123.7732 | 13.3045 | 24499987.87 | 24500000 | 2022 | 8AR CONSTRUCTION AND DEVELOPMENT CORPORATION | 7768 | 2022 | 2022-07-25 | 03/11/2022 | 0 | 12.13 | 2022-08-02 | 8
2023 | Region VII | CEBU | CEBU CITY (CAPITAL) (CEBU) | P00721834VS | Construction of Flood Mitigation Structure | 123.9229 | 10.3687 | 44100000 | 43973120.48 | 2023 | BNR CONSTRUCTION & DEVELOPMENT CORP. | 7769 | 2023 | 2023-10-22 | 03/21/2023 | 126879.52 | 0 | 2023-12-20 | 59
2022 | Region XII | SULTAN KUDARAT | KALAMANSIG (SULTAN KUDARAT) | P00620096MN | Construction of Flood Mitigation Structure | 124.1358 | 6.532 | 91675000 | 91675000 | 2023 | JARGON CONSTRUCTION & SUPPLY | 7770 | 2022 | 2023-02-22 | 02/21/2022 | 0 | 0 | 2023-01-18 |  | 35
2021 | Region V | SORSOGON |  | P00526250LZ | Construction of Flood Mitigation Structure | 123.8616 | 12.9851 | 45079959.5 | 43509157.93 | 2022 | CENTERWAYS CONSTRUCTION AND DEVELOPMENT INC. | 7771 | 2021 | 2022-09-02 | 01/12/2022 | 1570801.57 | 0 | 2022-09-01 |  | 1
2024 | Region VII | CEBU | CITY OF BOGO (CEBU) | P00821055VS | Construction of Flood Mitigation Structure | 123.9885 | 11.0185 | 19600000 | 19600000 | 2024 | ADAMANT DEVELOPMENT CORPORATION | 7772 | 2024 | 2024-12-21 | 07/10/2024 | 0 | 0 | 2024-12-20 |  | 1
2023 | Region V | ALBAY | DARAGA (LOCSIN) (ALBAY) | P00725885LZ | Construction of Flood Mitigation Structure | 123.6786 | 13.1745 | 48222505.2 | 48222482.56 | 2023 | CENTERWAYS CONSTRUCTION AND DEVELOPMENT INC. | 7773 | 2023 | 2023-11-11 | 03/15/2023 | 22.64 | 0 | 2023-11-10 |  | 1
2022 | Region V | CAMARINES SUR | IRIGA CITY (CAMARINES SUR) | P00620330LZ | Rehabilitation / Major Repair of Flood Control Structure | 123.4223 | 13.4876 | 77200000 | 77199756.92 | 2022 | CENTERWAYS CONSTRUCTION AND DEVELOPMENT INC. | 7774 | 2022 | 2022-09-22 | 03/21/2022 | 243.08 | 0 | 2022-11-25 | 64
2023 | Region V | ALBAY | CITY OF LIGAO (ALBAY) | P00726986LZ | Construction of Flood Mitigation Structure | 123.5676 | 13.2602 | 115799772.2 | 115799772.2 | 2024 | 3DIAMONDS CONSTRUCTION CORPORATION | 7775 | 2023 | 2024-03-20 | 10/05/2023 | 0 | 0 | 2024-07-20 | 122
2021 | Region V | ALBAY |  | P00526173LZ | Construction of Flood Mitigation Structure | 123.7733 | 13.3047 | 24619763.98 | 12740000 | 2022 | DSB CONSTRUCTION & SUPPLY, INC. (FORMERLY: DSB CO | 7776 | 2021 | 2022-09-17 | 04/26/2022 | 11879763.98 | 0 | 2022-09-16 |  | 1
2024 | Region VII | CEBU | MANDAUE CITY (CEBU) | P00834652VS | Construction of Flood Mitigation Structure | 123.9235 | 10.3348 | 4900000 | 4884986.38 | 2024 | EMMARC CONSTRUCTION | 7777 | 2024 | 2024-10-11 | 04/19/2024 | 15013.62 | 0 | 2024-10-10 |  | 1
2024 | Region V | SORSOGON | BULUSAN (SORSOGON) | P00839680LZ | Construction of Flood Mitigation Structure | 124.1366 | 12.766 | 9900000 | 4851786.65 | 2024 | GDBS BUILDERS AND ENTERPRISE | 7778 | 2024 | 2024-04-25 | 02/16/2024 | 5048213.35 | 0 | 2024-04-24 |  | 1
2022 | Region VI | NEGROS OCCIDENTAL | SAGAY CITY (NEGROS OCCIDENTAL) | P00630632VS | Construction of Drainage Structure | 123.4223 | 10.9377 | 9899992.73 | 9898000 | 2023 | KENBE CONSTRUCTION & SUPPLY | 7779 | 2022 | 2023-02-28 | 02/08/2022 | 1992.73 | 0 | 2022-05-27 |  | 277
2022 | Region V | ALBAY | BACACAY (ALBAY) | P00631326LZ | Construction of Flood Mitigation Structure | 123.7738 | 13.3064 | 34299996.45 | 9800000 | 2022 | DSB CONSTRUCTION & SUPPLY, INC. (FORMERLY: DSB CO | 7780 | 2022 | 2022-09-30 | 05/30/2022 | 24499996.45 | 0 | 2022-10-31 | 31
2023 | Region V | MASBATE | CITY OF MASBATE (CAPITAL) (MASBATE) | P00726298LZ | Construction of Flood Mitigation Structure | 123.5702 | 12.3276 | 48999977.5 | 49000000 | 2023 | HKP CONSTRUCTION AND SUPPLY / A3 CONSTRUCTION & SUPPLY | 7781 | 2023 | 2023-06-15 | 04/11/2023 | 0 | 22.5 | 2023-11-18 | 156
2023 | Region VII | CEBU | CONSOLACION (CEBU) | P00733281VS | Construction of Slope Protection Structure | 123.9235 | 10.4274 | 67550000 | 67499225.33 | 2024 | VICENTE T. LAO CONSTRUCTION | 7782 | 2023 | 2024-02-02 | 05/18/2023 | 50774.67 | 0 | 2024-02-04 | 2
2023 | Region V | ALBAY | DARAGA (LOCSIN) (ALBAY) | P00726970LZ | Construction of Flood Mitigation Structure | 123.6819 | 13.1725 | 72343147 | 72342833.02 | 2023 | MUNTOPAR BUILDERS CORP. | 7783 | 2023 | 2023-10-31 | 04/05/2023 | 313.98 | 0 | 2023-11-15 | 15
2024 | Region VII | BOHOL | TAGBILARAN CITY (CAPITAL) (BOHOL) | P00832641VS | Construction of Drainage Structure | 123.8638 | 9.6396 | 4950000 | 4620000 | 2024 | 3N CONSTRUCTION & SUPPLY | 7784 | 2024 | 2024-10-06 | 05/28/2024 | 330000 | 0 | 2024-10-05 |  | 1
2023 | Region V | SORSOGON | BULUSAN (SORSOGON) | P00726317LZ | Construction of Flood Mitigation Structure | 124.1376 | 12.7456 | 58800000 | 28518879.11 | 2023 | CENTERWAYS CONSTRUCTION AND DEVELOPMENT INC. | 7785 | 2023 | 2023-11-15 | 04/11/2023 | 30281120.89 | 0 | 2023-12-14 | 29
2023 | Region V | ALBAY | SANTO DOMINGO (LIBOG) (ALBAY) | P00740446LZ | Construction of Flood Mitigation Structure | 123.8638 | 13.2967 | 96499999.52 | 96500000 | 2023 | HI-TONE CONSTRUCTION & DEVELOPMENT CORP. (FORMERLY | 7786 | 2023 | 2023-12-22 | 04/24/2023 | 0 | 0.48 | 2023-12-21 |  | 1
2022 | Region VII | CEBU | LILOAN (CEBU) | P00620027VS | Construction of Flood Mitigation Structure | 123.989 | 10.4347 | 86850000 | 86849993.95 | 2022 | BNR CONSTRUCTION & DEVELOPMENT CORP. / VSP STRUCTURE VENTURES CORP. (FORMERLY: VIRLO CONSTRUCTION) | 7787 | 2022 | 2022-12-31 | 03/07/2022 | 6.05 | 0 | 2022-12-30 |  | 1
2024 | Region V | SORSOGON | CASTILLA (SORSOGON) | P00820489LZ | Construction of Flood Mitigation Structure | 123.7739 | 12.952 | 115799996.2 | 111729100.9 | 2024 | CENTERWAYS CONSTRUCTION AND DEVELOPMENT INC. | 7788 | 2024 | 2024-11-06 | 02/21/2024 | 4070895.3 | 0 | 2024-11-05 |  | 1
2023 | Region V | SORSOGON | IROSIN (SORSOGON) | P00727226LZ | Construction of Flood Mitigation Structure | 123.9891 | 12.7325 | 68600000 | 38221649.44 | 2023 | AREMAR CONSTRUCTION CORPORATION | 7789 | 2023 | 2023-11-22 | 05/15/2023 | 30378350.56 | 0 | 2023-12-27 | 35
2022 | Region V | ALBAY | LIBON (ALBAY) | P00631003LZ | Rehabilitation / Major Repair of Flood Control Structure | 123.4224 | 13.3253 | 77200000 | 77199936.61 | 2022 | RICHMAR CONSTRUCTION | 7790 | 2022 | 2022-12-12 | 03/14/2022 | 63.39 | 0 | 2023-01-26 | 45
2022 | Region V | CAMARINES SUR | LAGONOY (CAMARINES SUR) | P00631420LZ | Construction of Flood Mitigation Structure | 123.5706 | 13.9173 | 49000000 | 49000000 | 2023 | E. GARCIA CONSTRUCTION CORP.(FOR. E. GARCIA CONST | 7791 | 2022 | 2023-06-24 | 03/17/2022 | 0 | 0 | 2023-06-29 | 5
2024 | Region V | ALBAY | CITY OF TABACO (ALBAY) | P00839659LZ | Construction of Flood Mitigation Structure | 123.6831 | 13.3496 | 6929999.21 | 6930000 | 2024 | 3RB CONSTRUCTION & SUPPLY | 7792 | 2024 | 2024-07-26 | 06/18/2024 | 0 | 0.79 | 2024-08-10 | 15
2023 | Region VII | CEBU | CONSOLACION (CEBU) | P00733288VS | Construction of Slope Protection Structure | 123.9262 | 10.4213 | 72332540 | 72332540 | 2023 | GONZALODO ENTERPRISES / RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R | 7793 | 2023 | 2023-11-17 | 05/18/2023 | 0 | 0 | 2023-11-30 | 13
2022 | Region V | CATANDUANES | SAN ANDRES (CALOLBON) (CATANDUANES) | P00631455LZ | Construction of Flood Mitigation Structure | 124.1404 | 13.5721 | 29398760 | 29398760 | 2023 | EURO CONSTRUCTION AND SUPPLY ( FORMERLY: EURO CONSTRUCTION AND TRADING) | 7794 | 2022 | 2023-06-16 | 03/02/2022 | 0 | 0 | 2023-05-07 |  | 40
2022 | Region V | CAMARINES SUR | CARAMOAN (CAMARINES SUR) | P00631426LZ | Construction of Slope Protection Structure | 123.8639 | 13.7683 | 29400000 | 29400000 | 2022 | IA FERRER CONSTRUCTION & SUPPLY | 7795 | 2022 | 2022-11-19 | 03/10/2022 | 0 | 0 | 2022-11-18 |  | 1
2022 | Region V | SORSOGON | GUBAT (SORSOGON) | P00620285LZ | Construction of Flood Mitigation Structure | 124.1433 | 12.9866 | 67550000 | 65185352.97 | 2022 | RMH CONSTRUCTION & SUPPLY / STEVEN CONSTRUCTION & SUPPLY | 7796 | 2022 | 2022-12-14 | 03/24/2022 | 2364647.03 | 0 | 2022-12-13 |  | 1
2023 | Region V | ALBAY | BACACAY (ALBAY) | P00740498LZ | Construction of Flood Mitigation Structure | 123.7744 | 13.3067 | 118739934.6 | 19300000 | 2024 | DSB CONSTRUCTION & SUPPLY, INC. (FORMERLY: DSB CO | 7797 | 2023 | 2024-03-06 | 05/15/2023 | 99439934.6 | 0 | 2024-03-05 |  | 1
2023 | Region V | SORSOGON | CITY OF SORSOGON (CAPITAL) (SORSOGON) | P00725898LZ | Construction of Flood Mitigation Structure | 123.9899 | 12.9832 | 83375978.68 | 83375874.08 | 2023 | CENTERWAYS CONSTRUCTION AND DEVELOPMENT INC. | 7798 | 2023 | 2023-11-30 | 02/23/2023 | 104.6 | 0 | 2023-12-08 | 8
2022 | Region V | ALBAY | CITY OF LIGAO (ALBAY) | P00630982LZ | Construction of Flood Mitigation Structure | 123.5764 | 13.2561 | 97100000 | 57828535.32 | 2023 | 3DIAMONDS CONSTRUCTION CORPORATION | 7799 | 2022 | 2023-07-15 | 04/07/2022 | 39271464.68 | 0 | 2023-07-14 |  | 1
2023 | Region VII | CEBU | RONDA (CEBU) | P00721895VS | Construction of Flood Mitigation Structure | 123.4225 | 10.0018 | 96498043.02 | 96497116.43 | 2023 | JCM AMEG BUILDERS CORPORATION (FORMERLY: AMEG CONSTRUCTION & SUPPLY) | 7800 | 2023 | 2023-07-10 | 03/16/2023 | 926.59 | 0 | 2024-01-23 | 197
2022 | Region VII | CEBU | CONSOLACION (CEBU) | P00632990VS | Construction of Slope Protection Structure | 123.927 | 10.4245 | 96500000 | 96500000 | 2023 | QUIRANTE CONSTRUCTION CORPORATION (FORMERLY: QUIRANTE CONSTRUCTION) / ZLREJ TRADING AND CONSTRUCTION CORPORATION | 7801 | 2022 | 2023-01-16 | 03/31/2022 | 0 | 0 | 2023-01-17 | 1
2023 | Region V | ALBAY | RAPU-RAPU (ALBAY) | P00726983LZ | Construction of Flood Mitigation Structure | 123.6854 | 13.3602 | 72368217.62 | 72367819.15 | 2024 | DSB CONSTRUCTION & SUPPLY, INC. (FORMERLY: DSB CO | 7802 | 2023 | 2024-01-15 | 07/03/2023 | 398.47 | 0 | 2024-01-17 | 2
2023 | Region VII | CEBU | CEBU CITY (CAPITAL) (CEBU) | P00721686VS | Construction of Flood Mitigation Structure | 123.8645 | 10.2984 | 9800000 | 9720072.79 | 2024 | YES CONSTRUCTION | 7803 | 2023 | 2024-05-07 | 11/15/2023 | 79927.21 | 0 | 2024-05-06 |  | 1
2022 | Region V | CATANDUANES | CARAMORAN (CATANDUANES) | P00639390LZ | Construction of Flood Mitigation Structure | 124.1441 | 13.7666 | 110974607.1 | 110974607.1 | 2023 | HI-TONE CONSTRUCTION & DEVELOPMENT CORP. (FORMERLY | 7804 | 2022 | 2023-06-28 | 07/25/2022 | 0 | 0 | 2023-06-27 |  | 1
2021 | Region V | SORSOGON |  | P00526344LZ | Construction of Flood Mitigation Structure | 123.9915 | 12.7822 | 289499939.2 | 144750000 | 2022 | MAKAPA CORPORATION | 7805 | 2021 | 2022-10-06 | 05/24/2021 | 144749939.2 | 0 | 2022-10-05 |  | 1
2023 | Region V | ALBAY | CITY OF LIGAO (ALBAY) | P00740680LZ | Construction of Flood Mitigation Structure | 123.5777 | 13.2562 | 48930000 | 48926316.82 | 2023 | HI-TONE CONSTRUCTION & DEVELOPMENT CORP. (FORMERLY | 7806 | 2023 | 2023-12-15 | 04/27/2023 | 3683.18 | 0 | 2023-12-14 |  | 1
2023 | Region V | SORSOGON | IROSIN (SORSOGON) | P00725904LZ | Rehabilitation / Major Repair of Flood Control Structure | 123.9916 | 12.7372 | 115800000 | 112322188.6 | 2024 | HI-TONE CONSTRUCTION & DEVELOPMENT CORP. (FORMERLY / CENTERWAYS CONSTRUCTION AND DEVELOPMENT INC. | 7807 | 2023 | 2024-04-30 | 10/06/2023 | 3477811.4 | 0 | 2024-09-13 | 136
2022 | Region V | ALBAY | CITY OF TABACO (ALBAY) | P00631335LZ | Rehabilitation / Major Repair of Flood Control Structure | 123.4225 | 13.1938 | 24499999.99 | 24500000 | 2022 | CAJUGOTAN BUILDERS AND DEVELOPMENT CORP. (FOR: CAJUGOTAN CONSTRUCTION & SUPPLY) | 7808 | 2022 | 2022-07-15 | 02/24/2022 | 0 | 0.01 | 2022-07-17 | 2
2024 | Region V | ALBAY | MALINAO (ALBAY) | P00820992LZ | Construction of Flood Mitigation Structure | 123.6854 | 13.3602 | 26949999.62 | 26950000 | 2024 | 8AR CONSTRUCTION AND DEVELOPMENT CORPORATION | 7809 | 2024 | 2024-08-12 | 03/18/2024 | 0 | 0.38 | 2024-08-11 |  | 1
2023 | Region V | CATANDUANES | CARAMORAN (CATANDUANES) | P00736062LZ | Construction of Flood Mitigation Structure | 124.1452 | 13.7648 | 192961477.8 | 192961477.8 | 2024 | SUNWEST, INC. (FORMERLY: SUNWEST CONSTRUCTION & DEVELOPMENT CORPORATION) | 7810 | 2023 | 2024-03-31 | 03/27/2023 | 0 | 0 | 2024-03-30 |  | 1
2022 | Region VII | CEBU | CITY OF TALISAY (CEBU) | P00633226VS | Construction of Flood Mitigation Structure | 123.8662 | 10.2532 | 14850000 | 14850000 | 2022 | QUIRANTE CONSTRUCTION CORPORATION (FORMERLY: QUIRANTE CONSTRUCTION) | 7811 | 2022 | 2022-09-30 | 04/13/2022 | 0 | 0 | 2022-09-30 | 0
2022 | Region V | SORSOGON | CASTILLA (SORSOGON) | P00631481LZ | Construction of Flood Mitigation Structure | 123.775 | 12.9522 | 58899904.98 | 9797426.1 | 2022 | CENTERWAYS CONSTRUCTION AND DEVELOPMENT INC. | 7812 | 2022 | 2022-09-12 | 03/17/2022 | 49102478.88 | 0 | 2022-09-11 |  | 1
2025 | Region VII | CEBU | CONSOLACION (CEBU) | P00936038VS | Construction of Drainage Structure | 123.9281 | 10.3971 | 4950000 | 4939190.15 | 2025 | XLA CONSTRUCTION | 7813 | 2025 | 2025-05-27 | 02/17/2025 | 10809.85 | 0 | 2025-05-27 | 0
2024 | Region V | MASBATE | MILAGROS (MASBATE) | P00820482LZ | Construction of Flood Mitigation Structure | 123.5786 | 12.2281 | 62724809.74 | 62724809.74 | 2024 | HKP CONSTRUCTION AND SUPPLY / A3 CONSTRUCTION & SUPPLY | 7814 | 2024 | 2024-10-16 | 02/20/2024 | 0 | 0 | 2024-10-26 | 10
2022 | Region V | SORSOGON | JUBAN (SORSOGON) | P00620320LZ | Construction of Flood Mitigation Structure | 123.9941 | 12.7944 | 174664974.6 | 174664974.6 | 2023 | MAKAPA CORPORATION | 7815 | 2022 | 2023-12-08 | 05/12/2022 | 0 | 0 | 2023-12-07 |  | 1
2023 | Region V | CAMARINES SUR | IRIGA CITY (CAMARINES SUR) | P00725903LZ | Rehabilitation / Major Repair of Flood Control Structure | 123.4226 | 13.4875 | 115642840.5 | 113285703 | 2024 | BICOL GOLDROCK CONSTRUCTION CORPORATION | 7816 | 2023 | 2024-03-14 | 07/12/2023 | 2357137.5 | 0 | 2024-08-01 | 140
2023 | Region V | ALBAY | CITY OF TABACO (ALBAY) | P00740479LZ | Construction of Flood Mitigation Structure | 123.6858 | 13.3339 | 135099999.9 | 135100000 | 2023 | SANRHO BUILDERS, INC.(FOR. SANRHO CONST. AND SUPPL | 7817 | 2023 | 2023-12-24 | 04/14/2023 | 0 | 0.1 | 2023-12-23 |  | 1
2022 | Region VII | BOHOL | TAGBILARAN CITY (CAPITAL) (BOHOL) | P00630645VS | Construction of Drainage Structure | 123.8673 | 9.6367 | 4950000 | 4836297.35 | 2023 | HUSAIN CONSTRUCTION AND SUPPLY CO. | 7818 | 2022 | 2023-04-03 | 03/24/2022 | 113702.65 | 0 | 2023-04-02 |  | 1
2023 | Region V | ALBAY | BACACAY (ALBAY) | P00726281LZ | Construction of Flood Mitigation Structure | 123.776 | 13.308 | 29399999.73 | 29400000 | 2023 | 8AR CONSTRUCTION AND DEVELOPMENT CORPORATION | 7819 | 2023 | 2023-08-15 | 03/27/2023 | 0 | 0.27 | 2023-09-21 | 37
2023 | Region VII | BOHOL | CALAPE (BOHOL) | P00721903VS | Construction of Flood Mitigation Structure | 123.8678 | 9.8792 | 51145000 | 50963842.39 | 2024 | BNYU DEVELOPMENT CORPORATION (FORMERLY:BNYU ENTERPRISES & CONSTRUCTION) | 7820 | 2023 | 2024-02-14 | 05/11/2023 | 181157.61 | 0 | 2024-02-13 |  | 1
2022 | Region VII | CEBU | CONSOLACION (CEBU) | P00632988VS | Construction of Slope Protection Structure | 123.9282 | 10.4276 | 96500000 | 96500000 | 2022 | QUIRANTE CONSTRUCTION CORPORATION (FORMERLY: QUIRANTE CONSTRUCTION) / ZLREJ TRADING AND CONSTRUCTION CORPORATION | 7821 | 2022 | 2022-12-19 | 03/31/2022 | 0 | 0 | 2023-01-17 | 29
2023 | Region VII | CEBU | PINAMUNGAJAN (CEBU) | P00721672VS | Construction of Flood Mitigation Structure | 123.5848 | 10.3098 | 49000000 | 48912091.55 | 2024 | VEN RAY CONSTRUCTION CORPORATION | 7822 | 2023 | 2024-11-09 | 06/01/2023 | 87908.45 | 0 | 2024-11-08 |  | 1
2023 | Region VII | CEBU | RONDA (CEBU) | P00721894VS | Construction of Flood Mitigation Structure | 123.423 | 10.0015 | 96497701.27 | 96497234.15 | 2023 | JCM AMEG BUILDERS CORPORATION (FORMERLY: AMEG CONSTRUCTION & SUPPLY) | 7823 | 2023 | 2023-06-29 | 03/16/2023 | 467.12 | 0 | 2024-01-23 | 208
2022 | Region X | MISAMIS OCCIDENTAL | PLARIDEL (MISAMIS OCCIDENTAL) | P00620155MN | Construction of Flood Mitigation Structure | 123.686 | 8.6086 | 29400000 | 29399995 | 2022 | RRJ BUILDERS CONSTRUCTION AND GENERAL MERCHANDISE | 7824 | 2022 | 2022-12-05 | 03/24/2022 | 5 | 0 | 2022-10-29 |  | 37
2023 | Region V | SORSOGON | BARCELONA (SORSOGON) | P00737579LZ | Construction of Flood Mitigation Structure | 124.1461 | 12.8458 | 54450000 | 9603000 | 2023 | ALHADRAX CONSTRUCTION AND SUPPLY | 7825 | 2023 | 2023-10-29 | 05/02/2023 | 44847000 | 0 | 2023-10-28 |  | 1
2023 | Region VII | CEBU | CARMEN (CEBU) | P00721771VS | Construction of Flood Mitigation Structure | 123.995 | 10.6037 | 106150000 | 106149965.2 | 2024 | MORTAR MASTERS & CONCRETE BUILDERS / VSP STRUCTURE VENTURES CORP. (FORMERLY: VIRLO CONSTRUCTION) | 7826 | 2023 | 2024-01-19 | 02/20/2023 | 34.8 | 0 | 2024-03-02 | 43
2022 | Region V | SORSOGON | BARCELONA (SORSOGON) | P00640589LZ | Construction of Drainage Structure | 124.1463 | 12.8618 | 19800000 | 19206000 | 2023 | ALHADRAX CONSTRUCTION AND SUPPLY | 7827 | 2022 | 2023-03-16 | 08/19/2022 | 594000 | 0 | 2023-03-15 |  | 1
2024 | Region V | SORSOGON | CASTILLA (SORSOGON) | P00820490LZ | Construction of Flood Mitigation Structure | 123.7764 | 12.9526 | 121589992.5 | 117298238.6 | 2024 | CENTERWAYS CONSTRUCTION AND DEVELOPMENT INC. | 7828 | 2024 | 2024-11-11 | 02/21/2024 | 4291753.9 | 0 | 2024-11-10 |  | 1
2023 | Region V | ALBAY | MANITO (ALBAY) | P00736070LZ | Construction of Dike | 123.8699 | 13.1138 | 96498496.16 | 96497986.44 | 2023 | JCM AMEG BUILDERS CORPORATION (FORMERLY: AMEG CONSTRUCTION & SUPPLY) | 7829 | 2023 | 2023-09-15 | 02/27/2023 | 509.72 | 0 | 2023-12-04 | 80
2024 | Region V | ALBAY | CITY OF LIGAO (ALBAY) | P00823622LZ | Construction of Flood Mitigation Structure | 123.5854 | 13.2405 | 96500000 | 96499961.98 | 2024 | SISBRO CONSTRUCTION CORPORATION (FORMERLY: SISBRO CONSTRUCTION & SUPPLY) | 7830 | 2024 | 2024-12-31 | 04/08/2024 | 38.02 | 0 | 2025-01-31 | 31
2023 | Region V | ALBAY | OAS (ALBAY) | P00740464LZ | Construction of Dike | 123.424 | 13.1695 | 72305000 | 72289030 | 2023 | RICHMAR CONSTRUCTION | 7831 | 2023 | 2023-10-23 | 04/27/2023 | 15970 | 0 | 2024-01-05 | 74
2023 | Region V | SORSOGON | CITY OF SORSOGON (CAPITAL) (SORSOGON) | P00740688LZ | Construction of Flood Mitigation Structure | 123.9951 | 12.9712 | 18129984.4 | 18129860.73 | 2023 | ALHADRAX CONSTRUCTION AND SUPPLY | 7832 | 2023 | 2023-10-20 | 05/25/2023 | 123.67 | 0 | 2023-10-19 |  | 1
2022 | Region VII | BOHOL | CATIGBIAN (BOHOL) | P00620031VS | Construction of Flood Mitigation Structure | 123.9954 | 9.8429 | 96500000 | 95439684.51 | 2023 | CEBU 7H TECHNOCHEM INDUSTRIES, INC. | 7833 | 2022 | 2023-04-19 | 07/15/2022 | 1060315.49 | 0 | 2023-04-18 |  | 1
2021 | Region V | CATANDUANES |  | P00561838LZ | Construction of Flood Mitigation Structure | 124.1466 | 13.9099 | 14848859.47 | 14848757.9 | 2023 | BICOL GOLDROCK CONSTRUCTION CORPORATION | 7834 | 2021 | 2023-01-30 | 01/18/2022 | 101.57 | 0 | 2022-12-27 |  | 34
2022 | Region V | ALBAY | CAMALIG (ALBAY) | P00631000LZ | Rehabilitation / Major Repair of Flood Control Structure | 123.6863 | 13.1805 | 57898447.57 | 57898374.99 | 2022 | MAKAPA CORPORATION | 7835 | 2022 | 2022-10-18 | 03/16/2022 | 72.58 | 0 | 2022-10-17 |  | 1
2022 | Region X | LANAO DEL NORTE | LALA (LANAO DEL NORTE) | P00620213MN | Construction of Flood Mitigation Structure | 123.778 | 7.9197 | 102983835 | 99395118.03 | 2023 | KOUZBARY BUILDERS / AL-NOORWAY CORPORATION | 7836 | 2022 | 2023-04-08 | 06/13/2022 | 3588716.97 | 0 | 2023-04-07 |  | 1
2022 | Region X | LANAO DEL NORTE | KOLAMBUGAN (LANAO DEL NORTE) | P00620146MN | Construction of Slope Protection Structure | 123.9289 | 8.1323 | 49000000 | 49000000 | 2022 | PLD CONSTRUCTION AND DEVELOPMENT INC. (FORMERLY: PLD CONSTRUCTION) | 7837 | 2022 | 2022-12-10 | 03/18/2022 | 0 | 0 | 2022-12-14 | 4
2023 | Region VII | BOHOL | TUBIGON (BOHOL) | P00721937VS | Construction of Flood Mitigation Structure | 123.9955 | 9.9494 | 11760000 | 11705000 | 2023 | HUSAIN CONSTRUCTION AND SUPPLY CO. | 7838 | 2023 | 2023-10-13 | 03/15/2023 | 55000 | 0 | 2023-11-08 | 26
2023 | Region VII | CEBU | CEBU CITY (CAPITAL) (CEBU) | P00732025VS | Construction of Flood Mitigation Structure | 123.8728 | 10.2836 | 11880000 | 11834060.05 | 2024 | YES CONSTRUCTION | 7839 | 2023 | 2024-05-19 | 11/15/2023 | 45939.95 | 0 | 2024-05-18 |  | 1
2022 | Region V | ALBAY | LIBON (ALBAY) | P00630996LZ | Rehabilitation / Major Repair of Flood Control Structure | 123.4241 | 13.2937 | 77097625.36 | 77097561.51 | 2022 | HI-TONE CONSTRUCTION & DEVELOPMENT CORP. (FORMERLY | 7840 | 2022 | 2022-12-08 | 03/14/2022 | 63.85 | 0 | 2022-12-07 |  | 1
2021 | Region V | CATANDUANES |  | P00561839LZ | Construction of Flood Mitigation Structure | 124.147 | 13.908 | 14848758.86 | 14848733.84 | 2022 | AL-JON CONSTRUCTION DEVELOPMENT, INC. (FORMERLY: ALJON CONSTRUCTION & SUPPLY) | 7841 | 2021 | 2022-07-26 | 01/18/2022 | 25.02 | 0 | 2022-07-25 |  | 1
2024 | Region VII | CEBU | ARGAO (CEBU) | P00820193VS | Construction of Flood Mitigation Structure | 123.5862 | 9.8897 | 4900000 | 4850001.98 | 2024 | AR ADLAWAN CONSTRUCTION | 7842 | 2024 | 2024-04-10 | 02/19/2024 | 49998.02 | 0 | 2024-04-09 |  | 1
2023 | Region V | ALBAY | DARAGA (LOCSIN) (ALBAY) | P00726967LZ | Construction of Flood Mitigation Structure | 123.6865 | 13.1808 | 72334861.15 | 72294714.06 | 2023 | NEXT GENERATION CONSTRUCTION AND SUPPLY CORPORATION | 7843 | 2023 | 2023-10-24 | 04/19/2023 | 40147.09 | 0 | 2023-10-23 |  | 1
2023 | Region V | ALBAY | LEGAZPI CITY (CAPITAL) (ALBAY) | P00737387LZ | Construction of Dike | 123.7797 | 13.121 | 57898489.6 | 57898479.61 | 2023 | MUNTOPAR BUILDERS CORP. | 7844 | 2023 | 2023-09-03 | 02/27/2023 | 9.99 | 0 | 2023-09-02 |  | 1
2023 | Region VII | CEBU | DAANBANTAYAN (CEBU) | P00721528VS | Construction of Flood Mitigation Structure | 123.9971 | 11.2512 | 67550000 | 67550000 | 2023 | WTG CONSTRUCTION & DEVELOPMENT CORPORATION | 7845 | 2023 | 2023-10-27 | 02/14/2023 | 0 | 0 | 2023-10-26 |  | 1
2022 | Region V | SORSOGON | BULAN (SORSOGON) | P00640588LZ | Construction of Drainage Structure | 123.8728 | 12.6722 | 14850000 | 14404521 | 2023 | RMH CONSTRUCTION & SUPPLY | 7846 | 2022 | 2023-03-29 | 09/01/2022 | 445479 | 0 | 2023-03-28 |  | 1
2022 | Region V | ALBAY | LIBON (ALBAY) | P00631375LZ | Rehabilitation / Major Repair of Flood Control Structure | 123.4245 | 13.3256 | 19600000 | 19599978.9 | 2022 | MAKAPA CORPORATION | 7847 | 2022 | 2022-09-19 | 02/17/2022 | 21.1 | 0 | 2022-09-18 |  | 1
2023 | Region VII | CEBU | TABUELAN (CEBU) | P00721668VS | Construction of Drainage Structure | 123.8741 | 10.8417 | 5625200 | 5625200 | 2023 | WTG CONSTRUCTION & DEVELOPMENT CORPORATION | 7848 | 2023 | 2023-05-26 | 02/09/2023 | 0 | 0 | 2023-05-25 |  | 1
2023 | Region V | SORSOGON | BARCELONA (SORSOGON) | P00737580LZ | Construction of Flood Mitigation Structure | 124.1471 | 12.8174 | 54450000 | 4801500 | 2023 | ALHADRAX CONSTRUCTION AND SUPPLY | 7849 | 2023 | 2023-10-29 | 05/02/2023 | 49648500 | 0 | 2023-10-28 |  | 1
2022 | Region V | ALBAY | CITY OF LIGAO (ALBAY) | P00640476LZ | Construction of Revetment | 123.5867 | 13.2411 | 89100000 | 89100000 | 2023 | CENTERWAYS CONSTRUCTION AND DEVELOPMENT INC. / FS CO BUILDERS AND SUPPLY | 7850 | 2022 | 2023-03-17 | 06/06/2022 | 0 | 0 | 2023-03-16 |  | 1
2024 | Region VII | BOHOL | ANTEQUERA (BOHOL) | P00820879VS | Construction of Flood Mitigation Structure | 123.929 | 9.7498 | 67550000 | 67500000 | 2025 | N.N. YU CONSTRUCTION, INC. (FORMERLY: YU CONSTRUCTION) | 7851 | 2024 | 2025-04-10 | 05/03/2024 | 50000 | 0 | 2025-04-09 |  | 1
2023 | Region V | ALBAY | MANITO (ALBAY) | P00726977LZ | Construction of Flood Mitigation Structure | 123.6866 | 13.1636 | 72314383.82 | 72374494.71 | 2023 | PEDXING BUILDERS, INC. (FORMERLY: PEDXING BUILDERS) / PEDXING BUILDERS, INC. (FORMERLY: PEDXING BUILDERS) | 7852 | 2023 | 2023-10-19 | 04/04/2023 | 0 | 60110.89 | 2023-10-13 |  | 6
2022 | Region VII | CEBU | MINGLANILLA (CEBU) | P00620036VS | Construction of Flood Mitigation Structure | 123.7802 | 10.2445 | 91675000 | 91675000 | 2023 | PRIME GIGABUILD CONSTRUCTION CORP. (FORMERLY: RON DANIELL CONSTRUCTION CORPORATION) | 7853 | 2022 | 2023-01-16 | 03/25/2022 | 0 | 0 | 2023-01-15 |  | 1
2023 | Region V | ALBAY | SANTO DOMINGO (LIBOG) (ALBAY) | P00740474LZ | Construction of Flood Mitigation Structure | 123.7802 | 13.261 | 96499976.03 | 96500000 | 2023 | HI-TONE CONSTRUCTION & DEVELOPMENT CORP. (FORMERLY | 7854 | 2023 | 2023-12-10 | 04/12/2023 | 0 | 23.97 | 2023-12-09 |  | 1
2024 | Region V | SORSOGON | CITY OF SORSOGON (CAPITAL) (SORSOGON) | P00846126LZ | Construction of Flood Mitigation Structure | 123.9971 | 12.9697 | 79199947.93 | 9899988.72 | 2024 | AREMAR CONSTRUCTION CORPORATION | 7855 | 2024 | 2024-12-11 | 05/17/2024 | 69299959.21 | 0 | 2024-12-10 |  | 1
2024 | Region V | CAMARINES SUR | BULA (CAMARINES SUR) | P00821382LZ | Construction of Flood Mitigation Structure | 123.4248 | 13.4703 | 139925000 | 139925000 | 2024 | SUNWEST, INC. (FORMERLY: SUNWEST CONSTRUCTION & DEVELOPMENT CORPORATION) | 7856 | 2024 | 2024-09-20 | 02/21/2024 | 0 | 0 | 2024-12-27 | 98
2023 | Region V | ALBAY | SANTO DOMINGO (LIBOG) (ALBAY) | P00740657LZ | Construction of Flood Mitigation Structure | 123.7809 | 13.236 | 48999998.94 | 49000000 | 2023 | HI-TONE CONSTRUCTION & DEVELOPMENT CORP. (FORMERLY | 7857 | 2023 | 2023-11-03 | 06/08/2023 | 0 | 1.06 | 2023-11-14 | 11
2022 | Region VII | CEBU | DAANBANTAYAN (CEBU) | P00620032VS | Construction of Flood Mitigation Structure | 123.9979 | 11.2512 | 57900000 | 57900000 | 2022 | WTG CONSTRUCTION & DEVELOPMENT CORPORATION | 7858 | 2022 | 2022-12-12 | 02/21/2022 | 0 | 0 | 2022-12-11 |  | 1
2023 | Region X | LANAO DEL SUR | BACOLOD-KALAWI (BACOLOD GRANDE) (LANAO DEL SUR) | P00733985MN | Construction of Flood Mitigation Structure | 124.1489 | 7.864 | 28950000 | 28255451.89 | 2024 | RENREN TRADING AND CONSTRUCTION SERVICES | 7859 | 2023 | 2024-01-22 | 06/15/2023 | 694548.11 | 0 | 2023-11-03 |  | 80
2022 | Region V | MASBATE | DIMASALANG (MASBATE) | P00620749LZ | Construction of Revetment | 123.8743 | 12.1784 | 35263856.64 | 35247120.61 | 2022 | SPRING STAR CONSTRUCTION AND SUPPLY | 7860 | 2022 | 2022-09-12 | 02/16/2022 | 16736.03 | 0 | 2022-10-12 | 30
2023 | Region V | ALBAY | CAMALIG (ALBAY) | P00740670LZ | Construction of Dike | 123.5897 | 13.1172 | 48909111.71 | 48909052.85 | 2023 | GRELIPS CONSTRUCTION & DEVELOPMENT / 3RB CONSTRUCTION & SUPPLY | 7861 | 2023 | 2023-10-13 | 04/17/2023 | 58.86 | 0 | 2023-10-12 |  | 1
2022 | Region VII | CEBU | CONSOLACION (CEBU) | P00632987VS | Construction of Slope Protection Structure | 123.9294 | 10.454 | 96500000 | 96500000 | 2023 | QUIRANTE CONSTRUCTION CORPORATION (FORMERLY: QUIRANTE CONSTRUCTION) / ZLREJ TRADING AND CONSTRUCTION CORPORATION | 7862 | 2022 | 2023-01-16 | 03/31/2022 | 0 | 0 | 2023-01-17 | 1
2022 | Region X | LANAO DEL NORTE | BAROY (LANAO DEL NORTE) | P00620149MN | Construction of Slope Protection Structure | 123.7812 | 8.0042 | 39200000 | 37216949.34 | 2022 | LANAO BUILDER AND ENTERPRISES | 7863 | 2022 | 2022-10-05 | 03/18/2022 | 1983050.66 | 0 | 2022-10-04 |  | 1
2024 | Region VII | CEBU | LILOAN (CEBU) | P00820053VS | Construction of Flood Mitigation Structure | 123.9996 | 10.4384 | 149849060 | 149847604.4 | 2025 | MC GEOMETRIC PROPORTIONS, INC. / ALPHA & OMEGA GEN. CONTRACTOR & DEVELOPMENT CORP. | 7864 | 2024 | 2025-03-10 | 04/04/2024 | 1455.6 | 0 | 2025-03-09 |  | 1
2022 | Region V | SORSOGON | CASTILLA (SORSOGON) | P00631483LZ | Construction of Flood Mitigation Structure | 123.7832 | 12.9783 | 58899904.98 | 9797412.68 | 2022 | CENTERWAYS CONSTRUCTION AND DEVELOPMENT INC. | 7865 | 2022 | 2022-09-12 | 03/17/2022 | 49102492.3 | 0 | 2022-09-11 |  | 1
2022 | Region V | MASBATE | SAN FERNANDO (MASBATE) | P00620736LZ | Construction of Flood Mitigation Structure | 123.6867 | 12.4756 | 44100000 | 41894584.96 | 2022 | A3 CONSTRUCTION & SUPPLY | 7866 | 2022 | 2022-09-05 | 03/17/2022 | 2205415.04 | 0 | 2022-11-10 | 66
2024 | Region V | MASBATE | DIMASALANG (MASBATE) | P00821017LZ | Construction of Flood Mitigation Structure | 123.8753 | 12.1803 | 48978049 | 48962315.19 | 2024 | HKP CONSTRUCTION AND SUPPLY / A3 CONSTRUCTION & SUPPLY | 7867 | 2024 | 2024-09-12 | 02/15/2024 | 15733.81 | 0 | 2024-09-11 |  | 1
2023 | Region VII | CEBU | LILOAN (CEBU) | P00744359VS | Rehabilitation / Major Repair of Flood Control Structure | 123.9997 | 10.4384 | 15541325 | 15484008.07 | 2023 | VSP STRUCTURE VENTURES CORP. (FORMERLY: VIRLO CONSTRUCTION) | 7868 | 2023 | 2023-07-27 | 03/30/2023 | 57316.93 | 0 | 2023-07-26 |  | 1
2022 | Region V | CATANDUANES | CARAMORAN (CATANDUANES) | P00631447LZ | Construction of Flood Mitigation Structure | 124.1489 | 13.7565 | 77199160.36 | 38600000 | 2023 | HI-TONE CONSTRUCTION & DEVELOPMENT CORP. (FORMERLY | 7869 | 2022 | 2023-07-08 | 06/28/2022 | 38599160.36 | 0 | 2023-07-07 |  | 1
2022 | Region X | LANAO DEL NORTE | BAROY (LANAO DEL NORTE) | P00620145MN | Construction of Slope Protection Structure | 123.7833 | 8.0208 | 39200000 | 39200000 | 2022 | LANAO BUILDER AND ENTERPRISES | 7870 | 2022 | 2022-11-25 | 03/18/2022 | 0 | 0 | 2022-12-03 | 8
2023 | Region X | MISAMIS OCCIDENTAL | BONIFACIO (MISAMIS OCCIDENTAL) | P00721383MN | Construction of Slope Protection Structure | 123.5912 | 8.0482 | 49000000 | 47530000 | 2025 | MINDANAO ROCK | 7871 | 2023 | 2025-01-28 | 02/10/2023 | 1470000 | 0 | 2023-08-02 |  | 545
2023 | Region V | ALBAY | MALINAO (ALBAY) | P00726624LZ | Rehabilitation / Major Repair of Flood Control Structure | 123.6868 | 13.3908 | 101324366 | 101324366 | 2023 | MAKAPA CORPORATION | 7872 | 2023 | 2023-12-02 | 02/20/2023 | 0 | 0 | 2023-12-01 |  | 1
2023 | Region VII | CEBU | RONDA (CEBU) | P00721896VS | Construction of Flood Mitigation Structure | 123.4251 | 10.0011 | 96498253.02 | 96498238.76 | 2023 | JCM AMEG BUILDERS CORPORATION (FORMERLY: AMEG CONSTRUCTION & SUPPLY) | 7873 | 2023 | 2023-07-10 | 03/16/2023 | 14.26 | 0 | 2024-01-23 | 197
2022 | Region X | LANAO DEL NORTE | MAIGO (LANAO DEL NORTE) | P00620150MN | Construction of Slope Protection Structure | 123.9294 | 8.1327 | 49000000 | 49000000 | 2023 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R | 7874 | 2022 | 2023-06-12 | 03/18/2022 | 0 | 0 | 2023-07-06 | 24
2022 | Region VII | CEBU | COMPOSTELA (CEBU) | P00620026VS | Construction of Flood Mitigation Structure | 124.0001 | 10.4384 | 56578915 | 56548278.06 | 2022 | VSP STRUCTURE VENTURES CORP. (FORMERLY: VIRLO CONSTRUCTION) / SQUARE CUBE CONSTRUCTION(FORMERLY SQUARE CUBE TRAD | 7875 | 2022 | 2022-11-08 | 03/07/2022 | 30636.94 | 0 | 2022-11-19 | 11
2024 | Region VII | CEBU | MANDAUE CITY (CEBU) | P00834653VS | Construction of Flood Mitigation Structure | 123.9296 | 10.3487 | 24257940 | 24205775 | 2025 | ON POINT CONSTRUCTION AND DEVELOPMENT CORPORATION (FORMERLY:ON POINT CONSTRUCTION) | 7876 | 2024 | 2025-02-24 | 07/04/2024 | 52165 | 0 | 2025-04-18 | 53
2023 | Region V | SORSOGON | PRIETO DIAZ (SORSOGON) | P00737577LZ | Construction of Flood Mitigation Structure | 124.1495 | 13.0721 | 4950000 | 4801500 | 2023 | ALHADRAX CONSTRUCTION AND SUPPLY | 7877 | 2023 | 2023-07-25 | 05/02/2023 | 148500 | 0 | 2023-07-01 |  | 24
2022 | Region V | SORSOGON | CASTILLA (SORSOGON) | P00640596LZ | Construction of Flood Mitigation Structure | 123.7852 | 12.8676 | 49499989.68 | 29699990.04 | 2023 | ALNINO CONSTRUCTION & SUPPLY CORPORATION (FORMERLY: AL NINO CONSTRUCTION & SUPPLY) | 7878 | 2022 | 2023-02-24 | 04/04/2022 | 19799999.64 | 0 | 2023-02-24 | 0
2022 | Region V | SORSOGON | DONSOL (SORSOGON) | P00630975LZ | Construction of Flood Mitigation Structure | 123.5915 | 12.912 | 67549977.01 | 65156884.39 | 2023 | CENTERWAYS CONSTRUCTION AND DEVELOPMENT INC. | 7879 | 2022 | 2023-03-07 | 06/15/2022 | 2393092.62 | 0 | 2023-03-06 |  | 1
2022 | Region V | ALBAY | CITY OF TABACO (ALBAY) | P00640569LZ | Construction of Flood Mitigation Structure | 123.4255 | 13.2156 | 66329638.23 | 14850000 | 2022 | JORMAND CONSTRUCTION & SUPPLY | 7880 | 2022 | 2022-11-11 | 06/23/2022 | 51479638.23 | 0 | 2023-01-03 | 53
2023 | Region VII | CEBU | LILOAN (CEBU) | P00721828VS | Construction of Flood Mitigation Structure | 124.0007 | 10.4361 | 49000000 | 48952952.29 | 2023 | VSP STRUCTURE VENTURES CORP. (FORMERLY: VIRLO CONSTRUCTION) | 7881 | 2023 | 2023-07-10 | 01/30/2023 | 47047.71 | 0 | 2023-08-26 | 47
2024 | Region V | MASBATE | SAN FERNANDO (MASBATE) | P00821012LZ | Construction of Flood Mitigation Structure | 123.6869 | 12.48 | 49000000 | 48999991.64 | 2024 | NEXT GENERATION CONSTRUCTION AND SUPPLY CORPORATION | 7882 | 2024 | 2024-11-29 | 04/08/2024 | 8.36 | 0 | 2025-02-16 | 79
2023 | Region V | SORSOGON | PRIETO DIAZ (SORSOGON) | P00726315LZ | Rehabilitation / Major Repair of Flood Control Structure | 124.15 | 13.0114 | 58800000 | 28511748.95 | 2023 | CENTERWAYS CONSTRUCTION AND DEVELOPMENT INC. | 7883 | 2023 | 2023-11-15 | 04/11/2023 | 30288251.05 | 0 | 2023-12-14 | 29
2024 | Region X | LANAO DEL NORTE | TUBOD (CAPITAL) (LANAO DEL NORTE) | P00820908MN | Construction of Flood Mitigation Structure | 123.7874 | 8.0395 | 115800000 | 115800000 | 2024 | PLD CONSTRUCTION AND DEVELOPMENT INC. (FORMERLY: PLD CONSTRUCTION) / LANAO BUILDER AND ENTERPRISES | 7884 | 2024 | 2024-12-10 | 02/13/2024 | 0 | 0 | 2025-01-19 | 40
2022 | Region V | SORSOGON | BULAN (SORSOGON) | P00632974LZ | Construction of Flood Mitigation Structure | 123.8753 | 12.6581 | 49500000 | 19001820.12 | 2022 | DOUBLE R CONSTRUCTION AND SUPPLY / STEVEN CONSTRUCTION & SUPPLY | 7885 | 2022 | 2022-08-08 | 02/14/2022 | 30498179.88 | 0 | 2022-08-07 |  | 1
2022 | Region V | SORSOGON | DONSOL (SORSOGON) | P00640598LZ | Construction of Flood Mitigation Structure | 123.5918 | 12.9055 | 59399996.63 | 39600000 | 2022 | ALNINO CONSTRUCTION & SUPPLY CORPORATION (FORMERLY: AL NINO CONSTRUCTION & SUPPLY) | 7886 | 2022 | 2022-11-11 | 04/04/2022 | 19799996.63 | 0 | 2022-11-12 | 1
2022 | Region V | ALBAY | LIBON (ALBAY) | P00620305LZ | Construction of Flood Mitigation Structure | 123.4256 | 13.2894 | 48249492.67 | 48249492.67 | 2022 | MAKAPA CORPORATION | 7887 | 2022 | 2022-12-20 | 03/21/2022 | 0 | 0 | 2022-12-19 |  | 1
2022 | Region V | SORSOGON | CASIGURAN (SORSOGON) | P00620757LZ | Construction of Flood Mitigation Structure | 124.0016 | 12.8703 | 39199988.75 | 37978793.24 | 2022 | AREMAR CONSTRUCTION CORPORATION | 7888 | 2022 | 2022-09-29 | 02/16/2022 | 1221195.51 | 0 | 2022-09-26 |  | 3
2023 | Region V | ALBAY | MALINAO (ALBAY) | P00737553LZ | Construction of Flood Mitigation Structure | 123.6883 | 13.3967 | 30689724.37 | 19800000 | 2023 | JORMAND CONSTRUCTION & SUPPLY | 7889 | 2023 | 2023-08-31 | 04/27/2023 | 10889724.37 | 0 | 2023-09-23 | 23
2022 | Region VII | CEBU | TABOGON (CEBU) | P00620119VS | Construction of Flood Mitigation Structure | 123.9306 | 10.9733 | 49000000 | 49000000 | 2022 | JJ &J CONSTRUCTION & GENERAL SUPPLY / SAN NARCISO BUILDERS CORPORATION(FOR. SAN NARCISO | 7890 | 2022 | 2022-12-29 | 02/18/2022 | 0 | 0 | 2022-12-28 |  | 1
2022 | Region V | CATANDUANES | CARAMORAN (CATANDUANES) | P00631446LZ | Construction of Flood Mitigation Structure | 124.1526 | 13.7588 | 77199160.36 | 38598662.63 | 2023 | HI-TONE CONSTRUCTION & DEVELOPMENT CORP. (FORMERLY | 7891 | 2022 | 2023-07-08 | 06/28/2022 | 38600497.73 | 0 | 2023-07-07 |  | 1
2022 | Region VII | CEBU | PINAMUNGAJAN (CEBU) | P00620124VS | Construction of Flood Mitigation Structure | 123.5918 | 10.2609 | 49000000 | 48749331.99 | 2023 | VEN RAY CONSTRUCTION CORPORATION | 7892 | 2022 | 2023-03-02 | 06/02/2022 | 250668.01 | 0 | 2023-03-01 |  | 1
2024 | Region VI | NEGROS OCCIDENTAL | SAN CARLOS CITY (NEGROS OCCIDENTAL) | P00820853VS | Construction of Flood Mitigation Structure | 123.4261 | 10.5055 | 72375000 | 72374843.77 | 2025 | RKVT CONSTRUCTION / WILKINSON CONSTRUCTION | 7893 | 2024 | 2025-02-06 | 05/07/2024 | 156.23 | 0 | 2025-02-05 |  | 1
2023 | Region V | SORSOGON | MAGALLANES (SORSOGON) | P00742488LZ | Construction of Flood Mitigation Structure | 123.8755 | 12.7951 | 98999982.07 | 49499988.79 | 2024 | STEVEN CONSTRUCTION & SUPPLY | 7894 | 2023 | 2024-02-21 | 04/12/2023 | 49499993.28 | 0 | 2024-02-20 |  | 1
2022 | Region V | SORSOGON | CASIGURAN (SORSOGON) | P00640594LZ | Construction of Flood Mitigation Structure | 124.0017 | 12.8735 | 49499997.74 | 48015009.98 | 2023 | C.T. LEONCIO CONSTRUCTION & TRADING | 7895 | 2022 | 2023-01-16 | 08/16/2022 | 1484987.76 | 0 | 2023-01-15 |  | 1
2023 | Region V | ALBAY | DARAGA (LOCSIN) (ALBAY) | P00727381LZ | Construction of Dike | 123.6889 | 13.1611 | 48962411.81 | 48962384.09 | 2023 | VERZONTAL INFRASTRUCTURE CORPORATION (FORMERLY: VERZONTAL BUILDERS, INC.) | 7896 | 2023 | 2023-10-01 | 04/05/2023 | 27.72 | 0 | 2023-09-30 |  | 1
2024 | Region VII | CEBU | MANDAUE CITY (CEBU) | P00835011VS | Construction of Flood Mitigation Structure | 123.9316 | 10.353 | 99000000 | 98899888 | 2024 | QUIRANTE CONSTRUCTION CORPORATION (FORMERLY: QUIRANTE CONSTRUCTION) | 7897 | 2024 | 2024-08-19 | 03/15/2024 | 100112 | 0 | 2025-01-14 | 148
2022 | Region V | CATANDUANES | SAN MIGUEL (CATANDUANES) | P00639399LZ | Rehabilitation / Major Repair of Flood Control Structure | 124.1529 | 13.7471 | 110916629.2 | 110916629.2 | 2023 | HI-TONE CONSTRUCTION & DEVELOPMENT CORP. (FORMERLY | 7898 | 2022 | 2023-06-30 | 07/29/2022 | 0 | 0 | 2023-07-08 | 8
2024 | Region V | ALBAY | CITY OF LIGAO (ALBAY) | P00823603LZ | Construction of Flood Mitigation Structure | 123.5924 | 13.2586 | 96500000 | 96500000 | 2024 | SISBRO CONSTRUCTION CORPORATION (FORMERLY: SISBRO CONSTRUCTION & SUPPLY) / JACKNEL CONSTRUCTION | 7899 | 2024 | 2024-08-31 | 03/21/2024 | 0 | 0 | 2024-12-29 | 120
2022 | Region X | LANAO DEL NORTE | TUBOD (CAPITAL) (LANAO DEL NORTE) | P00620027MN | Construction of Drainage Structure | 123.7923 | 8.0481 | 53075000 | 53075000 | 2023 | MAMSAR CONSTRUCTION AND INDUSTRIAL CORPORATION | 7900 | 2022 | 2023-02-14 | 03/18/2022 | 0 | 0 | 2023-02-13 |  | 1
2023 | Region VII | CEBU | SOGOD (CEBU) | P00721772VS | Construction of Flood Mitigation Structure | 124.0019 | 10.7626 | 106150000 | 106149936.7 | 2023 | VSP STRUCTURE VENTURES CORP. (FORMERLY: VIRLO CONSTRUCTION) | 7901 | 2023 | 2023-12-05 | 04/05/2023 | 63.3 | 0 | 2024-02-09 | 66
2023 | Region VI | NEGROS OCCIDENTAL | SAN CARLOS CITY (NEGROS OCCIDENTAL) | P00721505VS | Construction of Flood Mitigation Structure | 123.427 | 10.4963 | 72374726.64 | 72374744.87 | 2023 | C'ZARLES CONSTRUCTION & SUPPLY | 7902 | 2023 | 2023-10-02 | 03/02/2023 | 0 | 18.23 | 2023-10-01 |  | 1
2024 | Region X | LANAO DEL NORTE | KOLAMBUGAN (LANAO DEL NORTE) | P00821088MN | Construction of Flood Mitigation Structure | 123.8759 | 8.1017 | 49000000 | 49000000 | 2024 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R | 7903 | 2024 | 2024-09-09 | 01/25/2024 | 0 | 0 | 2024-09-15 | 6
2022 | Region X | LANAO DEL NORTE | TUBOD (CAPITAL) (LANAO DEL NORTE) | P00620035MN | Construction of Flood Mitigation Structure | 123.9326 | 7.9253 | 80641190 | 80641190 | 2023 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R | 7904 | 2022 | 2023-01-06 | 03/18/2022 | 0 | 0 | 2023-01-05 |  | 1
2022 | Region X | MISAMIS OCCIDENTAL | TANGUB CITY (MISAMIS OCCIDENTAL) | P00630585MN | Construction of Slope Protection Structure | 123.6893 | 8.0541 | 29400000 | 29400000 | 2022 | WEISENWORK CONSTRUCTION | 7905 | 2022 | 2022-11-04 | 01/24/2022 | 0 | 0 | 2022-10-26 |  | 9
2023 | Region V | SORSOGON | BARCELONA (SORSOGON) | P00737575LZ | Construction of Flood Mitigation Structure | 124.1536 | 12.8204 | 54450000 | 19773947.82 | 2023 | ALHADRAX CONSTRUCTION AND SUPPLY | 7906 | 2023 | 2023-10-29 | 05/02/2023 | 34676052.18 | 0 | 2023-10-28 |  | 1
2023 | Region V | SORSOGON | DONSOL (SORSOGON) | P00740687LZ | Construction of Flood Mitigation Structure | 123.5934 | 13.0113 | 56939964.51 | 27439999.43 | 2023 | CENTERWAYS CONSTRUCTION AND DEVELOPMENT INC. / CHEEREL CONSTRUCTION & SUPPLY | 7907 | 2023 | 2023-11-17 | 03/27/2023 | 29499965.08 | 0 | 2023-11-18 | 1
2022 | Region V | SORSOGON | CASTILLA (SORSOGON) | P00631482LZ | Construction of Flood Mitigation Structure | 123.793 | 12.9775 | 58899904.98 | 9797964.61 | 2022 | CENTERWAYS CONSTRUCTION AND DEVELOPMENT INC. | 7908 | 2022 | 2022-09-12 | 03/17/2022 | 49101940.37 | 0 | 2022-09-11 |  | 1
2022 | Region V | SORSOGON | IROSIN (SORSOGON) | P00631472LZ | Construction of Flood Mitigation Structure | 124.0022 | 12.7003 | 58800000 | 28518000 | 2022 | MUNTOPAR BUILDERS CORP. | 7909 | 2022 | 2022-10-13 | 02/15/2022 | 30282000 | 0 | 2022-10-12 |  | 1
2023 | Region VII | CEBU | CEBU CITY (CAPITAL) (CEBU) | P00721539VS | Construction of Flood Mitigation Structure | 123.8759 | 10.2842 | 86850000 | 86670915 | 2023 | WTG CONSTRUCTION & DEVELOPMENT CORPORATION | 7910 | 2023 | 2023-12-11 | 04/20/2023 | 179085 | 0 | 2024-01-26 | 46
2024 | Region V | ALBAY | MALINAO (ALBAY) | P00821613LZ | Construction of Flood Mitigation Structure | 123.6894 | 13.3756 | 48999999.64 | 49000000 | 2024 | 8AR CONSTRUCTION AND DEVELOPMENT CORPORATION | 7911 | 2024 | 2024-08-28 | 04/29/2024 | 0 | 0.36 | 2024-10-15 | 48
2022 | Region X | LANAO DEL NORTE | TUBOD (CAPITAL) (LANAO DEL NORTE) | P00620036MN | Construction of Flood Mitigation Structure | 123.9327 | 7.9251 | 80641190 | 80641190 | 2023 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R | 7912 | 2022 | 2023-01-04 | 03/18/2022 | 0 | 0 | 2023-01-05 | 1
2023 | Region V | SORSOGON | DONSOL (SORSOGON) | P00737582LZ | Rehabilitation / Major Repair of Flood Control Structure | 123.5935 | 12.9094 | 71669931.81 | 4949990.65 | 2023 | CENTERWAYS CONSTRUCTION AND DEVELOPMENT INC. | 7913 | 2023 | 2023-11-22 | 02/23/2023 | 66719941.16 | 0 | 2023-11-21 |  | 1
2024 | Region VII | CEBU | RONDA (CEBU) | P00834592VS | Construction of Flood Mitigation Structure | 123.4272 | 9.9976 | 57896109.96 | 57895609.96 | 2024 | JCM AMEG BUILDERS CORPORATION (FORMERLY: AMEG CONSTRUCTION & SUPPLY) | 7914 | 2024 | 2024-06-11 | 03/18/2024 | 500 | 0 | 2024-11-04 | 146
2022 | Region X | LANAO DEL NORTE | TUBOD (CAPITAL) (LANAO DEL NORTE) | P00620138MN | Construction of Flood Mitigation Structure | 123.7934 | 8.0484 | 49000000 | 49000000 | 2023 | LANAO BUILDER AND ENTERPRISES | 7915 | 2022 | 2023-02-06 | 03/18/2022 | 0 | 0 | 2023-02-05 |  | 1
2024 | Region V | SORSOGON | CITY OF SORSOGON (CAPITAL) (SORSOGON) | P00846131LZ | Construction of Flood Mitigation Structure | 124.003 | 12.9852 | 79199947.93 | 49499971.87 | 2024 | AREMAR CONSTRUCTION CORPORATION | 7916 | 2024 | 2024-12-11 | 05/17/2024 | 29699976.06 | 0 | 2024-12-10 |  | 1
2021 | Region V | SORSOGON |  | P00525687LZ | Construction of Flood Mitigation Structure | 123.8763 | 12.66 | 96499967.01 | 96499967.01 | 2022 | CENTERWAYS CONSTRUCTION AND DEVELOPMENT INC. | 7917 | 2021 | 2022-12-15 | 11/02/2021 | 0 | 0 | 2022-12-14 |  | 1
2024 | Region VII | CEBU | MANDAUE CITY (CEBU) | P00820857VS | Construction of Flood Mitigation Structure | 123.9335 | 10.35 | 57900000 | 57800000 | 2024 | ZLREJ TRADING AND CONSTRUCTION CORPORATION | 7918 | 2024 | 2024-12-27 | 03/15/2024 | 100000 | 0 | 2024-12-30 | 3
2024 | Region VII | CEBU | RONDA (CEBU) | P00834591VS | Construction of Flood Mitigation Structure | 123.4274 | 9.9983 | 57896114.55 | 57896010.27 | 2024 | JCM AMEG BUILDERS CORPORATION (FORMERLY: AMEG CONSTRUCTION & SUPPLY) | 7919 | 2024 | 2024-07-10 | 03/18/2024 | 104.28 | 0 | 2024-11-04 | 117
2023 | Region V | ALBAY | CITY OF LIGAO (ALBAY) | P00740478LZ | Construction of Flood Mitigation Structure | 123.5941 | 13.2491 | 192932380.2 | 192932374.8 | 2023 | SANRHO BUILDERS, INC.(FOR. SANRHO CONST. AND SUPPL / SISBRO CONSTRUCTION CORPORATION (FORMERLY: SISBRO CONSTRUCTION & SUPPLY) | 7920 | 2023 | 2023-09-07 | 04/24/2023 | 5.4 | 0 | 2024-03-06 | 181
2023 | Region V | ALBAY | DARAGA (LOCSIN) (ALBAY) | P00736143LZ | Construction of Dike | 123.6902 | 13.1797 | 48248494.74 | 48248322.88 | 2023 | 3DIAMONDS CONSTRUCTION CORPORATION | 7921 | 2023 | 2023-11-30 | 07/03/2023 | 171.86 | 0 | 2023-12-06 | 6
2024 | Region V | ALBAY | CITY OF LIGAO (ALBAY) | P00823591LZ | Construction of Flood Mitigation Structure | 123.5952 | 13.2613 | 96500000 | 96500000 | 2024 | SISBRO CONSTRUCTION CORPORATION (FORMERLY: SISBRO CONSTRUCTION & SUPPLY) | 7922 | 2024 | 2024-10-31 | 03/21/2024 | 0 | 0 | 2024-12-29 | 59
2023 | Region V | ALBAY | BACACAY (ALBAY) | P00737554LZ | Construction of Flood Mitigation Structure | 123.7948 | 13.2887 | 30689724.37 | 4950000 | 2023 | JORMAND CONSTRUCTION & SUPPLY | 7923 | 2023 | 2023-08-31 | 04/27/2023 | 25739724.37 | 0 | 2023-09-23 | 23
2023 | Region VII | CEBU | CATMON (CEBU) | P00721773VS | Construction of Flood Mitigation Structure | 124.0034 | 10.7278 | 77200000 | 77199721.33 | 2023 | QUIRANTE CONSTRUCTION CORPORATION (FORMERLY: QUIRANTE CONSTRUCTION) | 7924 | 2023 | 2023-12-11 | 04/18/2023 | 278.67 | 0 | 2024-01-20 | 40
2022 | Region V | SORSOGON | BULAN (SORSOGON) | P00632976LZ | Construction of Flood Mitigation Structure | 123.9339 | 12.6625 | 49500000 | 28505318.96 | 2022 | DOUBLE R CONSTRUCTION AND SUPPLY / STEVEN CONSTRUCTION & SUPPLY | 7925 | 2022 | 2022-08-08 | 02/14/2022 | 20994681.04 | 0 | 2022-08-07 |  | 1
2024 | Region VII | BOHOL | TUBIGON (BOHOL) | P00820074VS | Construction of Flood Mitigation Structure | 123.934 | 9.9105 | 53075000 | 52974619.82 | 2024 | N.N. YU CONSTRUCTION, INC. (FORMERLY: YU CONSTRUCTION) | 7926 | 2024 | 2024-10-17 | 04/11/2024 | 100380.18 | 0 | 2024-11-08 | 22
2022 | Region V | SORSOGON | DONSOL (SORSOGON) | P00632978LZ | Construction of Drainage Structure | 123.5953 | 12.9056 | 58899904.98 | 4947163.72 | 2022 | CENTERWAYS CONSTRUCTION AND DEVELOPMENT INC. | 7927 | 2022 | 2022-09-12 | 03/17/2022 | 53952741.26 | 0 | 2022-09-11 |  | 1
2024 | Region VII | CEBU | RONDA (CEBU) | P00834590VS | Construction of Flood Mitigation Structure | 123.429 | 9.9879 | 57896705.85 | 57896205.85 | 2024 | JCM AMEG BUILDERS CORPORATION (FORMERLY: AMEG CONSTRUCTION & SUPPLY) | 7928 | 2024 | 2024-07-02 | 03/18/2024 | 500 | 0 | 2024-11-04 | 125
2022 | Region V | SORSOGON | CITY OF SORSOGON (CAPITAL) (SORSOGON) | P00640597LZ | Construction of Flood Mitigation Structure | 123.9343 | 12.9976 | 37124986.19 | 37118332.97 | 2023 | STEVEN CONSTRUCTION & SUPPLY | 7929 | 2022 | 2023-03-24 | 07/11/2022 | 6653.22 | 0 | 2023-03-25 | 1
2024 | Region X | LANAO DEL NORTE | BAROY (LANAO DEL NORTE) | P00821220MN | Construction of Flood Mitigation Structure | 123.8764 | 8.1021 | 49000000 | 48009820.77 | 2024 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R | 7930 | 2024 | 2024-09-06 | 01/25/2024 | 990179.23 | 0 | 2024-09-05 |  | 1
2022 | Region V | ALBAY | BACACAY (ALBAY) | P00620312LZ | Construction of Flood Mitigation Structure | 123.7956 | 13.2832 | 138372507.5 | 138408985 | 2022 | HI-TONE CONSTRUCTION & DEVELOPMENT CORP. (FORMERLY / FS CO BUILDERS AND SUPPLY | 7931 | 2022 | 2022-12-15 | 03/28/2022 | 0 | 36477.5 | 2023-01-12 | 28
2024 | Region V | ALBAY | DARAGA (LOCSIN) (ALBAY) | P00844785LZ | Construction of Dike | 123.6921 | 13.1727 | 29398953.17 | 29398860.04 | 2024 | MJMS CONSTRUCTION & DEVELOPMENT CORP. | 7932 | 2024 | 2024-10-01 | 05/29/2024 | 93.13 | 0 | 2024-09-30 |  | 1
2023 | Region V | SORSOGON | CITY OF SORSOGON (CAPITAL) (SORSOGON) | P00742491LZ | Construction of Flood Mitigation Structure | 124.0036 | 12.985 | 54449963.17 | 28643555.23 | 2024 | CENTERWAYS CONSTRUCTION AND DEVELOPMENT INC. / CHEEREL CONSTRUCTION & SUPPLY | 7933 | 2023 | 2024-03-05 | 07/18/2023 | 25806407.94 | 0 | 2024-03-04 |  | 1
2023 | Region VII | CEBU | ARGAO (CEBU) | P00721530VS | Construction of Flood Mitigation Structure | 123.5958 | 9.889 | 67550000 | 67549021.12 | 2023 | ZLREJ TRADING AND CONSTRUCTION CORPORATION / GICAR CONSTRUCTION, INC. | 7934 | 2023 | 2023-10-09 | 02/10/2023 | 978.88 | 0 | 2023-10-30 | 21
2023 | Region VII | CEBU | CONSOLACION (CEBU) | P00733286VS | Construction of Slope Protection Structure | 123.9347 | 10.4761 | 96500000 | 96500000 | 2023 | GICAR CONSTRUCTION, INC. | 7935 | 2023 | 2023-12-15 | 05/18/2023 | 0 | 0 | 2023-12-22 | 7
2020 | Region V | SORSOGON |  | P00448861LZ | Construction of Flood Mitigation Structure | 123.8768 | 12.6638 | 144750970.2 | 144546166.9 | 2022 | CENTERWAYS CONSTRUCTION AND DEVELOPMENT INC. | 7936 | 2020 | 2022-12-10 | 12/11/2020 | 204803.3 | 0 | 2022-12-09 |  | 1
2022 | Region V | ALBAY | BACACAY (ALBAY) | P00631328LZ | Construction of Slope Protection Structure | 123.7961 | 13.2793 | 34299735.52 | 19600000 | 2023 | 3DIAMONDS CONSTRUCTION CORPORATION | 7937 | 2022 | 2023-01-27 | 08/25/2022 | 14699735.52 | 0 | 2023-01-26 |  | 1
2022 | Region V | ALBAY | DARAGA (LOCSIN) (ALBAY) | P00621547LZ | Rehabilitation / Major Repair of Flood Control Structure | 123.6927 | 13.1739 | 48248347.9 | 48248324.35 | 2022 | HI-TONE CONSTRUCTION & DEVELOPMENT CORP. (FORMERLY | 7938 | 2022 | 2022-10-07 | 04/11/2022 | 23.55 | 0 | 2022-10-06 |  | 1
2022 | Region V | SORSOGON | CITY OF SORSOGON (CAPITAL) (SORSOGON) | P00630963LZ | Construction of Slope Protection Structure | 124.0041 | 12.9744 | 87149953.56 | 67544199.13 | 2022 | CENTERWAYS CONSTRUCTION AND DEVELOPMENT INC. | 7939 | 2022 | 2022-11-15 | 02/23/2022 | 19605754.43 | 0 | 2022-11-14 |  | 1
2022 | Region V | ALBAY | CITY OF LIGAO (ALBAY) | P00630984LZ | Construction of Flood Mitigation Structure | 123.5974 | 13.2571 | 57900000 | 56047451.41 | 2023 | RCDS CONSTRUCTION & SUPPLY, INC.(FOR RCDS CONST. | 7940 | 2022 | 2023-06-15 | 06/09/2022 | 1852548.59 | 0 | 2023-06-14 |  | 1
2024 | Region VII | CEBU | TABOGON (CEBU) | P00834646VS | Construction of Flood Mitigation Structure | 124.0042 | 10.9715 | 19600000 | 19600000 | 2024 | QG DEVELOPMENT CORPORATION | 7941 | 2024 | 2024-12-21 | 07/10/2024 | 0 | 0 | 2024-12-20 |  | 1
2023 | Region VII | CEBU | RONDA (CEBU) | P00721892VS | Construction of Dike | 123.4291 | 9.9869 | 96497353.67 | 96497197.73 | 2023 | AR ADLAWAN CONSTRUCTION | 7942 | 2023 | 2023-09-26 | 03/16/2023 | 155.94 | 0 | 2024-01-15 | 111
2022 | Region VII | CEBU | CONSOLACION (CEBU) | P00632989VS | Construction of Slope Protection Structure | 123.9348 | 10.4359 | 96500000 | 96500000 | 2023 | QUIRANTE CONSTRUCTION CORPORATION (FORMERLY: QUIRANTE CONSTRUCTION) / ZLREJ TRADING AND CONSTRUCTION CORPORATION | 7943 | 2022 | 2023-01-16 | 03/31/2022 | 0 | 0 | 2023-01-17 | 1
2022 | Region V | CAMARINES SUR | GARCHITORENA (CAMARINES SUR) | P00639547LZ | Construction of Flood Mitigation Structure | 123.6936 | 13.8817 | 49000000 | 49000000 | 2023 | PARTIDO CONSTRUCTION & SUPPLY | 7944 | 2022 | 2023-06-05 | 04/05/2022 | 0 | 0 | 2023-06-05 | 0
2021 | Region V | SORSOGON |  | P00448861LZ | Construction of Flood Mitigation Structure | 123.8768 | 12.6638 | 144750970.2 | 144546166.9 | 2022 | CENTERWAYS CONSTRUCTION AND DEVELOPMENT INC. | 7945 | 2021 | 2022-12-10 | 12/11/2020 | 204803.3 | 0 | 2022-12-09 |  | 1
2022 | Region V | ALBAY | BACACAY (ALBAY) | P00631329LZ | Construction of Slope Protection Structure | 123.7963 | 13.2792 | 34299735.52 | 14700000 | 2023 | 3DIAMONDS CONSTRUCTION CORPORATION | 7946 | 2022 | 2023-01-27 | 08/25/2022 | 19599735.52 | 0 | 2023-01-26 |  | 1
2022 | Region V | ALBAY | GUINOBATAN (ALBAY) | P00640578LZ | Rehabilitation / Major Repair of Flood Control Structure | 123.5987 | 13.195 | 49500000 | 49499990.45 | 2022 | CENTERWAYS CONSTRUCTION AND DEVELOPMENT INC. / FS CO BUILDERS AND SUPPLY | 7947 | 2022 | 2022-11-25 | 04/11/2022 | 9.55 | 0 | 2022-11-24 |  | 1
2022 | Region V | SORSOGON | CITY OF SORSOGON (CAPITAL) (SORSOGON) | P00631484LZ | Construction of Flood Mitigation Structure | 124.0051 | 12.9857 | 87149953.56 | 19599857.32 | 2022 | CENTERWAYS CONSTRUCTION AND DEVELOPMENT INC. | 7948 | 2022 | 2022-11-15 | 02/23/2022 | 67550096.24 | 0 | 2022-11-14 |  | 1
2023 | Region V | ALBAY | LEGAZPI CITY (CAPITAL) (ALBAY) | P00740667LZ | Construction of Dike | 123.5987 | 13.1304 | 48824408.37 | 48824307.51 | 2023 | MUNTOPAR BUILDERS CORP. | 7949 | 2023 | 2023-10-01 | 04/05/2023 | 100.86 | 0 | 2023-09-30 |  | 1
2023 | Region VII | CEBU | RONDA (CEBU) | P00721891VS | Construction of Dike | 123.4291 | 9.9869 | 96497353.39 | 96497299.22 | 2023 | AR ADLAWAN CONSTRUCTION | 7950 | 2023 | 2023-09-26 | 03/16/2023 | 54.17 | 0 | 2024-01-15 | 111
2024 | Region V | ALBAY | DARAGA (LOCSIN) (ALBAY) | P00824780LZ | Construction of Slope Protection Structure | 123.694 | 13.1726 | 24498876.83 | 24498721.87 | 2024 | FEDERAL AGGREGATES AND DEVELOPMENT CORP. | 7951 | 2024 | 2024-07-22 | 03/20/2024 | 154.96 | 0 | 2024-07-25 | 3
2020 | Region V | SORSOGON |  | P00448887LZ | Rehabilitation / Major Repair of Flood Control Structure | 123.877 | 12.6704 | 144749531.1 | 144749727.7 | 2022 | CENTERWAYS CONSTRUCTION AND DEVELOPMENT INC. / L BROS CONSTRUCTION AND SUPPLY INC (FORMERLY: L BROS. CONSTRUCTION & SUPPLY) | 7952 | 2020 | 2022-10-06 | 12/11/2020 | 0 | 196.6 | 2022-10-05 |  | 1
2024 | Region VII | CEBU | SAN REMIGIO (CEBU) | P00820189VS | Construction of Flood Mitigation Structure | 123.9348 | 10.9768 | 29400000 | 29400000 | 2024 | DINAH RBS CONSTRUCTION AND SUPPLY INCORPORATED (FORMERLY: DINAH JANE CONSTRUCTION AND SUPPLY) | 7953 | 2024 | 2024-09-03 | 02/13/2024 | 0 | 0 | 2024-09-02 |  | 1
2021 | Region V | SORSOGON |  | P00448887LZ | Rehabilitation / Major Repair of Flood Control Structure | 123.877 | 12.6704 | 144749531.1 | 144749727.7 | 2022 | CENTERWAYS CONSTRUCTION AND DEVELOPMENT INC. / L BROS CONSTRUCTION AND SUPPLY INC (FORMERLY: L BROS. CONSTRUCTION & SUPPLY) | 7954 | 2021 | 2022-10-06 | 12/11/2020 | 0 | 196.6 | 2022-10-05 |  | 1
2023 | Region V | ALBAY | BACACAY (ALBAY) | P00727207LZ | Construction of Flood Mitigation Structure | 123.7966 | 13.2835 | 46059971.1 | 24500000 | 2023 | JORMAND CONSTRUCTION & SUPPLY | 7955 | 2023 | 2023-09-15 | 05/09/2023 | 21559971.1 | 0 | 2023-10-22 | 37
2022 | Region V | ALBAY | JOVELLAR (ALBAY) | P00640577LZ | Construction of Flood Mitigation Structure | 123.6014 | 13.0736 | 4950000 | 4949357.65 | 2023 | HI-TONE CONSTRUCTION & DEVELOPMENT CORP. (FORMERLY | 7956 | 2022 | 2023-01-21 | 08/15/2022 | 642.35 | 0 | 2023-01-20 |  | 1
2022 | Region X | LANAO DEL NORTE | KOLAMBUGAN (LANAO DEL NORTE) | P00620151MN | Construction of Slope Protection Structure | 123.8772 | 8.1022 | 49000000 | 49000000 | 2023 | AL HUSSEIN CONSTRUCTION | 7957 | 2022 | 2023-01-15 | 03/18/2022 | 0 | 0 | 2023-01-24 | 9
2024 | Region V | ALBAY | DARAGA (LOCSIN) (ALBAY) | P00824775LZ | Construction of Slope Protection Structure | 123.6941 | 13.1721 | 19598901.03 | 19598426.97 | 2024 | NEXT GENERATION CONSTRUCTION AND SUPPLY CORPORATION | 7958 | 2024 | 2024-07-24 | 03/25/2024 | 474.06 | 0 | 2024-07-23 |  | 1
2022 | Region V | ALBAY | BACACAY (ALBAY) | P00632943LZ | Construction of Flood Mitigation Structure | 123.797 | 13.2759 | 26728184.83 | 11880000 | 2022 | 8AR CONSTRUCTION AND DEVELOPMENT CORPORATION | 7959 | 2022 | 2022-09-11 | 04/18/2022 | 14848184.83 | 0 | 2022-09-10 |  | 1
2024 | Region V | ALBAY | GUINOBATAN (ALBAY) | P00820505LZ | Construction of Flood Mitigation Structure | 123.602 | 13.1976 | 72374521.65 | 72374521.65 | 2025 | 3DIAMONDS CONSTRUCTION CORPORATION | 7960 | 2024 | 2025-02-17 | 07/31/2024 | 0 | 0 | 2025-03-28 | 39
2023 | Region IX | ZAMBOANGA DEL NORTE | DAPITAN CITY (ZAMBOANGA DEL NORTE) | P00721232MN | Construction of Flood Mitigation Structure | 123.4292 | 8.543 | 67550000 | 67547185.67 | 2024 | ESR CONSTRUCTION AND DEVELOPMENT CORPORATION (FORMERLY: ESR CONSTRUCTION & SUPPLIES) | 7961 | 2023 | 2024-02-01 | 04/17/2023 | 2814.33 | 0 | 2024-01-31 |  | 1
2022 | Region V | ALBAY | BACACAY (ALBAY) | P00631332LZ | Rehabilitation / Major Repair of Flood Control Structure | 123.7973 | 13.2883 | 24499215.53 | 24500000 | 2022 | JORMAND CONSTRUCTION & SUPPLY | 7962 | 2022 | 2022-09-04 | 03/11/2022 | 0 | 784.47 | 2022-09-03 |  | 1
2024 | Region V | ALBAY | DARAGA (LOCSIN) (ALBAY) | P00839664LZ | Construction of Flood Mitigation Structure | 123.6945 | 13.1496 | 49498955.14 | 49498701.76 | 2024 | STEVEN CONSTRUCTION & SUPPLY | 7963 | 2024 | 2024-09-07 | 04/23/2024 | 253.38 | 0 | 2024-10-18 | 41
2024 | Region V | MASBATE | USON (MASBATE) | P00821018LZ | Construction of Flood Mitigation Structure | 123.7983 | 11.9835 | 48871471.75 | 48848417.08 | 2024 | A3 CONSTRUCTION & SUPPLY | 7964 | 2024 | 2024-09-03 | 02/06/2024 | 23054.67 | 0 | 2024-09-02 |  | 1
2023 | Region VII | CEBU | MANDAUE CITY (CEBU) | P00721885VS | Construction of Flood Mitigation Structure | 123.939 | 10.3273 | 173700000 | 173700000 | 2024 | ZLREJ TRADING AND CONSTRUCTION CORPORATION / GICAR CONSTRUCTION, INC. | 7965 | 2023 | 2024-08-08 | 05/29/2023 | 0 | 0 | 2024-08-07 |  | 1
2022 | Region V | MASBATE | USON (MASBATE) | P00620748LZ | Construction of Revetment | 123.7985 | 12.174 | 35278715.81 | 35277048.57 | 2022 | ALGIMAR CONSTRUCTION CORPORATION | 7966 | 2022 | 2022-08-30 | 02/14/2022 | 1667.24 | 0 | 2022-10-10 | 41
2023 | Region VII | CEBU | SIBONGA (CEBU) | P00721763VS | Construction of Flood Mitigation Structure | 123.6058 | 10.0205 | 91675000 | 91674113 | 2023 | QUIRANTE CONSTRUCTION CORPORATION (FORMERLY: QUIRANTE CONSTRUCTION) | 7967 | 2023 | 2023-11-21 | 03/22/2023 | 887 | 0 | 2024-01-12 | 52
2024 | Region VII | CEBU | RONDA (CEBU) | P00834588VS | Construction of Flood Mitigation Structure | 123.4294 | 9.9892 | 57896665.99 | 57896625.61 | 2024 | JCM AMEG BUILDERS CORPORATION (FORMERLY: AMEG CONSTRUCTION & SUPPLY) | 7968 | 2024 | 2024-05-13 | 03/18/2024 | 40.38 | 0 | 2024-11-04 | 175
2023 | Region V | ALBAY | DARAGA (LOCSIN) (ALBAY) | P00742198LZ | Construction of Dike | 123.6945 | 13.1854 | 98998949.89 | 98998745.95 | 2023 | MUNTOPAR BUILDERS CORP. | 7969 | 2023 | 2023-11-17 | 05/03/2023 | 203.94 | 0 | 2023-11-16 |  | 1
2022 | Region V | ALBAY | BACACAY (ALBAY) | P00639394LZ | Construction of Slope Protection Structure | 123.7988 | 13.2917 | 95534998.71 | 95535000 | 2023 | HI-TONE CONSTRUCTION & DEVELOPMENT CORP. (FORMERLY | 7970 | 2022 | 2023-01-29 | 06/03/2022 | 0 | 1.29 | 2023-01-28 |  | 1
2024 | Region IX | ZAMBOANGA DEL SUR | PAGADIAN CITY (CAPITAL) (ZAMBOANGA DEL SUR) | P00821074MN | Construction of Flood Mitigation Structure | 123.4301 | 7.8215 | 9800000 | 9789807.14 | 2025 | GENETIAN BUILDERS AND ENTERPRISES INCORPORATED (FORMERLY: GENETIAN BUILDERS) | 7971 | 2024 | 2025-01-08 | 05/13/2024 | 10192.86 | 0 | 2024-08-19 |  | 142
2022 | Region V | ALBAY | DARAGA (LOCSIN) (ALBAY) | P00630969LZ | Construction of Flood Mitigation Structure | 123.695 | 13.1841 | 72373387.42 | 72373166.5 | 2022 | CBC CONSTRUCTION & SUPPLY / ALPHARD PRIMECON CONSTRUCTION | 7972 | 2022 | 2022-10-28 | 03/21/2022 | 220.92 | 0 | 2022-10-27 |  | 1
2024 | Region VII | CEBU | CONSOLACION (CEBU) | P00834573VS | Construction of Flood Mitigation Structure | 123.9403 | 10.3773 | 57900000 | 57893912.76 | 2025 | ZLREJ TRADING AND CONSTRUCTION CORPORATION | 7973 | 2024 | 2025-02-23 | 08/28/2024 | 6087.24 | 0 | 2025-02-22 |  | 1
2023 | Region V | CAMARINES SUR | GOA (CAMARINES SUR) | P00736103LZ | Construction of Flood Mitigation Structure | 123.4308 | 13.7813 | 95536200 | 95536200 | 2024 | HGG BUILDERS & SUPPLY | 7974 | 2023 | 2024-04-01 | 02/26/2023 | 0 | 0 | 2024-03-31 |  | 1
2022 | Region V | CAMARINES SUR | GARCHITORENA (CAMARINES SUR) | P00631425LZ | Construction of Flood Mitigation Structure | 123.6955 | 13.8472 | 29400000 | 29400000 | 2022 | HGG BUILDERS & SUPPLY | 7975 | 2022 | 2022-12-06 | 04/05/2022 | 0 | 0 | 2022-12-05 |  | 1
2022 | Region V | CAMARINES SUR | GOA (CAMARINES SUR) | P00631418LZ | Construction of Flood Mitigation Structure | 123.431 | 13.7803 | 19600000 | 19600000 | 2022 | SPRING STAR CONSTRUCTION AND SUPPLY | 7976 | 2022 | 2022-07-19 | 02/15/2022 | 0 | 0 | 2022-08-12 | 24
2022 | Region V | ALBAY | DARAGA (LOCSIN) (ALBAY) | P00630998LZ | Rehabilitation / Major Repair of Flood Control Structure | 123.6957 | 13.1823 | 57898454.19 | 57898302.5 | 2022 | MAKAPA CORPORATION | 7977 | 2022 | 2022-09-20 | 03/16/2022 | 151.69 | 0 | 2022-09-19 |  | 1
2022 | Region VII | CEBU | DUMANJUG (CEBU) | P00620450VS | Construction of Flood Mitigation Structure | 123.431 | 10.0595 | 48999951.73 | 48999951.73 | 2022 | QM BUILDERS | 7978 | 2022 | 2022-10-25 | 03/23/2022 | 0 | 0 | 2022-10-24 |  | 1
2022 | Region V | ALBAY | DARAGA (LOCSIN) (ALBAY) | P00621128LZ | Construction of Dike | 123.6958 | 13.1825 | 72373310.95 | 72372927.18 | 2022 | NUMERICAL GATE CONSTRUCTION & SUPPLY CORPORATION | 7979 | 2022 | 2022-10-25 | 03/04/2022 | 383.77 | 0 | 2022-10-24 |  | 1
2022 | Region VII | CEBU | DUMANJUG (CEBU) | P00620039VS | Construction of Flood Mitigation Structure | 123.4312 | 10.0596 | 50174536.56 | 50174536.56 | 2022 | QM BUILDERS | 7980 | 2022 | 2022-09-28 | 02/21/2022 | 0 | 0 | 2022-09-27 |  | 1
2022 | Region V | ALBAY | BACACAY (ALBAY) | P00632945LZ | Rehabilitation / Major Repair of Flood Control Structure | 123.7989 | 13.2681 | 26728184.83 | 14850000 | 2022 | 8AR CONSTRUCTION AND DEVELOPMENT CORPORATION | 7981 | 2022 | 2022-09-11 | 04/18/2022 | 11878184.83 | 0 | 2022-09-10 |  | 1
2023 | Region V | ALBAY | DARAGA (LOCSIN) (ALBAY) | P00726968LZ | Construction of Flood Mitigation Structure | 123.696 | 13.1691 | 72373502.03 | 72372955.14 | 2023 | NEXT GENERATION CONSTRUCTION AND SUPPLY CORPORATION | 7982 | 2023 | 2023-11-02 | 04/04/2023 | 546.89 | 0 | 2023-11-01 |  | 1
2022 | Region V | SORSOGON | BULAN (SORSOGON) | P00630965LZ | Construction of Flood Mitigation Structure | 123.941 | 12.7524 | 57900000 | 56157105.99 | 2022 | CENTERWAYS CONSTRUCTION AND DEVELOPMENT INC. | 7983 | 2022 | 2022-12-05 | 03/24/2022 | 1742894.01 | 0 | 2022-12-04 |  | 1
2023 | Region VII | CEBU | RONDA (CEBU) | P00721907VS | Construction of Flood Mitigation Structure | 123.4313 | 9.9853 | 72373238.72 | 72372872.6 | 2023 | JCM AMEG BUILDERS CORPORATION (FORMERLY: AMEG CONSTRUCTION & SUPPLY) | 7984 | 2023 | 2023-07-10 | 03/16/2023 | 366.12 | 0 | 2023-12-02 | 145
2022 | Region VII | CEBU | CONSOLACION (CEBU) | P00620131VS | Construction of Flood Mitigation Structure | 123.9411 | 10.41 | 46279520 | 46279520 | 2022 | PHIL ASIA RESOURCES & DEVELOPMENT CORP. / WTG CONSTRUCTION & DEVELOPMENT CORPORATION | 7985 | 2022 | 2022-08-23 | 02/15/2022 | 0 | 0 | 2022-09-01 | 9
2023 | Region VII | CEBU | MALABUYOC (CEBU) | P00731620VS | Construction of Flood Mitigation Structure | 123.4315 | 9.9844 | 96015747.66 | 96014076.83 | 2023 | LEGACY CONSTRUCTION CORPORATION (FORMERLY: LEGACY CONSTRUCTION) | 7986 | 2023 | 2023-12-18 | 02/08/2023 | 1670.83 | 0 | 2023-12-17 |  | 1
2023 | Region VII | CEBU | CEBU CITY (CAPITAL) (CEBU) | P00721787VS | Construction of Flood Mitigation Structure | 123.7991 | 10.3415 | 86850000 | 86704127.07 | 2024 | A.S.T BUILDERS / TRI4 CONSTRUCTION & DEVELOPMENT CORP. | 7987 | 2023 | 2024-03-28 | 06/20/2023 | 145872.93 | 0 | 2024-03-27 |  | 1
2023 | Region VII | CEBU | MALABUYOC (CEBU) | P00732013VS | Construction of Flood Mitigation Structure | 123.4315 | 9.9844 | 96498219.65 | 96498218.47 | 2023 | QM BUILDERS | 7988 | 2023 | 2023-12-19 | 02/08/2023 | 1.18 | 0 | 2023-12-18 |  | 1
2023 | Region VII | CEBU | MALABUYOC (CEBU) | P00732012VS | Construction of Flood Mitigation Structure | 123.4315 | 9.9844 | 96498241.6 | 96498180.8 | 2023 | QM BUILDERS | 7989 | 2023 | 2023-08-15 | 02/08/2023 | 60.8 | 0 | 2023-12-18 | 125
2023 | Region VII | CEBU | MALABUYOC (CEBU) | P00733742VS | Construction of Flood Mitigation Structure | 123.4315 | 9.9844 | 19597462.26 | 19303500 | 2023 | QG DEVELOPMENT CORPORATION | 7990 | 2023 | 2023-10-07 | 04/11/2023 | 293962.26 | 0 | 2023-10-06 |  | 1
2022 | Region VII | CEBU | CONSOLACION (CEBU) | P00632986VS | Construction of Slope Protection Structure | 123.9417 | 10.4222 | 53075000 | 53075000 | 2022 | QUIRANTE CONSTRUCTION CORPORATION (FORMERLY: QUIRANTE CONSTRUCTION) / ZLREJ TRADING AND CONSTRUCTION CORPORATION | 7991 | 2022 | 2022-10-03 | 03/31/2022 | 0 | 0 | 2022-10-06 | 3
2022 | Region IX | ZAMBOANGA DEL SUR | PAGADIAN CITY (CAPITAL) (ZAMBOANGA DEL SUR) | P00630567MN | Construction of Flood Mitigation Structure | 123.4319 | 7.8187 | 7350000 | 7332475.49 | 2023 | GENETIAN BUILDERS AND ENTERPRISES INCORPORATED (FORMERLY: GENETIAN BUILDERS) | 7992 | 2022 | 2023-09-05 | 07/19/2022 | 17524.51 | 0 | 2022-12-01 |  | 278
2023 | Region VII | CEBU | RONDA (CEBU) | P00733251VS | Construction of Flood Mitigation Structure | 123.432 | 9.982 | 96497447.87 | 96497256.46 | 2023 | LEGACY CONSTRUCTION CORPORATION (FORMERLY: LEGACY CONSTRUCTION) | 7993 | 2023 | 2023-12-18 | 04/11/2023 | 191.41 | 0 | 2024-02-18 | 62
2023 | Region VII | CEBU | CONSOLACION (CEBU) | P00733287VS | Construction of Slope Protection Structure | 123.9423 | 10.4257 | 96500000 | 96410000 | 2023 | GONZALODO ENTERPRISES / RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R | 7994 | 2023 | 2023-11-20 | 05/18/2023 | 90000 | 0 | 2023-12-26 | 36
2024 | Region VII | CEBU | DUMANJUG (CEBU) | P00820194VS | Construction of Flood Mitigation Structure | 123.432 | 10.0493 | 4898203.72 | 4898131.85 | 2024 | ADAMANT DEVELOPMENT CORPORATION | 7995 | 2024 | 2024-05-26 | 02/16/2024 | 71.87 | 0 | 2024-05-25 |  | 1
2024 | Region VII | CEBU | CONSOLACION (CEBU) | P00820054VS | Construction of Flood Mitigation Structure | 123.9426 | 10.3714 | 144750000 | 144699797.6 | 2024 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R | 7996 | 2024 | 2024-10-28 | 02/16/2024 | 50202.4 | 0 | 2025-01-01 | 65
2024 | Region X | LANAO DEL NORTE | TANGCAL (LANAO DEL NORTE) | P00836182MN | Construction of Flood Mitigation Structure | 123.944 | 8.0427 | 4894060.53 | 4841201 | 2025 | LANAO BUILDER AND ENTERPRISES | 7997 | 2024 | 2025-02-03 | 07/15/2024 | 52859.53 | 0 | 2025-01-05 |  | 29
2023 | Region VII | CEBU | MANDAUE CITY (CEBU) | P00721883VS | Construction of Flood Mitigation Structure | 123.9443 | 10.3422 | 115800000 | 115600000 | 2024 | ZLREJ TRADING AND CONSTRUCTION CORPORATION / GICAR CONSTRUCTION, INC. | 7998 | 2023 | 2024-05-08 | 05/29/2023 | 200000 | 0 | 2024-05-07 |  | 1
2023 | Region VII | CEBU | MANDAUE CITY (CEBU) | P00733266VS | Construction of Flood Mitigation Structure | 123.9452 | 10.3424 | 96500000 | 96399888 | 2024 | QUIRANTE CONSTRUCTION CORPORATION (FORMERLY: QUIRANTE CONSTRUCTION) | 7999 | 2023 | 2024-02-13 | 05/12/2023 | 100112 | 0 | 2024-04-11 | 58
2023 | Region VII | CEBU | CONSOLACION (CEBU) | P00721979VS | Construction of Flood Mitigation Structure | 123.946 | 10.4052 | 96500000 | 96500000 | 2023 | QUIRANTE CONSTRUCTION CORPORATION (FORMERLY: QUIRANTE CONSTRUCTION) / ZLREJ TRADING AND CONSTRUCTION CORPORATION | 8000 | 2023 | 2023-11-27 | 03/21/2023 | 0 | 0 | 2023-11-26 |  | 1
2023 | Region VIII | LEYTE | ABUYOG (LEYTE) | P00733321VS | Construction of Flood Mitigation Structure | 125.0094 | 10.7418 | 48249234.49 | 48248733.47 | 2024 | JUCONS CONSTRUCTION OPC (FORMERLY:JUCONS CONSTRUCTION &SUPPLY) | 8001 | 2023 | 2024-04-05 | 07/05/2023 | 501.02 | 0 | 2024-04-05 | 0
2022 | Region X | MISAMIS ORIENTAL | TAGOLOAN (MISAMIS ORIENTAL) | P00620214MN | Construction of Flood Mitigation Structure | 124.7754 | 8.5352 | 86850000 | 83793901.28 | 2023 | ME 3 CONSTRUCTION | 8002 | 2022 | 2023-11-01 | 07/15/2022 | 3056098.72 | 0 | 2023-10-31 |  | 1
2023 | Region VIII | LEYTE | KANANGA (LEYTE) | P00721555VS | Construction of Flood Mitigation Structure | 124.566 | 11.2029 | 96500000 | 96499999.89 | 2024 | LEDA CONSTRUCTION INCORPORATED | 8003 | 2023 | 2024-01-29 | 04/05/2023 | 0.11 | 0 | 2024-01-28 |  | 1
2023 | Region X | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY (CAPITAL) (MISAMIS ORIENTAL) | P00721267MN | Construction of Revetment | 124.7756 | 8.5122 | 91675000 | 89377158.78 | 2024 | RAMISES CONSTRUCTION | 8004 | 2023 | 2024-06-26 | 02/13/2023 | 2297841.22 | 0 | 2024-06-25 |  | 1
2024 | Region X | BUKIDNON | MARAMAG (BUKIDNON) | P00836176MN | Construction of Drainage Structure | 125.0099 | 7.748 | 4950000 | 4933284.23 | 2024 | CAAB DEVELOPMENT CORP. | 8005 | 2024 | 2024-11-21 | 06/10/2024 | 16715.77 | 0 | 2024-11-20 |  | 1
2022 | Region VIII | BILIRAN | BILIRAN (BILIRAN) | P00630668VS | Construction of Flood Mitigation Structure | 124.4556 | 11.4775 | 4947820.11 | 4947824.24 | 2022 | ED1SON DEVELOPMENT & CONSTRUCTION INC. | 8006 | 2022 | 2022-07-20 | 03/15/2022 | 0 | 4.13 | 2022-07-19 |  | 1
2023 | Region XII | SOUTH COTABATO | CITY OF KORONADAL (CAPITAL) (SOUTH COTABATO) | P00732163MN | Construction of Flood Mitigation Structure | 124.8439 | 6.5032 | 34300000 | 34299901.86 | 2023 | REYDAN BUILDERS | 8007 | 2023 | 2023-11-15 | 06/08/2023 | 98.14 | 0 | 2023-11-14 |  | 1
2022 | Region X | LANAO DEL NORTE | LINAMON (LANAO DEL NORTE) | P00620147MN | Construction of Slope Protection Structure | 124.1563 | 8.1846 | 49000000 | 49000000 | 2022 | LANAO BUILDER AND ENTERPRISES | 8008 | 2022 | 2022-09-12 | 03/18/2022 | 0 | 0 | 2022-09-19 | 7
2022 | Region VIII | LEYTE | HILONGOS (LEYTE) | P00644763VS | Rehabilitation / Major Repair of Flood Control Structure | 124.7768 | 10.3508 | 24125000 | 24064687.5 | 2023 | DC BROS BUILDERS AND TRADING | 8009 | 2022 | 2023-07-10 | 01/12/2023 | 60312.5 | 0 | 2023-07-09 |  | 1
2022 | Region VIII | LEYTE | JARO (LEYTE) | P00620186VS | Construction of Flood Mitigation Structure | 124.7773 | 11.1843 | 48586422.81 | 48586389.57 | 2022 | JUCONS CONSTRUCTION OPC (FORMERLY:JUCONS CONSTRUCTION &SUPPLY) | 8010 | 2022 | 2022-12-20 | 02/21/2022 | 33.24 | 0 | 2023-01-12 | 23
2022 | Region X | CAMIGUIN | MAMBAJAO (CAPITAL) (CAMIGUIN) | P00620137MN | Construction of Flood Mitigation Structure | 124.7791 | 9.1983 | 48999959.2 | 49000000 | 2023 | JAPUZ-JANSOL ENTERPRISES | 8011 | 2022 | 2023-02-03 | 02/15/2022 | 0 | 40.8 | 2022-08-12 |  | 175
2023 | Region VIII | SAMAR (WESTERN SAMAR) | GANDARA (SAMAR (WESTERN SAMAR)) | P00721805VS | Construction of Flood Mitigation Structure | 124.7823 | 11.9968 | 53075000 | 52970012.17 | 2023 | JUPA CONSTRUCTION | 8012 | 2023 | 2023-11-25 | 04/04/2023 | 104987.83 | 0 | 2023-12-01 | 6
2022 | Region X | MISAMIS ORIENTAL | TAGOLOAN (MISAMIS ORIENTAL) | P00620350MN | Construction of Flood Mitigation Structure | 124.7826 | 8.5365 | 48250000 | 47276009.03 | 2023 | TRIPARCO DEVELOPMENT CORPORATION | 8013 | 2022 | 2023-08-21 | 11/07/2022 | 973990.97 | 0 | 2023-07-28 |  | 24
2023 | Region X | MISAMIS ORIENTAL | BALINGASAG (MISAMIS ORIENTAL) | P00721639MN | Construction of Flood Mitigation Structure | 124.7827 | 8.7725 | 96500000 | 96500000 | 2023 | ROAD EDGE TRADING & DEVELOPMENT SERVICES | 8014 | 2023 | 2023-10-16 | 04/20/2023 | 0 | 0 | 2024-02-16 | 123
2023 | Region X | MISAMIS ORIENTAL | BALINGASAG (MISAMIS ORIENTAL) | P00721557MN | Construction of Flood Mitigation Structure | 124.7827 | 8.7725 | 72375000 | 72375000 | 2024 | DICON BUILDERS CORP. | 8015 | 2023 | 2024-01-10 | 04/25/2023 | 0 | 0 | 2024-01-09 |  | 1
2023 | Region XII | SOUTH COTABATO | NORALA (SOUTH COTABATO) | P00721509MN | Construction of Flood Mitigation Structure | 124.6981 | 6.5133 | 34300000 | 34299868.03 | 2023 | PALMARES CONSTRUCTION & GENERAL MERCHANDISE CORP. (FORMERLY: PALMARES GENERAL MERCHANDISE) | 8016 | 2023 | 2023-10-10 | 04/17/2023 | 131.97 | 0 | 2023-10-09 |  | 1
2023 | Region VIII | LEYTE | TACLOBAN CITY (CAPITAL) (LEYTE) | P00721918VS | Construction of Flood Mitigation Structure | 124.9415 | 11.303 | 96497447.02 | 96096604.9 | 2024 | JELM CONSTRUCTION CORP. | 8017 | 2023 | 2024-02-15 | 05/23/2023 | 400842.12 | 0 | 2024-02-14 |  | 1
2022 | Region X | LANAO DEL SUR | DITSAAN-RAMAIN (LANAO DEL SUR) | P00620040MN | Construction of Flood Mitigation Structure | 124.3437 | 7.9849 | 125450000 | 121686414.2 | 2022 | M.M.A. ACHIEVER CONSTRUCTION & DEVELOPMENT CORP. | 8018 | 2022 | 2022-12-23 | 03/25/2022 | 3763585.8 | 0 | 2022-12-22 |  | 1
2023 | Region XII | SOUTH COTABATO | SANTO NIÃ‘O (SOUTH COTABATO) | P00721467MN | Construction of Flood Mitigation Structure | 124.6203 | 6.4736 | 106150000 | 106149850.6 | 2024 | GEMMA CONSTRUCTION SUPPLY, INC.(FORMERLY:GEMMA CON | 8019 | 2023 | 2024-10-07 | 09/19/2023 | 149.4 | 0 | 2024-10-10 | 3
2022 | Region VIII | LEYTE | KANANGA (LEYTE) | P00620190VS | Construction of Flood Mitigation Structure | 124.5662 | 11.1871 | 144750000 | 144750000 | 2022 | LEDA CONSTRUCTION INCORPORATED | 8020 | 2022 | 2022-12-19 | 03/25/2022 | 0 | 0 | 2022-12-18 |  | 1
2024 | Region VIII | LEYTE | JARO (LEYTE) | P00832681VS | Construction of Flood Mitigation Structure | 124.7828 | 11.1873 | 4899384.7 | 4862639.81 | 2024 | IVS BUILDERS | 8021 | 2024 | 2024-09-14 | 03/15/2024 | 36744.89 | 0 | 2024-09-13 |  | 1
2023 | Region VIII | LEYTE | SAN MIGUEL (LEYTE) | P00721708VS | Construction of Flood Mitigation Structure | 124.783 | 11.3651 | 49000000 | 48949999.55 | 2023 | LANOY CONSTRUCTION | 8022 | 2023 | 2023-07-10 | 03/28/2023 | 50000.45 | 0 | 2023-10-12 | 94
2023 | Region X | MISAMIS ORIENTAL | BALINGASAG (MISAMIS ORIENTAL) | P00721554MN | Construction of Flood Mitigation Structure | 124.7833 | 8.7679 | 72375000 | 72375000 | 2023 | EQUALYZ TRADING | 8023 | 2023 | 2023-09-06 | 04/05/2023 | 0 | 0 | 2023-12-20 | 105
2023 | Region X | MISAMIS ORIENTAL | BALINGASAG (MISAMIS ORIENTAL) | P00721555MN | Construction of Flood Mitigation Structure | 124.7833 | 8.7679 | 72375000 | 72375000 | 2023 | EQUALYZ TRADING | 8024 | 2023 | 2023-09-06 | 05/08/2023 | 0 | 0 | 2024-01-22 | 138
2023 | Region VIII | SAMAR (WESTERN SAMAR) | GANDARA (SAMAR (WESTERN SAMAR)) | P00721982VS | Construction of Flood Mitigation Structure | 124.7834 | 11.9999 | 53075000 | 53045950.9 | 2023 | JFR CONSTRUCTION INC. (FORMERLY:JFR CONSTRUCTION) | 8025 | 2023 | 2023-09-18 | 03/27/2023 | 29049.1 | 0 | 2023-11-23 | 66
2022 | Region X | CAMIGUIN | MAHINOG (CAMIGUIN) | P00620130MN | Construction of Flood Mitigation Structure | 124.7835 | 9.1763 | 29399963.46 | 28021001.32 | 2022 | CLC CONSTRUCTION SERVICES AND SUPPLY | 8026 | 2022 | 2022-09-15 | 02/09/2022 | 1378962.14 | 0 | 2022-07-17 |  | 60
2023 | Region X | MISAMIS ORIENTAL | BALINGASAG (MISAMIS ORIENTAL) | P00721538MN | Construction of Revetment | 124.7845 | 8.7785 | 72375000 | 72375000 | 2023 | LEGACY CONSTRUCTION CORPORATION (FORMERLY: LEGACY CONSTRUCTION) | 8027 | 2023 | 2023-12-11 | 06/15/2023 | 0 | 0 | 2024-02-20 | 71
2022 | Region X | CAMIGUIN | MAHINOG (CAMIGUIN) | P00634132MN | Construction of Drainage Structure | 124.7846 | 9.174 | 4949999.17 | 4939885.65 | 2022 | FNTC CONSTRUCTION | 8028 | 2022 | 2022-08-16 | 04/11/2022 | 10113.52 | 0 | 2022-07-02 |  | 45
2023 | Region X | MISAMIS ORIENTAL | BINUANGAN (MISAMIS ORIENTAL) | P00733987MN | Construction of Revetment | 124.7859 | 8.9177 | 72375000 | 72375000 | 2024 | VICENTE T. LAO CONSTRUCTION | 8029 | 2023 | 2024-03-08 | 04/23/2023 | 0 | 0 | 2024-03-07 |  | 1
2022 | Region X | MISAMIS ORIENTAL | TAGOLOAN (MISAMIS ORIENTAL) | P00630494MN | Construction of Flood Mitigation Structure | 124.7861 | 8.5348 | 67550000 | 65157953.24 | 2023 | TRIPARCO DEVELOPMENT CORPORATION | 8030 | 2022 | 2023-10-09 | 05/23/2022 | 2392046.76 | 0 | 2023-07-15 |  | 86
2023 | Region VIII | LEYTE | JARO (LEYTE) | P00721574VS | Construction of Flood Mitigation Structure | 124.7863 | 11.1885 | 55487451.22 | 54655168.88 | 2023 | FAIRCHILD BUILDERS & DEVELOPERS, INC. | 8031 | 2023 | 2023-12-18 | 04/27/2023 | 832282.34 | 0 | 2023-12-24 | 6
2022 | Region X | MISAMIS ORIENTAL | TAGOLOAN (MISAMIS ORIENTAL) | P00634957MN | Construction of Flood Mitigation Structure | 124.7869 | 8.5343 | 67550000 | 65499177.15 | 2023 | EQUI-PARCO CONSTRUCTION COMPANY | 8032 | 2022 | 2023-07-24 | 05/23/2022 | 2050822.85 | 0 | 2023-07-15 |  | 9
2024 | Region VIII | LEYTE | BATO (LEYTE) | P00834684VS | Construction of Flood Mitigation Structure | 124.7876 | 10.33 | 49000000 | 48265131.9 | 2024 | C N E CONSTRUCTION | 8033 | 2024 | 2024-12-11 | 05/20/2024 | 734868.1 | 0 | 2025-02-12 | 63
2022 | Region X | MISAMIS ORIENTAL | TAGOLOAN (MISAMIS ORIENTAL) | P00634956MN | Construction of Flood Mitigation Structure | 124.7876 | 8.5335 | 67550000 | 65170004.82 | 2023 | EQUI-PARCO CONSTRUCTION COMPANY | 8034 | 2022 | 2023-07-24 | 05/23/2022 | 2379995.18 | 0 | 2023-07-15 |  | 9
2022 | Region X | MISAMIS ORIENTAL | TAGOLOAN (MISAMIS ORIENTAL) | P00630495MN | Construction of Flood Mitigation Structure | 124.7876 | 8.5335 | 67550000 | 65153251.9 | 2023 | TRIPARCO DEVELOPMENT CORPORATION | 8035 | 2022 | 2023-07-24 | 05/23/2022 | 2396748.1 | 0 | 2023-07-15 |  | 9
2023 | Region XII | COTABATO (NORTH COTABATO) | KABACAN (COTABATO (NORTH COTABATO)) | P00721457MN | Construction of Flood Mitigation Structure | 124.7878 | 7.1306 | 72375000 | 72167177.4 | 2023 | MARCUS CONSTRUCTION & SUPPLY | 8036 | 2023 | 2023-12-29 | 03/21/2023 | 207822.6 | 0 | 2024-01-27 | 29
2023 | Region X | MISAMIS ORIENTAL | TAGOLOAN (MISAMIS ORIENTAL) | P00721416MN | Construction of Flood Mitigation Structure | 124.7878 | 8.5327 | 289500000 | 279359677.5 | 2024 | EQUI-PARCO CONSTRUCTION COMPANY / TRIPARCO DEVELOPMENT CORPORATION | 8037 | 2023 | 2024-05-26 | 03/29/2023 | 10140322.5 | 0 | 2024-05-25 |  | 1
2024 | Region X | MISAMIS ORIENTAL | TAGOLOAN (MISAMIS ORIENTAL) | P00820266MN | Construction of Flood Mitigation Structure | 124.7879 | 8.5325 | 96500000 | 96500000 | 2024 | SISBRO CONSTRUCTION CORPORATION (FORMERLY: SISBRO CONSTRUCTION & SUPPLY) | 8038 | 2024 | 2024-09-25 | 02/05/2024 | 0 | 0 | 2024-11-24 | 60
2023 | Region VIII | LEYTE | CITY OF BAYBAY (LEYTE) | P00721583VS | Construction of Flood Mitigation Structure | 124.788 | 10.7499 | 53075000 | 52588254.57 | 2023 | C N E CONSTRUCTION | 8039 | 2023 | 2023-12-15 | 04/04/2023 | 486745.43 | 0 | 2023-12-28 | 13
2024 | Region X | MISAMIS ORIENTAL | TAGOLOAN (MISAMIS ORIENTAL) | P00820274MN | Construction of Flood Mitigation Structure | 124.7882 | 8.5346 | 96500000 | 96500000 | 2024 | ROAD EDGE TRADING & DEVELOPMENT SERVICES | 8040 | 2024 | 2024-11-25 | 02/05/2024 | 0 | 0 | 2024-11-24 |  | 1
2024 | Region X | MISAMIS ORIENTAL | TAGOLOAN (MISAMIS ORIENTAL) | P00820265MN | Construction of Flood Mitigation Structure | 124.7889 | 8.5336 | 96500000 | 96500000 | 2024 | CAGALAWAN ENTERPRISES / SISBRO CONSTRUCTION CORPORATION (FORMERLY: SISBRO CONSTRUCTION & SUPPLY) | 8041 | 2024 | 2024-11-25 | 02/05/2024 | 0 | 0 | 2024-11-24 |  | 1
2021 | Region X | MISAMIS ORIENTAL |  | P00550572MN | Construction of Flood Mitigation Structure | 124.7897 | 8.7695 | 19600000 | 19795000 | 2022 | ONE NINE ONE TRADING | 8042 | 2021 | 2022-12-01 | 07/05/2022 | 0 | 195000 | 2022-12-27 | 26
2024 | Region VIII | LEYTE | JARO (LEYTE) | P00820360VS | Construction of Flood Mitigation Structure | 124.79 | 11.1182 | 67549448.75 | 67530749.5 | 2024 | FAIRCHILD BUILDERS & DEVELOPERS, INC. | 8043 | 2024 | 2024-11-25 | 03/13/2024 | 18699.25 | 0 | 2025-01-09 | 45
2023 | Region X | MISAMIS ORIENTAL | TAGOLOAN (MISAMIS ORIENTAL) | P00721417MN | Construction of Flood Mitigation Structure | 124.7902 | 8.5298 | 289500000 | 280801925.4 | 2024 | EQUI-PARCO CONSTRUCTION COMPANY / TRIPARCO DEVELOPMENT CORPORATION | 8044 | 2023 | 2024-07-20 | 03/29/2023 | 8698074.6 | 0 | 2024-07-19 |  | 1
2022 | Region XII | COTABATO (NORTH COTABATO) | KABACAN (COTABATO (NORTH COTABATO)) | P00620280MN | Construction of Revetment | 124.7903 | 7.1221 | 48250000 | 48999638.16 | 2023 | MARCUS CONSTRUCTION & SUPPLY | 8045 | 2022 | 2023-05-06 | 02/23/2022 | 0 | 749638.16 | 2023-05-05 |  | 1
2024 | Region X | MISAMIS ORIENTAL | LAGONGLONG (MISAMIS ORIENTAL) | P00835876MN | Construction of Flood Mitigation Structure | 124.7911 | 8.8132 | 49000000 | 49000000 | 2025 | JEJOR'S CONSTRUCTION CORPORATION | 8046 | 2024 | 2025-03-25 | 05/27/2024 | 0 | 0 | 2025-03-24 |  | 1
2023 | Region X | MISAMIS ORIENTAL | BALINGASAG (MISAMIS ORIENTAL) | P00721556MN | Construction of Flood Mitigation Structure | 124.7919 | 8.7697 | 72375000 | 72375000 | 2023 | ROAD EDGE TRADING & DEVELOPMENT SERVICES / CHIU BUILDERS | 8047 | 2023 | 2023-11-28 | 04/20/2023 | 0 | 0 | 2024-01-04 | 37
2023 | Region X | CAMIGUIN | MAHINOG (CAMIGUIN) | P00732485MN | Rehabilitation / Major Repair of Drainage Structure | 124.7925 | 9.1388 | 6369999.51 | 6322322.11 | 2023 | CLC CONSTRUCTION SERVICES AND SUPPLY | 8048 | 2023 | 2023-12-18 | 02/10/2023 | 47677.4 | 0 | 2023-07-11 |  | 160
2023 | Region X | MISAMIS ORIENTAL | TAGOLOAN (MISAMIS ORIENTAL) | P00721419MN | Construction of Flood Mitigation Structure | 124.7932 | 8.5274 | 274500000 | 266231274.7 | 2024 | HAPPY ALL3 BUILDERS CORPORATION / EQUI-PARCO CONSTRUCTION COMPANY | 8049 | 2023 | 2024-08-31 | 03/29/2023 | 8268725.3 | 0 | 2024-08-30 |  | 1
2024 | Region XII | COTABATO (NORTH COTABATO) | CARMEN (COTABATO (NORTH COTABATO)) | P00820095MN | Construction of Flood Mitigation Structure | 124.7946 | 7.2154 | 96500000 | 96345472.96 | 2024 | MARCUS CONSTRUCTION & SUPPLY | 8050 | 2024 | 2024-12-09 | 03/25/2024 | 154527.04 | 0 | 2024-12-08 |  | 1
2023 | Region X | MISAMIS ORIENTAL | TAGOLOAN (MISAMIS ORIENTAL) | P00721544MN | Construction of Flood Mitigation Structure | 124.7957 | 8.5363 | 77200000 | 77200000 | 2024 | RITCHE-NATHALIE BUILDERS & GENERAL MERCHANDISE | 8051 | 2023 | 2024-01-26 | 03/17/2023 | 0 | 0 | 2024-01-25 |  | 1
2024 | Region VIII | SAMAR (WESTERN SAMAR) | GANDARA (SAMAR (WESTERN SAMAR)) | P00820420VS | Construction of Flood Mitigation Structure | 124.7958 | 12.0153 | 29400000 | 29370339.61 | 2024 | ETAN CONSTRUCTION | 8052 | 2024 | 2024-10-15 | 04/18/2024 | 29660.39 | 0 | 2024-10-14 |  | 1
2022 | Region VIII | LEYTE | CITY OF BAYBAY (LEYTE) | P00620336VS | Construction of Flood Mitigation Structure | 124.796 | 10.6861 | 49000000 | 48402432.51 | 2023 | RJIR ENTERPRISES CORPORATION | 8053 | 2022 | 2023-02-05 | 02/23/2022 | 597567.49 | 0 | 2023-02-04 |  | 1
2021 | Region XII | COTABATO (NORTH COTABATO) |  | P00522328MN | Construction of Dike | 124.7961 | 7.0784 | 44100000 | 43424992.69 | 2022 | MARCUS CONSTRUCTION & SUPPLY | 8054 | 2021 | 2022-09-03 | 03/29/2021 | 675007.31 | 0 | 2022-05-10 |  | 116
2024 | Region X | MISAMIS ORIENTAL | TAGOLOAN (MISAMIS ORIENTAL) | P00835764MN | Construction of Flood Mitigation Structure | 124.7964 | 8.5375 | 96500000 | 96500000 | 2024 | RITCHE-NATHALIE DEVELOPMENT CORPORATION (FORMERLY: RITCHE-NATHALIE BUILDERS AND GEN. MERCHANDISE) | 8055 | 2024 | 2024-11-19 | 02/15/2024 | 0 | 0 | 2024-12-04 | 15
2023 | Region X | CAMIGUIN | MAHINOG (CAMIGUIN) | P00734388MN | Construction of Flood Mitigation Structure | 124.797 | 9.148 | 48999999.78 | 47521019.29 | 2024 | JEJOR'S CONSTRUCTION CORPORATION | 8056 | 2023 | 2024-09-29 | 04/20/2023 | 1478980.49 | 0 | 2023-10-21 |  | 344
2023 | Region VIII | LEYTE | SAN MIGUEL (LEYTE) | P00721709VS | Construction of Flood Mitigation Structure | 124.7975 | 11.3764 | 49000000 | 48936924.37 | 2023 | B. VICENCIO BUILDERS (BVB), INC. (FORMERLY:B. VICENCIO CONSTRUCTION) / VHITS D. G. BUILDERS & ENTERPRISES | 8057 | 2023 | 2023-11-11 | 05/24/2023 | 63075.63 | 0 | 2023-11-10 |  | 1
2024 | Region X | MISAMIS ORIENTAL | TAGOLOAN (MISAMIS ORIENTAL) | P00820896MN | Construction of Flood Mitigation Structure | 124.798 | 8.5383 | 96500000 | 96500000 | 2024 | RITCHE-NATHALIE DEVELOPMENT CORPORATION (FORMERLY: RITCHE-NATHALIE BUILDERS AND GEN. MERCHANDISE) | 8058 | 2024 | 2024-11-25 | 02/15/2024 | 0 | 0 | 2024-12-04 | 9
2022 | Region XII | SOUTH COTABATO | SURALLAH (SOUTH COTABATO) | P00630620MN | Construction of Flood Mitigation Structure | 124.7997 | 6.3492 | 44100000 | 44071697.8 | 2022 | BETTER WORK CONSTRUCTION / GABRIELLAS ENTERPRISES | 8059 | 2022 | 2022-07-20 | 03/09/2022 | 28302.2 | 0 | 2022-07-19 |  | 1
2023 | Region XII | SOUTH COTABATO | SURALLAH (SOUTH COTABATO) | P00732096MN | Construction of Flood Mitigation Structure | 124.8 | 6.3449 | 28950000 | 28899987.85 | 2023 | REYDAN BUILDERS | 8060 | 2023 | 2023-11-07 | 06/08/2023 | 50012.15 | 0 | 2023-11-06 |  | 1
2023 | Region XII | SOUTH COTABATO | BANGA (SOUTH COTABATO) | P00721510MN | Construction of Flood Mitigation Structure | 124.8006 | 6.3983 | 27440000 | 27439788.25 | 2023 | ALEXANDER BUILDERS | 8061 | 2023 | 2023-08-29 | 04/17/2023 | 211.75 | 0 | 2023-08-28 |  | 1
2023 | Region XII | COTABATO (NORTH COTABATO) | KABACAN (COTABATO (NORTH COTABATO)) | P00721298MN | Construction of Flood Mitigation Structure | 124.802 | 7.072 | 92640000 | 92638620.31 | 2024 | MUST ENTERPRISES / BORDERLINE CONSTRUCTION & SUPPLY | 8062 | 2023 | 2024-12-23 | 09/01/2023 | 1379.69 | 0 | 2025-01-15 | 23
2023 | Region VIII | LEYTE | CITY OF BAYBAY (LEYTE) | P00721969VS | Construction of Flood Mitigation Structure | 124.8047 | 10.7038 | 5880000 | 5756520 | 2023 | MERMIT CONSTRUCTION AND ENTERPRISES | 8063 | 2023 | 2023-08-02 | 04/05/2023 | 123480 | 0 | 2023-08-01 |  | 1
2022 | Region VIII | LEYTE | CITY OF BAYBAY (LEYTE) | P00620201VS | Construction of Flood Mitigation Structure | 124.8055 | 10.6649 | 49000000 | 48436562.67 | 2022 | RJIR ENTERPRISES CORPORATION | 8064 | 2022 | 2022-11-30 | 02/15/2022 | 563437.33 | 0 | 2022-11-29 |  | 1
2023 | Region VIII | LEYTE | CITY OF BAYBAY (LEYTE) | P00721582VS | Construction of Flood Mitigation Structure | 124.8055 | 10.6649 | 53075000 | 52408772.55 | 2023 | C N E CONSTRUCTION | 8065 | 2023 | 2023-12-05 | 04/04/2023 | 666227.45 | 0 | 2023-12-28 | 23
2022 | Region XII | COTABATO (NORTH COTABATO) | KABACAN (COTABATO (NORTH COTABATO)) | P00620282MN | Construction of Revetment | 124.8058 | 7.1412 | 48250000 | 48999996.61 | 2022 | MARCUS CONSTRUCTION & SUPPLY | 8066 | 2022 | 2022-12-19 | 03/24/2022 | 0 | 749996.61 | 2022-12-18 |  | 1
2023 | Region X | MISAMIS ORIENTAL | KINOGUITAN (MISAMIS ORIENTAL) | P00733988MN | Construction of Revetment | 124.8084 | 8.9951 | 72375000 | 72375000 | 2024 | VICENTE T. LAO CONSTRUCTION | 8067 | 2023 | 2024-01-30 | 04/23/2023 | 0 | 0 | 2024-02-06 | 7
2022 | Region VIII | LEYTE | SAN MIGUEL (LEYTE) | P00632039VS | Construction of Flood Mitigation Structure | 124.81 | 11.3563 | 49500000 | 49004805.5 | 2023 | JGO BUILDERS | 8068 | 2022 | 2023-04-21 | 06/01/2022 | 495194.5 | 0 | 2023-04-20 |  | 1
2022 | Region VIII | SAMAR (WESTERN SAMAR) | GANDARA (SAMAR (WESTERN SAMAR)) | P00644607VS | Rehabilitation / Major Repair of Flood Control Structure | 124.8109 | 12.0203 | 28950000 | 28728643.57 | 2022 | JFR CONSTRUCTION INC. (FORMERLY:JFR CONSTRUCTION) | 8069 | 2022 | 2022-11-11 | 03/25/2022 | 221356.43 | 0 | 2022-11-10 |  | 1
2024 | Region VIII | LEYTE | CITY OF BAYBAY (LEYTE) | P00834683VS | Construction of Flood Mitigation Structure | 124.8109 | 10.6634 | 49000000 | 48476248.01 | 2024 | C N E CONSTRUCTION | 8070 | 2024 | 2024-12-06 | 05/27/2024 | 523751.99 | 0 | 2025-02-19 | 75
2024 | Region VIII | SAMAR (WESTERN SAMAR) | GANDARA (SAMAR (WESTERN SAMAR)) | P00835023VS | Construction of Flood Mitigation Structure | 124.8111 | 12.0137 | 7920000 | 7887413.96 | 2024 | 5GG CONSTRUCTION (FORMERLY: 5G GALVEZ CONSTRUCTION AND SUPPLY) | 8071 | 2024 | 2024-10-28 | 04/26/2024 | 32586.04 | 0 | 2024-11-29 | 32
2023 | Region VIII | LEYTE | CITY OF BAYBAY (LEYTE) | P00733294VS | Construction of Flood Mitigation Structure | 124.8115 | 10.668 | 82025000 | 80786514.33 | 2023 | RJIR ENTERPRISES CORPORATION | 8072 | 2023 | 2023-11-06 | 05/31/2023 | 1238485.67 | 0 | 2024-02-23 | 109
2022 | Region VIII | SAMAR (WESTERN SAMAR) | GANDARA (SAMAR (WESTERN SAMAR)) | P00620463VS | Rehabilitation / Major Repair of Flood Control Structure | 124.8122 | 12.0192 | 39200000 | 38913945.6 | 2022 | JFR CONSTRUCTION INC. (FORMERLY:JFR CONSTRUCTION) | 8073 | 2022 | 2022-10-01 | 03/25/2022 | 286054.4 | 0 | 2022-09-30 |  | 1
2023 | Region VIII | SAMAR (WESTERN SAMAR) | GANDARA (SAMAR (WESTERN SAMAR)) | P00733763VS | Construction of Flood Mitigation Structure | 124.8129 | 12.0171 | 19800000 | 19761387.58 | 2024 | MDP CONSTRUCTION SERVICES | 8074 | 2023 | 2024-07-11 | 05/10/2023 | 38612.42 | 0 | 2024-02-13 |  | 149
2024 | Region VIII | SAMAR (WESTERN SAMAR) | GANDARA (SAMAR (WESTERN SAMAR)) | P00820421VS | Construction of Flood Mitigation Structure | 124.8132 | 12.0165 | 49000000 | 48485486.62 | 2024 | JUPA CONSTRUCTION | 8075 | 2024 | 2024-11-09 | 04/18/2024 | 514513.38 | 0 | 2024-11-08 |  | 1
2023 | Region X | MISAMIS ORIENTAL | BALINGASAG (MISAMIS ORIENTAL) | P00721638MN | Construction of Flood Mitigation Structure | 124.8133 | 8.9798 | 96500000 | 96500000 | 2023 | ROAD EDGE TRADING & DEVELOPMENT SERVICES | 8076 | 2023 | 2023-12-14 | 04/20/2023 | 0 | 0 | 2024-02-10 | 58
2023 | Region XII | SOUTH COTABATO | T'BOLI (SOUTH COTABATO) | P00732166MN | Construction of Flood Mitigation Structure | 124.8135 | 6.2291 | 24500000 | 24498872.03 | 2023 | SOUTHCAST CONSTRUCTION | 8077 | 2023 | 2023-08-02 | 04/12/2023 | 1127.97 | 0 | 2023-08-01 |  | 1
2022 | Region VIII | LEYTE | CITY OF BAYBAY (LEYTE) | P00630235VS | Construction of Flood Mitigation Structure | 124.8147 | 10.666 | 49000000 | 48485534.41 | 2022 | C N E CONSTRUCTION | 8078 | 2022 | 2022-12-14 | 03/02/2022 | 514465.59 | 0 | 2022-12-13 |  | 1
2022 | Region VIII | SAMAR (WESTERN SAMAR) | GANDARA (SAMAR (WESTERN SAMAR)) | P00620341VS | Construction of Flood Mitigation Structure | 124.8161 | 12.0253 | 49000000 | 48408761.87 | 2023 | RNMK CONSTRUCTION, SUPPLY AND DEVELOPMENT CORP. (FOR: RNMK CONST. & DEV'T) | 8079 | 2022 | 2023-11-29 | 02/08/2022 | 591238.13 | 0 | 2023-12-25 | 26
2022 | Region VIII | LEYTE | CITY OF BAYBAY (LEYTE) | P00620337VS | Construction of Flood Mitigation Structure | 124.8187 | 10.6813 | 49000000 | 48338500 | 2022 | RJIR ENTERPRISES CORPORATION | 8080 | 2022 | 2022-11-30 | 02/15/2022 | 661500 | 0 | 2022-11-29 |  | 1
2023 | Region VIII | LEYTE | CITY OF BAYBAY (LEYTE) | P00721967VS | Construction of Flood Mitigation Structure | 124.8187 | 10.6813 | 49000000 | 48216266.02 | 2024 | ARCA BUILDERS | 8081 | 2023 | 2024-03-22 | 05/23/2023 | 783733.98 | 0 | 2024-03-21 |  | 1
2024 | Region VIII | SAMAR (WESTERN SAMAR) | GANDARA (SAMAR (WESTERN SAMAR)) | P00820379VS | Construction of Flood Mitigation Structure | 124.8195 | 12.0191 | 67550000 | 67514703.27 | 2024 | JFR CONSTRUCTION INC. (FORMERLY:JFR CONSTRUCTION) | 8082 | 2024 | 2024-11-11 | 04/18/2024 | 35296.73 | 0 | 2024-11-23 | 12
2023 | Region XII | SULTAN KUDARAT | LUTAYAN (SULTAN KUDARAT) | P00721622MN | Construction of Flood Mitigation Structure | 124.8198 | 6.6002 | 97857256.94 | 97656143.98 | 2024 | ABU CONSTRUCTION | 8083 | 2023 | 2024-01-30 | 04/04/2023 | 201112.96 | 0 | 2024-01-30 | 0
2021 | Region VIII | LEYTE |  | P00549985VS | Construction of Flood Mitigation Structure | 124.8208 | 11.205 | 49000000 | 49000000 | 2022 | FAIRCHILD BUILDERS & DEVELOPERS, INC. / ONE MYRNA CONSTRUCTION AND SUPPLY | 8084 | 2021 | 2022-07-28 | 11/11/2021 | 0 | 0 | 2022-07-27 |  | 1
2022 | Region XII | SOUTH COTABATO | BANGA (SOUTH COTABATO) | P00620251MN | Construction of Flood Mitigation Structure | 124.8211 | 6.3731 | 101325000 | 80668846.82 | 2022 | AMPLEX CONSTRUCTION AND SUPPLIES | 8085 | 2022 | 2022-12-29 | 03/14/2022 | 20656153.18 | 0 | 2023-01-22 | 24
2022 | Region VIII | SAMAR (WESTERN SAMAR) | GANDARA (SAMAR (WESTERN SAMAR)) | P00620418VS | Construction of Flood Mitigation Structure | 124.8219 | 12.0272 | 49000000 | 48956362.43 | 2022 | PABLO S. LABASBAS CONSTRUCTION CORPORATION (FORMERLY: PABLOS. LABASBAS CONSTRUCTION CORPORATION) | 8086 | 2022 | 2022-10-11 | 03/25/2022 | 43637.57 | 0 | 2022-10-10 |  | 1
2021 | Region VIII | LEYTE |  | P00549986VS | Construction of Flood Mitigation Structure | 124.8248 | 11.2178 | 49000000 | 49000000 | 2022 | ED1SON DEVELOPMENT & CONSTRUCTION INC. / MILES CONSTRUCTION AND ENTERPRISES | 8087 | 2021 | 2022-07-28 | 11/11/2021 | 0 | 0 | 2022-07-27 |  | 1
2023 | Region XII | COTABATO (NORTH COTABATO) | KABACAN (COTABATO (NORTH COTABATO)) | P00721507MN | Construction of Flood Mitigation Structure | 124.8249 | 7.1285 | 40180000 | 40070140.29 | 2023 | BETTER WORK CONSTRUCTION | 8088 | 2023 | 2023-09-22 | 04/12/2023 | 109859.71 | 0 | 2023-11-07 | 46
2022 | Region XII | SOUTH COTABATO | T'BOLI (SOUTH COTABATO) | P00630531MN | Construction of Flood Mitigation Structure | 124.8258 | 6.2164 | 49408000 | 49407796.37 | 2022 | BETTER WORK CONSTRUCTION | 8089 | 2022 | 2022-07-28 | 03/02/2022 | 203.63 | 0 | 2022-07-28 | 0
2023 | Region XII | SOUTH COTABATO | T'BOLI (SOUTH COTABATO) | P00732162MN | Construction of Flood Mitigation Structure | 124.8265 | 6.2204 | 49000000 | 24499667.6 | 2023 | BETTER WORK CONSTRUCTION | 8090 | 2023 | 2023-08-07 | 04/17/2023 | 24500332.4 | 0 | 2023-08-06 |  | 1
2023 | Region XII | SULTAN KUDARAT | LUTAYAN (SULTAN KUDARAT) | P00721623MN | Construction of Flood Mitigation Structure | 124.8272 | 6.572 | 97880478.24 | 97730411.86 | 2023 | ABU CONSTRUCTION | 8091 | 2023 | 2023-11-24 | 04/24/2023 | 150066.38 | 0 | 2023-12-21 | 27
2024 | Region VIII | LEYTE | SAN MIGUEL (LEYTE) | P00820899VS | Construction of Flood Mitigation Structure | 124.8286 | 11.3047 | 96500000 | 96434585.4 | 2024 | JELM CONSTRUCTION CORP. | 8092 | 2024 | 2024-12-02 | 07/26/2024 | 65414.6 | 0 | 2025-05-04 | 153
2023 | Region VIII | LEYTE | SAN MIGUEL (LEYTE) | P00721922VS | Construction of Flood Mitigation Structure | 124.8319 | 11.292 | 96500000 | 96435000 | 2024 | D.L. AUREO CONSTRUCTION / JELM CONSTRUCTION CORP. | 8093 | 2023 | 2024-03-18 | 07/10/2023 | 65000 | 0 | 2024-04-17 | 30
2022 | Region VIII | SAMAR (WESTERN SAMAR) | GANDARA (SAMAR (WESTERN SAMAR)) | P00630243VS | Construction of Slope Protection Structure | 124.8332 | 12.0772 | 19600000 | 19492118.36 | 2022 | DANILORSO CORP. OPERATING UNDER THE NAME OF DRS BUILDERS AND CONSTRUCTION SUPPLIES | 8094 | 2022 | 2022-07-07 | 03/23/2022 | 107881.64 | 0 | 2022-08-13 | 37
2022 | Region VIII | SOUTHERN LEYTE | CITY OF MAASIN (CAPITAL) (SOUTHERN LEYTE) | P00632992VS | Construction of Flood Mitigation Structure | 124.8337 | 10.1357 | 96500000 | 96455982.75 | 2023 | ON POINT CONSTRUCTION AND DEVELOPMENT CORPORATION (FORMERLY:ON POINT CONSTRUCTION) / UKC BUILDERS, INC. | 8095 | 2022 | 2023-09-05 | 04/06/2022 | 44017.25 | 0 | 2023-09-04 |  | 1
2024 | Region XII | COTABATO (NORTH COTABATO) | KABACAN (COTABATO (NORTH COTABATO)) | P00835886MN | Construction of Flood Mitigation Structure | 124.8343 | 7.1251 | 29400000 | 29380000.45 | 2024 | BORDERLINE CONSTRUCTION & SUPPLY | 8096 | 2024 | 2024-09-23 | 03/25/2024 | 19999.55 | 0 | 2024-10-01 | 8
2022 | Region VIII | SOUTHERN LEYTE | CITY OF MAASIN (CAPITAL) (SOUTHERN LEYTE) | P00632047VS | Construction of Flood Mitigation Structure | 124.8344 | 10.1366 | 19800000 | 19776940.86 | 2023 | ON POINT CONSTRUCTION AND DEVELOPMENT CORPORATION (FORMERLY:ON POINT CONSTRUCTION) | 8097 | 2022 | 2023-02-12 | 04/06/2022 | 23059.14 | 0 | 2023-02-11 |  | 1
2024 | Region XII | COTABATO (NORTH COTABATO) | KABACAN (COTABATO (NORTH COTABATO)) | P00835887MN | Construction of Flood Mitigation Structure | 124.8349 | 7.1248 | 29400000 | 29379974.47 | 2024 | BORDERLINE CONSTRUCTION & SUPPLY | 8098 | 2024 | 2024-11-19 | 03/25/2024 | 20025.53 | 0 | 2024-11-18 |  | 1
2022 | Region X | MISAMIS ORIENTAL | KINOGUITAN (MISAMIS ORIENTAL) | P00630491MN | Construction of Flood Mitigation Structure | 124.8357 | 9.0041 | 67550000 | 64814025.23 | 2023 | TRIPARCO DEVELOPMENT CORPORATION | 8099 | 2022 | 2023-05-03 | 04/11/2022 | 2735974.77 | 0 | 2023-05-02 |  | 1
2023 | Region VIII | LEYTE | ALANGALANG (LEYTE) | P00721704VS | Construction of Flood Mitigation Structure | 124.8372 | 11.2407 | 49000000 | 48925057.49 | 2023 | C N E CONSTRUCTION / ONE MYRNA CONSTRUCTION AND SUPPLY | 8100 | 2023 | 2023-09-25 | 03/20/2023 | 74942.51 | 0 | 2023-10-04 | 9
2022 | Region X | MISAMIS ORIENTAL | BALINGASAG (MISAMIS ORIENTAL) | P00630588MN | Construction of Drainage Structure | 124.8376 | 8.7605 | 9800000 | 9800000 | 2022 | L & L CONSTRUCTION | 8101 | 2022 | 2022-11-30 | 06/05/2022 | 0 | 0 | 2022-11-30 | 0
2022 | Region VIII | SOUTHERN LEYTE | CITY OF MAASIN (CAPITAL) (SOUTHERN LEYTE) | P00630687VS | Construction of Flood Mitigation Structure | 124.839 | 10.1385 | 4900000 | 4950000 | 2022 | 3MC KING CIVIL ENGINEERING CONSTRUCTION | 8102 | 2022 | 2022-07-11 | 02/10/2022 | 0 | 50000 | 2022-07-10 |  | 1
2023 | Region VIII | LEYTE | BABATNGON (LEYTE) | P00731685VS | Construction of Drainage Structure | 124.839 | 11.422 | 24500000 | 24391539.96 | 2023 | HI-TRI DEVELOPMENT CORPORATION | 8103 | 2023 | 2023-09-14 | 04/14/2023 | 108460.04 | 0 | 2023-10-13 | 29
2022 | Region VIII | SOUTHERN LEYTE | CITY OF MAASIN (CAPITAL) (SOUTHERN LEYTE) | P00634058VS | Construction of Flood Mitigation Structure | 124.8398 | 10.1439 | 4950000 | 4924360.55 | 2022 | APTJ CONSTRUCTION SERVICES | 8104 | 2022 | 2022-09-04 | 04/06/2022 | 25639.45 | 0 | 2022-09-03 |  | 1
2024 | Region X | MISAMIS ORIENTAL | BALINGASAG (MISAMIS ORIENTAL) | P00836185MN | Construction of Flood Mitigation Structure | 124.8402 | 8.7858 | 39600000 | 39599823.02 | 2024 | ROAD EDGE TRADING & DEVELOPMENT SERVICES / CHIU BUILDERS | 8105 | 2024 | 2024-12-01 | 04/01/2024 | 176.98 | 0 | 2024-11-30 |  | 1
2022 | Region VIII | SAMAR (WESTERN SAMAR) | GANDARA (SAMAR (WESTERN SAMAR)) | P00630244VS | Construction of Slope Protection Structure | 124.8405 | 12.0889 | 19600000 | 19597359.34 | 2022 | PABLO S. LABASBAS CONSTRUCTION CORPORATION (FORMERLY: PABLOS. LABASBAS CONSTRUCTION CORPORATION) | 8106 | 2022 | 2022-12-05 | 03/23/2022 | 2640.66 | 0 | 2022-12-11 | 6
2022 | Region VIII | SOUTHERN LEYTE | CITY OF MAASIN (CAPITAL) (SOUTHERN LEYTE) | P00633031VS | Construction of Flood Mitigation Structure | 124.8406 | 10.1357 | 9800000 | 9787125 | 2022 | AMB ENTERPRISES | 8107 | 2022 | 2022-10-18 | 04/06/2022 | 12875 | 0 | 2022-09-30 |  | 18
2024 | Region X | MISAMIS ORIENTAL | BALINGASAG (MISAMIS ORIENTAL) | P00821223MN | Construction of Flood Mitigation Structure | 124.8413 | 8.7852 | 29400000 | 29399467.33 | 2024 | VEN RAY CONSTRUCTION CORPORATION | 8108 | 2024 | 2024-12-01 | 04/01/2024 | 532.67 | 0 | 2024-11-30 |  | 1
2024 | Region XII | COTABATO (NORTH COTABATO) | KABACAN (COTABATO (NORTH COTABATO)) | P00820349MN | Construction of Flood Mitigation Structure | 124.8434 | 7.1147 | 65620000 | 65592867.27 | 2024 | MARCUS CONSTRUCTION & SUPPLY | 8109 | 2024 | 2024-09-23 | 03/25/2024 | 27132.73 | 0 | 2024-10-19 | 26
2022 | Region XII | SOUTH COTABATO | CITY OF KORONADAL (CAPITAL) (SOUTH COTABATO) | P00630613MN | Construction of Flood Mitigation Structure | 124.8436 | 6.5006 | 49000000 | 48999530.71 | 2022 | REYDAN BUILDERS / PASE CONSTRUCTION | 8110 | 2022 | 2022-08-22 | 02/18/2022 | 469.29 | 0 | 2022-07-13 |  | 40
2024 | Region VIII | SOUTHERN LEYTE | CITY OF MAASIN (CAPITAL) (SOUTHERN LEYTE) | P00820260VS | Construction of Flood Mitigation Structure | 124.8438 | 10.1485 | 49000000 | 49000000 | 2024 | B. VICENCIO BUILDERS (BVB), INC. (FORMERLY:B. VICENCIO CONSTRUCTION) / JGO BUILDERS | 8111 | 2024 | 2024-12-11 | 02/13/2024 | 0 | 0 | 2024-12-17 | 6
2022 | Region VIII | SOUTHERN LEYTE | BONTOC (SOUTHERN LEYTE) | P00633029VS | Construction of Flood Mitigation Structure | 124.9427 | 10.3558 | 39200000 | 39157464.26 | 2023 | UNIMASTERS CONGLOMERATION, INCORPORATED | 8112 | 2022 | 2023-01-06 | 04/06/2022 | 42535.74 | 0 | 2023-01-05 |  | 1
2024 | Region VIII | SAMAR (WESTERN SAMAR) | SAN JORGE (SAMAR (WESTERN SAMAR)) | P00820256VS | Construction of Flood Mitigation Structure | 124.844 | 12.0006 | 9800000 | 9741200 | 2024 | DANILORSO CORP. OPERATING UNDER THE NAME OF DRS BUILDERS AND CONSTRUCTION SUPPLIES | 8113 | 2024 | 2024-10-11 | 04/18/2024 | 58800 | 0 | 2024-10-10 |  | 1
2023 | Region VIII | LEYTE | ISABEL (LEYTE) | P00731643VS | Construction of Flood Mitigation Structure | 124.4572 | 10.8986 | 96500000 | 96469960.03 | 2024 | RJIR ENTERPRISES CORPORATION | 8114 | 2023 | 2024-04-13 | 06/19/2023 | 30039.97 | 0 | 2024-04-12 |  | 1
2023 | Region XII | SOUTH COTABATO | TUPI (SOUTH COTABATO) | P00734408MN | Construction of Drainage Structure | 124.9445 | 6.3315 | 4950000 | 4948882.27 | 2023 | ROCKSTONE CONSTRUCTION SERVICES & SUPPLY | 8115 | 2023 | 2023-12-18 | 07/20/2023 | 1117.73 | 0 | 2023-12-17 |  | 1
2021 | Region V | CATANDUANES |  | P00561842LZ | Construction of Flood Mitigation Structure | 124.1628 | 13.9167 | 14848760 | 14837820.39 | 2022 | MECHANICS CONSTRUCTION CORPORATION | 8116 | 2021 | 2022-10-05 | 08/09/2021 | 10939.61 | 0 | 2022-04-04 |  | 184
2023 | Region VIII | LEYTE | BABATNGON (LEYTE) | P00731683VS | Construction of Drainage Structure | 124.8457 | 11.4208 | 3920000 | 3905246.26 | 2023 | JDR CONSTRUCTION | 8117 | 2023 | 2023-06-11 | 03/29/2023 | 14753.74 | 0 | 2023-06-10 |  | 1
2022 | Region XII | SULTAN KUDARAT | ESPERANZA (SULTAN KUDARAT) | P00631112MN | Construction of Flood Mitigation Structure | 124.5664 | 6.6741 | 4950000 | 4950000 | 2022 | CASTILLANES CONSTRUCTION AND SUPPLY | 8118 | 2022 | 2022-10-01 | 03/02/2022 | 0 | 0 | 2022-07-18 |  | 75
2024 | Region VIII | LEYTE | ORMOC CITY (LEYTE) | P00820243VS | Construction of Drainage Structure | 124.6205 | 11.014 | 6468000 | 6435658.12 | 2024 | MELGAZO CONSTRUCTION AND SUPPLY | 8119 | 2024 | 2024-04-17 | 02/08/2024 | 32341.88 | 0 | 2024-06-05 | 49
2023 | Region XII | SOUTH COTABATO | NORALA (SOUTH COTABATO) | P00721508MN | Construction of Flood Mitigation Structure | 124.6981 | 6.5261 | 27440000 | 27437932.69 | 2023 | BETTER WORK CONSTRUCTION | 8120 | 2023 | 2023-09-11 | 04/17/2023 | 2067.31 | 0 | 2023-09-10 |  | 1
2024 | Region VIII | BILIRAN | MARIPIPI (BILIRAN) | P00820224VS | Construction of Revetment | 124.3439 | 11.7711 | 9793338.66 | 9646438.6 | 2024 | RMA BUILDERS & SUPPLIES CORPORATION | 8121 | 2024 | 2024-04-10 | 02/14/2024 | 146900.06 | 0 | 2024-07-01 | 82
2024 | Region XII | COTABATO (NORTH COTABATO) | PIGCAWAYAN (COTABATO (NORTH COTABATO)) | P00820185MN | Construction of Flood Mitigation Structure | 124.458 | 7.312 | 16660000 | 16576700 | 2024 | LLABAN CONSTRUCTION & SUPPLY (FORMERLY: LLABAN CON | 8122 | 2024 | 2024-06-24 | 02/07/2024 | 83300 | 0 | 2024-06-23 |  | 1
2022 | Region XII | COTABATO (NORTH COTABATO) | PIGCAWAYAN (COTABATO (NORTH COTABATO)) | P00620272MN | Construction of Flood Mitigation Structure | 124.459 | 7.2812 | 49000000 | 49000000 | 2022 | LLABAN CONSTRUCTION & SUPPLY (FORMERLY: LLABAN CON / GFJ CONSTRUCTION SUPPLY & MERCHANDISE | 8123 | 2022 | 2022-11-03 | 02/02/2022 | 0 | 0 | 2022-10-15 |  | 19
2023 | Region VIII | BILIRAN | KAWAYAN (BILIRAN) | P00732033VS | Construction of Flood Mitigation Structure | 124.4592 | 11.6897 | 9894107.08 | 9894399.28 | 2023 | ROVING PREMIER CONTRACTORS, INC. | 8124 | 2023 | 2023-06-30 | 02/15/2023 | 0 | 292.2 | 2023-07-03 | 3
2022 | Region VIII | BILIRAN | NAVAL (CAPITAL) (BILIRAN) | P00620152VS | Construction of Flood Mitigation Structure | 124.4597 | 11.5794 | 19580481.6 | 18983276.9 | 2022 | SUNRISE BUILDERS | 8125 | 2022 | 2022-09-13 | 02/21/2022 | 597204.7 | 0 | 2022-09-12 |  | 1
2022 | Region VIII | BILIRAN | NAVAL (CAPITAL) (BILIRAN) | P00620159VS | Construction of Flood Mitigation Structure | 124.4607 | 11.5816 | 14685875.25 | 14215927.25 | 2022 | SUNRISE BUILDERS | 8126 | 2022 | 2022-07-10 | 02/21/2022 | 469948 | 0 | 2022-08-08 | 29
2024 | Region VIII | LEYTE | ISABEL (LEYTE) | P00820238VS | Construction of Flood Mitigation Structure | 124.4612 | 10.8867 | 5488000 | 5433119.87 | 2024 | CIRCLE Z VENTURES & DEVELOPMENT CORP. | 8127 | 2024 | 2024-06-05 | 02/12/2024 | 54880.13 | 0 | 2024-06-04 |  | 1
2023 | Region VII | BOHOL | ALICIA (BOHOL) | P00745643VS | Rehabilitation / Major Repair of Flood Control Structure | 124.4628 | 9.8737 | 96286735 | 96131344.04 | 2024 | KMCM BUILDERS AND DEVELOPMENT CORPORATION / GICAR CONSTRUCTION, INC. | 8128 | 2023 | 2024-02-16 | 08/11/2023 | 155390.96 | 0 | 2024-06-18 | 123
2024 | Region VIII | LEYTE | LEYTE (LEYTE) | P00832684VS | Construction of Flood Mitigation Structure | 124.4658 | 11.433 | 4949901.38 | 4900400.55 | 2024 | CIRCLE Z VENTURES & DEVELOPMENT CORP. | 8129 | 2024 | 2024-04-02 | 02/14/2024 | 49500.83 | 0 | 2024-06-16 | 75
2024 | Region VII | BOHOL | ALICIA (BOHOL) | P00820182VS | Construction of Flood Mitigation Structure | 124.4694 | 9.899 | 14700000 | 14677314.84 | 2024 | FUENTABUILT CONSTRUCTION CORP. | 8130 | 2024 | 2024-10-07 | 03/27/2024 | 22685.16 | 0 | 2024-10-06 |  | 1
2023 | Region VIII | BILIRAN | BILIRAN (BILIRAN) | P00721701VS | Rehabilitation / Major Repair of Flood Control Structure | 124.4706 | 11.474 | 19580626.85 | 18983417.75 | 2023 | CHUCON BUILDERS CORPORATION (FORMERLY: CHU CONSTRUCTION) | 8131 | 2023 | 2023-06-10 | 02/15/2023 | 597209.1 | 0 | 2023-07-08 | 28
2022 | Region VIII | BILIRAN | BILIRAN (BILIRAN) | P00633025VS | Construction of Flood Mitigation Structure | 124.471 | 11.5108 | 24475918.13 | 23741640.6 | 2022 | ROVING PREMIER CONTRACTORS, INC. | 8132 | 2022 | 2022-08-31 | 03/29/2022 | 734277.53 | 0 | 2022-09-03 | 3
2023 | Region VII | BOHOL | CANDIJAY (BOHOL) | P00721898VS | Construction of Flood Mitigation Structure | 124.471 | 9.8497 | 77200000 | 77070000 | 2023 | CLAIRE CONSTRUCTION AND SUPPLY CORPORATION / MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY | 8133 | 2023 | 2023-12-15 | 04/11/2023 | 130000 | 0 | 2024-01-14 | 30
2024 | Region VII | BOHOL | CANDIJAY (BOHOL) | P00820065VS | Construction of Flood Mitigation Structure | 124.4716 | 9.8488 | 139442500 | 139442021.8 | 2024 | FUENTABUILT CONSTRUCTION CORP. / M.R. VARGAS CONSTRUCTION CORPORATION (FORMERLY: M.R. VARGAS CONSTRUCTION) | 8134 | 2024 | 2024-12-07 | 06/11/2024 | 478.2 | 0 | 2025-05-10 | 154
2023 | Region VIII | BILIRAN | BILIRAN (BILIRAN) | P00721957VS | Construction of Flood Mitigation Structure | 124.472 | 11.48 | 24488773.56 | 23962264.9 | 2023 | VK BUILDERS INC. | 8135 | 2023 | 2023-07-16 | 03/12/2023 | 526508.66 | 0 | 2023-08-17 | 32
2024 | Region VIII | LEYTE | ISABEL (LEYTE) | P00820241VS | Construction of Flood Mitigation Structure | 124.4728 | 10.8787 | 4900000 | 4875499.34 | 2024 | CIRCLE Z VENTURES & DEVELOPMENT CORP. | 8136 | 2024 | 2024-06-12 | 02/19/2024 | 24500.66 | 0 | 2024-06-11 |  | 1
2023 | Region VIII | BILIRAN | BILIRAN (BILIRAN) | P00733307VS | Construction of Flood Mitigation Structure | 124.4735 | 11.4816 | 19588509.78 | 19098797.05 | 2023 | CHUCON BUILDERS CORPORATION (FORMERLY: CHU CONSTRUCTION) | 8137 | 2023 | 2023-08-24 | 04/02/2023 | 489712.73 | 0 | 2023-08-23 |  | 1
2023 | Region XII | SARANGANI | MAITUM (SARANGANI) | P00721660MN | Construction of Flood Mitigation Structure | 124.4742 | 6.0887 | 49000000 | 48999139.07 | 2023 | HI-TONE CONSTRUCTION & DEVELOPMENT CORP. (FORMERLY | 8138 | 2023 | 2023-12-14 | 05/02/2023 | 860.93 | 0 | 2024-01-25 | 42
2022 | Region XII | SARANGANI | MAITUM (SARANGANI) | P00620184MN | Construction of Flood Mitigation Structure | 124.4745 | 6.0863 | 49000000 | 48999481.86 | 2023 | J.G. ORANZA CONSTRUCTION | 8139 | 2022 | 2023-03-28 | 03/17/2022 | 518.14 | 0 | 2023-03-27 |  | 1
2022 | Region VII | BOHOL | GUINDULMAN (BOHOL) | P00620034VS | Construction of Flood Mitigation Structure | 124.4745 | 9.7657 | 96500000 | 94371932.71 | 2023 | N.N. YU CONSTRUCTION, INC. (FORMERLY: YU CONSTRUCTION) / MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY | 8140 | 2022 | 2023-04-02 | 05/02/2022 | 2128067.29 | 0 | 2023-04-01 |  | 1
2024 | Region VII | BOHOL | CANDIJAY (BOHOL) | P00835003VS | Construction of Flood Mitigation Structure | 124.4756 | 9.856 | 39600000 | 39525949.58 | 2024 | MOG CONSTRUCTION INC. / N.N. YU CONSTRUCTION, INC. (FORMERLY: YU CONSTRUCTION) | 8141 | 2024 | 2024-09-25 | 05/06/2024 | 74050.42 | 0 | 2024-09-24 |  | 1
2022 | Region X | MISAMIS ORIENTAL | ALUBIJID (MISAMIS ORIENTAL) | P00620344MN | Construction of Flood Mitigation Structure | 124.476 | 8.5731 | 144750000 | 141124491.5 | 2024 | VEN RAY CONSTRUCTION CORPORATION | 8142 | 2022 | 2024-03-25 | 06/06/2022 | 3625508.5 | 0 | 2024-05-19 | 55
2022 | Region X | MISAMIS ORIENTAL | ALUBIJID (MISAMIS ORIENTAL) | P00620345MN | Construction of Flood Mitigation Structure | 124.4762 | 8.5726 | 144750000 | 139728160.1 | 2023 | VEN RAY CONSTRUCTION CORPORATION | 8143 | 2022 | 2023-10-14 | 06/06/2022 | 5021839.9 | 0 | 2023-10-13 |  | 1
2022 | Region VIII | BILIRAN | BILIRAN (BILIRAN) | P00632995VS | Construction of Flood Mitigation Structure | 124.4772 | 11.5175 | 96279896.21 | 96499745.52 | 2023 | EZJONES CONSTRUCTION INC. / ROVING PREMIER CONTRACTORS, INC. | 8144 | 2022 | 2023-01-24 | 06/13/2022 | 0 | 219849.31 | 2023-01-27 | 3
2023 | Region VII | BOHOL | GUINDULMAN (BOHOL) | P00733736VS | Construction of Flood Mitigation Structure | 124.4789 | 9.761 | 49500000 | 49104025.8 | 2024 | JAMARI CONSTRUCTION (FORMERLY FRAE CONSTRUCTION) / ALTACS CONSTRUCTION | 8145 | 2023 | 2024-01-07 | 05/29/2023 | 395974.2 | 0 | 2024-01-06 |  | 1
2023 | Region VII | BOHOL | GUINDULMAN (BOHOL) | P00721901VS | Construction of Flood Mitigation Structure | 124.4792 | 9.7607 | 77200000 | 77200000 | 2023 | N.N. YU CONSTRUCTION, INC. (FORMERLY: YU CONSTRUCTION) | 8146 | 2023 | 2023-11-13 | 04/10/2023 | 0 | 0 | 2024-01-13 | 61
2023 | Region VIII | BILIRAN | KAWAYAN (BILIRAN) | P00733752VS | Construction of Flood Mitigation Structure | 124.48 | 11.692 | 4947511.76 | 4823823.95 | 2023 | ROVING PREMIER CONTRACTORS, INC. | 8147 | 2023 | 2023-07-20 | 03/29/2023 | 123687.81 | 0 | 2023-06-10 |  | 40
2023 | Region VIII | BILIRAN | KAWAYAN (BILIRAN) | P00732032VS | Construction of Flood Mitigation Structure | 124.4802 | 11.6931 | 9893470.08 | 9896464.35 | 2023 | ROVING PREMIER CONTRACTORS, INC. | 8148 | 2023 | 2023-06-30 | 02/15/2023 | 0 | 2994.27 | 2023-07-03 | 3
2022 | Region XII | SARANGANI | MAITUM (SARANGANI) | P00620089MN | Construction of Flood Mitigation Structure | 124.4805 | 6.0979 | 86850000 | 86849785.36 | 2023 | JDRC CONSTRUCTION & SUPPLIES, CORP. | 8149 | 2022 | 2023-01-25 | 02/24/2022 | 214.64 | 0 | 2023-01-30 | 5
2024 | Region VIII | BILIRAN | KAWAYAN (BILIRAN) | P00832671VS | Construction of Revetment | 124.4805 | 11.6924 | 14839605.86 | 14546001.04 | 2024 | ROVING PREMIER CONTRACTORS, INC. | 8150 | 2024 | 2024-04-29 | 02/11/2024 | 293604.82 | 0 | 2024-06-28 | 60
2023 | Region VIII | LEYTE | MATAG-OB (LEYTE) | P00733757VS | Construction of Flood Mitigation Structure | 124.4811 | 11.1531 | 4950000 | 4900499.85 | 2023 | JSONS BUILDERS | 8151 | 2023 | 2023-07-25 | 04/20/2023 | 49500.15 | 0 | 2023-07-27 | 2
2024 | Region VIII | BILIRAN | BILIRAN (BILIRAN) | P00834675VS | Construction of Flood Mitigation Structure | 124.4825 | 11.4919 | 29380396.06 | 28765800.3 | 2024 | RMA BUILDERS & SUPPLIES CORPORATION | 8152 | 2024 | 2024-07-25 | 02/27/2024 | 614595.76 | 0 | 2024-08-11 | 17
2022 | Region VIII | BILIRAN | KAWAYAN (BILIRAN) | P00630231VS | Construction of Flood Mitigation Structure | 124.4842 | 11.6941 | 9889353.31 | 9601120.25 | 2022 | SUNRISE BUILDERS | 8153 | 2022 | 2022-08-06 | 03/20/2022 | 288233.06 | 0 | 2022-08-05 |  | 1
2022 | Region VIII | BILIRAN | KAWAYAN (BILIRAN) | P00633235VS | Construction of Flood Mitigation Structure | 124.4849 | 11.6941 | 9792853.86 | 9322796.85 | 2022 | W.B. ALAGAO CONSTRUCTION | 8154 | 2022 | 2022-08-02 | 03/16/2022 | 470057.01 | 0 | 2022-08-01 |  | 1
2023 | Region VII | BOHOL | GUINDULMAN (BOHOL) | P00721906VS | Construction of Flood Mitigation Structure | 124.4854 | 9.786 | 96500000 | 96468183 | 2024 | EGB CONSTRUCTION CORPORATION (FORMERLY: EGB CONSTRUCTION) | 8155 | 2023 | 2024-02-18 | 04/11/2023 | 31817 | 0 | 2024-02-17 |  | 1
2023 | Region VIII | BILIRAN | BILIRAN (BILIRAN) | P00721961VS | Construction of Flood Mitigation Structure | 124.4864 | 11.4958 | 48959832.14 | 47902300.7 | 2023 | ROVING PREMIER CONTRACTORS, INC. | 8156 | 2023 | 2023-09-15 | 03/12/2023 | 1057531.44 | 0 | 2023-09-26 | 11
2024 | Region VIII | SAMAR (WESTERN SAMAR) | CALBAYOG CITY (SAMAR (WESTERN SAMAR)) | P00820255VS | Construction of Flood Mitigation Structure | 124.489 | 12.3538 | 9800000 | 9755762.05 | 2024 | MDP CONSTRUCTION SERVICES | 8157 | 2024 | 2024-12-04 | 09/03/2024 | 44237.95 | 0 | 2025-02-25 | 83
2022 | Region VIII | NORTHERN SAMAR | SAN JOSE (NORTHERN SAMAR) | P00630684VS | Construction of Drainage Structure | 124.4907 | 12.532 | 4949633.01 | 4801992.94 | 2022 | SAL CONSTRUCTION | 8158 | 2022 | 2022-08-04 | 02/21/2022 | 147640.07 | 0 | 2022-08-07 | 3
2023 | Region XII | COTABATO (NORTH COTABATO) | PIKIT (COTABATO (NORTH COTABATO)) | P00721450MN | Construction of Flood Mitigation Structure | 124.4922 | 7.0528 | 106150000 | 105228140.2 | 2024 | GEMMA CONSTRUCTION SUPPLY, INC.(FORMERLY:GEMMA CON | 8159 | 2023 | 2024-03-31 | 08/29/2023 | 921859.8 | 0 | 2024-06-09 | 70
2022 | Region X | LANAO DEL NORTE | ILIGAN CITY (LANAO DEL NORTE) | P00630583MN | Construction of Slope Protection Structure | 124.4947 | 8.2048 | 39200000 | 39200000 | 2022 | OLISON CORPORATION / A.C. RIVERO DEVELOPMENT CORPORATION | 8160 | 2022 | 2022-11-21 | 03/18/2022 | 0 | 0 | 2022-11-23 | 2
2022 | Region VII | BOHOL | GUINDULMAN (BOHOL) | P00642512VS | Rehabilitation / Major Repair of Flood Control Structure | 124.4958 | 9.7655 | 28033250 | 27612750.52 | 2022 | ZLREJ TRADING AND CONSTRUCTION CORPORATION | 8161 | 2022 | 2022-12-01 | 04/08/2022 | 420499.48 | 0 | 2022-11-30 |  | 1
2024 | Region VII | BOHOL | CANDIJAY (BOHOL) | P00832214VS | Construction of Flood Mitigation Structure | 124.4965 | 9.8089 | 96500000 | 96399998.65 | 2025 | ZLREJ TRADING AND CONSTRUCTION CORPORATION | 8162 | 2024 | 2025-04-07 | 06/10/2024 | 100001.35 | 0 | 2025-04-18 | 11
2024 | Region VII | BOHOL | CANDIJAY (BOHOL) | P00820868VS | Construction of Flood Mitigation Structure | 124.497 | 9.8108 | 144750000 | 144590167.8 | 2024 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY | 8163 | 2024 | 2024-10-07 | 05/06/2024 | 159832.2 | 0 | 2025-04-02 | 177
2024 | Region VII | BOHOL | CANDIJAY (BOHOL) | P00832227VS | Construction of Flood Mitigation Structure | 124.4974 | 9.8109 | 48250000 | 48190168 | 2025 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY | 8164 | 2024 | 2025-02-07 | 06/10/2024 | 59832 | 0 | 2025-02-17 | 10
2021 | Region VIII | BILIRAN |  | P00549887VS | Construction of Slope Protection Structure | 124.5004 | 11.5781 | 18587689.99 | 18067234.65 | 2022 | LCTING CONSTRUCTION AND DEVELOPMENT CORPORATION (FORMERLY: L.C. TING CONSTRUCTION) | 8165 | 2021 | 2022-12-21 | 03/29/2021 | 520455.34 | 0 | 2022-12-20 |  | 1
2022 | Region XII | SARANGANI | MAITUM (SARANGANI) | P00620185MN | Construction of Flood Mitigation Structure | 124.5026 | 6.0582 | 48020000 | 48017953.88 | 2022 | J.G. ORANZA CONSTRUCTION | 8166 | 2022 | 2022-09-22 | 02/16/2022 | 2046.12 | 0 | 2022-09-23 | 1
2024 | Region VIII | BILIRAN | BILIRAN (BILIRAN) | P00834678VS | Construction of Flood Mitigation Structure | 124.5048 | 11.4828 | 9791631.14 | 9610485.95 | 2024 | RMA BUILDERS & SUPPLIES CORPORATION | 8167 | 2024 | 2024-05-13 | 02/25/2024 | 181145.19 | 0 | 2024-07-02 | 50
2023 | Region VIII | LEYTE | LEYTE (LEYTE) | P00733756VS | Construction of Flood Mitigation Structure | 124.5049 | 11.3618 | 4899997.76 | 4812204.39 | 2023 | KAUIE BUILDERS & SUPPLIES INC. (FORMERLY: KAUIE BUILDERS AND CONSTRUCTION SUPPLIES) | 8168 | 2023 | 2023-05-10 | 03/27/2023 | 87793.37 | 0 | 2023-07-28 | 79
2024 | Region VIII | BILIRAN | BILIRAN (BILIRAN) | P00834670VS | Construction of Flood Mitigation Structure | 124.505 | 11.4836 | 19581553.06 | 19302950.5 | 2024 | RMA BUILDERS & SUPPLIES CORPORATION | 8169 | 2024 | 2024-08-16 | 03/10/2024 | 278602.56 | 0 | 2024-08-15 |  | 1
2022 | Region XII | COTABATO (NORTH COTABATO) | MIDSAYAP (COTABATO (NORTH COTABATO)) | P00620274MN | Construction of Flood Mitigation Structure | 124.5052 | 7.2323 | 49000000 | 48949154.29 | 2022 | MUST ENTERPRISES | 8170 | 2022 | 2022-12-05 | 02/02/2022 | 50845.71 | 0 | 2022-10-14 |  | 52
2023 | Region VIII | LEYTE | LEYTE (LEYTE) | P00732047VS | Construction of Flood Mitigation Structure | 124.5062 | 11.4377 | 9799998.48 | 9603998.51 | 2023 | CIRCLE Z VENTURES & DEVELOPMENT CORP. | 8171 | 2023 | 2023-04-18 | 02/23/2023 | 195999.97 | 0 | 2023-08-05 | 109
2024 | Region XII | COTABATO (NORTH COTABATO) | LIBUNGAN (COTABATO (NORTH COTABATO)) | P00820093MN | Construction of Flood Mitigation Structure | 124.507 | 7.2315 | 96500000 | 96017500 | 2024 | LLABAN CONSTRUCTION & SUPPLY (FORMERLY: LLABAN CON | 8172 | 2024 | 2024-11-21 | 02/19/2024 | 482500 | 0 | 2024-11-21 | 0
2023 | Region VIII | LEYTE | LEYTE (LEYTE) | P00721716VS | Construction of Flood Mitigation Structure | 124.5083 | 11.3545 | 48999998.92 | 48264998.94 | 2023 | RJIR ENTERPRISES CORPORATION | 8173 | 2023 | 2023-10-03 | 02/27/2023 | 734999.98 | 0 | 2023-12-27 | 85
2023 | Region VIII | BILIRAN | CULABA (BILIRAN) | P00732035VS | Construction of Flood Mitigation Structure | 124.5107 | 11.6815 | 9895674.64 | 9600783.5 | 2023 | INFRASERVE BUILDERS AND SUPPLIES | 8174 | 2023 | 2023-05-30 | 02/15/2023 | 294891.14 | 0 | 2023-05-29 |  | 1
2022 | Region VIII | LEYTE | MERIDA (LEYTE) | P00633238VS | Construction of Flood Mitigation Structure | 124.5117 | 10.873 | 29700000 | 29699901.67 | 2022 | RJIR ENTERPRISES CORPORATION | 8175 | 2022 | 2022-08-25 | 03/23/2022 | 98.33 | 0 | 2022-11-16 | 83
2022 | Region VIII | BILIRAN | BILIRAN (BILIRAN) | P00620409VS | Construction of Flood Mitigation Structure | 124.5146 | 11.4743 | 3916526 | 3779447.6 | 2022 | QYT CONSTRUCTION AND SUPPLIES | 8176 | 2022 | 2022-08-07 | 03/29/2022 | 137078.4 | 0 | 2022-08-06 |  | 1
2023 | Region VIII | LEYTE | MERIDA (LEYTE) | P00721551VS | Construction of Flood Mitigation Structure | 124.5169 | 10.9286 | 96500000 | 96348951.67 | 2024 | AQUALINE CONSTRUCTION CORPORATION (FORMERLY: AQUALINE CONSTRUCTION) / EVERBUILT CONSTRUCTION | 8177 | 2023 | 2024-01-20 | 05/08/2023 | 151048.33 | 0 | 2024-03-01 | 41
2023 | Region VIII | BILIRAN | CABUCGAYAN (BILIRAN) | P00721698VS | Construction of Flood Mitigation Structure | 124.5177 | 11.4758 | 19581448.85 | 18964633.2 | 2023 | SUNRISE BUILDERS | 8178 | 2023 | 2023-07-14 | 02/20/2023 | 616815.65 | 0 | 2023-07-13 |  | 1
2022 | Region VIII | BILIRAN | CABUCGAYAN (BILIRAN) | P00620163VS | Construction of Flood Mitigation Structure | 124.5179 | 11.4775 | 14687142.62 | 14173092.65 | 2022 | SUNRISE BUILDERS | 8179 | 2022 | 2022-07-30 | 02/21/2022 | 514049.97 | 0 | 2022-08-08 | 9
2022 | Region VIII | BILIRAN | CABUCGAYAN (BILIRAN) | P00620151VS | Construction of Flood Mitigation Structure | 124.5181 | 11.4775 | 29371629.64 | 28475794.9 | 2022 | SUNRISE BUILDERS | 8180 | 2022 | 2022-08-19 | 02/21/2022 | 895834.74 | 0 | 2022-08-18 |  | 1
2024 | Region VIII | BILIRAN | CULABA (BILIRAN) | P00834677VS | Construction of Flood Mitigation Structure | 124.5192 | 11.6713 | 9789141.94 | 9608685.75 | 2024 | RMA BUILDERS & SUPPLIES CORPORATION | 8181 | 2024 | 2024-04-12 | 02/27/2024 | 180456.19 | 0 | 2024-07-04 | 83
2022 | Region XII | COTABATO (NORTH COTABATO) | LIBUNGAN (COTABATO (NORTH COTABATO)) | P00630612MN | Rehabilitation / Major Repair of Flood Control Structure | 124.523 | 7.2385 | 29400000 | 29400000 | 2022 | LLABAN CONSTRUCTION & SUPPLY (FORMERLY: LLABAN CON | 8182 | 2022 | 2022-12-02 | 02/02/2022 | 0 | 0 | 2022-09-21 |  | 72
2023 | Region VIII | BILIRAN | CULABA (BILIRAN) | P00721958VS | Construction of Flood Mitigation Structure | 124.5243 | 11.6654 | 24481977.84 | 23938133.6 | 2023 | CHUROCK BUILDERS INC.(FORMERLY: CHUROCK BUILDERS) | 8183 | 2023 | 2023-07-23 | 03/12/2023 | 543844.24 | 0 | 2023-08-17 | 25
2024 | Region XII | COTABATO (NORTH COTABATO) | MIDSAYAP (COTABATO (NORTH COTABATO)) | P00833593MN | Construction of Drainage Structure | 124.5251 | 7.2126 | 4950000 | 4930000 | 2025 | LLABAN CONSTRUCTION & SUPPLY (FORMERLY: LLABAN CON | 8184 | 2024 | 2025-01-02 | 08/30/2024 | 20000 | 0 | 2025-01-01 |  | 1
2022 | Region VIII | BILIRAN | CULABA (BILIRAN) | P00620153VS | Construction of Flood Mitigation Structure | 124.5266 | 11.6658 | 24476937.33 | 24476943.86 | 2022 | YOYEN ENTERPRISES | 8185 | 2022 | 2022-07-04 | 02/21/2022 | 0 | 6.53 | 2022-07-29 | 25
2023 | Region VIII | BILIRAN | CULABA (BILIRAN) | P00733309VS | Construction of Flood Mitigation Structure | 124.5272 | 11.6659 | 19581054.68 | 19169852.5 | 2023 | 4K VERMARK CIVIL ENGINEERING CONSTRUCTION | 8186 | 2023 | 2023-07-28 | 03/30/2023 | 411202.18 | 0 | 2023-08-20 | 23
2024 | Region VIII | BILIRAN | CULABA (BILIRAN) | P00820220VS | Construction of Revetment | 124.5285 | 11.6662 | 29378901.22 | 29379045.5 | 2024 | VK BUILDERS INC. | 8187 | 2024 | 2024-07-29 | 02/11/2024 | 0 | 144.28 | 2024-07-28 |  | 1
2023 | Region VIII | LEYTE | ORMOC CITY (LEYTE) | P00731639VS | Construction of Flood Mitigation Structure | 124.5293 | 11.0745 | 96500000 | 96499917.29 | 2024 | LEDA CONSTRUCTION INCORPORATED | 8188 | 2023 | 2024-05-17 | 04/14/2023 | 82.71 | 0 | 2024-05-16 |  | 1
2022 | Region VIII | LEYTE | MERIDA (LEYTE) | P00633239VS | Construction of Flood Mitigation Structure | 124.5322 | 10.9803 | 29700000 | 29698999.03 | 2022 | RJIR ENTERPRISES CORPORATION | 8189 | 2022 | 2022-11-17 | 03/23/2022 | 1000.97 | 0 | 2022-11-16 |  | 1
2022 | Region VIII | LEYTE | MERIDA (LEYTE) | P00620191VS | Construction of Flood Mitigation Structure | 124.5323 | 10.9021 | 19599657.26 | 19599998.1 | 2022 | CIRCLE Z VENTURES & DEVELOPMENT CORP. | 8190 | 2022 | 2022-07-20 | 02/21/2022 | 0 | 340.84 | 2022-07-19 |  | 1
2022 | Region VIII | SAMAR (WESTERN SAMAR) | CALBAYOG CITY (SAMAR (WESTERN SAMAR)) | P00620212VS | Construction of Flood Mitigation Structure | 124.534 | 12.1613 | 49000000 | 48132095.02 | 2023 | JFR CONSTRUCTION INC. (FORMERLY:JFR CONSTRUCTION) | 8191 | 2022 | 2023-11-23 | 03/23/2022 | 867904.98 | 0 | 2023-12-04 | 11
2024 | Region XII | COTABATO (NORTH COTABATO) | LIBUNGAN (COTABATO (NORTH COTABATO)) | P00820110MN | Construction of Flood Mitigation Structure | 124.536 | 7.2412 | 57900000 | 57900000 | 2025 | LLABAN CONSTRUCTION & SUPPLY (FORMERLY: LLABAN CON / GFJ CONSTRUCTION SUPPLY & MERCHANDISE | 8192 | 2024 | 2025-02-12 | 07/15/2024 | 0 | 0 | 2025-02-11 |  | 1
2022 | Region XII | COTABATO (NORTH COTABATO) | LIBUNGAN (COTABATO (NORTH COTABATO)) | P00620273MN | Construction of Flood Mitigation Structure | 124.5373 | 7.2395 | 49000000 | 49000000 | 2022 | LLABAN CONSTRUCTION & SUPPLY (FORMERLY: LLABAN CON / REEM CONSTRUCTION AND SUPPLY | 8193 | 2022 | 2022-12-02 | 02/02/2022 | 0 | 0 | 2022-12-01 |  | 1
2024 | Region VIII | LEYTE | MERIDA (LEYTE) | P00820244VS | Construction of Drainage Structure | 124.538 | 10.9077 | 5880000 | 5860000 | 2024 | JSONS BUILDERS | 8194 | 2024 | 2024-05-22 | 02/13/2024 | 20000 | 0 | 2024-05-21 |  | 1
2023 | Region XII | SULTAN KUDARAT | ESPERANZA (SULTAN KUDARAT) | P00734413MN | Construction of Flood Mitigation Structure | 124.5399 | 6.6806 | 4950000 | 4563124.44 | 2023 | CURVE-LINE CONSTRUCTION | 8195 | 2023 | 2023-10-05 | 03/24/2023 | 386875.56 | 0 | 2023-08-06 |  | 60
2022 | Region VIII | LEYTE | LEYTE (LEYTE) | P00620061VS | Construction of Flood Mitigation Structure | 124.541 | 11.3169 | 192799333.6 | 190871336.4 | 2023 | EZJONES CONSTRUCTION INC. / JGO BUILDERS | 8196 | 2022 | 2023-09-16 | 03/07/2022 | 1927997.2 | 0 | 2023-09-16 | 0
2023 | Region VIII | SAMAR (WESTERN SAMAR) | CALBAYOG CITY (SAMAR (WESTERN SAMAR)) | P00721804VS | Construction of Flood Mitigation Structure | 124.5428 | 12.0638 | 53075000 | 52938612 | 2023 | ND CARANZO BUILDERS AND CONSTRUCTION SUPPLY | 8197 | 2023 | 2023-11-12 | 03/15/2023 | 136388 | 0 | 2023-11-11 |  | 1
2023 | Region VIII | LEYTE | ORMOC CITY (LEYTE) | P00721798VS | Construction of Flood Mitigation Structure | 124.5442 | 11.0291 | 106150000 | 104027000 | 2024 | RJIR ENTERPRISES CORPORATION / CIRCLE Z VENTURES & DEVELOPMENT CORP. | 8198 | 2023 | 2024-11-25 | 04/05/2023 | 2123000 | 0 | 2024-12-11 | 16
2021 | Region VIII | LEYTE |  | P00521714VS | Rehabilitation / Major Repair of Flood Control Structure | 124.5464 | 11.0359 | 40825154.49 | 38783901.98 | 2022 | PREMIUM MEGASTRUCTURES INC. | 8199 | 2021 | 2022-12-21 | 11/10/2021 | 2041252.51 | 0 | 2022-12-20 |  | 1
2022 | Region VIII | LEYTE | ORMOC CITY (LEYTE) | P00620064VS | Construction of Flood Mitigation Structure | 124.5464 | 11.0359 | 96499938.93 | 96499998.59 | 2023 | RJIR ENTERPRISES CORPORATION | 8200 | 2022 | 2023-09-18 | 02/21/2022 | 0 | 59.66 | 2023-09-17 |  | 1
2023 | Region XII | COTABATO (NORTH COTABATO) | ALAMADA (COTABATO (NORTH COTABATO)) | P00732492MN | Construction of Flood Mitigation Structure | 124.5464 | 7.3816 | 4950000 | 4900499.99 | 2023 | LLABAN CONSTRUCTION & SUPPLY (FORMERLY: LLABAN CON | 8201 | 2023 | 2023-03-29 | 02/22/2023 | 49500.01 | 0 | 2023-05-11 | 43
2024 | Region XII | COTABATO (NORTH COTABATO) | ALAMADA (COTABATO (NORTH COTABATO)) | P00833595MN | Construction of Flood Mitigation Structure | 124.5465 | 7.3814 | 4950000 | 4920000 | 2024 | LLABAN CONSTRUCTION & SUPPLY (FORMERLY: LLABAN CON | 8202 | 2024 | 2024-04-22 | 02/07/2024 | 30000 | 0 | 2024-04-25 | 3
2023 | Region VIII | LEYTE | ORMOC CITY (LEYTE) | P00721799VS | Construction of Flood Mitigation Structure | 124.5472 | 11.0322 | 106150000 | 106149999.4 | 2024 | RJIR ENTERPRISES CORPORATION | 8203 | 2023 | 2024-07-22 | 04/03/2023 | 0.6 | 0 | 2024-09-05 | 45
2022 | Region VIII | BILIRAN | CAIBIRAN (BILIRAN) | P00620164VS | Construction of Flood Mitigation Structure | 124.548 | 11.5662 | 39160876.26 | 39160876.26 | 2022 | YOYEN ENTERPRISES | 8204 | 2022 | 2022-08-29 | 02/21/2022 | 0 | 0 | 2022-08-28 |  | 1
2023 | Region VIII | BILIRAN | CAIBIRAN (BILIRAN) | P00721696VS | Construction of Flood Mitigation Structure | 124.5492 | 11.5686 | 24477292.75 | 24477379.47 | 2023 | CHUCON BUILDERS CORPORATION (FORMERLY: CHU CONSTRUCTION) | 8205 | 2023 | 2023-06-18 | 02/15/2023 | 0 | 86.72 | 2023-08-03 | 46
2023 | Region VIII | BILIRAN | CAIBIRAN (BILIRAN) | P00733305VS | Construction of Flood Mitigation Structure | 124.5499 | 11.5747 | 19590629.15 | 19590695.22 | 2023 | ROVING PREMIER CONTRACTORS, INC. | 8206 | 2023 | 2023-06-27 | 03/30/2023 | 0 | 66.07 | 2023-08-20 | 54
2022 | Region VIII | SAMAR (WESTERN SAMAR) | CALBAYOG CITY (SAMAR (WESTERN SAMAR)) | P00620342VS | Construction of Flood Mitigation Structure | 124.5516 | 12.1393 | 43929480 | 43612695.07 | 2022 | JFR CONSTRUCTION INC. (FORMERLY:JFR CONSTRUCTION) | 8207 | 2022 | 2022-10-25 | 02/08/2022 | 316784.93 | 0 | 2022-10-24 |  | 1
2023 | Region X | MISAMIS ORIENTAL | CITY OF EL SALVADOR (MISAMIS ORIENTAL) | P00721260MN | Construction of Flood Mitigation Structure | 124.5527 | 8.5332 | 86850000 | 86850000 | 2023 | RITCHE-NATHALIE BUILDERS & GENERAL MERCHANDISE | 8208 | 2023 | 2023-07-26 | 02/17/2023 | 0 | 0 | 2023-12-26 | 153
2023 | Region VIII | BILIRAN | CAIBIRAN (BILIRAN) | P00721959VS | Construction of Flood Mitigation Structure | 124.5539 | 11.5617 | 34279941.34 | 34280548.95 | 2023 | ROVING PREMIER CONTRACTORS, INC. | 8209 | 2023 | 2023-08-10 | 03/12/2023 | 0 | 607.61 | 2023-09-15 | 36
2024 | Region XII | SARANGANI | MAITUM (SARANGANI) | P00820203MN | Construction of Flood Mitigation Structure | 124.5549 | 6.0665 | 14700000 | 14514426.28 | 2024 | XIANN THIRDREI BUILDERS | 8210 | 2024 | 2024-10-14 | 04/09/2024 | 185573.72 | 0 | 2024-11-03 | 20
2022 | Region VIII | BILIRAN | CAIBIRAN (BILIRAN) | P00620160VS | Construction of Flood Mitigation Structure | 124.5564 | 11.5768 | 19582834.66 | 19582958.02 | 2022 | SUNRISE BUILDERS | 8211 | 2022 | 2022-08-14 | 02/21/2022 | 0 | 123.36 | 2022-08-13 |  | 1
2022 | Region VIII | LEYTE | ORMOC CITY (LEYTE) | P00630234VS | Construction of Flood Mitigation Structure | 124.5564 | 10.9968 | 48999987.9 | 48999998.84 | 2024 | RJIR ENTERPRISES CORPORATION | 8212 | 2022 | 2024-10-05 | 02/22/2022 | 0 | 10.94 | 2024-10-04 |  | 1
2023 | Region VIII | LEYTE | ORMOC CITY (LEYTE) | P00731641VS | Construction of Flood Mitigation Structure | 124.5598 | 11.1349 | 96500000 | 96499790.73 | 2024 | COLLERA CONSTRUCTION | 8213 | 2023 | 2024-03-02 | 05/08/2023 | 209.27 | 0 | 2024-03-01 |  | 1
2022 | Region VIII | BILIRAN | CABUCGAYAN (BILIRAN) | P00630229VS | Construction of Flood Mitigation Structure | 124.5633 | 11.4846 | 29370018.97 | 28080735 | 2022 | SUNRISE BUILDERS | 8214 | 2022 | 2022-08-19 | 02/21/2022 | 1289283.97 | 0 | 2022-08-18 |  | 1
2022 | Region VIII | BILIRAN | CAIBIRAN (BILIRAN) | P00633024VS | Construction of Flood Mitigation Structure | 124.5639 | 11.5749 | 48951948.48 | 48973319.76 | 2022 | CHUCON BUILDERS CORPORATION (FORMERLY: CHU CONSTRUCTION) | 8215 | 2022 | 2022-11-08 | 03/29/2022 | 0 | 21371.28 | 2022-11-07 |  | 1
2023 | Region VIII | LEYTE | KANANGA (LEYTE) | P00721554VS | Construction of Flood Mitigation Structure | 124.5645 | 11.1462 | 96500000 | 96492385 | 2024 | RJIR ENTERPRISES CORPORATION | 8216 | 2023 | 2024-02-26 | 04/03/2023 | 7615 | 0 | 2024-02-25 |  | 1
2022 | Region VIII | SAMAR (WESTERN SAMAR) | CALBAYOG CITY (SAMAR (WESTERN SAMAR)) | P00630239VS | Construction of Flood Mitigation Structure | 124.5647 | 12.1455 | 49000000 | 48603252.18 | 2022 | PABLO S. LABASBAS CONSTRUCTION CORPORATION (FORMERLY: PABLOS. LABASBAS CONSTRUCTION CORPORATION) | 8217 | 2022 | 2022-09-28 | 02/08/2022 | 396747.82 | 0 | 2022-09-27 |  | 1
2022 | Region VIII | LEYTE | ORMOC CITY (LEYTE) | P00630233VS | Construction of Flood Mitigation Structure | 124.5647 | 11.0025 | 48999968.6 | 48999996.64 | 2024 | RJIR ENTERPRISES CORPORATION | 8218 | 2022 | 2024-03-21 | 02/22/2022 | 0 | 28.04 | 2024-04-06 | 16
2024 | Region VIII | LEYTE | KANANGA (LEYTE) | P00820237VS | Construction of Flood Mitigation Structure | 124.5649 | 11.1469 | 5880000 | 5821197.36 | 2024 | RJIR ENTERPRISES CORPORATION | 8219 | 2024 | 2024-05-18 | 02/19/2024 | 58802.64 | 0 | 2024-05-17 |  | 1
2022 | Region XII | SARANGANI | KIAMBA (SARANGANI) | P00620098MN | Construction of Flood Mitigation Structure | 124.622 | 5.9969 | 104171750 | 103138477.3 | 2023 | LEGACY CONSTRUCTION CORPORATION (FORMERLY: LEGACY CONSTRUCTION) | 8220 | 2022 | 2023-04-06 | 04/18/2022 | 1033272.7 | 0 | 2023-04-05 |  | 1
2023 | Region VIII | LEYTE | TACLOBAN CITY (CAPITAL) (LEYTE) | P00733291VS | Construction of Flood Mitigation Structure | 124.9459 | 11.3186 | 101288703.8 | 101207765.1 | 2024 | AQUALINE CONSTRUCTION CORPORATION (FORMERLY: AQUALINE CONSTRUCTION) / ML_BUILDERS INC. | 8221 | 2023 | 2024-10-09 | 12/07/2023 | 80938.7 | 0 | 2024-10-08 |  | 1
2022 | Region V | CATANDUANES | CARAMORAN (CATANDUANES) | P00632972LZ | Construction of Flood Mitigation Structure | 124.1636 | 13.9154 | 39599999.5 | 39599999.28 | 2023 | AL-JON CONSTRUCTION DEVELOPMENT, INC. (FORMERLY: ALJON CONSTRUCTION & SUPPLY) | 8222 | 2022 | 2023-06-19 | 07/22/2022 | 0.22 | 0 | 2023-05-22 |  | 28
2023 | Region X | MISAMIS ORIENTAL | MEDINA (MISAMIS ORIENTAL) | P00721560MN | Construction of Flood Mitigation Structure | 125.0113 | 8.9102 | 72375000 | 72375000 | 2023 | EQUALYZ TRADING | 8223 | 2023 | 2023-10-09 | 04/25/2023 | 0 | 0 | 2024-01-09 | 92
2023 | Region VIII | LEYTE | TABANGO (LEYTE) | P00721715VS | Construction of Flood Mitigation Structure | 124.3462 | 11.3629 | 48999997.93 | 48754997.94 | 2024 | RJIR ENTERPRISES CORPORATION | 8224 | 2023 | 2024-01-07 | 03/09/2023 | 244999.99 | 0 | 2024-01-06 |  | 1
2024 | Region VIII | LEYTE | ORMOC CITY (LEYTE) | P00820909VS | Construction of Flood Mitigation Structure | 124.6222 | 11.0297 | 96500000 | 96377194.04 | 2024 | LEDA CONSTRUCTION INCORPORATED | 8225 | 2024 | 2024-11-20 | 02/14/2024 | 122805.96 | 0 | 2024-12-08 | 18
2023 | Region XII | SULTAN KUDARAT | ESPERANZA (SULTAN KUDARAT) | P00721624MN | Construction of Flood Mitigation Structure | 124.5674 | 6.6759 | 49000000 | 48999972.27 | 2024 | WOODRIDGE BUILDERS CONSTRUCTION & SUPPLIES, INC. | 8226 | 2023 | 2024-01-29 | 03/24/2023 | 27.73 | 0 | 2024-02-12 | 14
2024 | Region VIII | SAMAR (WESTERN SAMAR) | SAN JORGE (SAMAR (WESTERN SAMAR)) | P00820422VS | Construction of Flood Mitigation Structure | 124.8459 | 11.9817 | 49000000 | 47991241.99 | 2024 | JUPA CONSTRUCTION | 8227 | 2024 | 2024-12-08 | 04/18/2024 | 1008758.01 | 0 | 2024-12-07 |  | 1
2021 | Region V | CATANDUANES |  | P00561201LZ | Construction of Flood Mitigation Structure | 124.3477 | 13.6549 | 19598759.05 | 19598760 | 2022 | NQA CONSTRUCTION & SUPPLY | 8228 | 2021 | 2022-10-02 | 03/07/2022 | 0 | 0.95 | 2022-10-01 |  | 1
2024 | Region VIII | LEYTE | ALBUERA (LEYTE) | P00820884VS | Construction of Flood Mitigation Structure | 124.6983 | 10.9135 | 96500000 | 96499999.9 | 2024 | JM COLLERA KONSTRACT | 8229 | 2024 | 2024-11-20 | 03/13/2024 | 0.1 | 0 | 2025-01-05 | 46
2024 | Region X | BUKIDNON | TALAKAG (BUKIDNON) | P00820028MN | Construction of Flood Mitigation Structure | 124.6239 | 8.036 | 96500000 | 96500000 | 2025 | VEN RAY CONSTRUCTION CORPORATION | 8230 | 2024 | 2025-05-23 | 02/12/2024 | 0 | 0 | 2025-05-25 | 2
2021 | Region X | MISAMIS ORIENTAL |  | P00522055MN | Construction of Drainage Structure | 124.6245 | 8.507 | 106150000 | 95530061.09 | 2023 | ROAD EDGE TRADING & DEVELOPMENT SERVICES | 8231 | 2021 | 2023-12-31 | 11/22/2021 | 10619938.91 | 0 | 2023-12-30 |  | 1
2024 | Region X | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY (CAPITAL) (MISAMIS ORIENTAL) | P00836178MN | Construction of Flood Mitigation Structure | 124.6246 | 8.4203 | 24750000 | 24750000 | 2024 | GICAR CONSTRUCTION, INC. | 8232 | 2024 | 2024-07-25 | 02/27/2024 | 0 | 0 | 2024-10-22 | 89
2024 | Region XII | SULTAN KUDARAT | ISULAN (CAPITAL) (SULTAN KUDARAT) | P00820206MN | Construction of Flood Mitigation Structure | 124.6263 | 6.6732 | 29106856.94 | 29050363.85 | 2024 | ADDED CONSTRUCTION SERVICES | 8233 | 2024 | 2024-05-20 | 02/15/2024 | 56493.09 | 0 | 2024-08-08 | 80
2022 | Region XII | SULTAN KUDARAT | ISULAN (CAPITAL) (SULTAN KUDARAT) | P00634123MN | Construction of Flood Mitigation Structure | 124.6265 | 6.6645 | 49497743.12 | 49397332.88 | 2023 | CS CONST. AND SUPPLY INC. (FORMERLY: CS CONSTRUCTION AND SUPPLY) / GIBUILD DEVELOPMENT CORP. | 8234 | 2022 | 2023-04-25 | 05/25/2022 | 100410.24 | 0 | 2023-03-15 |  | 41
2023 | Region VIII | NORTHERN SAMAR | CATARMAN (CAPITAL) (NORTHERN SAMAR) | P00721971VS | Construction of Flood Mitigation Structure | 124.627 | 12.5097 | 22696455.2 | 22672048.91 | 2024 | M SQUARE H CONSTRUCTION & SUPPLY | 8235 | 2023 | 2024-03-11 | 09/11/2023 | 24406.29 | 0 | 2024-03-31 | 20
2024 | Region VIII | LEYTE | ORMOC CITY (LEYTE) | P00820242VS | Construction of Drainage Structure | 124.6271 | 11.0109 | 9408000 | 9402999.83 | 2024 | CIRCLE Z VENTURES & DEVELOPMENT CORP. | 8236 | 2024 | 2024-05-27 | 02/13/2024 | 5000.17 | 0 | 2024-05-26 |  | 1
2023 | Region X | MISAMIS ORIENTAL | MEDINA (MISAMIS ORIENTAL) | P00734024MN | Construction of Flood Mitigation Structure | 125.0113 | 8.9102 | 49000000 | 49000000 | 2024 | JEJOR'S CONSTRUCTION CORPORATION | 8237 | 2023 | 2024-02-26 | 05/18/2023 | 0 | 0 | 2024-02-25 |  | 1
2022 | Region X | LANAO DEL NORTE | LINAMON (LANAO DEL NORTE) | P00620030MN | Construction of Flood Mitigation Structure | 124.1656 | 8.1869 | 58438470 | 56685315.9 | 2024 | NDP CONSTRUCTION DEVELOPMENT / AL HUSSEIN CONSTRUCTION | 8238 | 2022 | 2024-03-25 | 05/30/2022 | 1753154.1 | 0 | 2023-01-23 |  | 427
2023 | Region VIII | LEYTE | TACLOBAN CITY (CAPITAL) (LEYTE) | P00731694VS | Construction of Flood Mitigation Structure | 124.9459 | 11.2533 | 48997835.49 | 48927835 | 2023 | JJ PALACIO CONSTRUCTION | 8239 | 2023 | 2023-08-22 | 05/15/2023 | 70000.49 | 0 | 2023-12-11 | 111
2023 | Region XII | SULTAN KUDARAT | TACURONG CITY (SULTAN KUDARAT) | P00721515MN | Construction of Flood Mitigation Structure | 124.6272 | 6.6675 | 48922088.57 | 48822060.78 | 2023 | JARGON CONSTRUCTION & SUPPLY | 8240 | 2023 | 2023-11-08 | 02/17/2023 | 100027.79 | 0 | 2023-11-12 | 4
2022 | Region XII | SULTAN KUDARAT | ISULAN (CAPITAL) (SULTAN KUDARAT) | P00620292MN | Construction of Flood Mitigation Structure | 124.6272 | 6.6619 | 37716010.98 | 37697510.48 | 2023 | CS CONST. AND SUPPLY INC. (FORMERLY: CS CONSTRUCTION AND SUPPLY) | 8241 | 2022 | 2023-02-06 | 03/16/2022 | 18500.5 | 0 | 2023-01-01 |  | 36
2023 | Region VIII | SAMAR (WESTERN SAMAR) | CALBAYOG CITY (SAMAR (WESTERN SAMAR)) | P00733324VS | Construction of Flood Mitigation Structure | 124.6276 | 12.0958 | 29400000 | 28870816.03 | 2023 | ETAN CONSTRUCTION | 8242 | 2023 | 2023-10-04 | 04/07/2023 | 529183.97 | 0 | 2023-10-03 |  | 1
2023 | Region X | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY (CAPITAL) (MISAMIS ORIENTAL) | P00721636MN | Construction of Flood Mitigation Structure | 124.6278 | 8.4186 | 96500000 | 96500000 | 2023 | RITCHE-NATHALIE BUILDERS & GENERAL MERCHANDISE | 8243 | 2023 | 2023-12-22 | 04/17/2023 | 0 | 0 | 2024-07-08 | 199
2022 | Region VIII | LEYTE | ORMOC CITY (LEYTE) | P00630232VS | Construction of Flood Mitigation Structure | 124.628 | 10.9813 | 48999936.02 | 48999999.6 | 2022 | A.C. RIVERO DEVELOPMENT CORPORATION | 8244 | 2022 | 2022-10-19 | 02/22/2022 | 0 | 63.58 | 2022-10-18 |  | 1
2023 | Region X | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY (CAPITAL) (MISAMIS ORIENTAL) | P00721641MN | Construction of Flood Mitigation Structure | 124.6289 | 8.4208 | 72375000 | 72375000 | 2023 | ROAD EDGE TRADING & DEVELOPMENT SERVICES | 8245 | 2023 | 2023-11-27 | 03/16/2023 | 0 | 0 | 2024-02-12 | 77
2023 | Region X | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY (CAPITAL) (MISAMIS ORIENTAL) | P00721608MN | Construction of Drainage Structure | 124.6294 | 8.4817 | 49000000 | 49000000 | 2024 | HI-TONE CONSTRUCTION & DEVELOPMENT CORP. (FORMERLY | 8246 | 2023 | 2024-02-28 | 03/14/2023 | 0 | 0 | 2024-02-27 |  | 1
2023 | Region X | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY (CAPITAL) (MISAMIS ORIENTAL) | P00732482MN | Construction of Drainage Structure | 124.6297 | 8.4794 | 39200000 | 39200000 | 2023 | CAGALAWAN ENTERPRISES | 8247 | 2023 | 2023-12-26 | 01/30/2023 | 0 | 0 | 2023-12-25 |  | 1
2023 | Region X | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY (CAPITAL) (MISAMIS ORIENTAL) | P00721266MN | Construction of Flood Mitigation Structure | 124.63 | 8.4249 | 67375000 | 66022355.72 | 2024 | TRIPARCO DEVELOPMENT CORPORATION | 8248 | 2023 | 2024-09-01 | 02/13/2023 | 1352644.28 | 0 | 2023-11-18 |  | 288
2024 | Region X | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY (CAPITAL) (MISAMIS ORIENTAL) | P00820016MN | Construction of Flood Mitigation Structure | 124.63 | 8.4254 | 87863250 | 86096230.7 | 2025 | TRIPARCO DEVELOPMENT CORPORATION | 8249 | 2024 | 2025-03-31 | 04/18/2024 | 1767019.3 | 0 | 2025-05-11 | 41
2023 | Region X | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY (CAPITAL) (MISAMIS ORIENTAL) | P00721265MN | Construction of Flood Mitigation Structure | 124.6301 | 8.4237 | 67375000 | 66022344.63 | 2024 | TRIPARCO DEVELOPMENT CORPORATION | 8250 | 2023 | 2024-07-31 | 02/13/2023 | 1352655.37 | 0 | 2024-07-30 |  | 1
2021 | Region X | MISAMIS ORIENTAL |  | P00522054MN | Construction of Drainage Structure | 124.6325 | 8.5022 | 101325000 | 96258829.05 | 2023 | GICAR CONSTRUCTION, INC. | 8251 | 2021 | 2023-12-31 | 11/22/2021 | 5066170.95 | 0 | 2023-12-30 |  | 1
2023 | Region X | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY (CAPITAL) (MISAMIS ORIENTAL) | P00732483MN | Construction of Drainage Structure | 124.6325 | 8.5019 | 39200000 | 39200000 | 2023 | JAMARI CONSTRUCTION (FORMERLY FRAE CONSTRUCTION) / ABAYCER CONSTRUCTION SUPPLIES AND GENERAL MERCHANDISE | 8252 | 2023 | 2023-11-16 | 01/30/2023 | 0 | 0 | 2023-11-15 |  | 1
2022 | Region VIII | NORTHERN SAMAR | CATARMAN (CAPITAL) (NORTHERN SAMAR) | P00620202VS | Construction of Flood Mitigation Structure | 124.633 | 12.508 | 48999286.71 | 48989055.06 | 2022 | SAL CONSTRUCTION / CDU CONSTRUCTION | 8253 | 2022 | 2022-11-16 | 02/21/2022 | 10231.65 | 0 | 2022-11-15 |  | 1
2024 | Region VIII | LEYTE | ORMOC CITY (LEYTE) | P00821063VS | Construction of Drainage Structure | 124.6332 | 10.9763 | 5586000 | 5531661.85 | 2024 | MJR CONSTRUCTION FIRM AND GENERAL MAINTENANCE, OPC | 8254 | 2024 | 2024-06-21 | 02/08/2024 | 54338.15 | 0 | 2024-06-20 |  | 1
2022 | Region X | CAMIGUIN | CATARMAN (CAMIGUIN) | P00632307MN | Construction of Slope Protection Structure | 124.6344 | 9.1806 | 96499999.99 | 96500000 | 2024 | ST. GERRARD CONSTRUCTION GEN. CONTRACTOR & DEVELOPMENT CORP. (FORMERLY:ST. GERRARD CONSTRUCTION) | 8255 | 2022 | 2024-09-01 | 06/29/2022 | 0 | 0.01 | 2023-02-14 |  | 565
2024 | Region VIII | LEYTE | ORMOC CITY (LEYTE) | P00820911VS | Construction of Flood Mitigation Structure | 124.6349 | 11.0404 | 96500000 | 96399999.99 | 2024 | JM COLLERA KONSTRACT | 8256 | 2024 | 2024-08-27 | 02/14/2024 | 100000.01 | 0 | 2024-12-08 | 103
2023 | Region X | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY (CAPITAL) (MISAMIS ORIENTAL) | P00721426MN | Construction of Flood Mitigation Structure | 124.6356 | 8.4575 | 82675000 | 81429903.46 | 2024 | EQUI-PARCO CONSTRUCTION COMPANY | 8257 | 2023 | 2024-05-29 | 03/27/2023 | 1245096.54 | 0 | 2024-02-18 |  | 101
2025 | Region XII | SOUTH COTABATO | SANTO NIÃ‘O (SOUTH COTABATO) | P00920429MN | Construction of Flood Mitigation Structure | 124.6363 | 6.4369 | 14700000 | 14689979.39 | 2025 | MFN BUILDERS | 8258 | 2025 | 2025-04-25 | 02/28/2025 | 10020.61 | 0 | 2025-06-29 | 65
2022 | Region X | CAMIGUIN | CATARMAN (CAMIGUIN) | P00620134MN | Construction of Drainage Structure | 124.6365 | 9.1754 | 19599985.51 | 19600000 | 2022 | JAPUZ-JANSOL ENTERPRISES | 8259 | 2022 | 2022-11-27 | 05/12/2022 | 0 | 14.49 | 2022-11-06 |  | 21
2024 | Region VIII | LEYTE | CAPOOCAN (LEYTE) | P00832682VS | Construction of Flood Mitigation Structure | 124.6376 | 11.2949 | 4899312.32 | 4849608.68 | 2024 | BEEROCK ENTERPRISES INCORPORATED | 8260 | 2024 | 2024-08-20 | 03/12/2024 | 49703.64 | 0 | 2024-09-10 | 21
2021 | Region X | MISAMIS ORIENTAL |  | P00522053MN | Construction of Drainage Structure | 124.6393 | 8.4816 | 106150000 | 102864606.3 | 2024 | C'ZARLES CONSTRUCTION & SUPPLY | 8261 | 2021 | 2024-03-25 | 11/22/2021 | 3285393.7 | 0 | 2022-11-07 |  | 504
2021 | Region XII | SULTAN KUDARAT |  | P00522377MN | Construction of Flood Mitigation Structure | 124.64 | 6.6238 | 48987968.9 | 47936892.16 | 2022 | PALMARES CONSTRUCTION & GENERAL MERCHANDISE CORP. (FORMERLY: PALMARES GENERAL MERCHANDISE) | 8262 | 2021 | 2022-11-13 | 03/28/2022 | 1051076.74 | 0 | 2022-11-12 |  | 1
2021 | Region XII | SULTAN KUDARAT |  | P00522379MN | Construction of Flood Mitigation Structure | 124.64 | 6.5878 | 48980625.23 | 48934696.13 | 2022 | CS CONST. AND SUPPLY INC. (FORMERLY: CS CONSTRUCTION AND SUPPLY) / ALPXR CONST. & BLDRS. CORP | 8263 | 2021 | 2022-10-22 | 03/08/2021 | 45929.1 | 0 | 2022-01-21 |  | 274
2024 | Region X | CAMIGUIN | CATARMAN (CAMIGUIN) | P00820060MN | Construction of Flood Mitigation Structure | 124.6409 | 9.1575 | 57899999.98 | 56153953.37 | 2024 | JEJOR'S CONSTRUCTION CORPORATION | 8264 | 2024 | 2024-10-02 | 03/20/2024 | 1746046.61 | 0 | 2024-10-01 |  | 1
2023 | Region XII | SULTAN KUDARAT | TACURONG CITY (SULTAN KUDARAT) | P00721516MN | Construction of Flood Mitigation Structure | 124.6414 | 6.6215 | 48882763.33 | 48999999.56 | 2023 | JARGON CONSTRUCTION & SUPPLY | 8265 | 2023 | 2023-10-17 | 02/17/2023 | 0 | 117236.23 | 2023-10-24 | 7
2022 | Region X | CAMIGUIN | CATARMAN (CAMIGUIN) | P00632310MN | Construction of Slope Protection Structure | 124.6417 | 9.1675 | 96499999.36 | 72210824.16 | 2024 | SUPREME ABF CONST. & CONST. SUPPLY COMPANY INC. | 8266 | 2022 | 2024-09-01 | 06/29/2022 | 24289175.2 | 0 | 2023-04-15 |  | 505
2024 | Region X | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY (CAPITAL) (MISAMIS ORIENTAL) | P00821077MN | Construction of Flood Mitigation Structure | 124.6419 | 8.474 | 9800000 | 9765203.1 | 2024 | STA ANA RAYCON CORP. | 8267 | 2024 | 2024-08-26 | 04/10/2024 | 34796.9 | 0 | 2024-08-18 |  | 8
2022 | Region VIII | NORTHERN SAMAR | CATARMAN (CAPITAL) (NORTHERN SAMAR) | P00620282VS | Construction of Flood Mitigation Structure | 124.6421 | 12.4912 | 104110916.9 | 104217207.7 | 2022 | EZJONES CONSTRUCTION INC. | 8268 | 2022 | 2022-11-24 | 02/28/2022 | 0 | 106290.8 | 2022-12-23 | 29
2022 | Region X | CAMIGUIN | CATARMAN (CAMIGUIN) | P00620132MN | Construction of Flood Mitigation Structure | 124.6427 | 9.1612 | 48999939.14 | 49000000 | 2023 | JEJOR'S CONSTRUCTION CORPORATION | 8269 | 2022 | 2023-01-29 | 05/12/2022 | 0 | 60.86 | 2023-01-05 |  | 24
2023 | Region VIII | LEYTE | ORMOC CITY (LEYTE) | P00733320VS | Construction of Flood Mitigation Structure | 124.6429 | 10.9664 | 49000000 | 48849298.66 | 2023 | AQUALINE CONSTRUCTION CORPORATION (FORMERLY: AQUALINE CONSTRUCTION) | 8270 | 2023 | 2023-10-16 | 04/20/2023 | 150701.34 | 0 | 2023-10-15 |  | 1
2024 | Region X | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY (CAPITAL) (MISAMIS ORIENTAL) | P00820063MN | Construction of Slope Protection Structure | 124.6431 | 8.4211 | 60909835 | 60252341.13 | 2025 | JEJOR'S CONSTRUCTION CORPORATION | 8271 | 2024 | 2025-04-28 | 03/04/2024 | 657493.87 | 0 | 2025-01-14 |  | 104
2022 | Region X | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY (CAPITAL) (MISAMIS ORIENTAL) | P00620025MN | Construction of Drainage Structure | 124.6431 | 8.5099 | 140215465 | 134600733.3 | 2024 | GICAR CONSTRUCTION, INC. | 8272 | 2022 | 2024-08-18 | 06/29/2022 | 5614731.7 | 0 | 2024-08-17 |  | 1
2022 | Region VIII | NORTHERN SAMAR | CATARMAN (CAPITAL) (NORTHERN SAMAR) | P00620338VS | Construction of Flood Mitigation Structure | 124.6435 | 12.5071 | 42261925.59 | 42254877.86 | 2022 | SAL CONSTRUCTION / CDU CONSTRUCTION | 8273 | 2022 | 2022-11-18 | 02/21/2022 | 7047.73 | 0 | 2022-10-26 |  | 23
2024 | Region XII | SULTAN KUDARAT | ISULAN (CAPITAL) (SULTAN KUDARAT) | P00820424MN | Construction of Flood Mitigation Structure | 124.6437 | 6.594 | 44959283.89 | 44859331.55 | 2024 | ROBETH CONST. AND DEV'T. CORP. (FORMERLY: ROBETH GEN. MDSE. CONST. & SUPPLY) | 8274 | 2024 | 2024-06-13 | 02/15/2024 | 99952.34 | 0 | 2024-08-26 | 74
2023 | Region XII | SULTAN KUDARAT | ISULAN (CAPITAL) (SULTAN KUDARAT) | P00721514MN | Construction of Flood Mitigation Structure | 124.6437 | 6.5911 | 48903080.69 | 48813031.51 | 2023 | JARGON CONSTRUCTION & SUPPLY | 8275 | 2023 | 2023-08-23 | 02/17/2023 | 90049.18 | 0 | 2023-08-25 | 2
2021 | Region XII | SULTAN KUDARAT |  | P00522378MN | Construction of Flood Mitigation Structure | 124.6438 | 6.5893 | 48993287.32 | 48013421.57 | 2022 | CS CONST. AND SUPPLY INC. (FORMERLY: CS CONSTRUCTION AND SUPPLY) | 8276 | 2021 | 2022-11-03 | 03/28/2022 | 979865.75 | 0 | 2022-11-12 | 9
2024 | Region XII | SOUTH COTABATO | NORALA (SOUTH COTABATO) | P00820354MN | Construction of Flood Mitigation Structure | 124.645 | 6.5869 | 39565000 | 39510024.3 | 2024 | ABU CONSTRUCTION | 8277 | 2024 | 2024-09-27 | 05/15/2024 | 54975.7 | 0 | 2024-09-28 | 1
2023 | Region VIII | NORTHERN SAMAR | CATARMAN (CAPITAL) (NORTHERN SAMAR) | P00721800VS | Construction of Flood Mitigation Structure | 124.6463 | 12.4917 | 221949552.3 | 110865287.6 | 2023 | EZJONES CONSTRUCTION INC. | 8278 | 2023 | 2023-12-15 | 03/15/2023 | 111084264.7 | 0 | 2024-01-07 | 23
2022 | Region VIII | NORTHERN SAMAR | CATARMAN (CAPITAL) (NORTHERN SAMAR) | P00620286VS | Construction of Flood Mitigation Structure | 124.6473 | 12.4912 | 96397878.94 | 96498826.48 | 2023 | EZJONES CONSTRUCTION INC. | 8279 | 2022 | 2023-04-04 | 02/28/2022 | 0 | 100947.54 | 2023-04-03 |  | 1
2023 | Region VIII | NORTHERN SAMAR | CATARMAN (CAPITAL) (NORTHERN SAMAR) | P00721801VS | Construction of Flood Mitigation Structure | 124.6499 | 12.4929 | 221949552.3 | 110859141.8 | 2023 | EZJONES CONSTRUCTION INC. | 8280 | 2023 | 2023-12-15 | 03/15/2023 | 111090410.5 | 0 | 2024-01-07 | 23
2024 | Region X | BUKIDNON | TALAKAG (BUKIDNON) | P00820144MN | Construction of Flood Mitigation Structure | 124.6514 | 7.9104 | 30380000 | 30380000 | 2024 | VEN RAY CONSTRUCTION CORPORATION | 8281 | 2024 | 2024-12-13 | 02/12/2024 | 0 | 0 | 2024-12-16 | 3
2021 | Region X | MISAMIS ORIENTAL |  | P00522073MN | Construction of Drainage Structure | 124.6516 | 8.4832 | 88912205 | 84440279.13 | 2024 | JEJOR'S CONSTRUCTION CORPORATION | 8282 | 2021 | 2024-04-21 | 07/29/2021 | 4471925.87 | 0 | 2023-09-04 |  | 230
2024 | Region X | BUKIDNON | TALAKAG (BUKIDNON) | P00820143MN | Construction of Flood Mitigation Structure | 124.6518 | 7.9092 | 49000000 | 49000000 | 2025 | VEN RAY CONSTRUCTION CORPORATION | 8283 | 2024 | 2025-01-20 | 02/12/2024 | 0 | 0 | 2025-01-20 | 0
2021 | Region X | MISAMIS ORIENTAL |  | P00522074MN | Construction of Flood Mitigation Structure | 124.6518 | 8.4835 | 96500000 | 91654271.43 | 2024 | JEJOR'S CONSTRUCTION CORPORATION | 8284 | 2021 | 2024-03-25 | 07/28/2021 | 4845728.57 | 0 | 2024-06-03 | 70
2023 | Region X | BUKIDNON | TALAKAG (BUKIDNON) | P00721370MN | Construction of Flood Mitigation Structure | 124.652 | 7.9108 | 7448000 | 7448000 | 2023 | VEN RAY CONSTRUCTION CORPORATION | 8285 | 2023 | 2023-06-22 | 02/27/2023 | 0 | 0 | 2023-06-22 | 0
2022 | Region VIII | SAMAR (WESTERN SAMAR) | CALBAYOG CITY (SAMAR (WESTERN SAMAR)) | P00630241VS | Construction of Slope Protection Structure | 124.6523 | 12.1303 | 19600000 | 19497944.21 | 2022 | PABLO S. LABASBAS CONSTRUCTION CORPORATION (FORMERLY: PABLOS. LABASBAS CONSTRUCTION CORPORATION) | 8286 | 2022 | 2022-11-05 | 03/23/2022 | 102055.79 | 0 | 2022-11-04 |  | 1
2022 | Region X | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY (CAPITAL) (MISAMIS ORIENTAL) | P00620053MN | Rehabilitation / Major Repair of Drainage Structure | 124.6564 | 8.4784 | 115800000 | 112325644.9 | 2024 | JEJOR'S CONSTRUCTION CORPORATION | 8287 | 2022 | 2024-03-25 | 06/29/2022 | 3474355.1 | 0 | 2023-04-23 |  | 337
2022 | Region X | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY (CAPITAL) (MISAMIS ORIENTAL) | P00620046MN | Rehabilitation / Major Repair of Drainage Structure | 124.6565 | 8.4922 | 98752310 | 97194243.34 | 2024 | VEN RAY CONSTRUCTION CORPORATION | 8288 | 2022 | 2024-03-25 | 06/29/2022 | 1558066.66 | 0 | 2024-09-24 | 183
2021 | Region X | MISAMIS ORIENTAL |  | P00522077MN | Rehabilitation / Major Repair of Flood Control Structure | 124.6566 | 8.4846 | 96500000 | 91435385.09 | 2024 | SUPREA PHILS. DEVELOPMENT CORP. / VEN RAY CONSTRUCTION CORPORATION | 8289 | 2021 | 2024-04-21 | 08/16/2021 | 5064614.91 | 0 | 2023-09-01 |  | 233
2024 | Region XII | COTABATO (NORTH COTABATO) | BANISILAN (COTABATO (NORTH COTABATO)) | P00833596MN | Construction of Drainage Structure | 124.6581 | 7.39 | 4950000 | 4949997.25 | 2025 | BETTER WORK CONSTRUCTION | 8290 | 2024 | 2025-01-27 | 09/17/2024 | 2.75 | 0 | 2025-01-26 |  | 1
2022 | Region X | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY (CAPITAL) (MISAMIS ORIENTAL) | P00620047MN | Rehabilitation / Major Repair of Drainage Structure | 124.6582 | 8.4912 | 106150000 | 102965502.4 | 2024 | JEJOR'S CONSTRUCTION CORPORATION | 8291 | 2022 | 2024-03-25 | 06/27/2022 | 3184497.6 | 0 | 2024-09-24 | 183
2022 | Region VIII | LEYTE | ORMOC CITY (LEYTE) | P00642534VS | Rehabilitation / Major Repair of Flood Control Structure | 124.6596 | 10.988 | 38600000 | 38599979.26 | 2022 | AQUALINE CONSTRUCTION CORPORATION (FORMERLY: AQUALINE CONSTRUCTION) | 8292 | 2022 | 2022-11-07 | 05/23/2022 | 20.74 | 0 | 2022-12-05 | 28
2022 | Region X | CAMIGUIN | MAMBAJAO (CAPITAL) (CAMIGUIN) | P00620136MN | Construction of Drainage Structure | 124.6596 | 9.2396 | 19599999.96 | 19600000 | 2023 | JANRHYLL CONSTRUCTION | 8293 | 2022 | 2023-04-23 | 05/12/2022 | 0 | 0.04 | 2022-10-06 |  | 199
2024 | Region XII | SOUTH COTABATO | NORALA (SOUTH COTABATO) | P00821096MN | Construction of Flood Mitigation Structure | 124.6599 | 6.5685 | 39201960 | 38420216.71 | 2024 | ACCELERATED METAL TECHNOLOGY & CONSTRUCTION, INC. | 8294 | 2024 | 2024-10-12 | 05/10/2024 | 781743.29 | 0 | 2024-10-11 |  | 1
2021 | Region X | MISAMIS ORIENTAL |  | P00522075MN | Construction of Drainage Structure | 124.6599 | 8.4839 | 121015825 | 114875026.6 | 2024 | JEJOR'S CONSTRUCTION CORPORATION | 8295 | 2021 | 2024-03-25 | 08/16/2021 | 6140798.4 | 0 | 2023-03-04 |  | 387
2022 | Region X | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY (CAPITAL) (MISAMIS ORIENTAL) | P00620049MN | Rehabilitation / Major Repair of Drainage Structure | 124.6602 | 8.4906 | 115800000 | 114009217 | 2024 | VEN RAY CONSTRUCTION CORPORATION | 8296 | 2022 | 2024-03-25 | 06/29/2022 | 1790783 | 0 | 2024-09-24 | 183
2023 | Region VIII | LEYTE | ORMOC CITY (LEYTE) | P00721576VS | Construction of Flood Mitigation Structure | 124.6603 | 10.957 | 57900000 | 57696132.04 | 2023 | REX E. MORALES CONSTRUCTION | 8297 | 2023 | 2023-10-29 | 04/03/2023 | 203867.96 | 0 | 2023-10-28 |  | 1
2022 | Region X | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY (CAPITAL) (MISAMIS ORIENTAL) | P00620048MN | Rehabilitation / Major Repair of Drainage Structure | 124.6622 | 8.49 | 115800000 | 114013627.6 | 2024 | VEN RAY CONSTRUCTION CORPORATION | 8298 | 2022 | 2024-03-25 | 06/06/2022 | 1786372.4 | 0 | 2024-09-01 | 160
2022 | Region VIII | NORTHERN SAMAR | CATARMAN (CAPITAL) (NORTHERN SAMAR) | P00632044VS | Construction of Drainage Structure | 124.6623 | 12.5118 | 4949562.2 | 4887350.18 | 2022 | RL TUBA CIVIL ENGINEERING CONSTRUCTION | 8299 | 2022 | 2022-09-19 | 03/31/2022 | 62212.02 | 0 | 2022-09-18 |  | 1
2024 | Region XII | SOUTH COTABATO | NORALA (SOUTH COTABATO) | P00820355MN | Construction of Flood Mitigation Structure | 124.6634 | 6.5675 | 39565000 | 39564960.1 | 2024 | BETTER WORK CONSTRUCTION | 8300 | 2024 | 2024-09-24 | 05/10/2024 | 39.9 | 0 | 2024-09-23 |  | 1
2022 | Region X | CAMIGUIN | MAMBAJAO (CAPITAL) (CAMIGUIN) | P00620133MN | Construction of Drainage Structure | 124.6679 | 9.2453 | 19599998.92 | 18718516.34 | 2022 | SHEEN-SHEEN CONSTRUCTION CORPORATION (FORMERLY: SHEEN-SHEEN CONSTRUCTION) | 8301 | 2022 | 2022-08-30 | 02/15/2022 | 881482.58 | 0 | 2022-07-09 |  | 52
2023 | Region X | CAMIGUIN | CATARMAN (CAMIGUIN) | P00721250MN | Construction of Flood Mitigation Structure | 124.6682 | 9.1311 | 115800000 | 115689618.4 | 2024 | VICTORIANO C. LIM CONSTRUCTION CORPORATION (FORMERLY: VICTORIANO C. LIM CONSTRUCTION) | 8302 | 2023 | 2024-07-23 | 04/11/2023 | 110381.6 | 0 | 2024-03-08 |  | 137
2022 | Region X | CAMIGUIN | CATARMAN (CAMIGUIN) | P00620129MN | Construction of Flood Mitigation Structure | 124.6687 | 9.1405 | 29399999.86 | 29400000 | 2023 | SHEEN-SHEEN CONSTRUCTION CORPORATION (FORMERLY: SHEEN-SHEEN CONSTRUCTION) | 8303 | 2022 | 2023-03-25 | 05/12/2022 | 0 | 0.14 | 2023-01-11 |  | 73
2022 | Region X | CAMIGUIN | CATARMAN (CAMIGUIN) | P00620024MN | Construction of Flood Mitigation Structure | 124.6687 | 9.1405 | 69577464.39 | 66446314.65 | 2023 | VICTORIANO C. LIM CONSTRUCTION CORPORATION (FORMERLY: VICTORIANO C. LIM CONSTRUCTION) | 8304 | 2022 | 2023-01-29 | 02/24/2022 | 3131149.74 | 0 | 2023-01-12 |  | 17
2023 | Region XII | SOUTH COTABATO | SANTO NIÃ‘O (SOUTH COTABATO) | P00721512MN | Construction of Flood Mitigation Structure | 124.6689 | 6.4277 | 45080000 | 45079806.32 | 2023 | BETTER WORK CONSTRUCTION / MEGALINE BUILDERS AND SUPPLY | 8305 | 2023 | 2023-09-28 | 04/17/2023 | 193.68 | 0 | 2023-09-27 |  | 1
2024 | Region VIII | LEYTE | ALBUERA (LEYTE) | P00820883VS | Construction of Flood Mitigation Structure | 124.6693 | 10.9488 | 96500000 | 96399778.3 | 2024 | AQUALINE CONSTRUCTION CORPORATION (FORMERLY: AQUALINE CONSTRUCTION) / EVERBUILT CONSTRUCTION | 8306 | 2024 | 2024-10-18 | 03/14/2024 | 100221.7 | 0 | 2025-01-06 | 80
2022 | Region X | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY (CAPITAL) (MISAMIS ORIENTAL) | P00620050MN | Rehabilitation / Major Repair of Flood Control Structure | 124.6706 | 8.482 | 115800000 | 112903335.6 | 2024 | JEJOR'S CONSTRUCTION CORPORATION | 8307 | 2022 | 2024-03-25 | 08/08/2022 | 2896664.4 | 0 | 2024-04-22 | 28
2023 | Region XII | SULTAN KUDARAT | TACURONG CITY (SULTAN KUDARAT) | P00732501MN | Construction of Drainage Structure | 124.6708 | 6.6954 | 14606042.29 | 14585227.83 | 2023 | C.A. BETALAC CONSTRUCTION & GEN. MDSE., INC. (FOR: C.A. BETALAC CONSTRUCTION & GEN. MDSE.) | 8308 | 2023 | 2023-11-19 | 02/27/2023 | 20814.46 | 0 | 2023-09-25 |  | 55
2024 | Region XII | SARANGANI | KIAMBA (SARANGANI) | P00835804MN | Construction of Flood Mitigation Structure | 124.672 | 5.9798 | 86850000 | 86846157.23 | 2024 | HI-TONE CONSTRUCTION & DEVELOPMENT CORP. (FORMERLY | 8309 | 2024 | 2024-11-12 | 05/02/2024 | 3842.77 | 0 | 2025-02-24 | 104
2023 | Region X | CAMIGUIN | CATARMAN (CAMIGUIN) | P00734023MN | Construction of Flood Mitigation Structure | 124.6722 | 9.1269 | 24499999.79 | 23763961.24 | 2023 | FNTC CONSTRUCTION | 8310 | 2023 | 2023-11-25 | 04/28/2023 | 736038.55 | 0 | 2023-10-02 |  | 54
2022 | Region XII | SULTAN KUDARAT | TACURONG CITY (SULTAN KUDARAT) | P00634146MN | Construction of Drainage Structure | 124.6727 | 6.6961 | 4937515.81 | 4932515 | 2022 | BEMA CONSTRUCTION AND GENERAL MERCHANDISE | 8311 | 2022 | 2022-07-26 | 06/08/2022 | 5000.81 | 0 | 2022-09-03 | 39
2023 | Region VIII | SAMAR (WESTERN SAMAR) | GANDARA (SAMAR (WESTERN SAMAR)) | P00733762VS | Rehabilitation / Major Repair of Flood Control Structure | 124.6734 | 11.984 | 48510000 | 48489599.83 | 2024 | JUPA CONSTRUCTION | 8312 | 2023 | 2024-02-19 | 05/31/2023 | 20400.17 | 0 | 2024-02-02 |  | 17
2024 | Region XII | COTABATO (NORTH COTABATO) | PIKIT (COTABATO (NORTH COTABATO)) | P00833594MN | Construction of Drainage Structure | 124.6749 | 7.0555 | 4950000 | 4900000 | 2024 | LLABAN CONSTRUCTION & SUPPLY (FORMERLY: LLABAN CON | 8313 | 2024 | 2024-04-29 | 02/07/2024 | 50000 | 0 | 2024-05-06 | 7
2023 | Region XII | COTABATO (NORTH COTABATO) | PIKIT (COTABATO (NORTH COTABATO)) | P00732493MN | Construction of Drainage Structure | 124.6749 | 7.0556 | 4950000 | 4900499.99 | 2023 | LLABAN CONSTRUCTION & SUPPLY (FORMERLY: LLABAN CON | 8314 | 2023 | 2023-07-31 | 02/20/2023 | 49500.01 | 0 | 2023-05-01 |  | 91
2022 | Region XII | MAGUINDANAO DEL SUR | MANGUDADATU (MAGUINDANAO) | P00633903MN | Construction of Flood Mitigation Structure | 124.6774 | 6.6606 | 96499768.8 | 95999761.1 | 2023 | LLABAN CONSTRUCTION & SUPPLY (FORMERLY: LLABAN CON / RNS CONSTRUCTION ENGINEERING | 8315 | 2022 | 2023-07-31 | 08/15/2022 | 500007.7 | 0 | 2023-07-26 |  | 5
2022 | Region X | CAMIGUIN | CATARMAN (CAMIGUIN) | P00620126MN | Construction of Flood Mitigation Structure | 124.6802 | 9.119 | 19599999.99 | 19034974.8 | 2022 | JAPUZ-JANSOL ENTERPRISES | 8316 | 2022 | 2022-11-27 | 05/12/2022 | 565025.19 | 0 | 2022-10-06 |  | 52
2024 | Region XII | SOUTH COTABATO | NORALA (SOUTH COTABATO) | P00820353MN | Construction of Flood Mitigation Structure | 124.6813 | 6.5511 | 29915000 | 29785008.72 | 2024 | REYDAN BUILDERS | 8317 | 2024 | 2024-09-11 | 05/10/2024 | 129991.28 | 0 | 2024-09-10 |  | 1
2023 | Region XII | SOUTH COTABATO | NORALA (SOUTH COTABATO) | P00732168MN | Construction of Flood Mitigation Structure | 124.6837 | 6.5507 | 49000000 | 24495251.86 | 2023 | BETTER WORK CONSTRUCTION | 8318 | 2023 | 2023-08-07 | 04/17/2023 | 24504748.14 | 0 | 2023-08-06 |  | 1
2023 | Region XII | SOUTH COTABATO | SANTO NIÃ‘O (SOUTH COTABATO) | P00732165MN | Construction of Flood Mitigation Structure | 124.6851 | 6.4112 | 29400000 | 29399875.1 | 2023 | BETTER WORK CONSTRUCTION | 8319 | 2023 | 2023-10-06 | 04/17/2023 | 124.9 | 0 | 2023-10-05 |  | 1
2022 | Region XII | SOUTH COTABATO | NORALA (SOUTH COTABATO) | P00630624MN | Construction of Flood Mitigation Structure | 124.6858 | 6.5436 | 98000000 | 48999928.43 | 2022 | NIRVANA CONSTRUCTION & SUPPLIES / FFJJ CONSTRUCTION | 8320 | 2022 | 2022-10-07 | 02/18/2022 | 49000071.57 | 0 | 2022-09-11 |  | 26
2023 | Region XII | SOUTH COTABATO | NORALA (SOUTH COTABATO) | P00721466MN | Construction of Flood Mitigation Structure | 124.6864 | 6.5483 | 67550000 | 67549845.83 | 2024 | ABU CONSTRUCTION | 8321 | 2023 | 2024-03-18 | 04/05/2023 | 154.17 | 0 | 2024-03-17 |  | 1
2023 | Region VIII | LEYTE | ALBUERA (LEYTE) | P00721577VS | Construction of Flood Mitigation Structure | 124.6892 | 10.934 | 55005000 | 55003847.3 | 2023 | AQUALINE CONSTRUCTION CORPORATION (FORMERLY: AQUALINE CONSTRUCTION) / EVERBUILT CONSTRUCTION | 8322 | 2023 | 2023-10-25 | 04/05/2023 | 1152.7 | 0 | 2023-11-29 | 35
2024 | Region VIII | LEYTE | ALBUERA (LEYTE) | P00834628VS | Construction of Flood Mitigation Structure | 124.6913 | 10.9202 | 96500000 | 96399999.99 | 2024 | JM COLLERA KONSTRACT | 8323 | 2024 | 2024-12-16 | 05/15/2024 | 100000.01 | 0 | 2025-03-09 | 83
2024 | Region X | CAMIGUIN | CATARMAN (CAMIGUIN) | P00820402MN | Construction of Flood Mitigation Structure | 124.6915 | 9.1138 | 19599999.81 | 19006200.13 | 2024 | SHEEN-SHEEN CONSTRUCTION CORPORATION (FORMERLY: SHEEN-SHEEN CONSTRUCTION) | 8324 | 2024 | 2024-04-16 | 02/15/2024 | 593799.68 | 0 | 2024-07-15 | 90
2022 | Region X | CAMIGUIN | CATARMAN (CAMIGUIN) | P00620041MN | Construction of Drainage Structure | 124.6917 | 9.1143 | 96499947.24 | 92157449.61 | 2022 | VICTORIANO C. LIM CONSTRUCTION CORPORATION (FORMERLY: VICTORIANO C. LIM CONSTRUCTION) | 8325 | 2022 | 2022-11-27 | 02/15/2022 | 4342497.63 | 0 | 2022-10-03 |  | 55
2024 | Region X | CAMIGUIN | MAMBAJAO (CAPITAL) (CAMIGUIN) | P00821083MN | Construction of Flood Mitigation Structure | 124.6933 | 9.2493 | 29399999.19 | 28809594.6 | 2025 | FNTC CONSTRUCTION | 8326 | 2024 | 2025-02-23 | 05/16/2024 | 590404.59 | 0 | 2025-02-01 |  | 22
2024 | Region XII | SOUTH COTABATO | SURALLAH (SOUTH COTABATO) | P00820352MN | Construction of Flood Mitigation Structure | 124.696 | 6.3989 | 29915000 | 29539716.7 | 2024 | VERGUZ CONSTRUCTION | 8327 | 2024 | 2024-08-22 | 05/15/2024 | 375283.3 | 0 | 2024-09-15 | 24
2023 | Region XII | SOUTH COTABATO | SURALLAH (SOUTH COTABATO) | P00734380MN | Construction of Flood Mitigation Structure | 124.6971 | 6.392 | 310576313.2 | 83327324.86 | 2024 | ABU CONSTRUCTION | 8328 | 2023 | 2024-04-11 | 08/30/2023 | 227248988.34 | 0 | 2024-04-10 |  | 1
2024 | Region XII | SULTAN KUDARAT | ISULAN (CAPITAL) (SULTAN KUDARAT) | P00820416MN | Construction of Flood Mitigation Structure | 124.5683 | 6.6756 | 45005247.52 | 44960045.66 | 2024 | CS CONST. AND SUPPLY INC. (FORMERLY: CS CONSTRUCTION AND SUPPLY) | 8329 | 2024 | 2024-05-20 | 02/15/2024 | 45201.86 | 0 | 2024-08-26 | 98
2024 | Region VIII | LEYTE | BABATNGON (LEYTE) | P00832680VS | Construction of Flood Mitigation Structure | 124.8461 | 11.4128 | 49500000 | 49458786.62 | 2024 | GO_SOLID BUILDERS INC. | 8330 | 2024 | 2024-08-19 | 04/11/2024 | 41213.38 | 0 | 2024-10-26 | 68
2024 | Region X | CAMIGUIN | SAGAY (CAMIGUIN) | P00820910MN | Construction of Flood Mitigation Structure | 124.7008 | 9.1111 | 96499997.86 | 94561570.35 | 2025 | JAPUZ-JANSOL ENTERPRISES | 8331 | 2024 | 2025-02-23 | 06/18/2024 | 1938427.51 | 0 | 2025-02-08 |  | 15
2023 | Region X | CAMIGUIN | MAMBAJAO (CAPITAL) (CAMIGUIN) | P00721374MN | Construction of Flood Mitigation Structure | 124.7013 | 9.241 | 48999999.24 | 48913540.2 | 2023 | SHEEN-SHEEN CONSTRUCTION CORPORATION (FORMERLY: SHEEN-SHEEN CONSTRUCTION) | 8332 | 2023 | 2023-10-24 | 02/27/2023 | 86459.04 | 0 | 2023-09-19 |  | 35
2023 | Region VIII | LEYTE | TACLOBAN CITY (CAPITAL) (LEYTE) | P00721617VS | Construction of Flood Mitigation Structure | 124.9459 | 11.2533 | 110971687.6 | 110859451.4 | 2024 | COLLERA CONSTRUCTION | 8333 | 2023 | 2024-03-18 | 06/19/2023 | 112236.2 | 0 | 2024-03-26 | 8
2022 | Region V | CATANDUANES | PANDAN (CATANDUANES) | P00631449LZ | Construction of Flood Mitigation Structure | 124.1667 | 14.0513 | 48998759.4 | 48753545.92 | 2022 | AL-JON CONSTRUCTION DEVELOPMENT, INC. (FORMERLY: ALJON CONSTRUCTION & SUPPLY) | 8334 | 2022 | 2022-12-16 | 03/02/2022 | 245213.48 | 0 | 2022-12-17 | 1
2022 | Region XII | SOUTH COTABATO | CITY OF KORONADAL (CAPITAL) (SOUTH COTABATO) | P00630614MN | Construction of Flood Mitigation Structure | 124.8461 | 6.5036 | 58800000 | 29398305.78 | 2022 | BETTER WORK CONSTRUCTION | 8335 | 2022 | 2022-09-03 | 03/02/2022 | 29401694.22 | 0 | 2022-08-06 |  | 28
2022 | Region VII | BOHOL | TRINIDAD (BOHOL) | P00630189VS | Construction of Flood Mitigation Structure | 124.3478 | 10.0811 | 66585000 | 66564785.83 | 2023 | LEDA CONSTRUCTION INCORPORATED | 8336 | 2022 | 2023-04-10 | 04/04/2022 | 20214.17 | 0 | 2023-04-09 |  | 1
2023 | Region X | MISAMIS ORIENTAL | MEDINA (MISAMIS ORIENTAL) | P00734371MN | Construction of Flood Mitigation Structure | 125.0113 | 8.9102 | 73500000 | 74250000 | 2023 | ROAD EDGE TRADING & DEVELOPMENT SERVICES | 8337 | 2023 | 2023-10-03 | 04/25/2023 | 0 | 750000 | 2024-01-18 | 107
2022 | Region VIII | LEYTE | KANANGA (LEYTE) | P00620194VS | Construction of Flood Mitigation Structure | 124.5683 | 11.191 | 48999756.46 | 48999997.17 | 2022 | LEDA CONSTRUCTION INCORPORATED | 8338 | 2022 | 2022-12-17 | 02/21/2022 | 0 | 240.71 | 2022-12-16 |  | 1
2022 | Region X | CAMIGUIN | MAMBAJAO (CAPITAL) (CAMIGUIN) | P00620128MN | Construction of Flood Mitigation Structure | 124.7024 | 9.2505 | 29399921.44 | 28079386.5 | 2022 | SHEEN-SHEEN CONSTRUCTION CORPORATION (FORMERLY: SHEEN-SHEEN CONSTRUCTION) | 8339 | 2022 | 2022-10-01 | 02/15/2022 | 1320534.94 | 0 | 2022-07-23 |  | 70
2023 | Region VIII | LEYTE | TACLOBAN CITY (CAPITAL) (LEYTE) | P00721618VS | Construction of Flood Mitigation Structure | 124.9461 | 11.3201 | 33773462.79 | 33650737.08 | 2023 | JGO BUILDERS | 8340 | 2023 | 2023-10-25 | 04/05/2023 | 122725.71 | 0 | 2023-10-24 |  | 1
2021 | Region V | CATANDUANES |  | P00526240LZ | Construction of Flood Mitigation Structure | 124.1684 | 14.0507 | 44098759.15 | 44098760 | 2022 | ROLCO CONSTRUCTION & DEVELOPMENT CORPORATION ( FOR | 8341 | 2021 | 2022-08-17 | 01/17/2022 | 0 | 0.85 | 2022-09-22 | 36
2022 | Region V | CATANDUANES | PANDAN (CATANDUANES) | P00631450LZ | Construction of Flood Mitigation Structure | 124.1731 | 14.0475 | 48999999.74 | 48998740.17 | 2022 | AL-JON CONSTRUCTION DEVELOPMENT, INC. (FORMERLY: ALJON CONSTRUCTION & SUPPLY) | 8342 | 2022 | 2022-10-13 | 03/02/2022 | 1259.57 | 0 | 2022-10-12 |  | 1
2022 | Region V | CATANDUANES | PANDAN (CATANDUANES) | P00640583LZ | Construction of Flood Mitigation Structure | 124.1731 | 14.0476 | 2970000 | 2970000 | 2022 | FDS CONSTRUCTION & SUPPLY | 8343 | 2022 | 2022-09-04 | 07/22/2022 | 0 | 0 | 2022-09-03 |  | 1
2024 | Region VII | BOHOL | GETAFE (BOHOL) | P00820179VS | Construction of Flood Mitigation Structure | 124.1747 | 10.1385 | 48403180 | 48403180 | 2025 | LEDA CONSTRUCTION INCORPORATED | 8344 | 2024 | 2025-03-02 | 03/07/2024 | 0 | 0 | 2025-02-07 |  | 23
2022 | Region V | SORSOGON | PRIETO DIAZ (SORSOGON) | P00631477LZ | Construction of Flood Mitigation Structure | 124.1812 | 13.0672 | 58800000 | 28518000 | 2022 | MUNTOPAR BUILDERS CORP. | 8345 | 2022 | 2022-09-04 | 02/15/2022 | 30282000 | 0 | 2022-09-03 |  | 1
2024 | Region VII | BOHOL | GETAFE (BOHOL) | P00820180VS | Construction of Flood Mitigation Structure | 124.185 | 10.1357 | 48403180 | 48403180 | 2025 | LEDA CONSTRUCTION INCORPORATED | 8346 | 2024 | 2025-01-10 | 03/07/2024 | 0 | 0 | 2025-02-04 | 25
2022 | Region V | CATANDUANES | VIRAC (CAPITAL) (CATANDUANES) | P00631448LZ | Construction of Flood Mitigation Structure | 124.1862 | 13.5895 | 48999999.86 | 48998760 | 2022 | A.V. LAYNES TRADING AND CONSTRUCTION | 8347 | 2022 | 2022-08-16 | 03/02/2022 | 1239.86 | 0 | 2022-08-15 |  | 1
2022 | Region X | LANAO DEL NORTE | ILIGAN CITY (LANAO DEL NORTE) | P00620139MN | Construction of Flood Mitigation Structure | 124.1884 | 8.1975 | 34300000 | 34300000 | 2022 | MAMSAR CONSTRUCTION AND INDUSTRIAL CORPORATION | 8348 | 2022 | 2022-10-30 | 03/18/2022 | 0 | 0 | 2022-10-29 |  | 1
2022 | Region X | LANAO DEL NORTE | ILIGAN CITY (LANAO DEL NORTE) | P00620140MN | Construction of Flood Mitigation Structure | 124.1893 | 8.1957 | 34300000 | 34300000 | 2023 | MAMSAR CONSTRUCTION AND INDUSTRIAL CORPORATION | 8349 | 2022 | 2023-05-12 | 03/18/2022 | 0 | 0 | 2023-05-12 | 0
2022 | Region X | LANAO DEL NORTE | ILIGAN CITY (LANAO DEL NORTE) | P00620141MN | Construction of Flood Mitigation Structure | 124.1899 | 8.1969 | 34300000 | 34300000 | 2022 | MAMSAR CONSTRUCTION AND INDUSTRIAL CORPORATION | 8350 | 2022 | 2022-10-30 | 03/18/2022 | 0 | 0 | 2022-10-29 |  | 1
2022 | Region X | LANAO DEL NORTE | ILIGAN CITY (LANAO DEL NORTE) | P00620142MN | Construction of Flood Mitigation Structure | 124.1901 | 8.1961 | 32020520 | 32020520 | 2023 | MAMSAR CONSTRUCTION AND INDUSTRIAL CORPORATION | 8351 | 2022 | 2023-05-06 | 03/18/2022 | 0 | 0 | 2023-05-05 |  | 1
2022 | Region XII | SULTAN KUDARAT | PALIMBANG (SULTAN KUDARAT) | P00620092MN | Construction of Flood Mitigation Structure | 124.1911 | 6.2063 | 67550000 | 67550000 | 2023 | LLABAN CONSTRUCTION & SUPPLY (FORMERLY: LLABAN CON / CBC SQUARE BUILDERS CO. | 8352 | 2022 | 2023-05-15 | 03/18/2022 | 0 | 0 | 2022-11-20 |  | 176
2024 | Region XII | SULTAN KUDARAT | PALIMBANG (SULTAN KUDARAT) | P00820207MN | Construction of Flood Mitigation Structure | 124.1936 | 6.2333 | 22050000 | 21174615 | 2024 | CS CONST. AND SUPPLY INC. (FORMERLY: CS CONSTRUCTION AND SUPPLY) | 8353 | 2024 | 2024-08-16 | 03/25/2024 | 875385 | 0 | 2024-09-09 | 24
2022 | Region V | CATANDUANES | VIRAC (CAPITAL) (CATANDUANES) | P00631443LZ | Construction of Flood Mitigation Structure | 124.198 | 13.5639 | 39200000 | 39198663.99 | 2023 | AL-JON CONSTRUCTION DEVELOPMENT, INC. (FORMERLY: ALJON CONSTRUCTION & SUPPLY) | 8354 | 2022 | 2023-03-01 | 03/02/2022 | 1336.01 | 0 | 2023-02-28 |  | 1
2022 | Region XII | SULTAN KUDARAT | PALIMBANG (SULTAN KUDARAT) | P00620095MN | Construction of Flood Mitigation Structure | 124.1981 | 6.2208 | 67550000 | 67550000 | 2022 | CS CONST. AND SUPPLY INC. (FORMERLY: CS CONSTRUCTION AND SUPPLY) | 8355 | 2022 | 2022-12-01 | 03/18/2022 | 0 | 0 | 2022-11-20 |  | 11
2023 | Region XII | SULTAN KUDARAT | PALIMBANG (SULTAN KUDARAT) | P00721316MN | Construction of Flood Mitigation Structure | 124.199 | 6.2191 | 84920000 | 84919952.15 | 2023 | CS CONST. AND SUPPLY INC. (FORMERLY: CS CONSTRUCTION AND SUPPLY) | 8356 | 2023 | 2023-08-01 | 02/24/2023 | 47.85 | 0 | 2023-10-13 | 73
2022 | Region XII | SULTAN KUDARAT | BAGUMBAYAN (SULTAN KUDARAT) | P00620093MN | Construction of Flood Mitigation Structure | 124.2082 | 6.1975 | 96500000 | 96499932.16 | 2022 | CS CONST. AND SUPPLY INC. (FORMERLY: CS CONSTRUCTION AND SUPPLY) | 8357 | 2022 | 2022-12-01 | 02/21/2022 | 67.84 | 0 | 2022-11-21 |  | 10
2023 | Region XII | SULTAN KUDARAT | PALIMBANG (SULTAN KUDARAT) | P00721393MN | Construction of Flood Mitigation Structure | 124.2083 | 6.1978 | 49000000 | 48999998.56 | 2023 | CS CONST. AND SUPPLY INC. (FORMERLY: CS CONSTRUCTION AND SUPPLY) | 8358 | 2023 | 2023-08-01 | 02/13/2023 | 1.44 | 0 | 2023-09-12 | 42
2022 | Region V | CATANDUANES | VIRAC (CAPITAL) (CATANDUANES) | P00631442LZ | Construction of Flood Mitigation Structure | 124.2227 | 13.5901 | 49000000 | 48998759.81 | 2022 | EMSYM CONSTRUCTION CORP. / NQA CONSTRUCTION & SUPPLY | 8359 | 2022 | 2022-12-03 | 03/22/2022 | 1240.19 | 0 | 2022-11-16 |  | 17
2022 | Region V | CATANDUANES | VIRAC (CAPITAL) (CATANDUANES) | P00631439LZ | Construction of Flood Mitigation Structure | 124.2245 | 13.5694 | 29398758.98 | 29395380.35 | 2022 | NIDA BUILDER'S & SUPPLIES | 8360 | 2022 | 2022-09-29 | 03/02/2022 | 3378.63 | 0 | 2022-10-02 | 3
2022 | Region V | CATANDUANES | VIRAC (CAPITAL) (CATANDUANES) | P00640584LZ | Construction of Flood Mitigation Structure | 124.2247 | 13.5694 | 29399999.48 | 29399911.31 | 2022 | AL-JON CONSTRUCTION DEVELOPMENT, INC. (FORMERLY: ALJON CONSTRUCTION & SUPPLY) | 8361 | 2022 | 2022-11-12 | 04/12/2022 | 88.17 | 0 | 2022-11-12 | 0
2023 | Region VII | BOHOL | DAGOHOY (BOHOL) | P00721816VS | Construction of Flood Mitigation Structure | 124.2262 | 9.9086 | 49000000 | 48997618.15 | 2024 | LEDA CONSTRUCTION INCORPORATED | 8362 | 2023 | 2024-06-03 | 02/21/2023 | 2381.85 | 0 | 2024-05-02 |  | 32
2022 | Region XII | MAGUINDANAO DEL NORTE | DATU PIANG (MAGUINDANAO) | P00620247MN | Construction of Revetment | 124.2313 | 7.1727 | 81250779.4 | 80448703.76 | 2023 | DCD BUILDERS & ENTERPISES / CORICS CONSTRUCTION | 8363 | 2022 | 2023-12-27 | 10/12/2022 | 802075.64 | 0 | 2023-12-15 |  | 12
2021 | Region XII | MAGUINDANAO DEL NORTE |  | P00522110MN | Construction of Flood Mitigation Structure | 124.2362 | 7.1897 | 67516067.45 | 67549998.47 | 2023 | ABU CONSTRUCTION | 8364 | 2021 | 2023-01-15 | 03/08/2022 | 0 | 33931.02 | 2023-02-11 | 27
2022 | Region V | CATANDUANES | VIRAC (CAPITAL) (CATANDUANES) | P00631440LZ | Construction of Flood Mitigation Structure | 124.2378 | 13.582 | 29398759.99 | 29400000 | 2022 | A.V. LAYNES TRADING AND CONSTRUCTION | 8365 | 2022 | 2022-11-05 | 03/02/2022 | 0 | 1240.01 | 2022-12-27 | 52
2022 | Region XII | MAGUINDANAO DEL NORTE | DATU PIANG (MAGUINDANAO) | P00620248MN | Construction of Revetment | 124.2398 | 7.1882 | 28949922.8 | 28811519.78 | 2023 | MUST ENTERPRISES | 8366 | 2022 | 2023-11-06 | 12/27/2022 | 138403.02 | 0 | 2023-09-18 |  | 49
2023 | Region VII | BOHOL | DAGOHOY (BOHOL) | P00721817VS | Construction of Flood Mitigation Structure | 124.2407 | 9.9271 | 49000000 | 48507745 | 2023 | LABB CONSTRUCTION DEVELOPMENT INC. (FORMERLY: LABB CONSTRUCTION) | 8367 | 2023 | 2023-11-08 | 02/21/2023 | 492255 | 0 | 2023-11-11 | 3
2023 | Region VII | BOHOL | DANAO (BOHOL) | P00721818VS | Construction of Flood Mitigation Structure | 124.2408 | 9.9272 | 49000000 | 48999860.9 | 2023 | LEDA CONSTRUCTION INCORPORATED | 8368 | 2023 | 2023-12-18 | 03/16/2023 | 139.1 | 0 | 2023-12-21 | 3
2022 | Region XII | MAGUINDANAO DEL NORTE | DATU PIANG (MAGUINDANAO) | P00620249MN | Construction of Revetment | 124.2448 | 7.1886 | 82024973.4 | 81974860.79 | 2023 | MUST ENTERPRISES | 8369 | 2022 | 2023-12-01 | 12/27/2022 | 50112.61 | 0 | 2023-11-09 |  | 22
2023 | Region X | LANAO DEL NORTE | ILIGAN CITY (LANAO DEL NORTE) | P00732486MN | Construction of Drainage Structure | 124.2452 | 8.2436 | 1980000 | 1978999.7 | 2023 | MILLENNIUM BUILDERS & CONSTRUCTION | 8370 | 2023 | 2023-06-23 | 02/22/2023 | 1000.3 | 0 | 2023-06-22 |  | 1
2022 | Region VIII | NORTHERN SAMAR | SAN ANTONIO (NORTHERN SAMAR) | P00620206VS | Construction of Flood Mitigation Structure | 124.2477 | 12.4172 | 48998956.3 | 48473345.46 | 2022 | CTC BUILDER AND SUPPLIES INCORPORATED (FOR. CTC BU / VCD CONSTRUCTION AND SUPPLY | 8371 | 2022 | 2022-12-21 | 02/21/2022 | 525610.84 | 0 | 2023-01-10 | 20
2022 | Region X | LANAO DEL NORTE | ILIGAN CITY (LANAO DEL NORTE) | P00630577MN | Construction of Flood Mitigation Structure | 124.2491 | 8.1823 | 39200000 | 39200000 | 2022 | RED CONSTRUCTION TECHNIK | 8372 | 2022 | 2022-12-09 | 03/18/2022 | 0 | 0 | 2022-12-19 | 10
2023 | Region XII | MAGUINDANAO DEL NORTE | COTABATO CITY (MAGUINDANAO) | P00721580MN | Construction of Flood Mitigation Structure | 124.2495 | 7.2253 | 48250000 | 48250000 | 2024 | JDRC CONSTRUCTION & SUPPLIES, CORP. | 8373 | 2023 | 2024-09-30 | 10/05/2023 | 0 | 0 | 2024-06-27 |  | 95
2022 | Region XII | MAGUINDANAO DEL NORTE | BULUAN (MAGUINDANAO) | P00633906MN | Construction of Flood Mitigation Structure | 124.25 | 7.2253 | 144749922.3 | 144621700.5 | 2023 | FFJJ CONSTRUCTION | 8374 | 2022 | 2023-12-22 | 08/15/2022 | 128221.8 | 0 | 2024-04-30 | 130
2022 | Region X | LANAO DEL NORTE | ILIGAN CITY (LANAO DEL NORTE) | P00630579MN | Construction of Flood Mitigation Structure | 124.2501 | 8.2209 | 39200000 | 37238197.29 | 2022 | AL HUSSEIN CONSTRUCTION | 8375 | 2022 | 2022-10-21 | 03/18/2022 | 1961802.71 | 0 | 2022-10-20 |  | 1
2022 | Region X | LANAO DEL NORTE | ILIGAN CITY (LANAO DEL NORTE) | P00620348MN | Construction of Flood Mitigation Structure | 124.2508 | 8.2506 | 49000000 | 49000000 | 2023 | M.M.A. ACHIEVER CONSTRUCTION & DEVELOPMENT CORP. / H & N BUILDERS & ENTERPRISES | 8376 | 2022 | 2023-07-15 | 03/24/2022 | 0 | 0 | 2023-07-14 |  | 1
2022 | Region X | LANAO DEL NORTE | ILIGAN CITY (LANAO DEL NORTE) | P00634133MN | Construction of Drainage Structure | 124.2522 | 8.2408 | 2970000 | 2970000 | 2022 | SILVER CONSTRUCTION | 8377 | 2022 | 2022-07-10 | 03/24/2022 | 0 | 0 | 2022-07-09 |  | 1
2021 | Region X | LANAO DEL NORTE |  | P00522071MN | Construction of Flood Mitigation Structure | 124.2536 | 8.2501 | 73624675 | 69946552.43 | 2023 | MAMSAR CONSTRUCTION AND INDUSTRIAL CORPORATION | 8378 | 2021 | 2023-12-27 | 03/05/2021 | 3678122.57 | 0 | 2023-12-26 |  | 1
2022 | Region X | LANAO DEL NORTE | ILIGAN CITY (LANAO DEL NORTE) | P00630580MN | Construction of Flood Mitigation Structure | 124.2549 | 8.1831 | 29400000 | 29400000 | 2022 | RED CONSTRUCTION TECHNIK | 8379 | 2022 | 2022-11-30 | 03/18/2022 | 0 | 0 | 2022-11-29 |  | 1
2023 | Region X | LANAO DEL NORTE | ILIGAN CITY (LANAO DEL NORTE) | P00721256MN | Construction of Flood Mitigation Structure | 124.2562 | 8.2188 | 48250000 | 48250000 | 2023 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R | 8380 | 2023 | 2023-08-23 | 02/22/2023 | 0 | 0 | 2023-10-06 | 44
2022 | Region X | LANAO DEL NORTE | ILIGAN CITY (LANAO DEL NORTE) | P00630581MN | Construction of Flood Mitigation Structure | 124.2569 | 8.195 | 29400000 | 24272381.65 | 2022 | N.B. SALBO CONSTRUCTION | 8381 | 2022 | 2022-09-28 | 03/18/2022 | 5127618.35 | 0 | 2022-09-30 | 2
2022 | Region X | LANAO DEL NORTE | ILIGAN CITY (LANAO DEL NORTE) | P00630578MN | Construction of Flood Mitigation Structure | 124.2571 | 8.186 | 29400000 | 29400000 | 2022 | IOS CONSTRUCTION SERVICES | 8382 | 2022 | 2022-09-30 | 03/18/2022 | 0 | 0 | 2022-09-30 | 0
2024 | Region X | LANAO DEL NORTE | ILIGAN CITY (LANAO DEL NORTE) | P00820403MN | Construction of Flood Mitigation Structure | 124.2574 | 8.1814 | 48250000 | 48250000 | 2024 | N.B. SALBO CONSTRUCTION | 8383 | 2024 | 2024-10-12 | 02/27/2024 | 0 | 0 | 2024-10-11 |  | 1
2022 | Region X | MISAMIS ORIENTAL | LUGAIT (MISAMIS ORIENTAL) | P00630487MN | Construction of Flood Mitigation Structure | 124.2592 | 8.3416 | 67550000 | 67550000 | 2022 | PYRAMID CONSOLIDATED BUILDERS & GEN. MDSE. | 8384 | 2022 | 2022-10-21 | 03/03/2022 | 0 | 0 | 2022-10-28 | 7
2022 | Region X | MISAMIS ORIENTAL | LUGAIT (MISAMIS ORIENTAL) | P00630488MN | Construction of Flood Mitigation Structure | 124.2621 | 8.3416 | 67550000 | 67550000 | 2022 | DL ENTERPRISES | 8385 | 2022 | 2022-12-25 | 02/28/2022 | 0 | 0 | 2022-12-24 |  | 1
2022 | Region X | MISAMIS ORIENTAL | LUGAIT (MISAMIS ORIENTAL) | P00630489MN | Construction of Flood Mitigation Structure | 124.263 | 8.3437 | 62725000 | 62725000 | 2022 | RAMISES CONSTRUCTION | 8386 | 2022 | 2022-11-11 | 03/24/2022 | 0 | 0 | 2022-11-10 |  | 1
2024 | Region X | LANAO DEL NORTE | TUBOD (CAPITAL) (LANAO DEL NORTE) | P00820039MN | Construction of Flood Mitigation Structure | 124.2643 | 8.1438 | 87725255 | 87725255 | 2024 | CDH CONSTRUCTION / AJJ STRUKTURE BUILDERS INC. | 8387 | 2024 | 2024-08-21 | 02/13/2024 | 0 | 0 | 2024-12-15 | 116
2022 | Region X | LANAO DEL NORTE | ILIGAN CITY (LANAO DEL NORTE) | P00620353MN | Rehabilitation / Major Repair of Flood Control Structure | 124.2674 | 8.2561 | 39200000 | 39200000 | 2023 | LECAR BUILDERS | 8388 | 2022 | 2023-03-26 | 03/24/2022 | 0 | 0 | 2023-03-25 |  | 1
2023 | Region X | MISAMIS ORIENTAL | LUGAIT (MISAMIS ORIENTAL) | P00732487MN | Construction of Flood Mitigation Structure | 124.2683 | 8.3412 | 4950000 | 4950000 | 2023 | LIGHT CONSTRUCTION & SUPPLY | 8389 | 2023 | 2023-10-04 | 06/02/2023 | 0 | 0 | 2023-10-03 |  | 1
2023 | Region V | CATANDUANES | SAN MIGUEL (CATANDUANES) | P00740438LZ | Construction of Flood Mitigation Structure | 124.272 | 13.7561 | 192816063.6 | 192816063.6 | 2024 | SUNWEST, INC. (FORMERLY: SUNWEST CONSTRUCTION & DEVELOPMENT CORPORATION) | 8390 | 2023 | 2024-03-22 | 04/04/2023 | 0 | 0 | 2024-03-21 |  | 1
2021 | Region VIII | NORTHERN SAMAR |  | P00521722VS | Construction of Flood Mitigation Structure | 124.2731 | 12.5662 | 48999689.58 | 48974593.23 | 2022 | C. A. CONSTRUCTION AND SUPPLY / CDU CONSTRUCTION | 8391 | 2021 | 2022-07-04 | 02/18/2021 | 25096.35 | 0 | 2021-12-05 |  | 211
2021 | Region XII | MAGUINDANAO DEL NORTE |  | P00522327MN | Construction of Revetment | 124.2782 | 7.1594 | 96482967.52 | 96499997.84 | 2023 | GEMMA CONSTRUCTION SUPPLY, INC.(FORMERLY:GEMMA CON | 8392 | 2021 | 2023-01-02 | 03/08/2022 | 0 | 17030.32 | 2023-04-01 | 89
2022 | Region V | CATANDUANES | BATO (CATANDUANES) | P00620732LZ | Construction of Flood Mitigation Structure | 124.2804 | 13.5941 | 24695020 | 24693780 | 2022 | AL-JON CONSTRUCTION DEVELOPMENT, INC. (FORMERLY: ALJON CONSTRUCTION & SUPPLY) | 8393 | 2022 | 2022-10-22 | 03/02/2022 | 1240 | 0 | 2022-10-21 |  | 1
2022 | Region VIII | NORTHERN SAMAR | ALLEN (NORTHERN SAMAR) | P00620207VS | Construction of Flood Mitigation Structure | 124.2816 | 12.518 | 29399512.57 | 28767754.96 | 2022 | CHRISTFER CONSTRUCTION & SUPPLY | 8394 | 2022 | 2022-11-26 | 02/21/2022 | 631757.61 | 0 | 2022-11-25 |  | 1
2022 | Region VIII | NORTHERN SAMAR | ALLEN (NORTHERN SAMAR) | P00620204VS | Construction of Flood Mitigation Structure | 124.2842 | 12.5033 | 48999584.5 | 48960370.3 | 2023 | C. A. CONSTRUCTION AND SUPPLY / CDU CONSTRUCTION | 8395 | 2022 | 2023-05-23 | 02/21/2022 | 39214.2 | 0 | 2023-05-22 |  | 1
2022 | Region X | MISAMIS ORIENTAL | NAAWAN (MISAMIS ORIENTAL) | P00632312MN | Construction of Flood Mitigation Structure | 124.2867 | 8.4376 | 144750000 | 137480516.6 | 2023 | ME 3 CONSTRUCTION | 8396 | 2022 | 2023-07-05 | 03/30/2022 | 7269483.4 | 0 | 2023-07-04 |  | 1
2022 | Region V | CATANDUANES | BAGAMANOC (CATANDUANES) | P00631436LZ | Construction of Flood Mitigation Structure | 124.2868 | 13.9517 | 48998758.78 | 48995422.15 | 2022 | AL-JON CONSTRUCTION DEVELOPMENT, INC. (FORMERLY: ALJON CONSTRUCTION & SUPPLY) | 8397 | 2022 | 2022-12-19 | 03/02/2022 | 3336.63 | 0 | 2023-01-19 | 31
2022 | Region V | CATANDUANES | BAGAMANOC (CATANDUANES) | P00631438LZ | Construction of Flood Mitigation Structure | 124.2868 | 13.9517 | 9798755.02 | 9793940.02 | 2022 | NIDA BUILDER'S & SUPPLIES | 8398 | 2022 | 2022-10-26 | 03/02/2022 | 4815 | 0 | 2022-10-25 |  | 1
2022 | Region X | MISAMIS ORIENTAL | NAAWAN (MISAMIS ORIENTAL) | P00632313MN | Construction of Flood Mitigation Structure | 124.2872 | 8.4386 | 144750000 | 137503763.4 | 2023 | TRIPARCO DEVELOPMENT CORPORATION | 8399 | 2022 | 2023-07-08 | 03/30/2022 | 7246236.6 | 0 | 2023-07-07 |  | 1
2023 | Region X | MISAMIS ORIENTAL | MANTICAO (MISAMIS ORIENTAL) | P00734372MN | Construction of Flood Mitigation Structure | 124.2883 | 8.4068 | 198000000 | 129000000 | 2024 | PYRAMID CONSOLIDATED BUILDERS & GEN. MDSE. / FFJJ CONSTRUCTION | 8400 | 2023 | 2024-04-17 | 04/11/2023 | 69000000 | 0 | 2024-04-16 |  | 1
2023 | Region VII | BOHOL | SIERRA BULLONES (BOHOL) | P00721902VS | Construction of Flood Mitigation Structure | 124.2907 | 9.8056 | 77200000 | 77199999.91 | 2024 | ZLREJ TRADING AND CONSTRUCTION CORPORATION / GICAR CONSTRUCTION, INC. | 8401 | 2023 | 2024-08-22 | 04/27/2023 | 0.09 | 0 | 2024-04-21 |  | 123
2023 | Region VII | BOHOL | SIERRA BULLONES (BOHOL) | P00733703VS | Construction of Flood Mitigation Structure | 124.2908 | 9.8051 | 96500000 | 98999836.9 | 2024 | CLAIRE CONSTRUCTION AND SUPPLY CORPORATION / MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY | 8402 | 2023 | 2024-04-15 | 04/25/2023 | 0 | 2499836.9 | 2024-05-14 | 29
2022 | Region X | MISAMIS ORIENTAL | NAAWAN (MISAMIS ORIENTAL) | P00632316MN | Construction of Flood Mitigation Structure | 124.2914 | 8.4367 | 144750000 | 137497779.3 | 2023 | EQUI-PARCO CONSTRUCTION COMPANY | 8403 | 2022 | 2023-07-08 | 03/30/2022 | 7252220.7 | 0 | 2023-07-07 |  | 1
2022 | Region X | MISAMIS ORIENTAL | NAAWAN (MISAMIS ORIENTAL) | P00632314MN | Construction of Flood Mitigation Structure | 124.2917 | 8.4372 | 144750000 | 137507127.9 | 2023 | NORTHERN BUILDERS | 8404 | 2022 | 2023-07-08 | 03/30/2022 | 7242872.1 | 0 | 2023-07-07 |  | 1
2023 | Region VII | BOHOL | DAGOHOY (BOHOL) | P00721815VS | Construction of Flood Mitigation Structure | 124.292 | 9.9086 | 19600000 | 19599982.18 | 2023 | LABB CONSTRUCTION DEVELOPMENT INC. (FORMERLY: LABB CONSTRUCTION) | 8405 | 2023 | 2023-09-10 | 02/21/2023 | 17.82 | 0 | 2023-09-07 |  | 3
2023 | Region X | MISAMIS ORIENTAL | MANTICAO (MISAMIS ORIENTAL) | P00734389MN | Construction of Flood Mitigation Structure | 124.2924 | 8.4061 | 4950000 | 4950000 | 2023 | H & N BUILDERS & ENTERPRISES | 8406 | 2023 | 2023-07-29 | 03/28/2023 | 0 | 0 | 2023-07-28 |  | 1
2024 | Region X | MISAMIS ORIENTAL | MANTICAO (MISAMIS ORIENTAL) | P00820267MN | Construction of Flood Mitigation Structure | 124.293 | 8.4062 | 95264800 | 95264800 | 2024 | ROAD EDGE TRADING & DEVELOPMENT SERVICES | 8407 | 2024 | 2024-11-18 | 02/05/2024 | 0 | 0 | 2025-01-15 | 58
2022 | Region X | MISAMIS ORIENTAL | NAAWAN (MISAMIS ORIENTAL) | P00632317MN | Construction of Flood Mitigation Structure | 124.2944 | 8.4349 | 144750000 | 137501620.1 | 2023 | EQUI-PARCO CONSTRUCTION COMPANY | 8408 | 2022 | 2023-07-17 | 05/23/2022 | 7248379.9 | 0 | 2023-07-16 |  | 1
2022 | Region X | MISAMIS ORIENTAL | NAAWAN (MISAMIS ORIENTAL) | P00632315MN | Construction of Flood Mitigation Structure | 124.2949 | 8.4357 | 144750000 | 137507828.5 | 2023 | NORTHERN BUILDERS | 8409 | 2022 | 2023-07-08 | 03/30/2022 | 7242171.5 | 0 | 2023-07-07 |  | 1
2022 | Region VII | BOHOL | DAGOHOY (BOHOL) | P00620035VS | Construction of Flood Mitigation Structure | 124.2951 | 9.9088 | 96500000 | 96500000 | 2023 | LABB CONSTRUCTION DEVELOPMENT INC. (FORMERLY: LABB CONSTRUCTION) | 8410 | 2022 | 2023-07-23 | 04/06/2022 | 0 | 0 | 2023-05-29 |  | 55
2023 | Region V | CATANDUANES | BATO (CATANDUANES) | P00742479LZ | Construction of Flood Mitigation Structure | 124.2951 | 13.6093 | 9899996.06 | 9899996.06 | 2024 | HI-DENSITY INTERNATIONAL CONSTRUCTION AND DEVELOPMENT INC. | 8411 | 2023 | 2024-01-29 | 09/22/2023 | 0 | 0 | 2024-01-28 |  | 1
2022 | Region V | CATANDUANES | PANGANIBAN (PAYO) (CATANDUANES) | P00631452LZ | Construction of Flood Mitigation Structure | 124.2957 | 13.9083 | 29400000 | 29398959.54 | 2022 | MS2 BUILDER AND SUPPLIES INC. | 8412 | 2022 | 2022-09-03 | 03/02/2022 | 1040.46 | 0 | 2022-09-05 | 2
2022 | Region V | CATANDUANES | PANGANIBAN (PAYO) (CATANDUANES) | P00631451LZ | Construction of Flood Mitigation Structure | 124.2959 | 13.9056 | 29399999.73 | 29398959.94 | 2022 | EMSYM CONSTRUCTION CORP. | 8413 | 2022 | 2022-10-31 | 03/22/2022 | 1039.79 | 0 | 2022-11-02 | 2
2022 | Region V | CATANDUANES | BATO (CATANDUANES) | P00631437LZ | Construction of Flood Mitigation Structure | 124.298 | 13.6073 | 49000000 | 48998760 | 2022 | A.V. LAYNES TRADING AND CONSTRUCTION | 8414 | 2022 | 2022-10-19 | 03/02/2022 | 1240 | 0 | 2022-11-11 | 23
2024 | Region VII | BOHOL | GARCIA HERNANDEZ (BOHOL) | P00834980VS | Construction of Flood Mitigation Structure | 124.2994 | 9.6629 | 99000000 | 98944930.25 | 2025 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY | 8415 | 2024 | 2025-03-05 | 04/12/2024 | 55069.75 | 0 | 2025-05-19 | 75
2023 | Region VII | BOHOL | GARCIA HERNANDEZ (BOHOL) | P00721782VS | Rehabilitation / Major Repair of Flood Control Structure | 124.3002 | 9.6158 | 86850000 | 86849987.16 | 2023 | FUENTABUILT CONSTRUCTION CORP. / M.R. VARGAS CONSTRUCTION CORPORATION (FORMERLY: M.R. VARGAS CONSTRUCTION) | 8416 | 2023 | 2023-12-18 | 02/24/2023 | 12.84 | 0 | 2023-12-17 |  | 1
2022 | Region VIII | NORTHERN SAMAR | VICTORIA (NORTHERN SAMAR) | P00620203VS | Construction of Flood Mitigation Structure | 124.3004 | 12.4577 | 48999518.03 | 48044665.17 | 2022 | RNMK CONSTRUCTION, SUPPLY AND DEVELOPMENT CORP. (FOR: RNMK CONST. & DEV'T) / CDU CONSTRUCTION | 8417 | 2022 | 2022-10-10 | 02/21/2022 | 954852.86 | 0 | 2022-10-23 | 13
2023 | Region VII | BOHOL | GARCIA HERNANDEZ (BOHOL) | P00721783VS | Rehabilitation / Major Repair of Flood Control Structure | 124.3005 | 9.6158 | 86850000 | 86848873.54 | 2023 | JAS MIXER CONSTRUCTION AND DEVELOPMENT CORPORATION / M.R. VARGAS CONSTRUCTION CORPORATION (FORMERLY: M.R. VARGAS CONSTRUCTION) | 8418 | 2023 | 2023-12-18 | 02/24/2023 | 1126.46 | 0 | 2023-12-17 |  | 1
2023 | Region V | CATANDUANES | BATO (CATANDUANES) | P00737569LZ | Construction of Flood Mitigation Structure | 124.3007 | 13.632 | 4949997.56 | 4807350.58 | 2023 | NVR CONSTRUCTION | 8419 | 2023 | 2023-05-14 | 02/17/2023 | 142646.98 | 0 | 2023-05-13 |  | 1
2023 | Region VII | BOHOL | GARCIA HERNANDEZ (BOHOL) | P00745641VS | Rehabilitation / Major Repair of Flood Control Structure | 124.3009 | 9.6182 | 96300245 | 96300240.26 | 2024 | KMCM BUILDERS AND DEVELOPMENT CORPORATION / GICAR CONSTRUCTION, INC. | 8420 | 2023 | 2024-02-20 | 08/10/2023 | 4.74 | 0 | 2024-06-17 | 118
2024 | Region VII | CEBU | SAN FRANCISCO (CEBU) | P00835010VS | Construction of Flood Mitigation Structure | 124.305 | 10.59 | 4950000 | 4945000 | 2024 | BARR STEEL CONSTRUCTION | 8421 | 2024 | 2024-11-09 | 08/12/2024 | 5000 | 0 | 2024-11-08 |  | 1
2024 | Region VII | BOHOL | GARCIA HERNANDEZ (BOHOL) | P00834599VS | Construction of Flood Mitigation Structure | 124.3085 | 9.6171 | 57900000 | 57877936 | 2025 | MOG CONSTRUCTION INC. / N.N. YU CONSTRUCTION, INC. (FORMERLY: YU CONSTRUCTION) | 8422 | 2024 | 2025-03-06 | 05/28/2024 | 22064 | 0 | 2025-03-29 | 23
2021 | Region XII | MAGUINDANAO DEL NORTE |  | P00522326MN | Construction of Flood Mitigation Structure | 124.3092 | 7.1403 | 96490689.91 | 96499999.09 | 2023 | GEMMA CONSTRUCTION SUPPLY, INC.(FORMERLY:GEMMA CON | 8423 | 2021 | 2023-01-02 | 03/08/2022 | 0 | 9309.18 | 2023-03-31 | 88
2022 | Region V | CATANDUANES | BATO (CATANDUANES) | P00620731LZ | Construction of Flood Mitigation Structure | 124.3114 | 13.5891 | 44100000 | 44092985.45 | 2023 | E.R. RODRIGUEZ CONSTRUCTION CORPORATION (FORMERLY: E.R. RODRIGUEZ CONSTRUCTION) | 8424 | 2022 | 2023-09-05 | 03/02/2022 | 7014.55 | 0 | 2023-08-28 |  | 8
2024 | Region X | LANAO DEL NORTE | ILIGAN CITY (LANAO DEL NORTE) | P00820909MN | Construction of Flood Mitigation Structure | 124.3149 | 8.2402 | 9800000 | 9650000 | 2024 | THE HUANG BUILDERS INC. | 8425 | 2024 | 2024-09-04 | 05/27/2024 | 150000 | 0 | 2024-09-03 |  | 1
2024 | Region X | LANAO DEL NORTE | ILIGAN CITY (LANAO DEL NORTE) | P00820282MN | Construction of Flood Mitigation Structure | 124.3166 | 8.253 | 77200000 | 77198185.6 | 2024 | VICTORIANO C. LIM CONSTRUCTION CORPORATION (FORMERLY: VICTORIANO C. LIM CONSTRUCTION) | 8426 | 2024 | 2024-09-20 | 03/19/2024 | 1814.4 | 0 | 2024-12-28 | 99
2023 | Region V | CATANDUANES | BATO (CATANDUANES) | P00737572LZ | Construction of Dike | 124.3195 | 13.6163 | 4950000 | 4948753.5 | 2023 | TNB BUILDERS | 8427 | 2023 | 2023-06-13 | 02/17/2023 | 1246.5 | 0 | 2023-06-12 |  | 1
2022 | Region X | LANAO DEL NORTE | ILIGAN CITY (LANAO DEL NORTE) | P00630582MN | Construction of Flood Mitigation Structure | 124.3218 | 8.2438 | 49000000 | 49000000 | 2022 | GRACE CONSTRUCTION CORPORATION | 8428 | 2022 | 2022-10-22 | 03/24/2022 | 0 | 0 | 2022-10-21 |  | 1
2024 | Region X | LANAO DEL NORTE | ILIGAN CITY (LANAO DEL NORTE) | P00820152MN | Construction of Flood Mitigation Structure | 124.3231 | 8.2317 | 12250000 | 12250000 | 2024 | ALFAHAD BUILDERS AND ENTERPRISES | 8429 | 2024 | 2024-05-31 | 01/30/2024 | 0 | 0 | 2024-05-31 | 0
2024 | Region VII | BOHOL | PILAR (BOHOL) | P00821149VS | Construction of Flood Mitigation Structure | 124.3264 | 9.8084 | 130509495 | 130419495 | 2024 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY | 8430 | 2024 | 2024-08-15 | 03/05/2024 | 90000 | 0 | 2025-01-30 | 168
2023 | Region VIII | NORTHERN SAMAR | LAVEZARES (NORTHERN SAMAR) | P00733758VS | Construction of Flood Mitigation Structure | 124.3308 | 12.5358 | 9899577.08 | 9895774.56 | 2023 | CALIFORNIAROCK CONSTRUCTION | 8431 | 2023 | 2023-10-15 | 06/20/2023 | 3802.52 | 0 | 2023-10-14 |  | 1
2022 | Region X | LANAO DEL SUR | MARAWI CITY (CAPITAL) (LANAO DEL SUR) | P00631073MN | Construction of Drainage Structure | 124.3347 | 8.0031 | 9900000 | 9602355.78 | 2022 | TJB CONSTRUCTION | 8432 | 2022 | 2022-12-12 | 07/15/2022 | 297644.22 | 0 | 2022-12-09 |  | 3
2022 | Region X | LANAO DEL SUR | DITSAAN-RAMAIN (LANAO DEL SUR) | P00631074MN | Construction of Drainage Structure | 124.3376 | 8.0056 | 6930000 | 6720593.89 | 2022 | TJB CONSTRUCTION | 8433 | 2022 | 2022-12-12 | 07/25/2022 | 209406.11 | 0 | 2022-12-05 |  | 7
2023 | Region VII | BOHOL | SAN MIGUEL (BOHOL) | P00721813VS | Construction of Flood Mitigation Structure | 124.3382 | 9.9812 | 49000000 | 48999999.81 | 2023 | LEDA CONSTRUCTION INCORPORATED | 8434 | 2023 | 2023-12-27 | 02/21/2023 | 0.19 | 0 | 2023-12-26 |  | 1
2023 | Region X | LANAO DEL SUR | DITSAAN-RAMAIN (LANAO DEL SUR) | P00721665MN | Construction of Flood Mitigation Structure | 124.3435 | 7.985 | 115800000 | 114640737.1 | 2024 | M.M.A. ACHIEVER CONSTRUCTION & DEVELOPMENT CORP. | 8435 | 2023 | 2024-03-23 | 05/29/2023 | 1159262.9 | 0 | 2024-03-22 |  | 1
2021 | Region VIII | SOUTHERN LEYTE |  | P00549879VS | Construction of Slope Protection Structure | 124.8464 | 10.1317 | 96500000 | 96500000 | 2022 | A.C. RIVERO DEVELOPMENT CORPORATION | 8436 | 2021 | 2022-12-06 | 11/22/2021 | 0 | 0 | 2022-12-05 |  | 1
2024 | Region X | BUKIDNON | IMPASUG-ONG (BUKIDNON) | P00820030MN | Construction of Flood Mitigation Structure | 125.0119 | 8.3059 | 96500000 | 96500000 | 2025 | ROSBILL CONSTRUCTION AND SUPPLY | 8437 | 2024 | 2025-03-21 | 01/31/2024 | 0 | 0 | 2025-03-20 |  | 1
2023 | Region VIII | LEYTE | TACLOBAN CITY (CAPITAL) (LEYTE) | P00721598VS | Construction of Revetment | 124.9465 | 11.3389 | 55481515.98 | 55361832.97 | 2024 | SAMARINAN CONSTRUCTION AND DEVELOPMENT CORPORATION (FORMERLY: SAMARINAN CONSTRUCTION) | 8438 | 2023 | 2024-01-05 | 03/23/2023 | 119683.01 | 0 | 2024-01-04 |  | 1
2023 | Region VII | BOHOL | UBAY (BOHOL) | P00721667VS | Construction of Flood Mitigation Structure | 124.5686 | 9.9755 | 49000000 | 48999999.44 | 2024 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R | 8439 | 2023 | 2024-03-02 | 03/29/2023 | 0.56 | 0 | 2024-01-31 |  | 31
2023 | Region VIII | LEYTE | ALBUERA (LEYTE) | P00733319VS | Construction of Flood Mitigation Structure | 124.7028 | 10.9013 | 29400000 | 28900007.47 | 2023 | AICON INDUSTRIES | 8440 | 2023 | 2023-07-20 | 04/26/2023 | 499992.53 | 0 | 2023-10-21 | 93
2023 | Region VIII | BILIRAN | MARIPIPI (BILIRAN) | P00732038VS | Construction of Flood Mitigation Structure | 124.3479 | 11.808 | 4945926.72 | 4802990.4 | 2023 | INFRASERVE BUILDERS AND SUPPLIES | 8441 | 2023 | 2023-04-20 | 03/01/2023 | 142936.32 | 0 | 2023-05-13 | 23
2023 | Region VIII | LEYTE | BABATNGON (LEYTE) | P00721710VS | Construction of Flood Mitigation Structure | 124.8475 | 11.4109 | 49000000 | 48899539.72 | 2023 | FAIRCHILD BUILDERS & DEVELOPERS, INC. / GO_SOLID BUILDERS INC. | 8442 | 2023 | 2023-12-12 | 03/28/2023 | 100460.28 | 0 | 2023-12-11 |  | 1
2024 | Region XII | SULTAN KUDARAT | ISULAN (CAPITAL) (SULTAN KUDARAT) | P00820419MN | Construction of Flood Mitigation Structure | 124.5721 | 6.6463 | 45010131.39 | 44954629.65 | 2024 | ROBETH CONST. AND DEV'T. CORP. (FORMERLY: ROBETH GEN. MDSE. CONST. & SUPPLY) | 8443 | 2024 | 2024-06-10 | 02/15/2024 | 55501.74 | 0 | 2024-08-26 | 77
2023 | Region X | CAMIGUIN | MAMBAJAO (CAPITAL) (CAMIGUIN) | P00721375MN | Construction of Flood Mitigation Structure | 124.7033 | 9.2452 | 49292188.72 | 48771663.88 | 2023 | SHEEN-SHEEN CONSTRUCTION CORPORATION (FORMERLY: SHEEN-SHEEN CONSTRUCTION) | 8444 | 2023 | 2023-10-29 | 02/27/2023 | 520524.84 | 0 | 2023-10-29 | 0
2022 | Region X | BUKIDNON | MARAMAG (BUKIDNON) | P00630572MN | Construction of Revetment | 125.0133 | 7.7187 | 39200000 | 39200000 | 2023 | PYRAMID CONSOLIDATED BUILDERS & GEN. MDSE. | 8445 | 2022 | 2023-02-01 | 02/07/2022 | 0 | 0 | 2023-01-31 |  | 1
2023 | Region VIII | BILIRAN | MARIPIPI (BILIRAN) | P00732039VS | Construction of Flood Mitigation Structure | 124.3489 | 11.7769 | 4945855.94 | 4946975.56 | 2023 | M.B. ANG CONSTRUCTION & SUPPLY | 8446 | 2023 | 2023-08-15 | 02/27/2023 | 0 | 1119.62 | 2023-08-14 |  | 1
2022 | Region VIII | SOUTHERN LEYTE | BONTOC (SOUTHERN LEYTE) | P00620062VS | Construction of Flood Mitigation Structure | 124.9471 | 10.3552 | 48777855 | 48743543.85 | 2023 | ST. MATTHEW GEN. CONTRACTOR & DEVELOPMENT CORP. | 8447 | 2022 | 2023-07-19 | 02/22/2022 | 34311.15 | 0 | 2023-07-18 |  | 1
2024 | Region XII | SULTAN KUDARAT | ISULAN (CAPITAL) (SULTAN KUDARAT) | P00820420MN | Construction of Flood Mitigation Structure | 124.5724 | 6.6552 | 45008654.58 | 44953154.08 | 2024 | ROBETH CONST. AND DEV'T. CORP. (FORMERLY: ROBETH GEN. MDSE. CONST. & SUPPLY) | 8448 | 2024 | 2024-06-28 | 02/15/2024 | 55500.5 | 0 | 2024-08-26 | 59
2024 | Region VIII | NORTHERN SAMAR | SAN ROQUE (NORTHERN SAMAR) | P00820250VS | Rehabilitation / Major Repair of Flood Control Structure | 124.8486 | 12.528 | 48999978.1 | 48982964.54 | 2025 | JCL CONSTRUCTION AND SUPPLY | 8449 | 2024 | 2025-03-03 | 06/07/2024 | 17013.56 | 0 | 2025-03-02 |  | 1
2022 | Region X | CAMIGUIN | CATARMAN (CAMIGUIN) | P00630576MN | Construction of Flood Mitigation Structure | 124.7046 | 9.1472 | 4949999.73 | 4702476.58 | 2022 | R AND L BUILDERS AND CONSTRUCTION SUPPLY CORP. | 8450 | 2022 | 2022-08-16 | 03/17/2022 | 247523.15 | 0 | 2022-06-08 |  | 69
2022 | Region VIII | LEYTE | TOLOSA (LEYTE) | P00620415VS | Construction of Flood Mitigation Structure | 125.0133 | 11.0498 | 24500000 | 24435006.02 | 2022 | XDR CONSTRUCTION AND SUPPLY | 8451 | 2022 | 2022-10-06 | 05/16/2022 | 64993.98 | 0 | 2022-10-30 | 24
2022 | Region V | CATANDUANES | BARAS (CATANDUANES) | P00631445LZ | Construction of Flood Mitigation Structure | 124.3492 | 13.65 | 19299817.24 | 19300000 | 2022 | E.R. RODRIGUEZ CONSTRUCTION CORPORATION (FORMERLY: E.R. RODRIGUEZ CONSTRUCTION) | 8452 | 2022 | 2022-11-07 | 04/08/2022 | 0 | 182.76 | 2022-11-08 | 1
2024 | Region VIII | LEYTE | TANAUAN (LEYTE) | P00820228VS | Construction of Flood Mitigation Structure | 124.9472 | 11.0824 | 19600000 | 19403992.94 | 2024 | ROCKWORLD INDUSTRIES | 8453 | 2024 | 2024-05-20 | 03/18/2024 | 196007.06 | 0 | 2024-08-26 | 98
2023 | Region XII | SOUTH COTABATO | CITY OF KORONADAL (CAPITAL) (SOUTH COTABATO) | P00721391MN | Construction of Flood Mitigation Structure | 124.8488 | 6.4956 | 39200000 | 24499823.52 | 2023 | BETTER WORK CONSTRUCTION / MANUELA CONSTRUCTION SERVICES | 8454 | 2023 | 2023-08-18 | 04/17/2023 | 14700176.48 | 0 | 2023-08-19 | 1
2022 | Region XII | SULTAN KUDARAT | ISULAN (CAPITAL) (SULTAN KUDARAT) | P00620285MN | Construction of Flood Mitigation Structure | 124.5729 | 6.6516 | 48991147.6 | 48999100.07 | 2022 | CS CONST. AND SUPPLY INC. (FORMERLY: CS CONSTRUCTION AND SUPPLY) | 8455 | 2022 | 2022-12-19 | 02/22/2022 | 0 | 7952.47 | 2023-01-02 | 14
2024 | Region X | MISAMIS ORIENTAL | MEDINA (MISAMIS ORIENTAL) | P00820256MN | Construction of Flood Mitigation Structure | 125.014 | 8.9168 | 120625000 | 120623720 | 2024 | ROAD EDGE TRADING & DEVELOPMENT SERVICES | 8456 | 2024 | 2024-09-24 | 02/12/2024 | 1280 | 0 | 2024-11-03 | 40
2023 | Region VIII | LEYTE | TACLOBAN CITY (CAPITAL) (LEYTE) | P00733326VS | Construction of Revetment | 124.9473 | 11.32 | 48999257.25 | 48606003.37 | 2023 | JGO BUILDERS | 8457 | 2023 | 2023-10-30 | 03/23/2023 | 393253.88 | 0 | 2023-10-29 |  | 1
2022 | Region VIII | BILIRAN | MARIPIPI (BILIRAN) | P00630667VS | Construction of Flood Mitigation Structure | 124.3493 | 11.7774 | 4945318.21 | 4732669.5 | 2022 | M.B. ANG CONSTRUCTION & SUPPLY | 8458 | 2022 | 2022-12-16 | 02/21/2022 | 212648.71 | 0 | 2022-12-15 |  | 1
2024 | Region XII | SOUTH COTABATO | BANGA (SOUTH COTABATO) | P00836194MN | Construction of Flood Mitigation Structure | 124.8504 | 6.3243 | 4950000 | 4949990.19 | 2024 | MR-B CONSTRUCTION SERVICES | 8459 | 2024 | 2024-08-22 | 05/10/2024 | 9.81 | 0 | 2024-08-21 |  | 1
2024 | Region XII | SULTAN KUDARAT | ISULAN (CAPITAL) (SULTAN KUDARAT) | P00820921MN | Construction of Flood Mitigation Structure | 124.5729 | 6.6516 | 48248454.28 | 47943654.07 | 2024 | KANAWAY BUILDERS CORPORATION | 8460 | 2024 | 2024-11-22 | 05/08/2024 | 304800.21 | 0 | 2024-11-26 | 4
2024 | Region X | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY (CAPITAL) (MISAMIS ORIENTAL) | P00820262MN | Construction of Flood Mitigation Structure | 124.576 | 8.4473 | 149575000 | 146125204.5 | 2025 | EQUI-PARCO CONSTRUCTION COMPANY | 8461 | 2024 | 2025-01-30 | 05/03/2024 | 3449795.5 | 0 | 2025-05-26 | 116
2021 | Region VIII | LEYTE |  | P00549893VS | Construction of Flood Mitigation Structure | 124.948 | 11.3176 | 34648502.55 | 33609332.12 | 2022 | KAUIE BUILDERS & SUPPLIES INC. (FORMERLY: KAUIE BUILDERS AND CONSTRUCTION SUPPLIES) | 8462 | 2021 | 2022-07-01 | 04/23/2021 | 1039170.43 | 0 | 2022-06-30 |  | 1
2023 | Region X | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY (CAPITAL) (MISAMIS ORIENTAL) | P00734387MN | Construction of Flood Mitigation Structure | 124.7055 | 8.4728 | 34650000 | 33611633.73 | 2023 | ALEBON GENUINE MERCHANDISING INCORPORATED | 8463 | 2023 | 2023-11-10 | 04/01/2023 | 1038366.27 | 0 | 2023-11-09 |  | 1
2024 | Region X | MISAMIS ORIENTAL | LIBERTAD (MISAMIS ORIENTAL) | P00835877MN | Construction of Flood Mitigation Structure | 124.3497 | 8.561 | 9800000 | 9800000 | 2024 | RBT VENTURES | 8464 | 2024 | 2024-10-06 | 02/29/2024 | 0 | 0 | 2024-10-05 |  | 1
2022 | Region XII | SOUTH COTABATO | CITY OF KORONADAL (CAPITAL) (SOUTH COTABATO) | P00620187MN | Construction of Flood Mitigation Structure | 124.8508 | 6.5017 | 58800000 | 29397132.27 | 2022 | BETTER WORK CONSTRUCTION | 8465 | 2022 | 2022-09-03 | 03/02/2022 | 29402867.73 | 0 | 2022-08-06 |  | 28
2023 | Region V | CATANDUANES | BARAS (CATANDUANES) | P00727222LZ | Construction of Flood Mitigation Structure | 124.3501 | 13.6517 | 49000000 | 48998497.98 | 2023 | A.V. LAYNES TRADING AND CONSTRUCTION | 8466 | 2023 | 2023-09-08 | 03/17/2023 | 1502.02 | 0 | 2023-09-29 | 21
2024 | Region VIII | LEYTE | KANANGA (LEYTE) | P00820239VS | Construction of Flood Mitigation Structure | 124.5779 | 11.1368 | 4900000 | 4850996.77 | 2024 | CIRCLE Z VENTURES & DEVELOPMENT CORP. | 8467 | 2024 | 2024-05-19 | 02/20/2024 | 49003.23 | 0 | 2024-05-18 |  | 1
2022 | Region VIII | LEYTE | TANAUAN (LEYTE) | P00620053VS | Construction of Flood Mitigation Structure | 125.0141 | 11.1293 | 30879711.2 | 30407316 | 2022 | MAMSAR CONSTRUCTION AND INDUSTRIAL CORPORATION | 8468 | 2022 | 2022-09-16 | 03/07/2022 | 472395.2 | 0 | 2022-09-15 |  | 1
2023 | Region X | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY (CAPITAL) (MISAMIS ORIENTAL) | P00734020MN | Construction of Flood Mitigation Structure | 124.7055 | 8.4728 | 9900000 | 9603918.56 | 2023 | ALL WEATHER CONSTRUCTION | 8469 | 2023 | 2023-11-20 | 04/14/2023 | 296081.44 | 0 | 2023-07-24 |  | 119
2024 | Region VIII | LEYTE | TOLOSA (LEYTE) | P00832677VS | Construction of Drainage Structure | 124.9489 | 11.1964 | 9900000 | 9881420.87 | 2024 | G.O.C. BUILDERS | 8470 | 2024 | 2024-08-16 | 02/22/2024 | 18579.13 | 0 | 2024-08-15 |  | 1
2023 | Region VIII | SOUTHERN LEYTE | CITY OF MAASIN (CAPITAL) (SOUTHERN LEYTE) | P00721972VS | Construction of Flood Mitigation Structure | 124.8535 | 10.1367 | 49000000 | 49000000 | 2023 | JQD CONSTRUCTION & GENERAL SERVICES | 8471 | 2023 | 2023-12-03 | 02/24/2023 | 0 | 0 | 2023-12-02 |  | 1
2022 | Region X | LANAO DEL SUR | DITSAAN-RAMAIN (LANAO DEL SUR) | P00634130MN | Construction of Drainage Structure | 124.3526 | 7.9709 | 9900000 | 9602479.28 | 2023 | TJB CONSTRUCTION | 8472 | 2022 | 2023-01-09 | 08/08/2022 | 297520.72 | 0 | 2023-01-01 |  | 8
2023 | Region X | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY (CAPITAL) (MISAMIS ORIENTAL) | P00721640MN | Construction of Flood Mitigation Structure | 124.5786 | 8.4606 | 72375000 | 71255247.92 | 2023 | PYRAMID CONSOLIDATED BUILDERS & GEN. MDSE. | 8473 | 2023 | 2023-11-28 | 03/16/2023 | 1119752.08 | 0 | 2024-02-16 | 80
2022 | Region VIII | LEYTE | TOLOSA (LEYTE) | P00620414VS | Construction of Flood Mitigation Structure | 125.0152 | 11.0559 | 24500000 | 24435002.77 | 2022 | XDR CONSTRUCTION AND SUPPLY | 8474 | 2022 | 2022-10-06 | 05/20/2022 | 64997.23 | 0 | 2022-11-03 | 28
2023 | Region VIII | LEYTE | TACLOBAN CITY (CAPITAL) (LEYTE) | P00721914VS | Construction of Revetment | 124.9493 | 11.3199 | 55485794.03 | 55285766.28 | 2024 | EZJONES CONSTRUCTION INC. | 8475 | 2023 | 2024-03-24 | 03/23/2023 | 200027.75 | 0 | 2024-03-28 | 4
2024 | Region X | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY (CAPITAL) (MISAMIS ORIENTAL) | P00821079MN | Construction of Flood Mitigation Structure | 124.7059 | 8.4713 | 49000000 | 47530417.08 | 2024 | ERS CONSTRUCTION / VICTORIANO C. LIM CONSTRUCTION CORPORATION (FORMERLY: VICTORIANO C. LIM CONSTRUCTION) | 8476 | 2024 | 2024-10-24 | 02/29/2024 | 1469582.92 | 0 | 2024-10-30 | 6
2022 | Region VIII | SAMAR (WESTERN SAMAR) | CALBAYOG CITY (SAMAR (WESTERN SAMAR)) | P00620060VS | Construction of Flood Mitigation Structure | 124.5788 | 12.1843 | 94570000 | 93928535.96 | 2024 | JFR CONSTRUCTION INC. (FORMERLY:JFR CONSTRUCTION) | 8477 | 2022 | 2024-04-22 | 03/04/2022 | 641464.04 | 0 | 2024-04-21 |  | 1
2022 | Region XII | COTABATO (NORTH COTABATO) | MATALAM (COTABATO (NORTH COTABATO)) | P00620279MN | Construction of Revetment | 124.9494 | 7.1421 | 48250000 | 46723426.11 | 2023 | JARGON CONSTRUCTION & SUPPLY | 8478 | 2022 | 2023-01-27 | 03/15/2022 | 1526573.89 | 0 | 2023-02-24 | 28
2023 | Region VII | BOHOL | SAN MIGUEL (BOHOL) | P00721814VS | Construction of Flood Mitigation Structure | 124.3532 | 10.0061 | 19600000 | 19599984.54 | 2023 | RL EARTH HAULING & EQUIPMENT SERVICES INC. | 8479 | 2023 | 2023-09-18 | 02/21/2023 | 15.46 | 0 | 2023-10-01 | 13
2022 | Region VIII | LEYTE | TANAUAN (LEYTE) | P00620327VS | Construction of Flood Mitigation Structure | 125.0153 | 11.5086 | 44100000 | 44099637.41 | 2022 | 888 ACY ENTERPRISES / JGO BUILDERS | 8480 | 2022 | 2022-11-21 | 03/13/2022 | 362.59 | 0 | 2022-11-20 |  | 1
2023 | Region X | LANAO DEL SUR | AMAI MANABILANG (LANAO DEL SUR) | P00721269MN | Construction of Flood Mitigation Structure | 124.7062 | 7.7552 | 48250000 | 47767418.63 | 2023 | M.M.A. ACHIEVER CONSTRUCTION & DEVELOPMENT CORP. | 8481 | 2023 | 2023-11-30 | 04/11/2023 | 482581.37 | 0 | 2023-11-29 |  | 1
2022 | Region VIII | LEYTE | TANAUAN (LEYTE) | P00620054VS | Construction of Flood Mitigation Structure | 125.0156 | 11.1274 | 17369381.06 | 17369031.34 | 2022 | JELM CONSTRUCTION CORP. / RT BUILDERS | 8482 | 2022 | 2022-08-18 | 03/07/2022 | 349.72 | 0 | 2022-08-17 |  | 1
2022 | Region VIII | LEYTE | TANAUAN (LEYTE) | P00620329VS | Construction of Flood Mitigation Structure | 124.9532 | 11.0765 | 48020000 | 48020000 | 2022 | LEDA CONSTRUCTION INCORPORATED | 8483 | 2022 | 2022-10-25 | 02/11/2022 | 0 | 0 | 2022-10-24 |  | 1
2022 | Region VIII | SAMAR (WESTERN SAMAR) | CALBAYOG CITY (SAMAR (WESTERN SAMAR)) | P00620211VS | Construction of Flood Mitigation Structure | 124.5792 | 12.1869 | 49000000 | 48610274.66 | 2024 | RNMK CONSTRUCTION, SUPPLY AND DEVELOPMENT CORP. (FOR: RNMK CONST. & DEV'T) | 8484 | 2022 | 2024-04-22 | 02/08/2022 | 389725.34 | 0 | 2024-05-07 | 15
2022 | Region VIII | SOUTHERN LEYTE | CITY OF MAASIN (CAPITAL) (SOUTHERN LEYTE) | P00632046VS | Construction of Flood Mitigation Structure | 124.8536 | 10.137 | 24750000 | 24715027.7 | 2023 | JQD CONSTRUCTION & GENERAL SERVICES | 8485 | 2022 | 2023-01-25 | 04/06/2022 | 34972.3 | 0 | 2023-01-24 |  | 1
2022 | Region VIII | BILIRAN | ALMERIA (BILIRAN) | P00633234VS | Construction of Flood Mitigation Structure | 124.3659 | 11.6366 | 4943652.05 | 4945511.65 | 2022 | INFRASERVE BUILDERS AND SUPPLIES | 8486 | 2022 | 2022-08-10 | 03/29/2022 | 0 | 1859.6 | 2022-06-10 |  | 61
2020 | Region VIII | LEYTE |  | P00420371VS | Construction of Dike | 125.0159 | 11.1209 | 192799217.9 | 94979372.12 | 2022 | L.N.R. CONSTRUCTION / SUNWEST, INC. (FORMERLY: SUNWEST CONSTRUCTION & DEVELOPMENT CORPORATION) | 8487 | 2020 | 2022-10-25 | 12/03/2020 | 97819845.78 | 0 | 2022-11-07 | 13
2022 | Region VIII | BILIRAN | CAIBIRAN (BILIRAN) | P00630663VS | Construction of Drainage Structure | 124.581 | 11.5698 | 4944999.11 | 4945075.35 | 2022 | MKB BUILDERS AND SUPPLY | 8488 | 2022 | 2022-07-28 | 03/16/2022 | 0 | 76.24 | 2022-07-27 |  | 1
2023 | Region X | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY (CAPITAL) (MISAMIS ORIENTAL) | P00721611MN | Construction of Flood Mitigation Structure | 124.7067 | 8.4698 | 49000000 | 47518988.99 | 2023 | JT GAMOLO CONSTRUCTION, INCORPORATION (FORMERLY:J.T. GAMOLO CONSTRUCTION) | 8489 | 2023 | 2023-10-25 | 03/29/2023 | 1481011.01 | 0 | 2023-11-27 | 33
2024 | Region VIII | NORTHERN SAMAR | LAVEZARES (NORTHERN SAMAR) | P00835028VS | Construction of Flood Mitigation Structure | 124.3661 | 12.5531 | 4949329.89 | 4934326.2 | 2024 | CALIFORNIAROCK CONSTRUCTION | 8490 | 2024 | 2024-07-15 | 04/25/2024 | 15003.69 | 0 | 2024-07-23 | 8
2022 | Region X | MISAMIS ORIENTAL | OPOL (MISAMIS ORIENTAL) | P00630485MN | Construction of Flood Mitigation Structure | 124.5817 | 8.508 | 62725000 | 56703295.7 | 2022 | LYD CONSTRUCTION / RUPLINO SEISMUNDO CONSTRUCTION CORPORATION (FORMERLY: R.R. SEISMUNDO CONSTRUCTION & SUPPLY) | 8491 | 2022 | 2022-10-25 | 03/11/2022 | 6021704.3 | 0 | 2022-10-24 |  | 1
2021 | Region VIII | LEYTE |  | P00420371VS | Construction of Dike | 125.0159 | 11.1209 | 192799217.9 | 94979372.12 | 2022 | L.N.R. CONSTRUCTION / SUNWEST, INC. (FORMERLY: SUNWEST CONSTRUCTION & DEVELOPMENT CORPORATION) | 8492 | 2021 | 2022-10-25 | 12/03/2020 | 97819845.78 | 0 | 2022-11-07 | 13
2023 | Region VIII | SOUTHERN LEYTE | CITY OF MAASIN (CAPITAL) (SOUTHERN LEYTE) | P00733292VS | Construction of Flood Mitigation Structure | 124.8537 | 10.1386 | 67550000 | 67549985.32 | 2024 | ON POINT CONSTRUCTION AND DEVELOPMENT CORPORATION (FORMERLY:ON POINT CONSTRUCTION) / UKC BUILDERS, INC. | 8493 | 2023 | 2024-01-26 | 04/11/2023 | 14.68 | 0 | 2024-01-25 |  | 1
2022 | Region VIII | SOUTHERN LEYTE | CITY OF MAASIN (CAPITAL) (SOUTHERN LEYTE) | P00620225VS | Construction of Flood Mitigation Structure | 124.8537 | 10.1354 | 49000000 | 48938901.35 | 2023 | JQD CONSTRUCTION & GENERAL SERVICES | 8494 | 2022 | 2023-06-04 | 02/10/2022 | 61098.65 | 0 | 2023-06-03 |  | 1
2023 | Region VIII | SOUTHERN LEYTE | CITY OF MAASIN (CAPITAL) (SOUTHERN LEYTE) | P00732050VS | Construction of Flood Mitigation Structure | 124.8541 | 10.1478 | 9800000 | 9899981.77 | 2023 | DAV-LEY CONSTRUCTION SERVICES INC. (FORMERLY:DAV-LEY CONSTRUCTION SERVICES) | 8495 | 2023 | 2023-06-16 | 02/20/2023 | 0 | 99981.77 | 2023-06-15 |  | 1
2024 | Region VIII | LEYTE | TACLOBAN CITY (CAPITAL) (LEYTE) | P00834622VS | Construction of Flood Mitigation Structure | 124.9536 | 11.3175 | 96497346.95 | 96419743.33 | 2024 | JGO BUILDERS / R. YAO CONSTRUCTION | 8496 | 2024 | 2024-10-17 | 05/17/2024 | 77603.62 | 0 | 2025-02-08 | 114
2024 | Region X | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY (CAPITAL) (MISAMIS ORIENTAL) | P00821080MN | Construction of Flood Mitigation Structure | 124.7073 | 8.4679 | 49000000 | 48699961.11 | 2024 | RITCHE-NATHALIE DEVELOPMENT CORPORATION (FORMERLY: RITCHE-NATHALIE BUILDERS AND GEN. MERCHANDISE) | 8497 | 2024 | 2024-10-23 | 04/01/2024 | 300038.89 | 0 | 2024-12-01 | 39
2023 | Region VIII | NORTHERN SAMAR | LAS NAVAS (NORTHERN SAMAR) | P00721615VS | Construction of Flood Mitigation Structure | 125.0159 | 12.3227 | 66584930.31 | 65894529.87 | 2024 | JUPA CONSTRUCTION / CHRISTFER CONSTRUCTION & SUPPLY | 8498 | 2023 | 2024-07-02 | 02/07/2023 | 690400.44 | 0 | 2023-11-17 |  | 228
2022 | Region VIII | SOUTHERN LEYTE | MACROHON (SOUTHERN LEYTE) | P00631709VS | Construction of Slope Protection Structure | 124.9537 | 10.1352 | 96500000 | 96500000 | 2023 | COLLERA CONSTRUCTION | 8499 | 2022 | 2023-04-20 | 04/06/2022 | 0 | 0 | 2023-04-19 |  | 1
2024 | Region VIII | SAMAR (WESTERN SAMAR) | SAN JORGE (SAMAR (WESTERN SAMAR)) | P00820419VS | Construction of Flood Mitigation Structure | 124.8542 | 11.9807 | 49000000 | 48947871.3 | 2024 | JFR CONSTRUCTION INC. (FORMERLY:JFR CONSTRUCTION) | 8500 | 2024 | 2024-11-11 | 04/26/2024 | 52128.7 | 0 | 2024-12-15 | 34
2024 | Region VIII | LEYTE | ALBUERA (LEYTE) | P00834617VS | Construction of Flood Mitigation Structure | 124.7077 | 11.0256 | 96500000 | 96400000 | 2024 | JM COLLERA KONSTRACT | 8501 | 2024 | 2024-10-18 | 03/14/2024 | 100000 | 0 | 2025-01-06 | 80
2023 | Region XII | SULTAN KUDARAT | BAGUMBAYAN (SULTAN KUDARAT) | P00721474MN | Construction of Flood Mitigation Structure | 124.5819 | 6.6198 | 49000000 | 41854971.83 | 2023 | CS CONST. AND SUPPLY INC. (FORMERLY: CS CONSTRUCTION AND SUPPLY) / DALANON CONSTRUCTION CORPORATION (FORMERLY:DALANON CONSTRUCTION REF. SUPPLY & SERVICE) | 8502 | 2023 | 2023-10-20 | 03/08/2023 | 7145028.17 | 0 | 2023-11-28 | 39
2023 | Region VII | BOHOL | BIEN UNIDO (BOHOL) | P00721543VS | Construction of Flood Mitigation Structure | 124.3671 | 10.1498 | 78400000 | 78399988.26 | 2024 | LABB CONSTRUCTION DEVELOPMENT INC. (FORMERLY: LABB CONSTRUCTION) | 8503 | 2023 | 2024-03-28 | 04/17/2023 | 11.74 | 0 | 2024-03-27 |  | 1
2023 | Region XII | SOUTH COTABATO | CITY OF KORONADAL (CAPITAL) (SOUTH COTABATO) | P00734378MN | Construction of Flood Mitigation Structure | 124.8547 | 6.5234 | 310576313.2 | 77101733.66 | 2024 | ABU CONSTRUCTION | 8504 | 2023 | 2024-04-11 | 08/30/2023 | 233474579.54 | 0 | 2024-04-10 |  | 1
2024 | Region X | MISAMIS ORIENTAL | MEDINA (MISAMIS ORIENTAL) | P00820255MN | Construction of Flood Mitigation Structure | 125.0168 | 8.9202 | 120625000 | 120623945.2 | 2024 | ROAD EDGE TRADING & DEVELOPMENT SERVICES | 8505 | 2024 | 2024-09-16 | 02/12/2024 | 1054.8 | 0 | 2024-11-03 | 48
2024 | Region VIII | LEYTE | ALBUERA (LEYTE) | P00821064VS | Construction of Drainage Structure | 124.7077 | 10.8981 | 5488000 | 5433099.16 | 2024 | GMP BUILDERS | 8506 | 2024 | 2024-06-13 | 02/15/2024 | 54900.84 | 0 | 2024-06-12 |  | 1
2022 | Region X | MISAMIS ORIENTAL | OPOL (MISAMIS ORIENTAL) | P00630484MN | Construction of Flood Mitigation Structure | 124.582 | 8.5108 | 62725000 | 53541974.18 | 2022 | RITCHE-NATHALIE BUILDERS & GENERAL MERCHANDISE | 8507 | 2022 | 2022-09-01 | 03/03/2022 | 9183025.82 | 0 | 2022-10-16 | 45
2022 | Region VIII | SOUTHERN LEYTE | CITY OF MAASIN (CAPITAL) (SOUTHERN LEYTE) | P00620224VS | Construction of Flood Mitigation Structure | 124.8547 | 10.1581 | 49000000 | 48700120 | 2022 | ALPHA & OMEGA GEN. CONTRACTOR & DEVELOPMENT CORP. | 8508 | 2022 | 2022-12-06 | 02/10/2022 | 299880 | 0 | 2022-12-05 |  | 1
2021 | Region VIII | LEYTE |  | P00549892VS | Construction of Flood Mitigation Structure | 124.9553 | 11.3456 | 34646559.06 | 34471633.72 | 2022 | EZJONES CONSTRUCTION INC. | 8509 | 2021 | 2022-08-15 | 05/31/2021 | 174925.34 | 0 | 2022-08-14 |  | 1
2023 | Region X | MISAMIS ORIENTAL | MEDINA (MISAMIS ORIENTAL) | P00721258MN | Construction of Flood Mitigation Structure | 125.017 | 8.9202 | 114800000 | 113079596.3 | 2024 | JEJOR'S CONSTRUCTION CORPORATION | 8510 | 2023 | 2024-12-05 | 03/27/2023 | 1720403.7 | 0 | 2024-01-19 |  | 321
2022 | Region X | CAMIGUIN | MAMBAJAO (CAPITAL) (CAMIGUIN) | P00620135MN | Construction of Drainage Structure | 124.7141 | 9.2522 | 48999967.85 | 49000000 | 2023 | WDM CONSTRUCTION AND SUPPLIES | 8511 | 2022 | 2023-02-26 | 05/12/2022 | 0 | 32.15 | 2022-11-06 |  | 112
2022 | Region VIII | BILIRAN | CAIBIRAN (BILIRAN) | P00633026VS | Rehabilitation / Major Repair of Flood Control Structure | 124.5823 | 11.5731 | 4895315.06 | 4758246.25 | 2022 | INFRASERVE BUILDERS AND SUPPLIES | 8512 | 2022 | 2022-07-31 | 03/29/2022 | 137068.81 | 0 | 2022-07-30 |  | 1
2024 | Region X | CAMIGUIN | MAMBAJAO (CAPITAL) (CAMIGUIN) | P00820149MN | Construction of Drainage Structure | 124.7158 | 9.2497 | 19599999.5 | 19005665.26 | 2024 | TRESTON CONSTRUCTION | 8513 | 2024 | 2024-12-16 | 07/01/2024 | 594334.24 | 0 | 2024-12-15 |  | 1
2024 | Region XII | SOUTH COTABATO | POLOMOLOK (SOUTH COTABATO) | P00820923MN | Construction of Revetment | 125.0172 | 6.253 | 120625000 | 120624048.8 | 2025 | J.G. ORANZA CONSTRUCTION | 8514 | 2024 | 2025-02-04 | 06/27/2024 | 951.2 | 0 | 2025-04-14 | 69
2021 | Region VIII | LEYTE |  | P00549882VS | Construction of Slope Protection Structure | 124.9561 | 11.2915 | 288816611.2 | 143625981.6 | 2022 | EZJONES CONSTRUCTION INC. | 8515 | 2021 | 2022-10-25 | 12/01/2021 | 145190629.6 | 0 | 2022-11-15 | 21
2022 | Region VII | BOHOL | JAGNA (BOHOL) | P00630217VS | Construction of Flood Mitigation Structure | 124.3688 | 9.6497 | 49000000 | 48913198.93 | 2023 | LABB CONSTRUCTION DEVELOPMENT INC. (FORMERLY: LABB CONSTRUCTION) | 8516 | 2022 | 2023-02-14 | 04/18/2022 | 86801.07 | 0 | 2023-02-13 |  | 1
2024 | Region VIII | SOUTHERN LEYTE | CITY OF MAASIN (CAPITAL) (SOUTHERN LEYTE) | P00821065VS | Construction of Flood Mitigation Structure | 124.8557 | 10.1383 | 49000000 | 48940162.39 | 2025 | JQD CONSTRUCTION & GENERAL SERVICES | 8517 | 2024 | 2025-01-03 | 03/13/2024 | 59837.61 | 0 | 2025-01-02 |  | 1
2022 | Region X | MISAMIS ORIENTAL | OPOL (MISAMIS ORIENTAL) | P00630486MN | Construction of Flood Mitigation Structure | 124.5826 | 8.5043 | 62725000 | 62725000 | 2022 | JEJOR'S CONSTRUCTION CORPORATION | 8518 | 2022 | 2022-12-30 | 03/24/2022 | 0 | 0 | 2022-12-29 |  | 1
2022 | Region VIII | LEYTE | ALBUERA (LEYTE) | P00633240VS | Construction of Flood Mitigation Structure | 124.7194 | 10.8825 | 49500000 | 49499997.74 | 2023 | EZJONES CONSTRUCTION INC. | 8519 | 2022 | 2023-02-15 | 03/23/2022 | 2.26 | 0 | 2023-02-14 |  | 1
2022 | Region X | MISAMIS ORIENTAL | MEDINA (MISAMIS ORIENTAL) | P00620029MN | Construction of Flood Mitigation Structure | 125.0173 | 8.9199 | 130275000 | 126308189.9 | 2023 | JEJOR'S CONSTRUCTION CORPORATION | 8520 | 2022 | 2023-08-17 | 06/29/2022 | 3966810.1 | 0 | 2023-04-23 |  | 116
2023 | Region XII | SOUTH COTABATO | CITY OF KORONADAL (CAPITAL) (SOUTH COTABATO) | P00732164MN | Construction of Flood Mitigation Structure | 124.8563 | 6.5226 | 34300000 | 34299906.85 | 2023 | BETTER WORK CONSTRUCTION / MANUELA CONSTRUCTION SERVICES | 8521 | 2023 | 2023-08-30 | 04/17/2023 | 93.15 | 0 | 2023-08-29 |  | 1
2022 | Region V | CATANDUANES | BARAS (CATANDUANES) | P00620734LZ | Construction of Flood Mitigation Structure | 124.3706 | 13.6788 | 47530000 | 47332760 | 2022 | NQA CONSTRUCTION & SUPPLY | 8522 | 2022 | 2022-11-14 | 03/02/2022 | 197240 | 0 | 2022-11-13 |  | 1
2024 | Region VIII | SAMAR (WESTERN SAMAR) | PAGSANGHAN (SAMAR (WESTERN SAMAR)) | P00835022VS | Construction of Flood Mitigation Structure | 124.7195 | 11.9651 | 19800000 | 19777562.05 | 2024 | ETAN CONSTRUCTION | 8523 | 2024 | 2024-12-09 | 06/03/2024 | 22437.95 | 0 | 2024-12-18 | 9
2023 | Region X | MISAMIS ORIENTAL | MEDINA (MISAMIS ORIENTAL) | P00734025MN | Construction of Flood Mitigation Structure | 125.0174 | 8.9204 | 49000000 | 49000000 | 2024 | JEJOR'S CONSTRUCTION CORPORATION | 8524 | 2023 | 2024-03-05 | 05/08/2023 | 0 | 0 | 2024-03-04 |  | 1
2022 | Region XII | SULTAN KUDARAT | ISULAN (CAPITAL) (SULTAN KUDARAT) | P00620284MN | Construction of Flood Mitigation Structure | 124.5826 | 6.6331 | 48774941.12 | 48714938.9 | 2022 | CS CONST. AND SUPPLY INC. (FORMERLY: CS CONSTRUCTION AND SUPPLY) | 8525 | 2022 | 2022-09-26 | 02/22/2022 | 60002.22 | 0 | 2022-09-10 |  | 16
2023 | Region VIII | SAMAR (WESTERN SAMAR) | GANDARA (SAMAR (WESTERN SAMAR)) | P00721803VS | Construction of Flood Mitigation Structure | 124.857 | 12.1086 | 53075000 | 52879569.42 | 2023 | JFR CONSTRUCTION INC. (FORMERLY:JFR CONSTRUCTION) | 8526 | 2023 | 2023-09-15 | 03/15/2023 | 195430.58 | 0 | 2023-11-11 | 57
2023 | Region V | CATANDUANES | BARAS (CATANDUANES) | P00737574LZ | Construction of Flood Mitigation Structure | 124.3708 | 13.6645 | 19800000 | 19800000 | 2023 | A.V. LAYNES TRADING AND CONSTRUCTION | 8527 | 2023 | 2023-08-03 | 02/17/2023 | 0 | 0 | 2023-08-02 |  | 1
2024 | Region VIII | LEYTE | PALO (LEYTE) | P00820890VS | Construction of Flood Mitigation Structure | 124.9563 | 11.1725 | 41495000 | 41469137.1 | 2024 | AQUALINE CONSTRUCTION CORPORATION (FORMERLY: AQUALINE CONSTRUCTION) | 8528 | 2024 | 2024-09-25 | 04/23/2024 | 25862.9 | 0 | 2024-10-29 | 34
2023 | Region X | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY (CAPITAL) (MISAMIS ORIENTAL) | P00733991MN | Construction of Flood Mitigation Structure | 124.7203 | 8.4772 | 48250000 | 47033116.57 | 2024 | ME 3 CONSTRUCTION | 8529 | 2023 | 2024-12-30 | 04/11/2023 | 1216883.43 | 0 | 2023-11-29 |  | 397
2023 | Region XII | SULTAN KUDARAT | BAGUMBAYAN (SULTAN KUDARAT) | P00721517MN | Construction of Flood Mitigation Structure | 124.5828 | 6.6169 | 49000000 | 44679385.64 | 2023 | PALMARES CONSTRUCTION & GENERAL MERCHANDISE CORP. (FORMERLY: PALMARES GENERAL MERCHANDISE) | 8530 | 2023 | 2023-08-30 | 03/16/2023 | 4320614.36 | 0 | 2023-11-18 | 80
2021 | Region VIII | LEYTE |  | P00521576VS | Construction of Flood Mitigation Structure | 125.0181 | 11.1093 | 96399566.94 | 94857069.67 | 2024 | L.N.R. CONSTRUCTION / SUNWEST, INC. (FORMERLY: SUNWEST CONSTRUCTION & DEVELOPMENT CORPORATION) | 8531 | 2021 | 2024-01-25 | 02/22/2021 | 1542497.27 | 0 | 2024-01-24 |  | 1
2022 | Region VIII | SAMAR (WESTERN SAMAR) | ALMAGRO (SAMAR (WESTERN SAMAR)) | P00633245VS | Rehabilitation / Major Repair of Flood Control Structure | 124.3733 | 11.9459 | 19800000 | 19684401.73 | 2022 | PABLO S. LABASBAS CONSTRUCTION CORPORATION (FORMERLY: PABLOS. LABASBAS CONSTRUCTION CORPORATION) | 8532 | 2022 | 2022-10-13 | 03/25/2022 | 115598.27 | 0 | 2022-10-12 |  | 1
2021 | Region VIII | LEYTE |  | P00549881VS | Construction of Slope Protection Structure | 124.9571 | 11.2925 | 288816611.2 | 144016391.7 | 2022 | EZJONES CONSTRUCTION INC. | 8533 | 2021 | 2022-10-25 | 12/01/2021 | 144800219.5 | 0 | 2022-11-15 | 21
2022 | Region VII | BOHOL | ANDA (BOHOL) | P00630191VS | Construction of Slope Protection Structure | 124.5834 | 9.8035 | 76929800 | 76929652.14 | 2022 | JAS MIXER CONSTRUCTION AND DEVELOPMENT CORPORATION / M.R. VARGAS CONSTRUCTION CORPORATION (FORMERLY: M.R. VARGAS CONSTRUCTION) | 8534 | 2022 | 2022-12-21 | 04/12/2022 | 147.86 | 0 | 2022-12-20 |  | 1
2022 | Region VIII | LEYTE | ALBUERA (LEYTE) | P00620196VS | Construction of Flood Mitigation Structure | 124.7213 | 10.8821 | 19599407.12 | 19599393.93 | 2022 | MAC BUILDERS CORP. (FORMERLY: MAC BUILDERS DEVELOPMENT CORPORATION) | 8535 | 2022 | 2022-09-18 | 02/21/2022 | 13.19 | 0 | 2022-09-17 |  | 1
2023 | Region VIII | LEYTE | TACLOBAN CITY (CAPITAL) (LEYTE) | P00721597VS | Construction of Revetment | 124.9573 | 11.305 | 55485296.15 | 55353184.87 | 2023 | AQUALINE CONSTRUCTION CORPORATION (FORMERLY: AQUALINE CONSTRUCTION) | 8536 | 2023 | 2023-10-16 | 03/02/2023 | 132111.28 | 0 | 2023-10-15 |  | 1
2024 | Region VIII | NORTHERN SAMAR | SAN ROQUE (NORTHERN SAMAR) | P00834685VS | Construction of Flood Mitigation Structure | 124.8576 | 12.5284 | 48999642.4 | 48989659.89 | 2024 | EZJONES CONSTRUCTION INC. | 8537 | 2024 | 2024-12-05 | 04/25/2024 | 9982.51 | 0 | 2025-02-17 | 74
2021 | Region X | LANAO DEL SUR |  | P00550569MN | Construction of Drainage Structure | 124.3734 | 7.9692 | 9900000 | 7470121.06 | 2022 | MAC CONSTRUCTION | 8538 | 2021 | 2022-09-19 | 05/23/2022 | 2429878.94 | 0 | 2022-09-18 |  | 1
2022 | Region VII | BOHOL | ANDA (BOHOL) | P00630190VS | Construction of Slope Protection Structure | 124.5836 | 9.803 | 77200000 | 77199954.39 | 2022 | FUENTABUILT CONSTRUCTION CORP. / M.R. VARGAS CONSTRUCTION CORPORATION (FORMERLY: M.R. VARGAS CONSTRUCTION) | 8539 | 2022 | 2022-12-21 | 04/12/2022 | 45.61 | 0 | 2022-12-20 |  | 1
2024 | Region VIII | SOUTHERN LEYTE | PADRE BURGOS (SOUTHERN LEYTE) | P00820138VS | Construction of Flood Mitigation Structure | 125.0184 | 10.0279 | 61760000 | 61683587.9 | 2024 | ALPHA & OMEGA GEN. CONTRACTOR & DEVELOPMENT CORP. | 8540 | 2024 | 2024-11-15 | 03/13/2024 | 76412.1 | 0 | 2024-12-05 | 20
2023 | Region XII | SOUTH COTABATO | NORALA (SOUTH COTABATO) | P00732167MN | Construction of Flood Mitigation Structure | 124.7219 | 6.4936 | 49000000 | 24499940.38 | 2023 | REYDAN BUILDERS | 8541 | 2023 | 2023-08-07 | 04/17/2023 | 24500059.62 | 0 | 2023-08-06 |  | 1
2022 | Region VIII | LEYTE | ABUYOG (LEYTE) | P00620200VS | Construction of Flood Mitigation Structure | 124.9578 | 10.6783 | 49000000 | 48019930.67 | 2022 | LEDA CONSTRUCTION INCORPORATED | 8542 | 2022 | 2022-11-30 | 02/15/2022 | 980069.33 | 0 | 2022-11-29 |  | 1
2023 | Region VIII | LEYTE | SAN ISIDRO (LEYTE) | P00733313VS | Rehabilitation / Major Repair of Flood Control Structure | 124.3774 | 11.4072 | 37631866.52 | 37443688.48 | 2024 | RJIR ENTERPRISES CORPORATION | 8543 | 2023 | 2024-01-26 | 05/29/2023 | 188178.04 | 0 | 2024-03-03 | 37
2022 | Region VIII | BILIRAN | CAIBIRAN (BILIRAN) | P00630670VS | Construction of Flood Mitigation Structure | 124.5844 | 11.5661 | 4944855.44 | 4946008.05 | 2022 | CHUROCK BUILDERS INC.(FORMERLY: CHUROCK BUILDERS) | 8544 | 2022 | 2022-08-02 | 03/16/2022 | 0 | 1152.61 | 2022-08-01 |  | 1
2024 | Region XII | SARANGANI | KIAMBA (SARANGANI) | P00821094MN | Construction of Flood Mitigation Structure | 124.722 | 5.9368 | 34300000 | 34298956.6 | 2024 | SHEPPERD CONSTRUCTION AND SUPPLY | 8545 | 2024 | 2024-08-26 | 02/13/2024 | 1043.4 | 0 | 2024-08-25 |  | 1
2021 | Region VIII | LEYTE |  | P00521577VS | Construction of Flood Mitigation Structure | 125.0185 | 11.1004 | 96399560.14 | 94953700.39 | 2022 | SUNWEST, INC. (FORMERLY: SUNWEST CONSTRUCTION & DEVELOPMENT CORPORATION) | 8546 | 2021 | 2022-12-29 | 02/22/2021 | 1445859.75 | 0 | 2022-12-30 | 1
2024 | Region VIII | SOUTHERN LEYTE | CITY OF MAASIN (CAPITAL) (SOUTHERN LEYTE) | P00820262VS | Construction of Flood Mitigation Structure | 124.8576 | 10.1299 | 49000000 | 49000000 | 2024 | ALPHA & OMEGA GEN. CONTRACTOR & DEVELOPMENT CORP. | 8547 | 2024 | 2024-10-09 | 02/13/2024 | 0 | 0 | 2024-10-08 |  | 1
2023 | Region VIII | BILIRAN | ALMERIA (BILIRAN) | P00732034VS | Construction of Flood Mitigation Structure | 124.378 | 11.6203 | 4945318.82 | 4817730 | 2023 | MKB BUILDERS AND SUPPLY | 8548 | 2023 | 2023-10-16 | 02/27/2023 | 127588.82 | 0 | 2023-04-28 |  | 171
2023 | Region VIII | LEYTE | ABUYOG (LEYTE) | P00721911VS | Construction of Flood Mitigation Structure | 124.9578 | 10.6783 | 53075000 | 52282484.62 | 2023 | LEDA CONSTRUCTION INCORPORATED | 8549 | 2023 | 2023-12-29 | 04/04/2023 | 792515.38 | 0 | 2023-12-28 |  | 1
2024 | Region X | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY (CAPITAL) (MISAMIS ORIENTAL) | P00833586MN | Construction of Drainage Structure | 124.5845 | 8.4852 | 19800000 | 19800000 | 2024 | CAGALAWAN ENTERPRISES | 8550 | 2024 | 2024-09-15 | 02/28/2024 | 0 | 0 | 2024-09-14 |  | 1
2023 | Region X | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY (CAPITAL) (MISAMIS ORIENTAL) | P00732484MN | Construction of Flood Mitigation Structure | 124.7243 | 8.4602 | 9900000 | 9519432.69 | 2023 | BLACK ROAD CONSTRUCTION | 8551 | 2023 | 2023-06-15 | 02/13/2023 | 380567.31 | 0 | 2023-06-14 |  | 1
2021 | Region VIII | LEYTE |  | P00521572VS | Construction of Flood Mitigation Structure | 125.0189 | 11.1131 | 96399695.12 | 94857029.25 | 2023 | L.N.R. CONSTRUCTION / SUNWEST, INC. (FORMERLY: SUNWEST CONSTRUCTION & DEVELOPMENT CORPORATION) | 8552 | 2021 | 2023-06-13 | 02/22/2021 | 1542665.87 | 0 | 2023-06-12 |  | 1
2023 | Region VIII | SOUTHERN LEYTE | CITY OF MAASIN (CAPITAL) (SOUTHERN LEYTE) | P00721606VS | Construction of Flood Mitigation Structure | 124.8577 | 10.1294 | 84437500 | 84411723.69 | 2023 | ST. TIMOTHY CONSTRUCTION CORPORATION | 8553 | 2023 | 2023-12-13 | 02/21/2023 | 25776.31 | 0 | 2023-12-12 |  | 1
2024 | Region VIII | LEYTE | TANAUAN (LEYTE) | P00820369VS | Construction of Flood Mitigation Structure | 124.9585 | 11.0826 | 96500000 | 96450000.44 | 2024 | EZJONES CONSTRUCTION INC. / XDR CONSTRUCTION AND SUPPLY | 8554 | 2024 | 2024-09-14 | 02/15/2024 | 49999.56 | 0 | 2024-11-23 | 70
2022 | Region X | BUKIDNON | TALAKAG (BUKIDNON) | P00620122MN | Construction of Flood Mitigation Structure | 124.585 | 8.1506 | 49000000 | 49000000 | 2023 | VEN RAY CONSTRUCTION CORPORATION | 8555 | 2022 | 2023-03-02 | 04/11/2022 | 0 | 0 | 2023-03-01 |  | 1
2023 | Region VIII | LEYTE | TACLOBAN CITY (CAPITAL) (LEYTE) | P00733289VS | Construction of Revetment | 124.9586 | 11.2394 | 96499745.52 | 96381079.66 | 2024 | CTC BUILDER AND SUPPLIES INCORPORATED (FOR. CTC BU / AICON INDUSTRIES | 8556 | 2023 | 2024-03-19 | 05/26/2023 | 118665.86 | 0 | 2024-03-19 | 0
2024 | Region X | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY (CAPITAL) (MISAMIS ORIENTAL) | P00821078MN | Construction of Flood Mitigation Structure | 124.7244 | 8.4602 | 19600000 | 19206336.98 | 2024 | 5S DEVELOPMENT CORPORATION | 8557 | 2024 | 2024-09-17 | 02/26/2024 | 393663.02 | 0 | 2024-09-16 |  | 1
2023 | Region VIII | LEYTE | TACLOBAN CITY (CAPITAL) (LEYTE) | P00721616VS | Construction of Flood Mitigation Structure | 124.9588 | 11.3363 | 107474311.5 | 110974526 | 2024 | CTC BUILDER AND SUPPLIES INCORPORATED (FOR. CTC BU / AICON INDUSTRIES | 8558 | 2023 | 2024-03-19 | 05/26/2023 | 0 | 3500214.5 | 2024-03-19 | 0
2024 | Region XII | SULTAN KUDARAT | ISULAN (CAPITAL) (SULTAN KUDARAT) | P00820422MN | Construction of Flood Mitigation Structure | 124.585 | 6.6222 | 44938301.06 | 44893181.63 | 2024 | CS CONST. AND SUPPLY INC. (FORMERLY: CS CONSTRUCTION AND SUPPLY) | 8559 | 2024 | 2024-08-25 | 02/15/2024 | 45119.43 | 0 | 2024-08-26 | 1
2021 | Region VIII | LEYTE |  | P00521573VS | Construction of Flood Mitigation Structure | 125.0189 | 11.1133 | 96209937.62 | 95246996.07 | 2023 | SUNWEST, INC. (FORMERLY: SUNWEST CONSTRUCTION & DEVELOPMENT CORPORATION) | 8560 | 2021 | 2023-05-21 | 09/06/2021 | 962941.55 | 0 | 2023-05-20 |  | 1
2024 | Region VIII | BILIRAN | ALMERIA (BILIRAN) | P00832667VS | Construction of Flood Mitigation Structure | 124.3781 | 11.6207 | 4944449.18 | 4850108.5 | 2024 | W.B. ALAGAO CONSTRUCTION | 8561 | 2024 | 2024-05-16 | 02/12/2024 | 94340.68 | 0 | 2024-05-15 |  | 1
2023 | Region VIII | NORTHERN SAMAR | SAN ROQUE (NORTHERN SAMAR) | P00721614VS | Construction of Flood Mitigation Structure | 124.8592 | 12.5298 | 50421066.69 | 50411055.55 | 2023 | CDU CONSTRUCTION | 8562 | 2023 | 2023-10-10 | 03/07/2023 | 10011.14 | 0 | 2023-12-15 | 66
2022 | Region VIII | LEYTE | HINDANG (LEYTE) | P00633242VS | Construction of Flood Mitigation Structure | 124.725 | 10.4356 | 49500000 | 48412000 | 2022 | GREENPLAINS CONSTRUCTION | 8563 | 2022 | 2022-11-12 | 03/30/2022 | 1088000 | 0 | 2022-11-11 |  | 1
2023 | Region VIII | BILIRAN | KAWAYAN (BILIRAN) | P00733749VS | Construction of Flood Mitigation Structure | 124.3825 | 11.6943 | 4945210.24 | 4875580.7 | 2023 | M.B. ANG CONSTRUCTION & SUPPLY | 8564 | 2023 | 2023-06-12 | 03/30/2023 | 69629.54 | 0 | 2023-06-11 |  | 1
2023 | Region XII | SOUTH COTABATO | TUPI (SOUTH COTABATO) | P00721314MN | Construction of Flood Mitigation Structure | 124.9602 | 6.248 | 50180000 | 50139871.77 | 2023 | MRRM TRADING & CONSTRUCTION / SALMEGA BUILDERS | 8565 | 2023 | 2023-09-01 | 03/30/2023 | 40128.23 | 0 | 2023-08-31 |  | 1
2023 | Region VIII | LEYTE | KANANGA (LEYTE) | P00731640VS | Construction of Flood Mitigation Structure | 124.585 | 11.1246 | 96500000 | 96299800.62 | 2023 | RJIR ENTERPRISES CORPORATION / RED AXE BUILDERS & SUPPLY | 8566 | 2023 | 2023-10-23 | 03/28/2023 | 200199.38 | 0 | 2024-01-20 | 89
2023 | Region X | BUKIDNON | MALITBOG (BUKIDNON) | P00721368MN | Construction of Flood Mitigation Structure | 125.0191 | 8.5517 | 10147900 | 10147900 | 2023 | RAMISES CONSTRUCTION | 8567 | 2023 | 2023-07-30 | 02/20/2023 | 0 | 0 | 2023-07-29 |  | 1
2024 | Region X | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY (CAPITAL) (MISAMIS ORIENTAL) | P00820146MN | Construction of Flood Mitigation Structure | 124.5857 | 8.2904 | 12250000 | 12250000 | 2024 | ALEBON GENUINE MERCHANDISING INCORPORATED | 8568 | 2024 | 2024-07-26 | 01/30/2024 | 0 | 0 | 2024-08-10 | 15
2023 | Region VIII | LEYTE | ABUYOG (LEYTE) | P00721912VS | Construction of Flood Mitigation Structure | 124.9603 | 10.6898 | 53075000 | 52517168.88 | 2024 | FAIRCHILD BUILDERS & DEVELOPERS, INC. | 8569 | 2023 | 2024-03-12 | 07/12/2023 | 557831.12 | 0 | 2024-04-05 | 24
2024 | Region VIII | NORTHERN SAMAR | SAN ROQUE (NORTHERN SAMAR) | P00820253VS | Construction of Flood Mitigation Structure | 124.8597 | 12.5293 | 48999971.66 | 48919995.76 | 2024 | CDU CONSTRUCTION | 8570 | 2024 | 2024-11-08 | 02/12/2024 | 79975.9 | 0 | 2024-12-06 | 28
2022 | Region V | CATANDUANES | BARAS (CATANDUANES) | P00620735LZ | Construction of Flood Mitigation Structure | 124.3829 | 13.7118 | 44100000 | 44098760 | 2022 | NQA CONSTRUCTION & SUPPLY | 8571 | 2022 | 2022-11-17 | 03/02/2022 | 1240 | 0 | 2022-11-24 | 7
2022 | Region XII | COTABATO (NORTH COTABATO) | PIKIT (COTABATO (NORTH COTABATO)) | P00620239MN | Construction of Flood Mitigation Structure | 124.7268 | 7.1114 | 109671285 | 109671285 | 2023 | AGONG BUILDERS AND CONSTRUCTION SUPPLY, INC. / ABU CONSTRUCTION | 8572 | 2022 | 2023-12-15 | 05/23/2022 | 0 | 0 | 2023-12-14 |  | 1
2020 | Region VIII | LEYTE |  | P00420374VS | Construction of Flood Mitigation Structure | 125.0191 | 11.1133 | 192799217.9 | 96499739.99 | 2022 | L.N.R. CONSTRUCTION / SUNWEST, INC. (FORMERLY: SUNWEST CONSTRUCTION & DEVELOPMENT CORPORATION) | 8573 | 2020 | 2022-10-25 | 12/03/2020 | 96299477.91 | 0 | 2022-11-07 | 13
2022 | Region VIII | LEYTE | TACLOBAN CITY (CAPITAL) (LEYTE) | P00630688VS | Construction of Drainage Structure | 124.9604 | 11.252 | 14847356.97 | 14550776.82 | 2022 | ESPERAS CONSTRUCTION & DEVELOPMENT CORP. | 8574 | 2022 | 2022-08-07 | 02/21/2022 | 296580.15 | 0 | 2022-08-06 |  | 1
2024 | Region VIII | BILIRAN | CABUCGAYAN (BILIRAN) | P00832666VS | Construction of Revetment | 124.5858 | 11.484 | 9894096.29 | 9716102.55 | 2024 | INFRASERVE BUILDERS AND SUPPLIES | 8575 | 2024 | 2024-05-30 | 02/14/2024 | 177993.74 | 0 | 2024-06-03 | 4
2024 | Region VIII | SOUTHERN LEYTE | CITY OF MAASIN (CAPITAL) (SOUTHERN LEYTE) | P00835032VS | Construction of Flood Mitigation Structure | 124.8606 | 10.1996 | 9800000 | 9782580.42 | 2024 | DAV-LEY CONSTRUCTION SERVICES INC. (FORMERLY:DAV-LEY CONSTRUCTION SERVICES) | 8576 | 2024 | 2024-07-03 | 03/07/2024 | 17419.58 | 0 | 2024-07-02 |  | 1
2023 | Region VIII | LEYTE | TANAUAN (LEYTE) | P00721793VS | Construction of Flood Mitigation Structure | 124.9604 | 11.0846 | 106148981.9 | 106149990.9 | 2023 | JELM CONSTRUCTION CORP. | 8577 | 2023 | 2023-06-30 | 03/15/2023 | 0 | 1009 | 2024-01-07 | 191
2022 | Region XII | SULTAN KUDARAT | ISULAN (CAPITAL) (SULTAN KUDARAT) | P00620286MN | Construction of Flood Mitigation Structure | 124.586 | 6.6212 | 48968231.47 | 48968970.3 | 2023 | JARGON CONSTRUCTION & SUPPLY | 8578 | 2022 | 2023-03-24 | 02/22/2022 | 0 | 738.83 | 2023-03-09 |  | 15
2024 | Region XII | SARANGANI | KIAMBA (SARANGANI) | P00835806MN | Construction of Flood Mitigation Structure | 124.7309 | 5.9332 | 53075000 | 52675000 | 2024 | EC SOLICON BUILDERS & SUPPLY, INC. | 8579 | 2024 | 2024-11-25 | 05/30/2024 | 400000 | 0 | 2025-01-15 | 51
2022 | Region X | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY (CAPITAL) (MISAMIS ORIENTAL) | P00632609MN | Construction of Drainage Structure | 124.3849 | 8.2922 | 4950000 | 4893595.87 | 2022 | NAHARO BUILDERS, INC. | 8580 | 2022 | 2022-11-30 | 06/08/2022 | 56404.13 | 0 | 2022-10-12 |  | 49
2022 | Region VIII | LEYTE | TANAUAN (LEYTE) | P00620067VS | Construction of Flood Mitigation Structure | 125.0192 | 11.1132 | 85543510.98 | 85641231.29 | 2023 | 888 ACY ENTERPRISES / JGO BUILDERS | 8581 | 2022 | 2023-12-31 | 03/07/2022 | 0 | 97720.31 | 2023-12-30 |  | 1
2023 | Region XII | SOUTH COTABATO | CITY OF KORONADAL (CAPITAL) (SOUTH COTABATO) | P00721621MN | Construction of Flood Mitigation Structure | 124.8639 | 6.4896 | 39200000 | 14673207.7 | 2023 | BETTER WORK CONSTRUCTION / MANUELA CONSTRUCTION SERVICES | 8582 | 2023 | 2023-08-18 | 04/17/2023 | 24526792.3 | 0 | 2023-08-19 | 1
2022 | Region VIII | LEYTE | TACLOBAN CITY (CAPITAL) (LEYTE) | P00630245VS | Construction of Drainage Structure | 124.9623 | 11.2504 | 14698851.94 | 14402527.38 | 2022 | DICA CONST. & DEVELOPMENT CORP. | 8583 | 2022 | 2022-08-18 | 03/04/2022 | 296324.56 | 0 | 2022-08-17 |  | 1
2024 | Region XII | SULTAN KUDARAT | ISULAN (CAPITAL) (SULTAN KUDARAT) | P00820421MN | Construction of Flood Mitigation Structure | 124.5862 | 6.6193 | 44934156.54 | 43564921.74 | 2024 | LEGACY CONSTRUCTION CORPORATION (FORMERLY: LEGACY CONSTRUCTION) | 8584 | 2024 | 2024-06-14 | 02/15/2024 | 1369234.8 | 0 | 2024-08-26 | 73
2022 | Region VIII | LEYTE | TANAUAN (LEYTE) | P00620055VS | Construction of Flood Mitigation Structure | 125.0193 | 11.1264 | 17369957.8 | 17154778.04 | 2022 | MWJ CONSTRUCTION | 8585 | 2022 | 2022-08-10 | 02/28/2022 | 215179.76 | 0 | 2022-08-10 | 0
2022 | Region V | CATANDUANES | BARAS (CATANDUANES) | P00640586LZ | Construction of Flood Mitigation Structure | 124.3853 | 13.7109 | 9800000 | 9799999.55 | 2022 | NQA CONSTRUCTION & SUPPLY | 8586 | 2022 | 2022-10-20 | 07/14/2022 | 0.45 | 0 | 2022-11-15 | 26
2022 | Region VIII | SAMAR (WESTERN SAMAR) | GANDARA (SAMAR (WESTERN SAMAR)) | P00630242VS | Construction of Slope Protection Structure | 124.8652 | 12.1042 | 19600000 | 19214439.87 | 2022 | DANILORSO CORP. OPERATING UNDER THE NAME OF DRS BUILDERS AND CONSTRUCTION SUPPLIES | 8587 | 2022 | 2022-09-22 | 03/23/2022 | 385560.13 | 0 | 2022-08-13 |  | 40
2023 | Region X | BUKIDNON | TALAKAG (BUKIDNON) | P00721369MN | Construction of Flood Mitigation Structure | 124.5868 | 8.2897 | 11760000 | 11760000 | 2023 | CYRUS JAMES BUILDERS AND SUPPLIES | 8588 | 2023 | 2023-08-04 | 02/20/2023 | 0 | 0 | 2023-08-08 | 4
2021 | Region VIII | LEYTE |  | P00521575VS | Construction of Flood Mitigation Structure | 125.0197 | 11.0972 | 96399510.65 | 94953612.4 | 2022 | SUNWEST, INC. (FORMERLY: SUNWEST CONSTRUCTION & DEVELOPMENT CORPORATION) | 8589 | 2021 | 2022-12-28 | 02/22/2021 | 1445898.25 | 0 | 2022-12-30 | 2
2023 | Region VIII | BILIRAN | ALMERIA (BILIRAN) | P00733751VS | Construction of Flood Mitigation Structure | 124.3865 | 11.6024 | 4945896.1 | 4911827.07 | 2023 | R.K. ENGINEERING & CONSTRUCTION WORKS | 8590 | 2023 | 2023-08-31 | 04/02/2023 | 34069.03 | 0 | 2023-07-24 |  | 38
2023 | Region X | CAMIGUIN | MAMBAJAO (CAPITAL) (CAMIGUIN) | P00734022MN | Construction of Flood Mitigation Structure | 124.7319 | 9.2482 | 48999999.32 | 47527222.7 | 2024 | JEJOR'S CONSTRUCTION CORPORATION | 8591 | 2023 | 2024-09-01 | 04/27/2023 | 1472776.62 | 0 | 2023-12-27 |  | 249
2023 | Region VIII | BILIRAN | CABUCGAYAN (BILIRAN) | P00732037VS | Construction of Flood Mitigation Structure | 124.5875 | 11.4786 | 4946220.82 | 4825038.4 | 2023 | INFRASERVE BUILDERS AND SUPPLIES | 8592 | 2023 | 2023-06-16 | 02/20/2023 | 121182.42 | 0 | 2023-07-03 | 17
2023 | Region VIII | LEYTE | VILLABA (LEYTE) | P00733317VS | Construction of Flood Mitigation Structure | 124.3868 | 11.2224 | 48999993.79 | 48754993.65 | 2023 | RJIR ENTERPRISES CORPORATION | 8593 | 2023 | 2023-12-05 | 04/17/2023 | 245000.14 | 0 | 2024-02-14 | 71
2024 | Region VIII | LEYTE | TACLOBAN CITY (CAPITAL) (LEYTE) | P00834692VS | Construction of Flood Mitigation Structure | 124.9642 | 11.2347 | 6858986.04 | 6849543.43 | 2024 | LMKT VALLEY CONSTRUCTION | 8594 | 2024 | 2024-09-30 | 07/09/2024 | 9442.61 | 0 | 2024-11-09 | 40
2022 | Region XII | SOUTH COTABATO | CITY OF KORONADAL (CAPITAL) (SOUTH COTABATO) | P00620186MN | Construction of Flood Mitigation Structure | 124.8706 | 6.4956 | 39200000 | 39184361.82 | 2022 | BETTER WORK CONSTRUCTION | 8595 | 2022 | 2022-10-19 | 03/02/2022 | 15638.18 | 0 | 2022-09-26 |  | 23
2023 | Region X | BUKIDNON | TALAKAG (BUKIDNON) | P00721263MN | Construction of Revetment | 124.5877 | 8.1509 | 7141260 | 7031955 | 2023 | VEN RAY CONSTRUCTION CORPORATION | 8596 | 2023 | 2023-11-27 | 06/26/2023 | 109305 | 0 | 2023-11-27 | 0
2024 | Region VIII | LEYTE | PALOMPON (LEYTE) | P00820246VS | Construction of Drainage Structure | 124.3869 | 11.0933 | 9800000 | 9605575.48 | 2024 | MAVI CONSTRUCTION INC. | 8597 | 2024 | 2024-07-11 | 02/13/2024 | 194424.52 | 0 | 2024-07-10 |  | 1
2023 | Region VIII | SAMAR (WESTERN SAMAR) | CALBIGA (SAMAR (WESTERN SAMAR)) | P00721588VS | Construction of Flood Mitigation Structure | 125.0198 | 11.6246 | 110974922.1 | 110970734.9 | 2023 | EBS CONSTRUCTION AND SUPPLIES | 8598 | 2023 | 2023-12-04 | 02/13/2023 | 4187.2 | 0 | 2024-01-27 | 54
2023 | Region VIII | LEYTE | TACLOBAN CITY (CAPITAL) (LEYTE) | P00733327VS | Construction of Revetment | 124.9658 | 11.264 | 48998339.86 | 48539779.74 | 2023 | JGO BUILDERS | 8599 | 2023 | 2023-10-20 | 03/23/2023 | 458560.12 | 0 | 2023-10-19 |  | 1
2024 | Region VIII | LEYTE | VILLABA (LEYTE) | P00820235VS | Construction of Flood Mitigation Structure | 124.3877 | 11.2277 | 49000000 | 48754999.82 | 2024 | RJIR ENTERPRISES CORPORATION | 8600 | 2024 | 2024-09-17 | 02/14/2024 | 245000.18 | 0 | 2024-12-13 | 87
2023 | Region XII | SOUTH COTABATO | CITY OF KORONADAL (CAPITAL) (SOUTH COTABATO) | P00732094MN | Construction of Flood Mitigation Structure | 124.8709 | 6.4969 | 28950000 | 28949945.96 | 2023 | VYS CONSTRUCTION | 8601 | 2023 | 2023-10-25 | 06/08/2023 | 54.04 | 0 | 2023-11-13 | 19
2024 | Region VIII | LEYTE | VILLABA (LEYTE) | P00820232VS | Construction of Flood Mitigation Structure | 124.388 | 11.1735 | 39199999.99 | 39099716.63 | 2024 | KAUIE BUILDERS & SUPPLIES INC. (FORMERLY: KAUIE BUILDERS AND CONSTRUCTION SUPPLIES) | 8602 | 2024 | 2024-11-04 | 02/14/2024 | 100283.36 | 0 | 2024-11-22 | 18
2023 | Region X | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY (CAPITAL) (MISAMIS ORIENTAL) | P00721268MN | Construction of Revetment | 124.7344 | 8.4883 | 91675000 | 89367869.51 | 2024 | RAMISES CONSTRUCTION | 8603 | 2023 | 2024-08-05 | 03/29/2023 | 2307130.49 | 0 | 2024-08-04 |  | 1
2023 | Region VIII | LEYTE | TANAUAN (LEYTE) | P00721570VS | Construction of Flood Mitigation Structure | 125.0198 | 11.0972 | 89742656.31 | 89542656 | 2023 | LANOY CONSTRUCTION | 8604 | 2023 | 2023-12-31 | 03/16/2023 | 200000.31 | 0 | 2023-12-30 |  | 1
2023 | Region XII | SOUTH COTABATO | CITY OF KORONADAL (CAPITAL) (SOUTH COTABATO) | P00732095MN | Construction of Flood Mitigation Structure | 124.8716 | 6.5079 | 28950000 | 28942551.32 | 2023 | ABU CONSTRUCTION | 8605 | 2023 | 2023-12-07 | 06/08/2023 | 7448.68 | 0 | 2023-12-06 |  | 1
2022 | Region X | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY (CAPITAL) (MISAMIS ORIENTAL) | P00620382MN | Construction of Flood Mitigation Structure | 124.5882 | 8.4708 | 29400000 | 28118087.95 | 2023 | VEN RAY CONSTRUCTION CORPORATION | 8606 | 2022 | 2023-05-30 | 03/24/2022 | 1281912.05 | 0 | 2023-05-29 |  | 1
2024 | Region VIII | LEYTE | ALBUERA (LEYTE) | P00820247VS | Rehabilitation / Major Repair of Flood Control Structure | 124.7374 | 10.8694 | 9408000 | 6863307.29 | 2024 | RJIR ENTERPRISES CORPORATION | 8607 | 2024 | 2024-06-12 | 02/14/2024 | 2544692.71 | 0 | 2024-06-11 |  | 1
2022 | Region VIII | SAMAR (WESTERN SAMAR) | SANTA RITA (SAMAR (WESTERN SAMAR)) | P00620221VS | Construction of Flood Mitigation Structure | 125.0199 | 11.4665 | 39199999.41 | 39197942.28 | 2022 | CDU CONSTRUCTION | 8608 | 2022 | 2022-10-02 | 02/14/2022 | 2057.13 | 0 | 2022-11-16 | 45
2023 | Region V | CATANDUANES | VIGA (CATANDUANES) | P00737573LZ | Construction of Flood Mitigation Structure | 124.3897 | 13.8712 | 9900000 | 8118000 | 2023 | AL-JON CONSTRUCTION DEVELOPMENT, INC. (FORMERLY: ALJON CONSTRUCTION & SUPPLY) | 8609 | 2023 | 2023-07-10 | 03/20/2023 | 1782000 | 0 | 2023-07-13 | 3
2023 | Region VIII | SOUTHERN LEYTE | CITY OF MAASIN (CAPITAL) (SOUTHERN LEYTE) | P00733764VS | Construction of Flood Mitigation Structure | 124.8725 | 10.1778 | 4900000 | 4881237.85 | 2023 | DAV-LEY CONSTRUCTION SERVICES INC. (FORMERLY:DAV-LEY CONSTRUCTION SERVICES) | 8610 | 2023 | 2023-06-21 | 03/22/2023 | 18762.15 | 0 | 2023-06-20 |  | 1
2023 | Region VIII | LEYTE | TACLOBAN CITY (CAPITAL) (LEYTE) | P00721915VS | Construction of Revetment | 124.9659 | 11.2641 | 55484320.82 | 55433308.96 | 2023 | JFR CONSTRUCTION INC. (FORMERLY:JFR CONSTRUCTION) / PYUKEI CONSTRUCTION INC. | 8611 | 2023 | 2023-12-04 | 04/20/2023 | 51011.86 | 0 | 2023-12-03 |  | 1
2022 | Region X | BUKIDNON | TALAKAG (BUKIDNON) | P00620031MN | Construction of Flood Mitigation Structure | 124.5883 | 8.1517 | 96500000 | 96500000 | 2023 | VEN RAY CONSTRUCTION CORPORATION | 8612 | 2022 | 2023-06-12 | 04/11/2022 | 0 | 0 | 2023-06-11 |  | 1
2022 | Region X | BUKIDNON | KALILANGAN (BUKIDNON) | P00620125MN | Construction of Flood Mitigation Structure | 124.7392 | 7.7444 | 49000000 | 49000000 | 2023 | M. MONTESCLAROS ENTERPRISES, INC. | 8613 | 2022 | 2023-03-02 | 02/21/2022 | 0 | 0 | 2023-03-03 | 1
2022 | Region VIII | LEYTE | TANAUAN (LEYTE) | P00620068VS | Construction of Flood Mitigation Structure | 125.0201 | 11.1112 | 84997658.71 | 84334716.98 | 2023 | EZJONES CONSTRUCTION INC. / MWJ CONSTRUCTION | 8614 | 2022 | 2023-04-30 | 02/28/2022 | 662941.73 | 0 | 2023-04-29 |  | 1
2024 | Region VIII | LEYTE | TANAUAN (LEYTE) | P00820368VS | Construction of Flood Mitigation Structure | 124.9663 | 11.0915 | 96500000 | 96414342.2 | 2024 | PABLO S. LABASBAS CONSTRUCTION CORPORATION (FORMERLY: PABLOS. LABASBAS CONSTRUCTION CORPORATION) / JGO BUILDERS | 8615 | 2024 | 2024-10-21 | 02/15/2024 | 85657.8 | 0 | 2024-11-23 | 33
2022 | Region VIII | LEYTE | PALOMPON (LEYTE) | P00620197VS | Construction of Flood Mitigation Structure | 124.3897 | 11.079 | 29399600.35 | 29399997.45 | 2022 | A.C. RIVERO DEVELOPMENT CORPORATION | 8616 | 2022 | 2022-08-19 | 02/21/2022 | 0 | 397.1 | 2022-08-18 |  | 1
2022 | Region X | BUKIDNON | TALAKAG (BUKIDNON) | P00620123MN | Construction of Flood Mitigation Structure | 124.5883 | 8.1511 | 49000000 | 37728091.79 | 2023 | EQUI-PARCO CONSTRUCTION COMPANY | 8617 | 2022 | 2023-03-20 | 03/24/2022 | 11271908.21 | 0 | 2023-03-19 |  | 1
2021 | Region X | BUKIDNON |  | P00522298MN | Construction of Flood Mitigation Structure | 124.7393 | 7.7447 | 88780000 | 42600672.19 | 2022 | PYRAMID CONSOLIDATED BUILDERS & GEN. MDSE. / C'ZARLES CONSTRUCTION & SUPPLY | 8618 | 2021 | 2022-10-31 | 08/16/2021 | 46179327.81 | 0 | 2022-03-12 |  | 233
2023 | Region VIII | LEYTE | TANAUAN (LEYTE) | P00721567VS | Construction of Flood Mitigation Structure | 125.022 | 11.1049 | 113247456.4 | 113122740.6 | 2024 | EZJONES CONSTRUCTION INC. / MWJ CONSTRUCTION | 8619 | 2023 | 2024-03-17 | 03/15/2023 | 124715.8 | 0 | 2024-03-16 |  | 1
2023 | Region X | BUKIDNON | KALILANGAN (BUKIDNON) | P00721239MN | Construction of Flood Mitigation Structure | 124.7405 | 7.7433 | 188000000 | 183984802.2 | 2025 | M. MONTESCLAROS ENTERPRISES, INC. | 8620 | 2023 | 2025-01-31 | 03/29/2023 | 4015197.8 | 0 | 2024-06-13 |  | 232
2022 | Region VIII | SOUTHERN LEYTE | CITY OF MAASIN (CAPITAL) (SOUTHERN LEYTE) | P00620223VS | Construction of Flood Mitigation Structure | 124.8728 | 10.1779 | 49000000 | 48999980.89 | 2023 | ALPHA & OMEGA GEN. CONTRACTOR & DEVELOPMENT CORP. | 8621 | 2022 | 2023-02-27 | 02/10/2022 | 19.11 | 0 | 2023-02-26 |  | 1
2023 | Region VIII | LEYTE | VILLABA (LEYTE) | P00721713VS | Construction of Flood Mitigation Structure | 124.3898 | 11.2277 | 48999993.11 | 48019993.25 | 2023 | RJIR ENTERPRISES CORPORATION | 8622 | 2023 | 2023-08-08 | 02/12/2023 | 979999.86 | 0 | 2023-12-12 | 126
2022 | Region VIII | LEYTE | TANAUAN (LEYTE) | P00620069VS | Construction of Flood Mitigation Structure | 125.022 | 11.1102 | 85067153.81 | 84652058.28 | 2023 | EZJONES CONSTRUCTION INC. / MWJ CONSTRUCTION | 8623 | 2022 | 2023-01-10 | 02/28/2022 | 415095.53 | 0 | 2023-02-08 | 29
2022 | Region VIII | LEYTE | TANAUAN (LEYTE) | P00620459VS | Construction of Flood Mitigation Structure | 124.9675 | 11.0927 | 95563231.14 | 95712057.88 | 2023 | SUNWEST, INC. (FORMERLY: SUNWEST CONSTRUCTION & DEVELOPMENT CORPORATION) | 8624 | 2022 | 2023-10-02 | 07/19/2022 | 0 | 148826.74 | 2023-10-01 |  | 1
2023 | Region VIII | SAMAR (WESTERN SAMAR) | CALBAYOG CITY (SAMAR (WESTERN SAMAR)) | P00721857VS | Construction of Flood Mitigation Structure | 124.5887 | 12.0705 | 19600000 | 19572816.61 | 2023 | JFR CONSTRUCTION INC. (FORMERLY:JFR CONSTRUCTION) | 8625 | 2023 | 2023-08-08 | 02/10/2023 | 27183.39 | 0 | 2023-08-07 |  | 1
2021 | Region X | BUKIDNON |  | P00522299MN | Construction of Flood Mitigation Structure | 124.7407 | 7.7463 | 88780000 | 42628073.21 | 2022 | PYRAMID CONSOLIDATED BUILDERS & GEN. MDSE. / C'ZARLES CONSTRUCTION & SUPPLY | 8626 | 2021 | 2022-10-31 | 08/16/2021 | 46151926.79 | 0 | 2022-03-12 |  | 233
2021 | Region XII | COTABATO (NORTH COTABATO) |  | P00522329MN | Construction of Flood Mitigation Structure | 124.8755 | 6.9522 | 48395340 | 47654560.49 | 2022 | JARGON CONSTRUCTION & SUPPLY | 8627 | 2021 | 2022-12-02 | 05/20/2022 | 740779.51 | 0 | 2022-12-21 | 19
2022 | Region VIII | LEYTE | VILLABA (LEYTE) | P00620417VS | Construction of Flood Mitigation Structure | 124.3902 | 11.2111 | 48999987.53 | 48754987.6 | 2022 | RJIR ENTERPRISES CORPORATION | 8628 | 2022 | 2022-12-15 | 06/06/2022 | 244999.93 | 0 | 2023-04-05 | 111
2023 | Region VIII | SAMAR (WESTERN SAMAR) | SAN JORGE (SAMAR (WESTERN SAMAR)) | P00721807VS | Construction of Flood Mitigation Structure | 124.8769 | 11.9762 | 53075000 | 53013228.8 | 2023 | CDU CONSTRUCTION | 8629 | 2023 | 2023-08-22 | 03/21/2023 | 61771.2 | 0 | 2023-11-17 | 87
2023 | Region VIII | SAMAR (WESTERN SAMAR) | SANTA RITA (SAMAR (WESTERN SAMAR)) | P00721590VS | Construction of Flood Mitigation Structure | 125.0221 | 11.4661 | 110974953.7 | 110974893.6 | 2023 | B. VICENCIO BUILDERS (BVB), INC. (FORMERLY:B. VICENCIO CONSTRUCTION) | 8630 | 2023 | 2023-12-16 | 02/13/2023 | 60.1 | 0 | 2024-01-27 | 42
2021 | Region XII | SULTAN KUDARAT |  | P00522111MN | Construction of Flood Mitigation Structure | 124.5889 | 6.5875 | 67550000 | 67550000 | 2022 | LEGACY CONSTRUCTION CORPORATION (FORMERLY: LEGACY CONSTRUCTION) | 8631 | 2021 | 2022-11-02 | 02/12/2021 | 0 | 0 | 2021-12-11 |  | 326
2022 | Region VIII | LEYTE | DAGAMI (LEYTE) | P00620330VS | Construction of Flood Mitigation Structure | 124.8779 | 11.0805 | 48999996.69 | 48931747.46 | 2023 | LANOY CONSTRUCTION / BEEROCK ENTERPRISES INCORPORATED | 8632 | 2022 | 2023-04-05 | 03/23/2022 | 68249.23 | 0 | 2023-04-08 | 3
2022 | Region VIII | LEYTE | VILLABA (LEYTE) | P00631713VS | Construction of Flood Mitigation Structure | 124.3902 | 11.2113 | 48999330.68 | 48019343.9 | 2023 | RJIR ENTERPRISES CORPORATION | 8633 | 2022 | 2023-03-08 | 06/06/2022 | 979986.78 | 0 | 2023-04-05 | 28
2023 | Region XII | SOUTH COTABATO | TUPI (SOUTH COTABATO) | P00721311MN | Construction of Flood Mitigation Structure | 124.9676 | 6.3135 | 53075000 | 53074049.88 | 2023 | AMPLEX CONSTRUCTION AND SUPPLIES | 8634 | 2023 | 2023-12-02 | 03/30/2023 | 950.12 | 0 | 2023-12-01 |  | 1
2024 | Region X | MISAMIS ORIENTAL | JASAAN (MISAMIS ORIENTAL) | P00820285MN | Construction of Flood Mitigation Structure | 124.7409 | 8.6917 | 96500000 | 96500000 | 2024 | SISBRO CONSTRUCTION CORPORATION (FORMERLY: SISBRO CONSTRUCTION & SUPPLY) | 8635 | 2024 | 2024-07-24 | 02/05/2024 | 0 | 0 | 2024-12-06 | 135
2024 | Region X | BUKIDNON | TALAKAG (BUKIDNON) | P00820145MN | Construction of Flood Mitigation Structure | 124.5891 | 8.2888 | 49000000 | 49000000 | 2024 | RAMISES CONSTRUCTION | 8636 | 2024 | 2024-12-26 | 02/16/2024 | 0 | 0 | 2025-01-24 | 29
2024 | Region VIII | LEYTE | DAGAMI (LEYTE) | P00820410VS | Construction of Flood Mitigation Structure | 124.8779 | 11.0806 | 48999487.54 | 48949180.01 | 2024 | XDR CONSTRUCTION AND SUPPLY | 8637 | 2024 | 2024-10-23 | 02/22/2024 | 50307.53 | 0 | 2024-10-27 | 4
2024 | Region X | MISAMIS ORIENTAL | JASAAN (MISAMIS ORIENTAL) | P00820286MN | Construction of Flood Mitigation Structure | 124.7411 | 8.6911 | 96500000 | 96500000 | 2024 | SISBRO CONSTRUCTION CORPORATION (FORMERLY: SISBRO CONSTRUCTION & SUPPLY) | 8638 | 2024 | 2024-07-25 | 02/05/2024 | 0 | 0 | 2024-11-19 | 117
2023 | Region VIII | LEYTE | VILLABA (LEYTE) | P00733316VS | Construction of Flood Mitigation Structure | 124.3903 | 11.2278 | 48999995.14 | 48754995.16 | 2023 | RJIR ENTERPRISES CORPORATION | 8639 | 2023 | 2023-12-05 | 05/04/2023 | 244999.98 | 0 | 2024-03-02 | 88
2022 | Region XII | SULTAN KUDARAT | LAMBAYONG (MARIANO MARCOS) (SULTAN KUDARAT) | P00620287MN | Construction of Flood Mitigation Structure | 124.5894 | 6.7925 | 48883568.47 | 48833568.47 | 2022 | CS CONST. AND SUPPLY INC. (FORMERLY: CS CONSTRUCTION AND SUPPLY) | 8640 | 2022 | 2022-12-16 | 02/22/2022 | 50000 | 0 | 2023-01-06 | 21
2022 | Region VIII | LEYTE | ALANGALANG (LEYTE) | P00620413VS | Construction of Flood Mitigation Structure | 124.8804 | 11.1936 | 24500000 | 24444842.56 | 2022 | A2C ENTERPRISES INC. (FORMERLY: M.G. CORPIN CONSTRUCTION) | 8641 | 2022 | 2022-12-12 | 05/20/2022 | 55157.44 | 0 | 2022-12-27 | 15
2022 | Region VIII | LEYTE | VILLABA (LEYTE) | P00620416VS | Construction of Flood Mitigation Structure | 124.3905 | 11.2275 | 48999999.77 | 48019999.8 | 2023 | RJIR ENTERPRISES CORPORATION | 8642 | 2022 | 2023-01-23 | 03/25/2022 | 979999.97 | 0 | 2023-01-22 |  | 1
2022 | Region VIII | LEYTE | HILONGOS (LEYTE) | P00633027VS | Construction of Flood Mitigation Structure | 124.7418 | 10.3807 | 49000000 | 48436562.36 | 2022 | RJIR ENTERPRISES CORPORATION | 8643 | 2022 | 2022-12-24 | 03/30/2022 | 563437.64 | 0 | 2022-12-23 |  | 1
2022 | Region VIII | LEYTE | ALANGALANG (LEYTE) | P00620412VS | Construction of Flood Mitigation Structure | 124.8805 | 11.1934 | 29400000 | 29350002.32 | 2022 | VHITS D. G. BUILDERS & ENTERPRISES | 8644 | 2022 | 2022-10-11 | 05/20/2022 | 49997.68 | 0 | 2022-11-09 | 29
2024 | Region VIII | LEYTE | VILLABA (LEYTE) | P00820234VS | Construction of Flood Mitigation Structure | 124.3909 | 11.2127 | 48999999.49 | 48899918.9 | 2024 | KAUIE BUILDERS & SUPPLIES INC. (FORMERLY: KAUIE BUILDERS AND CONSTRUCTION SUPPLIES) | 8645 | 2024 | 2024-09-03 | 03/25/2024 | 100080.59 | 0 | 2025-01-22 | 141
2023 | Region X | BUKIDNON | MALITBOG (BUKIDNON) | P00721264MN | Construction of Revetment | 125.0221 | 8.5543 | 12923280 | 12868659.67 | 2023 | RAMISES CONSTRUCTION | 8646 | 2023 | 2023-07-30 | 03/27/2023 | 54620.33 | 0 | 2023-07-29 |  | 1
2022 | Region XII | SULTAN KUDARAT | COLUMBIO (SULTAN KUDARAT) | P00620291MN | Construction of Flood Mitigation Structure | 124.9678 | 6.6484 | 37681366.27 | 36720677.65 | 2023 | ABU CONSTRUCTION | 8647 | 2022 | 2023-03-30 | 02/22/2022 | 960688.62 | 0 | 2023-01-15 |  | 74
2024 | Region XII | SULTAN KUDARAT | ISULAN (CAPITAL) (SULTAN KUDARAT) | P00820417MN | Construction of Flood Mitigation Structure | 124.5898 | 6.5888 | 44934870.16 | 44883889.43 | 2024 | SOPHIA GEU CONSTRUCTION AND SUPPLY CORPORATION (FORMERLY:SOPHIA CONSTRUCTION AND SUPPLY) | 8648 | 2024 | 2024-06-10 | 02/15/2024 | 50980.73 | 0 | 2024-08-26 | 77
2024 | Region X | BUKIDNON | MANOLO FORTICH (BUKIDNON) | P00820398MN | Construction of Flood Mitigation Structure | 124.881 | 8.3765 | 6860000 | 6860000 | 2024 | BUILDZONE CONSTRUCTION AND SUPPLY | 8649 | 2024 | 2024-12-03 | 06/21/2024 | 0 | 0 | 2024-12-04 | 1
2023 | Region VIII | LEYTE | ABUYOG (LEYTE) | P00721584VS | Construction of Flood Mitigation Structure | 124.7418 | 10.3807 | 50903750 | 50283641.39 | 2023 | C N E CONSTRUCTION | 8650 | 2023 | 2023-12-29 | 04/04/2023 | 620108.61 | 0 | 2023-12-28 |  | 1
2024 | Region VIII | LEYTE | VILLABA (LEYTE) | P00820233VS | Construction of Flood Mitigation Structure | 124.3909 | 11.2144 | 48999998 | 48899611.47 | 2024 | KAUIE BUILDERS & SUPPLIES INC. (FORMERLY: KAUIE BUILDERS AND CONSTRUCTION SUPPLIES) | 8651 | 2024 | 2024-09-03 | 03/07/2024 | 100386.53 | 0 | 2025-01-04 | 123
2022 | Region VIII | LEYTE | TANAUAN (LEYTE) | P00620066VS | Construction of Flood Mitigation Structure | 125.0221 | 11.1158 | 58267835.85 | 58382391.64 | 2022 | 888 ACY ENTERPRISES / JGO BUILDERS | 8652 | 2022 | 2022-10-29 | 03/07/2022 | 0 | 114555.79 | 2022-10-28 |  | 1
2021 | Region VIII | LEYTE |  | P00549989VS | Construction of Flood Mitigation Structure | 124.393 | 11.2164 | 29399995.42 | 28664998.43 | 2022 | RJIR ENTERPRISES CORPORATION | 8653 | 2021 | 2022-09-01 | 11/28/2021 | 734996.99 | 0 | 2022-10-13 | 42
2023 | Region VIII | LEYTE | DULAG (LEYTE) | P00721796VS | Construction of Spur Dike | 124.9689 | 10.9508 | 63689999.51 | 63371976.78 | 2024 | LANOY CONSTRUCTION | 8654 | 2023 | 2024-03-29 | 04/26/2023 | 318022.73 | 0 | 2024-03-28 |  | 1
2022 | Region X | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY (CAPITAL) (MISAMIS ORIENTAL) | P00631088MN | Construction of Drainage Structure | 124.3931 | 8.2754 | 4950000 | 4825876.1 | 2023 | JAMRAY BUILDERS AND ENTERPRISES | 8655 | 2022 | 2023-10-01 | 03/28/2022 | 124123.9 | 0 | 2022-09-30 |  | 366
2023 | Region VIII | LEYTE | BURAUEN (LEYTE) | P00721794VS | Construction of Flood Mitigation Structure | 124.8815 | 10.9675 | 55487270.16 | 55280408.9 | 2024 | LANOY CONSTRUCTION | 8656 | 2023 | 2024-02-24 | 03/13/2023 | 206861.26 | 0 | 2024-02-23 |  | 1
2022 | Region X | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY (CAPITAL) (MISAMIS ORIENTAL) | P00631087MN | Construction of Drainage Structure | 124.3931 | 8.2754 | 4950000 | 4950000 | 2022 | GREEN BUILDER AND ENTERPRISES | 8657 | 2022 | 2022-10-28 | 06/27/2022 | 0 | 0 | 2022-10-27 |  | 1
2024 | Region VIII | LEYTE | PALO (LEYTE) | P00832679VS | Construction of Drainage Structure | 124.9695 | 11.1433 | 29700000 | 29656565.85 | 2024 | G.O.C. BUILDERS | 8658 | 2024 | 2024-08-14 | 02/22/2024 | 43434.15 | 0 | 2024-08-13 |  | 1
2022 | Region VIII | BILIRAN | CABUCGAYAN (BILIRAN) | P00620158VS | Construction of Flood Mitigation Structure | 124.5909 | 11.4859 | 24474493.5 | 23471039.25 | 2022 | M.B. ANG CONSTRUCTION & SUPPLY | 8659 | 2022 | 2022-07-30 | 02/21/2022 | 1003454.25 | 0 | 2022-07-29 |  | 1
2023 | Region VIII | LEYTE | ALBUERA (LEYTE) | P00731642VS | Construction of Flood Mitigation Structure | 124.7419 | 10.8793 | 96499121.55 | 96362987.12 | 2023 | COLLERA CONSTRUCTION | 8660 | 2023 | 2023-11-30 | 03/15/2023 | 136134.43 | 0 | 2024-01-07 | 38
2023 | Region VIII | SOUTHERN LEYTE | SOGOD (SOUTHERN LEYTE) | P00721609VS | Construction of Flood Mitigation Structure | 125.0226 | 10.371 | 90710243.83 | 90709209.85 | 2024 | DYSON CONSTRUCTION AND TRADING CORPORATION / UNIMASTERS CONGLOMERATION, INCORPORATED | 8661 | 2023 | 2024-07-16 | 06/06/2023 | 1033.98 | 0 | 2024-07-15 |  | 1
2023 | Region VIII | LEYTE | ALBUERA (LEYTE) | P00721553VS | Construction of Flood Mitigation Structure | 124.7419 | 10.8792 | 96500000 | 96499999.16 | 2024 | RJIR ENTERPRISES CORPORATION | 8662 | 2023 | 2024-01-31 | 04/11/2023 | 0.84 | 0 | 2024-02-03 | 3
2022 | Region VIII | LEYTE | TACLOBAN CITY (CAPITAL) (LEYTE) | P00630680VS | Construction of Slope Protection Structure | 124.9703 | 11.2533 | 49498489.75 | 49473423.01 | 2022 | EZJONES CONSTRUCTION INC. | 8663 | 2022 | 2022-08-25 | 03/10/2022 | 25066.74 | 0 | 2022-11-03 | 70
2021 | Region X | BUKIDNON |  | P00522300MN | Construction of Flood Mitigation Structure | 124.7421 | 7.7476 | 88780000 | 42477952 | 2022 | JEJOR'S CONSTRUCTION CORPORATION | 8664 | 2021 | 2022-10-31 | 08/16/2021 | 46302048 | 0 | 2022-03-12 |  | 233
2023 | Region V | CATANDUANES | GIGMOTO (CATANDUANES) | P00737570LZ | Construction of Flood Mitigation Structure | 124.3933 | 13.7799 | 9899999.27 | 9898760 | 2023 | NQA CONSTRUCTION & SUPPLY | 8665 | 2023 | 2023-07-26 | 02/17/2023 | 1239.27 | 0 | 2023-07-25 |  | 1
2022 | Region VIII | LEYTE | TACLOBAN CITY (CAPITAL) (LEYTE) | P00630689VS | Construction of Drainage Structure | 125.0226 | 11.2038 | 8905344.97 | 8683212.11 | 2022 | MIGHTY A'S CONSTRUCTION & HARDWARE SUPPLY | 8666 | 2022 | 2022-12-22 | 02/16/2022 | 222132.86 | 0 | 2022-12-21 |  | 1
2023 | Region XII | SULTAN KUDARAT | ISULAN (CAPITAL) (SULTAN KUDARAT) | P00721513MN | Construction of Flood Mitigation Structure | 124.591 | 6.5862 | 48940410.28 | 48840410.28 | 2023 | SOPHIA GEU CONSTRUCTION AND SUPPLY CORPORATION (FORMERLY:SOPHIA CONSTRUCTION AND SUPPLY) | 8667 | 2023 | 2023-05-11 | 02/17/2023 | 100000 | 0 | 2023-08-05 | 86
2024 | Region X | MISAMIS ORIENTAL | TALISAYAN (MISAMIS ORIENTAL) | P00836183MN | Construction of Drainage Structure | 124.8831 | 8.9989 | 14850000 | 14850000 | 2025 | CHIU BUILDERS | 8668 | 2024 | 2025-01-10 | 05/17/2024 | 0 | 0 | 2025-01-09 |  | 1
2023 | Region VIII | BILIRAN | ALMERIA (BILIRAN) | P00733306VS | Construction of Flood Mitigation Structure | 124.3939 | 11.6184 | 19585675.56 | 19586246.51 | 2023 | SUNRISE BUILDERS | 8669 | 2023 | 2023-08-21 | 03/30/2023 | 0 | 570.95 | 2023-08-20 |  | 1
2021 | Region VIII | LEYTE |  | P00549883VS | Construction of Slope Protection Structure | 124.9706 | 11.2523 | 96401109.29 | 95326942.74 | 2022 | EZJONES CONSTRUCTION INC. | 8670 | 2021 | 2022-07-15 | 12/01/2021 | 1074166.55 | 0 | 2022-11-05 | 113
2023 | Region VIII | SAMAR (WESTERN SAMAR) | CALBAYOG CITY (SAMAR (WESTERN SAMAR)) | P00721802VS | Construction of Flood Mitigation Structure | 124.5911 | 12.075 | 57514000 | 57382293.04 | 2023 | CDU CONSTRUCTION | 8671 | 2023 | 2023-11-29 | 03/15/2023 | 131706.96 | 0 | 2023-11-28 |  | 1
2021 | Region VIII | LEYTE |  | P00549987VS | Construction of Flood Mitigation Structure | 124.3942 | 11.2154 | 19599996.69 | 19011989.81 | 2022 | KAUIE BUILDERS & SUPPLIES INC. (FORMERLY: KAUIE BUILDERS AND CONSTRUCTION SUPPLIES) | 8672 | 2021 | 2022-07-28 | 11/28/2021 | 588006.88 | 0 | 2022-07-27 |  | 1
2022 | Region X | BUKIDNON | KALILANGAN (BUKIDNON) | P00620124MN | Construction of Flood Mitigation Structure | 124.7422 | 7.7233 | 49000000 | 49000000 | 2023 | PYRAMID CONSOLIDATED BUILDERS & GEN. MDSE. | 8673 | 2022 | 2023-04-17 | 03/15/2022 | 0 | 0 | 2023-04-17 | 0
2022 | Region VIII | LEYTE | DULAG (LEYTE) | P00620283VS | Construction of Flood Mitigation Structure | 125.0232 | 10.9356 | 95999969.92 | 96005970.72 | 2022 | FAIRCHILD BUILDERS & DEVELOPERS, INC. / LANOY CONSTRUCTION | 8674 | 2022 | 2022-12-25 | 03/07/2022 | 0 | 6000.8 | 2022-12-30 | 5
2022 | Region X | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY (CAPITAL) (MISAMIS ORIENTAL) | P00631090MN | Construction of Drainage Structure | 124.3949 | 8.2626 | 4950000 | 3655608.55 | 2022 | FOUNTAINHEAD CONSTRUCTION AND SUPPLY | 8675 | 2022 | 2022-09-30 | 02/21/2022 | 1294391.45 | 0 | 2022-06-16 |  | 106
2021 | Region XII | SOUTH COTABATO |  | P00522255MN | Construction of Revetment | 124.9707 | 6.2496 | 29400000 | 29398635.49 | 2022 | REYDAN BUILDERS | 8676 | 2021 | 2022-07-28 | 03/08/2022 | 1364.51 | 0 | 2022-09-14 | 48
2023 | Region X | MISAMIS ORIENTAL | TALISAYAN (MISAMIS ORIENTAL) | P00721541MN | Construction of Revetment | 124.8849 | 8.9937 | 72375000 | 72375000 | 2024 | RITCHE-NATHALIE BUILDERS & GENERAL MERCHANDISE | 8677 | 2023 | 2024-03-02 | 04/20/2023 | 0 | 0 | 2024-03-01 |  | 1
2022 | Region VIII | LEYTE | TANAUAN (LEYTE) | P00620284VS | Construction of Flood Mitigation Structure | 124.9708 | 11.0951 | 97363937.65 | 97464803.92 | 2022 | EZJONES CONSTRUCTION INC. / MWJ CONSTRUCTION | 8678 | 2022 | 2022-11-09 | 03/24/2022 | 0 | 100866.27 | 2023-03-17 | 128
2022 | Region VIII | LEYTE | ALBUERA (LEYTE) | P00620189VS | Construction of Flood Mitigation Structure | 124.7438 | 10.8585 | 19599938.73 | 19599998.75 | 2022 | RJIR ENTERPRISES CORPORATION | 8679 | 2022 | 2022-07-20 | 02/21/2022 | 0 | 60.02 | 2022-07-19 |  | 1
2024 | Region VIII | LEYTE | PALO (LEYTE) | P00832678VS | Construction of Drainage Structure | 125.024 | 11.0365 | 19800000 | 19779330.56 | 2024 | G.O.C. BUILDERS | 8680 | 2024 | 2024-11-05 | 05/27/2024 | 20669.44 | 0 | 2024-11-04 |  | 1
2023 | Region X | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY (CAPITAL) (MISAMIS ORIENTAL) | P00721635MN | Construction of Flood Mitigation Structure | 124.5917 | 8.4733 | 96500000 | 96500000 | 2024 | RITCHE-NATHALIE BUILDERS & GENERAL MERCHANDISE | 8681 | 2023 | 2024-07-30 | 03/29/2023 | 0 | 0 | 2024-09-03 | 35
2024 | Region XII | COTABATO (NORTH COTABATO) | M'LANG (COTABATO (NORTH COTABATO)) | P00820101MN | Construction of Flood Mitigation Structure | 124.8864 | 6.9453 | 86850000 | 86849999.38 | 2024 | JARGON CONSTRUCTION & SUPPLY | 8682 | 2024 | 2024-12-05 | 02/19/2024 | 0.62 | 0 | 2024-12-07 | 2
2024 | Region VIII | LEYTE | SANTA FE (LEYTE) | P00832619VS | Construction of Flood Mitigation Structure | 124.974 | 11.1405 | 99000000 | 98900000 | 2024 | ONE MYRNA CONSTRUCTION AND SUPPLY | 8683 | 2024 | 2024-07-22 | 02/15/2024 | 100000 | 0 | 2024-11-23 | 124
2024 | Region X | MISAMIS ORIENTAL | MEDINA (MISAMIS ORIENTAL) | P00820911MN | Construction of Flood Mitigation Structure | 125.0243 | 8.9017 | 77200000 | 77200000 | 2024 | EQUALYZ TRADING | 8684 | 2024 | 2024-05-29 | 02/27/2024 | 0 | 0 | 2024-11-21 | 176
2023 | Region VIII | LEYTE | ALBUERA (LEYTE) | P00733318VS | Construction of Flood Mitigation Structure | 124.7438 | 10.8585 | 49000000 | 48849922.65 | 2023 | AQUALINE CONSTRUCTION CORPORATION (FORMERLY: AQUALINE CONSTRUCTION) / EVERBUILT CONSTRUCTION | 8685 | 2023 | 2023-12-03 | 05/08/2023 | 150077.35 | 0 | 2023-12-02 |  | 1
2022 | Region X | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY (CAPITAL) (MISAMIS ORIENTAL) | P00631091MN | Construction of Slope Protection Structure | 124.395 | 8.2959 | 4950000 | 4691762.96 | 2022 | BLACK ROAD CONSTRUCTION | 8686 | 2022 | 2022-10-04 | 03/16/2022 | 258237.04 | 0 | 2022-08-11 |  | 54
2024 | Region VIII | SAMAR (WESTERN SAMAR) | MATUGUINAO (SAMAR (WESTERN SAMAR)) | P00821165VS | Construction of Flood Mitigation Structure | 124.8866 | 12.1447 | 49000000 | 48957864.27 | 2024 | CDU CONSTRUCTION | 8687 | 2024 | 2024-11-06 | 09/03/2024 | 42135.73 | 0 | 2025-04-23 | 168
2022 | Region VIII | SOUTHERN LEYTE | SOGOD (SOUTHERN LEYTE) | P00620233VS | Construction of Flood Mitigation Structure | 125.025 | 10.4329 | 49000000 | 48999998.5 | 2023 | PABLO S. LABASBAS CONSTRUCTION CORPORATION (FORMERLY: PABLOS. LABASBAS CONSTRUCTION CORPORATION) | 8688 | 2022 | 2023-03-14 | 02/10/2022 | 1.5 | 0 | 2023-03-13 |  | 1
2023 | Region XII | SOUTH COTABATO | BANGA (SOUTH COTABATO) | P00734377MN | Construction of Flood Mitigation Structure | 124.744 | 6.4686 | 310576313.2 | 75619408.99 | 2024 | ABU CONSTRUCTION | 8689 | 2023 | 2024-04-11 | 08/30/2023 | 234956904.21 | 0 | 2024-04-10 |  | 1
2021 | Region X | BUKIDNON |  | P00522301MN | Construction of Flood Mitigation Structure | 124.7443 | 7.7479 | 88780000 | 41781267.84 | 2022 | JEJOR'S CONSTRUCTION CORPORATION | 8690 | 2021 | 2022-10-31 | 08/16/2021 | 46998732.16 | 0 | 2022-03-12 |  | 233
2022 | Region XII | SULTAN KUDARAT | LAMBAYONG (MARIANO MARCOS) (SULTAN KUDARAT) | P00630627MN | Construction of Flood Mitigation Structure | 124.5917 | 6.7961 | 36236776.45 | 35511954.62 | 2023 | JARGON CONSTRUCTION & SUPPLY | 8691 | 2022 | 2023-06-15 | 02/22/2022 | 724821.83 | 0 | 2023-02-27 |  | 108
2022 | Region X | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY (CAPITAL) (MISAMIS ORIENTAL) | P00632608MN | Construction of Drainage Structure | 124.395 | 8.2959 | 4950000 | 4900433.19 | 2022 | ZDA CONSTRUCTION AND ENTERPRISES | 8692 | 2022 | 2022-12-22 | 06/08/2022 | 49566.81 | 0 | 2022-10-02 |  | 81
2024 | Region VIII | LEYTE | PALO (LEYTE) | P00832616VS | Construction of Flood Mitigation Structure | 124.9742 | 11.133 | 99000000 | 98919330.45 | 2024 | FAIRCHILD BUILDERS & DEVELOPERS, INC. / GO_SOLID BUILDERS INC. | 8693 | 2024 | 2024-12-16 | 02/23/2024 | 80669.55 | 0 | 2025-01-04 | 19
2024 | Region X | MISAMIS ORIENTAL | TALISAYAN (MISAMIS ORIENTAL) | P00836184MN | Construction of Drainage Structure | 124.888 | 8.9919 | 9900000 | 9897154.82 | 2024 | CHIU BUILDERS | 8694 | 2024 | 2024-11-12 | 04/18/2024 | 2845.18 | 0 | 2024-11-12 | 0
2022 | Region XII | SOUTH COTABATO | POLOMOLOK (SOUTH COTABATO) | P00634422MN | Construction of Drainage Structure | 125.0256 | 6.2525 | 49000000 | 48998762.8 | 2023 | CHL CONSTRUCTION & DEVELOPMENT ENTERPRISES, INC. | 8695 | 2022 | 2023-07-08 | 01/05/2023 | 1237.2 | 0 | 2023-07-07 |  | 1
2022 | Region XII | SOUTH COTABATO | CITY OF KORONADAL (CAPITAL) (SOUTH COTABATO) | P00630625MN | Construction of Flood Mitigation Structure | 124.8881 | 6.4506 | 98000000 | 48999998.25 | 2022 | NIRVANA CONSTRUCTION & SUPPLIES / FFJJ CONSTRUCTION | 8696 | 2022 | 2022-10-07 | 02/18/2022 | 49000001.75 | 0 | 2022-09-11 |  | 26
2022 | Region X | BUKIDNON | KALILANGAN (BUKIDNON) | P00630476MN | Construction of Flood Mitigation Structure | 124.7443 | 7.7491 | 77200000 | 74899002.44 | 2024 | PYRAMID CONSOLIDATED BUILDERS & GEN. MDSE. / TKS BUILDERS & SUPPLIES | 8697 | 2022 | 2024-03-03 | 04/11/2022 | 2300997.56 | 0 | 2023-01-04 |  | 424
2022 | Region VIII | LEYTE | ORMOC CITY (LEYTE) | P00620195VS | Construction of Flood Mitigation Structure | 124.592 | 11.0255 | 29399426.24 | 29399996.87 | 2022 | JV ENTERPRISES | 8698 | 2022 | 2022-10-11 | 02/21/2022 | 0 | 570.63 | 2022-10-17 | 6
2023 | Region VIII | BILIRAN | NAVAL (CAPITAL) (BILIRAN) | P00721697VS | Rehabilitation / Major Repair of Flood Control Structure | 124.3953 | 11.5788 | 39156017.32 | 39156323.62 | 2023 | ROVING PREMIER CONTRACTORS, INC. | 8699 | 2023 | 2023-06-21 | 02/15/2023 | 0 | 306.3 | 2023-08-22 | 62
2022 | Region X | MISAMIS ORIENTAL | MEDINA (MISAMIS ORIENTAL) | P00630589MN | Construction of Flood Mitigation Structure | 125.0258 | 8.8885 | 19600000 | 19600000 | 2022 | IOS CONSTRUCTION SERVICES | 8700 | 2022 | 2022-07-22 | 02/10/2022 | 0 | 0 | 2022-07-29 | 7
2022 | Region VIII | SAMAR (WESTERN SAMAR) | MATUGUINAO (SAMAR (WESTERN SAMAR)) | P00620209VS | Construction of Flood Mitigation Structure | 124.8889 | 12.1256 | 49000000 | 48876644.33 | 2024 | JFR CONSTRUCTION INC. (FORMERLY:JFR CONSTRUCTION) | 8701 | 2022 | 2024-02-19 | 02/08/2022 | 123355.67 | 0 | 2024-04-28 | 69
2023 | Region X | BUKIDNON | PANGANTUCAN (BUKIDNON) | P00721372MN | Construction of Flood Mitigation Structure | 124.7444 | 7.8715 | 16684500 | 16684500 | 2023 | C'ZARLES CONSTRUCTION & SUPPLY | 8702 | 2023 | 2023-09-13 | 02/20/2023 | 0 | 0 | 2023-09-16 | 3
2022 | Region X | CAMIGUIN | SAGAY (CAMIGUIN) | P00620131MN | Construction of Flood Mitigation Structure | 124.7446 | 9.1028 | 45262279.88 | 43224902.92 | 2023 | SHEEN-SHEEN CONSTRUCTION CORPORATION (FORMERLY: SHEEN-SHEEN CONSTRUCTION) | 8703 | 2022 | 2023-05-28 | 05/21/2022 | 2037376.96 | 0 | 2022-11-12 |  | 197
2023 | Region X | CAMIGUIN | SAGAY (CAMIGUIN) | P00721612MN | Construction of Flood Mitigation Structure | 124.7446 | 9.1027 | 46944939.33 | 46937543.46 | 2024 | SHEEN-SHEEN CONSTRUCTION CORPORATION (FORMERLY: SHEEN-SHEEN CONSTRUCTION) | 8704 | 2023 | 2024-04-30 | 04/21/2023 | 7395.87 | 0 | 2023-12-13 |  | 139
2022 | Region X | BUKIDNON | KALILANGAN (BUKIDNON) | P00630478MN | Construction of Flood Mitigation Structure | 124.7447 | 7.7549 | 77200000 | 74142798.44 | 2024 | PYRAMID CONSOLIDATED BUILDERS & GEN. MDSE. / TKS BUILDERS & SUPPLIES | 8705 | 2022 | 2024-03-03 | 04/11/2022 | 3057201.56 | 0 | 2023-01-04 |  | 424
2023 | Region VIII | LEYTE | PALO (LEYTE) | P00733290VS | Construction of Flood Mitigation Structure | 124.9742 | 11.1687 | 115800000 | 115759997.6 | 2024 | EZJONES CONSTRUCTION INC. / MWJ CONSTRUCTION | 8706 | 2023 | 2024-04-19 | 07/04/2023 | 40002.4 | 0 | 2024-04-18 |  | 1
2022 | Region XII | SULTAN KUDARAT | ISULAN (CAPITAL) (SULTAN KUDARAT) | P00620288MN | Construction of Flood Mitigation Structure | 124.5925 | 6.5835 | 48659562.83 | 47675700.22 | 2022 | SOPHIA GEU CONSTRUCTION AND SUPPLY CORPORATION (FORMERLY:SOPHIA CONSTRUCTION AND SUPPLY) / CS CONST. AND SUPPLY INC. (FORMERLY: CS CONSTRUCTION AND SUPPLY) | 8707 | 2022 | 2022-08-09 | 02/22/2022 | 983862.61 | 0 | 2022-08-28 | 19
2022 | Region VIII | LEYTE | TACLOBAN CITY (CAPITAL) (LEYTE) | P00620056VS | Construction of Flood Mitigation Structure | 125.0275 | 11.2091 | 81943074.78 | 82017181.14 | 2023 | AQUALINE CONSTRUCTION CORPORATION (FORMERLY: AQUALINE CONSTRUCTION) | 8708 | 2022 | 2023-06-10 | 03/07/2022 | 0 | 74106.36 | 2023-06-09 |  | 1
2022 | Region XII | SOUTH COTABATO | CITY OF KORONADAL (CAPITAL) (SOUTH COTABATO) | P00620097MN | Construction of Flood Mitigation Structure | 124.8897 | 6.4475 | 70866705 | 70866458.53 | 2022 | ABU CONSTRUCTION | 8709 | 2022 | 2022-12-29 | 03/04/2022 | 246.47 | 0 | 2022-11-23 |  | 36
2022 | Region VIII | BILIRAN | CAIBIRAN (BILIRAN) | P00620410VS | Construction of Flood Mitigation Structure | 124.5927 | 11.5601 | 3916380.76 | 3787170.76 | 2022 | QYT CONSTRUCTION AND SUPPLIES | 8710 | 2022 | 2022-08-10 | 03/29/2022 | 129210 | 0 | 2022-08-09 |  | 1
2023 | Region VIII | LEYTE | TANAUAN (LEYTE) | P00721980VS | Construction of Flood Mitigation Structure | 124.9801 | 11.0968 | 106150000 | 106099988.8 | 2024 | EZJONES CONSTRUCTION INC. / MWJ CONSTRUCTION | 8711 | 2023 | 2024-04-29 | 05/31/2023 | 50011.2 | 0 | 2024-04-30 | 1
2022 | Region X | BUKIDNON | KALILANGAN (BUKIDNON) | P00630477MN | Construction of Flood Mitigation Structure | 124.7452 | 7.7513 | 77200000 | 74899470.65 | 2023 | PYRAMID CONSOLIDATED BUILDERS & GEN. MDSE. / TKS BUILDERS & SUPPLIES | 8712 | 2022 | 2023-07-31 | 04/11/2022 | 2300529.35 | 0 | 2023-01-04 |  | 208
2023 | Region X | MISAMIS ORIENTAL | GINGOOG CITY (MISAMIS ORIENTAL) | P00721615MN | Construction of Revetment | 125.0284 | 8.7184 | 49000000 | 49000000 | 2023 | RITCHE-NATHALIE BUILDERS & GENERAL MERCHANDISE | 8713 | 2023 | 2023-11-23 | 03/22/2023 | 0 | 0 | 2023-12-01 | 8
2024 | Region X | CAMIGUIN | SAGAY (CAMIGUIN) | P00820399MN | Construction of Drainage Structure | 124.7459 | 9.1061 | 9799999.22 | 9505538.46 | 2024 | SHEEN-SHEEN CONSTRUCTION CORPORATION (FORMERLY: SHEEN-SHEEN CONSTRUCTION) | 8714 | 2024 | 2024-09-29 | 02/19/2024 | 294460.76 | 0 | 2024-07-10 |  | 81
2022 | Region X | MISAMIS ORIENTAL | MEDINA (MISAMIS ORIENTAL) | P00634966MN | Construction of Flood Mitigation Structure | 125.0285 | 8.8909 | 19600000 | 19600000 | 2022 | ONE NINE ONE TRADING | 8715 | 2022 | 2022-09-10 | 04/07/2022 | 0 | 0 | 2022-09-23 | 13
2023 | Region X | BUKIDNON | PANGANTUCAN (BUKIDNON) | P00721371MN | Construction of Flood Mitigation Structure | 124.7462 | 7.872 | 28919800 | 28919800 | 2023 | C'ZARLES CONSTRUCTION & SUPPLY | 8716 | 2023 | 2023-11-08 | 02/20/2023 | 0 | 0 | 2023-11-09 | 1
2024 | Region VIII | BILIRAN | NAVAL (CAPITAL) (BILIRAN) | P00820223VS | Construction of Revetment | 124.3954 | 11.5842 | 9790314.76 | 9791565.03 | 2024 | MKB BUILDERS AND SUPPLY | 8717 | 2024 | 2024-06-04 | 02/14/2024 | 0 | 1250.27 | 2024-06-03 |  | 1
2023 | Region VIII | BILIRAN | ALMERIA (BILIRAN) | P00721960VS | Construction of Flood Mitigation Structure | 124.3957 | 11.62 | 14694210.87 | 14694663.36 | 2023 | SUNRISE BUILDERS | 8718 | 2023 | 2023-10-16 | 03/09/2023 | 0 | 452.49 | 2023-08-27 |  | 50
2024 | Region X | BUKIDNON | PANGANTUCAN (BUKIDNON) | P00820020MN | Construction of Flood Mitigation Structure | 124.7464 | 7.872 | 72375000 | 70727334.57 | 2025 | C'ZARLES CONSTRUCTION & SUPPLY | 8719 | 2024 | 2025-01-30 | 05/03/2024 | 1647665.43 | 0 | 2025-02-25 | 26
2022 | Region XII | SULTAN KUDARAT | LAMBAYONG (MARIANO MARCOS) (SULTAN KUDARAT) | P00630628MN | Construction of Flood Mitigation Structure | 124.5929 | 6.7989 | 36244429.84 | 35747834.15 | 2023 | VICENTE T. LAO CONSTRUCTION | 8720 | 2022 | 2023-02-06 | 02/22/2022 | 496595.69 | 0 | 2023-01-06 |  | 31
2022 | Region VIII | SOUTHERN LEYTE | CITY OF MAASIN (CAPITAL) (SOUTHERN LEYTE) | P00633210VS | Construction of Slope Protection Structure | 124.8903 | 10.219 | 69300000 | 69299998.05 | 2023 | JGO BUILDERS | 8721 | 2022 | 2023-06-16 | 04/06/2022 | 1.95 | 0 | 2023-06-15 |  | 1
2023 | Region VIII | NORTHERN SAMAR | LAS NAVAS (NORTHERN SAMAR) | P00721718VS | Construction of Flood Mitigation Structure | 125.0302 | 12.3392 | 28174744.13 | 28171755.08 | 2023 | JCL CONSTRUCTION AND SUPPLY | 8722 | 2023 | 2023-11-24 | 02/27/2023 | 2989.05 | 0 | 2023-09-23 |  | 62
2023 | Region VIII | LEYTE | TANAUAN (LEYTE) | P00721981VS | Construction of Flood Mitigation Structure | 124.9802 | 11.0976 | 106150000 | 106099996.4 | 2024 | EZJONES CONSTRUCTION INC. / MWJ CONSTRUCTION | 8723 | 2023 | 2024-05-27 | 06/29/2023 | 50003.6 | 0 | 2024-05-29 | 2
2024 | Region X | BUKIDNON | PANGANTUCAN (BUKIDNON) | P00820019MN | Construction of Flood Mitigation Structure | 124.7466 | 7.8735 | 72375000 | 70821287.43 | 2025 | C'ZARLES CONSTRUCTION & SUPPLY | 8724 | 2024 | 2025-01-30 | 05/03/2024 | 1553712.57 | 0 | 2025-02-25 | 26
2022 | Region VIII | LEYTE | BABATNGON (LEYTE) | P00633236VS | Construction of Flood Mitigation Structure | 124.8905 | 11.3889 | 29700000 | 29679661.26 | 2022 | GO_SOLID BUILDERS INC. | 8725 | 2022 | 2022-12-26 | 05/20/2022 | 20338.74 | 0 | 2022-12-25 |  | 1
2024 | Region XII | SOUTH COTABATO | GENERAL SANTOS CITY (DADIANGAS) (SOUTH COTABATO) | P00820204MN | Construction of Flood Mitigation Structure | 125.0308 | 6.0668 | 14700000 | 14644747.05 | 2024 | GRECO CONSTRUCTION AND SUPPLY | 8726 | 2024 | 2024-07-22 | 03/12/2024 | 55252.95 | 0 | 2024-07-21 |  | 1
2022 | Region XII | SULTAN KUDARAT | BAGUMBAYAN (SULTAN KUDARAT) | P00620094MN | Construction of Flood Mitigation Structure | 124.5933 | 6.5786 | 62725000 | 43632913.5 | 2023 | CASTILLANES CONSTRUCTION AND SUPPLY / C.B. GARAY PHILWIDE BUILDERS | 8727 | 2022 | 2023-05-08 | 03/18/2022 | 19092086.5 | 0 | 2022-11-17 |  | 172
2022 | Region X | BUKIDNON | KIBAWE (BUKIDNON) | P00630496MN | Construction of Revetment | 124.9816 | 7.5698 | 57900000 | 57900000 | 2023 | PYRAMID CONSOLIDATED BUILDERS & GEN. MDSE. | 8728 | 2022 | 2023-02-01 | 02/18/2022 | 0 | 0 | 2023-01-31 |  | 1
2022 | Region X | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY (CAPITAL) (MISAMIS ORIENTAL) | P00631086MN | Construction of Drainage Structure | 124.3959 | 8.2905 | 4950000 | 4687588.04 | 2023 | BLACK ROAD CONSTRUCTION | 8729 | 2022 | 2023-09-21 | 03/16/2022 | 262411.96 | 0 | 2022-07-13 |  | 435
2022 | Region X | BUKIDNON | KALILANGAN (BUKIDNON) | P00630479MN | Construction of Flood Mitigation Structure | 124.7471 | 7.7578 | 77200000 | 77200000 | 2025 | PYRAMID CONSOLIDATED BUILDERS & GEN. MDSE. | 8730 | 2022 | 2025-03-30 | 04/11/2022 | 0 | 0 | 2023-01-04 |  | 816
2023 | Region XII | SOUTH COTABATO | CITY OF KORONADAL (CAPITAL) (SOUTH COTABATO) | P00732169MN | Construction of Flood Mitigation Structure | 124.8917 | 6.4454 | 49000000 | 24442424.42 | 2023 | REYDAN BUILDERS | 8731 | 2023 | 2023-08-07 | 04/17/2023 | 24557575.58 | 0 | 2023-08-06 |  | 1
2022 | Region X | MISAMIS ORIENTAL | MEDINA (MISAMIS ORIENTAL) | P00630590MN | Construction of Flood Mitigation Structure | 125.0326 | 8.8949 | 19600000 | 19600000 | 2022 | IOS CONSTRUCTION SERVICES | 8732 | 2022 | 2022-09-17 | 02/10/2022 | 0 | 0 | 2022-09-27 | 10
2024 | Region VIII | LEYTE | VILLABA (LEYTE) | P00820230VS | Construction of Flood Mitigation Structure | 124.3963 | 11.2131 | 48999999.39 | 48754998.58 | 2024 | RJIR ENTERPRISES CORPORATION | 8733 | 2024 | 2024-11-25 | 02/14/2024 | 245000.81 | 0 | 2024-12-13 | 18
2023 | Region X | MISAMIS ORIENTAL | TAGOLOAN (MISAMIS ORIENTAL) | P00721547MN | Construction of Flood Mitigation Structure | 124.7474 | 8.5566 | 77200000 | 77200000 | 2023 | RITCHE-NATHALIE BUILDERS & GENERAL MERCHANDISE | 8734 | 2023 | 2023-10-13 | 03/17/2023 | 0 | 0 | 2023-11-26 | 44
2022 | Region VIII | NORTHERN SAMAR | CATARMAN (CAPITAL) (NORTHERN SAMAR) | P00620205VS | Construction of Flood Mitigation Structure | 124.5947 | 12.372 | 48999889.14 | 48273490.24 | 2022 | RNMK CONSTRUCTION, SUPPLY AND DEVELOPMENT CORP. (FOR: RNMK CONST. & DEV'T) | 8735 | 2022 | 2022-09-30 | 02/21/2022 | 726398.9 | 0 | 2022-09-18 |  | 12
2024 | Region VIII | BILIRAN | NAVAL (CAPITAL) (BILIRAN) | P00834676VS | Rehabilitation / Major Repair of Flood Control Structure | 124.3971 | 11.5778 | 24488590.31 | 23957986.34 | 2024 | RMA BUILDERS & SUPPLIES CORPORATION | 8736 | 2024 | 2024-07-28 | 02/25/2024 | 530603.97 | 0 | 2024-07-27 |  | 1
2023 | Region VIII | LEYTE | TACLOBAN CITY (CAPITAL) (LEYTE) | P00732052VS | Construction of Drainage Structure | 124.9816 | 11.2356 | 4946417.19 | 4916992.38 | 2023 | ADB DYNAMIC BUILDERS & SUPPLY | 8737 | 2023 | 2023-09-24 | 06/16/2023 | 29424.81 | 0 | 2023-09-23 |  | 1
2024 | Region VIII | LEYTE | ALANGALANG (LEYTE) | P00821060VS | Construction of Flood Mitigation Structure | 124.8931 | 11.1913 | 49000000 | 48974657.75 | 2024 | A2C ENTERPRISES INC. (FORMERLY: M.G. CORPIN CONSTRUCTION) | 8738 | 2024 | 2024-10-21 | 04/26/2024 | 25342.25 | 0 | 2024-11-10 | 20
2022 | Region X | MISAMIS ORIENTAL | MEDINA (MISAMIS ORIENTAL) | P00630591MN | Construction of Flood Mitigation Structure | 125.0329 | 8.8947 | 19600000 | 19600000 | 2022 | EQUALYZ TRADING | 8739 | 2022 | 2022-07-25 | 02/10/2022 | 0 | 0 | 2022-07-29 | 4
2022 | Region X | BUKIDNON | KALILANGAN (BUKIDNON) | P00630481MN | Construction of Flood Mitigation Structure | 124.7482 | 7.7632 | 70445000 | 67648074.81 | 2024 | PYRAMID CONSOLIDATED BUILDERS & GEN. MDSE. | 8740 | 2022 | 2024-01-28 | 04/11/2022 | 2796925.19 | 0 | 2022-12-05 |  | 419
2022 | Region VIII | LEYTE | VILLABA (LEYTE) | P00620187VS | Construction of Flood Mitigation Structure | 124.398 | 11.2238 | 48999999.77 | 48754999.65 | 2023 | RJIR ENTERPRISES CORPORATION | 8741 | 2022 | 2023-01-23 | 03/25/2022 | 245000.12 | 0 | 2023-01-22 |  | 1
2021 | Region XII | SULTAN KUDARAT |  | P00522263MN | Construction of Flood Mitigation Structure | 124.5982 | 6.8077 | 45707637.14 | 45250027.88 | 2022 | CS CONST. AND SUPPLY INC. (FORMERLY: CS CONSTRUCTION AND SUPPLY) | 8742 | 2021 | 2022-10-18 | 11/23/2021 | 457609.26 | 0 | 2022-10-20 | 2
2023 | Region VIII | LEYTE | PALO (LEYTE) | P00721703VS | Construction of Flood Mitigation Structure | 124.9816 | 11.1655 | 49000000 | 48509603.99 | 2023 | JGO BUILDERS | 8743 | 2023 | 2023-09-11 | 03/24/2023 | 490396.01 | 0 | 2023-10-08 | 27
2023 | Region XII | COTABATO (NORTH COTABATO) | PRESIDENT ROXAS (COTABATO (NORTH COTABATO)) | P00721390MN | Construction of Flood Mitigation Structure | 125.0367 | 7.0964 | 29400000 | 29400000 | 2023 | LLABAN CONSTRUCTION & SUPPLY (FORMERLY: LLABAN CON | 8744 | 2023 | 2023-09-28 | 03/24/2023 | 0 | 0 | 2023-10-29 | 31
2024 | Region X | MISAMIS ORIENTAL | JASAAN (MISAMIS ORIENTAL) | P00820252MN | Construction of Flood Mitigation Structure | 124.7483 | 8.6576 | 95264800 | 95264800 | 2024 | MIKKIL CONSTRUCTION / VICTORIANO C. LIM CONSTRUCTION CORPORATION (FORMERLY: VICTORIANO C. LIM CONSTRUCTION) | 8745 | 2024 | 2024-10-20 | 02/05/2024 | 0 | 0 | 2024-11-22 | 33
2022 | Region X | BUKIDNON | MARAMAG (BUKIDNON) | P00620120MN | Construction of Revetment | 124.9824 | 7.7727 | 23520000 | 23520000 | 2022 | MAFIL BUILDERS, INC. / MORTAR MASTERS & CONCRETE BUILDERS | 8746 | 2022 | 2022-11-06 | 02/10/2022 | 0 | 0 | 2022-11-05 |  | 1
2024 | Region VII | BOHOL | DUERO (BOHOL) | P00820183VS | Construction of Flood Mitigation Structure | 124.3983 | 9.6819 | 39200000 | 39199915.31 | 2024 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY | 8747 | 2024 | 2024-06-15 | 02/28/2024 | 84.69 | 0 | 2024-09-25 | 102
2022 | Region XII | SULTAN KUDARAT | LAMBAYONG (MARIANO MARCOS) (SULTAN KUDARAT) | P00630626MN | Construction of Flood Mitigation Structure | 124.5991 | 6.8058 | 36222801.53 | 36122315.18 | 2022 | CS CONST. AND SUPPLY INC. (FORMERLY: CS CONSTRUCTION AND SUPPLY) | 8748 | 2022 | 2022-10-27 | 02/22/2022 | 100486.35 | 0 | 2022-10-29 | 2
2023 | Region VIII | LEYTE | ALANGALANG (LEYTE) | P00721963VS | Construction of Flood Mitigation Structure | 124.8935 | 11.1922 | 48020000 | 48000157.14 | 2023 | RT BUILDERS | 8749 | 2023 | 2023-10-26 | 04/12/2023 | 19842.86 | 0 | 2023-10-25 |  | 1
2024 | Region X | BUKIDNON | KIBAWE (BUKIDNON) | P00836175MN | Construction of Flood Mitigation Structure | 125.0393 | 7.4241 | 4950000 | 4950000 | 2024 | ROJAYME CONSTRUCTION SERVICES | 8750 | 2024 | 2024-10-22 | 06/10/2024 | 0 | 0 | 2024-10-21 |  | 1
2022 | Region X | BUKIDNON | KALILANGAN (BUKIDNON) | P00630480MN | Construction of Flood Mitigation Structure | 124.7487 | 7.7586 | 96500000 | 96500000 | 2023 | PYRAMID CONSOLIDATED BUILDERS & GEN. MDSE. / TKS BUILDERS & SUPPLIES | 8751 | 2022 | 2023-07-31 | 04/11/2022 | 0 | 0 | 2023-07-30 |  | 1
2023 | Region VIII | BILIRAN | NAVAL (CAPITAL) (BILIRAN) | P00732042VS | Construction of Flood Mitigation Structure | 124.3987 | 11.5913 | 4946693.51 | 4793346.1 | 2023 | QYT CONSTRUCTION AND SUPPLIES | 8752 | 2023 | 2023-05-12 | 02/27/2023 | 153347.41 | 0 | 2023-05-11 |  | 1
2022 | Region XII | SULTAN KUDARAT | LAMBAYONG (MARIANO MARCOS) (SULTAN KUDARAT) | P00630629MN | Construction of Flood Mitigation Structure | 124.5992 | 6.8121 | 39180365.38 | 37901489.13 | 2022 | LEGACY CONSTRUCTION CORPORATION (FORMERLY: LEGACY CONSTRUCTION) | 8753 | 2022 | 2022-10-24 | 02/22/2022 | 1278876.25 | 0 | 2022-10-24 | 0
2022 | Region VIII | LEYTE | ALANGALANG (LEYTE) | P00620411VS | Construction of Flood Mitigation Structure | 124.8961 | 11.2048 | 29400000 | 29350003.78 | 2022 | R&B LAURINE CONSTRUCTION | 8754 | 2022 | 2022-10-12 | 05/20/2022 | 49996.22 | 0 | 2022-11-09 | 28
2022 | Region X | BUKIDNON | QUEZON (BUKIDNON) | P00620116MN | Construction of Revetment | 125.0396 | 7.7244 | 23520000 | 23520000 | 2023 | UY CONDEV CORPORATION (FORMERLY:UY CONSTRUCTION & | 8755 | 2022 | 2023-02-20 | 02/10/2022 | 0 | 0 | 2022-11-16 |  | 96
2023 | Region X | MISAMIS ORIENTAL | TAGOLOAN (MISAMIS ORIENTAL) | P00721548MN | Construction of Flood Mitigation Structure | 124.7491 | 8.5545 | 77200000 | 77200000 | 2023 | RITCHE-NATHALIE BUILDERS & GENERAL MERCHANDISE | 8756 | 2023 | 2023-10-13 | 03/17/2023 | 0 | 0 | 2023-11-26 | 44
2024 | Region XII | COTABATO (NORTH COTABATO) | PRESIDENT ROXAS (COTABATO (NORTH COTABATO)) | P00820197MN | Construction of Dike | 125.0412 | 7.1022 | 49000000 | 48754903.39 | 2025 | MAER SUMMIT KONSTRUKT CO. | 8757 | 2024 | 2025-03-22 | 06/07/2024 | 245096.61 | 0 | 2025-03-21 |  | 1
2023 | Region VII | BOHOL | DUERO (BOHOL) | P00745642VS | Rehabilitation / Major Repair of Flood Control Structure | 124.3996 | 9.68 | 96285770 | 96284961.9 | 2024 | KMCM BUILDERS AND DEVELOPMENT CORPORATION / GICAR CONSTRUCTION, INC. | 8758 | 2023 | 2024-03-06 | 08/14/2023 | 808.1 | 0 | 2024-06-21 | 107
2024 | Region VIII | NORTHERN SAMAR | SAN ROQUE (NORTHERN SAMAR) | P00820254VS | Rehabilitation / Major Repair of Flood Control Structure | 124.8968 | 12.5459 | 48999972.33 | 48958664.15 | 2024 | ESD CRUZ CONSTRUCTION & SUPPLY | 8759 | 2024 | 2024-12-09 | 04/17/2024 | 41308.18 | 0 | 2025-01-10 | 32
2022 | Region X | BUKIDNON | MARAMAG (BUKIDNON) | P00630574MN | Construction of Revetment | 124.9826 | 7.7736 | 39200000 | 39200000 | 2022 | PYRAMID CONSOLIDATED BUILDERS & GEN. MDSE. | 8760 | 2022 | 2022-12-03 | 02/02/2022 | 0 | 0 | 2022-11-27 |  | 6
2022 | Region XII | SULTAN KUDARAT | LAMBAYONG (MARIANO MARCOS) (SULTAN KUDARAT) | P00620290MN | Construction of Flood Mitigation Structure | 124.5992 | 6.8022 | 48989889.72 | 48939622.32 | 2023 | RELY CONSTRUCTION & SUPPLY INC.(FORMERLY: RELY CONSTRUCTION AND SUPPLY) | 8761 | 2022 | 2023-04-17 | 03/21/2022 | 50267.4 | 0 | 2023-04-16 |  | 1
2022 | Region VIII | SAMAR (WESTERN SAMAR) | SAN SEBASTIAN (SAMAR (WESTERN SAMAR)) | P00620219VS | Construction of Flood Mitigation Structure | 125.0414 | 11.6798 | 39199999.88 | 39198893.41 | 2022 | JFR CONSTRUCTION INC. (FORMERLY:JFR CONSTRUCTION) | 8762 | 2022 | 2022-10-21 | 02/14/2022 | 1106.47 | 0 | 2022-10-20 |  | 1
2023 | Region X | BUKIDNON | KALILANGAN (BUKIDNON) | P00721248MN | Construction of Flood Mitigation Structure | 124.7509 | 7.7402 | 142174000 | 139626673 | 2024 | TKS BUILDERS & SUPPLIES | 8763 | 2023 | 2024-04-14 | 04/11/2023 | 2547327 | 0 | 2024-02-03 |  | 71
2024 | Region VIII | BILIRAN | NAVAL (CAPITAL) (BILIRAN) | P00834674VS | Rehabilitation / Major Repair of Flood Control Structure | 124.3998 | 11.5746 | 19594249.53 | 19595819.67 | 2024 | LCTING CONSTRUCTION AND DEVELOPMENT CORPORATION (FORMERLY: L.C. TING CONSTRUCTION) | 8764 | 2024 | 2024-08-04 | 03/13/2024 | 0 | 1570.14 | 2024-08-03 |  | 1
2021 | Region XII | SULTAN KUDARAT |  | P00522262MN | Construction of Flood Mitigation Structure | 124.5997 | 6.8026 | 45712941.45 | 45612941.4 | 2022 | EINS HANA CONSTRUCTION CORPORATION | 8765 | 2021 | 2022-11-02 | 11/23/2021 | 100000.05 | 0 | 2022-11-04 | 2
2022 | Region VIII | NORTHERN SAMAR | SAN ROQUE (NORTHERN SAMAR) | P00620208VS | Rehabilitation / Major Repair of Flood Control Structure | 124.897 | 12.5456 | 48999924.2 | 48998803.15 | 2023 | ESD CRUZ CONSTRUCTION & SUPPLY | 8766 | 2022 | 2023-01-06 | 02/11/2022 | 1121.05 | 0 | 2023-01-05 |  | 1
2022 | Region X | CAMIGUIN | MAMBAJAO (CAPITAL) (CAMIGUIN) | P00620127MN | Construction of Flood Mitigation Structure | 124.7512 | 9.2259 | 19599999.82 | 18619950.53 | 2023 | GCMG CONSTRUCTION | 8767 | 2022 | 2023-03-30 | 05/12/2022 | 980049.29 | 0 | 2022-10-06 |  | 175
2024 | Region XII | COTABATO (NORTH COTABATO) | MAKILALA (COTABATO (NORTH COTABATO)) | P00820412MN | Construction of Revetment | 125.042 | 6.9208 | 49000000 | 48755000 | 2025 | LLABAN CONSTRUCTION & SUPPLY (FORMERLY: LLABAN CON | 8768 | 2024 | 2025-02-17 | 04/17/2024 | 245000 | 0 | 2025-01-29 |  | 19
2023 | Region VII | BOHOL | DUERO (BOHOL) | P00745644VS | Rehabilitation / Major Repair of Flood Control Structure | 124.4002 | 9.6944 | 96280945 | 96280926.01 | 2024 | ZLREJ TRADING AND CONSTRUCTION CORPORATION / WTG CONSTRUCTION & DEVELOPMENT CORPORATION | 8769 | 2023 | 2024-04-22 | 08/11/2023 | 18.99 | 0 | 2024-06-18 | 57
2024 | Region VIII | LEYTE | TANAUAN (LEYTE) | P00820366VS | Construction of Flood Mitigation Structure | 124.9835 | 11.1097 | 96500000 | 96440245.88 | 2024 | AQUALINE CONSTRUCTION CORPORATION (FORMERLY: AQUALINE CONSTRUCTION) | 8770 | 2024 | 2024-08-19 | 02/15/2024 | 59754.12 | 0 | 2024-11-23 | 96
2023 | Region X | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY (CAPITAL) (MISAMIS ORIENTAL) | P00734385MN | Construction of Flood Mitigation Structure | 124.6025 | 8.4989 | 24750000 | 24377496.18 | 2023 | GICAR CONSTRUCTION, INC. | 8771 | 2023 | 2023-11-28 | 03/23/2023 | 372503.82 | 0 | 2023-12-26 | 28
2024 | Region VIII | SAMAR (WESTERN SAMAR) | SAN JORGE (SAMAR (WESTERN SAMAR)) | P00820378VS | Construction of Flood Mitigation Structure | 124.8981 | 11.9636 | 57900000 | 57850536.76 | 2024 | CDU CONSTRUCTION | 8772 | 2024 | 2024-12-17 | 04/18/2024 | 49463.24 | 0 | 2024-12-24 | 7
2024 | Region X | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY (CAPITAL) (MISAMIS ORIENTAL) | P00820273MN | Construction of Flood Mitigation Structure | 124.7516 | 8.4953 | 114835000 | 110634633.4 | 2025 | OLISON CORPORATION / MAMSAR CONSTRUCTION AND INDUSTRIAL CORPORATION | 8773 | 2024 | 2025-04-12 | 05/03/2024 | 4200366.6 | 0 | 2025-04-11 |  | 1
2024 | Region XII | COTABATO (NORTH COTABATO) | MAKILALA (COTABATO (NORTH COTABATO)) | P00820413MN | Construction of Revetment | 125.042 | 6.9208 | 49000000 | 48778642.42 | 2024 | R.D. INTERIOR JUNIOR CONSTRUCTION / ARBY'S BUILDERS AND CONSTRUCTION SUPPLY CORP. | 8774 | 2024 | 2024-12-05 | 03/21/2024 | 221357.58 | 0 | 2025-01-02 | 28
2024 | Region VIII | LEYTE | TANAUAN (LEYTE) | P00820367VS | Construction of Flood Mitigation Structure | 124.9835 | 11.1097 | 96500000 | 96399868.3 | 2024 | LEDA CONSTRUCTION INCORPORATED / TACLOBAN 6500 INC.(FORMERLY:LTZ CONSTRUCTION AND SUPPLY) | 8775 | 2024 | 2024-07-25 | 04/11/2024 | 100131.7 | 0 | 2025-01-18 | 177
2021 | Region X | MISAMIS ORIENTAL |  | P00522065MN | Construction of Flood Mitigation Structure | 124.6032 | 8.4874 | 28950000 | 26883199.83 | 2023 | VEN RAY CONSTRUCTION CORPORATION | 8776 | 2021 | 2023-03-31 | 09/06/2021 | 2066800.17 | 0 | 2023-03-30 |  | 1
2023 | Region VIII | LEYTE | VILLABA (LEYTE) | P00721965VS | Construction of Flood Mitigation Structure | 124.4026 | 11.2394 | 19599998.65 | 19402201.44 | 2024 | JVM BOLLARD CONSTRUCTION AND SUPPLY | 8777 | 2023 | 2024-02-17 | 06/20/2023 | 197797.21 | 0 | 2024-02-16 |  | 1
2023 | Region VIII | LEYTE | CITY OF BAYBAY (LEYTE) | P00721968VS | Construction of Flood Mitigation Structure | 124.7518 | 10.8373 | 29400000 | 28900234.74 | 2023 | C N E CONSTRUCTION | 8778 | 2023 | 2023-10-18 | 03/23/2023 | 499765.26 | 0 | 2023-12-16 | 59
2022 | Region VII | BOHOL | DUERO (BOHOL) | P00642513VS | Rehabilitation / Major Repair of Flood Control Structure | 124.4067 | 9.7093 | 28950000 | 28948912.26 | 2022 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY | 8779 | 2022 | 2022-11-02 | 04/06/2022 | 1087.74 | 0 | 2022-11-01 |  | 1
2024 | Region XII | COTABATO (NORTH COTABATO) | PRESIDENT ROXAS (COTABATO (NORTH COTABATO)) | P00820102MN | Construction of Revetment | 125.0434 | 7.1013 | 96500000 | 96493871.31 | 2025 | MARCUS CONSTRUCTION & SUPPLY | 8780 | 2024 | 2025-03-19 | 04/09/2024 | 6128.69 | 0 | 2025-03-18 |  | 1
2022 | Region VIII | LEYTE | TANAUAN (LEYTE) | P00620449VS | Construction of Flood Mitigation Structure | 124.9838 | 11.1054 | 96306519.04 | 95455345.07 | 2023 | L.N.R. CONSTRUCTION / SUNWEST, INC. (FORMERLY: SUNWEST CONSTRUCTION & DEVELOPMENT CORPORATION) | 8781 | 2022 | 2023-11-06 | 06/29/2022 | 851173.97 | 0 | 2023-11-05 |  | 1
2021 | Region XII | SULTAN KUDARAT |  | P00522266MN | Construction of Flood Mitigation Structure | 124.6033 | 6.817 | 45710512.44 | 45243240.79 | 2022 | CS CONST. AND SUPPLY INC. (FORMERLY: CS CONSTRUCTION AND SUPPLY) | 8782 | 2021 | 2022-10-18 | 11/23/2021 | 467271.65 | 0 | 2022-10-20 | 2
2024 | Region VIII | LEYTE | ALBUERA (LEYTE) | P00820128VS | Construction of Flood Mitigation Structure | 124.7528 | 10.8515 | 96500000 | 96400000 | 2024 | JM COLLERA KONSTRACT | 8783 | 2024 | 2024-08-20 | 02/19/2024 | 100000 | 0 | 2024-12-13 | 115
2023 | Region VIII | LEYTE | VILLABA (LEYTE) | P00721966VS | Rehabilitation / Major Repair of Flood Control Structure | 124.4078 | 11.2116 | 14699996.71 | 14433400.56 | 2023 | KAUIE BUILDERS & SUPPLIES INC. (FORMERLY: KAUIE BUILDERS AND CONSTRUCTION SUPPLIES) | 8784 | 2023 | 2023-05-18 | 03/09/2023 | 266596.15 | 0 | 2023-09-26 | 131
2023 | Region VIII | LEYTE | TUNGA (LEYTE) | P00721572VS | Construction of Flood Mitigation Structure | 124.7538 | 11.2425 | 55486952.8 | 55480232.43 | 2024 | LANOY CONSTRUCTION | 8785 | 2023 | 2024-04-19 | 04/11/2023 | 6720.37 | 0 | 2024-04-18 |  | 1
2023 | Region VIII | SAMAR (WESTERN SAMAR) | CITY OF CATBALOGAN (CAPITAL) (SAMAR (WESTERN SAMAR)) | P00721921VS | Construction of Flood Mitigation Structure | 124.8981 | 11.7856 | 57899998.26 | 57899899.57 | 2023 | CDU CONSTRUCTION | 8786 | 2023 | 2023-09-24 | 04/18/2023 | 98.69 | 0 | 2024-03-07 | 165
2024 | Region X | MISAMIS ORIENTAL | GINGOOG CITY (MISAMIS ORIENTAL) | P00835779MN | Construction of Flood Mitigation Structure | 125.0436 | 8.8702 | 96500000 | 96500000 | 2024 | RITCHE-NATHALIE DEVELOPMENT CORPORATION (FORMERLY: RITCHE-NATHALIE BUILDERS AND GEN. MERCHANDISE) | 8787 | 2024 | 2024-12-23 | 04/11/2024 | 0 | 0 | 2025-02-22 | 61
2023 | Region VIII | LEYTE | HILONGOS (LEYTE) | P00721619VS | Construction of Flood Mitigation Structure | 124.7544 | 10.3737 | 106150000 | 104982350 | 2024 | KOUZBARY BUILDERS | 8788 | 2023 | 2024-02-05 | 02/21/2023 | 1167650 | 0 | 2024-02-04 |  | 1
2022 | Region X | MISAMIS ORIENTAL | GITAGUM (MISAMIS ORIENTAL) | P00630593MN | Construction of Flood Mitigation Structure | 124.4084 | 8.5973 | 49000000 | 48250000 | 2022 | ROAD EDGE TRADING & DEVELOPMENT SERVICES | 8789 | 2022 | 2022-10-23 | 02/28/2022 | 750000 | 0 | 2022-10-22 |  | 1
2021 | Region VIII | LEYTE |  | P00521716VS | Construction of Flood Mitigation Structure | 124.9848 | 10.7702 | 39200000 | 38643360 | 2022 | LANOY CONSTRUCTION | 8790 | 2021 | 2022-07-09 | 07/27/2021 | 556640 | 0 | 2022-07-08 |  | 1
2024 | Region XII | SULTAN KUDARAT | ISULAN (CAPITAL) (SULTAN KUDARAT) | P00820922MN | Construction of Flood Mitigation Structure | 124.6034 | 6.5447 | 48238812.24 | 48112936.13 | 2024 | KANAWAY BUILDERS CORPORATION | 8791 | 2024 | 2024-12-02 | 05/15/2024 | 125876.11 | 0 | 2024-12-01 |  | 1
2024 | Region X | MISAMIS ORIENTAL | JASAAN (MISAMIS ORIENTAL) | P00820902MN | Construction of Flood Mitigation Structure | 124.7554 | 8.2685 | 48250000 | 48250000 | 2025 | VICENTE T. LAO CONSTRUCTION | 8792 | 2024 | 2025-01-04 | 03/06/2024 | 0 | 0 | 2025-01-03 |  | 1
2023 | Region VIII | LEYTE | TANAUAN (LEYTE) | P00721855VS | Construction of Flood Mitigation Structure | 124.9873 | 11.1116 | 49000000 | 48499177.4 | 2023 | JELM CONSTRUCTION CORP. | 8793 | 2023 | 2023-08-28 | 03/28/2023 | 500822.6 | 0 | 2023-10-12 | 45
2023 | Region VIII | LEYTE | BURAUEN (LEYTE) | P00721797VS | Construction of Flood Mitigation Structure | 124.8995 | 10.9721 | 110974916.5 | 109863168.9 | 2024 | FAIRCHILD BUILDERS & DEVELOPERS, INC. | 8794 | 2023 | 2024-03-13 | 03/15/2023 | 1111747.6 | 0 | 2024-03-12 |  | 1
2023 | Region X | MISAMIS ORIENTAL | TAGOLOAN (MISAMIS ORIENTAL) | P00721543MN | Construction of Flood Mitigation Structure | 124.7555 | 8.5132 | 53075000 | 53075000 | 2023 | EQUALYZ TRADING | 8795 | 2023 | 2023-12-16 | 03/17/2023 | 0 | 0 | 2023-12-15 |  | 1
2023 | Region X | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY (CAPITAL) (MISAMIS ORIENTAL) | P00721373MN | Rehabilitation / Major Repair of Flood Control Structure | 124.6036 | 8.4992 | 24500000 | 24500000 | 2023 | ESR CONSTRUCTION AND DEVELOPMENT CORPORATION (FORMERLY: ESR CONSTRUCTION & SUPPLIES) | 8796 | 2023 | 2023-09-23 | 01/30/2023 | 0 | 0 | 2023-09-22 |  | 1
2022 | Region XII | COTABATO (NORTH COTABATO) | MAKILALA (COTABATO (NORTH COTABATO)) | P00620276MN | Construction of Flood Mitigation Structure | 125.046 | 6.9256 | 49000000 | 48509973.26 | 2022 | LLABAN CONSTRUCTION & SUPPLY (FORMERLY: LLABAN CON | 8797 | 2022 | 2022-11-14 | 02/23/2022 | 490026.74 | 0 | 2022-11-14 | 0
2023 | Region VIII | LEYTE | VILLABA (LEYTE) | P00733315VS | Construction of Flood Mitigation Structure | 124.4091 | 11.218 | 29399998.66 | 28958998.68 | 2023 | RJIR ENTERPRISES CORPORATION | 8798 | 2023 | 2023-09-18 | 04/06/2023 | 440999.98 | 0 | 2023-12-24 | 97
2023 | Region X | MISAMIS ORIENTAL | TAGOLOAN (MISAMIS ORIENTAL) | P00721542MN | Construction of Flood Mitigation Structure | 124.757 | 8.5131 | 96500000 | 96500000 | 2023 | ALPHA & OMEGA GEN. CONTRACTOR & DEVELOPMENT CORP. | 8799 | 2023 | 2023-11-23 | 03/17/2023 | 0 | 0 | 2024-01-01 | 39
2022 | Region X | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY (CAPITAL) (MISAMIS ORIENTAL) | P00620381MN | Construction of Flood Mitigation Structure | 124.6037 | 8.499 | 29400000 | 29399500.5 | 2022 | RAMISES CONSTRUCTION | 8800 | 2022 | 2022-11-25 | 03/24/2022 | 499.5 | 0 | 2023-02-15 | 82
2023 | Region VIII | SOUTHERN LEYTE | SOGOD (SOUTHERN LEYTE) | P00721909VS | Construction of Flood Mitigation Structure | 124.9875 | 10.3854 | 48250000 | 48249095.67 | 2024 | JUCONS CONSTRUCTION OPC (FORMERLY:JUCONS CONSTRUCTION &SUPPLY) | 8801 | 2023 | 2024-05-07 | 09/11/2023 | 904.33 | 0 | 2024-05-06 |  | 1
2024 | Region X | MISAMIS ORIENTAL | TAGOLOAN (MISAMIS ORIENTAL) | P00820017MN | Construction of Flood Mitigation Structure | 124.7578 | 8.511 | 125450000 | 125450000 | 2024 | ARCINUE COMM'L CORPORATION / CROWNWORKS CONSTRUCTION INC. | 8802 | 2024 | 2024-09-12 | 03/11/2024 | 0 | 0 | 2025-01-10 | 120
2021 | Region X | MISAMIS ORIENTAL |  | P00522296MN | Construction of Flood Mitigation Structure | 124.6039 | 8.49 | 83747525 | 73840576.7 | 2024 | VEN RAY CONSTRUCTION CORPORATION | 8803 | 2021 | 2024-03-25 | 07/23/2021 | 9906948.3 | 0 | 2023-12-30 |  | 86
2023 | Region XII | COTABATO (NORTH COTABATO) | MAKILALA (COTABATO (NORTH COTABATO)) | P00721506MN | Construction of Revetment | 125.046 | 6.9256 | 49000000 | 49000000 | 2024 | MAER SUMMIT KONSTRUKT CO. | 8804 | 2023 | 2024-03-07 | 06/21/2023 | 0 | 0 | 2024-03-06 |  | 1
2023 | Region VIII | LEYTE | ABUYOG (LEYTE) | P00721581VS | Construction of Flood Mitigation Structure | 124.9889 | 10.7705 | 53075000 | 52485867.5 | 2024 | LANOY CONSTRUCTION | 8805 | 2023 | 2024-02-27 | 04/04/2023 | 589132.5 | 0 | 2024-02-26 |  | 1
2022 | Region VIII | LEYTE | BURAUEN (LEYTE) | P00620185VS | Construction of Flood Mitigation Structure | 124.9016 | 10.9615 | 48999999.44 | 48998557.03 | 2023 | FAIRCHILD BUILDERS & DEVELOPERS, INC. | 8806 | 2022 | 2023-07-05 | 03/21/2022 | 1442.41 | 0 | 2023-07-04 |  | 1
2021 | Region X | MISAMIS ORIENTAL |  | P00522067MN | Construction of Flood Mitigation Structure | 124.6041 | 8.4908 | 28950000 | 28054126.43 | 2023 | M. MONTESCLAROS ENTERPRISES, INC. | 8807 | 2021 | 2023-12-31 | 07/23/2021 | 895873.57 | 0 | 2023-12-30 |  | 1
2024 | Region VIII | LEYTE | VILLABA (LEYTE) | P00820231VS | Construction of Flood Mitigation Structure | 124.4107 | 11.1698 | 49000000 | 48558999.82 | 2024 | RJIR ENTERPRISES CORPORATION | 8808 | 2024 | 2024-05-28 | 02/14/2024 | 441000.18 | 0 | 2024-12-13 | 199
2024 | Region X | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY (CAPITAL) (MISAMIS ORIENTAL) | P00821076MN | Construction of Flood Mitigation Structure | 124.7587 | 8.5094 | 9800000 | 9499999.99 | 2024 | M & L CONSTRUCTION & ENTERPRISES | 8809 | 2024 | 2024-06-25 | 03/14/2024 | 300000.01 | 0 | 2024-06-24 |  | 1
2024 | Region VII | BOHOL | DUERO (BOHOL) | P00820348VS | Construction of Flood Mitigation Structure | 124.4123 | 9.7135 | 96500000 | 96019080.53 | 2025 | LEDA CONSTRUCTION INCORPORATED | 8810 | 2024 | 2025-04-15 | 03/08/2024 | 480919.47 | 0 | 2025-04-14 |  | 1
2023 | Region VIII | NORTHERN SAMAR | CATUBIG (NORTHERN SAMAR) | P00721720VS | Construction of Flood Mitigation Structure | 125.0473 | 12.4423 | 19599741.7 | 19403506.94 | 2024 | MIK AND MEL CONSTRUCTION AND SUPPLY | 8811 | 2023 | 2024-01-25 | 02/07/2023 | 196234.76 | 0 | 2023-09-03 |  | 144
2022 | Region VIII | LEYTE | BURAUEN (LEYTE) | P00620335VS | Construction of Flood Mitigation Structure | 124.9017 | 10.9616 | 48999999.2 | 48999538.87 | 2023 | FAIRCHILD BUILDERS & DEVELOPERS, INC. | 8812 | 2022 | 2023-03-15 | 03/21/2022 | 460.33 | 0 | 2023-03-14 |  | 1
2023 | Region VIII | LEYTE | TACLOBAN CITY (CAPITAL) (LEYTE) | P00731696VS | Construction of Drainage Structure | 124.9899 | 11.2057 | 4898841.95 | 4849444.8 | 2023 | G.O.C. BUILDERS | 8813 | 2023 | 2023-06-20 | 02/23/2023 | 49397.15 | 0 | 2023-06-19 |  | 1
2024 | Region X | MISAMIS ORIENTAL | TAGOLOAN (MISAMIS ORIENTAL) | P00820018MN | Construction of Flood Mitigation Structure | 124.7606 | 8.5108 | 125450000 | 125450000 | 2024 | ARCINUE COMM'L CORPORATION / CROWNWORKS CONSTRUCTION INC. | 8814 | 2024 | 2024-10-10 | 03/11/2024 | 0 | 0 | 2025-01-10 | 92
2022 | Region X | BUKIDNON | MARAMAG (BUKIDNON) | P00620121MN | Construction of Revetment | 125.0478 | 7.8693 | 23520000 | 23520000 | 2022 | PHILIPPIANS CDO CONSTRUCTION CORPORATION | 8815 | 2022 | 2022-11-25 | 02/10/2022 | 0 | 0 | 2022-11-24 |  | 1
2023 | Region X | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY (CAPITAL) (MISAMIS ORIENTAL) | P00721610MN | Construction of Flood Mitigation Structure | 124.6042 | 8.4992 | 49000000 | 49000000 | 2023 | MORTAR MASTERS & CONCRETE BUILDERS | 8816 | 2023 | 2023-12-21 | 03/14/2023 | 0 | 0 | 2024-01-10 | 20
2023 | Region X | BUKIDNON | IMPASUG-ONG (BUKIDNON) | P00732055MN | Construction of Flood Mitigation Structure | 124.9906 | 8.2917 | 96500000 | 96500000 | 2024 | ROSBILL CONSTRUCTION AND SUPPLY | 8817 | 2023 | 2024-05-22 | 02/28/2023 | 0 | 0 | 2024-06-05 | 14
2023 | Region VIII | NORTHERN SAMAR | MONDRAGON (NORTHERN SAMAR) | P00721585VS | Construction of Flood Mitigation Structure | 124.761 | 12.5231 | 3919874.7 | 3914636.25 | 2023 | C. A. CONSTRUCTION AND SUPPLY | 8818 | 2023 | 2023-12-31 | 08/17/2023 | 5238.45 | 0 | 2024-01-06 | 6
2023 | Region VIII | LEYTE | BURAUEN (LEYTE) | P00721795VS | Construction of Flood Mitigation Structure | 124.902 | 10.9602 | 55487499.76 | 55486287.1 | 2023 | FAIRCHILD BUILDERS & DEVELOPERS, INC. | 8819 | 2023 | 2023-12-15 | 04/11/2023 | 1212.66 | 0 | 2024-02-27 | 74
2022 | Region XII | SOUTH COTABATO | POLOMOLOK (SOUTH COTABATO) | P00620240MN | Construction of Flood Mitigation Structure | 125.0481 | 6.2275 | 70968995 | 70968904.86 | 2022 | AMPLEX CONSTRUCTION AND SUPPLIES | 8820 | 2022 | 2022-11-15 | 03/29/2022 | 90.14 | 0 | 2022-11-20 | 5
2023 | Region VIII | BILIRAN | NAVAL (CAPITAL) (BILIRAN) | P00732040VS | Construction of Drainage Structure | 124.4131 | 11.552 | 4946821.05 | 4840465 | 2023 | MKB BUILDERS AND SUPPLY | 8821 | 2023 | 2023-08-30 | 02/27/2023 | 106356.05 | 0 | 2023-08-29 |  | 1
2021 | Region X | MISAMIS ORIENTAL |  | P00522295MN | Construction of Flood Mitigation Structure | 124.6045 | 8.4847 | 77200000 | 73261616.42 | 2024 | DL ENTERPRISES / MORTAR MASTERS & CONCRETE BUILDERS | 8822 | 2021 | 2024-03-25 | 08/27/2021 | 3938383.58 | 0 | 2022-06-21 |  | 643
2023 | Region X | MISAMIS ORIENTAL | TAGOLOAN (MISAMIS ORIENTAL) | P00721415MN | Construction of Flood Mitigation Structure | 124.7619 | 8.5387 | 289500000 | 282250640.7 | 2025 | RAMISES CONSTRUCTION / EQUI-PARCO CONSTRUCTION COMPANY | 8823 | 2023 | 2025-02-07 | 02/13/2023 | 7249359.3 | 0 | 2023-12-08 |  | 427
2024 | Region VIII | SOUTHERN LEYTE | CITY OF MAASIN (CAPITAL) (SOUTHERN LEYTE) | P00835033VS | Construction of Flood Mitigation Structure | 124.9026 | 10.1858 | 4900000 | 4892155.47 | 2024 | PABLO S. LABASBAS CONSTRUCTION CORPORATION (FORMERLY: PABLOS. LABASBAS CONSTRUCTION CORPORATION) | 8824 | 2024 | 2024-06-06 | 03/07/2024 | 7844.53 | 0 | 2024-06-05 |  | 1
2023 | Region X | BUKIDNON | MARAMAG (BUKIDNON) | P00721246MN | Construction of Flood Mitigation Structure | 125.0482 | 7.8543 | 53075000 | 52518810.52 | 2023 | JT GAMOLO CONSTRUCTION, INCORPORATION (FORMERLY:J.T. GAMOLO CONSTRUCTION) | 8825 | 2023 | 2023-11-24 | 02/28/2023 | 556189.48 | 0 | 2023-11-23 |  | 1
2022 | Region VIII | BILIRAN | NAVAL (CAPITAL) (BILIRAN) | P00620162VS | Construction of Flood Mitigation Structure | 124.4133 | 11.5583 | 29396988.67 | 29397165.65 | 2022 | SUNRISE BUILDERS | 8826 | 2022 | 2022-08-13 | 02/21/2022 | 0 | 176.98 | 2022-08-26 | 13
2023 | Region VIII | LEYTE | PALO (LEYTE) | P00731682VS | Rehabilitation / Major Repair of Drainage Structure | 124.991 | 11.185 | 4900000 | 4885000.65 | 2023 | Z.A.S. CONSTRUCTION AND SUPPLY (FORMERLY: Z.A.S. CONSTRUCTION) | 8827 | 2023 | 2023-10-06 | 05/10/2023 | 14999.35 | 0 | 2023-10-07 | 1
2023 | Region XII | SOUTH COTABATO | NORALA (SOUTH COTABATO) | P00734376MN | Construction of Flood Mitigation Structure | 124.605 | 6.5314 | 310576313.2 | 74137420.79 | 2024 | ABU CONSTRUCTION | 8828 | 2023 | 2024-04-11 | 08/30/2023 | 236438892.41 | 0 | 2024-04-10 |  | 1
2024 | Region X | MISAMIS ORIENTAL | TAGOLOAN (MISAMIS ORIENTAL) | P00835759MN | Construction of Flood Mitigation Structure | 124.7629 | 8.5092 | 96500000 | 96500000 | 2024 | ED1SON DEVELOPMENT & CONSTRUCTION INC. / CROWNWORKS CONSTRUCTION INC. | 8829 | 2024 | 2024-10-18 | 03/11/2024 | 0 | 0 | 2025-01-08 | 82
2024 | Region XII | COTABATO (NORTH COTABATO) | PRESIDENT ROXAS (COTABATO (NORTH COTABATO)) | P00820334MN | Construction of Dike | 125.0489 | 7.1423 | 96500000 | 96499999.99 | 2024 | JARGON CONSTRUCTION & SUPPLY | 8830 | 2024 | 2024-12-19 | 05/17/2024 | 0.01 | 0 | 2025-02-23 | 66
2024 | Region VIII | BILIRAN | NAVAL (CAPITAL) (BILIRAN) | P00832664VS | Construction of Revetment | 124.4147 | 11.5692 | 5934989.62 | 5807387.3 | 2024 | ANG YAP BUILDERS AND AGGREGATE SUPPLIES INC. | 8831 | 2024 | 2024-04-22 | 02/18/2024 | 127602.32 | 0 | 2024-04-26 | 4
2023 | Region VIII | LEYTE | TACLOBAN CITY (CAPITAL) (LEYTE) | P00732053VS | Construction of Flood Mitigation Structure | 124.9935 | 11.1944 | 4947375.47 | 4944375 | 2023 | AGDCON BUILDERS | 8832 | 2023 | 2023-09-05 | 03/23/2023 | 3000.47 | 0 | 2023-07-06 |  | 61
2021 | Region X | MISAMIS ORIENTAL |  | P00522066MN | Construction of Flood Mitigation Structure | 124.6052 | 8.4854 | 28950000 | 27213384.44 | 2022 | ROAD EDGE TRADING & DEVELOPMENT SERVICES | 8833 | 2021 | 2022-12-26 | 09/24/2021 | 1736615.56 | 0 | 2022-04-20 |  | 250
2024 | Region VIII | LEYTE | TUNGA (LEYTE) | P00820122VS | Construction of Flood Mitigation Structure | 124.7647 | 11.2563 | 57900000 | 57899999.79 | 2024 | LANOY CONSTRUCTION | 8834 | 2024 | 2024-12-13 | 03/14/2024 | 0.21 | 0 | 2024-12-31 | 18
2024 | Region XII | COTABATO (NORTH COTABATO) | PRESIDENT ROXAS (COTABATO (NORTH COTABATO)) | P00820411MN | Construction of Dike | 125.0491 | 7.1414 | 49000000 | 48996447.53 | 2024 | JARGON CONSTRUCTION & SUPPLY | 8835 | 2024 | 2024-12-16 | 04/17/2024 | 3552.47 | 0 | 2025-01-29 | 44
2023 | Region VIII | LEYTE | ALANGALANG (LEYTE) | P00733311VS | Construction of Flood Mitigation Structure | 124.9029 | 11.1899 | 49039200 | 48974200 | 2023 | JFR CONSTRUCTION INC. (FORMERLY:JFR CONSTRUCTION) / PYUKEI CONSTRUCTION INC. | 8836 | 2023 | 2023-12-29 | 05/24/2023 | 65000 | 0 | 2023-12-30 | 1
2022 | Region VIII | LEYTE | BABATNGON (LEYTE) | P00632038VS | Construction of Flood Mitigation Structure | 124.9067 | 11.3608 | 49500000 | 49005390.61 | 2023 | JGO BUILDERS | 8837 | 2022 | 2023-03-27 | 05/20/2022 | 494609.39 | 0 | 2023-03-26 |  | 1
2023 | Region VIII | BILIRAN | NAVAL (CAPITAL) (BILIRAN) | P00721700VS | Construction of Flood Mitigation Structure | 124.4157 | 11.5579 | 29393463.85 | 29393468.65 | 2023 | SUNRISE BUILDERS | 8838 | 2023 | 2023-11-11 | 02/20/2023 | 0 | 4.8 | 2023-11-10 |  | 1
2023 | Region VIII | LEYTE | TUNGA (LEYTE) | P00721573VS | Construction of Flood Mitigation Structure | 124.7647 | 11.2565 | 55487499.19 | 55209715.8 | 2024 | LANOY CONSTRUCTION | 8839 | 2023 | 2024-04-13 | 04/26/2023 | 277783.39 | 0 | 2024-04-12 |  | 1
2023 | Region XII | COTABATO (NORTH COTABATO) | PRESIDENT ROXAS (COTABATO (NORTH COTABATO)) | P00721504MN | Construction of Dike | 125.0495 | 7.1414 | 48510000 | 48510000 | 2024 | JARGON CONSTRUCTION & SUPPLY | 8840 | 2023 | 2024-04-11 | 03/22/2023 | 0 | 0 | 2024-02-04 |  | 67
2023 | Region X | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY (CAPITAL) (MISAMIS ORIENTAL) | P00721637MN | Construction of Flood Mitigation Structure | 124.6056 | 8.4986 | 96500000 | 96499465 | 2023 | RITCHE-NATHALIE BUILDERS & GENERAL MERCHANDISE | 8841 | 2023 | 2023-12-22 | 03/29/2023 | 535 | 0 | 2024-04-30 | 130
2022 | Region X | MISAMIS ORIENTAL | GINGOOG CITY (MISAMIS ORIENTAL) | P00620032MN | Construction of Flood Mitigation Structure | 125.0509 | 8.8609 | 96500000 | 95174796.84 | 2023 | JEJOR'S CONSTRUCTION CORPORATION | 8842 | 2022 | 2023-11-26 | 06/29/2022 | 1325203.16 | 0 | 2023-04-23 |  | 217
2023 | Region VIII | NORTHERN SAMAR | ROSARIO (NORTHERN SAMAR) | P00733322VS | Construction of Flood Mitigation Structure | 124.4209 | 12.5221 | 6859812.51 | 6853647.94 | 2023 | SAL CONSTRUCTION | 8843 | 2023 | 2023-10-18 | 07/25/2023 | 6164.57 | 0 | 2023-11-02 | 15
2022 | Region X | BUKIDNON | KIBAWE (BUKIDNON) | P00620118MN | Construction of Revetment | 124.9947 | 7.5787 | 23520000 | 23520000 | 2022 | PYRAMID CONSOLIDATED BUILDERS & GEN. MDSE. | 8844 | 2022 | 2022-11-11 | 02/15/2022 | 0 | 0 | 2022-11-10 |  | 1
2024 | Region X | MISAMIS ORIENTAL | TAGOLOAN (MISAMIS ORIENTAL) | P00835760MN | Construction of Flood Mitigation Structure | 124.765 | 8.5108 | 96500000 | 96500000 | 2024 | ED1SON DEVELOPMENT & CONSTRUCTION INC. / CROWNWORKS CONSTRUCTION INC. | 8845 | 2024 | 2024-11-25 | 03/11/2024 | 0 | 0 | 2025-01-08 | 44
2024 | Region VIII | NORTHERN SAMAR | PAMBUJAN (NORTHERN SAMAR) | P00820252VS | Construction of Flood Mitigation Structure | 124.9068 | 12.5477 | 48999915.71 | 48969801.32 | 2024 | CDU CONSTRUCTION | 8846 | 2024 | 2024-09-08 | 02/12/2024 | 30114.39 | 0 | 2025-01-05 | 119
2023 | Region XII | SULTAN KUDARAT | ISULAN (CAPITAL) (SULTAN KUDARAT) | P00721648MN | Construction of Flood Mitigation Structure | 124.6057 | 6.5354 | 67460599.24 | 67360598.33 | 2024 | SOPHIA GEU CONSTRUCTION AND SUPPLY CORPORATION (FORMERLY:SOPHIA CONSTRUCTION AND SUPPLY) / ALPXR CONST. & BLDRS. CORP | 8847 | 2023 | 2024-01-10 | 06/13/2023 | 100000.91 | 0 | 2024-02-07 | 28
2022 | Region VIII | SAMAR (WESTERN SAMAR) | HINABANGAN (SAMAR (WESTERN SAMAR)) | P00620220VS | Construction of Flood Mitigation Structure | 125.0517 | 11.6919 | 19600000.19 | 19598254.88 | 2022 | ETAN CONSTRUCTION | 8848 | 2022 | 2022-07-20 | 02/09/2022 | 1745.31 | 0 | 2022-07-27 | 7
2023 | Region VIII | SOUTHERN LEYTE | SOGOD (SOUTHERN LEYTE) | P00721910VS | Construction of Flood Mitigation Structure | 124.9948 | 10.4151 | 19300000 | 19299932 | 2024 | JUCONS CONSTRUCTION OPC (FORMERLY:JUCONS CONSTRUCTION &SUPPLY) | 8849 | 2023 | 2024-03-28 | 09/11/2023 | 68 | 0 | 2024-03-27 |  | 1
2023 | Region X | MISAMIS ORIENTAL | JASAAN (MISAMIS ORIENTAL) | P00721545MN | Construction of Flood Mitigation Structure | 124.7652 | 8.6302 | 77200000 | 77200000 | 2023 | RITCHE-NATHALIE BUILDERS & GENERAL MERCHANDISE | 8850 | 2023 | 2023-11-27 | 03/17/2023 | 0 | 0 | 2023-11-26 |  | 1
2022 | Region VIII | NORTHERN SAMAR | PAMBUJAN (NORTHERN SAMAR) | P00620065VS | Construction of Spur Dike | 124.9068 | 12.5449 | 77199579.05 | 77199786.05 | 2022 | JBM ENGINEERS AND SUPPLY / CDU CONSTRUCTION | 8851 | 2022 | 2022-12-02 | 02/21/2022 | 0 | 207 | 2022-12-01 |  | 1
2022 | Region X | BUKIDNON | KIBAWE (BUKIDNON) | P00630575MN | Construction of Revetment | 125.0521 | 7.5309 | 39200000 | 39200000 | 2022 | PYRAMID CONSOLIDATED BUILDERS & GEN. MDSE. | 8852 | 2022 | 2022-12-17 | 02/07/2022 | 0 | 0 | 2022-12-16 |  | 1
2023 | Region XII | COTABATO (NORTH COTABATO) | PIKIT (COTABATO (NORTH COTABATO)) | P00734412MN | Construction of Flood Mitigation Structure | 124.6058 | 6.5354 | 9900000 | 9900000 | 2023 | AKV BUILDERS AND CONSTRUCTION SUPPLIES | 8853 | 2023 | 2023-09-07 | 05/09/2023 | 0 | 0 | 2023-09-06 |  | 1
2023 | Region VIII | LEYTE | TACLOBAN CITY (CAPITAL) (LEYTE) | P00732054VS | Construction of Flood Mitigation Structure | 124.995 | 11.2141 | 9898729.12 | 9714254.25 | 2023 | ZTATIK BUILDER INC. | 8854 | 2023 | 2023-09-30 | 05/26/2023 | 184474.87 | 0 | 2023-10-05 | 5
2022 | Region X | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY (CAPITAL) (MISAMIS ORIENTAL) | P00631089MN | Construction of Drainage Structure | 124.4229 | 8.2814 | 4950000 | 4660068.53 | 2022 | AKC BUILDERS | 8855 | 2022 | 2022-10-14 | 06/08/2022 | 289931.47 | 0 | 2022-10-19 | 5
2024 | Region X | MISAMIS ORIENTAL | JASAAN (MISAMIS ORIENTAL) | P00820287MN | Construction of Flood Mitigation Structure | 124.7652 | 8.6302 | 96500000 | 96500000 | 2024 | MIKKIL CONSTRUCTION / VICTORIANO C. LIM CONSTRUCTION CORPORATION (FORMERLY: VICTORIANO C. LIM CONSTRUCTION) | 8856 | 2024 | 2024-11-25 | 02/05/2024 | 0 | 0 | 2024-12-04 | 9
2022 | Region VIII | SOUTHERN LEYTE | CITY OF MAASIN (CAPITAL) (SOUTHERN LEYTE) | P00632048VS | Construction of Flood Mitigation Structure | 124.9083 | 10.1226 | 4950000 | 4936756.85 | 2022 | 3MC KING CIVIL ENGINEERING CONSTRUCTION | 8857 | 2022 | 2022-08-28 | 04/06/2022 | 13243.15 | 0 | 2022-08-27 |  | 1
2023 | Region X | BUKIDNON | KIBAWE (BUKIDNON) | P00721247MN | Construction of Revetment | 125.0533 | 7.5315 | 53075000 | 53075000 | 2023 | PYRAMID CONSOLIDATED BUILDERS & GEN. MDSE. | 8858 | 2023 | 2023-12-03 | 02/28/2023 | 0 | 0 | 2023-12-02 |  | 1
2024 | Region XII | SULTAN KUDARAT | ISULAN (CAPITAL) (SULTAN KUDARAT) | P00820418MN | Construction of Flood Mitigation Structure | 124.606 | 6.5405 | 45011424.73 | 44944137.95 | 2024 | SOPHIA GEU CONSTRUCTION AND SUPPLY CORPORATION (FORMERLY:SOPHIA CONSTRUCTION AND SUPPLY) | 8859 | 2024 | 2024-06-21 | 02/15/2024 | 67286.78 | 0 | 2024-08-26 | 66
2022 | Region VIII | BILIRAN | BILIRAN (BILIRAN) | P00644459VS | Rehabilitation / Major Repair of Flood Control Structure | 124.425 | 11.5289 | 28941113.4 | 28564526.52 | 2023 | ROVING PREMIER CONTRACTORS, INC. | 8860 | 2022 | 2023-01-13 | 11/10/2022 | 376586.88 | 0 | 2023-04-07 | 84
2024 | Region X | MISAMIS ORIENTAL | JASAAN (MISAMIS ORIENTAL) | P00835766MN | Construction of Flood Mitigation Structure | 124.7669 | 8.6301 | 96500000 | 96500000 | 2024 | RITCHE-NATHALIE DEVELOPMENT CORPORATION (FORMERLY: RITCHE-NATHALIE BUILDERS AND GEN. MERCHANDISE) | 8861 | 2024 | 2024-12-18 | 02/15/2024 | 0 | 0 | 2024-12-17 |  | 1
2024 | Region VIII | SOUTHERN LEYTE | BONTOC (SOUTHERN LEYTE) | P00820258VS | Construction of Flood Mitigation Structure | 124.9092 | 10.3911 | 49000000 | 49000000 | 2024 | FAIRCHILD BUILDERS & DEVELOPERS, INC. / ZTATIK BUILDER INC. | 8862 | 2024 | 2024-10-09 | 02/13/2024 | 0 | 0 | 2024-10-08 |  | 1
2023 | Region X | BUKIDNON | MARAMAG (BUKIDNON) | P00721367MN | Construction of Revetment | 125.0542 | 7.8635 | 29400000 | 29262806.08 | 2023 | PHILIPPIANS CDO CONSTRUCTION CORPORATION | 8863 | 2023 | 2023-12-16 | 04/21/2023 | 137193.92 | 0 | 2023-12-15 |  | 1
2024 | Region XII | SULTAN KUDARAT | ISULAN (CAPITAL) (SULTAN KUDARAT) | P00820423MN | Construction of Flood Mitigation Structure | 124.606 | 6.5393 | 45279587.22 | 45229031.59 | 2024 | ROBETH CONST. AND DEV'T. CORP. (FORMERLY: ROBETH GEN. MDSE. CONST. & SUPPLY) | 8864 | 2024 | 2024-06-15 | 02/15/2024 | 50555.63 | 0 | 2024-09-04 | 81
2022 | Region VIII | LEYTE | CALUBIAN (LEYTE) | P00632042VS | Construction of Flood Mitigation Structure | 124.426 | 11.4492 | 4899994.93 | 4801994.29 | 2022 | RED AXE BUILDERS & SUPPLY | 8865 | 2022 | 2022-07-27 | 03/25/2022 | 98000.64 | 0 | 2022-07-26 |  | 1
2023 | Region XII | SARANGANI | MAASIM (SARANGANI) | P00732496MN | Construction of Slope Protection Structure | 124.9958 | 5.8705 | 19800000 | 19792020.81 | 2024 | THE TRENDSETTER CONSTRUCTION AND SUPPLY CORP. | 8866 | 2023 | 2024-12-23 | 08/08/2023 | 7979.19 | 0 | 2024-10-03 |  | 81
2022 | Region VIII | LEYTE | INOPACAN (LEYTE) | P00620063VS | Construction of Flood Mitigation Structure | 124.7669 | 10.485 | 96500000 | 95520631.32 | 2023 | B. VICENCIO BUILDERS (BVB), INC. (FORMERLY:B. VICENCIO CONSTRUCTION) / C N E CONSTRUCTION | 8867 | 2022 | 2023-01-17 | 03/10/2022 | 979368.68 | 0 | 2023-01-16 |  | 1
2023 | Region X | MISAMIS ORIENTAL | TALISAYAN (MISAMIS ORIENTAL) | P00721539MN | Construction of Revetment | 124.9112 | 8.9802 | 72375000 | 72375000 | 2023 | RITCHE-NATHALIE BUILDERS & GENERAL MERCHANDISE | 8868 | 2023 | 2023-12-26 | 04/25/2023 | 0 | 0 | 2024-01-10 | 15
2022 | Region VIII | SOUTHERN LEYTE | HINUNANGAN (SOUTHERN LEYTE) | P00620234VS | Construction of Flood Mitigation Structure | 125.0544 | 10.2951 | 19600000 | 19599998.8 | 2023 | JQD CONSTRUCTION & GENERAL SERVICES | 8869 | 2022 | 2023-06-19 | 02/10/2022 | 1.2 | 0 | 2023-06-18 |  | 1
2023 | Region XII | SOUTH COTABATO | SANTO NIÃ‘O (SOUTH COTABATO) | P00721511MN | Construction of Flood Mitigation Structure | 124.6069 | 6.5286 | 49000000 | 49000000 | 2023 | ARCINUE COMM'L CORPORATION | 8870 | 2023 | 2023-11-24 | 04/17/2023 | 0 | 0 | 2023-11-23 |  | 1
2023 | Region XII | SARANGANI | MAASIM (SARANGANI) | P00734407MN | Construction of Drainage Structure | 124.9963 | 5.8697 | 49500000 | 49498514.75 | 2024 | REYDAN BUILDERS | 8871 | 2023 | 2024-06-12 | 05/08/2023 | 1485.25 | 0 | 2024-06-11 |  | 1
2022 | Region VIII | LEYTE | ORMOC CITY (LEYTE) | P00620188VS | Construction of Flood Mitigation Structure | 124.6072 | 11.0208 | 19599814.46 | 19599995.43 | 2023 | RJIR ENTERPRISES CORPORATION | 8872 | 2022 | 2023-06-19 | 02/24/2022 | 0 | 180.97 | 2023-06-29 | 10
2022 | Region VIII | SOUTHERN LEYTE | MACROHON (SOUTHERN LEYTE) | P00620222VS | Construction of Flood Mitigation Structure | 124.9145 | 10.0943 | 49000000 | 49000000 | 2022 | ON POINT CONSTRUCTION AND DEVELOPMENT CORPORATION (FORMERLY:ON POINT CONSTRUCTION) | 8873 | 2022 | 2022-07-31 | 02/10/2022 | 0 | 0 | 2022-10-06 | 67
2023 | Region VIII | LEYTE | TACLOBAN CITY (CAPITAL) (LEYTE) | P00731695VS | Construction of Drainage Structure | 124.9966 | 11.1998 | 9799559.01 | 9749397.76 | 2023 | PAFJ CONSTRUCTION AND SUPPLY, INC. | 8874 | 2023 | 2023-08-30 | 04/19/2023 | 50161.25 | 0 | 2023-08-29 |  | 1
2022 | Region VIII | LEYTE | CALUBIAN (LEYTE) | P00634059VS | Construction of Flood Mitigation Structure | 124.426 | 11.4492 | 4899992.87 | 4801991.23 | 2022 | RED AXE BUILDERS & SUPPLY | 8875 | 2022 | 2022-07-27 | 03/25/2022 | 98001.64 | 0 | 2022-07-26 |  | 1
2023 | Region X | MISAMIS ORIENTAL | JASAAN (MISAMIS ORIENTAL) | P00721546MN | Construction of Flood Mitigation Structure | 124.7671 | 8.6301 | 77200000 | 77200000 | 2023 | RITCHE-NATHALIE BUILDERS & GENERAL MERCHANDISE | 8876 | 2023 | 2023-11-27 | 03/17/2023 | 0 | 0 | 2023-11-26 |  | 1
2023 | Region VIII | NORTHERN SAMAR | CATUBIG (NORTHERN SAMAR) | P00721586VS | Construction of Flood Mitigation Structure | 125.0544 | 12.4058 | 55487102.33 | 54377358.61 | 2023 | JUPA CONSTRUCTION | 8877 | 2023 | 2023-10-24 | 02/07/2023 | 1109743.72 | 0 | 2023-11-02 | 9
2023 | Region XII | SULTAN KUDARAT | LAMBAYONG (MARIANO MARCOS) (SULTAN KUDARAT) | P00721471MN | Construction of Flood Mitigation Structure | 124.6089 | 6.685 | 106150000 | 106044862.4 | 2024 | VICENTE T. LAO CONSTRUCTION | 8878 | 2023 | 2024-08-26 | 08/30/2023 | 105137.6 | 0 | 2024-07-21 |  | 36
2023 | Region VIII | LEYTE | MAYORGA (LEYTE) | P00721571VS | Construction of Flood Mitigation Structure | 124.997 | 10.8817 | 55487344.49 | 55482311.18 | 2023 | FAIRCHILD BUILDERS & DEVELOPERS, INC. | 8879 | 2023 | 2023-09-18 | 03/13/2023 | 5033.31 | 0 | 2023-11-30 | 73
2024 | Region VIII | BILIRAN | NAVAL (CAPITAL) (BILIRAN) | P00832670VS | Rehabilitation / Major Repair of Flood Control Structure | 124.4278 | 11.5256 | 6922885.16 | 6775427.7 | 2024 | RMA BUILDERS & SUPPLIES CORPORATION | 8880 | 2024 | 2024-05-04 | 02/18/2024 | 147457.46 | 0 | 2024-05-06 | 2
2024 | Region X | MISAMIS ORIENTAL | JASAAN (MISAMIS ORIENTAL) | P00835767MN | Construction of Flood Mitigation Structure | 124.7689 | 8.6301 | 96500000 | 96500000 | 2024 | RITCHE-NATHALIE DEVELOPMENT CORPORATION (FORMERLY: RITCHE-NATHALIE BUILDERS AND GEN. MERCHANDISE) | 8881 | 2024 | 2024-12-18 | 02/15/2024 | 0 | 0 | 2024-12-17 |  | 1
2023 | Region X | MISAMIS ORIENTAL | GINGOOG CITY (MISAMIS ORIENTAL) | P00721537MN | Construction of Revetment | 125.0561 | 8.8515 | 72375000 | 72375000 | 2024 | RITCHE-NATHALIE BUILDERS & GENERAL MERCHANDISE | 8882 | 2023 | 2024-03-04 | 04/25/2023 | 0 | 0 | 2024-03-09 | 5
2023 | Region XII | SULTAN KUDARAT | LAMBAYONG (MARIANO MARCOS) (SULTAN KUDARAT) | P00721473MN | Construction of Flood Mitigation Structure | 124.6093 | 6.6813 | 115800000 | 110005802.7 | 2024 | THREE W BUILDERS, INC. | 8883 | 2023 | 2024-06-14 | 08/29/2023 | 5794197.3 | 0 | 2024-06-13 |  | 1
2023 | Region VIII | LEYTE | SANTA FE (LEYTE) | P00733755VS | Construction of Flood Mitigation Structure | 124.9181 | 11.1848 | 5940000 | 5934012.79 | 2023 | CEY BUILDERS | 8884 | 2023 | 2023-07-13 | 05/18/2023 | 5987.21 | 0 | 2023-07-12 |  | 1
2024 | Region VIII | BILIRAN | NAVAL (CAPITAL) (BILIRAN) | P00820916VS | Construction of Flood Mitigation Structure | 124.4282 | 11.5257 | 24484709.56 | 23980324.5 | 2024 | RMA BUILDERS & SUPPLIES CORPORATION | 8885 | 2024 | 2024-07-30 | 02/27/2024 | 504385.06 | 0 | 2024-07-29 |  | 1
2022 | Region VIII | LEYTE | BABATNGON (LEYTE) | P00633237VS | Construction of Flood Mitigation Structure | 124.9193 | 11.3522 | 19800000 | 19778276.71 | 2023 | LUG KONSTRACT, INC. (FORMERLY: LUG KONSTRACT) | 8886 | 2022 | 2023-03-06 | 05/20/2022 | 21723.29 | 0 | 2022-12-27 |  | 69
2022 | Region X | MISAMIS ORIENTAL | TAGOLOAN (MISAMIS ORIENTAL) | P00620349MN | Construction of Flood Mitigation Structure | 124.7691 | 8.5382 | 48250000 | 47284715.1 | 2024 | TRIPARCO DEVELOPMENT CORPORATION | 8887 | 2022 | 2024-02-02 | 11/07/2022 | 965284.9 | 0 | 2023-06-03 |  | 244
2024 | Region VIII | SOUTHERN LEYTE | BONTOC (SOUTHERN LEYTE) | P00820263VS | Construction of Flood Mitigation Structure | 124.9195 | 10.3827 | 49000000 | 49000000 | 2024 | ON POINT CONSTRUCTION AND DEVELOPMENT CORPORATION (FORMERLY:ON POINT CONSTRUCTION) | 8888 | 2024 | 2024-07-08 | 02/13/2024 | 0 | 0 | 2024-10-08 | 92
2023 | Region VII | BOHOL | DUERO (BOHOL) | P00733702VS | Construction of Flood Mitigation Structure | 124.4293 | 9.7389 | 79200000 | 78999999.76 | 2024 | JAMARI CONSTRUCTION (FORMERLY FRAE CONSTRUCTION) / ALTACS CONSTRUCTION | 8889 | 2023 | 2024-03-13 | 05/26/2023 | 200000.24 | 0 | 2024-03-12 |  | 1
2023 | Region VIII | LEYTE | PALO (LEYTE) | P00721711VS | Rehabilitation / Major Repair of Flood Control Structure | 124.9971 | 11.1609 | 20413400 | 20194672.1 | 2023 | KAUIE BUILDERS & SUPPLIES INC. (FORMERLY: KAUIE BUILDERS AND CONSTRUCTION SUPPLIES) | 8890 | 2023 | 2023-08-08 | 03/24/2023 | 218727.9 | 0 | 2023-09-02 | 25
2023 | Region VIII | NORTHERN SAMAR | CATUBIG (NORTHERN SAMAR) | P00721719VS | Construction of Flood Mitigation Structure | 125.0566 | 12.4024 | 19599968.55 | 19402210.15 | 2024 | MIK AND MEL CONSTRUCTION AND SUPPLY | 8891 | 2023 | 2024-01-25 | 02/07/2023 | 197758.4 | 0 | 2023-09-03 |  | 144
2024 | Region XII | SARANGANI | KIAMBA (SARANGANI) | P00833570MN | Construction of Flood Mitigation Structure | 124.6095 | 6.0072 | 99000000 | 98999858.7 | 2024 | J.G. ORANZA CONSTRUCTION | 8892 | 2024 | 2024-11-21 | 05/27/2024 | 141.3 | 0 | 2025-03-06 | 105
2024 | Region X | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY (CAPITAL) (MISAMIS ORIENTAL) | P00836179MN | Construction of Drainage Structure | 124.6096 | 8.5038 | 9900000 | 9900000 | 2024 | ABAYCER CONSTRUCTION SUPPLIES AND GENERAL MERCHANDISE | 8893 | 2024 | 2024-09-30 | 03/11/2024 | 0 | 0 | 2024-10-05 | 5
2022 | Region VIII | SAMAR (WESTERN SAMAR) | BASEY (SAMAR (WESTERN SAMAR)) | P00620215VS | Construction of Flood Mitigation Structure | 125.0584 | 11.2882 | 39199990.66 | 39197894.48 | 2023 | CDU CONSTRUCTION | 8894 | 2022 | 2023-01-15 | 02/14/2022 | 2096.18 | 0 | 2023-01-14 |  | 1
2023 | Region XII | SOUTH COTABATO | LAKE SEBU (SOUTH COTABATO) | P00721470MN | Construction of Flood Mitigation Structure | 124.7694 | 6.2427 | 57900000 | 57899993.65 | 2023 | AMPLEX CONSTRUCTION AND SUPPLIES | 8895 | 2023 | 2023-08-31 | 03/10/2023 | 6.35 | 0 | 2023-10-12 | 42
2023 | Region VIII | LEYTE | SANTA FE (LEYTE) | P00721707VS | Construction of Flood Mitigation Structure | 124.9199 | 11.1861 | 49000000 | 48948975.79 | 2023 | FAIRCHILD BUILDERS & DEVELOPERS, INC. | 8896 | 2023 | 2023-10-09 | 03/24/2023 | 51024.21 | 0 | 2023-10-08 |  | 1
2024 | Region VIII | SOUTHERN LEYTE | MALITBOG (SOUTHERN LEYTE) | P00820261VS | Construction of Flood Mitigation Structure | 124.9979 | 10.1473 | 49000000 | 49000000 | 2024 | JDR CONSTRUCTION / JGO BUILDERS | 8897 | 2024 | 2024-10-25 | 02/13/2024 | 0 | 0 | 2024-10-30 | 5
2022 | Region VIII | LEYTE | ISABEL (LEYTE) | P00620198VS | Construction of Flood Mitigation Structure | 124.4311 | 10.9614 | 19599962.94 | 19599997.66 | 2022 | CLMB CONSTRUCTION | 8898 | 2022 | 2022-07-20 | 02/21/2022 | 0 | 34.72 | 2022-07-19 |  | 1
2023 | Region VIII | LEYTE | ORMOC CITY (LEYTE) | P00721717VS | Construction of Flood Mitigation Structure | 124.6096 | 11.0251 | 22540000 | 22089199.87 | 2024 | RJIR ENTERPRISES CORPORATION | 8899 | 2023 | 2024-07-25 | 04/03/2023 | 450800.13 | 0 | 2024-07-24 |  | 1
2022 | Region X | MISAMIS ORIENTAL | VILLANUEVA (MISAMIS ORIENTAL) | P00630482MN | Construction of Flood Mitigation Structure | 124.7699 | 8.5785 | 62725000 | 62725000 | 2022 | ROAD EDGE TRADING & DEVELOPMENT SERVICES | 8900 | 2022 | 2022-12-17 | 02/28/2022 | 0 | 0 | 2022-12-16 |  | 1
2024 | Region X | BUKIDNON | MARAMAG (BUKIDNON) | P00820051MN | Construction of Revetment | 124.9223 | 7.7958 | 57900000 | 57900000 | 2024 | M. MONTESCLAROS ENTERPRISES, INC. / RRN CONSTRUCTION & DEV'T. CORP. (FORMERLY: RRN CONSTRUCTION) | 8901 | 2024 | 2024-12-14 | 02/16/2024 | 0 | 0 | 2024-12-13 |  | 1
2024 | Region VII | BOHOL | UBAY (BOHOL) | P00835002VS | Construction of Flood Mitigation Structure | 124.4318 | 9.952 | 39200000 | 39565619.24 | 2025 | ZLREJ TRADING AND CONSTRUCTION CORPORATION | 8902 | 2024 | 2025-04-15 | 05/09/2024 | 0 | 365619.24 | 2025-05-07 | 22
2022 | Region VIII | LEYTE | MAYORGA (LEYTE) | P00620184VS | Construction of Flood Mitigation Structure | 124.9984 | 10.8812 | 48999959.43 | 48307483.94 | 2022 | FAIRCHILD BUILDERS & DEVELOPERS, INC. | 8903 | 2022 | 2022-11-11 | 03/01/2022 | 692475.49 | 0 | 2022-11-12 | 1
2021 | Region XII | SULTAN KUDARAT |  | P00522264MN | Construction of Flood Mitigation Structure | 124.6108 | 6.8377 | 45711313.38 | 45686809.57 | 2022 | CS CONST. AND SUPPLY INC. (FORMERLY: CS CONSTRUCTION AND SUPPLY) | 8904 | 2021 | 2022-12-09 | 11/23/2021 | 24503.81 | 0 | 2022-10-02 |  | 68
2023 | Region X | MISAMIS ORIENTAL | GINGOOG CITY (MISAMIS ORIENTAL) | P00721549MN | Construction of Flood Mitigation Structure | 125.0585 | 8.8532 | 67550000 | 67550000 | 2024 | DICON BUILDERS CORP. | 8905 | 2023 | 2024-02-10 | 05/08/2023 | 0 | 0 | 2024-02-21 | 11
2022 | Region VIII | LEYTE | SANTA FE (LEYTE) | P00632037VS | Construction of Flood Mitigation Structure | 124.9233 | 11.2098 | 49500000 | 49400027.77 | 2022 | JJ PALACIO CONSTRUCTION | 8906 | 2022 | 2022-10-10 | 05/20/2022 | 99972.23 | 0 | 2022-12-04 | 55
2023 | Region VIII | LEYTE | TOLOSA (LEYTE) | P00721705VS | Construction of Flood Mitigation Structure | 124.9987 | 11.0405 | 49000000 | 48491990.63 | 2023 | COLLERA CONSTRUCTION | 8907 | 2023 | 2023-07-21 | 03/20/2023 | 508009.37 | 0 | 2023-10-04 | 75
2024 | Region VIII | BILIRAN | KAWAYAN (BILIRAN) | P00832668VS | Construction of Flood Mitigation Structure | 124.4323 | 11.703 | 4946592.67 | 4845187.5 | 2024 | M.B. ANG CONSTRUCTION & SUPPLY | 8908 | 2024 | 2024-04-25 | 02/11/2024 | 101405.17 | 0 | 2024-04-24 |  | 1
2022 | Region XII | SULTAN KUDARAT | LAMBAYONG (MARIANO MARCOS) (SULTAN KUDARAT) | P00620289MN | Construction of Flood Mitigation Structure | 124.6116 | 6.854 | 48979223.92 | 48879220.9 | 2023 | CS CONST. AND SUPPLY INC. (FORMERLY: CS CONSTRUCTION AND SUPPLY) / GIBUILD DEVELOPMENT CORP. | 8909 | 2022 | 2023-06-15 | 05/25/2022 | 100003.02 | 0 | 2023-02-08 |  | 127
2023 | Region XII | COTABATO (NORTH COTABATO) | MAKILALA (COTABATO (NORTH COTABATO)) | P00721454MN | Construction of Flood Mitigation Structure | 125.0606 | 6.9376 | 72375000 | 72374996.63 | 2024 | LLABAN CONSTRUCTION & SUPPLY (FORMERLY: LLABAN CON | 8910 | 2023 | 2024-04-28 | 08/31/2023 | 3.37 | 0 | 2024-04-27 |  | 1
2024 | Region VIII | SOUTHERN LEYTE | BONTOC (SOUTHERN LEYTE) | P00820259VS | Construction of Flood Mitigation Structure | 124.9245 | 10.3733 | 49000000 | 48934168.88 | 2024 | FAIRCHILD BUILDERS & DEVELOPERS, INC. | 8911 | 2024 | 2024-10-09 | 02/13/2024 | 65831.12 | 0 | 2024-10-08 |  | 1
2023 | Region VIII | LEYTE | TACLOBAN CITY (CAPITAL) (LEYTE) | P00731697VS | Construction of Drainage Structure | 125.0005 | 11.2375 | 9013094.2 | 8920501.93 | 2023 | G.O.C. BUILDERS | 8912 | 2023 | 2023-04-12 | 02/23/2023 | 92592.27 | 0 | 2023-07-01 | 80
2023 | Region VII | BOHOL | DUERO (BOHOL) | P00733735VS | Construction of Flood Mitigation Structure | 124.4331 | 9.7231 | 49500000 | 49434062.86 | 2024 | E.R. VENZON CONSTRUCTION | 8913 | 2023 | 2024-01-30 | 04/11/2023 | 65937.14 | 0 | 2024-01-29 |  | 1
2022 | Region XII | COTABATO (NORTH COTABATO) | BANISILAN (COTABATO (NORTH COTABATO)) | P00632612MN | Construction of Flood Mitigation Structure | 124.7714 | 7.5167 | 4950000 | 4898265.99 | 2022 | SAREX BUILDERS AND SUPPLY | 8914 | 2022 | 2022-08-06 | 03/28/2022 | 51734.01 | 0 | 2022-08-05 |  | 1
2023 | Region X | MISAMIS ORIENTAL | BALINGASAG (MISAMIS ORIENTAL) | P00733986MN | Construction of Revetment | 124.7718 | 8.7119 | 72375000 | 72375000 | 2024 | VICENTE T. LAO CONSTRUCTION | 8915 | 2023 | 2024-03-08 | 04/23/2023 | 0 | 0 | 2024-03-07 |  | 1
2024 | Region VIII | LEYTE | PALOMPON (LEYTE) | P00820245VS | Construction of Flood Mitigation Structure | 124.4336 | 11.0425 | 5880000 | 5821084.15 | 2024 | LIMAR CONSTRUCTION | 8916 | 2024 | 2024-06-11 | 02/13/2024 | 58915.85 | 0 | 2024-06-10 |  | 1
2024 | Region X | MISAMIS ORIENTAL | GINGOOG CITY (MISAMIS ORIENTAL) | P00835778MN | Construction of Flood Mitigation Structure | 125.0637 | 8.8522 | 96500000 | 96500000 | 2025 | RITCHE-NATHALIE DEVELOPMENT CORPORATION (FORMERLY: RITCHE-NATHALIE BUILDERS AND GEN. MERCHANDISE) | 8917 | 2024 | 2025-04-28 | 05/06/2024 | 0 | 0 | 2025-04-27 |  | 1
2022 | Region VIII | LEYTE | ABUYOG (LEYTE) | P00620281VS | Construction of Flood Mitigation Structure | 125.0013 | 10.7274 | 96500000 | 95536997.78 | 2022 | JUCONS CONSTRUCTION OPC (FORMERLY:JUCONS CONSTRUCTION &SUPPLY) / EZJONES CONSTRUCTION INC. | 8918 | 2022 | 2022-11-16 | 03/01/2022 | 963002.22 | 0 | 2022-11-24 | 8
2022 | Region X | BUKIDNON | MARAMAG (BUKIDNON) | P00630499MN | Construction of Revetment | 124.9256 | 7.7917 | 67550000 | 67550000 | 2023 | PYRAMID CONSOLIDATED BUILDERS & GEN. MDSE. | 8919 | 2022 | 2023-01-19 | 02/24/2022 | 0 | 0 | 2023-01-18 |  | 1
2022 | Region XII | SULTAN KUDARAT | LAMBAYONG (MARIANO MARCOS) (SULTAN KUDARAT) | P00630631MN | Construction of Flood Mitigation Structure | 124.6116 | 6.854 | 36230988.82 | 36130907.87 | 2023 | CS CONST. AND SUPPLY INC. (FORMERLY: CS CONSTRUCTION AND SUPPLY) / GIBUILD DEVELOPMENT CORP. | 8920 | 2022 | 2023-06-15 | 05/25/2022 | 100080.95 | 0 | 2023-03-02 |  | 105
2024 | Region VIII | LEYTE | ABUYOG (LEYTE) | P00820362VS | Construction of Flood Mitigation Structure | 125.0015 | 10.7322 | 96500000 | 96499959.2 | 2024 | PABLO S. LABASBAS CONSTRUCTION CORPORATION (FORMERLY: PABLOS. LABASBAS CONSTRUCTION CORPORATION) / JGO BUILDERS | 8921 | 2024 | 2024-12-12 | 03/18/2024 | 40.8 | 0 | 2024-12-11 |  | 1
2022 | Region X | MISAMIS ORIENTAL | GINGOOG CITY (MISAMIS ORIENTAL) | P00620033MN | Construction of Flood Mitigation Structure | 125.0639 | 8.8523 | 77200000 | 74496866.33 | 2023 | EQUI-PARCO CONSTRUCTION COMPANY | 8922 | 2022 | 2023-07-30 | 06/29/2022 | 2703133.67 | 0 | 2023-06-02 |  | 58
2023 | Region VIII | LEYTE | PALO (LEYTE) | P00721856VS | Construction of Flood Mitigation Structure | 125.0017 | 11.143 | 49000000 | 48950000 | 2023 | MWJ CONSTRUCTION | 8923 | 2023 | 2023-06-22 | 03/28/2023 | 50000 | 0 | 2023-10-12 | 112
2022 | Region VIII | LEYTE | CALUBIAN (LEYTE) | P00632043VS | Construction of Flood Mitigation Structure | 124.4355 | 11.4327 | 4899994.35 | 4798557.51 | 2022 | KAUIE BUILDERS & SUPPLIES INC. (FORMERLY: KAUIE BUILDERS AND CONSTRUCTION SUPPLIES) | 8924 | 2022 | 2022-07-27 | 03/25/2022 | 101436.84 | 0 | 2022-07-26 |  | 1
2022 | Region XII | COTABATO (NORTH COTABATO) | MATALAM (COTABATO (NORTH COTABATO)) | P00620281MN | Construction of Revetment | 124.9271 | 7.1195 | 48250000 | 48252314.01 | 2023 | MARCUS CONSTRUCTION & SUPPLY / ALZEN ENGINEERING & CONSTRUCTION SUPPLIES | 8925 | 2022 | 2023-05-12 | 05/20/2022 | 0 | 2314.01 | 2023-07-02 | 51
2022 | Region XII | SULTAN KUDARAT | LAMBAYONG (MARIANO MARCOS) (SULTAN KUDARAT) | P00630630MN | Construction of Flood Mitigation Structure | 124.6125 | 6.8518 | 36249922.23 | 35887489.97 | 2023 | CS CONST. AND SUPPLY INC. (FORMERLY: CS CONSTRUCTION AND SUPPLY) / GIBUILD DEVELOPMENT CORP. | 8926 | 2022 | 2023-05-31 | 04/11/2022 | 362432.26 | 0 | 2022-11-13 |  | 199
2022 | Region X | MISAMIS ORIENTAL | VILLANUEVA (MISAMIS ORIENTAL) | P00630483MN | Construction of Flood Mitigation Structure | 124.772 | 8.5766 | 62725000 | 62725000 | 2022 | ROAD EDGE TRADING & DEVELOPMENT SERVICES | 8927 | 2022 | 2022-12-20 | 03/03/2022 | 0 | 0 | 2022-12-19 |  | 1
2022 | Region VIII | SAMAR (WESTERN SAMAR) | HINABANGAN (SAMAR (WESTERN SAMAR)) | P00620214VS | Construction of Flood Mitigation Structure | 125.0654 | 11.7032 | 29399999.71 | 29399393.89 | 2022 | CDU CONSTRUCTION | 8928 | 2022 | 2022-10-04 | 02/14/2022 | 605.82 | 0 | 2022-10-27 | 23
2022 | Region VIII | LEYTE | CALUBIAN (LEYTE) | P00632041VS | Construction of Flood Mitigation Structure | 124.4357 | 11.4307 | 4899993.6 | 4851201.35 | 2022 | LUG KONSTRACT, INC. (FORMERLY: LUG KONSTRACT) | 8929 | 2022 | 2022-07-26 | 03/25/2022 | 48792.25 | 0 | 2022-07-26 | 0
2023 | Region VIII | LEYTE | TACLOBAN CITY (CAPITAL) (LEYTE) | P00731693VS | Construction of Drainage Structure | 125.0019 | 11.2477 | 10777945.99 | 10672104.06 | 2023 | G.O.C. BUILDERS | 8930 | 2023 | 2023-11-02 | 06/16/2023 | 105841.93 | 0 | 2023-11-01 |  | 1
2024 | Region X | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY (CAPITAL) (MISAMIS ORIENTAL) | P00820897MN | Construction of Flood Mitigation Structure | 124.6128 | 8.3888 | 72375000 | 72375000 | 2024 | RITCHE-NATHALIE DEVELOPMENT CORPORATION (FORMERLY: RITCHE-NATHALIE BUILDERS AND GEN. MERCHANDISE) | 8931 | 2024 | 2024-12-27 | 02/12/2024 | 0 | 0 | 2025-02-24 | 59
2022 | Region VIII | LEYTE | DAGAMI (LEYTE) | P00620332VS | Construction of Flood Mitigation Structure | 124.9293 | 11.0686 | 48999999.72 | 48999996.54 | 2023 | LANOY CONSTRUCTION | 8932 | 2022 | 2023-03-30 | 03/21/2022 | 3.18 | 0 | 2023-03-29 |  | 1
2021 | Region X | MISAMIS ORIENTAL |  | P00522059MN | Construction of Flood Mitigation Structure | 124.7739 | 8.5902 | 96500000 | 80672953.52 | 2022 | ROAD EDGE TRADING & DEVELOPMENT SERVICES | 8933 | 2021 | 2022-12-13 | 04/01/2022 | 15827046.48 | 0 | 2023-01-19 | 37
2022 | Region VIII | SAMAR (WESTERN SAMAR) | CALBAYOG CITY (SAMAR (WESTERN SAMAR)) | P00630238VS | Construction of Flood Mitigation Structure | 124.4442 | 12.1642 | 49000000 | 48698693.64 | 2022 | JFR CONSTRUCTION INC. (FORMERLY:JFR CONSTRUCTION) | 8934 | 2022 | 2022-10-19 | 03/23/2022 | 301306.36 | 0 | 2022-10-18 |  | 1
2024 | Region VIII | LEYTE | TANAUAN (LEYTE) | P00820371VS | Construction of Flood Mitigation Structure | 125.002 | 11.1463 | 96500000 | 96427104.08 | 2024 | PABLO S. LABASBAS CONSTRUCTION CORPORATION (FORMERLY: PABLOS. LABASBAS CONSTRUCTION CORPORATION) / AICON INDUSTRIES | 8935 | 2024 | 2024-10-10 | 02/15/2024 | 72895.92 | 0 | 2024-11-23 | 44
2024 | Region X | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY (CAPITAL) (MISAMIS ORIENTAL) | P00835771MN | Construction of Flood Mitigation Structure | 124.6128 | 8.3885 | 96500000 | 96500000 | 2024 | RITCHE-NATHALIE DEVELOPMENT CORPORATION (FORMERLY: RITCHE-NATHALIE BUILDERS AND GEN. MERCHANDISE) | 8936 | 2024 | 2024-12-27 | 02/27/2024 | 0 | 0 | 2025-05-20 | 144
2024 | Region XII | SOUTH COTABATO | SURALLAH (SOUTH COTABATO) | P00820205MN | Construction of Flood Mitigation Structure | 124.7739 | 6.2985 | 15680000 | 15670474.94 | 2024 | SOUTHCAST CONSTRUCTION | 8937 | 2024 | 2024-06-16 | 01/30/2024 | 9525.06 | 0 | 2024-06-15 |  | 1
2022 | Region X | MISAMIS ORIENTAL | GINGOOG CITY (MISAMIS ORIENTAL) | P00620034MN | Construction of Flood Mitigation Structure | 125.0658 | 8.8496 | 96500000 | 92833000 | 2023 | MINDANAO ROCK / LT POWER BUILDERS DEVELOPMENT CORPORATION | 8938 | 2022 | 2023-04-24 | 06/29/2022 | 3667000 | 0 | 2023-04-23 |  | 1
2023 | Region VIII | LEYTE | PALO (LEYTE) | P00721854VS | Construction of Flood Mitigation Structure | 125.0021 | 11.1424 | 49000000 | 48939239.49 | 2023 | JELM CONSTRUCTION CORP. / R. YAO CONSTRUCTION | 8939 | 2023 | 2023-07-03 | 03/20/2023 | 60760.51 | 0 | 2023-10-04 | 93
2023 | Region VIII | BILIRAN | NAVAL (CAPITAL) (BILIRAN) | P00733750VS | Construction of Flood Mitigation Structure | 124.4462 | 11.53 | 4945295.62 | 4821663.8 | 2023 | SUNRISE BUILDERS | 8940 | 2023 | 2023-05-31 | 03/30/2023 | 123631.82 | 0 | 2023-06-11 | 11
2024 | Region X | MISAMIS ORIENTAL | CAGAYAN DE ORO CITY (CAPITAL) (MISAMIS ORIENTAL) | P00835772MN | Construction of Flood Mitigation Structure | 124.6128 | 8.3885 | 72375000 | 72375000 | 2024 | RITCHE-NATHALIE DEVELOPMENT CORPORATION (FORMERLY: RITCHE-NATHALIE BUILDERS AND GEN. MERCHANDISE) | 8941 | 2024 | 2024-12-20 | 02/28/2024 | 0 | 0 | 2025-03-22 | 92
2022 | Region XII | COTABATO (NORTH COTABATO) | MATALAM (COTABATO (NORTH COTABATO)) | P00620099MN | Construction of Flood Mitigation Structure | 124.9296 | 7.1219 | 52110000 | 51590891.41 | 2023 | JARGON CONSTRUCTION & SUPPLY | 8942 | 2022 | 2023-09-08 | 09/12/2022 | 519108.59 | 0 | 2023-08-18 |  | 21
2022 | Region X | MISAMIS ORIENTAL | VILLANUEVA (MISAMIS ORIENTAL) | P00630490MN | Construction of Flood Mitigation Structure | 124.774 | 8.5902 | 67550000 | 67550000 | 2022 | CAGALAWAN ENTERPRISES / FFJJ CONSTRUCTION | 8943 | 2022 | 2022-12-13 | 03/03/2022 | 0 | 0 | 2022-12-12 |  | 1
2022 | Region VIII | SOUTHERN LEYTE | LIBAGON (SOUTHERN LEYTE) | P00620229VS | Construction of Flood Mitigation Structure | 125.0663 | 10.2781 | 25003720 | 25003720 | 2023 | GREAT PACIFIC BUILDERS AND GEN. CONTRACTOR INC. | 8944 | 2022 | 2023-05-02 | 02/16/2022 | 0 | 0 | 2023-05-01 |  | 1
2022 | Region VIII | LEYTE | PALO (LEYTE) | P00620328VS | Construction of Flood Mitigation Structure | 125.0021 | 11.1454 | 48020000 | 48020000 | 2022 | LEDA CONSTRUCTION INCORPORATED | 8945 | 2022 | 2022-10-25 | 02/11/2022 | 0 | 0 | 2022-10-24 |  | 1
2021 | Region XII | SULTAN KUDARAT |  | P00522265MN | Construction of Flood Mitigation Structure | 124.6133 | 6.8494 | 45709473.62 | 45049458.57 | 2022 | CS CONST. AND SUPPLY INC. (FORMERLY: CS CONSTRUCTION AND SUPPLY) / GIBUILD DEVELOPMENT CORP. | 8946 | 2021 | 2022-07-26 | 11/23/2021 | 660015.05 | 0 | 2022-07-25 |  | 1
2023 | Region VIII | BILIRAN | NAVAL (CAPITAL) (BILIRAN) | P00732041VS | Construction of Flood Mitigation Structure | 124.4464 | 11.5298 | 4945940.3 | 4790143.2 | 2023 | SUNRISE BUILDERS | 8947 | 2023 | 2023-05-05 | 02/20/2023 | 155797.1 | 0 | 2023-05-04 |  | 1
2023 | Region VIII | LEYTE | HILONGOS (LEYTE) | P00721580VS | Construction of Flood Mitigation Structure | 124.7749 | 10.3492 | 53075000 | 52329124.56 | 2023 | RJIR ENTERPRISES CORPORATION | 8948 | 2023 | 2023-09-04 | 04/04/2023 | 745875.44 | 0 | 2023-12-28 | 115
2024 | Region VIII | LEYTE | TACLOBAN CITY (CAPITAL) (LEYTE) | P00832223VS | Construction of Flood Mitigation Structure | 125.0026 | 11.2065 | 164050625.8 | 164049999.4 | 2024 | EZJONES CONSTRUCTION INC. / JB KONSTRUKTURA COMPANY | 8949 | 2024 | 2024-11-25 | 03/06/2024 | 626.4 | 0 | 2025-02-07 | 74
2023 | Region VIII | LEYTE | SANTA FE (LEYTE) | P00721964VS | Construction of Flood Mitigation Structure | 124.9298 | 11.2049 | 48020000 | 47988909.99 | 2023 | RT BUILDERS | 8950 | 2023 | 2023-11-14 | 05/02/2023 | 31090.01 | 0 | 2023-11-14 | 0
2022 | Region VIII | NORTHERN SAMAR | CATARMAN (CAPITAL) (NORTHERN SAMAR) | P00630682VS | Construction of Drainage Structure | 124.6135 | 12.5076 | 4949667.32 | 4900810.34 | 2022 | C. A. CONSTRUCTION AND SUPPLY | 8951 | 2022 | 2022-07-21 | 02/21/2022 | 48856.98 | 0 | 2022-07-20 |  | 1
2019 | Region VIII | SAMAR (WESTERN SAMAR) |  | P00320211VS | Construction of Flood Mitigation Structure | 125.0668 | 11.2788 | 233876034.9 | 227812286.4 | 2023 | NORTHERN BUILDERS / RIANNE CONSTRUCTION | 8952 | 2019 | 2023-08-08 | 08/14/2019 | 6063748.5 | 0 | 2023-08-07 |  | 1
2022 | Region VII | BOHOL | UBAY (BOHOL) | P00630213VS | Construction of Flood Mitigation Structure | 124.4465 | 10.0025 | 34300000 | 33272696 | 2023 | JA ACHACOSO ENTERPRISES & GENERAL SERVICES | 8953 | 2022 | 2023-03-26 | 03/16/2022 | 1027304 | 0 | 2022-11-14 |  | 132
2022 | Region VIII | LEYTE | PALO (LEYTE) | P00620421VS | Construction of Flood Mitigation Structure | 125.0028 | 11.1453 | 33774296.22 | 33674274.99 | 2022 | EZJONES CONSTRUCTION INC. / MWJ CONSTRUCTION | 8954 | 2022 | 2022-12-29 | 06/13/2022 | 100021.23 | 0 | 2022-12-28 |  | 1
2024 | Region VIII | NORTHERN SAMAR | PAMBUJAN (NORTHERN SAMAR) | P00835031VS | Construction of Drainage Structure | 124.9301 | 12.5628 | 9899959.65 | 9883728.36 | 2025 | J SQUARE BUILDERS AND CONSTRUCTION SUPPLY | 8955 | 2024 | 2025-01-31 | 06/07/2024 | 16231.29 | 0 | 2024-10-03 |  | 120
2020 | Region VIII | SAMAR (WESTERN SAMAR) |  | P00320211VS | Construction of Flood Mitigation Structure | 125.0668 | 11.2788 | 233876034.9 | 227812286.4 | 2023 | NORTHERN BUILDERS / RIANNE CONSTRUCTION | 8956 | 2020 | 2023-08-08 | 08/14/2019 | 6063748.5 | 0 | 2023-08-07 |  | 1
2023 | Region VIII | LEYTE | TACLOBAN CITY (CAPITAL) (LEYTE) | P00721917VS | Construction of Flood Mitigation Structure | 125.0028 | 11.2524 | 55466554.48 | 55021203.86 | 2023 | ED1SON DEVELOPMENT & CONSTRUCTION INC. / TWENTYSIX CONSTRUCTION INC. | 8957 | 2023 | 2023-12-19 | 03/23/2023 | 445350.62 | 0 | 2024-01-14 | 26
2024 | Region VIII | BILIRAN | NAVAL (CAPITAL) (BILIRAN) | P00832665VS | Construction of Revetment | 124.4465 | 11.5305 | 4945530.11 | 4886183.75 | 2024 | RMA BUILDERS & SUPPLIES CORPORATION | 8958 | 2024 | 2024-03-15 | 02/18/2024 | 59346.36 | 0 | 2024-05-01 | 47
2022 | Region X | BUKIDNON | DAMULOG (BUKIDNON) | P00630573MN | Construction of Revetment | 124.9326 | 7.4763 | 39200000 | 39200000 | 2022 | PYRAMID CONSOLIDATED BUILDERS & GEN. MDSE. | 8959 | 2022 | 2022-12-11 | 02/15/2022 | 0 | 0 | 2022-12-10 |  | 1
2021 | Region X | MISAMIS ORIENTAL |  | P00522056MN | Construction of Drainage Structure | 124.6137 | 8.52 | 101325000 | 96179476.23 | 2024 | JEJOR'S CONSTRUCTION CORPORATION | 8960 | 2021 | 2024-04-30 | 11/22/2021 | 5145523.77 | 0 | 2023-06-24 |  | 311
2021 | Region VIII | SAMAR (WESTERN SAMAR) |  | P00320211VS | Construction of Flood Mitigation Structure | 125.0668 | 11.2788 | 233876034.9 | 227812286.4 | 2023 | NORTHERN BUILDERS / RIANNE CONSTRUCTION | 8961 | 2021 | 2023-08-08 | 08/14/2019 | 6063748.5 | 0 | 2023-08-07 |  | 1
2021 | Region VIII | LEYTE | TACLOBAN CITY (CAPITAL) (LEYTE) | P00620236VS | Construction of Flood Mitigation Structure | 125.0045 | 11.2235 | 48991358.55 | 48013198.2 | 2023 | LEDA CONSTRUCTION INCORPORATED | 8962 | 2022 | 2023-01-20 | 02/17/2022 | 978160.35 | 0 | 2023-01-19 |  | 1
2022 | Region VIII | BILIRAN | BILIRAN (BILIRAN) | P00620172VS | Rehabilitation / Major Repair of Flood Control Structure | 124.4475 | 11.4908 | 29371402.63 | 28108432.3 | 2022 | YOYEN ENTERPRISES | 8963 | 2022 | 2022-08-19 | 02/21/2022 | 1262970.33 | 0 | 2022-08-18 |  | 1
2022 | Region VIII | LEYTE | KANANGA (LEYTE) | P00820907VS | Construction of Flood Mitigation Structure | 124.6143 | 11.1908 | 96500000 | 96373321.44 | 2024 | LEDA CONSTRUCTION INCORPORATED | 8964 | 2024 | 2024-11-25 | 02/13/2024 | 126678.56 | 0 | 2024-12-07 | 12
2024 | Region X | BUKIDNON | DAMULOG (BUKIDNON) | P00620117MN | Construction of Revetment | 124.9331 | 7.4753 | 23520000 | 23520000 | 2022 | PYRAMID CONSOLIDATED BUILDERS & GEN. MDSE. | 8965 | 2022 | 2022-11-13 | 02/17/2022 | 0 | 0 | 2022-11-12 |  | 1
2022 | Region VIII | SAMAR (WESTERN SAMAR) | CALBAYOG CITY (SAMAR (WESTERN SAMAR)) | P00630240VS | Construction of Flood Mitigation Structure | 124.6175 | 12.1023 | 49000000 | 48637574.32 | 2022 | JFR CONSTRUCTION INC. (FORMERLY:JFR CONSTRUCTION) | 8966 | 2022 | 2022-10-28 | 02/08/2022 | 362425.68 | 0 | 2022-10-27 |  | 1
2023 | Region VIII | LEYTE | TACLOBAN CITY (CAPITAL) (LEYTE) | P00733329VS | Construction of Flood Mitigation Structure | 125.0045 | 11.2235 | 48990558.22 | 48603557.57 | 2024 | B. VICENCIO BUILDERS (BVB), INC. (FORMERLY:B. VICENCIO CONSTRUCTION) | 8968 | 2023 | 2024-01-28 | 04/05/2023 | 387000.65 | 0 | 2024-01-27 |  | 1
2022 | Region VIII | BILIRAN | BILIRAN (BILIRAN) | P00620165VS | Construction of Flood Mitigation Structure | 124.4481 | 11.4878 | 19588764.68 | 19588846.94 | 2022 | CHUCON BUILDERS CORPORATION (FORMERLY: CHU CONSTRUCTION) | 8969 | 2022 | 2022-10-11 | 03/17/2022 | 0 | 82.26 | 2022-10-10 |  | 1
2023 | Region VIII | LEYTE | SANTA FE (LEYTE) | P00721706VS | Construction of Flood Mitigation Structure | 124.937 | 11.2081 | 49000000 | 48965004.89 | 2023 | CHUCON BUILDERS CORPORATION (FORMERLY: CHU CONSTRUCTION) / MILES CONSTRUCTION AND ENTERPRISES | 8970 | 2023 | 2023-09-19 | 03/22/2023 | 34995.11 | 0 | 2023-10-06 | 17
2022 | Region XII | COTABATO (NORTH COTABATO) | PRESIDENT ROXAS (COTABATO (NORTH COTABATO)) | P00620278MN | Construction of Revetment | 125.0689 | 7.1328 | 48999217.09 | 48999217.01 | 2023 | LLABAN CONSTRUCTION & SUPPLY (FORMERLY: LLABAN CON | 8971 | 2022 | 2023-01-23 | 03/24/2022 | 0.08 | 0 | 2023-01-22 |  | 1
2023 | Region XII | SARANGANI | KIAMBA (SARANGANI) | P00721305MN | Construction of Flood Mitigation Structure | 124.62 | 5.9919 | 115800000 | 104667981.5 | 2023 | JDRC CONSTRUCTION & SUPPLIES, CORP. | 8972 | 2023 | 2023-11-26 | 03/15/2023 | 11132018.5 | 0 | 2024-01-28 | 63
2022 | Region XII | COTABATO (NORTH COTABATO) | PRESIDENT ROXAS (COTABATO (NORTH COTABATO)) | P00620275MN | Construction of Dike | 125.0693 | 7.1335 | 48507232.68 | 48510000 | 2023 | JTL KONSTRUCT CORPORATION / VICENTE T. LAO CONSTRUCTION | 8973 | 2022 | 2023-01-12 | 03/18/2022 | 0 | 2767.32 | 2023-01-14 | 2
2023 | Region VIII | LEYTE | VILLABA (LEYTE) | P00733314VS | Construction of Flood Mitigation Structure | 124.4482 | 11.2533 | 14699998.22 | 14552997.72 | 2023 | RED AXE BUILDERS & SUPPLY | 8974 | 2023 | 2023-09-11 | 05/04/2023 | 147000.5 | 0 | 2023-11-21 | 71
2022 | Region VIII | LEYTE | PALO (LEYTE) | P00620051VS | Construction of Flood Mitigation Structure | 125.0049 | 11.1539 | 13290600.96 | 12920671.72 | 2022 | 820 BUILDERS AND SUPPLIES | 8975 | 2022 | 2022-09-27 | 03/07/2022 | 369929.24 | 0 | 2022-09-26 |  | 1
2022 | Region VIII | LEYTE | MACARTHUR (LEYTE) | P00620334VS | Construction of Flood Mitigation Structure | 124.937 | 10.8406 | 48999999.4 | 48992529.6 | 2022 | LANOY CONSTRUCTION | 8976 | 2022 | 2022-12-10 | 03/21/2022 | 7469.8 | 0 | 2022-12-09 |  | 1
2023 | Region XII | SARANGANI | MALAPATAN (SARANGANI) | P00721584MN | Construction of Flood Mitigation Structure | 124.6201 | 5.9892 | 101325000 | 101285746.9 | 2024 | JDRC CONSTRUCTION & SUPPLIES, CORP. | 8977 | 2023 | 2024-03-12 | 08/29/2023 | 39253.1 | 0 | 2024-06-08 | 88
2022 | Region VIII | LEYTE | PALO (LEYTE) | P00620052VS | Construction of Flood Mitigation Structure | 125.0049 | 11.1539 | 24099590.73 | 24124097.61 | 2022 | 820 BUILDERS AND SUPPLIES | 8978 | 2022 | 2022-11-28 | 03/07/2022 | 0 | 24506.88 | 2022-11-29 | 1
2023 | Region VIII | BILIRAN | BILIRAN (BILIRAN) | P00721699VS | Construction of Flood Mitigation Structure | 124.4537 | 11.4954 | 19581445.65 | 19581741.14 | 2023 | SUNRISE BUILDERS | 8979 | 2023 | 2023-10-31 | 02/20/2023 | 0 | 295.49 | 2023-10-30 |  | 1
2023 | Region X | BUKIDNON | DON CARLOS (BUKIDNON) | P00734019MN | Construction of Flood Mitigation Structure | 124.9379 | 7.6954 | 29400000 | 29400000 | 2024 | VICENTE T. LAO CONSTRUCTION | 8980 | 2023 | 2024-02-06 | 06/12/2023 | 0 | 0 | 2024-02-05 |  | 1
2024 | Region XII | COTABATO (NORTH COTABATO) | PIGCAWAYAN (COTABATO (NORTH COTABATO)) | P00820184MN | Construction of Flood Mitigation Structure | 124.4552 | 7.3058 | 49000000 | 48755000 | 2024 | LLABAN CONSTRUCTION & SUPPLY (FORMERLY: LLABAN CON | 8981 | 2024 | 2024-11-04 | 02/07/2024 | 245000 | 0 | 2024-09-07 |  | 58
2024 | Region X | BUKIDNON | QUEZON (BUKIDNON) | P00836177MN | Construction of Flood Mitigation Structure | 125.071 | 7.7361 | 4950000 | 4950000 | 2024 | REVILO CONSTRUCTION | 8982 | 2024 | 2024-08-05 | 04/08/2024 | 0 | 0 | 2024-08-04 |  | 1
2023 | Region VIII | SOUTHERN LEYTE | MACROHON (SOUTHERN LEYTE) | P00721607VS | Construction of Flood Mitigation Structure | 124.9382 | 10.0801 | 84437500 | 84354739.01 | 2024 | ST. TIMOTHY CONSTRUCTION CORPORATION | 8983 | 2023 | 2024-03-30 | 02/21/2023 | 82760.99 | 0 | 2024-03-29 |  | 1
2023 | Region VIII | LEYTE | TACLOBAN CITY (CAPITAL) (LEYTE) | P00733293VS | Construction of Flood Mitigation Structure | 125.0052 | 11.2342 | 96480563 | 96280895.96 | 2023 | LANOY CONSTRUCTION | 8984 | 2023 | 2023-11-22 | 03/30/2023 | 199667.04 | 0 | 2023-12-22 | 30
2023 | Region XII | SOUTH COTABATO | POLOMOLOK (SOUTH COTABATO) | P00721313MN | Construction of Flood Mitigation Structure | 125.0726 | 6.2069 | 49697500 | 42634628.85 | 2023 | ACCELERATED METAL TECHNOLOGY & CONSTRUCTION, INC. | 8985 | 2023 | 2023-10-08 | 04/18/2023 | 7062871.15 | 0 | 2023-10-07 |  | 1
2022 | Region VIII | LEYTE | DAGAMI (LEYTE) | P00620333VS | Construction of Flood Mitigation Structure | 124.9393 | 11.078 | 48999980.64 | 48991275.51 | 2023 | LANOY CONSTRUCTION | 8986 | 2022 | 2023-03-03 | 03/21/2022 | 8705.13 | 0 | 2023-03-04 | 1
2024 | Region XII | COTABATO (NORTH COTABATO) | PRESIDENT ROXAS (COTABATO (NORTH COTABATO)) | P00820112MN | Rehabilitation / Major Repair of Flood Control Structure | 125.076 | 7.1318 | 67016235 | 67016235 | 2024 | VICENTE T. LAO CONSTRUCTION | 8987 | 2024 | 2024-12-16 | 03/21/2024 | 0 | 0 | 2025-03-01 | 75
2023 | Region VIII | LEYTE | TACLOBAN CITY (CAPITAL) (LEYTE) | P00733330VS | Construction of Flood Mitigation Structure | 125.0062 | 11.2523 | 48982523.22 | 48901822.33 | 2024 | B. VICENCIO BUILDERS (BVB), INC. (FORMERLY:B. VICENCIO CONSTRUCTION) | 8988 | 2023 | 2024-06-05 | 11/06/2023 | 80700.89 | 0 | 2024-06-04 |  | 1
2023 | Region VIII | LEYTE | ISABEL (LEYTE) | P00721552VS | Construction of Flood Mitigation Structure | 124.4554 | 10.8915 | 96500000 | 95674838.32 | 2023 | COLLERA CONSTRUCTION | 8989 | 2023 | 2023-10-25 | 05/08/2023 | 825161.68 | 0 | 2024-03-01 | 128
2022 | Region VIII | LEYTE | DAGAMI (LEYTE) | P00620331VS | Construction of Flood Mitigation Structure | 124.9393 | 11.078 | 48999961.53 | 48991679.56 | 2022 | LANOY CONSTRUCTION | 8990 | 2022 | 2022-12-29 | 02/24/2022 | 8281.97 | 0 | 2022-12-29 | 0
2022 | Region XII | COTABATO (NORTH COTABATO) | MAKILALA (COTABATO (NORTH COTABATO)) | P00620277MN | Construction of Flood Mitigation Structure | 125.0778 | 6.9459 | 49000000 | 49000000 | 2023 | LLABAN CONSTRUCTION & SUPPLY (FORMERLY: LLABAN CON / NARAGSAK CONSTRUCTION | 8991 | 2022 | 2023-07-27 | 02/23/2022 | 0 | 0 | 2023-03-23 |  | 126
2022 | Region VIII | LEYTE | DAGAMI (LEYTE) | P00620462VS | Construction of Flood Mitigation Structure | 124.9395 | 11.078 | 49999895.94 | 48999893.55 | 2023 | LANOY CONSTRUCTION | 8992 | 2022 | 2023-04-14 | 04/06/2022 | 1000002.39 | 0 | 2023-04-15 | 1
2023 | Region VIII | LEYTE | SANTA FE (LEYTE) | P00721962VS | Construction of Flood Mitigation Structure | 124.9396 | 11.2004 | 48020000 | 48000822.54 | 2023 | RT BUILDERS | 8993 | 2023 | 2023-12-27 | 06/13/2023 | 19177.46 | 0 | 2023-12-26 |  | 1
2023 | Region VIII | LEYTE | TACLOBAN CITY (CAPITAL) (LEYTE) | P00721600VS | Construction of Flood Mitigation Structure | 124.94 | 11.3032 | 110974061.7 | 109883701.5 | 2024 | PABLO S. LABASBAS CONSTRUCTION CORPORATION (FORMERLY: PABLOS. LABASBAS CONSTRUCTION CORPORATION) / JGO BUILDERS | 8994 | 2023 | 2024-01-26 | 05/09/2023 | 1090360.2 | 0 | 2024-02-01 | 6
2022 | Region VIII | SOUTHERN LEYTE | TOMAS OPPUS (SOUTHERN LEYTE) | P00633211VS | Construction of Slope Protection Structure | 124.9412 | 10.1982 | 69300000 | 69299998.43 | 2023 | JGO BUILDERS | 8995 | 2022 | 2023-06-16 | 04/06/2022 | 1.57 | 0 | 2023-06-15 |  | 1
2023 | Region X | MISAMIS ORIENTAL | MEDINA (MISAMIS ORIENTAL) | P00734370MN | Construction of Flood Mitigation Structure | 125.0068 | 8.9102 | 74250000 | 74250000 | 2023 | ROAD EDGE TRADING & DEVELOPMENT SERVICES | 8996 | 2023 | 2023-11-03 | 04/25/2023 | 0 | 0 | 2024-01-09 | 67
2023 | Region VIII | LEYTE | PALO (LEYTE) | P00733754VS | Construction of Flood Mitigation Structure | 125.0069 | 11.1653 | 4950000 | 4930818.93 | 2023 | QUELLING CONSTRUCTION | 8997 | 2023 | 2023-08-17 | 05/18/2023 | 19181.07 | 0 | 2023-08-16 |  | 1
2024 | Region VIII | NORTHERN SAMAR | LAOANG (NORTHERN SAMAR) | P00835030VS | Construction of Flood Mitigation Structure | 125.008 | 12.5655 | 29399980.43 | 29300446.86 | 2024 | JBM ENGINEERS AND SUPPLY | 8998 | 2024 | 2024-10-07 | 04/25/2024 | 99533.57 | 0 | 2025-01-18 | 103
2022 | Region VIII | LEYTE | PALO (LEYTE) | P00620057VS | Construction of Flood Mitigation Structure | 125.0083 | 11.1638 | 37619411.75 | 37233087.6 | 2023 | JELM CONSTRUCTION CORP. | 8999 | 2022 | 2023-04-02 | 08/04/2022 | 386324.15 | 0 | 2023-04-01 |  | 1
2022 | Region VIII | LEYTE | PALO (LEYTE) | P00620422VS | Construction of Flood Mitigation Structure | 125.0093 | 11.1378 | 25784718.26 | 25725438.95 | 2023 | AICON INDUSTRIES | 9000 | 2022 | 2023-06-22 | 12/29/2022 | 59279.31 | 0 | 2023-06-21 |  | 1
2022 | Region XI | DAVAO DEL SUR | DAVAO CITY (DAVAO DEL SUR) | P00633897MN | Construction of Flood Mitigation Structure | 125.5257 | 7.0748 | 96500000 | 96500000 | 2023 | GENESIS88 CONSTRUCTION INC. / GEMMA CONSTRUCTION SUPPLY, INC.(FORMERLY:GEMMA CON | 9001 | 2022 | 2023-08-20 | 04/13/2022 | 0 | 0 | 2023-09-18 | 29
2022 | Region VIII | SOUTHERN LEYTE | LIMASAWA (SOUTHERN LEYTE) | P00631708VS | Construction of Slope Protection Structure | 125.078 | 9.917 | 96500000 | 96423465.57 | 2023 | COLLERA CONSTRUCTION | 9002 | 2022 | 2023-04-20 | 04/06/2022 | 76534.43 | 0 | 2023-04-19 |  | 1
2024 | Region XIII | AGUSAN DEL NORTE | BUTUAN CITY (CAPITAL) (AGUSAN DEL NORTE) | P00833604MN | Construction of Drainage Structure | 125.5258 | 8.9437 | 4946981.51 | 4946981.51 | 2024 | FHD CONSTRUCTION AND SUPPLY | 9003 | 2024 | 2024-07-24 | 03/12/2024 | 0 | 0 | 2024-07-23 |  | 1
2022 | Region VIII | NORTHERN SAMAR | LAOANG (NORTHERN SAMAR) | P00630685VS | Construction of Flood Mitigation Structure | 125.0788 | 12.5058 | 34299893.87 | 33812940.77 | 2022 | JUPA CONSTRUCTION / RL TUBA CIVIL ENGINEERING CONSTRUCTION | 9004 | 2022 | 2022-11-08 | 02/14/2022 | 486953.1 | 0 | 2022-10-10 |  | 29
2021 | Region VIII | SOUTHERN LEYTE |  | P00549880VS | Construction of Slope Protection Structure | 125.0789 | 9.9236 | 96500000 | 96500000 | 2023 | B. VICENCIO BUILDERS (BVB), INC. (FORMERLY:B. VICENCIO CONSTRUCTION) / JGO BUILDERS | 9005 | 2021 | 2023-02-04 | 11/22/2021 | 0 | 0 | 2023-02-03 |  | 1
2022 | Region XI | DAVAO DEL SUR | DAVAO CITY (DAVAO DEL SUR) | P00633925MN | Construction of Flood Mitigation Structure | 125.5259 | 7.0742 | 6860000 | 6860000 | 2023 | GENESIS88 CONSTRUCTION INC. | 9006 | 2022 | 2023-07-27 | 04/13/2022 | 0 | 0 | 2023-07-26 |  | 1
2025 | Region XII | SOUTH COTABATO | GENERAL SANTOS CITY (DADIANGAS) (SOUTH COTABATO) | P00935912MN | Construction of Drainage Structure | 125.1789 | 6.1142 | 4950000 | 4939993.97 | 2025 | BAYTORR CONSTRUCTION AND DEVELOPMENT CORPORATION | 9007 | 2025 | 2025-05-12 | 03/14/2025 | 10006.03 | 0 | 2025-05-11 |  | 1
2022 | Region VIII | EASTERN SAMAR | ORAS (EASTERN SAMAR) | P00620322VS | Construction of Flood Mitigation Structure | 125.3898 | 12.1731 | 48984779.46 | 48999959.35 | 2022 | 888 ACY ENTERPRISES | 9008 | 2022 | 2022-11-11 | 02/13/2022 | 0 | 15179.89 | 2022-11-10 |  | 1
2022 | Region XI | DAVAO DE ORO | MARAGUSAN (SAN MARIANO) (DAVAO DE ORO) | P00620224MN | Construction of Revetment | 126.1271 | 7.4169 | 86849904.32 | 86842922.3 | 2023 | METRO GEAR CONSTRUCTION CORP. / RUPLINO SEISMUNDO CONSTRUCTION CORPORATION (FORMERLY: R.R. SEISMUNDO CONSTRUCTION & SUPPLY) | 9009 | 2022 | 2023-04-02 | 04/04/2022 | 6982.02 | 0 | 2023-04-01 |  | 1
2024 | Region XII | COTABATO (NORTH COTABATO) | MAKILALA (COTABATO (NORTH COTABATO)) | P00820414MN | Construction of Revetment | 125.0792 | 6.9379 | 49000000 | 48755000 | 2024 | LLABAN CONSTRUCTION & SUPPLY (FORMERLY: LLABAN CON | 9010 | 2024 | 2024-11-21 | 02/20/2024 | 245000 | 0 | 2024-12-03 | 12
2022 | Region XIII | SURIGAO DEL NORTE | SISON (SURIGAO DEL NORTE) | P00630543MN | Construction of Flood Mitigation Structure | 125.5264 | 9.6795 | 96500000 | 96499885.76 | 2023 | GICAR CONSTRUCTION, INC. | 9011 | 2022 | 2023-07-27 | 03/11/2022 | 114.24 | 0 | 2023-07-26 |  | 1
2023 | Region VIII | SOUTHERN LEYTE | LIMASAWA (SOUTHERN LEYTE) | P00721605VS | Construction of Flood Mitigation Structure | 125.0792 | 9.9236 | 84437500 | 84374606.74 | 2024 | PABLO S. LABASBAS CONSTRUCTION CORPORATION (FORMERLY: PABLOS. LABASBAS CONSTRUCTION CORPORATION) | 9012 | 2023 | 2024-01-04 | 02/21/2023 | 62893.26 | 0 | 2024-01-03 |  | 1
2023 | Region X | MISAMIS ORIENTAL | GINGOOG CITY (MISAMIS ORIENTAL) | P00721540MN | Construction of Revetment | 125.1801 | 8.8874 | 72375000 | 72375000 | 2024 | RITCHE-NATHALIE BUILDERS & GENERAL MERCHANDISE | 9013 | 2023 | 2024-02-27 | 04/20/2023 | 0 | 0 | 2024-03-04 | 6
2022 | Region X | BUKIDNON | SAN FERNANDO (BUKIDNON) | P00620113MN | Construction of Flood Mitigation Structure | 125.3932 | 7.6902 | 49000000 | 48955205.61 | 2022 | JEJOR'S CONSTRUCTION CORPORATION | 9014 | 2022 | 2022-11-21 | 01/28/2022 | 44794.39 | 0 | 2022-11-20 |  | 1
2022 | Region XIII | AGUSAN DEL NORTE | BUTUAN CITY (CAPITAL) (AGUSAN DEL NORTE) | P00630533MN | Construction of Flood Mitigation Structure | 125.5282 | 8.9739 | 139925000 | 139924995.6 | 2023 | ADFIL CORPORATION | 9015 | 2022 | 2023-08-20 | 04/20/2022 | 4.4 | 0 | 2023-08-22 | 2
2022 | Region XI | DAVAO DE ORO | NEW BATAAN (DAVAO DE ORO) | P00620223MN | Construction of Revetment | 126.1283 | 7.4706 | 86849547.62 | 86849347.53 | 2023 | AB APONESTO CONSTRUCTION PARTS AND SUPPLY, INC. | 9016 | 2022 | 2023-03-02 | 04/04/2022 | 200.09 | 0 | 2023-03-01 |  | 1
2022 | Region VIII | SAMAR (WESTERN SAMAR) | BASEY (SAMAR (WESTERN SAMAR)) | P00620218VS | Construction of Flood Mitigation Structure | 125.0818 | 11.3078 | 22539999.99 | 22538367.58 | 2022 | JFR CONSTRUCTION INC. (FORMERLY:JFR CONSTRUCTION) | 9017 | 2022 | 2022-10-03 | 02/14/2022 | 1632.41 | 0 | 2022-10-15 | 12
2023 | Region X | BUKIDNON | CITY OF MALAYBALAY (CAPITAL) (BUKIDNON) | P00721534MN | Construction of Flood Mitigation Structure | 125.1808 | 8.0653 | 96500000 | 96499999.62 | 2024 | RITCHE-NATHALIE BUILDERS & GENERAL MERCHANDISE | 9018 | 2023 | 2024-03-05 | 03/13/2023 | 0.38 | 0 | 2024-03-04 |  | 1
2023 | Region X | BUKIDNON | SAN FERNANDO (BUKIDNON) | P00732050MN | Construction of Flood Mitigation Structure | 125.3943 | 7.797 | 96500000 | 96500000 | 2023 | ROSBILL CONSTRUCTION AND SUPPLY | 9019 | 2023 | 2023-11-21 | 02/28/2023 | 0 | 0 | 2023-12-03 | 12
2023 | Region XI | DAVAO DE ORO | PANTUKAN (DAVAO DE ORO) | P00721568MN | Construction of Revetment | 125.9103 | 7.1015 | 91675000 | 91673488.29 | 2023 | R.A. PAHATI CONST. & SUPPLY, INC. | 9020 | 2023 | 2023-12-19 | 03/17/2023 | 1511.71 | 0 | 2024-01-13 | 25
2022 | Region XIII | AGUSAN DEL NORTE | BUTUAN CITY (CAPITAL) (AGUSAN DEL NORTE) | P00630547MN | Construction of Drainage Structure | 125.5288 | 8.9443 | 135100000 | 135099705.3 | 2023 | M. MONTESCLAROS ENTERPRISES, INC. | 9021 | 2022 | 2023-06-13 | 04/20/2022 | 294.7 | 0 | 2023-06-12 |  | 1
2022 | Region XI | DAVAO OCCIDENTAL | JOSE ABAD SANTOS (TRINIDAD) (DAVAO OCCIDENTAL) | P00620056MN | Construction of Revetment | 125.5293 | 5.7676 | 68813185 | 68810185 | 2022 | ALPHA & OMEGA GEN. CONTRACTOR & DEVELOPMENT CORP. | 9022 | 2022 | 2022-08-13 | 02/24/2022 | 3000 | 0 | 2022-08-12 |  | 1
2022 | Region VIII | EASTERN SAMAR | LLORENTE (EASTERN SAMAR) | P00630677VS | Construction of Flood Mitigation Structure | 125.5297 | 11.4394 | 9898988.07 | 9899995.36 | 2022 | DRAGON CONSTRUCTION | 9023 | 2022 | 2022-08-05 | 03/31/2022 | 0 | 1007.29 | 2022-08-04 |  | 1
2023 | Region XIII | AGUSAN DEL NORTE | JABONGA (AGUSAN DEL NORTE) | P00721326MN | Construction of Dike | 125.5299 | 9.3214 | 120625000 | 120624592.9 | 2024 | EQUI-PARCO CONSTRUCTION COMPANY | 9024 | 2023 | 2024-06-05 | 05/30/2023 | 407.1 | 0 | 2024-06-11 | 6
2023 | Region XIII | AGUSAN DEL NORTE | BUTUAN CITY (CAPITAL) (AGUSAN DEL NORTE) | P00721329MN | Construction of Drainage Structure | 125.5318 | 8.9457 | 193000000 | 192999993.1 | 2024 | RAMISES CONSTRUCTION / EQUI-PARCO CONSTRUCTION COMPANY | 9025 | 2023 | 2024-10-18 | 07/28/2023 | 6.9 | 0 | 2024-12-04 | 47
2022 | Region XIII | AGUSAN DEL NORTE | BUTUAN CITY (CAPITAL) (AGUSAN DEL NORTE) | P00630548MN | Construction of Drainage Structure | 125.5323 | 8.9365 | 135100000 | 135099965.5 | 2023 | ADFIL CORPORATION | 9026 | 2022 | 2023-05-18 | 04/11/2022 | 34.5 | 0 | 2023-05-17 |  | 1
2024 | Region XIII | AGUSAN DEL NORTE | BUTUAN CITY (CAPITAL) (AGUSAN DEL NORTE) | P00835855MN | Rehabilitation / Major Repair of Flood Control Structure | 125.5328 | 8.9619 | 96482283.74 | 96482281.4 | 2024 | RAMISES CONSTRUCTION | 9027 | 2024 | 2024-11-25 | 06/05/2024 | 2.34 | 0 | 2025-05-15 | 171
2022 | Region XI | DAVAO DEL SUR | DAVAO CITY (DAVAO DEL SUR) | P00633910MN | Construction of Drainage Structure | 125.5738 | 7.0405 | 6860000 | 6860000 | 2022 | MITZ CONSTRUCTION AND SUPPLY | 9028 | 2022 | 2022-12-26 | 06/09/2022 | 0 | 0 | 2022-12-25 |  | 1
2022 | Region XIII | AGUSAN DEL SUR | ESPERANZA (AGUSAN DEL SUR) | P00620191MN | Construction of Flood Mitigation Structure | 125.6446 | 8.6734 | 26460000 | 26459992.51 | 2023 | LM CONSTRUCTION AND GENERAL MARKETING | 9029 | 2022 | 2023-04-28 | 06/03/2022 | 7.49 | 0 | 2023-04-27 |  | 1
2024 | Region XIII | AGUSAN DEL NORTE | TUBAY (AGUSAN DEL NORTE) | P00820373MN | Construction of Flood Mitigation Structure | 125.5329 | 9.1535 | 96500000 | 96499972.48 | 2024 | EQUI-PARCO CONSTRUCTION COMPANY | 9030 | 2024 | 2024-12-03 | 05/03/2024 | 27.52 | 0 | 2024-12-27 | 24
2022 | Region XI | DAVAO OCCIDENTAL | MALITA (DAVAO OCCIDENTAL) | P00631106MN | Construction of Slope Protection Structure | 125.533 | 6.4528 | 14850000 | 14839942.58 | 2022 | DISEM CONSTRUCTION AND SUPPLY | 9031 | 2022 | 2022-07-31 | 03/23/2022 | 10057.42 | 0 | 2022-07-30 |  | 1
2022 | Region XI | DAVAO OCCIDENTAL | MALITA (DAVAO OCCIDENTAL) | P00630349MN | Construction of Slope Protection Structure | 125.5334 | 6.4531 | 14700000 | 14695835.77 | 2022 | FORTSTONE CONSTRUCTION ENTERPRISES | 9032 | 2022 | 2022-07-04 | 02/24/2022 | 4164.23 | 0 | 2022-07-03 |  | 1
2022 | Region XIII | AGUSAN DEL NORTE | CITY OF CABADBARAN (AGUSAN DEL NORTE) | P00630540MN | Construction of Flood Mitigation Structure | 125.5335 | 9.1284 | 115800000 | 115799995.1 | 2023 | TRIPARCO DEVELOPMENT CORPORATION | 9033 | 2022 | 2023-03-31 | 06/28/2022 | 4.9 | 0 | 2023-05-02 | 32
2023 | Region XIII | AGUSAN DEL NORTE | TUBAY (AGUSAN DEL NORTE) | P00721651MN | Construction of Flood Mitigation Structure | 125.5342 | 9.1542 | 159225000 | 159223478.1 | 2024 | EQUI-PARCO CONSTRUCTION COMPANY | 9034 | 2023 | 2024-01-31 | 07/20/2023 | 1521.9 | 0 | 2024-05-28 | 118
2021 | Region XI | DAVAO DEL SUR |  | P00550529MN | Construction of Flood Mitigation Structure | 125.5346 | 7.0588 | 86850000 | 86850000 | 2023 | GENESIS88 CONSTRUCTION INC. | 9035 | 2021 | 2023-06-04 | 12/05/2021 | 0 | 0 | 2023-06-03 |  | 1
2024 | Region XIII | AGUSAN DEL NORTE | CITY OF CABADBARAN (AGUSAN DEL NORTE) | P00835844MN | Construction of Flood Mitigation Structure | 125.5371 | 9.1275 | 193000000 | 192999918.7 | 2025 | TRIPARCO DEVELOPMENT CORPORATION | 9036 | 2024 | 2025-05-15 | 05/03/2024 | 81.3 | 0 | 2025-06-30 | 46
2022 | Region XIII | AGUSAN DEL NORTE | BUTUAN CITY (CAPITAL) (AGUSAN DEL NORTE) | P00630542MN | Construction of Flood Mitigation Structure | 125.5373 | 8.9733 | 106150000 | 106149994.9 | 2024 | ME 3 CONSTRUCTION | 9037 | 2022 | 2024-03-06 | 04/11/2022 | 5.1 | 0 | 2024-03-05 |  | 1
2022 | Region XIII | AGUSAN DEL NORTE | BUTUAN CITY (CAPITAL) (AGUSAN DEL NORTE) | P00630549MN | Construction of Drainage Structure | 125.5378 | 8.9621 | 154400000 | 154399819.6 | 2023 | TRIPARCO DEVELOPMENT CORPORATION | 9038 | 2022 | 2023-12-02 | 04/20/2022 | 180.4 | 0 | 2023-12-02 | 0
2022 | Region XIII | AGUSAN DEL NORTE | TUBAY (AGUSAN DEL NORTE) | P00620102MN | Construction of Flood Mitigation Structure | 125.5381 | 9.1526 | 106150000 | 106149980.6 | 2023 | TRIPARCO DEVELOPMENT CORPORATION | 9039 | 2022 | 2023-07-31 | 09/22/2022 | 19.4 | 0 | 2023-08-06 | 6
2022 | Region XI | DAVAO DEL SUR | DAVAO CITY (DAVAO DEL SUR) | P00633894MN | Construction of Flood Mitigation Structure | 125.5384 | 7.0685 | 86850000 | 86850000 | 2023 | GENESIS88 CONSTRUCTION INC. | 9040 | 2022 | 2023-04-15 | 04/13/2022 | 0 | 0 | 2023-05-21 | 36
2022 | Region XI | DAVAO DEL SUR | DAVAO CITY (DAVAO DEL SUR) | P00633895MN | Construction of Flood Mitigation Structure | 125.5384 | 7.0685 | 86850000 | 86850000 | 2023 | GENESIS88 CONSTRUCTION INC. | 9041 | 2022 | 2023-04-28 | 04/13/2022 | 0 | 0 | 2023-05-21 | 23
2022 | Region XIII | SURIGAO DEL NORTE | MAINIT (SURIGAO DEL NORTE) | P00630648MN | Construction of Flood Mitigation Structure | 125.5386 | 9.5406 | 49000000 | 48999990.04 | 2022 | JMT CONSTRUCTION | 9042 | 2022 | 2022-09-10 | 02/11/2022 | 9.96 | 0 | 2022-09-12 | 2
2022 | Region XI | DAVAO DEL SUR | DAVAO CITY (DAVAO DEL SUR) | P00633900MN | Construction of Revetment | 125.5399 | 7.0669 | 96500000 | 96500000 | 2023 | GENESIS88 CONSTRUCTION INC. | 9043 | 2022 | 2023-02-10 | 06/21/2022 | 0 | 0 | 2023-08-02 | 173
2022 | Region VIII | EASTERN SAMAR | GENERAL MACARTHUR (EASTERN SAMAR) | P00620180VS | Construction of Flood Mitigation Structure | 125.5403 | 11.2436 | 25249702.91 | 25249692.26 | 2022 | DRAGON CONSTRUCTION | 9044 | 2022 | 2022-10-24 | 02/13/2022 | 10.65 | 0 | 2022-11-06 | 13
2022 | Region XIII | AGUSAN DEL NORTE | BUTUAN CITY (CAPITAL) (AGUSAN DEL NORTE) | P00620257MN | Construction of Flood Mitigation Structure | 125.5404 | 8.8878 | 96500000 | 96495931.27 | 2024 | ME 3 CONSTRUCTION / HAPPY ALL3 BUILDERS CORPORATION | 9045 | 2022 | 2024-08-17 | 08/22/2022 | 4068.73 | 0 | 2024-08-16 |  | 1
2024 | Region XIII | AGUSAN DEL NORTE | CITY OF CABADBARAN (AGUSAN DEL NORTE) | P00821209MN | Construction of Flood Mitigation Structure | 125.5405 | 9.1091 | 96500000 | 96499018.71 | 2024 | ME 3 CONSTRUCTION | 9046 | 2024 | 2024-08-15 | 02/21/2024 | 981.29 | 0 | 2024-10-31 | 77
2023 | Region XIII | AGUSAN DEL NORTE | BUTUAN CITY (CAPITAL) (AGUSAN DEL NORTE) | P00732103MN | Construction of Drainage Structure | 125.5405 | 8.9475 | 241250000 | 241249035.5 | 2024 | ME 3 CONSTRUCTION / EQUI-PARCO CONSTRUCTION COMPANY | 9047 | 2023 | 2024-11-15 | 07/28/2023 | 964.5 | 0 | 2024-11-15 | 0
2023 | Region XIII | AGUSAN DEL NORTE | BUTUAN CITY (CAPITAL) (AGUSAN DEL NORTE) | P00721328MN | Construction of Drainage Structure | 125.5405 | 8.9477 | 289500000 | 289499997.3 | 2024 | ME 3 CONSTRUCTION / EQUI-PARCO CONSTRUCTION COMPANY | 9048 | 2023 | 2024-12-05 | 07/28/2023 | 2.7 | 0 | 2024-12-04 |  | 1
2023 | Region XIII | AGUSAN DEL NORTE | BUTUAN CITY (CAPITAL) (AGUSAN DEL NORTE) | P00732105MN | Construction of Drainage Structure | 125.5408 | 8.9509 | 193000000 | 192999392.8 | 2024 | ADFIL CORPORATION | 9049 | 2023 | 2024-11-30 | 07/21/2023 | 607.2 | 0 | 2025-01-27 | 58
2023 | Region XIII | AGUSAN DEL NORTE | BUTUAN CITY (CAPITAL) (AGUSAN DEL NORTE) | P00734012MN | Construction of Drainage Structure | 125.5408 | 8.9509 | 144750000 | 144749612 | 2024 | EQUI-PARCO CONSTRUCTION COMPANY | 9050 | 2023 | 2024-07-30 | 07/28/2023 | 388 | 0 | 2024-09-21 | 53
2022 | Region XI | DAVAO DEL SUR | DAVAO CITY (DAVAO DEL SUR) | P00633899MN | Construction of Revetment | 125.5414 | 7.0649 | 96500000 | 96500000 | 2023 | GENESIS88 CONSTRUCTION INC. | 9051 | 2022 | 2023-04-15 | 06/13/2022 | 0 | 0 | 2023-08-24 | 131
2022 | Region XI | DAVAO DEL SUR | DAVAO CITY (DAVAO DEL SUR) | P00633918MN | Construction of Drainage Structure | 125.5426 | 7.0819 | 4900000 | 4899871.34 | 2022 | DICON BUILDERS CORP. | 9052 | 2022 | 2022-08-23 | 04/13/2022 | 128.66 | 0 | 2022-08-22 |  | 1
2022 | Region XI | DAVAO DEL SUR | DAVAO CITY (DAVAO DEL SUR) | P00633916MN | Construction of Drainage Structure | 125.5428 | 7.0812 | 4900000 | 4899450.44 | 2022 | DINGO BUILDERS AND SUPPLY | 9053 | 2022 | 2022-12-24 | 06/05/2022 | 549.56 | 0 | 2022-12-23 |  | 1
2025 | Region XIII | AGUSAN DEL NORTE | BUTUAN CITY (CAPITAL) (AGUSAN DEL NORTE) | P00920380MN | Construction of Flood Mitigation Structure | 125.5431 | 8.9394 | 96455183.12 | 96158174.5 | 2025 | RAMISES CONSTRUCTION | 9054 | 2025 | 2025-05-30 | 02/12/2025 | 297008.62 | 0 | 2025-12-07 | 191
2023 | Region XIII | AGUSAN DEL NORTE | SANTIAGO (AGUSAN DEL NORTE) | P00721324MN | Construction of Flood Mitigation Structure | 125.5441 | 9.2583 | 144750000 | 144749974.6 | 2024 | RAMISES CONSTRUCTION / EQUI-PARCO CONSTRUCTION COMPANY | 9055 | 2023 | 2024-07-09 | 07/25/2023 | 25.4 | 0 | 2024-07-08 |  | 1
2023 | Region XIII | AGUSAN DEL NORTE | BUTUAN CITY (CAPITAL) (AGUSAN DEL NORTE) | P00721332MN | Construction of Drainage Structure | 125.5442 | 8.9473 | 144750000 | 144749954.9 | 2024 | EQUI-PARCO CONSTRUCTION COMPANY | 9056 | 2023 | 2024-09-20 | 07/28/2023 | 45.1 | 0 | 2024-09-21 | 1
2023 | Region XIII | AGUSAN DEL NORTE | BUTUAN CITY (CAPITAL) (AGUSAN DEL NORTE) | P00721337MN | Construction of Flood Mitigation Structure | 125.5455 | 8.9495 | 144750000 | 144749968.1 | 2024 | EQUI-PARCO CONSTRUCTION COMPANY / TRIPARCO DEVELOPMENT CORPORATION | 9057 | 2023 | 2024-04-28 | 04/20/2023 | 31.9 | 0 | 2024-04-27 |  | 1
2021 | Region XI | DAVAO DEL SUR |  | P00522311MN | Construction of Revetment | 125.5457 | 7.0617 | 65369100 | 65369100 | 2022 | GENESIS88 CONSTRUCTION INC. | 9058 | 2021 | 2022-12-18 | 12/01/2021 | 0 | 0 | 2022-12-17 |  | 1
2021 | Region XI | DAVAO DEL SUR |  | P00550520MN | Construction of Revetment | 125.5458 | 7.0613 | 88780000 | 88780000 | 2023 | GENESIS88 CONSTRUCTION INC. | 9059 | 2021 | 2023-02-25 | 12/16/2021 | 0 | 0 | 2023-02-24 |  | 1
2023 | Region XI | DAVAO DEL SUR | DAVAO CITY (DAVAO DEL SUR) | P00721432MN | Construction of Revetment | 125.5461 | 7.0605 | 76042000 | 76042000 | 2024 | GENESIS88 CONSTRUCTION INC. | 9060 | 2023 | 2024-03-14 | 02/20/2023 | 0 | 0 | 2024-03-27 | 13
2021 | Region XI | DAVAO DEL SUR |  | P00522313MN | Construction of Revetment | 125.5463 | 7.0628 | 64848000 | 64848000 | 2022 | GENESIS88 CONSTRUCTION INC. | 9061 | 2021 | 2022-10-17 | 12/01/2021 | 0 | 0 | 2022-10-16 |  | 1
2023 | Region XI | DAVAO DEL SUR | DAVAO CITY (DAVAO DEL SUR) | P00734375MN | Construction of Revetment | 125.5465 | 7.0626 | 99000000 | 99000000 | 2023 | GENESIS88 CONSTRUCTION INC. | 9062 | 2023 | 2023-12-16 | 04/19/2023 | 0 | 0 | 2024-02-14 | 60
2021 | Region XI | DAVAO DEL SUR |  | P00522312MN | Construction of Revetment | 125.5467 | 7.0626 | 65427000 | 65427000 | 2022 | GENESIS88 CONSTRUCTION INC. | 9063 | 2021 | 2022-12-18 | 12/01/2021 | 0 | 0 | 2022-12-17 |  | 1
2021 | Region XI | DAVAO DEL SUR |  | P00522307MN | Construction of Revetment | 125.5485 | 7.0633 | 57900000 | 57900000 | 2022 | GENESIS88 CONSTRUCTION INC. | 9064 | 2021 | 2022-10-01 | 12/01/2021 | 0 | 0 | 2022-09-30 |  | 1
2024 | Region VIII | EASTERN SAMAR | CITY OF BORONGAN (CAPITAL) (EASTERN SAMAR) | P00820125VS | Construction of Flood Mitigation Structure | 125.5499 | 11.4094 | 77200000 | 77199970.5 | 2024 | JAMA88 BUILDERS INC. / P.B. OBIAL CONSTRUCTION | 9065 | 2024 | 2024-09-16 | 02/19/2024 | 29.5 | 0 | 2024-09-21 | 5
2022 | Region XI | DAVAO DEL SUR | DAVAO CITY (DAVAO DEL SUR) | P00633911MN | Construction of Drainage Structure | 125.55 | 7.0506 | 9800000 | 9800000 | 2022 | DELOUKRIS BUILDERS | 9066 | 2022 | 2022-12-03 | 06/06/2022 | 0 | 0 | 2022-12-02 |  | 1
2023 | Region XIII | AGUSAN DEL NORTE | SANTIAGO (AGUSAN DEL NORTE) | P00721340MN | Rehabilitation / Major Repair of Flood Control Structure | 125.5505 | 9.2594 | 125450000 | 125449033.6 | 2024 | RAMISES CONSTRUCTION / TRIPARCO DEVELOPMENT CORPORATION | 9067 | 2023 | 2024-05-31 | 04/24/2023 | 966.4 | 0 | 2024-06-04 | 4
2021 | Region XI | DAVAO DEL SUR |  | P00522306MN | Construction of Flood Mitigation Structure | 125.5515 | 7.0498 | 67550000 | 67550000 | 2022 | ARCINUE COMM'L CORPORATION / MINDALIFI CONSTRUCTION AND SUPPLY | 9068 | 2021 | 2022-08-26 | 12/01/2021 | 0 | 0 | 2022-08-25 |  | 1
2022 | Region XI | DAVAO DEL SUR | DAVAO CITY (DAVAO DEL SUR) | P00620361MN | Construction of Revetment | 125.5521 | 7.0506 | 43425000 | 43425000 | 2024 | MORTAR MASTERS & CONCRETE BUILDERS | 9069 | 2022 | 2024-01-17 | 06/05/2022 | 0 | 0 | 2024-01-16 |  | 1
2022 | Region XIII | AGUSAN DEL NORTE | JABONGA (AGUSAN DEL NORTE) | P00630536MN | Construction of Dike | 125.5536 | 9.3195 | 139925000 | 139924798.9 | 2023 | EQUI-PARCO CONSTRUCTION COMPANY | 9070 | 2022 | 2023-07-29 | 04/20/2022 | 201.1 | 0 | 2023-07-28 |  | 1
2023 | Region XIII | DINAGAT ISLANDS | LIBJO (ALBOR) (DINAGAT ISLANDS) | P00721397MN | Construction of Flood Mitigation Structure | 125.5544 | 10.2547 | 9800000 | 9795000 | 2023 | R.F. VARQUEZ CONSTRUCTION | 9071 | 2023 | 2023-07-07 | 03/06/2023 | 5000 | 0 | 2023-07-02 |  | 5
2021 | Region XIII | AGUSAN DEL NORTE |  | P00522122MN | Construction of Revetment | 125.5545 | 9.4168 | 96500000 | 96499998.05 | 2022 | EQUI-PARCO CONSTRUCTION COMPANY | 9072 | 2021 | 2022-07-27 | 04/23/2021 | 1.95 | 0 | 2022-07-26 |  | 1
2022 | Region XI | DAVAO DEL SUR | DAVAO CITY (DAVAO DEL SUR) | P00620360MN | Construction of Revetment | 125.555 | 7.0483 | 135100000 | 131775297.1 | 2023 | LEDCORE CONSTRUCTION AND DEVELOPMENT CORP, / ABU CONSTRUCTION | 9073 | 2022 | 2023-05-30 | 06/08/2022 | 3324702.9 | 0 | 2023-05-29 |  | 1
2024 | Region XIII | AGUSAN DEL NORTE | BUTUAN CITY (CAPITAL) (AGUSAN DEL NORTE) | P00820212MN | Construction of Flood Mitigation Structure | 125.5553 | 8.8707 | 14694467.22 | 14694455.68 | 2024 | ADFIL CORPORATION | 9074 | 2024 | 2024-11-05 | 05/08/2024 | 11.54 | 0 | 2024-11-13 | 8
2023 | Region XI | DAVAO DEL SUR | DAVAO CITY (DAVAO DEL SUR) | P00721498MN | Construction of Revetment | 125.5558 | 7.1771 | 49000000 | 47576550.62 | 2023 | ALPHA & OMEGA GEN. CONTRACTOR & DEVELOPMENT CORP. | 9075 | 2023 | 2023-10-06 | 03/09/2023 | 1423449.38 | 0 | 2023-10-05 |  | 1
2022 | Region XIII | AGUSAN DEL NORTE | JABONGA (AGUSAN DEL NORTE) | P00620101MN | Construction of Revetment | 125.5559 | 9.323 | 77200000 | 77199989.47 | 2022 | TRIPARCO DEVELOPMENT CORPORATION | 9076 | 2022 | 2022-10-17 | 03/08/2022 | 10.53 | 0 | 2022-10-16 |  | 1
2023 | Region XIII | AGUSAN DEL NORTE | BUTUAN CITY (CAPITAL) (AGUSAN DEL NORTE) | P00721334MN | Construction of Flood Mitigation Structure | 125.5561 | 8.8939 | 173700000 | 173699926 | 2024 | ME 3 CONSTRUCTION / EQUI-PARCO CONSTRUCTION COMPANY | 9077 | 2023 | 2024-05-31 | 05/18/2023 | 74 | 0 | 2024-06-24 | 24
2024 | Region XIII | AGUSAN DEL NORTE | JABONGA (AGUSAN DEL NORTE) | P00820208MN | Construction of Slope Protection Structure | 125.5565 | 9.3566 | 19600000 | 19599997.21 | 2024 | ARQ BUILDERS | 9078 | 2024 | 2024-11-14 | 03/05/2024 | 2.79 | 0 | 2024-11-13 |  | 1
2022 | Region XIII | AGUSAN DEL NORTE | BUTUAN CITY (CAPITAL) (AGUSAN DEL NORTE) | P00634124MN | Construction of Flood Mitigation Structure | 125.5582 | 8.8936 | 98971666.04 | 98971642.71 | 2023 | NORTHERN BUILDERS | 9079 | 2022 | 2023-05-12 | 07/13/2022 | 23.33 | 0 | 2023-05-28 | 16
2022 | Region XI | DAVAO DEL SUR | DAVAO CITY (DAVAO DEL SUR) | P00620359MN | Construction of Revetment | 125.5587 | 7.0471 | 144750000 | 144744450.1 | 2024 | GENESIS88 CONSTRUCTION INC. / GEMMA CONSTRUCTION SUPPLY, INC.(FORMERLY:GEMMA CON | 9080 | 2022 | 2024-03-12 | 07/11/2022 | 5549.9 | 0 | 2024-06-19 | 99
2022 | Region XIII | AGUSAN DEL NORTE | CITY OF CABADBARAN (AGUSAN DEL NORTE) | P00630564MN | Construction of Flood Mitigation Structure | 125.5604 | 9.1088 | 96500000 | 96499999.47 | 2023 | DATREBIL CONSTRUCTION & SUPPLY | 9081 | 2022 | 2023-04-18 | 04/10/2022 | 0.53 | 0 | 2023-04-19 | 1
2024 | Region XIII | AGUSAN DEL NORTE | CITY OF CABADBARAN (AGUSAN DEL NORTE) | P00821208MN | Rehabilitation / Major Repair of Flood Control Structure | 125.5607 | 9.1089 | 96500000 | 95534997.85 | 2024 | JD-RG CONSTRUCTION AND SUPPLIES CORP. (FORMERLY: JD-RG CONSTRUCTION CORPORATION) | 9082 | 2024 | 2024-08-07 | 03/26/2024 | 965002.15 | 0 | 2024-12-04 | 119
2021 | Region XI | DAVAO DEL SUR |  | P00522309MN | Construction of Revetment | 125.5611 | 7.0463 | 96500000 | 96500000 | 2023 | MONOLITHIC CONSTRUCTION & CONCRETE PRODUCTS, INC. | 9083 | 2021 | 2023-04-15 | 12/01/2021 | 0 | 0 | 2023-04-14 |  | 1
2024 | Region XIII | AGUSAN DEL NORTE | SANTIAGO (AGUSAN DEL NORTE) | P00820387MN | Construction of Flood Mitigation Structure | 125.5615 | 9.2317 | 49000000 | 48249968.08 | 2024 | ERRA CONSTRUCTION AND DEVELOPMENT INC. (FORMERLY ERRA CONSTRUCTION) | 9084 | 2024 | 2024-07-04 | 02/21/2024 | 750031.92 | 0 | 2024-07-03 |  | 1
2022 | Region XI | DAVAO DEL SUR | DAVAO CITY (DAVAO DEL SUR) | P00620365MN | Rehabilitation / Major Repair of Flood Control Structure | 125.5616 | 7.077 | 96500000 | 96500000 | 2023 | GENESIS88 CONSTRUCTION INC. | 9085 | 2022 | 2023-04-15 | 06/05/2022 | 0 | 0 | 2023-07-14 | 90
2023 | Region XIII | AGUSAN DEL NORTE | BUTUAN CITY (CAPITAL) (AGUSAN DEL NORTE) | P00721486MN | Construction of Revetment | 125.5616 | 8.9853 | 86847002.41 | 86847002.2 | 2023 | NORTHERN BUILDERS | 9086 | 2023 | 2023-12-20 | 03/21/2023 | 0.21 | 0 | 2024-03-05 | 76
2022 | Region XI | DAVAO DEL SUR | DAVAO CITY (DAVAO DEL SUR) | P00620364MN | Rehabilitation / Major Repair of Flood Control Structure | 125.5617 | 7.077 | 96500000 | 96500000 | 2023 | GENESIS88 CONSTRUCTION INC. | 9087 | 2022 | 2023-04-15 | 06/05/2022 | 0 | 0 | 2023-07-14 | 90
2021 | Region XI | DAVAO DEL SUR |  | P00522308MN | Construction of Revetment | 125.5617 | 7.0466 | 96500000 | 96500000 | 2023 | KODUS PEERS CONSTRUCTION CORPORATION / RELY CONSTRUCTION & SUPPLY INC.(FORMERLY: RELY CONSTRUCTION AND SUPPLY) | 9088 | 2021 | 2023-03-20 | 12/01/2021 | 0 | 0 | 2023-04-24 | 35
2023 | Region XI | DAVAO OCCIDENTAL | MALITA (DAVAO OCCIDENTAL) | P00721281MN | Construction of Revetment | 125.5618 | 6.4569 | 86850000 | 86840559.07 | 2023 | AMETHYST HORIZON BUILDERS AND GEN. CONTRACTOR AND DEVELOPMENT CORP. | 9089 | 2023 | 2023-11-02 | 04/05/2023 | 9440.93 | 0 | 2023-11-01 |  | 1
2022 | Region XI | DAVAO DEL SUR | DAVAO CITY (DAVAO DEL SUR) | P00620362MN | Rehabilitation / Major Repair of Flood Control Structure | 125.5633 | 7.077 | 96500000 | 96500000 | 2023 | GENESIS88 CONSTRUCTION INC. | 9090 | 2022 | 2023-04-15 | 06/02/2022 | 0 | 0 | 2023-07-11 | 87
2022 | Region XI | DAVAO DEL SUR | DAVAO CITY (DAVAO DEL SUR) | P00620363MN | Rehabilitation / Major Repair of Flood Control Structure | 125.5634 | 7.0769 | 96500000 | 96500000 | 2023 | GENESIS88 CONSTRUCTION INC. | 9091 | 2022 | 2023-04-15 | 06/06/2022 | 0 | 0 | 2023-07-15 | 91
2022 | Region XI | DAVAO DEL SUR | DAVAO CITY (DAVAO DEL SUR) | P00633912MN | Construction of Drainage Structure | 125.5636 | 7.0987 | 9800000 | 9800000 | 2022 | TWO DEGREES CONSTRUCTION AND SUPPLY | 9092 | 2022 | 2022-09-08 | 04/13/2022 | 0 | 0 | 2022-09-07 |  | 1
2021 | Region XI | DAVAO DEL SUR |  | P00550537MN | Construction of Revetment | 125.5641 | 7.0486 | 96500000 | 94273146.01 | 2024 | MORTAR MASTERS & CONCRETE BUILDERS | 9093 | 2021 | 2024-08-31 | 12/01/2021 | 2226853.99 | 0 | 2024-08-30 |  | 1
2022 | Region XI | DAVAO DEL SUR | DAVAO CITY (DAVAO DEL SUR) | P00633920MN | Construction of Drainage Structure | 125.5643 | 7.0978 | 6860000 | 6736112.96 | 2022 | SNAS CONSTRUCTION AND SUPPLIES | 9094 | 2022 | 2022-11-17 | 06/07/2022 | 123887.04 | 0 | 2022-11-16 |  | 1
2021 | Region XI | DAVAO DEL SUR |  | P00550538MN | Construction of Flood Mitigation Structure | 125.5648 | 7.0453 | 96500000 | 96500000 | 2023 | DREIRICH BUILDERS / THREE W BUILDERS, INC. | 9095 | 2021 | 2023-05-25 | 12/01/2021 | 0 | 0 | 2023-05-24 |  | 1
2021 | Region XI | DAVAO DEL SUR |  | P00550536MN | Construction of Revetment | 125.5651 | 7.0461 | 96500000 | 96500000 | 2022 | MRD GEMPESAW CONSTRUCTION CORP. / MONOLITHIC CONSTRUCTION & CONCRETE PRODUCTS, INC. | 9096 | 2021 | 2022-10-31 | 12/01/2021 | 0 | 0 | 2022-11-07 | 7
2021 | Region XI | DAVAO DEL SUR |  | P00550531MN | Construction of Flood Mitigation Structure | 125.5651 | 7.054 | 67550000 | 67329059.28 | 2022 | TKS BUILDERS & SUPPLIES / LEDCORE CONSTRUCTION AND DEVELOPMENT CORP, | 9097 | 2021 | 2022-08-13 | 12/22/2021 | 220940.72 | 0 | 2022-10-11 | 59
2023 | Region XI | DAVAO DEL SUR | DAVAO CITY (DAVAO DEL SUR) | P00734395MN | Construction of Revetment | 125.5659 | 7.0778 | 99000000 | 99000000 | 2023 | AGONG BUILDERS AND CONSTRUCTION SUPPLY, INC. / GENESIS88 CONSTRUCTION INC. | 9098 | 2023 | 2023-11-25 | 05/30/2023 | 0 | 0 | 2024-03-06 | 102
2022 | Region XIII | AGUSAN DEL NORTE | TUBAY (AGUSAN DEL NORTE) | P00620188MN | Construction of Flood Mitigation Structure | 125.566 | 9.2166 | 41985160 | 41985061.75 | 2022 | ERRA CONSTRUCTION AND DEVELOPMENT INC. (FORMERLY ERRA CONSTRUCTION) | 9099 | 2022 | 2022-07-26 | 02/17/2022 | 98.25 | 0 | 2022-08-09 | 14
2020 | Region XI | DAVAO DEL SUR |  | P00420010MN | Construction of Revetment | 125.5668 | 7.0608 | 86136865 | 86136865 | 2023 | A.Y.U. ENGINEERING & CONSTRUCTION / ABU CONSTRUCTION | 9100 | 2020 | 2023-03-20 | 12/13/2020 | 0 | 0 | 2023-03-19 |  | 1
2021 | Region XI | DAVAO DEL SUR |  | P00420010MN | Construction of Revetment | 125.5668 | 7.0608 | 86136865 | 86136865 | 2023 | A.Y.U. ENGINEERING & CONSTRUCTION / ABU CONSTRUCTION | 9101 | 2021 | 2023-03-20 | 12/13/2020 | 0 | 0 | 2023-03-19 |  | 1
2023 | Region XI | DAVAO DEL SUR | DAVAO CITY (DAVAO DEL SUR) | P00734394MN | Construction of Revetment | 125.5669 | 7.0781 | 99000000 | 99000000 | 2023 | AGONG BUILDERS AND CONSTRUCTION SUPPLY, INC. / GENESIS88 CONSTRUCTION INC. | 9102 | 2023 | 2023-12-16 | 05/30/2023 | 0 | 0 | 2024-03-06 | 81
2023 | Region XI | DAVAO OCCIDENTAL | MALITA (DAVAO OCCIDENTAL) | P00721577MN | Construction of Flood Mitigation Structure | 125.5669 | 6.4918 | 96500000 | 96500000 | 2024 | LEGACY CONSTRUCTION CORPORATION (FORMERLY: LEGACY CONSTRUCTION) | 9103 | 2023 | 2024-02-20 | 05/05/2023 | 0 | 0 | 2024-02-19 |  | 1
2020 | Region XI | DAVAO DEL SUR |  | P00444620MN | Construction of Revetment | 125.5674 | 7.0603 | 26055000 | 26055000 | 2022 | ABU CONSTRUCTION | 9104 | 2020 | 2022-07-19 | 12/17/2020 | 0 | 0 | 2022-07-18 |  | 1
2021 | Region XI | DAVAO DEL SUR |  | P00444620MN | Construction of Revetment | 125.5674 | 7.0603 | 26055000 | 26055000 | 2022 | ABU CONSTRUCTION | 9105 | 2021 | 2022-07-19 | 12/17/2020 | 0 | 0 | 2022-07-18 |  | 1
2022 | Region XIII | SURIGAO DEL NORTE | TUBOD (SURIGAO DEL NORTE) | P00630650MN | Construction of Flood Mitigation Structure | 125.5678 | 9.5943 | 49000000 | 48996788.08 | 2022 | C.V. CONSTRUCTION & DEVELOPMENT | 9106 | 2022 | 2022-09-22 | 02/11/2022 | 3211.92 | 0 | 2022-09-23 | 1
2022 | Region XIII | SURIGAO DEL NORTE | PLACER (SURIGAO DEL NORTE) | P00630641MN | Construction of Flood Mitigation Structure | 125.5681 | 9.6302 | 49000000 | 48999966.7 | 2022 | JMT CONSTRUCTION | 9107 | 2022 | 2022-10-28 | 02/11/2022 | 33.3 | 0 | 2022-10-27 |  | 1
2020 | Region XI | DAVAO DEL SUR |  | P00444621MN | Construction of Revetment | 125.5686 | 7.0601 | 38600000 | 38600000 | 2022 | ABU CONSTRUCTION | 9108 | 2020 | 2022-08-17 | 12/17/2020 | 0 | 0 | 2022-08-16 |  | 1
2021 | Region XI | DAVAO DEL SUR |  | P00444621MN | Construction of Revetment | 125.5686 | 7.0601 | 38600000 | 38600000 | 2022 | ABU CONSTRUCTION | 9109 | 2021 | 2022-08-17 | 12/17/2020 | 0 | 0 | 2022-08-16 |  | 1
2023 | Region XI | DAVAO DEL SUR | DAVAO CITY (DAVAO DEL SUR) | P00721431MN | Construction of Revetment | 125.5688 | 7.0725 | 94570000 | 94500000 | 2023 | GENESIS88 CONSTRUCTION INC. | 9110 | 2023 | 2023-11-25 | 02/20/2023 | 70000 | 0 | 2023-11-28 | 3
2021 | Region XI | DAVAO DEL SUR |  | P00550535MN | Construction of Revetment | 125.5691 | 7.0627 | 87573750 | 87573750 | 2023 | LEGACY CONSTRUCTION CORPORATION (FORMERLY: LEGACY CONSTRUCTION) | 9111 | 2021 | 2023-05-31 | 12/05/2021 | 0 | 0 | 2023-05-30 |  | 1
2024 | Region XIII | DINAGAT ISLANDS | SAN JOSE (CAPITAL) (DINAGAT ISLANDS) | P00820127MN | Construction of Flood Mitigation Structure | 125.5694 | 10.0067 | 72375000 | 72374922.41 | 2024 | CARTESIAN BUILDERS CORPORATION (FORMERLY: CARTESIAN BUILDERS) | 9112 | 2024 | 2024-10-30 | 03/05/2024 | 77.59 | 0 | 2024-10-29 |  | 1
2024 | Region XIII | AGUSAN DEL NORTE | KITCHARAO (AGUSAN DEL NORTE) | P00821097MN | Construction of Flood Mitigation Structure | 125.5697 | 9.4545 | 24500000 | 24418718.81 | 2024 | ARQ BUILDERS | 9113 | 2024 | 2024-08-25 | 04/23/2024 | 81281.19 | 0 | 2024-09-05 | 11
2023 | Region XI | DAVAO DEL SUR | DAVAO CITY (DAVAO DEL SUR) | P00721428MN | Construction of Revetment | 125.5698 | 7.0677 | 188175000 | 188175000 | 2024 | GENESIS88 CONSTRUCTION INC. / ABU CONSTRUCTION | 9114 | 2023 | 2024-09-30 | 08/14/2023 | 0 | 0 | 2024-11-19 | 50
2023 | Region XI | DAVAO DEL SUR | DAVAO CITY (DAVAO DEL SUR) | P00721430MN | Construction of Revetment | 125.5699 | 7.0708 | 94570000 | 94500000 | 2023 | GENESIS88 CONSTRUCTION INC. | 9115 | 2023 | 2023-12-29 | 02/20/2023 | 70000 | 0 | 2023-12-28 |  | 1
2022 | Region XI | DAVAO DEL SUR | DAVAO CITY (DAVAO DEL SUR) | P00620358MN | Construction of Revetment | 125.5703 | 7.0711 | 72375000 | 72375000 | 2023 | GENESIS88 CONSTRUCTION INC. | 9116 | 2022 | 2023-02-24 | 04/13/2022 | 0 | 0 | 2023-02-23 |  | 1
2022 | Region XIII | SURIGAO DEL NORTE | TUBOD (SURIGAO DEL NORTE) | P00630643MN | Construction of Flood Mitigation Structure | 125.5703 | 9.5942 | 49000000 | 48999671.93 | 2022 | JMT CONSTRUCTION | 9117 | 2022 | 2022-10-10 | 02/11/2022 | 328.07 | 0 | 2022-10-10 | 0
2022 | Region XIII | DINAGAT ISLANDS | SAN JOSE (CAPITAL) (DINAGAT ISLANDS) | P00631115MN | Construction of Flood Mitigation Structure | 125.5704 | 10.0101 | 4950000 | 4946614.79 | 2022 | RJB CONSTRUCTION & SUPPLY | 9118 | 2022 | 2022-08-11 | 03/15/2022 | 3385.21 | 0 | 2022-08-10 |  | 1
2022 | Region XIII | AGUSAN DEL NORTE | BUTUAN CITY (CAPITAL) (AGUSAN DEL NORTE) | P00620256MN | Construction of Flood Mitigation Structure | 125.5706 | 8.7795 | 97322180 | 97321479.64 | 2023 | ME 3 CONSTRUCTION | 9119 | 2022 | 2023-11-15 | 12/06/2022 | 700.36 | 0 | 2023-11-14 |  | 1
2021 | Region XI | DAVAO DEL SUR |  | P00550534MN | Construction of Revetment | 125.5709 | 7.068 | 85306000 | 85306000 | 2023 | THREE W BUILDERS, INC. | 9120 | 2021 | 2023-03-27 | 12/05/2021 | 0 | 0 | 2023-03-26 |  | 1
2020 | Region XI | DAVAO DEL SUR |  | P00420401MN | Construction of Flood Mitigation Structure | 125.571 | 7.2623 | 67550000 | 67550000 | 2022 | RAKKI CORPORATION / RELY CONSTRUCTION & SUPPLY INC.(FORMERLY: RELY CONSTRUCTION AND SUPPLY) | 9121 | 2020 | 2022-12-20 | 12/16/2020 | 0 | 0 | 2022-12-19 |  | 1
2021 | Region XI | DAVAO DEL SUR |  | P00420401MN | Construction of Flood Mitigation Structure | 125.571 | 7.2623 | 67550000 | 67550000 | 2022 | RAKKI CORPORATION / RELY CONSTRUCTION & SUPPLY INC.(FORMERLY: RELY CONSTRUCTION AND SUPPLY) | 9122 | 2021 | 2022-12-20 | 12/16/2020 | 0 | 0 | 2022-12-19 |  | 1
2022 | Region XI | DAVAO DEL SUR | DAVAO CITY (DAVAO DEL SUR) | P00620077MN | Construction of Revetment | 125.5722 | 7.0718 | 75270000 | 75270000 | 2023 | GENESIS88 CONSTRUCTION INC. | 9123 | 2022 | 2023-02-28 | 04/13/2022 | 0 | 0 | 2023-02-27 |  | 1
2021 | Region XIII | AGUSAN DEL NORTE |  | P00522126MN | Construction of Flood Mitigation Structure | 125.5731 | 8.7767 | 96500000 | 96499728.2 | 2023 | ME 3 CONSTRUCTION | 9124 | 2021 | 2023-03-15 | 08/16/2021 | 271.8 | 0 | 2023-05-23 | 69
2024 | Region XII | COTABATO (NORTH COTABATO) | MAKILALA (COTABATO (NORTH COTABATO)) | P00820415MN | Construction of Revetment | 125.0819 | 6.9383 | 49000000 | 48755000 | 2024 | LLABAN CONSTRUCTION & SUPPLY (FORMERLY: LLABAN CON | 9125 | 2024 | 2024-11-21 | 02/20/2024 | 245000 | 0 | 2024-12-03 | 12
2023 | Region VIII | SAMAR (WESTERN SAMAR) | MARABUT (SAMAR (WESTERN SAMAR)) | P00732049VS | Construction of Flood Mitigation Structure | 125.1836 | 11.2083 | 19599998.1 | 19456364.68 | 2023 | ETAN CONSTRUCTION | 9126 | 2023 | 2023-08-04 | 04/03/2023 | 143633.42 | 0 | 2023-11-19 | 107
2022 | Region XI | DAVAO DE ORO | MAWAB (DAVAO DE ORO) | P00630766MN | Construction of Revetment | 125.9182 | 7.8091 | 67549897.37 | 67549897.37 | 2022 | LEGACY CONSTRUCTION CORPORATION (FORMERLY: LEGACY CONSTRUCTION) | 9127 | 2022 | 2022-12-13 | 02/23/2022 | 0 | 0 | 2022-12-21 | 8
2024 | Region XIII | AGUSAN DEL NORTE | BUENAVISTA (AGUSAN DEL NORTE) | P00820386MN | Construction of Flood Mitigation Structure | 125.3989 | 8.9272 | 67550000 | 67324492.17 | 2024 | ERRA CONSTRUCTION AND DEVELOPMENT INC. (FORMERLY ERRA CONSTRUCTION) | 9128 | 2024 | 2024-07-31 | 02/21/2024 | 225507.83 | 0 | 2024-08-17 | 17
2023 | Region XI | DAVAO ORIENTAL | GOVERNOR GENEROSO (DAVAO ORIENTAL) | P00721289MN | Construction of Flood Mitigation Structure | 126.1366 | 6.6779 | 39200000 | 39200000 | 2023 | MAER SUMMIT KONSTRUKT CO. | 9129 | 2023 | 2023-11-06 | 03/27/2023 | 0 | 0 | 2023-11-05 |  | 1
2023 | Region X | BUKIDNON | CITY OF VALENCIA (BUKIDNON) | P00721413MN | Construction of Flood Mitigation Structure | 125.1881 | 7.9659 | 188000000 | 184139315.4 | 2024 | M. MONTESCLAROS ENTERPRISES, INC. | 9130 | 2023 | 2024-02-21 | 03/29/2023 | 3860684.6 | 0 | 2024-01-21 |  | 31
2022 | Region XII | COTABATO (NORTH COTABATO) | MAGPET (COTABATO (NORTH COTABATO)) | P00620237MN | Construction of Dike | 125.0834 | 7.1285 | 67550000 | 67550000 | 2023 | MARCUS CONSTRUCTION & SUPPLY | 9131 | 2022 | 2023-11-30 | 02/24/2022 | 0 | 0 | 2023-04-12 |  | 232
2021 | Region XI | DAVAO DE ORO |  | P00550463MN | Construction of Drainage Structure | 125.9207 | 7.5095 | 8819892.15 | 8818897.77 | 2022 | AGONG BUILDERS AND CONSTRUCTION SUPPLY, INC. | 9132 | 2021 | 2022-09-18 | 03/24/2022 | 994.38 | 0 | 2022-09-17 |  | 1
2022 | Region XI | DAVAO DEL SUR | DAVAO CITY (DAVAO DEL SUR) | P00630602MN | Rehabilitation / Major Repair of Drainage Structure | 125.6446 | 7.0996 | 9800000 | 9800000 | 2023 | ROSBILL CONSTRUCTION AND SUPPLY | 9133 | 2022 | 2023-02-22 | 04/06/2022 | 0 | 0 | 2023-02-21 |  | 1
2023 | Region XIII | AGUSAN DEL NORTE | KITCHARAO (AGUSAN DEL NORTE) | P00734035MN | Construction of Flood Mitigation Structure | 125.5747 | 9.4525 | 29400000 | 29057806.81 | 2024 | ARQ BUILDERS | 9134 | 2023 | 2024-01-10 | 05/11/2023 | 342193.19 | 0 | 2024-01-09 |  | 1
2022 | Region XI | DAVAO DEL SUR | MALALAG (DAVAO DEL SUR) | P00644823MN | Rehabilitation / Major Repair of Flood Control Structure | 125.3989 | 6.5988 | 48250000 | 48250000 | 2023 | TKS BUILDERS & SUPPLIES / ACC GOLDEN CONSTRUCTION SERVICES | 9135 | 2022 | 2023-09-17 | 03/30/2023 | 0 | 0 | 2023-09-16 |  | 1
2023 | Region XIII | AGUSAN DEL NORTE | BUENAVISTA (AGUSAN DEL NORTE) | P00721344MN | Construction of Flood Mitigation Structure | 125.3998 | 8.971 | 96500000 | 96498619.17 | 2023 | ADFIL CORPORATION | 9136 | 2023 | 2023-10-18 | 02/16/2023 | 1380.83 | 0 | 2023-10-17 |  | 1
2023 | Region XI | DAVAO DEL SUR | MALALAG (DAVAO DEL SUR) | P00732488MN | Construction of Flood Mitigation Structure | 125.4013 | 6.604 | 4950000 | 4950000 | 2023 | R.C. MELGAZO BUILDERS | 9137 | 2023 | 2023-05-01 | 02/17/2023 | 0 | 0 | 2023-04-30 |  | 1
2024 | Region XIII | AGUSAN DEL NORTE | BUENAVISTA (AGUSAN DEL NORTE) | P00820124MN | Construction of Flood Mitigation Structure | 125.4014 | 8.9249 | 49000000 | 48229136.27 | 2024 | C'ZARLES CONSTRUCTION & SUPPLY | 9138 | 2024 | 2024-07-17 | 03/05/2024 | 770863.73 | 0 | 2024-07-16 |  | 1
2023 | Region XIII | AGUSAN DEL NORTE | BUENAVISTA (AGUSAN DEL NORTE) | P00721345MN | Construction of Flood Mitigation Structure | 125.4027 | 8.925 | 96500000 | 96499998.2 | 2023 | ERRA CONSTRUCTION AND DEVELOPMENT INC. (FORMERLY ERRA CONSTRUCTION) / ROIM BUILDERS & CONSTRUCTION SUPPLY | 9139 | 2023 | 2023-09-15 | 02/16/2023 | 1.8 | 0 | 2023-10-31 | 46
2023 | Region XIII | SURIGAO DEL NORTE | MALIMONO (SURIGAO DEL NORTE) | P00746151MN | Rehabilitation / Major Repair of Flood Control Structure | 125.4046 | 9.6106 | 144750000 | 144749996.6 | 2024 | SANTECH BUILDERS CORPORATION | 9140 | 2023 | 2024-12-15 | 01/15/2024 | 3.4 | 0 | 2025-03-03 | 78
2023 | Region XII | SARANGANI | ALABEL (CAPITAL) (SARANGANI) | P00721303MN | Construction of Flood Mitigation Structure | 125.4047 | 6.1094 | 77200000 | 77186230.46 | 2023 | REYDAN BUILDERS | 9141 | 2023 | 2023-11-15 | 04/05/2023 | 13769.54 | 0 | 2024-01-08 | 54
2023 | Region XIII | SURIGAO DEL NORTE | MALIMONO (SURIGAO DEL NORTE) | P00746150MN | Rehabilitation / Major Repair of Flood Control Structure | 125.405 | 9.6106 | 144750000 | 144749996.8 | 2024 | GICAR CONSTRUCTION, INC. | 9142 | 2023 | 2024-12-15 | 01/15/2024 | 3.2 | 0 | 2025-03-18 | 93
2024 | Region XII | SARANGANI | MALAPATAN (SARANGANI) | P00820201MN | Construction of Flood Mitigation Structure | 125.4103 | 6.0166 | 29400000 | 29385001.95 | 2024 | EDCL CONSTRUCTION AND SUPPLY | 9143 | 2024 | 2024-08-10 | 02/13/2024 | 14998.05 | 0 | 2024-08-09 |  | 1
2021 | Region XI | DAVAO DEL SUR |  | P00522202MN | Construction of Flood Mitigation Structure | 125.4114 | 6.8438 | 29400000 | 29399992.54 | 2022 | VIBRANIUM BUILDERS CORPORATION | 9144 | 2021 | 2022-08-01 | 01/05/2022 | 7.46 | 0 | 2022-07-31 |  | 1
2023 | Region XI | DAVAO DEL SUR | SANTA CRUZ (DAVAO DEL SUR) | P00721279MN | Construction of Flood Mitigation Structure | 125.4115 | 6.8353 | 62725000 | 62725000 | 2023 | DREIRICH BUILDERS / THREE W BUILDERS, INC. | 9145 | 2023 | 2023-10-16 | 02/17/2023 | 0 | 0 | 2023-10-15 |  | 1
2024 | Region XIII | AGUSAN DEL NORTE | BUENAVISTA (AGUSAN DEL NORTE) | P00821203MN | Construction of Flood Mitigation Structure | 125.4129 | 8.9698 | 96500000 | 96486681.01 | 2024 | JD-RG CONSTRUCTION AND SUPPLIES CORP. (FORMERLY: JD-RG CONSTRUCTION CORPORATION) | 9146 | 2024 | 2024-09-20 | 03/21/2024 | 13318.99 | 0 | 2024-11-29 | 70
2022 | Region XI | DAVAO DEL SUR | DAVAO CITY (DAVAO DEL SUR) | P00630594MN | Construction of Drainage Structure | 125.413 | 7.0641 | 9800000 | 9671178.66 | 2022 | ZULAR-AZ CONSTRUCTION AND SUPPLY, INC. | 9147 | 2022 | 2022-09-30 | 04/22/2022 | 128821.34 | 0 | 2022-09-29 |  | 1
2023 | Region XIII | SURIGAO DEL NORTE | MALIMONO (SURIGAO DEL NORTE) | P00746154MN | Rehabilitation / Major Repair of Flood Control Structure | 125.4131 | 9.5781 | 144750000 | 144749721.9 | 2024 | GICAR CONSTRUCTION, INC. | 9148 | 2023 | 2024-11-26 | 01/15/2024 | 278.1 | 0 | 2025-02-04 | 70
2023 | Region VIII | EASTERN SAMAR | TAFT (EASTERN SAMAR) | P00732044VS | Construction of Drainage Structure | 125.4135 | 11.9057 | 9899999.97 | 9899996.18 | 2023 | ST. ROCH CONSTRUCTION | 9149 | 2023 | 2023-10-23 | 04/10/2023 | 3.79 | 0 | 2023-10-22 |  | 1
2022 | Region XIII | SURIGAO DEL NORTE | MALIMONO (SURIGAO DEL NORTE) | P00630636MN | Construction of Flood Mitigation Structure | 125.4183 | 9.5674 | 19600000 | 19419790.5 | 2023 | RJB CONSTRUCTION & SUPPLY | 9150 | 2022 | 2023-07-01 | 03/24/2022 | 180209.5 | 0 | 2023-05-04 |  | 58
2022 | Region XIII | AGUSAN DEL NORTE | BUENAVISTA (AGUSAN DEL NORTE) | P00630141MN | Construction of Flood Mitigation Structure | 125.4185 | 8.8841 | 125450000 | 125449709.1 | 2023 | C'ZARLES CONSTRUCTION & SUPPLY | 9151 | 2022 | 2023-10-22 | 10/07/2022 | 290.9 | 0 | 2023-10-21 |  | 1
2024 | Region XIII | SURIGAO DEL NORTE | MALIMONO (SURIGAO DEL NORTE) | P00836200MN | Construction of Flood Mitigation Structure | 125.419 | 9.6158 | 99000000 | 98999840.66 | 2025 | RCDG CONSTRUCTION CORPORATION / LPO1 GROUP OF COMPANIES INC. | 9152 | 2024 | 2025-02-27 | 06/28/2024 | 159.34 | 0 | 2025-04-02 | 34
2022 | Region VIII | EASTERN SAMAR | MAYDOLONG (EASTERN SAMAR) | P00630678VS | Construction of Flood Mitigation Structure | 125.4192 | 11.5034 | 4949998.65 | 4949994.6 | 2022 | TUBIGAN BUILDERS | 9153 | 2022 | 2022-07-12 | 04/07/2022 | 4.05 | 0 | 2022-07-11 |  | 1
2023 | Region XIII | SURIGAO DEL NORTE | MALIMONO (SURIGAO DEL NORTE) | P00746153MN | Rehabilitation / Major Repair of Flood Control Structure | 125.4196 | 9.5682 | 144750000 | 144749283.6 | 2024 | SANTECH BUILDERS CORPORATION | 9154 | 2023 | 2024-11-21 | 01/15/2024 | 716.4 | 0 | 2025-02-09 | 80
2023 | Region XIII | SURIGAO DEL NORTE | MALIMONO (SURIGAO DEL NORTE) | P00734002MN | Construction of Flood Mitigation Structure | 125.423 | 9.569 | 96500000 | 96499988.91 | 2024 | C.V. CONSTRUCTION & DEVELOPMENT | 9155 | 2023 | 2024-04-12 | 05/09/2023 | 11.09 | 0 | 2024-04-11 |  | 1
2022 | Region XIII | SURIGAO DEL NORTE | SAN FRANCISCO (ANAO-AON) (SURIGAO DEL NORTE) | P00630632MN | Construction of Flood Mitigation Structure | 125.4272 | 9.7748 | 39200000 | 39199647.2 | 2022 | C.V. CONSTRUCTION & DEVELOPMENT | 9156 | 2022 | 2022-11-14 | 02/11/2022 | 352.8 | 0 | 2022-11-19 | 5
2023 | Region XIII | SURIGAO DEL NORTE | MALIMONO (SURIGAO DEL NORTE) | P00721341MN | Construction of Flood Mitigation Structure | 125.4278 | 9.5422 | 154400000 | 154399963.3 | 2024 | ME 3 CONSTRUCTION / EQUI-PARCO CONSTRUCTION COMPANY | 9157 | 2023 | 2024-03-15 | 04/18/2023 | 36.7 | 0 | 2024-04-10 | 26
2022 | Region VIII | EASTERN SAMAR | ORAS (EASTERN SAMAR) | P00620324VS | Construction of Flood Mitigation Structure | 125.4329 | 12.1761 | 48984764.4 | 48999985.68 | 2023 | PABLO S. LABASBAS CONSTRUCTION CORPORATION (FORMERLY: PABLOS. LABASBAS CONSTRUCTION CORPORATION) | 9158 | 2022 | 2023-01-02 | 04/05/2022 | 0 | 15221.28 | 2023-01-01 |  | 1
2023 | Region VIII | EASTERN SAMAR | LLORENTE (EASTERN SAMAR) | P00732043VS | Construction of Flood Mitigation Structure | 125.4381 | 11.605 | 19799998.84 | 19799999.97 | 2023 | ST. ROCH CONSTRUCTION | 9159 | 2023 | 2023-07-18 | 02/16/2023 | 0 | 1.13 | 2023-08-08 | 21
2022 | Region VIII | EASTERN SAMAR | CITY OF BORONGAN (CAPITAL) (EASTERN SAMAR) | P00620183VS | Rehabilitation / Major Repair of Drainage Structure | 125.4389 | 11.6206 | 4949996.39 | 4896620.89 | 2022 | TUBIGAN BUILDERS | 9160 | 2022 | 2022-07-16 | 04/07/2022 | 53375.5 | 0 | 2022-07-15 |  | 1
2022 | Region VIII | EASTERN SAMAR | ORAS (EASTERN SAMAR) | P00620175VS | Construction of Flood Mitigation Structure | 125.4406 | 12.1862 | 19599999.37 | 19599967.51 | 2022 | J.A. DEVELOPERS AND ENGINEERS | 9161 | 2022 | 2022-07-04 | 02/13/2022 | 31.86 | 0 | 2022-07-03 |  | 1
2022 | Region VIII | EASTERN SAMAR | CITY OF BORONGAN (CAPITAL) (EASTERN SAMAR) | P00620181VS | Rehabilitation / Major Repair of Flood Control Structure | 125.4421 | 11.5983 | 48999999.89 | 48999992.98 | 2022 | 888 ACY ENTERPRISES | 9162 | 2022 | 2022-07-22 | 03/17/2022 | 6.91 | 0 | 2022-10-20 | 90
2023 | Region VIII | EASTERN SAMAR | DOLORES (EASTERN SAMAR) | P00733753VS | Construction of Flood Mitigation Structure | 125.4428 | 12.0319 | 14849992.73 | 14849999.91 | 2023 | PABLO S. LABASBAS CONSTRUCTION CORPORATION (FORMERLY: PABLOS. LABASBAS CONSTRUCTION CORPORATION) | 9163 | 2023 | 2023-11-13 | 04/18/2023 | 0 | 7.18 | 2023-11-27 | 14
2022 | Region XI | DAVAO DEL SUR | SANTA CRUZ (DAVAO DEL SUR) | P00630607MN | Construction of Revetment | 125.4518 | 6.8783 | 49000000 | 49000000 | 2022 | DREIRICH BUILDERS / THREE W BUILDERS, INC. | 9164 | 2022 | 2022-08-31 | 02/21/2022 | 0 | 0 | 2022-08-30 |  | 1
2023 | Region XI | DAVAO DEL SUR | DAVAO CITY (DAVAO DEL SUR) | P00721384MN | Construction of Cutoff Channel | 125.4518 | 7.2111 | 24500000 | 24301419.01 | 2023 | RITCHE-NATHALIE BUILDERS & GENERAL MERCHANDISE | 9165 | 2023 | 2023-09-09 | 03/09/2023 | 198580.99 | 0 | 2023-09-08 |  | 1
2022 | Region VIII | EASTERN SAMAR | CITY OF BORONGAN (CAPITAL) (EASTERN SAMAR) | P00620176VS | Construction of Flood Mitigation Structure | 125.4547 | 11.5858 | 49000000.71 | 48999993.8 | 2022 | 888 ACY ENTERPRISES | 9166 | 2022 | 2022-12-02 | 02/13/2022 | 6.91 | 0 | 2022-12-01 |  | 1
2024 | Region XI | DAVAO DEL SUR | DAVAO CITY (DAVAO DEL SUR) | P00820296MN | Construction of Revetment | 125.4599 | 7.1781 | 86850000 | 86513783.34 | 2024 | ALFREGO BUILDERS & SUPPLY | 9167 | 2024 | 2024-11-06 | 03/05/2024 | 336216.66 | 0 | 2024-12-12 | 36
2022 | Region VIII | EASTERN SAMAR | CITY OF BORONGAN (CAPITAL) (EASTERN SAMAR) | P00620326VS | Rehabilitation / Major Repair of Flood Control Structure | 125.4604 | 11.5411 | 19600000 | 19599983.4 | 2022 | J.A. DEVELOPERS AND ENGINEERS | 9168 | 2022 | 2022-08-04 | 03/31/2022 | 16.6 | 0 | 2022-08-03 |  | 1
2023 | Region XI | DAVAO DEL SUR | DAVAO CITY (DAVAO DEL SUR) | P00721496MN | Construction of Revetment | 125.4621 | 7.1763 | 49000000 | 47696875.08 | 2023 | ALFREGO BUILDERS & SUPPLY | 9169 | 2023 | 2023-08-21 | 03/09/2023 | 1303124.92 | 0 | 2023-09-18 | 28
2022 | Region XI | DAVAO OCCIDENTAL | MALITA (DAVAO OCCIDENTAL) | P00620058MN | Construction of Revetment | 125.4651 | 6.3675 | 96500000 | 96500000 | 2022 | ALPHA & OMEGA GEN. CONTRACTOR & DEVELOPMENT CORP. | 9170 | 2022 | 2022-10-02 | 02/24/2022 | 0 | 0 | 2022-10-01 |  | 1
2022 | Region XI | DAVAO OCCIDENTAL | MALITA (DAVAO OCCIDENTAL) | P00620059MN | Construction of Revetment | 125.4651 | 6.3674 | 96500000 | 96500000 | 2022 | ALPHA & OMEGA GEN. CONTRACTOR & DEVELOPMENT CORP. | 9171 | 2022 | 2022-10-02 | 02/24/2022 | 0 | 0 | 2022-10-01 |  | 1
2022 | Region XI | DAVAO OCCIDENTAL | MALITA (DAVAO OCCIDENTAL) | P00620060MN | Construction of Revetment | 125.4652 | 6.3676 | 96500000 | 96500000 | 2022 | ALPHA & OMEGA GEN. CONTRACTOR & DEVELOPMENT CORP. | 9172 | 2022 | 2022-10-02 | 02/24/2022 | 0 | 0 | 2022-10-01 |  | 1
2023 | Region XI | DAVAO OCCIDENTAL | SANTA MARIA (DAVAO OCCIDENTAL) | P00721282MN | Construction of Revetment | 125.4662 | 6.4948 | 77200000 | 77189371.31 | 2023 | GREAT PACIFIC BUILDERS AND GEN. CONTRACTOR INC. | 9173 | 2023 | 2023-10-04 | 03/16/2023 | 10628.69 | 0 | 2023-10-03 |  | 1
2022 | Region XI | DAVAO OCCIDENTAL | SANTA MARIA (DAVAO OCCIDENTAL) | P00620064MN | Construction of Revetment | 125.4673 | 6.4764 | 96500000 | 96500000 | 2022 | ALPHA & OMEGA GEN. CONTRACTOR & DEVELOPMENT CORP. | 9174 | 2022 | 2022-10-02 | 02/24/2022 | 0 | 0 | 2022-10-01 |  | 1
2024 | Region XI | DAVAO DEL SUR | DAVAO CITY (DAVAO DEL SUR) | P00820410MN | Construction of Revetment | 125.4707 | 7.1544 | 49000000 | 48866414.37 | 2024 | ALFREGO BUILDERS & SUPPLY | 9175 | 2024 | 2024-10-02 | 03/05/2024 | 133585.63 | 0 | 2024-10-01 |  | 1
2022 | Region XI | DAVAO DEL SUR | DAVAO CITY (DAVAO DEL SUR) | P00620065MN | Construction of Flood Mitigation Structure | 125.4707 | 7.178 | 50807250 | 50632025.64 | 2023 | O. G. SANTOS CONSTRUCTION | 9176 | 2022 | 2023-05-10 | 03/08/2022 | 175224.36 | 0 | 2022-10-23 |  | 199
2022 | Region XI | DAVAO DEL SUR | DAVAO CITY (DAVAO DEL SUR) | P00630503MN | Construction of Revetment | 125.4709 | 7.1666 | 96500000 | 93749272.96 | 2023 | ST. TIMOTHY CONSTRUCTION CORPORATION | 9177 | 2022 | 2023-02-03 | 03/08/2022 | 2750727.04 | 0 | 2023-01-02 |  | 32
2022 | Region XIII | SURIGAO DEL NORTE | MAINIT (SURIGAO DEL NORTE) | P00630649MN | Construction of Flood Mitigation Structure | 125.4744 | 9.485 | 49000000 | 48997260.67 | 2023 | GICAR CONSTRUCTION, INC. | 9178 | 2022 | 2023-01-13 | 02/11/2022 | 2739.33 | 0 | 2023-01-14 | 1
2022 | Region XIII | SURIGAO DEL NORTE | MAINIT (SURIGAO DEL NORTE) | P00630637MN | Construction of Flood Mitigation Structure | 125.4759 | 9.5539 | 49000000 | 48999839.78 | 2022 | GICAR CONSTRUCTION, INC. | 9179 | 2022 | 2022-10-26 | 02/11/2022 | 160.22 | 0 | 2022-10-27 | 1
2023 | Region XI | DAVAO OCCIDENTAL | SANTA MARIA (DAVAO OCCIDENTAL) | P00721578MN | Construction of Flood Mitigation Structure | 125.4786 | 6.5377 | 96500000 | 96489010.67 | 2024 | SCP CONSTRUCTION | 9180 | 2023 | 2024-03-15 | 05/29/2023 | 10989.33 | 0 | 2024-03-14 |  | 1
2024 | Region XIII | SURIGAO DEL NORTE | SURIGAO CITY (CAPITAL) (SURIGAO DEL NORTE) | P00820369MN | Construction of Flood Mitigation Structure | 125.4792 | 9.7784 | 96500000 | 96499986.9 | 2024 | MONOLITHIC CONSTRUCTION & CONCRETE PRODUCTS, INC. | 9181 | 2024 | 2024-11-28 | 02/26/2024 | 13.1 | 0 | 2024-11-30 | 2
2023 | Region XIII | AGUSAN DEL NORTE | BUTUAN CITY (CAPITAL) (AGUSAN DEL NORTE) | P00721330MN | Construction of Drainage Structure | 125.4794 | 8.9464 | 289500000 | 289499999.8 | 2024 | ME 3 CONSTRUCTION / EQUI-PARCO CONSTRUCTION COMPANY | 9182 | 2023 | 2024-10-18 | 07/28/2023 | 0.2 | 0 | 2025-02-13 | 118
2023 | Region XI | DAVAO DEL SUR | DAVAO CITY (DAVAO DEL SUR) | P00721497MN | Construction of Revetment | 125.4799 | 7.1342 | 49000000 | 47647054.64 | 2023 | ALFREGO BUILDERS & SUPPLY | 9183 | 2023 | 2023-10-06 | 03/09/2023 | 1352945.36 | 0 | 2023-10-05 |  | 1
2022 | Region XI | DAVAO DEL SUR | DAVAO CITY (DAVAO DEL SUR) | P00630516MN | Construction of Flood Mitigation Structure | 125.4799 | 7.1222 | 115800000 | 95525289.12 | 2023 | MAER SUMMIT KONSTRUKT CO. | 9184 | 2022 | 2023-05-15 | 04/08/2022 | 20274710.88 | 0 | 2023-05-29 | 14
2023 | Region XIII | SURIGAO DEL NORTE | SURIGAO CITY (CAPITAL) (SURIGAO DEL NORTE) | P00721588MN | Construction of Revetment | 125.4801 | 9.7689 | 96500000 | 96472570.51 | 2024 | GICAR CONSTRUCTION, INC. | 9185 | 2023 | 2024-04-14 | 04/18/2023 | 27429.49 | 0 | 2024-04-18 | 4
2024 | Region XIII | SURIGAO DEL NORTE | SURIGAO CITY (CAPITAL) (SURIGAO DEL NORTE) | P00820114MN | Construction of Flood Mitigation Structure | 125.4806 | 9.7831 | 96500000 | 96499949.84 | 2024 | MONOLITHIC CONSTRUCTION & CONCRETE PRODUCTS, INC. | 9186 | 2024 | 2024-12-09 | 02/26/2024 | 50.16 | 0 | 2025-02-28 | 81
2023 | Region XIII | SURIGAO DEL NORTE | SURIGAO CITY (CAPITAL) (SURIGAO DEL NORTE) | P00721587MN | Construction of Revetment | 125.4808 | 9.7678 | 96500000 | 96494216.75 | 2023 | GICAR CONSTRUCTION, INC. | 9187 | 2023 | 2023-12-19 | 04/18/2023 | 5783.25 | 0 | 2024-04-20 | 123
2024 | Region XIII | AGUSAN DEL NORTE | BUTUAN CITY (CAPITAL) (AGUSAN DEL NORTE) | P00820929MN | Construction of Flood Mitigation Structure | 125.4812 | 8.9978 | 98400007.99 | 98400007.99 | 2025 | ADFIL CORPORATION | 9188 | 2024 | 2025-02-20 | 05/14/2024 | 0 | 0 | 2025-03-08 | 16
2023 | Region XIII | SURIGAO DEL NORTE | SURIGAO CITY (CAPITAL) (SURIGAO DEL NORTE) | P00721652MN | Construction of Revetment | 125.4829 | 9.7414 | 193000000 | 192999869.6 | 2024 | SANTECH BUILDERS CORPORATION / GICAR CONSTRUCTION, INC. | 9189 | 2023 | 2024-07-08 | 05/18/2023 | 130.4 | 0 | 2024-07-09 | 1
2024 | Region XIII | SURIGAO DEL NORTE | SURIGAO CITY (CAPITAL) (SURIGAO DEL NORTE) | P00821205MN | Construction of Flood Mitigation Structure | 125.483 | 9.7417 | 110975000 | 110974983.1 | 2025 | GICAR CONSTRUCTION, INC. | 9190 | 2024 | 2025-02-27 | 07/12/2024 | 16.9 | 0 | 2025-03-07 | 8
2022 | Region XI | DAVAO DEL SUR | DAVAO CITY (DAVAO DEL SUR) | P00630512MN | Construction of Flood Mitigation Structure | 125.4848 | 7.0031 | 96500000 | 93355006.08 | 2023 | DREIRICH BUILDERS / THREE W BUILDERS, INC. | 9191 | 2022 | 2023-03-04 | 03/08/2022 | 3144993.92 | 0 | 2023-03-03 |  | 1
2023 | Region XI | DAVAO DEL SUR | DAVAO CITY (DAVAO DEL SUR) | P00721274MN | Construction of Revetment | 125.4863 | 7.0877 | 72375000 | 71928738.54 | 2023 | EDCL CONSTRUCTION AND SUPPLY | 9192 | 2023 | 2023-12-17 | 03/17/2023 | 446261.46 | 0 | 2023-12-16 |  | 1
2024 | Region XI | DAVAO DEL SUR | DAVAO CITY (DAVAO DEL SUR) | P00820916MN | Construction of Revetment | 125.4863 | 7.0877 | 68515000 | 68509429.13 | 2024 | EDCL CONSTRUCTION AND SUPPLY | 9193 | 2024 | 2024-11-09 | 03/05/2024 | 5570.87 | 0 | 2024-11-08 |  | 1
2022 | Region XI | DAVAO OCCIDENTAL | SANTA MARIA (DAVAO OCCIDENTAL) | P00620061MN | Construction of Revetment | 125.4865 | 6.535 | 96500000 | 96489997.96 | 2022 | ST. MATTHEW GEN. CONTRACTOR & DEVELOPMENT CORP. | 9194 | 2022 | 2022-10-29 | 03/23/2022 | 10002.04 | 0 | 2022-10-28 |  | 1
2022 | Region XI | DAVAO DEL SUR | DAVAO CITY (DAVAO DEL SUR) | P00620263MN | Construction of Revetment | 125.4868 | 7.0431 | 49000000 | 47532139.96 | 2022 | ALPHA & OMEGA GEN. CONTRACTOR & DEVELOPMENT CORP. | 9195 | 2022 | 2022-10-05 | 03/08/2022 | 1467860.04 | 0 | 2022-10-04 |  | 1
2024 | Region XIII | AGUSAN DEL NORTE | BUTUAN CITY (CAPITAL) (AGUSAN DEL NORTE) | P00835820MN | Construction of Flood Mitigation Structure | 125.4872 | 8.9319 | 193000000 | 192999989.2 | 2025 | TRIPARCO DEVELOPMENT CORPORATION | 9196 | 2024 | 2025-02-28 | 04/10/2024 | 10.8 | 0 | 2025-05-26 | 87
2023 | Region XIII | AGUSAN DEL NORTE | BUTUAN CITY (CAPITAL) (AGUSAN DEL NORTE) | P00721336MN | Construction of Flood Mitigation Structure | 125.4875 | 8.984 | 144750000 | 144749992.5 | 2024 | RAMISES CONSTRUCTION / EQUI-PARCO CONSTRUCTION COMPANY | 9197 | 2023 | 2024-01-31 | 04/18/2023 | 7.5 | 0 | 2024-04-27 | 87
2024 | Region XI | DAVAO DEL SUR | DAVAO CITY (DAVAO DEL SUR) | P00820292MN | Construction of Revetment | 125.4893 | 6.9875 | 67550000 | 67547960.92 | 2024 | RELY CONSTRUCTION & SUPPLY INC.(FORMERLY: RELY CONSTRUCTION AND SUPPLY) | 9198 | 2024 | 2024-11-07 | 03/05/2024 | 2039.08 | 0 | 2024-11-06 |  | 1
2024 | Region XI | DAVAO DEL SUR | DAVAO CITY (DAVAO DEL SUR) | P00820291MN | Construction of Revetment | 125.4895 | 7.0153 | 67779670 | 67779661.61 | 2024 | EDCL CONSTRUCTION AND SUPPLY | 9199 | 2024 | 2024-11-08 | 03/05/2024 | 8.39 | 0 | 2024-11-07 |  | 1
2022 | Region XI | DAVAO DEL SUR | DAVAO CITY (DAVAO DEL SUR) | P00630525MN | Construction of Revetment | 125.4903 | 7.1088 | 86850000 | 86576807.55 | 2022 | TKS BUILDERS & SUPPLIES / LEDCORE CONSTRUCTION AND DEVELOPMENT CORP, | 9200 | 2022 | 2022-12-26 | 03/08/2022 | 273192.45 | 0 | 2022-12-25 |  | 1
2024 | Region XIII | SURIGAO DEL NORTE | SISON (SURIGAO DEL NORTE) | P00835891MN | Construction of Flood Mitigation Structure | 125.4912 | 9.6505 | 29400000 | 29104565.61 | 2024 | C.V. CONSTRUCTION & DEVELOPMENT | 9201 | 2024 | 2024-12-07 | 04/30/2024 | 295434.39 | 0 | 2024-12-24 | 17
2022 | Region XI | DAVAO DEL SUR | DAVAO CITY (DAVAO DEL SUR) | P00630600MN | Construction of Drainage Structure | 125.4919 | 7.1055 | 19300000 | 19299981.53 | 2023 | AIMEK CONSTRUCTION AND SUPPLY | 9202 | 2022 | 2023-02-16 | 07/27/2022 | 18.47 | 0 | 2023-02-15 |  | 1
2023 | Region XI | DAVAO OCCIDENTAL | MALITA (DAVAO OCCIDENTAL) | P00733995MN | Construction of Revetment | 125.4929 | 6.4085 | 96500000 | 96488648.31 | 2024 | YPR GEN. CONTRACTOR AND CONSTRUCTION SUPPLY INC. | 9203 | 2023 | 2024-02-20 | 05/05/2023 | 11351.69 | 0 | 2024-02-19 |  | 1
2024 | Region XIII | AGUSAN DEL NORTE | BUTUAN CITY (CAPITAL) (AGUSAN DEL NORTE) | P00835857MN | Rehabilitation / Major Repair of Flood Control Structure | 125.4947 | 8.9483 | 193000000 | 192999520.5 | 2025 | TRIPARCO DEVELOPMENT CORPORATION | 9204 | 2024 | 2025-02-28 | 05/13/2024 | 479.5 | 0 | 2025-03-15 | 15
2022 | Region XI | DAVAO DEL SUR | DAVAO CITY (DAVAO DEL SUR) | P00630595MN | Construction of Drainage Structure | 125.4956 | 6.995 | 9800000 | 9505381.79 | 2023 | MITZ CONSTRUCTION AND SUPPLY | 9205 | 2022 | 2023-07-21 | 08/03/2022 | 294618.21 | 0 | 2023-01-07 |  | 195
2022 | Region XIII | SURIGAO DEL NORTE | SURIGAO CITY (CAPITAL) (SURIGAO DEL NORTE) | P00634125MN | Construction of Flood Mitigation Structure | 125.498 | 9.7253 | 49500000 | 48503241.04 | 2023 | ED1SON DEVELOPMENT & CONSTRUCTION INC. / TWENTYSIX CONSTRUCTION INC. | 9206 | 2022 | 2023-04-30 | 04/13/2022 | 996758.96 | 0 | 2022-10-24 |  | 188
2022 | Region XI | DAVAO DEL SUR | DAVAO CITY (DAVAO DEL SUR) | P00631096MN | Construction of Drainage Structure | 125.4988 | 7.1088 | 29700000 | 29595077.47 | 2023 | LOTRIM CONSTRUCTION, INC. | 9207 | 2022 | 2023-04-03 | 07/26/2022 | 104922.53 | 0 | 2023-04-02 |  | 1
2024 | Region XIII | AGUSAN DEL NORTE | BUTUAN CITY (CAPITAL) (AGUSAN DEL NORTE) | P00835856MN | Rehabilitation / Major Repair of Flood Control Structure | 125.4999 | 8.9431 | 193000000 | 192998943.6 | 2025 | TRIPARCO DEVELOPMENT CORPORATION | 9208 | 2024 | 2025-02-28 | 05/03/2024 | 1056.4 | 0 | 2025-03-05 | 5
2022 | Region XIII | SURIGAO DEL NORTE | SURIGAO CITY (CAPITAL) (SURIGAO DEL NORTE) | P00630545MN | Construction of Flood Mitigation Structure | 125.5004 | 9.7251 | 96500000 | 96500000 | 2023 | SANTECH BUILDERS CORPORATION / GICAR CONSTRUCTION, INC. | 9209 | 2022 | 2023-02-26 | 03/11/2022 | 0 | 0 | 2023-02-23 |  | 3
2022 | Region XI | DAVAO DEL SUR | DAVAO CITY (DAVAO DEL SUR) | P00633919MN | Construction of Drainage Structure | 125.5012 | 7.0427 | 9800000 | 9800000 | 2022 | AGONG BUILDERS AND CONSTRUCTION SUPPLY, INC. | 9210 | 2022 | 2022-11-18 | 06/06/2022 | 0 | 0 | 2022-11-17 |  | 1
2022 | Region XI | DAVAO DEL SUR | DAVAO CITY (DAVAO DEL SUR) | P00633929MN | Rehabilitation / Major Repair of Drainage Structure | 125.5018 | 7.0479 | 9800000 | 9652199.8 | 2022 | H-ROYAL CONSTRUCTION | 9211 | 2022 | 2022-11-06 | 04/13/2022 | 147800.2 | 0 | 2022-11-05 |  | 1
2022 | Region XIII | SURIGAO DEL NORTE | SURIGAO CITY (CAPITAL) (SURIGAO DEL NORTE) | P00630546MN | Construction of Flood Mitigation Structure | 125.5035 | 9.703 | 86850000 | 86849199.88 | 2023 | GICAR CONSTRUCTION, INC. | 9212 | 2022 | 2023-03-15 | 03/11/2022 | 800.12 | 0 | 2023-05-06 | 52
2023 | Region XIII | SURIGAO DEL NORTE | SURIGAO CITY (CAPITAL) (SURIGAO DEL NORTE) | P00721489MN | Construction of Flood Mitigation Structure | 125.5043 | 9.7183 | 96500000 | 96499997.47 | 2024 | GICAR CONSTRUCTION, INC. | 9213 | 2023 | 2024-03-04 | 02/27/2023 | 2.53 | 0 | 2024-01-31 |  | 33
2022 | Region XIII | AGUSAN DEL NORTE | BUTUAN CITY (CAPITAL) (AGUSAN DEL NORTE) | P00630551MN | Construction of Drainage Structure | 125.5053 | 8.944 | 67343386.32 | 67343386.21 | 2023 | ME 3 CONSTRUCTION | 9214 | 2022 | 2023-06-21 | 03/29/2022 | 0.11 | 0 | 2023-07-30 | 39
2024 | Region XI | DAVAO DEL SUR | DAVAO CITY (DAVAO DEL SUR) | P00820290MN | Construction of Revetment | 125.5076 | 7.2292 | 86850000 | 86845020.11 | 2024 | ARCINUE COMM'L CORPORATION | 9215 | 2024 | 2024-12-13 | 03/05/2024 | 4979.89 | 0 | 2024-12-12 |  | 1
2023 | Region XIII | AGUSAN DEL NORTE | MAGALLANES (AGUSAN DEL NORTE) | P00721590MN | Construction of Flood Mitigation Structure | 125.5118 | 9.0295 | 48250000 | 48249999.19 | 2023 | TRIPARCO DEVELOPMENT CORPORATION | 9216 | 2023 | 2023-11-03 | 04/18/2023 | 0.81 | 0 | 2023-11-02 |  | 1
2022 | Region VIII | EASTERN SAMAR | GIPORLOS (EASTERN SAMAR) | P00630675VS | Construction of Drainage Structure | 125.5121 | 11.0878 | 4949981.91 | 4949999.85 | 2022 | BORONGAN MBC MERCHANDISING AND CONSTRUCTION | 9217 | 2022 | 2022-07-21 | 04/07/2022 | 0 | 17.94 | 2022-07-20 |  | 1
2022 | Region XIII | AGUSAN DEL NORTE | BUTUAN CITY (CAPITAL) (AGUSAN DEL NORTE) | P00630550MN | Construction of Drainage Structure | 125.5126 | 8.9439 | 86589691.07 | 86589691.07 | 2022 | ADFIL CORPORATION | 9218 | 2022 | 2022-12-23 | 02/28/2022 | 0 | 0 | 2023-02-18 | 57
2023 | Region XI | DAVAO DEL SUR | DAVAO CITY (DAVAO DEL SUR) | P00721433MN | Construction of Revetment | 125.5132 | 7.2125 | 96500000 | 96498666.24 | 2024 | ABU CONSTRUCTION / ALFREGO BUILDERS & SUPPLY | 9219 | 2023 | 2024-01-04 | 03/09/2023 | 1333.76 | 0 | 2024-01-03 |  | 1
2022 | Region XIII | SURIGAO DEL NORTE | MAINIT (SURIGAO DEL NORTE) | P00620255MN | Construction of Flood Mitigation Structure | 125.5136 | 9.5359 | 54560135 | 54529499.96 | 2022 | JMT CONSTRUCTION | 9220 | 2022 | 2022-12-13 | 03/11/2022 | 30635.04 | 0 | 2022-12-24 | 11
2022 | Region XI | DAVAO DEL SUR | DAVAO CITY (DAVAO DEL SUR) | P00630502MN | Construction of Revetment | 125.5142 | 7.2125 | 96500000 | 96498186.61 | 2023 | ST. TIMOTHY CONSTRUCTION CORPORATION | 9221 | 2022 | 2023-01-03 | 03/08/2022 | 1813.39 | 0 | 2023-01-02 |  | 1
2021 | Region XI | DAVAO DEL SUR |  | P00550553MN | Construction of Drainage Structure | 125.5149 | 7.0578 | 9800000 | 9800000 | 2022 | GRECO CONSTRUCTION AND SUPPLY | 9222 | 2021 | 2022-07-29 | 11/18/2021 | 0 | 0 | 2022-07-28 |  | 1
2023 | Region XIII | AGUSAN DEL NORTE | BUTUAN CITY (CAPITAL) (AGUSAN DEL NORTE) | P00721331MN | Construction of Drainage Structure | 125.5152 | 8.9425 | 289500000 | 289499996.4 | 2024 | ME 3 CONSTRUCTION / EQUI-PARCO CONSTRUCTION COMPANY | 9223 | 2023 | 2024-10-18 | 07/28/2023 | 3.6 | 0 | 2024-11-28 | 41
2022 | Region VIII | EASTERN SAMAR | QUINAPONDAN (EASTERN SAMAR) | P00620059VS | Construction of Flood Mitigation Structure | 125.5158 | 11.1536 | 58800000 | 57900000 | 2023 | 888 ACY ENTERPRISES / JGO BUILDERS | 9224 | 2022 | 2023-02-09 | 04/07/2022 | 900000 | 0 | 2023-02-08 |  | 1
2022 | Region XIII | SURIGAO DEL NORTE | SISON (SURIGAO DEL NORTE) | P00630544MN | Construction of Flood Mitigation Structure | 125.5179 | 9.6806 | 86850000 | 86849971.99 | 2023 | JMT CONSTRUCTION | 9225 | 2022 | 2023-04-23 | 03/11/2022 | 28.01 | 0 | 2023-04-22 |  | 1
2022 | Region XIII | AGUSAN DEL NORTE | MAGALLANES (AGUSAN DEL NORTE) | P00620351MN | Construction of Flood Mitigation Structure | 125.5187 | 9.0165 | 49000000 | 48999998.08 | 2022 | TRIPARCO DEVELOPMENT CORPORATION | 9226 | 2022 | 2022-10-26 | 04/10/2022 | 1.92 | 0 | 2022-10-25 |  | 1
2023 | Region XI | DAVAO OCCIDENTAL | MALITA (DAVAO OCCIDENTAL) | P00721579MN | Construction of Flood Mitigation Structure | 125.5191 | 6.3459 | 96500000 | 96475000.01 | 2024 | LEGACY CONSTRUCTION CORPORATION (FORMERLY: LEGACY CONSTRUCTION) | 9227 | 2023 | 2024-02-20 | 05/05/2023 | 24999.99 | 0 | 2024-02-19 |  | 1
2021 | Region XI | DAVAO DEL SUR |  | P00550521MN | Construction of Flood Mitigation Structure | 125.5207 | 7.0488 | 57900000 | 56738426.26 | 2023 | A.Y.U. ENGINEERING & CONSTRUCTION | 9228 | 2021 | 2023-08-15 | 12/05/2021 | 1161573.74 | 0 | 2023-08-16 | 1
2022 | Region XI | DAVAO DEL SUR | DAVAO CITY (DAVAO DEL SUR) | P00633917MN | Construction of Drainage Structure | 125.5219 | 7.0717 | 29400000 | 29400000 | 2023 | PRIMECON BUILDERS, INC. | 9229 | 2022 | 2023-03-07 | 06/02/2022 | 0 | 0 | 2023-04-05 | 29
2022 | Region XI | DAVAO DEL SUR | DAVAO CITY (DAVAO DEL SUR) | P00633908MN | Construction of Drainage Structure | 125.5221 | 7.0766 | 29400000 | 29400000 | 2023 | C'ZARLES CONSTRUCTION & SUPPLY | 9230 | 2022 | 2023-04-05 | 04/13/2022 | 0 | 0 | 2023-04-04 |  | 1
2023 | Region XIII | SURIGAO DEL NORTE | SISON (SURIGAO DEL NORTE) | P00721490MN | Construction of Flood Mitigation Structure | 125.523 | 9.6798 | 115800000 | 115799955.5 | 2024 | GICAR CONSTRUCTION, INC. | 9231 | 2023 | 2024-03-21 | 04/20/2023 | 44.5 | 0 | 2024-03-20 |  | 1
2022 | Region XI | DAVAO DEL SUR | DAVAO CITY (DAVAO DEL SUR) | P00633924MN | Construction of Flood Mitigation Structure | 125.524 | 7.0567 | 13720000 | 13719527.94 | 2022 | A.T. DUMLAO CONSTRUCTION, INC. FORMERLYANDONI T. D | 9232 | 2022 | 2022-11-09 | 04/13/2022 | 472.06 | 0 | 2022-11-08 |  | 1
2021 | Region XIII | SURIGAO DEL NORTE |  | P00522332MN | Construction of Flood Mitigation Structure | 125.5248 | 9.6788 | 109045000 | 109044995.1 | 2022 | GICAR CONSTRUCTION, INC. | 9233 | 2021 | 2022-10-02 | 04/26/2021 | 4.9 | 0 | 2022-10-01 |  | 1
2023 | Region XIII | AGUSAN DEL NORTE | BUTUAN CITY (CAPITAL) (AGUSAN DEL NORTE) | P00721327MN | Rehabilitation / Major Repair of Flood Control Structure | 125.5251 | 8.9275 | 144750000 | 144749999.7 | 2024 | EQUI-PARCO CONSTRUCTION COMPANY | 9234 | 2023 | 2024-09-16 | 10/06/2023 | 0.3 | 0 | 2024-09-15 |  | 1
2023 | Region XIII | AGUSAN DEL NORTE | BUTUAN CITY (CAPITAL) (AGUSAN DEL NORTE) | P00721653MN | Construction of Flood Mitigation Structure | 125.5252 | 8.9766 | 53075000 | 53074985.79 | 2023 | ADFIL CORPORATION | 9235 | 2023 | 2023-08-14 | 05/18/2023 | 14.21 | 0 | 2023-11-09 | 87
2022 | Region XIII | SURIGAO DEL NORTE | SISON (SURIGAO DEL NORTE) | P00630647MN | Construction of Flood Mitigation Structure | 125.5257 | 9.6619 | 49000000 | 48467977.5 | 2022 | GICAR CONSTRUCTION, INC. | 9236 | 2022 | 2022-11-30 | 02/11/2022 | 532022.5 | 0 | 2022-12-24 | 24
2022 | Region XI | DAVAO DEL SUR | DAVAO CITY (DAVAO DEL SUR) | P00633896MN | Construction of Flood Mitigation Structure | 125.5257 | 7.0748 | 96500000 | 96500000 | 2023 | GENESIS88 CONSTRUCTION INC. / GEMMA CONSTRUCTION SUPPLY, INC.(FORMERLY:GEMMA CON | 9237 | 2022 | 2023-08-20 | 04/13/2022 | 0 | 0 | 2023-10-11 | 52
2023 | Region XII | COTABATO (NORTH COTABATO) | MAGPET (COTABATO (NORTH COTABATO)) | P00721505MN | Construction of Flood Mitigation Structure | 125.0839 | 7.1296 | 49000000 | 49000000 | 2023 | LLABAN CONSTRUCTION & SUPPLY (FORMERLY: LLABAN CON | 9238 | 2023 | 2023-11-20 | 03/24/2023 | 0 | 0 | 2024-01-26 | 67
2023 | Region XIII | SURIGAO DEL NORTE | SOCORRO (SURIGAO DEL NORTE) | P00734420MN | Construction of Flood Mitigation Structure | 125.9212 | 9.6518 | 49500000 | 49399902.5 | 2024 | ROAD EDGE TRADING & DEVELOPMENT SERVICES | 9239 | 2023 | 2024-04-14 | 07/13/2023 | 100097.5 | 0 | 2024-04-13 |  | 1
2022 | Region XI | DAVAO DE ORO | MARAGUSAN (SAN MARIANO) (DAVAO DE ORO) | P00620264MN | Construction of Revetment | 126.1386 | 7.3811 | 48999979.44 | 48999342.16 | 2022 | LICSAL CONSTRUCTION CORPORATION | 9240 | 2022 | 2022-12-08 | 04/04/2022 | 637.28 | 0 | 2022-12-07 |  | 1
2021 | Region XII | COTABATO (NORTH COTABATO) |  | P00522365MN | Construction of Flood Mitigation Structure | 125.0889 | 6.9454 | 48999212.65 | 49000000 | 2023 | LLABAN CONSTRUCTION & SUPPLY (FORMERLY: LLABAN CON | 9241 | 2021 | 2023-02-02 | 03/07/2022 | 0 | 787.35 | 2023-02-01 |  | 1
2022 | Region XIII | AGUSAN DEL SUR | PROSPERIDAD (CAPITAL) (AGUSAN DEL SUR) | P00620296MN | Construction of Flood Mitigation Structure | 125.9264 | 8.6389 | 45080000 | 45079964.27 | 2023 | EQUI-PARCO CONSTRUCTION COMPANY | 9242 | 2022 | 2023-03-23 | 05/24/2022 | 35.73 | 0 | 2023-05-02 | 40
2023 | Region XIII | DINAGAT ISLANDS | SAN JOSE (CAPITAL) (DINAGAT ISLANDS) | P00734037MN | Construction of Flood Mitigation Structure | 125.5752 | 10.0031 | 29400000 | 29388645.37 | 2024 | NAHARO BUILDERS, INC. | 9243 | 2023 | 2024-11-08 | 05/02/2023 | 11354.63 | 0 | 2024-08-16 |  | 84
2022 | Region XI | DAVAO DEL SUR | DAVAO CITY (DAVAO DEL SUR) | P00634967MN | Construction of Drainage Structure | 125.6447 | 7.2315 | 9800000 | 9800000 | 2022 | LPS CONSTRUCTION GROUP, INC. | 9244 | 2022 | 2022-11-13 | 04/13/2022 | 0 | 0 | 2022-11-12 |  | 1
2023 | Region X | BUKIDNON | CITY OF MALAYBALAY (CAPITAL) (BUKIDNON) | P00733989MN | Construction of Flood Mitigation Structure | 125.1885 | 8.0836 | 96500000 | 96500000 | 2024 | ROSBILL CONSTRUCTION AND SUPPLY | 9245 | 2023 | 2024-03-25 | 08/31/2023 | 0 | 0 | 2024-06-09 | 76
2024 | Region XIII | AGUSAN DEL SUR | ESPERANZA (AGUSAN DEL SUR) | P00820364MN | Construction of Flood Mitigation Structure | 125.6447 | 8.6734 | 77200000 | 77199943.13 | 2024 | J.M. LACORTE CONSTRUCTION | 9246 | 2024 | 2024-12-18 | 04/17/2024 | 56.87 | 0 | 2025-04-10 | 113
2022 | Region VIII | SAMAR (WESTERN SAMAR) | BASEY (SAMAR (WESTERN SAMAR)) | P00620217VS | Construction of Flood Mitigation Structure | 125.0921 | 11.2944 | 39200000 | 38024021.38 | 2023 | B. VICENCIO BUILDERS (BVB), INC. (FORMERLY:B. VICENCIO CONSTRUCTION) | 9247 | 2022 | 2023-01-14 | 02/13/2022 | 1175978.62 | 0 | 2023-01-13 |  | 1
2022 | Region XI | DAVAO DEL SUR | DAVAO CITY (DAVAO DEL SUR) | P00631100MN | Construction of Drainage Structure | 125.5753 | 7.1605 | 5445000 | 5445000 | 2022 | LLM UNIFIED BUILDERS & TRADING CORP. (FORMERLY:LLM CONCRETE PRODUCTS) | 9248 | 2022 | 2022-07-04 | 03/31/2022 | 0 | 0 | 2022-07-03 |  | 1
2022 | Region XI | DAVAO DE ORO | NABUNTURAN (CAPITAL) (DAVAO DE ORO) | P00634136MN | Construction of Revetment | 125.9297 | 7.5622 | 6859998.76 | 6859984.22 | 2022 | AGONG BUILDERS AND CONSTRUCTION SUPPLY, INC. | 9249 | 2022 | 2022-07-20 | 03/29/2022 | 14.54 | 0 | 2022-07-19 |  | 1
2023 | Region XI | DAVAO DEL SUR | DAVAO CITY (DAVAO DEL SUR) | P00721292MN | Construction of Revetment | 125.6456 | 7.2578 | 96500000 | 96500000 | 2023 | GENESIS88 CONSTRUCTION INC. | 9250 | 2023 | 2023-10-27 | 02/20/2023 | 0 | 0 | 2023-10-26 |  | 1
2023 | Region XI | DAVAO DE ORO | NEW BATAAN (DAVAO DE ORO) | P00721617MN | Construction of Revetment | 126.1408 | 7.5717 | 49000000 | 41642463.58 | 2023 | ROSBILL CONSTRUCTION AND SUPPLY | 9251 | 2023 | 2023-12-02 | 05/26/2023 | 7357536.42 | 0 | 2023-12-01 |  | 1
2022 | Region XIII | DINAGAT ISLANDS | LORETO (DINAGAT ISLANDS) | P00630559MN | Construction of Flood Mitigation Structure | 125.576 | 10.361 | 96500000 | 95534810.12 | 2023 | JMT CONSTRUCTION | 9252 | 2022 | 2023-11-16 | 03/17/2022 | 965189.88 | 0 | 2023-09-15 |  | 62
2023 | Region X | BUKIDNON | CITY OF VALENCIA (BUKIDNON) | P00721412MN | Construction of Flood Mitigation Structure | 125.1938 | 7.9657 | 188000000 | 183887563.2 | 2024 | M. MONTESCLAROS ENTERPRISES, INC. | 9253 | 2023 | 2024-04-28 | 03/29/2023 | 4112436.8 | 0 | 2024-01-21 |  | 98
2024 | Region XI | DAVAO DE ORO | NABUNTURAN (CAPITAL) (DAVAO DE ORO) | P00835879MN | Construction of Revetment | 125.9312 | 7.5618 | 49000000 | 48999885.55 | 2025 | TAGUM BUILDERS CONTRACTORS CORP. (FORMERLY: TAGUM | 9254 | 2024 | 2025-02-28 | 09/25/2024 | 114.45 | 0 | 2025-04-12 | 43
2021 | Region X | BUKIDNON |  | P00522341MN | Construction of Flood Mitigation Structure | 125.0939 | 7.8988 | 48250000 | 45835692.71 | 2023 | M. MONTESCLAROS ENTERPRISES, INC. | 9255 | 2021 | 2023-08-27 | 03/25/2022 | 2414307.29 | 0 | 2022-11-09 |  | 291
2022 | Region XIII | SURIGAO DEL NORTE | ALEGRIA (SURIGAO DEL NORTE) | P00634152MN | Construction of Flood Mitigation Structure | 125.5781 | 9.4838 | 9900000 | 9899347.33 | 2022 | GICAR CONSTRUCTION, INC. | 9256 | 2022 | 2022-12-09 | 04/01/2022 | 652.67 | 0 | 2022-12-09 | 0
2023 | Region XI | DAVAO DE ORO | MARAGUSAN (SAN MARIANO) (DAVAO DE ORO) | P00721618MN | Construction of Revetment | 126.1418 | 7.3367 | 49000000 | 48997610.2 | 2024 | AB APONESTO CONSTRUCTION PARTS AND SUPPLY, INC. | 9257 | 2023 | 2024-04-22 | 05/26/2023 | 2389.8 | 0 | 2024-04-21 |  | 1
2021 | Region XI | DAVAO DEL SUR |  | P00522191MN | Construction of Flood Mitigation Structure | 125.6472 | 7.2572 | 24500000 | 24500000 | 2023 | RELY CONSTRUCTION & SUPPLY INC.(FORMERLY: RELY CONSTRUCTION AND SUPPLY) | 9258 | 2021 | 2023-03-24 | 04/13/2022 | 0 | 0 | 2023-03-23 |  | 1
2022 | Region XI | DAVAO DE ORO | NABUNTURAN (CAPITAL) (DAVAO DE ORO) | P00620169MN | Construction of Revetment | 125.935 | 7.5744 | 48999970.51 | 48999953.58 | 2022 | TAGUM BUILDERS CONTRACTORS CORP. (FORMERLY: TAGUM | 9259 | 2022 | 2022-11-08 | 02/15/2022 | 16.93 | 0 | 2022-11-07 |  | 1
2022 | Region X | BUKIDNON | KITAOTAO (BUKIDNON) | P00630498MN | Construction of Revetment | 125.1973 | 7.5898 | 67550000 | 67550000 | 2023 | PYRAMID CONSOLIDATED BUILDERS & GEN. MDSE. | 9260 | 2022 | 2023-06-07 | 02/24/2022 | 0 | 0 | 2023-06-06 |  | 1
2022 | Region XIII | SURIGAO DEL NORTE | ALEGRIA (SURIGAO DEL NORTE) | P00642637MN | Rehabilitation / Major Repair of Flood Control Structure | 125.5783 | 9.4851 | 120625000 | 120619605.8 | 2023 | GONZALODO ENTERPRISES / RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R | 9261 | 2022 | 2023-05-09 | 09/12/2022 | 5394.2 | 0 | 2023-05-08 |  | 1
2023 | Region XI | DAVAO DEL NORTE | SANTO TOMAS (DAVAO DEL NORTE) | P00734401MN | Construction of Flood Mitigation Structure | 125.6492 | 7.4626 | 19800000 | 19268153.77 | 2024 | FORDEX CONSTRUCTION CORPORATION | 9262 | 2023 | 2024-05-17 | 11/17/2023 | 531846.23 | 0 | 2024-05-16 |  | 1
2023 | Region XIII | SURIGAO DEL NORTE | GENERAL LUNA (SURIGAO DEL NORTE) | P00734011MN | Construction of Flood Mitigation Structure | 126.1427 | 9.8249 | 77200000 | 77189906.96 | 2024 | DUROS DEVELOPMENT CORP. | 9263 | 2023 | 2024-11-02 | 05/03/2023 | 10093.04 | 0 | 2024-11-01 |  | 1
2021 | Region XII | SOUTH COTABATO |  | P00550515MN | Construction of Drainage Structure | 125.1973 | 6.1286 | 39200000 | 39193358.97 | 2023 | VICENTE T. LAO CONSTRUCTION | 9264 | 2021 | 2023-12-19 | 03/22/2022 | 6641.03 | 0 | 2023-10-27 |  | 53
2022 | Region XIII | AGUSAN DEL SUR | PROSPERIDAD (CAPITAL) (AGUSAN DEL SUR) | P00620192MN | Construction of Dike | 125.9454 | 8.5562 | 11760000 | 11759986.07 | 2022 | ABADA CONSTRUCTION AND SUPPLY | 9265 | 2022 | 2022-11-17 | 03/18/2022 | 13.93 | 0 | 2022-11-16 |  | 1
2023 | Region XIII | AGUSAN DEL NORTE | BUTUAN CITY (CAPITAL) (AGUSAN DEL NORTE) | P00721333MN | Construction of Flood Mitigation Structure | 125.5785 | 8.9489 | 144750000 | 144749994.7 | 2024 | ME 3 CONSTRUCTION | 9266 | 2023 | 2024-04-09 | 04/24/2023 | 5.3 | 0 | 2024-04-08 |  | 1
2022 | Region XI | DAVAO DEL SUR | DAVAO CITY (DAVAO DEL SUR) | P00620079MN | Construction of Revetment | 125.6524 | 7.1515 | 67550000 | 67550000 | 2023 | GENESIS88 CONSTRUCTION INC. | 9267 | 2022 | 2023-02-26 | 04/07/2022 | 0 | 0 | 2023-02-25 |  | 1
2022 | Region X | MISAMIS ORIENTAL | GINGOOG CITY (MISAMIS ORIENTAL) | P00620028MN | Construction of Flood Mitigation Structure | 125.0941 | 8.8237 | 96500000 | 94563372.94 | 2024 | TRIPARCO DEVELOPMENT CORPORATION | 9268 | 2022 | 2024-02-08 | 08/08/2022 | 1936627.06 | 0 | 2023-06-02 |  | 251
2022 | Region VIII | SOUTHERN LEYTE | HINUNANGAN (SOUTHERN LEYTE) | P00620226VS | Construction of Flood Mitigation Structure | 125.201 | 10.3827 | 49000000 | 49000000 | 2022 | ST. TIMOTHY CONSTRUCTION CORPORATION | 9269 | 2022 | 2022-11-15 | 02/16/2022 | 0 | 0 | 2022-12-11 | 26
2023 | Region XIII | AGUSAN DEL SUR | PROSPERIDAD (CAPITAL) (AGUSAN DEL SUR) | P00721484MN | Construction of Flood Mitigation Structure | 125.9484 | 8.6377 | 96500000 | 96498838.04 | 2024 | J.M. LACORTE CONSTRUCTION | 9270 | 2023 | 2024-09-03 | 03/31/2023 | 1161.96 | 0 | 2024-09-02 |  | 1
2022 | Region XI | DAVAO ORIENTAL | GOVERNOR GENEROSO (DAVAO ORIENTAL) | P00620180MN | Construction of Flood Mitigation Structure | 126.1441 | 6.4614 | 19600000 | 19600000 | 2022 | LEGACY CONSTRUCTION CORPORATION (FORMERLY: LEGACY CONSTRUCTION) | 9271 | 2022 | 2022-09-30 | 02/21/2022 | 0 | 0 | 2022-09-29 |  | 1
2023 | Region X | BUKIDNON | CITY OF VALENCIA (BUKIDNON) | P00721420MN | Construction of Flood Mitigation Structure | 125.0949 | 7.9036 | 49000000 | 48250000 | 2024 | M. MONTESCLAROS ENTERPRISES, INC. | 9272 | 2023 | 2024-01-01 | 01/31/2023 | 750000 | 0 | 2023-12-31 |  | 1
2022 | Region XIII | SURIGAO DEL NORTE | BACUAG (SURIGAO DEL NORTE) | P00630634MN | Construction of Flood Mitigation Structure | 125.6539 | 9.5904 | 49000000 | 48510346.88 | 2022 | ROIM BUILDERS & CONSTRUCTION SUPPLY | 9273 | 2022 | 2022-10-13 | 04/01/2022 | 489653.12 | 0 | 2022-10-12 |  | 1
2022 | Region XIII | SURIGAO DEL NORTE | TUBOD (SURIGAO DEL NORTE) | P00630552MN | Construction of Flood Mitigation Structure | 125.5795 | 9.5496 | 82025000 | 82014385.81 | 2023 | PYRAMID CONSOLIDATED BUILDERS & GEN. MDSE. / C'ZARLES CONSTRUCTION & SUPPLY | 9274 | 2022 | 2023-12-31 | 03/11/2022 | 10614.19 | 0 | 2023-04-23 |  | 252
2024 | Region X | MISAMIS ORIENTAL | MAGSAYSAY (LINUGOS) (MISAMIS ORIENTAL) | P00820015MN | Construction of Flood Mitigation Structure | 125.2041 | 9.0039 | 86853860 | 86852678.85 | 2024 | RITCHE-NATHALIE DEVELOPMENT CORPORATION (FORMERLY: RITCHE-NATHALIE BUILDERS AND GEN. MERCHANDISE) | 9275 | 2024 | 2024-12-20 | 03/14/2024 | 1181.15 | 0 | 2025-01-06 | 17
2022 | Region XI | DAVAO OCCIDENTAL | MALITA (DAVAO OCCIDENTAL) | P00630608MN | Construction of Slope Protection Structure | 125.5803 | 6.4817 | 14700000 | 14695699.85 | 2022 | FORTSTONE CONSTRUCTION ENTERPRISES | 9276 | 2022 | 2022-07-04 | 02/24/2022 | 4300.15 | 0 | 2022-07-03 |  | 1
2023 | Region X | BUKIDNON | CITY OF VALENCIA (BUKIDNON) | P00721414MN | Construction of Flood Mitigation Structure | 125.0951 | 7.8951 | 183000000 | 178780664 | 2025 | M. MONTESCLAROS ENTERPRISES, INC. | 9277 | 2023 | 2025-01-26 | 02/13/2023 | 4219336 | 0 | 2023-12-08 |  | 415
2022 | Region XIII | AGUSAN DEL SUR | ESPERANZA (AGUSAN DEL SUR) | P00620106MN | Construction of Revetment | 125.6545 | 8.6596 | 96500000 | 96499842.72 | 2023 | ADFIL CORPORATION | 9278 | 2022 | 2023-05-22 | 03/29/2022 | 157.28 | 0 | 2023-05-21 |  | 1
2022 | Region XI | DAVAO DE ORO | MARAGUSAN (SAN MARIANO) (DAVAO DE ORO) | P00620265MN | Construction of Revetment | 126.1446 | 7.3683 | 48999973.13 | 48995984.83 | 2022 | LICSAL CONSTRUCTION CORPORATION | 9279 | 2022 | 2022-12-08 | 04/04/2022 | 3988.3 | 0 | 2022-12-07 |  | 1
2022 | Region XII | SARANGANI | GLAN (SARANGANI) | P00634140MN | Construction of Drainage Structure | 125.2103 | 5.8189 | 4950000 | 4942646.4 | 2023 | GRECO CONSTRUCTION AND SUPPLY | 9280 | 2022 | 2023-06-28 | 07/28/2022 | 7353.6 | 0 | 2023-02-01 |  | 147
2022 | Region XIII | AGUSAN DEL SUR | PROSPERIDAD (CAPITAL) (AGUSAN DEL SUR) | P00620293MN | Construction of Flood Mitigation Structure | 125.9487 | 8.6374 | 45080000 | 45079878.7 | 2023 | J.M. LACORTE CONSTRUCTION | 9281 | 2022 | 2023-08-24 | 05/24/2022 | 121.3 | 0 | 2023-09-19 | 26
2023 | Region XIII | DINAGAT ISLANDS | TUBAJON (DINAGAT ISLANDS) | P00721395MN | Construction of Flood Mitigation Structure | 125.5808 | 10.2872 | 1960000 | 1958638.87 | 2023 | BAMBOE CONSTRUCTION | 9282 | 2023 | 2023-05-15 | 03/08/2023 | 1361.13 | 0 | 2023-06-04 | 20
2023 | Region XIII | SURIGAO DEL SUR | TAGO (SURIGAO DEL SUR) | P00746138MN | Rehabilitation / Major Repair of Slope Protection Structure | 126.1529 | 8.9839 | 15440000 | 15439540.08 | 2024 | ROWIE'S CONSTRUCTION | 9283 | 2023 | 2024-07-21 | 01/10/2024 | 459.92 | 0 | 2024-07-20 |  | 1
2021 | Region X | BUKIDNON |  | P00522061MN | Construction of Flood Mitigation Structure | 125.0967 | 7.9194 | 120625000 | 114591423.9 | 2022 | M. MONTESCLAROS ENTERPRISES, INC. | 9284 | 2021 | 2022-12-23 | 08/16/2021 | 6033576.1 | 0 | 2022-06-10 |  | 196
2022 | Region XIII | SURIGAO DEL NORTE | TAGANA-AN (SURIGAO DEL NORTE) | P00630635MN | Construction of Flood Mitigation Structure | 125.581 | 9.698 | 49000000 | 48506718.4 | 2022 | C.V. CONSTRUCTION & DEVELOPMENT | 9285 | 2022 | 2022-12-31 | 03/14/2022 | 493281.6 | 0 | 2022-11-23 |  | 38
2022 | Region XIII | SURIGAO DEL NORTE | TAGANA-AN (SURIGAO DEL NORTE) | P00631118MN | Construction of Flood Mitigation Structure | 125.6549 | 9.713 | 6930000 | 6855886.45 | 2023 | ROMZ BUILDERS | 9286 | 2022 | 2023-01-09 | 04/01/2022 | 74113.55 | 0 | 2022-08-19 |  | 143
2024 | Region X | BUKIDNON | CITY OF MALAYBALAY (CAPITAL) (BUKIDNON) | P00835862MN | Construction of Flood Mitigation Structure | 125.213 | 7.9999 | 49000000 | 49000000 | 2024 | VEN RAY CONSTRUCTION CORPORATION | 9287 | 2024 | 2024-12-13 | 02/27/2024 | 0 | 0 | 2024-12-12 |  | 1
2023 | Region XIII | SURIGAO DEL SUR | CARRASCAL (SURIGAO DEL SUR) | P00732101MN | Construction of Flood Mitigation Structure | 125.9516 | 9.372 | 106150000 | 106149995.5 | 2024 | J.M. LUCIANO CONSTRUCTION, INC. / VJP CONSTRUCTION & SUPPLY | 9288 | 2023 | 2024-01-03 | 05/29/2023 | 4.5 | 0 | 2024-01-02 |  | 1
2022 | Region XI | DAVAO DEL SUR | MATANAO (DAVAO DEL SUR) | P00630522MN | Construction of Revetment | 125.2144 | 6.7037 | 67550000 | 67550000 | 2022 | TKS BUILDERS & SUPPLIES | 9289 | 2022 | 2022-11-14 | 03/01/2022 | 0 | 0 | 2022-11-13 |  | 1
2022 | Region XIII | SURIGAO DEL NORTE | ALEGRIA (SURIGAO DEL NORTE) | P00630645MN | Construction of Flood Mitigation Structure | 125.581 | 9.477 | 39200000 | 39180150.39 | 2022 | JMT CONSTRUCTION | 9290 | 2022 | 2022-09-24 | 02/11/2022 | 19849.61 | 0 | 2022-09-24 | 0
2023 | Region X | BUKIDNON | CITY OF VALENCIA (BUKIDNON) | P00721245MN | Construction of Flood Mitigation Structure | 125.0977 | 7.8929 | 120275000 | 117572812.2 | 2024 | M. MONTESCLAROS ENTERPRISES, INC. | 9291 | 2023 | 2024-06-26 | 02/13/2023 | 2702187.8 | 0 | 2023-12-08 |  | 201
2024 | Region XIII | AGUSAN DEL SUR | VERUELA (AGUSAN DEL SUR) | P00820360MN | Construction of Flood Mitigation Structure | 125.9557 | 8.0683 | 77200000 | 77199999.77 | 2024 | ROCK DIWATA BUILDERS, INC. | 9292 | 2024 | 2024-10-21 | 02/16/2024 | 0.23 | 0 | 2024-11-20 | 30
2021 | Region XI | DAVAO DEL SUR |  | P00522192MN | Construction of Flood Mitigation Structure | 125.6555 | 7.1157 | 24500000 | 24500000 | 2023 | RELY CONSTRUCTION & SUPPLY INC.(FORMERLY: RELY CONSTRUCTION AND SUPPLY) | 9293 | 2021 | 2023-03-16 | 04/13/2022 | 0 | 0 | 2023-03-15 |  | 1
2024 | Region XII | SOUTH COTABATO | GENERAL SANTOS CITY (DADIANGAS) (SOUTH COTABATO) | P00833598MN | Construction of Drainage Structure | 125.2182 | 6.1232 | 4950000 | 4948990.26 | 2024 | MIGO CONSTRUCTION | 9294 | 2024 | 2024-05-07 | 02/23/2024 | 1009.74 | 0 | 2024-05-06 |  | 1
2023 | Region XIII | SURIGAO DEL SUR | TAGO (SURIGAO DEL SUR) | P00721662MN | Construction of Dike | 126.1536 | 8.9584 | 49000000 | 48999797.35 | 2023 | J.M. LUCIANO CONSTRUCTION, INC. | 9295 | 2023 | 2023-12-06 | 04/05/2023 | 202.65 | 0 | 2023-12-15 | 9
2021 | Region X | BUKIDNON |  | P00522070MN | Construction of Flood Mitigation Structure | 125.098 | 7.8882 | 64800715 | 61533022.77 | 2022 | M. MONTESCLAROS ENTERPRISES, INC. | 9296 | 2021 | 2022-07-25 | 07/23/2021 | 3267692.23 | 0 | 2022-03-21 |  | 126
2024 | Region XIII | AGUSAN DEL SUR | VERUELA (AGUSAN DEL SUR) | P00821211MN | Construction of Flood Mitigation Structure | 125.9603 | 8.0844 | 96500000 | 96499972.45 | 2024 | ROCK DIWATA BUILDERS, INC. | 9297 | 2024 | 2024-11-18 | 04/08/2024 | 27.55 | 0 | 2024-12-02 | 14
2021 | Region XIII | SURIGAO DEL NORTE |  | P00550455MN | Construction of Drainage Structure | 126.1556 | 9.7859 | 53075000 | 51483191.93 | 2022 | BOOMETRIX DEVELOPMENT CORP. | 9298 | 2021 | 2022-07-06 | 10/27/2021 | 1591808.07 | 0 | 2022-07-05 |  | 1
2021 | Region XI | DAVAO DEL SUR |  | P00550526MN | Construction of Flood Mitigation Structure | 125.6556 | 7.1518 | 96500000 | 96500000 | 2022 | GENESIS88 CONSTRUCTION INC. / GEMMA CONSTRUCTION SUPPLY, INC.(FORMERLY:GEMMA CON | 9299 | 2021 | 2022-09-09 | 12/01/2021 | 0 | 0 | 2022-09-08 |  | 1
2022 | Region XI | DAVAO DEL SUR | MATANAO (DAVAO DEL SUR) | P00630521MN | Construction of Revetment | 125.2202 | 6.7225 | 67550000 | 67550000 | 2022 | TKS BUILDERS & SUPPLIES | 9300 | 2022 | 2022-11-17 | 02/18/2022 | 0 | 0 | 2022-11-16 |  | 1
2024 | Region X | BUKIDNON | CITY OF VALENCIA (BUKIDNON) | P00820023MN | Construction of Flood Mitigation Structure | 125.0981 | 7.8923 | 43425000 | 42472153.73 | 2024 | M. MONTESCLAROS ENTERPRISES, INC. | 9301 | 2024 | 2024-12-28 | 03/04/2024 | 952846.27 | 0 | 2024-12-27 |  | 1
2024 | Region XIII | AGUSAN DEL NORTE | BUTUAN CITY (CAPITAL) (AGUSAN DEL NORTE) | P00820120MN | Construction of Flood Mitigation Structure | 125.5815 | 8.9483 | 96497405.45 | 96497405.32 | 2024 | TRIPARCO DEVELOPMENT CORPORATION | 9302 | 2024 | 2024-12-20 | 04/12/2024 | 0.13 | 0 | 2025-05-05 | 136
2023 | Region XIII | AGUSAN DEL SUR | VERUELA (AGUSAN DEL SUR) | P00721485MN | Construction of Flood Mitigation Structure | 125.9606 | 8.0797 | 106150000 | 106149968.4 | 2023 | ROCK DIWATA BUILDERS, INC. / FFJJ CONSTRUCTION | 9303 | 2023 | 2023-11-28 | 04/18/2023 | 31.6 | 0 | 2023-12-12 | 14
2024 | Region XIII | AGUSAN DEL SUR | TRENTO (AGUSAN DEL SUR) | P00820388MN | Construction of Flood Mitigation Structure | 126.1557 | 8.0173 | 67550000 | 67550000 | 2024 | JQG BUILDERS | 9304 | 2024 | 2024-11-01 | 02/16/2024 | 0 | 0 | 2024-10-31 |  | 1
2023 | Region XIII | AGUSAN DEL SUR | ROSARIO (AGUSAN DEL SUR) | P00721479MN | Construction of Flood Mitigation Structure | 125.9606 | 8.0797 | 106150000 | 106149732.5 | 2024 | CM TAN CONSTRUCTION | 9305 | 2023 | 2024-02-09 | 04/20/2023 | 267.5 | 0 | 2024-02-08 |  | 1
2021 | Region VIII | SOUTHERN LEYTE |  | P00549878VS | Construction of Slope Protection Structure | 125.2228 | 10.0952 | 96500000 | 96500000 | 2022 | MORTAR MASTERS & CONCRETE BUILDERS / JM COLLERA KONSTRACT | 9306 | 2021 | 2022-10-07 | 11/22/2021 | 0 | 0 | 2022-10-06 |  | 1
2022 | Region XI | DAVAO DEL SUR | DAVAO CITY (DAVAO DEL SUR) | P00630597MN | Construction of Drainage Structure | 125.5818 | 7.1294 | 9800000 | 9800000 | 2022 | CJEP BUILDERS AND ENGINEERING SERVICES | 9307 | 2022 | 2022-08-17 | 03/31/2022 | 0 | 0 | 2022-08-20 | 3
2022 | Region X | BUKIDNON | CITY OF VALENCIA (BUKIDNON) | P00634129MN | Construction of Flood Mitigation Structure | 125.0982 | 7.9186 | 143550000 | 140591612 | 2023 | M. MONTESCLAROS ENTERPRISES, INC. | 9308 | 2022 | 2023-11-27 | 07/15/2022 | 2958388 | 0 | 2023-05-09 |  | 202
2024 | Region XIII | AGUSAN DEL SUR | TRENTO (AGUSAN DEL SUR) | P00820389MN | Construction of Flood Mitigation Structure | 126.1557 | 8.0188 | 77200000 | 77200000 | 2024 | BBC CONSTRUCTION / ADFIL CORPORATION | 9309 | 2024 | 2024-11-21 | 02/16/2024 | 0 | 0 | 2024-11-20 |  | 1
2021 | Region XI | DAVAO DEL SUR |  | P00550554MN | Construction of Flood Mitigation Structure | 125.6573 | 7.1142 | 49000000 | 49000000 | 2022 | MONOLITHIC CONSTRUCTION & CONCRETE PRODUCTS, INC. | 9310 | 2021 | 2022-07-10 | 11/21/2021 | 0 | 0 | 2022-07-09 |  | 1
2024 | Region XIII | AGUSAN DEL SUR | VERUELA (AGUSAN DEL SUR) | P00820359MN | Construction of Flood Mitigation Structure | 125.9619 | 8.0815 | 173700000 | 173699867.9 | 2024 | ROCK DIWATA BUILDERS, INC. | 9311 | 2024 | 2024-11-18 | 02/22/2024 | 132.1 | 0 | 2024-12-16 | 28
2021 | Region XI | DAVAO DEL SUR |  | P00550539MN | Rehabilitation / Major Repair of Drainage Structure | 125.6573 | 7.1143 | 57900000 | 57900000 | 2023 | VICENTE T. LAO CONSTRUCTION | 9312 | 2021 | 2023-11-24 | 09/26/2022 | 0 | 0 | 2023-11-23 |  | 1
2023 | Region XIII | AGUSAN DEL SUR | TRENTO (AGUSAN DEL SUR) | P00721519MN | Rehabilitation / Major Repair of Flood Control Structure | 126.1565 | 8.019 | 49000000 | 49000000 | 2023 | ADFIL CORPORATION | 9313 | 2023 | 2023-11-09 | 04/03/2023 | 0 | 0 | 2023-11-08 |  | 1
2023 | Region XIII | AGUSAN DEL SUR | SAN FRANCISCO (AGUSAN DEL SUR) | P00734417MN | Construction of Flood Mitigation Structure | 125.9704 | 8.5106 | 49000000 | 48999999.42 | 2024 | YES CONSTRUCTION / ARN BUILDERS, INC. (FOR: ARN BUILDERS) | 9314 | 2023 | 2024-03-27 | 06/20/2023 | 0.58 | 0 | 2024-03-30 | 3
2023 | Region X | MISAMIS ORIENTAL | GINGOOG CITY (MISAMIS ORIENTAL) | P00721561MN | Construction of Flood Mitigation Structure | 125.0983 | 8.8272 | 65957750 | 65957750 | 2024 | VEN RAY CONSTRUCTION CORPORATION | 9315 | 2023 | 2024-02-28 | 05/22/2023 | 0 | 0 | 2024-03-04 | 5
2023 | Region XIII | SURIGAO DEL NORTE | TAGANA-AN (SURIGAO DEL NORTE) | P00734003MN | Construction of Flood Mitigation Structure | 125.5818 | 9.6926 | 96500000 | 96499662.25 | 2023 | C.V. CONSTRUCTION & DEVELOPMENT | 9316 | 2023 | 2023-11-20 | 05/09/2023 | 337.75 | 0 | 2024-02-11 | 83
2022 | Region VIII | SOUTHERN LEYTE | PINTUYAN (SOUTHERN LEYTE) | P00620407VS | Construction of Slope Protection Structure | 125.224 | 9.968 | 96500000 | 96500000 | 2023 | COLLERA CONSTRUCTION | 9317 | 2022 | 2023-04-20 | 04/06/2022 | 0 | 0 | 2023-04-19 |  | 1
2023 | Region XI | DAVAO ORIENTAL | LUPON (DAVAO ORIENTAL) | P00732070MN | Construction of Flood Mitigation Structure | 126.1589 | 7.1578 | 86850000 | 85053656.01 | 2024 | ROSBILL CONSTRUCTION AND SUPPLY | 9318 | 2023 | 2024-02-06 | 03/30/2023 | 1796343.99 | 0 | 2024-02-05 |  | 1
2024 | Region XIII | AGUSAN DEL NORTE | BUTUAN CITY (CAPITAL) (AGUSAN DEL NORTE) | P00833295MN | Rehabilitation / Major Repair of Flood Control Structure | 125.658 | 9.0119 | 193000000 | 192999994.4 | 2025 | EQUI-PARCO CONSTRUCTION COMPANY | 9319 | 2024 | 2025-02-16 | 03/06/2024 | 5.6 | 0 | 2025-02-22 | 6
2022 | Region XI | DAVAO DE ORO | MACO (DAVAO DE ORO) | P00620268MN | Construction of Revetment | 125.9706 | 7.3738 | 48999963.76 | 48999917.26 | 2023 | ALPHA & OMEGA GEN. CONTRACTOR & DEVELOPMENT CORP. | 9320 | 2022 | 2023-01-29 | 04/06/2022 | 46.5 | 0 | 2023-01-28 |  | 1
2023 | Region XIII | AGUSAN DEL NORTE | BUTUAN CITY (CAPITAL) (AGUSAN DEL NORTE) | P00721488MN | Rehabilitation / Major Repair of Flood Control Structure | 125.6584 | 9.0127 | 113870000 | 113869975 | 2024 | EQUI-PARCO CONSTRUCTION COMPANY | 9321 | 2023 | 2024-03-12 | 04/17/2023 | 25 | 0 | 2024-03-25 | 13
2023 | Region XIII | AGUSAN DEL NORTE | LAS NIEVES (AGUSAN DEL NORTE) | P00721342MN | Construction of Flood Mitigation Structure | 125.5818 | 8.7287 | 96500000 | 95431916.75 | 2024 | DATREBIL CONSTRUCTION & SUPPLY | 9322 | 2023 | 2024-08-31 | 03/06/2023 | 1068083.25 | 0 | 2024-09-04 | 4
2023 | Region XII | SARANGANI | GLAN (SARANGANI) | P00721304MN | Construction of Flood Mitigation Structure | 125.2278 | 5.8242 | 96500000 | 96499427.78 | 2024 | AAA ROCK CONSTRUCTION CORPORATION (FORMERLY: DAVAO ROCK MIXER ENTERPRISES) / CHARIFER BUILDERS, INC. | 9323 | 2023 | 2024-01-23 | 04/05/2023 | 572.22 | 0 | 2024-02-11 | 19
2024 | Region X | BUKIDNON | CITY OF VALENCIA (BUKIDNON) | P00820026MN | Construction of Flood Mitigation Structure | 125.0984 | 7.8913 | 67550000 | 66097734.85 | 2025 | M. MONTESCLAROS ENTERPRISES, INC. | 9324 | 2024 | 2025-02-06 | 04/18/2024 | 1452265.15 | 0 | 2025-02-10 | 4
2023 | Region XIII | SURIGAO DEL SUR | TAGO (SURIGAO DEL SUR) | P00744978MN | Rehabilitation / Major Repair of Flood Control Structure | 126.1592 | 8.9927 | 92059070 | 92057573.39 | 2024 | GICAR CONSTRUCTION, INC. | 9325 | 2023 | 2024-03-04 | 06/13/2023 | 1496.61 | 0 | 2024-03-11 | 7
2022 | Region X | MISAMIS ORIENTAL | GINGOOG CITY (MISAMIS ORIENTAL) | P00620161MN | Construction of Revetment | 125.0984 | 8.8182 | 48250000 | 43424990.3 | 2024 | ROAD EDGE TRADING & DEVELOPMENT SERVICES | 9326 | 2022 | 2024-03-09 | 06/29/2022 | 4825009.7 | 0 | 2023-01-23 |  | 411
2023 | Region XIII | AGUSAN DEL NORTE | LAS NIEVES (AGUSAN DEL NORTE) | P00721346MN | Construction of Flood Mitigation Structure | 125.5819 | 8.7428 | 96500000 | 96499990.36 | 2024 | TRIPARCO DEVELOPMENT CORPORATION | 9327 | 2023 | 2024-02-15 | 02/16/2023 | 9.64 | 0 | 2024-02-14 |  | 1
2024 | Region XIII | AGUSAN DEL SUR | SAN FRANCISCO (AGUSAN DEL SUR) | P00836162MN | Construction of Flood Mitigation Structure | 125.9709 | 8.5114 | 49500000 | 49499999.46 | 2025 | YES CONSTRUCTION / ARN BUILDERS, INC. (FOR: ARN BUILDERS) | 9328 | 2024 | 2025-01-17 | 06/11/2024 | 0.54 | 0 | 2025-01-16 |  | 1
2022 | Region XII | SARANGANI | GLAN (SARANGANI) | P00634141MN | Construction of Flood Mitigation Structure | 125.2304 | 5.8897 | 4950000 | 4947996.36 | 2022 | JAYSABB CONSTRUCTION AND SUPPLY | 9329 | 2022 | 2022-11-08 | 06/14/2022 | 2003.64 | 0 | 2022-11-07 |  | 1
2022 | Region XIII | SURIGAO DEL SUR | CITY OF TANDAG (CAPITAL) (SURIGAO DEL SUR) | P00630653MN | Construction of Dike | 126.1647 | 9.1356 | 4900000 | 4436701.22 | 2022 | SURIGAO LA SUERTE CORPORATION | 9330 | 2022 | 2022-12-31 | 08/08/2022 | 463298.78 | 0 | 2023-01-01 | 1
2022 | Region XI | DAVAO OCCIDENTAL | JOSE ABAD SANTOS (TRINIDAD) (DAVAO OCCIDENTAL) | P00620057MN | Construction of Revetment | 125.6593 | 5.9617 | 96500000 | 96500000 | 2022 | ST. TIMOTHY CONSTRUCTION CORPORATION | 9331 | 2022 | 2022-10-02 | 02/24/2022 | 0 | 0 | 2022-10-01 |  | 1
2024 | Region X | BUKIDNON | LANTAPAN (BUKIDNON) | P00820141MN | Construction of Flood Mitigation Structure | 125.0985 | 8.0052 | 9800000 | 9800000 | 2024 | AL-NAJIM CONSTRUCTION CORPORATION | 9332 | 2024 | 2024-07-23 | 01/26/2024 | 0 | 0 | 2024-07-22 |  | 1
2023 | Region XIII | AGUSAN DEL SUR | SAN FRANCISCO (AGUSAN DEL SUR) | P00734418MN | Construction of Flood Mitigation Structure | 125.9714 | 8.5114 | 49000000 | 48999991.43 | 2024 | YES CONSTRUCTION / ARN BUILDERS, INC. (FOR: ARN BUILDERS) | 9333 | 2023 | 2024-03-18 | 05/16/2023 | 8.57 | 0 | 2024-03-17 |  | 1
2023 | Region XIII | AGUSAN DEL NORTE | BUTUAN CITY (CAPITAL) (AGUSAN DEL NORTE) | P00721487MN | Rehabilitation / Major Repair of Flood Control Structure | 125.6598 | 9.0117 | 113870000 | 113869997.2 | 2024 | EQUI-PARCO CONSTRUCTION COMPANY | 9334 | 2023 | 2024-03-12 | 04/17/2023 | 2.8 | 0 | 2024-03-25 | 13
2023 | Region XIII | SURIGAO DEL SUR | TAGO (SURIGAO DEL SUR) | P00734005MN | Construction of Flood Mitigation Structure | 126.1661 | 9.0025 | 96500000 | 96499979.92 | 2024 | ME 3 CONSTRUCTION / EVENPAR CONSTRUCTION AND DEVELOPMENT CORPORATION (FORMERLY: EVEN PAR CONST. CO. INC.) | 9335 | 2023 | 2024-05-03 | 04/17/2023 | 20.08 | 0 | 2024-05-03 | 0
2023 | Region X | BUKIDNON | CITY OF MALAYBALAY (CAPITAL) (BUKIDNON) | P00733990MN | Construction of Flood Mitigation Structure | 125.2338 | 7.9717 | 96500000 | 96500000 | 2024 | ROSBILL CONSTRUCTION AND SUPPLY | 9336 | 2023 | 2024-11-13 | 04/11/2023 | 0 | 0 | 2024-11-12 |  | 1
2022 | Region X | BUKIDNON | CITY OF VALENCIA (BUKIDNON) | P00620215MN | Construction of Flood Mitigation Structure | 125.0998 | 7.8914 | 144750000 | 137151056.3 | 2023 | M. MONTESCLAROS ENTERPRISES, INC. | 9337 | 2022 | 2023-12-31 | 05/23/2022 | 7598943.7 | 0 | 2023-03-17 |  | 289
2023 | Region XIII | AGUSAN DEL NORTE | LAS NIEVES (AGUSAN DEL NORTE) | P00721343MN | Construction of Revetment | 125.5819 | 8.7282 | 96500000 | 96499985.03 | 2024 | DATREBIL CONSTRUCTION & SUPPLY | 9338 | 2023 | 2024-02-18 | 03/06/2023 | 14.97 | 0 | 2024-02-17 |  | 1
2022 | Region XI | DAVAO DE ORO | MACO (DAVAO DE ORO) | P00620228MN | Construction of Revetment | 125.9744 | 7.395 | 77199984.81 | 77199984.81 | 2023 | GIZA BUILDERS CORPORATION (FORMERLY: LITO HEAVY EQUIPMENT AND TRUCKING SERVICES) / ABU CONSTRUCTION | 9339 | 2022 | 2023-01-02 | 04/04/2022 | 0 | 0 | 2023-01-01 |  | 1
2022 | Region XIII | AGUSAN DEL NORTE | BUTUAN CITY (CAPITAL) (AGUSAN DEL NORTE) | P00644473MN | Rehabilitation / Major Repair of Flood Control Structure | 125.6622 | 9.0117 | 154400000 | 154399877.5 | 2023 | EQUI-PARCO CONSTRUCTION COMPANY / TRIPARCO DEVELOPMENT CORPORATION | 9340 | 2022 | 2023-07-31 | 12/09/2022 | 122.5 | 0 | 2023-08-04 | 4
2022 | Region XII | SOUTH COTABATO | GENERAL SANTOS CITY (DADIANGAS) (SOUTH COTABATO) | P00631108MN | Construction of Drainage Structure | 125.2344 | 6.2072 | 4950000 | 4914570.5 | 2022 | VANVI CONSTRUCTION | 9341 | 2022 | 2022-08-09 | 02/24/2022 | 35429.5 | 0 | 2022-05-23 |  | 78
2024 | Region XII | COTABATO (NORTH COTABATO) | MAGPET (COTABATO (NORTH COTABATO)) | P00820344MN | Construction of Dike | 125.102 | 7.1226 | 96500000 | 96017492.67 | 2025 | MAER SUMMIT KONSTRUKT CO. | 9342 | 2024 | 2025-05-27 | 07/03/2024 | 482507.33 | 0 | 2025-06-08 | 12
2024 | Region XI | DAVAO DEL NORTE | PANABO CITY (DAVAO DEL NORTE) | P00833287MN | Construction of Revetment | 125.6671 | 7.2759 | 47767500 | 48249996.91 | 2024 | AARJG BUILDERS CORPORATION / RUPLINO SEISMUNDO CONSTRUCTION CORPORATION (FORMERLY: R.R. SEISMUNDO CONSTRUCTION & SUPPLY) | 9343 | 2024 | 2024-12-15 | 05/22/2024 | 0 | 482496.91 | 2025-01-17 | 33
2022 | Region XII | SOUTH COTABATO | GENERAL SANTOS CITY (DADIANGAS) (SOUTH COTABATO) | P00630530MN | Construction of Revetment | 125.235 | 6.2078 | 91675000 | 91629683.47 | 2023 | J.G. ORANZA CONSTRUCTION | 9344 | 2022 | 2023-01-20 | 02/24/2022 | 45316.53 | 0 | 2022-12-22 |  | 29
2022 | Region XIII | SURIGAO DEL NORTE | ALEGRIA (SURIGAO DEL NORTE) | P00630640MN | Construction of Flood Mitigation Structure | 125.5824 | 9.5021 | 49000000 | 48997779.87 | 2023 | GICAR CONSTRUCTION, INC. | 9345 | 2022 | 2023-03-09 | 02/11/2022 | 2220.13 | 0 | 2023-03-09 | 0
2021 | Region XIII | AGUSAN DEL SUR |  | P00522271MN | Rehabilitation / Major Repair of Flood Control Structure | 125.9764 | 8.5088 | 49000000 | 49000000 | 2022 | A.T. DUMLAO CONSTRUCTION, INC. FORMERLYANDONI T. D / LCTING CONSTRUCTION AND DEVELOPMENT CORPORATION (FORMERLY: L.C. TING CONSTRUCTION) | 9346 | 2021 | 2022-07-14 | 06/11/2021 | 0 | 0 | 2022-07-13 |  | 1
2022 | Region XI | DAVAO DE ORO | NABUNTURAN (CAPITAL) (DAVAO DE ORO) | P00620080MN | Construction of Revetment | 125.9764 | 7.6082 | 57899903 | 57898840.84 | 2022 | GP & H CONSTRUCTION INCORPORATED (FORMERLY: GP & H CONSTRUCTION & SUPPLY) | 9347 | 2022 | 2022-12-22 | 04/06/2022 | 1062.16 | 0 | 2022-12-21 |  | 1
2022 | Region XIII | SURIGAO DEL SUR | TAGO (SURIGAO DEL SUR) | P00620253MN | Construction of Flood Mitigation Structure | 126.1678 | 9.0031 | 86850000 | 86849919.38 | 2023 | CM TAN CONSTRUCTION | 9348 | 2022 | 2023-05-30 | 07/18/2022 | 80.62 | 0 | 2023-05-29 |  | 1
2022 | Region XI | DAVAO DE ORO | MACO (DAVAO DE ORO) | P00620230MN | Construction of Revetment | 125.9786 | 7.3877 | 77199830.31 | 77199830.31 | 2023 | GP & H CONSTRUCTION INCORPORATED (FORMERLY: GP & H CONSTRUCTION & SUPPLY) | 9349 | 2022 | 2023-01-02 | 04/04/2022 | 0 | 0 | 2023-01-01 |  | 1
2022 | Region XIII | SURIGAO DEL SUR | CORTES (SURIGAO DEL SUR) | P00630656MN | Construction of Flood Mitigation Structure | 126.1733 | 9.1444 | 9800000 | 9779099.12 | 2022 | JMT CONSTRUCTION | 9350 | 2022 | 2022-11-08 | 08/08/2022 | 20900.88 | 0 | 2022-11-07 |  | 1
2022 | Region XII | SARANGANI | GLAN (SARANGANI) | P00634142MN | Construction of Flood Mitigation Structure | 125.2363 | 5.8419 | 4950000 | 4844775.59 | 2023 | VERGUZ CONSTRUCTION | 9351 | 2022 | 2023-08-07 | 06/23/2022 | 105224.41 | 0 | 2022-12-16 |  | 234
2023 | Region XIII | AGUSAN DEL SUR | SAN FRANCISCO (AGUSAN DEL SUR) | P00734419MN | Construction of Drainage Structure | 125.9803 | 8.5067 | 4950000 | 4950000 | 2024 | DAVE CONSTRUCTION | 9352 | 2023 | 2024-03-01 | 10/02/2023 | 0 | 0 | 2024-02-29 |  | 1
2022 | Region XIII | SURIGAO DEL SUR | CORTES (SURIGAO DEL SUR) | P00630658MN | Construction of Flood Mitigation Structure | 126.1733 | 9.2411 | 4900000 | 4540872.44 | 2022 | SURIGAO LA SUERTE CORPORATION | 9353 | 2022 | 2022-11-05 | 06/27/2022 | 359127.56 | 0 | 2022-11-04 |  | 1
2023 | Region XIII | AGUSAN DEL NORTE | LAS NIEVES (AGUSAN DEL NORTE) | P00734001MN | Construction of Flood Mitigation Structure | 125.6698 | 8.7436 | 4819547.16 | 4811448.34 | 2023 | OLIN DEVELOPMENT ENGINEERING & CONSTRUCTION | 9354 | 2023 | 2023-10-18 | 06/21/2023 | 8098.82 | 0 | 2023-10-17 |  | 1
2024 | Region XIII | AGUSAN DEL NORTE | BUTUAN CITY (CAPITAL) (AGUSAN DEL NORTE) | P00820376MN | Construction of Flood Mitigation Structure | 125.5825 | 8.7596 | 137272364.1 | 137272357.6 | 2025 | ME 3 CONSTRUCTION | 9355 | 2024 | 2025-05-30 | 05/08/2024 | 6.5 | 0 | 2025-06-24 | 25
2022 | Region VIII | NORTHERN SAMAR | GAMAY (NORTHERN SAMAR) | P00630236VS | Construction of Flood Mitigation Structure | 125.2364 | 12.3656 | 48999939.29 | 48917835.03 | 2022 | JUPA CONSTRUCTION / JCL CONSTRUCTION AND SUPPLY | 9356 | 2022 | 2022-10-15 | 02/14/2022 | 82104.26 | 0 | 2022-11-09 | 25
2023 | Region X | BUKIDNON | CITY OF VALENCIA (BUKIDNON) | P00721366MN | Construction of Flood Mitigation Structure | 125.1031 | 7.9439 | 49000000 | 49000000 | 2023 | M. MONTESCLAROS ENTERPRISES, INC. | 9357 | 2023 | 2023-11-11 | 01/31/2023 | 0 | 0 | 2023-11-10 |  | 1
2023 | Region XI | DAVAO DE ORO | MACO (DAVAO DE ORO) | P00734027MN | Construction of Drainage Structure | 125.9927 | 7.3941 | 14700000 | 14700000 | 2023 | GIZA BUILDERS CORPORATION (FORMERLY: LITO HEAVY EQUIPMENT AND TRUCKING SERVICES) | 9358 | 2023 | 2023-11-30 | 03/17/2023 | 0 | 0 | 2023-09-22 |  | 69
2022 | Region XI | DAVAO DEL NORTE | KAPALONG (DAVAO DEL NORTE) | P00620234MN | Construction of Flood Mitigation Structure | 125.6716 | 7.6399 | 96500000 | 96417657.68 | 2023 | TAGUM BUILDERS CONTRACTORS CORP. (FORMERLY: TAGUM / THREE W BUILDERS, INC. | 9359 | 2022 | 2023-02-02 | 04/08/2022 | 82342.32 | 0 | 2023-02-01 |  | 1
2021 | Region XII | SOUTH COTABATO |  | P00522371MN | Construction of Revetment | 125.2374 | 6.205 | 49000000 | 45389626.18 | 2023 | J.G. ORANZA CONSTRUCTION | 9360 | 2021 | 2023-03-21 | 03/11/2022 | 3610373.82 | 0 | 2023-03-20 |  | 1
2022 | Region X | BUKIDNON | IMPASUG-ONG (BUKIDNON) | P00630571MN | Construction of Flood Mitigation Structure | 125.106 | 8.2886 | 24500000 | 24500000 | 2022 | MAMAWAG CONSTRUCTION | 9361 | 2022 | 2022-11-28 | 01/28/2022 | 0 | 0 | 2022-11-27 |  | 1
2023 | Region XII | SOUTH COTABATO | GENERAL SANTOS CITY (DADIANGAS) (SOUTH COTABATO) | P00721460MN | Construction of Flood Mitigation Structure | 125.1075 | 6.0844 | 51145000 | 51143542.75 | 2023 | MJ TIONGSON CONSTRUCTION (FORMERLY: MJT BUILDERS) / REYDAN BUILDERS | 9362 | 2023 | 2023-09-23 | 02/21/2023 | 1457.25 | 0 | 2023-09-22 |  | 1
2022 | Region XIII | SURIGAO DEL NORTE | ALEGRIA (SURIGAO DEL NORTE) | P00630644MN | Construction of Flood Mitigation Structure | 125.5827 | 9.4746 | 49000000 | 48492094.22 | 2022 | C.V. CONSTRUCTION & DEVELOPMENT | 9363 | 2022 | 2022-08-07 | 02/11/2022 | 507905.78 | 0 | 2022-08-24 | 17
2022 | Region XI | DAVAO DE ORO | MONTEVISTA (DAVAO DE ORO) | P00620229MN | Construction of Revetment | 125.9971 | 7.7296 | 86849957.05 | 86849797.88 | 2022 | DBR CONSTRUCTION CORPORATION (FORMERLY: D.B. RAVELO CONSTRUCTION & SUPPLY) / RELY CONSTRUCTION & SUPPLY INC.(FORMERLY: RELY CONSTRUCTION AND SUPPLY) | 9364 | 2022 | 2022-12-15 | 04/04/2022 | 159.17 | 0 | 2023-01-01 | 17
2022 | Region XI | DAVAO DEL NORTE | CARMEN (DAVAO DEL NORTE) | P00630606MN | Construction of Dike | 125.6719 | 7.4012 | 49000000 | 49000000 | 2022 | O. G. SANTOS CONSTRUCTION | 9365 | 2022 | 2022-11-11 | 02/17/2022 | 0 | 0 | 2022-11-10 |  | 1
2022 | Region VIII | NORTHERN SAMAR | GAMAY (NORTHERN SAMAR) | P00630237VS | Construction of Flood Mitigation Structure | 125.2375 | 12.3643 | 48999944.75 | 48509900 | 2023 | CDU CONSTRUCTION | 9366 | 2022 | 2023-05-05 | 02/14/2022 | 490044.75 | 0 | 2023-01-08 |  | 117
2023 | Region XII | SOUTH COTABATO | GENERAL SANTOS CITY (DADIANGAS) (SOUTH COTABATO) | P00721463MN | Construction of Flood Mitigation Structure | 125.2409 | 6.1136 | 51145000 | 51144987.94 | 2024 | VICENTE T. LAO CONSTRUCTION | 9367 | 2023 | 2024-03-13 | 04/11/2023 | 12.06 | 0 | 2024-03-12 |  | 1
2024 | Region XII | SARANGANI | ALABEL (CAPITAL) (SARANGANI) | P00835802MN | Construction of Flood Mitigation Structure | 125.2428 | 6.1146 | 96500000 | 96445530.38 | 2024 | J.G. ORANZA CONSTRUCTION | 9368 | 2024 | 2024-10-21 | 04/05/2024 | 54469.62 | 0 | 2025-01-28 | 99
2022 | Region XII | SARANGANI | MALUNGON (SARANGANI) | P00620090MN | Construction of Flood Mitigation Structure | 125.2462 | 6.3087 | 96500000 | 96464665.61 | 2023 | HI-TONE CONSTRUCTION & DEVELOPMENT CORP. (FORMERLY | 9369 | 2022 | 2023-05-05 | 02/24/2022 | 35334.39 | 0 | 2023-05-04 |  | 1
2022 | Region XI | DAVAO DEL SUR | DAVAO CITY (DAVAO DEL SUR) | P00633926MN | Rehabilitation / Major Repair of Drainage Structure | 125.5832 | 7.0853 | 29400000 | 28517829.2 | 2022 | GRECO CONSTRUCTION AND SUPPLY | 9370 | 2022 | 2022-10-29 | 04/13/2022 | 882170.8 | 0 | 2022-10-28 |  | 1
2022 | Region XI | DAVAO DEL NORTE | CARMEN (DAVAO DEL NORTE) | P00630604MN | Construction of Dike | 125.6721 | 7.4009 | 49000000 | 49000000 | 2023 | AKN CONSTRUCTION CORPORATION | 9371 | 2022 | 2023-05-03 | 02/17/2022 | 0 | 0 | 2023-05-02 |  | 1
2023 | Region XI | DAVAO DE ORO | MONTEVISTA (DAVAO DE ORO) | P00721439MN | Construction of Revetment | 125.9972 | 7.7319 | 57900000 | 57896600 | 2023 | AB APONESTO CONSTRUCTION PARTS AND SUPPLY, INC. | 9372 | 2023 | 2023-09-10 | 02/16/2023 | 3400 | 0 | 2023-10-10 | 30
2022 | Region XIII | SURIGAO DEL SUR | CORTES (SURIGAO DEL SUR) | P00630652MN | Construction of Flood Mitigation Structure | 126.1733 | 9.2411 | 6011320 | 6011284.2 | 2023 | SURIGAO LA SUERTE CORPORATION | 9373 | 2022 | 2023-02-08 | 08/15/2022 | 35.8 | 0 | 2023-02-07 |  | 1
2022 | Region XI | DAVAO DEL SUR | DAVAO CITY (DAVAO DEL SUR) | P00620166MN | Construction of Flood Mitigation Structure | 125.6721 | 7.2533 | 49000000 | 49000000 | 2022 | GENESIS88 CONSTRUCTION INC. | 9374 | 2022 | 2022-09-04 | 02/16/2022 | 0 | 0 | 2022-09-03 |  | 1
2023 | Region XIII | SURIGAO DEL SUR | MADRID (SURIGAO DEL SUR) | P00721350MN | Construction of Flood Mitigation Structure | 125.9983 | 9.2573 | 109045000 | 109044905.4 | 2024 | HAPPY ALL3 BUILDERS CORPORATION / TRIPARCO DEVELOPMENT CORPORATION | 9375 | 2023 | 2024-07-10 | 04/24/2023 | 94.6 | 0 | 2024-07-31 | 21
2024 | Region XIII | SURIGAO DEL SUR | CORTES (SURIGAO DEL SUR) | P00835814MN | Construction of Dike | 126.178 | 9.1633 | 48250000 | 48249389.19 | 2025 | ST. TIMOTHY CONSTRUCTION CORPORATION | 9376 | 2024 | 2025-02-06 | 06/28/2024 | 610.81 | 0 | 2025-02-05 |  | 1
2023 | Region XII | SARANGANI | ALABEL (CAPITAL) (SARANGANI) | P00734406MN | Construction of Flood Mitigation Structure | 125.2478 | 6.1144 | 49500000 | 49499127.67 | 2024 | BETTER WORK CONSTRUCTION / 3 K'S INDUSTRIAL MAINTENANCE AND SERVICES, INC. | 9377 | 2023 | 2024-05-02 | 04/03/2023 | 872.33 | 0 | 2024-04-01 |  | 31
2022 | Region X | BUKIDNON | QUEZON (BUKIDNON) | P00620119MN | Construction of Revetment | 125.1104 | 7.6097 | 23520000 | 23519362.67 | 2022 | ER SALAC BUILDERS CORPORATION | 9378 | 2022 | 2022-11-13 | 02/17/2022 | 637.33 | 0 | 2022-11-12 |  | 1
2022 | Region XIII | SURIGAO DEL SUR | CORTES (SURIGAO DEL SUR) | P00630657MN | Construction of Flood Mitigation Structure | 126.1788 | 9.1629 | 19600000 | 15288477.5 | 2023 | SURIGAO LA SUERTE CORPORATION | 9379 | 2022 | 2023-03-03 | 08/03/2022 | 4311522.5 | 0 | 2023-04-01 | 29
2023 | Region XII | SOUTH COTABATO | GENERAL SANTOS CITY (DADIANGAS) (SOUTH COTABATO) | P00721465MN | Construction of Flood Mitigation Structure | 125.1106 | 6.1302 | 51145000 | 51144998.16 | 2023 | RUCS KONSULT & CONSTRUCTION SERVICES / SALMEGA BUILDERS | 9380 | 2023 | 2023-08-27 | 02/21/2023 | 1.84 | 0 | 2023-08-26 |  | 1
2024 | Region XII | SARANGANI | ALABEL (CAPITAL) (SARANGANI) | P00820099MN | Construction of Flood Mitigation Structure | 125.2499 | 6.1174 | 96500000 | 96499688.84 | 2024 | RFP BUILDERS CONSTRUCTION AND SUPPLIES CORPORATION / REYDAN BUILDERS | 9381 | 2024 | 2024-07-01 | 02/20/2024 | 311.16 | 0 | 2024-12-14 | 166
2022 | Region XI | DAVAO OCCIDENTAL | DON MARCELINO (DAVAO OCCIDENTAL) | P00620063MN | Construction of Revetment | 125.6749 | 6.207 | 96500000 | 96500000 | 2022 | ALPHA & OMEGA GEN. CONTRACTOR & DEVELOPMENT CORP. | 9382 | 2022 | 2022-10-10 | 02/24/2022 | 0 | 0 | 2022-10-01 |  | 9
2022 | Region XI | DAVAO DE ORO | MABINI (DOÃ‘A ALICIA) (DAVAO DE ORO) | P00620368MN | Construction of Revetment | 125.9986 | 7.2456 | 19599959.18 | 19599088.71 | 2022 | THEORBIA'S CONSTRUCTION SUPPLIES AND ENGINEERING SERVICES | 9383 | 2022 | 2022-12-17 | 03/29/2022 | 870.47 | 0 | 2022-12-16 |  | 1
2023 | Region XIII | SURIGAO DEL SUR | MADRID (SURIGAO DEL SUR) | P00721349MN | Construction of Flood Mitigation Structure | 126.0015 | 9.2659 | 109045000 | 109044970 | 2024 | LCTING CONSTRUCTION AND DEVELOPMENT CORPORATION (FORMERLY: L.C. TING CONSTRUCTION) | 9384 | 2023 | 2024-06-06 | 04/24/2023 | 30 | 0 | 2024-06-05 |  | 1
2022 | Region XI | DAVAO DE ORO | MONTEVISTA (DAVAO DE ORO) | P00620269MN | Construction of Revetment | 126.0034 | 7.7091 | 48999976.61 | 48999898.13 | 2022 | AB APONESTO CONSTRUCTION PARTS AND SUPPLY, INC. | 9385 | 2022 | 2022-11-05 | 02/15/2022 | 78.48 | 0 | 2022-11-04 |  | 1
2023 | Region XIII | AGUSAN DEL SUR | ROSARIO (AGUSAN DEL SUR) | P00721338MN | Construction of Flood Mitigation Structure | 126.005 | 8.3738 | 144750000 | 144749601.4 | 2024 | CM TAN CONSTRUCTION | 9386 | 2023 | 2024-03-27 | 04/20/2023 | 398.6 | 0 | 2024-04-08 | 12
2023 | Region XIII | AGUSAN DEL NORTE | BUTUAN CITY (CAPITAL) (AGUSAN DEL NORTE) | P00721335MN | Construction of Flood Mitigation Structure | 125.5839 | 8.9485 | 144750000 | 144749857.1 | 2024 | RAMISES CONSTRUCTION | 9387 | 2023 | 2024-11-26 | 09/18/2023 | 142.9 | 0 | 2024-11-25 |  | 1
2023 | Region XI | DAVAO DEL NORTE | SANTO TOMAS (DAVAO DEL NORTE) | P00721437MN | Construction of Flood Mitigation Structure | 125.6784 | 7.5004 | 77200000 | 77177147 | 2024 | GP & H CONSTRUCTION INCORPORATED (FORMERLY: GP & H CONSTRUCTION & SUPPLY) | 9388 | 2023 | 2024-10-15 | 08/09/2023 | 22853 | 0 | 2024-12-30 | 76
2023 | Region XI | DAVAO DE ORO | MONTEVISTA (DAVAO DE ORO) | P00721277MN | Construction of Revetment | 126.0051 | 7.6929 | 57900000 | 57898265.04 | 2023 | NEN BUILDERS AND DEVELOPMENT SERVICES CORPORATION | 9389 | 2023 | 2023-08-14 | 02/16/2023 | 1734.96 | 0 | 2023-10-10 | 57
2022 | Region XII | SARANGANI | ALABEL (CAPITAL) (SARANGANI) | P00620091MN | Construction of Flood Mitigation Structure | 125.2502 | 6.1146 | 96500000 | 96408812.01 | 2023 | VICENTE T. LAO CONSTRUCTION | 9390 | 2022 | 2023-05-04 | 02/24/2022 | 91187.99 | 0 | 2023-05-03 |  | 1
2022 | Region XIII | SURIGAO DEL NORTE | TAGANA-AN (SURIGAO DEL NORTE) | P00630638MN | Construction of Flood Mitigation Structure | 125.5839 | 9.6937 | 49000000 | 48508680.35 | 2022 | C.V. CONSTRUCTION & DEVELOPMENT | 9391 | 2022 | 2022-12-12 | 04/01/2022 | 491319.65 | 0 | 2022-12-11 |  | 1
2022 | Region XII | SOUTH COTABATO | GENERAL SANTOS CITY (DADIANGAS) (SOUTH COTABATO) | P00630529MN | Construction of Revetment | 125.1111 | 6.1297 | 91675000 | 88424895.91 | 2023 | LEGACY CONSTRUCTION CORPORATION (FORMERLY: LEGACY CONSTRUCTION) | 9392 | 2022 | 2023-09-17 | 02/24/2022 | 3250104.09 | 0 | 2023-02-25 |  | 204
2024 | Region XI | DAVAO DEL NORTE | PANABO CITY (DAVAO DEL NORTE) | P00833568MN | Construction of Drainage Structure | 125.6804 | 7.2927 | 4950000 | 4949927.64 | 2024 | TWO DEGREES CONSTRUCTION AND SUPPLY | 9393 | 2024 | 2024-09-23 | 03/08/2024 | 72.36 | 0 | 2024-09-22 |  | 1
2021 | Region XIII | SURIGAO DEL SUR |  | P00522135MN | Construction of Revetment | 126.1887 | 9.074 | 77200000 | 77199953.75 | 2022 | J.M. LUCIANO CONSTRUCTION, INC. | 9394 | 2021 | 2022-10-06 | 03/16/2021 | 46.25 | 0 | 2022-10-05 |  | 1
2022 | Region XIII | AGUSAN DEL SUR | ROSARIO (AGUSAN DEL SUR) | P00620347MN | Construction of Flood Mitigation Structure | 126.0061 | 8.373 | 57900000 | 57899988.14 | 2023 | CM TAN CONSTRUCTION | 9395 | 2022 | 2023-03-30 | 06/30/2022 | 11.86 | 0 | 2023-03-29 |  | 1
2022 | Region XIII | SURIGAO DEL SUR | CITY OF TANDAG (CAPITAL) (SURIGAO DEL SUR) | P00620105MN | Construction of Revetment | 126.1911 | 9.0775 | 101325000 | 101324948.6 | 2024 | J.M. LUCIANO CONSTRUCTION, INC. | 9396 | 2022 | 2024-05-08 | 11/29/2022 | 51.4 | 0 | 2024-05-07 |  | 1
2024 | Region XI | DAVAO OCCIDENTAL | DON MARCELINO (DAVAO OCCIDENTAL) | P00820069MN | Construction of Flood Mitigation Structure | 125.6813 | 6.1608 | 116566210 | 116555947.6 | 2024 | SCP CONSTRUCTION | 9397 | 2024 | 2024-10-22 | 02/26/2024 | 10262.4 | 0 | 2024-10-21 |  | 1
2022 | Region X | BUKIDNON | QUEZON (BUKIDNON) | P00630497MN | Construction of Revetment | 125.1113 | 7.7031 | 67550000 | 67550000 | 2023 | PYRAMID CONSOLIDATED BUILDERS & GEN. MDSE. | 9398 | 2022 | 2023-02-04 | 02/18/2022 | 0 | 0 | 2023-02-03 |  | 1
2023 | Region XIII | DINAGAT ISLANDS | TUBAJON (DINAGAT ISLANDS) | P00721396MN | Construction of Flood Mitigation Structure | 125.5842 | 10.2914 | 4900000 | 4897988.93 | 2023 | BAMBOE CONSTRUCTION | 9399 | 2023 | 2023-05-31 | 02/23/2023 | 2011.07 | 0 | 2023-06-21 | 21
2023 | Region XI | DAVAO DE ORO | MONTEVISTA (DAVAO DE ORO) | P00721278MN | Construction of Revetment | 126.0065 | 7.6865 | 67550000 | 67549999.8 | 2023 | ROSBILL CONSTRUCTION AND SUPPLY | 9400 | 2023 | 2023-12-20 | 02/16/2023 | 0.2 | 0 | 2023-12-28 | 8
2024 | Region XI | DAVAO DEL SUR | HAGONOY (DAVAO DEL SUR) | P00820173MN | Construction of Flood Mitigation Structure | 125.2636 | 6.6742 | 14700000 | 14700000 | 2024 | R.C. MELGAZO BUILDERS | 9401 | 2024 | 2024-06-13 | 02/16/2024 | 0 | 0 | 2024-06-12 |  | 1
2022 | Region XI | DAVAO OCCIDENTAL | DON MARCELINO (DAVAO OCCIDENTAL) | P00634139MN | Construction of Revetment | 125.682 | 6.0865 | 49500000 | 49490002.98 | 2022 | ST. MATTHEW GEN. CONTRACTOR & DEVELOPMENT CORP. | 9402 | 2022 | 2022-09-20 | 03/29/2022 | 9997.02 | 0 | 2022-09-19 |  | 1
2021 | Region XIII | SURIGAO DEL SUR |  | P00522133MN | Construction of Revetment | 126.1948 | 9.0787 | 74027080 | 72293424.04 | 2022 | CM TAN CONSTRUCTION | 9403 | 2021 | 2022-08-29 | 03/04/2021 | 1733655.96 | 0 | 2022-08-28 |  | 1
2022 | Region XI | DAVAO DEL SUR | DAVAO CITY (DAVAO DEL SUR) | P00633927MN | Rehabilitation / Major Repair of Drainage Structure | 125.5851 | 7.0897 | 6860000 | 6860000 | 2023 | VIBRANIUM BUILDERS CORPORATION | 9404 | 2022 | 2023-01-11 | 06/02/2022 | 0 | 0 | 2023-01-18 | 7
2023 | Region X | MISAMIS ORIENTAL | GINGOOG CITY (MISAMIS ORIENTAL) | P00721536MN | Construction of Revetment | 125.1135 | 8.8266 | 72375000 | 72375000 | 2024 | RITCHE-NATHALIE BUILDERS & GENERAL MERCHANDISE | 9405 | 2023 | 2024-03-01 | 04/25/2023 | 0 | 0 | 2024-03-11 | 10
2022 | Region XI | DAVAO DE ORO | MONTEVISTA (DAVAO DE ORO) | P00630767MN | Construction of Revetment | 126.0073 | 7.6845 | 39199820.16 | 39199816.62 | 2022 | AB APONESTO CONSTRUCTION PARTS AND SUPPLY, INC. | 9406 | 2022 | 2022-11-12 | 03/18/2022 | 3.54 | 0 | 2022-11-11 |  | 1
2023 | Region XI | DAVAO OCCIDENTAL | DON MARCELINO (DAVAO OCCIDENTAL) | P00721280MN | Construction of Revetment | 125.6847 | 6.1994 | 77200000 | 77189414.06 | 2023 | YPR GEN. CONTRACTOR AND CONSTRUCTION SUPPLY INC. | 9407 | 2023 | 2023-10-04 | 03/16/2023 | 10585.94 | 0 | 2023-10-03 |  | 1
2023 | Region XIII | AGUSAN DEL SUR | ROSARIO (AGUSAN DEL SUR) | P00721339MN | Construction of Flood Mitigation Structure | 126.0074 | 8.3753 | 144750000 | 144749195.2 | 2024 | CM TAN CONSTRUCTION | 9408 | 2023 | 2024-03-27 | 04/20/2023 | 804.8 | 0 | 2024-04-08 | 12
2022 | Region XIII | AGUSAN DEL SUR | ROSARIO (AGUSAN DEL SUR) | P00634149MN | Construction of Flood Mitigation Structure | 126.0078 | 8.3739 | 49500000 | 49499997.17 | 2023 | VICENTE T. LAO CONSTRUCTION | 9409 | 2022 | 2023-05-01 | 06/30/2022 | 2.83 | 0 | 2023-04-30 |  | 1
2023 | Region XIII | SURIGAO DEL SUR | CITY OF TANDAG (CAPITAL) (SURIGAO DEL SUR) | P00734007MN | Construction of Flood Mitigation Structure | 126.1953 | 9.0812 | 96500000 | 96499030.26 | 2024 | ROWIE'S CONSTRUCTION / JARGON CONSTRUCTION & SUPPLY | 9410 | 2023 | 2024-02-27 | 04/17/2023 | 969.74 | 0 | 2024-02-26 |  | 1
2022 | Region XIII | AGUSAN DEL NORTE | CARMEN (AGUSAN DEL NORTE) | P00620103MN | Construction of Flood Mitigation Structure | 125.2636 | 9.0063 | 120625000 | 120624636.4 | 2023 | C'ZARLES CONSTRUCTION & SUPPLY | 9411 | 2022 | 2023-06-20 | 08/25/2022 | 363.6 | 0 | 2023-06-19 |  | 1
2024 | Region XIII | SURIGAO DEL NORTE | SAN BENITO (SURIGAO DEL NORTE) | P00836198MN | Construction of Slope Protection Structure | 126.0121 | 9.9679 | 39600000 | 39499723.17 | 2025 | BOOMETRIX DEVELOPMENT CORP. | 9412 | 2024 | 2025-01-17 | 04/05/2024 | 100276.83 | 0 | 2025-01-16 |  | 1
2022 | Region XII | COTABATO (NORTH COTABATO) | MAGPET (COTABATO (NORTH COTABATO)) | P00632611MN | Construction of Dike | 125.1154 | 7.1154 | 9900000 | 9900000 | 2022 | MARCUS CONSTRUCTION & SUPPLY | 9413 | 2022 | 2022-11-04 | 03/29/2022 | 0 | 0 | 2022-10-05 |  | 30
2023 | Region XII | SOUTH COTABATO | GENERAL SANTOS CITY (DADIANGAS) (SOUTH COTABATO) | P00721464MN | Construction of Flood Mitigation Structure | 125.1158 | 6.1299 | 86850000 | 86847861.53 | 2024 | JDRC CONSTRUCTION & SUPPLIES, CORP. | 9414 | 2023 | 2024-03-03 | 03/30/2023 | 2138.47 | 0 | 2024-03-19 | 16
2023 | Region XIII | SURIGAO DEL SUR | CITY OF TANDAG (CAPITAL) (SURIGAO DEL SUR) | P00734010MN | Construction of Flood Mitigation Structure | 126.197 | 9.0837 | 57900000 | 57895510.38 | 2023 | J.M. LUCIANO CONSTRUCTION, INC. | 9415 | 2023 | 2023-12-05 | 04/17/2023 | 4489.62 | 0 | 2024-01-22 | 48
2024 | Region XI | DAVAO DEL NORTE | PANABO CITY (DAVAO DEL NORTE) | P00833569MN | Construction of Drainage Structure | 125.6849 | 7.3044 | 4950000 | 4949981.72 | 2024 | TWO DEGREES CONSTRUCTION AND SUPPLY | 9416 | 2024 | 2024-12-26 | 03/08/2024 | 18.28 | 0 | 2024-12-25 |  | 1
2022 | Region XI | DAVAO DEL SUR | DAVAO CITY (DAVAO DEL SUR) | P00620073MN | Construction of Flood Mitigation Structure | 125.5867 | 7.0782 | 82025000 | 82025000 | 2022 | ARCINUE COMM'L CORPORATION / MINDALIFI CONSTRUCTION AND SUPPLY | 9417 | 2022 | 2022-12-07 | 03/01/2022 | 0 | 0 | 2023-01-09 | 33
2022 | Region XI | DAVAO DEL SUR | HAGONOY (DAVAO DEL SUR) | P00620217MN | Construction of Revetment | 125.2641 | 6.6713 | 77606265 | 77606265 | 2022 | LEGACY CONSTRUCTION CORPORATION (FORMERLY: LEGACY CONSTRUCTION) | 9418 | 2022 | 2022-10-08 | 02/18/2022 | 0 | 0 | 2022-10-07 |  | 1
2022 | Region XIII | AGUSAN DEL SUR | ROSARIO (AGUSAN DEL SUR) | P00633907MN | Construction of Waterway | 126.0133 | 8.3957 | 96500000 | 96499999.5 | 2023 | ARQ BUILDERS / MONOLITHIC CONSTRUCTION & CONCRETE PRODUCTS, INC. | 9419 | 2022 | 2023-08-20 | 10/19/2022 | 0.5 | 0 | 2023-08-19 |  | 1
2021 | Region XIII | DINAGAT ISLANDS |  | P00522278MN | Rehabilitation / Major Repair of Flood Control Structure | 125.587 | 10.2804 | 9800000 | 9799935.19 | 2022 | LYCS BUILDERS AND TRADING | 9420 | 2021 | 2022-07-13 | 03/16/2021 | 64.81 | 0 | 2021-07-23 |  | 355
2022 | Region XII | COTABATO (NORTH COTABATO) | MAGPET (COTABATO (NORTH COTABATO)) | P00620346MN | Construction of Flood Mitigation Structure | 125.1161 | 7.115 | 96500000 | 96500000 | 2023 | LLABAN CONSTRUCTION & SUPPLY (FORMERLY: LLABAN CON | 9421 | 2022 | 2023-12-04 | 03/29/2022 | 0 | 0 | 2023-06-04 |  | 183
2022 | Region XI | DAVAO OCCIDENTAL | DON MARCELINO (DAVAO OCCIDENTAL) | P00620062MN | Construction of Revetment | 125.6884 | 6.1527 | 96500000 | 96500000 | 2022 | ALPHA & OMEGA GEN. CONTRACTOR & DEVELOPMENT CORP. | 9422 | 2022 | 2022-10-10 | 02/24/2022 | 0 | 0 | 2022-10-01 |  | 9
2022 | Region XIII | SURIGAO DEL SUR | SAN AGUSTIN (SURIGAO DEL SUR) | P00620100MN | Construction of Flood Mitigation Structure | 126.2067 | 8.7533 | 100360000 | 100347111.5 | 2023 | CM TAN CONSTRUCTION | 9423 | 2022 | 2023-09-30 | 07/08/2022 | 12888.5 | 0 | 2023-09-29 |  | 1
2022 | Region XI | DAVAO ORIENTAL | LUPON (DAVAO ORIENTAL) | P00620176MN | Construction of Drainage Structure | 126.0135 | 6.9058 | 49000000 | 49000000 | 2022 | RMT CORPORATION (FORMERLY: MELROBE BUILDERS & CONSTRUCTION SUPPLIES) / ABU CONSTRUCTION | 9424 | 2022 | 2022-11-24 | 03/28/2022 | 0 | 0 | 2022-11-23 |  | 1
2022 | Region XII | COTABATO (NORTH COTABATO) | MAGPET (COTABATO (NORTH COTABATO)) | P00620236MN | Construction of Dike | 125.1167 | 7.1159 | 50254304.98 | 50254305 | 2022 | MARCUS CONSTRUCTION & SUPPLY | 9425 | 2022 | 2022-12-13 | 03/29/2022 | 0 | 0.02 | 2023-01-28 | 46
2023 | Region X | BUKIDNON | KITAOTAO (BUKIDNON) | P00734018MN | Construction of Flood Mitigation Structure | 125.2643 | 7.5206 | 4900000 | 4893715.86 | 2023 | REVILO CONSTRUCTION | 9426 | 2023 | 2023-10-14 | 05/18/2023 | 6284.14 | 0 | 2023-10-13 |  | 1
2022 | Region XIII | AGUSAN DEL NORTE | KITCHARAO (AGUSAN DEL NORTE) | P00620252MN | Construction of Flood Mitigation Structure | 125.5889 | 9.4422 | 115800000 | 115799987.6 | 2022 | C'ZARLES CONSTRUCTION & SUPPLY | 9427 | 2022 | 2022-11-12 | 03/18/2022 | 12.4 | 0 | 2022-11-11 |  | 1
2022 | Region VIII | SOUTHERN LEYTE | HINUNDAYAN (SOUTHERN LEYTE) | P00633028VS | Construction of Flood Mitigation Structure | 125.2649 | 10.311 | 20580000 | 20580000 | 2022 | LANOY CONSTRUCTION | 9428 | 2022 | 2022-12-03 | 04/06/2022 | 0 | 0 | 2022-12-02 |  | 1
2023 | Region XIII | SURIGAO DEL SUR | SAN AGUSTIN (SURIGAO DEL SUR) | P00721491MN | Construction of Flood Mitigation Structure | 126.2067 | 8.7533 | 102290000 | 102280040.2 | 2024 | CM TAN CONSTRUCTION | 9429 | 2023 | 2024-02-27 | 03/27/2023 | 9959.8 | 0 | 2024-02-26 |  | 1
2022 | Region XIII | AGUSAN DEL SUR | ESPERANZA (AGUSAN DEL SUR) | P00620189MN | Construction of Flood Mitigation Structure | 125.6891 | 8.6797 | 14700000 | 14699469.14 | 2023 | J.M. LACORTE CONSTRUCTION | 9430 | 2022 | 2023-05-02 | 06/13/2022 | 530.86 | 0 | 2023-05-01 |  | 1
2022 | Region XI | DAVAO DEL SUR | DAVAO CITY (DAVAO DEL SUR) | P00620370MN | Construction of Revetment | 125.5903 | 7.0753 | 77200000 | 77200000 | 2023 | ARCINUE COMM'L CORPORATION / MINDALIFI CONSTRUCTION AND SUPPLY | 9431 | 2022 | 2023-05-02 | 04/13/2022 | 0 | 0 | 2023-05-25 | 23
2022 | Region VIII | NORTHERN SAMAR | PALAPAG (NORTHERN SAMAR) | P00620340VS | Construction of Flood Mitigation Structure | 125.1169 | 12.5526 | 48999843.2 | 48748724.4 | 2023 | JUPA CONSTRUCTION | 9432 | 2022 | 2023-03-15 | 02/11/2022 | 251118.8 | 0 | 2022-11-16 |  | 119
2022 | Region XI | DAVAO DE ORO | MONTEVISTA (DAVAO DE ORO) | P00630768MN | Construction of Flood Mitigation Structure | 126.0222 | 7.6724 | 48999963.5 | 48999930.84 | 2023 | RELY CONSTRUCTION & SUPPLY INC.(FORMERLY: RELY CONSTRUCTION AND SUPPLY) | 9433 | 2022 | 2023-02-20 | 02/23/2022 | 32.66 | 0 | 2023-01-31 |  | 20
2024 | Region XI | DAVAO DEL SUR | HAGONOY (DAVAO DEL SUR) | P00820316MN | Construction of Revetment | 125.2652 | 6.6706 | 89177580 | 89177580 | 2024 | ROAD EDGE TRADING & DEVELOPMENT SERVICES | 9434 | 2024 | 2024-09-22 | 02/22/2024 | 0 | 0 | 2024-09-16 |  | 6
2024 | Region XIII | SURIGAO DEL SUR | SAN AGUSTIN (SURIGAO DEL SUR) | P00820368MN | Construction of Flood Mitigation Structure | 126.2082 | 8.753 | 96500000 | 96499216.69 | 2024 | CM TAN CONSTRUCTION | 9435 | 2024 | 2024-08-30 | 03/19/2024 | 783.31 | 0 | 2025-01-15 | 138
2023 | Region XI | DAVAO DEL SUR | SULOP (DAVAO DEL SUR) | P00721646MN | Construction of Flood Mitigation Structure | 125.2696 | 6.6291 | 96500000 | 96500000 | 2023 | LEGACY CONSTRUCTION CORPORATION (FORMERLY: LEGACY CONSTRUCTION) | 9436 | 2023 | 2023-12-01 | 03/21/2023 | 0 | 0 | 2023-11-30 |  | 1
2023 | Region XII | SOUTH COTABATO | GENERAL SANTOS CITY (DADIANGAS) (SOUTH COTABATO) | P00721462MN | Construction of Flood Mitigation Structure | 125.117 | 6.0862 | 65137500 | 65136465.86 | 2023 | J.G. ORANZA CONSTRUCTION | 9437 | 2023 | 2023-04-24 | 02/21/2023 | 1034.14 | 0 | 2023-08-06 | 104
2021 | Region XI | DAVAO DEL SUR |  | P00550460MN | Construction of Drainage Structure | 125.5914 | 7.0827 | 96500000 | 96500000 | 2022 | RITZ BUILDERS CONSTRUCTION INC. (FORMERLY:RITZTOK CONSTRUCTION AND SUPPLY) / ARCINUE COMM'L CORPORATION | 9438 | 2021 | 2022-11-26 | 01/16/2022 | 0 | 0 | 2022-11-25 |  | 1
2023 | Region XI | DAVAO DEL SUR | SULOP (DAVAO DEL SUR) | P00721445MN | Construction of Revetment | 125.2697 | 6.6211 | 91675000 | 91490150.4 | 2023 | ROSBILL CONSTRUCTION AND SUPPLY | 9439 | 2023 | 2023-12-10 | 03/20/2023 | 184849.6 | 0 | 2023-12-09 |  | 1
2022 | Region VIII | SOUTHERN LEYTE | SAINT BERNARD (SOUTHERN LEYTE) | P00620230VS | Construction of Flood Mitigation Structure | 125.1172 | 10.3035 | 49000000 | 49000000 | 2023 | ALPHA & OMEGA GEN. CONTRACTOR & DEVELOPMENT CORP. | 9440 | 2022 | 2023-12-14 | 02/16/2022 | 0 | 0 | 2023-12-13 |  | 1
2022 | Region XI | DAVAO DE ORO | NABUNTURAN (CAPITAL) (DAVAO DE ORO) | P00620076MN | Construction of Revetment | 126.0253 | 7.5235 | 67549998.87 | 67549498.88 | 2022 | LEGACY CONSTRUCTION CORPORATION (FORMERLY: LEGACY CONSTRUCTION) | 9441 | 2022 | 2022-12-16 | 04/04/2022 | 499.99 | 0 | 2022-12-15 |  | 1
2022 | Region XIII | SURIGAO DEL SUR | CITY OF TANDAG (CAPITAL) (SURIGAO DEL SUR) | P00634154MN | Construction of Flood Mitigation Structure | 126.2092 | 9.0508 | 14850000 | 14848228.87 | 2023 | ROWIE'S CONSTRUCTION | 9442 | 2022 | 2023-05-03 | 08/15/2022 | 1771.13 | 0 | 2023-05-02 |  | 1
2022 | Region XIII | AGUSAN DEL SUR | ESPERANZA (AGUSAN DEL SUR) | P00620194MN | Construction of Flood Mitigation Structure | 125.6895 | 8.6735 | 26460000 | 26459609.73 | 2023 | CM TAN CONSTRUCTION | 9443 | 2022 | 2023-03-09 | 06/13/2022 | 390.27 | 0 | 2023-03-08 |  | 1
2023 | Region VIII | NORTHERN SAMAR | PALAPAG (NORTHERN SAMAR) | P00721587VS | Construction of Flood Mitigation Structure | 125.1175 | 12.5501 | 55487426.05 | 54932000 | 2023 | MCU CONSTRUCTION | 9444 | 2023 | 2023-10-24 | 02/07/2023 | 555426.05 | 0 | 2023-11-02 | 9
2022 | Region XI | DAVAO DEL SUR | SULOP (DAVAO DEL SUR) | P00644824MN | Construction of Revetment | 125.271 | 6.6244 | 67550000 | 67550000 | 2023 | REYDAN BUILDERS | 9445 | 2022 | 2023-07-24 | 03/21/2023 | 0 | 0 | 2023-09-24 | 62
2021 | Region XIII | AGUSAN DEL SUR |  | P00522333MN | Construction of Flood Mitigation Structure | 125.6898 | 8.6733 | 101325000 | 101324994 | 2022 | CM TAN CONSTRUCTION | 9446 | 2021 | 2022-12-15 | 04/20/2022 | 6 | 0 | 2022-12-14 |  | 1
2025 | Region XIII | SURIGAO DEL SUR | TAGO (SURIGAO DEL SUR) | P00935921MN | Construction of Drainage Structure | 126.2103 | 9.035 | 4950000 | 4934983.08 | 2025 | CRJ CONST AND DEVELOPMENT INC | 9447 | 2025 | 2025-04-23 | 02/19/2025 | 15016.92 | 0 | 2025-06-17 | 55
2022 | Region XI | DAVAO DE ORO | MONKAYO (DAVAO DE ORO) | P00630765MN | Construction of Revetment | 126.0299 | 7.7923 | 67549987.53 | 67549125.73 | 2023 | TYER ONE CONSTRUCTION CORPORATION / RELY CONSTRUCTION & SUPPLY INC.(FORMERLY: RELY CONSTRUCTION AND SUPPLY) | 9448 | 2022 | 2023-01-23 | 02/23/2022 | 861.8 | 0 | 2023-01-31 | 8
2024 | Region VIII | NORTHERN SAMAR | PALAPAG (NORTHERN SAMAR) | P00820416VS | Construction of Flood Mitigation Structure | 125.1176 | 12.5479 | 48999981.57 | 48988827.59 | 2024 | JCL CONSTRUCTION AND SUPPLY | 9449 | 2024 | 2024-12-08 | 04/25/2024 | 11153.98 | 0 | 2025-03-19 | 101
2021 | Region XI | DAVAO DEL SUR |  | P00522362MN | Construction of Flood Mitigation Structure | 125.5924 | 7.0767 | 29400000 | 29400000 | 2023 | VICENTE T. LAO CONSTRUCTION | 9450 | 2021 | 2023-08-30 | 07/12/2021 | 0 | 0 | 2023-08-29 |  | 1
2023 | Region VIII | SOUTHERN LEYTE | SAN RICARDO (SOUTHERN LEYTE) | P00733710VS | Construction of Flood Mitigation Structure | 125.2711 | 10.0021 | 9900000 | 9875201.19 | 2023 | TUBIGAN BUILDERS | 9451 | 2023 | 2023-10-17 | 07/31/2023 | 24798.81 | 0 | 2023-11-25 | 39
2023 | Region XIII | SURIGAO DEL SUR | SAN MIGUEL (SURIGAO DEL SUR) | P00721492MN | Rehabilitation / Major Repair of Flood Control Structure | 126.031 | 8.9403 | 60795000 | 60794962.84 | 2024 | ME 3 CONSTRUCTION / EVENPAR CONSTRUCTION AND DEVELOPMENT CORPORATION (FORMERLY: EVEN PAR CONST. CO. INC.) | 9452 | 2023 | 2024-06-12 | 06/26/2023 | 37.16 | 0 | 2024-06-11 |  | 1
2022 | Region XI | DAVAO DEL NORTE | CARMEN (DAVAO DEL NORTE) | P00620085MN | Rehabilitation / Major Repair of Flood Control Structure | 125.6948 | 7.4705 | 86850000 | 86850000 | 2023 | AKN CONSTRUCTION CORPORATION | 9453 | 2022 | 2023-12-16 | 03/01/2022 | 0 | 0 | 2023-12-15 |  | 1
2023 | Region XIII | SURIGAO DEL SUR | SAN AGUSTIN (SURIGAO DEL SUR) | P00732100MN | Construction of Flood Mitigation Structure | 126.2112 | 8.7109 | 106150000 | 106149909.7 | 2024 | HAPPY ALL3 BUILDERS CORPORATION / TRIPARCO DEVELOPMENT CORPORATION | 9454 | 2023 | 2024-05-11 | 03/27/2023 | 90.3 | 0 | 2024-05-10 |  | 1
2022 | Region XI | DAVAO DEL SUR | DAVAO CITY (DAVAO DEL SUR) | P00633922MN | Construction of Drainage Structure | 125.5944 | 7.0761 | 6860000 | 6860000 | 2022 | JB DANTE BUILDERS & SUPPLY | 9455 | 2022 | 2022-10-11 | 04/13/2022 | 0 | 0 | 2022-10-10 |  | 1
2024 | Region X | MISAMIS ORIENTAL | GINGOOG CITY (MISAMIS ORIENTAL) | P00820257MN | Construction of Flood Mitigation Structure | 125.1179 | 8.8232 | 96500000 | 96495215.41 | 2024 | ROAD EDGE TRADING & DEVELOPMENT SERVICES | 9456 | 2024 | 2024-10-10 | 04/25/2024 | 4784.59 | 0 | 2025-03-04 | 145
2021 | Region XIII | SURIGAO DEL SUR |  | P00522339MN | Rehabilitation / Major Repair of Flood Control Structure | 126.0324 | 8.9392 | 110010000 | 110009989.7 | 2023 | CM TAN CONSTRUCTION | 9457 | 2021 | 2023-04-12 | 08/06/2021 | 10.3 | 0 | 2023-04-11 |  | 1
2022 | Region XI | DAVAO DEL SUR | HAGONOY (DAVAO DEL SUR) | P00630511MN | Construction of Flood Mitigation Structure | 125.2721 | 6.6643 | 67550000 | 67550000 | 2022 | TKS BUILDERS & SUPPLIES / LEDCORE CONSTRUCTION AND DEVELOPMENT CORP, | 9458 | 2022 | 2022-11-08 | 02/18/2022 | 0 | 0 | 2022-11-07 |  | 1
2022 | Region XIII | AGUSAN DEL SUR | SANTA JOSEFA (AGUSAN DEL SUR) | P00634147MN | Construction of Flood Mitigation Structure | 126.0333 | 7.9893 | 49500000 | 49499995.15 | 2023 | VICENTE T. LAO CONSTRUCTION | 9459 | 2022 | 2023-06-05 | 06/30/2022 | 4.85 | 0 | 2023-06-04 |  | 1
2021 | Region XIII | AGUSAN DEL SUR |  | P00522334MN | Construction of Flood Mitigation Structure | 125.695 | 8.6727 | 96500000 | 96486483.84 | 2023 | CM TAN CONSTRUCTION | 9460 | 2021 | 2023-04-25 | 05/30/2022 | 13516.16 | 0 | 2023-06-22 | 58
2022 | Region XI | DAVAO ORIENTAL | CITY OF MATI (CAPITAL) (DAVAO ORIENTAL) | P00620071MN | Construction of Flood Mitigation Structure | 126.2114 | 6.5059 | 96500000 | 94474095.6 | 2023 | MAVERICK BUILDERS INCORPORATED (FORMERLY MAVERICK | 9461 | 2022 | 2023-01-22 | 02/28/2022 | 2025904.4 | 0 | 2023-01-21 |  | 1
2020 | Region XI | DAVAO DEL SUR |  | P00444617MN | Construction of Revetment | 125.5965 | 7.0707 | 28950000 | 28950000 | 2023 | ABU CONSTRUCTION | 9462 | 2020 | 2023-03-23 | 12/17/2020 | 0 | 0 | 2023-03-22 |  | 1
2024 | Region X | MISAMIS ORIENTAL | GINGOOG CITY (MISAMIS ORIENTAL) | P00820258MN | Construction of Flood Mitigation Structure | 125.118 | 8.8209 | 96500000 | 96499464 | 2024 | ROAD EDGE TRADING & DEVELOPMENT SERVICES | 9463 | 2024 | 2024-12-09 | 04/25/2024 | 536 | 0 | 2025-03-04 | 85
2021 | Region XI | DAVAO DEL SUR |  | P00444617MN | Construction of Revetment | 125.5965 | 7.0707 | 28950000 | 28950000 | 2023 | ABU CONSTRUCTION | 9464 | 2021 | 2023-03-23 | 12/17/2020 | 0 | 0 | 2023-03-22 |  | 1
2021 | Region XIII | AGUSAN DEL SUR |  | P00522267MN | Construction of Flood Mitigation Structure | 126.0346 | 7.9885 | 49000000 | 49000000 | 2022 | J.M. LACORTE CONSTRUCTION | 9465 | 2021 | 2022-07-14 | 08/09/2021 | 0 | 0 | 2022-07-13 |  | 1
2022 | Region VIII | EASTERN SAMAR | LAWAAN (EASTERN SAMAR) | P00620182VS | Rehabilitation / Major Repair of Flood Control Structure | 125.2722 | 11.1387 | 29399991.21 | 29399997.3 | 2022 | J.A. DEVELOPERS AND ENGINEERS | 9466 | 2022 | 2022-08-20 | 04/05/2022 | 0 | 6.09 | 2022-08-19 |  | 1
2020 | Region XI | DAVAO DEL SUR |  | P00444616MN | Construction of Revetment | 125.5966 | 7.0697 | 28950000 | 28950000 | 2022 | MITZ CONSTRUCTION AND SUPPLY | 9467 | 2020 | 2022-08-22 | 12/17/2020 | 0 | 0 | 2022-08-21 |  | 1
2022 | Region X | BUKIDNON | CITY OF VALENCIA (BUKIDNON) | P00634119MN | Construction of Flood Mitigation Structure | 125.1188 | 7.9346 | 148500000 | 145375675.4 | 2024 | M. MONTESCLAROS ENTERPRISES, INC. | 9468 | 2022 | 2024-03-03 | 08/15/2022 | 3124324.6 | 0 | 2023-08-28 |  | 188
2023 | Region XI | DAVAO DE ORO | MONKAYO (DAVAO DE ORO) | P00721438MN | Construction of Revetment | 126.0358 | 7.8018 | 77200000 | 77199435.22 | 2023 | AB APONESTO CONSTRUCTION PARTS AND SUPPLY, INC. | 9469 | 2023 | 2023-10-18 | 02/16/2023 | 564.78 | 0 | 2023-11-17 | 30
2022 | Region XIII | SURIGAO DEL SUR | SAN AGUSTIN (SURIGAO DEL SUR) | P00630562MN | Construction of Dike | 126.2189 | 8.7403 | 96500000 | 96499747.18 | 2023 | LCTING CONSTRUCTION AND DEVELOPMENT CORPORATION (FORMERLY: L.C. TING CONSTRUCTION) | 9470 | 2022 | 2023-09-26 | 08/15/2022 | 252.82 | 0 | 2023-07-20 |  | 68
2023 | Region XIII | AGUSAN DEL SUR | SIBAGAT (AGUSAN DEL SUR) | P00721483MN | Construction of Flood Mitigation Structure | 125.6953 | 8.8261 | 137512500 | 137512439.7 | 2024 | CM TAN CONSTRUCTION | 9471 | 2023 | 2024-06-13 | 04/20/2023 | 60.3 | 0 | 2024-06-12 |  | 1
2021 | Region XI | DAVAO DEL SUR |  | P00444616MN | Construction of Revetment | 125.5966 | 7.0697 | 28950000 | 28950000 | 2022 | MITZ CONSTRUCTION AND SUPPLY | 9472 | 2021 | 2022-08-22 | 12/17/2020 | 0 | 0 | 2022-08-21 |  | 1
2020 | Region XI | DAVAO DEL SUR |  | P00444646MN | Construction of Revetment | 125.5972 | 7.0691 | 29400000 | 29400000 | 2022 | RAKKI CORPORATION | 9473 | 2020 | 2022-08-18 | 12/13/2020 | 0 | 0 | 2022-08-17 |  | 1
2022 | Region XIII | AGUSAN DEL SUR | SIBAGAT (AGUSAN DEL SUR) | P00620354MN | Construction of Flood Mitigation Structure | 125.6966 | 8.8225 | 49000000 | 48968540.68 | 2023 | CM TAN CONSTRUCTION | 9474 | 2022 | 2023-09-07 | 06/13/2022 | 31459.32 | 0 | 2023-09-06 |  | 1
2022 | Region XI | DAVAO DE ORO | MONKAYO (DAVAO DE ORO) | P00630764MN | Construction of Revetment | 126.0372 | 7.7971 | 67549969.15 | 67549964.47 | 2022 | RELY CONSTRUCTION & SUPPLY INC.(FORMERLY: RELY CONSTRUCTION AND SUPPLY) | 9475 | 2022 | 2022-11-18 | 02/23/2022 | 4.68 | 0 | 2022-10-18 |  | 31
2024 | Region XII | SARANGANI | ALABEL (CAPITAL) (SARANGANI) | P00820200MN | Construction of Flood Mitigation Structure | 125.2722 | 6.0878 | 49000000 | 48996335.51 | 2024 | SALMEGA BUILDERS | 9476 | 2024 | 2024-05-15 | 02/13/2024 | 3664.49 | 0 | 2024-09-08 | 116
2023 | Region XIII | SURIGAO DEL SUR | SAN AGUSTIN (SURIGAO DEL SUR) | P00732098MN | Construction of Flood Mitigation Structure | 126.2191 | 8.7402 | 49000000 | 48999935.28 | 2024 | LICSAL CONSTRUCTION CORPORATION | 9477 | 2023 | 2024-05-22 | 05/10/2023 | 64.72 | 0 | 2024-05-21 |  | 1
2024 | Region XI | DAVAO DEL SUR | HAGONOY (DAVAO DEL SUR) | P00820307MN | Construction of Flood Mitigation Structure | 125.2725 | 6.6644 | 89178545 | 89178545 | 2024 | ROAD EDGE TRADING & DEVELOPMENT SERVICES | 9478 | 2024 | 2024-09-17 | 02/22/2024 | 0 | 0 | 2024-09-16 |  | 1
2021 | Region XI | DAVAO DEL SUR |  | P00444646MN | Construction of Revetment | 125.5972 | 7.0691 | 29400000 | 29400000 | 2022 | RAKKI CORPORATION | 9479 | 2021 | 2022-08-18 | 12/13/2020 | 0 | 0 | 2022-08-17 |  | 1
2022 | Region XII | COTABATO (NORTH COTABATO) | MAGPET (COTABATO (NORTH COTABATO)) | P00620383MN | Construction of Flood Mitigation Structure | 125.1196 | 7.1155 | 49000000 | 49000000 | 2023 | MARCUS CONSTRUCTION & SUPPLY | 9480 | 2022 | 2023-09-04 | 03/29/2022 | 0 | 0 | 2023-06-18 |  | 78
2023 | Region XIII | AGUSAN DEL SUR | SANTA JOSEFA (AGUSAN DEL SUR) | P00721518MN | Construction of Flood Mitigation Structure | 126.0387 | 7.9853 | 49000000 | 48999999.99 | 2023 | J.M. LACORTE CONSTRUCTION | 9481 | 2023 | 2023-11-09 | 04/03/2023 | 0.01 | 0 | 2023-11-08 |  | 1
2024 | Region XIII | SURIGAO DEL SUR | TAGO (SURIGAO DEL SUR) | P00820213MN | Construction of Flood Mitigation Structure | 126.2303 | 8.9521 | 29400000 | 29399932.61 | 2025 | MELROSHEAN CONSTRUCTION CORPORATION | 9482 | 2024 | 2025-01-09 | 06/28/2024 | 67.39 | 0 | 2025-01-08 |  | 1
2022 | Region XIII | SURIGAO DEL NORTE | GIGAQUIT (SURIGAO DEL NORTE) | P00630651MN | Construction of Flood Mitigation Structure | 125.6968 | 9.5976 | 49000000 | 48409915.17 | 2022 | JMT CONSTRUCTION | 9483 | 2022 | 2022-10-24 | 02/11/2022 | 590084.83 | 0 | 2022-10-23 |  | 1
2023 | Region XI | DAVAO DEL SUR | SULOP (DAVAO DEL SUR) | P00721446MN | Construction of Revetment | 125.277 | 6.6589 | 101325000 | 101150000 | 2023 | ROSBILL CONSTRUCTION AND SUPPLY | 9484 | 2023 | 2023-12-10 | 03/20/2023 | 175000 | 0 | 2023-12-09 |  | 1
2022 | Region XI | DAVAO DEL SUR | DAVAO CITY (DAVAO DEL SUR) | P00633913MN | Construction of Drainage Structure | 125.5973 | 7.0871 | 6860000 | 6860000 | 2022 | MICAH CONSTRUCTION & SUPPLY | 9485 | 2022 | 2022-08-12 | 04/13/2022 | 0 | 0 | 2022-08-11 |  | 1
2023 | Region XIII | SURIGAO DEL NORTE | SAN BENITO (SURIGAO DEL NORTE) | P00721401MN | Construction of Flood Mitigation Structure | 126.0391 | 9.9435 | 29400000 | 29395023.19 | 2023 | DQT BUILDERS AND SUPPLY | 9486 | 2023 | 2023-11-16 | 05/03/2023 | 4976.81 | 0 | 2023-11-15 |  | 1
2022 | Region XIII | SURIGAO DEL NORTE | GIGAQUIT (SURIGAO DEL NORTE) | P00630633MN | Construction of Flood Mitigation Structure | 125.6988 | 9.5591 | 39200000 | 39195621.87 | 2022 | CHARLZ CONSTRUCTION, INC. | 9487 | 2022 | 2022-11-21 | 02/11/2022 | 4378.13 | 0 | 2022-11-05 |  | 16
2023 | Region XIII | SURIGAO DEL SUR | TAGO (SURIGAO DEL SUR) | P00734006MN | Construction of Flood Mitigation Structure | 126.2308 | 9.0159 | 96500000 | 96499332.54 | 2024 | LCTING CONSTRUCTION AND DEVELOPMENT CORPORATION (FORMERLY: L.C. TING CONSTRUCTION) | 9488 | 2023 | 2024-02-16 | 04/28/2023 | 667.46 | 0 | 2024-02-17 | 1
2024 | Region XI | DAVAO DEL SUR | SULOP (DAVAO DEL SUR) | P00820314MN | Construction of Revetment | 125.2778 | 6.6593 | 91675000 | 91500000 | 2025 | ROSBILL CONSTRUCTION AND SUPPLY | 9489 | 2024 | 2025-01-20 | 04/11/2024 | 175000 | 0 | 2025-01-19 |  | 1
2023 | Region VIII | SOUTHERN LEYTE | LILOAN (SOUTHERN LEYTE) | P00721920VS | Construction of Flood Mitigation Structure | 125.1201 | 10.137 | 48250000 | 48248051.51 | 2024 | JUCONS CONSTRUCTION OPC (FORMERLY:JUCONS CONSTRUCTION &SUPPLY) | 9490 | 2023 | 2024-03-24 | 09/11/2023 | 1948.49 | 0 | 2024-03-23 |  | 1
2024 | Region XIII | DINAGAT ISLANDS | BASILISA (RIZAL) (DINAGAT ISLANDS) | P00820930MN | Construction of Flood Mitigation Structure | 125.5987 | 10.0602 | 57900000 | 57193333.19 | 2024 | CARTESIAN BUILDERS CORPORATION (FORMERLY: CARTESIAN BUILDERS) | 9491 | 2024 | 2024-09-29 | 03/05/2024 | 706666.81 | 0 | 2024-09-29 | 0
2022 | Region XI | DAVAO DE ORO | NABUNTURAN (CAPITAL) (DAVAO DE ORO) | P00620078MN | Construction of Revetment | 126.041 | 7.4711 | 57215576.41 | 57215519.61 | 2022 | LEGACY CONSTRUCTION CORPORATION (FORMERLY: LEGACY CONSTRUCTION) / DOUBLE J CONSTRUCTION AND SUPPLY | 9492 | 2022 | 2022-11-29 | 03/28/2022 | 56.8 | 0 | 2022-11-28 |  | 1
2022 | Region XIII | SURIGAO DEL SUR | TAGO (SURIGAO DEL SUR) | P00620254MN | Construction of Flood Mitigation Structure | 126.2335 | 9.0144 | 86850000 | 86849162.75 | 2023 | LCTING CONSTRUCTION AND DEVELOPMENT CORPORATION (FORMERLY: L.C. TING CONSTRUCTION) | 9493 | 2022 | 2023-05-22 | 08/08/2022 | 837.25 | 0 | 2023-05-22 | 0
2024 | Region XI | DAVAO DEL SUR | SULOP (DAVAO DEL SUR) | P00820315MN | Construction of Revetment | 125.2783 | 6.6598 | 91675000 | 90271251.25 | 2025 | ROSBILL CONSTRUCTION AND SUPPLY | 9494 | 2024 | 2025-01-25 | 04/16/2024 | 1403748.75 | 0 | 2025-01-24 |  | 1
2023 | Region XII | COTABATO (NORTH COTABATO) | MAGPET (COTABATO (NORTH COTABATO)) | P00721453MN | Construction of Flood Mitigation Structure | 125.1212 | 7.1138 | 77200000 | 77173242.35 | 2024 | MARCUS CONSTRUCTION & SUPPLY | 9495 | 2023 | 2024-06-21 | 10/24/2023 | 26757.65 | 0 | 2024-09-22 | 93
2022 | Region XI | DAVAO DEL SUR | DAVAO CITY (DAVAO DEL SUR) | P00620372MN | Construction of Revetment | 125.599 | 7.1012 | 77200000 | 77200000 | 2023 | DREIRICH BUILDERS / THREE W BUILDERS, INC. | 9496 | 2022 | 2023-07-03 | 04/13/2022 | 0 | 0 | 2023-08-03 | 31
2022 | Region XI | DAVAO DE ORO | COMPOSTELA (DAVAO DE ORO) | P00620226MN | Construction of Revetment | 126.0412 | 7.6529 | 78225734.03 | 78225730.03 | 2022 | AB APONESTO CONSTRUCTION PARTS AND SUPPLY, INC. | 9497 | 2022 | 2022-12-20 | 02/28/2022 | 4 | 0 | 2023-01-10 | 21
2023 | Region XIII | SURIGAO DEL SUR | SAN AGUSTIN (SURIGAO DEL SUR) | P00732099MN | Construction of Flood Mitigation Structure | 126.2349 | 8.7675 | 106150000 | 106149442.1 | 2024 | ME 3 CONSTRUCTION / EVENPAR CONSTRUCTION AND DEVELOPMENT CORPORATION (FORMERLY: EVEN PAR CONST. CO. INC.) | 9498 | 2023 | 2024-04-04 | 03/27/2023 | 557.9 | 0 | 2024-04-03 |  | 1
2024 | Region XI | DAVAO DEL SUR | SULOP (DAVAO DEL SUR) | P00821193MN | Construction of Flood Mitigation Structure | 125.279 | 6.6438 | 96500000 | 96500000 | 2024 | LEGACY CONSTRUCTION CORPORATION (FORMERLY: LEGACY CONSTRUCTION) | 9499 | 2024 | 2024-12-28 | 05/02/2024 | 0 | 0 | 2024-12-27 |  | 1
2022 | Region XI | DAVAO DEL NORTE | CARMEN (DAVAO DEL NORTE) | P00634122MN | Construction of Revetment | 125.7038 | 7.3489 | 99000000 | 99000000 | 2022 | WERR CORPORATION INTERNATIONAL / METRO GEAR CONSTRUCTION CORP. | 9500 | 2022 | 2022-12-01 | 04/07/2022 | 0 | 0 | 2022-11-30 |  | 1
2022 | Region XIII | DINAGAT ISLANDS | BASILISA (RIZAL) (DINAGAT ISLANDS) | P00631116MN | Construction of Flood Mitigation Structure | 125.6001 | 10.0588 | 29700000 | 29699901.51 | 2023 | ALGAMON CONSTRUCTION CORPORATION (FORMERLY: ALGAMON CONSTRUCTION) | 9501 | 2022 | 2023-03-13 | 03/10/2022 | 98.49 | 0 | 2023-04-21 | 39
2021 | Region XI | DAVAO DE ORO |  | P00550484MN | Construction of Revetment | 126.0419 | 7.198 | 5939949.36 | 5914418.11 | 2022 | SNN BUILDERS AND CONSTRUCTION SUPPLY CORPORATION | 9502 | 2021 | 2022-07-21 | 03/24/2022 | 25531.25 | 0 | 2022-07-20 |  | 1
2023 | Region XII | SOUTH COTABATO | GENERAL SANTOS CITY (DADIANGAS) (SOUTH COTABATO) | P00734410MN | Construction of Flood Mitigation Structure | 125.1213 | 6.0654 | 19800000 | 19798637.03 | 2023 | HANNA VIA CONSTRUCTION, INC. (FORMERLY:HANNA VIA DESIGN & CONSTRUCTION) | 9503 | 2023 | 2023-12-01 | 05/25/2023 | 1362.97 | 0 | 2023-11-30 |  | 1
2020 | Region XIII | SURIGAO DEL SUR |  | P00444660MN | Construction of Revetment | 126.2355 | 9.0144 | 49000000 | 48999951.28 | 2022 | JMT CONSTRUCTION | 9504 | 2020 | 2022-07-22 | 12/08/2020 | 48.72 | 0 | 2022-09-11 | 51
2022 | Region XI | DAVAO DEL SUR | KIBLAWAN (DAVAO DEL SUR) | P00630523MN | Construction of Revetment | 125.2797 | 6.6461 | 67550000 | 67550000 | 2023 | VICENTE T. LAO CONSTRUCTION | 9505 | 2022 | 2023-02-07 | 02/18/2022 | 0 | 0 | 2023-02-06 |  | 1
2024 | Region XIII | SURIGAO DEL SUR | CITY OF BISLIG (SURIGAO DEL SUR) | P00835815MN | Construction of Flood Mitigation Structure | 126.2559 | 8.1812 | 96500000 | 96499535.19 | 2025 | ME 3 CONSTRUCTION / EVENPAR CONSTRUCTION AND DEVELOPMENT CORPORATION (FORMERLY: EVEN PAR CONST. CO. INC.) | 9506 | 2024 | 2025-03-31 | 04/11/2024 | 464.81 | 0 | 2025-04-25 | 25
2024 | Region XIII | SURIGAO DEL SUR | BAROBO (SURIGAO DEL SUR) | P00836199MN | Construction of Flood Mitigation Structure | 126.0433 | 8.5386 | 49500000 | 49498336.47 | 2025 | LCTING CONSTRUCTION AND DEVELOPMENT CORPORATION (FORMERLY: L.C. TING CONSTRUCTION) | 9507 | 2024 | 2025-01-30 | 04/15/2024 | 1663.53 | 0 | 2025-01-29 |  | 1
2022 | Region XI | DAVAO DEL NORTE | KAPALONG (DAVAO DEL NORTE) | P00620218MN | Construction of Revetment | 125.7076 | 7.5694 | 86850000 | 86849997.25 | 2022 | TAGUM BUILDERS CONTRACTORS CORP. (FORMERLY: TAGUM | 9508 | 2022 | 2022-11-23 | 03/01/2022 | 2.75 | 0 | 2022-12-26 | 33
2022 | Region XIII | AGUSAN DEL NORTE | BUTUAN CITY (CAPITAL) (AGUSAN DEL NORTE) | P00630541MN | Construction of Flood Mitigation Structure | 125.6004 | 8.9597 | 139925000 | 139924964.4 | 2024 | RAMISES CONSTRUCTION / EQUI-PARCO CONSTRUCTION COMPANY | 9509 | 2022 | 2024-07-31 | 04/20/2022 | 35.6 | 0 | 2024-09-01 | 32
2023 | Region XII | SARANGANI | ALABEL (CAPITAL) (SARANGANI) | P00734033MN | Construction of Flood Mitigation Structure | 125.2814 | 6.1794 | 49000000 | 48999483.45 | 2023 | SHEPPERD CONSTRUCTION AND SUPPLY | 9510 | 2023 | 2023-11-22 | 04/03/2023 | 516.55 | 0 | 2023-11-21 |  | 1
2023 | Region XI | DAVAO ORIENTAL | LUPON (DAVAO ORIENTAL) | P00721503MN | Construction of Flood Mitigation Structure | 126.045 | 6.9152 | 49000000 | 49000000 | 2023 | MAVERICK BUILDERS INCORPORATED (FORMERLY MAVERICK | 9511 | 2023 | 2023-12-03 | 03/24/2023 | 0 | 0 | 2023-12-26 | 23
2023 | Region XIII | SURIGAO DEL SUR | CITY OF BISLIG (SURIGAO DEL SUR) | P00721481MN | Construction of Revetment | 126.2571 | 8.184 | 110975000 | 110974996.6 | 2024 | LCTING CONSTRUCTION AND DEVELOPMENT CORPORATION (FORMERLY: L.C. TING CONSTRUCTION) | 9512 | 2023 | 2024-01-21 | 03/27/2023 | 3.4 | 0 | 2024-01-20 |  | 1
2022 | Region X | BUKIDNON | CITY OF VALENCIA (BUKIDNON) | P00634120MN | Construction of Flood Mitigation Structure | 125.1232 | 7.9389 | 148500000 | 145162014.7 | 2024 | M. MONTESCLAROS ENTERPRISES, INC. | 9513 | 2022 | 2024-03-03 | 08/15/2022 | 3337985.3 | 0 | 2023-08-28 |  | 188
2024 | Region XII | SARANGANI | ALABEL (CAPITAL) (SARANGANI) | P00820202MN | Construction of Flood Mitigation Structure | 125.2839 | 6.1063 | 49000000 | 48889616.12 | 2024 | YURUSA CONSTRUCTION & DEVELOPMENT CORP. / EDCL CONSTRUCTION AND SUPPLY | 9514 | 2024 | 2024-07-29 | 02/13/2024 | 110383.88 | 0 | 2024-09-08 | 41
2024 | Region XIII | SURIGAO DEL SUR | CITY OF BISLIG (SURIGAO DEL SUR) | P00835816MN | Construction of Flood Mitigation Structure | 126.2685 | 8.2062 | 96500000 | 96499134.76 | 2025 | ME 3 CONSTRUCTION / EVENPAR CONSTRUCTION AND DEVELOPMENT CORPORATION (FORMERLY: EVEN PAR CONST. CO. INC.) | 9515 | 2024 | 2025-05-02 | 04/15/2024 | 865.24 | 0 | 2025-05-06 | 4
2022 | Region XIII | AGUSAN DEL SUR | CITY OF BAYUGAN (AGUSAN DEL SUR) | P00620193MN | Construction of Revetment | 125.708 | 8.803 | 26460000 | 26459996.92 | 2023 | ADFIL CORPORATION | 9516 | 2022 | 2023-02-17 | 05/24/2022 | 3.08 | 0 | 2023-02-16 |  | 1
2023 | Region VIII | NORTHERN SAMAR | GAMAY (NORTHERN SAMAR) | P00733323VS | Construction of Flood Mitigation Structure | 125.2853 | 12.3551 | 24499202.26 | 24254200 | 2024 | CDU CONSTRUCTION | 9517 | 2023 | 2024-11-07 | 04/19/2023 | 245002.26 | 0 | 2023-10-14 |  | 390
2022 | Region X | BUKIDNON | CITY OF VALENCIA (BUKIDNON) | P00634121MN | Construction of Flood Mitigation Structure | 125.1234 | 7.9371 | 148500000 | 145429609.5 | 2024 | M. MONTESCLAROS ENTERPRISES, INC. | 9518 | 2022 | 2024-03-03 | 08/15/2022 | 3070390.5 | 0 | 2023-08-11 |  | 205
2023 | Region VIII | NORTHERN SAMAR | GAMAY (NORTHERN SAMAR) | P00733761VS | Construction of Flood Mitigation Structure | 125.2853 | 12.3551 | 9899328.51 | 9893850.8 | 2024 | CDU CONSTRUCTION | 9519 | 2023 | 2024-06-04 | 04/19/2023 | 5477.71 | 0 | 2023-08-15 |  | 294
2021 | Region XIII | SURIGAO DEL SUR |  | P00522290MN | Construction of Revetment | 126.2693 | 8.2084 | 45569089.25 | 45569089 | 2022 | A.T. DUMLAO CONSTRUCTION, INC. FORMERLYANDONI T. D / MONOLITHIC CONSTRUCTION & CONCRETE PRODUCTS, INC. | 9520 | 2021 | 2022-09-15 | 03/26/2021 | 0.25 | 0 | 2022-08-07 |  | 39
2022 | Region XI | DAVAO DEL SUR | DAVAO CITY (DAVAO DEL SUR) | P00620376MN | Rehabilitation / Major Repair of Flood Control Structure | 125.6006 | 7.0864 | 96500000 | 96500000 | 2023 | LEGACY CONSTRUCTION CORPORATION (FORMERLY: LEGACY CONSTRUCTION) | 9521 | 2022 | 2023-03-06 | 04/13/2022 | 0 | 0 | 2023-03-05 |  | 1
2022 | Region XIII | SURIGAO DEL NORTE | CLAVER (SURIGAO DEL NORTE) | P00630537MN | Construction of Flood Mitigation Structure | 125.709 | 9.5745 | 57900000 | 57899995.35 | 2022 | CHARLZ CONSTRUCTION, INC. | 9522 | 2022 | 2022-11-21 | 03/11/2022 | 4.65 | 0 | 2022-12-17 | 26
2022 | Region X | BUKIDNON | CITY OF VALENCIA (BUKIDNON) | P00634118MN | Construction of Flood Mitigation Structure | 125.1253 | 7.941 | 99000000 | 96920496.22 | 2024 | M. MONTESCLAROS ENTERPRISES, INC. | 9523 | 2022 | 2024-01-28 | 08/15/2022 | 2079503.78 | 0 | 2023-06-09 |  | 233
2022 | Region XI | DAVAO ORIENTAL | LUPON (DAVAO ORIENTAL) | P00630609MN | Construction of Flood Mitigation Structure | 126.0461 | 6.9224 | 29400000 | 29400000 | 2022 | MAVERICK BUILDERS INCORPORATED (FORMERLY MAVERICK | 9524 | 2022 | 2022-09-11 | 02/21/2022 | 0 | 0 | 2022-09-10 |  | 1
2022 | Region X | MISAMIS ORIENTAL | GINGOOG CITY (MISAMIS ORIENTAL) | P00620216MN | Construction of Revetment | 125.126 | 8.8298 | 96500000 | 93318046.4 | 2023 | ROAD EDGE TRADING & DEVELOPMENT SERVICES | 9525 | 2022 | 2023-06-13 | 03/21/2022 | 3181953.6 | 0 | 2023-01-13 |  | 151
2022 | Region XIII | SURIGAO DEL SUR | LANUZA (SURIGAO DEL SUR) | P00630654MN | Construction of Flood Mitigation Structure | 126.0478 | 9.2233 | 29400000 | 29399993.12 | 2023 | LCTING CONSTRUCTION AND DEVELOPMENT CORPORATION (FORMERLY: L.C. TING CONSTRUCTION) | 9526 | 2022 | 2023-04-13 | 08/15/2022 | 6.88 | 0 | 2023-04-12 |  | 1
2022 | Region XIII | SURIGAO DEL NORTE | CLAVER (SURIGAO DEL NORTE) | P00630534MN | Construction of Flood Mitigation Structure | 125.7091 | 9.5568 | 57900000 | 56169526.72 | 2022 | CTB CONSTRUCTION AND DEVELOPMENT CORPORATION (FORMERLY : CTB ENGINEERING CONSTRUCTION) / CHARLZ CONSTRUCTION, INC. | 9527 | 2022 | 2022-11-15 | 03/11/2022 | 1730473.28 | 0 | 2023-01-06 | 52
2020 | Region XI | DAVAO DEL SUR |  | P00420017MN | Construction of Revetment | 125.6014 | 7.065 | 60296095 | 60296095 | 2022 | ABU CONSTRUCTION | 9528 | 2020 | 2022-09-19 | 12/16/2020 | 0 | 0 | 2022-09-18 |  | 1
2022 | Region XIII | SURIGAO DEL SUR | LINGIG (SURIGAO DEL SUR) | P00632321MN | Rehabilitation / Major Repair of Slope Protection Structure | 126.2759 | 8.1072 | 96500000 | 95311709.99 | 2023 | DELPAR CONSTRUCTION & SUPPLIES | 9529 | 2022 | 2023-12-08 | 06/22/2022 | 1188290.01 | 0 | 2023-12-10 | 2
2020 | Region XI | DAVAO DEL SUR |  | P00420021MN | Construction of Revetment | 125.6014 | 7.065 | 86136865 | 86136865 | 2022 | RAKKI CORPORATION / RELY CONSTRUCTION & SUPPLY INC.(FORMERLY: RELY CONSTRUCTION AND SUPPLY) | 9530 | 2020 | 2022-11-22 | 12/16/2020 | 0 | 0 | 2022-11-21 |  | 1
2021 | Region XII | SOUTH COTABATO |  | P00522256MN | Construction of Revetment | 125.1264 | 6.1263 | 49000000 | 48976421.12 | 2023 | LEGACY CONSTRUCTION CORPORATION (FORMERLY: LEGACY CONSTRUCTION) | 9531 | 2021 | 2023-01-06 | 03/08/2022 | 23578.88 | 0 | 2022-09-25 |  | 103
2023 | Region X | BUKIDNON | CABANGLASAN (BUKIDNON) | P00721550MN | Construction of Flood Mitigation Structure | 125.2892 | 8.0181 | 57900000 | 57900000 | 2023 | C'ZARLES CONSTRUCTION & SUPPLY | 9532 | 2023 | 2023-10-23 | 03/13/2023 | 0 | 0 | 2023-11-01 | 9
2023 | Region XIII | SURIGAO DEL NORTE | SANTA MONICA (SAPAO) (SURIGAO DEL NORTE) | P00721628MN | Construction of Flood Mitigation Structure | 126.048 | 9.9634 | 49500000 | 48998470.45 | 2023 | DUROS DEVELOPMENT CORP. | 9533 | 2023 | 2023-12-20 | 03/19/2023 | 501529.55 | 0 | 2023-12-19 |  | 1
2022 | Region XI | DAVAO ORIENTAL | CITY OF MATI (CAPITAL) (DAVAO ORIENTAL) | P00620271MN | Construction of Flood Mitigation Structure | 126.2782 | 6.969 | 29400000 | 28518595.69 | 2022 | RAKKI CORPORATION | 9534 | 2022 | 2022-10-16 | 03/28/2022 | 881404.31 | 0 | 2022-10-15 |  | 1
2022 | Region XI | DAVAO DEL NORTE | CARMEN (DAVAO DEL NORTE) | P00630605MN | Construction of Dike | 125.7133 | 7.3354 | 19600000 | 19600000 | 2023 | RUPLINO SEISMUNDO CONSTRUCTION CORPORATION (FORMERLY: R.R. SEISMUNDO CONSTRUCTION & SUPPLY) | 9535 | 2022 | 2023-01-19 | 03/25/2022 | 0 | 0 | 2023-01-18 |  | 1
2021 | Region XI | DAVAO DEL SUR |  | P00420017MN | Construction of Revetment | 125.6014 | 7.065 | 60296095 | 60296095 | 2022 | ABU CONSTRUCTION | 9536 | 2021 | 2022-09-19 | 12/16/2020 | 0 | 0 | 2022-09-18 |  | 1
2023 | Region X | MISAMIS ORIENTAL | GINGOOG CITY (MISAMIS ORIENTAL) | P00721558MN | Construction of Flood Mitigation Structure | 125.1265 | 8.8326 | 72375000 | 72374966.78 | 2024 | C'ZARLES CONSTRUCTION & SUPPLY | 9537 | 2023 | 2024-03-06 | 05/22/2023 | 33.22 | 0 | 2024-03-05 |  | 1
2023 | Region XIII | SURIGAO DEL NORTE | DAPA (SURIGAO DEL NORTE) | P00734422MN | Construction of Drainage Structure | 126.0499 | 9.7591 | 4950000 | 4154118.08 | 2024 | RADIAN CONSTRUCTION AND SUPPLY | 9538 | 2023 | 2024-01-22 | 08/30/2023 | 795881.92 | 0 | 2024-01-22 | 0
2022 | Region XI | DAVAO DE ORO | MONKAYO (DAVAO DE ORO) | P00630759MN | Construction of Revetment | 126.0508 | 7.8328 | 96499862.66 | 96499845.28 | 2023 | AGONG BUILDERS AND CONSTRUCTION SUPPLY, INC. / ABU CONSTRUCTION | 9539 | 2022 | 2023-04-02 | 02/23/2022 | 17.38 | 0 | 2023-04-01 |  | 1
2023 | Region X | BUKIDNON | CITY OF VALENCIA (BUKIDNON) | P00721261MN | Construction of Flood Mitigation Structure | 125.1265 | 7.94 | 115625000 | 113036569.7 | 2024 | M. MONTESCLAROS ENTERPRISES, INC. | 9540 | 2023 | 2024-11-08 | 02/13/2023 | 2588430.3 | 0 | 2023-12-08 |  | 336
2021 | Region XI | DAVAO DEL SUR |  | P00420021MN | Construction of Revetment | 125.6014 | 7.065 | 86136865 | 86136865 | 2022 | RAKKI CORPORATION / RELY CONSTRUCTION & SUPPLY INC.(FORMERLY: RELY CONSTRUCTION AND SUPPLY) | 9541 | 2021 | 2022-11-22 | 12/16/2020 | 0 | 0 | 2022-11-21 |  | 1
2024 | Region XIII | SURIGAO DEL SUR | CITY OF BISLIG (SURIGAO DEL SUR) | P00820372MN | Construction of Flood Mitigation Structure | 126.2844 | 8.1758 | 123188040 | 123188026.7 | 2024 | ROCK DIWATA BUILDERS, INC. | 9542 | 2024 | 2024-11-18 | 03/01/2024 | 13.3 | 0 | 2024-12-25 | 37
2024 | Region XII | SARANGANI | ALABEL (CAPITAL) (SARANGANI) | P00820098MN | Construction of Flood Mitigation Structure | 125.2901 | 6.1877 | 96500000 | 96499943.24 | 2024 | J.G. ORANZA CONSTRUCTION | 9543 | 2024 | 2024-12-11 | 02/20/2024 | 56.76 | 0 | 2024-12-14 | 3
2022 | Region XIII | SURIGAO DEL NORTE | DAPA (SURIGAO DEL NORTE) | P00620301MN | Construction of Flood Mitigation Structure | 126.0513 | 9.7722 | 19800000 | 19562161.77 | 2022 | R26 CONSTRUCTION, INC. | 9544 | 2022 | 2022-10-19 | 03/24/2022 | 237838.23 | 0 | 2022-10-18 |  | 1
2023 | Region XI | DAVAO ORIENTAL | CATEEL (DAVAO ORIENTAL) | P00721272MN | Construction of Revetment | 126.301 | 7.7319 | 96500000 | 96499069.79 | 2023 | DBR CONSTRUCTION CORPORATION (FORMERLY: D.B. RAVELO CONSTRUCTION & SUPPLY) / RELY CONSTRUCTION & SUPPLY INC.(FORMERLY: RELY CONSTRUCTION AND SUPPLY) | 9545 | 2023 | 2023-08-16 | 03/28/2023 | 930.21 | 0 | 2024-02-11 | 179
2021 | Region XI | DAVAO DEL SUR |  | P00550552MN | Construction of Drainage Structure | 125.6016 | 7.0523 | 9800000 | 9800000 | 2022 | GRECO CONSTRUCTION AND SUPPLY | 9546 | 2021 | 2022-07-07 | 11/18/2021 | 0 | 0 | 2022-07-06 |  | 1
2023 | Region XII | SARANGANI | ALABEL (CAPITAL) (SARANGANI) | P00732494MN | Construction of Flood Mitigation Structure | 125.2905 | 6.0997 | 9900000 | 9899844.05 | 2023 | KURDZ CONSTRUCTION | 9547 | 2023 | 2023-06-27 | 04/03/2023 | 155.95 | 0 | 2023-08-29 | 63
2022 | Region XI | DAVAO DEL NORTE | CARMEN (DAVAO DEL NORTE) | P00630510MN | Construction of Dike | 125.7144 | 7.3366 | 67550000 | 67550000 | 2022 | RELY CONSTRUCTION & SUPPLY INC.(FORMERLY: RELY CONSTRUCTION AND SUPPLY) | 9548 | 2022 | 2022-12-05 | 03/01/2022 | 0 | 0 | 2022-12-04 |  | 1
2023 | Region X | MISAMIS ORIENTAL | GINGOOG CITY (MISAMIS ORIENTAL) | P00721559MN | Construction of Flood Mitigation Structure | 125.1266 | 8.8369 | 72375000 | 72374989.72 | 2024 | LCTING CONSTRUCTION AND DEVELOPMENT CORPORATION (FORMERLY: L.C. TING CONSTRUCTION) | 9549 | 2023 | 2024-05-23 | 06/08/2023 | 10.28 | 0 | 2024-05-22 |  | 1
2022 | Region XIII | SURIGAO DEL NORTE | DAPA (SURIGAO DEL NORTE) | P00630560MN | Construction of Flood Mitigation Structure | 126.0522 | 9.7545 | 96500000 | 95534725.09 | 2023 | BOOMETRIX DEVELOPMENT CORP. / MONOLITHIC CONSTRUCTION & CONCRETE PRODUCTS, INC. | 9550 | 2022 | 2023-03-19 | 03/06/2022 | 965274.91 | 0 | 2023-03-18 |  | 1
2022 | Region XI | DAVAO ORIENTAL | CATEEL (DAVAO ORIENTAL) | P00630515MN | Construction of Flood Mitigation Structure | 126.3012 | 7.7281 | 67550000 | 67547375.44 | 2022 | RITZ BUILDERS CONSTRUCTION INC. (FORMERLY:RITZTOK CONSTRUCTION AND SUPPLY) | 9551 | 2022 | 2022-11-08 | 02/21/2022 | 2624.56 | 0 | 2022-11-19 | 11
2023 | Region XIII | DINAGAT ISLANDS | BASILISA (RIZAL) (DINAGAT ISLANDS) | P00721399MN | Construction of Flood Mitigation Structure | 125.602 | 10.0589 | 9800000 | 9794998.31 | 2023 | ALGAMON CONSTRUCTION CORPORATION (FORMERLY: ALGAMON CONSTRUCTION) | 9552 | 2023 | 2023-07-13 | 03/08/2023 | 5001.69 | 0 | 2023-08-02 | 20
2023 | Region XI | DAVAO DEL NORTE | CARMEN (DAVAO DEL NORTE) | P00721276MN | Construction of Flood Mitigation Structure | 125.7158 | 7.3534 | 86850000 | 86850000 | 2024 | ROSBILL CONSTRUCTION AND SUPPLY / AARJG BUILDERS CORPORATION | 9553 | 2023 | 2024-06-13 | 08/09/2023 | 0 | 0 | 2024-06-12 |  | 1
2022 | Region XIII | AGUSAN DEL NORTE | LAS NIEVES (AGUSAN DEL NORTE) | P00630539MN | Construction of Flood Mitigation Structure | 125.6026 | 8.7326 | 173700000 | 173699978.5 | 2023 | ADFIL CORPORATION | 9554 | 2022 | 2023-06-08 | 04/22/2022 | 21.5 | 0 | 2023-06-09 | 1
2023 | Region X | BUKIDNON | CITY OF VALENCIA (BUKIDNON) | P00721237MN | Construction of Flood Mitigation Structure | 125.1275 | 7.9422 | 188000000 | 184246728.2 | 2024 | M. MONTESCLAROS ENTERPRISES, INC. | 9555 | 2023 | 2024-05-27 | 02/13/2023 | 3753271.8 | 0 | 2023-12-08 |  | 171
2023 | Region XIII | SURIGAO DEL NORTE | DAPA (SURIGAO DEL NORTE) | P00734009MN | Construction of Drainage Structure | 126.0522 | 9.7579 | 67550000 | 67049933.5 | 2025 | BOOMETRIX DEVELOPMENT CORP. | 9556 | 2023 | 2025-03-20 | 08/30/2023 | 500066.5 | 0 | 2025-03-19 |  | 1
2024 | Region X | BUKIDNON | CABANGLASAN (BUKIDNON) | P00820027MN | Construction of Flood Mitigation Structure | 125.2916 | 8.015 | 96500000 | 96499793.05 | 2024 | C'ZARLES CONSTRUCTION & SUPPLY | 9557 | 2024 | 2024-08-20 | 01/31/2024 | 206.95 | 0 | 2024-10-25 | 66
2024 | Region XI | DAVAO DEL NORTE | SANTO TOMAS (DAVAO DEL NORTE) | P00833288MN | Construction of Revetment | 125.7175 | 7.5337 | 48250000 | 48250000 | 2024 | ROSBILL CONSTRUCTION AND SUPPLY / AARJG BUILDERS CORPORATION | 9558 | 2024 | 2024-11-08 | 05/22/2024 | 0 | 0 | 2024-11-07 |  | 1
2023 | Region XIII | SURIGAO DEL SUR | CITY OF BISLIG (SURIGAO DEL SUR) | P00721656MN | Construction of Flood Mitigation Structure | 126.3116 | 8.2172 | 96500000 | 96499796.19 | 2024 | CONCEPCION BASIC BUILDERS INC. | 9559 | 2023 | 2024-08-23 | 03/22/2023 | 203.81 | 0 | 2024-08-24 | 1
2022 | Region XIII | DINAGAT ISLANDS | SAN JOSE (CAPITAL) (DINAGAT ISLANDS) | P00620195MN | Construction of Flood Mitigation Structure | 125.6042 | 10.0027 | 35924840 | 35775817.5 | 2023 | CARTESIAN BUILDERS CORPORATION (FORMERLY: CARTESIAN BUILDERS) | 9560 | 2022 | 2023-11-13 | 03/01/2022 | 149022.5 | 0 | 2023-11-04 |  | 9
2024 | Region XII | COTABATO (NORTH COTABATO) | MAGPET (COTABATO (NORTH COTABATO)) | P00820194MN | Construction of Dike | 125.1287 | 7.1122 | 49000000 | 49000000 | 2025 | JARGON CONSTRUCTION & SUPPLY | 9561 | 2024 | 2025-03-25 | 02/18/2024 | 0 | 0 | 2025-03-07 |  | 18
2022 | Region XIII | SURIGAO DEL NORTE | DAPA (SURIGAO DEL NORTE) | P00634151MN | Embankment | 126.0535 | 9.7544 | 14850000 | 14767348.1 | 2022 | MEGA MYKON BUILDERS | 9562 | 2022 | 2022-07-20 | 05/27/2022 | 82651.9 | 0 | 2022-10-16 | 88
2024 | Region XII | SARANGANI | MALAPATAN (SARANGANI) | P00835888MN | Construction of Flood Mitigation Structure | 125.2933 | 6.046 | 49000000 | 48995985.15 | 2024 | ESCORR BUILDERS AND TRADERS, INC. | 9563 | 2024 | 2024-10-28 | 04/05/2024 | 4014.85 | 0 | 2024-10-30 | 2
2022 | Region XIII | SURIGAO DEL SUR | CITY OF BISLIG (SURIGAO DEL SUR) | P00620259MN | Construction of Flood Mitigation Structure | 126.3147 | 8.2204 | 62725000 | 62723880.33 | 2023 | CONCEPCION BASIC BUILDERS INC. | 9564 | 2022 | 2023-03-17 | 03/14/2022 | 1119.67 | 0 | 2023-04-06 | 20
2023 | Region X | BUKIDNON | CITY OF VALENCIA (BUKIDNON) | P00721238MN | Construction of Flood Mitigation Structure | 125.129 | 7.9465 | 188000000 | 183949115 | 2024 | M. MONTESCLAROS ENTERPRISES, INC. | 9565 | 2023 | 2024-01-28 | 03/29/2023 | 4050885 | 0 | 2024-01-21 |  | 7
2020 | Region XI | DAVAO DEL SUR |  | P00420006MN | Construction of Revetment | 125.6043 | 7.0582 | 45080000 | 45080000 | 2022 | LEGACY CONSTRUCTION CORPORATION (FORMERLY: LEGACY CONSTRUCTION) | 9566 | 2020 | 2022-08-28 | 02/27/2020 | 0 | 0 | 2022-08-10 |  | 18
2022 | Region XIII | SURIGAO DEL NORTE | DAPA (SURIGAO DEL NORTE) | P00634150MN | Construction of Drainage Structure | 126.0537 | 9.7588 | 4950000 | 4892235.61 | 2022 | MEGA MYKON BUILDERS | 9567 | 2022 | 2022-10-26 | 05/27/2022 | 57764.39 | 0 | 2022-10-27 | 1
2023 | Region XII | SARANGANI | ALABEL (CAPITAL) (SARANGANI) | P00721585MN | Construction of Flood Mitigation Structure | 125.2943 | 6.101 | 96500000 | 96499426.29 | 2024 | MRRM TRADING & CONSTRUCTION / SALMEGA BUILDERS | 9568 | 2023 | 2024-04-30 | 07/11/2023 | 573.71 | 0 | 2024-05-02 | 2
2023 | Region XI | DAVAO ORIENTAL | CATEEL (DAVAO ORIENTAL) | P00721271MN | Construction of Flood Mitigation Structure | 126.3208 | 7.7537 | 96500000 | 96499675.54 | 2024 | DREIRICH BUILDERS / THREE W BUILDERS, INC. | 9569 | 2023 | 2024-09-30 | 03/28/2023 | 324.46 | 0 | 2024-10-07 | 7
2023 | Region XIII | AGUSAN DEL SUR | SAN LUIS (AGUSAN DEL SUR) | P00721482MN | Construction of Flood Mitigation Structure | 125.7192 | 8.5454 | 137512500 | 137511331.6 | 2024 | ARQ BUILDERS | 9570 | 2023 | 2024-04-06 | 03/27/2023 | 1168.4 | 0 | 2024-04-15 | 9
2024 | Region X | BUKIDNON | SAN FERNANDO (BUKIDNON) | P00835863MN | Construction of Flood Mitigation Structure | 125.2956 | 7.9149 | 29400000 | 29400000 | 2024 | REFUGE CONSTRUCTION SERVICES | 9571 | 2024 | 2024-10-03 | 02/27/2024 | 0 | 0 | 2024-10-02 |  | 1
2024 | Region XII | COTABATO (NORTH COTABATO) | MAGPET (COTABATO (NORTH COTABATO)) | P00820196MN | Construction of Revetment | 125.1301 | 7.113 | 49000000 | 49000000 | 2025 | JARGON CONSTRUCTION & SUPPLY | 9572 | 2024 | 2025-03-20 | 04/17/2024 | 0 | 0 | 2025-04-06 | 17
2022 | Region XI | DAVAO DEL SUR | DAVAO CITY (DAVAO DEL SUR) | P00633921MN | Construction of Drainage Structure | 125.6047 | 7.0848 | 6860000 | 6860000 | 2022 | CJEP BUILDERS AND ENGINEERING SERVICES | 9573 | 2022 | 2022-08-24 | 04/13/2022 | 0 | 0 | 2022-08-23 |  | 1
2022 | Region XI | DAVAO DEL NORTE | SANTO TOMAS (DAVAO DEL NORTE) | P00620067MN | Construction of Flood Mitigation Structure | 125.7209 | 7.5302 | 86850000 | 86850000 | 2023 | AB APONESTO CONSTRUCTION PARTS AND SUPPLY, INC. | 9574 | 2022 | 2023-12-19 | 02/24/2022 | 0 | 0 | 2024-01-04 | 16
2023 | Region XII | SARANGANI | ALABEL (CAPITAL) (SARANGANI) | P00721586MN | Construction of Flood Mitigation Structure | 125.2958 | 6.1028 | 115800000 | 115798238.9 | 2024 | GEMMA CONSTRUCTION SUPPLY, INC.(FORMERLY:GEMMA CON | 9575 | 2023 | 2024-07-03 | 08/18/2023 | 1761.1 | 0 | 2024-07-02 |  | 1
2024 | Region X | BUKIDNON | CITY OF MALAYBALAY (CAPITAL) (BUKIDNON) | P00820042MN | Construction of Flood Mitigation Structure | 125.1315 | 8.0928 | 141750000 | 141855000 | 2025 | JT GAMOLO CONSTRUCTION, INCORPORATION (FORMERLY:J.T. GAMOLO CONSTRUCTION) | 9576 | 2024 | 2025-03-25 | 01/31/2024 | 0 | 105000 | 2025-03-24 |  | 1
2024 | Region XIII | SURIGAO DEL NORTE | SANTA MONICA (SAPAO) (SURIGAO DEL NORTE) | P00820932MN | Construction of Flood Mitigation Structure | 126.0542 | 9.9895 | 72375000 | 72274740.23 | 2025 | BOOMETRIX DEVELOPMENT CORP. | 9577 | 2024 | 2025-05-15 | 02/16/2024 | 100259.77 | 0 | 2024-11-17 |  | 179
2024 | Region XI | DAVAO ORIENTAL | CITY OF MATI (CAPITAL) (DAVAO ORIENTAL) | P00820182MN | Construction of Flood Mitigation Structure | 126.3358 | 7.0064 | 49000000 | 45949999.96 | 2024 | ECOMIXED CONSTRUCTION AND DEVELOPMENT CORPORATION | 9578 | 2024 | 2024-08-31 | 03/08/2024 | 3050000.04 | 0 | 2024-12-14 | 105
2022 | Region X | MISAMIS ORIENTAL | GINGOOG CITY (MISAMIS ORIENTAL) | P00620042MN | Construction of Flood Mitigation Structure | 125.1317 | 8.8401 | 77200000 | 74883766.56 | 2023 | ROAD EDGE TRADING & DEVELOPMENT SERVICES / CHIU BUILDERS | 9579 | 2022 | 2023-05-24 | 06/29/2022 | 2316233.44 | 0 | 2023-03-24 |  | 61
2021 | Region XI | DAVAO DEL SUR |  | P00522103MN | Rehabilitation / Major Repair of Flood Control Structure | 125.6053 | 7.0633 | 67550000 | 67550000 | 2022 | THREE W BUILDERS, INC. | 9580 | 2021 | 2022-12-13 | 09/06/2021 | 0 | 0 | 2022-12-12 |  | 1
2021 | Region VIII | NORTHERN SAMAR |  | P00521724VS | Construction of Flood Mitigation Structure | 125.2966 | 12.3847 | 48999610.89 | 47299306 | 2022 | CDU CONSTRUCTION | 9581 | 2021 | 2022-08-05 | 03/15/2021 | 1700304.89 | 0 | 2022-03-26 |  | 132
2024 | Region XIII | SURIGAO DEL NORTE | SANTA MONICA (SAPAO) (SURIGAO DEL NORTE) | P00820931MN | Construction of Flood Mitigation Structure | 126.0558 | 9.9854 | 72375000 | 72274865.65 | 2025 | BOOMETRIX DEVELOPMENT CORP. | 9582 | 2024 | 2025-05-21 | 02/16/2024 | 100134.35 | 0 | 2024-11-25 |  | 177
2022 | Region XIII | SURIGAO DEL SUR | CITY OF BISLIG (SURIGAO DEL SUR) | P00620302MN | Construction of Flood Mitigation Structure | 126.3368 | 8.1823 | 49000000 | 48999755.09 | 2023 | O. G. SANTOS CONSTRUCTION | 9583 | 2022 | 2023-06-06 | 02/14/2022 | 244.91 | 0 | 2023-06-05 |  | 1
2022 | Region XIII | SURIGAO DEL NORTE | CLAVER (SURIGAO DEL NORTE) | P00630538MN | Construction of Flood Mitigation Structure | 125.721 | 9.5664 | 57900000 | 57900000 | 2022 | CHARLZ CONSTRUCTION, INC. / GC BUILDERS | 9584 | 2022 | 2022-11-08 | 03/11/2022 | 0 | 0 | 2022-11-07 |  | 1
2023 | Region XII | SOUTH COTABATO | POLOMOLOK (SOUTH COTABATO) | P00721312MN | Construction of Flood Mitigation Structure | 125.1329 | 6.1999 | 53075000 | 53060946.53 | 2023 | J.G. ORANZA CONSTRUCTION | 9585 | 2023 | 2023-07-09 | 02/21/2023 | 14053.47 | 0 | 2023-08-05 | 27
2020 | Region XI | DAVAO DEL SUR |  | P00444643MN | Construction of Revetment | 125.6056 | 7.0609 | 19600000 | 19600000 | 2022 | LEGACY CONSTRUCTION CORPORATION (FORMERLY: LEGACY CONSTRUCTION) | 9586 | 2020 | 2022-10-17 | 12/10/2020 | 0 | 0 | 2022-10-16 |  | 1
2022 | Region VIII | NORTHERN SAMAR | GAMAY (NORTHERN SAMAR) | P00620339VS | Construction of Flood Mitigation Structure | 125.2969 | 12.3839 | 48999580.9 | 48900935.42 | 2023 | MIK AND MEL CONSTRUCTION AND SUPPLY / CDU CONSTRUCTION | 9587 | 2022 | 2023-02-05 | 02/09/2022 | 98645.48 | 0 | 2022-11-04 |  | 93
2024 | Region XI | DAVAO DE ORO | COMPOSTELA (DAVAO DE ORO) | P00835884MN | Construction of Flood Mitigation Structure | 126.0559 | 7.606 | 4899449.27 | 4899242.17 | 2024 | ROSBILL CONSTRUCTION AND SUPPLY | 9588 | 2024 | 2024-07-22 | 04/26/2024 | 207.1 | 0 | 2024-08-20 | 29
2024 | Region XI | DAVAO ORIENTAL | BOSTON (DAVAO ORIENTAL) | P00820304MN | Construction of Flood Mitigation Structure | 126.3368 | 7.8767 | 28950000 | 28949891.48 | 2024 | GMPA CONSTRUCTION SERVICES | 9589 | 2024 | 2024-08-22 | 03/19/2024 | 108.52 | 0 | 2024-11-08 | 78
2021 | Region XI | DAVAO DEL SUR |  | P00444643MN | Construction of Revetment | 125.6056 | 7.0609 | 19600000 | 19600000 | 2022 | LEGACY CONSTRUCTION CORPORATION (FORMERLY: LEGACY CONSTRUCTION) | 9590 | 2021 | 2022-10-17 | 12/10/2020 | 0 | 0 | 2022-10-16 |  | 1
2022 | Region XII | SOUTH COTABATO | GENERAL SANTOS CITY (DADIANGAS) (SOUTH COTABATO) | P00620235MN | Construction of Revetment | 125.1336 | 6.2012 | 86850000 | 86848180.34 | 2022 | LLABAN CONSTRUCTION & SUPPLY (FORMERLY: LLABAN CON / TAJ BUILDERS AND SUPPLY | 9591 | 2022 | 2022-11-17 | 03/29/2022 | 1819.66 | 0 | 2022-11-16 |  | 1
2024 | Region XII | SARANGANI | MALAPATAN (SARANGANI) | P00835805MN | Construction of Flood Mitigation Structure | 125.2984 | 6.0273 | 96500000 | 96497759.33 | 2024 | J.G. ORANZA CONSTRUCTION | 9592 | 2024 | 2024-11-20 | 04/05/2024 | 2240.67 | 0 | 2025-01-28 | 69
2021 | Region XI | DAVAO DE ORO |  | P00550575MN | Construction of Flood Mitigation Structure | 126.0581 | 7.6078 | 4949929.19 | 4949929.19 | 2022 | BQPC CORPORATION | 9593 | 2021 | 2022-11-15 | 03/28/2022 | 0 | 0 | 2022-09-16 |  | 60
2022 | Region XIII | SURIGAO DEL SUR | HINATUAN (SURIGAO DEL SUR) | P00620258MN | Construction of Flood Mitigation Structure | 126.3369 | 8.3739 | 62725000 | 62724987.39 | 2022 | LCTING CONSTRUCTION AND DEVELOPMENT CORPORATION (FORMERLY: L.C. TING CONSTRUCTION) | 9594 | 2022 | 2022-08-30 | 03/14/2022 | 12.61 | 0 | 2023-05-18 | 261
2024 | Region XIII | SURIGAO DEL NORTE | GIGAQUIT (SURIGAO DEL NORTE) | P00820384MN | Construction of Flood Mitigation Structure | 125.7246 | 9.4812 | 139925000 | 138817742.1 | 2024 | GICAR CONSTRUCTION, INC. | 9595 | 2024 | 2024-07-31 | 02/26/2024 | 1107257.9 | 0 | 2025-02-18 | 202
2022 | Region XII | SOUTH COTABATO | GENERAL SANTOS CITY (DADIANGAS) (SOUTH COTABATO) | P00620238MN | Construction of Revetment | 125.1336 | 6.1983 | 96500000 | 96498596.33 | 2022 | J.G. ORANZA CONSTRUCTION | 9596 | 2022 | 2022-11-29 | 03/29/2022 | 1403.67 | 0 | 2022-12-08 | 9
2024 | Region XIII | DINAGAT ISLANDS | DINAGAT (DINAGAT ISLANDS) | P00820126MN | Construction of Flood Mitigation Structure | 125.6058 | 9.9797 | 72375000 | 72374992.88 | 2024 | GICAR CONSTRUCTION, INC. | 9597 | 2024 | 2024-12-13 | 03/05/2024 | 7.12 | 0 | 2024-12-14 | 1
2023 | Region X | BUKIDNON | CABANGLASAN (BUKIDNON) | P00734017MN | Construction of Flood Mitigation Structure | 125.2999 | 8.0726 | 4900000 | 4900000 | 2023 | GREAT PACIFIC BUILDERS AND GEN. CONTRACTOR INC. | 9598 | 2023 | 2023-07-07 | 03/15/2023 | 0 | 0 | 2023-07-06 |  | 1
2023 | Region XI | DAVAO ORIENTAL | LUPON (DAVAO ORIENTAL) | P00721389MN | Construction of Flood Mitigation Structure | 126.0593 | 6.9668 | 49000000 | 48997980.39 | 2023 | MAVERICK BUILDERS INCORPORATED (FORMERLY MAVERICK | 9599 | 2023 | 2023-11-12 | 03/24/2023 | 2019.61 | 0 | 2023-11-11 |  | 1
2021 | Region XIII | SURIGAO DEL SUR |  | P00522291MN | Construction of Revetment | 126.3369 | 8.3742 | 38963487.8 | 38963427.44 | 2022 | LEGACY CONSTRUCTION CORPORATION (FORMERLY: LEGACY CONSTRUCTION) | 9600 | 2021 | 2022-11-15 | 12/15/2021 | 60.36 | 0 | 2023-01-07 | 53
2022 | Region XIII | SURIGAO DEL NORTE | CLAVER (SURIGAO DEL NORTE) | P00630553MN | Construction of Flood Mitigation Structure | 125.7257 | 9.5744 | 57900000 | 57899998.84 | 2023 | CHARLZ CONSTRUCTION, INC. | 9601 | 2022 | 2023-01-07 | 03/11/2022 | 1.16 | 0 | 2023-01-14 | 7
2023 | Region X | BUKIDNON | CITY OF MALAYBALAY (CAPITAL) (BUKIDNON) | P00732049MN | Construction of Flood Mitigation Structure | 125.1354 | 8.1523 | 96500000 | 96499999.25 | 2024 | HGG BUILDERS & SUPPLY | 9602 | 2023 | 2024-02-24 | 02/28/2023 | 0.75 | 0 | 2024-02-23 |  | 1
2022 | Region XIII | SURIGAO DEL SUR | LANUZA (SURIGAO DEL SUR) | P00630655MN | Construction of Flood Mitigation Structure | 126.0626 | 9.2308 | 29400000 | 29399774.88 | 2023 | O. G. SANTOS CONSTRUCTION | 9603 | 2022 | 2023-02-22 | 08/01/2022 | 225.12 | 0 | 2023-02-21 |  | 1
2024 | Region X | BUKIDNON | CABANGLASAN (BUKIDNON) | P00820046MN | Construction of Flood Mitigation Structure | 125.3017 | 7.9973 | 96500000 | 96500000 | 2025 | ROSBILL CONSTRUCTION AND SUPPLY | 9604 | 2024 | 2025-05-09 | 01/31/2024 | 0 | 0 | 2025-05-08 |  | 1
2022 | Region XIII | AGUSAN DEL SUR | CITY OF BAYUGAN (AGUSAN DEL SUR) | P00620352MN | Construction of Flood Mitigation Structure | 125.7308 | 8.7314 | 49000000 | 48999901.68 | 2023 | CM TAN CONSTRUCTION | 9605 | 2022 | 2023-03-19 | 05/24/2022 | 98.32 | 0 | 2023-03-18 |  | 1
2022 | Region XIII | SURIGAO DEL SUR | CITY OF BISLIG (SURIGAO DEL SUR) | P00620303MN | Construction of Drainage Structure | 126.3375 | 8.1828 | 49000000 | 48999970.58 | 2023 | A.T. DUMLAO CONSTRUCTION, INC. FORMERLYANDONI T. D / MONOLITHIC CONSTRUCTION & CONCRETE PRODUCTS, INC. | 9606 | 2022 | 2023-09-16 | 03/04/2022 | 29.42 | 0 | 2023-09-17 | 1
2024 | Region X | BUKIDNON | IMPASUG-ONG (BUKIDNON) | P00820047MN | Construction of Flood Mitigation Structure | 125.1357 | 8.1502 | 96500000 | 96500000 | 2025 | ROSBILL CONSTRUCTION AND SUPPLY | 9607 | 2024 | 2025-04-10 | 01/31/2024 | 0 | 0 | 2025-04-09 |  | 1
2022 | Region XI | DAVAO DEL SUR | DAVAO CITY (DAVAO DEL SUR) | P00620163MN | Construction of Flood Mitigation Structure | 125.606 | 7.0485 | 29400000 | 29400000 | 2023 | GENESIS88 CONSTRUCTION INC. | 9608 | 2022 | 2023-10-26 | 03/31/2022 | 0 | 0 | 2023-10-25 |  | 1
2022 | Region XII | SARANGANI | ALABEL (CAPITAL) (SARANGANI) | P00620183MN | Construction of Flood Mitigation Structure | 125.3019 | 6.1099 | 29400000 | 29399996.68 | 2022 | SILVER HAMMER CONSTRUCTION AND SUPPLIES | 9609 | 2022 | 2022-10-03 | 03/20/2022 | 3.32 | 0 | 2022-10-14 | 11
2023 | Region XI | DAVAO DE ORO | MONKAYO (DAVAO DE ORO) | P00721563MN | Construction of Revetment | 126.0664 | 7.7468 | 96500000 | 96499596.51 | 2023 | ROSBILL CONSTRUCTION AND SUPPLY | 9610 | 2023 | 2023-12-06 | 03/28/2023 | 403.49 | 0 | 2024-02-06 | 62
2023 | Region XII | SARANGANI | ALABEL (CAPITAL) (SARANGANI) | P00734000MN | Construction of Flood Mitigation Structure | 125.3037 | 6.1123 | 77200000 | 77188853.74 | 2023 | J.G. ORANZA CONSTRUCTION | 9611 | 2023 | 2023-12-15 | 05/02/2023 | 11146.26 | 0 | 2024-01-25 | 41
2023 | Region XIII | SURIGAO DEL NORTE | GIGAQUIT (SURIGAO DEL NORTE) | P00721629MN | Construction of Flood Mitigation Structure | 125.7319 | 9.4985 | 49000000 | 47523238.44 | 2023 | ABOA CONSTRUCTION AND SUPPLY / CHARLZ CONSTRUCTION, INC. | 9612 | 2023 | 2023-07-31 | 03/24/2023 | 1476761.56 | 0 | 2023-10-04 | 65
2024 | Region XIII | SURIGAO DEL SUR | HINATUAN (SURIGAO DEL SUR) | P00820928MN | Construction of Flood Mitigation Structure | 126.3377 | 8.3705 | 115800000 | 115796983.1 | 2024 | LCTING CONSTRUCTION AND DEVELOPMENT CORPORATION (FORMERLY: L.C. TING CONSTRUCTION) | 9613 | 2024 | 2024-11-27 | 04/15/2024 | 3016.9 | 0 | 2025-04-03 | 127
2022 | Region XII | SOUTH COTABATO | GENERAL SANTOS CITY (DADIANGAS) (SOUTH COTABATO) | P00620283MN | Construction of Revetment | 125.1383 | 6.1209 | 49000000 | 48849784.13 | 2022 | MJ TIONGSON CONSTRUCTION (FORMERLY: MJT BUILDERS) / REYDAN BUILDERS | 9614 | 2022 | 2022-10-01 | 02/24/2022 | 150215.87 | 0 | 2022-08-31 |  | 31
2021 | Region XI | DAVAO DEL SUR |  | P00522319MN | Construction of Flood Mitigation Structure | 125.606 | 7.0493 | 71796000 | 71796000 | 2022 | PRIMECON BUILDERS, INC. / ARCINUE COMM'L CORPORATION | 9615 | 2021 | 2022-10-20 | 12/05/2021 | 0 | 0 | 2023-01-28 | 100
2023 | Region XIII | SURIGAO DEL NORTE | BURGOS (SURIGAO DEL NORTE) | P00734421MN | Construction of Flood Mitigation Structure | 126.07 | 10.0239 | 4950000 | 4948878.13 | 2023 | BAMBOE CONSTRUCTION | 9616 | 2023 | 2023-08-27 | 05/03/2023 | 1121.87 | 0 | 2023-08-28 | 1
2022 | Region VIII | NORTHERN SAMAR | LAPINIG (NORTHERN SAMAR) | P00633244VS | Rehabilitation / Major Repair of Flood Control Structure | 125.3047 | 12.315 | 49499783.9 | 49004700 | 2022 | CDU CONSTRUCTION | 9617 | 2022 | 2022-12-05 | 05/20/2022 | 495083.9 | 0 | 2022-12-17 | 12
2022 | Region XIII | SURIGAO DEL SUR | HINATUAN (SURIGAO DEL SUR) | P00632319MN | Construction of Slope Protection Structure | 126.3436 | 8.4322 | 106150000 | 106149679.1 | 2023 | NEWINGTON BUILDERS, INC.(FOR: E. GARDIOLA CONSTRUC | 9618 | 2022 | 2023-09-12 | 09/19/2022 | 320.9 | 0 | 2023-09-14 | 2
2022 | Region XIII | SURIGAO DEL NORTE | GIGAQUIT (SURIGAO DEL NORTE) | P00630642MN | Construction of Flood Mitigation Structure | 125.7381 | 9.4986 | 49000000 | 48990622.84 | 2022 | JMT CONSTRUCTION | 9619 | 2022 | 2022-08-25 | 02/11/2022 | 9377.16 | 0 | 2022-08-24 |  | 1
2020 | Region XI | DAVAO DEL SUR |  | P00420007MN | Construction of Revetment | 125.6063 | 7.0538 | 77523275 | 77523275 | 2022 | APEIRON CONSTRUCTION SOLUTIONS / ABU CONSTRUCTION | 9620 | 2020 | 2022-12-19 | 12/10/2020 | 0 | 0 | 2022-12-18 |  | 1
2023 | Region XII | SOUTH COTABATO | GENERAL SANTOS CITY (DADIANGAS) (SOUTH COTABATO) | P00734409MN | Construction of Drainage Structure | 125.1384 | 6.1372 | 9900000 | 9899952.37 | 2023 | MJ TIONGSON CONSTRUCTION (FORMERLY: MJT BUILDERS) | 9621 | 2023 | 2023-09-14 | 04/11/2023 | 47.63 | 0 | 2023-09-23 | 9
2023 | Region XI | DAVAO DE ORO | MONKAYO (DAVAO DE ORO) | P00721562MN | Construction of Revetment | 126.0708 | 7.7444 | 96500000 | 96499253.36 | 2023 | ROSBILL CONSTRUCTION AND SUPPLY | 9622 | 2023 | 2023-12-27 | 03/28/2023 | 746.64 | 0 | 2024-02-06 | 41
2024 | Region XII | SARANGANI | ALABEL (CAPITAL) (SARANGANI) | P00833571MN | Construction of Flood Mitigation Structure | 125.305 | 6.1136 | 89100000 | 89000301.34 | 2025 | J.G. ORANZA CONSTRUCTION | 9623 | 2024 | 2025-02-17 | 05/27/2024 | 99698.66 | 0 | 2025-02-16 |  | 1
2024 | Region XIII | SURIGAO DEL SUR | CITY OF BISLIG (SURIGAO DEL SUR) | P00833294MN | Construction of Flood Mitigation Structure | 126.3457 | 8.1844 | 173700000 | 173699971.7 | 2024 | J.M. LUCIANO CONSTRUCTION, INC. / SURIGAO LA SUERTE CORPORATION | 9624 | 2024 | 2024-09-15 | 03/06/2024 | 28.3 | 0 | 2024-12-29 | 105
2022 | Region XIII | SURIGAO DEL NORTE | CLAVER (SURIGAO DEL NORTE) | P00634153MN | Construction of Flood Mitigation Structure | 125.7381 | 9.5864 | 4950000 | 4875748.77 | 2022 | ZI 9 BUILDERS AND SUPPLIES | 9625 | 2022 | 2022-07-14 | 04/13/2022 | 74251.23 | 0 | 2022-07-13 |  | 1
2023 | Region XII | SOUTH COTABATO | GENERAL SANTOS CITY (DADIANGAS) (SOUTH COTABATO) | P00721315MN | Construction of Flood Mitigation Structure | 125.1385 | 6.1912 | 51145000 | 51089346.18 | 2024 | TSQUARE CONSTRUCTION CORPORATION (FORMERLY:T-SQUARE BUILDERS) | 9626 | 2023 | 2024-02-02 | 07/10/2023 | 55653.82 | 0 | 2023-12-24 |  | 40
2022 | Region XI | DAVAO DE ORO | COMPOSTELA (DAVAO DE ORO) | P00630761MN | Construction of Revetment | 126.0716 | 7.6411 | 72374937.84 | 72370604.7 | 2023 | VICENTE T. LAO CONSTRUCTION | 9627 | 2022 | 2023-04-17 | 03/18/2022 | 4333.14 | 0 | 2023-04-16 |  | 1
2022 | Region XIII | AGUSAN DEL SUR | CITY OF BAYUGAN (AGUSAN DEL SUR) | P00620294MN | Construction of Flood Mitigation Structure | 125.7418 | 8.7072 | 45080000 | 45079990.82 | 2023 | A.T. DUMLAO CONSTRUCTION, INC. FORMERLYANDONI T. D | 9628 | 2022 | 2023-07-13 | 06/13/2022 | 9.18 | 0 | 2023-07-12 |  | 1
2023 | Region XIII | SURIGAO DEL SUR | CITY OF BISLIG (SURIGAO DEL SUR) | P00732106MN | Construction of Flood Mitigation Structure | 126.3477 | 8.1858 | 77200000 | 77199029.74 | 2023 | J.M. LUCIANO CONSTRUCTION, INC. | 9629 | 2023 | 2023-07-21 | 03/17/2023 | 970.26 | 0 | 2024-04-01 | 255
2022 | Region XII | SOUTH COTABATO | GENERAL SANTOS CITY (DADIANGAS) (SOUTH COTABATO) | P00630528MN | Construction of Revetment | 125.1404 | 6.0948 | 62725000 | 62723813.21 | 2022 | J.G. ORANZA CONSTRUCTION | 9630 | 2022 | 2022-09-10 | 02/24/2022 | 1186.79 | 0 | 2022-09-09 |  | 1
2021 | Region XI | DAVAO DEL SUR |  | P00420007MN | Construction of Revetment | 125.6063 | 7.0538 | 77523275 | 77523275 | 2022 | APEIRON CONSTRUCTION SOLUTIONS / ABU CONSTRUCTION | 9631 | 2021 | 2022-12-19 | 12/10/2020 | 0 | 0 | 2022-12-18 |  | 1
2022 | Region VIII | NORTHERN SAMAR | LAPINIG (NORTHERN SAMAR) | P00633243VS | Rehabilitation / Major Repair of Flood Control Structure | 125.3067 | 12.3156 | 49499297.58 | 49491713.8 | 2023 | CDU CONSTRUCTION | 9632 | 2022 | 2023-02-09 | 05/20/2022 | 7583.78 | 0 | 2023-02-12 | 3
2024 | Region XIII | SURIGAO DEL NORTE | BURGOS (SURIGAO DEL NORTE) | P00836163MN | Construction of Flood Mitigation Structure | 126.073 | 10.0207 | 99000000 | 98999966.68 | 2024 | RCDG CONSTRUCTION CORPORATION / LPO1 GROUP OF COMPANIES INC. | 9633 | 2024 | 2024-12-22 | 05/13/2024 | 33.32 | 0 | 2024-12-27 | 5
2023 | Region XI | DAVAO ORIENTAL | BOSTON (DAVAO ORIENTAL) | P00721502MN | Construction of Flood Mitigation Structure | 126.352 | 7.8699 | 29400000 | 29399619.39 | 2023 | RANGAY CONSTRUCTION AND SUPPLY | 9634 | 2023 | 2023-08-29 | 04/05/2023 | 380.61 | 0 | 2023-11-25 | 88
2023 | Region X | BUKIDNON | CITY OF MALAYBALAY (CAPITAL) (BUKIDNON) | P00721533MN | Construction of Flood Mitigation Structure | 125.1417 | 8.0161 | 72375000 | 72374999.37 | 2024 | RITCHE-NATHALIE BUILDERS & GENERAL MERCHANDISE | 9635 | 2023 | 2024-03-05 | 03/13/2023 | 0.63 | 0 | 2024-03-04 |  | 1
2024 | Region XIII | AGUSAN DEL NORTE | LAS NIEVES (AGUSAN DEL NORTE) | P00820378MN | Construction of Flood Mitigation Structure | 125.6073 | 8.7322 | 168635680 | 168635678.1 | 2025 | ADFIL CORPORATION | 9636 | 2024 | 2025-02-28 | 02/22/2024 | 1.9 | 0 | 2025-03-20 | 20
2023 | Region XII | SARANGANI | MALAPATAN (SARANGANI) | P00734405MN | Construction of Drainage Structure | 125.3092 | 6.0343 | 4950000 | 4949593.99 | 2023 | SILVER HAMMER CONSTRUCTION AND SUPPLIES | 9637 | 2023 | 2023-08-22 | 04/26/2023 | 406.01 | 0 | 2023-08-22 | 0
2024 | Region XIII | SURIGAO DEL NORTE | BURGOS (SURIGAO DEL NORTE) | P00833300MN | Construction of Flood Mitigation Structure | 126.0735 | 10.0203 | 48250000 | 48249809.12 | 2024 | RCDG CONSTRUCTION CORPORATION / KENT MARKETING GROUP OF COMPANIES INC. | 9638 | 2024 | 2024-10-01 | 03/06/2024 | 190.88 | 0 | 2024-09-30 |  | 1
2021 | Region XI | DAVAO DEL SUR |  | P00522102MN | Rehabilitation / Major Repair of Flood Control Structure | 125.608 | 7.049 | 77200000 | 77200000 | 2022 | JARGON CONSTRUCTION & SUPPLY | 9639 | 2021 | 2022-12-23 | 09/22/2021 | 0 | 0 | 2022-12-22 |  | 1
2022 | Region XI | DAVAO ORIENTAL | CATEEL (DAVAO ORIENTAL) | P00620170MN | Construction of Flood Mitigation Structure | 126.3664 | 7.7668 | 9800000 | 9799417.14 | 2022 | RITZ BUILDERS CONSTRUCTION INC. (FORMERLY:RITZTOK CONSTRUCTION AND SUPPLY) | 9640 | 2022 | 2022-08-26 | 02/21/2022 | 582.86 | 0 | 2022-08-10 |  | 16
2022 | Region VIII | EASTERN SAMAR | ORAS (EASTERN SAMAR) | P00620325VS | Construction of Flood Mitigation Structure | 125.3176 | 12.2398 | 48984766.27 | 48999969.4 | 2022 | 888 ACY ENTERPRISES | 9641 | 2022 | 2022-11-11 | 02/13/2022 | 0 | 15203.13 | 2022-11-10 |  | 1
2021 | Region XIII | AGUSAN DEL SUR |  | P00522127MN | Construction of Flood Mitigation Structure | 125.7451 | 8.4393 | 96500000 | 96497913.33 | 2023 | MADYAW CONSTRUCTION & DEV. CORPORATION | 9642 | 2021 | 2023-03-25 | 03/29/2021 | 2086.67 | 0 | 2023-04-04 | 10
2023 | Region XIII | SURIGAO DEL SUR | TAGO (SURIGAO DEL SUR) | P00721520MN | Construction of Flood Mitigation Structure | 126.0761 | 8.9231 | 49000000 | 48999999.94 | 2025 | LCTING CONSTRUCTION AND DEVELOPMENT CORPORATION (FORMERLY: L.C. TING CONSTRUCTION) | 9643 | 2023 | 2025-03-09 | 04/04/2023 | 0.06 | 0 | 2023-12-14 |  | 451
2024 | Region XIII | DINAGAT ISLANDS | DINAGAT (DINAGAT ISLANDS) | P00820116MN | Construction of Flood Mitigation Structure | 125.6095 | 9.9895 | 67550000 | 67548671.39 | 2024 | CARTESIAN BUILDERS CORPORATION (FORMERLY: CARTESIAN BUILDERS) | 9644 | 2024 | 2024-09-25 | 03/05/2024 | 1328.61 | 0 | 2024-09-25 | 0
2023 | Region XII | SOUTH COTABATO | GENERAL SANTOS CITY (DADIANGAS) (SOUTH COTABATO) | P00721461MN | Construction of Flood Mitigation Structure | 125.1421 | 6.1531 | 51145000 | 51143096.92 | 2023 | J.G. ORANZA CONSTRUCTION | 9645 | 2023 | 2023-10-27 | 02/21/2023 | 1903.08 | 0 | 2023-10-28 | 1
2022 | Region XIII | SURIGAO DEL SUR | HINATUAN (SURIGAO DEL SUR) | P00632320MN | Construction of Slope Protection Structure | 126.3708 | 8.4774 | 106150000 | 106149809.5 | 2023 | NEWINGTON BUILDERS, INC.(FOR: E. GARDIOLA CONSTRUC | 9646 | 2022 | 2023-09-12 | 09/19/2022 | 190.5 | 0 | 2023-09-14 | 2
2024 | Region X | BUKIDNON | SAN FERNANDO (BUKIDNON) | P00835756MN | Construction of Flood Mitigation Structure | 125.3222 | 7.9681 | 96500000 | 96500000 | 2024 | ROSBILL CONSTRUCTION AND SUPPLY | 9647 | 2024 | 2024-10-26 | 01/31/2024 | 0 | 0 | 2024-10-25 |  | 1
2023 | Region XI | DAVAO ORIENTAL | BOSTON (DAVAO ORIENTAL) | P00721386MN | Construction of Slope Protection Structure | 126.3726 | 7.8476 | 43120000 | 43105338.71 | 2023 | JHARKHA CONSTRUCTION AND SUPPLY | 9648 | 2023 | 2023-08-15 | 03/28/2023 | 14661.29 | 0 | 2023-09-12 | 28
2022 | Region XI | DAVAO DEL NORTE | CITY OF TAGUM (CAPITAL) (DAVAO DEL NORTE) | P00620219MN | Construction of Dike | 125.7455 | 7.3725 | 47211408 | 47211408 | 2023 | O. G. SANTOS CONSTRUCTION | 9649 | 2022 | 2023-08-07 | 03/01/2022 | 0 | 0 | 2023-08-06 |  | 1
2023 | Region XI | DAVAO ORIENTAL | LUPON (DAVAO ORIENTAL) | P00734031MN | Construction of Flood Mitigation Structure | 126.0762 | 6.8921 | 34300000 | 34300000 | 2023 | AGONG BUILDERS AND CONSTRUCTION SUPPLY, INC. | 9650 | 2023 | 2023-11-20 | 03/30/2023 | 0 | 0 | 2023-11-19 |  | 1
2021 | Region XII | SOUTH COTABATO |  | P00522370MN | Construction of Revetment | 125.1424 | 6.0943 | 49000000 | 48998990.7 | 2022 | JDRC CONSTRUCTION & SUPPLIES, CORP. | 9651 | 2021 | 2022-09-30 | 03/08/2022 | 1009.3 | 0 | 2022-10-18 | 18
2024 | Region X | BUKIDNON | SAN FERNANDO (BUKIDNON) | P00835758MN | Construction of Flood Mitigation Structure | 125.3247 | 7.9695 | 96500000 | 96500000 | 2024 | ROSBILL CONSTRUCTION AND SUPPLY | 9652 | 2024 | 2024-11-17 | 02/22/2024 | 0 | 0 | 2024-11-16 |  | 1
2023 | Region XIII | DINAGAT ISLANDS | DINAGAT (DINAGAT ISLANDS) | P00721398MN | Construction of Flood Mitigation Structure | 125.61 | 9.9902 | 9800000 | 9779976.14 | 2023 | CARTESIAN BUILDERS CORPORATION (FORMERLY: CARTESIAN BUILDERS) | 9653 | 2023 | 2023-08-03 | 02/23/2023 | 20023.86 | 0 | 2023-08-03 | 0
2024 | Region XI | DAVAO ORIENTAL | CATEEL (DAVAO ORIENTAL) | P00820174MN | Construction of Flood Mitigation Structure | 126.3791 | 7.7438 | 14700000 | 14699816.87 | 2024 | LICSAL CONSTRUCTION CORPORATION | 9654 | 2024 | 2024-10-15 | 02/12/2024 | 183.13 | 0 | 2024-10-31 | 16
2022 | Region XI | DAVAO ORIENTAL | LUPON (DAVAO ORIENTAL) | P00630610MN | Construction of Flood Mitigation Structure | 126.0762 | 6.974 | 29400000 | 29398234.15 | 2022 | MAVERICK BUILDERS INCORPORATED (FORMERLY MAVERICK | 9655 | 2022 | 2022-10-11 | 02/21/2022 | 1765.85 | 0 | 2022-10-10 |  | 1
2022 | Region XI | DAVAO DEL SUR | DAVAO CITY (DAVAO DEL SUR) | P00633923MN | Construction of Drainage Structure | 125.6126 | 7.0614 | 6860000 | 6860000 | 2023 | C'ZARLES CONSTRUCTION & SUPPLY | 9656 | 2022 | 2023-01-10 | 04/13/2022 | 0 | 0 | 2023-01-09 |  | 1
2024 | Region XII | SOUTH COTABATO | GENERAL SANTOS CITY (DADIANGAS) (SOUTH COTABATO) | P00820328MN | Construction of Revetment | 125.1424 | 6.1505 | 69962500 | 69961399.76 | 2024 | JDRC CONSTRUCTION & SUPPLIES, CORP. | 9657 | 2024 | 2024-10-18 | 03/12/2024 | 1100.24 | 0 | 2024-10-17 |  | 1
2023 | Region X | BUKIDNON | SAN FERNANDO (BUKIDNON) | P00721243MN | Construction of Flood Mitigation Structure | 125.3305 | 7.9234 | 101325000 | 99002702.01 | 2024 | M. MONTESCLAROS ENTERPRISES, INC. | 9658 | 2023 | 2024-02-01 | 02/13/2023 | 2322297.99 | 0 | 2023-10-27 |  | 97
2024 | Region XI | DAVAO ORIENTAL | TARRAGONA (DAVAO ORIENTAL) | P00820074MN | Construction of Flood Mitigation Structure | 126.4086 | 7.0567 | 48250000 | 48248389.36 | 2025 | P.L. SEBASTIAN CONSTRUCTION, INC. (FORMERLY: P.L. SEBASTIAN CONSTRUCTION) | 9659 | 2024 | 2025-01-13 | 03/19/2024 | 1610.64 | 0 | 2025-01-12 |  | 1
2024 | Region XIII | AGUSAN DEL SUR | CITY OF BAYUGAN (AGUSAN DEL SUR) | P00820210MN | Construction of Flood Mitigation Structure | 125.7471 | 8.7396 | 29400000 | 29399610.23 | 2024 | J.M. LACORTE CONSTRUCTION | 9660 | 2024 | 2024-12-10 | 08/12/2024 | 389.77 | 0 | 2025-04-07 | 118
2023 | Region XIII | SURIGAO DEL NORTE | BURGOS (SURIGAO DEL NORTE) | P00721589MN | Rehabilitation / Major Repair of Flood Control Structure | 126.0766 | 10.0165 | 48443000 | 47951985.95 | 2024 | LCTING CONSTRUCTION AND DEVELOPMENT CORPORATION (FORMERLY: L.C. TING CONSTRUCTION) | 9661 | 2023 | 2024-04-24 | 03/28/2023 | 491014.05 | 0 | 2024-04-23 |  | 1
2023 | Region XIII | AGUSAN DEL NORTE | LAS NIEVES (AGUSAN DEL NORTE) | P00721477MN | Construction of Flood Mitigation Structure | 125.6133 | 8.7226 | 115800000 | 115799197.3 | 2024 | ME 3 CONSTRUCTION / EVENPAR CONSTRUCTION AND DEVELOPMENT CORPORATION (FORMERLY: EVEN PAR CONST. CO. INC.) | 9662 | 2023 | 2024-05-30 | 04/20/2023 | 802.7 | 0 | 2024-05-29 |  | 1
2023 | Region XIII | AGUSAN DEL NORTE | LAS NIEVES (AGUSAN DEL NORTE) | P00721478MN | Construction of Flood Mitigation Structure | 125.6133 | 8.7226 | 115800000 | 115799566.4 | 2024 | ME 3 CONSTRUCTION / EVENPAR CONSTRUCTION AND DEVELOPMENT CORPORATION (FORMERLY: EVEN PAR CONST. CO. INC.) | 9663 | 2023 | 2024-05-30 | 04/20/2023 | 433.6 | 0 | 2024-05-29 |  | 1
2024 | Region XIII | AGUSAN DEL SUR | SAN LUIS (AGUSAN DEL SUR) | P00820363MN | Construction of Flood Mitigation Structure | 125.7485 | 8.4754 | 77200000 | 77199705.93 | 2024 | J.M. LACORTE CONSTRUCTION / LEXICON DEVELOPMENT CORPORATION | 9664 | 2024 | 2024-12-11 | 04/17/2024 | 294.07 | 0 | 2025-04-24 | 134
2022 | Region XI | DAVAO ORIENTAL | TARRAGONA (DAVAO ORIENTAL) | P00620175MN | Rehabilitation / Major Repair of Flood Control Structure | 126.4106 | 7.0373 | 29400000 | 29399769.79 | 2022 | RITZ BUILDERS CONSTRUCTION INC. (FORMERLY:RITZTOK CONSTRUCTION AND SUPPLY) | 9665 | 2022 | 2022-12-02 | 02/21/2022 | 230.21 | 0 | 2022-12-09 | 7
2023 | Region XI | DAVAO ORIENTAL | GOVERNOR GENEROSO (DAVAO ORIENTAL) | P00721620MN | Construction of Flood Mitigation Structure | 126.0767 | 6.6304 | 24500000 | 24132496.94 | 2023 | MAER SUMMIT KONSTRUKT CO. | 9666 | 2023 | 2023-11-15 | 03/27/2023 | 367503.06 | 0 | 2023-12-08 | 23
2024 | Region X | BUKIDNON | CITY OF MALAYBALAY (CAPITAL) (BUKIDNON) | P00835776MN | Construction of Flood Mitigation Structure | 125.144 | 8.0108 | 135100000 | 135100000 | 2025 | RITCHE-NATHALIE DEVELOPMENT CORPORATION (FORMERLY: RITCHE-NATHALIE BUILDERS AND GEN. MERCHANDISE) | 9667 | 2024 | 2025-02-18 | 02/27/2024 | 0 | 0 | 2025-02-17 |  | 1
2023 | Region X | BUKIDNON | SAN FERNANDO (BUKIDNON) | P00721244MN | Construction of Flood Mitigation Structure | 125.3307 | 7.9211 | 66550000 | 65122870.63 | 2024 | M. MONTESCLAROS ENTERPRISES, INC. | 9668 | 2023 | 2024-03-17 | 03/29/2023 | 1427129.37 | 0 | 2023-11-22 |  | 116
2022 | Region XI | DAVAO ORIENTAL | BOSTON (DAVAO ORIENTAL) | P00620171MN | Construction of Flood Mitigation Structure | 126.4142 | 7.8272 | 29400000 | 29398519.57 | 2022 | RDJM CONSTRUCTION AND SUPPLY | 9669 | 2022 | 2022-09-06 | 02/08/2022 | 1480.43 | 0 | 2022-09-05 |  | 1
2022 | Region XI | DAVAO DEL NORTE | CARMEN (DAVAO DEL NORTE) | P00630524MN | Construction of Revetment | 125.7492 | 7.3915 | 67550000 | 67549987.12 | 2023 | RELY CONSTRUCTION & SUPPLY INC.(FORMERLY: RELY CONSTRUCTION AND SUPPLY) | 9670 | 2022 | 2023-12-28 | 03/01/2022 | 12.88 | 0 | 2023-12-27 |  | 1
2023 | Region XIII | SURIGAO DEL SUR | LIANGA (SURIGAO DEL SUR) | P00746137MN | Construction of Flood Mitigation Structure | 126.0857 | 8.6428 | 134798785.9 | 134798744.4 | 2024 | CM TAN CONSTRUCTION | 9671 | 2023 | 2024-11-27 | 01/10/2024 | 41.5 | 0 | 2024-11-26 |  | 1
2024 | Region VIII | NORTHERN SAMAR | PALAPAG (NORTHERN SAMAR) | P00820251VS | Construction of Flood Mitigation Structure | 125.1465 | 12.5 | 9799917.39 | 9791028.32 | 2024 | DEACONS TEMPLE CONSTRUCTION & SUPPLY | 9672 | 2024 | 2024-11-10 | 05/15/2024 | 8889.07 | 0 | 2024-11-09 |  | 1
2021 | Region XI | DAVAO DEL SUR |  | P00550458MN | Construction of Drainage Structure | 125.6134 | 7.0706 | 96500000 | 96500000 | 2023 | MITZ CONSTRUCTION AND SUPPLY / O. G. SANTOS CONSTRUCTION | 9673 | 2021 | 2023-01-25 | 01/16/2022 | 0 | 0 | 2023-01-24 |  | 1
2023 | Region X | BUKIDNON | SAN FERNANDO (BUKIDNON) | P00721365MN | Construction of Flood Mitigation Structure | 125.3309 | 7.9248 | 49000000 | 49000000 | 2023 | M. MONTESCLAROS ENTERPRISES, INC. | 9674 | 2023 | 2023-11-11 | 01/31/2023 | 0 | 0 | 2023-11-10 |  | 1
2023 | Region XI | DAVAO ORIENTAL | CATEEL (DAVAO ORIENTAL) | P00721388MN | Construction of Flood Mitigation Structure | 126.438 | 7.8092 | 19600000 | 19599646.11 | 2024 | JHARKHA CONSTRUCTION AND SUPPLY | 9675 | 2023 | 2024-06-03 | 05/23/2023 | 353.89 | 0 | 2024-06-14 | 11
2021 | Region XI | DAVAO DEL SUR |  | P00522101MN | Construction of Drainage Structure | 125.6137 | 7.0942 | 56610760 | 56610760 | 2023 | ABU CONSTRUCTION | 9676 | 2021 | 2023-04-30 | 08/16/2021 | 0 | 0 | 2023-04-29 |  | 1
2021 | Region XI | DAVAO DEL NORTE |  | P00550542MN | Construction of Revetment | 125.7495 | 7.388 | 49000000 | 48125352 | 2022 | LEGACY CONSTRUCTION CORPORATION (FORMERLY: LEGACY CONSTRUCTION) | 9677 | 2021 | 2022-10-04 | 01/27/2022 | 874648 | 0 | 2022-10-03 |  | 1
2023 | Region XI | DAVAO DE ORO | COMPOSTELA (DAVAO DE ORO) | P00721647MN | Construction of Revetment | 126.0885 | 7.6762 | 93315500 | 93315500 | 2023 | LEGACY CONSTRUCTION CORPORATION (FORMERLY: LEGACY CONSTRUCTION) | 9678 | 2023 | 2023-11-15 | 03/21/2023 | 0 | 0 | 2024-01-18 | 64
2021 | Region X | BUKIDNON |  | P00522062MN | Construction of Flood Mitigation Structure | 125.3309 | 7.9206 | 61064235 | 57865469.51 | 2022 | M. MONTESCLAROS ENTERPRISES, INC. | 9679 | 2021 | 2022-07-28 | 08/16/2021 | 3198765.49 | 0 | 2022-04-14 |  | 105
2021 | Region XI | DAVAO DEL SUR |  | P00550459MN | Construction of Drainage Structure | 125.6138 | 7.0909 | 96500000 | 96500000 | 2022 | MAER SUMMIT KONSTRUKT CO. | 9680 | 2021 | 2022-10-27 | 01/16/2022 | 0 | 0 | 2022-10-26 |  | 1
2022 | Region XI | DAVAO DEL NORTE | CITY OF TAGUM (CAPITAL) (DAVAO DEL NORTE) | P00620233MN | Construction of Flood Mitigation Structure | 125.7512 | 7.4788 | 57900000 | 57900000 | 2022 | GP & H CONSTRUCTION INCORPORATED (FORMERLY: GP & H CONSTRUCTION & SUPPLY) | 9681 | 2022 | 2022-11-28 | 02/22/2022 | 0 | 0 | 2022-12-02 | 4
2024 | Region XI | DAVAO ORIENTAL | TARRAGONA (DAVAO ORIENTAL) | P00833298MN | Construction of Revetment | 126.4431 | 7.0209 | 48250000 | 48249684.37 | 2024 | ECBJ EASTCOAST CONSTRUCTION | 9682 | 2024 | 2024-07-15 | 04/22/2024 | 315.63 | 0 | 2025-01-06 | 175
2024 | Region XI | DAVAO DEL SUR | MAGSAYSAY (DAVAO DEL SUR) | P00820065MN | Construction of Revetment | 125.1481 | 6.7461 | 115800000 | 115800000 | 2024 | ALPHA & OMEGA GEN. CONTRACTOR & DEVELOPMENT CORP. | 9683 | 2024 | 2024-10-26 | 03/07/2024 | 0 | 0 | 2024-10-25 |  | 1
2023 | Region XI | DAVAO DE ORO | COMPOSTELA (DAVAO DE ORO) | P00721644MN | Construction of Revetment | 126.0886 | 7.6757 | 96500000 | 96499992.3 | 2024 | AB APONESTO CONSTRUCTION PARTS AND SUPPLY, INC. | 9684 | 2023 | 2024-12-06 | 03/28/2023 | 7.7 | 0 | 2024-12-06 | 0
2022 | Region XIII | AGUSAN DEL NORTE | NASIPIT (AGUSAN DEL NORTE) | P00620104MN | Construction of Flood Mitigation Structure | 125.3335 | 8.9704 | 120625000 | 120624963.4 | 2023 | ADFIL CORPORATION | 9685 | 2022 | 2023-04-30 | 10/07/2022 | 36.6 | 0 | 2023-07-02 | 63
2024 | Region XI | DAVAO ORIENTAL | MANAY (DAVAO ORIENTAL) | P00833292MN | Construction of Revetment | 126.4699 | 7.1398 | 96500000 | 96495097.92 | 2024 | O. G. SANTOS CONSTRUCTION | 9686 | 2024 | 2024-10-28 | 04/22/2024 | 4902.08 | 0 | 2025-03-26 | 149
2023 | Region XI | DAVAO DEL NORTE | CARMEN (DAVAO DEL NORTE) | P00734402MN | Construction of Flood Mitigation Structure | 125.753 | 7.4083 | 9900000 | 9876434.36 | 2024 | FORDEX CONSTRUCTION CORPORATION | 9687 | 2023 | 2024-06-02 | 11/17/2023 | 23565.64 | 0 | 2024-06-01 |  | 1
2022 | Region XI | DAVAO DEL SUR | MAGSAYSAY (DAVAO DEL SUR) | P00630526MN | Construction of Revetment | 125.1486 | 6.7508 | 67550000 | 67550000 | 2022 | TKS BUILDERS & SUPPLIES | 9688 | 2022 | 2022-11-05 | 02/18/2022 | 0 | 0 | 2022-11-04 |  | 1
2022 | Region XI | DAVAO ORIENTAL | LUPON (DAVAO ORIENTAL) | P00620178MN | Construction of Flood Mitigation Structure | 126.0889 | 6.9047 | 19600000 | 19600000 | 2022 | FAJR CONSTRUCTION PARTS AND SUPPLY | 9689 | 2022 | 2022-10-08 | 02/21/2022 | 0 | 0 | 2022-10-07 |  | 1
2022 | Region XI | DAVAO DEL SUR | DAVAO CITY (DAVAO DEL SUR) | P00631101MN | Rehabilitation / Major Repair of Flood Control Structure | 125.6158 | 7.0837 | 4950000 | 4950000 | 2022 | CJEP BUILDERS AND ENGINEERING SERVICES | 9690 | 2022 | 2022-08-29 | 04/13/2022 | 0 | 0 | 2022-08-28 |  | 1
2022 | Region XI | DAVAO DEL SUR | CITY OF DIGOS (CAPITAL) (DAVAO DEL SUR) | P00630509MN | Construction of Flood Mitigation Structure | 125.3336 | 6.7801 | 173700000 | 173600437.6 | 2024 | P.L. SEBASTIAN CONSTRUCTION, INC. (FORMERLY: P.L. SEBASTIAN CONSTRUCTION) | 9691 | 2022 | 2024-02-25 | 03/25/2022 | 99562.4 | 0 | 2024-02-24 |  | 1
2024 | Region XI | DAVAO ORIENTAL | MANAY (DAVAO ORIENTAL) | P00833296MN | Construction of Revetment | 126.4797 | 7.1227 | 48250000 | 48249609.7 | 2024 | ECBJ EASTCOAST CONSTRUCTION | 9692 | 2024 | 2024-07-22 | 04/22/2024 | 390.3 | 0 | 2024-12-20 | 151
2023 | Region VIII | EASTERN SAMAR | HERNANI (EASTERN SAMAR) | P00733310VS | Construction of Flood Mitigation Structure | 125.6168 | 11.3218 | 24124924.27 | 24123628.52 | 2023 | QUEEN MARIECRIS CONSTRUCTION CORP. | 9693 | 2023 | 2023-12-06 | 07/12/2023 | 1295.75 | 0 | 2023-12-05 |  | 1
2023 | Region XI | DAVAO DE ORO | COMPOSTELA (DAVAO DE ORO) | P00721571MN | Construction of Flood Mitigation Structure | 126.0893 | 7.6758 | 96500000 | 51859623.25 | 2024 | METRO GEAR CONSTRUCTION CORP. / REPLICON CONSTRUCTION CORPORATION | 9694 | 2023 | 2024-11-08 | 08/09/2023 | 44640376.75 | 0 | 2024-11-07 |  | 1
2024 | Region XII | SOUTH COTABATO | GENERAL SANTOS CITY (DADIANGAS) (SOUTH COTABATO) | P00820325MN | Construction of Revetment | 125.1492 | 6.1111 | 120625000 | 120624229.7 | 2025 | J.G. ORANZA CONSTRUCTION | 9695 | 2024 | 2025-03-21 | 08/12/2024 | 770.3 | 0 | 2025-06-01 | 72
2022 | Region XI | DAVAO DEL SUR | CITY OF DIGOS (CAPITAL) (DAVAO DEL SUR) | P00630506MN | Construction of Flood Mitigation Structure | 125.3339 | 6.7862 | 173700000 | 173625230.3 | 2023 | MAC BUILDERS CORP. (FORMERLY: MAC BUILDERS DEVELOPMENT CORPORATION) | 9696 | 2022 | 2023-03-27 | 03/11/2022 | 74769.7 | 0 | 2023-03-26 |  | 1
2022 | Region XI | DAVAO ORIENTAL | MANAY (DAVAO ORIENTAL) | P00620380MN | Construction of Flood Mitigation Structure | 126.4842 | 7.1161 | 96500000 | 96499661.76 | 2022 | MAC BUILDERS CORP. (FORMERLY: MAC BUILDERS DEVELOPMENT CORPORATION) | 9697 | 2022 | 2022-12-12 | 03/28/2022 | 338.24 | 0 | 2023-03-01 | 79
2022 | Region XI | DAVAO DEL NORTE | CARMEN (DAVAO DEL NORTE) | P00630603MN | Construction of Revetment | 125.7551 | 7.4027 | 49000000 | 49000000 | 2022 | GP & H CONSTRUCTION INCORPORATED (FORMERLY: GP & H CONSTRUCTION & SUPPLY) | 9698 | 2022 | 2022-11-17 | 02/11/2022 | 0 | 0 | 2022-11-16 |  | 1
2022 | Region XI | DAVAO DEL SUR | DAVAO CITY (DAVAO DEL SUR) | P00634137MN | Construction of Drainage Structure | 125.6192 | 7.1313 | 29700000 | 29700000 | 2023 | MARK ANTHONY CONSTRUCTION & SUPPLY | 9699 | 2022 | 2023-05-07 | 06/09/2022 | 0 | 0 | 2023-05-06 |  | 1
2021 | Region XII | SOUTH COTABATO |  | P00522369MN | Construction of Revetment | 125.151 | 6.1304 | 29400000 | 22631367.51 | 2022 | J.G. ORANZA CONSTRUCTION | 9700 | 2021 | 2022-09-20 | 03/08/2022 | 6768632.49 | 0 | 2022-10-11 | 21
2022 | Region XI | DAVAO DEL SUR | CITY OF DIGOS (CAPITAL) (DAVAO DEL SUR) | P00630508MN | Construction of Flood Mitigation Structure | 125.3349 | 6.7963 | 173700000 | 173700000 | 2023 | MAC BUILDERS CORP. (FORMERLY: MAC BUILDERS DEVELOPMENT CORPORATION) | 9701 | 2022 | 2023-11-23 | 03/24/2022 | 0 | 0 | 2023-11-22 |  | 1
2023 | Region XI | DAVAO ORIENTAL | MANAY (DAVAO ORIENTAL) | P00732066MN | Construction of Revetment | 126.4852 | 7.1178 | 96500000 | 96496078.47 | 2023 | O. G. SANTOS CONSTRUCTION | 9702 | 2023 | 2023-10-30 | 04/04/2023 | 3921.53 | 0 | 2024-03-07 | 129
2022 | Region XI | DAVAO DEL NORTE | ASUNCION (SAUG) (DAVAO DEL NORTE) | P00620231MN | Construction of Revetment | 125.756 | 7.5317 | 96500000 | 96498062.26 | 2022 | LEGACY CONSTRUCTION CORPORATION (FORMERLY: LEGACY CONSTRUCTION) | 9703 | 2022 | 2022-12-05 | 02/24/2022 | 1937.74 | 0 | 2022-12-22 | 17
2021 | Region XI | DAVAO DEL SUR |  | P00522089MN | Construction of Flood Mitigation Structure | 125.6193 | 7.0895 | 69646945 | 69518600 | 2023 | VICENTE T. LAO CONSTRUCTION | 9704 | 2021 | 2023-10-16 | 01/16/2022 | 128345 | 0 | 2023-09-12 |  | 34
2022 | Region XI | DAVAO DEL SUR | CITY OF DIGOS (CAPITAL) (DAVAO DEL SUR) | P00630507MN | Construction of Flood Mitigation Structure | 125.335 | 6.7915 | 173700000 | 173700000 | 2023 | MAC BUILDERS CORP. (FORMERLY: MAC BUILDERS DEVELOPMENT CORPORATION) | 9705 | 2022 | 2023-12-16 | 03/11/2022 | 0 | 0 | 2023-12-15 |  | 1
2023 | Region XI | DAVAO DE ORO | COMPOSTELA (DAVAO DE ORO) | P00721573MN | Construction of Revetment | 126.0896 | 7.6762 | 96500000 | 96499994.56 | 2024 | METRO GEAR CONSTRUCTION CORP. / REPLICON CONSTRUCTION CORPORATION | 9706 | 2023 | 2024-03-22 | 03/24/2023 | 5.44 | 0 | 2024-03-24 | 2
2022 | Region XI | DAVAO DEL NORTE | ASUNCION (SAUG) (DAVAO DEL NORTE) | P00620220MN | Construction of Flood Mitigation Structure | 125.7565 | 7.5394 | 57900000 | 57882638.53 | 2023 | LEGACY CONSTRUCTION CORPORATION (FORMERLY: LEGACY CONSTRUCTION) | 9707 | 2022 | 2023-03-12 | 03/01/2022 | 17361.47 | 0 | 2023-03-12 | 0
2021 | Region XI | DAVAO DEL SUR |  | P00550540MN | Construction of Flood Mitigation Structure | 125.6193 | 7.0895 | 48250000 | 47723221.79 | 2023 | MRD GEMPESAW CONSTRUCTION CORP. / MONOLITHIC CONSTRUCTION & CONCRETE PRODUCTS, INC. | 9708 | 2021 | 2023-05-24 | 12/23/2021 | 526778.21 | 0 | 2023-05-23 |  | 1
2024 | Region XI | DAVAO ORIENTAL | MANAY (DAVAO ORIENTAL) | P00833291MN | Construction of Flood Mitigation Structure | 126.5031 | 7.3553 | 96500000 | 96498973.69 | 2024 | O. G. SANTOS CONSTRUCTION | 9709 | 2024 | 2024-09-21 | 04/22/2024 | 1026.31 | 0 | 2025-04-04 | 195
2024 | Region XII | SOUTH COTABATO | GENERAL SANTOS CITY (DADIANGAS) (SOUTH COTABATO) | P00821202MN | Construction of Revetment | 125.1511 | 6.1305 | 96500000 | 96400433.63 | 2025 | J.G. ORANZA CONSTRUCTION | 9710 | 2024 | 2025-04-25 | 07/22/2024 | 99566.37 | 0 | 2025-04-30 | 5
2021 | Region XI | DAVAO DEL SUR |  | P00550464MN | Rehabilitation / Major Repair of Flood Control Structure | 125.3372 | 6.7659 | 19600000 | 19600000 | 2022 | ROSBILL CONSTRUCTION AND SUPPLY | 9711 | 2021 | 2022-08-12 | 03/24/2022 | 0 | 0 | 2022-08-11 |  | 1
2022 | Region XI | DAVAO DE ORO | COMPOSTELA (DAVAO DE ORO) | P00620266MN | Construction of Revetment | 126.0898 | 7.6761 | 48999997.02 | 48999996.26 | 2022 | THREE W BUILDERS, INC. | 9712 | 2022 | 2022-11-05 | 02/15/2022 | 0.76 | 0 | 2022-11-04 |  | 1
2024 | Region XI | DAVAO ORIENTAL | CARAGA (DAVAO ORIENTAL) | P00833299MN | Construction of Revetment | 126.5053 | 7.3453 | 48250000 | 48249988.81 | 2024 | ECBJ EASTCOAST CONSTRUCTION | 9713 | 2024 | 2024-11-29 | 04/22/2024 | 11.19 | 0 | 2024-12-22 | 23
2022 | Region XI | DAVAO DEL SUR | DAVAO CITY (DAVAO DEL SUR) | P00630596MN | Construction of Dike | 125.3453 | 7.4404 | 9800000 | 9504924.22 | 2022 | RK STAR ECOENGINEERING | 9714 | 2022 | 2022-08-10 | 05/05/2022 | 295075.78 | 0 | 2022-08-09 |  | 1
2022 | Region XI | DAVAO DEL NORTE | ASUNCION (SAUG) (DAVAO DEL NORTE) | P00620232MN | Construction of Flood Mitigation Structure | 125.7575 | 7.5389 | 86850000 | 86850000 | 2023 | R.A. PAHATI CONST. & SUPPLY, INC. | 9715 | 2022 | 2023-01-22 | 02/22/2022 | 0 | 0 | 2023-01-21 |  | 1
2022 | Region XI | DAVAO DEL SUR | HAGONOY (DAVAO DEL SUR) | P00630518MN | Construction of Revetment | 125.3461 | 6.7198 | 67550000 | 67550000 | 2023 | TKS BUILDERS & SUPPLIES / LEDCORE CONSTRUCTION AND DEVELOPMENT CORP, | 9716 | 2022 | 2023-04-01 | 02/18/2022 | 0 | 0 | 2023-03-31 |  | 1
2022 | Region VIII | SAMAR (WESTERN SAMAR) | BASEY (SAMAR (WESTERN SAMAR)) | P00632045VS | Construction of Flood Mitigation Structure | 125.1519 | 11.2717 | 25479999.46 | 25739029.39 | 2022 | EMB CONSTRUCTION AND SUPPLY | 9717 | 2022 | 2022-08-08 | 03/22/2022 | 0 | 259029.93 | 2022-11-24 | 108
2023 | Region XIII | SURIGAO DEL SUR | LIANGA (SURIGAO DEL SUR) | P00734004MN | Construction of Dike | 126.0898 | 8.642 | 96500000 | 96499679.89 | 2024 | CM TAN CONSTRUCTION | 9718 | 2023 | 2024-02-28 | 05/10/2023 | 320.11 | 0 | 2024-02-28 | 0
2022 | Region XI | DAVAO DEL SUR | DAVAO CITY (DAVAO DEL SUR) | P00631098MN | Construction of Drainage Structure | 125.6208 | 7.0903 | 6930000 | 6930000 | 2023 | HEXAMINDZ CORPORATION (FORMERLY:KILUSANG MAGKAIBIG | 9719 | 2022 | 2023-09-01 | 03/31/2022 | 0 | 0 | 2023-06-30 |  | 63
2024 | Region XI | DAVAO ORIENTAL | CARAGA (DAVAO ORIENTAL) | P00820076MN | Construction of Flood Mitigation Structure | 126.5069 | 7.3453 | 48250000 | 48247726.58 | 2024 | DBR CONSTRUCTION CORPORATION (FORMERLY: D.B. RAVELO CONSTRUCTION & SUPPLY) | 9720 | 2024 | 2024-11-15 | 04/08/2024 | 2273.42 | 0 | 2024-12-08 | 23
2022 | Region XI | DAVAO DEL NORTE | SANTO TOMAS (DAVAO DEL NORTE) | P00634999MN | Construction of Drainage Structure | 125.6218 | 7.5276 | 4950000 | 4919156.22 | 2023 | AB APONESTO CONSTRUCTION PARTS AND SUPPLY, INC. | 9721 | 2022 | 2023-01-15 | 06/02/2022 | 30843.78 | 0 | 2022-12-25 |  | 21
2023 | Region XI | DAVAO DEL SUR | CITY OF DIGOS (CAPITAL) (DAVAO DEL SUR) | P00721501MN | Construction of Revetment | 125.3475 | 6.7635 | 39200000 | 39200000 | 2023 | TKS BUILDERS & SUPPLIES | 9722 | 2023 | 2023-10-05 | 02/17/2023 | 0 | 0 | 2023-10-04 |  | 1
2023 | Region X | BUKIDNON | CITY OF MALAYBALAY (CAPITAL) (BUKIDNON) | P00721535MN | Construction of Flood Mitigation Structure | 125.1536 | 8.1927 | 96500000 | 96499999.3 | 2023 | RITCHE-NATHALIE BUILDERS & GENERAL MERCHANDISE | 9723 | 2023 | 2023-12-17 | 03/13/2023 | 0.7 | 0 | 2023-12-16 |  | 1
2023 | Region XI | DAVAO ORIENTAL | TARRAGONA (DAVAO ORIENTAL) | P00734404MN | Construction of Flood Mitigation Structure | 126.5081 | 7.5732 | 4950000 | 4949987.48 | 2023 | JAI BUILDERS CORPORATION ( FORMERLY JAI BUILDERS AND SUPPLY) | 9724 | 2023 | 2023-07-14 | 04/04/2023 | 12.52 | 0 | 2023-08-19 | 36
2021 | Region XIII | AGUSAN DEL SUR |  | P00550439MN | Construction of Flood Mitigation Structure | 125.761 | 8.4629 | 139925000 | 139924981.4 | 2022 | CM TAN CONSTRUCTION | 9725 | 2021 | 2022-12-15 | 04/20/2022 | 18.6 | 0 | 2022-12-14 |  | 1
2021 | Region XIII | SURIGAO DEL SUR |  | P00550524MN | Construction of Flood Mitigation Structure | 126.09 | 8.642 | 96500000 | 81722678.26 | 2023 | ARQ BUILDERS | 9726 | 2021 | 2023-01-09 | 01/18/2022 | 14777321.74 | 0 | 2022-12-29 |  | 11
2022 | Region XI | DAVAO DEL SUR | DAVAO CITY (DAVAO DEL SUR) | P00633928MN | Rehabilitation / Major Repair of Drainage Structure | 125.6222 | 7.0718 | 6860000 | 6860000 | 2023 | BQPC CORPORATION | 9727 | 2022 | 2023-03-25 | 04/13/2022 | 0 | 0 | 2023-03-24 |  | 1
2024 | Region VIII | EASTERN SAMAR | DOLORES (EASTERN SAMAR) | P00820144VS | Rehabilitation / Major Repair of Flood Control Structure | 125.348 | 12.0373 | 49545995 | 49545983.48 | 2024 | PABLO S. LABASBAS CONSTRUCTION CORPORATION (FORMERLY: PABLOS. LABASBAS CONSTRUCTION CORPORATION) / JAMA88 BUILDERS INC. | 9728 | 2024 | 2024-11-02 | 03/18/2024 | 11.52 | 0 | 2024-11-01 |  | 1
2022 | Region XI | DAVAO DEL SUR | DAVAO CITY (DAVAO DEL SUR) | P00620167MN | Rehabilitation / Major Repair of Drainage Structure | 125.6229 | 7.114 | 29400000 | 29400000 | 2023 | JD SOMOZA BUILDERS | 9729 | 2022 | 2023-04-16 | 04/13/2022 | 0 | 0 | 2023-04-15 |  | 1
2022 | Region XIII | AGUSAN DEL SUR | CITY OF BAYUGAN (AGUSAN DEL SUR) | P00620298MN | Construction of Flood Mitigation Structure | 125.771 | 8.7122 | 45080000 | 45079998.73 | 2023 | ARQ BUILDERS | 9730 | 2022 | 2023-03-24 | 06/13/2022 | 1.27 | 0 | 2023-03-23 |  | 1
2024 | Region X | BUKIDNON | CITY OF MALAYBALAY (CAPITAL) (BUKIDNON) | P00820034MN | Construction of Flood Mitigation Structure | 125.154 | 8.0377 | 96500000 | 96500000 | 2024 | ROSBILL CONSTRUCTION AND SUPPLY | 9731 | 2024 | 2024-12-16 | 01/31/2024 | 0 | 0 | 2025-01-01 | 16
2022 | Region XI | DAVAO ORIENTAL | CARAGA (DAVAO ORIENTAL) | P00620379MN | Construction of Flood Mitigation Structure | 126.5142 | 7.4165 | 96500000 | 96499999.58 | 2022 | ECBJ EASTCOAST CONSTRUCTION / MAC BUILDERS CORP. (FORMERLY: MAC BUILDERS DEVELOPMENT CORPORATION) | 9732 | 2022 | 2022-10-10 | 03/28/2022 | 0.42 | 0 | 2023-03-07 | 148
2024 | Region XIII | AGUSAN DEL SUR | TRENTO (AGUSAN DEL SUR) | P00820366MN | Construction of Flood Mitigation Structure | 126.0914 | 8.0216 | 77200000 | 77199995.82 | 2024 | ROCK DIWATA BUILDERS, INC. | 9733 | 2024 | 2024-09-30 | 02/16/2024 | 4.18 | 0 | 2024-11-30 | 61
2024 | Region X | BUKIDNON | SAN FERNANDO (BUKIDNON) | P00835774MN | Construction of Flood Mitigation Structure | 125.3514 | 7.8961 | 112905000 | 112905000 | 2024 | GENESIS88 CONSTRUCTION INC. | 9734 | 2024 | 2024-11-12 | 03/21/2024 | 0 | 0 | 2024-12-24 | 42
2024 | Region XIII | AGUSAN DEL NORTE | REMEDIOS T. ROMUALDEZ (AGUSAN DEL NORTE) | P00820117MN | Construction of Flood Mitigation Structure | 125.6248 | 9.0505 | 72375000 | 72174973.97 | 2024 | ARQ BUILDERS | 9735 | 2024 | 2024-11-14 | 02/12/2024 | 200026.03 | 0 | 2024-11-21 | 7
2022 | Region XII | SOUTH COTABATO | GENERAL SANTOS CITY (DADIANGAS) (SOUTH COTABATO) | P00634144MN | Construction of Drainage Structure | 125.1542 | 6.1005 | 4950000 | 4914808.13 | 2022 | HANNA VIA CONSTRUCTION, INC. (FORMERLY:HANNA VIA DESIGN & CONSTRUCTION) | 9736 | 2022 | 2022-07-17 | 03/29/2022 | 35191.87 | 0 | 2022-07-10 |  | 7
2022 | Region XI | DAVAO ORIENTAL | CARAGA (DAVAO ORIENTAL) | P00630517MN | Construction of Flood Mitigation Structure | 126.5204 | 7.4164 | 67550000 | 67549604.08 | 2022 | KODUS PEERS CONSTRUCTION CORPORATION / O. G. SANTOS CONSTRUCTION | 9737 | 2022 | 2022-12-21 | 02/21/2022 | 395.92 | 0 | 2022-12-25 | 4
2022 | Region XI | DAVAO DE ORO | COMPOSTELA (DAVAO DE ORO) | P00631102MN | Rehabilitation / Major Repair of Flood Control Structure | 126.0924 | 7.6723 | 48999445.2 | 48999429.74 | 2023 | AB APONESTO CONSTRUCTION PARTS AND SUPPLY, INC. | 9738 | 2022 | 2023-05-23 | 03/18/2022 | 15.46 | 0 | 2023-05-22 |  | 1
2023 | Region VIII | SAMAR (WESTERN SAMAR) | BASEY (SAMAR (WESTERN SAMAR)) | P00721589VS | Construction of Flood Mitigation Structure | 125.1558 | 11.3393 | 110974982.1 | 110974928.2 | 2023 | B. VICENCIO BUILDERS (BVB), INC. (FORMERLY:B. VICENCIO CONSTRUCTION) / ALPHAHAWK CONSTRUCTION CORP. | 9739 | 2023 | 2023-05-10 | 02/13/2023 | 53.9 | 0 | 2024-01-27 | 262
2021 | Region XI | DAVAO DEL SUR |  | P00522194MN | Construction of Flood Mitigation Structure | 125.6249 | 7.0736 | 39200000 | 39200000 | 2022 | GENESIS88 CONSTRUCTION INC. | 9740 | 2021 | 2022-09-07 | 11/21/2021 | 0 | 0 | 2022-09-06 |  | 1
2022 | Region XI | DAVAO ORIENTAL | MANAY (DAVAO ORIENTAL) | P00620377MN | Construction of Flood Mitigation Structure | 126.524 | 7.1729 | 96500000 | 96497439.49 | 2022 | MAC BUILDERS CORP. (FORMERLY: MAC BUILDERS DEVELOPMENT CORPORATION) | 9741 | 2022 | 2022-11-25 | 03/28/2022 | 2560.51 | 0 | 2023-03-09 | 104
2024 | Region XIII | AGUSAN DEL NORTE | NASIPIT (AGUSAN DEL NORTE) | P00836195MN | Construction of Flood Mitigation Structure | 125.3543 | 8.9294 | 19600000 | 19799998.83 | 2024 | ERRA CONSTRUCTION AND DEVELOPMENT INC. (FORMERLY ERRA CONSTRUCTION) | 9742 | 2024 | 2024-09-03 | 06/06/2024 | 0 | 199998.83 | 2024-09-02 |  | 1
2022 | Region XIII | AGUSAN DEL SUR | LA PAZ (AGUSAN DEL SUR) | P00634148MN | Construction of Flood Mitigation Structure | 125.779 | 8.2396 | 49500000 | 49499973.79 | 2023 | VICENTE T. LAO CONSTRUCTION | 9743 | 2022 | 2023-06-05 | 06/30/2022 | 26.21 | 0 | 2023-06-04 |  | 1
2022 | Region XI | DAVAO DE ORO | NEW BATAAN (DAVAO DE ORO) | P00620225MN | Construction of Revetment | 126.0933 | 7.6044 | 86849998.54 | 86849711.45 | 2022 | AB APONESTO CONSTRUCTION PARTS AND SUPPLY, INC. | 9744 | 2022 | 2022-12-30 | 04/04/2022 | 287.09 | 0 | 2022-12-29 |  | 1
2022 | Region VIII | SAMAR (WESTERN SAMAR) | BASEY (SAMAR (WESTERN SAMAR)) | P00620216VS | Construction of Flood Mitigation Structure | 125.1584 | 11.3426 | 49000000.98 | 48997687.3 | 2022 | JFR CONSTRUCTION INC. (FORMERLY:JFR CONSTRUCTION) | 9745 | 2022 | 2022-09-18 | 02/14/2022 | 2313.68 | 0 | 2022-12-03 | 76
2022 | Region VIII | EASTERN SAMAR | ORAS (EASTERN SAMAR) | P00620323VS | Construction of Flood Mitigation Structure | 125.3548 | 12.2174 | 48984764.58 | 48999967.04 | 2022 | 888 ACY ENTERPRISES | 9746 | 2022 | 2022-09-13 | 02/13/2022 | 0 | 15202.46 | 2022-09-12 |  | 1
2024 | Region XI | DAVAO DEL NORTE | CITY OF TAGUM (CAPITAL) (DAVAO DEL NORTE) | P00836188MN | Construction of Drainage Structure | 125.779 | 7.407 | 4950000 | 4949970.75 | 2024 | CARESYSTEM TECHNOLOGY SOLUTION CO., INC. | 9747 | 2024 | 2024-09-05 | 05/14/2024 | 29.25 | 0 | 2024-09-05 | 0
2022 | Region VIII | SOUTHERN LEYTE | HINUNANGAN (SOUTHERN LEYTE) | P00620227VS | Construction of Flood Mitigation Structure | 125.1589 | 10.5296 | 49000000 | 49000000 | 2023 | ST. GERRARD CONSTRUCTION GEN. CONTRACTOR & DEVELOPMENT CORP. (FORMERLY:ST. GERRARD CONSTRUCTION) | 9748 | 2022 | 2023-01-09 | 02/16/2022 | 0 | 0 | 2023-01-08 |  | 1
2023 | Region XIII | SURIGAO DEL NORTE | DAPA (SURIGAO DEL NORTE) | P00732466MN | Construction of Slope Protection Structure | 126.0938 | 9.76 | 59400000 | 58899989.45 | 2023 | BOOMETRIX DEVELOPMENT CORP. | 9749 | 2023 | 2023-10-01 | 05/10/2023 | 500010.55 | 0 | 2023-09-30 |  | 1
2022 | Region XI | DAVAO ORIENTAL | MANAY (DAVAO ORIENTAL) | P00630501MN | Construction of Flood Mitigation Structure | 126.5351 | 7.1905 | 67550000 | 67549370.29 | 2022 | MITZ CONSTRUCTION AND SUPPLY / O. G. SANTOS CONSTRUCTION | 9750 | 2022 | 2022-12-02 | 02/21/2022 | 629.71 | 0 | 2023-01-07 | 36
2022 | Region XIII | SURIGAO DEL NORTE | GENERAL LUNA (SURIGAO DEL NORTE) | P00634126MN | Construction of Slope Protection Structure | 126.0994 | 9.7667 | 89100000 | 72789588.85 | 2022 | BOOMETRIX DEVELOPMENT CORP. | 9751 | 2022 | 2022-12-15 | 07/28/2022 | 16310411.15 | 0 | 2023-01-22 | 38
2022 | Region VIII | SOUTHERN LEYTE | SILAGO (SOUTHERN LEYTE) | P00620231VS | Construction of Flood Mitigation Structure | 125.1593 | 10.5266 | 49000000 | 48994280.63 | 2022 | ST. MATTHEW GEN. CONTRACTOR & DEVELOPMENT CORP. | 9752 | 2022 | 2022-10-13 | 02/16/2022 | 5719.37 | 0 | 2022-10-12 |  | 1
2021 | Region XI | DAVAO DEL SUR |  | P00522078MN | Construction of Flood Mitigation Facility | 125.6249 | 7.0736 | 96500000 | 96500000 | 2023 | RELY CONSTRUCTION & SUPPLY INC.(FORMERLY: RELY CONSTRUCTION AND SUPPLY) | 9753 | 2021 | 2023-11-28 | 06/05/2022 | 0 | 0 | 2023-11-27 |  | 1
2023 | Region XI | DAVAO DEL SUR | SULOP (DAVAO DEL SUR) | P00721576MN | Construction of Flood Mitigation Structure | 125.357 | 6.5833 | 90710000 | 90243232.16 | 2024 | J.H.R. ENTERPRISES | 9754 | 2023 | 2024-06-08 | 08/15/2023 | 466767.84 | 0 | 2024-06-07 |  | 1
2024 | Region XI | DAVAO ORIENTAL | MANAY (DAVAO ORIENTAL) | P00821194MN | Construction of Flood Mitigation Structure | 126.5382 | 7.2097 | 57900000 | 57898426.51 | 2024 | AGONG BUILDERS AND CONSTRUCTION SUPPLY, INC. | 9755 | 2024 | 2024-11-04 | 03/27/2024 | 1573.49 | 0 | 2024-11-03 |  | 1
2022 | Region XI | DAVAO DEL NORTE | CITY OF TAGUM (CAPITAL) (DAVAO DEL NORTE) | P00620084MN | Rehabilitation / Major Repair of Flood Control Structure | 125.7812 | 7.3957 | 56900000 | 56899821.8 | 2022 | LICSAL CONSTRUCTION CORPORATION | 9756 | 2022 | 2022-12-26 | 03/01/2022 | 178.2 | 0 | 2022-12-25 |  | 1
2022 | Region XI | DAVAO ORIENTAL | GOVERNOR GENEROSO (DAVAO ORIENTAL) | P00620181MN | Construction of Flood Mitigation Structure | 126.0996 | 6.6276 | 49000000 | 49000000 | 2022 | MAER SUMMIT KONSTRUKT CO. | 9757 | 2022 | 2022-10-10 | 02/21/2022 | 0 | 0 | 2022-10-09 |  | 1
2024 | Region XII | SOUTH COTABATO | GENERAL SANTOS CITY (DADIANGAS) (SOUTH COTABATO) | P00836193MN | Construction of Flood Mitigation Structure | 125.1614 | 6.1101 | 24750000 | 24748196.43 | 2025 | PLUS CONSTRUCTION INDUSTRIES CORP. | 9758 | 2024 | 2025-02-04 | 08/14/2024 | 1803.57 | 0 | 2025-02-03 |  | 1
2021 | Region XI | DAVAO DEL SUR |  | P00550456MN | Rehabilitation / Major Repair of Flood Control Structure | 125.362 | 6.7607 | 57900000 | 57900000 | 2022 | THREE W BUILDERS, INC. | 9759 | 2021 | 2022-12-19 | 03/24/2022 | 0 | 0 | 2022-12-18 |  | 1
2023 | Region XI | DAVAO DE ORO | COMPOSTELA (DAVAO DE ORO) | P00721500MN | Construction of Revetment | 126.0998 | 7.6557 | 31066000 | 31065458.31 | 2023 | DAVAO CONCRETE PRODUCTS CONSTRUCTION AND TRADING CORPORATION (FORMERLY: DAVAO CONCRETE PRODUCTS) | 9760 | 2023 | 2023-08-20 | 02/13/2023 | 541.69 | 0 | 2023-08-19 |  | 1
2022 | Region XIII | AGUSAN DEL SUR | CITY OF BAYUGAN (AGUSAN DEL SUR) | P00620297MN | Construction of Flood Mitigation Structure | 125.7955 | 8.7114 | 44206820 | 44206819.84 | 2023 | MADYAW CONSTRUCTION & DEV. CORPORATION | 9761 | 2022 | 2023-03-03 | 05/24/2022 | 0.16 | 0 | 2023-03-03 | 0
2023 | Region XI | DAVAO ORIENTAL | GOVERNOR GENEROSO (DAVAO ORIENTAL) | P00721619MN | Construction of Flood Mitigation Structure | 126.106 | 6.6328 | 14700000 | 14394496.26 | 2023 | MAER SUMMIT KONSTRUKT CO. | 9762 | 2023 | 2023-08-15 | 03/27/2023 | 305503.74 | 0 | 2023-09-12 | 28
2022 | Region XI | DAVAO ORIENTAL | MANAY (DAVAO ORIENTAL) | P00620075MN | Construction of Revetment | 126.5384 | 7.2114 | 63333915 | 63332916.37 | 2023 | MAVERICK BUILDERS INCORPORATED (FORMERLY MAVERICK | 9763 | 2022 | 2023-03-14 | 02/21/2022 | 998.63 | 0 | 2023-03-18 | 4
2024 | Region X | MISAMIS ORIENTAL | GINGOOG CITY (MISAMIS ORIENTAL) | P00836151MN | Construction of Flood Mitigation Structure | 125.1631 | 8.8433 | 99000000 | 98995000 | 2024 | ROAD EDGE TRADING & DEVELOPMENT SERVICES / EQUALYZ TRADING | 9764 | 2024 | 2024-10-31 | 06/10/2024 | 5000 | 0 | 2025-04-19 | 170
2022 | Region XI | DAVAO DEL SUR | DAVAO CITY (DAVAO DEL SUR) | P00620165MN | Construction of Revetment | 125.6255 | 7.0732 | 39200000 | 39200000 | 2022 | GENESIS88 CONSTRUCTION INC. | 9765 | 2022 | 2022-09-24 | 03/23/2022 | 0 | 0 | 2022-09-23 |  | 1
2023 | Region X | BUKIDNON | SAN FERNANDO (BUKIDNON) | P00721262MN | Construction of Flood Mitigation Structure | 125.366 | 7.8697 | 57899929.25 | 56560489.27 | 2024 | M. MONTESCLAROS ENTERPRISES, INC. | 9766 | 2023 | 2024-05-01 | 02/13/2023 | 1339439.98 | 0 | 2023-11-04 |  | 179
2022 | Region XIII | SURIGAO DEL NORTE | BACUAG (SURIGAO DEL NORTE) | P00630646MN | Construction of Flood Mitigation Structure | 125.628 | 9.5691 | 49000000 | 48999993.79 | 2022 | JMT CONSTRUCTION | 9767 | 2022 | 2022-11-21 | 03/11/2022 | 6.21 | 0 | 2022-11-20 |  | 1
2024 | Region XI | DAVAO ORIENTAL | BAGANGA (DAVAO ORIENTAL) | P00820177MN | Construction of Flood Mitigation Structure | 126.5399 | 7.6418 | 49000000 | 48997746.86 | 2024 | LICSAL CONSTRUCTION CORPORATION | 9768 | 2024 | 2024-10-04 | 02/12/2024 | 2253.14 | 0 | 2024-10-03 |  | 1
2023 | Region XI | DAVAO DE ORO | COMPOSTELA (DAVAO DE ORO) | P00721569MN | Construction of Revetment | 126.1087 | 7.6709 | 96500000 | 96499753.59 | 2023 | AB APONESTO CONSTRUCTION PARTS AND SUPPLY, INC. | 9769 | 2023 | 2023-12-10 | 03/24/2023 | 246.41 | 0 | 2024-01-26 | 47
2024 | Region XI | DAVAO DEL NORTE | CITY OF TAGUM (CAPITAL) (DAVAO DEL NORTE) | P00836189MN | Construction of Drainage Structure | 125.7999 | 7.4005 | 4950000 | 4949999.92 | 2024 | RUBIKS CONSTRUCTION CORPORATION | 9770 | 2024 | 2024-08-26 | 04/02/2024 | 0.08 | 0 | 2024-08-26 | 0
2022 | Region X | BUKIDNON | SAN FERNANDO (BUKIDNON) | P00620115MN | Construction of Flood Mitigation Structure | 125.367 | 7.8716 | 49000000 | 48999992 | 2023 | M. MONTESCLAROS ENTERPRISES, INC. | 9771 | 2022 | 2023-09-03 | 01/28/2022 | 8 | 0 | 2023-09-02 |  | 1
2022 | Region XII | SOUTH COTABATO | GENERAL SANTOS CITY (DADIANGAS) (SOUTH COTABATO) | P00634143MN | Construction of Drainage Structure | 125.1642 | 6.1136 | 7920000 | 7210020.33 | 2022 | CROSMAK CONSTRUCTION WORKS INCORPORATED | 9772 | 2022 | 2022-07-20 | 03/29/2022 | 709979.67 | 0 | 2022-07-19 |  | 1
2022 | Region XI | DAVAO DEL NORTE | CITY OF TAGUM (CAPITAL) (DAVAO DEL NORTE) | P00632610MN | Construction of Drainage Structure | 125.8151 | 7.4175 | 4950000 | 4949815.11 | 2022 | RUPLINO SEISMUNDO CONSTRUCTION CORPORATION (FORMERLY: R.R. SEISMUNDO CONSTRUCTION & SUPPLY) | 9773 | 2022 | 2022-09-11 | 04/07/2022 | 184.89 | 0 | 2022-09-10 |  | 1
2024 | Region X | BUKIDNON | SAN FERNANDO (BUKIDNON) | P00820043MN | Construction of Flood Mitigation Structure | 125.3703 | 7.8606 | 144750000 | 144750000 | 2025 | JT GAMOLO CONSTRUCTION, INCORPORATION (FORMERLY:J.T. GAMOLO CONSTRUCTION) | 9774 | 2024 | 2025-03-25 | 01/31/2024 | 0 | 0 | 2025-03-24 |  | 1
2022 | Region XI | DAVAO ORIENTAL | MANAY (DAVAO ORIENTAL) | P00620173MN | Construction of Revetment | 126.5403 | 7.232 | 49000000 | 48999024.42 | 2022 | MITZ CONSTRUCTION AND SUPPLY | 9775 | 2022 | 2022-09-28 | 02/08/2022 | 975.58 | 0 | 2022-09-27 |  | 1
2023 | Region XIII | SURIGAO DEL SUR | LANUZA (SURIGAO DEL SUR) | P00734008MN | Construction of Slope Protection Structure | 126.1119 | 9.2536 | 96500000 | 95527824.85 | 2024 | LCTING CONSTRUCTION AND DEVELOPMENT CORPORATION (FORMERLY: L.C. TING CONSTRUCTION) | 9776 | 2023 | 2024-02-22 | 05/18/2023 | 972175.15 | 0 | 2024-02-21 |  | 1
2024 | Region XII | COTABATO (NORTH COTABATO) | MAKILALA (COTABATO (NORTH COTABATO)) | P00820190MN | Construction of Dike | 125.166 | 6.9101 | 49000000 | 48755000 | 2024 | LLABAN CONSTRUCTION & SUPPLY (FORMERLY: LLABAN CON | 9777 | 2024 | 2024-12-04 | 02/20/2024 | 245000 | 0 | 2024-12-03 |  | 1
2022 | Region XI | DAVAO ORIENTAL | MANAY (DAVAO ORIENTAL) | P00620378MN | Construction of Flood Mitigation Structure | 126.5424 | 7.2108 | 96500000 | 96496047.93 | 2022 | MAC BUILDERS CORP. (FORMERLY: MAC BUILDERS DEVELOPMENT CORPORATION) | 9778 | 2022 | 2022-12-15 | 03/28/2022 | 3952.07 | 0 | 2023-03-01 | 76
2023 | Region XIII | AGUSAN DEL NORTE | TUBAY (AGUSAN DEL NORTE) | P00721625MN | Construction of Slope Protection Structure | 125.6305 | 9.1018 | 49000000 | 48999995.59 | 2024 | ARQ BUILDERS | 9779 | 2023 | 2024-04-30 | 09/13/2023 | 4.41 | 0 | 2024-05-08 | 8
2023 | Region XII | SARANGANI | ALABEL (CAPITAL) (SARANGANI) | P00734379MN | Construction of Flood Mitigation Structure | 125.3748 | 6.0832 | 99000000 | 98981162.22 | 2024 | VICENTE T. LAO CONSTRUCTION | 9780 | 2023 | 2024-06-03 | 05/02/2023 | 18837.78 | 0 | 2024-05-11 |  | 23
2024 | Region XI | DAVAO ORIENTAL | CARAGA (DAVAO ORIENTAL) | P00833297MN | Construction of Revetment | 126.5439 | 7.3242 | 48250000 | 48249965.4 | 2024 | ECBJ EASTCOAST CONSTRUCTION | 9781 | 2024 | 2024-08-16 | 04/22/2024 | 34.6 | 0 | 2024-12-22 | 128
2024 | Region XIII | AGUSAN DEL NORTE | CITY OF CABADBARAN (AGUSAN DEL NORTE) | P00820380MN | Construction of Flood Mitigation Structure | 125.6306 | 9.1017 | 72375000 | 72271912.08 | 2024 | DATREBIL CONSTRUCTION & SUPPLY | 9782 | 2024 | 2024-12-01 | 02/21/2024 | 103087.92 | 0 | 2024-11-30 |  | 1
2023 | Region X | BUKIDNON | SAN FERNANDO (BUKIDNON) | P00732051MN | Construction of Flood Mitigation Structure | 125.3776 | 7.8382 | 96500000 | 96500000 | 2023 | ROSBILL CONSTRUCTION AND SUPPLY | 9783 | 2023 | 2023-11-21 | 04/19/2023 | 0 | 0 | 2024-01-27 | 67
2023 | Region XI | DAVAO DE ORO | NEW BATAAN (DAVAO DE ORO) | P00721564MN | Construction of Revetment | 126.1167 | 7.5568 | 96500000 | 96500000 | 2024 | ROSBILL CONSTRUCTION AND SUPPLY | 9784 | 2023 | 2024-03-03 | 05/26/2023 | 0 | 0 | 2024-03-02 |  | 1
2022 | Region XI | DAVAO DEL NORTE | CITY OF TAGUM (CAPITAL) (DAVAO DEL NORTE) | P00620222MN | Construction of Flood Mitigation Structure | 125.8278 | 7.4342 | 95500000 | 95499998.73 | 2022 | GP & H CONSTRUCTION INCORPORATED (FORMERLY: GP & H CONSTRUCTION & SUPPLY) | 9785 | 2022 | 2022-12-27 | 02/24/2022 | 1.27 | 0 | 2022-12-27 | 0
2024 | Region XII | COTABATO (NORTH COTABATO) | MAKILALA (COTABATO (NORTH COTABATO)) | P00820191MN | Construction of Dike | 125.1675 | 6.9132 | 49000000 | 48755000 | 2024 | LLABAN CONSTRUCTION & SUPPLY (FORMERLY: LLABAN CON | 9786 | 2024 | 2024-12-03 | 02/20/2024 | 245000 | 0 | 2024-12-03 | 0
2022 | Region XI | DAVAO DE ORO | MACO (DAVAO DE ORO) | P00630763MN | Construction of Revetment | 125.828 | 7.4357 | 67549978.79 | 67549978.79 | 2023 | C'ZARLES CONSTRUCTION & SUPPLY | 9787 | 2022 | 2023-03-29 | 03/18/2022 | 0 | 0 | 2023-03-28 |  | 1
2023 | Region XII | SOUTH COTABATO | GENERAL SANTOS CITY (DADIANGAS) (SOUTH COTABATO) | P00734411MN | Construction of Drainage Structure | 125.1689 | 6.117 | 4950000 | 4949311.86 | 2023 | GRECO CONSTRUCTION AND SUPPLY | 9788 | 2023 | 2023-07-10 | 04/11/2023 | 688.14 | 0 | 2023-07-09 |  | 1
2023 | Region XI | DAVAO ORIENTAL | CARAGA (DAVAO ORIENTAL) | P00721427MN | Construction of Flood Mitigation Structure | 126.5476 | 7.321 | 96500000 | 96499134.78 | 2023 | MAVERICK BUILDERS INCORPORATED (FORMERLY MAVERICK | 9789 | 2023 | 2023-09-11 | 03/28/2023 | 865.22 | 0 | 2024-02-29 | 171
2023 | Region XI | DAVAO OCCIDENTAL | MALITA (DAVAO OCCIDENTAL) | P00732490MN | Construction of Revetment | 125.6323 | 6.337 | 19800000 | 19789822.44 | 2023 | HVC SAGITTARIUS COMMERCIAL & CONSTRUCTION | 9790 | 2023 | 2023-07-03 | 02/09/2023 | 10177.56 | 0 | 2023-07-02 |  | 1
2021 | Region XI | DAVAO DEL SUR |  | P00550457MN | Rehabilitation / Major Repair of Flood Control Structure | 125.3793 | 6.743 | 48250000 | 48250000 | 2022 | VICENTE T. LAO CONSTRUCTION | 9791 | 2021 | 2022-09-19 | 03/24/2022 | 0 | 0 | 2022-09-18 |  | 1
2022 | Region XI | DAVAO DEL SUR | DAVAO CITY (DAVAO DEL SUR) | P00630599MN | Construction of Drainage Structure | 125.6369 | 7.0881 | 9800000 | 9800000 | 2023 | ROSBILL CONSTRUCTION AND SUPPLY | 9792 | 2022 | 2023-07-02 | 04/06/2022 | 0 | 0 | 2023-07-01 |  | 1
2023 | Region XI | DAVAO DE ORO | COMPOSTELA (DAVAO DE ORO) | P00721572MN | Construction of Revetment | 126.1245 | 7.6408 | 96500000 | 96499980.76 | 2024 | METRO GEAR CONSTRUCTION CORP. / REPLICON CONSTRUCTION CORPORATION | 9793 | 2023 | 2024-03-22 | 03/28/2023 | 19.24 | 0 | 2024-03-28 | 6
2022 | Region XI | DAVAO ORIENTAL | BAGANGA (DAVAO ORIENTAL) | P00620172MN | Construction of Flood Mitigation Structure | 126.5481 | 7.6754 | 29400000 | 29399619.35 | 2023 | JAI BUILDERS CORPORATION ( FORMERLY JAI BUILDERS AND SUPPLY) | 9794 | 2022 | 2023-01-03 | 02/21/2022 | 380.65 | 0 | 2022-12-13 |  | 21
2021 | Region XI | DAVAO DEL NORTE |  | P00550505MN | Construction of Drainage Structure | 125.8317 | 7.4594 | 9900000 | 9900000 | 2022 | ROSBILL CONSTRUCTION AND SUPPLY | 9795 | 2021 | 2022-12-28 | 08/18/2022 | 0 | 0 | 2023-01-16 | 19
2023 | Region XII | SARANGANI | ALABEL (CAPITAL) (SARANGANI) | P00733999MN | Construction of Flood Mitigation Structure | 125.3801 | 6.0925 | 77200000 | 77199980.12 | 2024 | JDRC CONSTRUCTION & SUPPLIES, CORP. | 9796 | 2023 | 2024-03-12 | 05/02/2023 | 19.88 | 0 | 2024-03-25 | 13
2020 | Region XI | DAVAO DEL SUR |  | P00420399MN | Construction of Flood Mitigation Structure | 125.6385 | 7.1263 | 74570375 | 74570375 | 2022 | ACD ASTROBUILT CONSTRUCTION & DEVELOPMENT, INC. (FORMERLY:ASTROBUILT CONSTRUCTION & DEVELOPMENT) / ABU CONSTRUCTION | 9797 | 2020 | 2022-12-07 | 12/17/2020 | 0 | 0 | 2022-12-06 |  | 1
2024 | Region XII | SOUTH COTABATO | GENERAL SANTOS CITY (DADIANGAS) (SOUTH COTABATO) | P00833600MN | Construction of Drainage Structure | 125.1696 | 6.1183 | 4950000 | 4948404.37 | 2024 | A.L. ACHARON CONSTRUCTION AND SUPPLY | 9798 | 2024 | 2024-07-10 | 02/23/2024 | 1595.63 | 0 | 2024-07-09 |  | 1
2023 | Region XI | DAVAO ORIENTAL | BAGANGA (DAVAO ORIENTAL) | P00721443MN | Construction of Flood Mitigation Structure | 126.5492 | 7.5749 | 96500000 | 96499472.49 | 2023 | GREAT PACIFIC BUILDERS AND GEN. CONTRACTOR INC. | 9799 | 2023 | 2023-07-24 | 03/03/2023 | 527.51 | 0 | 2023-11-19 | 118
2023 | Region XII | SARANGANI | MALAPATAN (SARANGANI) | P00721306MN | Construction of Flood Mitigation Structure | 125.3808 | 6.0558 | 96500000 | 96480601.49 | 2024 | J.G. ORANZA CONSTRUCTION | 9800 | 2023 | 2024-04-15 | 08/30/2023 | 19398.51 | 0 | 2024-06-19 | 65
2021 | Region XI | DAVAO DEL SUR |  | P00420399MN | Construction of Flood Mitigation Structure | 125.6385 | 7.1263 | 74570375 | 74570375 | 2022 | ACD ASTROBUILT CONSTRUCTION & DEVELOPMENT, INC. (FORMERLY:ASTROBUILT CONSTRUCTION & DEVELOPMENT) / ABU CONSTRUCTION | 9801 | 2021 | 2022-12-07 | 12/17/2020 | 0 | 0 | 2022-12-06 |  | 1
2024 | Region XII | COTABATO (NORTH COTABATO) | MAKILALA (COTABATO (NORTH COTABATO)) | P00820192MN | Construction of Dike | 125.1706 | 6.9168 | 49000000 | 48262644.03 | 2025 | AGONG BUILDERS AND CONSTRUCTION SUPPLY, INC. / JARGON CONSTRUCTION & SUPPLY | 9802 | 2024 | 2025-01-24 | 04/17/2024 | 737355.97 | 0 | 2025-01-29 | 5
2024 | Region X | BUKIDNON | SAN FERNANDO (BUKIDNON) | P00820038MN | Construction of Flood Mitigation Structure | 125.385 | 7.828 | 96500000 | 96500000 | 2025 | ROSBILL CONSTRUCTION AND SUPPLY | 9803 | 2024 | 2025-01-23 | 01/31/2024 | 0 | 0 | 2025-01-28 | 5
2022 | Region VIII | EASTERN SAMAR | ORAS (EASTERN SAMAR) | P00620179VS | Construction of Flood Mitigation Structure | 125.3854 | 12.2055 | 48984765.36 | 49000000 | 2022 | PABLO S. LABASBAS CONSTRUCTION CORPORATION (FORMERLY: PABLOS. LABASBAS CONSTRUCTION CORPORATION) | 9804 | 2022 | 2022-11-04 | 02/13/2022 | 0 | 15234.64 | 2022-11-03 |  | 1
2022 | Region VIII | SOUTHERN LEYTE | LIBAGON (SOUTHERN LEYTE) | P00620228VS | Construction of Flood Mitigation Structure | 125.1707 | 10.3631 | 19600000 | 19568359.5 | 2022 | JQD CONSTRUCTION & GENERAL SERVICES | 9805 | 2022 | 2022-11-19 | 02/10/2022 | 31640.5 | 0 | 2022-11-18 |  | 1
2023 | Region XI | DAVAO ORIENTAL | CARAGA (DAVAO ORIENTAL) | P00721442MN | Construction of Flood Mitigation Structure | 126.5508 | 7.3222 | 57900000 | 57896577.84 | 2023 | JHARKHA CONSTRUCTION AND SUPPLY | 9806 | 2023 | 2023-05-04 | 03/03/2023 | 3422.16 | 0 | 2023-12-10 | 220
2024 | Region XII | SOUTH COTABATO | GENERAL SANTOS CITY (DADIANGAS) (SOUTH COTABATO) | P00833599MN | Construction of Drainage Structure | 125.1733 | 6.1149 | 9900000 | 9899281.94 | 2024 | DRU CONSTRUCTION | 9807 | 2024 | 2024-06-21 | 02/23/2024 | 718.06 | 0 | 2024-06-20 |  | 1
2023 | Region XI | DAVAO ORIENTAL | BAGANGA (DAVAO ORIENTAL) | P00721441MN | Construction of Flood Mitigation Structure | 126.5518 | 7.5768 | 67550000 | 67549886.03 | 2023 | O. G. SANTOS CONSTRUCTION | 9808 | 2023 | 2023-06-20 | 03/03/2023 | 113.97 | 0 | 2023-11-10 | 143
2022 | Region XI | DAVAO DEL SUR | DAVAO CITY (DAVAO DEL SUR) | P00620168MN | Rehabilitation / Major Repair of Flood Control Structure | 125.6387 | 7.1099 | 45080000 | 43727225.07 | 2022 | LANDEVTECH CONSTRUCTION, INC. / RELY CONSTRUCTION & SUPPLY INC.(FORMERLY: RELY CONSTRUCTION AND SUPPLY) | 9809 | 2022 | 2022-10-09 | 02/23/2022 | 1352774.93 | 0 | 2022-10-08 |  | 1
2023 | Region XI | DAVAO DEL NORTE | CITY OF TAGUM (CAPITAL) (DAVAO DEL NORTE) | P00734373MN | Construction of Flood Mitigation Structure | 125.832 | 7.3672 | 148500000 | 148466210.5 | 2023 | ROSBILL CONSTRUCTION AND SUPPLY / NICOMAG UTILITY PROJECTS CONSTRUCTION | 9810 | 2023 | 2023-12-17 | 04/11/2023 | 33789.5 | 0 | 2024-02-27 | 72
2023 | Region XIII | AGUSAN DEL NORTE | REMEDIOS T. ROMUALDEZ (AGUSAN DEL NORTE) | P00721626MN | Construction of Flood Mitigation Structure | 125.6392 | 9.0468 | 24500000 | 24153330.25 | 2024 | ARQ BUILDERS | 9811 | 2023 | 2024-03-31 | 05/25/2023 | 346669.75 | 0 | 2024-04-10 | 10
2024 | Region XI | DAVAO DEL NORTE | CITY OF TAGUM (CAPITAL) (DAVAO DEL NORTE) | P00836190MN | Construction of Flood Mitigation Structure | 125.8343 | 7.3659 | 148500000 | 148499998.4 | 2024 | KANAWAY BUILDERS CORPORATION | 9812 | 2024 | 2024-12-04 | 04/02/2024 | 1.6 | 0 | 2025-02-14 | 72
2022 | Region XIII | AGUSAN DEL SUR | PROSPERIDAD (CAPITAL) (AGUSAN DEL SUR) | P00620356MN | Construction of Flood Mitigation Structure | 125.8387 | 8.6798 | 49000000 | 48999771.46 | 2023 | MADYAW CONSTRUCTION & DEV. CORPORATION | 9813 | 2022 | 2023-06-15 | 06/13/2022 | 228.54 | 0 | 2023-06-23 | 8
2022 | Region XIII | SURIGAO DEL NORTE | BACUAG (SURIGAO DEL NORTE) | P00630532MN | Construction of Flood Mitigation Structure | 125.6405 | 9.5783 | 72375000 | 71651428.31 | 2023 | JMT CONSTRUCTION | 9814 | 2022 | 2023-06-30 | 03/11/2022 | 723571.69 | 0 | 2023-07-08 | 8
2024 | Region XII | COTABATO (NORTH COTABATO) | MAKILALA (COTABATO (NORTH COTABATO)) | P00820188MN | Construction of Dike | 125.1745 | 6.9203 | 49000000 | 48753175.91 | 2024 | LLABAN CONSTRUCTION & SUPPLY (FORMERLY: LLABAN CON | 9815 | 2024 | 2024-12-02 | 02/20/2024 | 246824.09 | 0 | 2024-12-03 | 1
2022 | Region XI | DAVAO DE ORO | MABINI (DOÃ‘A ALICIA) (DAVAO DE ORO) | P00620081MN | Construction of Revetment | 125.8415 | 7.2845 | 67549912.57 | 67548568.84 | 2022 | GP & H CONSTRUCTION INCORPORATED (FORMERLY: GP & H CONSTRUCTION & SUPPLY) | 9816 | 2022 | 2022-12-10 | 04/04/2022 | 1343.73 | 0 | 2022-12-10 | 0
2023 | Region XI | DAVAO ORIENTAL | CATEEL (DAVAO ORIENTAL) | P00721285MN | Construction of Flood Mitigation Structure | 126.5518 | 7.5768 | 67550000 | 67548470.73 | 2023 | J.H.R. ENTERPRISES | 9817 | 2023 | 2023-10-10 | 05/16/2023 | 1529.27 | 0 | 2024-03-12 | 154
2022 | Region XIII | AGUSAN DEL SUR | ESPERANZA (AGUSAN DEL SUR) | P00620355MN | Construction of Flood Mitigation Structure | 125.6412 | 8.6655 | 49000000 | 48999983.23 | 2023 | GIOVANNI CONSTRUCTION | 9818 | 2022 | 2023-06-05 | 06/13/2022 | 16.77 | 0 | 2023-06-04 |  | 1
2022 | Region XI | DAVAO ORIENTAL | CARAGA (DAVAO ORIENTAL) | P00620221MN | Construction of Flood Mitigation Structure | 126.5526 | 7.3217 | 93000000 | 92989850.86 | 2023 | MAVERICK BUILDERS INCORPORATED (FORMERLY MAVERICK | 9819 | 2022 | 2023-01-24 | 02/21/2022 | 10149.14 | 0 | 2023-01-23 |  | 1
2022 | Region XIII | AGUSAN DEL SUR | PROSPERIDAD (CAPITAL) (AGUSAN DEL SUR) | P00620190MN | Construction of Flood Mitigation Structure | 125.8415 | 8.681 | 11760000 | 11759997.45 | 2023 | DAVE CONSTRUCTION | 9820 | 2022 | 2023-01-03 | 06/13/2022 | 2.55 | 0 | 2023-01-02 |  | 1
2024 | Region XII | COTABATO (NORTH COTABATO) | ARAKAN (COTABATO (NORTH COTABATO)) | P00820193MN | Construction of Dike | 125.1774 | 7.274 | 34300000 | 34299999.54 | 2024 | LLABAN CONSTRUCTION & SUPPLY (FORMERLY: LLABAN CON | 9821 | 2024 | 2024-09-10 | 02/20/2024 | 0.46 | 0 | 2024-11-26 | 77
2023 | Region XI | DAVAO ORIENTAL | BAGANGA (DAVAO ORIENTAL) | P00721387MN | Construction of Slope Protection Structure | 126.5527 | 7.6618 | 29400000 | 29399700.03 | 2023 | JHARKHA CONSTRUCTION AND SUPPLY | 9822 | 2023 | 2023-06-30 | 03/28/2023 | 299.97 | 0 | 2023-11-18 | 141
2023 | Region XIII | AGUSAN DEL SUR | ESPERANZA (AGUSAN DEL SUR) | P00721655MN | Construction of Revetment | 125.6413 | 8.6656 | 53075000 | 53074962.28 | 2023 | ADFIL CORPORATION | 9823 | 2023 | 2023-10-25 | 03/31/2023 | 37.72 | 0 | 2024-01-23 | 90
2023 | Region XI | DAVAO ORIENTAL | BAGANGA (DAVAO ORIENTAL) | P00732067MN | Construction of Revetment | 126.5544 | 7.5707 | 96500000 | 96499312.8 | 2023 | JHARKHA CONSTRUCTION AND SUPPLY / O. G. SANTOS CONSTRUCTION | 9824 | 2023 | 2023-08-16 | 04/04/2023 | 687.2 | 0 | 2024-03-07 | 204
2024 | Region XIII | AGUSAN DEL NORTE | REMEDIOS T. ROMUALDEZ (AGUSAN DEL NORTE) | P00820118MN | Construction of Flood Mitigation Structure | 125.6419 | 9.0697 | 72375000 | 72174935.35 | 2024 | ARQ BUILDERS | 9825 | 2024 | 2024-11-15 | 02/12/2024 | 200064.65 | 0 | 2024-11-14 |  | 1
2022 | Region XI | DAVAO ORIENTAL | BAGANGA (DAVAO ORIENTAL) | P00620068MN | Construction of Flood Mitigation Structure | 126.5572 | 7.5774 | 96500000 | 96499762.52 | 2022 | GP & H CONSTRUCTION INCORPORATED (FORMERLY: GP & H CONSTRUCTION & SUPPLY) | 9826 | 2022 | 2022-11-21 | 02/21/2022 | 237.48 | 0 | 2023-02-04 | 75
2022 | Region XIII | AGUSAN DEL SUR | PROSPERIDAD (CAPITAL) (AGUSAN DEL SUR) | P00620295MN | Construction of Flood Mitigation Structure | 125.8417 | 8.6809 | 45080000 | 45079929.26 | 2023 | EQUI-PARCO CONSTRUCTION COMPANY | 9827 | 2022 | 2023-03-14 | 06/03/2022 | 70.74 | 0 | 2023-03-13 |  | 1
2023 | Region XIII | AGUSAN DEL NORTE | REMEDIOS T. ROMUALDEZ (AGUSAN DEL NORTE) | P00721627MN | Construction of Flood Mitigation Structure | 125.6419 | 9.0697 | 24500000 | 24436494 | 2024 | ARQ BUILDERS | 9828 | 2023 | 2024-04-11 | 05/25/2023 | 63506 | 0 | 2024-04-10 |  | 1
2023 | Region X | BUKIDNON | QUEZON (BUKIDNON) | P00732481MN | Construction of Flood Mitigation Structure | 125.1778 | 7.7519 | 4950000 | 4950000 | 2023 | ELC CONSTRUCTION AND TRADING | 9829 | 2023 | 2023-08-15 | 02/26/2023 | 0 | 0 | 2023-08-14 |  | 1
2023 | Region XI | DAVAO ORIENTAL | BAGANGA (DAVAO ORIENTAL) | P00721570MN | Construction of Flood Mitigation Structure | 126.5634 | 7.5734 | 67550000 | 66536750 | 2024 | LEGACY CONSTRUCTION CORPORATION (FORMERLY: LEGACY CONSTRUCTION) | 9830 | 2023 | 2024-01-15 | 03/22/2023 | 1013250 | 0 | 2024-01-17 | 2
2023 | Region XIII | AGUSAN DEL SUR | LORETO (AGUSAN DEL SUR) | P00734036MN | Construction of Flood Mitigation Structure | 125.8423 | 8.0908 | 9800000 | 9800000 | 2023 | DAVE CONSTRUCTION | 9831 | 2023 | 2023-10-15 | 05/16/2023 | 0 | 0 | 2023-10-16 | 1
2021 | Region XIII | AGUSAN DEL SUR |  | P00522129MN | Construction of Revetment | 125.6421 | 8.6682 | 115800000 | 115032425.2 | 2023 | ADFIL CORPORATION | 9832 | 2021 | 2023-02-11 | 01/03/2022 | 767574.8 | 0 | 2023-02-10 |  | 1
2022 | Region XII | SOUTH COTABATO | GENERAL SANTOS CITY (DADIANGAS) (SOUTH COTABATO) | P00631109MN | Construction of Drainage Structure | 125.1781 | 6.1147 | 4950000 | 4587878.27 | 2022 | HANNA VIA CONSTRUCTION, INC. (FORMERLY:HANNA VIA DESIGN & CONSTRUCTION) | 9833 | 2022 | 2022-08-08 | 03/29/2022 | 362121.73 | 0 | 2022-08-05 |  | 3
2022 | Region VIII | SOUTHERN LEYTE | HINUNANGAN (SOUTHERN LEYTE) | P00620232VS | Construction of Flood Mitigation Structure | 125.1789 | 10.3694 | 49000000 | 49000000 | 2022 | ST. GERRARD CONSTRUCTION GEN. CONTRACTOR & DEVELOPMENT CORP. (FORMERLY:ST. GERRARD CONSTRUCTION) | 9834 | 2022 | 2022-10-13 | 02/16/2022 | 0 | 0 | 2022-10-12 |  | 1
2023 | Region XIII | AGUSAN DEL SUR | LORETO (AGUSAN DEL SUR) | P00732502MN | Construction of Flood Mitigation Structure | 125.8424 | 8.0909 | 9800000 | 9800000 | 2023 | DAVE CONSTRUCTION | 9835 | 2023 | 2023-10-15 | 04/21/2023 | 0 | 0 | 2023-10-16 | 1
2021 | Region XI | BATANGAS |  | P00522361MN | Construction of Revetment | 125.8425 | 7.2836 | 14699920.95 | 14699920.95 | 2022 | AGONG BUILDERS AND CONSTRUCTION SUPPLY, INC. | 9836 | 2021 | 2022-08-28 | 03/24/2022 | 0 | 0 | 2022-08-27 |  | 1
2024 | Region XIII | AGUSAN DEL SUR | LORETO (AGUSAN DEL SUR) | P00833603MN | Construction of Flood Mitigation Structure | 125.8425 | 8.0908 | 7920000 | 7920000 | 2024 | DAVE CONSTRUCTION | 9837 | 2024 | 2024-08-17 | 05/27/2024 | 0 | 0 | 2024-08-16 |  | 1
2022 | Region XI | DAVAO DE ORO | MACO (DAVAO DE ORO) | P00630762MN | Construction of Revetment | 125.8442 | 7.4105 | 67549964.53 | 67549964.53 | 2023 | DREIRICH BUILDERS / THREE W BUILDERS, INC. | 9838 | 2022 | 2023-01-31 | 04/04/2022 | 0 | 0 | 2023-01-30 |  | 1
2022 | Region XI | DAVAO DEL NORTE | CITY OF TAGUM (CAPITAL) (DAVAO DEL NORTE) | P00620055MN | Construction of Flood Mitigation Structure | 125.8466 | 7.4712 | 76200000 | 76200000 | 2022 | GP & H CONSTRUCTION INCORPORATED (FORMERLY: GP & H CONSTRUCTION & SUPPLY) | 9839 | 2022 | 2022-12-24 | 02/24/2022 | 0 | 0 | 2022-12-23 |  | 1
2022 | Region XI | DAVAO ORIENTAL | CARAGA (DAVAO ORIENTAL) | P00620174MN | Construction of Flood Mitigation Structure | 126.5653 | 7.2867 | 49000000 | 48999657.73 | 2022 | MITZ CONSTRUCTION AND SUPPLY / O. G. SANTOS CONSTRUCTION | 9840 | 2022 | 2022-10-21 | 02/08/2022 | 342.27 | 0 | 2022-10-20 |  | 1
2024 | Region XIII | AGUSAN DEL NORTE | BUTUAN CITY (CAPITAL) (AGUSAN DEL NORTE) | P00836197MN | Construction of Flood Mitigation Structure | 125.6422 | 8.9948 | 7903686.58 | 7883330.97 | 2024 | HAPPY ALL3 BUILDERS CORPORATION | 9841 | 2024 | 2024-12-27 | 06/05/2024 | 20355.61 | 0 | 2024-12-30 | 3
2024 | Region XI | DAVAO ORIENTAL | BAGANGA (DAVAO ORIENTAL) | P00820178MN | Construction of Flood Mitigation Structure | 126.5695 | 7.5652 | 9800000 | 9799963.68 | 2024 | DBR CONSTRUCTION CORPORATION (FORMERLY: D.B. RAVELO CONSTRUCTION & SUPPLY) | 9842 | 2024 | 2024-10-26 | 04/08/2024 | 36.32 | 0 | 2024-10-25 |  | 1
2024 | Region XIII | AGUSAN DEL SUR | ESPERANZA (AGUSAN DEL SUR) | P00820428MN | Construction of Flood Mitigation Structure | 125.6423 | 8.6693 | 29400000 | 29399925.1 | 2024 | BBC CONSTRUCTION | 9843 | 2024 | 2024-10-23 | 04/17/2024 | 74.9 | 0 | 2024-12-11 | 49
2022 | Region XI | DAVAO DEL SUR | DAVAO CITY (DAVAO DEL SUR) | P00631099MN | Construction of Drainage Structure | 125.6431 | 7.1617 | 4950000 | 4950000 | 2022 | AGONG BUILDERS AND CONSTRUCTION SUPPLY, INC. | 9844 | 2022 | 2022-10-30 | 04/10/2022 | 0 | 0 | 2022-10-29 |  | 1
2022 | Region XI | DAVAO DEL SUR | DAVAO CITY (DAVAO DEL SUR) | P00631097MN | Construction of Drainage Structure | 125.6434 | 7.1761 | 9900000 | 9900000 | 2022 | WANGCON DEVELOPMENT CORPORATION | 9845 | 2022 | 2022-07-26 | 03/31/2022 | 0 | 0 | 2022-07-25 |  | 1
2022 | Region XI | DAVAO DEL SUR | DAVAO CITY (DAVAO DEL SUR) | P00630601MN | Construction of Flood Mitigation Structure | 125.6438 | 7.2385 | 49000000 | 49000000 | 2023 | GENESIS88 CONSTRUCTION INC. | 9846 | 2022 | 2023-03-31 | 04/13/2022 | 0 | 0 | 2023-05-18 | 48
2022 | Region XI | DAVAO DE ORO | MACO (DAVAO DE ORO) | P00620267MN | Construction of Revetment | 125.8488 | 7.3634 | 48999826.55 | 48999826.55 | 2023 | C'ZARLES CONSTRUCTION & SUPPLY | 9847 | 2022 | 2023-02-18 | 04/04/2022 | 0 | 0 | 2023-02-18 | 0
2021 | Region XI | DAVAO DE ORO |  | P00550576MN | Construction of Revetment | 125.8496 | 7.3636 | 9899977.72 | 9899973.73 | 2022 | AGONG BUILDERS AND CONSTRUCTION SUPPLY, INC. | 9848 | 2021 | 2022-10-28 | 03/24/2022 | 3.99 | 0 | 2022-10-27 |  | 1
2022 | Region XI | DAVAO DE ORO | MABINI (DOÃ‘A ALICIA) (DAVAO DE ORO) | P00634135MN | Construction of Drainage Structure | 125.8558 | 7.2815 | 2939999.89 | 2939999.89 | 2022 | TWO DEGREES CONSTRUCTION AND SUPPLY | 9849 | 2022 | 2022-07-08 | 03/29/2022 | 0 | 0 | 2022-07-07 |  | 1
2022 | Region XI | DAVAO DE ORO | MABINI (DOÃ‘A ALICIA) (DAVAO DE ORO) | P00634998MN | Construction of Drainage Structure | 125.8694 | 7.2964 | 4899928.17 | 4899928.17 | 2022 | TWO DEGREES CONSTRUCTION AND SUPPLY | 9850 | 2022 | 2022-09-06 | 03/29/2022 | 0 | 0 | 2022-09-05 |  | 1
2022 | Region XI | DAVAO DE ORO | MABINI (DOÃ‘A ALICIA) (DAVAO DE ORO) | P00620367MN | Construction of Revetment | 125.8709 | 7.2849 | 19599910.02 | 19599910.02 | 2022 | AGONG BUILDERS AND CONSTRUCTION SUPPLY, INC. | 9851 | 2022 | 2022-10-18 | 03/29/2022 | 0 | 0 | 2022-10-17 |  | 1
2022 | Region XIII | AGUSAN DEL SUR | LORETO (AGUSAN DEL SUR) | P00620300MN | Construction of Flood Mitigation Structure | 125.8777 | 8.1237 | 33765900 | 33765900 | 2023 | DAVE CONSTRUCTION / CM TAN CONSTRUCTION | 9852 | 2022 | 2023-05-19 | 07/11/2022 | 0 | 0 | 2023-05-18 |  | 1
2021 | Region XIII | AGUSAN DEL SUR |  | P00522268MN | Construction of Flood Mitigation Structure | 125.8817 | 8.1182 | 49000000 | 49000000 | 2022 | DAVE CONSTRUCTION / FFJJ CONSTRUCTION | 9853 | 2021 | 2022-07-27 | 08/02/2021 | 0 | 0 | 2022-07-26 |  | 1
2023 | Region XI | DAVAO DE ORO | PANTUKAN (DAVAO DE ORO) | P00721616MN | Construction of Revetment | 125.8909 | 7.1383 | 34300000 | 34299422.58 | 2023 | R.A. PAHATI CONST. & SUPPLY, INC. | 9854 | 2023 | 2023-12-24 | 03/10/2023 | 577.42 | 0 | 2023-12-24 | 0
2022 | Region XIII | SURIGAO DEL NORTE | DEL CARMEN (SURIGAO DEL NORTE) | P00644676MN | Construction of Flood Mitigation Structure | 125.8953 | 9.8953 | 77200000 | 75671068.01 | 2024 | ROAD EDGE TRADING & DEVELOPMENT SERVICES | 9855 | 2022 | 2024-04-05 | 11/25/2022 | 1528931.99 | 0 | 2024-04-04 |  | 1
2023 | Region XIII | SURIGAO DEL NORTE | PILAR (SURIGAO DEL NORTE) | P00745952MN | Rehabilitation / Major Repair of Flood Control Structure | 125.9056 | 9.6453 | 93137880.05 | 92206234.28 | 2024 | DQT BUILDERS AND SUPPLY / ARN BUILDERS, INC. (FOR: ARN BUILDERS) | 9856 | 2023 | 2024-05-19 | 11/28/2023 | 931645.77 | 0 | 2024-10-16 | 150